LedgerService | getTaxInvoice | response | customerAccountId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | issuedAt | string (date-time) | yes
LedgerService | getTaxInvoice | response | supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | getTaxInvoice | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | legalCurrency | string |  | The legal entity's currency (AED in the UAE), in which the law requires the tax and the gross amount (CHG-FIN-011). (pattern ^[A-Z]{3}$; read-only)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency | object |  | The gross amount payable in the legal currency (Executive Regulation Art. (read-only)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | legalFxRate | object |  | Units of the legal currency per one unit of currency, printed with the tax where the invoice is not in the legal currency (Art. (read-only; nullable)
LedgerService | getTaxInvoice | response | legalFxRateSource | object |  | uaeCentralBank for a UAE legal entity (Decree-Law Art. (read-only; nullable)
LedgerService | getTaxInvoice | response | paidCurrency | string |  | Where the guest paid in a currency they selected (orders.Order.chargeCurrency, CHG-FIN-001), printed as payment information with paidAmount and the charge rate. (pattern ^[A-Z]{3}$; read-only; nullable)
LedgerService | getTaxInvoice | response | paidAmount | object |  | What the guest paid in paidCurrency (orders.Order.chargeTotal). (read-only)
LedgerService | getTaxInvoice | response | paidAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | paidAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | paidAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | reverseChargeStatement | string |  | Where the recipient must account for the tax, the statement saying so and the Decree-Law provision (Art. (read-only; nullable)
LedgerService | getTaxInvoice | response | creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | languages | array of string
LedgerService | getTaxInvoice | response | supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | getTaxInvoice | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | getTaxInvoice | response | issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | getTaxInvoice | response | lines | array of FinTaxInvoiceLine | yes
LedgerService | getTaxInvoice | response | lines[].lineNumber | integer | yes | (min 1)
LedgerService | getTaxInvoice | response | lines[].orderId | string (uuid)
LedgerService | getTaxInvoice | response | lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | lines[].description | string | yes | (max length 500)
LedgerService | getTaxInvoice | response | lines[].quantity | number | yes
LedgerService | getTaxInvoice | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | lines[].taxRate | number |  | (min 0; max 100)
LedgerService | getTaxInvoice | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | getTaxInvoice | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency | object |  | The amount payable for the line in the legal currency (AED), Executive Regulation Art. (read-only)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | getTaxInvoice | response | taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | getTaxInvoice | response | taxSummary[].taxRate | number
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | getTaxInvoice | param (path) | invoiceId | string (uuid) | yes
WhiteLabelService | getTenantAppStatus | response | tenantId | string (uuid) | yes
WhiteLabelService | getTenantAppStatus | response | isPublished | boolean | yes | True once any version has been published.
WhiteLabelService | getTenantAppStatus | response | darkAppModules | array of string |  | The app-modules switched off for this tenant (ADAM CR-164, option A, 18 October 2026; CHG-CRA-005): their keys (for example AM-MARKETING-CRM-P01), from the tenant's release flags. (read-only)
WhiteLabelService | getTenantAppStatus | response | publishedVersion | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | publishedAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | draftVersion | string |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | hasUnpublishedChanges | boolean |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | activeModuleCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | licensedModuleCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | activePageCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | isInMaintenance | boolean | yes
WhiteLabelService | getTenantAppStatus | response | maintenanceMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantAppStatus | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.storeUrl | object |  | The store page of the tenant's app for each platform. (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.storeUrl.ios | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.storeUrl.android | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | getTenantAppStatus | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.phone | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.address | object |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantAppStatus | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | getTenantAppStatus | response | availabilityMessage | object |  | What the sold-out or closed screen says (WEB-029). (nullable)
WhiteLabelService | getTenantAppStatus | response | venues | array of object |  | Public: the venues a guest can pick (decided 28 September, audit R267; schema named 29 September, readiness close-out, our build plan). (max items 200)
WhiteLabelService | getTenantAppStatus | response | venues[].venueId | string (uuid) | yes | The venue's scope node (tenancy.OrgUnit.id, level venue): what every guest screen that declares venueId from: session reads once the guest picks it.
WhiteLabelService | getTenantAppStatus | response | venues[].name | string | yes | The venue's name (tenancy.OrgUnit.name). (max length 200)
WhiteLabelService | getTenantAppStatus | response | venues[].contact | object |  | The venue's own contact (address, phone, email), from the venue's settings (tenancy.VenueSettings, read through venueSettingsRecords). (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].contact.phone | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].contact.address | object |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].city | string |  | Shown under the name so two venues with similar names can be told apart. (max length 120; nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday | object |  | Today's opening hours in the venue's time zone, from tenancy.VenueSettings opening hours. (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday.opens | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday.closes | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | getTenantAppStatus | response | whatsNew | array of object |  | Public: the guest "what's new" (decided 29 September, rev 3 GAP-B2). (max items 10)
WhiteLabelService | getTenantAppStatus | response | whatsNew[].version | string | yes | The release version.
WhiteLabelService | getTenantAppStatus | response | whatsNew[].publishedAt | string (date-time) | yes | When the release reached the tenant's cell.
WhiteLabelService | getTenantAppStatus | response | whatsNew[].notes | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantAppStatus | response | recentChanges | array of object |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | recentChanges[].area | string
WhiteLabelService | getTenantAppStatus | response | recentChanges[].description | string
WhiteLabelService | getTenantAppStatus | response | recentChanges[].principalId | string (uuid)
WhiteLabelService | getTenantAppStatus | response | recentChanges[].at | string (date-time)
WhiteLabelService | getTenantConfig | response | tenantId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | version | string | yes | The draft's working version label; the published one is ConfigVersion.version.
WhiteLabelService | getTenantConfig | response | isDraft | boolean |  | True for the working draft, which is the only row. (read-only)
WhiteLabelService | getTenantConfig | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload).
WhiteLabelService | getTenantConfig | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getTenantConfig | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getTenantConfig | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getTenantConfig | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getTenantConfig | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getTenantConfig | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getTenantConfig | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getTenantConfig | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getTenantConfig | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getTenantConfig | response | brand.showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | getTenantConfig | response | appIcons | AppIcons
WhiteLabelService | getTenantConfig | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getTenantConfig | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getTenantConfig | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | getTenantConfig | response | appIcons.derived[].size | string
WhiteLabelService | getTenantConfig | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | getTenantConfig | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getTenantConfig | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getTenantConfig | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlow | BookingFlowConfig |  | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
WhiteLabelService | getTenantConfig | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getTenantConfig | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getTenantConfig | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getTenantConfig | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getTenantConfig | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getTenantConfig | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getTenantConfig | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getTenantConfig | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getTenantConfig | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getTenantConfig | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getTenantConfig | response | bookingFlows | array of BookingFlow |  | Every venue's booking flows in the draft (whitelabel.booking_flow), so a publish snapshots them with the rest (decided 29 September, W12). (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].id | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getTenantConfig | response | bookingFlows[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getTenantConfig | response | bookingFlows[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getTenantConfig | response | bookingFlows[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getTenantConfig | response | bookingFlows[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getTenantConfig | response | theme | Theme
WhiteLabelService | getTenantConfig | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | getTenantConfig | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getTenantConfig | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getTenantConfig | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getTenantConfig | response | theme.venueSkins | array of object |  | The guest app skin each venue takes (ADAM CR-280, option B, 28 October 2026; CHG-R11TEN-007): one entry per venue, naming one of the approved app design's skins (handoff/design-tokens/guest-app.yaml,… (default [])
WhiteLabelService | getTenantConfig | response | theme.venueSkins[].venueId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | theme.venueSkins[].skinKey | GuestAppSkinKey: enum (park, water, stadium, theatre, dining, kids, museum, rooms, …) | yes | The guest app's skins per venue kind, as the approved Mobile App v4 design draws them (handoff/design-tokens/guest-app.yaml skins.byVenueKind; ADAM CR-280, CHG-R11TEN-007).
WhiteLabelService | getTenantConfig | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getTenantConfig | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | fonts | FontConfig
WhiteLabelService | getTenantConfig | response | fonts.primaryLatin | string | yes
WhiteLabelService | getTenantConfig | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getTenantConfig | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getTenantConfig | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getTenantConfig | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | getTenantConfig | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | getTenantConfig | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | getTenantConfig | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | getTenantConfig | response | footer.columns | array of object
WhiteLabelService | getTenantConfig | response | footer.columns[].heading | string
WhiteLabelService | getTenantConfig | response | footer.columns[].sortOrder | integer |  | The column's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | getTenantConfig | response | footer.columns[].links | array of object |  | The column's links in display order, stored on the column row as one value (R8 blocker WHITE-C24).
WhiteLabelService | getTenantConfig | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | getTenantConfig | response | footer.legalLinks.termsUrl | string
WhiteLabelService | getTenantConfig | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | getTenantConfig | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | footer.copyrightText | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks | array of object
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].platform | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].url | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].sortOrder | integer |  | The link's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | getTenantConfig | response | notificationBranding | object |  | BL-003. (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.senderName | string
WhiteLabelService | getTenantConfig | response | notificationBranding.replyToEmail | string (email)
WhiteLabelService | getTenantConfig | response | notificationBranding.smsSenderId | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.whatsappBusinessId | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.logoAssetId | string (uuid) |  | (nullable)
WhiteLabelService | getTenantConfig | response | enabledPaymentMethods | array of string |  | BL-004. (nullable)
WhiteLabelService | getTenantConfig | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | getTenantConfig | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | getTenantConfig | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | getTenantConfig | response | header | HeaderConfig
WhiteLabelService | getTenantConfig | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | getTenantConfig | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | getTenantConfig | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getTenantConfig | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | getTenantConfig | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | navigation.items[].icon | string
WhiteLabelService | getTenantConfig | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | getTenantConfig | response | navigation.items[].isVisible | boolean | yes | At most five may be visible when kind is bottomNavigation; the rest overflow.
WhiteLabelService | getTenantConfig | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | getTenantConfig | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getTenantConfig | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getTenantConfig | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | homepage | HomepageLayout |  | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | getTenantConfig | response | homepage.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | getTenantConfig | response | homepage.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | getTenantConfig | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | homepage.sections | array of object | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getTenantConfig | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getTenantConfig | response | homepage.sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | getTenantConfig | response | homepage.sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | getTenantConfig | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | getTenantConfig | response | modules | array of ModuleEnablement
WhiteLabelService | getTenantConfig | response | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getTenantConfig | response | modules[].displayName | string
WhiteLabelService | getTenantConfig | response | modules[].isLicensed | boolean | yes | From the tenant's subscription.
WhiteLabelService | getTenantConfig | response | modules[].isEnabled | boolean | yes
WhiteLabelService | getTenantConfig | response | modules[].referencedBy | array of string |  | Navigation items and homepage sections pointing at this module. (read-only)
WhiteLabelService | getTenantConfig | response | features | array of FeatureToggle
WhiteLabelService | getTenantConfig | response | features[].featureKey | object | yes | guestCheckout is off by default (decided 17 September 2026, matrix 2.6.28, placement settled by [ADR-0045](../../docs/adr/0045-every-order-carries-a-proven-contact.md) 18 September): the venue sets t…
WhiteLabelService | getTenantConfig | response | features[].displayName | string
WhiteLabelService | getTenantConfig | response | features[].isEnabled | boolean | yes
WhiteLabelService | getTenantConfig | response | features[].changeScope | object | yes | Wallet and payment integrations are buildTime on native apps — enabling one needs a release, not a publish. (read-only)
WhiteLabelService | getTenantConfig | response | features[].requiresConfiguration | boolean |  | True where the feature needs credentials or setup elsewhere first.
WhiteLabelService | getTenantConfig | response | languages | LanguageConfig
WhiteLabelService | getTenantConfig | response | languages.languages | array of string | yes | A tenant may add or select interface languages beyond English and Arabic (Chinmay, 2 October, workbook Q145; CHG-CSA-039).
WhiteLabelService | getTenantConfig | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage | array of object |  | How complete the interface strings are in each enabled language (CHG-CSA-039). (read-only)
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage[].language | string
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage[].coveragePercent | number |  | (min 0; max 100)
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage[].status | enum (complete, draft, missing)
WhiteLabelService | getTenantConfig | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | getTenantConfig | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].language | string
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].areas | array of string |  | The kinds of the missing items, from the closed list contentPages, banners, promoBlocks, faqs, policies (ADAM CR-194).
WhiteLabelService | getTenantConfig | response | updatedAt | string (date-time)
WhiteLabelService | getTenantConfig | response | isInMaintenance | boolean |  | Written by setMaintenanceMode; read by getTenantAppStatus. (default False)
WhiteLabelService | getTenantConfig | response | maintenanceMessage | object |  | The message on the branded maintenance screen. (nullable)
WhiteLabelService | getTenantConfig | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion.storeUrl | object |  | The store page of the tenant's app for each platform. (nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion.storeUrl.ios | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion.storeUrl.android | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | getTenantConfig | response | contact | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | contact.phone | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.address | object |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantConfig | response | availability | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | availabilityMessage | object |  | Live state, written by setMaintenanceMode (audit R073). (nullable)
WhiteLabelService | getTenantConfig | response | venues | array of object |  | The tenant's active venues, for the guest venue picker on WEB-001 and GST-001 (decided 28 September, audit R267).
WhiteLabelService | getTenantConfig | response | venues[].venueId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | venues[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | venues[].city | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | venues[].openingHours | object |  | Today's hours as shown to a guest, e.g. (nullable)
WhiteLabelService | getTenantConfig | param (query) | version | string |  | Read a published version's snapshot instead of the working draft.
PlatformService | getTenantLicences | response | poweredByRemovable | boolean |  | Whether the tenant's licence lets it switch "Powered by TICVAI" off (Chinmay, 2 October, workbook Q160 and the pre-apply round; CHG-CSA-036). (default False; read-only)
PlatformService | getTenantLicences | response | tenantId | string (uuid) | yes
PlatformService | getTenantLicences | response | planId | string (uuid) |  | (nullable)
PlatformService | getTenantLicences | response | licensedModules | array of object | yes | Union of plan modules and add-ons.
PlatformService | getTenantLicences | response | licensedModules[].moduleKey | string | yes
PlatformService | getTenantLicences | response | licensedModules[].displayName | string
PlatformService | getTenantLicences | response | licensedModules[].source | enum (plan, addOn) | yes
PlatformService | getTenantLicences | response | licensedModules[].validTo | string (date) |  | (nullable)
PlatformService | getTenantLicences | response | limits | array of EntitlementLimit | yes
PlatformService | getTenantLicences | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | getTenantLicences | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | getTenantLicences | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | getTenantLicences | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | getTenantLicences | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | getTenantLicences | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | getTenantLicences | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | getTenantLicences | param (path) | tenantId | string (uuid) | yes
WhiteLabelService | getTheme | response | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | getTheme | response | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getTheme | response | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getTheme | response | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getTheme | response | venueSkins | array of object |  | The guest app skin each venue takes (ADAM CR-280, option B, 28 October 2026; CHG-R11TEN-007): one entry per venue, naming one of the approved app design's skins (handoff/design-tokens/guest-app.yaml,… (default [])
WhiteLabelService | getTheme | response | venueSkins[].venueId | string (uuid) | yes
WhiteLabelService | getTheme | response | venueSkins[].skinKey | GuestAppSkinKey: enum (park, water, stadium, theatre, dining, kids, museum, rooms, …) | yes | The guest app's skins per venue kind, as the approved Mobile App v4 design draws them (handoff/design-tokens/guest-app.yaml skins.byVenueKind; ADAM CR-280, CHG-R11TEN-007).
WhiteLabelService | getTheme | response | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getTheme | response | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.payButton | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.link | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.badge | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
OrderService | getTillShiftPolicy | response | id | string (uuid) |  | (read-only)
OrderService | getTillShiftPolicy | response | venueId | string (uuid) | yes
OrderService | getTillShiftPolicy | response | scopePath | string |  | (read-only)
OrderService | getTillShiftPolicy | response | requireOpenApproval | boolean |  | Every shift opens pendingApproval and waits for approveShiftOpen (SHIFT_APPROVE_OPEN). (default False)
OrderService | getTillShiftPolicy | response | openingFloatTolerance | object |  | How far a declared opening float may differ from the box's allocated float before the shift waits for approval (states/shift.yaml, pendingApproval). (nullable)
OrderService | getTillShiftPolicy | response | openingFloatTolerance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getTillShiftPolicy | response | openingFloatTolerance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getTillShiftPolicy | response | openingFloatTolerance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getTillShiftPolicy | response | depositBoxRequired | boolean |  | A shift cannot open without a deposit box (OpenShiftRequest.depositBoxCode); refused 400 otherwise. (default True)
OrderService | getTillShiftPolicy | response | bagNumberRequired | boolean |  | A shift cannot open without a bag number (OpenShiftRequest.bagNumber). (default False)
OrderService | getTillShiftPolicy | response | requireCloseApproval | boolean |  | Every counted shift waits in pendingClosure for approveShiftClose (SHIFT_APPROVE_CLOSE), even within the variance threshold. (default False)
OrderService | getTillShiftPolicy | response | autoCloseAfterHours | integer |  | Hours after which an open or suspended shift nobody closed is closed by the inactivity job as autoClosed and the supervisors are told (states/shift.yaml). (min 1; max 48; default 14; nullable)
OrderService | getTillShiftPolicy | response | noSaleAlertCount | integer |  | No-sales in one shift (recordNoSale) at which the supervisors are alerted on the venue's alerting channel; the count is on POS-020. (min 1; default 10; nullable)
OrderService | getTillShiftPolicy | response | updatedAt | string (date-time) |  | (read-only)
OrderService | getTillShiftPolicy | param (path) | venueId | string (uuid) | yes
AiService | getTranslationProposals | response | targetLocale | string | yes
AiService | getTranslationProposals | response | translationJobId | string (uuid) |  | The job to follow with getTranslationProposals (contract gap CHG-WIR-017, CMS-011; CHG-CSA-045). (read-only)
AiService | getTranslationProposals | response | status | enum (running, completed, failed) |  | running while drafts are still being written; drafts then holds those done so far. (read-only)
AiService | getTranslationProposals | response | drafts | array of object | yes
AiService | getTranslationProposals | response | drafts[].proposalId | string (uuid) | yes | The ai.proposed_action id of this draft (r8 walk of ticket 27926).
AiService | getTranslationProposals | response | drafts[].fieldPath | string | yes | Where the draft goes inside the target, as a dotted path in the target's own body, for example localeVariants.ar.title on a content block or name.ar on a product.
AiService | getTranslationProposals | response | drafts[].targetKind | enum (contentBlock, productName, emailTemplate, messageTemplate) | yes
AiService | getTranslationProposals | response | drafts[].targetRef | string | yes | The id of the block, product or template the draft sits on.
AiService | getTranslationProposals | response | drafts[].draftText | string | yes | The first-pass translation, as saved on the draft.
AiService | getTranslationProposals | param (path) | translationJobId | string (uuid) | yes
VenueOpsService | getTransportDeparture | response | departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportDeparture | response | performanceId | string (uuid) | yes
VenueOpsService | getTransportDeparture | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportDeparture | response | routeCode | string |  | The price card's label, e.g.
VenueOpsService | getTransportDeparture | response | departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | getTransportDeparture | response | arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | getTransportDeparture | response | durationMinutes | integer | yes | (min 0)
VenueOpsService | getTransportDeparture | response | period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | getTransportDeparture | response | seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | getTransportDeparture | response | fitsParty | boolean
VenueOpsService | getTransportDeparture | response | fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportDeparture | response | fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportDeparture | response | fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportDeparture | response | fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportDeparture | response | partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportDeparture | response | partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportDeparture | response | partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportDeparture | response | partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportDeparture | param (path) | departureId | string (uuid) | yes
VenueOpsService | getTransportDeparture | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | getTransportFareTable | response | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | getTransportFareTable | response | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | matrix | array of object |  | matrix only.
VenueOpsService | getTransportFareTable | response | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | getTransportFareTable | response | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | getTransportFareTable | response | passengerTypes[].name | LocalisedText | yes
VenueOpsService | getTransportFareTable | response | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | getTransportFareTable | response | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | getTransportFareTable | response | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | getTransportFareTable | response | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | getTransportFareTable | response | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | getTransportFareTable | response | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | getTransportFareTable | response | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | getTransportFareTable | response | effectiveFrom | string (date-time) | yes
VenueOpsService | getTransportFareTable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | effectiveTo | string (date-time) |  | When the next version takes over; null when none is set (CHG-RUL-012). (read-only; nullable)
VenueOpsService | getTransportFareTable | response | upcoming | object |  | The next version, set and not yet in force (CHG-RUL-012); null when none. (read-only; nullable)
VenueOpsService | getTransportFareTable | response | upcoming.id | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | upcoming.effectiveFrom | string (date-time)
VenueOpsService | getTransportFareTable | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportFareTable | param (query) | at | string (date-time) |  | The instant whose table is returned (the travel time for a guest).
VenueOpsService | getTransportFareTable | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | getTransportRouteMap | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRouteMap | response | lineCode | string
VenueOpsService | getTransportRouteMap | response | colour | string
VenueOpsService | getTransportRouteMap | response | stops | array of object | yes | Every stop in route order.
VenueOpsService | getTransportRouteMap | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRouteMap | response | stops[].sequence | integer | yes
VenueOpsService | getTransportRouteMap | response | stops[].name | string | yes | Localised to the caller.
VenueOpsService | getTransportRouteMap | response | stops[].shortName | string
VenueOpsService | getTransportRouteMap | response | stops[].latitude | number |  | (nullable)
VenueOpsService | getTransportRouteMap | response | stops[].longitude | number |  | (nullable)
VenueOpsService | getTransportRouteMap | response | stops[].offsetMinutes | integer
VenueOpsService | getTransportRouteMap | response | stops[].onJourney | boolean | yes | Between the boarding and alighting stops
VenueOpsService | getTransportRouteMap | response | stops[].isBoarding | boolean
VenueOpsService | getTransportRouteMap | response | stops[].isAlighting | boolean
VenueOpsService | getTransportRouteMap | response | intermediateStopCount | integer |  | Stops between boarding and alighting — the number behind "Show full route (n stops)".
VenueOpsService | getTransportRouteMap | response | bounds | object |  | The box around the stops with coordinates, for the map's initial view. (nullable)
VenueOpsService | getTransportRouteMap | response | bounds.south | number
VenueOpsService | getTransportRouteMap | response | bounds.west | number
VenueOpsService | getTransportRouteMap | response | bounds.north | number
VenueOpsService | getTransportRouteMap | response | bounds.east | number
VenueOpsService | getTransportRouteMap | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportRouteMap | param (query) | fromStationId | string (uuid)
VenueOpsService | getTransportRouteMap | param (query) | toStationId | string (uuid)
VenueOpsService | getTransportRouteMap | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
AiService | getVenueHistoryImport | response | id | string (uuid) | yes | (read-only)
AiService | getVenueHistoryImport | response | venueId | string (uuid) | yes
AiService | getVenueHistoryImport | response | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | getVenueHistoryImport | response | assetId | string (uuid)
AiService | getVenueHistoryImport | response | sourceSystem | string |  | (nullable)
AiService | getVenueHistoryImport | response | columnMapping | object
AiService | getVenueHistoryImport | response | dryRun | boolean |  | (default False)
AiService | getVenueHistoryImport | response | status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | getVenueHistoryImport | response | periodFrom | string (date) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | periodTo | string (date) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | monthsCovered | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsRead | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsLoaded | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsRejected | integer |  | (read-only)
AiService | getVenueHistoryImport | response | findings | array of object |  | (read-only)
AiService | getVenueHistoryImport | response | findings[].row | integer
AiService | getVenueHistoryImport | response | findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | getVenueHistoryImport | response | findings[].detail | string
AiService | getVenueHistoryImport | response | requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | getVenueHistoryImport | response | createdAt | string (date-time) |  | (read-only)
AiService | getVenueHistoryImport | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getVenueHistoryImport | param (path) | importId | string (uuid) | yes
VenueOpsService | getVenueMap | response | version | integer |  | The published version these points and paths belong to, which is the number a client caches and sends back as version. (read-only; nullable)
VenueOpsService | getVenueMap | response | map | VenueMap |  | A park map, or a floor plan.
VenueOpsService | getVenueMap | response | map.id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | map.name | string | yes
VenueOpsService | getVenueMap | response | map.venueId | string (uuid) | yes
VenueOpsService | getVenueMap | response | map.scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | getVenueMap | response | map.kind | enum (park, floor, zone, parking)
VenueOpsService | getVenueMap | response | map.floorLevel | integer |  | (nullable)
VenueOpsService | getVenueMap | response | map.status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | getVenueMap | response | map.publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | getVenueMap | response | map.isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | getVenueMap | response | map.baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | getVenueMap | response | map.baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | getVenueMap | response | map.baseImageAlignment.imageWidthPx | integer
VenueOpsService | getVenueMap | response | map.baseImageAlignment.imageHeightPx | integer
VenueOpsService | getVenueMap | response | map.baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | getVenueMap | response | map.tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.boundsGeoJson | string |  | (nullable)
VenueOpsService | getVenueMap | response | map.graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | getVenueMap | response | map.modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | getVenueMap | response | map.modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | getVenueMap | response | map.modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | getVenueMap | response | map.modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | getVenueMap | response | map.modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | getVenueMap | response | map.modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | getVenueMap | response | map.modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | getVenueMap | response | map.model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | getVenueMap | response | points | array of VenuePoint
VenueOpsService | getVenueMap | response | points[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | points[].mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | getVenueMap | response | points[].kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | getVenueMap | response | points[].name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | getVenueMap | response | points[].nameLocalised | object |  | (nullable)
VenueOpsService | getVenueMap | response | points[].position | object | yes | Drawing coordinates.
VenueOpsService | getVenueMap | response | points[].position.x | number | yes
VenueOpsService | getVenueMap | response | points[].position.y | number | yes
VenueOpsService | getVenueMap | response | points[].outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | getVenueMap | response | points[].productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | getVenueMap | response | points[].accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | getVenueMap | response | points[].isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | getVenueMap | response | points[].openingHours | string |  | (nullable)
VenueOpsService | getVenueMap | response | points[].iconRef | string |  | (nullable)
VenueOpsService | getVenueMap | response | points[].isActive | boolean |  | (default True)
VenueOpsService | getVenueMap | response | points[].isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | getVenueMap | response | points[].isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | getVenueMap | response | points[].description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | getVenueMap | response | points[].media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | getVenueMap | response | points[].media[].assetId | string (uuid) | yes
VenueOpsService | getVenueMap | response | points[].media[].kind | enum (image, video) | yes
VenueOpsService | getVenueMap | response | points[].media[].isPrimary | boolean |  | (default False)
VenueOpsService | getVenueMap | response | points[].media[].altText | string |  | (max length 200; nullable)
VenueOpsService | getVenueMap | response | points[].featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | getVenueMap | response | points[].featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | getVenueMap | response | points[].featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | getVenueMap | response | points[].featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | getVenueMap | response | points[].typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | getVenueMap | response | points[].interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | getVenueMap | response | points[].cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | getVenueMap | response | points[].retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | getVenueMap | response | paths | array of VenuePath
VenueOpsService | getVenueMap | response | paths[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | paths[].mapId | string (uuid) | yes | From the path of the operation that writes the path. (read-only)
VenueOpsService | getVenueMap | response | paths[].fromPointId | string (uuid) | yes
VenueOpsService | getVenueMap | response | paths[].toPointId | string (uuid) | yes
VenueOpsService | getVenueMap | response | paths[].geometry | string |  | The centreline this edge follows, as an encoded polyline. (nullable)
VenueOpsService | getVenueMap | response | paths[].distanceMetres | number |  | Computed by the server from geometry and the georeference. (read-only; nullable)
VenueOpsService | getVenueMap | response | paths[].isStepFree | boolean |  | The single most important attribute on this object. (default True)
VenueOpsService | getVenueMap | response | paths[].isIndoor | boolean |  | (default False)
VenueOpsService | getVenueMap | response | paths[].restrictedByPointId | string (uuid) |  | Where a path is one-way, it is because of a thing on it — not because of the path. (nullable)
VenueOpsService | getVenueMap | response | paths[].closedReason | string |  | Set by setPathClosure during works or an incident, never by sending it here. (read-only; nullable)
VenueOpsService | getVenueMap | response | paths[].isClosed | boolean |  | Closed by setPathClosure; routing does not use a closed path. (default False; read-only)
VenueOpsService | getVenueMap | response | paths[].expectedReopenAt | string (date-time) |  | When a closed path is expected to reopen (setPathClosure). (read-only; nullable)
VenueOpsService | getVenueMap | response | paths[].closedNote | string |  | The free text with an other closure reason (setPathClosure; audit R222). (max length 500; read-only; nullable)
VenueOpsService | getVenueMap | response | resources | array of PlacedResource |  | The bookable resources placed on this version of the map (rev 3 REV3-15).
VenueOpsService | getVenueMap | response | resources[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | resources[].mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | getVenueMap | response | resources[].resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | getVenueMap | response | resources[].label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | getVenueMap | response | resources[].kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | getVenueMap | response | resources[].zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | getVenueMap | response | resources[].capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | getVenueMap | response | resources[].priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | getVenueMap | response | resources[].variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | getVenueMap | response | resources[].position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | getVenueMap | response | resources[].position.x | number | yes
VenueOpsService | getVenueMap | response | resources[].position.y | number | yes
VenueOpsService | getVenueMap | response | resources[].boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | getVenueMap | response | resources[].boundary[].x | number
VenueOpsService | getVenueMap | response | resources[].boundary[].y | number
VenueOpsService | getVenueMap | response | resources[].isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | getVenueMap | response | model3d | object |  | The 3D layer of the version read (ADR-0069; 3 October 2026, r1 additions). (nullable)
VenueOpsService | getVenueMap | response | model3d.modelAssetId | string (uuid) | yes
VenueOpsService | getVenueMap | response | model3d.sizeBytes | integer |  | (nullable)
VenueOpsService | getVenueMap | response | model3d.transform | VenueModelTransform | yes | ADR-0069 section 3: the navigation file's anchor.
VenueOpsService | getVenueMap | response | model3d.transform.originLat | number | yes | (min -90; max 90)
VenueOpsService | getVenueMap | response | model3d.transform.originLng | number | yes | (min -180; max 180)
VenueOpsService | getVenueMap | response | model3d.transform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | getVenueMap | response | model3d.transform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | getVenueMap | response | model3d.transform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | getVenueMap | response | model3d.transform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | getVenueMap | param (path) | mapId | string (uuid) | yes
VenueOpsService | getVenueMap | param (query) | version | integer |  | Absent means the published version.
VenueOpsService | getVenueMap | param (query) | draft | boolean |  | Read the working draft instead of a published version.
VenueOpsService | getVenueMap | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | getVenueMapGraph | response | mapId | string (uuid) | yes
VenueOpsService | getVenueMapGraph | response | version | integer | yes | Bumped by a publish or a closure, and stored as VenueMap.graphVersion.
VenueOpsService | getVenueMapGraph | response | generatedAt | string (date-time)
VenueOpsService | getVenueMapGraph | response | nodes | array of object | yes
VenueOpsService | getVenueMapGraph | response | nodes[].pointId | string (uuid)
VenueOpsService | getVenueMapGraph | response | nodes[].x | number
VenueOpsService | getVenueMapGraph | response | nodes[].y | number
VenueOpsService | getVenueMapGraph | response | nodes[].kind | string
VenueOpsService | getVenueMapGraph | response | nodes[].isStepFree | boolean
VenueOpsService | getVenueMapGraph | response | edges | array of object | yes
VenueOpsService | getVenueMapGraph | response | edges[].from | string (uuid)
VenueOpsService | getVenueMapGraph | response | edges[].to | string (uuid)
VenueOpsService | getVenueMapGraph | response | edges[].distanceMetres | number
VenueOpsService | getVenueMapGraph | response | edges[].isStepFree | boolean
VenueOpsService | getVenueMapGraph | response | edges[].throughPointId | string |  | Where an access point restricts this edge. (nullable)
VenueOpsService | getVenueMapGraph | response | edges[].isClosed | boolean
VenueOpsService | getVenueMapGraph | response | components | integer |  | How many disconnected parts.
VenueOpsService | getVenueMapGraph | param (path) | mapId | string (uuid) | yes
VenueOpsService | getVenueMapGraph | param (query) | draft | boolean |  | The working draft's graph instead of the published one.
VenueOpsService | getVenueMapGraph | param (query) | stepFreeOnly | boolean |  | Returns the step-free subgraph, not a filtered copy of the whole one.
VenueOpsService | getVenueMapGraph | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | getVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | getVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | getVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | getVisitPlan | response | ownership | enum (anonymous, account) |  | anonymous while the plan belongs to a device session (built and changed only; it lapses with the session), account once the guest signed in and the plan moved to their account, where it is saved and… (read-only)
VenueOpsService | getVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | getVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | getVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | getVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | getVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | getVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | getVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | getVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | getVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | getVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | getVisitPlan | response | inputs.pace | enum (packed, balanced, relaxed) |  | (default relaxed)
VenueOpsService | getVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | getVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | getVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | getVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | getVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | getVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | getVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | getVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | getVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | getVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | getVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | getVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | getVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | excluded[].name | string |  | The point's name, worked out on read for the left-out banner (r8 walk of ticket 28693). (nullable)
VenueOpsService | getVisitPlan | response | excluded[].limit | object |  | The rule that left it out, worked out on read from the product's eligibility rule: for heightRule a minimum or maximum height in centimetres, for ageRule a minimum or maximum age in years. (nullable)
VenueOpsService | getVisitPlan | response | excluded[].limit.kind | enum (minHeightCm, maxHeightCm, minAge, maxAge)
VenueOpsService | getVisitPlan | response | excluded[].limit.value | integer |  | (min 0)
VenueOpsService | getVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | getVisitPlan | response | estimate | object |  | An estimated total, computed on read from current catalogue prices and stored nowhere (r8 walk of tickets 28693 and 28200; lead decision of 20 October 2026, option A; DI-1098, "with associated costin… (read-only; nullable)
VenueOpsService | getVisitPlan | response | estimate.total | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getVisitPlan | response | estimate.total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getVisitPlan | response | estimate.total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getVisitPlan | response | estimate.total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getVisitPlan | response | estimate.currency | string | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | getVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | getVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | getVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | getVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | getVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | getVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | getVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].name | string |  | What the stop is called on the timeline (GST-059, GST-053; r8 walk of ticket 28693): the point's name, or the performance's title for a show, in the request language. (read-only; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].zoneName | string |  | The name of the zone the stop is in, from the point's zone on the map the plan was laid out on. (read-only; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | getVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | getVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | getVisitPlan | response | days[].items[].addOnProductIds | array of string (uuid) |  | Add-ons the guest put on this stop with addAddOn (CHG-RUL-009), beside an accepted suggestion, as catalogue product ids. (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | getVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | getVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | getVisitPlan | param (query) | version | integer |  | Absent means the current version.
VenueOpsService | getVisitPlannerOptions | response | venueId | string (uuid) | yes
VenueOpsService | getVisitPlannerOptions | response | presets | array of VisitPlanPreset | yes | (max items 50)
VenueOpsService | getVisitPlannerOptions | response | presets[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlannerOptions | response | presets[].presetKey | string | yes | The key generateVisitPlan.presetKey names. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$)
VenueOpsService | getVisitPlannerOptions | response | presets[].name | string | yes | (max length 120)
VenueOpsService | getVisitPlannerOptions | response | presets[].nameLocalised | object |  | (nullable)
VenueOpsService | getVisitPlannerOptions | response | presets[].description | string |  | (max length 500; nullable)
VenueOpsService | getVisitPlannerOptions | response | presets[].descriptionLocalised | object |  | (nullable)
VenueOpsService | getVisitPlannerOptions | response | presets[].pace | enum (packed, balanced, relaxed) | yes
VenueOpsService | getVisitPlannerOptions | response | presets[].interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | getVisitPlannerOptions | response | presets[].mustIncludePointIds | array of string (uuid) |  | (max items 10)
VenueOpsService | getVisitPlannerOptions | response | presets[].isBuiltIn | boolean | yes | True for the six seeded rows; a built-in row can be changed or switched off, never deleted. (read-only)
VenueOpsService | getVisitPlannerOptions | response | presets[].isActive | boolean | yes | (default True)
VenueOpsService | getVisitPlannerOptions | response | presets[].sortOrder | integer | yes | The order GST-052 lists the presets in. (min 0)
VenueOpsService | getVisitPlannerOptions | response | presets[].scopePath | string | yes | The partition key (ADR-0005): the venue the preset belongs to. (read-only)
VenueOpsService | getVisitPlannerOptions | response | presets[].updatedAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlannerOptions | response | interestTags | array of object | yes | Per published park map of the venue, the interest tags its points carry. (max items 50)
VenueOpsService | getVisitPlannerOptions | response | interestTags[].mapId | string (uuid) | yes
VenueOpsService | getVisitPlannerOptions | response | interestTags[].mapName | string
VenueOpsService | getVisitPlannerOptions | response | interestTags[].tags | array of string | yes | (max items 50)
VenueOpsService | getVisitPlannerOptions | response | cuisineTags | array of object |  | Per published park map of the venue, the cuisine tags of its published dining points (kind restaurant, cafe, or a kiosk that sells food), each tag once (ADAM CR-220, option A; Chinmay, 25 October 202… (max items 50)
VenueOpsService | getVisitPlannerOptions | response | cuisineTags[].mapId | string (uuid) | yes
VenueOpsService | getVisitPlannerOptions | response | cuisineTags[].mapName | string
VenueOpsService | getVisitPlannerOptions | response | cuisineTags[].tags | array of string | yes | (max items 50)
VenueOpsService | getVisitPlannerOptions | response | retailTags | array of object |  | Per published park map of the venue, the retail tags of its published shops and retail kiosks (kind shop, or a kiosk that sells goods), each tag once (ADAM CR-220, option A; CHG-R10ORD-015). (max items 50)
VenueOpsService | getVisitPlannerOptions | response | retailTags[].mapId | string (uuid) | yes
VenueOpsService | getVisitPlannerOptions | response | retailTags[].mapName | string
VenueOpsService | getVisitPlannerOptions | response | retailTags[].tags | array of string | yes | (max items 50)
VenueOpsService | getVisitPlannerOptions | response | fastTrackBundles | array of object | yes | (max items 50)
VenueOpsService | getVisitPlannerOptions | response | fastTrackBundles[].bundleId | string (uuid) | yes
VenueOpsService | getVisitPlannerOptions | response | fastTrackBundles[].name | string | yes
VenueOpsService | getVisitPlannerOptions | param (path) | venueId | string (uuid) | yes
OrderService | getVisitReminder | response | id | string (uuid) |  | (read-only)
OrderService | getVisitReminder | response | orderId | string (uuid) |  | (read-only)
OrderService | getVisitReminder | response | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | getVisitReminder | response | enabled | boolean | yes
OrderService | getVisitReminder | response | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | getVisitReminder | response | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | getVisitReminder | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | getVisitReminder | param (path) | orderId | string (uuid) | yes
VenueOpsService | getWaitTimes | param (query) | venueId | string (uuid) | yes
VenueOpsService | getWaitTimes | param (query) | category | string (uuid) |  | A catalogue product category id (ProductCategory, catalogue contract).
VenueOpsService | getWaitingGuest | response | id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | getWaitingGuest | response | queueId | string (uuid) | yes
VenueOpsService | getWaitingGuest | response | queueName | LocalisedText
VenueOpsService | getWaitingGuest | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getWaitingGuest | response | partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | getWaitingGuest | response | partySize | integer | yes
VenueOpsService | getWaitingGuest | response | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | getWaitingGuest | response | positionInQueue | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | partiesAhead | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | isFastPass | boolean
VenueOpsService | getWaitingGuest | response | priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | getWaitingGuest | response | priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | getWaitingGuest | response | priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | getWaitingGuest | response | accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | getWaitingGuest | response | entitlementId | string |  | (nullable)
VenueOpsService | getWaitingGuest | response | calledAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | admittedCount | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | joinedAt | string (date-time) | yes
VenueOpsService | getWaitingGuest | response | syncedAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | overriddenByPrincipalId | string (uuid) |  | Who let the party past the queue (overrideWaitingGuest, 4 October 2026, CHG-FXC-003), with overrideReason and overriddenAt. (read-only; nullable)
VenueOpsService | getWaitingGuest | response | overrideReason | string |  | (read-only; nullable)
VenueOpsService | getWaitingGuest | response | overriddenAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | getWaitingGuest | param (path) | entryId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | response | waitingEntryId | string (uuid) | yes | A UUIDv7 minted on arrival; what the waiting page polls with.
CatalogueService | getWaitingRoomPosition | response | performanceId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | response | state | enum (notRequired, waiting, admitted, expired, closed) | yes | notRequired: the room is off, go to the sale.
CatalogueService | getWaitingRoomPosition | response | position | integer |  | Place in the room; null unless waiting. (min 1; nullable)
CatalogueService | getWaitingRoomPosition | response | aheadOfYou | integer |  | (min 0; nullable)
CatalogueService | getWaitingRoomPosition | response | estimatedWaitSeconds | integer |  | At the current release rate. (min 0; nullable)
CatalogueService | getWaitingRoomPosition | response | pollAfterSeconds | integer |  | (min 1; default 5)
CatalogueService | getWaitingRoomPosition | response | admission | object |  | Set when state is admitted. (nullable)
CatalogueService | getWaitingRoomPosition | response | admission.token | string | yes | The signed token, opaque to the client.
CatalogueService | getWaitingRoomPosition | response | admission.tokenId | string (uuid) |  | The token's unique id.
CatalogueService | getWaitingRoomPosition | response | admission.performanceId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | response | admission.expiresAt | string (date-time) | yes
CatalogueService | getWaitingRoomPosition | param (path) | performanceId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | param (path) | waitingEntryId | string (uuid) | yes
MarketingService | getWaiverStatus | response | isSatisfied | boolean
MarketingService | getWaiverStatus | response | missingFormIds | array of string (uuid)
MarketingService | getWaiverStatus | response | expiringWithinDays | integer |  | (nullable)
MarketingService | getWaiverStatus | param (path) | subjectId | string (uuid) | yes
MarketingService | getWaiverStatus | param (query) | productId | string (uuid)
WalletService | getWallet | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | getWallet | response | subjectId | string (uuid) | yes
WalletService | getWallet | response | transferRules | object |  | What the venue allows this guest to do with a transfer, read from the venue's WalletTransferRules so a guest screen can hide or limit the action (r8 walk of tickets 28310 and 28345). (read-only; nullable)
WalletService | getWallet | response | transferRules.peerToPeerAllowed | boolean
WalletService | getWallet | response | transferRules.withinSharedWalletOnly | boolean
WalletService | getWallet | response | transferRules.maximumPerTransfer | object |  | (nullable)
WalletService | getWallet | response | transferRules.maximumPerTransfer.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | transferRules.maximumPerTransfer.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | transferRules.maximumPerTransfer.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWallet | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | getWallet | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | getWallet | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWallet | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | getWallet | response | credits[].sourceRef | string |  | (nullable)
WalletService | getWallet | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | getWallet | response | bonusBalance | object |  | Promotional value.
WalletService | getWallet | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | status | enum (active, suspended, closed) | yes
WalletService | getWallet | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | getWallet | response | expiresAt | string (date-time) |  | (nullable)
WalletService | getWallet | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | getWallet | param (path) | subjectId | string (uuid) | yes
WalletService | getWallet | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
WalletService | getWalletAutoReloadSetting | response | walletId | string (uuid) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | subjectId | string (uuid) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | enabled | boolean | yes
WalletService | getWalletAutoReloadSetting | response | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletAutoReloadSetting | response | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletAutoReloadSetting | response | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletAutoReloadSetting | response | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletAutoReloadSetting | response | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletAutoReloadSetting | response | paymentTokenId | string (uuid) |  | (nullable)
WalletService | getWalletAutoReloadSetting | response | maximumPerDay | integer |  | (min 1; nullable)
WalletService | getWalletAutoReloadSetting | response | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | getWalletAutoReloadSetting | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | getWalletAutoReloadSetting | param (path) | walletId | string (uuid) | yes
MarketingService | getWishlist | response | subjectId | string (uuid) | yes
MarketingService | getWishlist | response | items | array of WishlistItem | yes | Newest first: ordered by addedAt descending, id as the tiebreak (CHG-MKT-002).
MarketingService | getWishlist | response | items[].id | string (uuid) | yes
MarketingService | getWishlist | response | items[].subjectId | string (uuid) | yes | The guest who saved it. (read-only)
MarketingService | getWishlist | response | items[].variantId | string (uuid) | yes
MarketingService | getWishlist | response | items[].productName | string |  | Catalogue's, not Marketing's.
MarketingService | getWishlist | response | items[].performanceId | string (uuid) |  | (nullable)
MarketingService | getWishlist | response | items[].performanceStartsAt | string (date-time) |  | The saved performance's start, from Catalogue's variantListingFacts; null for a date-less entry. (nullable)
MarketingService | getWishlist | response | items[].price | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | getWishlist | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | getWishlist | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | getWishlist | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | getWishlist | response | items[].imageAssetRef | string |  | The product's primary media, from Catalogue's variantListingFacts. (nullable)
MarketingService | getWishlist | response | items[].isAvailable | boolean | yes | False where the product has been withdrawn or the performance has passed.
MarketingService | getWishlist | response | items[].unavailableReason | string |  | Why isAvailable is false, in Catalogue's words (variantListingFacts.reason), or performancePassed; null when available. (nullable)
MarketingService | getWishlist | response | items[].note | string |  | (nullable)
MarketingService | getWishlist | response | items[].addedAt | string (date-time) | yes
MarketingService | getWishlist | param (path) | subjectId | string (uuid) | yes
TenancyService | getWorkstation | response | id | string (uuid) | yes
TenancyService | getWorkstation | response | code | string | yes | (max length 64)
TenancyService | getWorkstation | response | name | string | yes | (max length 200)
TenancyService | getWorkstation | response | venueId | string (uuid) | yes
TenancyService | getWorkstation | response | regionId | string (uuid) | yes
TenancyService | getWorkstation | response | departmentId | string (uuid) |  | (nullable)
TenancyService | getWorkstation | response | outletId | string (uuid) |  | The outlet this till stands in (CHG-CSP-006). (nullable)
TenancyService | getWorkstation | response | scopePath | string | yes
TenancyService | getWorkstation | response | saleBoard | object | yes | Determines which front end loads.
TenancyService | getWorkstation | response | saleBoard.id | string (uuid) | yes
TenancyService | getWorkstation | response | saleBoard.kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | getWorkstation | response | saleBoard.name | string
TenancyService | getWorkstation | response | saleBoardSource | enum (outlet, workstation) |  | Where saleBoard came from (decided 2 October 2026, Chinmay, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006): outlet when the till uses its outlet's layout, workstation when this til… (read-only)
TenancyService | getWorkstation | response | cashDrawerLimit | Money |  | This till's drawer limit, overriding the venue's (VenueSettings.cashDrawerLimit; DEC-179; CHG-CSP-016). (nullable)
TenancyService | getWorkstation | response | cashierInputMode | enum (keyboard, touch, scanner, hybrid) |  | BL-061. (default hybrid)
TenancyService | getWorkstation | response | guestDisplayContent | array of enum (lineItems, total, loyaltyBalance, promotions, branding, upsell, queuePosition) |  | BL-061. (default ['lineItems'])
TenancyService | getWorkstation | response | accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator. (nullable)
TenancyService | getWorkstation | response | devices | array of DeviceBinding
TenancyService | getWorkstation | response | devices[].deviceId | string (uuid) |  | The registered device (CR-155): the platform.device row's own id.
TenancyService | getWorkstation | response | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | getWorkstation | response | devices[].driver | string | yes | Driver identifier.
TenancyService | getWorkstation | response | devices[].identifier | string |  | Serial
TenancyService | getWorkstation | response | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | getWorkstation | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
TenancyService | getWorkstation | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
TenancyService | getWorkstation | response | timeZone | string | yes
TenancyService | getWorkstation | response | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | getWorkstation | response | edgeNodeId | string (uuid) |  | Present when deploymentProfile is venueEdge. (nullable)
TenancyService | getWorkstation | response | healthScore | integer |  | Board 1 of the client's POS set. (min 0; max 100; read-only; nullable)
TenancyService | getWorkstation | response | configurationProfileId | string (uuid) |  | Which profile this workstation runs, and at which version. (nullable)
TenancyService | getWorkstation | response | configurationProfileVersion | integer |  | The version of configurationProfileId this workstation runs, written when a deployment reaches it; null with no profile (R8 blocker APPROVALS-TENANCY-C08, CHG-R8MIG-019). (read-only; nullable)
TenancyService | getWorkstation | response | catalogueState | CatalogueState |  | The workstation's local catalogue position.
TenancyService | getWorkstation | response | catalogueState.appliedBundleVersion | string | yes
TenancyService | getWorkstation | response | catalogueState.appliedAt | string (date-time) | yes
TenancyService | getWorkstation | response | catalogueState.staleAfter | string (date-time) | yes | Beyond this the terminal refuses to trade.
TenancyService | getWorkstation | response | catalogueState.isStale | boolean | yes
TenancyService | getWorkstation | response | catalogueState.pendingBundleVersion | string |  | Published but not yet applied. (nullable)
TenancyService | getWorkstation | response | offlineCapable | boolean |  | Derived from deploymentProfile.
TenancyService | getWorkstation | response | isActive | boolean
TenancyService | getWorkstation | param (path) | workstationId | string (uuid) | yes
TenancyService | getWorkstationHealth | response | score | integer
TenancyService | getWorkstationHealth | response | status | enum (healthy, warning, degraded, offline)
TenancyService | getWorkstationHealth | response | contributors | array of object
TenancyService | getWorkstationHealth | response | contributors[].factor | enum (heartbeatAge, deviceOffline, deviceBattery, firmwareOutdated, syncBacklog, errorRate, profileDrift)
TenancyService | getWorkstationHealth | response | contributors[].detail | string
TenancyService | getWorkstationHealth | response | contributors[].weight | integer
TenancyService | getWorkstationHealth | param (path) | workstationId | string (uuid) | yes
OrderService | getWorkstationShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | getWorkstationShift | response | workstationId | string (uuid) | yes
OrderService | getWorkstationShift | response | venueId | string (uuid) | yes
OrderService | getWorkstationShift | response | scopePath | string | yes
OrderService | getWorkstationShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | getWorkstationShift | response | principalDisplayName | string
OrderService | getWorkstationShift | response | incidents | array of object |  | BL-097.
OrderService | getWorkstationShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | getWorkstationShift | response | incidents[].at | string (date-time)
OrderService | getWorkstationShift | response | incidents[].principalId | string (uuid)
OrderService | getWorkstationShift | response | incidents[].note | string |  | (nullable)
OrderService | getWorkstationShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | getWorkstationShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getWorkstationShift | response | depositBoxCode | string |  | (nullable)
OrderService | getWorkstationShift | response | bagNumber | string |  | (nullable)
OrderService | getWorkstationShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | getWorkstationShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | getWorkstationShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | getWorkstationShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | getWorkstationShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | getWorkstationShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | getWorkstationShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | getWorkstationShift | response | openedAt | string (date-time) | yes
OrderService | getWorkstationShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | getWorkstationShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | getWorkstationShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | getWorkstationShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | getWorkstationShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | getWorkstationShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | getWorkstationShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | getWorkstationShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | getWorkstationShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | getWorkstationShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | getWorkstationShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | getWorkstationShift | response | approvals | array of object
OrderService | getWorkstationShift | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | getWorkstationShift | response | approvals[].principalId | string (uuid) | yes
OrderService | getWorkstationShift | response | approvals[].at | string (date-time) | yes
OrderService | getWorkstationShift | response | approvals[].reason | string
OrderService | giveShiftVarianceReason | request | reason | enum (tillError, unrecordedRefund, miscount, other) | yes | The same reasons as CloseShiftRequest.cashierReason (DI-803), recorded as the shift's cashierReason.
OrderService | giveShiftVarianceReason | request | note | string |  | What happened, in the cashier's words; recorded as the shift's cashierNote (appended to a note given with the count). (max length 1000)
OrderService | giveShiftVarianceReason | response | shiftId | string (uuid) | yes
OrderService | giveShiftVarianceReason | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | giveShiftVarianceReason | response | outcome | enum (closed, referredToSupervisor, awaitingCloseApproval) | yes | closed: within the venue's threshold, the shift is closed.
OrderService | giveShiftVarianceReason | response | countedAt | string (date-time) | yes
OrderService | giveShiftVarianceReason | response | countNumber | integer |  | 1 for the first count of the close, 2 for a recount the supervisor asked for, and so on. (min 1)
OrderService | giveShiftVarianceReason | response | varianceReasonRequired | boolean |  | The count found a difference within the threshold and no reason came with it (the client's policy of 6 October 2026, T10.1; CHG-R4-019). (default False)
OrderService | giveShiftVarianceReason | param (path) | shiftId | string (uuid) | yes
OrderService | giveShiftVarianceReason | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | grantDelegation | request | overSubjectId | string (uuid) | yes
IdentityService | grantDelegation | request | delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) | yes
IdentityService | grantDelegation | request | permission | string | yes
IdentityService | grantDelegation | request | overObjectRef | string |  | (nullable)
IdentityService | grantDelegation | request | quota | integer |  | (nullable)
IdentityService | grantDelegation | request | validTo | string (date-time) |  | (nullable)
IdentityService | grantDelegation | request | isRevocableBySubject | boolean |  | (default True)
IdentityService | grantDelegation | response | grantedByKind | enum (principal, subject, system) |  | Who made the grant (CHG-R8MIG-021). (default principal; read-only)
IdentityService | grantDelegation | response | grantedByPrincipalId | string (uuid) |  | The staff member who made the grant; set when grantedByKind is principal. (read-only; nullable)
IdentityService | grantDelegation | response | grantedBySubjectId | string (uuid) |  | The guest who made the grant (the account holder); set when grantedByKind is subject. (read-only; nullable)
IdentityService | grantDelegation | response | id | string (uuid) | yes
IdentityService | grantDelegation | response | principalId | string (uuid) |  | (nullable)
IdentityService | grantDelegation | response | roleId | string (uuid) |  | The role this grant gives, with its own and inherited permissions. (nullable)
IdentityService | grantDelegation | response | permission | string | yes | From the permission enum. (nullable)
IdentityService | grantDelegation | response | subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | grantDelegation | response | overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | grantDelegation | response | overSubjectName | string |  | The display name of the guest acted for (pii.subject.display_name), read with the grant; null for a staff grant. (read-only; nullable)
IdentityService | grantDelegation | response | overSubjectIsMinor | boolean |  | Whether the guest acted for is under the region's RegionSettings.minorAgeThreshold today, computed from their date of birth, which is never returned; null when no date of birth is held. (read-only; nullable)
IdentityService | grantDelegation | response | overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | grantDelegation | response | delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer, sharedEntitlement) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | grantDelegation | response | quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | grantDelegation | response | isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | grantDelegation | response | scopePath | string | yes
IdentityService | grantDelegation | response | effect | enum (ALLOW, DENY) | yes
IdentityService | grantDelegation | response | permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | grantDelegation | response | revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | grantDelegation | response | revokedByKind | enum (principal, subject, system) |  | Who revoked the grant (decided 25 October 2026, Chinmay, ADAM CR-209 option A; CHG-R10ID-004): a staff member (revoked_by_principal_id), a guest (revokedBySubjectId, for example the owner taking back… (read-only; nullable)
IdentityService | grantDelegation | response | revokedBySubjectId | string (uuid) |  | The guest who revoked the grant; set when revokedByKind is subject (ADAM CR-209), since a guest is not a principal and cannot fill revoked_by_principal_id. (read-only; nullable)
IdentityService | grantDelegation | response | validFrom | string (date-time) |  | (nullable)
IdentityService | grantDelegation | response | validTo | string (date-time) |  | (nullable)
IdentityService | grantDelegation | response | createdByPrincipalId | string (uuid)
IdentityService | grantDelegation | response | createdAt | string (date-time)
IdentityService | grantDelegation | param (path) | subjectId | string (uuid) | yes
IdentityService | grantDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestLogout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestLogout | param (query) | allDevices | boolean
IdentityService | guestPasswordLogin | request | identifier | string | yes | The email address or E.164 mobile number the account was registered with. (max length 256)
IdentityService | guestPasswordLogin | request | password | string | yes | Compared with GuestCredential.passwordHash and never stored (ADR-0071, CHG-CRD-003). (min length 8; max length 256)
IdentityService | guestPasswordLogin | request | deviceId | string |  | Names the device; a new sign-in here ends the previous session on it.
IdentityService | guestPasswordLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestPasswordLogin | response | subjectId | string (uuid) | yes
IdentityService | guestPasswordLogin | response | displayName | string |  | (nullable)
IdentityService | guestPasswordLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestPasswordLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestPasswordLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestPasswordLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestPasswordLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestPasswordLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestPasswordLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestPasswordLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestPasswordLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestPasswordLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestPasswordLogin | response | tokens | object | yes | The new access and refresh tokens; refreshToken returns the next pair.
IdentityService | guestPasswordLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestPasswordLogin | response | tokens.refreshToken | string | yes
IdentityService | guestPasswordLogin | response | tokens.expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | guestPasswordLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestSocialLogin | request | provider | enum (apple, google) | yes
IdentityService | guestSocialLogin | request | idToken | string | yes
IdentityService | guestSocialLogin | request | deviceId | string |  | Send the app's installationId (the value it registers its push token with, marketing-crm registerGuestDevice), so revoking that device signs this session out (endGuestDeviceSessions, CHG-MOD-009).
IdentityService | guestSocialLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestSocialLogin | response | subjectId | string (uuid) | yes
IdentityService | guestSocialLogin | response | displayName | string |  | (nullable)
IdentityService | guestSocialLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestSocialLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestSocialLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestSocialLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestSocialLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestSocialLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestSocialLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestSocialLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestSocialLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestSocialLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestSocialLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestSocialLogin | response | tokens | object | yes | The new access and refresh tokens; refreshToken returns the next pair.
IdentityService | guestSocialLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestSocialLogin | response | tokens.refreshToken | string | yes
IdentityService | guestSocialLogin | response | tokens.expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | guestSocialLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestUaePassLogin | request | code | string | yes
IdentityService | guestUaePassLogin | request | redirectUri | string | yes
IdentityService | guestUaePassLogin | request | state | string
IdentityService | guestUaePassLogin | request | deviceId | string |  | Send the app's installationId (the value it registers its push token with, marketing-crm registerGuestDevice), so revoking that device signs this session out (endGuestDeviceSessions, CHG-MOD-009).
IdentityService | guestUaePassLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestUaePassLogin | response | subjectId | string (uuid) | yes
IdentityService | guestUaePassLogin | response | displayName | string |  | (nullable)
IdentityService | guestUaePassLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestUaePassLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestUaePassLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestUaePassLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestUaePassLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestUaePassLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestUaePassLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestUaePassLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestUaePassLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestUaePassLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestUaePassLogin | response | tokens | object | yes | The new access and refresh tokens; refreshToken returns the next pair.
IdentityService | guestUaePassLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestUaePassLogin | response | tokens.refreshToken | string | yes
IdentityService | guestUaePassLogin | response | tokens.expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | guestUaePassLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | handoverToAgent | request | reason | enum (guestRequested, assistantRefused, assistantFailed, outOfScope, negativeSentiment, complexIntent, paymentIssue) | yes
MarketingService | handoverToAgent | request | summary | string |  | The assistant's own summary of what the guest wants, so the agent opens with context rather than reading a transcript while somebody waits.
MarketingService | handoverToAgent | request | preferredQueueId | string (uuid)
MarketingService | handoverToAgent | response | id | string (uuid) | yes
MarketingService | handoverToAgent | response | telephony | object |  | BL-083. (nullable)
MarketingService | handoverToAgent | response | telephony.providerCallId | string
MarketingService | handoverToAgent | response | telephony.direction | enum (inbound, outbound, transferred)
MarketingService | handoverToAgent | response | telephony.fromNumberMasked | string |  | Masked, and it is still personal data. (nullable)
MarketingService | handoverToAgent | response | telephony.recordingRef | string |  | Held by the provider, referenced here. (nullable)
MarketingService | handoverToAgent | response | telephony.agentState | enum (available, onCall, wrapUp, away, offline) |  | (nullable)
MarketingService | handoverToAgent | response | assistSessionId | string (uuid) |  | BL-094. (nullable)
MarketingService | handoverToAgent | response | channel | ConversationChannel: enum (webChat, inAppChat, whatsapp, sms, email, kiosk, voice) | yes
MarketingService | handoverToAgent | response | state | ConversationState: enum (withAssistant, queued, withAgent, waitingOnGuest, resolved, abandoned, timedOut) | yes | withAssistant and queued are different, and the second has a person waiting.
MarketingService | handoverToAgent | response | subjectId | string (uuid) |  | 22.8.3. (nullable)
MarketingService | handoverToAgent | response | venueId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | assignedPrincipalId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | queueId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | queuePosition | integer |  | Place among the unclaimed conversations in queueId, from the live agent queue (audit R149). (read-only; nullable)
MarketingService | handoverToAgent | response | estimatedWaitSeconds | integer |  | From the live agent queue — the conversations ahead divided across that queue's agents online now (audit R149). (read-only; nullable)
MarketingService | handoverToAgent | response | handoverReason | enum (guestRequested, assistantRefused, assistantFailed, outOfScope, negativeSentiment, complexIntent, paymentIssue) |  | (nullable)
MarketingService | handoverToAgent | response | handoverSummary | string |  | The assistant's own account of what the guest wants, so an agent opens with context rather than reading a transcript while somebody waits. (nullable)
MarketingService | handoverToAgent | response | sentiment | enum (positive, neutral, negative, escalating) |  | 22.8.16. (nullable)
MarketingService | handoverToAgent | response | intent | string |  | 22.8.13. (nullable)
MarketingService | handoverToAgent | response | locale | string
MarketingService | handoverToAgent | response | caseId | string (uuid) |  | 22.8.12. (nullable)
MarketingService | handoverToAgent | response | messages | array of ConversationMessage
MarketingService | handoverToAgent | response | messages[].id | string (uuid) | yes
MarketingService | handoverToAgent | response | messages[].sender | enum (guest, agent, assistant, system) | yes | Resolved, never declared.
MarketingService | handoverToAgent | response | messages[].senderPrincipalId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | messages[].body | string | yes
MarketingService | handoverToAgent | response | messages[].attachments | array of object
MarketingService | handoverToAgent | response | messages[].attachments[].assetId | string (uuid)
MarketingService | handoverToAgent | response | messages[].attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | handoverToAgent | response | messages[].aiInteractionId | string (uuid) |  | Where the assistant sent it. (nullable)
MarketingService | handoverToAgent | response | messages[].sentAt | string (date-time) | yes
MarketingService | handoverToAgent | response | messages[].readAt | string (date-time) |  | (nullable)
MarketingService | handoverToAgent | response | firstResponseSeconds | integer |  | (read-only; nullable)
MarketingService | handoverToAgent | response | startedAt | string (date-time)
MarketingService | handoverToAgent | response | closedAt | string (date-time) |  | (nullable)
MarketingService | handoverToAgent | response | outcome | enum (resolved, caseRaised, abandonedByGuest, timedOut, spam) |  | (nullable)
MarketingService | handoverToAgent | param (path) | conversationId | string (uuid) | yes
MarketingService | handoverToAgent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | holdCourse | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | holdCourse | request | course | integer | yes | (min 1)
FnbService | holdCourse | request | reason | enum (tableNotReady, guestRequest, kitchenBackedUp, awaitingPrevious, other) |  | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | holdCourse | request | note | string |  | Free text. (max length 500; nullable)
FnbService | holdCourse | response | id | string (uuid) | yes
FnbService | holdCourse | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | holdCourse | response | orderNumber | string
FnbService | holdCourse | response | outletId | string (uuid) | yes
FnbService | holdCourse | response | tableLabel | string |  | (nullable)
FnbService | holdCourse | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | holdCourse | response | coursing | object |  | BL-131. (nullable)
FnbService | holdCourse | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | holdCourse | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | holdCourse | response | priority | integer |  | Higher fires sooner.
FnbService | holdCourse | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | holdCourse | response | prioritiseReason | string |  | (nullable)
FnbService | holdCourse | response | lines | array of object | yes
FnbService | holdCourse | response | lines[].lineId | string (uuid) | yes
FnbService | holdCourse | response | lines[].name | string | yes
FnbService | holdCourse | response | lines[].quantity | integer | yes
FnbService | holdCourse | response | lines[].modifiers | array of string
FnbService | holdCourse | response | lines[].note | string |  | (nullable)
FnbService | holdCourse | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | holdCourse | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | holdCourse | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | holdCourse | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | holdCourse | response | lines[].course | integer |  | (nullable)
FnbService | holdCourse | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | holdCourse | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | holdCourse | response | createdAt | string (date-time) | yes
FnbService | holdCourse | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | holdCourse | response | elapsedSeconds | integer
FnbService | holdCourse | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | holdCourse | param (path) | ticketId | string (uuid) | yes
FnbService | holdCourse | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | holdOrder | request | label | string |  | How the cashier will find it again — a name, a description, a party size. (max length 60)
OrderService | holdOrder | request | holdUntil | string (date-time)
OrderService | holdOrder | request | recordedAt | string (date-time) | yes
OrderService | holdOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | holdOrder | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | holdOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | holdOrder | response | channel | object | yes | Where it came from.
OrderService | holdOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | holdOrder | response | venueId | string (uuid) | yes
OrderService | holdOrder | response | scopePath | string | yes
OrderService | holdOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | holdOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | holdOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | holdOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | holdOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | holdOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | holdOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | holdOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | holdOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | holdOrder | response | droppedPromotions[].name | string
OrderService | holdOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | holdOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | holdOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines | array of OrderLine | yes
OrderService | holdOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | holdOrder | response | lines[].variantId | string (uuid) | yes
OrderService | holdOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | holdOrder | response | lines[].performanceId | string (uuid)
OrderService | holdOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | holdOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | holdOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | holdOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | holdOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | holdOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | holdOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | holdOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | holdOrder | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | holdOrder | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | holdOrder | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | holdOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | holdOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | holdOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | holdOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].holderName | string |  | (nullable)
OrderService | holdOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | holdOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | holdOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | holdOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | holdOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | holdOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | holdOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | holdOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | holdOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | holdOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | holdOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | holdOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | holdOrder | response | payments | array of Payment
OrderService | holdOrder | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | holdOrder | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | holdOrder | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | holdOrder | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | holdOrder | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | holdOrder | response | payments[].id | string (uuid) | yes
OrderService | holdOrder | response | payments[].orderId | string (uuid) | yes
OrderService | holdOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | holdOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | holdOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | holdOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | holdOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | holdOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | holdOrder | response | payments[].providerName | string |  | (nullable)
OrderService | holdOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | holdOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | holdOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | holdOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | holdOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | holdOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | holdOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | holdOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | principalId | string (uuid)
OrderService | holdOrder | response | workstationId | string (uuid)
OrderService | holdOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | holdOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | holdOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | holdOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | holdOrder | response | createdAt | string (date-time) | yes
OrderService | holdOrder | response | recordedAt | string (date-time) | yes
OrderService | holdOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | holdOrder | param (path) | orderId | string (uuid) | yes
OrderService | holdOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | identifyGuest | request | token | string | yes
MarketingService | identifyGuest | request | tokenKind | enum (qr, rfid, nfc, membershipCard, walletPass, phone, email, appDeviceId, …) |  | Optional. (nullable)
MarketingService | identifyGuest | response | subjectId | string (uuid) | yes
MarketingService | identifyGuest | response | displayName | string
MarketingService | identifyGuest | response | matchedOn | enum (qr, rfid, nfc, membershipCard, walletPass, phone, email, appDeviceId, …) | yes | Which identifier resolved.
MarketingService | identifyGuest | response | confidence | enum (exact, probable) |  | probable where the match was on a shared identifier.
MarketingService | identifyGuest | response | entitlements | array of object |  | Live entitlements, so a gate or a till does not make a second call.
MarketingService | identifyGuest | response | entitlements[].entitlementId | string (uuid)
MarketingService | identifyGuest | response | entitlements[].productName | string
MarketingService | identifyGuest | response | entitlements[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) |  | What the storage layer holds, and what a guest is shown.
MarketingService | identifyGuest | response | entitlements[].validTo | string (date)
MarketingService | identifyGuest | response | loyalty | LoyaltyPosition
MarketingService | identifyGuest | response | loyalty.leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | identifyGuest | response | loyalty.subjectId | string (uuid) | yes
MarketingService | identifyGuest | response | loyalty.programmeId | string (uuid) | yes
MarketingService | identifyGuest | response | loyalty.pointsBalance | integer | yes
MarketingService | identifyGuest | response | loyalty.lifetimePoints | integer
MarketingService | identifyGuest | response | loyalty.tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | identifyGuest | response | loyalty.tierCode | string | yes
MarketingService | identifyGuest | response | loyalty.tierName | string
MarketingService | identifyGuest | response | loyalty.pointsToNextTier | integer |  | (nullable)
MarketingService | identifyGuest | response | loyalty.nextExpiryPoints | integer |  | (nullable)
MarketingService | identifyGuest | response | loyalty.nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | identifyGuest | response | isBarred | boolean |  | BL-134.
MarketingService | identifyGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | importTicketTemplate | request | format | string | yes | The definition format of the file. (max length 30)
OrderService | importTicketTemplate | request | fileRef | string (uuid) | yes | The uploaded definition file.
OrderService | importTicketTemplate | request | name | string | yes | (max length 120)
OrderService | importTicketTemplate | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
OrderService | importTicketTemplate | response | id | string (uuid) | yes
OrderService | importTicketTemplate | response | name | string | yes
OrderService | importTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | importTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | importTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | importTicketTemplate | response | appliesToProductKinds | array of string
OrderService | importTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | importTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | importTicketTemplate | response | layoutRef | string
OrderService | importTicketTemplate | response | localeVariants | object
OrderService | importTicketTemplate | response | isActive | boolean | yes
OrderService | importTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | importTransportNetwork | request | format | enum (csvBundle, gtfs) | yes | A zip of the four CSV files described on importTransportNetwork, or a GTFS static feed.
VenueOpsService | importTransportNetwork | request | sourceRef | string (uuid) | yes | The uploaded file, as the MediaAsset.id from assets.completeUpload.
VenueOpsService | importTransportNetwork | request | include | array of enum (stations, routes, timetables) |  | Which parts of the file to read.
VenueOpsService | importTransportNetwork | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | importTransportNetwork | response | venueId | string (uuid) | yes | (read-only)
VenueOpsService | importTransportNetwork | response | format | enum (csvBundle, gtfs) | yes
VenueOpsService | importTransportNetwork | response | sourceRef | string (uuid) | yes
VenueOpsService | importTransportNetwork | response | status | TransportNetworkImportStatus: enum (validating, previewReady, failed, applied, expired) | yes | validating → previewReady or failed; previewReady → applied, or expired after 7 days unapplied (proposed, client to correct).
VenueOpsService | importTransportNetwork | response | preview | object |  | What applying would write. (read-only; nullable)
VenueOpsService | importTransportNetwork | response | preview.stationsToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.stationsToUpdate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.routesToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.routesToUpdate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.stopsToWrite | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.timetablesToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | findings | array of TransportNetworkImportFinding |  | (max items 1000; read-only)
VenueOpsService | importTransportNetwork | response | findings[].code | enum (nothingFound, fileMissing, headerMismatch, stationCodeDuplicate, stationCoordinatesMissing, routeCodeDuplicate, routeStopUnknownStation, routeOffsetsNotIncreasing, …) | yes | stationCoordinatesMissing is a warning (the station is listed and left off the map); routeActiveStopsChanged is a warning (those stops are skipped); every other code is an error and blocks the apply.
VenueOpsService | importTransportNetwork | response | findings[].severity | enum (error, warning) | yes
VenueOpsService | importTransportNetwork | response | findings[].file | string |  | e.g. (nullable)
VenueOpsService | importTransportNetwork | response | findings[].row | integer |  | (min 1; nullable)
VenueOpsService | importTransportNetwork | response | findings[].reference | string |  | The station (nullable)
VenueOpsService | importTransportNetwork | response | findings[].message | string | yes | (max length 500)
VenueOpsService | importTransportNetwork | response | createdBy | string (uuid) |  | (read-only)
VenueOpsService | importTransportNetwork | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | importTransportNetwork | response | appliedBy | string (uuid) |  | (read-only; nullable)
VenueOpsService | importTransportNetwork | response | appliedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | importTransportNetwork | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | importVenueGeometry | request | format | enum (pdfPlan, svgPlan, dwgPlan, dxfPlan, rasterPlan, glbModel, navigationFile) | yes | glbModel and navigationFile added 3 October 2026 (r1 additions, ADR-0069): a GLB with its navigation file, or the navigation file alone.
VenueOpsService | importVenueGeometry | request | sourceRef | string (uuid) | yes | The drawing, as the MediaAsset.id from assets.completeUpload.
VenueOpsService | importVenueGeometry | request | navigationFileRef | string (uuid) |  | The navigation (pathway) file that goes with a GLB (ADR-0069 section 2; the VenueNavigationFile schema), uploaded like sourceRef as JSON. (nullable)
VenueOpsService | importVenueGeometry | request | ocr | object |  | The OCR step (3 October 2026, r1 additions); VenueMapOcrOptions. (nullable)
VenueOpsService | importVenueGeometry | request | ocr.mode | enum (auto, off) |  | off skips it, for a plan whose text is noise (a dimensioned drawing). (default auto)
VenueOpsService | importVenueGeometry | request | ocr.languages | array of enum (en, ar) |  | The scripts to read.
VenueOpsService | importVenueGeometry | request | handMarkedPaths | object |  | A raster plan with hand-marked paths (3 October 2026, r1 additions); VenueMapHandMarkedPaths. (nullable)
VenueOpsService | importVenueGeometry | request | handMarkedPaths.markColour | string |  | The marker's colour, where the operator knows it (#E53935 for a red pen). (pattern ^#[0-9A-Fa-f]{6}$; nullable)
VenueOpsService | importVenueGeometry | request | handMarkedPaths.note | string |  | Anything the marks mean that the image does not say ("dashed = staff only"). (max length 300; nullable)
VenueOpsService | importVenueGeometry | request | layerMapping | object |  | Each role takes a list.
VenueOpsService | importVenueGeometry | request | layerMapping.buildingLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.pathLayer | array of string |  | Optional, and the platform derives paths without it.
VenueOpsService | importVenueGeometry | request | layerMapping.zoneLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.labelLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.boundaryLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.exitLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.emergencyExitLayer | array of string |  | Separate from exitLayer, and drawings usually blur them.
VenueOpsService | importVenueGeometry | request | layerMapping.poiLayers | object |  | Where a drawing already marks toilets, first aid and the rest.
VenueOpsService | importVenueGeometry | request | layerMapping.resourceLayer | array of string |  | The bookable resources drawn on the plan — cabanas, loungers, tables (decided 29 September, rev 3 REV3-15).
VenueOpsService | importVenueGeometry | request | layerMapping.keepOutLayer | array of string |  | Water, planting, back-of-house, plant rooms.
VenueOpsService | importVenueGeometry | request | digitNormalisation | boolean |  | A١ and A1 are one section to a person and two to a computer, and the failure is silent — the seats simply do not join, and you get geometry with no seats or seats with no geometry. (default True)
VenueOpsService | importVenueGeometry | request | georeference | object |  | 19.2.56. (nullable)
VenueOpsService | importVenueGeometry | request | georeference.originLat | number
VenueOpsService | importVenueGeometry | request | georeference.originLng | number
VenueOpsService | importVenueGeometry | request | georeference.scaleMetresPerUnit | number
VenueOpsService | importVenueGeometry | request | georeference.rotationDegrees | number |  | (default 0)
VenueOpsService | importVenueGeometry | request | georeference.anchors | array of object |  | Two points far apart. (min items 2; max items 4)
VenueOpsService | importVenueGeometry | request | georeference.anchors[].label | string
VenueOpsService | importVenueGeometry | request | georeference.anchors[].planX | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].planY | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].lat | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].lng | number
VenueOpsService | importVenueGeometry | request | manifestRef | string (uuid) |  | The seating manifest, where this map has seats, as the MediaAsset.id from assets.completeUpload, uploaded the same way as sourceRef. (nullable)
VenueOpsService | importVenueGeometry | request | resourceManifestRef | string (uuid) |  | The resource manifest, where this map carries bookable resources (decided 29 September, rev 3 REV3-15), uploaded like manifestRef. (nullable)
VenueOpsService | importVenueGeometry | request | priceBands | array of object |  | What each price band sells as, so a placed resource can be bought: the band code the manifest uses and the catalogue.ProductVariant that prices it (Family 6, Medium 10, Large 15, XL 20 on the Coastal… (nullable)
VenueOpsService | importVenueGeometry | request | priceBands[].code | string | yes | (max length 40)
VenueOpsService | importVenueGeometry | request | priceBands[].name | string |  | (nullable)
VenueOpsService | importVenueGeometry | request | priceBands[].variantId | string (uuid) | yes
VenueOpsService | importVenueGeometry | request | createMissingResources | boolean |  | Where a manifest label has no resources.Resource with that code at this venue, create one through resources.createResource (kind, capacity and zone as attributes) instead of reporting resourceCodeUnm… (default False)
VenueOpsService | importVenueGeometry | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
VenueOpsService | importVenueGeometry | response | id | string (uuid) | yes
VenueOpsService | importVenueGeometry | response | mapId | string (uuid)
VenueOpsService | importVenueGeometry | response | sourceRef | string (uuid) |  | The drawing the import read: importVenueGeometry's sourceRef, an assets.MediaAsset id (ADAM CR-207, option A; CHG-R10ORD-013). (nullable)
VenueOpsService | importVenueGeometry | response | format | enum (pdfPlan, svgPlan, dwgPlan, dxfPlan, rasterPlan, glbModel, navigationFile) |  | The format importVenueGeometry took (ADAM CR-207). (nullable)
VenueOpsService | importVenueGeometry | response | createdAt | string (date-time) |  | When the import was started (ADAM CR-207). (read-only)
VenueOpsService | importVenueGeometry | response | status | enum (parsing, previewReady, committed, failed) | yes
VenueOpsService | importVenueGeometry | response | outcome | enum (parsed, parsedWithFindings, nothingFound, noLayersMatched, unreadable) | yes
VenueOpsService | importVenueGeometry | response | shapesFound | integer
VenueOpsService | importVenueGeometry | response | layersFound | array of string |  | Every layer name in the source, decoded.
VenueOpsService | importVenueGeometry | response | unmappedLayers | array of string
VenueOpsService | importVenueGeometry | response | manifestRowsRead | integer |  | (nullable)
VenueOpsService | importVenueGeometry | response | resourcesFound | integer |  | Bookable resource shapes found on the resource layer (rev 3 REV3-15). (nullable)
VenueOpsService | importVenueGeometry | response | resourceRowsJoined | integer |  | Resource manifest rows that joined a shape and a resources.Resource. (nullable)
VenueOpsService | importVenueGeometry | response | manifestRowsJoined | integer |  | The number to check against your own count. (nullable)
VenueOpsService | importVenueGeometry | response | findings | array of object |  | Named against the spec, so a finding maps to a section of handoff/venue-map-input-spec.md rather than to a stack trace.
VenueOpsService | importVenueGeometry | response | findings[].code | enum (duplicateLayerName, geometryOnLayerZero, unmappedLayer, mixedLayerContent, sectionCodeMismatch, digitScriptMismatch, mergedCells, totalRowDetected, …) | yes | A closed set, and each one names a rule in the spec.
VenueOpsService | importVenueGeometry | response | findings[].severity | enum (error, warning, info) | yes | warning is the important level here.
VenueOpsService | importVenueGeometry | response | findings[].message | string | yes
VenueOpsService | importVenueGeometry | response | findings[].specSection | string |  | Which part of the spec covers it — §2 Layers, §4 Digits. (nullable)
VenueOpsService | importVenueGeometry | response | findings[].affected | array of string |  | The layers, sections or rows involved.
VenueOpsService | importVenueGeometry | response | ocr | object |  | What the OCR step read off a scanned PDF or a raster (3 October 2026, r1 additions). (nullable)
VenueOpsService | importVenueGeometry | response | ocr.pagesRead | integer
VenueOpsService | importVenueGeometry | response | ocr.meanConfidence | number |  | (min 0; max 1; nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks | array of object
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].text | string | yes | (max length 500)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].language | enum (en, ar) |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].confidence | number | yes | (min 0; max 1)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].planX | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].planY | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].widthUnits | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].heightUnits | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | handMarkedPaths | object |  | The hand-marked strokes the import found on a raster plan sent with handMarkedPaths (3 October 2026, r1 additions). (nullable)
VenueOpsService | importVenueGeometry | response | handMarkedPaths.strokesFound | integer
VenueOpsService | importVenueGeometry | response | handMarkedPaths.markColourUsed | string |  | The colour the import matched. (nullable)
VenueOpsService | importVenueGeometry | response | handMarkedPaths.totalLengthUnits | number |  | In drawing units. (nullable)
VenueOpsService | importVenueGeometry | response | model | object |  | The GLB and navigation file, measured (glbModel and navigationFile imports; ADR-0069 sections 1, 2, 3 and 6; 3 October 2026). (nullable)
VenueOpsService | importVenueGeometry | response | model.sizeBytes | integer |  | The GLB. (nullable)
VenueOpsService | importVenueGeometry | response | model.lod0TrianglesMaxZone | integer |  | The most LOD0 triangles any one zone carries, which is what is on screen near the camera. (nullable)
VenueOpsService | importVenueGeometry | response | model.trianglesTotal | integer |  | Across every zone and LOD. (nullable)
VenueOpsService | importVenueGeometry | response | model.drawCalls | integer |  | Over 150 is a warning. (nullable)
VenueOpsService | importVenueGeometry | response | model.textureMemoryBytes | integer |  | After KTX2 transcoding. (nullable)
VenueOpsService | importVenueGeometry | response | model.maxTexturePx | integer |  | Over 2048 is a warning. (nullable)
VenueOpsService | importVenueGeometry | response | model.zones | integer |  | (nullable)
VenueOpsService | importVenueGeometry | response | model.nodes | integer
VenueOpsService | importVenueGeometry | response | model.edges | integer
VenueOpsService | importVenueGeometry | response | model.locations | integer
VenueOpsService | importVenueGeometry | response | model.anchorResidualMaxMetres | number |  | The worst control point. (nullable)
VenueOpsService | importVenueGeometry | response | model.publishable3d | boolean |  | True when no finding below is an error: the next publish carries the 3D layer.
VenueOpsService | importVenueGeometry | response | model.findings | array of object
VenueOpsService | importVenueGeometry | response | model.findings[].code | enum (modelOverDownloadBudget, zoneOverDownloadBudget, triangleBudgetExceeded, triangleTotalExceeded, drawCallBudgetExceeded, textureBudgetExceeded, textureTooLarge, uncompressedTextures, …) | yes | A closed set, separate from findings so the plan importer's codes stay as they were.
VenueOpsService | importVenueGeometry | response | model.findings[].severity | enum (error, warning, info) | yes
VenueOpsService | importVenueGeometry | response | model.findings[].message | string | yes
VenueOpsService | importVenueGeometry | response | model.findings[].measured | number |  | The number found. (nullable)
VenueOpsService | importVenueGeometry | response | model.findings[].limit | number |  | The budget it was measured against. (nullable)
VenueOpsService | importVenueGeometry | response | model.findings[].affected | array of string |  | The zones, nodes, locations or codes involved.
VenueOpsService | importVenueGeometry | param (path) | mapId | string (uuid) | yes
VenueOpsService | importVenueGeometry | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | importVenueHistory | request | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | importVenueHistory | request | assetId | string (uuid) | yes | The uploaded export, in the asset library.
AiService | importVenueHistory | request | sourceSystem | string |  | What produced the file, e.g. (nullable)
AiService | importVenueHistory | request | columnMapping | object | yes | Target field to source column, e.g.
AiService | importVenueHistory | request | dryRun | boolean |  | Validate and report without loading. (default False)
AiService | importVenueHistory | response | id | string (uuid) | yes | (read-only)
AiService | importVenueHistory | response | venueId | string (uuid) | yes
AiService | importVenueHistory | response | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | importVenueHistory | response | assetId | string (uuid)
AiService | importVenueHistory | response | sourceSystem | string |  | (nullable)
AiService | importVenueHistory | response | columnMapping | object
AiService | importVenueHistory | response | dryRun | boolean |  | (default False)
AiService | importVenueHistory | response | status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | importVenueHistory | response | periodFrom | string (date) |  | (read-only; nullable)
AiService | importVenueHistory | response | periodTo | string (date) |  | (read-only; nullable)
AiService | importVenueHistory | response | monthsCovered | integer |  | (read-only)
AiService | importVenueHistory | response | rowsRead | integer |  | (read-only)
AiService | importVenueHistory | response | rowsLoaded | integer |  | (read-only)
AiService | importVenueHistory | response | rowsRejected | integer |  | (read-only)
AiService | importVenueHistory | response | findings | array of object |  | (read-only)
AiService | importVenueHistory | response | findings[].row | integer
AiService | importVenueHistory | response | findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | importVenueHistory | response | findings[].detail | string
AiService | importVenueHistory | response | requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | importVenueHistory | response | createdAt | string (date-time) |  | (read-only)
AiService | importVenueHistory | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | importVenueHistory | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | importVenueHistory | param (path) | venueId | string (uuid) | yes
AiService | importVenueHistory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | ingestFxRates | request | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | request | pairs | array of string |  | AED/USD form.
LedgerService | ingestFxRates | request | effectiveFrom | string (date) |  | Defaults to the next business day in the region timezone. (nullable)
LedgerService | ingestFxRates | request | dryRun | boolean |  | Fetch and report without writing. (default False)
LedgerService | ingestFxRates | response | source | FxRateSource: enum (manual, uaeCentralBank, ecb, openExchangeRates, cardScheme, provider) |  | Where the rate came from, and which provider specifically.
LedgerService | ingestFxRates | response | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) |  | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | response | ratesWritten | integer
LedgerService | ingestFxRates | response | unchanged | integer
LedgerService | ingestFxRates | response | largestMove | string |  | The number a person reads. (pattern ^-?\d+(\.\d{1,6})?$; nullable)
LedgerService | ingestFxRates | response | rates | array of FxRate
LedgerService | ingestFxRates | response | rates[].id | string (uuid) |  | (read-only)
LedgerService | ingestFxRates | response | rates[].fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | ingestFxRates | response | rates[].toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | ingestFxRates | response | rates[].rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | ingestFxRates | response | rates[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | response | rates[].source | object |  | (read-only)
LedgerService | ingestFxRates | response | rates[].effectiveFrom | string (date-time) | yes
LedgerService | ingestFxRates | response | rates[].effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | ingestFxRates | response | rates[].setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | ingestFxRates | response | rates[].note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | ingestFxRates | response | rates[].providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | ingestFxRates | response | rates[].fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | ingestFxRates | response | rates[].chargeable | boolean |  | With venueId, true where a guest may select this currency and pay in it at that venue (tenancy.VenueSettings.chargeCurrencies), false where it is shown as an approximate price only (CHG-FIN-001). (read-only)
LedgerService | ingestFxRates | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | ingestKnowledgeDocument | request | id | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | request | collectionId | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | request | title | string | yes
AiService | ingestKnowledgeDocument | request | sourceAssetId | string (uuid) | yes
AiService | ingestKnowledgeDocument | request | mimeType | string
AiService | ingestKnowledgeDocument | request | venueId | string (uuid) |  | A venue to narrow the document to (R8 blocker ORDERS-MONEY-C36): the document's scopePath becomes that venue's path, which must be at or below the collection's node (else 400). (nullable)
AiService | ingestKnowledgeDocument | request | reingestDocumentId | string (uuid) |  | An indexed or failed document in this collection to process again from sourceAssetId. (nullable)
AiService | ingestKnowledgeDocument | request | supersedesDocumentId | string (uuid) |  | The indexed document in this collection that this one replaces. (nullable)
AiService | ingestKnowledgeDocument | request | status | enum (processing, indexed, failed, superseded) |  | (read-only)
AiService | ingestKnowledgeDocument | request | chunkCount | integer |  | (read-only)
AiService | ingestKnowledgeDocument | request | failureReason | string |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | request | indexedAt | string (date-time) |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | request | scopePath | string |  | Added 29 September (AI design 3.1): ai.knowledge_document had no policy, so neither did its chunks. (read-only)
AiService | ingestKnowledgeDocument | response | id | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | response | collectionId | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | response | title | string | yes
AiService | ingestKnowledgeDocument | response | sourceAssetId | string (uuid) | yes
AiService | ingestKnowledgeDocument | response | mimeType | string
AiService | ingestKnowledgeDocument | response | venueId | string (uuid) |  | A venue to narrow the document to (R8 blocker ORDERS-MONEY-C36): the document's scopePath becomes that venue's path, which must be at or below the collection's node (else 400). (nullable)
AiService | ingestKnowledgeDocument | response | reingestDocumentId | string (uuid) |  | An indexed or failed document in this collection to process again from sourceAssetId. (nullable)
AiService | ingestKnowledgeDocument | response | supersedesDocumentId | string (uuid) |  | The indexed document in this collection that this one replaces. (nullable)
AiService | ingestKnowledgeDocument | response | status | enum (processing, indexed, failed, superseded) |  | (read-only)
AiService | ingestKnowledgeDocument | response | chunkCount | integer |  | (read-only)
AiService | ingestKnowledgeDocument | response | failureReason | string |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | response | indexedAt | string (date-time) |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | response | scopePath | string |  | Added 29 September (AI design 3.1): ai.knowledge_document had no policy, so neither did its chunks. (read-only)
AiService | ingestKnowledgeDocument | param (path) | collectionId | string (uuid) | yes
AiService | ingestKnowledgeDocument | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | inquirePaymentStatus | response | tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | inquirePaymentStatus | response | tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | inquirePaymentStatus | response | tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | inquirePaymentStatus | response | tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | inquirePaymentStatus | response | tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | inquirePaymentStatus | response | id | string (uuid) | yes
OrderService | inquirePaymentStatus | response | orderId | string (uuid) | yes
OrderService | inquirePaymentStatus | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | inquirePaymentStatus | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | inquirePaymentStatus | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | inquirePaymentStatus | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | inquirePaymentStatus | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | inquirePaymentStatus | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | inquirePaymentStatus | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | inquirePaymentStatus | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | inquirePaymentStatus | response | providerName | string |  | (nullable)
OrderService | inquirePaymentStatus | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | inquirePaymentStatus | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | inquirePaymentStatus | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | inquirePaymentStatus | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | inquirePaymentStatus | response | nextAction.kind | enum (redirect, terminal)
OrderService | inquirePaymentStatus | response | nextAction.url | string (uri) |  | (nullable)
OrderService | inquirePaymentStatus | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | response | recordedAt | string (date-time) | yes
OrderService | inquirePaymentStatus | response | syncedAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | param (path) | paymentId | string (uuid) | yes
OrderService | inquirePaymentStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | issueCreditMemo | request | kind | enum (full, partial) | yes
LedgerService | issueCreditMemo | request | reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | issueCreditMemo | request | refundId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | request | cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | request | lines | array of object |  | Required for partial.
LedgerService | issueCreditMemo | request | lines[].lineNumber | integer | yes | (min 1)
LedgerService | issueCreditMemo | request | lines[].quantity | number |  | (nullable)
LedgerService | issueCreditMemo | request | lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | request | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | request | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | request | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | request | note | string |  | (max length 500; nullable)
LedgerService | issueCreditMemo | response | id | string (uuid) | yes | (read-only)
LedgerService | issueCreditMemo | response | creditMemoNumber | string | yes | Server-assigned from the legal entity's credit memo series, in sequence without gaps. (read-only)
LedgerService | issueCreditMemo | response | taxInvoiceId | string (uuid) | yes
LedgerService | issueCreditMemo | response | taxInvoiceNumber | string |  | (read-only)
LedgerService | issueCreditMemo | response | kind | enum (full, partial) | yes
LedgerService | issueCreditMemo | response | reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | issueCreditMemo | response | refundId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | legalEntityId | string (uuid) | yes
LedgerService | issueCreditMemo | response | buyerSubjectId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | issuedAt | string (date-time) | yes
LedgerService | issueCreditMemo | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | legalFxRate | object |  | The invoice's own legalFxRate, never today's (CHG-FIN-011). (read-only; nullable)
LedgerService | issueCreditMemo | response | invoiceSupplyValue | object |  | The value of the supply shown on the tax invoice (Executive Regulation Art. (read-only)
LedgerService | issueCreditMemo | response | invoiceSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | invoiceSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | invoiceSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | correctedSupplyValue | object |  | The correct value of the supply after this credit note (Art. (read-only)
LedgerService | issueCreditMemo | response | correctedSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | correctedSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | correctedSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | supplierName | string |  | Snapshot of the legal entity at issue, as on the invoice (Art. (read-only)
LedgerService | issueCreditMemo | response | supplierAddress | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | supplierTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | buyerName | string |  | The recipient as on the invoice; name, address and TRN where they are registered (Art. (read-only; nullable)
LedgerService | issueCreditMemo | response | buyerAddress | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | buyerTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | note | string |  | The brief explanation of why the credit note was issued, printed on it (Art. (nullable)
LedgerService | issueCreditMemo | response | renditionAssetId | string (uuid) |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | issueCreditMemo | response | issuedByPrincipalId | string (uuid) |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | lines | array of FinCreditMemoLine | yes
LedgerService | issueCreditMemo | response | lines[].invoiceLineNumber | integer | yes | (min 1)
LedgerService | issueCreditMemo | response | lines[].description | string |  | (max length 500)
LedgerService | issueCreditMemo | response | lines[].quantity | number |  | (nullable)
LedgerService | issueCreditMemo | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | lines[].taxRate | number
LedgerService | issueCreditMemo | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | issueCreditMemo | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | scopePath | string |  | (read-only)
LedgerService | issueCreditMemo | param (path) | invoiceId | string (uuid) | yes
LedgerService | issueCreditMemo | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | issueGameCard | request | id | string (uuid) | yes | Client-generated UUIDv7 for this request, and the idempotency key: it must equal the Idempotency-Key header, and a mismatch is the shared 409 Conflict.
VenueOpsService | issueGameCard | request | kind | enum (physical, digital) | yes
VenueOpsService | issueGameCard | request | cardCode | string |  | Required for physical cards, which are pre-printed.
VenueOpsService | issueGameCard | request | venueId | string (uuid) | yes
VenueOpsService | issueGameCard | request | subjectId | string (uuid)
VenueOpsService | issueGameCard | request | initialCredits | integer |  | (min 0; default 0)
VenueOpsService | issueGameCard | request | validMonths | integer |  | (min 1)
VenueOpsService | issueGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | issueGameCard | response | kind | string
VenueOpsService | issueGameCard | response | venueId | string (uuid) | yes
VenueOpsService | issueGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | issueGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | issueGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | issueGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | issueGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | issueGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | issueGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | issueGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | issueGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | issueGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | issueGameCard | response | id | string (uuid) |  | The card's own id (4 October 2026, CHG-FXC-006): the {cardId} of setGameCardLifecycle, which had no column to match, and the id of the Wallet view wallet.loadGameCredits and wallet.adjustGameCard ret… (read-only)
VenueOpsService | issueGameCard | response | walletId | string (uuid) |  | Where the card's credits are held (4 October 2026, CHG-FXC-006). (read-only; nullable)
VenueOpsService | issueGameCard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | issueTaxInvoice | request | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | issueTaxInvoice | request | orderIds | array of string (uuid) | yes | One order for simplified and full; one or more for consolidated. (min items 1)
LedgerService | issueTaxInvoice | request | recipient | FinTaxInvoiceRecipient |  | Who the invoice is addressed to.
LedgerService | issueTaxInvoice | request | recipient.name | string | yes | (max length 300)
LedgerService | issueTaxInvoice | request | recipient.address | string |  | The recipient's postal address. (max length 1000; nullable)
LedgerService | issueTaxInvoice | request | recipient.countryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | issueTaxInvoice | request | recipient.taxRegistrationNumber | string |  | The recipient's TRN where they are VAT-registered. (max length 30; nullable)
LedgerService | issueTaxInvoice | request | recipient.customerAccountId | string (uuid) |  | The B2B credit account (payments B2bCreditAccount) where a company is invoiced. (nullable)
LedgerService | issueTaxInvoice | request | languages | array of string |  | Overrides the template's languages for this document, within those the template offers.
LedgerService | issueTaxInvoice | request | supersedesInvoiceId | string (uuid) |  | A simplified invoice this full invoice replaces for the same supply. (nullable)
LedgerService | issueTaxInvoice | request | deliverToEmail | string (email) |  | Sends the PDF on issue as well as returning it. (nullable)
LedgerService | issueTaxInvoice | response | id | string (uuid) | yes | (read-only)
LedgerService | issueTaxInvoice | response | invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | issueTaxInvoice | response | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | issueTaxInvoice | response | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | issueTaxInvoice | response | legalEntityId | string (uuid) | yes
LedgerService | issueTaxInvoice | response | templateId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | venueId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | orderIds | array of string (uuid)
LedgerService | issueTaxInvoice | response | supplierName | string
LedgerService | issueTaxInvoice | response | supplierAddress | string |  | (nullable)
LedgerService | issueTaxInvoice | response | supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | issueTaxInvoice | response | buyerName | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerAddress | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | issueTaxInvoice | response | buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | issueTaxInvoice | response | customerAccountId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | issuedAt | string (date-time) | yes
LedgerService | issueTaxInvoice | response | supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | issueTaxInvoice | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | legalCurrency | string |  | The legal entity's currency (AED in the UAE), in which the law requires the tax and the gross amount (CHG-FIN-011). (pattern ^[A-Z]{3}$; read-only)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency | object |  | The gross amount payable in the legal currency (Executive Regulation Art. (read-only)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | legalFxRate | object |  | Units of the legal currency per one unit of currency, printed with the tax where the invoice is not in the legal currency (Art. (read-only; nullable)
LedgerService | issueTaxInvoice | response | legalFxRateSource | object |  | uaeCentralBank for a UAE legal entity (Decree-Law Art. (read-only; nullable)
LedgerService | issueTaxInvoice | response | paidCurrency | string |  | Where the guest paid in a currency they selected (orders.Order.chargeCurrency, CHG-FIN-001), printed as payment information with paidAmount and the charge rate. (pattern ^[A-Z]{3}$; read-only; nullable)
LedgerService | issueTaxInvoice | response | paidAmount | object |  | What the guest paid in paidCurrency (orders.Order.chargeTotal). (read-only)
LedgerService | issueTaxInvoice | response | paidAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | paidAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | paidAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | reverseChargeStatement | string |  | Where the recipient must account for the tax, the statement saying so and the Decree-Law provision (Art. (read-only; nullable)
LedgerService | issueTaxInvoice | response | creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | languages | array of string
LedgerService | issueTaxInvoice | response | supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | issueTaxInvoice | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | issueTaxInvoice | response | issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | issueTaxInvoice | response | lines | array of FinTaxInvoiceLine | yes
LedgerService | issueTaxInvoice | response | lines[].lineNumber | integer | yes | (min 1)
LedgerService | issueTaxInvoice | response | lines[].orderId | string (uuid)
LedgerService | issueTaxInvoice | response | lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | lines[].description | string | yes | (max length 500)
LedgerService | issueTaxInvoice | response | lines[].quantity | number | yes
LedgerService | issueTaxInvoice | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | lines[].taxRate | number |  | (min 0; max 100)
LedgerService | issueTaxInvoice | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | issueTaxInvoice | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency | object |  | The amount payable for the line in the legal currency (AED), Executive Regulation Art. (read-only)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | issueTaxInvoice | response | taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | issueTaxInvoice | response | taxSummary[].taxRate | number
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | issueTaxInvoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | issueWalletPass | request | entitlementId | string (uuid) | yes
OrderService | issueWalletPass | request | platform | enum (apple, google) | yes
OrderService | issueWalletPass | response | id | string (uuid) | yes
OrderService | issueWalletPass | response | entitlementId | string (uuid) | yes
OrderService | issueWalletPass | response | platform | enum (apple, google) | yes
OrderService | issueWalletPass | response | serialNumber | string | yes
OrderService | issueWalletPass | response | passUrl | string (uri) |  | What the app adds to the wallet (R8 blocker ORDERS-MONEY-C39, CHG-R8MIG-017): for apple a short-lived signed link to the .pkpass file (signed with the brand's Pass Type ID certificate), for google th… (read-only)
OrderService | issueWalletPass | response | authenticationToken | string (password) |  | Write-only.
OrderService | issueWalletPass | response | status | enum (issued, updated, voided, expired) | yes
OrderService | issueWalletPass | response | lastPushedAt | string (date-time) |  | (nullable)
OrderService | issueWalletPass | response | deviceRegistrations | integer |  | How many devices hold it.
OrderService | issueWalletPass | response | scopePath | string |  | The partition key (ADR-0005).
OrderService | issueWalletPass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | joinQueue | request | id | string (uuid) | yes
VenueOpsService | joinQueue | request | queueId | string (uuid) | yes
VenueOpsService | joinQueue | request | partySize | integer | yes | (min 1)
VenueOpsService | joinQueue | request | entitlementId | string |  | Fast Pass or priority entitlement. (nullable)
VenueOpsService | joinQueue | request | partyHeightsCm | array of integer |  | Where the queue has a height requirement.
VenueOpsService | joinQueue | request | accessibilityNeedDeclared | boolean |  | The party declares an accessibility need (5.6.7; decided 29 September, build pass). (default False)
VenueOpsService | joinQueue | request | promotionCode | string |  | A promotion code the guest holds, checked against the lane's QueueFastPass.promotionIds (5.6.34). (max length 64; nullable)
VenueOpsService | joinQueue | request | recordedAt | string (date-time) | yes
VenueOpsService | joinQueue | response | id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | joinQueue | response | queueId | string (uuid) | yes
VenueOpsService | joinQueue | response | queueName | LocalisedText
VenueOpsService | joinQueue | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | joinQueue | response | partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | joinQueue | response | partySize | integer | yes
VenueOpsService | joinQueue | response | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | joinQueue | response | positionInQueue | integer |  | (nullable)
VenueOpsService | joinQueue | response | partiesAhead | integer |  | (nullable)
VenueOpsService | joinQueue | response | estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | isFastPass | boolean
VenueOpsService | joinQueue | response | priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | joinQueue | response | priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | joinQueue | response | priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | joinQueue | response | accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | joinQueue | response | entitlementId | string |  | (nullable)
VenueOpsService | joinQueue | response | calledAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | admittedCount | integer |  | (nullable)
VenueOpsService | joinQueue | response | joinedAt | string (date-time) | yes
VenueOpsService | joinQueue | response | syncedAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | overriddenByPrincipalId | string (uuid) |  | Who let the party past the queue (overrideWaitingGuest, 4 October 2026, CHG-FXC-003), with overrideReason and overriddenAt. (read-only; nullable)
VenueOpsService | joinQueue | response | overrideReason | string |  | (read-only; nullable)
VenueOpsService | joinQueue | response | overriddenAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | joinQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | joinRestaurantWaitlist | request | id | string (uuid) | yes
FnbService | joinRestaurantWaitlist | request | outletId | string (uuid) | yes
FnbService | joinRestaurantWaitlist | request | subjectId | string (uuid) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | partySize | integer | yes
FnbService | joinRestaurantWaitlist | request | quotedWaitMinutes | integer |  | (nullable)
FnbService | joinRestaurantWaitlist | request | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes | (read-only)
FnbService | joinRestaurantWaitlist | request | notifiedAt | string (date-time) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | joinRestaurantWaitlist | request | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | joinRestaurantWaitlist | request | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | joinRestaurantWaitlist | response | id | string (uuid) | yes
FnbService | joinRestaurantWaitlist | response | outletId | string (uuid) | yes
FnbService | joinRestaurantWaitlist | response | subjectId | string (uuid) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | partySize | integer | yes
FnbService | joinRestaurantWaitlist | response | quotedWaitMinutes | integer |  | (nullable)
FnbService | joinRestaurantWaitlist | response | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes | (read-only)
FnbService | joinRestaurantWaitlist | response | notifiedAt | string (date-time) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | joinRestaurantWaitlist | response | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | joinRestaurantWaitlist | response | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | joinRestaurantWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | joinWaitlist | request | id | string (uuid) |  | (read-only)
CatalogueService | joinWaitlist | request | performanceId | string (uuid) | yes
CatalogueService | joinWaitlist | request | variantId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | request | subjectId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | request | contactPoint | string |  | Where the offer goes.
CatalogueService | joinWaitlist | request | partySize | integer | yes | (min 1)
CatalogueService | joinWaitlist | request | status | object |  | Set by the server. (read-only)
CatalogueService | joinWaitlist | request | position | integer |  | First in, first offered. (read-only)
CatalogueService | joinWaitlist | request | offeredAt | string (date-time) |  | (read-only; nullable)
CatalogueService | joinWaitlist | request | offerExpiresAt | string (date-time) |  | The offer moves on when this passes. (read-only; nullable)
CatalogueService | joinWaitlist | request | joinedAt | string (date-time) |  | (read-only)
CatalogueService | joinWaitlist | response | id | string (uuid) |  | (read-only)
CatalogueService | joinWaitlist | response | performanceId | string (uuid) | yes
CatalogueService | joinWaitlist | response | variantId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | response | contactPoint | string |  | Where the offer goes.
CatalogueService | joinWaitlist | response | partySize | integer | yes | (min 1)
CatalogueService | joinWaitlist | response | status | object |  | Set by the server. (read-only)
CatalogueService | joinWaitlist | response | position | integer |  | First in, first offered. (read-only)
CatalogueService | joinWaitlist | response | offeredAt | string (date-time) |  | (read-only; nullable)
CatalogueService | joinWaitlist | response | offerExpiresAt | string (date-time) |  | The offer moves on when this passes. (read-only; nullable)
CatalogueService | joinWaitlist | response | joinedAt | string (date-time) |  | (read-only)
CatalogueService | joinWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | launchCampaign | request | scheduledFor | string (date-time)
MarketingService | launchCampaign | request | confirmAudienceSize | integer |  | Guard against a segment that has grown unexpectedly.
MarketingService | launchCampaign | response | campaignId | string (uuid) | yes
MarketingService | launchCampaign | response | audienceSize | integer | yes
MarketingService | launchCampaign | response | queuedCount | integer | yes
MarketingService | launchCampaign | response | excluded | array of object | yes | Why each excluded guest was excluded, in aggregate.
MarketingService | launchCampaign | response | excluded[].reason | enum (noConsent, consentRequiresRenewal, suppressed, noAddress, frequencyCap, outsideSendWindow)
MarketingService | launchCampaign | response | excluded[].count | integer
MarketingService | launchCampaign | response | scheduledFor | string (date-time) |  | (nullable)
MarketingService | launchCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | launchCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | leaveQueue | param (path) | entryId | string (uuid) | yes
VenueOpsService | leaveQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | leaveRestaurantWaitlist | request | note | string |  | Why, where the guest or host gave a reason. (max length 300; nullable)
FnbService | leaveRestaurantWaitlist | response | id | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | response | outletId | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | response | subjectId | string (uuid) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | partySize | integer | yes
FnbService | leaveRestaurantWaitlist | response | quotedWaitMinutes | integer |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes | (read-only)
FnbService | leaveRestaurantWaitlist | response | notifiedAt | string (date-time) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | leaveRestaurantWaitlist | response | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | leaveRestaurantWaitlist | response | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | leaveRestaurantWaitlist | param (path) | entryId | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | leaveWaitlist | param (path) | entryId | string (uuid) | yes
CatalogueService | leaveWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | linkGuestCheckout | request | orderReference | string | yes
IdentityService | linkGuestCheckout | request | verificationCode | string |  | From the booking confirmation.
IdentityService | linkGuestCheckout | response | attachedOrderCount | integer |  | The named booking plus any other orders with the same verified contact detail.
IdentityService | linkGuestCheckout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | list86Events | response | items | array of EightySixEvent | yes
FnbService | list86Events | response | items[].id | string (uuid) | yes
FnbService | list86Events | response | items[].outletId | string (uuid)
FnbService | list86Events | response | items[].menuItemId | string (uuid) | yes
FnbService | list86Events | response | items[].offAt | string (date-time) | yes
FnbService | list86Events | response | items[].backAt | string (date-time) |  | (nullable)
FnbService | list86Events | response | items[].reason | enum (ranOut, qualityIssue, equipmentDown, supplierFailure, seasonal, other) |  | other always carries a note (audit R222).
FnbService | list86Events | response | items[].note | string |  | The note given with the 86. (max length 500; nullable)
FnbService | list86Events | response | items[].calledByPrincipalId | string (uuid)
FnbService | list86Events | response | items[].source | enum (manual, dailyCount) |  | Who took the item off (CHG-CSA-017). (default manual; read-only)
FnbService | list86Events | response | items[].refusedOrderCount | integer |  | (default 0; read-only)
FnbService | list86Events | response | nextCursor | string
FnbService | list86Events | response | hasMore | boolean | yes
FnbService | list86Events | param (path) | outletId | string (uuid) | yes
FnbService | list86Events | param (query) | from | string (date) |  | First calendar day, in the Region's time zone, not UTC.
FnbService | list86Events | param (query) | pageSize | integer
FnbService | list86Events | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listActiveSessions | response | items | array of ActiveSession | yes
IdentityService | listActiveSessions | response | items[].status | object | yes | A registry that only holds live sessions cannot answer why one ended.
IdentityService | listActiveSessions | response | items[].sessionId | string | yes | The session's identity.session.id, written as text, and the key forceLogout takes in its path (R8 blocker fix, IDENTITY-C02).
IdentityService | listActiveSessions | response | items[].principalId | string (uuid) | yes
IdentityService | listActiveSessions | response | items[].principalName | string |  | Read from identity.principal with the row.
IdentityService | listActiveSessions | response | items[].endedAt | string (date-time) |  | When the session ended; null exactly while active, and set on every other status (R8 blocker IDENTITY-C46, CHG-R8MIG-015; a table CHECK since ADAM CR-242, 26 October 2026). (read-only; nullable)
IdentityService | listActiveSessions | response | items[].endedByPrincipalId | string (uuid) |  | Who ended it (forceLogout's caller or supervisor; the principal itself when changeOwnCredential ended its other sessions); null when the principal signed out or it expired. (read-only; nullable)
IdentityService | listActiveSessions | response | items[].endReason | string |  | Why it was ended, as forceLogout was given it (or supervisor-takeover from the till door, or credential-changed when changeOwnCredential ended it; ADAM CR-242). (min length 3; max length 500; read-only; nullable)
IdentityService | listActiveSessions | response | items[].roleId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].roleName | string |  | Read from identity.role with the row. (nullable)
IdentityService | listActiveSessions | response | items[].workstationId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].workstationName | string |  | Read from the workstation with the row. (nullable)
IdentityService | listActiveSessions | response | items[].venueId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].ipAddress | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].deviceInfo | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].hasOpenShift | boolean |  | Revoking this session leaves cash unreconciled.
IdentityService | listActiveSessions | response | items[].mfaSatisfied | boolean
IdentityService | listActiveSessions | response | items[].startedAt | string (date-time) | yes
IdentityService | listActiveSessions | response | items[].lastSeenAt | string (date-time) | yes
IdentityService | listActiveSessions | response | nextCursor | string
IdentityService | listActiveSessions | response | hasMore | boolean | yes
IdentityService | listActiveSessions | param (header) | X-Supervisor-Principal-Id | string (uuid) |  | With no session (POS-000), the supervisor signing the step-up (CHG-RUL-015).
IdentityService | listActiveSessions | param (header) | X-Supervisor-Username | string |  | With no session (POS-000), the supervisor's employee number, instead of X-Supervisor-Principal-Id (exactly one of the two; R8 blocker fix, IDENTITY-C44).
IdentityService | listActiveSessions | param (header) | X-Supervisor-Pin | string (password) |  | With no session (POS-000), the supervisor's staff PIN, as SupervisorStepUp.credential (CHG-RUL-015).
IdentityService | listActiveSessions | param (query) | venueId | string (uuid) |  | Exact match on ActiveSession.venueId.
IdentityService | listActiveSessions | param (query) | principalId | string (uuid) |  | Exact match on ActiveSession.principalId.
IdentityService | listActiveSessions | param (query) | workstationId | string (uuid) |  | Exact match on ActiveSession.workstationId — who holds this till, which POS-000 Sign In asks before offering a force-logout, without paging through every session in the venue.
IdentityService | listActiveSessions | param (query) | status | SessionStatus: enum (active, signedOut, terminated, expired) |  | Which sessions come back (R8 blocker IDENTITY-C46, CHG-R8MIG-015): active when absent, the live holder BO-053 and POS-000 ask about; another value returns the ended sessions of that status, kept with…
IdentityService | listActiveSessions | param (query) | pageSize | integer
IdentityService | listActiveSessions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiCapabilities | response | items | array of AiCapabilityRegistration | yes
AiService | listAiCapabilities | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiCapabilities | response | items[].capabilityKey | string | yes | Stable key, unique per tenant: assistant.guest, forecast.attendance, risk.transaction, config.assistant, recommend.checkout.
AiService | listAiCapabilities | response | items[].family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …) | yes | The fourteen capabilities of the AI system design (section 1.1), C1 to C14 in order: gateway and model registry, governance decision point, action pipeline and human oversight, knowledge and retrieva…
AiService | listAiCapabilities | response | items[].name | string
AiService | listAiCapabilities | response | items[].description | string |  | (nullable)
AiService | listAiCapabilities | response | items[].ownerPrincipalId | string (uuid) |  | The accountable business owner (AIC-144). (nullable)
AiService | listAiCapabilities | response | items[].businessFunction | string |  | (nullable)
AiService | listAiCapabilities | response | items[].riskClass | AiRiskClass: enum (low, medium, high, critical) | yes | Business, customer, financial, operational, security and compliance impact of a capability or action type (AIC-144, ADM-521).
AiService | listAiCapabilities | response | items[].autonomyCeiling | object |  | The first-release ceiling for this capability (design 3.8 table). (read-only)
AiService | listAiCapabilities | response | items[].autonomyLevel | object | yes | The level in force at this scope.
AiService | listAiCapabilities | response | items[].dataCategories | array of string |  | Data categories the capability reads (ADM-524).
AiService | listAiCapabilities | response | items[].lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | listAiCapabilities | response | items[].lifecycle.development | enum (draft, pilot, active, retired)
AiService | listAiCapabilities | response | items[].lifecycle.staging | enum (draft, pilot, active, retired)
AiService | listAiCapabilities | response | items[].lifecycle.production | enum (draft, pilot, active, retired)
AiService | listAiCapabilities | response | items[].degradationMode | enum (rulesOnly, searchOnly, humanHandoff, hidden, failOpen, lastPublished) |  | What the capability does when its model or the service is unavailable (design 3.7, AIC-241).
AiService | listAiCapabilities | response | items[].status | enum (active, paused) |  | Paused by pauseAiCapability: the capability answers from its degradation mode until resumed. (read-only)
AiService | listAiCapabilities | response | items[].pausedReason | string |  | (read-only; nullable)
AiService | listAiCapabilities | response | items[].pausedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiCapabilities | response | items[].updatedAt | string (date-time) |  | (read-only)
AiService | listAiCapabilities | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiCapabilities | response | nextCursor | string
AiService | listAiCapabilities | response | hasMore | boolean | yes
AiService | listAiCapabilities | param (query) | family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …)
AiService | listAiCapabilities | param (query) | status | enum (active, paused)
AiService | listAiCapabilities | param (query) | riskClass | AiRiskClass: enum (low, medium, high, critical)
AiService | listAiCapabilities | param (query) | pageSize | integer
AiService | listAiCapabilities | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiConversations | response | items | array of AiConversation | yes
AiService | listAiConversations | response | items[].id | string (uuid) | yes
AiService | listAiConversations | response | items[].principalId | string (uuid) | yes | The staff member who opened the conversation; null when a guest opened it (subjectId). (nullable)
AiService | listAiConversations | response | items[].subjectId | string (uuid) |  | The guest who opened the conversation (a guest is not a principal); null for staff. (nullable)
AiService | listAiConversations | response | items[].profileKey | string |  | The assistant profile the conversation runs under (configureAssistantProfile), as createAiConversation set it; null for the module's default profile (R8 blocker WHITE-C27). (nullable)
AiService | listAiConversations | response | items[].scopePath | string
AiService | listAiConversations | response | items[].module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
AiService | listAiConversations | response | items[].locale | string
AiService | listAiConversations | response | items[].messageCount | integer
AiService | listAiConversations | response | items[].startedAt | string (date-time) | yes
AiService | listAiConversations | response | items[].lastMessageAt | string (date-time)
AiService | listAiConversations | response | nextCursor | string
AiService | listAiConversations | response | hasMore | boolean | yes
AiService | listAiConversations | param (query) | pageSize | integer
AiService | listAiConversations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiEvaluations | response | items | array of AiEvaluationRun | yes
AiService | listAiEvaluations | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiEvaluations | response | items[].suiteId | string (uuid) | yes
AiService | listAiEvaluations | response | items[].releaseId | string (uuid) |  | (nullable)
AiService | listAiEvaluations | response | items[].kind | enum (offline, backtest, shadow) | yes
AiService | listAiEvaluations | response | items[].candidateRef | string
AiService | listAiEvaluations | response | items[].baselineRef | string |  | (nullable)
AiService | listAiEvaluations | response | items[].status | enum (queued, running, passed, failed, error) | yes | (read-only)
AiService | listAiEvaluations | response | items[].metrics | object |  | (read-only; nullable)
AiService | listAiEvaluations | response | items[].gate | object |  | The promotion gate thresholds (design 3.5 table) and whether each passed. (read-only; nullable)
AiService | listAiEvaluations | response | items[].isolationCasesPassed | boolean |  | False blocks release, whatever the other metrics say. (read-only)
AiService | listAiEvaluations | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listAiEvaluations | response | items[].startedAt | string (date-time) |  | (read-only)
AiService | listAiEvaluations | response | items[].completedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiEvaluations | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiEvaluations | response | nextCursor | string
AiService | listAiEvaluations | response | hasMore | boolean | yes
AiService | listAiEvaluations | param (query) | releaseId | string (uuid)
AiService | listAiEvaluations | param (query) | capabilityKey | string
AiService | listAiEvaluations | param (query) | status | enum (queued, running, passed, failed, error)
AiService | listAiEvaluations | param (query) | pageSize | integer
AiService | listAiEvaluations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiGovernanceAlerts | response | items | array of AiGovernanceAlert | yes
AiService | listAiGovernanceAlerts | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiGovernanceAlerts | response | items[].kind | enum (policyViolation, crossScopeAttempt, maskingDefect, dataUsage, behaviourDrift, inputDrift, bias, overrideRateShift, …) | yes
AiService | listAiGovernanceAlerts | response | items[].severity | enum (info, low, medium, high, critical) | yes
AiService | listAiGovernanceAlerts | response | items[].capabilityKey | string |  | (nullable)
AiService | listAiGovernanceAlerts | response | items[].releaseId | string (uuid) |  | For promotionReady and evaluationRegression: the release concerned. (nullable)
AiService | listAiGovernanceAlerts | response | items[].subjectRef | string |  | (nullable)
AiService | listAiGovernanceAlerts | response | items[].evidence | object |  | (nullable)
AiService | listAiGovernanceAlerts | response | items[].status | enum (open, acknowledged, dismissed, resolved, incidentOpened) | yes | (read-only)
AiService | listAiGovernanceAlerts | response | items[].incidentId | string (uuid) |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].raisedAt | string (date-time) |  | (read-only)
AiService | listAiGovernanceAlerts | response | items[].decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].decidedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].note | string |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiGovernanceAlerts | response | nextCursor | string
AiService | listAiGovernanceAlerts | response | hasMore | boolean | yes
AiService | listAiGovernanceAlerts | param (query) | kind | enum (policyViolation, crossScopeAttempt, maskingDefect, dataUsage, behaviourDrift, inputDrift, bias, overrideRateShift, …)
AiService | listAiGovernanceAlerts | param (query) | status | enum (open, acknowledged, dismissed, resolved, incidentOpened)
AiService | listAiGovernanceAlerts | param (query) | severity | enum (info, low, medium, high, critical)
AiService | listAiGovernanceAlerts | param (query) | pageSize | integer
AiService | listAiGovernanceAlerts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiGovernancePolicyVersions | response | items | array of AiGovernancePolicyVersion | yes
AiService | listAiGovernancePolicyVersions | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiGovernancePolicyVersions | response | items[].policyId | string (uuid) | yes
AiService | listAiGovernancePolicyVersions | response | items[].version | integer | yes | (min 1)
AiService | listAiGovernancePolicyVersions | response | items[].status | enum (draft, simulated, published, superseded) | yes
AiService | listAiGovernancePolicyVersions | response | items[].rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | listAiGovernancePolicyVersions | response | items[].rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | listAiGovernancePolicyVersions | response | items[].rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | listAiGovernancePolicyVersions | response | items[].rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | listAiGovernancePolicyVersions | response | items[].changeNote | string |  | (nullable)
AiService | listAiGovernancePolicyVersions | response | items[].simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | listAiGovernancePolicyVersions | response | items[].publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiGovernancePolicyVersions | response | nextCursor | string
AiService | listAiGovernancePolicyVersions | response | hasMore | boolean | yes
AiService | listAiGovernancePolicyVersions | param (query) | policyId | string (uuid)
AiService | listAiGovernancePolicyVersions | param (query) | status | enum (draft, simulated, published, superseded)
AiService | listAiGovernancePolicyVersions | param (query) | kind | enum (action, data, scope, autonomy, approval, environment)
AiService | listAiGovernancePolicyVersions | param (query) | pageSize | integer
AiService | listAiGovernancePolicyVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiIncidents | response | items | array of AiIncident | yes
AiService | listAiIncidents | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiIncidents | response | items[].reference | string | yes | (read-only)
AiService | listAiIncidents | response | items[].title | string | yes
AiService | listAiIncidents | response | items[].kind | enum (governance, operational, both)
AiService | listAiIncidents | response | items[].severity | enum (low, medium, high, critical) | yes
AiService | listAiIncidents | response | items[].status | enum (open, contained, investigating, remediating, closed) | yes | (read-only)
AiService | listAiIncidents | response | items[].capabilityKeys | array of string
AiService | listAiIncidents | response | items[].alertIds | array of string (uuid)
AiService | listAiIncidents | response | items[].operationalIncidentRef | string |  | The linked operational incident, where both apply (AIC-250). (nullable)
AiService | listAiIncidents | response | items[].containment | array of object |  | (read-only)
AiService | listAiIncidents | response | items[].containment[].action | string
AiService | listAiIncidents | response | items[].containment[].targetRef | string
AiService | listAiIncidents | response | items[].containment[].at | string (date-time)
AiService | listAiIncidents | response | items[].containment[].byPrincipalId | string (uuid)
AiService | listAiIncidents | response | items[].rootCause | string |  | (nullable)
AiService | listAiIncidents | response | items[].remediation | string |  | (nullable)
AiService | listAiIncidents | response | items[].impact | string |  | The post-incident review's impact (closeAiIncident, CHG-CSA-045). (nullable)
AiService | listAiIncidents | response | items[].controlFailure | string |  | (nullable)
AiService | listAiIncidents | response | items[].lessonsLearned | string |  | (nullable)
AiService | listAiIncidents | response | items[].ownerPrincipalId | string (uuid) |  | (nullable)
AiService | listAiIncidents | response | items[].openedAt | string (date-time) |  | (read-only)
AiService | listAiIncidents | response | items[].containedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiIncidents | response | items[].closedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiIncidents | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiIncidents | response | nextCursor | string
AiService | listAiIncidents | response | hasMore | boolean | yes
AiService | listAiIncidents | param (query) | status | enum (open, contained, investigating, remediating, closed)
AiService | listAiIncidents | param (query) | severity | enum (low, medium, high, critical)
AiService | listAiIncidents | param (query) | pageSize | integer
AiService | listAiIncidents | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiTrainingRuns | response | items | array of AiTrainingRun | yes
AiService | listAiTrainingRuns | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiTrainingRuns | response | items[].capabilityKey | string | yes
AiService | listAiTrainingRuns | response | items[].suggestionKind | object |  | (nullable)
AiService | listAiTrainingRuns | response | items[].forecastDefinitionKey | string |  | (nullable)
AiService | listAiTrainingRuns | response | items[].trainingWindowFrom | string (date)
AiService | listAiTrainingRuns | response | items[].trainingWindowTo | string (date)
AiService | listAiTrainingRuns | response | items[].dataCutoffAt | string (date-time)
AiService | listAiTrainingRuns | response | items[].includesImportedHistory | boolean |  | (default False)
AiService | listAiTrainingRuns | response | items[].featureSetVersion | string
AiService | listAiTrainingRuns | response | items[].artefactRef | string |  | The model file in the tenant's Blob container. (nullable)
AiService | listAiTrainingRuns | response | items[].backtestRunId | string (uuid) |  | (nullable)
AiService | listAiTrainingRuns | response | items[].releaseId | string (uuid) |  | (nullable)
AiService | listAiTrainingRuns | response | items[].status | enum (queued, training, backtesting, shadow, gatePassed, gateFailed, failed) | yes
AiService | listAiTrainingRuns | response | items[].metrics | object |  | (nullable)
AiService | listAiTrainingRuns | response | items[].startedAt | string (date-time)
AiService | listAiTrainingRuns | response | items[].completedAt | string (date-time) |  | (nullable)
AiService | listAiTrainingRuns | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiTrainingRuns | response | nextCursor | string
AiService | listAiTrainingRuns | response | hasMore | boolean | yes
AiService | listAiTrainingRuns | param (query) | capabilityKey | string
AiService | listAiTrainingRuns | param (query) | status | enum (queued, training, backtesting, shadow, gatePassed, gateFailed, failed)
AiService | listAiTrainingRuns | param (query) | pageSize | integer
AiService | listAiTrainingRuns | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listAlerts | param (query) | status | AlertStatus: enum (raised, acknowledged, resolved, expired) |  | Defaults to open alerts (decided 28 September, audit R158): with no status the list holds raised and acknowledged alerts, never resolved or expired ones.
ReportingService | listAlerts | param (query) | severity | AlertSeverity: enum (info, warning, critical)
ReportingService | listAlerts | param (query) | workstationId | string (uuid) |  | Only alerts raised for this workstation.
ReportingService | listAlerts | param (query) | shiftId | string (uuid) |  | Only alerts raised during this till shift.
ReportingService | listAlerts | param (query) | itemId | string (uuid) |  | Only alerts raised about this inventory item.
CatalogueService | listAlternativeCodes | param (path) | productId | string (uuid) | yes
WhiteLabelService | listAnalyticsProviders | response | items | array of StorefrontAnalyticsProvider | yes
WhiteLabelService | listAnalyticsProviders | response | items[].id | string (uuid) |  | (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].venueId | string (uuid) |  | (nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | listAnalyticsProviders | response | items[].providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].measurementId | string | yes | What the tag or SDK reports to. (max length 100)
WhiteLabelService | listAnalyticsProviders | response | items[].surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | listAnalyticsProviders | response | items[].consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | listAnalyticsProviders | response | items[].isEnabled | boolean | yes | (default True)
WhiteLabelService | listAnalyticsProviders | response | items[].reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listAnalyticsProviders | response | nextCursor | string
WhiteLabelService | listAnalyticsProviders | response | hasMore | boolean | yes
WhiteLabelService | listAnalyticsProviders | param (query) | venueId | string (uuid) |  | Staff, the rows of this venue only; guest, the venue being browsed, so its rows win over the tenant's
WhiteLabelService | listAnalyticsProviders | param (query) | pageSize | integer
WhiteLabelService | listAnalyticsProviders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listAnalyticsProviders | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
WhiteLabelService | listAppBuilds | response | items | array of AppBuild | yes
WhiteLabelService | listAppBuilds | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listAppBuilds | response | items[].platform | enum (ios, android) | yes
WhiteLabelService | listAppBuilds | response | items[].configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | listAppBuilds | response | items[].storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | listAppBuilds | response | items[].buildNumber | integer |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the white-label jobs component's, in the workers host, from appBuild.requested (ADAM CR-106); from submitted on it is read from the store with the client's credential, or… (read-only)
WhiteLabelService | listAppBuilds | response | items[].failureReason | string |  | (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listAppBuilds | response | items[].submitToStore | boolean |  | (default False)
WhiteLabelService | listAppBuilds | response | items[].requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | listAppBuilds | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listAppBuilds | response | nextCursor | string
WhiteLabelService | listAppBuilds | response | hasMore | boolean | yes
WhiteLabelService | listAppBuilds | param (query) | platform | enum (ios, android)
WhiteLabelService | listAppBuilds | param (query) | pageSize | integer
WhiteLabelService | listAppBuilds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listApprovalRequests | response | items | array of ApprovalRequest | yes
TenancyService | listApprovalRequests | response | items[].id | string | yes
TenancyService | listApprovalRequests | response | items[].kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | listApprovalRequests | response | items[].rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | listApprovalRequests | response | items[].outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | listApprovalRequests | response | items[].reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | listApprovalRequests | response | items[].status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | listApprovalRequests | response | items[].subjectContract | string
TenancyService | listApprovalRequests | response | items[].subjectType | string
TenancyService | listApprovalRequests | response | items[].subjectId | string
TenancyService | listApprovalRequests | response | items[].scopePath | string
TenancyService | listApprovalRequests | response | items[].summary | string
TenancyService | listApprovalRequests | response | items[].amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | listApprovalRequests | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | listApprovalRequests | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | listApprovalRequests | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | listApprovalRequests | response | items[].attributes | object |  | The attributes the raising contract sent (CreateApprovalRequest.attributes), stored as given (ADAM CR-172, fix round 3; CHG-CRA-005). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].justification | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].requestedByPrincipalId | string (uuid) |  | The principal who raised the request, or for whom the raising contract raised it. (nullable)
TenancyService | listApprovalRequests | response | items[].requestedBySubjectId | string (uuid) |  | The guest who raised the request (ADAM CR-101; CHG-R10ID-016), set by the server from the guest session; null for a request a principal raised. (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].matrixVersion | integer
TenancyService | listApprovalRequests | response | items[].mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | listApprovalRequests | response | items[].currentLevel | integer
TenancyService | listApprovalRequests | response | items[].totalLevels | integer
TenancyService | listApprovalRequests | response | items[].approvers | array of object |  | The approver chain, fixed when the request is routed (ADAM CR-102, option 1, accepted 15 October 2026; CHG-R10ID-015). (read-only)
TenancyService | listApprovalRequests | response | items[].approvers[].level | integer | yes | The level of the chain this approver decides at. (min 1)
TenancyService | listApprovalRequests | response | items[].approvers[].principalId | string (uuid) | yes | The approver, a principal of the tenant.
TenancyService | listApprovalRequests | response | items[].approvers[].isDelegate | boolean | yes | True when the approver stands in for another through an ApprovalDelegation in force at routing.
TenancyService | listApprovalRequests | response | items[].pendingApprovers | array of object |  | The rows of approvers at currentLevel who have not decided yet, with their names; derived, not stored (CHG-R10ID-015).
TenancyService | listApprovalRequests | response | items[].pendingApprovers[].principalId | string (uuid)
TenancyService | listApprovalRequests | response | items[].pendingApprovers[].displayName | string
TenancyService | listApprovalRequests | response | items[].pendingApprovers[].isDelegate | boolean
TenancyService | listApprovalRequests | response | items[].decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | listApprovalRequests | response | items[].decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | listApprovalRequests | response | items[].decisions[].level | integer | yes
TenancyService | listApprovalRequests | response | items[].decisions[].principalId | string (uuid) |  | The approver; null when an external workflow system decided (externalApproverRef set). (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].externalApproverRef | string |  | Who decided in the external provider's system, as it named them (recordExternalApprovalDecision); null for an internal approver (CHG-R8MIG-009). (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].externalApproverName | string |  | The external approver's display name, where the provider sent one (CHG-R8MIG-009). (max length 200; nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].displayName | string
TenancyService | listApprovalRequests | response | items[].decisions[].isDelegate | boolean
TenancyService | listApprovalRequests | response | items[].decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].decision | enum (approve, reject, return, requestInformation) | yes | return and requestInformation are stored as decisions too, their comment in comment (decideApprovalRequest; CHG-R8MIG-009).
TenancyService | listApprovalRequests | response | items[].decisions[].comment | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].reason | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].usedMfa | boolean
TenancyService | listApprovalRequests | response | items[].decisions[].signatureRef | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].decidedAt | string (date-time) | yes
TenancyService | listApprovalRequests | response | items[].escalations | array of object |  | 11.1.48.
TenancyService | listApprovalRequests | response | items[].escalations[].at | string (date-time) | yes
TenancyService | listApprovalRequests | response | items[].escalations[].reason | string |  | The requester's or approver's reason; for an automatic escalation, the SLA rule that fired. (max length 300)
TenancyService | listApprovalRequests | response | items[].escalations[].fromLevel | integer
TenancyService | listApprovalRequests | response | items[].escalations[].toLevel | integer | yes
TenancyService | listApprovalRequests | response | items[].escalations[].wasAutomatic | boolean | yes
TenancyService | listApprovalRequests | response | items[].escalations[].escalatedByPrincipalId | string (uuid) |  | Who escalated it by hand (escalateApprovalRequest's caller); null for an automatic one. (nullable)
TenancyService | listApprovalRequests | response | items[].escalations[].addedApproverPrincipalId | string (uuid) |  | The approver the escalation added at toLevel; the original approver stays in the chain. (nullable)
TenancyService | listApprovalRequests | response | items[].resubmittedFromId | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].reopenedFromId | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].slaDueAt | string (date-time) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].slaBreached | boolean
TenancyService | listApprovalRequests | response | items[].expiresAt | string (date-time) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].assignedToPrincipalId | string (uuid) |  | Who claimed or was assigned the request in a shared queue (assignApprovalRequest; DI-723; CHG-CSP-042). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].assignedToDepartmentId | string (uuid) |  | The department queue it was assigned to, where it went to a department rather than a person (CHG-CSP-042). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].assignedAt | string (date-time) |  | (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].assignmentNote | string |  | The note assignApprovalRequest was given, kept with the assignment (R8 blocker APPROVALS-TENANCY-C02, CHG-R8MIG-009). (max length 500; read-only; nullable)
TenancyService | listApprovalRequests | response | items[].approvalMatrixId | string (uuid) |  | The matrix routing chose at submit (with matrixVersion), so a decision is checked against the matrix the request was routed by (CHG-R8MIG-009). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].ruleId | string (uuid) |  | The matrix rule that matched on kind, scope, amount and attributes (CHG-R8MIG-009). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].cancelReason | string |  | Why the request was cancelled, as cancelApprovalRequest was given it (CHG-R8MIG-009). (max length 500; read-only; nullable)
TenancyService | listApprovalRequests | response | items[].requestedAt | string (date-time) | yes
TenancyService | listApprovalRequests | response | items[].completedAt | string (date-time) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | listApprovalRequests | response | items[].aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | listApprovalRequests | response | items[].aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | listApprovalRequests | response | items[].aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | listApprovalRequests | response | items[].aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | listApprovalRequests | response | items[].aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | listApprovalRequests | response | items[].aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | listApprovalRequests | response | items[].aiAssessment.assessedAt | string (date-time)
TenancyService | listApprovalRequests | response | nextCursor | string
TenancyService | listApprovalRequests | response | hasMore | boolean | yes
TenancyService | listApprovalRequests | param (query) | assignedToMe | boolean
TenancyService | listApprovalRequests | param (query) | raisedByMe | boolean
TenancyService | listApprovalRequests | param (query) | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …)
TenancyService | listApprovalRequests | param (query) | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …)
TenancyService | listApprovalRequests | param (query) | breachingWithinMinutes | integer |  | 11.1.15.
TenancyService | listApprovalRequests | param (query) | sort | enum (slaProximity, aiPriority) |  | slaProximity (the default, as before) or aiPriority: highest aiAssessment.priorityScore first, requests with no assessment after them in SLA order (29 September, build pass, group G2; 11.1.74).
TenancyService | listApprovalRequests | param (query) | pageSize | integer
TenancyService | listApprovalRequests | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listAuditRecords | response | items | array of AuditRecord | yes
TenancyService | listAuditRecords | response | items[].id | string (uuid) | yes | (read-only)
TenancyService | listAuditRecords | response | items[].principalId | string (uuid) |  | Who acted.
TenancyService | listAuditRecords | response | items[].orgUnitId | string (uuid) |  | The scope node the action happened in. (nullable)
TenancyService | listAuditRecords | response | items[].workstationId | string (uuid) |  | The workstation it was done from, where there was one. (nullable)
TenancyService | listAuditRecords | response | items[].action | string | yes | What was done, as the writing operation names it; the operation's operationId, or the consumer's or the job's name (ADAM CR-179).
TenancyService | listAuditRecords | response | items[].subjectRef | string |  | The thing acted on — a profile, a shift, an order. (nullable)
TenancyService | listAuditRecords | response | items[].occurredAt | string (date-time) | yes | When.
TenancyService | listAuditRecords | response | items[].platformStaffGrantId | string (uuid) |  | Set when a TICVAI platform operator acted, naming the grant they acted under (identity.openPlatformStaffGrant; decided 28 September, audit R098). (nullable)
TenancyService | listAuditRecords | response | nextCursor | string
TenancyService | listAuditRecords | response | hasMore | boolean | yes
TenancyService | listAuditRecords | param (query) | orgUnitId | string (uuid)
TenancyService | listAuditRecords | param (query) | principalId | string (uuid)
TenancyService | listAuditRecords | param (query) | workstationId | string (uuid)
TenancyService | listAuditRecords | param (query) | action | string
TenancyService | listAuditRecords | param (query) | subjectRef | string |  | The thing acted on.
TenancyService | listAuditRecords | param (query) | platformStaffGrantId | string (uuid) |  | Exact match on AuditRecord.platformStaffGrantId: what a platform operator did under one grant (audit R098).
TenancyService | listAuditRecords | param (query) | from | string (date-time)
TenancyService | listAuditRecords | param (query) | to | string (date-time)
TenancyService | listAuditRecords | param (query) | pageSize | integer
TenancyService | listAuditRecords | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listBanners | response | items | array of Banner | yes
WhiteLabelService | listBanners | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listBanners | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listBanners | response | items[].subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listBanners | response | items[].imageAssetRef | string (uuid) | yes
WhiteLabelService | listBanners | response | items[].placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | listBanners | response | items[].linkTarget | LinkTarget
WhiteLabelService | listBanners | response | items[].linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | listBanners | response | items[].linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | listBanners | response | items[].linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | listBanners | response | items[].linkTarget.contentPageId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.productId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.eventId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | listBanners | response | items[].linkTarget.url | string
WhiteLabelService | listBanners | response | items[].startsAt | string (date-time) | yes
WhiteLabelService | listBanners | response | items[].endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | listBanners | response | items[].state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | listBanners | response | items[].sortOrder | integer
WhiteLabelService | listBanners | response | items[].isActive | boolean
WhiteLabelService | listBanners | response | nextCursor | string
WhiteLabelService | listBanners | response | hasMore | boolean | yes
WhiteLabelService | listBanners | param (query) | state | ScheduleState: enum (draft, scheduled, active, expired)
WhiteLabelService | listBanners | param (query) | pageSize | integer
WhiteLabelService | listBanners | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listBillingStatements | response | items | array of BillingStatement | yes
OrderService | listBillingStatements | response | items[].id | string (uuid) | yes | A name-based UUID (v5) of agreementId, periodStart and periodEnd, so the same statement has the same id on every read (ADAM CR-099).
OrderService | listBillingStatements | response | items[].agreementId | string (uuid) | yes | The membership agreement this statement is one billing cycle of (identity.customer_membership.id; ADAM CR-099).
OrderService | listBillingStatements | response | items[].subjectId | string (uuid) |  | (read-only)
OrderService | listBillingStatements | response | items[].periodStart | string (date) | yes
OrderService | listBillingStatements | response | items[].periodEnd | string (date) | yes
OrderService | listBillingStatements | response | items[].lines | array of BillingStatementLine
OrderService | listBillingStatements | response | items[].lines[].occurredAt | string (date-time) | yes
OrderService | listBillingStatements | response | items[].lines[].kind | enum (charge, refund, failedAttempt, adjustment) | yes
OrderService | listBillingStatements | response | items[].lines[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].description | string
OrderService | listBillingStatements | response | items[].lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].taxRate | number |  | 2.14.23. (nullable)
OrderService | listBillingStatements | response | items[].lines[].taxInvoiceId | string (uuid) |  | The finance tax invoice issued for this charge, where one was (issueTaxInvoice); the guest downloads it with getTaxDocumentRendition. (nullable)
OrderService | listBillingStatements | response | items[].lines[].declineClass | string |  | Present on failedAttempt only, and it is what turns *"your payment failed"* into something a guest can act on: a soft decline means try again, a hard one means the card needs replacing. (nullable)
OrderService | listBillingStatements | response | items[].total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].pdfUrl | string (uri) |  | Set when getBillingStatement is called with format=pdf; a short-lived link. (read-only; nullable)
OrderService | listBillingStatements | response | items[].isTaxInvoice | boolean | yes | Always false, and stated rather than assumed. (default False; read-only)
OrderService | listBillingStatements | response | nextCursor | string
OrderService | listBillingStatements | response | hasMore | boolean | yes
OrderService | listBillingStatements | param (query) | subjectId | string (uuid) |  | The guest whose statements a staff caller reads (ADAM CR-099).
OrderService | listBillingStatements | param (query) | from | string (date) |  | Only statements whose periodEnd is on or after this date.
OrderService | listBillingStatements | param (query) | to | string (date) |  | Only statements whose periodStart is on or before this date.
OrderService | listBillingStatements | param (query) | pageSize | integer
OrderService | listBillingStatements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listBookableOutlets | response | items | array of BookableOutlet | yes
FnbService | listBookableOutlets | response | items[].outletId | string (uuid) | yes
FnbService | listBookableOutlets | response | items[].venueId | string (uuid) | yes
FnbService | listBookableOutlets | response | items[].name | string | yes
FnbService | listBookableOutlets | response | items[].kind | string |  | (nullable)
FnbService | listBookableOutlets | response | items[].cuisine | array of string
FnbService | listBookableOutlets | response | items[].zone | string |  | (nullable)
FnbService | listBookableOutlets | response | items[].imageAssetRef | string |  | (nullable)
FnbService | listBookableOutlets | response | items[].depositMayApply | boolean |  | The venue's orders.DepositPolicy.dining is on, so a booking from its party size takes a deposit (rev 3 REV3-8b).
FnbService | listBookableOutlets | response | items[].waitlistOpen | boolean |  | The outlet takes walk-in waitlist places today (joinRestaurantWaitlist).
FnbService | listBookableOutlets | response | nextCursor | string
FnbService | listBookableOutlets | response | hasMore | boolean | yes
FnbService | listBookableOutlets | param (path) | venueId | string (uuid) | yes
FnbService | listBookableOutlets | param (query) | date | string (date) |  | Only outlets open on this calendar day (the region's time zone).
FnbService | listBookableOutlets | param (query) | pageSize | integer
FnbService | listBookableOutlets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listBookableVenueMaps | response | venueId | string (uuid) | yes
VenueOpsService | listBookableVenueMaps | response | maps | array of BookableVenueMapRef | yes | (max items 50)
VenueOpsService | listBookableVenueMaps | response | maps[].mapId | string (uuid) | yes
VenueOpsService | listBookableVenueMaps | response | maps[].name | string | yes
VenueOpsService | listBookableVenueMaps | response | maps[].kind | enum (park, floor, zone, parking) | yes
VenueOpsService | listBookableVenueMaps | response | maps[].floorLevel | integer |  | (nullable)
VenueOpsService | listBookableVenueMaps | response | maps[].publishedVersion | integer | yes | The VenueMap.publishedVersion a guest is served; send it to getVenueMap as version.
VenueOpsService | listBookableVenueMaps | response | maps[].placedResourceCount | integer | yes | Placed resources on the published version. (min 0)
VenueOpsService | listBookableVenueMaps | response | maps[].kinds | array of enum (cabana, lounger, table, pitch, other) |  | The kinds of spot on this map, e.g.
VenueOpsService | listBookableVenueMaps | param (query) | venueId | string (uuid) | yes | The venue whose bookable maps are wanted.
VenueOpsService | listBookableVenueMaps | param (query) | productId | string (uuid) |  | Only maps with a placed resource sold by this product's price-band variants.
VenueOpsService | listBookableVenueMaps | param (query) | kind | enum (cabana, lounger, table, pitch, other) |  | Only maps carrying at least one placed resource of this kind (PlacedResource.kind).
VenueOpsService | listBookableVenueMaps | param (query) | onlyBookable | boolean |  | true (default): only maps whose published version carries at least one placed resource.
WhiteLabelService | listBookingFlowTypes | response | items | array of BookingFlowType | yes
WhiteLabelService | listBookingFlowTypes | response | items[].key | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | listBookingFlowTypes | response | items[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listBookingFlowTypes | response | items[].description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listBookingFlowTypes | response | items[].productKinds | array of string | yes | The catalogue ProductKind values this type books.
WhiteLabelService | listBookingFlowTypes | response | items[].steps | array of object | yes | In the type's default order.
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].requirement | enum (required, optional, conditional) | yes
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].condition | object |  | For conditional, when a guest meets the step. (nullable)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].defaultEnabled | boolean |  | (default True)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].defaultSortOrder | integer | yes | (min 0)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].settingsOwned | array of string |  | Names of BookingFlowSettings (venue-wide) or BookingFlowLevelSettings (this flow) fields shown beside the step.
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].stepSettings | array of object |  | The step's own settings, kept in BookingFlowStep.settings.
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints | array of object | yes | first and last pin a step; before puts stepKey somewhere ahead of otherStepKey.
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].kind | enum (first, last, before) | yes
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].otherStepKey | object |  | Required when kind is before. (nullable)
WhiteLabelService | listBookingFlowTypes | response | nextCursor | string
WhiteLabelService | listBookingFlowTypes | response | hasMore | boolean | yes
WhiteLabelService | listBookingFlowTypes | param (query) | productKind | string |  | Only the types that serve this catalogue product kind.
WhiteLabelService | listBookingFlowTypes | param (query) | pageSize | integer
WhiteLabelService | listBookingFlowTypes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listBookingFlows | response | items | array of BookingFlow | yes
WhiteLabelService | listBookingFlows | response | items[].id | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | listBookingFlows | response | items[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | listBookingFlows | response | items[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | listBookingFlows | response | items[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | listBookingFlows | response | items[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | listBookingFlows | response | items[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | listBookingFlows | response | items[].steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlows | response | items[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | listBookingFlows | response | items[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | listBookingFlows | response | items[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | listBookingFlows | response | items[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | listBookingFlows | response | items[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | listBookingFlows | response | items[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | listBookingFlows | response | items[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | listBookingFlows | response | items[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | listBookingFlows | response | items[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | listBookingFlows | response | items[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | listBookingFlows | response | items[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | listBookingFlows | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listBookingFlows | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listBookingFlows | response | nextCursor | string
WhiteLabelService | listBookingFlows | response | hasMore | boolean | yes
WhiteLabelService | listBookingFlows | param (path) | venueId | string (uuid) | yes
WhiteLabelService | listBookingFlows | param (query) | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …)
WhiteLabelService | listBookingFlows | param (query) | pageSize | integer
WhiteLabelService | listBookingFlows | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listCashMovements | response | items | array of CashMovement | yes
OrderService | listCashMovements | response | items[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | listCashMovements | response | items[].kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | listCashMovements | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listCashMovements | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listCashMovements | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listCashMovements | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listCashMovements | response | items[].denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | listCashMovements | response | items[].denominations[].id | string (uuid)
OrderService | listCashMovements | response | items[].denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | listCashMovements | response | items[].denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | listCashMovements | response | items[].denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | listCashMovements | response | items[].denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | listCashMovements | response | items[].denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | listCashMovements | response | items[].denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | listCashMovements | response | items[].denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listCashMovements | response | items[].denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | listCashMovements | response | items[].denominations[].countedAt | string (date-time)
OrderService | listCashMovements | response | items[].denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | listCashMovements | response | items[].reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | listCashMovements | response | items[].reason | string |  | (max length 500)
OrderService | listCashMovements | response | items[].recordedAt | string (date-time) | yes
OrderService | listCashMovements | response | items[].shiftId | string (uuid) | yes
OrderService | listCashMovements | response | items[].depositBoxId | string (uuid) |  | The box the cash moved in or out of. (nullable)
OrderService | listCashMovements | response | items[].witnessPrincipalId | string (uuid) |  | The cashier who countersigned a withdrawal. (nullable)
OrderService | listCashMovements | response | items[].withdrawalReason | object |  | (nullable)
OrderService | listCashMovements | response | items[].authorisedByPrincipalId | string (uuid) | yes | The principal who authorised the movement, recorded for audit.
OrderService | listCashMovements | response | items[].sequence | integer | yes | Monotonic within the shift.
OrderService | listCashMovements | response | items[].syncedAt | string (date-time) |  | (nullable)
OrderService | listCashMovements | response | nextCursor | string
OrderService | listCashMovements | response | hasMore | boolean | yes
OrderService | listCashMovements | param (path) | shiftId | string (uuid) | yes
OrderService | listCashMovements | param (query) | pageSize | integer
OrderService | listCashMovements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listConfigVersions | response | items | array of ConfigVersion | yes
WhiteLabelService | listConfigVersions | response | items[].version | string | yes | Named by the server (ADAM CR-154; CHG-CRA-004): the next integer for the tenant, 1, 2, ..., taken in the publish transaction. (read-only)
WhiteLabelService | listConfigVersions | response | items[].publishedAt | string (date-time) | yes
WhiteLabelService | listConfigVersions | response | items[].publishedByPrincipalId | string (uuid) | yes
WhiteLabelService | listConfigVersions | response | items[].publishedByName | string
WhiteLabelService | listConfigVersions | response | items[].note | string | yes
WhiteLabelService | listConfigVersions | response | items[].reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step, where the tenant's publish-review policy is on (CHG-CSA-042). (default notRequired; read-only)
WhiteLabelService | listConfigVersions | response | items[].approvalRequestId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | listConfigVersions | response | items[].isCurrent | boolean | yes
WhiteLabelService | listConfigVersions | response | items[].scheduledFor | string (date-time) |  | (nullable)
WhiteLabelService | listConfigVersions | response | items[].activationFailedAt | string (date-time) |  | When the scheduled activation of this version failed its validation again; null when it has not failed (R8 blocker IDENTITY-C63). (read-only; nullable)
WhiteLabelService | listConfigVersions | response | items[].activationFailure | string |  | Why the scheduled activation failed, in the validation's words (R8 blocker IDENTITY-C63). (max length 2000; read-only; nullable)
WhiteLabelService | listConfigVersions | response | items[].contentHash | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges | array of object |  | Changes in this version that will not reach guests until the next store release.
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].area | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].description | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].platforms | array of enum (ios, android, web)
WhiteLabelService | listConfigVersions | response | items[].snapshot | object |  | What this version contained. (read-only)
WhiteLabelService | listConfigVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listConfigVersions | response | nextCursor | string
WhiteLabelService | listConfigVersions | response | hasMore | boolean | yes
WhiteLabelService | listConfigVersions | param (query) | pageSize | integer
WhiteLabelService | listConfigVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentAnswers | response | items | array of BookingConsentRecord | yes
MarketingService | listConsentAnswers | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listConsentAnswers | response | items[].questionId | string (uuid) | yes
MarketingService | listConsentAnswers | response | items[].questionVersion | integer | yes | (min 1)
MarketingService | listConsentAnswers | response | items[].questionKind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | listConsentAnswers | response | items[].answer | enum (yes, no) | yes
MarketingService | listConsentAnswers | response | items[].scope | enum (perPerson, perBooking) | yes
MarketingService | listConsentAnswers | response | items[].blocksBooking | boolean |  | The answer is the question's blockingAnswer at that version. (read-only)
MarketingService | listConsentAnswers | response | items[].cartId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].cartLineId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].orderId | string (uuid) |  | Set by orders.checkoutCart when the cart becomes an order. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].orderLineId | string (uuid) |  | (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].personIndex | integer |  | (min 0; nullable)
MarketingService | listConsentAnswers | response | items[].personName | string |  | (max length 120; nullable)
MarketingService | listConsentAnswers | response | items[].personSubjectId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].answeredBySubjectId | string (uuid) |  | The guest who answered, from the session. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].answeredByPrincipalId | string (uuid) |  | The staff member who answered on the guest's behalf. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | listConsentAnswers | response | items[].answeredAt | string (date-time) | yes
MarketingService | listConsentAnswers | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | listConsentAnswers | response | nextCursor | string
MarketingService | listConsentAnswers | response | hasMore | boolean | yes
MarketingService | listConsentAnswers | param (query) | orderId | string (uuid)
MarketingService | listConsentAnswers | param (query) | subjectId | string (uuid)
MarketingService | listConsentAnswers | param (query) | questionId | string (uuid)
MarketingService | listConsentAnswers | param (query) | pageSize | integer
MarketingService | listConsentAnswers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentPurposes | response | items | array of ConsentPurposeConfig | yes
MarketingService | listConsentPurposes | response | items[].id | string (uuid) |  | The purpose row's id (marketing.consent_purpose.id), the value consentPurposeId and a consent's purposeId carry (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-022). (read-only)
MarketingService | listConsentPurposes | response | items[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment) | yes | storedPaymentCredential (a card saved for later, storePaymentToken) and facePassEnrolment (a face enrolled for entry, enrolFacePass) are purposes of their own (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-…
MarketingService | listConsentPurposes | response | items[].displayName | string
MarketingService | listConsentPurposes | response | items[].description | string
MarketingService | listConsentPurposes | response | items[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | listConsentPurposes | response | items[].noticeVersion | string | yes | Current version of the notice.
MarketingService | listConsentPurposes | response | items[].isRequiredForService | boolean | yes | True for transactional.
MarketingService | listConsentPurposes | response | items[].expiresAfterMonths | integer |  | (nullable)
MarketingService | listConsentPurposes | response | nextCursor | string
MarketingService | listConsentPurposes | response | hasMore | boolean | yes
MarketingService | listConsentPurposes | param (query) | pageSize | integer
MarketingService | listConsentPurposes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentQuestions | response | items | array of ConsentQuestion | yes
MarketingService | listConsentQuestions | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listConsentQuestions | response | items[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | listConsentQuestions | response | items[].text | object | yes | The question as the guest reads it, per locale.
MarketingService | listConsentQuestions | response | items[].helpText | object |  | (nullable)
MarketingService | listConsentQuestions | response | items[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | listConsentQuestions | response | items[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | listConsentQuestions | response | items[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | listConsentQuestions | response | items[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | listConsentQuestions | response | items[].status | enum (active, retired) | yes | (default active)
MarketingService | listConsentQuestions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | listConsentQuestions | response | items[].updatedAt | string (date-time) |  | (read-only)
MarketingService | listConsentQuestions | response | nextCursor | string
MarketingService | listConsentQuestions | response | hasMore | boolean | yes
MarketingService | listConsentQuestions | param (query) | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom)
MarketingService | listConsentQuestions | param (query) | status | enum (active, retired)
MarketingService | listConsentQuestions | param (query) | pageSize | integer
MarketingService | listConsentQuestions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listContentBlocks | response | items | array of ContentBlock | yes
WhiteLabelService | listContentBlocks | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listContentBlocks | response | items[].pageId | string (uuid) |  | (nullable)
WhiteLabelService | listContentBlocks | response | items[].kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | listContentBlocks | response | items[].position | integer
WhiteLabelService | listContentBlocks | response | items[].body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | listContentBlocks | response | items[].localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | listContentBlocks | response | items[].status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | listContentBlocks | response | items[].publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | listContentBlocks | response | items[].expireAt | string (date-time) |  | (nullable)
WhiteLabelService | listContentBlocks | response | items[].audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | listContentBlocks | response | items[].approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | listContentBlocks | response | items[].reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step of publishContentBlock, where the tenant's publish-review policy is on (r8 walk of ticket 27919). (default notRequired; read-only)
WhiteLabelService | listContentBlocks | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listContentBlocks | response | nextCursor | string
WhiteLabelService | listContentBlocks | response | hasMore | boolean | yes
WhiteLabelService | listContentBlocks | param (query) | pageKey | string | yes
WhiteLabelService | listContentBlocks | param (query) | pageSize | integer
WhiteLabelService | listContentBlocks | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listContentPages | response | items | array of ContentPage | yes
WhiteLabelService | listContentPages | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listContentPages | response | items[].slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | listContentPages | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listContentPages | response | items[].body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | listContentPages | response | items[].isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | listContentPages | response | items[].status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | listContentPages | response | items[].iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | listContentPages | response | items[].categoryCode | string |  | (nullable)
WhiteLabelService | listContentPages | response | items[].sortOrder | integer
WhiteLabelService | listContentPages | response | items[].isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | listContentPages | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listContentPages | response | nextCursor | string
WhiteLabelService | listContentPages | response | hasMore | boolean | yes
WhiteLabelService | listContentPages | param (query) | status | ContentStatus: enum (draft, published, archived) |  | Only pages in this state; with none, every state.
WhiteLabelService | listContentPages | param (query) | categoryCode | string |  | Only pages with this categoryCode.
WhiteLabelService | listContentPages | param (query) | slug | string |  | Only the page with this slug — how a screen fetches one known page.
WhiteLabelService | listContentPages | param (query) | pageSize | integer
WhiteLabelService | listContentPages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listCreditMemos | response | items | array of FinCreditMemo | yes
LedgerService | listCreditMemos | response | items[].id | string (uuid) | yes | (read-only)
LedgerService | listCreditMemos | response | items[].creditMemoNumber | string | yes | Server-assigned from the legal entity's credit memo series, in sequence without gaps. (read-only)
LedgerService | listCreditMemos | response | items[].taxInvoiceId | string (uuid) | yes
LedgerService | listCreditMemos | response | items[].taxInvoiceNumber | string |  | (read-only)
LedgerService | listCreditMemos | response | items[].kind | enum (full, partial) | yes
LedgerService | listCreditMemos | response | items[].reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | listCreditMemos | response | items[].refundId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].legalEntityId | string (uuid) | yes
LedgerService | listCreditMemos | response | items[].buyerSubjectId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].issuedAt | string (date-time) | yes
LedgerService | listCreditMemos | response | items[].currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].legalFxRate | object |  | The invoice's own legalFxRate, never today's (CHG-FIN-011). (read-only; nullable)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue | object |  | The value of the supply shown on the tax invoice (Executive Regulation Art. (read-only)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue | object |  | The correct value of the supply after this credit note (Art. (read-only)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].supplierName | string |  | Snapshot of the legal entity at issue, as on the invoice (Art. (read-only)
LedgerService | listCreditMemos | response | items[].supplierAddress | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].supplierTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].buyerName | string |  | The recipient as on the invoice; name, address and TRN where they are registered (Art. (read-only; nullable)
LedgerService | listCreditMemos | response | items[].buyerAddress | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].buyerTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].note | string |  | The brief explanation of why the credit note was issued, printed on it (Art. (nullable)
LedgerService | listCreditMemos | response | items[].renditionAssetId | string (uuid) |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | listCreditMemos | response | items[].issuedByPrincipalId | string (uuid) |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].lines | array of FinCreditMemoLine | yes
LedgerService | listCreditMemos | response | items[].lines[].invoiceLineNumber | integer | yes | (min 1)
LedgerService | listCreditMemos | response | items[].lines[].description | string |  | (max length 500)
LedgerService | listCreditMemos | response | items[].lines[].quantity | number |  | (nullable)
LedgerService | listCreditMemos | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].lines[].taxRate | number
LedgerService | listCreditMemos | response | items[].lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | listCreditMemos | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].scopePath | string |  | (read-only)
LedgerService | listCreditMemos | response | nextCursor | string
LedgerService | listCreditMemos | response | hasMore | boolean | yes
LedgerService | listCreditMemos | param (query) | taxInvoiceId | string (uuid)
LedgerService | listCreditMemos | param (query) | refundId | string (uuid)
LedgerService | listCreditMemos | param (query) | legalEntityId | string (uuid)
LedgerService | listCreditMemos | param (query) | issuedFrom | string (date)
LedgerService | listCreditMemos | param (query) | issuedTo | string (date)
LedgerService | listCreditMemos | param (query) | pageSize | integer
LedgerService | listCreditMemos | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listCustomerBadges | response | items | array of MarketingCustomerBadge | yes
MarketingService | listCustomerBadges | response | items[].id | string (uuid)
MarketingService | listCustomerBadges | response | items[].customerId | string (uuid) | yes
MarketingService | listCustomerBadges | response | items[].badgeId | string (uuid) | yes
MarketingService | listCustomerBadges | response | items[].challengeId | string (uuid) |  | (nullable)
MarketingService | listCustomerBadges | response | items[].sourceType | enum (challenge, purchase, manager) |  | Why the badge was awarded (R8 blocker ORDERS-MONEY-C14): challenge (a completed challenge, challengeId set), purchase (sourceReferenceId the order), manager (awarded by hand, as BO-826 does). (max length 30; nullable)
MarketingService | listCustomerBadges | response | items[].sourceReferenceId | string (uuid) |  | (nullable)
MarketingService | listCustomerBadges | response | items[].awardedAt | string (date-time) | yes
MarketingService | listCustomerBadges | response | items[].expiresAt | string (date-time) |  | (nullable)
MarketingService | listCustomerBadges | response | items[].status | enum (awarded, expired, revoked) | yes | Written by the server, never sent (R8 blocker ORDERS-MONEY-C14). (max length 20; read-only)
MarketingService | listCustomerBadges | response | nextCursor | string
MarketingService | listCustomerBadges | response | hasMore | boolean | yes
MarketingService | listCustomerBadges | param (path) | customerId | string (uuid) | yes
MarketingService | listCustomerBadges | param (query) | pageSize | integer
MarketingService | listCustomerBadges | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listDashboards | param (query) | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) |  | Narrows the library to one module.
ReportingService | listDashboards | param (query) | includeArchived | boolean |  | Archived dashboards are left out unless this is true — the "unless asked for" that Dashboard.archivedAt promises.
IdentityService | listDelegations | response | items | object | yes
IdentityService | listDelegations | response | items.heldByThisGuest | array of DelegatedAccess
IdentityService | listDelegations | response | items.heldByThisGuest[].grantedByKind | enum (principal, subject, system) |  | Who made the grant (CHG-R8MIG-021). (default principal; read-only)
IdentityService | listDelegations | response | items.heldByThisGuest[].grantedByPrincipalId | string (uuid) |  | The staff member who made the grant; set when grantedByKind is principal. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].grantedBySubjectId | string (uuid) |  | The guest who made the grant (the account holder); set when grantedByKind is subject. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].id | string (uuid) | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].principalId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].roleId | string (uuid) |  | The role this grant gives, with its own and inherited permissions. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].permission | string | yes | From the permission enum. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overSubjectName | string |  | The display name of the guest acted for (pii.subject.display_name), read with the grant; null for a staff grant. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overSubjectIsMinor | boolean |  | Whether the guest acted for is under the region's RegionSettings.minorAgeThreshold today, computed from their date of birth, which is never returned; null when no date of birth is held. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer, sharedEntitlement) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | listDelegations | response | items.heldByThisGuest[].scopePath | string | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].effect | enum (ALLOW, DENY) | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].revokedByKind | enum (principal, subject, system) |  | Who revoked the grant (decided 25 October 2026, Chinmay, ADAM CR-209 option A; CHG-R10ID-004): a staff member (revoked_by_principal_id), a guest (revokedBySubjectId, for example the owner taking back… (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].revokedBySubjectId | string (uuid) |  | The guest who revoked the grant; set when revokedByKind is subject (ADAM CR-209), since a guest is not a principal and cannot fill revoked_by_principal_id. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].validFrom | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].validTo | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].createdByPrincipalId | string (uuid)
IdentityService | listDelegations | response | items.heldByThisGuest[].createdAt | string (date-time)
IdentityService | listDelegations | response | items.heldOverThisGuest | array of DelegatedAccess
IdentityService | listDelegations | response | items.heldOverThisGuest[].grantedByKind | enum (principal, subject, system) |  | Who made the grant (CHG-R8MIG-021). (default principal; read-only)
IdentityService | listDelegations | response | items.heldOverThisGuest[].grantedByPrincipalId | string (uuid) |  | The staff member who made the grant; set when grantedByKind is principal. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].grantedBySubjectId | string (uuid) |  | The guest who made the grant (the account holder); set when grantedByKind is subject. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].id | string (uuid) | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].principalId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].roleId | string (uuid) |  | The role this grant gives, with its own and inherited permissions. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].permission | string | yes | From the permission enum. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overSubjectName | string |  | The display name of the guest acted for (pii.subject.display_name), read with the grant; null for a staff grant. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overSubjectIsMinor | boolean |  | Whether the guest acted for is under the region's RegionSettings.minorAgeThreshold today, computed from their date of birth, which is never returned; null when no date of birth is held. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer, sharedEntitlement) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | listDelegations | response | items.heldOverThisGuest[].scopePath | string | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].effect | enum (ALLOW, DENY) | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].revokedByKind | enum (principal, subject, system) |  | Who revoked the grant (decided 25 October 2026, Chinmay, ADAM CR-209 option A; CHG-R10ID-004): a staff member (revoked_by_principal_id), a guest (revokedBySubjectId, for example the owner taking back… (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].revokedBySubjectId | string (uuid) |  | The guest who revoked the grant; set when revokedByKind is subject (ADAM CR-209), since a guest is not a principal and cannot fill revoked_by_principal_id. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].validFrom | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].validTo | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].createdByPrincipalId | string (uuid)
IdentityService | listDelegations | response | items.heldOverThisGuest[].createdAt | string (date-time)
IdentityService | listDelegations | response | nextCursor | string
IdentityService | listDelegations | response | hasMore | boolean | yes
IdentityService | listDelegations | param (path) | subjectId | string (uuid) | yes
IdentityService | listDelegations | param (query) | pageSize | integer
IdentityService | listDelegations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listDeliveryLocations | response | items | array of DeliveryLocation | yes
FnbService | listDeliveryLocations | response | items[].id | string (uuid) | yes
FnbService | listDeliveryLocations | response | items[].venueId | string (uuid) | yes
FnbService | listDeliveryLocations | response | items[].kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | listDeliveryLocations | response | items[].label | string | yes | What a runner is told.
FnbService | listDeliveryLocations | response | items[].zone | string |  | (nullable)
FnbService | listDeliveryLocations | response | items[].opensAt | string (time) |  | When a collection point opens, local to the venue (r8 walk of ticket 27820). (nullable)
FnbService | listDeliveryLocations | response | items[].closesAt | string (time) |  | When a collection point closes, local to the venue; retail collectBy defaults to this on the day. (nullable)
FnbService | listDeliveryLocations | response | items[].tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | listDeliveryLocations | response | items[].seatId | string |  | Set where the seat is the address. (nullable)
FnbService | listDeliveryLocations | response | items[].servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | listDeliveryLocations | response | items[].isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | listDeliveryLocations | response | items[].unserviceableReason | string |  | (nullable)
FnbService | listDeliveryLocations | response | items[].walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | listDeliveryLocations | response | items[].codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | listDeliveryLocations | response | nextCursor | string
FnbService | listDeliveryLocations | response | hasMore | boolean | yes
FnbService | listDeliveryLocations | param (path) | venueId | string (uuid) | yes
FnbService | listDeliveryLocations | param (query) | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …)
FnbService | listDeliveryLocations | param (query) | servingOutletId | string (uuid) |  | Only locations this outlet delivers to.
FnbService | listDeliveryLocations | param (query) | pageSize | integer
FnbService | listDeliveryLocations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listDenominations | param (query) | includeInactive | boolean
OrderService | listDepositBoxes | response | items | array of DepositBox | yes
OrderService | listDepositBoxes | response | items[].id | string (uuid) |  | (read-only)
OrderService | listDepositBoxes | response | items[].cashierPrincipalId | string (uuid) | yes
OrderService | listDepositBoxes | response | items[].cashierName | string |  | (read-only)
OrderService | listDepositBoxes | response | items[].venueId | string (uuid) | yes
OrderService | listDepositBoxes | response | items[].workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | listDepositBoxes | response | items[].shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | listDepositBoxes | response | items[].status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | listDepositBoxes | response | items[].openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].openingDenominations | array of object |  | 5.8.3.
OrderService | listDepositBoxes | response | items[].openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | listDepositBoxes | response | items[].openingDenominations[].count | integer | yes | (min 0)
OrderService | listDepositBoxes | response | items[].withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | listDepositBoxes | response | items[].foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not in the box's own currency. (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | listDepositBoxes | response | items[].expectedTotal | object |  | The figure the box's close count is measured against, filled when the box is counted. (nullable)
OrderService | listDepositBoxes | response | items[].expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].variance | object |  | Counted minus expected; negative is short. (nullable)
OrderService | listDepositBoxes | response | items[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | listDepositBoxes | response | items[].allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | listDepositBoxes | response | items[].closedAt | string (date-time) |  | (nullable)
OrderService | listDepositBoxes | response | items[].recordedAt | string (date-time) |  | When the device made the write (R113; CHG-OFL-003): for an allocation, the same moment as allocatedAt, kept in recorded_at, the column every offline-written table carries for the sync to order replay…
OrderService | listDepositBoxes | response | nextCursor | string
OrderService | listDepositBoxes | response | hasMore | boolean | yes
OrderService | listDepositBoxes | param (query) | openOnly | boolean |  | True: only the boxes not yet closed (allocated, open, suspended, closing).
OrderService | listDepositBoxes | param (query) | pageSize | integer
OrderService | listDepositBoxes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listDevices | response | items | array of RegisteredDevice | yes
TenancyService | listDevices | response | items[].scopePath | string | yes | Where the row is owned. (read-only)
TenancyService | listDevices | response | items[].id | string (uuid) | yes | (read-only)
TenancyService | listDevices | response | items[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | listDevices | response | items[].driver | string | yes | Built to an open standard where one exists — ESC/POS, UnifiedPOS, OSDP.
TenancyService | listDevices | response | items[].identifier | string |  | (nullable)
TenancyService | listDevices | response | items[].workstationId | string (uuid) |  | Required for every kind except mobileHandset, which is bound to no workstation (18.1.5, 29 September), and except an access-control device (one with a hardwareType), which is placed in the gate topol… (nullable)
TenancyService | listDevices | response | items[].model | string |  | (nullable)
TenancyService | listDevices | response | items[].hardwareType | DeviceHardwareType: enum (standardTurnstile, fullHeightTurnstile, tripodTurnstile, speedGate, wideLane, accessiblePodGate, buggyGate, vipGate, …) |  | The specific hardware under a device's kind (ADR-0067, accepted 1 October: one device register).
TenancyService | listDevices | response | items[].hardwareModelId | string (uuid) |  | The model in the hardware library (access setHardwareModel; ADR-0067). (nullable)
TenancyService | listDevices | response | items[].serialNumber | string |  | The manufacturer's serial (ADR-0067: was on the access-control device row, now access.device_placement). (max length 100; nullable)
TenancyService | listDevices | response | items[].ipNetworkReference | string |  | Network address or reference the device is reached at (ADR-0067). (nullable)
TenancyService | listDevices | response | items[].configurationVersion | string |  | Access configuration version the device reports running (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].localRuleVersion | string |  | Admission rule package the device reports running (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].credentialSecurityPackageVersion | string |  | Credential security package the device reports running (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].scannerHealth | string |  | Component health as the device or vendor reports it on its heartbeat (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].controllerHealth | string |  | (read-only; nullable)
TenancyService | listDevices | response | items[].cameraHealth | string |  | Where the device has a camera. (read-only; nullable)
TenancyService | listDevices | response | items[].connectivity | string |  | Reported connectivity. (read-only; nullable)
TenancyService | listDevices | response | items[].pushToken | string (password) |  | BL-163. (nullable)
TenancyService | listDevices | response | items[].pushPlatform | enum (ios, android, web, windows) |  | (nullable)
TenancyService | listDevices | response | items[].pushFailureCount | integer |  | Consecutive failures. (default 0; read-only)
TenancyService | listDevices | response | items[].offlineScope | enum (none, readOnly, sellAndScan, fullVenue) |  | BL-163. (nullable)
TenancyService | listDevices | response | items[].firmwareVersion | string |  | As the device last reported it on its heartbeat. (read-only; nullable)
TenancyService | listDevices | response | items[].isRequired | boolean |  | True blocks shift open when the device is unreachable.
TenancyService | listDevices | response | items[].status | enum (online, offline, error, consumableLow, needsAttention, localMode, unknown) |  | What the device last said on its heartbeat; unknown until it has. (default unknown; read-only)
TenancyService | listDevices | response | items[].batteryPercent | integer |  | Board 1 of the client's POS design set, 20 August. (min 0; max 100; read-only; nullable)
TenancyService | listDevices | response | items[].lastCheckedAt | string (date-time) |  | Distinct from lastHeartbeatAt. (read-only; nullable)
TenancyService | listDevices | response | items[].health | enum (healthy, warning, degraded, offline, unknown) |  | Derived, not reported. (default unknown; read-only)
TenancyService | listDevices | response | items[].lastHeartbeatAt | string (date-time) |  | (read-only; nullable)
TenancyService | listDevices | response | items[].capabilities | array of DeviceCapability: enum (genderClassification, dynamicQr, rfid, nfc, facePass, offline, heightCheck) |  | BL-179. (read-only)
TenancyService | listDevices | response | items[].enrolmentState | enum (registered, enrolled, provisioned, active, deactivated, retired) |  | BL-160. (default registered; read-only)
TenancyService | listDevices | response | items[].retiredAt | string (date-time) |  | Set when enrolmentState reaches retired, and null otherwise. (read-only; nullable)
TenancyService | listDevices | response | items[].configurationProfileId | string (uuid) |  | The profile this device was provisioned with. (read-only; nullable)
TenancyService | listDevices | response | items[].approvalStatus | object |  | A new device waits for approval before it may go live (decided 2 October 2026, Chinmay, critical set 1, BO-196: "Secure enrolment code + pending approval"; DEC-241; CHG-CSP-011; MoM 15 September, DI-… (default pendingApproval; read-only)
TenancyService | listDevices | response | items[].enrolmentCode | string |  | A one-time code the device must present to enrol (DEC-241; CHG-CSP-011). (max length 12; read-only; nullable)
TenancyService | listDevices | response | items[].enrolmentCodeExpiresAt | string (date-time) |  | When the enrolment code stops working (24 hours after registration, proposed; client to correct). (read-only; nullable)
TenancyService | listDevices | response | items[].testedByPrincipalId | string (uuid) |  | Who recorded the device's acceptance test (DeviceEnrolment.testResult on the move to provisioned). (read-only; nullable)
TenancyService | listDevices | response | items[].approvedByPrincipalId | string (uuid) |  | Who approved the device into production, never the person who tested it (decided 2 October 2026, Chinmay, critical set 1, BO-203: "Approver must differ from the tester"; DEC-245; CHG-CSP-011). (read-only; nullable)
TenancyService | listDevices | response | items[].approvedAt | string (date-time) |  | (read-only; nullable)
TenancyService | listDevices | response | nextCursor | string
TenancyService | listDevices | response | hasMore | boolean | yes
TenancyService | listDevices | param (query) | workstationId | string (uuid)
TenancyService | listDevices | param (query) | kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …)
TenancyService | listDevices | param (query) | pageSize | integer
TenancyService | listDevices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listDiningOutlets | response | items | array of DiningOutlet | yes
FnbService | listDiningOutlets | response | items[].outletId | string (uuid) | yes
FnbService | listDiningOutlets | response | items[].name | string | yes
FnbService | listDiningOutlets | response | items[].kind | string | yes
FnbService | listDiningOutlets | response | items[].zone | string |  | (nullable)
FnbService | listDiningOutlets | response | items[].cuisine | array of string
FnbService | listDiningOutlets | response | items[].isOpenNow | boolean | yes
FnbService | listDiningOutlets | response | items[].opensAt | string (date-time) |  | (nullable)
FnbService | listDiningOutlets | response | items[].closesAt | string (date-time) |  | (nullable)
FnbService | listDiningOutlets | response | items[].orderingMethod | GuestOrderingMethod: enum (tableService, appToTable, appToCollect, counterOnly, notAvailable) | yes | How a guest may order at this outlet.
FnbService | listDiningOutlets | response | items[].estimatedWaitMinutes | integer |  | From current kitchen ticket volume, not a fixed figure. (nullable)
FnbService | listDiningOutlets | response | items[].imageAssetRef | string |  | (nullable)
FnbService | listDiningOutlets | response | items[].menuId | string (uuid) |  | (nullable)
FnbService | listDiningOutlets | response | items[].admissionContext | object |  | Inside the venue or standalone (decided 2 October 2026, Chinmay: DEC-070, workbook Q70; CHG-CLN-008): the outlet's tenancy.Outlet.admissionContext, so the guest sees before ordering whether an admiss…
FnbService | listDiningOutlets | response | nextCursor | string
FnbService | listDiningOutlets | response | hasMore | boolean | yes
FnbService | listDiningOutlets | param (path) | venueId | string (uuid) | yes
FnbService | listDiningOutlets | param (query) | openNow | boolean
FnbService | listDiningOutlets | param (query) | orderingMethod | GuestOrderingMethod: enum (tableService, appToTable, appToCollect, counterOnly, notAvailable)
FnbService | listDiningOutlets | param (query) | pageSize | integer
FnbService | listDiningOutlets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listEntitlements | response | items | array of Entitlement | yes
AccessService | listEntitlements | response | items[].id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | listEntitlements | response | items[].templateId | string (uuid) | yes | The definition it was issued against.
AccessService | listEntitlements | response | items[].productId | string (uuid) | yes
AccessService | listEntitlements | response | items[].productName | string |  | Read with the entitlement, not stored on it (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009), as TicketStatus.productName: the product's name from catalogue.product (catalogue#productRecords), in the cal… (read-only)
AccessService | listEntitlements | response | items[].venueName | string |  | The venue's name, read from platform.scope by venueId; not stored. (read-only)
AccessService | listEntitlements | response | items[].imageUrl | string (uri) |  | The product's primary image (catalogue.product_media), read with the entitlement; null when the product has none. (read-only; nullable)
AccessService | listEntitlements | response | items[].guestCategory | string |  | The guest category of the order line it was issued for (adult, child, ...), from the line's variant (catalogue#productRecords); null for an entitlement no order line issued. (read-only; nullable)
AccessService | listEntitlements | response | items[].orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id). (nullable)
AccessService | listEntitlements | response | items[].orderLineId | string (uuid) |  | The order line it was issued for; the ticket list groups cards by it (CHG-R8MIG-009).
AccessService | listEntitlements | response | items[].subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | listEntitlements | response | items[].venueId | string (uuid)
AccessService | listEntitlements | response | items[].scopePath | string
AccessService | listEntitlements | response | items[].mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | listEntitlements | response | items[].changeVersion | integer (int64) | yes | What the offline package's delta counts (ADAM CR-239, option A; Chinmay, 25 October 2026; CHG-R10ORD-011). (read-only)
AccessService | listEntitlements | response | items[].mediaLinkedAt | string (date-time) |  | When the entitlement was put on its media (ADAM CR-226, option A; Chinmay, 25 October 2026; CHG-R10ORD-012): written when mediaCode is set or rotated: at issue (issueOrderEntitlements, onto new media… (read-only; nullable)
AccessService | listEntitlements | response | items[].rotationSecret | string |  | The rotation seed, stored on the entitlement (ADAM CR-167, option A; CHG-R10ORD-010): the Base32 shared secret the rotating code is derived from (getEntitlementCredential rotation.secret, audit R230)… (nullable)
AccessService | listEntitlements | response | items[].credentialFormat | object |  | The credential this entitlement was issued with, resolved once at issue by issueOrderEntitlements: the product's credentialFormatOverride, else the sales channel's ticketCredentialFormat, else platfo… (nullable)
AccessService | listEntitlements | response | items[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | listEntitlements | response | items[].statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | listEntitlements | response | items[].validFrom | string (date-time) | yes
AccessService | listEntitlements | response | items[].validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | listEntitlements | response | items[].entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | listEntitlements | response | items[].entriesAllowed | integer |  | (nullable)
AccessService | listEntitlements | response | items[].lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | listEntitlements | response | items[].firstEntryAt | string (date-time) |  | recordedAt of the first admission, written by the same writes as lastEntryAt; it starts a time-bound entitlement's window (DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listEntitlements | response | items[].timeBoundUntil | string (date-time) |  | Where the template is time-bound, when its window closes: firstEntryAt plus the validity rule's minutesAfterFirstScan (decided 2 October 2026, Chinmay, BO-159; DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listEntitlements | response | items[].lifecycleLabel | enum (created, pendingFulfillment, active, partiallyUsed, used, expired, suspended, cancelled, …) |  | The Virtual Ticket status in the client's 13 names, mapped onto the entitlement model (decided 2 October 2026, Chinmay, critical set 2, BO-336: "Map the pack's 13 names onto the model; add any missin… (read-only)
AccessService | listEntitlements | response | items[].cancellationKind | enum (voided, refunded, performanceCancelled, superseded) |  | Which act cancelled the entitlement, so the pack's Voided, Refunded and Reissued / superseded are told apart while status keeps the one r1 value cancelled (DEC-266; CHG-CSP-033). (read-only; nullable)
AccessService | listEntitlements | response | items[].frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | listEntitlements | response | items[].suspendedReason | string |  | (nullable)
AccessService | listEntitlements | response | items[].freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | listEntitlements | response | items[].freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | listEntitlements | response | items[].isNameBound | boolean |  | (default False)
AccessService | listEntitlements | response | items[].holderName | string |  | (nullable)
AccessService | listEntitlements | response | items[].sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | listEntitlements | response | items[].issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | listEntitlements | response | items[].supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | listEntitlements | response | items[].walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | listEntitlements | response | items[].facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | listEntitlements | response | items[].invitationId | string (uuid) |  | The invitation that issued it (4 October 2026, CHG-FXC-007): orders.issueInvitation issues the entitlement without an order, because an invitation never enters the order path. (nullable)
AccessService | listEntitlements | response | nextCursor | string
AccessService | listEntitlements | response | hasMore | boolean | yes
AccessService | listEntitlements | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | listEntitlements | param (query) | includeExpired | boolean
AccessService | listEntitlements | param (query) | pageSize | integer
AccessService | listEntitlements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listEvents | response | items | array of Event | yes
CatalogueService | listEvents | response | items[].id | string (uuid) | yes
CatalogueService | listEvents | response | items[].code | string | yes
CatalogueService | listEvents | response | items[].name | string | yes
CatalogueService | listEvents | response | items[].venueId | string (uuid) | yes
CatalogueService | listEvents | response | items[].scopePath | string | yes
CatalogueService | listEvents | response | items[].parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | listEvents | response | items[].performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | listEvents | response | items[].isActive | boolean
CatalogueService | listEvents | response | items[].lifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | Where the event is in its lifecycle (4 October 2026, CHG-FXC-003; catalogue.event had nowhere to keep it). (read-only)
CatalogueService | listEvents | response | items[].lifecycleStateChangedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | listEvents | response | items[].scheduledLifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | A move waiting for its effectiveFrom (ADAM CR-109, option 2; CHG-R10CAT-009): written by setEventLifecycleState when effectiveFrom is in the future, applied and cleared by the event lifecycle job in… (read-only; nullable)
CatalogueService | listEvents | response | items[].scheduledLifecycleAt | string (date-time) |  | When the waiting move is applied (the request's effectiveFrom; ADAM CR-109). (read-only; nullable)
CatalogueService | listEvents | response | items[].scheduledLifecycleReason | string |  | The reason given with the waiting move, carried on event.lifecycleChanged when it is applied (ADAM CR-109). (max length 500; read-only; nullable)
CatalogueService | listEvents | response | nextCursor | string
CatalogueService | listEvents | response | hasMore | boolean | yes
CatalogueService | listEvents | param (query) | venueId | string (uuid) |  | Whose venue to read, for a caller with no venue (as listProductCategories; GPS-C30).
CatalogueService | listEvents | param (query) | pageSize | integer
CatalogueService | listEvents | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listEvents | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
FnbService | listFnbOrders | response | items | array of FnbOrder | yes
FnbService | listFnbOrders | response | items[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | listFnbOrders | response | items[].outletId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | listFnbOrders | response | items[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | listFnbOrders | response | items[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | listFnbOrders | response | items[].tableVisitId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | listFnbOrders | response | items[].lines | array of object | yes
FnbService | listFnbOrders | response | items[].lines[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].lines[].menuItemId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].lines[].quantity | integer | yes | (min 1)
FnbService | listFnbOrders | response | items[].lines[].modifierOptionIds | array of string (uuid)
FnbService | listFnbOrders | response | items[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | listFnbOrders | response | items[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | listFnbOrders | response | items[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | listFnbOrders | response | items[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | listFnbOrders | response | items[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | listFnbOrders | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | listFnbOrders | response | items[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | listFnbOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | listFnbOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | listFnbOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | listFnbOrders | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | listFnbOrders | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | listFnbOrders | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | listFnbOrders | response | items[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | listFnbOrders | response | items[].kitchenTickets[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | listFnbOrders | response | items[].kitchenTickets[].orderNumber | string
FnbService | listFnbOrders | response | items[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | listFnbOrders | response | items[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | listFnbOrders | response | items[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].lines | array of object | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].elapsedSeconds | integer
FnbService | listFnbOrders | response | items[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | listFnbOrders | response | items[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | items[].createdAt | string (date-time) | yes
FnbService | listFnbOrders | response | items[].recordedAt | string (date-time)
FnbService | listFnbOrders | response | items[].syncedAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | nextCursor | string
FnbService | listFnbOrders | response | hasMore | boolean | yes
FnbService | listFnbOrders | param (query) | outletId | string (uuid)
FnbService | listFnbOrders | param (query) | tableVisitId | string (uuid)
FnbService | listFnbOrders | param (query) | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …)
FnbService | listFnbOrders | param (query) | pageSize | integer
FnbService | listFnbOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listForecastVersions | response | items | array of AiForecastVersion | yes
AiService | listForecastVersions | response | items[].id | string (uuid) |  | (read-only)
AiService | listForecastVersions | response | items[].definitionId | string (uuid) | yes
AiService | listForecastVersions | response | items[].versionNumber | integer | yes | (min 1)
AiService | listForecastVersions | response | items[].module | object |  | The module of the version's definition (AiForecastDefinition.module), copied when the version is produced; the module whose AI publish permission publishForecastVersion requires (CHG-FUP-004). (read-only)
AiService | listForecastVersions | response | items[].status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | listForecastVersions | response | items[].basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | listForecastVersions | response | items[].maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | listForecastVersions | response | items[].maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | listForecastVersions | response | items[].maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | listForecastVersions | response | items[].maturity.sources | array of object
AiService | listForecastVersions | response | items[].maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | listForecastVersions | response | items[].maturity.limitedHistory | boolean
AiService | listForecastVersions | response | items[].maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | listForecastVersions | response | items[].producerRef | string
AiService | listForecastVersions | response | items[].modelVersion | string |  | (nullable)
AiService | listForecastVersions | response | items[].dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | listForecastVersions | response | items[].horizonStart | string (date-time)
AiService | listForecastVersions | response | items[].horizonEnd | string (date-time)
AiService | listForecastVersions | response | items[].qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | listForecastVersions | response | items[].publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | listForecastVersions | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
AiService | listForecastVersions | response | items[].decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | listForecastVersions | response | items[].createdAt | string (date-time) |  | (read-only)
AiService | listForecastVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listForecastVersions | response | nextCursor | string
AiService | listForecastVersions | response | hasMore | boolean | yes
AiService | listForecastVersions | param (query) | definitionKey | string
AiService | listForecastVersions | param (query) | status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed)
AiService | listForecastVersions | param (query) | pageSize | integer
AiService | listForecastVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listFulfilmentSlots | response | items | FulfilmentSlots | yes
FnbService | listFulfilmentSlots | response | items.slots | array of object
FnbService | listFulfilmentSlots | response | items.slots[].start | string (date-time)
FnbService | listFulfilmentSlots | response | items.slots[].end | string (date-time) |  | (nullable)
FnbService | listFulfilmentSlots | response | items.slots[].isAsap | boolean
FnbService | listFulfilmentSlots | response | nextCursor | string
FnbService | listFulfilmentSlots | response | hasMore | boolean | yes
FnbService | listFulfilmentSlots | param (path) | outletId | string (uuid) | yes
FnbService | listFulfilmentSlots | param (query) | mode | enum (collection, delivery) | yes
FnbService | listFulfilmentSlots | param (query) | date | string (date) |  | A calendar day, in the Region's time zone, not UTC.
FnbService | listFulfilmentSlots | param (query) | pageSize | integer
FnbService | listFulfilmentSlots | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listFulfilmentSlots | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
LedgerService | listFxRates | response | items | array of FxRate | yes
LedgerService | listFxRates | response | items[].id | string (uuid) |  | (read-only)
LedgerService | listFxRates | response | items[].fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listFxRates | response | items[].toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listFxRates | response | items[].rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | listFxRates | response | items[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | listFxRates | response | items[].source | object |  | (read-only)
LedgerService | listFxRates | response | items[].effectiveFrom | string (date-time) | yes
LedgerService | listFxRates | response | items[].effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | listFxRates | response | items[].setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | listFxRates | response | items[].note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | listFxRates | response | items[].providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | listFxRates | response | items[].fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | listFxRates | response | items[].chargeable | boolean |  | With venueId, true where a guest may select this currency and pay in it at that venue (tenancy.VenueSettings.chargeCurrencies), false where it is shown as an approximate price only (CHG-FIN-001). (read-only)
LedgerService | listFxRates | response | nextCursor | string
LedgerService | listFxRates | response | hasMore | boolean | yes
LedgerService | listFxRates | param (query) | asAt | string (date-time) |  | Rates in force at this instant.
LedgerService | listFxRates | param (query) | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation)
LedgerService | listFxRates | param (query) | venueId | string (uuid) |  | Narrows the region's rates to the currencies this venue shows.
LedgerService | listFxRates | param (query) | chargeable | boolean |  | With venueId, only the currencies a guest may select and pay in at that venue (tenancy.VenueSettings.chargeCurrencies; CHG-FIN-001).
LedgerService | listFxRates | param (query) | pageSize | integer
LedgerService | listFxRates | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listGroupArrivalCheck | param (query) | pageSize | integer
CatalogueService | listGroupPackages | response | items | array of GroupPackageDefinition | yes
CatalogueService | listGroupPackages | response | items[].id | string (uuid) |  | (read-only)
CatalogueService | listGroupPackages | response | items[].productId | string |  | (read-only)
CatalogueService | listGroupPackages | response | items[].name | string |  | Read from the package's product, not stored here (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009): catalogue.product.name, in the caller's language. (read-only)
CatalogueService | listGroupPackages | response | items[].unitPrice | object |  | The product's price per participant (pricingBasis perParticipant) or per package, read from the product's current price; not stored here. (read-only)
CatalogueService | listGroupPackages | response | items[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | listGroupPackages | response | items[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | listGroupPackages | response | items[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | listGroupPackages | response | items[].minimumSize | integer |  | The smallest group the package is sold to; null means one participant. (min 1; nullable)
CatalogueService | listGroupPackages | response | items[].kind | enum (school, party, corporate, tourOperator, community) | yes | corporate, tourOperator and community are the group types the approved group-booking screens draw beside school and party (CHG-SGU-024; R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009).
CatalogueService | listGroupPackages | response | items[].maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | listGroupPackages | response | items[].durationMinutes | integer | yes | (min 15)
CatalogueService | listGroupPackages | response | items[].hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | listGroupPackages | response | items[].pricingBasis | enum (perParticipant, perPackage)
CatalogueService | listGroupPackages | response | items[].freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | listGroupPackages | response | items[].paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | listGroupPackages | response | items[].includes | array of string
CatalogueService | listGroupPackages | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | listGroupPackages | response | nextCursor | string
CatalogueService | listGroupPackages | response | hasMore | boolean | yes
CatalogueService | listGroupPackages | param (query) | venueId | string (uuid) |  | Whose venue to read, for a caller with no venue (R8 blocker fix, GPS-C01 and WHITE-C05).
CatalogueService | listGroupPackages | param (query) | kind | enum (school, party)
CatalogueService | listGroupPackages | param (query) | pageSize | integer
CatalogueService | listGroupPackages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listGroupPackages | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
MarketingService | listGuestDevices | response | items | array of GuestDevice | yes
MarketingService | listGuestDevices | response | items[].id | string (uuid) | yes
MarketingService | listGuestDevices | response | items[].subjectId | string (uuid) | yes
MarketingService | listGuestDevices | response | items[].platform | enum (ios, android, web) | yes
MarketingService | listGuestDevices | response | items[].installationId | string (uuid) |  | The app install the registration came from, as registerGuestDevice.installationId sent it (CHG-MKT-001). (nullable)
MarketingService | listGuestDevices | response | items[].tokenFingerprint | string |  | A keyed hash of the token, not the token (decided 14 October 2026, CHG-MKT-001; ADR-0063 section 4 as amended): HMAC-SHA-256 of the token under the tenant's blind-index key, written as 64 lowercase h… (max length 64; nullable)
MarketingService | listGuestDevices | response | items[].tokenRef | string |  | The push token, encrypted by the application (decided 14 October 2026, Chinmay, ADAM CR-086, CHG-MKT-001; ADR-0063 section 4 as amended), written by the server from registerGuestDevice.token: AES-256… (nullable)
MarketingService | listGuestDevices | response | items[].appVersion | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].osVersion | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].deviceModel | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].locale | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].status | enum (active, revoked, failed) | yes | active is sent to.
MarketingService | listGuestDevices | response | items[].failureCount | integer |  | Consecutive delivery failures.
MarketingService | listGuestDevices | response | items[].registeredAt | string (date-time) | yes
MarketingService | listGuestDevices | response | items[].lastSeenAt | string (date-time) |  | (nullable)
MarketingService | listGuestDevices | response | items[].revokedAt | string (date-time) |  | (nullable)
MarketingService | listGuestDevices | response | items[].pendingSessionEndInstallationId | string (uuid) |  | Set only by the server (a value a client sends is ignored) and never returned (R8 blocker IDENTITY-C23). (nullable)
MarketingService | listGuestDevices | response | nextCursor | string
MarketingService | listGuestDevices | response | hasMore | boolean | yes
MarketingService | listGuestDevices | param (path) | subjectId | string (uuid) | yes
MarketingService | listGuestDevices | param (query) | pageSize | integer
MarketingService | listGuestDevices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listGuidedChoices | response | items | array of GuidedChoice | yes
WhiteLabelService | listGuidedChoices | response | items[].id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | listGuidedChoices | response | items[].mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | listGuidedChoices | response | items[].showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | listGuidedChoices | response | items[].behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | listGuidedChoices | response | items[].showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | listGuidedChoices | response | items[].questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | listGuidedChoices | response | items[].questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listGuidedChoices | response | items[].questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | listGuidedChoices | response | items[].questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | listGuidedChoices | response | items[].questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | listGuidedChoices | response | items[].status | object | yes | (read-only)
WhiteLabelService | listGuidedChoices | response | items[].source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | listGuidedChoices | response | items[].suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listGuidedChoices | response | nextCursor | string
WhiteLabelService | listGuidedChoices | response | hasMore | boolean | yes
WhiteLabelService | listGuidedChoices | param (path) | venueId | string (uuid) | yes
WhiteLabelService | listGuidedChoices | param (query) | status | GuidedChoiceStatus: enum (draft, published)
WhiteLabelService | listGuidedChoices | param (query) | source | enum (manual, aiSuggested)
WhiteLabelService | listGuidedChoices | param (query) | pageSize | integer
WhiteLabelService | listGuidedChoices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listKitchenStations | response | items | array of KitchenStation | yes
FnbService | listKitchenStations | response | items[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | listKitchenStations | response | items[].id | string (uuid) | yes
FnbService | listKitchenStations | response | items[].code | string | yes
FnbService | listKitchenStations | response | items[].name | string | yes
FnbService | listKitchenStations | response | items[].outletId | string (uuid)
FnbService | listKitchenStations | response | items[].menuItemIds | array of string (uuid) |  | Items routed to this station.
FnbService | listKitchenStations | response | items[].displayWorkstationIds | array of string (uuid) |  | The kitchen displays assigned to this station (decided 28 September, audit R277), as tenancy Workstation ids, primary first and fallbacks after it.
FnbService | listKitchenStations | response | items[].displayEndpoint | string |  | The P15 Kitchen Display device this station's tickets go to (19 Sep: the display is TICVAI software on commodity hardware, per station, with a fallback device where the primary is down — 18 Aug minut… (nullable)
FnbService | listKitchenStations | response | items[].printerDeviceIds | array of string (uuid) |  | The kitchen printers assigned to this station (Chinmay, 2 October, workbook Q187: kitchen printers are in release 1; CHG-CSA-014), as tenancy RegisteredDevice ids of kind receiptPrinter or labelPrint…
FnbService | listKitchenStations | response | items[].servesOutletIds | array of string (uuid) |  | A producing outlet's station serving other outlets (Chinmay, 2 October, workbook Q186 and Q188; DI-330; CHG-CSA-015).
FnbService | listKitchenStations | response | items[].isActive | boolean
FnbService | listKitchenStations | response | nextCursor | string
FnbService | listKitchenStations | response | hasMore | boolean | yes
FnbService | listKitchenStations | param (query) | outletId | string (uuid) |  | One outlet's stations.
FnbService | listKitchenStations | param (query) | pageSize | integer
FnbService | listKitchenStations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listKitchenTickets | response | items | array of KitchenTicket | yes
FnbService | listKitchenTickets | response | items[].id | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | listKitchenTickets | response | items[].orderNumber | string
FnbService | listKitchenTickets | response | items[].outletId | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].tableLabel | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | listKitchenTickets | response | items[].coursing | object |  | BL-131. (nullable)
FnbService | listKitchenTickets | response | items[].buzzerCode | string |  | BL-128. (nullable)
FnbService | listKitchenTickets | response | items[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listKitchenTickets | response | items[].priority | integer |  | Higher fires sooner.
FnbService | listKitchenTickets | response | items[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | listKitchenTickets | response | items[].prioritiseReason | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines | array of object | yes
FnbService | listKitchenTickets | response | items[].lines[].lineId | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].lines[].name | string | yes
FnbService | listKitchenTickets | response | items[].lines[].quantity | integer | yes
FnbService | listKitchenTickets | response | items[].lines[].modifiers | array of string
FnbService | listKitchenTickets | response | items[].lines[].note | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | listKitchenTickets | response | items[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].course | integer |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listKitchenTickets | response | items[].createdAt | string (date-time) | yes
FnbService | listKitchenTickets | response | items[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | listKitchenTickets | response | items[].elapsedSeconds | integer
FnbService | listKitchenTickets | response | items[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | listKitchenTickets | response | nextCursor | string
FnbService | listKitchenTickets | response | hasMore | boolean | yes
FnbService | listKitchenTickets | param (query) | stationId | string (uuid) |  | Route to a preparation station — grill, cold, bar.
FnbService | listKitchenTickets | param (query) | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | listKitchenTickets | param (query) | course | integer |  | The course filter (decided 28 September, audit R277).
FnbService | listKitchenTickets | param (query) | pageSize | integer
FnbService | listKitchenTickets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listLandingPageTemplates | response | items | array of LandingPageTemplate | yes
WhiteLabelService | listLandingPageTemplates | response | items[].templateKey | string | yes
WhiteLabelService | listLandingPageTemplates | response | items[].name | string | yes
WhiteLabelService | listLandingPageTemplates | response | items[].presetKey | string |  | The Site Builder preset it belongs to (SiteSetupProgress.presetKey). (nullable)
WhiteLabelService | listLandingPageTemplates | response | items[].thumbnailUrl | string |  | (nullable)
WhiteLabelService | listLandingPageTemplates | response | items[].layout | HomepageLayout | yes | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | listLandingPageTemplates | response | items[].layout.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | listLandingPageTemplates | response | items[].layout.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | listLandingPageTemplates | response | items[].layout.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | listLandingPageTemplates | response | items[].layout.sections | array of object | yes
WhiteLabelService | listLandingPageTemplates | response | nextCursor | string
WhiteLabelService | listLandingPageTemplates | response | hasMore | boolean | yes
WhiteLabelService | listLandingPageTemplates | param (query) | pageSize | integer
WhiteLabelService | listLandingPageTemplates | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listLeaderboard | response | items | array of LeaderboardEntry | yes
MarketingService | listLeaderboard | response | items[].rank | integer | yes | (min 1)
MarketingService | listLeaderboard | response | items[].nickname | string | yes | Always present, and never their real name.
MarketingService | listLeaderboard | response | items[].points | integer | yes
MarketingService | listLeaderboard | response | items[].isMe | boolean |  | How a client highlights the caller's own row without learning who anybody else is. (default False)
MarketingService | listLeaderboard | response | nextCursor | string
MarketingService | listLeaderboard | response | hasMore | boolean | yes
MarketingService | listLeaderboard | param (query) | programmeId | string (uuid) | yes
MarketingService | listLeaderboard | param (query) | window | enum (week, month, season) |  | Monthly, confirmed 20 September.
MarketingService | listLeaderboard | param (query) | pageSize | integer
MarketingService | listLeaderboard | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listLoyaltyProgrammes | response | items | array of LoyaltyProgramme | yes
MarketingService | listLoyaltyProgrammes | response | items[].tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].id | string (uuid) |  | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].code | string | yes | (max length 40)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].name | string | yes | (max length 120)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].rank | integer | yes | Order, not threshold.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].isActive | boolean |  | (default True)
MarketingService | listLoyaltyProgrammes | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | listLoyaltyProgrammes | response | items[].name | string | yes
MarketingService | listLoyaltyProgrammes | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | listLoyaltyProgrammes | response | items[].earnRules | array of object | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].points | number | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].multiplier | number
MarketingService | listLoyaltyProgrammes | response | items[].pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].isActive | boolean
MarketingService | listLoyaltyProgrammes | response | nextCursor | string
MarketingService | listLoyaltyProgrammes | response | hasMore | boolean | yes
MarketingService | listLoyaltyProgrammes | param (query) | pageSize | integer
MarketingService | listLoyaltyProgrammes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listLoyaltyProgrammes | param (query) | venueId | string (uuid) |  | Whose venue to read, for a caller with no venue (R8 blocker fix, as listProductCategories): a visitor with no credential, or an app before sign-in, must send it (missing is 400 venue-required, an id…
MarketingService | listLoyaltyProgrammes | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
RetailService | listMerchandise | response | items | array of MerchandiseItem or GuestMerchandiseItem | yes
RetailService | listMerchandise | response | nextCursor | string
RetailService | listMerchandise | response | hasMore | boolean | yes
RetailService | listMerchandise | param (query) | outletId | string (uuid) |  | Exact match.
RetailService | listMerchandise | param (query) | categoryId | string (uuid) |  | Exact match on categoryId.
RetailService | listMerchandise | param (query) | inStockOnly | boolean |  | True returns only items with onHand greater than zero at their own outlet.
RetailService | listMerchandise | param (query) | search | string |  | Case-insensitive "contains" match over name, sku, barcode and description.
RetailService | listMerchandise | param (query) | pageSize | integer
RetailService | listMerchandise | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | listMerchandise | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
MarketingService | listMyCases | response | items | array of Case | yes
MarketingService | listMyCases | response | items[].id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | listMyCases | response | items[].caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | listMyCases | response | items[].subjectId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | listMyCases | response | items[].subject | string | yes | The case's one-line title, not a person.
MarketingService | listMyCases | response | items[].kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | listMyCases | response | items[].channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | listMyCases | response | items[].recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | listMyCases | response | items[].syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | listMyCases | response | items[].categoryId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | listMyCases | response | items[].membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | listMyCases | response | items[].status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | listMyCases | response | items[].priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | listMyCases | response | items[].assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].relatedOrderId | string |  | (nullable)
MarketingService | listMyCases | response | items[].slaDueAt | string (date-time) |  | (nullable)
MarketingService | listMyCases | response | items[].isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | listMyCases | response | items[].slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | listMyCases | response | items[].escalationCount | integer
MarketingService | listMyCases | response | items[].createdAt | string (date-time) | yes
MarketingService | listMyCases | response | items[].resolvedAt | string (date-time) |  | (nullable)
MarketingService | listMyCases | response | nextCursor | string
MarketingService | listMyCases | response | hasMore | boolean | yes
MarketingService | listMyCases | param (query) | pageSize | integer
MarketingService | listMyCases | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listMyEntitlements | response | items | array of Entitlement | yes
AccessService | listMyEntitlements | response | items[].id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | listMyEntitlements | response | items[].templateId | string (uuid) | yes | The definition it was issued against.
AccessService | listMyEntitlements | response | items[].productId | string (uuid) | yes
AccessService | listMyEntitlements | response | items[].productName | string |  | Read with the entitlement, not stored on it (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009), as TicketStatus.productName: the product's name from catalogue.product (catalogue#productRecords), in the cal… (read-only)
AccessService | listMyEntitlements | response | items[].venueName | string |  | The venue's name, read from platform.scope by venueId; not stored. (read-only)
AccessService | listMyEntitlements | response | items[].imageUrl | string (uri) |  | The product's primary image (catalogue.product_media), read with the entitlement; null when the product has none. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].guestCategory | string |  | The guest category of the order line it was issued for (adult, child, ...), from the line's variant (catalogue#productRecords); null for an entitlement no order line issued. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id). (nullable)
AccessService | listMyEntitlements | response | items[].orderLineId | string (uuid) |  | The order line it was issued for; the ticket list groups cards by it (CHG-R8MIG-009).
AccessService | listMyEntitlements | response | items[].subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | listMyEntitlements | response | items[].venueId | string (uuid)
AccessService | listMyEntitlements | response | items[].scopePath | string
AccessService | listMyEntitlements | response | items[].mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | listMyEntitlements | response | items[].changeVersion | integer (int64) | yes | What the offline package's delta counts (ADAM CR-239, option A; Chinmay, 25 October 2026; CHG-R10ORD-011). (read-only)
AccessService | listMyEntitlements | response | items[].mediaLinkedAt | string (date-time) |  | When the entitlement was put on its media (ADAM CR-226, option A; Chinmay, 25 October 2026; CHG-R10ORD-012): written when mediaCode is set or rotated: at issue (issueOrderEntitlements, onto new media… (read-only; nullable)
AccessService | listMyEntitlements | response | items[].rotationSecret | string |  | The rotation seed, stored on the entitlement (ADAM CR-167, option A; CHG-R10ORD-010): the Base32 shared secret the rotating code is derived from (getEntitlementCredential rotation.secret, audit R230)… (nullable)
AccessService | listMyEntitlements | response | items[].credentialFormat | object |  | The credential this entitlement was issued with, resolved once at issue by issueOrderEntitlements: the product's credentialFormatOverride, else the sales channel's ticketCredentialFormat, else platfo… (nullable)
AccessService | listMyEntitlements | response | items[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | listMyEntitlements | response | items[].statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | listMyEntitlements | response | items[].validFrom | string (date-time) | yes
AccessService | listMyEntitlements | response | items[].validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | listMyEntitlements | response | items[].entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | listMyEntitlements | response | items[].entriesAllowed | integer |  | (nullable)
AccessService | listMyEntitlements | response | items[].lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].firstEntryAt | string (date-time) |  | recordedAt of the first admission, written by the same writes as lastEntryAt; it starts a time-bound entitlement's window (DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listMyEntitlements | response | items[].timeBoundUntil | string (date-time) |  | Where the template is time-bound, when its window closes: firstEntryAt plus the validity rule's minutesAfterFirstScan (decided 2 October 2026, Chinmay, BO-159; DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listMyEntitlements | response | items[].lifecycleLabel | enum (created, pendingFulfillment, active, partiallyUsed, used, expired, suspended, cancelled, …) |  | The Virtual Ticket status in the client's 13 names, mapped onto the entitlement model (decided 2 October 2026, Chinmay, critical set 2, BO-336: "Map the pack's 13 names onto the model; add any missin… (read-only)
AccessService | listMyEntitlements | response | items[].cancellationKind | enum (voided, refunded, performanceCancelled, superseded) |  | Which act cancelled the entitlement, so the pack's Voided, Refunded and Reissued / superseded are told apart while status keeps the one r1 value cancelled (DEC-266; CHG-CSP-033). (read-only; nullable)
AccessService | listMyEntitlements | response | items[].frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | listMyEntitlements | response | items[].suspendedReason | string |  | (nullable)
AccessService | listMyEntitlements | response | items[].freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | listMyEntitlements | response | items[].freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | listMyEntitlements | response | items[].isNameBound | boolean |  | (default False)
AccessService | listMyEntitlements | response | items[].holderName | string |  | (nullable)
AccessService | listMyEntitlements | response | items[].sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | listMyEntitlements | response | items[].issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | listMyEntitlements | response | items[].supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | listMyEntitlements | response | items[].walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | listMyEntitlements | response | items[].facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].invitationId | string (uuid) |  | The invitation that issued it (4 October 2026, CHG-FXC-007): orders.issueInvitation issues the entitlement without an order, because an invitation never enters the order path. (nullable)
AccessService | listMyEntitlements | response | nextCursor | string
AccessService | listMyEntitlements | response | hasMore | boolean | yes
AccessService | listMyEntitlements | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | listMyEntitlements | param (query) | state | enum (usableNow, upcoming, expired, all) |  | What each value returns (R8 blocker fix, WHITE-C08), against the entitlement's status (states/entitlement-status.yaml), its validFrom and validTo, and now in the venue's time zone (a null validTo is…
AccessService | listMyEntitlements | param (query) | includeShared | boolean |  | Entitlements shared with this guest by somebody else (shareEntitlement).
AccessService | listMyEntitlements | param (query) | pageSize | integer
AccessService | listMyEntitlements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listMyFavouriteRoutes | response | items | array of FavouriteRoute | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].venueId | string (uuid) | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].fromStationName | string |  | (read-only)
VenueOpsService | listMyFavouriteRoutes | response | items[].toStationName | string |  | (read-only)
VenueOpsService | listMyFavouriteRoutes | response | items[].label | string |  | (nullable)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listMyFavouriteRoutes | response | items[].createdAt | string (date-time) | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].subjectId | string (uuid) |  | The guest who saved it (4 October 2026, CHG-FXC-003; transport.favourite_route had no owner column). (read-only)
VenueOpsService | listMyFavouriteRoutes | response | nextCursor | string
VenueOpsService | listMyFavouriteRoutes | response | hasMore | boolean | yes
VenueOpsService | listMyFavouriteRoutes | param (query) | venueId | string (uuid) | yes
VenueOpsService | listMyFavouriteRoutes | param (query) | pageSize | integer
VenueOpsService | listMyFavouriteRoutes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyNotifications | response | items | array of GuestNotification | yes
MarketingService | listMyNotifications | response | items[].id | string | yes
MarketingService | listMyNotifications | response | items[].kind | enum (queueCall, orderReady, bookingChange, venueAlert, offer, other)
MarketingService | listMyNotifications | response | items[].title | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | listMyNotifications | response | items[].body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | listMyNotifications | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listMyNotifications | response | items[].deepLink | string |  | Where tapping the notification leads in the app (an order, a queue ticket, a booking). (nullable)
MarketingService | listMyNotifications | response | items[].queuedAt | string (date-time) | yes
MarketingService | listMyNotifications | response | items[].read | boolean | yes
MarketingService | listMyNotifications | response | nextCursor | string
MarketingService | listMyNotifications | response | hasMore | boolean | yes
MarketingService | listMyNotifications | response | unreadCount | integer |  | (min 0)
MarketingService | listMyNotifications | param (query) | pageSize | integer
MarketingService | listMyNotifications | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyNotifications | param (query) | unreadOnly | boolean
MarketingService | listMyNotifications | param (query) | venueId | string (uuid) |  | Only notifications from this venue.
OrderService | listMyOrders | response | items | array of Order | yes
OrderService | listMyOrders | response | items[].id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | listMyOrders | response | items[].orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | listMyOrders | response | items[].orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | listMyOrders | response | items[].channel | object | yes | Where it came from.
OrderService | listMyOrders | response | items[].channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | listMyOrders | response | items[].venueId | string (uuid) | yes
OrderService | listMyOrders | response | items[].scopePath | string | yes
OrderService | listMyOrders | response | items[].status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | listMyOrders | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | listMyOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | listMyOrders | response | items[].chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | listMyOrders | response | items[].chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | listMyOrders | response | items[].chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | listMyOrders | response | items[].chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | listMyOrders | response | items[].droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | listMyOrders | response | items[].droppedPromotions[].promotionId | string (uuid) | yes
OrderService | listMyOrders | response | items[].droppedPromotions[].name | string
OrderService | listMyOrders | response | items[].droppedPromotions[].reason | enum (budgetCapReached)
OrderService | listMyOrders | response | items[].totalPriceVariance | object |  | Sum across lines.
OrderService | listMyOrders | response | items[].totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].lines | array of OrderLine | yes
OrderService | listMyOrders | response | items[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | listMyOrders | response | items[].lines[].variantId | string (uuid) | yes
OrderService | listMyOrders | response | items[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | listMyOrders | response | items[].lines[].performanceId | string (uuid)
OrderService | listMyOrders | response | items[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | listMyOrders | response | items[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | listMyOrders | response | items[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | listMyOrders | response | items[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | listMyOrders | response | items[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | listMyOrders | response | items[].lines[].quantity | integer | yes | (min 1)
OrderService | listMyOrders | response | items[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | listMyOrders | response | items[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | listMyOrders | response | items[].lines[].holderName | string |  | (nullable)
OrderService | listMyOrders | response | items[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | listMyOrders | response | items[].lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | listMyOrders | response | items[].lines[].priceVariance | object |  | Server minus quoted.
OrderService | listMyOrders | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | listMyOrders | response | items[].lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | listMyOrders | response | items[].lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | listMyOrders | response | items[].lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | listMyOrders | response | items[].lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | listMyOrders | response | items[].payments | array of Payment
OrderService | listMyOrders | response | items[].payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].id | string (uuid) | yes
OrderService | listMyOrders | response | items[].payments[].orderId | string (uuid) | yes
OrderService | listMyOrders | response | items[].payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | listMyOrders | response | items[].payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | listMyOrders | response | items[].payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | listMyOrders | response | items[].payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | listMyOrders | response | items[].payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | listMyOrders | response | items[].payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | listMyOrders | response | items[].payments[].providerName | string |  | (nullable)
OrderService | listMyOrders | response | items[].payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | listMyOrders | response | items[].payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | listMyOrders | response | items[].payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | listMyOrders | response | items[].payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | items[].payments[].recordedAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | items[].principalId | string (uuid)
OrderService | listMyOrders | response | items[].workstationId | string (uuid)
OrderService | listMyOrders | response | items[].shiftId | string (uuid) |  | (nullable)
OrderService | listMyOrders | response | items[].subjectId | string (uuid) |  | (nullable)
OrderService | listMyOrders | response | items[].holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | listMyOrders | response | items[].heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | listMyOrders | response | items[].createdAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].recordedAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].syncedAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | nextCursor | string
OrderService | listMyOrders | response | hasMore | boolean | yes
OrderService | listMyOrders | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
OrderService | listMyOrders | param (query) | since | string (date) |  | Only orders whose createdAt falls on or after this date.
OrderService | listMyOrders | param (query) | pageSize | integer
OrderService | listMyOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listMyPaymentIssues | response | items | array of DunningCase | yes
OrderService | listMyPaymentIssues | response | items[].id | string (uuid) | yes
OrderService | listMyPaymentIssues | response | items[].subjectId | string (uuid)
OrderService | listMyPaymentIssues | response | items[].orderId | string |  | The order whose renewal failed.
OrderService | listMyPaymentIssues | response | items[].amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyPaymentIssues | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyPaymentIssues | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyPaymentIssues | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyPaymentIssues | response | items[].state | DunningState: enum (scheduled, inProgress, exhausted, recovered, resolvedManually) | yes | BL-100.
OrderService | listMyPaymentIssues | response | items[].declineClass | object |  | From the most recent attempt.
OrderService | listMyPaymentIssues | response | items[].attemptsMade | integer | yes
OrderService | listMyPaymentIssues | response | items[].nextAttemptAt | string (date-time) |  | Null where the case has ended or the decline is hard. (nullable)
OrderService | listMyPaymentIssues | response | items[].firstFailedAt | string (date-time) | yes
OrderService | listMyPaymentIssues | response | items[].resolvedAt | string (date-time) |  | (nullable)
OrderService | listMyPaymentIssues | response | items[].resolution | enum (paidByOtherMeans, cardReplaced, writeOff, cancelledByGuest, None) |  | (nullable)
OrderService | listMyPaymentIssues | response | items[].resolutionNote | string |  | What resolveDunningCase was told, which had nowhere to land until now. (max length 500; nullable)
OrderService | listMyPaymentIssues | response | items[].resolvedByPrincipalId | string (uuid) |  | Who closed it. (read-only; nullable)
OrderService | listMyPaymentIssues | response | items[].scopePath | string |  | The partition key (ADR-0005).
OrderService | listMyPaymentIssues | response | nextCursor | string
OrderService | listMyPaymentIssues | response | hasMore | boolean | yes
OrderService | listMyPaymentIssues | param (query) | pageSize | integer
OrderService | listMyPaymentIssues | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listMyTableReservations | response | items | array of MyTableBooking | yes
FnbService | listMyTableReservations | response | items[].kind | enum (reservation, waitlist) | yes
FnbService | listMyTableReservations | response | items[].outletId | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].outletName | string
FnbService | listMyTableReservations | response | items[].reservation | object |  | (nullable)
FnbService | listMyTableReservations | response | items[].reservation.id | string (uuid) |  | (read-only)
FnbService | listMyTableReservations | response | items[].reservation.outletId | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].reservation.subjectId | string (uuid) |  | (nullable)
FnbService | listMyTableReservations | response | items[].reservation.guestName | string
FnbService | listMyTableReservations | response | items[].reservation.contactPoint | string
FnbService | listMyTableReservations | response | items[].reservation.partySize | integer | yes | (min 1)
FnbService | listMyTableReservations | response | items[].reservation.startsAt | string (date-time) | yes
FnbService | listMyTableReservations | response | items[].reservation.durationMinutes | integer |  | How long the cover is held.
FnbService | listMyTableReservations | response | items[].reservation.tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | listMyTableReservations | response | items[].reservation.status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | listMyTableReservations | response | items[].reservation.groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | listMyTableReservations | response | items[].reservation.notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | listMyTableReservations | response | items[].reservation.seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | listMyTableReservations | response | items[].reservation.occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | listMyTableReservations | response | items[].reservation.takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.actualPartySize | integer |  | (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.createdAt | string (date-time) |  | (read-only)
FnbService | listMyTableReservations | response | items[].waitlistEntry | object |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.id | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.outletId | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.subjectId | string (uuid) |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.partySize | integer | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.quotedWaitMinutes | integer |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes | (read-only)
FnbService | listMyTableReservations | response | items[].waitlistEntry.notifiedAt | string (date-time) |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | listMyTableReservations | response | items[].waitlistEntry.syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | listMyTableReservations | response | nextCursor | string
FnbService | listMyTableReservations | response | hasMore | boolean | yes
FnbService | listMyTableReservations | param (query) | include | enum (reservations, waitlist) |  | Which kinds to list.
FnbService | listMyTableReservations | param (query) | upcomingOnly | boolean |  | Only bookings from today and live waitlist places (waiting, notified).
FnbService | listMyTableReservations | param (query) | pageSize | integer
FnbService | listMyTableReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listOperationalRequirements | response | items | array of AiOperationalRequirement | yes
AiService | listOperationalRequirements | response | items[].id | string (uuid) |  | (read-only)
AiService | listOperationalRequirements | response | items[].versionId | string (uuid) | yes
AiService | listOperationalRequirements | response | items[].kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …) | yes
AiService | listOperationalRequirements | response | items[].targetContract | string |  | The owning module that applies it: workforce, fnb, inventory, resources, access.
AiService | listOperationalRequirements | response | items[].subjectRef | string |  | A role, outlet, gate, item or resource type. (nullable)
AiService | listOperationalRequirements | response | items[].periodStart | string (date-time) | yes
AiService | listOperationalRequirements | response | items[].periodEnd | string (date-time)
AiService | listOperationalRequirements | response | items[].quantity | number | yes
AiService | listOperationalRequirements | response | items[].quantityP90 | number |  | The requirement at the forecast's 90th percentile, for planning to the busy case. (nullable)
AiService | listOperationalRequirements | response | items[].unit | string
AiService | listOperationalRequirements | response | items[].productivityStandard | object |  | The standard used, e.g. (nullable)
AiService | listOperationalRequirements | response | items[].status | enum (issued, accepted, modified, rejected, handedOver, expired) |  | (read-only)
AiService | listOperationalRequirements | response | items[].decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listOperationalRequirements | response | items[].decidedAt | string (date-time) |  | (read-only; nullable)
AiService | listOperationalRequirements | response | items[].decisionNote | string |  | (nullable)
AiService | listOperationalRequirements | response | items[].handoverRef | string |  | The owning module's record once handed over. (read-only; nullable)
AiService | listOperationalRequirements | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listOperationalRequirements | response | nextCursor | string
AiService | listOperationalRequirements | response | hasMore | boolean | yes
AiService | listOperationalRequirements | param (query) | kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …)
AiService | listOperationalRequirements | param (query) | status | enum (issued, accepted, modified, rejected, handedOver, expired)
AiService | listOperationalRequirements | param (query) | from | string (date-time)
AiService | listOperationalRequirements | param (query) | to | string (date-time)
AiService | listOperationalRequirements | param (query) | versionId | string (uuid)
AiService | listOperationalRequirements | param (query) | pageSize | integer
AiService | listOperationalRequirements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOrderRefunds | response | items | array of Refund | yes
OrderService | listOrderRefunds | response | items[].id | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].orderId | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | listOrderRefunds | response | items[].fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | listOrderRefunds | response | items[].taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | listOrderRefunds | response | items[].settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | listOrderRefunds | response | items[].fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | listOrderRefunds | response | items[].fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].tenderCurrency | string |  | A refund goes back in the currency the guest paid (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | listOrderRefunds | response | items[].tenderAmount | object |  | The refund in tenderCurrency, at that currency's own scale (CHG-FIN-001), its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192). (read-only)
OrderService | listOrderRefunds | response | items[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrderRefunds | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | listOrderRefunds | response | items[].lines | array of object |  | What the refund took from each order line (ADAM CR-208, option A; CHG-R10ORD-014): child rows, orders.refund_line, one per line refunded, written by createRefund. (read-only)
OrderService | listOrderRefunds | response | items[].lines[].orderLineId | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].lines[].refundedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrderRefunds | response | items[].lines[].appliedPercentage | number |  | The time band of this line's own performance (ADAM CR-208). (nullable)
OrderService | listOrderRefunds | response | items[].payments | array of object |  | What the refund took from each payment (ADAM CR-208, option A; CHG-R10ORD-014): child rows, orders.refund_payment (the decision's refund_allocation; naming-and-style bans allocation in DDL), one per… (read-only)
OrderService | listOrderRefunds | response | items[].payments[].paymentId | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].payments[].refundedAmount | object | yes | In the base currency, for the ledger.
OrderService | listOrderRefunds | response | items[].payments[].tenderAmount | object |  | In the payment's tender currency (Payment.tenderCurrency), at that currency's scale; null where the payment was in the base currency. (nullable)
OrderService | listOrderRefunds | response | items[].status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | listOrderRefunds | response | items[].reason | string
OrderService | listOrderRefunds | response | items[].requestedByPrincipalId | string (uuid)
OrderService | listOrderRefunds | response | items[].secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | listOrderRefunds | response | items[].approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | listOrderRefunds | response | items[].ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | listOrderRefunds | response | items[].gatewayReference | string |  | (nullable)
OrderService | listOrderRefunds | response | items[].createdAt | string (date-time) | yes
OrderService | listOrderRefunds | response | items[].completedAt | string (date-time) |  | (nullable)
OrderService | listOrderRefunds | response | nextCursor | string
OrderService | listOrderRefunds | response | hasMore | boolean | yes
OrderService | listOrderRefunds | param (path) | orderId | string (uuid) | yes
OrderService | listOrderRefunds | param (query) | pageSize | integer
OrderService | listOrderRefunds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOrders | response | items | array of OrderSummary | yes
OrderService | listOrders | response | items[].id | string (uuid) | yes
OrderService | listOrders | response | items[].orderNumber | string | yes
OrderService | listOrders | response | items[].status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | listOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrders | response | items[].refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listOrders | response | items[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrders | response | items[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrders | response | items[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrders | response | items[].channel | object |  | The same vocabulary as Order.channel, which this projects.
OrderService | listOrders | response | items[].lineCount | integer
OrderService | listOrders | response | items[].principalId | string (uuid) |  | The cashier who raised it — what the held-orders list shows.
OrderService | listOrders | response | items[].holdLabel | string |  | As Order.holdLabel. (nullable)
OrderService | listOrders | response | items[].heldUntil | string (date-time) |  | As Order.heldUntil, so a held-orders list can warn about the ones about to lapse. (nullable)
OrderService | listOrders | response | items[].createdAt | string (date-time) | yes
OrderService | listOrders | response | nextCursor | string
OrderService | listOrders | response | hasMore | boolean | yes
OrderService | listOrders | param (query) | venueId | string (uuid) |  | Exact match.
OrderService | listOrders | param (query) | principalId | string (uuid) |  | The cashier who raised the order.
OrderService | listOrders | param (query) | shiftId | string (uuid) |  | Exact match on the shift the order was taken in.
OrderService | listOrders | param (query) | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …)
OrderService | listOrders | param (query) | createdFrom | string (date-time) |  | Only orders whose createdAt is at or after this instant.
OrderService | listOrders | param (query) | createdTo | string (date-time) |  | Only orders whose createdAt is before this instant.
OrderService | listOrders | param (query) | workstationId | string (uuid) |  | Exact match on the till the order was taken on (Order.workstationId).
OrderService | listOrders | param (query) | subjectId | string (uuid) |  | Exact match on the guest the order belongs to (Order.subjectId).
OrderService | listOrders | param (query) | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) |  | Only orders with at least one payment in this tender (Payment.tender), so a split order matches each tender it used.
OrderService | listOrders | param (query) | pageSize | integer
OrderService | listOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listOrgUnits | response | items | array of OrgUnit | yes
TenancyService | listOrgUnits | response | items[].id | string (uuid) | yes
TenancyService | listOrgUnits | response | items[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | listOrgUnits | response | items[].parentId | string (uuid) |  | (nullable)
TenancyService | listOrgUnits | response | items[].path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | listOrgUnits | response | items[].code | string | yes | (max length 64)
TenancyService | listOrgUnits | response | items[].name | string | yes | (max length 200)
TenancyService | listOrgUnits | response | items[].isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | listOrgUnits | response | items[].childCount | integer |  | (min 0)
TenancyService | listOrgUnits | response | nextCursor | string
TenancyService | listOrgUnits | response | hasMore | boolean | yes
TenancyService | listOrgUnits | param (query) | under | string |  | Return descendants of this path only.
TenancyService | listOrgUnits | param (query) | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet)
TenancyService | listOrgUnits | param (query) | includeInactive | boolean
TenancyService | listOrgUnits | param (query) | pageSize | integer
TenancyService | listOrgUnits | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOwnGroupBookings | response | items | array of GroupBooking | yes
OrderService | listOwnGroupBookings | response | items[].id | string (uuid) | yes
OrderService | listOwnGroupBookings | response | items[].kind | enum (general, school, corporate, party) |  | (default general)
OrderService | listOwnGroupBookings | response | items[].packageProductId | string |  | The school-trip format or party package. (nullable)
OrderService | listOwnGroupBookings | response | items[].yearGroup | string |  | (max length 40; nullable)
OrderService | listOwnGroupBookings | response | items[].accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | listOwnGroupBookings | response | items[].celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | listOwnGroupBookings | response | items[].celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | listOwnGroupBookings | response | items[].allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | listOwnGroupBookings | response | items[].finalHeadcountDueBy | string (date-time) |  | (nullable)
OrderService | listOwnGroupBookings | response | items[].quoteSentAt | string (date-time) |  | (read-only; nullable)
OrderService | listOwnGroupBookings | response | items[].riskAssessmentSentAt | string (date-time) |  | (read-only; nullable)
OrderService | listOwnGroupBookings | response | items[].preferredDate | string (date) |  | The date the guest asked for on requestGroupBooking — what its 409 dateUnavailable is checked against. (nullable)
OrderService | listOwnGroupBookings | response | items[].performanceId | string (uuid) |  | The session, for a timed or session package (DEC-121, Chinmay, 2 October 2026: a date and, for session products, a session; R8 blocker ORDERS-MONEY-C41, CHG-R8MIG-017): a catalogue.performance on pre… (nullable)
OrderService | listOwnGroupBookings | response | items[].orderId | string (uuid) | yes
OrderService | listOwnGroupBookings | response | items[].leaderSubjectId | string (uuid) | yes
OrderService | listOwnGroupBookings | response | items[].organisationName | string |  | (nullable)
OrderService | listOwnGroupBookings | response | items[].expectedSize | integer | yes
OrderService | listOwnGroupBookings | response | items[].confirmedSize | integer |  | (nullable)
OrderService | listOwnGroupBookings | response | items[].minimumSize | integer |  | Below which the group rate does not apply. (nullable)
OrderService | listOwnGroupBookings | response | items[].attendeeCaptureRequired | boolean |  | Whether names are needed before admission. (default False)
OrderService | listOwnGroupBookings | response | items[].attendeeCaptureDueBy | string (date-time) |  | (nullable)
OrderService | listOwnGroupBookings | response | items[].status | enum (provisional, confirmed, namesPending, complete, cancelled) | yes
OrderService | listOwnGroupBookings | response | items[].version | integer |  | The row's version, its ETag (accepted 26 October 2026, Chinmay, ADAM CR-257 option A): 1 on create and bumped on every write; getGroupBooking and updateGroupBooking send it as ETag, and updateGroupBo… (min 1; default 1; read-only)
OrderService | listOwnGroupBookings | response | nextCursor | string
OrderService | listOwnGroupBookings | response | hasMore | boolean | yes
OrderService | listOwnGroupBookings | param (query) | status | enum (provisional, confirmed, namesPending, complete, cancelled) |  | Exact match.
OrderService | listOwnGroupBookings | param (query) | pageSize | integer
OrderService | listOwnGroupBookings | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listOwnPlatformStaffGrants | response | items | array of PlatformStaffGrant | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].id | string (uuid) | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].operatorPrincipalId | string (uuid) | yes | The platform operator, from the Control Plane token (its subject). (read-only)
IdentityService | listOwnPlatformStaffGrants | response | items[].operatorDisplayName | string |  | (read-only)
IdentityService | listOwnPlatformStaffGrants | response | items[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].reason | string | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].ticketRef | string |  | (nullable)
IdentityService | listOwnPlatformStaffGrants | response | items[].openedAt | string (date-time) | yes | (read-only)
IdentityService | listOwnPlatformStaffGrants | response | items[].expiresAt | string (date-time) | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].scopePath | string |  | The tenant root. (read-only)
IdentityService | listOwnPlatformStaffGrants | response | nextCursor | string
IdentityService | listOwnPlatformStaffGrants | response | hasMore | boolean | yes
IdentityService | listOwnPlatformStaffGrants | param (header) | X-Tenant-Id | string (uuid) |  | Which tenant a call acts in, where one cell holds many tenant databases (ADR-0038; R8 blocker fix, APPROVALS-TENANCY-C44).
IdentityService | listOwnPlatformStaffGrants | param (query) | activeOnly | boolean |  | True returns only grants whose window is open now.
IdentityService | listOwnPlatformStaffGrants | param (query) | pageSize | integer
IdentityService | listOwnPlatformStaffGrants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOwnRefundRequests | response | items | array of Refund | yes
OrderService | listOwnRefundRequests | response | items[].id | string (uuid) | yes
OrderService | listOwnRefundRequests | response | items[].orderId | string (uuid) | yes
OrderService | listOwnRefundRequests | response | items[].batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | listOwnRefundRequests | response | items[].fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | listOwnRefundRequests | response | items[].taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | listOwnRefundRequests | response | items[].settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | listOwnRefundRequests | response | items[].fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | listOwnRefundRequests | response | items[].fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOwnRefundRequests | response | items[].fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOwnRefundRequests | response | items[].fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOwnRefundRequests | response | items[].tenderCurrency | string |  | A refund goes back in the currency the guest paid (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | listOwnRefundRequests | response | items[].tenderAmount | object |  | The refund in tenderCurrency, at that currency's own scale (CHG-FIN-001), its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192). (read-only)
OrderService | listOwnRefundRequests | response | items[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOwnRefundRequests | response | items[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOwnRefundRequests | response | items[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOwnRefundRequests | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOwnRefundRequests | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOwnRefundRequests | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOwnRefundRequests | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOwnRefundRequests | response | items[].appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | listOwnRefundRequests | response | items[].lines | array of object |  | What the refund took from each order line (ADAM CR-208, option A; CHG-R10ORD-014): child rows, orders.refund_line, one per line refunded, written by createRefund. (read-only)
OrderService | listOwnRefundRequests | response | items[].lines[].orderLineId | string (uuid) | yes
OrderService | listOwnRefundRequests | response | items[].lines[].refundedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOwnRefundRequests | response | items[].lines[].appliedPercentage | number |  | The time band of this line's own performance (ADAM CR-208). (nullable)
OrderService | listOwnRefundRequests | response | items[].payments | array of object |  | What the refund took from each payment (ADAM CR-208, option A; CHG-R10ORD-014): child rows, orders.refund_payment (the decision's refund_allocation; naming-and-style bans allocation in DDL), one per… (read-only)
OrderService | listOwnRefundRequests | response | items[].payments[].paymentId | string (uuid) | yes
OrderService | listOwnRefundRequests | response | items[].payments[].refundedAmount | object | yes | In the base currency, for the ledger.
OrderService | listOwnRefundRequests | response | items[].payments[].tenderAmount | object |  | In the payment's tender currency (Payment.tenderCurrency), at that currency's scale; null where the payment was in the base currency. (nullable)
OrderService | listOwnRefundRequests | response | items[].status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | listOwnRefundRequests | response | items[].reason | string
OrderService | listOwnRefundRequests | response | items[].requestedByPrincipalId | string (uuid)
OrderService | listOwnRefundRequests | response | items[].secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | listOwnRefundRequests | response | items[].approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | listOwnRefundRequests | response | items[].ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | listOwnRefundRequests | response | items[].gatewayReference | string |  | (nullable)
OrderService | listOwnRefundRequests | response | items[].createdAt | string (date-time) | yes
OrderService | listOwnRefundRequests | response | items[].completedAt | string (date-time) |  | (nullable)
OrderService | listOwnRefundRequests | response | nextCursor | string
OrderService | listOwnRefundRequests | response | hasMore | boolean | yes
OrderService | listOwnRefundRequests | param (query) | orderId | string (uuid) |  | Only the refunds on this order.
OrderService | listOwnRefundRequests | param (query) | pageSize | integer
OrderService | listOwnRefundRequests | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOwnResaleListings | response | items | array of ResaleListing | yes
OrderService | listOwnResaleListings | response | items[].id | string (uuid) | yes | (read-only)
OrderService | listOwnResaleListings | response | items[].entitlementId | string (uuid) | yes
OrderService | listOwnResaleListings | response | items[].sellerSubjectId | string (uuid) | yes
OrderService | listOwnResaleListings | response | items[].askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOwnResaleListings | response | items[].askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOwnResaleListings | response | items[].askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOwnResaleListings | response | items[].askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOwnResaleListings | response | items[].priceCapPercent | number |  | A ceiling as a percentage of face value, because uncapped resale is a venue watching its own tickets sold at four times the price with its name on them. (read-only; nullable)
OrderService | listOwnResaleListings | response | items[].sellerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | listOwnResaleListings | response | items[].buyerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | listOwnResaleListings | response | items[].status | enum (pendingReview, listed, reserved, sold, withdrawn, expired, rejected) | yes | pendingReview and rejected added 29 September (DM5): a listing the marketplace's moderationMode sends to review waits there until approveListingModeration lists or rejects it. (read-only)
OrderService | listOwnResaleListings | response | items[].listedAt | string (date-time) |  | (read-only)
OrderService | listOwnResaleListings | response | items[].soldToSubjectId | string (uuid) |  | (read-only; nullable)
OrderService | listOwnResaleListings | response | items[].reviewReasons | array of enum (highResalePrice, unusualDiscount, highValueTicket, vipTicket, sellerRisk, newSeller, multipleListings, identityIssue, …) |  | Why the listing was sent to review (DM5, 29 September). (read-only)
OrderService | listOwnResaleListings | response | items[].moderatedByPrincipalId | string (uuid) |  | (read-only; nullable)
OrderService | listOwnResaleListings | response | items[].moderatedAt | string (date-time) |  | (read-only; nullable)
OrderService | listOwnResaleListings | response | items[].moderationReason | string |  | (max length 1000; read-only; nullable)
OrderService | listOwnResaleListings | response | items[].payoutStatus | enum (pending, held, paid, failed) |  | The seller is paid after the buyer is admitted, not after they pay. (read-only)
OrderService | listOwnResaleListings | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | listOwnResaleListings | response | nextCursor | string
OrderService | listOwnResaleListings | response | hasMore | boolean | yes
OrderService | listOwnResaleListings | param (query) | entitlementId | string (uuid) |  | Only the listings of this entitlement.
OrderService | listOwnResaleListings | param (query) | status | enum (pendingReview, listed, reserved, sold, withdrawn, expired, rejected) |  | Exact match.
OrderService | listOwnResaleListings | param (query) | pageSize | integer
OrderService | listOwnResaleListings | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listParkingFacilities | response | items | array of ParkingFacility | yes
AccessService | listParkingFacilities | response | items[].id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | listParkingFacilities | response | items[].name | string | yes
AccessService | listParkingFacilities | response | items[].venueId | string (uuid) | yes
AccessService | listParkingFacilities | response | items[].mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | listParkingFacilities | response | items[].capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | listParkingFacilities | response | items[].takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | listParkingFacilities | response | items[].vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | listParkingFacilities | response | items[].vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | listParkingFacilities | response | items[].pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | listParkingFacilities | response | items[].isActive | boolean
AccessService | listParkingFacilities | response | items[].productVariantId | string (uuid) |  | The catalogue variant sold for parking here (4 October 2026, CHG-FXC-010; GST-027, WEB-041): what addCartLine sells when a guest buys parking at this car park. (nullable)
AccessService | listParkingFacilities | response | nextCursor | string
AccessService | listParkingFacilities | response | hasMore | boolean | yes
AccessService | listParkingFacilities | param (query) | venueId | string (uuid) |  | Required for a guest caller; optional for staff, where it narrows the list.
AccessService | listParkingFacilities | param (query) | pageSize | integer
AccessService | listParkingFacilities | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listParkingFacilities | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
OrderService | listPaymentTokens | response | items | array of PaymentToken | yes
OrderService | listPaymentTokens | response | items[].id | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].subjectId | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].providerId | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].token | string (password) | yes | Write-only, never returned.
OrderService | listPaymentTokens | response | items[].method | string
OrderService | listPaymentTokens | response | items[].maskedIdentifier | string |  | What a guest sees — the last four digits, the card brand.
OrderService | listPaymentTokens | response | items[].expiresAt | string (date) |  | (nullable)
OrderService | listPaymentTokens | response | items[].revokedAt | string (date-time) |  | When the guest removed it (revokePaymentToken); a removed token is never returned or charged (CHG-R8MIG-022). (read-only; nullable)
OrderService | listPaymentTokens | response | items[].isDefault | boolean | yes
OrderService | listPaymentTokens | response | items[].consentPurposeId | string (uuid) |  | Storing a card for future use is a purpose a guest consents to, separate from the payment they are making now. (nullable)
OrderService | listPaymentTokens | response | nextCursor | string
OrderService | listPaymentTokens | response | hasMore | boolean | yes
OrderService | listPaymentTokens | param (query) | subjectId | string (uuid) |  | The guest whose saved methods a staff caller reads (ADAM CR-099, option 1; CHG-R10ORD-016).
OrderService | listPaymentTokens | param (query) | pageSize | integer
OrderService | listPaymentTokens | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPerformances | response | items | array of Performance | yes
CatalogueService | listPerformances | response | items[].id | string (uuid) | yes
CatalogueService | listPerformances | response | items[].eventId | string (uuid) | yes
CatalogueService | listPerformances | response | items[].startsAt | string (date-time) | yes
CatalogueService | listPerformances | response | items[].endsAt | string (date-time) | yes
CatalogueService | listPerformances | response | items[].approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | listPerformances | response | items[].requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | listPerformances | response | items[].status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | listPerformances | response | items[].admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | listPerformances | response | items[].seatMapId | string (uuid) |  | (nullable)
CatalogueService | listPerformances | response | items[].language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | listPerformances | response | items[].format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | listPerformances | response | items[].minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | listPerformances | response | nextCursor | string
CatalogueService | listPerformances | response | hasMore | boolean | yes
CatalogueService | listPerformances | param (path) | eventId | string (uuid) | yes
CatalogueService | listPerformances | param (query) | from | string (date-time) |  | Only performances whose startsAt is at or after this instant.
CatalogueService | listPerformances | param (query) | to | string (date-time) |  | Only performances whose startsAt is before this instant.
CatalogueService | listPerformances | param (query) | categoryId | string (uuid) |  | Only performances of products in this product category (a product in several categories matches each), the calendar's category filter (17 September minutes M17-03, added 30 September).
CatalogueService | listPerformances | param (query) | language | string |  | Only performances given in this language, e.g.
CatalogueService | listPerformances | param (query) | pageSize | integer
CatalogueService | listPerformances | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPerformances | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
WhiteLabelService | listPolicies | param (query) | includeHistory | boolean |  | Every version rather than the current one per kind (audit R163).
WhiteLabelService | listPolicies | param (query) | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) |  | Only this policy kind.
IdentityService | listPrincipals | response | items | array of Principal | yes
IdentityService | listPrincipals | response | items[].id | string (uuid) | yes
IdentityService | listPrincipals | response | items[].username | string | yes
IdentityService | listPrincipals | response | items[].displayName | string | yes
IdentityService | listPrincipals | response | items[].isActive | boolean | yes
IdentityService | listPrincipals | response | items[].validFrom | string (date-time) |  | (nullable)
IdentityService | listPrincipals | response | items[].validTo | string (date-time) |  | Past this, resolution returns DENY regardless of grants. (nullable)
IdentityService | listPrincipals | response | items[].primaryRoleId | string (uuid) |  | Determines the landing screen when the principal holds several roles and picks one at login. (nullable)
IdentityService | listPrincipals | response | items[].roles | array of RoleSummary |  | Read with the principal, never stored on it (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): one item per role the principal holds through a live grant, an identity.delegated_access row with this…
IdentityService | listPrincipals | response | items[].roles[].id | string (uuid) | yes
IdentityService | listPrincipals | response | items[].roles[].code | string | yes
IdentityService | listPrincipals | response | items[].roles[].name | string | yes
IdentityService | listPrincipals | response | items[].roles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | listPrincipals | response | items[].roles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | listPrincipals | response | items[].roles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | listPrincipals | response | items[].lastLoginAt | string (date-time) |  | (nullable)
IdentityService | listPrincipals | response | items[].mustChangeCredential | boolean |  | The principal must replace their credential before the session is usable (14 October 2026, CHG-CRD-001, ADAM CR-078; createPrincipal took it and nothing stored it). (default True)
IdentityService | listPrincipals | response | items[].ssoProviderId | string (uuid) |  | Set when single sign-on provisioned this principal (completeSsoAuthorization, from the tenant's identity.sso_provider; 14 October 2026, CHG-CRD-001). (read-only; nullable)
IdentityService | listPrincipals | response | nextCursor | string
IdentityService | listPrincipals | response | hasMore | boolean | yes
IdentityService | listPrincipals | param (query) | scopePath | string |  | Principals whose home scope (identity.principal.home_scope_id) is this node or any node beneath it — a prefix match on the materialised path, the way scope_path is compared everywhere (shared/common.…
IdentityService | listPrincipals | param (query) | isActive | boolean |  | Exact match on Principal.isActive.
IdentityService | listPrincipals | param (query) | pageSize | integer
IdentityService | listPrincipals | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProductCategories | param (query) | kind | enum (category, brand, collection, season, department) |  | Only categories of this kind (category, brand, collection, season or department).
CatalogueService | listProductCategories | param (query) | venueId | string (uuid) |  | Whose venue to read, for a caller with no venue (R8 blocker fix, GPS-C01 and WHITE-C05).
CatalogueService | listProductCategories | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | listProductStartTimes | response | items | array of ProductStartTime | yes
VenueOpsService | listProductStartTimes | response | items[].startsAt | string (date-time) | yes
VenueOpsService | listProductStartTimes | response | items[].endsAt | string (date-time) | yes | startsAt plus the variant's durationMinutes; the cart line's bookedWindow.endsAt.
VenueOpsService | listProductStartTimes | response | items[].freeCount | integer | yes | Resources of the room type free for the whole window. (min 1)
VenueOpsService | listProductStartTimes | response | items[].maxCapacity | integer |  | The most people one free room of the type holds in this window (the largest capacity among the free resources), so the guest sees before choosing whether the party fits; the cart line's attendees abo… (min 1; nullable)
VenueOpsService | listProductStartTimes | response | nextCursor | string
VenueOpsService | listProductStartTimes | response | hasMore | boolean | yes
VenueOpsService | listProductStartTimes | param (query) | productId | string (uuid) | yes | A catalogue.Product with requiresTimeWindow true, else 422.
VenueOpsService | listProductStartTimes | param (query) | variantId | string (uuid) | yes | The length variant; its length value's durationMinutes is the window.
VenueOpsService | listProductStartTimes | param (query) | date | string (date) | yes | The venue-local date.
VenueOpsService | listProductStartTimes | param (query) | stepMinutes | enum (15, 30, 60) |  | Spacing of the offered start times.
VenueOpsService | listProductStartTimes | param (query) | pageSize | integer
VenueOpsService | listProductStartTimes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listProductStartTimes | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | listProductVariants | response | items | array of ProductVariant | yes
CatalogueService | listProductVariants | response | items[].id | string (uuid) | yes
CatalogueService | listProductVariants | response | items[].listPrice | Money |  | The list price on the caller's channel now, resolved on read from the price lists (listProductVariants; R8 blocker cause GPS-C27, CHG-R8SPN-028). (read-only; nullable)
CatalogueService | listProductVariants | response | items[].referencePrice | Money |  | The price a saving is measured against (accepted 26 October 2026, Chinmay, ADAM CR-253 option C), set by the back office on the variant (updateProductVariant). (nullable)
CatalogueService | listProductVariants | response | items[].savingPercent | integer |  | Computed by the server, never in the browser (ADAM CR-253): with a referencePrice and a listPrice below it, the whole percent the list price saves, floor((referencePrice - listPrice) / referencePrice… (read-only; nullable)
CatalogueService | listProductVariants | response | items[].productId | string (uuid) | yes
CatalogueService | listProductVariants | response | items[].sku | string | yes
CatalogueService | listProductVariants | response | items[].axisValues | object | yes
CatalogueService | listProductVariants | response | items[].name | string |  | Taken from their variant tables, 20 September. (max length 150; nullable)
CatalogueService | listProductVariants | response | items[].barcode | string |  | Taken from their variant tables, 20 September. (max length 64; nullable)
CatalogueService | listProductVariants | response | items[].isDefault | boolean |  | Taken from their variant tables. (default False)
CatalogueService | listProductVariants | response | items[].isActive | boolean | yes | False when retired.
CatalogueService | listProductVariants | response | items[].description | object |  | Who this ticket type is for and what it includes, shown behind the (i) on each Adult, Child, Senior or Infant row (decided 29 September, 23SEP-6). (nullable)
CatalogueService | listProductVariants | response | nextCursor | string
CatalogueService | listProductVariants | response | hasMore | boolean | yes
CatalogueService | listProductVariants | param (path) | productId | string (uuid) | yes
CatalogueService | listProductVariants | param (query) | channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) |  | The channel listPrice is priced for (GPS-C27, CHG-R8SPN-028).
CatalogueService | listProductVariants | param (query) | pageSize | integer
CatalogueService | listProductVariants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProductVariants | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | listProducts | response | items | array of Product | yes
CatalogueService | listProducts | response | items[].id | string (uuid) | yes
CatalogueService | listProducts | response | items[].code | string | yes | (max length 64)
CatalogueService | listProducts | response | items[].familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | listProducts | response | items[].name | string | yes | (max length 200)
CatalogueService | listProducts | response | items[].description | string
CatalogueService | listProducts | response | items[].nameLocalised | object |  | The product's name in each of the tenant's enabled languages (6 October 2026, CHG-R4-011; the tenant's languages, not the venue's: CHG-R8PRD-009, ADAM CR-213), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | listProducts | response | items[].descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | listProducts | response | items[].kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | listProducts | response | items[].venueId | string (uuid) | yes
CatalogueService | listProducts | response | items[].scopePath | string | yes
CatalogueService | listProducts | response | items[].createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | listProducts | response | items[].approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | listProducts | response | items[].responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | listProducts | response | items[].onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | listProducts | response | items[].onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | listProducts | response | items[].validTo | string (date-time) |  | The last moment the product's entitlements are valid; null means the same as onSaleTo (ADAM CR-167 as the lead ruled it, 26 October 2026; CHG-R10OPN-003). (nullable)
CatalogueService | listProducts | response | items[].categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | listProducts | response | items[].lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | listProducts | response | items[].isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | listProducts | response | items[].isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | listProducts | response | items[].hasVariants | boolean | yes
CatalogueService | listProducts | response | items[].variantCount | integer
CatalogueService | listProducts | response | items[].segmentTags | array of string |  | 7.3.5.
CatalogueService | listProducts | response | items[].codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | listProducts | response | items[].channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | listProducts | response | items[].entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | listProducts | response | items[].blockedOffline | boolean |  | True for seated and retail.
CatalogueService | listProducts | response | items[].dataMaskValues | object |  | Custom fields.
CatalogueService | listProducts | response | items[].guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | listProducts | response | items[].notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | listProducts | response | items[].salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | listProducts | response | items[].salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | listProducts | response | items[].salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | listProducts | response | items[].salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | listProducts | response | items[].bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | listProducts | response | items[].displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | listProducts | response | items[].displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | listProducts | response | items[].displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | listProducts | response | items[].displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | listProducts | response | items[].media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | listProducts | response | items[].media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | listProducts | response | items[].media[].kind | enum (image, video) | yes
CatalogueService | listProducts | response | items[].media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | listProducts | response | items[].media[].displayOrder | integer |  | (default 100)
CatalogueService | listProducts | response | items[].media[].url | string (uri) |  | The asset's stable CDN address, for a guest card (ADAM CR-221, option A, decided 25 October 2026; CHG-R10CAT-014): the asset library's public address for the asset, set on guest-facing reads (searchC… (read-only; nullable)
CatalogueService | listProducts | response | items[].media[].thumbnailUrl | string (uri) |  | The asset library's thumbnail address for the asset, on the same reads and with the same rule as url (ADAM CR-221). (read-only; nullable)
CatalogueService | listProducts | response | items[].media[].altText | object |  | (nullable)
CatalogueService | listProducts | response | items[].consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | listProducts | response | items[].addOnProductIds | array of string (uuid) |  | The add-ons offered with this product, in display order (accepted 26 October 2026, Chinmay, ADAM CR-252 option A): each a kind: addOn product of the same venue (a coffee break, a working lunch, an AV…
CatalogueService | listProducts | response | items[].requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | listProducts | response | items[].productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | listProducts | response | items[].operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | listProducts | response | items[].businessUnitId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | listProducts | response | items[].attractionId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].siteId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].locationId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | listProducts | response | items[].marketCode | string |  | (max length 40; nullable)
CatalogueService | listProducts | response | items[].salesTerritory | string |  | (max length 100; nullable)
CatalogueService | listProducts | response | items[].eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | listProducts | response | items[].createdAt | string (date-time) | yes | When the product was created (ADAM CR-204, option A, decided 25 October 2026; CHG-R10CAT-007): catalogue.product.created_at, NOT NULL DEFAULT now(), set by the server and never by a request. (read-only)
CatalogueService | listProducts | response | items[].updatedAt | string (date-time) |  | When the product last changed (ADAM CR-204): set by updateProduct and by every product sub-resource PUT and bulk change that versions the product; null until the first change after creation. (read-only; nullable)
CatalogueService | listProducts | response | nextCursor | string
CatalogueService | listProducts | response | hasMore | boolean | yes
CatalogueService | listProducts | param (query) | venueId | string (uuid)
CatalogueService | listProducts | param (query) | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …)
CatalogueService | listProducts | param (query) | isSellable | boolean
CatalogueService | listProducts | param (query) | categoryId | string (uuid) |  | Only products filed under this category (Product.categoryId) or any category below it in the tree, so a tile for *Guided tours* also lists what sits under its subcategories.
CatalogueService | listProducts | param (query) | entitlementTemplateId | string (uuid) |  | Products using this template (client feedback of 6 October 2026, N32; CHG-R6-040): only products whose entitlementTemplateId is this one.
CatalogueService | listProducts | param (query) | segmentTag | string |  | Only products carrying this tag in segmentTags, or a tag below it (level matches level/beginner; level/beginner matches only itself).
CatalogueService | listProducts | param (query) | guidedAnswerIds | array of string (uuid) |  | Help me choose answers, as filters (decided 29 September, W4).
CatalogueService | listProducts | param (query) | pageSize | integer
CatalogueService | listProducts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProducts | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | listPromotions | response | items | array of Promotion or GuestPromotion | yes
CatalogueService | listPromotions | response | nextCursor | string
CatalogueService | listPromotions | response | hasMore | boolean | yes
CatalogueService | listPromotions | param (query) | venueId | string (uuid)
CatalogueService | listPromotions | param (query) | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended)
CatalogueService | listPromotions | param (query) | activeAt | string (date-time)
CatalogueService | listPromotions | param (query) | pageSize | integer
CatalogueService | listPromotions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPromotions | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
AiService | listProposedActions | param (query) | targetOperation | string |  | Only the proposals whose targetOperation is this, e.g.
AiService | listProposedActions | param (query) | mapId | string (uuid) |  | Only the proposals about this venue map (ProposedAction.mapId): BO-093 re-reads a map's walkway segments with their confidence after a reload (ADAM CR-207).
WhiteLabelService | listPublishedContentPages | response | items | array of PublishedContentPage | yes
WhiteLabelService | listPublishedContentPages | response | items[].id | string (uuid) | yes
WhiteLabelService | listPublishedContentPages | response | items[].slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | listPublishedContentPages | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listPublishedContentPages | response | items[].body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | listPublishedContentPages | response | items[].iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | listPublishedContentPages | response | items[].categoryCode | string |  | (nullable)
WhiteLabelService | listPublishedContentPages | response | items[].sortOrder | integer
WhiteLabelService | listPublishedContentPages | response | nextCursor | string
WhiteLabelService | listPublishedContentPages | response | hasMore | boolean | yes
WhiteLabelService | listPublishedContentPages | param (query) | categoryCode | string |  | Only live pages with this categoryCode.
WhiteLabelService | listPublishedContentPages | param (query) | slug | string |  | Only the live page with this slug.
WhiteLabelService | listPublishedContentPages | param (query) | pageSize | integer
WhiteLabelService | listPublishedContentPages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listPublishedPolicies | param (query) | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) |  | Only this policy kind, how the checkout reads the terms alone.
VenueOpsService | listQueues | response | items | array of Queue | yes
VenueOpsService | listQueues | response | items[].code | string | yes | (max length 64)
VenueOpsService | listQueues | response | items[].name | LocalisedText | yes
VenueOpsService | listQueues | response | items[].venueId | string (uuid) | yes
VenueOpsService | listQueues | response | items[].attractionProductId | string (uuid)
VenueOpsService | listQueues | response | items[].assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | listQueues | response | items[].accessPointId | string (uuid) |  | (nullable)
VenueOpsService | listQueues | response | items[].kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | listQueues | response | items[].operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | listQueues | response | items[].operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | listQueues | response | items[].operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | listQueues | response | items[].operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | listQueues | response | items[].operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | listQueues | response | items[].parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | listQueues | response | items[].loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | listQueues | response | items[].inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | listQueues | response | items[].notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | listQueues | response | items[].capacityPerCycle | integer | yes | (min 1)
VenueOpsService | listQueues | response | items[].cycleMinutes | number | yes | (min 0)
VenueOpsService | listQueues | response | items[].maxPartySize | integer |  | (default 6)
VenueOpsService | listQueues | response | items[].returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | listQueues | response | items[].heightRequirementCm | integer |  | (nullable)
VenueOpsService | listQueues | response | items[].fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | listQueues | response | items[].zone | string |  | (nullable)
VenueOpsService | listQueues | response | items[].fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | listQueues | response | items[].fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | listQueues | response | items[].fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | listQueues | response | items[].fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | listQueues | response | items[].fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | listQueues | response | items[].fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | listQueues | response | items[].fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | listQueues | response | items[].fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | listQueues | response | items[].id | string (uuid) | yes
VenueOpsService | listQueues | response | items[].status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | listQueues | response | items[].statusReason | string |  | (nullable)
VenueOpsService | listQueues | response | items[].waitingPartyCount | integer | yes
VenueOpsService | listQueues | response | items[].waitingGuestCount | integer
VenueOpsService | listQueues | response | items[].currentWaitMinutes | integer |  | (nullable)
VenueOpsService | listQueues | response | items[].waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | listQueues | response | items[].waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | listQueues | response | items[].manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | listQueues | response | items[].manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | listQueues | response | items[].expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | listQueues | response | nextCursor | string
VenueOpsService | listQueues | response | hasMore | boolean | yes
VenueOpsService | listQueues | param (query) | venueId | string (uuid)
VenueOpsService | listQueues | param (query) | openOnly | boolean
VenueOpsService | listQueues | param (query) | pageSize | integer
VenueOpsService | listQueues | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listQueues | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
ReportingService | listReports | response | items | array of ReportDefinition | yes
ReportingService | listReports | response | items[].name | string | yes | (max length 200)
ReportingService | listReports | response | items[].description | string |  | (max length 1000)
ReportingService | listReports | response | items[].category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | listReports | response | items[].dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | listReports | response | items[].columns | array of ReportColumn | yes | (min items 1)
ReportingService | listReports | response | items[].columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | listReports | response | items[].columns[].field | string | yes
ReportingService | listReports | response | items[].columns[].label | string
ReportingService | listReports | response | items[].columns[].aggregation | object |  | (default none)
ReportingService | listReports | response | items[].columns[].sortOrder | integer
ReportingService | listReports | response | items[].columns[].sortDirection | enum (asc, desc)
ReportingService | listReports | response | items[].columns[].format | string |  | (nullable)
ReportingService | listReports | response | items[].columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | listReports | response | items[].columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | listReports | response | items[].columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | listReports | response | items[].columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | listReports | response | items[].columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | listReports | response | items[].columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | listReports | response | items[].filters | array of ReportFilter
ReportingService | listReports | response | items[].filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | listReports | response | items[].filters[].field | string | yes
ReportingService | listReports | response | items[].filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | listReports | response | items[].filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | listReports | response | items[].filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | listReports | response | items[].filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | listReports | response | items[].groupBy | array of string
ReportingService | listReports | response | items[].parameters | array of ReportParameter
ReportingService | listReports | response | items[].parameters[].key | string | yes
ReportingService | listReports | response | items[].parameters[].label | string | yes
ReportingService | listReports | response | items[].parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | listReports | response | items[].parameters[].isRequired | boolean | yes
ReportingService | listReports | response | items[].parameters[].defaultValue | object |  | Open on purpose.
ReportingService | listReports | response | items[].requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | listReports | response | items[].maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | listReports | response | items[].id | string (uuid) | yes
ReportingService | listReports | response | items[].version | string | yes | The current version.
ReportingService | listReports | response | items[].isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | listReports | response | items[].isRetired | boolean | yes
ReportingService | listReports | response | items[].estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | listReports | response | items[].createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | listReports | response | items[].createdAt | string (date-time) | yes
ReportingService | listReports | response | items[].lastRunAt | string (date-time) |  | (nullable)
ReportingService | listReports | response | items[].scopePath | string |  | The partition key (ADR-0005).
ReportingService | listReports | response | nextCursor | string
ReportingService | listReports | response | hasMore | boolean | yes
ReportingService | listReports | param (query) | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …)
ReportingService | listReports | param (query) | search | string |  | Matched case-insensitively as a substring of the report definition's name or description; no wildcards.
ReportingService | listReports | param (query) | pageSize | integer
ReportingService | listReports | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listReservations | response | items | array of Reservation | yes
OrderService | listReservations | response | items[].id | string (uuid) | yes
OrderService | listReservations | response | items[].venueId | string (uuid) | yes
OrderService | listReservations | response | items[].subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | listReservations | response | items[].status | enum (held, converted, expired, cancelled) | yes
OrderService | listReservations | response | items[].lines | array of CreateOrderLine
OrderService | listReservations | response | items[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | listReservations | response | items[].lines[].variantId | string (uuid) | yes
OrderService | listReservations | response | items[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | listReservations | response | items[].lines[].performanceId | string (uuid)
OrderService | listReservations | response | items[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | listReservations | response | items[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | listReservations | response | items[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | listReservations | response | items[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | listReservations | response | items[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | listReservations | response | items[].lines[].quantity | integer | yes | (min 1)
OrderService | listReservations | response | items[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | listReservations | response | items[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | listReservations | response | items[].lines[].holderName | string |  | (nullable)
OrderService | listReservations | response | items[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | listReservations | response | items[].expiresAt | string (date-time) | yes
OrderService | listReservations | response | items[].createdAt | string (date-time) | yes
OrderService | listReservations | response | items[].convertedOrderId | string (uuid) |  | (nullable)
OrderService | listReservations | response | nextCursor | string
OrderService | listReservations | response | hasMore | boolean | yes
OrderService | listReservations | param (query) | status | enum (held, converted, expired, cancelled) |  | Exact match.
OrderService | listReservations | param (query) | expiringWithinMinutes | integer |  | Only held reservations whose expiresAt falls within this many minutes of now — the ones about to release capacity.
OrderService | listReservations | param (query) | pageSize | integer
OrderService | listReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | listRetailSales | response | items | array of RetailSale | yes
RetailService | listRetailSales | response | items[].id | string | yes
RetailService | listRetailSales | response | items[].receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | listRetailSales | response | items[].receiptBarcode | string |  | The barcode printed on the receipt (R8 blocker APPROVALS-TENANCY-C34): the receipt number as printed, encoded as a Code 128 barcode, stored so lookupRetailSale finds a sale by receiptBarcode with an… (max length 64; read-only)
RetailService | listRetailSales | response | items[].cashierPrincipalId | string (uuid) |  | The staff member who rang the sale up, from the session (null for a guest's own sale). (read-only; nullable)
RetailService | listRetailSales | response | items[].orderId | string | yes | The order in the Order & Payment context.
RetailService | listRetailSales | response | items[].outletId | string (uuid) | yes
RetailService | listRetailSales | response | items[].shiftId | string |  | (nullable)
RetailService | listRetailSales | response | items[].subjectId | string (uuid) |  | (nullable)
RetailService | listRetailSales | response | items[].lines | array of object | yes
RetailService | listRetailSales | response | items[].lines[].lineId | string
RetailService | listRetailSales | response | items[].lines[].merchandiseId | string (uuid)
RetailService | listRetailSales | response | items[].lines[].orderLineId | string (uuid) |  | The order line the amounts were copied from (CreateRetailSaleLine.orderLineId; r8 re-walk, CHG-R8RW-004). (nullable)
RetailService | listRetailSales | response | items[].lines[].name | string
RetailService | listRetailSales | response | items[].lines[].quantity | integer
RetailService | listRetailSales | response | items[].lines[].overrideReason | string |  | The reason given with a manual price override (CreateRetailSaleLine.overrideReason); null when the price was not overridden. (max length 200; nullable)
RetailService | listRetailSales | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].serialNumbers | array of string
RetailService | listRetailSales | response | items[].lines[].returnedQuantity | integer
RetailService | listRetailSales | response | items[].lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | listRetailSales | response | items[].lines[].notReturnableReason | string |  | (nullable)
RetailService | listRetailSales | response | items[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].reprintCount | integer
RetailService | listRetailSales | response | items[].createdAt | string (date-time) | yes
RetailService | listRetailSales | response | items[].recordedAt | string (date-time)
RetailService | listRetailSales | response | nextCursor | string
RetailService | listRetailSales | response | hasMore | boolean | yes
RetailService | listRetailSales | param (query) | outletId | string (uuid) |  | Exact match.
RetailService | listRetailSales | param (query) | shiftId | string |  | Exact match.
RetailService | listRetailSales | param (query) | createdFrom | string (date-time) |  | Sales with createdAt at or after this instant.
RetailService | listRetailSales | param (query) | createdTo | string (date-time) |  | Sales with createdAt before this instant.
RetailService | listRetailSales | param (query) | pageSize | integer
RetailService | listRetailSales | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listRewards | response | items | array of MarketingReward | yes
MarketingService | listRewards | response | items[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | listRewards | response | items[].id | string (uuid)
MarketingService | listRewards | response | items[].loyaltyProgramId | string (uuid) | yes
MarketingService | listRewards | response | items[].code | string | yes | (max length 100)
MarketingService | listRewards | response | items[].name | string | yes | (max length 200)
MarketingService | listRewards | response | items[].type | string | yes | (max length 30)
MarketingService | listRewards | response | items[].productId | string (uuid) |  | (nullable)
MarketingService | listRewards | response | items[].pointsCost | number |  | (nullable)
MarketingService | listRewards | response | items[].discountValue | number |  | (nullable)
MarketingService | listRewards | response | items[].validityDays | integer |  | (nullable)
MarketingService | listRewards | response | items[].isActive | boolean | yes
MarketingService | listRewards | response | nextCursor | string
MarketingService | listRewards | response | hasMore | boolean | yes
MarketingService | listRewards | param (query) | programmeId | string (uuid)
MarketingService | listRewards | param (query) | pageSize | integer
MarketingService | listRewards | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listRewards | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
IdentityService | listRoles | response | items | array of Role | yes
IdentityService | listRoles | response | items[].id | string (uuid) | yes
IdentityService | listRoles | response | items[].code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | listRoles | response | items[].name | string | yes
IdentityService | listRoles | response | items[].description | string
IdentityService | listRoles | response | items[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | listRoles | response | items[].inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | listRoles | response | items[].isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | listRoles | response | items[].presetCode | string |  | The preset this role was started from, for the record only (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): the first of createRole.presetCodes, or null for a role ticked by hand. (max length 64; read-only; nullable)
IdentityService | listRoles | response | items[].principalCount | integer |  | Computed on read, never stored (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): the distinct principals holding this role through a live grant (identity.delegated_access with this role_id, a prin… (read-only)
IdentityService | listRoles | response | items[].grantCount | integer |  | Computed on read, never stored (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): the live grants of this role (the rows principalCount counts, one per grant, so a principal granted the role at two… (read-only)
IdentityService | listRoles | response | nextCursor | string
IdentityService | listRoles | response | hasMore | boolean | yes
IdentityService | listRoles | param (query) | pageSize | integer
IdentityService | listRoles | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listRotaAssignments | response | items | array of RotaAssignment | yes
TenancyService | listRotaAssignments | response | items[].overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | listRotaAssignments | response | items[].restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | listRotaAssignments | response | items[].breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | listRotaAssignments | response | items[].labourCost | object |  | Cost at the point of scheduling.
TenancyService | listRotaAssignments | response | items[].labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | listRotaAssignments | response | items[].labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | listRotaAssignments | response | items[].labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | listRotaAssignments | response | items[].id | string (uuid) |  | (read-only)
TenancyService | listRotaAssignments | response | items[].principalId | string (uuid) | yes
TenancyService | listRotaAssignments | response | items[].displayName | string |  | (read-only)
TenancyService | listRotaAssignments | response | items[].venueId | string (uuid) | yes
TenancyService | listRotaAssignments | response | items[].departmentId | string (uuid) |  | (nullable)
TenancyService | listRotaAssignments | response | items[].position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | listRotaAssignments | response | items[].requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | listRotaAssignments | response | items[].workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | listRotaAssignments | response | items[].startsAt | string (date-time) | yes
TenancyService | listRotaAssignments | response | items[].endsAt | string (date-time) | yes
TenancyService | listRotaAssignments | response | items[].status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | listRotaAssignments | response | items[].breakMinutes | integer |  | (nullable)
TenancyService | listRotaAssignments | response | items[].note | string |  | (nullable)
TenancyService | listRotaAssignments | response | nextCursor | string
TenancyService | listRotaAssignments | response | hasMore | boolean | yes
TenancyService | listRotaAssignments | param (query) | from | string (date) |  | First calendar day, in the Region's time zone, not UTC.
TenancyService | listRotaAssignments | param (query) | to | string (date) |  | Last calendar day, in the Region's time zone, not UTC.
TenancyService | listRotaAssignments | param (query) | principalId | string (uuid)
TenancyService | listRotaAssignments | param (query) | departmentId | string (uuid)
TenancyService | listRotaAssignments | param (query) | pageSize | integer
TenancyService | listRotaAssignments | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listSaleBoards | param (query) | venueId | string (uuid)
TenancyService | listSaleBoards | param (query) | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed)
InventoryService | listSerialisedItems | response | items | array of SerialisedItem | yes
InventoryService | listSerialisedItems | response | items[].id | string (uuid) | yes
InventoryService | listSerialisedItems | response | items[].itemId | string (uuid) | yes
InventoryService | listSerialisedItems | response | items[].batchId | string (uuid) |  | The batch it arrived in, where the item is both lotted and serialised. (nullable)
InventoryService | listSerialisedItems | response | items[].serial | string | yes | Unique within the item, not globally.
InventoryService | listSerialisedItems | response | items[].locationId | string (uuid)
InventoryService | listSerialisedItems | response | items[].status | enum (inStock, reserved, sold, returned, damaged, lost, inTransit, warranty) | yes
InventoryService | listSerialisedItems | response | items[].soldOnOrderLineId | string (uuid) |  | The link that makes serialisation worth having. (nullable)
InventoryService | listSerialisedItems | response | items[].warrantyUntil | string (date) |  | (nullable)
InventoryService | listSerialisedItems | response | items[].receivedAt | string (date-time)
InventoryService | listSerialisedItems | response | nextCursor | string
InventoryService | listSerialisedItems | response | hasMore | boolean | yes
InventoryService | listSerialisedItems | param (query) | serial | string |  | Exact match.
InventoryService | listSerialisedItems | param (query) | status | string
InventoryService | listSerialisedItems | param (query) | pageSize | integer
InventoryService | listSerialisedItems | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listShifts | response | items | array of Shift | yes
OrderService | listShifts | response | items[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | listShifts | response | items[].workstationId | string (uuid) | yes
OrderService | listShifts | response | items[].venueId | string (uuid) | yes
OrderService | listShifts | response | items[].scopePath | string | yes
OrderService | listShifts | response | items[].principalId | string (uuid) | yes | Who opened it.
OrderService | listShifts | response | items[].principalDisplayName | string
OrderService | listShifts | response | items[].incidents | array of object |  | BL-097.
OrderService | listShifts | response | items[].incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | listShifts | response | items[].incidents[].at | string (date-time)
OrderService | listShifts | response | items[].incidents[].principalId | string (uuid)
OrderService | listShifts | response | items[].incidents[].note | string |  | (nullable)
OrderService | listShifts | response | items[].status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | listShifts | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | listShifts | response | items[].depositBoxCode | string |  | (nullable)
OrderService | listShifts | response | items[].bagNumber | string |  | (nullable)
OrderService | listShifts | response | items[].openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | listShifts | response | items[].expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | listShifts | response | items[].countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | listShifts | response | items[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | listShifts | response | items[].cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | listShifts | response | items[].varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | listShifts | response | items[].heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | listShifts | response | items[].openedAt | string (date-time) | yes
OrderService | listShifts | response | items[].businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | listShifts | response | items[].recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | listShifts | response | items[].suspendedAt | string (date-time) |  | (nullable)
OrderService | listShifts | response | items[].suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | listShifts | response | items[].closedAt | string (date-time) |  | (nullable)
OrderService | listShifts | response | items[].closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | listShifts | response | items[].recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | listShifts | response | items[].recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | listShifts | response | items[].recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | listShifts | response | items[].countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | listShifts | response | items[].syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | listShifts | response | items[].approvals | array of object
OrderService | listShifts | response | items[].approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | listShifts | response | items[].approvals[].principalId | string (uuid) | yes
OrderService | listShifts | response | items[].approvals[].at | string (date-time) | yes
OrderService | listShifts | response | items[].approvals[].reason | string
OrderService | listShifts | response | nextCursor | string
OrderService | listShifts | response | hasMore | boolean | yes
OrderService | listShifts | param (query) | workstationId | string (uuid)
OrderService | listShifts | param (query) | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed)
OrderService | listShifts | param (query) | openedFrom | string (date-time)
OrderService | listShifts | param (query) | openedTo | string (date-time)
OrderService | listShifts | param (query) | businessDate | string (date) |  | The shifts of one business date (Shift.businessDate, closing at the venue's businessDayCutoff; CHG-R6-032), as the daily reconciliation asks for them.
OrderService | listShifts | param (query) | pageSize | integer
OrderService | listShifts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listSyncRejections | response | items | array of SyncRejection | yes
OrderService | listSyncRejections | response | items[].id | string (uuid) | yes
OrderService | listSyncRejections | response | items[].workstationId | string (uuid) | yes
OrderService | listSyncRejections | response | items[].kind | enum (order, payment, refund, void, scan, cashMovement) | yes | What was refused.
OrderService | listSyncRejections | response | items[].recordedAt | string (date-time)
OrderService | listSyncRejections | response | items[].rejectedAt | string (date-time) | yes
OrderService | listSyncRejections | response | items[].problem | Problem | yes | RFC 9457 problem details.
OrderService | listSyncRejections | response | items[].problem.type | string (uri) | yes | The problem type URI, https://api.ticvai.com/problems/<slug>.
OrderService | listSyncRejections | response | items[].problem.title | string | yes
OrderService | listSyncRejections | response | items[].problem.status | integer | yes
OrderService | listSyncRejections | response | items[].problem.detail | string
OrderService | listSyncRejections | response | items[].problem.instance | string
OrderService | listSyncRejections | response | items[].problem.traceId | string
OrderService | listSyncRejections | response | items[].problem.errors | array of object
OrderService | listSyncRejections | response | items[].payload | object |  | Deliberately open: the journal entry exactly as the till sent it.
OrderService | listSyncRejections | response | items[].resolvedAt | string (date-time) |  | (read-only; nullable)
OrderService | listSyncRejections | response | items[].resolvedByPrincipalId | string (uuid) |  | (read-only; nullable)
OrderService | listSyncRejections | response | items[].resolution | enum (posted, voided, refunded) |  | What resolveSyncRejection recorded. (read-only; nullable)
OrderService | listSyncRejections | response | items[].resolvedRecordId | string (uuid) |  | The order, void or refund the resolution produced — what stops the entry being posted twice. (read-only; nullable)
OrderService | listSyncRejections | response | nextCursor | string
OrderService | listSyncRejections | response | hasMore | boolean | yes
OrderService | listSyncRejections | param (query) | workstationId | string (uuid) |  | Exact match on the till that journalled the entry.
OrderService | listSyncRejections | param (query) | kind | enum (order, payment, refund, void, scan) |  | Exact match on SyncRejection.kind.
OrderService | listSyncRejections | param (query) | resolved | boolean |  | false returns only rejections still waiting for a decision (resolvedAt null), true only those resolved.
OrderService | listSyncRejections | param (query) | pageSize | integer
OrderService | listSyncRejections | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listTableCombinations | response | items | array of TableCombination | yes
FnbService | listTableCombinations | response | items[].id | string (uuid) |  | (read-only)
FnbService | listTableCombinations | response | items[].outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | listTableCombinations | response | items[].tableIds | array of string (uuid) | yes | (min items 2)
FnbService | listTableCombinations | response | items[].combinedCovers | integer | yes | (min 1)
FnbService | listTableCombinations | response | items[].setupMinutes | integer |  | (default 5)
FnbService | listTableCombinations | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | listTableCombinations | response | nextCursor | string
FnbService | listTableCombinations | response | hasMore | boolean | yes
FnbService | listTableCombinations | param (path) | outletId | string (uuid) | yes
FnbService | listTableCombinations | param (path) | outletId | string (uuid) | yes
FnbService | listTableCombinations | param (query) | pageSize | integer
FnbService | listTableCombinations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listTableReservations | response | items | array of TableReservation | yes
FnbService | listTableReservations | response | items[].id | string (uuid) |  | (read-only)
FnbService | listTableReservations | response | items[].outletId | string (uuid) | yes
FnbService | listTableReservations | response | items[].subjectId | string (uuid) |  | (nullable)
FnbService | listTableReservations | response | items[].guestName | string
FnbService | listTableReservations | response | items[].contactPoint | string
FnbService | listTableReservations | response | items[].partySize | integer | yes | (min 1)
FnbService | listTableReservations | response | items[].startsAt | string (date-time) | yes
FnbService | listTableReservations | response | items[].durationMinutes | integer |  | How long the cover is held.
FnbService | listTableReservations | response | items[].tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | listTableReservations | response | items[].tables[].reservationId | string (uuid) | yes
FnbService | listTableReservations | response | items[].tables[].tableId | string (uuid) | yes
FnbService | listTableReservations | response | items[].tables[].createdAt | string (date-time) | yes
FnbService | listTableReservations | response | items[].status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | listTableReservations | response | items[].groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | listTableReservations | response | items[].notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | listTableReservations | response | items[].seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | listTableReservations | response | items[].occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | listTableReservations | response | items[].takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | listTableReservations | response | items[].actualPartySize | integer |  | (read-only; nullable)
FnbService | listTableReservations | response | items[].tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | listTableReservations | response | items[].deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | listTableReservations | response | items[].deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listTableReservations | response | items[].deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | listTableReservations | response | items[].deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | listTableReservations | response | items[].deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | listTableReservations | response | items[].deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | listTableReservations | response | items[].deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | listTableReservations | response | items[].deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | listTableReservations | response | items[].createdAt | string (date-time) |  | (read-only)
FnbService | listTableReservations | response | nextCursor | string
FnbService | listTableReservations | response | hasMore | boolean | yes
FnbService | listTableReservations | param (query) | outletId | string (uuid)
FnbService | listTableReservations | param (query) | date | string (date) |  | A calendar day, in the Region's time zone, not UTC.
FnbService | listTableReservations | param (query) | pageSize | integer
FnbService | listTableReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listTaxInvoices | response | items | array of FinTaxInvoice | yes
LedgerService | listTaxInvoices | response | items[].id | string (uuid) | yes | (read-only)
LedgerService | listTaxInvoices | response | items[].invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | listTaxInvoices | response | items[].invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | listTaxInvoices | response | items[].status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | listTaxInvoices | response | items[].legalEntityId | string (uuid) | yes
LedgerService | listTaxInvoices | response | items[].templateId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].venueId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].orderIds | array of string (uuid)
LedgerService | listTaxInvoices | response | items[].supplierName | string
LedgerService | listTaxInvoices | response | items[].supplierAddress | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | listTaxInvoices | response | items[].buyerName | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerAddress | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | listTaxInvoices | response | items[].buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].customerAccountId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].issuedAt | string (date-time) | yes
LedgerService | listTaxInvoices | response | items[].supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | listTaxInvoices | response | items[].currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].legalCurrency | string |  | The legal entity's currency (AED in the UAE), in which the law requires the tax and the gross amount (CHG-FIN-011). (pattern ^[A-Z]{3}$; read-only)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency | object |  | The gross amount payable in the legal currency (Executive Regulation Art. (read-only)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].legalFxRate | object |  | Units of the legal currency per one unit of currency, printed with the tax where the invoice is not in the legal currency (Art. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].legalFxRateSource | object |  | uaeCentralBank for a UAE legal entity (Decree-Law Art. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].paidCurrency | string |  | Where the guest paid in a currency they selected (orders.Order.chargeCurrency, CHG-FIN-001), printed as payment information with paidAmount and the charge rate. (pattern ^[A-Z]{3}$; read-only; nullable)
LedgerService | listTaxInvoices | response | items[].paidAmount | object |  | What the guest paid in paidCurrency (orders.Order.chargeTotal). (read-only)
LedgerService | listTaxInvoices | response | items[].paidAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].paidAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].paidAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].reverseChargeStatement | string |  | Where the recipient must account for the tax, the statement saying so and the Decree-Law provision (Art. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].languages | array of string
LedgerService | listTaxInvoices | response | items[].supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | listTaxInvoices | response | items[].issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].lines | array of FinTaxInvoiceLine | yes
LedgerService | listTaxInvoices | response | items[].lines[].lineNumber | integer | yes | (min 1)
LedgerService | listTaxInvoices | response | items[].lines[].orderId | string (uuid)
LedgerService | listTaxInvoices | response | items[].lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].lines[].description | string | yes | (max length 500)
LedgerService | listTaxInvoices | response | items[].lines[].quantity | number | yes
LedgerService | listTaxInvoices | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].lines[].taxRate | number |  | (min 0; max 100)
LedgerService | listTaxInvoices | response | items[].lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | listTaxInvoices | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].grossAmountInLegalCurrency | object |  | The amount payable for the line in the legal currency (AED), Executive Regulation Art. (read-only)
LedgerService | listTaxInvoices | response | items[].taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxRate | number
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | listTaxInvoices | response | nextCursor | string
LedgerService | listTaxInvoices | response | hasMore | boolean | yes
LedgerService | listTaxInvoices | param (query) | orderId | string (uuid) |  | Invoices covering this order, including a consolidated invoice that names it.
LedgerService | listTaxInvoices | param (query) | legalEntityId | string (uuid)
LedgerService | listTaxInvoices | param (query) | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated)
LedgerService | listTaxInvoices | param (query) | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded)
LedgerService | listTaxInvoices | param (query) | issuedFrom | string (date) |  | A day in the time zone of the region at or above the caller's scope, local midnight to local midnight.
LedgerService | listTaxInvoices | param (query) | issuedTo | string (date) |  | A day in the time zone of the region at or above the caller's scope, local midnight to local midnight.
LedgerService | listTaxInvoices | param (query) | pageSize | integer
LedgerService | listTaxInvoices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
PlatformService | listTenants | response | items | array of Tenant | yes
PlatformService | listTenants | response | items[].id | string (uuid) | yes
PlatformService | listTenants | response | items[].code | string | yes
PlatformService | listTenants | response | items[].name | string | yes
PlatformService | listTenants | response | items[].status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | listTenants | response | items[].suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | listTenants | response | items[].suspensionReason | string |  | (nullable)
PlatformService | listTenants | response | items[].suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | listTenants | response | items[].suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | listTenants | response | items[].terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | listTenants | response | items[].terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | listTenants | response | items[].terminationReason | string |  | (max length 1000; nullable)
PlatformService | listTenants | response | items[].terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].planId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].planVersion | string |  | The version of the plan the tenant is on (with planId, the key of the plan row; R8 blocker APPROVALS-TENANCY-C15, CHG-R8INT-023). (read-only; nullable)
PlatformService | listTenants | response | items[].planName | string |  | (nullable)
PlatformService | listTenants | response | items[].cellCount | integer
PlatformService | listTenants | response | items[].venueCount | integer
PlatformService | listTenants | response | items[].cellHost | string |  | The host of the tenant's home cell (the host part of Cell.apiEndpoint of the cell that holds the tenant in its home region), derived on read through control.cell_tenant. (read-only; nullable)
PlatformService | listTenants | response | items[].cellHosts | array of object |  | One entry per region the tenant is in, for a multi-region tenant; the entry with isHome true is cellHost. (read-only)
PlatformService | listTenants | response | items[].cellHosts[].regionId | string (uuid) | yes
PlatformService | listTenants | response | items[].cellHosts[].cellId | string (uuid) | yes
PlatformService | listTenants | response | items[].cellHosts[].host | string | yes
PlatformService | listTenants | response | items[].cellHosts[].isHome | boolean | yes
PlatformService | listTenants | response | items[].regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | listTenants | response | items[].billingEmail | string
PlatformService | listTenants | response | items[].billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | listTenants | response | items[].accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].createdAt | string (date-time) | yes
PlatformService | listTenants | response | items[].activatedAt | string (date-time) |  | (nullable)
PlatformService | listTenants | response | nextCursor | string
PlatformService | listTenants | response | hasMore | boolean | yes
PlatformService | listTenants | param (query) | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated)
PlatformService | listTenants | param (query) | planId | string (uuid)
PlatformService | listTenants | param (query) | pageSize | integer
PlatformService | listTenants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listTicketTransfers | response | items | array of TicketTransfer | yes
OrderService | listTicketTransfers | response | items[].id | string (uuid) | yes
OrderService | listTicketTransfers | response | items[].orderId | string (uuid) | yes
OrderService | listTicketTransfers | response | items[].ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | listTicketTransfers | response | items[].fromSubjectId | string (uuid)
OrderService | listTicketTransfers | response | items[].toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | listTicketTransfers | response | items[].recipientAddressMasked | string
OrderService | listTicketTransfers | response | items[].status | enum (offered, claimed, expired, cancelled) | yes
OrderService | listTicketTransfers | response | items[].claimUrl | string |  | The link the recipient is sent (R8 blocker fix, ORDERS-MONEY-C12). (nullable)
OrderService | listTicketTransfers | response | items[].claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | listTicketTransfers | response | items[].offeredAt | string (date-time) | yes
OrderService | listTicketTransfers | response | items[].claimedAt | string (date-time) |  | (nullable)
OrderService | listTicketTransfers | response | items[].expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | listTicketTransfers | response | nextCursor | string
OrderService | listTicketTransfers | response | hasMore | boolean | yes
OrderService | listTicketTransfers | param (query) | direction | enum (sent, received) |  | sent for transfers the caller offered, received for those they claimed.
OrderService | listTicketTransfers | param (query) | status | enum (offered, claimed, expired, cancelled) |  | Exact match on TicketTransfer.status.
OrderService | listTicketTransfers | param (query) | pageSize | integer
OrderService | listTicketTransfers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportPassOffers | response | items | array of PassOffer | yes
VenueOpsService | listTransportPassOffers | response | items[].passTypeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportPassOffers | response | items[].catalogueProductId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | items[].routeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportPassOffers | response | items[].name | string | yes
VenueOpsService | listTransportPassOffers | response | items[].description | string
VenueOpsService | listTransportPassOffers | response | items[].kind | enum (multiTrip, unlimited)
VenueOpsService | listTransportPassOffers | response | items[].trips | integer |  | (nullable)
VenueOpsService | listTransportPassOffers | response | items[].validityDays | integer | yes
VenueOpsService | listTransportPassOffers | response | items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | listTransportPassOffers | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listTransportPassOffers | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listTransportPassOffers | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listTransportPassOffers | response | items[].saving | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | listTransportPassOffers | response | items[].saving.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listTransportPassOffers | response | items[].saving.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listTransportPassOffers | response | items[].saving.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listTransportPassOffers | response | items[].variants | array of object |  | What addCartLine sells for this pass (4 October 2026, CHG-FXC-011; GST-050, GST-056): one catalogue variant of catalogueProductId per passenger type.
VenueOpsService | listTransportPassOffers | response | items[].variants[].passengerTypeId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | items[].variants[].variantId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | nextCursor | string
VenueOpsService | listTransportPassOffers | response | hasMore | boolean | yes
VenueOpsService | listTransportPassOffers | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | param (query) | toStationId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | param (query) | pageSize | integer
VenueOpsService | listTransportPassOffers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportPassOffers | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | listTransportRoutes | response | items | array of TransportRoute | yes
VenueOpsService | listTransportRoutes | response | items[].venueId | string (uuid) | yes
VenueOpsService | listTransportRoutes | response | items[].code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | listTransportRoutes | response | items[].lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | listTransportRoutes | response | items[].name | LocalisedText | yes
VenueOpsService | listTransportRoutes | response | items[].colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | listTransportRoutes | response | items[].pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | listTransportRoutes | response | items[].bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | listTransportRoutes | response | items[].stops | array of RouteStop | yes
VenueOpsService | listTransportRoutes | response | items[].stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | listTransportRoutes | response | items[].stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | listTransportRoutes | response | items[].stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | listTransportRoutes | response | items[].stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | listTransportRoutes | response | items[].stops[].station | Station
VenueOpsService | listTransportRoutes | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | listTransportRoutes | response | items[].totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | listTransportRoutes | response | items[].catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | listTransportRoutes | response | items[].catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | listTransportRoutes | response | items[].statusReason | string |  | Why the route's status last changed (setTransportRouteStatus). (max length 500; read-only; nullable)
VenueOpsService | listTransportRoutes | response | nextCursor | string
VenueOpsService | listTransportRoutes | response | hasMore | boolean | yes
VenueOpsService | listTransportRoutes | param (query) | venueId | string (uuid) | yes
VenueOpsService | listTransportRoutes | param (query) | fromStationId | string (uuid)
VenueOpsService | listTransportRoutes | param (query) | toStationId | string (uuid)
VenueOpsService | listTransportRoutes | param (query) | status | TransportRouteStatus: enum (draft, active, suspended, retired)
VenueOpsService | listTransportRoutes | param (query) | pageSize | integer
VenueOpsService | listTransportRoutes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportStations | response | items | array of Station | yes
VenueOpsService | listTransportStations | response | items[].venueId | string (uuid) | yes
VenueOpsService | listTransportStations | response | items[].code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | listTransportStations | response | items[].name | LocalisedText | yes
VenueOpsService | listTransportStations | response | items[].shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | listTransportStations | response | items[].latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | listTransportStations | response | items[].longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | listTransportStations | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportStations | response | items[].active | boolean | yes | (default True)
VenueOpsService | listTransportStations | response | nextCursor | string
VenueOpsService | listTransportStations | response | hasMore | boolean | yes
VenueOpsService | listTransportStations | param (query) | venueId | string (uuid) | yes
VenueOpsService | listTransportStations | param (query) | includeInactive | boolean
VenueOpsService | listTransportStations | param (query) | pageSize | integer
VenueOpsService | listTransportStations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listVenueHistoryImports | response | items | array of AiHistoryImport | yes
AiService | listVenueHistoryImports | response | items[].id | string (uuid) | yes | (read-only)
AiService | listVenueHistoryImports | response | items[].venueId | string (uuid) | yes
AiService | listVenueHistoryImports | response | items[].dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | listVenueHistoryImports | response | items[].assetId | string (uuid)
AiService | listVenueHistoryImports | response | items[].sourceSystem | string |  | (nullable)
AiService | listVenueHistoryImports | response | items[].columnMapping | object
AiService | listVenueHistoryImports | response | items[].dryRun | boolean |  | (default False)
AiService | listVenueHistoryImports | response | items[].status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | listVenueHistoryImports | response | items[].periodFrom | string (date) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].periodTo | string (date) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].monthsCovered | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsRead | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsLoaded | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsRejected | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].findings | array of object |  | (read-only)
AiService | listVenueHistoryImports | response | items[].findings[].row | integer
AiService | listVenueHistoryImports | response | items[].findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | listVenueHistoryImports | response | items[].findings[].detail | string
AiService | listVenueHistoryImports | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | listVenueHistoryImports | response | items[].createdAt | string (date-time) |  | (read-only)
AiService | listVenueHistoryImports | response | items[].completedAt | string (date-time) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listVenueHistoryImports | response | nextCursor | string
AiService | listVenueHistoryImports | response | hasMore | boolean | yes
AiService | listVenueHistoryImports | param (path) | venueId | string (uuid) | yes
AiService | listVenueHistoryImports | param (query) | pageSize | integer
AiService | listVenueHistoryImports | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listVisitPlanAlternatives | response | items | array of VisitPlanAlternative | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].kind | enum (attraction, show, meal, shop, rest) | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].venueId | string (uuid) | yes | The item's day venue; an alternative is never from another venue (30 September, MoM 4.7).
VenueOpsService | listVisitPlanAlternatives | response | items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].productId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].name | string
VenueOpsService | listVisitPlanAlternatives | response | items[].startsAt | string (date-time) | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].durationMinutes | integer
VenueOpsService | listVisitPlanAlternatives | response | items[].walkMinutes | integer |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].expectedWaitMinutes | integer |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].matchedInterests | array of string
VenueOpsService | listVisitPlanAlternatives | response | items[].reason | string | yes | Why it is offered, in words the sheet shows, e.g.
VenueOpsService | listVisitPlanAlternatives | response | nextCursor | string
VenueOpsService | listVisitPlanAlternatives | response | hasMore | boolean | yes
VenueOpsService | listVisitPlanAlternatives | param (path) | planId | string (uuid) | yes
VenueOpsService | listVisitPlanAlternatives | param (path) | itemId | string (uuid) | yes
VenueOpsService | listVisitPlanAlternatives | param (query) | kind | enum (attraction, show, meal, shop, rest) |  | Only alternatives of this kind.
VenueOpsService | listVisitPlanAlternatives | param (query) | pageSize | integer
VenueOpsService | listVisitPlanAlternatives | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WalletService | listWalletTransactions | response | items | array of WalletTransaction | yes
WalletService | listWalletTransactions | response | items[].id | string | yes
WalletService | listWalletTransactions | response | items[].walletId | string (uuid) |  | The wallet this movement is on (SD-027, 29 September).
WalletService | listWalletTransactions | response | items[].walletHoldId | string (uuid) |  | The hold a spend settled, where it came through holdWalletFunds. (nullable)
WalletService | listWalletTransactions | response | items[].kind | WalletTransactionKind: enum (topUp, spend, refund, adjustment, bonus, expiry, transfer) | yes
WalletService | listWalletTransactions | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | listWalletTransactions | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | listWalletTransactions | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | listWalletTransactions | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | listWalletTransactions | response | items[].balanceAfter | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | listWalletTransactions | response | items[].balanceAfter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | listWalletTransactions | response | items[].balanceAfter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | listWalletTransactions | response | items[].balanceAfter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | listWalletTransactions | response | items[].orderId | string |  | (nullable)
WalletService | listWalletTransactions | response | items[].venueId | string (uuid) |  | (nullable)
WalletService | listWalletTransactions | response | items[].reason | string |  | (nullable)
WalletService | listWalletTransactions | response | items[].principalId | string (uuid) |  | (nullable)
WalletService | listWalletTransactions | response | items[].recordedAt | string (date-time) | yes
WalletService | listWalletTransactions | response | nextCursor | string
WalletService | listWalletTransactions | response | hasMore | boolean | yes
WalletService | listWalletTransactions | param (path) | subjectId | string (uuid) | yes
WalletService | listWalletTransactions | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
WalletService | listWalletTransactions | param (query) | pageSize | integer
WalletService | listWalletTransactions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WalletService | loadGameCredits | request | id | string (uuid) | yes
WalletService | loadGameCredits | request | credits | integer | yes | (min 1)
WalletService | loadGameCredits | request | bonusCredits | integer |  | (min 0; default 0)
WalletService | loadGameCredits | request | amountPaid | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | request | amountPaid.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | request | amountPaid.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | request | amountPaid.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | request | orderId | string
WalletService | loadGameCredits | request | recordedAt | string (date-time) | yes
WalletService | loadGameCredits | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | loadGameCredits | response | subjectId | string (uuid) | yes
WalletService | loadGameCredits | response | transferRules | object |  | What the venue allows this guest to do with a transfer, read from the venue's WalletTransferRules so a guest screen can hide or limit the action (r8 walk of tickets 28310 and 28345). (read-only; nullable)
WalletService | loadGameCredits | response | transferRules.peerToPeerAllowed | boolean
WalletService | loadGameCredits | response | transferRules.withinSharedWalletOnly | boolean
WalletService | loadGameCredits | response | transferRules.maximumPerTransfer | object |  | (nullable)
WalletService | loadGameCredits | response | transferRules.maximumPerTransfer.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | transferRules.maximumPerTransfer.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | transferRules.maximumPerTransfer.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | loadGameCredits | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | loadGameCredits | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | response | credits[].sourceRef | string |  | (nullable)
WalletService | loadGameCredits | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | loadGameCredits | response | bonusBalance | object |  | Promotional value.
WalletService | loadGameCredits | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | status | enum (active, suspended, closed) | yes
WalletService | loadGameCredits | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | loadGameCredits | response | expiresAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | param (path) | cardCode | string | yes
WalletService | loadGameCredits | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logColdChain | request | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | logColdChain | request | id | string (uuid) | yes
FnbService | logColdChain | request | goodsReceiptId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | transferId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | recordedAt | string (date-time) | yes
FnbService | logColdChain | request | valueCelsius | number | yes
FnbService | logColdChain | request | thresholdCelsius | number
FnbService | logColdChain | request | decision | enum (accepted, acceptedWithNote, partiallyRejected, rejected) | yes
FnbService | logColdChain | request | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | supplierClaimRaised | boolean |  | (default False)
FnbService | logColdChain | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | logColdChain | response | id | string (uuid) | yes
FnbService | logColdChain | response | goodsReceiptId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | transferId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | recordedAt | string (date-time) | yes
FnbService | logColdChain | response | valueCelsius | number | yes
FnbService | logColdChain | response | thresholdCelsius | number
FnbService | logColdChain | response | decision | enum (accepted, acceptedWithNote, partiallyRejected, rejected) | yes
FnbService | logColdChain | response | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | supplierClaimRaised | boolean |  | (default False)
FnbService | logColdChain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logKitchenException | request | kind | enum (equipmentDown, itemRanOut, lateDelivery, staffShort, powerLoss, spillage, other) | yes | chased is not offered here — chaseStation records it.
FnbService | logKitchenException | request | outletId | string (uuid) | yes | The outlet whose kitchen it happened in.
FnbService | logKitchenException | request | stationId | string (uuid) |  | (nullable)
FnbService | logKitchenException | request | ticketId | string (uuid) |  | The ticket it happened on, where there was one. (nullable)
FnbService | logKitchenException | request | durationMinutes | integer |  | (nullable)
FnbService | logKitchenException | request | note | string |  | (nullable)
FnbService | logKitchenException | request | recordedAt | string (date-time) | yes | Device time, not arrival time.
FnbService | logKitchenException | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | logKitchenException | response | id | string (uuid) | yes
FnbService | logKitchenException | response | outletId | string (uuid)
FnbService | logKitchenException | response | stationId | string (uuid) |  | (nullable)
FnbService | logKitchenException | response | ticketId | string (uuid) |  | (nullable)
FnbService | logKitchenException | response | kind | enum (equipmentDown, itemRanOut, lateDelivery, staffShort, powerLoss, spillage, chased, other) | yes | other always carries a note (audit R222).
FnbService | logKitchenException | response | durationMinutes | integer |  | (nullable)
FnbService | logKitchenException | response | raisedAt | string (date-time) | yes
FnbService | logKitchenException | response | raisedByPrincipalId | string (uuid)
FnbService | logKitchenException | response | note | string |  | (nullable)
FnbService | logKitchenException | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logTemperature | request | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | logTemperature | request | id | string (uuid) | yes
FnbService | logTemperature | request | checkPointId | string (uuid) | yes | The unit, station or delivery being read.
FnbService | logTemperature | request | checkPointKind | enum (fridge, freezer, holdingCabinet, blastChiller, coreProbe, delivery, displayCounter, ambient)
FnbService | logTemperature | request | recordedAt | string (date-time) | yes
FnbService | logTemperature | request | recordedByPrincipalId | string (uuid)
FnbService | logTemperature | request | valueCelsius | number | yes
FnbService | logTemperature | request | minCelsius | number |  | (nullable)
FnbService | logTemperature | request | maxCelsius | number |  | (nullable)
FnbService | logTemperature | request | outcome | enum (inRange, outOfRange, notTaken) | yes | notTaken is a record, not an absence.
FnbService | logTemperature | request | deviceReported | boolean |  | A probe reading and a person's reading are different evidence. (default False)
FnbService | logTemperature | request | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | log | TemperatureLog |  | Board 5J of the client F&B pack, 20 August.
FnbService | logTemperature | response | log.scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | logTemperature | response | log.id | string (uuid) | yes
FnbService | logTemperature | response | log.checkPointId | string (uuid) | yes | The unit, station or delivery being read.
FnbService | logTemperature | response | log.checkPointKind | enum (fridge, freezer, holdingCabinet, blastChiller, coreProbe, delivery, displayCounter, ambient)
FnbService | logTemperature | response | log.recordedAt | string (date-time) | yes
FnbService | logTemperature | response | log.recordedByPrincipalId | string (uuid)
FnbService | logTemperature | response | log.valueCelsius | number | yes
FnbService | logTemperature | response | log.minCelsius | number |  | (nullable)
FnbService | logTemperature | response | log.maxCelsius | number |  | (nullable)
FnbService | logTemperature | response | log.outcome | enum (inRange, outOfRange, notTaken) | yes | notTaken is a record, not an absence.
FnbService | logTemperature | response | log.deviceReported | boolean |  | A probe reading and a person's reading are different evidence. (default False)
FnbService | logTemperature | response | log.correctiveActionId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction | CorrectiveAction |  | What was done about a finding, and who signed it.
FnbService | logTemperature | response | correctiveAction.id | string (uuid) | yes
FnbService | logTemperature | response | correctiveAction.raisedAt | string (date-time) | yes
FnbService | logTemperature | response | correctiveAction.raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | logTemperature | response | correctiveAction.source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | logTemperature | response | correctiveAction.sourceRef | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | logTemperature | response | correctiveAction.actionTaken | string |  | (nullable)
FnbService | logTemperature | response | correctiveAction.disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | logTemperature | response | correctiveAction.signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.signedAt | string (date-time) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | logTemperature | response | correctiveAction.scopePath | string |  | The partition key (ADR-0005).
FnbService | logTemperature | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | login | request | username | string | yes | (max length 256)
IdentityService | login | request | credential | string | yes | The password for password; the PIN for pin, card and rfid. (max length 512)
IdentityService | login | request | method | enum (password, pin, card, rfid, sso) |  | pin is how a till is actually used. (default password)
IdentityService | login | request | workstationId | string (uuid) |  | Identifies the device.
IdentityService | login | request | deviceFingerprint | string |  | (max length 256)
IdentityService | login | response | accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | login | response | refreshToken | string | yes
IdentityService | login | response | expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | login | response | mustChangeCredential | boolean | yes | The credential just used is temporary (14 October 2026, CHG-CRD-001, ADAM CR-078): the principal's Principal.mustChangeCredential, set at creation and by resetPrincipalCredential.
IdentityService | login | response | requiresRoleSelection | boolean | yes
IdentityService | login | response | requiresMfa | boolean | yes | True when the principal holds any permission listed in PasswordPolicy.mfaRequiredForPermissions (decided 28 September, audit R135).
IdentityService | login | response | hasMfaMethod | boolean |  | Whether the principal has an active MFA method.
IdentityService | login | response | mfaMethods | array of MfaMethod |  | The principal's active methods, so the client can offer the right one for the signIn challenge.
IdentityService | login | response | mfaMethods[].id | string (uuid) | yes
IdentityService | login | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | login | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | login | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | login | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | login | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | login | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | login | response | mfaMethods[].label | string |  | (nullable)
IdentityService | login | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | login | response | mfaMethods[].isActive | boolean | yes
IdentityService | login | response | mfaMethods[].isPrimary | boolean
IdentityService | login | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | login | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | login | response | availableRoles | array of RoleSummary
IdentityService | login | response | availableRoles[].id | string (uuid) | yes
IdentityService | login | response | availableRoles[].code | string | yes
IdentityService | login | response | availableRoles[].name | string | yes
IdentityService | login | response | availableRoles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | login | response | availableRoles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | login | response | availableRoles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | login | response | availableRoles[].scope.id | string (uuid) | yes
IdentityService | login | response | availableRoles[].scope.level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | login | response | availableRoles[].scope.path | string | yes | Materialised ltree path.
IdentityService | login | response | availableRoles[].scope.code | string |  | (nullable)
IdentityService | login | response | availableRoles[].scope.name | string |  | (nullable)
IdentityService | login | response | session | Session
IdentityService | login | response | session.sessionId | string (uuid) | yes
IdentityService | login | response | session.principalId | string (uuid) | yes
IdentityService | login | response | session.roleId | string (uuid) | yes
IdentityService | login | response | session.displayName | string
IdentityService | login | response | session.scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | login | response | session.scope[].id | string (uuid) | yes
IdentityService | login | response | session.scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | login | response | session.scope[].path | string | yes | Materialised ltree path.
IdentityService | login | response | session.scope[].code | string |  | (nullable)
IdentityService | login | response | session.scope[].name | string |  | (nullable)
IdentityService | login | response | session.effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | login | response | session.permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path, after deny resolution.
IdentityService | login | response | session.permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | login | response | session.permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | login | response | session.saleBoardId | string (uuid) |  | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | login | response | session.workstation | WorkstationContext
IdentityService | login | response | session.workstation.id | string (uuid) | yes
IdentityService | login | response | session.workstation.code | string | yes
IdentityService | login | response | session.workstation.venueId | string (uuid) | yes
IdentityService | login | response | session.workstation.regionId | string (uuid) | yes
IdentityService | login | response | session.workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | login | response | session.workstation.devices | array of object
IdentityService | login | response | session.workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | login | response | session.workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | login | response | session.workstation.timezone | string
IdentityService | login | response | session.workstation.cellName | string |  | The cell this workstation's region is served from, which is the cell the commerce host answering this request is deployed in (one cell per tenant per region, ADR-0014): the host fills it from its own…
IdentityService | login | response | session.workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | login | response | session.workstation.pinLength | enum (4, 6, 8) |  | The tenant's PasswordPolicy.pinLength, carried to the device (14 October 2026, CHG-CRD-002, ADAM CR-078). (read-only)
IdentityService | login | response | session.availableRoles | array of RoleSummary |  | The roles the principal may choose, one per grant (IDENTITY-C45, CHG-R8SPN-032), resolved on read as LoginResponse.availableRoles is, so EMP-002 can list them on a cold open or after a relaunch (getC… (read-only)
IdentityService | login | response | session.availableRoles[].id | string (uuid) | yes
IdentityService | login | response | session.availableRoles[].code | string | yes
IdentityService | login | response | session.availableRoles[].name | string | yes
IdentityService | login | response | session.availableRoles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | login | response | session.availableRoles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | login | response | session.availableRoles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | login | response | session.openedAt | string (date-time)
IdentityService | login | response | session.expiresAt | string (date-time) |  | When the session ends at the latest: openedAt plus PasswordPolicy.sessionMaxHours (12 hours by default; proposed, client to correct).
IdentityService | login | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | lookupMerchandise | response | merchandiseId | string (uuid) | yes
RetailService | lookupMerchandise | response | outletId | string (uuid) |  | The outlet whose price and stock this is: the asking workstation's outlet, or outletId for a caller with none (decided 28 September, audit R215).
RetailService | lookupMerchandise | response | sku | string
RetailService | lookupMerchandise | response | name | string | yes
RetailService | lookupMerchandise | response | listPrice | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | lookupMerchandise | response | listPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupMerchandise | response | listPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupMerchandise | response | listPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupMerchandise | response | effectivePrice | object | yes | After any live promotion.
RetailService | lookupMerchandise | response | effectivePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupMerchandise | response | effectivePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupMerchandise | response | effectivePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupMerchandise | response | appliedPromotionCode | string |  | (nullable)
RetailService | lookupMerchandise | response | onHand | number | yes
RetailService | lookupMerchandise | response | isAvailable | boolean
RetailService | lookupMerchandise | response | siblingOutlets | array of object |  | Stock elsewhere in the venue, so a colleague can be sent.
RetailService | lookupMerchandise | response | siblingOutlets[].outletId | string (uuid)
RetailService | lookupMerchandise | response | siblingOutlets[].outletName | string
RetailService | lookupMerchandise | response | siblingOutlets[].onHand | number
RetailService | lookupMerchandise | param (query) | barcode | string |  | Exact match on barcode, within the venue.
RetailService | lookupMerchandise | param (query) | sku | string |  | Exact match on sku, within the venue.
RetailService | lookupMerchandise | param (query) | includeSiblingOutlets | boolean |  | False leaves siblingOutlets empty.
RetailService | lookupMerchandise | param (query) | outletId | string (uuid) |  | The outlet to price and count at, for a caller with no workstation (audit R215).
RetailService | lookupMerchandise | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
RetailService | lookupRetailSale | response | items | array of RetailSale | yes
RetailService | lookupRetailSale | response | items[].id | string | yes
RetailService | lookupRetailSale | response | items[].receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | lookupRetailSale | response | items[].receiptBarcode | string |  | The barcode printed on the receipt (R8 blocker APPROVALS-TENANCY-C34): the receipt number as printed, encoded as a Code 128 barcode, stored so lookupRetailSale finds a sale by receiptBarcode with an… (max length 64; read-only)
RetailService | lookupRetailSale | response | items[].cashierPrincipalId | string (uuid) |  | The staff member who rang the sale up, from the session (null for a guest's own sale). (read-only; nullable)
RetailService | lookupRetailSale | response | items[].orderId | string | yes | The order in the Order & Payment context.
RetailService | lookupRetailSale | response | items[].outletId | string (uuid) | yes
RetailService | lookupRetailSale | response | items[].shiftId | string |  | (nullable)
RetailService | lookupRetailSale | response | items[].subjectId | string (uuid) |  | (nullable)
RetailService | lookupRetailSale | response | items[].lines | array of object | yes
RetailService | lookupRetailSale | response | items[].lines[].lineId | string
RetailService | lookupRetailSale | response | items[].lines[].merchandiseId | string (uuid)
RetailService | lookupRetailSale | response | items[].lines[].orderLineId | string (uuid) |  | The order line the amounts were copied from (CreateRetailSaleLine.orderLineId; r8 re-walk, CHG-R8RW-004). (nullable)
RetailService | lookupRetailSale | response | items[].lines[].name | string
RetailService | lookupRetailSale | response | items[].lines[].quantity | integer
RetailService | lookupRetailSale | response | items[].lines[].overrideReason | string |  | The reason given with a manual price override (CreateRetailSaleLine.overrideReason); null when the price was not overridden. (max length 200; nullable)
RetailService | lookupRetailSale | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].serialNumbers | array of string
RetailService | lookupRetailSale | response | items[].lines[].returnedQuantity | integer
RetailService | lookupRetailSale | response | items[].lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | lookupRetailSale | response | items[].lines[].notReturnableReason | string |  | (nullable)
RetailService | lookupRetailSale | response | items[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].reprintCount | integer
RetailService | lookupRetailSale | response | items[].createdAt | string (date-time) | yes
RetailService | lookupRetailSale | response | items[].recordedAt | string (date-time)
RetailService | lookupRetailSale | response | nextCursor | string
RetailService | lookupRetailSale | response | hasMore | boolean | yes
RetailService | lookupRetailSale | response | matchedBy | enum (receiptBarcode, receiptNumber, orderNumber) | yes | The identifier used, by the precedence above (audit R215).
RetailService | lookupRetailSale | param (query) | receiptNumber | string |  | Exact match on receiptNumber.
RetailService | lookupRetailSale | param (query) | orderNumber | string |  | Exact match on the order number of the order in the Order & Payment context.
RetailService | lookupRetailSale | param (query) | receiptBarcode | string |  | Exact match on the barcode printed on the receipt.
RetailService | lookupRetailSale | param (query) | pageSize | integer
RetailService | lookupRetailSale | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | lookupShopAndDrop | param (query) | entitlementId | string |  | Exact match on the ticket scanned at the collection point.
RetailService | lookupShopAndDrop | param (query) | dropReference | string |  | Exact match on dropReference, as printed on the slip.
RetailService | lookupShopAndDrop | param (query) | receiptNumber | string |  | Exact match on the receipt number of the sale the goods came from.
MarketingService | markMyNotificationsRead | request | ids | array of string |  | (max items 200)
MarketingService | markMyNotificationsRead | request | all | boolean |  | (default False)
MarketingService | markMyNotificationsRead | response | unreadCount | integer | yes | (min 0)
MarketingService | markMyNotificationsRead | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | markOrderCollected | request | verifiedBy | enum (buzzer, orderNumber, name, qr, none)
FnbService | markOrderCollected | request | recordedAt | string (date-time) | yes | Device time of the collection.
FnbService | markOrderCollected | response | id | string (uuid) | yes
FnbService | markOrderCollected | response | orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | markOrderCollected | response | outletId | string (uuid) | yes
FnbService | markOrderCollected | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | markOrderCollected | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | markOrderCollected | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | markOrderCollected | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | markOrderCollected | response | lines | array of object | yes
FnbService | markOrderCollected | response | lines[].id | string (uuid) | yes
FnbService | markOrderCollected | response | lines[].menuItemId | string (uuid) | yes
FnbService | markOrderCollected | response | lines[].quantity | integer | yes | (min 1)
FnbService | markOrderCollected | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | markOrderCollected | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | markOrderCollected | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | markOrderCollected | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | markOrderCollected | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | markOrderCollected | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | markOrderCollected | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | markOrderCollected | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | markOrderCollected | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | markOrderCollected | response | kitchenTickets[].id | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | markOrderCollected | response | kitchenTickets[].orderNumber | string
FnbService | markOrderCollected | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | markOrderCollected | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | markOrderCollected | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | markOrderCollected | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines | array of object | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].name | string | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | markOrderCollected | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | markOrderCollected | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | markOrderCollected | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].elapsedSeconds | integer
FnbService | markOrderCollected | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | markOrderCollected | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | response | createdAt | string (date-time) | yes
FnbService | markOrderCollected | response | recordedAt | string (date-time)
FnbService | markOrderCollected | response | syncedAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | param (path) | orderId | string (uuid) | yes | The F&B order (FnbOrder.id), which is what this closes — not a sales order.
FnbService | markOrderCollected | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | modifyOrder | request | id | string (uuid) | yes | Client-generated UUIDv7 of this modification, not of the order — the order is the path's orderId.
OrderService | modifyOrder | request | addLines | array of CreateOrderLine
OrderService | modifyOrder | request | addLines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | modifyOrder | request | addLines[].variantId | string (uuid) | yes
OrderService | modifyOrder | request | addLines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | modifyOrder | request | addLines[].performanceId | string (uuid)
OrderService | modifyOrder | request | addLines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | modifyOrder | request | addLines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | modifyOrder | request | addLines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | modifyOrder | request | addLines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | modifyOrder | request | addLines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | modifyOrder | request | addLines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | modifyOrder | request | addLines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | modifyOrder | request | addLines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | modifyOrder | request | addLines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | modifyOrder | request | addLines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | modifyOrder | request | addLines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | modifyOrder | request | addLines[].quantity | integer | yes | (min 1)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | modifyOrder | request | addLines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | request | addLines[].holderName | string |  | (nullable)
OrderService | modifyOrder | request | addLines[].dataMaskValues | object |  | Deliberately open.
OrderService | modifyOrder | request | removeLineIds | array of string (uuid)
OrderService | modifyOrder | request | reason | string |  | (max length 500)
OrderService | modifyOrder | request | recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order | Order | yes
OrderService | modifyOrder | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | modifyOrder | response | order.orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | modifyOrder | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | modifyOrder | response | order.channel | object | yes | Where it came from.
OrderService | modifyOrder | response | order.channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | modifyOrder | response | order.venueId | string (uuid) | yes
OrderService | modifyOrder | response | order.scopePath | string | yes
OrderService | modifyOrder | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | modifyOrder | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | modifyOrder | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | modifyOrder | response | order.chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | modifyOrder | response | order.chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | modifyOrder | response | order.chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | modifyOrder | response | order.chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | modifyOrder | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | modifyOrder | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | modifyOrder | response | order.droppedPromotions[].name | string
OrderService | modifyOrder | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | modifyOrder | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | modifyOrder | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.lines | array of OrderLine | yes
OrderService | modifyOrder | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | modifyOrder | response | order.lines[].variantId | string (uuid) | yes
OrderService | modifyOrder | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | modifyOrder | response | order.lines[].performanceId | string (uuid)
OrderService | modifyOrder | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | modifyOrder | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | modifyOrder | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | modifyOrder | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | modifyOrder | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | modifyOrder | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | modifyOrder | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | modifyOrder | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | modifyOrder | response | order.lines[].holderName | string |  | (nullable)
OrderService | modifyOrder | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | modifyOrder | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | modifyOrder | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | modifyOrder | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | modifyOrder | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | modifyOrder | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | modifyOrder | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | modifyOrder | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | modifyOrder | response | order.payments | array of Payment
OrderService | modifyOrder | response | order.payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].id | string (uuid) | yes
OrderService | modifyOrder | response | order.payments[].orderId | string (uuid) | yes
OrderService | modifyOrder | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | modifyOrder | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | modifyOrder | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | modifyOrder | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | modifyOrder | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | modifyOrder | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | modifyOrder | response | order.payments[].providerName | string |  | (nullable)
OrderService | modifyOrder | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | modifyOrder | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | modifyOrder | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | modifyOrder | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | modifyOrder | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | modifyOrder | response | order.principalId | string (uuid)
OrderService | modifyOrder | response | order.workstationId | string (uuid)
OrderService | modifyOrder | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | modifyOrder | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | modifyOrder | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | modifyOrder | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | modifyOrder | response | order.createdAt | string (date-time) | yes
OrderService | modifyOrder | response | order.recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | modifyOrder | response | addedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | addedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | addedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | addedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | removedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | removedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | removedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | removedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | balanceDue | object | yes | Positive means the guest pays; negative means a refund is due.
OrderService | modifyOrder | response | balanceDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | balanceDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | balanceDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | refundId | string (uuid) |  | (nullable)
OrderService | modifyOrder | response | revokedEntitlementIds | array of string (uuid)
OrderService | modifyOrder | response | issuedEntitlementIds | array of string (uuid)
OrderService | modifyOrder | param (path) | orderId | string (uuid) | yes
OrderService | modifyOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | notifyServer | request | reason | enum (foodReady, guestWaiting, billRequested, assistanceNeeded, allergyQuery)
FnbService | notifyServer | param (path) | visitId | string (uuid) | yes
FnbService | notifyServer | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | openAiIncident | request | title | string | yes
AiService | openAiIncident | request | kind | enum (governance, operational, both) |  | (default governance)
AiService | openAiIncident | request | severity | enum (low, medium, high, critical) | yes
AiService | openAiIncident | request | capabilityKeys | array of string
AiService | openAiIncident | request | alertIds | array of string (uuid)
AiService | openAiIncident | request | operationalIncidentRef | string |  | (nullable)
AiService | openAiIncident | request | ownerPrincipalId | string (uuid) |  | (nullable)
AiService | openAiIncident | response | id | string (uuid) |  | (read-only)
AiService | openAiIncident | response | reference | string | yes | (read-only)
AiService | openAiIncident | response | title | string | yes
AiService | openAiIncident | response | kind | enum (governance, operational, both)
AiService | openAiIncident | response | severity | enum (low, medium, high, critical) | yes
AiService | openAiIncident | response | status | enum (open, contained, investigating, remediating, closed) | yes | (read-only)
AiService | openAiIncident | response | capabilityKeys | array of string
AiService | openAiIncident | response | alertIds | array of string (uuid)
AiService | openAiIncident | response | operationalIncidentRef | string |  | The linked operational incident, where both apply (AIC-250). (nullable)
AiService | openAiIncident | response | containment | array of object |  | (read-only)
AiService | openAiIncident | response | containment[].action | string
AiService | openAiIncident | response | containment[].targetRef | string
AiService | openAiIncident | response | containment[].at | string (date-time)
AiService | openAiIncident | response | containment[].byPrincipalId | string (uuid)
AiService | openAiIncident | response | rootCause | string |  | (nullable)
AiService | openAiIncident | response | remediation | string |  | (nullable)
AiService | openAiIncident | response | impact | string |  | The post-incident review's impact (closeAiIncident, CHG-CSA-045). (nullable)
AiService | openAiIncident | response | controlFailure | string |  | (nullable)
AiService | openAiIncident | response | lessonsLearned | string |  | (nullable)
AiService | openAiIncident | response | ownerPrincipalId | string (uuid) |  | (nullable)
AiService | openAiIncident | response | openedAt | string (date-time) |  | (read-only)
AiService | openAiIncident | response | containedAt | string (date-time) |  | (read-only; nullable)
AiService | openAiIncident | response | closedAt | string (date-time) |  | (read-only; nullable)
AiService | openAiIncident | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | openAiIncident | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | openPlatformStaffGrant | request | id | string (uuid) | yes | Client-generated UUIDv7 for the grant.
IdentityService | openPlatformStaffGrant | request | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | What the operator may do in this tenant while the grant is open. (min items 1)
IdentityService | openPlatformStaffGrant | request | reason | string | yes | (min length 3; max length 500)
IdentityService | openPlatformStaffGrant | request | ticketRef | string |  | The support case this access serves, where there is one. (max length 100; nullable)
IdentityService | openPlatformStaffGrant | request | expiresAt | string (date-time) | yes | At most 8 hours after opening (proposed, client to correct).
IdentityService | openPlatformStaffGrant | response | id | string (uuid) | yes
IdentityService | openPlatformStaffGrant | response | operatorPrincipalId | string (uuid) | yes | The platform operator, from the Control Plane token (its subject). (read-only)
IdentityService | openPlatformStaffGrant | response | operatorDisplayName | string |  | (read-only)
IdentityService | openPlatformStaffGrant | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | openPlatformStaffGrant | response | reason | string | yes
IdentityService | openPlatformStaffGrant | response | ticketRef | string |  | (nullable)
IdentityService | openPlatformStaffGrant | response | openedAt | string (date-time) | yes | (read-only)
IdentityService | openPlatformStaffGrant | response | expiresAt | string (date-time) | yes
IdentityService | openPlatformStaffGrant | response | scopePath | string |  | The tenant root. (read-only)
IdentityService | openPlatformStaffGrant | param (header) | X-Tenant-Id | string (uuid) |  | Which tenant a call acts in, where one cell holds many tenant databases (ADR-0038; R8 blocker fix, APPROVALS-TENANCY-C44).
IdentityService | openPlatformStaffGrant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | openShift | request | workstationId | string (uuid) | yes
OrderService | openShift | request | openingFloat | array of CashCountLine | yes | A count is a list of lines and the line is the row. (min items 1)
OrderService | openShift | request | openingFloat[].id | string (uuid)
OrderService | openShift | request | openingFloat[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | openShift | request | openingFloat[].depositBoxId | string (uuid) |  | (nullable)
OrderService | openShift | request | openingFloat[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | openShift | request | openingFloat[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | openShift | request | openingFloat[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | openShift | request | openingFloat[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | openShift | request | openingFloat[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | request | openingFloat[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | request | openingFloat[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | request | openingFloat[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | request | openingFloat[].countedBy | string (uuid) |  | (nullable)
OrderService | openShift | request | openingFloat[].countedAt | string (date-time)
OrderService | openShift | request | openingFloat[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | openShift | request | depositBoxCode | string |  | Physical container assigned to this shift. (max length 64)
OrderService | openShift | request | bagNumber | string |  | Required where the venue configures bag numbers as mandatory. (max length 64)
OrderService | openShift | request | recordedAt | string (date-time) |  | When the device recorded it.
OrderService | openShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | openShift | response | workstationId | string (uuid) | yes
OrderService | openShift | response | venueId | string (uuid) | yes
OrderService | openShift | response | scopePath | string | yes
OrderService | openShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | openShift | response | principalDisplayName | string
OrderService | openShift | response | incidents | array of object |  | BL-097.
OrderService | openShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | openShift | response | incidents[].at | string (date-time)
OrderService | openShift | response | incidents[].principalId | string (uuid)
OrderService | openShift | response | incidents[].note | string |  | (nullable)
OrderService | openShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | openShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | openShift | response | depositBoxCode | string |  | (nullable)
OrderService | openShift | response | bagNumber | string |  | (nullable)
OrderService | openShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | openShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | openShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | openShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | openShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | openShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | openShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | openShift | response | openedAt | string (date-time) | yes
OrderService | openShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | openShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | openShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | openShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | openShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | openShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | openShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | openShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | openShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | openShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | openShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | openShift | response | approvals | array of object
OrderService | openShift | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | openShift | response | approvals[].principalId | string (uuid) | yes
OrderService | openShift | response | approvals[].at | string (date-time) | yes
OrderService | openShift | response | approvals[].reason | string
OrderService | openShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | openTableVisit | request | id | string (uuid) | yes
FnbService | openTableVisit | request | tableId | string (uuid) | yes
FnbService | openTableVisit | request | covers | integer | yes | Captured at seating because it drives split-by-covers at close. (min 1)
FnbService | openTableVisit | request | serverPrincipalId | string (uuid)
FnbService | openTableVisit | request | subjectId | string (uuid)
FnbService | openTableVisit | request | recordedAt | string (date-time) | yes
FnbService | openTableVisit | response | id | string (uuid) | yes
FnbService | openTableVisit | response | tableId | string (uuid) | yes
FnbService | openTableVisit | response | tableLabel | string
FnbService | openTableVisit | response | outletId | string (uuid) | yes
FnbService | openTableVisit | response | covers | integer | yes
FnbService | openTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | openTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders | array of FnbOrder | yes
FnbService | openTableVisit | response | orders[].id | string (uuid) | yes
FnbService | openTableVisit | response | orders[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | openTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | openTableVisit | response | orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | openTableVisit | response | orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | openTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | openTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | openTableVisit | response | orders[].lines | array of object | yes
FnbService | openTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | openTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | openTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | openTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | openTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | openTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | openTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | openTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | openTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | openTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | openTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | openTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | openTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | openTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | openTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | openTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | openTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | openTableVisit | response | orders[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | openTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | openTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | openTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | openTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | openTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | openedAt | string (date-time) | yes
FnbService | openTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | openTableVisit | response | serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | openTableVisit | response | note | string |  | The server's note on the visit (updateTableVisit). (max length 500; read-only; nullable)
FnbService | openTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | overrideAiDecision | request | humanDecision | object | yes
AiService | overrideAiDecision | request | reason | string | yes | (max length 2000)
AiService | overrideAiDecision | response | id | string (uuid) |  | (read-only)
AiService | overrideAiDecision | response | kind | enum (override, pause, resume, cancel, retry, rollback, capabilityPause, capabilityResume) | yes
AiService | overrideAiDecision | response | targetKind | enum (plan, step, decision, capability) | yes
AiService | overrideAiDecision | response | targetRef | string | yes
AiService | overrideAiDecision | response | decisionRecordId | string (uuid) |  | (nullable)
AiService | overrideAiDecision | response | originalDecision | object |  | (nullable)
AiService | overrideAiDecision | response | humanDecision | object |  | (nullable)
AiService | overrideAiDecision | response | reason | string |  | (max length 2000)
AiService | overrideAiDecision | response | principalId | string (uuid) |  | (read-only)
AiService | overrideAiDecision | response | createdAt | string (date-time) |  | (read-only)
AiService | overrideAiDecision | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | overrideAiDecision | param (path) | decisionRecordId | string (uuid) | yes
AiService | overrideAiDecision | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | pauseAiCapability | request | reason | string | yes | (max length 1000)
AiService | pauseAiCapability | request | incidentId | string (uuid) |  | (nullable)
AiService | pauseAiCapability | response | id | string (uuid) |  | (read-only)
AiService | pauseAiCapability | response | capabilityKey | string | yes | Stable key, unique per tenant: assistant.guest, forecast.attendance, risk.transaction, config.assistant, recommend.checkout.
AiService | pauseAiCapability | response | family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …) | yes | The fourteen capabilities of the AI system design (section 1.1), C1 to C14 in order: gateway and model registry, governance decision point, action pipeline and human oversight, knowledge and retrieva…
AiService | pauseAiCapability | response | name | string
AiService | pauseAiCapability | response | description | string |  | (nullable)
AiService | pauseAiCapability | response | ownerPrincipalId | string (uuid) |  | The accountable business owner (AIC-144). (nullable)
AiService | pauseAiCapability | response | businessFunction | string |  | (nullable)
AiService | pauseAiCapability | response | riskClass | AiRiskClass: enum (low, medium, high, critical) | yes | Business, customer, financial, operational, security and compliance impact of a capability or action type (AIC-144, ADM-521).
AiService | pauseAiCapability | response | autonomyCeiling | object |  | The first-release ceiling for this capability (design 3.8 table). (read-only)
AiService | pauseAiCapability | response | autonomyLevel | object | yes | The level in force at this scope.
AiService | pauseAiCapability | response | dataCategories | array of string |  | Data categories the capability reads (ADM-524).
AiService | pauseAiCapability | response | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | pauseAiCapability | response | lifecycle.development | enum (draft, pilot, active, retired)
AiService | pauseAiCapability | response | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | pauseAiCapability | response | lifecycle.production | enum (draft, pilot, active, retired)
AiService | pauseAiCapability | response | degradationMode | enum (rulesOnly, searchOnly, humanHandoff, hidden, failOpen, lastPublished) |  | What the capability does when its model or the service is unavailable (design 3.7, AIC-241).
AiService | pauseAiCapability | response | status | enum (active, paused) |  | Paused by pauseAiCapability: the capability answers from its degradation mode until resumed. (read-only)
AiService | pauseAiCapability | response | pausedReason | string |  | (read-only; nullable)
AiService | pauseAiCapability | response | pausedAt | string (date-time) |  | (read-only; nullable)
AiService | pauseAiCapability | response | updatedAt | string (date-time) |  | (read-only)
AiService | pauseAiCapability | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | pauseAiCapability | param (path) | capabilityKey | string | yes
AiService | pauseAiCapability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | payByLink | request | providerToken | string (password) | yes
OrderService | payByLink | request | email | string (email) |  | Optional, and only to send the ticket. (nullable)
OrderService | payByLink | response | orderId | string (uuid)
OrderService | payByLink | response | entitlementIds | array of string (uuid) |  | Empty at response time (ADAM CR-099): the entitlements are written from order.paid after this answer; read them from the order.
OrderService | payByLink | param (path) | token | string | yes
OrderService | payByLink | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | previewGuidedChoice | request | behaviour | enum (filter, recommend) | yes
WhiteLabelService | previewGuidedChoice | request | questions | array of object | yes | Same shape and bounds as GuidedChoice.questions. (min items 1; max items 4)
WhiteLabelService | previewGuidedChoice | response | combinations | array of object | yes
WhiteLabelService | previewGuidedChoice | response | combinations[].answerKeys | array of string | yes | The answer picked on each question, in order.
WhiteLabelService | previewGuidedChoice | response | combinations[].productsLeft | integer | yes | The venue's products the combination leaves (filter behaviour); 0 is the case to fix. (min 0)
WhiteLabelService | previewGuidedChoice | response | combinations[].sampleProductIds | array of string (uuid) |  | (max items 3)
WhiteLabelService | previewGuidedChoice | response | combinations[].target | object |  | The result the combination ends on (recommend behaviour), as the last answer's target. (nullable)
WhiteLabelService | previewGuidedChoice | param (path) | venueId | string (uuid) | yes
OrderService | previewProductTickets | param (path) | productId | string (uuid) | yes
OrderService | previewProductTickets | param (query) | locale | string |  | The language to render in; the venue's default when omitted.
FnbService | printOrderLabel | response | ticketId | string (uuid) | yes
FnbService | printOrderLabel | response | orderNumber | string | yes
FnbService | printOrderLabel | response | guestName | string |  | (nullable)
FnbService | printOrderLabel | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | printOrderLabel | response | deliveryLabel | string |  | Where it is going, as a runner would read it. (nullable)
FnbService | printOrderLabel | response | buzzerCode | string |  | (nullable)
FnbService | printOrderLabel | response | lines | array of object | yes
FnbService | printOrderLabel | response | lines[].name | string | yes
FnbService | printOrderLabel | response | lines[].quantity | integer | yes
FnbService | printOrderLabel | response | lines[].modifiers | array of string
FnbService | printOrderLabel | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | printOrderLabel | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) | yes | Every allergen on the order, together.
FnbService | printOrderLabel | param (path) | ticketId | string (uuid) | yes
FnbService | printOrderLabel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | prioritiseKitchenTicket | request | reason | string | yes | (min length 3; max length 500)
FnbService | prioritiseKitchenTicket | request | priority | integer |  | Absent means the top of the queue (decided 28 September, audit R125 (2)): the ticket takes the highest priority on the rail. (min 0; max 100; default 100)
FnbService | prioritiseKitchenTicket | response | id | string (uuid) | yes
FnbService | prioritiseKitchenTicket | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | prioritiseKitchenTicket | response | orderNumber | string
FnbService | prioritiseKitchenTicket | response | outletId | string (uuid) | yes
FnbService | prioritiseKitchenTicket | response | tableLabel | string |  | (nullable)
FnbService | prioritiseKitchenTicket | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | prioritiseKitchenTicket | response | coursing | object |  | BL-131. (nullable)
FnbService | prioritiseKitchenTicket | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | prioritiseKitchenTicket | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | prioritiseKitchenTicket | response | priority | integer |  | Higher fires sooner.
FnbService | prioritiseKitchenTicket | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | prioritiseKitchenTicket | response | prioritiseReason | string |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines | array of object | yes
FnbService | prioritiseKitchenTicket | response | lines[].lineId | string (uuid) | yes
FnbService | prioritiseKitchenTicket | response | lines[].name | string | yes
FnbService | prioritiseKitchenTicket | response | lines[].quantity | integer | yes
FnbService | prioritiseKitchenTicket | response | lines[].modifiers | array of string
FnbService | prioritiseKitchenTicket | response | lines[].note | string |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | prioritiseKitchenTicket | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | prioritiseKitchenTicket | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | prioritiseKitchenTicket | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | prioritiseKitchenTicket | response | lines[].course | integer |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | prioritiseKitchenTicket | response | createdAt | string (date-time) | yes
FnbService | prioritiseKitchenTicket | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | prioritiseKitchenTicket | response | elapsedSeconds | integer
FnbService | prioritiseKitchenTicket | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | prioritiseKitchenTicket | param (path) | ticketId | string (uuid) | yes
FnbService | prioritiseKitchenTicket | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | promoteAiRelease | request | toStage | enum (canary, production) |  | (nullable)
AiService | promoteAiRelease | request | canaryScope | object |  | (nullable)
AiService | promoteAiRelease | request | note | string |  | (max length 1000; nullable)
AiService | promoteAiRelease | response | id | string (uuid) |  | (read-only)
AiService | promoteAiRelease | response | capabilityKey | string | yes
AiService | promoteAiRelease | response | artefactKind | enum (model, prompt, routing, embedding, retrieval, rule) | yes
AiService | promoteAiRelease | response | candidateRef | string | yes
AiService | promoteAiRelease | response | currentRef | string |  | What production runs now: the rule, or the previously promoted artefact. (nullable)
AiService | promoteAiRelease | response | previousRef | string |  | (read-only; nullable)
AiService | promoteAiRelease | response | layer | enum (platform, tenant) | yes
AiService | promoteAiRelease | response | module | object |  | Whose AI this release is, and so who promotes it (Chinmay, 2 October, workbook Q7: "AI release promotion goes to whoever holds it"; CHG-FUP-004). (nullable)
AiService | promoteAiRelease | response | suggestionKind | object |  | Where the capability answers a requestSuggestion kind: promotion rewrites that kind's assignment in AiPolicy.suggestionProviders. (nullable)
AiService | promoteAiRelease | response | stage | enum (draft, offlineEval, shadow, canary, production, monitored, rolledBack, rejected) | yes | (read-only)
AiService | promoteAiRelease | response | shadowStartedAt | string (date-time) |  | (read-only; nullable)
AiService | promoteAiRelease | response | gatePassedAt | string (date-time) |  | When the shadow run passed its gate and promotionReady was raised. (read-only; nullable)
AiService | promoteAiRelease | response | canaryScope | object |  | Venues or share of traffic in canary. (nullable)
AiService | promoteAiRelease | response | promotedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | promoteAiRelease | response | promotedAt | string (date-time) |  | (read-only; nullable)
AiService | promoteAiRelease | response | rolledBackByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | promoteAiRelease | response | rolledBackAt | string (date-time) |  | (read-only; nullable)
AiService | promoteAiRelease | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | promoteAiRelease | param (path) | releaseId | string (uuid) | yes
AiService | promoteAiRelease | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | proposeGuidedChoice | request | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | request | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | proposeGuidedChoice | request | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | proposeGuidedChoice | request | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | proposeGuidedChoice | request | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | proposeGuidedChoice | request | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | proposeGuidedChoice | request | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | proposeGuidedChoice | request | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | proposeGuidedChoice | request | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | request | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | request | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | proposeGuidedChoice | request | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | proposeGuidedChoice | request | status | object | yes | (read-only)
WhiteLabelService | proposeGuidedChoice | request | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | proposeGuidedChoice | request | suggestionRef | string | yes | The id of the ai AiGuidedChoiceSuggestion that produced the proposal (suggestGuidedChoice); ai getGuidedChoiceSuggestion reads it back.
WhiteLabelService | proposeGuidedChoice | request | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | request | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | proposeGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | proposeGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | proposeGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | proposeGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | proposeGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | proposeGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | proposeGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | proposeGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | proposeGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | proposeGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | proposeGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | proposeGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | proposeGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | proposeGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | proposeMarketingContent | request | targetKind | enum (messageTemplate, subjectLine, notificationWording, contentBlock, contentPage, banner, promoBlock, homepageSection) | yes
AiService | proposeMarketingContent | request | targetRef | string |  | The template, campaign, block, page, banner or promo block the draft is for. (nullable)
AiService | proposeMarketingContent | request | channel | enum (email, sms, push, whatsapp, inApp, web, app) |  | Sets the length and form limits (an SMS segment, a push title) the draft must meet. (nullable)
AiService | proposeMarketingContent | request | brief | string | yes | What the content is for, in the author's words. (min length 10; max length 4000)
AiService | proposeMarketingContent | request | objective | enum (awareness, conversion, retention, reactivation, information) |  | (nullable)
AiService | proposeMarketingContent | request | tone | string |  | (max length 200; nullable)
AiService | proposeMarketingContent | request | locales | array of string | yes | (min items 1; max items 10)
AiService | proposeMarketingContent | request | variants | integer |  | (min 1; max 5; default 1)
AiService | proposeMarketingContent | request | glossaryRef | string |  | Terms that must not be changed or translated, as for proposeTranslations. (nullable)
AiService | proposeMarketingContent | request | groundingRefs | array of string |  | Products, events, offers or pages the text may cite, read as the caller. (max items 50)
AiService | proposeMarketingContent | response | targetKind | enum (messageTemplate, subjectLine, notificationWording, contentBlock, contentPage, banner, promoBlock, homepageSection) | yes
AiService | proposeMarketingContent | response | targetRef | string |  | (nullable)
AiService | proposeMarketingContent | response | drafts | array of object | yes
AiService | proposeMarketingContent | response | drafts[].proposedActionId | string (uuid) | yes | The ai.proposed_action row; decideProposedAction takes it.
AiService | proposeMarketingContent | response | drafts[].locale | string | yes
AiService | proposeMarketingContent | response | drafts[].variantNumber | integer | yes | (min 1; max 5)
AiService | proposeMarketingContent | response | drafts[].targetContract | string |  | marketing-crm or white-label.
AiService | proposeMarketingContent | response | drafts[].targetOperation | string |  | The owner's save operation the draft is shaped for.
AiService | proposeMarketingContent | response | drafts[].fields | object | yes | The drafted text by field, e.g.
AiService | proposeMarketingContent | response | drafts[].glossaryViolations | array of string |  | Glossary terms the draft changed.
AiService | proposeMarketingContent | response | drafts[].decisionRecordId | string (uuid)
AiService | proposeMarketingContent | response | traceId | string
AiService | proposeMarketingContent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | proposeTranslations | request | targetLocale | string | yes
AiService | proposeTranslations | request | scope | enum (allGaps, contentBlocks, productNames, emailTemplates, messageTemplates) |  | messageTemplates (29 September, build; 22.9.18) covers every channel of a marketing-crm message template: email, SMS, push, WhatsApp and in-app.
AiService | proposeTranslations | request | glossaryRef | string |  | Terms that must not be translated — a venue's ride names, its brand, its membership tiers. (nullable)
AiService | proposeTranslations | response | targetLocale | string | yes
AiService | proposeTranslations | response | translationJobId | string (uuid) |  | The job to follow with getTranslationProposals (contract gap CHG-WIR-017, CMS-011; CHG-CSA-045). (read-only)
AiService | proposeTranslations | response | status | enum (running, completed, failed) |  | running while drafts are still being written; drafts then holds those done so far. (read-only)
AiService | proposeTranslations | response | drafts | array of object | yes
AiService | proposeTranslations | response | drafts[].proposalId | string (uuid) | yes | The ai.proposed_action id of this draft (r8 walk of ticket 27926).
AiService | proposeTranslations | response | drafts[].fieldPath | string | yes | Where the draft goes inside the target, as a dotted path in the target's own body, for example localeVariants.ar.title on a content block or name.ar on a product.
AiService | proposeTranslations | response | drafts[].targetKind | enum (contentBlock, productName, emailTemplate, messageTemplate) | yes
AiService | proposeTranslations | response | drafts[].targetRef | string | yes | The id of the block, product or template the draft sits on.
AiService | proposeTranslations | response | drafts[].draftText | string | yes | The first-pass translation, as saved on the draft.
AiService | proposeTranslations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | proposeVenueLabels | param (path) | mapId | string (uuid) | yes
AiService | proposeVenueLabels | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | publishAiGovernancePolicy | response | id | string (uuid) |  | (read-only)
AiService | publishAiGovernancePolicy | response | policyId | string (uuid) | yes
AiService | publishAiGovernancePolicy | response | version | integer | yes | (min 1)
AiService | publishAiGovernancePolicy | response | status | enum (draft, simulated, published, superseded) | yes
AiService | publishAiGovernancePolicy | response | rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | publishAiGovernancePolicy | response | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | publishAiGovernancePolicy | response | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | publishAiGovernancePolicy | response | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | publishAiGovernancePolicy | response | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | publishAiGovernancePolicy | response | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | publishAiGovernancePolicy | response | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | publishAiGovernancePolicy | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | publishAiGovernancePolicy | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | publishAiGovernancePolicy | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | publishAiGovernancePolicy | response | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | publishAiGovernancePolicy | response | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | publishAiGovernancePolicy | response | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | publishAiGovernancePolicy | response | changeNote | string |  | (nullable)
AiService | publishAiGovernancePolicy | response | simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | publishAiGovernancePolicy | response | draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | publishAiGovernancePolicy | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | publishAiGovernancePolicy | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | publishAiGovernancePolicy | response | supersededAt | string (date-time) |  | (read-only; nullable)
AiService | publishAiGovernancePolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | publishAiGovernancePolicy | param (path) | versionId | string (uuid) | yes
AiService | publishAiGovernancePolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | publishBundle | request | venueId | string (uuid) | yes
CatalogueService | publishBundle | request | note | string |  | (max length 500)
CatalogueService | publishBundle | request | staleAfterHours | integer |  | How long a terminal may trade on this bundle before refusing. (min 1)
CatalogueService | publishBundle | response | version | string | yes
CatalogueService | publishBundle | response | venueId | string (uuid) | yes
CatalogueService | publishBundle | response | publishedAt | string (date-time) | yes
CatalogueService | publishBundle | response | publishedBy | string (uuid) | yes
CatalogueService | publishBundle | response | contentHash | string | yes
CatalogueService | publishBundle | response | signatureKeyId | string |  | Key that signed this bundle.
CatalogueService | publishBundle | response | staleAfter | string (date-time) | yes
CatalogueService | publishBundle | response | sizeBytes | integer | yes
CatalogueService | publishBundle | response | note | string
CatalogueService | publishBundle | response | appliedByWorkstations | integer
CatalogueService | publishBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | publishChannelAvailability | request | channels | array of object |  | Channels the product is published on, with channel-specific sites, POS groups, venues and effective dates
CatalogueService | publishChannelAvailability | request | channels[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | publishChannelAvailability | request | channels[].enabled | boolean
CatalogueService | publishChannelAvailability | request | channels[].siteIds | array of string |  | Specific sites/webstores; empty = all
CatalogueService | publishChannelAvailability | request | channels[].posGroupIds | array of string |  | Specific POS groups; empty = all
CatalogueService | publishChannelAvailability | request | channels[].venueIds | array of string |  | Availability by venue; empty = all the product's venues
CatalogueService | publishChannelAvailability | request | channels[].effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | publishChannelAvailability | request | channels[].effectiveTo | string (date-time) |  | (nullable)
CatalogueService | publishChannelAvailability | request | productId | string (uuid) |  | Product id
CatalogueService | publishChannelAvailability | response | channels | array of object |  | Channels the product is published on, with channel-specific sites, POS groups, venues and effective dates
CatalogueService | publishChannelAvailability | response | channels[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | publishChannelAvailability | response | channels[].enabled | boolean
CatalogueService | publishChannelAvailability | response | channels[].siteIds | array of string |  | Specific sites/webstores; empty = all
CatalogueService | publishChannelAvailability | response | channels[].posGroupIds | array of string |  | Specific POS groups; empty = all
CatalogueService | publishChannelAvailability | response | channels[].venueIds | array of string |  | Availability by venue; empty = all the product's venues
CatalogueService | publishChannelAvailability | response | channels[].effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | publishChannelAvailability | response | channels[].effectiveTo | string (date-time) |  | (nullable)
CatalogueService | publishChannelAvailability | response | publicationPreview | array of object |  | Preview of where the product will actually be on sale
CatalogueService | publishChannelAvailability | response | publicationPreview[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | publishChannelAvailability | response | publicationPreview[].venueId | string
CatalogueService | publishChannelAvailability | response | publicationPreview[].exposed | boolean
CatalogueService | publishChannelAvailability | response | publicationPreview[].reason | string |  | (nullable)
CatalogueService | publishChannelAvailability | response | validationIssues | array of object |  | Missing channel dependencies (decided 29 September, readiness close-out)
CatalogueService | publishChannelAvailability | response | validationIssues[].code | enum (channelNotConfigured, noPriceForChannel, noCapacityAllocation, productNotApproved, venueNotAssigned)
CatalogueService | publishChannelAvailability | response | validationIssues[].message | string
CatalogueService | publishChannelAvailability | response | productId | string (uuid) |  | Product id
CatalogueService | publishChannelAvailability | response | issuedEntitlementsUnaffected | integer |  | Valid issued tickets/entitlements that remain valid whatever the channel change (pack p.10 Important Rule)
CatalogueService | publishChannelAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | publishChannelReadinessValidation | request | channelId | string |  | Channel ID
CatalogueService | publishChannelReadinessValidation | request | action | enum (validate, preview, submitForApproval, scheduleActivation, activate, returnForChanges, suspend) |  | Publication Action (pack p.17)
CatalogueService | publishChannelReadinessValidation | request | scheduledAt | string (date-time) |  | Activation time for scheduleActivation (nullable)
CatalogueService | publishChannelReadinessValidation | request | reason | string |  | Reason: mandatory when overriding warnings or returning for changes (nullable)
CatalogueService | publishChannelReadinessValidation | request | overrideWarnings | boolean |  | Proceed despite warnings (needs SALES_CHANNEL_OVERRIDE and a reason; ADAM CR-211); critical issues cannot be overridden
CatalogueService | publishChannelReadinessValidation | request | approvalRequestId | string (uuid) |  | The approved approval request submitForApproval raised; required by scheduleActivation and activate from pendingApproval, which are refused 409 approval-required without an approved one (ADAM CR-211). (nullable)
CatalogueService | publishChannelReadinessValidation | response | channelId | string |  | Channel: the configured channel's ID from the Sales Channel Command Center (ADM-258)
CatalogueService | publishChannelReadinessValidation | response | status | enum (draft, pendingApproval, scheduled, active, suspended) |  | Status after the action: the channel's SalesChannelProfile.status, the five values of the state model and the DDL (ADAM CR-211, option A; CHG-R10CAT-003).
CatalogueService | publishChannelReadinessValidation | response | approvalRequestId | string (uuid) |  | The approval request submitForApproval raised, to send back with scheduleActivation or activate once approved (ADAM CR-211). (nullable)
CatalogueService | publishChannelReadinessValidation | response | preview | object |  | The effective chain preview returns, Product -> Channel -> Customer -> Price -> Capacity -> Payment -> Fulfillment, one step per link in that order; null for any other action (ADAM CR-211). (nullable)
CatalogueService | publishChannelReadinessValidation | response | preview.steps | array of object
CatalogueService | publishChannelReadinessValidation | response | preview.steps[].stage | enum (product, channel, customer, price, capacity, payment, fulfillment) | yes
CatalogueService | publishChannelReadinessValidation | response | preview.steps[].summary | string |  | What is in effect at this link for the channel.
CatalogueService | publishChannelReadinessValidation | response | preview.steps[].result | enum (passed, warning, failed, notRequired)
CatalogueService | publishChannelReadinessValidation | response | readinessScore | number |  | Channel Readiness % (min 0; max 100)
CatalogueService | publishChannelReadinessValidation | response | checklist | array of object |  | Readiness Checklist (pack p.16) with each area's score (p.17)
CatalogueService | publishChannelReadinessValidation | response | checklist[].area | enum (channelProfile, products, pricing, capacity, schedule, eligibility, salesRules, payment, …)
CatalogueService | publishChannelReadinessValidation | response | checklist[].result | enum (passed, warning, failed, notRequired)
CatalogueService | publishChannelReadinessValidation | response | checklist[].scorePercent | number
CatalogueService | publishChannelReadinessValidation | response | issues | array of object |  | Issues by Issue Severity (pack p.17)
CatalogueService | publishChannelReadinessValidation | response | issues[].severity | enum (critical, high, medium, low, recommendation)
CatalogueService | publishChannelReadinessValidation | response | issues[].area | enum (channelProfile, products, pricing, capacity, schedule, eligibility, salesRules, payment, …)
CatalogueService | publishChannelReadinessValidation | response | issues[].code | string
CatalogueService | publishChannelReadinessValidation | response | issues[].message | string
CatalogueService | publishChannelReadinessValidation | response | aiInsights | array of string |  | AI Validation findings (pack p.17, e.g.
CatalogueService | publishChannelReadinessValidation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | publishContentBlock | request | publishAt | string (date-time) |  | (nullable)
WhiteLabelService | publishContentBlock | request | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | publishContentBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | publishContentBlock | response | pageId | string (uuid) |  | (nullable)
WhiteLabelService | publishContentBlock | response | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | publishContentBlock | response | position | integer
WhiteLabelService | publishContentBlock | response | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | publishContentBlock | response | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | publishContentBlock | response | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | publishContentBlock | response | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | publishContentBlock | response | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | publishContentBlock | response | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | publishContentBlock | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | publishContentBlock | response | reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step of publishContentBlock, where the tenant's publish-review policy is on (r8 walk of ticket 27919). (default notRequired; read-only)
WhiteLabelService | publishContentBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | publishContentBlock | param (path) | blockId | string (uuid) | yes
WhiteLabelService | publishContentBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | publishForecastVersion | request | note | string |  | (max length 1000; nullable)
AiService | publishForecastVersion | response | id | string (uuid) |  | (read-only)
AiService | publishForecastVersion | response | definitionId | string (uuid) | yes
AiService | publishForecastVersion | response | versionNumber | integer | yes | (min 1)
AiService | publishForecastVersion | response | module | object |  | The module of the version's definition (AiForecastDefinition.module), copied when the version is produced; the module whose AI publish permission publishForecastVersion requires (CHG-FUP-004). (read-only)
AiService | publishForecastVersion | response | status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | publishForecastVersion | response | basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | publishForecastVersion | response | maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | publishForecastVersion | response | maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | publishForecastVersion | response | maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | publishForecastVersion | response | maturity.sources | array of object
AiService | publishForecastVersion | response | maturity.sources[].source | enum (venueSettings, startingPattern, calendar, weather, bookingsOnHand, ownHistory, importedHistory, configuration, …) | yes
AiService | publishForecastVersion | response | maturity.sources[].detail | string |  | e.g. (nullable)
AiService | publishForecastVersion | response | maturity.sources[].observations | integer |  | (nullable)
AiService | publishForecastVersion | response | maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | publishForecastVersion | response | maturity.limitedHistory | boolean
AiService | publishForecastVersion | response | maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | publishForecastVersion | response | maturity.nextStage.stage | enum (learning, established, learned)
AiService | publishForecastVersion | response | maturity.nextStage.needs | string
AiService | publishForecastVersion | response | maturity.nextStage.expectedBy | string (date) |  | (nullable)
AiService | publishForecastVersion | response | producerRef | string
AiService | publishForecastVersion | response | modelVersion | string |  | (nullable)
AiService | publishForecastVersion | response | dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | publishForecastVersion | response | horizonStart | string (date-time)
AiService | publishForecastVersion | response | horizonEnd | string (date-time)
AiService | publishForecastVersion | response | qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | publishForecastVersion | response | publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | publishForecastVersion | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | publishForecastVersion | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | publishForecastVersion | response | createdAt | string (date-time) |  | (read-only)
AiService | publishForecastVersion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | publishForecastVersion | param (path) | versionId | string (uuid) | yes
AiService | publishForecastVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | publishGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | publishGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | publishGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | publishGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | publishGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | publishGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | publishGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | publishGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | publishGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | publishGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | publishGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | publishGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | publishGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | publishGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | publishGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | publishGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | publishGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | publishGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | publishGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | publishGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | publishGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | publishMenu | request | effectiveAt | string (date-time) |  | Absent or null publishes now. (nullable)
FnbService | publishMenu | request | channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where the version goes live.
FnbService | publishMenu | request | note | string |  | (nullable)
FnbService | publishMenu | response | id | string (uuid) | yes | (read-only)
FnbService | publishMenu | response | menuId | string (uuid) | yes
FnbService | publishMenu | response | version | integer | yes | (min 1)
FnbService | publishMenu | response | status | enum (draft, scheduled, live, superseded) | yes
FnbService | publishMenu | response | effectiveAt | string (date-time) |  | (nullable)
FnbService | publishMenu | response | publishedAt | string (date-time) |  | (nullable)
FnbService | publishMenu | response | publishedByPrincipalId | string (uuid) |  | (nullable)
FnbService | publishMenu | response | restoredFromVersion | integer |  | Set on a version written by rollbackMenu — the version it restored. (nullable)
FnbService | publishMenu | response | channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
FnbService | publishMenu | response | note | string |  | (nullable)
FnbService | publishMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | publishMenu | response | availability.daysOfWeek | array of integer
FnbService | publishMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | publishMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | publishMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | publishMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | publishMenu | response | sections | array of MenuSection |  | The sections and items as published.
FnbService | publishMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | publishMenu | response | sections[].code | string | yes
FnbService | publishMenu | response | sections[].name | string | yes
FnbService | publishMenu | response | sections[].sortOrder | integer | yes
FnbService | publishMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | publishMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | publishMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | publishMenu | response | sections[].items[].name | string | yes
FnbService | publishMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | publishMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | publishMenu | response | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | publishMenu | response | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | publishMenu | response | sections[].items[].sortOrder | integer
FnbService | publishMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | publishMenu | response | sections[].items[].stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | publishMenu | response | sections[].items[].menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | publishMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | publishMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | publishMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | publishMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | publishMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | publishMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | publishMenu | response | sections[].items[].unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | publishMenu | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | publishMenu | param (path) | menuId | string (uuid) | yes
FnbService | publishMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | publishPromotion | response | code | string | yes | Unique per tenant (6 October 2026, CHG-R4-015; the rule of audit R108 for configuration codes). (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | publishPromotion | response | name | string | yes | (max length 200)
CatalogueService | publishPromotion | response | nameLocalised | object |  | The promotion's name in each of the tenant's enabled languages (ADAM CR-231, option A, decided 25 October 2026; CHG-R10CAT-012), keyed by ISO 639-1 code, as Product.nameLocalised. (nullable)
CatalogueService | publishPromotion | response | description | string |  | (max length 1000)
CatalogueService | publishPromotion | response | descriptionLocalised | object |  | The description in each enabled language, as nameLocalised; falls back to description. (nullable)
CatalogueService | publishPromotion | response | label | object |  | The guest-facing label, the pill on the offer card (BUNDLE, RENTAL, MEMBERSHIP, SEASON, PARKING on WEB-032), per language as nameLocalised (ADAM CR-225 and CR-231, option A, decided 25 October 2026;… (nullable)
CatalogueService | publishPromotion | response | venues | array of PromotionVenue |  | Where a guest may use the offer, as the offer card's venue line shows it (ADAM CR-225, option A, decided 25 October 2026; CHG-R10CAT-012).
CatalogueService | publishPromotion | response | venues[].venueId | string (uuid) | yes | A venue node of the tenant (checked with tenancy#scopeRecords on write).
CatalogueService | publishPromotion | response | venues[].name | string | yes | The venue's name as the back office gives it for guests. (max length 200)
CatalogueService | publishPromotion | response | venues[].nameLocalised | object |  | The name in each enabled language; falls back to name (ADAM CR-231). (nullable)
CatalogueService | publishPromotion | response | venueId | string (uuid) | yes
CatalogueService | publishPromotion | response | discount | Discount | yes
CatalogueService | publishPromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | publishPromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | publishPromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | publishPromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | publishPromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | publishPromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | publishPromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | publishPromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | publishPromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | publishPromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | publishPromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | publishPromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | publishPromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.productKinds | array of string
CatalogueService | publishPromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | publishPromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | publishPromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | publishPromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | publishPromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | publishPromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | publishPromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | publishPromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | publishPromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | publishPromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | publishPromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | publishPromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | publishPromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | publishPromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | publishPromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | publishPromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | publishPromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | publishPromotion | response | validFrom | string (date-time) | yes
CatalogueService | publishPromotion | response | validTo | string (date-time)
CatalogueService | publishPromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | publishPromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | publishPromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | publishPromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | publishPromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | publishPromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | publishPromotion | response | id | string (uuid) | yes
CatalogueService | publishPromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | publishPromotion | response | isPaused | boolean
CatalogueService | publishPromotion | response | redemptionCount | integer
CatalogueService | publishPromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | publishPromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | publishPromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | publishPromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | publishPromptTemplate | request | layer | enum (platform, tenant) | yes
AiService | publishPromptTemplate | request | task | string | yes
AiService | publishPromptTemplate | request | body | string | yes
AiService | publishPromptTemplate | request | variables | array of string
AiService | publishPromptTemplate | request | outputSchema | object |  | (nullable)
AiService | publishPromptTemplate | response | id | string (uuid) |  | (read-only)
AiService | publishPromptTemplate | response | templateKey | string | yes
AiService | publishPromptTemplate | response | version | integer | yes | (min 1)
AiService | publishPromptTemplate | response | layer | enum (platform, tenant) | yes
AiService | publishPromptTemplate | response | task | string | yes | The gateway task it serves (design 3.3), e.g.
AiService | publishPromptTemplate | response | body | string |  | The template text.
AiService | publishPromptTemplate | response | variables | array of string
AiService | publishPromptTemplate | response | outputSchema | object |  | JSON Schema the structured output must satisfy, where the task has one. (nullable)
AiService | publishPromptTemplate | response | status | enum (draft, published, retired) | yes
AiService | publishPromptTemplate | response | contentHash | string |  | (read-only)
AiService | publishPromptTemplate | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | publishPromptTemplate | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | publishPromptTemplate | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | publishPromptTemplate | param (path) | templateKey | string | yes
AiService | publishPromptTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | publishTenantConfig | request | note | string | yes | (min length 3; max length 500)
WhiteLabelService | publishTenantConfig | request | scheduledFor | string (date-time) |  | Publish at a future time.
WhiteLabelService | publishTenantConfig | response | version | string | yes | Named by the server (ADAM CR-154; CHG-CRA-004): the next integer for the tenant, 1, 2, ..., taken in the publish transaction. (read-only)
WhiteLabelService | publishTenantConfig | response | publishedAt | string (date-time) | yes
WhiteLabelService | publishTenantConfig | response | publishedByPrincipalId | string (uuid) | yes
WhiteLabelService | publishTenantConfig | response | publishedByName | string
WhiteLabelService | publishTenantConfig | response | note | string | yes
WhiteLabelService | publishTenantConfig | response | reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step, where the tenant's publish-review policy is on (CHG-CSA-042). (default notRequired; read-only)
WhiteLabelService | publishTenantConfig | response | approvalRequestId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | publishTenantConfig | response | isCurrent | boolean | yes
WhiteLabelService | publishTenantConfig | response | scheduledFor | string (date-time) |  | (nullable)
WhiteLabelService | publishTenantConfig | response | activationFailedAt | string (date-time) |  | When the scheduled activation of this version failed its validation again; null when it has not failed (R8 blocker IDENTITY-C63). (read-only; nullable)
WhiteLabelService | publishTenantConfig | response | activationFailure | string |  | Why the scheduled activation failed, in the validation's words (R8 blocker IDENTITY-C63). (max length 2000; read-only; nullable)
WhiteLabelService | publishTenantConfig | response | contentHash | string
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges | array of object |  | Changes in this version that will not reach guests until the next store release.
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges[].area | string
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges[].description | string
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges[].platforms | array of enum (ios, android, web)
WhiteLabelService | publishTenantConfig | response | snapshot | object |  | What this version contained. (read-only)
WhiteLabelService | publishTenantConfig | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | publishTenantConfig | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | publishTransportTimetable | response | name | string | yes | (max length 120)
VenueOpsService | publishTransportTimetable | response | validFrom | string (date) | yes
VenueOpsService | publishTransportTimetable | response | validTo | string (date) |  | (nullable)
VenueOpsService | publishTransportTimetable | response | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | publishTransportTimetable | response | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | publishTransportTimetable | response | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | publishTransportTimetable | response | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | publishTransportTimetable | response | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | publishTransportTimetable | response | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | publishTransportTimetable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | publishTransportTimetable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | publishTransportTimetable | response | status | TransportTimetableStatus: enum (draft, published, superseded, withdrawn) | yes
VenueOpsService | publishTransportTimetable | response | publishedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | publishTransportTimetable | response | releasedThrough | string (date) |  | The last date whose departures have been generated. (read-only; nullable)
VenueOpsService | publishTransportTimetable | response | supersededById | string (uuid) |  | (read-only; nullable)
VenueOpsService | publishTransportTimetable | param (path) | timetableId | string (uuid) | yes
VenueOpsService | publishTransportTimetable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | publishVenueMap | request | note | string |  | (max length 300)
VenueOpsService | publishVenueMap | response | id | string (uuid) | yes | (read-only)
VenueOpsService | publishVenueMap | response | name | string | yes
VenueOpsService | publishVenueMap | response | venueId | string (uuid) | yes
VenueOpsService | publishVenueMap | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | publishVenueMap | response | kind | enum (park, floor, zone, parking)
VenueOpsService | publishVenueMap | response | floorLevel | integer |  | (nullable)
VenueOpsService | publishVenueMap | response | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | publishVenueMap | response | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | publishVenueMap | response | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | publishVenueMap | response | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | publishVenueMap | response | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | publishVenueMap | response | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | publishVenueMap | response | baseImageAlignment.imageWidthPx | integer
VenueOpsService | publishVenueMap | response | baseImageAlignment.imageHeightPx | integer
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].planX | number
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].planY | number
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].imageX | number
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].imageY | number
VenueOpsService | publishVenueMap | response | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | publishVenueMap | response | boundsGeoJson | string |  | (nullable)
VenueOpsService | publishVenueMap | response | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | publishVenueMap | response | modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | publishVenueMap | response | navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | publishVenueMap | response | modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | publishVenueMap | response | modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | publishVenueMap | response | modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | publishVenueMap | response | modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | publishVenueMap | response | modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | publishVenueMap | response | modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints[].label | string | yes
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints[].x | number | yes
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints[].z | number | yes
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints[].lat | number | yes
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints[].lng | number | yes
VenueOpsService | publishVenueMap | response | modelTransform.controlPoints[].residualMetres | number |  | Measured at import. (read-only; nullable)
VenueOpsService | publishVenueMap | response | model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | publishVenueMap | param (path) | mapId | string (uuid) | yes
VenueOpsService | publishVenueMap | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | publishWalletConfiguration | request | mode | enum (validateOnly, publish) |  | (default validateOnly)
WalletService | publishWalletConfiguration | request | note | string |  | (nullable)
WalletService | publishWalletConfiguration | response | version | integer
WalletService | publishWalletConfiguration | response | publishedAt | string (date-time) |  | (nullable)
WalletService | publishWalletConfiguration | response | publishedBy | string (uuid) |  | (nullable)
WalletService | publishWalletConfiguration | response | note | string |  | (nullable)
WalletService | publishWalletConfiguration | response | findings | array of object
WalletService | publishWalletConfiguration | response | findings[].severity | enum (blocking, warning)
WalletService | publishWalletConfiguration | response | findings[].code | string
WalletService | publishWalletConfiguration | response | findings[].message | string
WalletService | publishWalletConfiguration | response | scopePath | string
WalletService | publishWalletConfiguration | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | quoteTransportFare | request | routeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | passengers | array of object |  | Omitted, one of the default type. (max items 10)
VenueOpsService | quoteTransportFare | request | passengers[].code | string | yes
VenueOpsService | quoteTransportFare | request | passengers[].count | integer | yes | (min 0; max 99)
VenueOpsService | quoteTransportFare | request | passTypeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | travelAt | string (date-time) |  | When the trip is travelled (the departure's time; for a pass, its first valid day).
VenueOpsService | quoteTransportFare | request | at | string (date-time) |  | Deprecated on 3 October (CHG-RUL-012): quotes price at travel time, so send travelAt.
VenueOpsService | quoteTransportFare | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | response | stopsTravelled | integer | yes | (min 1)
VenueOpsService | quoteTransportFare | response | adultFare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | lines | array of object
VenueOpsService | quoteTransportFare | response | lines[].code | string | yes
VenueOpsService | quoteTransportFare | response | lines[].catalogueVariantId | string (uuid)
VenueOpsService | quoteTransportFare | response | lines[].count | integer | yes
VenueOpsService | quoteTransportFare | response | lines[].unitPrice | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | passTypeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | response | saving | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | saving.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | saving.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | saving.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | raiseMyCase | request | id | string (uuid) | yes | Created on the device, so a retry after a dropped connection carries the same id and is the same case.
MarketingService | raiseMyCase | request | kind | CaseKind: enum (lostProperty, complaint, question, accessibility, refundRequest, other) | yes | What the guest says the case is about, in their words rather than the venue's taxonomy — raiseMyCase asks for it and categoryId is what staff file it under.
MarketingService | raiseMyCase | request | summary | string | yes | Lands in Case.subject — the case's one-line title. (max length 200)
MarketingService | raiseMyCase | request | recordedAt | string (date-time) | yes | Device time when the guest raised it.
MarketingService | raiseMyCase | request | detail | string |  | Required, and not empty, when kind is other (decided 28 September, audit R222); a 400 otherwise. (nullable)
MarketingService | raiseMyCase | request | venueId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | request | orderRef | string |  | (nullable)
MarketingService | raiseMyCase | response | id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | raiseMyCase | response | caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | raiseMyCase | response | subjectId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | raiseMyCase | response | subject | string | yes | The case's one-line title, not a person.
MarketingService | raiseMyCase | response | kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | raiseMyCase | response | channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | raiseMyCase | response | recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | raiseMyCase | response | syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | raiseMyCase | response | categoryId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | raiseMyCase | response | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | raiseMyCase | response | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | raiseMyCase | response | priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | raiseMyCase | response | assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | venueId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | relatedOrderId | string |  | (nullable)
MarketingService | raiseMyCase | response | slaDueAt | string (date-time) |  | (nullable)
MarketingService | raiseMyCase | response | isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | raiseMyCase | response | slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | raiseMyCase | response | escalationCount | integer
MarketingService | raiseMyCase | response | createdAt | string (date-time) | yes
MarketingService | raiseMyCase | response | resolvedAt | string (date-time) |  | (nullable)
MarketingService | raiseMyCase | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | rebalanceStationLoad | request | moves | array of object | yes
FnbService | rebalanceStationLoad | request | moves[].fromStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | request | moves[].toStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | request | moves[].categoryIds | array of string (uuid)
FnbService | rebalanceStationLoad | request | revertAt | string (date-time) |  | (nullable)
FnbService | rebalanceStationLoad | response | moves | array of object | yes
FnbService | rebalanceStationLoad | response | moves[].fromStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | response | moves[].toStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | response | moves[].categoryIds | array of string (uuid)
FnbService | rebalanceStationLoad | response | revertAt | string (date-time) |  | (nullable)
FnbService | rebalanceStationLoad | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | recallKitchenTicket | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | recallKitchenTicket | response | id | string (uuid) | yes
FnbService | recallKitchenTicket | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | recallKitchenTicket | response | orderNumber | string
FnbService | recallKitchenTicket | response | outletId | string (uuid) | yes
FnbService | recallKitchenTicket | response | tableLabel | string |  | (nullable)
FnbService | recallKitchenTicket | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | recallKitchenTicket | response | coursing | object |  | BL-131. (nullable)
FnbService | recallKitchenTicket | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | recallKitchenTicket | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | recallKitchenTicket | response | priority | integer |  | Higher fires sooner.
FnbService | recallKitchenTicket | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | recallKitchenTicket | response | prioritiseReason | string |  | (nullable)
FnbService | recallKitchenTicket | response | lines | array of object | yes
FnbService | recallKitchenTicket | response | lines[].lineId | string (uuid) | yes
FnbService | recallKitchenTicket | response | lines[].name | string | yes
FnbService | recallKitchenTicket | response | lines[].quantity | integer | yes
FnbService | recallKitchenTicket | response | lines[].modifiers | array of string
FnbService | recallKitchenTicket | response | lines[].note | string |  | (nullable)
FnbService | recallKitchenTicket | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | recallKitchenTicket | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | recallKitchenTicket | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | recallKitchenTicket | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | recallKitchenTicket | response | lines[].course | integer |  | (nullable)
FnbService | recallKitchenTicket | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | recallKitchenTicket | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | recallKitchenTicket | response | createdAt | string (date-time) | yes
FnbService | recallKitchenTicket | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | recallKitchenTicket | response | elapsedSeconds | integer
FnbService | recallKitchenTicket | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | recallKitchenTicket | param (path) | ticketId | string (uuid) | yes
FnbService | recallKitchenTicket | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | recommendSeats | request | partySize | integer | yes | (min 1; max 50)
CatalogueService | recommendSeats | request | strategy | SeatRecommendationStrategy: enum (bestAvailable, bestValue, closestToStage, accessible, contiguous) | yes
CatalogueService | recommendSeats | request | categoryIds | array of string (uuid)
CatalogueService | recommendSeats | request | maxPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | recommendSeats | request | maxPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | recommendSeats | request | maxPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | recommendSeats | request | maxPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | recommendSeats | request | accessibleCount | integer |  | Wheelchair spaces in the party. (default 0)
CatalogueService | recommendSeats | request | maxOptions | integer |  | (max 10; default 3)
CatalogueService | recommendSeats | response | options | array of SeatRecommendation | yes
CatalogueService | recommendSeats | response | options[].seatIds | array of string | yes
CatalogueService | recommendSeats | response | options[].displayLabels | array of string
CatalogueService | recommendSeats | response | options[].totalPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | recommendSeats | response | options[].totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | recommendSeats | response | options[].totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | recommendSeats | response | options[].totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | recommendSeats | response | options[].categoryId | string (uuid)
CatalogueService | recommendSeats | response | options[].isContiguous | boolean | yes
CatalogueService | recommendSeats | response | options[].rank | integer | yes | Best first.
CatalogueService | recommendSeats | response | options[].rationale | string |  | Why this option was chosen — closest to stage, best value in category, only contiguous block remaining.
CatalogueService | recommendSeats | param (path) | performanceId | string (uuid) | yes
CatalogueService | recommendSeats | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | recordAnswerFeedback | request | rating | enum (helpful, notHelpful) | yes
AiService | recordAnswerFeedback | request | reason | enum (wrong, outdated, incomplete, notGrounded, unsafe, other) |  | (nullable)
AiService | recordAnswerFeedback | request | comment | string |  | (max length 1000; nullable)
AiService | recordAnswerFeedback | response | id | string (uuid) |  | (read-only)
AiService | recordAnswerFeedback | response | messageId | string (uuid) | yes
AiService | recordAnswerFeedback | response | conversationId | string (uuid) |  | (nullable)
AiService | recordAnswerFeedback | response | rating | enum (helpful, notHelpful) | yes
AiService | recordAnswerFeedback | response | reason | enum (wrong, outdated, incomplete, notGrounded, unsafe, other) |  | (nullable)
AiService | recordAnswerFeedback | response | comment | string |  | (max length 1000; nullable)
AiService | recordAnswerFeedback | response | audience | enum (staff, guest) |  | (read-only)
AiService | recordAnswerFeedback | response | principalId | string (uuid) |  | (read-only; nullable)
AiService | recordAnswerFeedback | response | subjectId | string (uuid) |  | The guest, where the audience is guest. (read-only; nullable)
AiService | recordAnswerFeedback | response | createdAt | string (date-time) |  | (read-only)
AiService | recordAnswerFeedback | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | recordAnswerFeedback | param (path) | messageId | string (uuid) | yes
AiService | recordAnswerFeedback | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | recordAttendance | request | kind | enum (clockIn, clockOut, breakStart, breakEnd) | yes
TenancyService | recordAttendance | request | occurredAt | string (date-time) | yes | Device time.
TenancyService | recordAttendance | request | assignmentId | string (uuid) |  | (nullable)
TenancyService | recordAttendance | request | accessPointId | string (uuid) |  | (nullable)
TenancyService | recordAttendance | request | latitude | number |  | (nullable)
TenancyService | recordAttendance | request | longitude | number |  | (nullable)
TenancyService | recordAttendance | response | id | string (uuid) | yes
TenancyService | recordAttendance | response | principalId | string (uuid) | yes
TenancyService | recordAttendance | response | assignmentId | string (uuid) |  | (nullable)
TenancyService | recordAttendance | response | venueId | string (uuid)
TenancyService | recordAttendance | response | kind | enum (clockIn, clockOut, breakStart, breakEnd) | yes
TenancyService | recordAttendance | response | occurredAt | string (date-time) | yes | Device time — when it happened.
TenancyService | recordAttendance | response | recordedAt | string (date-time) |  | When the server received it.
TenancyService | recordAttendance | response | accessPointId | string (uuid) |  | (nullable)
TenancyService | recordAttendance | response | latitude | number |  | (nullable)
TenancyService | recordAttendance | response | longitude | number |  | (nullable)
TenancyService | recordAttendance | response | isAmended | boolean |  | (read-only)
TenancyService | recordAttendance | response | amendedByPrincipalId | string (uuid) |  | Who made the latest amendment. (read-only; nullable)
TenancyService | recordAttendance | response | amendmentReason | string |  | The latest amendment's reason. (read-only; nullable)
TenancyService | recordAttendance | response | originalOccurredAt | string (date-time) |  | The original is never overwritten. (nullable)
TenancyService | recordAttendance | response | amendments | array of AttendanceAmendment |  | Every correction, oldest first, one row each (decided 28 September, audit R129 (7)). (read-only)
TenancyService | recordAttendance | response | amendments[].id | string (uuid) | yes
TenancyService | recordAttendance | response | amendments[].attendanceRecordId | string (uuid) | yes
TenancyService | recordAttendance | response | amendments[].amendedByPrincipalId | string (uuid) | yes
TenancyService | recordAttendance | response | amendments[].amendedAt | string (date-time) | yes
TenancyService | recordAttendance | response | amendments[].occurredAtBefore | string (date-time) | yes | The record's time before this correction.
TenancyService | recordAttendance | response | amendments[].occurredAtAfter | string (date-time) | yes | The time this correction set (correctedAt on the request).
TenancyService | recordAttendance | response | amendments[].reason | string | yes | (max length 300)
TenancyService | recordAttendance | response | exception | enum (late, earlyLeave, missingClockOut, noShow, outOfGeofence, unscheduled) |  | Computed against the rota. (nullable)
TenancyService | recordAttendance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | recordConsent | request | purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment) | yes | storedPaymentCredential (a card saved for later, storePaymentToken) and facePassEnrolment (a face enrolled for entry, enrolFacePass) are purposes of their own (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-…
MarketingService | recordConsent | request | decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | recordConsent | request | channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) |  | Omit to apply to every channel the purpose covers.
MarketingService | recordConsent | request | noticeVersion | string | yes
MarketingService | recordConsent | request | source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordConsent | request | recordedAt | string (date-time) | yes
MarketingService | recordConsent | response | subjectId | string (uuid) | yes
MarketingService | recordConsent | response | purposes | array of object | yes
MarketingService | recordConsent | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment) | yes | storedPaymentCredential (a card saved for later, storePaymentToken) and facePassEnrolment (a face enrolled for entry, enrolFacePass) are purposes of their own (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-…
MarketingService | recordConsent | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | recordConsent | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | recordConsent | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | recordConsent | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | recordConsent | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | recordConsent | param (path) | subjectId | string (uuid) | yes
MarketingService | recordConsent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | recordConsentAnswers | request | cartId | string (uuid) | yes | The cart the answers are given for.
MarketingService | recordConsentAnswers | request | answers | array of object | yes | (min items 1; max items 200)
MarketingService | recordConsentAnswers | request | answers[].questionId | string (uuid) | yes
MarketingService | recordConsentAnswers | request | answers[].questionVersion | integer | yes | The version the guest was shown, from Cart.consentQuestions. (min 1)
MarketingService | recordConsentAnswers | request | answers[].answer | enum (yes, no) | yes
MarketingService | recordConsentAnswers | request | answers[].cartLineId | string (uuid) |  | For a perPerson question, the line the person is on. (nullable)
MarketingService | recordConsentAnswers | request | answers[].personIndex | integer |  | For a perPerson question, the person's row in that line's eligibilityDeclaration, counting from 0. (min 0; nullable)
MarketingService | recordConsentAnswers | request | answers[].personName | string |  | (max length 120; nullable)
MarketingService | recordConsentAnswers | request | answers[].personSubjectId | string (uuid) |  | Where the person is a known guest, such as the booker or a family member. (nullable)
MarketingService | recordConsentAnswers | request | source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordConsentAnswers | request | answeredAt | string (date-time) | yes
MarketingService | recordConsentAnswers | response | items | array of BookingConsentRecord | yes
MarketingService | recordConsentAnswers | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | recordConsentAnswers | response | items[].questionId | string (uuid) | yes
MarketingService | recordConsentAnswers | response | items[].questionVersion | integer | yes | (min 1)
MarketingService | recordConsentAnswers | response | items[].questionKind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | recordConsentAnswers | response | items[].answer | enum (yes, no) | yes
MarketingService | recordConsentAnswers | response | items[].scope | enum (perPerson, perBooking) | yes
MarketingService | recordConsentAnswers | response | items[].blocksBooking | boolean |  | The answer is the question's blockingAnswer at that version. (read-only)
MarketingService | recordConsentAnswers | response | items[].cartId | string (uuid) |  | (nullable)
MarketingService | recordConsentAnswers | response | items[].cartLineId | string (uuid) |  | (nullable)
MarketingService | recordConsentAnswers | response | items[].orderId | string (uuid) |  | Set by orders.checkoutCart when the cart becomes an order. (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].orderLineId | string (uuid) |  | (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].personIndex | integer |  | (min 0; nullable)
MarketingService | recordConsentAnswers | response | items[].personName | string |  | (max length 120; nullable)
MarketingService | recordConsentAnswers | response | items[].personSubjectId | string (uuid) |  | (nullable)
MarketingService | recordConsentAnswers | response | items[].answeredBySubjectId | string (uuid) |  | The guest who answered, from the session. (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].answeredByPrincipalId | string (uuid) |  | The staff member who answered on the guest's behalf. (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordConsentAnswers | response | items[].answeredAt | string (date-time) | yes
MarketingService | recordConsentAnswers | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | recordConsentAnswers | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | recordDashboardView | request | venueId | string (uuid) |  | The venue the dashboard was narrowed to when opened, as Dashboard.venueId. (nullable)
ReportingService | recordDashboardView | param (path) | dashboardId | string (uuid) | yes
ReportingService | recordDashboardView | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | recordGroupCheckIn | request | arrivedCount | integer | yes | Members of the booked group who have arrived. (min 0)
OrderService | recordGroupCheckIn | request | additionalGuests | integer |  | People who arrived beyond the booked size; they still need entitlements to be admitted. (min 0; default 0)
OrderService | recordGroupCheckIn | request | staffLeadersCount | integer |  | (min 0; default 0)
OrderService | recordGroupCheckIn | request | arrivalGateId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | request | actualArrivalAt | string (date-time) |  | Defaults to now on the first call; later calls keep the first arrival time. (nullable)
OrderService | recordGroupCheckIn | request | checkInIssues | array of enum (missingGuest, extraGuest, invalidTicket, wrongDate, lateArrival, paymentHold, missingCredential, accessibilityRequirement)
OrderService | recordGroupCheckIn | response | id | string (uuid) | yes | (read-only)
OrderService | recordGroupCheckIn | response | groupBookingId | string (uuid) | yes | Unique; one plan per group booking.
OrderService | recordGroupCheckIn | response | arrivalAt | string (date-time) |  | (nullable)
OrderService | recordGroupCheckIn | response | arrivalLocation | string |  | (max length 200; nullable)
OrderService | recordGroupCheckIn | response | meetingPoint | string |  | (max length 200; nullable)
OrderService | recordGroupCheckIn | response | entryGateId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | response | departureAt | string (date-time) |  | (nullable)
OrderService | recordGroupCheckIn | response | groupLeaders | string |  | (max length 500; nullable)
OrderService | recordGroupCheckIn | response | contactId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | response | ticketingMethod | string |  | (max length 60; nullable)
OrderService | recordGroupCheckIn | response | requirements | object |  | Seating, guides, catering, transportation, parking, accessibility, equipment and special requirements, as free text keyed by those names. (nullable)
OrderService | recordGroupCheckIn | response | operationalOwnerPrincipalId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | response | handoverNotes | string |  | (max length 4000; nullable)
OrderService | recordGroupCheckIn | response | handoverAttachmentIds | array of string (uuid)
OrderService | recordGroupCheckIn | response | handoverAcknowledgedByPrincipalId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | response | handoverAcknowledgedAt | string (date-time) |  | (nullable)
OrderService | recordGroupCheckIn | response | checkInStatus | enum (expected, partiallyArrived, arrived, noShow) | yes | (default expected)
OrderService | recordGroupCheckIn | response | actualArrivalAt | string (date-time) |  | (nullable)
OrderService | recordGroupCheckIn | response | arrivalGateId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | response | arrivedCount | integer |  | (min 0; default 0)
OrderService | recordGroupCheckIn | response | additionalGuests | integer |  | (min 0; default 0)
OrderService | recordGroupCheckIn | response | staffLeadersCount | integer |  | (min 0; default 0)
OrderService | recordGroupCheckIn | response | checkInIssues | array of enum (missingGuest, extraGuest, invalidTicket, wrongDate, lateArrival, paymentHold, missingCredential, accessibilityRequirement)
OrderService | recordGroupCheckIn | response | checkedInByPrincipalId | string (uuid) |  | (nullable)
OrderService | recordGroupCheckIn | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | recordGroupCheckIn | response | createdAt | string (date-time) | yes | (read-only)
OrderService | recordGroupCheckIn | response | updatedAt | string (date-time) |  | (read-only; nullable)
OrderService | recordGroupCheckIn | param (path) | groupBookingId | string (uuid) | yes
OrderService | recordGroupCheckIn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | recordLostItem | request | id | string (uuid) | yes | (read-only)
MarketingService | recordLostItem | request | foundOrLost | enum (lost, found) | yes | One entity, two directions.
MarketingService | recordLostItem | request | kind | enum (bag, phone, wallet, keys, clothing, jewellery, documents, toy, …) | yes
MarketingService | recordLostItem | request | description | string
MarketingService | recordLostItem | request | colour | string |  | (nullable)
MarketingService | recordLostItem | request | brand | string |  | (nullable)
MarketingService | recordLostItem | request | venueId | string (uuid) | yes
MarketingService | recordLostItem | request | lastSeenPointId | string (uuid) |  | A point on the venue map. (nullable)
MarketingService | recordLostItem | request | reportedAt | string (date-time) | yes | Device time — recordLostItem is offline-capable, so this is when the loss was reported or the find handed in, not when the device synced.
MarketingService | recordLostItem | request | syncedAt | string (date-time) |  | Server time the record arrived. (read-only)
MarketingService | recordLostItem | request | reportedBySubjectId | string (uuid) |  | (nullable)
MarketingService | recordLostItem | request | storageLocation | string |  | (nullable)
MarketingService | recordLostItem | request | status | enum (open, matched, claimed, disposed, returned) |  | (read-only)
MarketingService | recordLostItem | request | photoAssetIds | array of string (uuid)
MarketingService | recordLostItem | request | matchedItemId | string (uuid) |  | The other side of the match — set by matchLostItem match (to otherItemId) and cleared by unmatch, on both items. (read-only; nullable)
MarketingService | recordLostItem | request | caseId | string (uuid) |  | The case the guest raised about it (raiseMyCase with kind lostProperty), where there is one. (nullable)
MarketingService | recordLostItem | request | disposeAfter | string (date) |  | A retention date, because unclaimed property has one. (nullable)
MarketingService | recordLostItem | response | id | string (uuid) | yes | (read-only)
MarketingService | recordLostItem | response | foundOrLost | enum (lost, found) | yes | One entity, two directions.
MarketingService | recordLostItem | response | kind | enum (bag, phone, wallet, keys, clothing, jewellery, documents, toy, …) | yes
MarketingService | recordLostItem | response | description | string
MarketingService | recordLostItem | response | colour | string |  | (nullable)
MarketingService | recordLostItem | response | brand | string |  | (nullable)
MarketingService | recordLostItem | response | venueId | string (uuid) | yes
MarketingService | recordLostItem | response | lastSeenPointId | string (uuid) |  | A point on the venue map. (nullable)
MarketingService | recordLostItem | response | reportedAt | string (date-time) | yes | Device time — recordLostItem is offline-capable, so this is when the loss was reported or the find handed in, not when the device synced.
MarketingService | recordLostItem | response | syncedAt | string (date-time) |  | Server time the record arrived. (read-only)
MarketingService | recordLostItem | response | reportedBySubjectId | string (uuid) |  | (nullable)
MarketingService | recordLostItem | response | storageLocation | string |  | (nullable)
MarketingService | recordLostItem | response | status | enum (open, matched, claimed, disposed, returned) |  | (read-only)
MarketingService | recordLostItem | response | photoAssetIds | array of string (uuid)
MarketingService | recordLostItem | response | matchedItemId | string (uuid) |  | The other side of the match — set by matchLostItem match (to otherItemId) and cleared by unmatch, on both items. (read-only; nullable)
MarketingService | recordLostItem | response | caseId | string (uuid) |  | The case the guest raised about it (raiseMyCase with kind lostProperty), where there is one. (nullable)
MarketingService | recordLostItem | response | disposeAfter | string (date) |  | A retention date, because unclaimed property has one. (nullable)
MarketingService | recordLostItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | recordNoSale | request | id | string (uuid) | yes
OrderService | recordNoSale | request | reason | enum (changeForGuest, correctFloat, retrieveDroppedCash, tillCheck, other) | yes
OrderService | recordNoSale | request | note | string |  | (max length 300)
OrderService | recordNoSale | request | recordedAt | string (date-time) | yes
OrderService | recordNoSale | request | supervisorStepUp | object |  | The supervisor approving for a cashier without CASH_NO_SALE (r8 walk fix, CHG-R8WFC-005).
OrderService | recordNoSale | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | recordNoSale | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | recordNoSale | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | recordNoSale | response | approvedByPrincipalId | string (uuid) |  | The supervisor whose step-up approved it for a cashier without CASH_NO_SALE; null when the cashier held it (r8 walk fix, CHG-R8WFC-005). (read-only; nullable)
OrderService | recordNoSale | response | id | string (uuid) | yes
OrderService | recordNoSale | response | shiftId | string (uuid) | yes
OrderService | recordNoSale | response | workstationId | string (uuid)
OrderService | recordNoSale | response | reason | string | yes
OrderService | recordNoSale | response | note | string |  | (nullable)
OrderService | recordNoSale | response | principalId | string (uuid) | yes
OrderService | recordNoSale | response | recordedAt | string (date-time) | yes
OrderService | recordNoSale | response | countThisShift | integer |  | Running count.
OrderService | recordNoSale | param (path) | shiftId | string (uuid) | yes
OrderService | recordNoSale | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | recordOrderHandover | request | outcome | enum (served, collected, delivered, guestNotFound, refused) | yes | served, collected and delivered move the order to the FnbOrderStatus of the same name.
FnbService | recordOrderHandover | request | deliveredToLocationId | string (uuid) |  | Required where outcome is delivered (audit R125 (1)).
FnbService | recordOrderHandover | request | runnerPrincipalId | string (uuid)
FnbService | recordOrderHandover | request | note | string |  | Required for guestNotFound and refused. (max length 500)
FnbService | recordOrderHandover | request | recordedAt | string (date-time) | yes
FnbService | recordOrderHandover | response | orderId | string | yes
FnbService | recordOrderHandover | response | orderNumber | string
FnbService | recordOrderHandover | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | recordOrderHandover | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | recordOrderHandover | response | isReadyForCollection | boolean
FnbService | recordOrderHandover | response | lines | array of object | yes | Per-line status.
FnbService | recordOrderHandover | response | lines[].name | string
FnbService | recordOrderHandover | response | lines[].quantity | integer
FnbService | recordOrderHandover | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | recordOrderHandover | param (path) | orderId | string (uuid) | yes
FnbService | recordOrderHandover | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | recordRecommendationEvents | request | events | array of object | yes | (min items 1)
AiService | recordRecommendationEvents | request | events[].decisionId | string (uuid) |  | (nullable)
AiService | recordRecommendationEvents | request | events[].trackingId | string (uuid) | yes
AiService | recordRecommendationEvents | request | events[].eventType | enum (impression, click, addToCart, dismiss, decline) | yes
AiService | recordRecommendationEvents | request | events[].productId | string (uuid) |  | (nullable)
AiService | recordRecommendationEvents | request | events[].occurredAt | string (date-time) | yes
AiService | recordRecommendationEvents | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | recordStorefrontSessionEvents | request | batchId | string (uuid) | yes | UUIDv7 minted by the runtime; a retried beacon repeats it.
WhiteLabelService | recordStorefrontSessionEvents | request | sessionRef | string | yes | The runtime's own session id, SHA-256 hashed in the browser (64 lowercase hex); hashed again with the tenant's blind-index key on arrival (HMAC-SHA-256, ADR-0063) and published as storefront.sessionE… (max length 128; pattern ^[0-9a-f]{64}$)
WhiteLabelService | recordStorefrontSessionEvents | request | deviceIdHash | string |  | The runtime's own device id, SHA-256 hashed in the browser (64 lowercase hex); hashed again with the tenant's blind-index key on arrival (ADAM CR-107). (max length 128; pattern ^[0-9a-f]{64}$; nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | surface | enum (guestWeb, guestApp) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | venueId | string (uuid) |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | sessionStartedAt | string (date-time) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | interactions | array of object | yes | (min items 1; max items 50)
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].kind | enum (pageView, productView, seatMapOpened, addToCart, removeFromCart, checkoutStarted, paymentPageViewed, promoCodeTried, …) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].pageKind | enum (home, product, seatMap, cart, checkout, account, content, None) |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].productId | string (uuid) |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].at | string (date-time) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].dwellMs | integer |  | (min 0; nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints | object |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.webdriver | boolean
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.headless | boolean
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.pointerEvents | integer |  | (min 0)
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.interactionsPerMinute | number |  | (min 0)
MarketingService | redeemLoyaltyPoints | request | subjectId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | request | programmeId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | request | points | integer | yes
MarketingService | redeemLoyaltyPoints | request | rewardId | string (uuid) |  | (nullable)
MarketingService | redeemLoyaltyPoints | request | orderId | string (uuid) |  | Where points are being used against a sale rather than for a catalogue reward. (nullable)
MarketingService | redeemLoyaltyPoints | response | leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | redeemLoyaltyPoints | response | subjectId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | response | programmeId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | response | pointsBalance | integer | yes
MarketingService | redeemLoyaltyPoints | response | lifetimePoints | integer
MarketingService | redeemLoyaltyPoints | response | tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | redeemLoyaltyPoints | response | tierCode | string | yes
MarketingService | redeemLoyaltyPoints | response | tierName | string
MarketingService | redeemLoyaltyPoints | response | pointsToNextTier | integer |  | (nullable)
MarketingService | redeemLoyaltyPoints | response | nextExpiryPoints | integer |  | (nullable)
MarketingService | redeemLoyaltyPoints | response | nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | redeemLoyaltyPoints | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | refireItem | request | lineId | string (uuid) | yes | KitchenTicket.lines[].lineId.
FnbService | refireItem | request | reason | RefireReason: enum (overcooked, undercooked, wrongItem, dropped, cold, allergyRisk, guestChangedMind, lateAdd) | yes | Why a line was made again (refireItem).
FnbService | refireItem | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | refireItem | request | chargeable | boolean |  | False by default, and that default is the point. (default False)
FnbService | refireItem | response | id | string (uuid) | yes
FnbService | refireItem | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | refireItem | response | orderNumber | string
FnbService | refireItem | response | outletId | string (uuid) | yes
FnbService | refireItem | response | tableLabel | string |  | (nullable)
FnbService | refireItem | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | refireItem | response | coursing | object |  | BL-131. (nullable)
FnbService | refireItem | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | refireItem | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | refireItem | response | priority | integer |  | Higher fires sooner.
FnbService | refireItem | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | refireItem | response | prioritiseReason | string |  | (nullable)
FnbService | refireItem | response | lines | array of object | yes
FnbService | refireItem | response | lines[].lineId | string (uuid) | yes
FnbService | refireItem | response | lines[].name | string | yes
FnbService | refireItem | response | lines[].quantity | integer | yes
FnbService | refireItem | response | lines[].modifiers | array of string
FnbService | refireItem | response | lines[].note | string |  | (nullable)
FnbService | refireItem | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | refireItem | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | refireItem | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | refireItem | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | refireItem | response | lines[].course | integer |  | (nullable)
FnbService | refireItem | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | refireItem | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | refireItem | response | createdAt | string (date-time) | yes
FnbService | refireItem | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | refireItem | response | elapsedSeconds | integer
FnbService | refireItem | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | refireItem | param (path) | ticketId | string (uuid) | yes
FnbService | refireItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | refreshToken | request | refreshToken | string | yes
IdentityService | refreshToken | response | accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | refreshToken | response | refreshToken | string | yes
IdentityService | refreshToken | response | expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | refreshToken | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | regenerateDomainToken | response | id | string (uuid) | yes
WhiteLabelService | regenerateDomainToken | response | tenantId | string (uuid) | yes
WhiteLabelService | regenerateDomainToken | response | hostname | string | yes
WhiteLabelService | regenerateDomainToken | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) |  | guestApp is stored as guestWeb: the guest app is served on the guestWeb domain and has no domain of its own (r10 question 4; CHG-R10TEN-020).
WhiteLabelService | regenerateDomainToken | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | regenerateDomainToken | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | regenerateDomainToken | response | verificationToken | string |  | (read-only)
WhiteLabelService | regenerateDomainToken | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | regenerateDomainToken | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | regenerateDomainToken | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | regenerateDomainToken | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | regenerateDomainToken | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | regenerateDomainToken | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | regenerateDomainToken | response | validationExpiresAt | string (date-time) |  | When the validation window ends (ADAM CR-105, option 1; CHG-R10TEN-011): 7 days after claimCustomDomain or regenerateDomainToken issued the token (a proposed default the client can correct). (read-only; nullable)
WhiteLabelService | regenerateDomainToken | response | failureReason | string |  | (nullable)
WhiteLabelService | regenerateDomainToken | response | routing | enum (cname, delegatedSubdomain, apex) |  | How the hostname reaches TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; CHG-CSA-043). (default cname)
WhiteLabelService | regenerateDomainToken | response | dnsRecords | array of object |  | Every record the tenant must publish, with what is observed now (CHG-CSA-043): the TXT _dnsauth record, the CNAME, and CAA or NS where they apply. (read-only)
WhiteLabelService | regenerateDomainToken | response | dnsRecords[].type | enum (TXT, CNAME, CAA, NS) | yes
WhiteLabelService | regenerateDomainToken | response | dnsRecords[].name | string | yes
WhiteLabelService | regenerateDomainToken | response | dnsRecords[].expectedValue | string | yes
WhiteLabelService | regenerateDomainToken | response | dnsRecords[].observedValue | string |  | (nullable)
WhiteLabelService | regenerateDomainToken | response | dnsRecords[].status | enum (ok, missing, wrong) | yes
WhiteLabelService | regenerateDomainToken | response | revalidation | enum (none, pendingRevalidation, timedOut) |  | The two waits CMS-017 shows beside status (CHG-CSA-043). (default none; read-only)
WhiteLabelService | regenerateDomainToken | response | isCnameLost | boolean |  | Takeover warning (CHG-CSA-043). (read-only)
WhiteLabelService | regenerateDomainToken | response | isPrimary | boolean |  | The tenant's primary domain for its kind; the others redirect to it (setPrimaryDomain). (read-only)
WhiteLabelService | regenerateDomainToken | response | readiness | object |  | Per-domain setup a guest needs (CHG-CSA-043): the UAE Pass redirect URI registered for this hostname, the Apple Pay merchant domain verified, and the app links (Apple app-site association, Android as… (read-only)
WhiteLabelService | regenerateDomainToken | response | readiness.uaePassRedirect | enum (ready, pending, notApplicable)
WhiteLabelService | regenerateDomainToken | response | readiness.applePayDomain | enum (ready, pending, notApplicable)
WhiteLabelService | regenerateDomainToken | response | readiness.appLinks | enum (ready, pending, notApplicable)
WhiteLabelService | regenerateDomainToken | param (path) | domainId | string (uuid) | yes
WhiteLabelService | regenerateDomainToken | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | registerDeveloper | request | organisationName | string | yes | (max length 300)
PlatformService | registerDeveloper | request | contactEmail | string (email) | yes
PlatformService | registerDeveloper | request | websiteUrl | string |  | (nullable)
PlatformService | registerDeveloper | request | countryCode | string |  | (min length 2; max length 2)
PlatformService | registerDeveloper | request | partnerId | string (uuid) |  | Where this developer is also a commercial partner. (nullable)
PlatformService | registerDeveloper | response | id | string (uuid) | yes | (read-only)
PlatformService | registerDeveloper | response | organisationName | string | yes
PlatformService | registerDeveloper | response | contactEmail | string (email) | yes | The organisation's contact, who becomes its owner member on registration; unique without case (registerDeveloper 409 developer-already-registered; ADAM CR-098).
PlatformService | registerDeveloper | response | websiteUrl | string |  | (nullable)
PlatformService | registerDeveloper | response | countryCode | string
PlatformService | registerDeveloper | response | partnerId | string (uuid) |  | Where this developer is also a commercial partner. (nullable)
PlatformService | registerDeveloper | response | status | enum (pending, verified, suspended, closed) | yes | (read-only)
PlatformService | registerDeveloper | response | verifiedAt | string (date-time) |  | (read-only; nullable)
PlatformService | registerDeveloper | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | registerGuest | request | identifier | string | yes | Email address or mobile number in E.164. (max length 256)
IdentityService | registerGuest | request | channel | enum (email, sms, whatsapp) |  | Optional for a mobile number (ADAM CR-222, 25 October 2026): left out, the server picks WhatsApp first and SMS as the fallback (the lead, 25 October 2026, r10 Q5), from the tenant's configured delive…
IdentityService | registerGuest | request | displayName | string |  | (max length 200)
IdentityService | registerGuest | request | password | string |  | Optional. (min length 8; max length 256)
IdentityService | registerGuest | request | preferredLanguage | string |  | (pattern ^[a-z]{2}$)
IdentityService | registerGuest | request | consents | array of object |  | Consent captured at registration, recorded with the notice version.
IdentityService | registerGuest | request | consents[].purpose | string
IdentityService | registerGuest | request | consents[].granted | boolean
IdentityService | registerGuest | request | consents[].noticeVersion | string
IdentityService | registerGuest | response | subjectId | string (uuid) | yes
IdentityService | registerGuest | response | displayName | string |  | (nullable)
IdentityService | registerGuest | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | registerGuest | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | registerGuest | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | registerGuest | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | registerGuest | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | registerGuest | response | mfaMethods[].id | string (uuid) | yes
IdentityService | registerGuest | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | registerGuest | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | registerGuest | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | registerGuest | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | registerGuest | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | registerGuest | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | registerGuest | response | mfaMethods[].label | string |  | (nullable)
IdentityService | registerGuest | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | registerGuest | response | mfaMethods[].isActive | boolean | yes
IdentityService | registerGuest | response | mfaMethods[].isPrimary | boolean
IdentityService | registerGuest | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | registerGuest | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | registerGuest | response | homeCellName | string |  | (nullable)
IdentityService | registerGuest | response | preferredLanguage | string |  | (nullable)
IdentityService | registerGuest | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | registerGuest | response | tokens | object | yes | The new access and refresh tokens; refreshToken returns the next pair.
IdentityService | registerGuest | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | registerGuest | response | tokens.refreshToken | string | yes
IdentityService | registerGuest | response | tokens.expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | registerGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | registerGuestDevice | request | platform | enum (ios, android, web) | yes
MarketingService | registerGuestDevice | request | token | string | yes | The provider's push token. (max length 512)
MarketingService | registerGuestDevice | request | installationId | string (uuid) |  | A UUIDv7 the app makes once per install (once per browser profile for web) and sends on every registration from that install, so a rotated token updates the same row (CHG-MKT-001).
MarketingService | registerGuestDevice | request | appVersion | string
MarketingService | registerGuestDevice | request | osVersion | string
MarketingService | registerGuestDevice | request | deviceModel | string
MarketingService | registerGuestDevice | request | locale | string
MarketingService | registerGuestDevice | response | id | string (uuid) | yes
MarketingService | registerGuestDevice | response | subjectId | string (uuid) | yes
MarketingService | registerGuestDevice | response | platform | enum (ios, android, web) | yes
MarketingService | registerGuestDevice | response | installationId | string (uuid) |  | The app install the registration came from, as registerGuestDevice.installationId sent it (CHG-MKT-001). (nullable)
MarketingService | registerGuestDevice | response | tokenFingerprint | string |  | A keyed hash of the token, not the token (decided 14 October 2026, CHG-MKT-001; ADR-0063 section 4 as amended): HMAC-SHA-256 of the token under the tenant's blind-index key, written as 64 lowercase h… (max length 64; nullable)
MarketingService | registerGuestDevice | response | tokenRef | string |  | The push token, encrypted by the application (decided 14 October 2026, Chinmay, ADAM CR-086, CHG-MKT-001; ADR-0063 section 4 as amended), written by the server from registerGuestDevice.token: AES-256… (nullable)
MarketingService | registerGuestDevice | response | appVersion | string |  | (nullable)
MarketingService | registerGuestDevice | response | osVersion | string |  | (nullable)
MarketingService | registerGuestDevice | response | deviceModel | string |  | (nullable)
MarketingService | registerGuestDevice | response | locale | string |  | (nullable)
MarketingService | registerGuestDevice | response | status | enum (active, revoked, failed) | yes | active is sent to.
MarketingService | registerGuestDevice | response | failureCount | integer |  | Consecutive delivery failures.
MarketingService | registerGuestDevice | response | registeredAt | string (date-time) | yes
MarketingService | registerGuestDevice | response | lastSeenAt | string (date-time) |  | (nullable)
MarketingService | registerGuestDevice | response | revokedAt | string (date-time) |  | (nullable)
MarketingService | registerGuestDevice | response | pendingSessionEndInstallationId | string (uuid) |  | Set only by the server (a value a client sends is ignored) and never returned (R8 blocker IDENTITY-C23). (nullable)
MarketingService | registerGuestDevice | param (path) | subjectId | string (uuid) | yes
MarketingService | registerGuestDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | reindexSource | request | reason | enum (embeddingModelChanged, fieldsChanged, driftSuspected, initialBuild)
AiService | reindexSource | response | id | string (uuid) | yes
AiService | reindexSource | response | sourceId | string (uuid) | yes
AiService | reindexSource | response | kind | enum (full, incremental, removal)
AiService | reindexSource | response | reason | string
AiService | reindexSource | response | status | enum (queued, building, verifying, swapping, complete, failed) | yes
AiService | reindexSource | response | recordsTotal | integer
AiService | reindexSource | response | recordsEmbedded | integer
AiService | reindexSource | response | recordsFailed | integer |  | The number to watch.
AiService | reindexSource | response | failureSample | array of string
AiService | reindexSource | response | shadowCollection | string |  | Set only for a change of embedding model: the rebuild writes here and the alias swaps on completion. (nullable)
AiService | reindexSource | response | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | reindexSource | response | embeddingModel | string
AiService | reindexSource | response | startedAt | string (date-time) | yes
AiService | reindexSource | response | completedAt | string (date-time) |  | (nullable)
AiService | reindexSource | param (path) | sourceId | string (uuid) | yes
AiService | reindexSource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reissueEntitlement | request | reason | enum (venueClosure, weather, goodwill, systemError, medicalIssue, bereavement) | yes
OrderService | reissueEntitlement | request | validFrom | string (date) |  | (nullable)
OrderService | reissueEntitlement | request | note | string |  | (nullable)
OrderService | reissueEntitlement | response | entitlementId | string (uuid) | yes | The new entitlement.
OrderService | reissueEntitlement | response | replacesEntitlementId | string (uuid) | yes | The expired one, now voided.
OrderService | reissueEntitlement | response | reason | enum (venueClosure, weather, goodwill, systemError, medicalIssue, bereavement) | yes
OrderService | reissueEntitlement | response | validFrom | string (date) |  | (nullable)
OrderService | reissueEntitlement | response | note | string |  | (nullable)
OrderService | reissueEntitlement | param (path) | entitlementId | string (uuid) | yes
OrderService | reissueEntitlement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | rejectReceivedGoods | request | lines | array of object | yes | (min items 1)
InventoryService | rejectReceivedGoods | request | lines[].lineId | string (uuid) | yes | GoodsReceipt.lines[].lineId, the batch or expiry line rejected (audit R171).
InventoryService | rejectReceivedGoods | request | lines[].quantity | number | yes | (min 0)
InventoryService | rejectReceivedGoods | request | reason | enum (damaged, wrongItem, qualityFailure, shortDated, overDelivery, other) | yes | other requires note (decided 28 September, audit R222).
InventoryService | rejectReceivedGoods | request | note | string |  | Required, at least 3 characters, when reason is other (audit R222). (max length 1000)
InventoryService | rejectReceivedGoods | response | id | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152), e.g. (read-only)
InventoryService | rejectReceivedGoods | response | purchaseOrderId | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | locationId | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | deliveryNoteReference | string |  | (nullable)
InventoryService | rejectReceivedGoods | response | lines | array of object | yes
InventoryService | rejectReceivedGoods | response | lines[].lineId | string (uuid) |  | One batch or expiry line of the receipt. (read-only)
InventoryService | rejectReceivedGoods | response | lines[].itemId | string (uuid)
InventoryService | rejectReceivedGoods | response | lines[].itemName | string
InventoryService | rejectReceivedGoods | response | lines[].orderedQuantity | number
InventoryService | rejectReceivedGoods | response | lines[].receivedQuantity | number
InventoryService | rejectReceivedGoods | response | lines[].rejectedQuantity | number
InventoryService | rejectReceivedGoods | response | lines[].batchNumber | string |  | (nullable)
InventoryService | rejectReceivedGoods | response | lines[].expiryDate | string (date) |  | (nullable)
InventoryService | rejectReceivedGoods | response | lines[].unitCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | rejectReceivedGoods | response | lines[].unitCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | rejectReceivedGoods | response | lines[].unitCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | rejectReceivedGoods | response | lines[].unitCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | rejectReceivedGoods | response | totalValue | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | rejectReceivedGoods | response | totalValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | rejectReceivedGoods | response | totalValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | rejectReceivedGoods | response | totalValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | rejectReceivedGoods | response | receivedByPrincipalId | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | journalEntryId | string |  | The accrual the supplier invoice will later match against. (nullable)
InventoryService | rejectReceivedGoods | response | createdAt | string (date-time) | yes
InventoryService | rejectReceivedGoods | response | recordedAt | string (date-time)
InventoryService | rejectReceivedGoods | response | syncedAt | string (date-time) |  | (nullable)
InventoryService | rejectReceivedGoods | param (path) | receiptId | string (uuid) | yes
InventoryService | rejectReceivedGoods | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | rejectShiftVariance | request | reason | string | yes | Why a recount is needed, shown to the cashier. (min length 3; max length 500)
OrderService | rejectShiftVariance | request | supervisorStepUp | object |  | The supervisor sending the shift back, signing on this device (CHG-RUL-014, as reopenShift).
OrderService | rejectShiftVariance | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | rejectShiftVariance | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | rejectShiftVariance | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | rejectShiftVariance | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | rejectShiftVariance | response | workstationId | string (uuid) | yes
OrderService | rejectShiftVariance | response | venueId | string (uuid) | yes
OrderService | rejectShiftVariance | response | scopePath | string | yes
OrderService | rejectShiftVariance | response | principalId | string (uuid) | yes | Who opened it.
OrderService | rejectShiftVariance | response | principalDisplayName | string
OrderService | rejectShiftVariance | response | incidents | array of object |  | BL-097.
OrderService | rejectShiftVariance | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | rejectShiftVariance | response | incidents[].at | string (date-time)
OrderService | rejectShiftVariance | response | incidents[].principalId | string (uuid)
OrderService | rejectShiftVariance | response | incidents[].note | string |  | (nullable)
OrderService | rejectShiftVariance | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | rejectShiftVariance | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | rejectShiftVariance | response | depositBoxCode | string |  | (nullable)
OrderService | rejectShiftVariance | response | bagNumber | string |  | (nullable)
OrderService | rejectShiftVariance | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | rejectShiftVariance | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | rejectShiftVariance | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | rejectShiftVariance | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | rejectShiftVariance | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | rejectShiftVariance | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | rejectShiftVariance | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | rejectShiftVariance | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rejectShiftVariance | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rejectShiftVariance | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rejectShiftVariance | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | rejectShiftVariance | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | rejectShiftVariance | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | rejectShiftVariance | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | rejectShiftVariance | response | openedAt | string (date-time) | yes
OrderService | rejectShiftVariance | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | rejectShiftVariance | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | rejectShiftVariance | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | rejectShiftVariance | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | rejectShiftVariance | response | closedAt | string (date-time) |  | (nullable)
OrderService | rejectShiftVariance | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | rejectShiftVariance | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | rejectShiftVariance | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | rejectShiftVariance | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | rejectShiftVariance | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | rejectShiftVariance | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | rejectShiftVariance | response | approvals | array of object
OrderService | rejectShiftVariance | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | rejectShiftVariance | response | approvals[].principalId | string (uuid) | yes
OrderService | rejectShiftVariance | response | approvals[].at | string (date-time) | yes
OrderService | rejectShiftVariance | response | approvals[].reason | string
OrderService | rejectShiftVariance | param (path) | shiftId | string (uuid) | yes
OrderService | rejectShiftVariance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | releaseProductionPlan | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | releaseProductionPlan | response | id | string (uuid) | yes | (read-only)
FnbService | releaseProductionPlan | response | outletId | string (uuid)
FnbService | releaseProductionPlan | response | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone; a business date, closing at the venue's businessDayCutoff (tenancy VenueSettings, default 00:00; CHG-R6-032).
FnbService | releaseProductionPlan | response | status | enum (draft, released, superseded, cancelled) | yes | (read-only)
FnbService | releaseProductionPlan | response | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | releaseProductionPlan | response | lines | array of object | yes
FnbService | releaseProductionPlan | response | lines[].itemId | string (uuid) | yes
FnbService | releaseProductionPlan | response | lines[].suggestedQuantity | number |  | (nullable)
FnbService | releaseProductionPlan | response | lines[].plannedQuantity | number | yes
FnbService | releaseProductionPlan | response | lines[].uom | string
FnbService | releaseProductionPlan | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | releaseProductionPlan | response | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | releaseProductionPlan | param (path) | planId | string (uuid) | yes
FnbService | releaseProductionPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | releaseResourceBlock | param (path) | blockId | string (uuid) | yes
VenueOpsService | releaseResourceBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | relinquishCustomDomain | param (path) | domainId | string (uuid) | yes
WhiteLabelService | relinquishCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | relinquishResourceHold | param (path) | holdId | string (uuid) | yes
VenueOpsService | relinquishResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | relinquishSeatHold | param (path) | holdId | string (uuid) | yes
CatalogueService | relinquishSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | removeCartLine | response | id | string (uuid) | yes
OrderService | removeCartLine | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | removeCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | removeCartLine | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | removeCartLine | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | removeCartLine | response | venueId | string (uuid) | yes
OrderService | removeCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | removeCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | removeCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | removeCartLine | response | lines | array of CartLine | yes
OrderService | removeCartLine | response | lines[].id | string (uuid) | yes
OrderService | removeCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | removeCartLine | response | lines[].productName | string |  | (read-only)
OrderService | removeCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | removeCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | removeCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | removeCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | removeCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | removeCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | removeCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | removeCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | removeCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | removeCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | removeCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | removeCartLine | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | removeCartLine | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | removeCartLine | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | removeCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | removeCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | removeCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | removeCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | removeCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | removeCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | removeCartLine | response | conflicts | array of CartConflict
OrderService | removeCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | removeCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | removeCartLine | response | conflicts[].message | string
OrderService | removeCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | removeCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | removeCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | removeCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | removeCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | removeCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | removeCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | removeCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | removeCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | removeCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | removeCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | removeCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | removeCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | removeCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | removeCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | removeCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | removeCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | removeCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | removeCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | removeCartLine | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | removeCartLine | response | locale | string
OrderService | removeCartLine | response | createdAt | string (date-time)
OrderService | removeCartLine | response | updatedAt | string (date-time)
OrderService | removeCartLine | param (path) | cartId | string (uuid) | yes
OrderService | removeCartLine | param (path) | lineId | string (uuid) | yes
OrderService | removeCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | removeFromWishlist | param (path) | subjectId | string (uuid) | yes
MarketingService | removeFromWishlist | param (path) | itemId | string (uuid) | yes
MarketingService | removeFromWishlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reopenShift | request | reason | string | yes | (min length 3; max length 500)
OrderService | reopenShift | request | supervisorStepUp | object | yes | The supervisor signing the reopen on this device (audit R144).
OrderService | reopenShift | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | reopenShift | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | reopenShift | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | reopenShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reopenShift | response | workstationId | string (uuid) | yes
OrderService | reopenShift | response | venueId | string (uuid) | yes
OrderService | reopenShift | response | scopePath | string | yes
OrderService | reopenShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | reopenShift | response | principalDisplayName | string
OrderService | reopenShift | response | incidents | array of object |  | BL-097.
OrderService | reopenShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | reopenShift | response | incidents[].at | string (date-time)
OrderService | reopenShift | response | incidents[].principalId | string (uuid)
OrderService | reopenShift | response | incidents[].note | string |  | (nullable)
OrderService | reopenShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | reopenShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | reopenShift | response | depositBoxCode | string |  | (nullable)
OrderService | reopenShift | response | bagNumber | string |  | (nullable)
OrderService | reopenShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | reopenShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | reopenShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | reopenShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | reopenShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | reopenShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | reopenShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | reopenShift | response | openedAt | string (date-time) | yes
OrderService | reopenShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | reopenShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | reopenShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | reopenShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | reopenShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | reopenShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | reopenShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | reopenShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | reopenShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | reopenShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | reopenShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | reopenShift | response | approvals | array of object
OrderService | reopenShift | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | reopenShift | response | approvals[].principalId | string (uuid) | yes
OrderService | reopenShift | response | approvals[].at | string (date-time) | yes
OrderService | reopenShift | response | approvals[].reason | string
OrderService | reopenShift | param (path) | shiftId | string (uuid) | yes
OrderService | reopenShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | replaceMediaAsset | request | uploadId | string (uuid) | yes
VenueOpsService | replaceMediaAsset | request | note | string |  | (max length 500)
VenueOpsService | replaceMediaAsset | response | asset | MediaAsset | yes
VenueOpsService | replaceMediaAsset | response | asset.id | string (uuid) | yes
VenueOpsService | replaceMediaAsset | response | asset.kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | replaceMediaAsset | response | asset.status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | replaceMediaAsset | response | asset.filename | string | yes
VenueOpsService | replaceMediaAsset | response | asset.contentType | string | yes
VenueOpsService | replaceMediaAsset | response | asset.sizeBytes | integer | yes
VenueOpsService | replaceMediaAsset | response | asset.title | LocalisedText
VenueOpsService | replaceMediaAsset | response | asset.description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | replaceMediaAsset | response | asset.altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | replaceMediaAsset | response | asset.width | integer |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.height | integer |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.hasTransparency | boolean |  | Whether the image has an alpha channel with any pixel not fully opaque, recorded from the file when the upload completes; null for a file that is not an image (ADAM CR-106, option 1; CHG-R10TEN-012). (read-only; nullable)
VenueOpsService | replaceMediaAsset | response | asset.durationSeconds | number |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.customMetadata | object |  | BL-178. (nullable)
VenueOpsService | replaceMediaAsset | response | asset.sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | replaceMediaAsset | response | asset.tags | array of string
VenueOpsService | replaceMediaAsset | response | asset.categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | replaceMediaAsset | response | asset.venueId | string (uuid) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | replaceMediaAsset | response | asset.thumbnailUrl | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | replaceMediaAsset | response | asset.rights | MediaRights |  | Licensing terms.
VenueOpsService | replaceMediaAsset | response | asset.rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | replaceMediaAsset | response | asset.rights.licensor | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.licenceReference | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.validFrom | string (date) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.validTo | string (date) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | replaceMediaAsset | response | asset.rights.attributionRequired | boolean |  | (default False)
VenueOpsService | replaceMediaAsset | response | asset.rights.attributionText | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | replaceMediaAsset | response | asset.rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | replaceMediaAsset | response | asset.rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | replaceMediaAsset | response | asset.rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.isRightsExpired | boolean
VenueOpsService | replaceMediaAsset | response | asset.version | integer
VenueOpsService | replaceMediaAsset | response | asset.uploadedByPrincipalId | string (uuid)
VenueOpsService | replaceMediaAsset | response | asset.createdAt | string (date-time) | yes
VenueOpsService | replaceMediaAsset | response | asset.extractedText | string |  | The text pulled out of an uploaded document (R8 blocker ORDERS-MONEY-C19): written by the upload's processing job once text extraction finishes (PDF, Word and plain-text kinds), replaced when the fil… (read-only; nullable)
VenueOpsService | replaceMediaAsset | response | asset.releasedByPrincipalId | string (uuid) |  | The reviewer who released the asset from quarantined (R8 blocker ORDERS-MONEY-C24, CHG-R8MIG-022); null if it never was. (read-only; nullable)
VenueOpsService | replaceMediaAsset | response | asset.releasedAt | string (date-time) |  | When it was released from quarantined. (read-only; nullable)
VenueOpsService | replaceMediaAsset | response | affectedSurfaces | integer | yes | How many surfaces now show the new file.
VenueOpsService | replaceMediaAsset | response | liveSurfaces | integer |  | Of those, how many are published to guests right now.
VenueOpsService | replaceMediaAsset | response | derivativesRegenerating | boolean
VenueOpsService | replaceMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | replaceMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | replyToMyCase | request | message | string | yes | (min length 1; max length 10000)
MarketingService | replyToMyCase | response | id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | replyToMyCase | response | caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | replyToMyCase | response | subjectId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | replyToMyCase | response | subject | string | yes | The case's one-line title, not a person.
MarketingService | replyToMyCase | response | kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | replyToMyCase | response | channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | replyToMyCase | response | recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | replyToMyCase | response | syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | replyToMyCase | response | categoryId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | replyToMyCase | response | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | replyToMyCase | response | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | replyToMyCase | response | priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | replyToMyCase | response | assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | venueId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | relatedOrderId | string |  | (nullable)
MarketingService | replyToMyCase | response | slaDueAt | string (date-time) |  | (nullable)
MarketingService | replyToMyCase | response | isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | replyToMyCase | response | slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | replyToMyCase | response | escalationCount | integer
MarketingService | replyToMyCase | response | createdAt | string (date-time) | yes
MarketingService | replyToMyCase | response | resolvedAt | string (date-time) |  | (nullable)
MarketingService | replyToMyCase | response | description | string
MarketingService | replyToMyCase | response | resolutionNote | string |  | (nullable)
MarketingService | replyToMyCase | response | messages | array of CaseMessage
MarketingService | replyToMyCase | response | messages[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | replyToMyCase | response | messages[].resolution | string |  | What was actually done about it.
MarketingService | replyToMyCase | response | messages[].id | string | yes
MarketingService | replyToMyCase | response | messages[].body | string | yes
MarketingService | replyToMyCase | response | messages[].isInternal | boolean | yes
MarketingService | replyToMyCase | response | messages[].authorKind | enum (agent, guest, system, ai) | yes
MarketingService | replyToMyCase | response | messages[].authorPrincipalId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | messages[].channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | replyToMyCase | response | messages[].attachmentRefs | array of string
MarketingService | replyToMyCase | response | messages[].recordedAt | string (date-time) | yes | Device time — addCaseMessage is offline-capable.
MarketingService | replyToMyCase | response | messages[].syncedAt | string (date-time) |  | Server time the message arrived. (read-only)
MarketingService | replyToMyCase | response | messages[].caseId | string (uuid) | yes | The case this message belongs to, from the path of addCaseMessage (the opening one, createCase). (read-only)
MarketingService | replyToMyCase | param (path) | caseId | string (uuid) | yes
MarketingService | replyToMyCase | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reprintOrder | request | delivery | enum (print, email, sms, whatsapp, wallet) | yes
OrderService | reprintOrder | request | destination | string
OrderService | reprintOrder | request | lineIds | array of string (uuid) |  | Omit to reprint every line.
OrderService | reprintOrder | request | reason | enum (printerFault, guestRequest, lostTicket, notReceived, other)
OrderService | reprintOrder | request | recordedAt | string (date-time) | yes | When the till reprinted — device time, as for every offline-capable write.
OrderService | reprintOrder | response | reprintCount | integer |  | The order's total, the sum of lines[].reprintCount.
OrderService | reprintOrder | response | lines | array of object |  | The count per reprinted line, as recorded on OrderLine.reprintCount.
OrderService | reprintOrder | response | lines[].lineId | string (uuid) | yes
OrderService | reprintOrder | response | lines[].reprintCount | integer | yes
OrderService | reprintOrder | response | reissuedTicketIds | array of string (uuid) |  | The entitlements reprinted.
OrderService | reprintOrder | param (path) | orderId | string (uuid) | yes
OrderService | reprintOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | reprintReceipt | request | delivery | enum (print, email, sms, whatsapp) | yes
RetailService | reprintReceipt | request | destination | string |  | Required for anything but print.
RetailService | reprintReceipt | response | reprintCount | integer
RetailService | reprintReceipt | param (path) | saleId | string (uuid) | yes
RetailService | reprintReceipt | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | requestAppBuild | request | platform | enum (ios, android) | yes
WhiteLabelService | requestAppBuild | request | configVersion | string |  | A published ConfigVersion.version.
WhiteLabelService | requestAppBuild | request | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | requestAppBuild | request | submitToStore | boolean |  | Submit with the client's recorded API credential once built. (default False)
WhiteLabelService | requestAppBuild | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | requestAppBuild | response | platform | enum (ios, android) | yes
WhiteLabelService | requestAppBuild | response | configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | requestAppBuild | response | storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | requestAppBuild | response | versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | requestAppBuild | response | buildNumber | integer |  | (read-only)
WhiteLabelService | requestAppBuild | response | status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the white-label jobs component's, in the workers host, from appBuild.requested (ADAM CR-106); from submitted on it is read from the store with the client's credential, or… (read-only)
WhiteLabelService | requestAppBuild | response | failureReason | string |  | (read-only; nullable)
WhiteLabelService | requestAppBuild | response | packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | requestAppBuild | response | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | requestAppBuild | response | submitToStore | boolean |  | (default False)
WhiteLabelService | requestAppBuild | response | requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | requestAppBuild | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | requestAppBuild | response | finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | requestAppBuild | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | requestAppBuild | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | requestBill | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | requestBill | response | id | string (uuid) | yes
FnbService | requestBill | response | tableId | string (uuid) | yes
FnbService | requestBill | response | tableLabel | string
FnbService | requestBill | response | outletId | string (uuid) | yes
FnbService | requestBill | response | covers | integer | yes
FnbService | requestBill | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | requestBill | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | requestBill | response | subjectId | string (uuid) |  | (nullable)
FnbService | requestBill | response | orders | array of FnbOrder | yes
FnbService | requestBill | response | orders[].id | string (uuid) | yes
FnbService | requestBill | response | orders[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | requestBill | response | orders[].outletId | string (uuid) | yes
FnbService | requestBill | response | orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | requestBill | response | orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | requestBill | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | requestBill | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | requestBill | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | requestBill | response | orders[].lines | array of object | yes
FnbService | requestBill | response | orders[].lines[].id | string (uuid) | yes
FnbService | requestBill | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | requestBill | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | requestBill | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | requestBill | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | requestBill | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | requestBill | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | requestBill | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | requestBill | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | requestBill | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | requestBill | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | requestBill | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | requestBill | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | requestBill | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | requestBill | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | requestBill | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | requestBill | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | requestBill | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | requestBill | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | requestBill | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | requestBill | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | requestBill | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | requestBill | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | requestBill | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | requestBill | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | requestBill | response | orders[].kitchenTickets[].orderNumber | string
FnbService | requestBill | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | requestBill | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | requestBill | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | requestBill | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | requestBill | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | requestBill | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | requestBill | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | requestBill | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | requestBill | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | requestBill | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | requestBill | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | requestBill | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | requestBill | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | requestBill | response | orders[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | requestBill | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | requestBill | response | orders[].createdAt | string (date-time) | yes
FnbService | requestBill | response | orders[].recordedAt | string (date-time)
FnbService | requestBill | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | requestBill | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | requestBill | response | mergedFromVisitIds | array of string (uuid)
FnbService | requestBill | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | requestBill | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | requestBill | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | requestBill | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | requestBill | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | requestBill | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | requestBill | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | requestBill | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | requestBill | response | openedAt | string (date-time) | yes
FnbService | requestBill | response | closedAt | string (date-time) |  | (nullable)
FnbService | requestBill | response | serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | requestBill | response | serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | requestBill | response | note | string |  | The server's note on the visit (updateTableVisit). (max length 500; read-only; nullable)
FnbService | requestBill | param (path) | visitId | string (uuid) | yes
FnbService | requestBill | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | requestGroupBooking | request | kind | enum (general, school, corporate, party) | yes
OrderService | requestGroupBooking | request | packageProductId | string | yes
OrderService | requestGroupBooking | request | preferredDate | string (date) | yes
OrderService | requestGroupBooking | request | performanceId | string (uuid) |  | The session, for a timed or session package (DEC-121, Chinmay, 2 October 2026: a date and, for session products, a session; R8 blocker ORDERS-MONEY-C41, CHG-R8MIG-017): a catalogue.performance on pre… (nullable)
OrderService | requestGroupBooking | request | expectedSize | integer | yes | (min 2)
OrderService | requestGroupBooking | request | organisationName | string |  | The school. (max length 200; nullable)
OrderService | requestGroupBooking | request | yearGroup | string |  | (max length 40; nullable)
OrderService | requestGroupBooking | request | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | request | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | requestGroupBooking | request | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | requestGroupBooking | request | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | response | id | string (uuid) | yes
OrderService | requestGroupBooking | response | kind | enum (general, school, corporate, party) |  | (default general)
OrderService | requestGroupBooking | response | packageProductId | string |  | The school-trip format or party package. (nullable)
OrderService | requestGroupBooking | response | yearGroup | string |  | (max length 40; nullable)
OrderService | requestGroupBooking | response | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | response | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | requestGroupBooking | response | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | requestGroupBooking | response | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | response | finalHeadcountDueBy | string (date-time) |  | (nullable)
OrderService | requestGroupBooking | response | quoteSentAt | string (date-time) |  | (read-only; nullable)
OrderService | requestGroupBooking | response | riskAssessmentSentAt | string (date-time) |  | (read-only; nullable)
OrderService | requestGroupBooking | response | preferredDate | string (date) |  | The date the guest asked for on requestGroupBooking — what its 409 dateUnavailable is checked against. (nullable)
OrderService | requestGroupBooking | response | performanceId | string (uuid) |  | The session, for a timed or session package (DEC-121, Chinmay, 2 October 2026: a date and, for session products, a session; R8 blocker ORDERS-MONEY-C41, CHG-R8MIG-017): a catalogue.performance on pre… (nullable)
OrderService | requestGroupBooking | response | orderId | string (uuid) | yes
OrderService | requestGroupBooking | response | leaderSubjectId | string (uuid) | yes
OrderService | requestGroupBooking | response | organisationName | string |  | (nullable)
OrderService | requestGroupBooking | response | expectedSize | integer | yes
OrderService | requestGroupBooking | response | confirmedSize | integer |  | (nullable)
OrderService | requestGroupBooking | response | minimumSize | integer |  | Below which the group rate does not apply. (nullable)
OrderService | requestGroupBooking | response | attendeeCaptureRequired | boolean |  | Whether names are needed before admission. (default False)
OrderService | requestGroupBooking | response | attendeeCaptureDueBy | string (date-time) |  | (nullable)
OrderService | requestGroupBooking | response | status | enum (provisional, confirmed, namesPending, complete, cancelled) | yes
OrderService | requestGroupBooking | response | version | integer |  | The row's version, its ETag (accepted 26 October 2026, Chinmay, ADAM CR-257 option A): 1 on create and bumped on every write; getGroupBooking and updateGroupBooking send it as ETag, and updateGroupBo… (min 1; default 1; read-only)
OrderService | requestGroupBooking | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | requestGuestOtp | request | identifier | string | yes | (max length 256)
IdentityService | requestGuestOtp | request | channel | enum (whatsapp, sms, email) |  | Optional for a mobile number (ADAM CR-222, 25 October 2026): left out, the server picks WhatsApp first and SMS as the fallback (the lead, 25 October 2026, r10 Q5), from the tenant's configured delive…
IdentityService | requestGuestOtp | request | purpose | enum (login, register, verify, passwordReset, stepUp) |  | (default login)
IdentityService | requestGuestOtp | response | expiresInSeconds | integer
IdentityService | requestGuestOtp | response | resendAfterSeconds | integer
IdentityService | requestGuestOtp | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | requestSuggestion | request | kind | object | yes | A guest caller may ask for prepPlan, upsell, waitTime and itinerary only.
AiService | requestSuggestion | request | subjectRef | string |  | (nullable)
AiService | requestSuggestion | request | horizon | string |  | For a forecast — nextService, 7d, 28d, or an ISO period. (nullable)
AiService | requestSuggestion | request | context | object |  | What the caller already knows.
AiService | requestSuggestion | response | id | string (uuid) | yes
AiService | requestSuggestion | response | kind | SuggestionKind: enum (price, replenishment, requisition, demandForecast, prepPlan, menuEngineering, staffing, slaTarget, …) | yes | What is being suggested.
AiService | requestSuggestion | response | basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | requestSuggestion | response | scopePath | string
AiService | requestSuggestion | response | subjectRef | string |  | What it is about — a product, an outlet, an item, a party. (nullable)
AiService | requestSuggestion | response | value | object |  | The suggestion itself.
AiService | requestSuggestion | response | confidence | number |  | Null for a heuristic and that is honest. (min 0; max 1; nullable)
AiService | requestSuggestion | response | explanation | string |  | Plain words, always present, whatever the basis.
AiService | requestSuggestion | response | inputs | object |  | What went in.
AiService | requestSuggestion | response | producerRef | string |  | The rule name or the model id and version.
AiService | requestSuggestion | response | maturity | AiMaturity | yes | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | requestSuggestion | response | maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | requestSuggestion | response | maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | requestSuggestion | response | maturity.sources | array of object
AiService | requestSuggestion | response | maturity.sources[].source | enum (venueSettings, startingPattern, calendar, weather, bookingsOnHand, ownHistory, importedHistory, configuration, …) | yes
AiService | requestSuggestion | response | maturity.sources[].detail | string |  | e.g. (nullable)
AiService | requestSuggestion | response | maturity.sources[].observations | integer |  | (nullable)
AiService | requestSuggestion | response | maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | requestSuggestion | response | maturity.limitedHistory | boolean
AiService | requestSuggestion | response | maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | requestSuggestion | response | maturity.nextStage.stage | enum (learning, established, learned)
AiService | requestSuggestion | response | maturity.nextStage.needs | string
AiService | requestSuggestion | response | maturity.nextStage.expectedBy | string (date) |  | (nullable)
AiService | requestSuggestion | response | producedAt | string (date-time) | yes
AiService | requestSuggestion | response | expiresAt | string (date-time) |  | A demand forecast for Saturday is worthless on Sunday. (nullable)
AiService | requestSuggestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | rescheduleOrder | request | targetPerformanceId | string (uuid) | yes
OrderService | rescheduleOrder | request | lineIds | array of string (uuid) |  | Omit to move the whole order.
OrderService | rescheduleOrder | request | waiveFee | boolean |  | (default False)
OrderService | rescheduleOrder | request | reason | string |  | (max length 500)
OrderService | rescheduleOrder | request | recordedAt | string (date-time) | yes
OrderService | rescheduleOrder | response | orderId | string (uuid) | yes
OrderService | rescheduleOrder | response | outgoingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | rescheduleOrder | response | outgoingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | outgoingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | outgoingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | incomingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | rescheduleOrder | response | incomingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | incomingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | incomingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | exchangeFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | rescheduleOrder | response | exchangeFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | exchangeFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | exchangeFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | difference | object | yes | Only the difference settles.
OrderService | rescheduleOrder | response | difference.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | difference.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | difference.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | newLineIds | array of string (uuid)
OrderService | rescheduleOrder | response | revokedEntitlementIds | array of string (uuid)
OrderService | rescheduleOrder | response | issuedEntitlementIds | array of string (uuid)
OrderService | rescheduleOrder | param (path) | orderId | string (uuid) | yes
OrderService | rescheduleOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | reserveMerchandise | request | id | string (uuid) | yes
RetailService | reserveMerchandise | request | subjectId | string (uuid)
RetailService | reserveMerchandise | request | lines | array of object | yes | (min items 1)
RetailService | reserveMerchandise | request | lines[].merchandiseId | string (uuid) | yes
RetailService | reserveMerchandise | request | lines[].quantity | integer | yes | (min 1)
RetailService | reserveMerchandise | request | expiresAt | string (date-time) |  | At least 15 minutes from now and no later than the close of the venue's operating day (audit R215).
RetailService | reserveMerchandise | request | collectionNote | string |  | (max length 200)
RetailService | reserveMerchandise | response | id | string | yes
RetailService | reserveMerchandise | response | reservationNumber | string
RetailService | reserveMerchandise | response | outletId | string (uuid) | yes
RetailService | reserveMerchandise | response | subjectId | string (uuid) |  | (nullable)
RetailService | reserveMerchandise | response | lines | array of object | yes
RetailService | reserveMerchandise | response | lines[].merchandiseId | string (uuid)
RetailService | reserveMerchandise | response | lines[].name | string
RetailService | reserveMerchandise | response | lines[].quantity | integer
RetailService | reserveMerchandise | response | status | enum (reserved, collected, expired, cancelled) | yes
RetailService | reserveMerchandise | response | collectionNote | string |  | (nullable)
RetailService | reserveMerchandise | response | expiresAt | string (date-time) | yes
RetailService | reserveMerchandise | response | collectedAt | string (date-time) |  | (nullable)
RetailService | reserveMerchandise | param (path) | outletId | string (uuid) | yes
RetailService | reserveMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | resolveProductByCode | response | id | string (uuid) | yes
CatalogueService | resolveProductByCode | response | listPrice | Money |  | The list price on the caller's channel now, resolved on read from the price lists (listProductVariants; R8 blocker cause GPS-C27, CHG-R8SPN-028). (read-only; nullable)
CatalogueService | resolveProductByCode | response | referencePrice | Money |  | The price a saving is measured against (accepted 26 October 2026, Chinmay, ADAM CR-253 option C), set by the back office on the variant (updateProductVariant). (nullable)
CatalogueService | resolveProductByCode | response | savingPercent | integer |  | Computed by the server, never in the browser (ADAM CR-253): with a referencePrice and a listPrice below it, the whole percent the list price saves, floor((referencePrice - listPrice) / referencePrice… (read-only; nullable)
CatalogueService | resolveProductByCode | response | productId | string (uuid) | yes
CatalogueService | resolveProductByCode | response | sku | string | yes
CatalogueService | resolveProductByCode | response | axisValues | object | yes
CatalogueService | resolveProductByCode | response | name | string |  | Taken from their variant tables, 20 September. (max length 150; nullable)
CatalogueService | resolveProductByCode | response | barcode | string |  | Taken from their variant tables, 20 September. (max length 64; nullable)
CatalogueService | resolveProductByCode | response | isDefault | boolean |  | Taken from their variant tables. (default False)
CatalogueService | resolveProductByCode | response | isActive | boolean | yes | False when retired.
CatalogueService | resolveProductByCode | response | description | object |  | Who this ticket type is for and what it includes, shown behind the (i) on each Adult, Child, Senior or Infant row (decided 29 September, 23SEP-6). (nullable)
CatalogueService | resolveProductByCode | param (query) | code | string | yes
CatalogueService | resolveProductByCode | param (query) | partnerId | string (uuid) |  | Required from a staff caller (400 partner-required); a partner caller's own, which it may omit (ADAM CR-111).
MarketingService | respondToInvitation | request | response | enum (accept, decline) | yes
MarketingService | respondToInvitation | request | plusOnes | integer |  | (default 0)
MarketingService | respondToInvitation | response | id | string (uuid) | yes
MarketingService | respondToInvitation | response | campaignId | string (uuid) | yes
MarketingService | respondToInvitation | response | subjectId | string (uuid) |  | (nullable)
MarketingService | respondToInvitation | response | recipientEmail | string (email) |  | (nullable)
MarketingService | respondToInvitation | response | token | string | yes | Single-use and unguessable.
MarketingService | respondToInvitation | response | plusOnes | integer |  | (default 0)
MarketingService | respondToInvitation | response | status | enum (issued, viewed, accepted, declined, expired, revoked) | yes
MarketingService | respondToInvitation | response | entitlementIds | array of string (uuid)
MarketingService | respondToInvitation | response | respondedAt | string (date-time) |  | (nullable)
MarketingService | respondToInvitation | response | scopePath | string |  | The partition key (ADR-0005).
MarketingService | respondToInvitation | param (path) | token | string | yes
MarketingService | respondToInvitation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | restoreConfigVersion | request | discardDraftChanges | boolean |  | True overwrites unpublished changes in the draft. (default False)
WhiteLabelService | restoreConfigVersion | response | tenantId | string (uuid) | yes
WhiteLabelService | restoreConfigVersion | response | version | string | yes | The draft's working version label; the published one is ConfigVersion.version.
WhiteLabelService | restoreConfigVersion | response | isDraft | boolean |  | True for the working draft, which is the only row. (read-only)
WhiteLabelService | restoreConfigVersion | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload).
WhiteLabelService | restoreConfigVersion | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | restoreConfigVersion | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | restoreConfigVersion | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | restoreConfigVersion | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | restoreConfigVersion | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | restoreConfigVersion | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | restoreConfigVersion | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | restoreConfigVersion | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | restoreConfigVersion | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | restoreConfigVersion | response | brand.showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | restoreConfigVersion | response | appIcons | AppIcons
WhiteLabelService | restoreConfigVersion | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | restoreConfigVersion | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | restoreConfigVersion | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | restoreConfigVersion | response | appIcons.derived[].size | string
WhiteLabelService | restoreConfigVersion | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | restoreConfigVersion | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | restoreConfigVersion | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | restoreConfigVersion | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlow | BookingFlowConfig |  | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
WhiteLabelService | restoreConfigVersion | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | restoreConfigVersion | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | restoreConfigVersion | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | restoreConfigVersion | response | bookingFlows | array of BookingFlow |  | Every venue's booking flows in the draft (whitelabel.booking_flow), so a publish snapshots them with the rest (decided 29 September, W12). (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].id | string (uuid) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | theme | Theme
WhiteLabelService | restoreConfigVersion | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | restoreConfigVersion | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | restoreConfigVersion | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | restoreConfigVersion | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | restoreConfigVersion | response | theme.venueSkins | array of object |  | The guest app skin each venue takes (ADAM CR-280, option B, 28 October 2026; CHG-R11TEN-007): one entry per venue, naming one of the approved app design's skins (handoff/design-tokens/guest-app.yaml,… (default [])
WhiteLabelService | restoreConfigVersion | response | theme.venueSkins[].venueId | string (uuid) | yes
WhiteLabelService | restoreConfigVersion | response | theme.venueSkins[].skinKey | GuestAppSkinKey: enum (park, water, stadium, theatre, dining, kids, museum, rooms, …) | yes | The guest app's skins per venue kind, as the approved Mobile App v4 design draws them (handoff/design-tokens/guest-app.yaml skins.byVenueKind; ADAM CR-280, CHG-R11TEN-007).
WhiteLabelService | restoreConfigVersion | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | fonts | FontConfig
WhiteLabelService | restoreConfigVersion | response | fonts.primaryLatin | string | yes
WhiteLabelService | restoreConfigVersion | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | restoreConfigVersion | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | restoreConfigVersion | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | restoreConfigVersion | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | restoreConfigVersion | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | restoreConfigVersion | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | restoreConfigVersion | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | restoreConfigVersion | response | footer.columns | array of object
WhiteLabelService | restoreConfigVersion | response | footer.columns[].heading | string
WhiteLabelService | restoreConfigVersion | response | footer.columns[].sortOrder | integer |  | The column's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | restoreConfigVersion | response | footer.columns[].links | array of object |  | The column's links in display order, stored on the column row as one value (R8 blocker WHITE-C24).
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.termsUrl | string
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | footer.copyrightText | string
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks | array of object
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks[].platform | string
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks[].url | string
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks[].sortOrder | integer |  | The link's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | restoreConfigVersion | response | notificationBranding | object |  | BL-003. (nullable)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.senderName | string
WhiteLabelService | restoreConfigVersion | response | notificationBranding.replyToEmail | string (email)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.smsSenderId | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.whatsappBusinessId | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.logoAssetId | string (uuid) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | enabledPaymentMethods | array of string |  | BL-004. (nullable)
WhiteLabelService | restoreConfigVersion | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | restoreConfigVersion | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | restoreConfigVersion | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | restoreConfigVersion | response | header | HeaderConfig
WhiteLabelService | restoreConfigVersion | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | restoreConfigVersion | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | restoreConfigVersion | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | restoreConfigVersion | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | restoreConfigVersion | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | navigation.items[].icon | string
WhiteLabelService | restoreConfigVersion | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | restoreConfigVersion | response | navigation.items[].isVisible | boolean | yes | At most five may be visible when kind is bottomNavigation; the rest overflow.
WhiteLabelService | restoreConfigVersion | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | restoreConfigVersion | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | restoreConfigVersion | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | restoreConfigVersion | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | homepage | HomepageLayout |  | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | restoreConfigVersion | response | homepage.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | restoreConfigVersion | response | homepage.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | restoreConfigVersion | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | homepage.sections | array of object | yes
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | restoreConfigVersion | response | modules | array of ModuleEnablement
WhiteLabelService | restoreConfigVersion | response | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | restoreConfigVersion | response | modules[].displayName | string
WhiteLabelService | restoreConfigVersion | response | modules[].isLicensed | boolean | yes | From the tenant's subscription.
WhiteLabelService | restoreConfigVersion | response | modules[].isEnabled | boolean | yes
WhiteLabelService | restoreConfigVersion | response | modules[].referencedBy | array of string |  | Navigation items and homepage sections pointing at this module. (read-only)
WhiteLabelService | restoreConfigVersion | response | features | array of FeatureToggle
WhiteLabelService | restoreConfigVersion | response | features[].featureKey | object | yes | guestCheckout is off by default (decided 17 September 2026, matrix 2.6.28, placement settled by [ADR-0045](../../docs/adr/0045-every-order-carries-a-proven-contact.md) 18 September): the venue sets t…
WhiteLabelService | restoreConfigVersion | response | features[].displayName | string
WhiteLabelService | restoreConfigVersion | response | features[].isEnabled | boolean | yes
WhiteLabelService | restoreConfigVersion | response | features[].changeScope | object | yes | Wallet and payment integrations are buildTime on native apps — enabling one needs a release, not a publish. (read-only)
WhiteLabelService | restoreConfigVersion | response | features[].requiresConfiguration | boolean |  | True where the feature needs credentials or setup elsewhere first.
WhiteLabelService | restoreConfigVersion | response | languages | LanguageConfig
WhiteLabelService | restoreConfigVersion | response | languages.languages | array of string | yes | A tenant may add or select interface languages beyond English and Arabic (Chinmay, 2 October, workbook Q145; CHG-CSA-039).
WhiteLabelService | restoreConfigVersion | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | restoreConfigVersion | response | languages.uiStringCoverage | array of object |  | How complete the interface strings are in each enabled language (CHG-CSA-039). (read-only)
WhiteLabelService | restoreConfigVersion | response | languages.uiStringCoverage[].language | string
WhiteLabelService | restoreConfigVersion | response | languages.uiStringCoverage[].coveragePercent | number |  | (min 0; max 100)
WhiteLabelService | restoreConfigVersion | response | languages.uiStringCoverage[].status | enum (complete, draft, missing)
WhiteLabelService | restoreConfigVersion | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps[].language | string
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps[].areas | array of string |  | The kinds of the missing items, from the closed list contentPages, banners, promoBlocks, faqs, policies (ADAM CR-194).
WhiteLabelService | restoreConfigVersion | response | updatedAt | string (date-time)
WhiteLabelService | restoreConfigVersion | response | isInMaintenance | boolean |  | Written by setMaintenanceMode; read by getTenantAppStatus. (default False)
WhiteLabelService | restoreConfigVersion | response | maintenanceMessage | object |  | The message on the branded maintenance screen. (nullable)
WhiteLabelService | restoreConfigVersion | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.storeUrl | object |  | The store page of the tenant's app for each platform. (nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.storeUrl.ios | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.storeUrl.android | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | restoreConfigVersion | response | contact | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | restoreConfigVersion | response | contact.phone | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.address | object |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | restoreConfigVersion | response | availability | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | restoreConfigVersion | response | availabilityMessage | object |  | Live state, written by setMaintenanceMode (audit R073). (nullable)
WhiteLabelService | restoreConfigVersion | response | venues | array of object |  | The tenant's active venues, for the guest venue picker on WEB-001 and GST-001 (decided 28 September, audit R267).
WhiteLabelService | restoreConfigVersion | response | venues[].venueId | string (uuid) | yes
WhiteLabelService | restoreConfigVersion | response | venues[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | venues[].city | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | venues[].openingHours | object |  | Today's hours as shown to a guest, e.g. (nullable)
WhiteLabelService | restoreConfigVersion | param (path) | version | string | yes
WhiteLabelService | restoreConfigVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | restoreWalletConfigurationVersion | request | reason | string | yes | (min length 1; max length 500)
WalletService | restoreWalletConfigurationVersion | response | version | integer
WalletService | restoreWalletConfigurationVersion | response | publishedAt | string (date-time) |  | (nullable)
WalletService | restoreWalletConfigurationVersion | response | publishedBy | string (uuid) |  | (nullable)
WalletService | restoreWalletConfigurationVersion | response | note | string |  | (nullable)
WalletService | restoreWalletConfigurationVersion | response | findings | array of object
WalletService | restoreWalletConfigurationVersion | response | findings[].severity | enum (blocking, warning)
WalletService | restoreWalletConfigurationVersion | response | findings[].code | string
WalletService | restoreWalletConfigurationVersion | response | findings[].message | string
WalletService | restoreWalletConfigurationVersion | response | scopePath | string
WalletService | restoreWalletConfigurationVersion | param (path) | version | integer | yes
WalletService | restoreWalletConfigurationVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | resumeOrder | response | order | Order | yes
OrderService | resumeOrder | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | resumeOrder | response | order.orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | resumeOrder | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | resumeOrder | response | order.channel | object | yes | Where it came from.
OrderService | resumeOrder | response | order.channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | resumeOrder | response | order.venueId | string (uuid) | yes
OrderService | resumeOrder | response | order.scopePath | string | yes
OrderService | resumeOrder | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | resumeOrder | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | resumeOrder | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | resumeOrder | response | order.chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | resumeOrder | response | order.chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | resumeOrder | response | order.chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | resumeOrder | response | order.chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | resumeOrder | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | resumeOrder | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | resumeOrder | response | order.droppedPromotions[].name | string
OrderService | resumeOrder | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | resumeOrder | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | resumeOrder | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.lines | array of OrderLine | yes
OrderService | resumeOrder | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | resumeOrder | response | order.lines[].variantId | string (uuid) | yes
OrderService | resumeOrder | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | resumeOrder | response | order.lines[].performanceId | string (uuid)
OrderService | resumeOrder | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | resumeOrder | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | resumeOrder | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | resumeOrder | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | resumeOrder | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | resumeOrder | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | resumeOrder | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | resumeOrder | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | resumeOrder | response | order.lines[].holderName | string |  | (nullable)
OrderService | resumeOrder | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | resumeOrder | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | resumeOrder | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | resumeOrder | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | resumeOrder | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | resumeOrder | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | resumeOrder | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | resumeOrder | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | resumeOrder | response | order.payments | array of Payment
OrderService | resumeOrder | response | order.payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].id | string (uuid) | yes
OrderService | resumeOrder | response | order.payments[].orderId | string (uuid) | yes
OrderService | resumeOrder | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | resumeOrder | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | resumeOrder | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | resumeOrder | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | resumeOrder | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | resumeOrder | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | resumeOrder | response | order.payments[].providerName | string |  | (nullable)
OrderService | resumeOrder | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | resumeOrder | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | resumeOrder | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | resumeOrder | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | resumeOrder | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | resumeOrder | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | resumeOrder | response | order.principalId | string (uuid)
OrderService | resumeOrder | response | order.workstationId | string (uuid)
OrderService | resumeOrder | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | resumeOrder | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | resumeOrder | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | resumeOrder | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | resumeOrder | response | order.createdAt | string (date-time) | yes
OrderService | resumeOrder | response | order.recordedAt | string (date-time) | yes
OrderService | resumeOrder | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | resumeOrder | response | hasChanged | boolean | yes | True where anything moved while the sale was parked.
OrderService | resumeOrder | response | changes | array of object
OrderService | resumeOrder | response | changes[].kind | enum (priceChanged, promotionExpired, promotionNowApplies, soldOut, seatHoldExpired, productWithdrawn)
OrderService | resumeOrder | response | changes[].lineId | string (uuid)
OrderService | resumeOrder | response | changes[].detail | string
OrderService | resumeOrder | response | changes[].wasAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | changes[].wasAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | changes[].wasAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | changes[].wasAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | changes[].nowAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | changes[].nowAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | changes[].nowAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | changes[].nowAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | param (path) | orderId | string (uuid) | yes
OrderService | resumeOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | resumeShift | request | recordedAt | string (date-time) | yes
OrderService | resumeShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | resumeShift | response | workstationId | string (uuid) | yes
OrderService | resumeShift | response | venueId | string (uuid) | yes
OrderService | resumeShift | response | scopePath | string | yes
OrderService | resumeShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | resumeShift | response | principalDisplayName | string
OrderService | resumeShift | response | incidents | array of object |  | BL-097.
OrderService | resumeShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | resumeShift | response | incidents[].at | string (date-time)
OrderService | resumeShift | response | incidents[].principalId | string (uuid)
OrderService | resumeShift | response | incidents[].note | string |  | (nullable)
OrderService | resumeShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | resumeShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | resumeShift | response | depositBoxCode | string |  | (nullable)
OrderService | resumeShift | response | bagNumber | string |  | (nullable)
OrderService | resumeShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | resumeShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | resumeShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | resumeShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | resumeShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | resumeShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | resumeShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | resumeShift | response | openedAt | string (date-time) | yes
OrderService | resumeShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | resumeShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | resumeShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | resumeShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | resumeShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | resumeShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | resumeShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | resumeShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | resumeShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | resumeShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | resumeShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | resumeShift | response | approvals | array of object
OrderService | resumeShift | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | resumeShift | response | approvals[].principalId | string (uuid) | yes
OrderService | resumeShift | response | approvals[].at | string (date-time) | yes
OrderService | resumeShift | response | approvals[].reason | string
OrderService | resumeShift | param (path) | shiftId | string (uuid) | yes
OrderService | resumeShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | retryMyDunningPayment | request | paymentTokenId | string (uuid) |  | A saved card other than the one that failed: the id of one of the guest's own PaymentToken rows (payments.token, stored through storePaymentToken), not a payments.method id, which names a kind of met… (nullable)
OrderService | retryMyDunningPayment | response | id | string (uuid) | yes
OrderService | retryMyDunningPayment | response | subjectId | string (uuid)
OrderService | retryMyDunningPayment | response | orderId | string |  | The order whose renewal failed.
OrderService | retryMyDunningPayment | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | retryMyDunningPayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | retryMyDunningPayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | retryMyDunningPayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | retryMyDunningPayment | response | state | DunningState: enum (scheduled, inProgress, exhausted, recovered, resolvedManually) | yes | BL-100.
OrderService | retryMyDunningPayment | response | declineClass | object |  | From the most recent attempt.
OrderService | retryMyDunningPayment | response | attemptsMade | integer | yes
OrderService | retryMyDunningPayment | response | nextAttemptAt | string (date-time) |  | Null where the case has ended or the decline is hard. (nullable)
OrderService | retryMyDunningPayment | response | firstFailedAt | string (date-time) | yes
OrderService | retryMyDunningPayment | response | resolvedAt | string (date-time) |  | (nullable)
OrderService | retryMyDunningPayment | response | resolution | enum (paidByOtherMeans, cardReplaced, writeOff, cancelledByGuest, None) |  | (nullable)
OrderService | retryMyDunningPayment | response | resolutionNote | string |  | What resolveDunningCase was told, which had nowhere to land until now. (max length 500; nullable)
OrderService | retryMyDunningPayment | response | resolvedByPrincipalId | string (uuid) |  | Who closed it. (read-only; nullable)
OrderService | retryMyDunningPayment | response | scopePath | string |  | The partition key (ADR-0005).
OrderService | retryMyDunningPayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | retryMyDunningPayment | param (path) | caseId | string (uuid) | yes
AiService | revokeAiPolicyException | request | reason | string | yes | (max length 1000)
AiService | revokeAiPolicyException | response | id | string (uuid) |  | (read-only)
AiService | revokeAiPolicyException | response | policyId | string (uuid) | yes
AiService | revokeAiPolicyException | response | capabilityKey | string |  | (nullable)
AiService | revokeAiPolicyException | response | reason | string | yes | (max length 2000)
AiService | revokeAiPolicyException | response | compensatingControls | array of string
AiService | revokeAiPolicyException | response | startsAt | string (date-time) |  | (nullable)
AiService | revokeAiPolicyException | response | expiresAt | string (date-time) | yes | Required.
AiService | revokeAiPolicyException | response | status | enum (active, expired, revoked) |  | (read-only)
AiService | revokeAiPolicyException | response | approvedByPrincipalId | string (uuid) |  | (read-only)
AiService | revokeAiPolicyException | response | revokedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | revokeAiPolicyException | response | revokedAt | string (date-time) |  | (read-only; nullable)
AiService | revokeAiPolicyException | response | revokeReason | string |  | (read-only; nullable)
AiService | revokeAiPolicyException | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | revokeAiPolicyException | param (path) | exceptionId | string (uuid) | yes
AiService | revokeAiPolicyException | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | revokeFacePass | param (path) | enrolmentId | string (uuid) | yes
AccessService | revokeFacePass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | revokeGuestDevice | param (path) | subjectId | string (uuid) | yes
MarketingService | revokeGuestDevice | param (path) | deviceId | string (uuid) | yes
MarketingService | revokeGuestDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | rollbackAiRelease | request | reason | string | yes | (max length 1000)
AiService | rollbackAiRelease | response | id | string (uuid) |  | (read-only)
AiService | rollbackAiRelease | response | capabilityKey | string | yes
AiService | rollbackAiRelease | response | artefactKind | enum (model, prompt, routing, embedding, retrieval, rule) | yes
AiService | rollbackAiRelease | response | candidateRef | string | yes
AiService | rollbackAiRelease | response | currentRef | string |  | What production runs now: the rule, or the previously promoted artefact. (nullable)
AiService | rollbackAiRelease | response | previousRef | string |  | (read-only; nullable)
AiService | rollbackAiRelease | response | layer | enum (platform, tenant) | yes
AiService | rollbackAiRelease | response | module | object |  | Whose AI this release is, and so who promotes it (Chinmay, 2 October, workbook Q7: "AI release promotion goes to whoever holds it"; CHG-FUP-004). (nullable)
AiService | rollbackAiRelease | response | suggestionKind | object |  | Where the capability answers a requestSuggestion kind: promotion rewrites that kind's assignment in AiPolicy.suggestionProviders. (nullable)
AiService | rollbackAiRelease | response | stage | enum (draft, offlineEval, shadow, canary, production, monitored, rolledBack, rejected) | yes | (read-only)
AiService | rollbackAiRelease | response | shadowStartedAt | string (date-time) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | gatePassedAt | string (date-time) |  | When the shadow run passed its gate and promotionReady was raised. (read-only; nullable)
AiService | rollbackAiRelease | response | canaryScope | object |  | Venues or share of traffic in canary. (nullable)
AiService | rollbackAiRelease | response | promotedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | promotedAt | string (date-time) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | rolledBackByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | rolledBackAt | string (date-time) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | rollbackAiRelease | param (path) | releaseId | string (uuid) | yes
AiService | rollbackAiRelease | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | rollbackMenu | request | toVersion | integer |  | A MenuVersion.version from listMenuVersions. (nullable)
FnbService | rollbackMenu | response | id | string (uuid) | yes | (read-only)
FnbService | rollbackMenu | response | menuId | string (uuid) | yes
FnbService | rollbackMenu | response | version | integer | yes | (min 1)
FnbService | rollbackMenu | response | status | enum (draft, scheduled, live, superseded) | yes
FnbService | rollbackMenu | response | effectiveAt | string (date-time) |  | (nullable)
FnbService | rollbackMenu | response | publishedAt | string (date-time) |  | (nullable)
FnbService | rollbackMenu | response | publishedByPrincipalId | string (uuid) |  | (nullable)
FnbService | rollbackMenu | response | restoredFromVersion | integer |  | Set on a version written by rollbackMenu — the version it restored. (nullable)
FnbService | rollbackMenu | response | channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
FnbService | rollbackMenu | response | note | string |  | (nullable)
FnbService | rollbackMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | rollbackMenu | response | availability.daysOfWeek | array of integer
FnbService | rollbackMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | rollbackMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | rollbackMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | rollbackMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | rollbackMenu | response | sections | array of MenuSection |  | The sections and items as published.
FnbService | rollbackMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | rollbackMenu | response | sections[].code | string | yes
FnbService | rollbackMenu | response | sections[].name | string | yes
FnbService | rollbackMenu | response | sections[].sortOrder | integer | yes
FnbService | rollbackMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | rollbackMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | rollbackMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | rollbackMenu | response | sections[].items[].name | string | yes
FnbService | rollbackMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | rollbackMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | rollbackMenu | response | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | rollbackMenu | response | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | rollbackMenu | response | sections[].items[].sortOrder | integer
FnbService | rollbackMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | rollbackMenu | response | sections[].items[].stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | rollbackMenu | response | sections[].items[].menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | rollbackMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | rollbackMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | rollbackMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | rollbackMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | rollbackMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | rollbackMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | rollbackMenu | response | sections[].items[].unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | rollbackMenu | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | rollbackMenu | param (path) | menuId | string (uuid) | yes
FnbService | rollbackMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | rotateApiCredential | request | overlapHours | integer |  | (min 0; max 720; default 72)
PlatformService | rotateApiCredential | response | clientSecret | string (password)
PlatformService | rotateApiCredential | response | oldSecretExpiresAt | string (date-time) |  | (nullable)
PlatformService | rotateApiCredential | param (path) | clientId | string (uuid) | yes
PlatformService | rotateApiCredential | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | runAiEvaluation | request | suiteId | string (uuid) | yes
AiService | runAiEvaluation | request | releaseId | string (uuid) |  | (nullable)
AiService | runAiEvaluation | request | candidateRef | string | yes
AiService | runAiEvaluation | request | baselineRef | string |  | (nullable)
AiService | runAiEvaluation | request | kind | enum (offline, backtest, shadow) | yes
AiService | runAiEvaluation | response | id | string (uuid) |  | (read-only)
AiService | runAiEvaluation | response | suiteId | string (uuid) | yes
AiService | runAiEvaluation | response | releaseId | string (uuid) |  | (nullable)
AiService | runAiEvaluation | response | kind | enum (offline, backtest, shadow) | yes
AiService | runAiEvaluation | response | candidateRef | string
AiService | runAiEvaluation | response | baselineRef | string |  | (nullable)
AiService | runAiEvaluation | response | status | enum (queued, running, passed, failed, error) | yes | (read-only)
AiService | runAiEvaluation | response | metrics | object |  | (read-only; nullable)
AiService | runAiEvaluation | response | gate | object |  | The promotion gate thresholds (design 3.5 table) and whether each passed. (read-only; nullable)
AiService | runAiEvaluation | response | isolationCasesPassed | boolean |  | False blocks release, whatever the other metrics say. (read-only)
AiService | runAiEvaluation | response | requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | runAiEvaluation | response | startedAt | string (date-time) |  | (read-only)
AiService | runAiEvaluation | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | runAiEvaluation | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | runAiEvaluation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | runForecast | response | id | string (uuid) |  | (read-only)
AiService | runForecast | response | definitionId | string (uuid) | yes
AiService | runForecast | response | versionNumber | integer | yes | (min 1)
AiService | runForecast | response | module | object |  | The module of the version's definition (AiForecastDefinition.module), copied when the version is produced; the module whose AI publish permission publishForecastVersion requires (CHG-FUP-004). (read-only)
AiService | runForecast | response | status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | runForecast | response | basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | runForecast | response | maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | runForecast | response | maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | runForecast | response | maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | runForecast | response | maturity.sources | array of object
AiService | runForecast | response | maturity.sources[].source | enum (venueSettings, startingPattern, calendar, weather, bookingsOnHand, ownHistory, importedHistory, configuration, …) | yes
AiService | runForecast | response | maturity.sources[].detail | string |  | e.g. (nullable)
AiService | runForecast | response | maturity.sources[].observations | integer |  | (nullable)
AiService | runForecast | response | maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | runForecast | response | maturity.limitedHistory | boolean
AiService | runForecast | response | maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | runForecast | response | maturity.nextStage.stage | enum (learning, established, learned)
AiService | runForecast | response | maturity.nextStage.needs | string
AiService | runForecast | response | maturity.nextStage.expectedBy | string (date) |  | (nullable)
AiService | runForecast | response | producerRef | string
AiService | runForecast | response | modelVersion | string |  | (nullable)
AiService | runForecast | response | dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | runForecast | response | horizonStart | string (date-time)
AiService | runForecast | response | horizonEnd | string (date-time)
AiService | runForecast | response | qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | runForecast | response | publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | runForecast | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | runForecast | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | runForecast | response | createdAt | string (date-time) |  | (read-only)
AiService | runForecast | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | runForecast | param (path) | definitionKey | string | yes
AiService | runForecast | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | runReport | request | parameters | object |  | Open on purpose; its shape is the report's.
ReportingService | runReport | request | venueId | string (uuid) |  | Narrows to one venue.
ReportingService | runReport | request | dateFrom | string (date) |  | Defaults to today in the venue's time zone when not sent (decided 28 September, audit R158).
ReportingService | runReport | request | dateTo | string (date) |  | Defaults to today in the venue's time zone when not sent (audit R158).
ReportingService | runReport | request | forceAsync | boolean |  | Queue regardless of size, for a result to be collected later. (default False)
ReportingService | runReport | response | executionId | string | yes
ReportingService | runReport | response | columns | array of object | yes
ReportingService | runReport | response | columns[].key | string
ReportingService | runReport | response | columns[].label | string
ReportingService | runReport | response | columns[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …)
ReportingService | runReport | response | rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | runReport | response | totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | runReport | response | rowCount | integer
ReportingService | runReport | response | nextCursor | string |  | (nullable)
ReportingService | runReport | response | generatedAt | string (date-time)
ReportingService | runReport | response | dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | runReport | param (path) | reportId | string (uuid) | yes
ReportingService | runReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | saveFavouriteRoute | request | venueId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | request | fromStationId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | request | toStationId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | request | label | string |  | (max length 60; nullable)
VenueOpsService | saveFavouriteRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | saveFavouriteRoute | response | venueId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | response | fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | saveFavouriteRoute | response | toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | saveFavouriteRoute | response | fromStationName | string |  | (read-only)
VenueOpsService | saveFavouriteRoute | response | toStationName | string |  | (read-only)
VenueOpsService | saveFavouriteRoute | response | label | string |  | (nullable)
VenueOpsService | saveFavouriteRoute | response | adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | saveFavouriteRoute | response | adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | saveFavouriteRoute | response | adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | saveFavouriteRoute | response | adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | saveFavouriteRoute | response | createdAt | string (date-time) | yes
VenueOpsService | saveFavouriteRoute | response | subjectId | string (uuid) |  | The guest who saved it (4 October 2026, CHG-FXC-003; transport.favourite_route had no owner column). (read-only)
VenueOpsService | saveFavouriteRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | saveNaturalLanguageQuery | request | name | string | yes | (max length 200)
ReportingService | saveNaturalLanguageQuery | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …)
ReportingService | saveNaturalLanguageQuery | response | name | string | yes | (max length 200)
ReportingService | saveNaturalLanguageQuery | response | description | string |  | (max length 1000)
ReportingService | saveNaturalLanguageQuery | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | saveNaturalLanguageQuery | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | saveNaturalLanguageQuery | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | saveNaturalLanguageQuery | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | saveNaturalLanguageQuery | response | columns[].field | string | yes
ReportingService | saveNaturalLanguageQuery | response | columns[].label | string
ReportingService | saveNaturalLanguageQuery | response | columns[].aggregation | object |  | (default none)
ReportingService | saveNaturalLanguageQuery | response | columns[].sortOrder | integer
ReportingService | saveNaturalLanguageQuery | response | columns[].sortDirection | enum (asc, desc)
ReportingService | saveNaturalLanguageQuery | response | columns[].format | string |  | (nullable)
ReportingService | saveNaturalLanguageQuery | response | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | saveNaturalLanguageQuery | response | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | saveNaturalLanguageQuery | response | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | saveNaturalLanguageQuery | response | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | saveNaturalLanguageQuery | response | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | saveNaturalLanguageQuery | response | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | saveNaturalLanguageQuery | response | filters | array of ReportFilter
ReportingService | saveNaturalLanguageQuery | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | saveNaturalLanguageQuery | response | filters[].field | string | yes
ReportingService | saveNaturalLanguageQuery | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | saveNaturalLanguageQuery | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | saveNaturalLanguageQuery | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | saveNaturalLanguageQuery | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | saveNaturalLanguageQuery | response | groupBy | array of string
ReportingService | saveNaturalLanguageQuery | response | parameters | array of ReportParameter
ReportingService | saveNaturalLanguageQuery | response | parameters[].key | string | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].label | string | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].isRequired | boolean | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | saveNaturalLanguageQuery | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | saveNaturalLanguageQuery | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | saveNaturalLanguageQuery | response | id | string (uuid) | yes
ReportingService | saveNaturalLanguageQuery | response | version | string | yes | The current version.
ReportingService | saveNaturalLanguageQuery | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | saveNaturalLanguageQuery | response | isRetired | boolean | yes
ReportingService | saveNaturalLanguageQuery | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | saveNaturalLanguageQuery | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | saveNaturalLanguageQuery | response | createdAt | string (date-time) | yes
ReportingService | saveNaturalLanguageQuery | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | saveNaturalLanguageQuery | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | saveNaturalLanguageQuery | param (path) | conversationId | string | yes
ReportingService | saveNaturalLanguageQuery | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | scheduleMenuPublish | request | effectiveAt | string (date-time) |  | Local midnight, in the Region's time zone, of the day the menu goes live, sent as a UTC instant like every date-time (for a Dubai outlet going live on 1 March, 2026-02-28T20:00:00Z).
FnbService | scheduleMenuPublish | request | cancelScheduleId | string (uuid) |  | A pending schedule from listMenuSchedules. (nullable)
FnbService | scheduleMenuPublish | response | id | string (uuid) | yes | (read-only)
FnbService | scheduleMenuPublish | response | menuId | string (uuid) | yes
FnbService | scheduleMenuPublish | response | effectiveAt | string (date-time) | yes
FnbService | scheduleMenuPublish | response | status | enum (pending, applied, cancelled) | yes
FnbService | scheduleMenuPublish | response | publishedVersion | integer |  | The MenuVersion.version that went live when the schedule fired. (read-only; nullable)
FnbService | scheduleMenuPublish | response | createdAt | string (date-time) |  | (read-only)
FnbService | scheduleMenuPublish | response | createdByPrincipalId | string (uuid) |  | (read-only)
FnbService | scheduleMenuPublish | response | cancelledAt | string (date-time) |  | (read-only; nullable)
FnbService | scheduleMenuPublish | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | scheduleMenuPublish | param (path) | menuId | string (uuid) | yes
FnbService | scheduleMenuPublish | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | searchCatalogue | param (query) | q | string | yes | Keywords matched case-insensitively against the product's name and summary, in the requested language and in English; every word must match.
CatalogueService | searchCatalogue | param (query) | venueId | string (uuid)
CatalogueService | searchCatalogue | param (query) | kind | enum (product, event, attraction, bundle, membership, merchandise, menuItem)
CatalogueService | searchCatalogue | param (query) | guidedAnswerIds | array of string (uuid) |  | Help me choose answers, as filters (decided 29 September, W4).
CatalogueService | searchCatalogue | param (query) | pageSize | integer
CatalogueService | searchCatalogue | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
MarketingService | searchGuests | response | items | array of GuestProfile | yes
MarketingService | searchGuests | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | searchGuests | response | items[].subjectId | string (uuid) | yes | Opaque reference.
MarketingService | searchGuests | response | items[].displayName | string |  | (nullable)
MarketingService | searchGuests | response | items[].email | string |  | (nullable)
MarketingService | searchGuests | response | items[].phone | string |  | (nullable)
MarketingService | searchGuests | response | items[].preferredLanguage | string |  | (nullable)
MarketingService | searchGuests | response | items[].preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) |  | Left out where the guest has no preferred channel: a guest who chose none in updateMyProfile is stored as null and answered without this field (ADAM CR-291, option B; CHG-R11GST-002).
MarketingService | searchGuests | response | items[].guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | searchGuests | response | items[].tags | array of string
MarketingService | searchGuests | response | items[].engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | searchGuests | response | items[].engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | searchGuests | response | items[].lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | searchGuests | response | items[].lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | searchGuests | response | items[].lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | searchGuests | response | items[].lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | searchGuests | response | items[].visitCount | integer
MarketingService | searchGuests | response | items[].lastVisitAt | string (date-time) |  | (nullable)
MarketingService | searchGuests | response | items[].isActive | boolean | yes
MarketingService | searchGuests | response | items[].mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | searchGuests | response | items[].mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | searchGuests | response | nextCursor | string
MarketingService | searchGuests | response | hasMore | boolean | yes
MarketingService | searchGuests | param (query) | search | string |  | Name, email, phone or membership number.
MarketingService | searchGuests | param (query) | segmentId | string (uuid)
MarketingService | searchGuests | param (query) | hasConsentFor | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment)
MarketingService | searchGuests | param (query) | pageSize | integer
MarketingService | searchGuests | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | searchMedia | response | items | array of MediaAsset | yes
VenueOpsService | searchMedia | response | items[].id | string (uuid) | yes
VenueOpsService | searchMedia | response | items[].kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | searchMedia | response | items[].status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | searchMedia | response | items[].filename | string | yes
VenueOpsService | searchMedia | response | items[].contentType | string | yes
VenueOpsService | searchMedia | response | items[].sizeBytes | integer | yes
VenueOpsService | searchMedia | response | items[].title | LocalisedText
VenueOpsService | searchMedia | response | items[].description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | searchMedia | response | items[].altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | searchMedia | response | items[].width | integer |  | (nullable)
VenueOpsService | searchMedia | response | items[].height | integer |  | (nullable)
VenueOpsService | searchMedia | response | items[].hasTransparency | boolean |  | Whether the image has an alpha channel with any pixel not fully opaque, recorded from the file when the upload completes; null for a file that is not an image (ADAM CR-106, option 1; CHG-R10TEN-012). (read-only; nullable)
VenueOpsService | searchMedia | response | items[].durationSeconds | number |  | (nullable)
VenueOpsService | searchMedia | response | items[].customMetadata | object |  | BL-178. (nullable)
VenueOpsService | searchMedia | response | items[].sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | searchMedia | response | items[].tags | array of string
VenueOpsService | searchMedia | response | items[].categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | searchMedia | response | items[].venueId | string (uuid) |  | (nullable)
VenueOpsService | searchMedia | response | items[].url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | searchMedia | response | items[].thumbnailUrl | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | searchMedia | response | items[].rights | MediaRights |  | Licensing terms.
VenueOpsService | searchMedia | response | items[].rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | searchMedia | response | items[].rights.licensor | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.licenceReference | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.validFrom | string (date) |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.validTo | string (date) |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | searchMedia | response | items[].rights.attributionRequired | boolean |  | (default False)
VenueOpsService | searchMedia | response | items[].rights.attributionText | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | searchMedia | response | items[].rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | searchMedia | response | items[].rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | searchMedia | response | items[].rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | searchMedia | response | items[].isRightsExpired | boolean
VenueOpsService | searchMedia | response | items[].version | integer
VenueOpsService | searchMedia | response | items[].uploadedByPrincipalId | string (uuid)
VenueOpsService | searchMedia | response | items[].createdAt | string (date-time) | yes
VenueOpsService | searchMedia | response | items[].extractedText | string |  | The text pulled out of an uploaded document (R8 blocker ORDERS-MONEY-C19): written by the upload's processing job once text extraction finishes (PDF, Word and plain-text kinds), replaced when the fil… (read-only; nullable)
VenueOpsService | searchMedia | response | items[].releasedByPrincipalId | string (uuid) |  | The reviewer who released the asset from quarantined (R8 blocker ORDERS-MONEY-C24, CHG-R8MIG-022); null if it never was. (read-only; nullable)
VenueOpsService | searchMedia | response | items[].releasedAt | string (date-time) |  | When it was released from quarantined. (read-only; nullable)
VenueOpsService | searchMedia | response | nextCursor | string
VenueOpsService | searchMedia | response | hasMore | boolean | yes
VenueOpsService | searchMedia | param (query) | kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d)
VenueOpsService | searchMedia | param (query) | tag | string
VenueOpsService | searchMedia | param (query) | collectionId | string (uuid)
VenueOpsService | searchMedia | param (query) | venueId | string (uuid)
VenueOpsService | searchMedia | param (query) | search | string |  | Matches filename, title, description and tags.
VenueOpsService | searchMedia | param (query) | unusedOnly | boolean
VenueOpsService | searchMedia | param (query) | rightsExpiringWithinDays | integer
VenueOpsService | searchMedia | param (query) | pageSize | integer
VenueOpsService | searchMedia | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | searchTransportDepartures | response | items | array of DepartureOffer | yes
VenueOpsService | searchTransportDepartures | response | items[].departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | searchTransportDepartures | response | items[].performanceId | string (uuid) | yes
VenueOpsService | searchTransportDepartures | response | items[].routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | searchTransportDepartures | response | items[].routeCode | string |  | The price card's label, e.g.
VenueOpsService | searchTransportDepartures | response | items[].departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | searchTransportDepartures | response | items[].arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | searchTransportDepartures | response | items[].durationMinutes | integer | yes | (min 0)
VenueOpsService | searchTransportDepartures | response | items[].period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | searchTransportDepartures | response | items[].seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | searchTransportDepartures | response | items[].fitsParty | boolean
VenueOpsService | searchTransportDepartures | response | items[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | searchTransportDepartures | response | items[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | searchTransportDepartures | response | items[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | searchTransportDepartures | response | items[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | searchTransportDepartures | response | items[].partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | searchTransportDepartures | response | items[].partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | searchTransportDepartures | response | items[].partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | searchTransportDepartures | response | items[].partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | searchTransportDepartures | response | nextCursor | string
VenueOpsService | searchTransportDepartures | response | hasMore | boolean | yes
VenueOpsService | searchTransportDepartures | response | adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | searchTransportDepartures | response | adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | searchTransportDepartures | response | adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | searchTransportDepartures | response | adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | searchTransportDepartures | response | periodCounts | object | yes | Departures on sale in each period on this date.
VenueOpsService | searchTransportDepartures | response | periodCounts.morning | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | response | periodCounts.afternoon | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | response | periodCounts.evening | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | response | periodCounts.night | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | searchTransportDepartures | param (query) | toStationId | string (uuid) | yes
VenueOpsService | searchTransportDepartures | param (query) | date | string (date) | yes | Travel date, venue local.
VenueOpsService | searchTransportDepartures | param (query) | period | TimePeriod: enum (morning, afternoon, evening, night)
VenueOpsService | searchTransportDepartures | param (query) | passengers | array of string |  | The party as code:count pairs, one per passenger type (adult:2, child:1).
VenueOpsService | searchTransportDepartures | param (query) | pageSize | integer
VenueOpsService | searchTransportDepartures | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | searchTransportDepartures | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
FnbService | seatTableReservation | request | tableIds | array of string (uuid) | yes | (min items 1)
FnbService | seatTableReservation | request | actualPartySize | integer
FnbService | seatTableReservation | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | seatTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | seatTableReservation | response | outletId | string (uuid) | yes
FnbService | seatTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | seatTableReservation | response | guestName | string
FnbService | seatTableReservation | response | contactPoint | string
FnbService | seatTableReservation | response | partySize | integer | yes | (min 1)
FnbService | seatTableReservation | response | startsAt | string (date-time) | yes
FnbService | seatTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | seatTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | seatTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | seatTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | seatTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | seatTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | seatTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | seatTableReservation | response | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | seatTableReservation | response | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | seatTableReservation | response | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | seatTableReservation | response | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | seatTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | seatTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | seatTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | seatTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | seatTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | seatTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | seatTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | seatTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | seatTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | seatTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | seatTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | seatTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | seatTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | seatTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | seatTableReservation | param (path) | reservationId | string (uuid) | yes
FnbService | seatTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | selectRole | request | roleId | string (uuid) | yes
IdentityService | selectRole | request | grantId | string (uuid) |  | RoleSummary.grantId of the card chosen: which grant of the role, and so which venue (IDENTITY-C45, CHG-R8SPN-032).
IdentityService | selectRole | response | sessionId | string (uuid) | yes
IdentityService | selectRole | response | principalId | string (uuid) | yes
IdentityService | selectRole | response | roleId | string (uuid) | yes
IdentityService | selectRole | response | displayName | string
IdentityService | selectRole | response | scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | selectRole | response | scope[].id | string (uuid) | yes
IdentityService | selectRole | response | scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | selectRole | response | scope[].path | string | yes | Materialised ltree path.
IdentityService | selectRole | response | scope[].code | string |  | (nullable)
IdentityService | selectRole | response | scope[].name | string |  | (nullable)
IdentityService | selectRole | response | effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | selectRole | response | permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path, after deny resolution.
IdentityService | selectRole | response | permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | selectRole | response | permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | selectRole | response | saleBoardId | string (uuid) |  | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | selectRole | response | workstation | WorkstationContext
IdentityService | selectRole | response | workstation.id | string (uuid) | yes
IdentityService | selectRole | response | workstation.code | string | yes
IdentityService | selectRole | response | workstation.venueId | string (uuid) | yes
IdentityService | selectRole | response | workstation.regionId | string (uuid) | yes
IdentityService | selectRole | response | workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | selectRole | response | workstation.devices | array of object
IdentityService | selectRole | response | workstation.devices[].kind | enum (receiptPrinter, ticketPrinter, cashDrawer, barcodeScanner, rfidReader, paymentTerminal, customerDisplay) | yes
IdentityService | selectRole | response | workstation.devices[].driver | string | yes
IdentityService | selectRole | response | workstation.devices[].identifier | string
IdentityService | selectRole | response | workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | selectRole | response | workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | selectRole | response | workstation.timezone | string
IdentityService | selectRole | response | workstation.cellName | string |  | The cell this workstation's region is served from, which is the cell the commerce host answering this request is deployed in (one cell per tenant per region, ADR-0014): the host fills it from its own…
IdentityService | selectRole | response | workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | selectRole | response | workstation.pinLength | enum (4, 6, 8) |  | The tenant's PasswordPolicy.pinLength, carried to the device (14 October 2026, CHG-CRD-002, ADAM CR-078). (read-only)
IdentityService | selectRole | response | availableRoles | array of RoleSummary |  | The roles the principal may choose, one per grant (IDENTITY-C45, CHG-R8SPN-032), resolved on read as LoginResponse.availableRoles is, so EMP-002 can list them on a cold open or after a relaunch (getC… (read-only)
IdentityService | selectRole | response | availableRoles[].id | string (uuid) | yes
IdentityService | selectRole | response | availableRoles[].code | string | yes
IdentityService | selectRole | response | availableRoles[].name | string | yes
IdentityService | selectRole | response | availableRoles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | selectRole | response | availableRoles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | selectRole | response | availableRoles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | selectRole | response | availableRoles[].scope.id | string (uuid) | yes
IdentityService | selectRole | response | availableRoles[].scope.level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | selectRole | response | availableRoles[].scope.path | string | yes | Materialised ltree path.
IdentityService | selectRole | response | availableRoles[].scope.code | string |  | (nullable)
IdentityService | selectRole | response | availableRoles[].scope.name | string |  | (nullable)
IdentityService | selectRole | response | openedAt | string (date-time)
IdentityService | selectRole | response | expiresAt | string (date-time) |  | When the session ends at the latest: openedAt plus PasswordPolicy.sessionMaxHours (12 hours by default; proposed, client to correct).
IdentityService | selectRole | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | semanticSearch | request | query | string | yes | (min length 2; max length 500)
AiService | semanticSearch | request | kinds | array of enum (product, entitlement, knowledge, faq, report, media)
AiService | semanticSearch | request | limit | integer |  | (max 100; default 20)
AiService | semanticSearch | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | sendAiMessage | request | content | string | yes | (min length 1; max length 8000)
AiService | sendAiMessage | request | collectionIds | array of string (uuid) |  | Restrict retrieval to named collections.
AiService | sendAiMessage | response | id | string (uuid) | yes
AiService | sendAiMessage | response | conversationId | string (uuid) | yes
AiService | sendAiMessage | response | role | enum (user, assistant, system) | yes
AiService | sendAiMessage | response | content | string | yes
AiService | sendAiMessage | response | sources | array of AiSource |  | The sources an answer was grounded in, stored with the answer (8.3.70).
AiService | sendAiMessage | response | sources[].kind | enum (document, product, entitlement, report, record)
AiService | sendAiMessage | response | sources[].id | string
AiService | sendAiMessage | response | sources[].title | string
AiService | sendAiMessage | response | sources[].collectionId | string (uuid) |  | (nullable)
AiService | sendAiMessage | response | sources[].excerpt | string
AiService | sendAiMessage | response | sources[].relevance | number
AiService | sendAiMessage | response | confidence | number |  | 8.1.5, 8.3.67. (nullable)
AiService | sendAiMessage | response | rationale | string |  | 8.3.68, 8.3.69. (nullable)
AiService | sendAiMessage | response | proposedAction | object |  | Present where the answer suggests a change. (nullable)
AiService | sendAiMessage | response | proposedAction.id | string (uuid) | yes
AiService | sendAiMessage | response | proposedAction.interactionId | string (uuid)
AiService | sendAiMessage | response | proposedAction.translationJobId | string (uuid) |  | The proposeTranslations job that drafted this proposal; getTranslationProposals reads a job's rows by it. (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.targetKind | enum (contentBlock, productName, emailTemplate, messageTemplate) |  | For a translation draft, what kind of thing it sits on (TranslationProposals.drafts[].targetKind); null on every other proposal (R8 blocker FOUNDATION-AI-C40). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.targetRef | string |  | For a translation draft, the id of the block, product or template it sits on (the path id of the target's own write, e.g. (max length 200; read-only; nullable)
AiService | sendAiMessage | response | proposedAction.locale | string |  | For a translation draft, the language it is in (the job's targetLocale); null otherwise. (max length 20; read-only; nullable)
AiService | sendAiMessage | response | proposedAction.fieldPath | string |  | For a translation draft, where it goes inside the target, as a dotted path in the target's own body (TranslationProposals.drafts[].fieldPath); null otherwise. (max length 300; read-only; nullable)
AiService | sendAiMessage | response | proposedAction.draftText | string |  | For a translation draft, the proposed text; null otherwise. (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.confidence | number |  | For a walkway segment (proposeWalkways), the model's confidence in it (WalkwayProposal.confidence); null on every other proposal (ADAM CR-207, CHG-R10ORD-013). (min 0; max 1; read-only; nullable)
AiService | sendAiMessage | response | proposedAction.basis | enum (handMarked, seen) |  | For a walkway segment, whether it was traced from a hand mark or seen in the picture (WalkwayProposal.basis); null otherwise (ADAM CR-207). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.reasoning | string |  | For a walkway segment, why the model proposed it (WalkwayProposal.reasoning); null otherwise (ADAM CR-207). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.distanceMetres | number |  | For a walkway segment, its length along the centreline; null where the plan has no georeference and on every other proposal (ADAM CR-207). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.mapId | string (uuid) |  | For a walkway segment, the venue map it is on (the path's mapId, which the target's request body does not carry); null otherwise (ADAM CR-207). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.kind | enum (pricing, promotion, operational, financial, configuration, content, audience) | yes | content (a marketing or storefront draft from proposeMarketingContent) and audience (a lookalike segment from proposeLookalikeSegment) added 29 September (build); both are applied by a person in the…
AiService | sendAiMessage | response | proposedAction.targetContract | string | yes | Which contract would perform it.
AiService | sendAiMessage | response | proposedAction.targetOperation | string | yes
AiService | sendAiMessage | response | proposedAction.payload | object | yes | The request body a person would submit, ready to review.
AiService | sendAiMessage | response | proposedAction.summary | string
AiService | sendAiMessage | response | proposedAction.status | enum (proposed, approved, rejected, applied, expired) | yes | Expiry (decided 28 September, audit R213): a proposed action expires 7 days after proposedAt; an approved action not applied expires 24 hours after decidedAt.
AiService | sendAiMessage | response | proposedAction.expiresAt | string (date-time) |  | When the expiry timer moves this action to expired — proposedAt plus 7 days while proposed, decidedAt plus 24 hours once approved, null once rejected, applied or expired (audit R213). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.approvalLevel | integer |  | 8.3.65. (min 1; max 2)
AiService | sendAiMessage | response | proposedAction.decidedByPrincipalId | string (uuid) |  | (nullable)
AiService | sendAiMessage | response | proposedAction.decisionReason | string |  | Required on rejection. (nullable)
AiService | sendAiMessage | response | proposedAction.proposedAt | string (date-time)
AiService | sendAiMessage | response | proposedAction.decidedAt | string (date-time) |  | (nullable)
AiService | sendAiMessage | response | proposedAction.scopePath | string |  | Added 29 September (AI design 3.1): ai.proposed_action had no policy — its only references were nullable. (read-only)
AiService | sendAiMessage | response | proposedAction.planId | string (uuid) |  | The plan this action presents for a decision (AI design 2.2 D, 3.8). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.approvalRequestId | string (uuid) |  | The approvals request deciding a tier 2 or matrix-caught action (AI design 2.3). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.changeSetHash | string |  | Hash of the change set approved; execution refuses a plan whose hash differs (AIC-181). (read-only; nullable)
AiService | sendAiMessage | response | traceId | string
AiService | sendAiMessage | response | provider | AiProviderKind: enum (openai, gemini, anthropic, azureOpenai, localLlm, openaiCompatible) |  | openaiCompatible (added 29 September, AI design 3.3): a customer endpoint that speaks the OpenAI API, taken with no custom development (AIC-009).
AiService | sendAiMessage | response | model | string
AiService | sendAiMessage | response | promptTokens | integer
AiService | sendAiMessage | response | completionTokens | integer
AiService | sendAiMessage | response | latencyMs | integer
AiService | sendAiMessage | response | createdAt | string (date-time) | yes
AiService | sendAiMessage | param (path) | conversationId | string (uuid) | yes
AiService | sendAiMessage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | sendConversationMessage | request | body | string | yes | (max length 4000)
MarketingService | sendConversationMessage | request | attachments | array of object
MarketingService | sendConversationMessage | request | attachments[].assetId | string (uuid)
MarketingService | sendConversationMessage | request | attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | sendConversationMessage | response | id | string (uuid) | yes
MarketingService | sendConversationMessage | response | sender | enum (guest, agent, assistant, system) | yes | Resolved, never declared.
MarketingService | sendConversationMessage | response | senderPrincipalId | string (uuid) |  | (nullable)
MarketingService | sendConversationMessage | response | body | string | yes
MarketingService | sendConversationMessage | response | attachments | array of object
MarketingService | sendConversationMessage | response | attachments[].assetId | string (uuid)
MarketingService | sendConversationMessage | response | attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | sendConversationMessage | response | aiInteractionId | string (uuid) |  | Where the assistant sent it. (nullable)
MarketingService | sendConversationMessage | response | sentAt | string (date-time) | yes
MarketingService | sendConversationMessage | response | readAt | string (date-time) |  | (nullable)
MarketingService | sendConversationMessage | param (path) | conversationId | string (uuid) | yes
MarketingService | sendConversationMessage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | sendGuestConversationMessage | request | body | string | yes | (min length 1; max length 4000)
MarketingService | sendGuestConversationMessage | request | attachments | array of object |  | What the guest attaches, from their own uploads or their own tickets
MarketingService | sendGuestConversationMessage | request | attachments[].assetId | string (uuid)
MarketingService | sendGuestConversationMessage | request | attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | sendGuestConversationMessage | response | id | string (uuid) | yes
MarketingService | sendGuestConversationMessage | response | sender | enum (guest, agent, assistant, system) | yes
MarketingService | sendGuestConversationMessage | response | body | string | yes
MarketingService | sendGuestConversationMessage | response | attachments | array of object
MarketingService | sendGuestConversationMessage | response | attachments[].assetId | string (uuid)
MarketingService | sendGuestConversationMessage | response | attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | sendGuestConversationMessage | response | sentAt | string (date-time) | yes
MarketingService | sendGuestConversationMessage | param (path) | conversationId | string (uuid) | yes
MarketingService | sendGuestConversationMessage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setAccessPointDirection | request | direction | Direction: enum (entry, exit, reentry, crossover) | yes
AccessService | setAccessPointDirection | request | reason | string | yes | Why the gate is turned round, kept on the log. (min length 3; max length 200)
AccessService | setAccessPointDirection | request | effectiveAt | string (date-time) |  | Absent or not in the future, at once; in the future, held pending until then. (nullable)
AccessService | setAccessPointDirection | response | id | string (uuid) | yes
AccessService | setAccessPointDirection | response | code | string | yes
AccessService | setAccessPointDirection | response | name | string | yes
AccessService | setAccessPointDirection | response | venueId | string (uuid) | yes
AccessService | setAccessPointDirection | response | accessAreaId | string (uuid) |  | The zone this access point admits to (R8 blocker FOUNDATION-AI-C12, CHG-R8MIG-004): an access.access_area row whose entityType is zone (named for the table it keys, as every key is). (nullable)
AccessService | setAccessPointDirection | response | scopePath | string
AccessService | setAccessPointDirection | response | externalCredentialSources | object |  | BL-108.
AccessService | setAccessPointDirection | response | scanAnomalyRules | object |  | BL-104.
AccessService | setAccessPointDirection | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | setAccessPointDirection | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | setAccessPointDirection | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | setAccessPointDirection | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | setAccessPointDirection | response | temporaryClosure | object |  | What the access point does while its attraction is temporarily closed (decided 2 October 2026, Chinmay, batch 6 set 9, BO-147: "Deny + reopening time + a virtual-queue return window where enabled"; D… (nullable)
AccessService | setAccessPointDirection | response | temporaryClosure.isClosed | boolean |  | (default False)
AccessService | setAccessPointDirection | response | temporaryClosure.reason | string |  | Shown to staff; the guest sees "Attraction temporarily closed". (max length 200; nullable)
AccessService | setAccessPointDirection | response | temporaryClosure.reopensAt | string (date-time) |  | When it is expected to reopen; shown to the guest when known. (nullable)
AccessService | setAccessPointDirection | response | temporaryClosure.offerVirtualQueueReturn | boolean |  | Offer a virtual-queue return window at the denied scan, where the attraction has a queue. (default False)
AccessService | setAccessPointDirection | response | temporaryClosure.queueId | string (uuid) |  | The virtual queue the return window is taken in. (nullable)
AccessService | setAccessPointDirection | response | antiPassbackEnabled | boolean
AccessService | setAccessPointDirection | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | setAccessPointDirection | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | setAccessPointDirection | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | setAccessPointDirection | response | geofence.latitude | number
AccessService | setAccessPointDirection | response | geofence.longitude | number
AccessService | setAccessPointDirection | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | setAccessPointDirection | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setAccessPointDirection | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setAccessPointDirection | response | isActive | boolean | yes
AccessService | setAccessPointDirection | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | setAccessPointDirection | response | directionEffectiveAt | string (date-time) |  | When a direction change set by setAccessPointDirection takes effect; held pending until then. (read-only; nullable)
AccessService | setAccessPointDirection | response | directionChangeReason | string |  | Why the gate was last turned round (setAccessPointDirection). (max length 200; read-only; nullable)
AccessService | setAccessPointDirection | param (path) | accessPointId | string (uuid) | yes
AccessService | setAccessPointDirection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setAccessPointGeofence | request | latitude | number
AccessService | setAccessPointGeofence | request | longitude | number
AccessService | setAccessPointGeofence | request | radiusMetres | integer |  | (min 5; max 5000)
AccessService | setAccessPointGeofence | request | enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setAccessPointGeofence | request | allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setAccessPointGeofence | response | id | string (uuid) | yes
AccessService | setAccessPointGeofence | response | code | string | yes
AccessService | setAccessPointGeofence | response | name | string | yes
AccessService | setAccessPointGeofence | response | venueId | string (uuid) | yes
AccessService | setAccessPointGeofence | response | accessAreaId | string (uuid) |  | The zone this access point admits to (R8 blocker FOUNDATION-AI-C12, CHG-R8MIG-004): an access.access_area row whose entityType is zone (named for the table it keys, as every key is). (nullable)
AccessService | setAccessPointGeofence | response | scopePath | string
AccessService | setAccessPointGeofence | response | externalCredentialSources | object |  | BL-108.
AccessService | setAccessPointGeofence | response | scanAnomalyRules | object |  | BL-104.
AccessService | setAccessPointGeofence | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | setAccessPointGeofence | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | setAccessPointGeofence | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | setAccessPointGeofence | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | setAccessPointGeofence | response | temporaryClosure | object |  | What the access point does while its attraction is temporarily closed (decided 2 October 2026, Chinmay, batch 6 set 9, BO-147: "Deny + reopening time + a virtual-queue return window where enabled"; D… (nullable)
AccessService | setAccessPointGeofence | response | temporaryClosure.isClosed | boolean |  | (default False)
AccessService | setAccessPointGeofence | response | temporaryClosure.reason | string |  | Shown to staff; the guest sees "Attraction temporarily closed". (max length 200; nullable)
AccessService | setAccessPointGeofence | response | temporaryClosure.reopensAt | string (date-time) |  | When it is expected to reopen; shown to the guest when known. (nullable)
AccessService | setAccessPointGeofence | response | temporaryClosure.offerVirtualQueueReturn | boolean |  | Offer a virtual-queue return window at the denied scan, where the attraction has a queue. (default False)
AccessService | setAccessPointGeofence | response | temporaryClosure.queueId | string (uuid) |  | The virtual queue the return window is taken in. (nullable)
AccessService | setAccessPointGeofence | response | antiPassbackEnabled | boolean
AccessService | setAccessPointGeofence | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | setAccessPointGeofence | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | setAccessPointGeofence | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | setAccessPointGeofence | response | geofence.latitude | number
AccessService | setAccessPointGeofence | response | geofence.longitude | number
AccessService | setAccessPointGeofence | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | setAccessPointGeofence | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setAccessPointGeofence | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setAccessPointGeofence | response | isActive | boolean | yes
AccessService | setAccessPointGeofence | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | setAccessPointGeofence | response | directionEffectiveAt | string (date-time) |  | When a direction change set by setAccessPointDirection takes effect; held pending until then. (read-only; nullable)
AccessService | setAccessPointGeofence | response | directionChangeReason | string |  | Why the gate was last turned round (setAccessPointDirection). (max length 200; read-only; nullable)
AccessService | setAccessPointGeofence | param (path) | accessPointId | string (uuid) | yes
AccessService | setAccessPointGeofence | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setAccessPointGroup | request | id | string (uuid) | yes | (read-only)
AccessService | setAccessPointGroup | request | venueId | string (uuid) | yes
AccessService | setAccessPointGroup | request | name | string | yes | Group name, e.g.
AccessService | setAccessPointGroup | request | parentGroupId | string (uuid) |  | Enclosing group, for nested groups (nullable)
AccessService | setAccessPointGroup | request | accessPointIds | array of string (uuid) |  | Member access points (access.access_point)
AccessService | setAccessPointGroup | request | scopePath | string | yes | ltree of the owning scope node (ADR-0005) (read-only)
AccessService | setAccessPointGroup | request | createdAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | request | updatedAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | response | id | string (uuid) | yes | (read-only)
AccessService | setAccessPointGroup | response | venueId | string (uuid) | yes
AccessService | setAccessPointGroup | response | name | string | yes | Group name, e.g.
AccessService | setAccessPointGroup | response | parentGroupId | string (uuid) |  | Enclosing group, for nested groups (nullable)
AccessService | setAccessPointGroup | response | accessPointIds | array of string (uuid) |  | Member access points (access.access_point)
AccessService | setAccessPointGroup | response | scopePath | string | yes | ltree of the owning scope node (ADR-0005) (read-only)
AccessService | setAccessPointGroup | response | createdAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | response | updatedAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | param (path) | groupId | string (uuid) | yes
AccessService | setAccessPointGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setAccessibleSeating | request | seatMapId | string (uuid)
CatalogueService | setAccessibleSeating | request | spaces | array of object
CatalogueService | setAccessibleSeating | request | spaces[].seatId | string (uuid)
CatalogueService | setAccessibleSeating | request | spaces[].kind | enum (wheelchairSpace, transferSeat, ambulant, easyAccess, assistanceDog, hearingLoop, visuallyImpaired)
CatalogueService | setAccessibleSeating | request | spaces[].routeDescription | string |  | (nullable)
CatalogueService | setAccessibleSeating | request | spaces[].stepFree | boolean |  | (default True)
CatalogueService | setAccessibleSeating | request | spaces[].nearestAccessibleWc | string |  | (nullable)
CatalogueService | setAccessibleSeating | request | eligibility | enum (open, selfDeclared, verifiedOnce, verifiedEachTime) |  | Contested in both directions. (default selfDeclared)
CatalogueService | setAccessibleSeating | request | minimumProvisionPercent | number |  | (nullable)
CatalogueService | setAccessibleSeating | request | scopePath | string
CatalogueService | setAccessibleSeating | response | seatMapId | string (uuid)
CatalogueService | setAccessibleSeating | response | spaces | array of object
CatalogueService | setAccessibleSeating | response | spaces[].seatId | string (uuid)
CatalogueService | setAccessibleSeating | response | spaces[].kind | enum (wheelchairSpace, transferSeat, ambulant, easyAccess, assistanceDog, hearingLoop, visuallyImpaired)
CatalogueService | setAccessibleSeating | response | spaces[].routeDescription | string |  | (nullable)
CatalogueService | setAccessibleSeating | response | spaces[].stepFree | boolean |  | (default True)
CatalogueService | setAccessibleSeating | response | spaces[].nearestAccessibleWc | string |  | (nullable)
CatalogueService | setAccessibleSeating | response | eligibility | enum (open, selfDeclared, verifiedOnce, verifiedEachTime) |  | Contested in both directions. (default selfDeclared)
CatalogueService | setAccessibleSeating | response | minimumProvisionPercent | number |  | (nullable)
CatalogueService | setAccessibleSeating | response | scopePath | string
CatalogueService | setAccessibleSeating | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setAgentAvailability | request | state | enum (available, busy, away, offline) | yes
MarketingService | setAgentAvailability | request | maxConcurrent | integer |  | How many conversations this agent takes at once.
MarketingService | setAgentAvailability | request | queueIds | array of string (uuid)
MarketingService | setAgentAvailability | response | id | string (uuid) |  | (read-only)
MarketingService | setAgentAvailability | response | principalId | string (uuid) | yes | The caller. (read-only)
MarketingService | setAgentAvailability | response | state | enum (available, busy, away, offline) | yes
MarketingService | setAgentAvailability | response | maxConcurrent | integer |  | (nullable)
MarketingService | setAgentAvailability | response | queueIds | array of string (uuid)
MarketingService | setAgentAvailability | response | expiresAt | string (date-time) |  | When this state lapses on its own — availability expires rather than persisting through a closed laptop. (read-only; nullable)
MarketingService | setAgentAvailability | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setAgentAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiByokEnablement | request | id | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | request | tenantId | string (uuid) | yes | (read-only)
AiService | setAiByokEnablement | request | enabled | boolean | yes
AiService | setAiByokEnablement | request | coverage | enum (perTask, allTasks) |  | Whether the tenant may supply a key per task or one key for everything. (default perTask)
AiService | setAiByokEnablement | request | allowedTasks | array of string |  | Where coverage is perTask: the gateway tasks a tenant key may serve.
AiService | setAiByokEnablement | request | taskModelMap | array of object |  | The provider's equivalent model for each task, chosen by TICVAI (Chinmay, 2 October, workbook Q1; closes AI-D20; CHG-CSA-001). (read-only)
AiService | setAiByokEnablement | request | taskModelMap[].taskKey | string
AiService | setAiByokEnablement | request | taskModelMap[].tier | string
AiService | setAiByokEnablement | request | taskModelMap[].modelId | string (uuid) |  | (nullable)
AiService | setAiByokEnablement | request | taskModelMap[].compatibilityPassed | boolean |  | Whether the provider's compatibility test passed for this task (AiProviderCompatibility, CHG-FUP-008); a task that has not passed stays on the TICVAI-managed model. (nullable)
AiService | setAiByokEnablement | request | reason | string |  | (max length 1000)
AiService | setAiByokEnablement | request | platformStaffGrantId | string (uuid) |  | The open platform-staff grant the change was made under (audit R098). (read-only)
AiService | setAiByokEnablement | request | decidedByPrincipalId | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | request | decidedAt | string (date-time) |  | (read-only)
AiService | setAiByokEnablement | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiByokEnablement | response | id | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | response | tenantId | string (uuid) | yes | (read-only)
AiService | setAiByokEnablement | response | enabled | boolean | yes
AiService | setAiByokEnablement | response | coverage | enum (perTask, allTasks) |  | Whether the tenant may supply a key per task or one key for everything. (default perTask)
AiService | setAiByokEnablement | response | allowedTasks | array of string |  | Where coverage is perTask: the gateway tasks a tenant key may serve.
AiService | setAiByokEnablement | response | taskModelMap | array of object |  | The provider's equivalent model for each task, chosen by TICVAI (Chinmay, 2 October, workbook Q1; closes AI-D20; CHG-CSA-001). (read-only)
AiService | setAiByokEnablement | response | taskModelMap[].taskKey | string
AiService | setAiByokEnablement | response | taskModelMap[].tier | string
AiService | setAiByokEnablement | response | taskModelMap[].modelId | string (uuid) |  | (nullable)
AiService | setAiByokEnablement | response | taskModelMap[].compatibilityPassed | boolean |  | Whether the provider's compatibility test passed for this task (AiProviderCompatibility, CHG-FUP-008); a task that has not passed stays on the TICVAI-managed model. (nullable)
AiService | setAiByokEnablement | response | reason | string |  | (max length 1000)
AiService | setAiByokEnablement | response | platformStaffGrantId | string (uuid) |  | The open platform-staff grant the change was made under (audit R098). (read-only)
AiService | setAiByokEnablement | response | decidedByPrincipalId | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | response | decidedAt | string (date-time) |  | (read-only)
AiService | setAiByokEnablement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiByokEnablement | param (path) | tenantId | string (uuid) | yes
AiService | setAiByokEnablement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiModel | request | id | string (uuid) |  | (read-only)
AiService | setAiModel | request | layer | enum (platform, tenant) | yes
AiService | setAiModel | request | providerKind | object |  | (nullable)
AiService | setAiModel | request | vendor | string |  | Whose model this is (CHG-FUP-008): the provider company as AiProvider.vendor names it. (pattern ^[a-z0-9][a-z0-9-]{1,49}$; nullable)
AiService | setAiModel | request | producerType | enum (llm, embedding, reranker, classical, rule) | yes
AiService | setAiModel | request | modelName | string | yes | The deployment or model name as the provider knows it, or the package and version for a classical model.
AiService | setAiModel | request | capabilities | array of AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech)
AiService | setAiModel | request | contextTokens | integer |  | (nullable)
AiService | setAiModel | request | toolCalling | boolean |  | (default False)
AiService | setAiModel | request | structuredOutput | boolean |  | (default False)
AiService | setAiModel | request | languages | array of string
AiService | setAiModel | request | residency | string |  | Where inference happens. (nullable)
AiService | setAiModel | request | inputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | request | inputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | request | inputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | request | inputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | request | outputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | request | outputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | request | outputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | request | outputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | request | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | setAiModel | request | lifecycle.development | enum (draft, pilot, active, retired)
AiService | setAiModel | request | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | setAiModel | request | lifecycle.production | enum (draft, pilot, active, retired)
AiService | setAiModel | request | isDefaultForTasks | array of string |  | Tasks this model is the default for (AIC-010), e.g.
AiService | setAiModel | request | curatedRange | array of object |  | TICVAI's curated range: the tasks this model may serve (Chinmay, 2 October, workbook Q1, Q2 and Q9; the AI/ML model selection of 2 October; CHG-CSA-001).
AiService | setAiModel | request | curatedRange[].taskKey | string
AiService | setAiModel | request | curatedRange[].tier | enum (small, strong, reasoning, vision, embedding, reranking, moderation, piiDetection, …)
AiService | setAiModel | request | curatedRange[].rank | integer |  | (min 1; max 5)
AiService | setAiModel | request | curatedRange[].byokEligible | boolean |  | (default True)
AiService | setAiModel | request | residencyClasses | array of AiResidencyClass: enum (uaeOnly, globalAllowed, onPrem) |  | The tenant residency classes whose calls this model may serve (CHG-CSA-002).
AiService | setAiModel | request | taskFitness | array of object |  | Evaluated fitness per task (21 September minutes, M21-09, our proposal): a score from the task's golden set (runAiEvaluation) and the band the task needs. (read-only)
AiService | setAiModel | request | taskFitness[].taskKey | string | yes
AiService | setAiModel | request | taskFitness[].score | number | yes | (min 0; max 1)
AiService | setAiModel | request | taskFitness[].floor | number |  | (min 0; max 1)
AiService | setAiModel | request | taskFitness[].ceiling | number |  | (min 0; max 1; nullable)
AiService | setAiModel | request | taskFitness[].evaluationRunId | string (uuid) |  | (nullable)
AiService | setAiModel | request | taskFitness[].evaluatedAt | string (date-time)
AiService | setAiModel | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiModel | response | id | string (uuid) |  | (read-only)
AiService | setAiModel | response | layer | enum (platform, tenant) | yes
AiService | setAiModel | response | providerKind | object |  | (nullable)
AiService | setAiModel | response | vendor | string |  | Whose model this is (CHG-FUP-008): the provider company as AiProvider.vendor names it. (pattern ^[a-z0-9][a-z0-9-]{1,49}$; nullable)
AiService | setAiModel | response | producerType | enum (llm, embedding, reranker, classical, rule) | yes
AiService | setAiModel | response | modelName | string | yes | The deployment or model name as the provider knows it, or the package and version for a classical model.
AiService | setAiModel | response | capabilities | array of AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech)
AiService | setAiModel | response | contextTokens | integer |  | (nullable)
AiService | setAiModel | response | toolCalling | boolean |  | (default False)
AiService | setAiModel | response | structuredOutput | boolean |  | (default False)
AiService | setAiModel | response | languages | array of string
AiService | setAiModel | response | residency | string |  | Where inference happens. (nullable)
AiService | setAiModel | response | inputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | response | inputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | response | inputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | response | inputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | response | outputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | response | outputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | response | outputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | response | outputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | response | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | setAiModel | response | lifecycle.development | enum (draft, pilot, active, retired)
AiService | setAiModel | response | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | setAiModel | response | lifecycle.production | enum (draft, pilot, active, retired)
AiService | setAiModel | response | isDefaultForTasks | array of string |  | Tasks this model is the default for (AIC-010), e.g.
AiService | setAiModel | response | curatedRange | array of object |  | TICVAI's curated range: the tasks this model may serve (Chinmay, 2 October, workbook Q1, Q2 and Q9; the AI/ML model selection of 2 October; CHG-CSA-001).
AiService | setAiModel | response | curatedRange[].taskKey | string
AiService | setAiModel | response | curatedRange[].tier | enum (small, strong, reasoning, vision, embedding, reranking, moderation, piiDetection, …)
AiService | setAiModel | response | curatedRange[].rank | integer |  | (min 1; max 5)
AiService | setAiModel | response | curatedRange[].byokEligible | boolean |  | (default True)
AiService | setAiModel | response | residencyClasses | array of AiResidencyClass: enum (uaeOnly, globalAllowed, onPrem) |  | The tenant residency classes whose calls this model may serve (CHG-CSA-002).
AiService | setAiModel | response | taskFitness | array of object |  | Evaluated fitness per task (21 September minutes, M21-09, our proposal): a score from the task's golden set (runAiEvaluation) and the band the task needs. (read-only)
AiService | setAiModel | response | taskFitness[].taskKey | string | yes
AiService | setAiModel | response | taskFitness[].score | number | yes | (min 0; max 1)
AiService | setAiModel | response | taskFitness[].floor | number |  | (min 0; max 1)
AiService | setAiModel | response | taskFitness[].ceiling | number |  | (min 0; max 1; nullable)
AiService | setAiModel | response | taskFitness[].evaluationRunId | string (uuid) |  | (nullable)
AiService | setAiModel | response | taskFitness[].evaluatedAt | string (date-time)
AiService | setAiModel | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiModel | param (path) | modelId | string (uuid) | yes
AiService | setAiModel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiPolicy | request | id | string (uuid) |  | Added 20 August. (read-only)
AiService | setAiPolicy | request | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | setAiPolicy | request | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue. (read-only)
AiService | setAiPolicy | request | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | setAiPolicy | request | allowedRoleIds | array of string (uuid)
AiService | setAiPolicy | request | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | setAiPolicy | request | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | setAiPolicy | request | scrubbing | object |  | Mandatory offline PII scrubbing and moderation on every LLM call (Chinmay, 2 October: "we may need to scrub personal info no matter what"; ADR-0020 amended; CHG-CSA-003). (read-only)
AiService | setAiPolicy | request | scrubbing.mode | enum (mandatory)
AiService | setAiPolicy | request | scrubbing.scrubberVersion | string |  | The pinned Presidio release (and recogniser set) in force, e.g. (read-only)
AiService | setAiPolicy | request | scrubbing.residualPatternCheck | array of enum (emiratesId, uaePhone, cardPan, iban, email) |  | The deterministic patterns run after Presidio; a match blocks the call (fail closed, 503 scrubber-unavailable). (read-only)
AiService | setAiPolicy | request | scrubbing.recognisers | array of string |  | The recogniser set in force, e.g.
AiService | setAiPolicy | request | scrubbing.reversibleTokens | boolean |  | Always true; the placeholder map stays in the cell.
AiService | setAiPolicy | request | scrubbing.guardModel | string |  | The input and output guard in force, e.g.
AiService | setAiPolicy | request | globalEndpointExclusions | object |  | What never goes to a global endpoint (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 6). (read-only)
AiService | setAiPolicy | request | globalEndpointExclusions.fieldCategories | array of enum (allergy, accessibility, familyAndChildren, health, biometric, religion, payment) |  | Allergy, accessibility and family or children data in F&B and booking prompts, and health, biometric, religion and payment data anywhere.
AiService | setAiPolicy | request | globalEndpointExclusions.fields | array of string |  | The schema fields held under those categories, e.g.
AiService | setAiPolicy | request | globalEndpointExclusions.blockedMedia | array of enum (image, audio, file) |  | Images, audio and files are never sent to a global endpoint.
AiService | setAiPolicy | request | monthlyTokenCeiling | integer |  | (nullable)
AiService | setAiPolicy | request | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | setAiPolicy | request | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | setAiPolicy | request | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | setAiPolicy | request | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | setAiPolicy | request | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | setAiPolicy | request | autonomyOverrides[].capabilityKey | string | yes
AiService | setAiPolicy | request | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | setAiPolicy | request | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | setAiPolicy | request | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | setAiPolicy | request | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | setAiPolicy | request | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | setAiPolicy | request | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | setAiPolicy | request | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | setAiPolicy | request | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | setAiPolicy | request | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | setAiPolicy | request | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | setAiPolicy | request | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | setAiPolicy | request | cascade.smallModel | string
AiService | setAiPolicy | request | cascade.largeModel | string
AiService | setAiPolicy | request | cascade.escalateBelow | number |  | (default 0.7)
AiService | setAiPolicy | request | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | setAiPolicy | request | chunking.sizeTokens | integer |  | (default 512)
AiService | setAiPolicy | request | chunking.overlapTokens | integer |  | (default 64)
AiService | setAiPolicy | request | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | setAiPolicy | request | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | setAiPolicy | request | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | setAiPolicy | request | hnsw.m | integer |  | (default 16)
AiService | setAiPolicy | request | hnsw.efConstruct | integer |  | (default 128)
AiService | setAiPolicy | request | hnsw.efSearch | integer |  | (default 64)
AiService | setAiPolicy | request | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | setAiPolicy | request | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | setAiPolicy | request | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | setAiPolicy | request | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | setAiPolicy | request | glossaryTerms | array of object |  | The tenant's translation glossary (R8 blocker FOUNDATION-AI-C05, the lead's answer of 20 October 2026): terms proposeTranslations and proposeContent keep as they are (keep) or always translate one wa… (max items 500; nullable)
AiService | setAiPolicy | request | glossaryTerms[].term | string | yes | (max length 200)
AiService | setAiPolicy | request | glossaryTerms[].rule | enum (keep, translateAs) | yes
AiService | setAiPolicy | request | glossaryTerms[].translations | object |  | For translateAs, the translation per locale (ar, fr, ...). (nullable)
AiService | setAiPolicy | request | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | setAiPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
AiService | setAiPolicy | response | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | setAiPolicy | response | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue. (read-only)
AiService | setAiPolicy | response | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | setAiPolicy | response | allowedRoleIds | array of string (uuid)
AiService | setAiPolicy | response | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | setAiPolicy | response | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | setAiPolicy | response | scrubbing | object |  | Mandatory offline PII scrubbing and moderation on every LLM call (Chinmay, 2 October: "we may need to scrub personal info no matter what"; ADR-0020 amended; CHG-CSA-003). (read-only)
AiService | setAiPolicy | response | scrubbing.mode | enum (mandatory)
AiService | setAiPolicy | response | scrubbing.scrubberVersion | string |  | The pinned Presidio release (and recogniser set) in force, e.g. (read-only)
AiService | setAiPolicy | response | scrubbing.residualPatternCheck | array of enum (emiratesId, uaePhone, cardPan, iban, email) |  | The deterministic patterns run after Presidio; a match blocks the call (fail closed, 503 scrubber-unavailable). (read-only)
AiService | setAiPolicy | response | scrubbing.recognisers | array of string |  | The recogniser set in force, e.g.
AiService | setAiPolicy | response | scrubbing.reversibleTokens | boolean |  | Always true; the placeholder map stays in the cell.
AiService | setAiPolicy | response | scrubbing.guardModel | string |  | The input and output guard in force, e.g.
AiService | setAiPolicy | response | globalEndpointExclusions | object |  | What never goes to a global endpoint (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 6). (read-only)
AiService | setAiPolicy | response | globalEndpointExclusions.fieldCategories | array of enum (allergy, accessibility, familyAndChildren, health, biometric, religion, payment) |  | Allergy, accessibility and family or children data in F&B and booking prompts, and health, biometric, religion and payment data anywhere.
AiService | setAiPolicy | response | globalEndpointExclusions.fields | array of string |  | The schema fields held under those categories, e.g.
AiService | setAiPolicy | response | globalEndpointExclusions.blockedMedia | array of enum (image, audio, file) |  | Images, audio and files are never sent to a global endpoint.
AiService | setAiPolicy | response | monthlyTokenCeiling | integer |  | (nullable)
AiService | setAiPolicy | response | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | setAiPolicy | response | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | setAiPolicy | response | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | setAiPolicy | response | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | setAiPolicy | response | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | setAiPolicy | response | autonomyOverrides[].capabilityKey | string | yes
AiService | setAiPolicy | response | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | setAiPolicy | response | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | setAiPolicy | response | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | setAiPolicy | response | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | setAiPolicy | response | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | setAiPolicy | response | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | setAiPolicy | response | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | setAiPolicy | response | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | setAiPolicy | response | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | setAiPolicy | response | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | setAiPolicy | response | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | setAiPolicy | response | cascade.smallModel | string
AiService | setAiPolicy | response | cascade.largeModel | string
AiService | setAiPolicy | response | cascade.escalateBelow | number |  | (default 0.7)
AiService | setAiPolicy | response | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | setAiPolicy | response | chunking.sizeTokens | integer |  | (default 512)
AiService | setAiPolicy | response | chunking.overlapTokens | integer |  | (default 64)
AiService | setAiPolicy | response | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | setAiPolicy | response | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | setAiPolicy | response | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | setAiPolicy | response | hnsw.m | integer |  | (default 16)
AiService | setAiPolicy | response | hnsw.efConstruct | integer |  | (default 128)
AiService | setAiPolicy | response | hnsw.efSearch | integer |  | (default 64)
AiService | setAiPolicy | response | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | setAiPolicy | response | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | setAiPolicy | response | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | setAiPolicy | response | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | setAiPolicy | response | glossaryTerms | array of object |  | The tenant's translation glossary (R8 blocker FOUNDATION-AI-C05, the lead's answer of 20 October 2026): terms proposeTranslations and proposeContent keep as they are (keep) or always translate one wa… (max items 500; nullable)
AiService | setAiPolicy | response | glossaryTerms[].term | string | yes | (max length 200)
AiService | setAiPolicy | response | glossaryTerms[].rule | enum (keep, translateAs) | yes
AiService | setAiPolicy | response | glossaryTerms[].translations | object |  | For translateAs, the translation per locale (ar, fr, ...). (nullable)
AiService | setAiPolicy | response | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | setAiPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiVenueSettings | request | id | string (uuid) |  | (read-only)
AiService | setAiVenueSettings | request | venueId | string (uuid) | yes
AiService | setAiVenueSettings | request | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | setAiVenueSettings | request | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | setAiVenueSettings | request | capacity | integer |  | (min 1; nullable)
AiService | setAiVenueSettings | request | openingHours | array of object |  | The usual week.
AiService | setAiVenueSettings | request | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | setAiVenueSettings | request | openingHours[].opensAt | string
AiService | setAiVenueSettings | request | openingHours[].closesAt | string
AiService | setAiVenueSettings | request | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | request | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | request | peakMonths | array of integer
AiService | setAiVenueSettings | request | averageSpend | object |  | (nullable)
AiService | setAiVenueSettings | request | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiVenueSettings | request | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiVenueSettings | request | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiVenueSettings | request | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | setAiVenueSettings | request | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | setAiVenueSettings | request | startingPatternKey | string |  | The starting pattern and version in use, e.g. (read-only)
AiService | setAiVenueSettings | request | updatedAt | string (date-time) |  | (read-only)
AiService | setAiVenueSettings | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiVenueSettings | response | id | string (uuid) |  | (read-only)
AiService | setAiVenueSettings | response | venueId | string (uuid) | yes
AiService | setAiVenueSettings | response | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | setAiVenueSettings | response | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | setAiVenueSettings | response | capacity | integer |  | (min 1; nullable)
AiService | setAiVenueSettings | response | openingHours | array of object |  | The usual week.
AiService | setAiVenueSettings | response | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | setAiVenueSettings | response | openingHours[].opensAt | string
AiService | setAiVenueSettings | response | openingHours[].closesAt | string
AiService | setAiVenueSettings | response | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | response | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | response | peakMonths | array of integer
AiService | setAiVenueSettings | response | averageSpend | object |  | (nullable)
AiService | setAiVenueSettings | response | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiVenueSettings | response | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiVenueSettings | response | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiVenueSettings | response | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | setAiVenueSettings | response | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | setAiVenueSettings | response | startingPatternKey | string |  | The starting pattern and version in use, e.g. (read-only)
AiService | setAiVenueSettings | response | updatedAt | string (date-time) |  | (read-only)
AiService | setAiVenueSettings | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiVenueSettings | param (path) | venueId | string (uuid) | yes
AiService | setAiVenueSettings | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | setAlertRule | request | id | string (uuid) | yes | (read-only)
ReportingService | setAlertRule | request | name | string | yes
ReportingService | setAlertRule | request | metric | object | yes | From the closed set, so a rule cannot watch something nothing produces — the same discipline MetricSource exists for.
ReportingService | setAlertRule | request | comparator | enum (above, below, outsideRange, changesBy, equals) | yes
ReportingService | setAlertRule | request | threshold | number or Money | yes | A reading of a metric or KPI, or a threshold on one.
ReportingService | setAlertRule | request | thresholdUpper | object |  | Required when comparator is outsideRange (decided 28 September, audit R158): the range is threshold to thresholdUpper, and a rule missing either, or with the upper not above the lower, is refused by… (nullable)
ReportingService | setAlertRule | request | windowMinutes | integer |  | The window is what stops an alert firing on noise. (default 15)
ReportingService | setAlertRule | request | severity | AlertSeverity: enum (info, warning, critical) | yes | How urgent an alert rule's breach is.
ReportingService | setAlertRule | request | deliverTo | array of enum (dashboardPanel, email, whatsapp, sms, push) |  | CF-134.
ReportingService | setAlertRule | request | recipientRoleIds | array of string (uuid)
ReportingService | setAlertRule | request | cooldownMinutes | integer |  | How long before the same rule may fire again. (default 30)
ReportingService | setAlertRule | request | isActive | boolean | yes
ReportingService | setAlertRule | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
ReportingService | setAlertRule | response | id | string (uuid) | yes | (read-only)
ReportingService | setAlertRule | response | name | string | yes
ReportingService | setAlertRule | response | metric | object | yes | From the closed set, so a rule cannot watch something nothing produces — the same discipline MetricSource exists for.
ReportingService | setAlertRule | response | comparator | enum (above, below, outsideRange, changesBy, equals) | yes
ReportingService | setAlertRule | response | threshold | number or Money | yes | A reading of a metric or KPI, or a threshold on one.
ReportingService | setAlertRule | response | thresholdUpper | object |  | Required when comparator is outsideRange (decided 28 September, audit R158): the range is threshold to thresholdUpper, and a rule missing either, or with the upper not above the lower, is refused by… (nullable)
ReportingService | setAlertRule | response | windowMinutes | integer |  | The window is what stops an alert firing on noise. (default 15)
ReportingService | setAlertRule | response | severity | AlertSeverity: enum (info, warning, critical) | yes | How urgent an alert rule's breach is.
ReportingService | setAlertRule | response | deliverTo | array of enum (dashboardPanel, email, whatsapp, sms, push) |  | CF-134.
ReportingService | setAlertRule | response | recipientRoleIds | array of string (uuid)
ReportingService | setAlertRule | response | cooldownMinutes | integer |  | How long before the same rule may fire again. (default 30)
ReportingService | setAlertRule | response | isActive | boolean | yes
ReportingService | setAlertRule | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
ReportingService | setAlertRule | param (path) | alertRuleId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
ReportingService | setAlertRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setAlternativeCodes | request | codes | array of AlternativeCode | yes
CatalogueService | setAlternativeCodes | request | codes[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | setAlternativeCodes | request | codes[].code | string | yes | (max length 128)
CatalogueService | setAlternativeCodes | request | codes[].partnerId | string (uuid) | yes
CatalogueService | setAlternativeCodes | request | codes[].partnerName | string
CatalogueService | setAlternativeCodes | request | codes[].variantId | string (uuid)
CatalogueService | setAlternativeCodes | request | codes[].note | string |  | (max length 200)
CatalogueService | setAlternativeCodes | param (path) | productId | string (uuid) | yes
CatalogueService | setAlternativeCodes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setAnalyticsProvider | request | id | string (uuid) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | request | venueId | string (uuid) |  | (nullable)
WhiteLabelService | setAnalyticsProvider | request | provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | setAnalyticsProvider | request | providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | request | measurementId | string | yes | What the tag or SDK reports to. (max length 100)
WhiteLabelService | setAnalyticsProvider | request | surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | setAnalyticsProvider | request | consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | setAnalyticsProvider | request | isEnabled | boolean | yes | (default True)
WhiteLabelService | setAnalyticsProvider | request | reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | request | reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | setAnalyticsProvider | request | hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | setAnalyticsProvider | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setAnalyticsProvider | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | response | id | string (uuid) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | response | venueId | string (uuid) |  | (nullable)
WhiteLabelService | setAnalyticsProvider | response | provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | setAnalyticsProvider | response | providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | response | measurementId | string | yes | What the tag or SDK reports to. (max length 100)
WhiteLabelService | setAnalyticsProvider | response | surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | setAnalyticsProvider | response | consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | setAnalyticsProvider | response | isEnabled | boolean | yes | (default True)
WhiteLabelService | setAnalyticsProvider | response | reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | response | reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | setAnalyticsProvider | response | hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | setAnalyticsProvider | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setAnalyticsProvider | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | param (path) | analyticsProviderId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
WhiteLabelService | setAnalyticsProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setApiClientStatus | request | status | enum (active, suspended) | yes
PlatformService | setApiClientStatus | request | reason | string |  | Required with suspended. (max length 500)
PlatformService | setApiClientStatus | response | id | string (uuid) | yes | (read-only)
PlatformService | setApiClientStatus | response | developerId | string (uuid) | yes
PlatformService | setApiClientStatus | response | name | string | yes
PlatformService | setApiClientStatus | response | clientId | string |  | (read-only)
PlatformService | setApiClientStatus | response | environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | setApiClientStatus | response | scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | setApiClientStatus | response | issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | setApiClientStatus | response | certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | setApiClientStatus | response | credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | setApiClientStatus | response | expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | setApiClientStatus | response | allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | setApiClientStatus | response | ipAllowList | array of string |  | 13.1.38.
PlatformService | setApiClientStatus | response | status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | setApiClientStatus | response | lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | setApiClientStatus | response | statusReason | string |  | Why the client was suspended (setApiClientStatus). (max length 500; read-only; nullable)
PlatformService | setApiClientStatus | param (path) | clientId | string (uuid) | yes
PlatformService | setApiClientStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setApiLicensing | request | id | string (uuid) |  | Added 20 August. (read-only)
PlatformService | setApiLicensing | request | tenantId | string (uuid) | yes | The tenant licensed, sent by TICVAI staff (ADAM CR-098; CHG-R10ID-011).
PlatformService | setApiLicensing | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | The example in the requirement is the shape: a venue licensing the ticketing API and not the F&B one.
PlatformService | setApiLicensing | request | callAllowancePerMonth | integer |  | (nullable)
PlatformService | setApiLicensing | request | catalogueWriteException | object |  | M17-04: the one way a client reaches a catalogue write, set by TICVAI platform staff only (setApiLicensing refuses anyone else 403 platform-staff-only). (nullable)
PlatformService | setApiLicensing | request | catalogueWriteException.clientId | string (uuid) | yes
PlatformService | setApiLicensing | request | catalogueWriteException.operationIds | array of enum (createProduct, updateProduct, setProductAttributes, createPriceList, updatePriceList, copyPriceList, setPrices, createChannelCapacity, …) | yes | (min items 1)
PlatformService | setApiLicensing | request | catalogueWriteException.reason | string | yes | (max length 500)
PlatformService | setApiLicensing | request | catalogueWriteException.grantedByPrincipalId | string (uuid) |  | (read-only)
PlatformService | setApiLicensing | request | catalogueWriteException.grantedUntil | string (date) | yes
PlatformService | setApiLicensing | request | overageRatePerThousand | number |  | (nullable)
PlatformService | setApiLicensing | request | revenueSharePercent | number |  | (nullable)
PlatformService | setApiLicensing | request | effectiveFrom | string (date)
PlatformService | setApiLicensing | request | effectiveTo | string (date) |  | (nullable)
PlatformService | setApiLicensing | response | id | string (uuid) |  | Added 20 August. (read-only)
PlatformService | setApiLicensing | response | tenantId | string (uuid) | yes | The tenant licensed, sent by TICVAI staff (ADAM CR-098; CHG-R10ID-011).
PlatformService | setApiLicensing | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | The example in the requirement is the shape: a venue licensing the ticketing API and not the F&B one.
PlatformService | setApiLicensing | response | callAllowancePerMonth | integer |  | (nullable)
PlatformService | setApiLicensing | response | catalogueWriteException | object |  | M17-04: the one way a client reaches a catalogue write, set by TICVAI platform staff only (setApiLicensing refuses anyone else 403 platform-staff-only). (nullable)
PlatformService | setApiLicensing | response | catalogueWriteException.clientId | string (uuid) | yes
PlatformService | setApiLicensing | response | catalogueWriteException.operationIds | array of enum (createProduct, updateProduct, setProductAttributes, createPriceList, updatePriceList, copyPriceList, setPrices, createChannelCapacity, …) | yes | (min items 1)
PlatformService | setApiLicensing | response | catalogueWriteException.reason | string | yes | (max length 500)
PlatformService | setApiLicensing | response | catalogueWriteException.grantedByPrincipalId | string (uuid) |  | (read-only)
PlatformService | setApiLicensing | response | catalogueWriteException.grantedUntil | string (date) | yes
PlatformService | setApiLicensing | response | overageRatePerThousand | number |  | (nullable)
PlatformService | setApiLicensing | response | revenueSharePercent | number |  | (nullable)
PlatformService | setApiLicensing | response | effectiveFrom | string (date)
PlatformService | setApiLicensing | response | effectiveTo | string (date) |  | (nullable)
PlatformService | setApiLicensing | param (path) | licenceId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
PlatformService | setApiLicensing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setAppIcons | request | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source, from assets createUpload then completeUpload.
WhiteLabelService | setAppIcons | response | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | setAppIcons | response | derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | setAppIcons | response | derived[].platform | enum (ios, android, web)
WhiteLabelService | setAppIcons | response | derived[].size | string
WhiteLabelService | setAppIcons | response | derived[].assetRef | string (uuid)
WhiteLabelService | setAppIcons | response | changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | setAppIcons | response | liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | setAppIcons | response | requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | setAppIcons | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setApprovalExternalProvider | request | id | string (uuid) |  | (read-only)
TenancyService | setApprovalExternalProvider | request | code | string | yes | The provider's stable name, and the key setApprovalExternalProvider upserts on.
TenancyService | setApprovalExternalProvider | request | name | string | yes
TenancyService | setApprovalExternalProvider | request | endpointUrl | string | yes | https only.
TenancyService | setApprovalExternalProvider | request | outboundAuth | enum (bearerToken, basic, oauthClientCredentials, mutualTls) |  | (default oauthClientCredentials)
TenancyService | setApprovalExternalProvider | request | outboundCredential | string (password) |  | The credential TICVAI presents to the provider. (nullable)
TenancyService | setApprovalExternalProvider | request | signingSecret | string (password) |  | Signs every request TICVAI sends, as webhook deliveries are signed, so the provider can tell it came from TICVAI. (nullable)
TenancyService | setApprovalExternalProvider | request | apiClientId | string (uuid) | yes | The public-api client the provider calls back as.
TenancyService | setApprovalExternalProvider | request | requestMapping | array of object |  | Stored whole on the provider row (request_mapping, jsonb; 3 October 2026, CHG-R1S-020: the r1 gate found no column held it).
TenancyService | setApprovalExternalProvider | request | requestMapping[].from | string | yes | A field of ApprovalRequest, e.g.
TenancyService | setApprovalExternalProvider | request | requestMapping[].to | string | yes | The provider's field name.
TenancyService | setApprovalExternalProvider | request | decisionMapping | array of object | yes | The provider's outcome values and the decision each means. (min items 2)
TenancyService | setApprovalExternalProvider | request | decisionMapping[].externalValue | string | yes
TenancyService | setApprovalExternalProvider | request | decisionMapping[].decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | setApprovalExternalProvider | request | timeoutMinutes | integer |  | How long a level waits for the provider before onTimeout applies. (default 1440)
TenancyService | setApprovalExternalProvider | request | onTimeout | enum (fallBackToRoles, escalate, reject) |  | (default fallBackToRoles)
TenancyService | setApprovalExternalProvider | request | maxAttempts | integer |  | Delivery attempts, with backoff, before a dispatch is failed and the level falls back as on timeout. (default 5)
TenancyService | setApprovalExternalProvider | request | status | enum (active, paused, disabled) |  | paused sends nothing and every level that names it falls back at once; the platform sets disabled after repeated failures, as it disables a failing webhook. (default active)
TenancyService | setApprovalExternalProvider | request | lastSuccessAt | string (date-time) |  | (read-only; nullable)
TenancyService | setApprovalExternalProvider | request | scopePath | string |  | (read-only)
TenancyService | setApprovalExternalProvider | response | id | string (uuid) |  | (read-only)
TenancyService | setApprovalExternalProvider | response | code | string | yes | The provider's stable name, and the key setApprovalExternalProvider upserts on.
TenancyService | setApprovalExternalProvider | response | name | string | yes
TenancyService | setApprovalExternalProvider | response | endpointUrl | string | yes | https only.
TenancyService | setApprovalExternalProvider | response | outboundAuth | enum (bearerToken, basic, oauthClientCredentials, mutualTls) |  | (default oauthClientCredentials)
TenancyService | setApprovalExternalProvider | response | outboundCredential | string (password) |  | The credential TICVAI presents to the provider. (nullable)
TenancyService | setApprovalExternalProvider | response | signingSecret | string (password) |  | Signs every request TICVAI sends, as webhook deliveries are signed, so the provider can tell it came from TICVAI. (nullable)
TenancyService | setApprovalExternalProvider | response | apiClientId | string (uuid) | yes | The public-api client the provider calls back as.
TenancyService | setApprovalExternalProvider | response | requestMapping | array of object |  | Stored whole on the provider row (request_mapping, jsonb; 3 October 2026, CHG-R1S-020: the r1 gate found no column held it).
TenancyService | setApprovalExternalProvider | response | requestMapping[].from | string | yes | A field of ApprovalRequest, e.g.
TenancyService | setApprovalExternalProvider | response | requestMapping[].to | string | yes | The provider's field name.
TenancyService | setApprovalExternalProvider | response | decisionMapping | array of object | yes | The provider's outcome values and the decision each means. (min items 2)
TenancyService | setApprovalExternalProvider | response | decisionMapping[].externalValue | string | yes
TenancyService | setApprovalExternalProvider | response | decisionMapping[].decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | setApprovalExternalProvider | response | timeoutMinutes | integer |  | How long a level waits for the provider before onTimeout applies. (default 1440)
TenancyService | setApprovalExternalProvider | response | onTimeout | enum (fallBackToRoles, escalate, reject) |  | (default fallBackToRoles)
TenancyService | setApprovalExternalProvider | response | maxAttempts | integer |  | Delivery attempts, with backoff, before a dispatch is failed and the level falls back as on timeout. (default 5)
TenancyService | setApprovalExternalProvider | response | status | enum (active, paused, disabled) |  | paused sends nothing and every level that names it falls back at once; the platform sets disabled after repeated failures, as it disables a failing webhook. (default active)
TenancyService | setApprovalExternalProvider | response | lastSuccessAt | string (date-time) |  | (read-only; nullable)
TenancyService | setApprovalExternalProvider | response | scopePath | string |  | (read-only)
TenancyService | setApprovalExternalProvider | param (path) | externalProviderId | string (uuid) | yes | The record's id (ADAM CR-245).
TenancyService | setApprovalExternalProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setApprovalMatrix | request | id | string (uuid) |  | (read-only)
TenancyService | setApprovalMatrix | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | setApprovalMatrix | request | scopeLevel | enum (tenant, region, venue) | yes
TenancyService | setApprovalMatrix | request | scopePath | string |  | (read-only)
TenancyService | setApprovalMatrix | request | version | integer | yes | 11.1.80. (read-only)
TenancyService | setApprovalMatrix | request | rules | array of ApprovalRule | yes
TenancyService | setApprovalMatrix | request | rules[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setApprovalMatrix | request | rules[].order | integer | yes | First match wins.
TenancyService | setApprovalMatrix | request | rules[].minAmount | object |  | Amounts compare in the venue's currency (the lead, 25 October 2026, r10 round 3, ADAM CR-102; CHG-R10ID-020): a request amount in another currency (a supplier's, a tender's) is converted into the cur…
TenancyService | setApprovalMatrix | request | rules[].minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | request | rules[].minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | request | rules[].minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | request | rules[].maxAmount | object |  | The upper bound, compared as minAmount is (venue currency, the day''s FX rate; CR-102).
TenancyService | setApprovalMatrix | request | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | request | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | request | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | request | rules[].riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | setApprovalMatrix | request | rules[].condition | string |  | 11.1.13. (max length 500; nullable)
TenancyService | setApprovalMatrix | request | rules[].approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | setApprovalMatrix | request | rules[].approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | setApprovalMatrix | request | rules[].mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | setApprovalMatrix | request | rules[].levels | integer |  | 11.1.3. (default 1)
TenancyService | setApprovalMatrix | request | rules[].requiresMfa | boolean |  | (default False)
TenancyService | setApprovalMatrix | request | rules[].requiresSignature | boolean |  | (default False)
TenancyService | setApprovalMatrix | request | rules[].slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | setApprovalMatrix | request | rules[].escalateAfterMinutes | integer |  | (nullable)
TenancyService | setApprovalMatrix | request | rules[].escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | setApprovalMatrix | request | rules[].expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | setApprovalMatrix | request | rules[].subjectTypes | array of string |  | Which subjects of the kind this rule matches (decided 2 October 2026, Chinmay; CHG-CSP-028, CHG-CSP-036, CHG-CSP-031): the CreateApprovalRequest.subjectType values, for example topologyPublication or…
TenancyService | setApprovalMatrix | request | rules[].signatureMethods | array of enum (platformKey, uaePass, externalCertificate, drawnSignature) |  | The signature methods this level accepts, where requiresSignature is true (design-notes correction on ADM-344, Block B: "Configuring which stages need a signature is a policy write"; CHG-CSP-045).
TenancyService | setApprovalMatrix | request | rules[].externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | setApprovalMatrix | request | rules[].code | string |  | A stable code for the rule, unique within its matrix (4 October 2026, CHG-FXC-005; enforced by a unique index on (matrix_id, code) since ADAM CR-102, CHG-R10ID-015, compared without case). (max length 64; nullable)
TenancyService | setApprovalMatrix | request | rules[].minimumApprovals | integer |  | N in N-of-M (CHG-FXC-005). (min 1; nullable)
TenancyService | setApprovalMatrix | request | rules[].requiredApproverRoleId | string (uuid) |  | A role that must be among the approvals whatever N is (the CFO in an N-of-M group); it is also one of approverRoleIds (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | request | rules[].rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this rule does; null is rejectRequest (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | request | rules[].allowRequestChanges | boolean |  | (default False)
TenancyService | setApprovalMatrix | request | rules[].allowDelegate | boolean |  | (default True)
TenancyService | setApprovalMatrix | request | rules[].allowReassign | boolean |  | (default False)
TenancyService | setApprovalMatrix | request | rules[].minPercentage | number |  | A percentage threshold (a discount or a margin impact) at or above which the rule applies, beside minAmount (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | request | rules[].matchAttributes | object |  | The request attributes a rule matches on (CHG-FXC-005): keys module, product, department, customerType, risk, exceptionType, legalEntity, each an exact value the request's attributes must carry. (nullable)
TenancyService | setApprovalMatrix | request | rules[].compositeMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) |  | The approvalMode the composite screen sent, kept so it reads back what it saved; mode, levels and minimumApprovals are what the engine runs (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | request | isActive | boolean
TenancyService | setApprovalMatrix | response | id | string (uuid) |  | (read-only)
TenancyService | setApprovalMatrix | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | setApprovalMatrix | response | scopeLevel | enum (tenant, region, venue) | yes
TenancyService | setApprovalMatrix | response | scopePath | string |  | (read-only)
TenancyService | setApprovalMatrix | response | version | integer | yes | 11.1.80. (read-only)
TenancyService | setApprovalMatrix | response | rules | array of ApprovalRule | yes
TenancyService | setApprovalMatrix | response | rules[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setApprovalMatrix | response | rules[].order | integer | yes | First match wins.
TenancyService | setApprovalMatrix | response | rules[].minAmount | object |  | Amounts compare in the venue's currency (the lead, 25 October 2026, r10 round 3, ADAM CR-102; CHG-R10ID-020): a request amount in another currency (a supplier's, a tender's) is converted into the cur…
TenancyService | setApprovalMatrix | response | rules[].minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | response | rules[].minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | response | rules[].minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | response | rules[].maxAmount | object |  | The upper bound, compared as minAmount is (venue currency, the day''s FX rate; CR-102).
TenancyService | setApprovalMatrix | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | response | rules[].riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | setApprovalMatrix | response | rules[].condition | string |  | 11.1.13. (max length 500; nullable)
TenancyService | setApprovalMatrix | response | rules[].approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | setApprovalMatrix | response | rules[].approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | setApprovalMatrix | response | rules[].mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | setApprovalMatrix | response | rules[].levels | integer |  | 11.1.3. (default 1)
TenancyService | setApprovalMatrix | response | rules[].requiresMfa | boolean |  | (default False)
TenancyService | setApprovalMatrix | response | rules[].requiresSignature | boolean |  | (default False)
TenancyService | setApprovalMatrix | response | rules[].slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | setApprovalMatrix | response | rules[].escalateAfterMinutes | integer |  | (nullable)
TenancyService | setApprovalMatrix | response | rules[].escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | setApprovalMatrix | response | rules[].expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | setApprovalMatrix | response | rules[].subjectTypes | array of string |  | Which subjects of the kind this rule matches (decided 2 October 2026, Chinmay; CHG-CSP-028, CHG-CSP-036, CHG-CSP-031): the CreateApprovalRequest.subjectType values, for example topologyPublication or…
TenancyService | setApprovalMatrix | response | rules[].signatureMethods | array of enum (platformKey, uaePass, externalCertificate, drawnSignature) |  | The signature methods this level accepts, where requiresSignature is true (design-notes correction on ADM-344, Block B: "Configuring which stages need a signature is a policy write"; CHG-CSP-045).
TenancyService | setApprovalMatrix | response | rules[].externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | setApprovalMatrix | response | rules[].code | string |  | A stable code for the rule, unique within its matrix (4 October 2026, CHG-FXC-005; enforced by a unique index on (matrix_id, code) since ADAM CR-102, CHG-R10ID-015, compared without case). (max length 64; nullable)
TenancyService | setApprovalMatrix | response | rules[].minimumApprovals | integer |  | N in N-of-M (CHG-FXC-005). (min 1; nullable)
TenancyService | setApprovalMatrix | response | rules[].requiredApproverRoleId | string (uuid) |  | A role that must be among the approvals whatever N is (the CFO in an N-of-M group); it is also one of approverRoleIds (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | response | rules[].rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this rule does; null is rejectRequest (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | response | rules[].allowRequestChanges | boolean |  | (default False)
TenancyService | setApprovalMatrix | response | rules[].allowDelegate | boolean |  | (default True)
TenancyService | setApprovalMatrix | response | rules[].allowReassign | boolean |  | (default False)
TenancyService | setApprovalMatrix | response | rules[].minPercentage | number |  | A percentage threshold (a discount or a margin impact) at or above which the rule applies, beside minAmount (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | response | rules[].matchAttributes | object |  | The request attributes a rule matches on (CHG-FXC-005): keys module, product, department, customerType, risk, exceptionType, legalEntity, each an exact value the request's attributes must carry. (nullable)
TenancyService | setApprovalMatrix | response | rules[].compositeMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) |  | The approvalMode the composite screen sent, kept so it reads back what it saved; mode, levels and minimumApprovals are what the engine runs (CHG-FXC-005). (nullable)
TenancyService | setApprovalMatrix | response | isActive | boolean
TenancyService | setApprovalMatrix | param (path) | matrixId | string (uuid) | yes | The record's id (ADAM CR-245).
TenancyService | setApprovalMatrix | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setBiometricVerificationProfile | request | faceRequirement | enum (notUsed, optional, required) | yes | Whether face verification is not used, allowed, or required at this location (e.g.
AccessService | setBiometricVerificationProfile | request | biometricType | enum (facePass, faceTag, otherProvider) | yes | Biometric model this profile uses
AccessService | setBiometricVerificationProfile | request | profileId | string (uuid) | yes | The profile row's key (access.biometric_profile.id, a UUIDv7); absent creates one (decided 29 September, writers pass)
AccessService | setBiometricVerificationProfile | request | selectType | enum (ticketProduct, ticketType, membership, annualPass, multiDayTicket, multiAttractionTicket, vipCredential, accreditation, …) | yes | Vocabulary listed under Select.
AccessService | setBiometricVerificationProfile | request | venueId | string | yes | Venue
AccessService | setBiometricVerificationProfile | request | parkId | string |  | Park
AccessService | setBiometricVerificationProfile | request | zoneId | string |  | Zone
AccessService | setBiometricVerificationProfile | request | attractionId | string |  | Attraction
AccessService | setBiometricVerificationProfile | request | gateId | string |  | Gate
AccessService | setBiometricVerificationProfile | request | name | string
AccessService | setBiometricVerificationProfile | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setBiometricVerificationProfile | response | faceRequirement | enum (notUsed, optional, required) | yes | Whether face verification is not used, allowed, or required at this location (e.g.
AccessService | setBiometricVerificationProfile | response | biometricType | enum (facePass, faceTag, otherProvider) | yes | Biometric model this profile uses
AccessService | setBiometricVerificationProfile | response | profileId | string | yes | Biometric verification profile identifier
AccessService | setBiometricVerificationProfile | response | selectType | enum (ticketProduct, ticketType, membership, annualPass, multiDayTicket, multiAttractionTicket, vipCredential, accreditation, …) | yes | Vocabulary listed under Select.
AccessService | setBiometricVerificationProfile | response | venueId | string | yes | Venue
AccessService | setBiometricVerificationProfile | response | parkId | string |  | Park
AccessService | setBiometricVerificationProfile | response | zoneId | string |  | Zone
AccessService | setBiometricVerificationProfile | response | attractionId | string |  | Attraction
AccessService | setBiometricVerificationProfile | response | gateId | string |  | Gate
AccessService | setBiometricVerificationProfile | response | name | string
AccessService | setBiometricVerificationProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setBleBeaconGeofence | request | beaconName | string |  | Beacon Name
AccessService | setBleBeaconGeofence | request | beaconId | string | yes | Beacon ID
AccessService | setBleBeaconGeofence | request | venue | string | yes | Venue
AccessService | setBleBeaconGeofence | request | zone | string |  | Zone
AccessService | setBleBeaconGeofence | request | gate | string |  | Gate
AccessService | setBleBeaconGeofence | request | proximityThreshold | integer |  | Metres
AccessService | setBleBeaconGeofence | request | activeInactive | enum (active, inactive) |  | Active/Inactive
AccessService | setBleBeaconGeofence | request | health | enum (healthy, degraded, offline) |  | Read-only, reported by the beacon
AccessService | setBleBeaconGeofence | request | lastDetected | string (date-time) |  | Last detected
AccessService | setBleBeaconGeofence | request | park | string |  | Park
AccessService | setBleBeaconGeofence | request | attraction | string |  | Attraction
AccessService | setBleBeaconGeofence | request | geofenceRadiusMeters | integer |  | Radius of a circular activation zone
AccessService | setBleBeaconGeofence | request | geofenceBoundary | array of string |  | Polygon points as lat,lng when the zone is drawn
AccessService | setBleBeaconGeofence | response | beaconName | string |  | Beacon Name
AccessService | setBleBeaconGeofence | response | beaconId | string | yes | Beacon ID
AccessService | setBleBeaconGeofence | response | venue | string | yes | Venue
AccessService | setBleBeaconGeofence | response | zone | string |  | Zone
AccessService | setBleBeaconGeofence | response | gate | string |  | Gate
AccessService | setBleBeaconGeofence | response | proximityThreshold | integer |  | Metres
AccessService | setBleBeaconGeofence | response | activeInactive | enum (active, inactive) |  | Active/Inactive
AccessService | setBleBeaconGeofence | response | health | enum (healthy, degraded, offline) |  | Read-only, reported by the beacon
AccessService | setBleBeaconGeofence | response | lastDetected | string (date-time) |  | Last detected
AccessService | setBleBeaconGeofence | response | park | string |  | Park
AccessService | setBleBeaconGeofence | response | attraction | string |  | Attraction
AccessService | setBleBeaconGeofence | response | geofenceRadiusMeters | integer |  | Radius of a circular activation zone
AccessService | setBleBeaconGeofence | response | geofenceBoundary | array of string |  | Polygon points as lat,lng when the zone is drawn
AccessService | setBleBeaconGeofence | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setBookingFlowConfig | request | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | request | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | request | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | request | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | request | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | request | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | request | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | request | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | request | heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | request | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | request | singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | request | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | request | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | request | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | request | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | setBookingFlowConfig | request | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | setBookingFlowConfig | request | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | request | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | request | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | request | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | request | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | request | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | request | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | request | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | response | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | response | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | response | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | response | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | response | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | response | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | response | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | response | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | response | heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | response | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | response | singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | response | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | response | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | response | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | response | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | setBookingFlowConfig | response | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | setBookingFlowConfig | response | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | response | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | response | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | response | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | response | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | response | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | response | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | response | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setBookingVelocityTime | request | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setBookingVelocityTime | request | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setBookingVelocityTime | request | ruleName | string |  | Rule name
CatalogueService | setBookingVelocityTime | request | ruleKind | enum (bookingVelocity, earlyBird, lastMinute, combined, decayEscalation) |  | Rule family (pack pp.80-81)
CatalogueService | setBookingVelocityTime | request | expectedPaceSource | enum (historicalBookingCurve, configuredTarget) |  | What pace variance is measured against; defaults to configuredTarget until a historical curve exists (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | request | expectedSalesPerDay | integer |  | Expected sales per day when expectedPaceSource is configuredTarget (nullable)
CatalogueService | setBookingVelocityTime | request | conditions | array of object |  | Conditions (all must hold unless conditionLogic is any)
CatalogueService | setBookingVelocityTime | request | conditions[].metric | enum (salesPerHour, salesPerDay, salesPerWeek, currentBookingPace, paceVariancePercent, remainingInventory, daysToEvent, occupancyPercent) |  | Input evaluated (pack p.80; daysToEvent 0 = same day)
CatalogueService | setBookingVelocityTime | request | conditions[].operator | enum (lt, lte, gt, gte, eq, between) |  | Comparison
CatalogueService | setBookingVelocityTime | request | conditions[].value | number |  | Threshold value (percent for percentages, count for counts, days for time-to-event)
CatalogueService | setBookingVelocityTime | request | conditions[].valueTo | number |  | Upper value when operator is between (nullable)
CatalogueService | setBookingVelocityTime | request | conditionLogic | enum (all, any) |  | How conditions combine; defaults to all (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule | array of object |  | Time-to-event steps (early-bird, decay/escalation); empty for condition-only rules
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].daysBefore | integer |  | Days before the event/visit (T-180 ...
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | request | action | object |  | Action when the conditions hold (for condition rules) (nullable)
CatalogueService | setBookingVelocityTime | request | action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | request | action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | action.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBookingVelocityTime | request | action.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBookingVelocityTime | request | action.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBookingVelocityTime | request | action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | request | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setBookingVelocityTime | request | enabled | boolean |  | Enabled
CatalogueService | setBookingVelocityTime | response | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setBookingVelocityTime | response | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setBookingVelocityTime | response | ruleName | string |  | Rule name
CatalogueService | setBookingVelocityTime | response | ruleKind | enum (bookingVelocity, earlyBird, lastMinute, combined, decayEscalation) |  | Rule family (pack pp.80-81)
CatalogueService | setBookingVelocityTime | response | expectedPaceSource | enum (historicalBookingCurve, configuredTarget) |  | What pace variance is measured against; defaults to configuredTarget until a historical curve exists (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | response | expectedSalesPerDay | integer |  | Expected sales per day when expectedPaceSource is configuredTarget (nullable)
CatalogueService | setBookingVelocityTime | response | conditions | array of object |  | Conditions (all must hold unless conditionLogic is any)
CatalogueService | setBookingVelocityTime | response | conditions[].metric | enum (salesPerHour, salesPerDay, salesPerWeek, currentBookingPace, paceVariancePercent, remainingInventory, daysToEvent, occupancyPercent) |  | Input evaluated (pack p.80; daysToEvent 0 = same day)
CatalogueService | setBookingVelocityTime | response | conditions[].operator | enum (lt, lte, gt, gte, eq, between) |  | Comparison
CatalogueService | setBookingVelocityTime | response | conditions[].value | number |  | Threshold value (percent for percentages, count for counts, days for time-to-event)
CatalogueService | setBookingVelocityTime | response | conditions[].valueTo | number |  | Upper value when operator is between (nullable)
CatalogueService | setBookingVelocityTime | response | conditionLogic | enum (all, any) |  | How conditions combine; defaults to all (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule | array of object |  | Time-to-event steps (early-bird, decay/escalation); empty for condition-only rules
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].daysBefore | integer |  | Days before the event/visit (T-180 ...
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | response | action | object |  | Action when the conditions hold (for condition rules) (nullable)
CatalogueService | setBookingVelocityTime | response | action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | response | action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | action.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBookingVelocityTime | response | action.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBookingVelocityTime | response | action.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBookingVelocityTime | response | action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | response | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setBookingVelocityTime | response | enabled | boolean |  | Enabled
CatalogueService | setBookingVelocityTime | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setBrandIdentity | request | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | setBrandIdentity | request | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | setBrandIdentity | request | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | setBrandIdentity | request | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | setBrandIdentity | request | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | setBrandIdentity | request | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | setBrandIdentity | request | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setBrandIdentity | request | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | setBrandIdentity | request | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | setBrandIdentity | request | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | setBrandIdentity | request | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | setBrandIdentity | request | showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | setBrandIdentity | response | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | setBrandIdentity | response | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | setBrandIdentity | response | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | setBrandIdentity | response | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | setBrandIdentity | response | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | setBrandIdentity | response | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | setBrandIdentity | response | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setBrandIdentity | response | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | setBrandIdentity | response | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | setBrandIdentity | response | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | setBrandIdentity | response | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | setBrandIdentity | response | showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | setBrandIdentity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | setCapabilityTemplate | request | id | string (uuid) |  | (read-only)
IdentityService | setCapabilityTemplate | request | code | string | yes | (max length 64)
IdentityService | setCapabilityTemplate | request | name | string | yes | (max length 200)
IdentityService | setCapabilityTemplate | request | description | string |  | (nullable)
IdentityService | setCapabilityTemplate | request | capabilities | array of string | yes
IdentityService | setCapabilityTemplate | request | module | string |  | The module a per-module preset belongs to (a contract name, as listModuleCapabilities; CHG-CSP-003). (nullable)
IdentityService | setCapabilityTemplate | request | presetLevel | enum (all, viewer, midLevel) |  | Which of the three per-module presets this is (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): All, Viewer or Mid-level. (nullable)
IdentityService | setCapabilityTemplate | request | isPreset | boolean |  | Seeded by the platform, not saved by the tenant (CHG-CSP-003). (default False; read-only)
IdentityService | setCapabilityTemplate | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
IdentityService | setCapabilityTemplate | response | id | string (uuid) |  | (read-only)
IdentityService | setCapabilityTemplate | response | code | string | yes | (max length 64)
IdentityService | setCapabilityTemplate | response | name | string | yes | (max length 200)
IdentityService | setCapabilityTemplate | response | description | string |  | (nullable)
IdentityService | setCapabilityTemplate | response | capabilities | array of string | yes
IdentityService | setCapabilityTemplate | response | module | string |  | The module a per-module preset belongs to (a contract name, as listModuleCapabilities; CHG-CSP-003). (nullable)
IdentityService | setCapabilityTemplate | response | presetLevel | enum (all, viewer, midLevel) |  | Which of the three per-module presets this is (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): All, Viewer or Mid-level. (nullable)
IdentityService | setCapabilityTemplate | response | isPreset | boolean |  | Seeded by the platform, not saved by the tenant (CHG-CSP-003). (default False; read-only)
IdentityService | setCapabilityTemplate | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
IdentityService | setCapabilityTemplate | param (path) | capabilityTemplateId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
IdentityService | setCapabilityTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setChannelConnectionConfiguration | request | id | string (uuid) | yes | (read-only)
CatalogueService | setChannelConnectionConfiguration | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setChannelConnectionConfiguration | request | salesChannelId | string (uuid) | yes
CatalogueService | setChannelConnectionConfiguration | request | connectorName | string | yes | (max length 200)
CatalogueService | setChannelConnectionConfiguration | request | partner | string |  | (max length 200; nullable)
CatalogueService | setChannelConnectionConfiguration | request | environment | enum (sandbox, uat, production) | yes
CatalogueService | setChannelConnectionConfiguration | request | connectionType | enum (ticvaiNative, restApi, webhook, otaAdapter, resellerApi, partnerApi, middleware, fileSftp, …) | yes
CatalogueService | setChannelConnectionConfiguration | request | direction | enum (outbound, inbound, bidirectional) |  | (default outbound)
CatalogueService | setChannelConnectionConfiguration | request | endpoint | string |  | (max length 500; nullable)
CatalogueService | setChannelConnectionConfiguration | request | apiVersion | string |  | (max length 40; nullable)
CatalogueService | setChannelConnectionConfiguration | request | authenticationType | enum (none, oauth, apiKey, clientCredentials, certificate, signedRequest)
CatalogueService | setChannelConnectionConfiguration | request | credentialsReference | string |  | A vault reference, never the secret. (max length 200; nullable)
CatalogueService | setChannelConnectionConfiguration | request | certificateReference | string |  | (max length 200; nullable)
CatalogueService | setChannelConnectionConfiguration | request | certificateExpiresAt | string (date-time) |  | (nullable)
CatalogueService | setChannelConnectionConfiguration | request | timeoutMs | integer |  | (min 1; nullable)
CatalogueService | setChannelConnectionConfiguration | request | rateLimitPerMinute | integer |  | (min 1; nullable)
CatalogueService | setChannelConnectionConfiguration | request | ipRestrictions | array of string
CatalogueService | setChannelConnectionConfiguration | request | retryPolicy | object |  | {maxAttempts, backoffSeconds}. (nullable)
CatalogueService | setChannelConnectionConfiguration | request | adapterId | string |  | (max length 100; nullable)
CatalogueService | setChannelConnectionConfiguration | request | connectionStatus | enum (notTested, connected, degraded, offline, disabled) |  | (default notTested)
CatalogueService | setChannelConnectionConfiguration | request | lastTests | object |  | [{test, result, testedAt}], the latest result per test. (read-only)
CatalogueService | setChannelConnectionConfiguration | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setChannelConnectionConfiguration | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setChannelConnectionConfiguration | response | id | string (uuid) | yes | (read-only)
CatalogueService | setChannelConnectionConfiguration | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setChannelConnectionConfiguration | response | salesChannelId | string (uuid) | yes
CatalogueService | setChannelConnectionConfiguration | response | connectorName | string | yes | (max length 200)
CatalogueService | setChannelConnectionConfiguration | response | partner | string |  | (max length 200; nullable)
CatalogueService | setChannelConnectionConfiguration | response | environment | enum (sandbox, uat, production) | yes
CatalogueService | setChannelConnectionConfiguration | response | connectionType | enum (ticvaiNative, restApi, webhook, otaAdapter, resellerApi, partnerApi, middleware, fileSftp, …) | yes
CatalogueService | setChannelConnectionConfiguration | response | direction | enum (outbound, inbound, bidirectional) |  | (default outbound)
CatalogueService | setChannelConnectionConfiguration | response | endpoint | string |  | (max length 500; nullable)
CatalogueService | setChannelConnectionConfiguration | response | apiVersion | string |  | (max length 40; nullable)
CatalogueService | setChannelConnectionConfiguration | response | authenticationType | enum (none, oauth, apiKey, clientCredentials, certificate, signedRequest)
CatalogueService | setChannelConnectionConfiguration | response | credentialsReference | string |  | A vault reference, never the secret. (max length 200; nullable)
CatalogueService | setChannelConnectionConfiguration | response | certificateReference | string |  | (max length 200; nullable)
CatalogueService | setChannelConnectionConfiguration | response | certificateExpiresAt | string (date-time) |  | (nullable)
CatalogueService | setChannelConnectionConfiguration | response | timeoutMs | integer |  | (min 1; nullable)
CatalogueService | setChannelConnectionConfiguration | response | rateLimitPerMinute | integer |  | (min 1; nullable)
CatalogueService | setChannelConnectionConfiguration | response | ipRestrictions | array of string
CatalogueService | setChannelConnectionConfiguration | response | retryPolicy | object |  | {maxAttempts, backoffSeconds}. (nullable)
CatalogueService | setChannelConnectionConfiguration | response | adapterId | string |  | (max length 100; nullable)
CatalogueService | setChannelConnectionConfiguration | response | connectionStatus | enum (notTested, connected, degraded, offline, disabled) |  | (default notTested)
CatalogueService | setChannelConnectionConfiguration | response | lastTests | object |  | [{test, result, testedAt}], the latest result per test. (read-only)
CatalogueService | setChannelConnectionConfiguration | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setChannelConnectionConfiguration | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setChannelConnectionConfiguration | param (path) | connectionId | string (uuid) | yes | The record's id (ADAM CR-245).
CatalogueService | setChannelConnectionConfiguration | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setChannelFeePayment | request | channelId | string |  | Channel ID
CatalogueService | setChannelFeePayment | request | fees | array of object |  | Fee Associations (pack p.14-15): which approved fee profile applies for each fee type; amounts are the Pricing/Fee Engine's
CatalogueService | setChannelFeePayment | request | fees[].feeType | enum (booking, transaction, channel, service, delivery, payment) |  | Maps to catalogue.fee.fee_type: booking -> bookingFee, transaction -> transactionFee, channel -> channelFee, service -> serviceFee, delivery -> deliveryFee, payment -> paymentFee (ADAM CR-212).
CatalogueService | setChannelFeePayment | request | fees[].feeProfileId | string |  | A catalogue.fee of the mapped type that is active, else feeProfileMissing (ADAM CR-212).
CatalogueService | setChannelFeePayment | request | paymentMethods | array of enum (card, cash, digitalWallet, paymentLink, accountCredit, b2bCredit) |  | Payment Methods the channel may expose (pack p.15)
CatalogueService | setChannelFeePayment | request | otherPaymentMethodCodes | array of string |  | Other configured payment methods, by their Payment configuration code
CatalogueService | setChannelFeePayment | request | fulfillmentMethods | array of enum (digitalTicket, email, mobileApp, appleGoogleWallet, printAtHome, posPrint, kioskPrint, rfid, …) |  | Fulfillment Methods (pack p.15-16; bulkCsvExport is the pre-generated ticket batch for partners that do not integrate, MoM 31 Aug §4.3)
CatalogueService | setChannelFeePayment | request | ticketCredentialFormat | enum (platformSignedQr, staticQr, rfidCard, None) |  | The ticket credential this channel's tickets carry (MoM 2 Sep 2026 §4.7, MOM-0330; 12 October 2026, CHG-R6-031). (nullable)
CatalogueService | setChannelFeePayment | response | channelId | string |  | Channel ID
CatalogueService | setChannelFeePayment | response | fees | array of object |  | Fee Associations (pack p.14-15): which approved fee profile applies for each fee type; amounts are the Pricing/Fee Engine's
CatalogueService | setChannelFeePayment | response | fees[].feeType | enum (booking, transaction, channel, service, delivery, payment) |  | Maps to catalogue.fee.fee_type: booking -> bookingFee, transaction -> transactionFee, channel -> channelFee, service -> serviceFee, delivery -> deliveryFee, payment -> paymentFee (ADAM CR-212).
CatalogueService | setChannelFeePayment | response | fees[].feeProfileId | string |  | A catalogue.fee of the mapped type that is active, else feeProfileMissing (ADAM CR-212).
CatalogueService | setChannelFeePayment | response | paymentMethods | array of enum (card, cash, digitalWallet, paymentLink, accountCredit, b2bCredit) |  | Payment Methods the channel may expose (pack p.15)
CatalogueService | setChannelFeePayment | response | otherPaymentMethodCodes | array of string |  | Other configured payment methods, by their Payment configuration code
CatalogueService | setChannelFeePayment | response | fulfillmentMethods | array of enum (digitalTicket, email, mobileApp, appleGoogleWallet, printAtHome, posPrint, kioskPrint, rfid, …) |  | Fulfillment Methods (pack p.15-16; bulkCsvExport is the pre-generated ticket batch for partners that do not integrate, MoM 31 Aug §4.3)
CatalogueService | setChannelFeePayment | response | validationIssues | array of object |  | Validation (pack p.16): incompatible combinations, e.g.
CatalogueService | setChannelFeePayment | response | validationIssues[].code | enum (paymentMethodNotApproved, feeProfileMissing, mediaProfileMissing, incompatibleCombination)
CatalogueService | setChannelFeePayment | response | validationIssues[].message | string
CatalogueService | setChannelFeePayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setChannelPricingCommercial | request | priceProfile | string |  | Price Profile: the ID of the approved price list or profile consumed (the Pricing Engine calculates the price)
CatalogueService | setChannelPricingCommercial | request | currency | string |  | Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | setChannelPricingCommercial | request | effectiveFrom | string (date) |  | Effective From
CatalogueService | setChannelPricingCommercial | request | effectiveTo | string (date) |  | Effective To; empty for open-ended (nullable)
CatalogueService | setChannelPricingCommercial | request | venue | string |  | Venue ID (nullable)
CatalogueService | setChannelPricingCommercial | request | event | string |  | Event ID (nullable)
CatalogueService | setChannelPricingCommercial | request | product | string |  | Product ID (nullable)
CatalogueService | setChannelPricingCommercial | request | customerSegment | string |  | Customer Segment ID (nullable)
CatalogueService | setChannelPricingCommercial | request | priority | integer |  | Priority: when several assignments match, the lower number wins (min 1)
CatalogueService | setChannelPricingCommercial | request | channelId | string |  | Channel ID
CatalogueService | setChannelPricingCommercial | request | pricingSource | enum (standardPriceList, channelPriceList, b2bRate, resellerRate, otaRate, posPrice, promotionalPriceProfile, dynamicPricingProfile) |  | Pricing Association (pack p.8): which kind of approved pricing this assignment consumes
CatalogueService | setChannelPricingCommercial | request | overridePermission | string |  | Override Permission: the permission a user needs to override price on this channel (nullable)
CatalogueService | setChannelPricingCommercial | request | fixedPriceOnly | boolean |  | Price Override Governance: use fixed price only
CatalogueService | setChannelPricingCommercial | request | promotionAllowed | boolean |  | Price Override Governance: apply promotion
CatalogueService | setChannelPricingCommercial | request | discountAllowed | boolean |  | Price Override Governance: apply discount
CatalogueService | setChannelPricingCommercial | request | priceOverrideAllowed | boolean |  | Price Override Governance: override price
CatalogueService | setChannelPricingCommercial | request | overrideRequiresApproval | boolean |  | Price Override Governance: require approval for override
CatalogueService | setChannelPricingCommercial | request | dynamicPricingAllowed | boolean |  | Price Override Governance: use dynamic pricing
CatalogueService | setChannelPricingCommercial | response | priceProfile | string |  | Price Profile: the ID of the approved price list or profile consumed (the Pricing Engine calculates the price)
CatalogueService | setChannelPricingCommercial | response | currency | string |  | Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | setChannelPricingCommercial | response | effectiveFrom | string (date) |  | Effective From
CatalogueService | setChannelPricingCommercial | response | effectiveTo | string (date) |  | Effective To; empty for open-ended (nullable)
CatalogueService | setChannelPricingCommercial | response | venue | string |  | Venue ID (nullable)
CatalogueService | setChannelPricingCommercial | response | event | string |  | Event ID (nullable)
CatalogueService | setChannelPricingCommercial | response | product | string |  | Product ID (nullable)
CatalogueService | setChannelPricingCommercial | response | customerSegment | string |  | Customer Segment ID (nullable)
CatalogueService | setChannelPricingCommercial | response | priority | integer |  | Priority: when several assignments match, the lower number wins (min 1)
CatalogueService | setChannelPricingCommercial | response | channelId | string |  | Channel ID
CatalogueService | setChannelPricingCommercial | response | pricingSource | enum (standardPriceList, channelPriceList, b2bRate, resellerRate, otaRate, posPrice, promotionalPriceProfile, dynamicPricingProfile) |  | Pricing Association (pack p.8): which kind of approved pricing this assignment consumes
CatalogueService | setChannelPricingCommercial | response | overridePermission | string |  | Override Permission: the permission a user needs to override price on this channel (nullable)
CatalogueService | setChannelPricingCommercial | response | fixedPriceOnly | boolean |  | Price Override Governance: use fixed price only
CatalogueService | setChannelPricingCommercial | response | promotionAllowed | boolean |  | Price Override Governance: apply promotion
CatalogueService | setChannelPricingCommercial | response | discountAllowed | boolean |  | Price Override Governance: apply discount
CatalogueService | setChannelPricingCommercial | response | priceOverrideAllowed | boolean |  | Price Override Governance: override price
CatalogueService | setChannelPricingCommercial | response | overrideRequiresApproval | boolean |  | Price Override Governance: require approval for override
CatalogueService | setChannelPricingCommercial | response | dynamicPricingAllowed | boolean |  | Price Override Governance: use dynamic pricing
CatalogueService | setChannelPricingCommercial | response | validationIssues | array of object |  | Price Validation (pack p.9)
CatalogueService | setChannelPricingCommercial | response | validationIssues[].code | enum (missingPrice, expiredPrice, currencyMismatch, conflictingProfiles, invalidOverride)
CatalogueService | setChannelPricingCommercial | response | validationIssues[].message | string
CatalogueService | setChannelPricingCommercial | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setChannelSalesRule | request | id | string (uuid) | yes | (read-only)
CatalogueService | setChannelSalesRule | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setChannelSalesRule | request | salesChannelId | string (uuid) | yes
CatalogueService | setChannelSalesRule | request | productId | string (uuid) |  | (nullable)
CatalogueService | setChannelSalesRule | request | ruleKind | enum (salesWindow, salesLimit, eligibility) | yes
CatalogueService | setChannelSalesRule | request | name | string |  | (max length 200; nullable)
CatalogueService | setChannelSalesRule | request | ruleLevel | enum (platform, product, channel, contractPartner) |  | (default channel)
CatalogueService | setChannelSalesRule | request | overridesProductRule | boolean |  | (default False)
CatalogueService | setChannelSalesRule | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setChannelSalesRule | request | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setChannelSalesRule | request | isActive | boolean | yes | (default True)
CatalogueService | setChannelSalesRule | request | salesStartDate | string (date) |  | (nullable)
CatalogueService | setChannelSalesRule | request | salesStartTime | string (time) |  | (nullable)
CatalogueService | setChannelSalesRule | request | salesEndDate | string (date) |  | (nullable)
CatalogueService | setChannelSalesRule | request | salesEndTime | string (time) |  | (nullable)
CatalogueService | setChannelSalesRule | request | timeZone | string |  | (max length 64; nullable)
CatalogueService | setChannelSalesRule | request | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun)
CatalogueService | setChannelSalesRule | request | hoursOfOperation | object |  | [{opensAt, closesAt}]. (nullable)
CatalogueService | setChannelSalesRule | request | blackoutDates | array of string |  | ISO dates.
CatalogueService | setChannelSalesRule | request | eventRelativeWindow | object |  | {anchor, opensMinutesBefore, closesMinutesBefore}. (nullable)
CatalogueService | setChannelSalesRule | request | minimumLeadDays | integer |  | (min 0; nullable)
CatalogueService | setChannelSalesRule | request | minimumQuantity | integer |  | (min 0; nullable)
CatalogueService | setChannelSalesRule | request | maximumQuantity | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | request | maximumPerTransaction | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | request | maximumPerCustomer | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | request | maximumPerDay | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | request | maximumPerEvent | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | request | maximumPerProduct | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | request | isReservationPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isHoldPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isPaymentLinkPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isPartialPaymentPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isSplitPaymentPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isDiscountPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isPromoCodePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isExchangePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isReschedulePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isUpgradePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | restrictions | array of enum (noRefunds, noCashPayment, noComplimentary, noManualDiscount, noSameDaySales, noSeatChanges)
CatalogueService | setChannelSalesRule | request | eligibilityDimension | enum (customerType, membership, loyaltyTier, country, residency, age, corporateAccount, partner, …) |  | (nullable)
CatalogueService | setChannelSalesRule | request | eligibilityOperator | enum (equals, notEquals, in, notIn, greaterThanOrEqual, lessThanOrEqual, between, None) |  | (nullable)
CatalogueService | setChannelSalesRule | request | eligibilityValues | array of string
CatalogueService | setChannelSalesRule | request | eligibilityEffect | enum (allow, deny, None) |  | (nullable)
CatalogueService | setChannelSalesRule | request | isGuestAllowed | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isLoginRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isMembershipRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isCorporateAccountRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | isIdentityVerificationRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setChannelSalesRule | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setChannelSalesRule | response | id | string (uuid) | yes | (read-only)
CatalogueService | setChannelSalesRule | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setChannelSalesRule | response | salesChannelId | string (uuid) | yes
CatalogueService | setChannelSalesRule | response | productId | string (uuid) |  | (nullable)
CatalogueService | setChannelSalesRule | response | ruleKind | enum (salesWindow, salesLimit, eligibility) | yes
CatalogueService | setChannelSalesRule | response | name | string |  | (max length 200; nullable)
CatalogueService | setChannelSalesRule | response | ruleLevel | enum (platform, product, channel, contractPartner) |  | (default channel)
CatalogueService | setChannelSalesRule | response | overridesProductRule | boolean |  | (default False)
CatalogueService | setChannelSalesRule | response | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setChannelSalesRule | response | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setChannelSalesRule | response | isActive | boolean | yes | (default True)
CatalogueService | setChannelSalesRule | response | salesStartDate | string (date) |  | (nullable)
CatalogueService | setChannelSalesRule | response | salesStartTime | string (time) |  | (nullable)
CatalogueService | setChannelSalesRule | response | salesEndDate | string (date) |  | (nullable)
CatalogueService | setChannelSalesRule | response | salesEndTime | string (time) |  | (nullable)
CatalogueService | setChannelSalesRule | response | timeZone | string |  | (max length 64; nullable)
CatalogueService | setChannelSalesRule | response | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun)
CatalogueService | setChannelSalesRule | response | hoursOfOperation | object |  | [{opensAt, closesAt}]. (nullable)
CatalogueService | setChannelSalesRule | response | blackoutDates | array of string |  | ISO dates.
CatalogueService | setChannelSalesRule | response | eventRelativeWindow | object |  | {anchor, opensMinutesBefore, closesMinutesBefore}. (nullable)
CatalogueService | setChannelSalesRule | response | minimumLeadDays | integer |  | (min 0; nullable)
CatalogueService | setChannelSalesRule | response | minimumQuantity | integer |  | (min 0; nullable)
CatalogueService | setChannelSalesRule | response | maximumQuantity | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | response | maximumPerTransaction | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | response | maximumPerCustomer | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | response | maximumPerDay | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | response | maximumPerEvent | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | response | maximumPerProduct | integer |  | (min 1; nullable)
CatalogueService | setChannelSalesRule | response | isReservationPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isHoldPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isPaymentLinkPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isPartialPaymentPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isSplitPaymentPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isDiscountPermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isPromoCodePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isExchangePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isReschedulePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isUpgradePermitted | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | restrictions | array of enum (noRefunds, noCashPayment, noComplimentary, noManualDiscount, noSameDaySales, noSeatChanges)
CatalogueService | setChannelSalesRule | response | eligibilityDimension | enum (customerType, membership, loyaltyTier, country, residency, age, corporateAccount, partner, …) |  | (nullable)
CatalogueService | setChannelSalesRule | response | eligibilityOperator | enum (equals, notEquals, in, notIn, greaterThanOrEqual, lessThanOrEqual, between, None) |  | (nullable)
CatalogueService | setChannelSalesRule | response | eligibilityValues | array of string
CatalogueService | setChannelSalesRule | response | eligibilityEffect | enum (allow, deny, None) |  | (nullable)
CatalogueService | setChannelSalesRule | response | isGuestAllowed | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isLoginRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isMembershipRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isCorporateAccountRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | isIdentityVerificationRequired | boolean |  | (nullable)
CatalogueService | setChannelSalesRule | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setChannelSalesRule | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setChannelSalesRule | param (path) | ruleId | string (uuid) | yes | Chosen by the caller on create, so a retried create cannot make two rules.
CatalogueService | setChannelSalesRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setCodeDistributionManager | request | channelsType | enum (email, sms, whatsapp, mobileApp, crmJourney, guestPortal, b2bPortal, partnerPortal, …) |  | Vocabulary listed under Distribution Channels.
CatalogueService | setCodeDistributionManager | request | assigneeType | enum (individualCustomer, customerSegment, membershipAccount, b2bCompany, reseller, travelAgency, school, hotel, …) |  | Who the codes are assigned to.
CatalogueService | setCodeDistributionManager | request | batchId | string |  | Batch ID
CatalogueService | setCodeDistributionManager | request | assigneeReference | string |  | Customer, segment, account or partner the codes go to
CatalogueService | setCodeDistributionManager | request | quantity | integer |  | Codes to assign
CatalogueService | setCodeDistributionManager | response | channelsType | enum (email, sms, whatsapp, mobileApp, crmJourney, guestPortal, b2bPortal, partnerPortal, …) |  | Vocabulary listed under Distribution Channels.
CatalogueService | setCodeDistributionManager | response | generated | string |  | Generated
CatalogueService | setCodeDistributionManager | response | assigned | string |  | Assigned
CatalogueService | setCodeDistributionManager | response | sent | string |  | Sent
CatalogueService | setCodeDistributionManager | response | delivered | string |  | Delivered
CatalogueService | setCodeDistributionManager | response | redeemed | string |  | Redeemed
CatalogueService | setCodeDistributionManager | response | expired | integer |  | Expired
CatalogueService | setCodeDistributionManager | response | cancelled | integer |  | Cancelled
CatalogueService | setCodeDistributionManager | response | viewed | string |  | Viewed where available
CatalogueService | setCodeDistributionManager | response | assigneeType | enum (individualCustomer, customerSegment, membershipAccount, b2bCompany, reseller, travelAgency, school, hotel, …) |  | Who the codes are assigned to.
CatalogueService | setCodeDistributionManager | response | batchId | string |  | Batch ID
CatalogueService | setCodeDistributionManager | response | partner | string |  | Partner, for a partner batch
CatalogueService | setCodeDistributionManager | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setConfigurationProfile | request | id | string (uuid) |  | Optional.
TenancyService | setConfigurationProfile | request | name | string | yes
TenancyService | setConfigurationProfile | request | scopePath | string
TenancyService | setConfigurationProfile | request | venueKindScope | array of string | yes | Which workstation types the profile applies to, as ConfigurationProfile.venueKindScope.
TenancyService | setConfigurationProfile | request | settings | object
TenancyService | setConfigurationProfile | request | status | enum (draft, published, deploying, deployed, superseded, rolledBack) | yes | The caller's choice on input: draft or published; sending published publishes this version.
TenancyService | setConfigurationProfile | request | version | integer |  | (read-only)
TenancyService | setConfigurationProfile | request | deployedCount | integer |  | (read-only)
TenancyService | setConfigurationProfile | request | publishedAt | string (date-time) |  | (read-only; nullable)
TenancyService | setConfigurationProfile | response | id | string (uuid) | yes | (read-only)
TenancyService | setConfigurationProfile | response | name | string | yes
TenancyService | setConfigurationProfile | response | scopePath | string
TenancyService | setConfigurationProfile | response | venueKindScope | array of string | yes | Which workstation types it applies to.
TenancyService | setConfigurationProfile | response | version | integer | yes | Immutable once deployed anywhere. (read-only)
TenancyService | setConfigurationProfile | response | settings | object
TenancyService | setConfigurationProfile | response | status | enum (draft, published, deploying, deployed, superseded, rolledBack) | yes | On input only draft or published; sending published publishes this version.
TenancyService | setConfigurationProfile | response | deployedCount | integer |  | (read-only)
TenancyService | setConfigurationProfile | response | publishedAt | string (date-time) |  | (read-only; nullable)
TenancyService | setConfigurationProfile | param (path) | profileId | string (uuid) | yes
TenancyService | setConfigurationProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setConsentPurposes | request | purposes | array of ConsentPurposeConfig | yes
MarketingService | setConsentPurposes | request | purposes[].id | string (uuid) |  | The purpose row's id (marketing.consent_purpose.id), the value consentPurposeId and a consent's purposeId carry (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-022). (read-only)
MarketingService | setConsentPurposes | request | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment) | yes | storedPaymentCredential (a card saved for later, storePaymentToken) and facePassEnrolment (a face enrolled for entry, enrolFacePass) are purposes of their own (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-…
MarketingService | setConsentPurposes | request | purposes[].displayName | string
MarketingService | setConsentPurposes | request | purposes[].description | string
MarketingService | setConsentPurposes | request | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | setConsentPurposes | request | purposes[].noticeVersion | string | yes | Current version of the notice.
MarketingService | setConsentPurposes | request | purposes[].isRequiredForService | boolean | yes | True for transactional.
MarketingService | setConsentPurposes | request | purposes[].expiresAfterMonths | integer |  | (nullable)
MarketingService | setConsentPurposes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setCookieBannerDesign | request | id | string (uuid) |  | (read-only)
MarketingService | setCookieBannerDesign | request | brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | setCookieBannerDesign | request | inheritsFromId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | request | channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | setCookieBannerDesign | request | logoAssetId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | request | title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | position | enum (top, bottom, popup, modal) | yes
MarketingService | setCookieBannerDesign | request | themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | setCookieBannerDesign | request | buttons | array of object
MarketingService | setCookieBannerDesign | request | buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | setCookieBannerDesign | request | buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | setCookieBannerDesign | request | links | array of object
MarketingService | setCookieBannerDesign | request | links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | setCookieBannerDesign | request | categories | array of object | yes | (min items 1)
MarketingService | setCookieBannerDesign | request | categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | setCookieBannerDesign | request | categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | setCookieBannerDesign | request | languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | setCookieBannerDesign | request | regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | setCookieBannerDesign | request | recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | setCookieBannerDesign | request | noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | setCookieBannerDesign | request | version | integer |  | (min 1; read-only)
MarketingService | setCookieBannerDesign | request | status | enum (draft, published, superseded) |  | (read-only)
MarketingService | setCookieBannerDesign | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setCookieBannerDesign | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setCookieBannerDesign | response | id | string (uuid) |  | (read-only)
MarketingService | setCookieBannerDesign | response | brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | setCookieBannerDesign | response | inheritsFromId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | response | channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | setCookieBannerDesign | response | logoAssetId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | response | title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | position | enum (top, bottom, popup, modal) | yes
MarketingService | setCookieBannerDesign | response | themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | setCookieBannerDesign | response | buttons | array of object
MarketingService | setCookieBannerDesign | response | buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | setCookieBannerDesign | response | buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | setCookieBannerDesign | response | links | array of object
MarketingService | setCookieBannerDesign | response | links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | setCookieBannerDesign | response | categories | array of object | yes | (min items 1)
MarketingService | setCookieBannerDesign | response | categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | setCookieBannerDesign | response | categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | setCookieBannerDesign | response | languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | setCookieBannerDesign | response | regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | setCookieBannerDesign | response | recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | setCookieBannerDesign | response | noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | setCookieBannerDesign | response | version | integer |  | (min 1; read-only)
MarketingService | setCookieBannerDesign | response | status | enum (draft, published, superseded) |  | (read-only)
MarketingService | setCookieBannerDesign | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setCookieBannerDesign | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setCookieBannerDesign | param (path) | bannerDesignId | string (uuid) | yes | The new version's id (ADAM CR-245).
MarketingService | setCookieBannerDesign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setCourseRules | request | outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setCourseRules | request | defaultCoursing | CoursingPolicy: enum (fireAndForget, holdAndFire, phased, timed, delayed) |  | How a ticket's courses are fired.
FnbService | setCourseRules | request | courseNames | array of string
FnbService | setCourseRules | request | autoFireMinutes | integer |  | (nullable)
FnbService | setCourseRules | request | serviceModeOverrides | object |  | A different default per service mode.
FnbService | setCourseRules | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setCourseRules | response | outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setCourseRules | response | defaultCoursing | CoursingPolicy: enum (fireAndForget, holdAndFire, phased, timed, delayed) |  | How a ticket's courses are fired.
FnbService | setCourseRules | response | courseNames | array of string
FnbService | setCourseRules | response | autoFireMinutes | integer |  | (nullable)
FnbService | setCourseRules | response | serviceModeOverrides | object |  | A different default per service mode.
FnbService | setCourseRules | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setCourseRules | param (path) | outletId | string (uuid) | yes
FnbService | setCourseRules | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setCourseRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setCredentialActivationDisplay | request | ruleId | string (uuid) |  | Absent creates a rule
AccessService | setCredentialActivationDisplay | request | venueId | string | yes | Venue the rule applies to
AccessService | setCredentialActivationDisplay | request | name | string | yes | (max length 200)
AccessService | setCredentialActivationDisplay | request | beforeActivationDisplay | array of enum (hideQr, blurQr, showCountdown, showAvailableAtVenue, showVenueDirections) | yes | What the guest sees before the credential activates
AccessService | setCredentialActivationDisplay | request | activeDisplay | array of enum (dynamicQr, activationTimer, credentialStatus, remainingEntitlements) | yes | What the guest sees once it is active
AccessService | setCredentialActivationDisplay | request | activationTriggers | array of string | yes | What activates the credential, e.g. (min items 1)
AccessService | setCredentialActivationDisplay | response | ruleId | string | yes
AccessService | setCredentialActivationDisplay | response | beforeActivationDisplay | array of enum (hideQr, blurQr, showCountdown, showAvailableAtVenue, showVenueDirections)
AccessService | setCredentialActivationDisplay | response | activeDisplay | array of enum (dynamicQr, activationTimer, credentialStatus, remainingEntitlements)
AccessService | setCredentialActivationDisplay | response | name | string
AccessService | setCredentialActivationDisplay | response | activationTriggers | array of string |  | Conditions that make the credential eligible, e.g.
AccessService | setCredentialActivationDisplay | param (path) | credentialPolicyId | string (uuid) | yes | Addresses the activation and display rule this write creates or replaces.
AccessService | setCredentialActivationDisplay | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setDeliveryLocationOutletMapping | request | mappings | array of object | yes | (min items 1)
FnbService | setDeliveryLocationOutletMapping | request | mappings[].locationId | string (uuid) | yes
FnbService | setDeliveryLocationOutletMapping | request | mappings[].servingOutletIds | array of string (uuid) | yes
FnbService | setDeliveryLocationOutletMapping | param (path) | venueId | string (uuid) | yes
FnbService | setDeliveryLocationOutletMapping | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setDeliveryLocationOutletMapping | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDemandOccupancyAvailability | request | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setDemandOccupancyAvailability | request | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setDemandOccupancyAvailability | request | ruleName | string |  | Rule name
CatalogueService | setDemandOccupancyAvailability | request | ruleKind | enum (occupancy, inventory, availability, demand) |  | Rule family (pack p.78-79)
CatalogueService | setDemandOccupancyAvailability | request | inputMetric | enum (ticketsSold, currentDemand, occupancyPercent, remainingCapacity, remainingInventory, availableSeats, capacityUtilization, salesPace) |  | Supported Input evaluated (pack p.78)
CatalogueService | setDemandOccupancyAvailability | request | tiers | array of object |  | Threshold matrix; tiers must not overlap
CatalogueService | setDemandOccupancyAvailability | request | tiers[].fromValue | number |  | From (inclusive)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].toValue | number |  | To (inclusive); empty for no upper bound (nullable)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setDemandOccupancyAvailability | request | demandIndexDefinition | string |  | Required when inputMetric is currentDemand: how the demand index is calculated (the pack requires it to be explicitly configured and documented) (nullable)
CatalogueService | setDemandOccupancyAvailability | request | exitThresholdOffset | number |  | Exit threshold: how far the metric must fall back below a tier's entry before the price reverses; defaults to 2 (points or units of the metric) (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | request | minimumDurationMinutes | integer |  | Minimum duration a threshold must hold before the price moves; defaults to 15 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | request | cooldownMinutes | integer |  | Cooldown after a movement before the next; defaults to 60 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | request | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setDemandOccupancyAvailability | request | enabled | boolean |  | Enabled
CatalogueService | setDemandOccupancyAvailability | response | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setDemandOccupancyAvailability | response | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setDemandOccupancyAvailability | response | ruleName | string |  | Rule name
CatalogueService | setDemandOccupancyAvailability | response | ruleKind | enum (occupancy, inventory, availability, demand) |  | Rule family (pack p.78-79)
CatalogueService | setDemandOccupancyAvailability | response | inputMetric | enum (ticketsSold, currentDemand, occupancyPercent, remainingCapacity, remainingInventory, availableSeats, capacityUtilization, salesPace) |  | Supported Input evaluated (pack p.78)
CatalogueService | setDemandOccupancyAvailability | response | tiers | array of object |  | Threshold matrix; tiers must not overlap
CatalogueService | setDemandOccupancyAvailability | response | tiers[].fromValue | number |  | From (inclusive)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].toValue | number |  | To (inclusive); empty for no upper bound (nullable)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setDemandOccupancyAvailability | response | demandIndexDefinition | string |  | Required when inputMetric is currentDemand: how the demand index is calculated (the pack requires it to be explicitly configured and documented) (nullable)
CatalogueService | setDemandOccupancyAvailability | response | exitThresholdOffset | number |  | Exit threshold: how far the metric must fall back below a tier's entry before the price reverses; defaults to 2 (points or units of the metric) (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | response | minimumDurationMinutes | integer |  | Minimum duration a threshold must hold before the price moves; defaults to 15 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | response | cooldownMinutes | integer |  | Cooldown after a movement before the next; defaults to 60 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | response | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setDemandOccupancyAvailability | response | enabled | boolean |  | Enabled
CatalogueService | setDemandOccupancyAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setDenominations | request | scopePath | string | yes | The region the write is made at — the materialised path of a region scope node.
OrderService | setDenominations | request | currencyCode | string | yes | (min length 3; max length 3)
OrderService | setDenominations | request | denominations | array of object | yes | (min items 1)
OrderService | setDenominations | request | denominations[].displayName | string | yes | (max length 60)
OrderService | setDenominations | request | denominations[].kind | enum (note, coin) | yes
OrderService | setDenominations | request | denominations[].value | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | setDenominations | request | denominations[].value.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setDenominations | request | denominations[].value.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setDenominations | request | denominations[].value.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setDenominations | request | denominations[].sortOrder | integer | yes | (min 0)
OrderService | setDenominations | request | denominations[].isActive | boolean |  | (default True)
OrderService | setDenominations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setDeveloperMembers | request | members | array of object | yes
PlatformService | setDeveloperMembers | request | members[].email | string (email)
PlatformService | setDeveloperMembers | request | members[].role | enum (owner, admin, developer, readOnly)
PlatformService | setDeveloperMembers | param (path) | developerId | string (uuid) | yes
PlatformService | setDeveloperMembers | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setDeviceAssignment | request | deviceId | string (uuid) | yes | From the path of setDeviceAssignment. (read-only)
TenancyService | setDeviceAssignment | request | ownerOrgUnitId | string (uuid) |  | Who the device belongs to — the cost centre that replaces it when it breaks. (nullable)
TenancyService | setDeviceAssignment | request | custodianPrincipalId | string (uuid) |  | Who is holding it right now. (nullable)
TenancyService | setDeviceAssignment | request | assignedWorkstationId | string (uuid) |  | (nullable)
TenancyService | setDeviceAssignment | request | locationScopePath | string |  | (nullable)
TenancyService | setDeviceAssignment | request | lastSeenLocation | string |  | Reported by the heartbeat; distinct from where it is supposed to be. (read-only; nullable)
TenancyService | setDeviceAssignment | request | assetTag | string |  | (nullable)
TenancyService | setDeviceAssignment | request | acquiredAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | request | warrantyExpiresAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | request | assignedAt | string (date-time) |  | (read-only)
TenancyService | setDeviceAssignment | request | scopePath | string |  | The device's own platform.device.scope_path, set by the server on every write (ADAM CR-278, option A, 28 October 2026; CHG-R11TEN-005), so whoever can change the device can change who holds it. (read-only)
TenancyService | setDeviceAssignment | response | deviceId | string (uuid) | yes | From the path of setDeviceAssignment. (read-only)
TenancyService | setDeviceAssignment | response | ownerOrgUnitId | string (uuid) |  | Who the device belongs to — the cost centre that replaces it when it breaks. (nullable)
TenancyService | setDeviceAssignment | response | custodianPrincipalId | string (uuid) |  | Who is holding it right now. (nullable)
TenancyService | setDeviceAssignment | response | assignedWorkstationId | string (uuid) |  | (nullable)
TenancyService | setDeviceAssignment | response | locationScopePath | string |  | (nullable)
TenancyService | setDeviceAssignment | response | lastSeenLocation | string |  | Reported by the heartbeat; distinct from where it is supposed to be. (read-only; nullable)
TenancyService | setDeviceAssignment | response | assetTag | string |  | (nullable)
TenancyService | setDeviceAssignment | response | acquiredAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | response | warrantyExpiresAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | response | assignedAt | string (date-time) |  | (read-only)
TenancyService | setDeviceAssignment | response | scopePath | string |  | The device's own platform.device.scope_path, set by the server on every write (ADAM CR-278, option A, 28 October 2026; CHG-R11TEN-005), so whoever can change the device can change who holds it. (read-only)
TenancyService | setDeviceAssignment | param (path) | deviceId | string (uuid) | yes
TenancyService | setDeviceAssignment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setDeviceBindingPolicy | request | venueId | string (uuid) | yes
AccessService | setDeviceBindingPolicy | request | maximumActiveDevices | integer |  | Devices the credential may be active on at once (min 1; default 1)
AccessService | setDeviceBindingPolicy | request | concurrentSessions | integer |  | (min 1; default 1)
AccessService | setDeviceBindingPolicy | request | deviceChangePolicy | enum (notAllowed, allowedBeforeFirstUse, otpVerificationRequired, operatorApprovalRequired, supervisorApprovalRequired) |  | (default otpVerificationRequired)
AccessService | setDeviceBindingPolicy | response | id | string (uuid) | yes | The ruleId (display rule) or policyId (transfer policy) of the operations
AccessService | setDeviceBindingPolicy | response | kind | enum (activationDisplay, transfer, virtualTicketIdentity, deviceBinding) | yes | Which policy this row is; the columns of the other kinds stay null
AccessService | setDeviceBindingPolicy | response | name | string |  | (max length 200; nullable)
AccessService | setDeviceBindingPolicy | response | venueId | string (uuid) |  | Required for activationDisplay and virtualTicketIdentity (one virtualTicketIdentity row per venue) (nullable)
AccessService | setDeviceBindingPolicy | response | beforeActivationDisplay | array of enum (hideQr, blurQr, showCountdown, showAvailableAtVenue, showVenueDirections) |  | activationDisplay - what the guest sees before the credential activates
AccessService | setDeviceBindingPolicy | response | activeDisplay | array of enum (dynamicQr, activationTimer, credentialStatus, remainingEntitlements) |  | activationDisplay - what the guest sees once it is active
AccessService | setDeviceBindingPolicy | response | activationTriggers | array of string |  | activationDisplay - what activates the credential, e.g.
AccessService | setDeviceBindingPolicy | response | transferAllowed | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | numberOfTransfers | integer |  | transfer (min 0; nullable)
AccessService | setDeviceBindingPolicy | response | beforeFirstValidationOnly | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | requireRecipientAccount | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | requireOtp | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | requireAcceptance | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | returnToSender | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | transferDeadlineHours | integer |  | transfer - hours before the visit after which transfer closes (min 0; nullable)
AccessService | setDeviceBindingPolicy | response | cancelPendingAllowed | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | transferAuditRequired | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | idGenerationPattern | string |  | virtualTicketIdentity - Virtual Ticket ID format: prefix, suffix and length (nullable)
AccessService | setDeviceBindingPolicy | response | ticketClassification | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | ticketOwnershipModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | holderAssignmentRequirements | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | transferabilityReference | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | validityModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | consumptionModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | entitlementModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | mediaRequirements | array of string |  | virtualTicketIdentity - media types a ticket of this configuration must carry
AccessService | setDeviceBindingPolicy | response | maximumActiveDevices | integer |  | deviceBinding (min 1; nullable)
AccessService | setDeviceBindingPolicy | response | concurrentSessions | integer |  | deviceBinding (min 1; nullable)
AccessService | setDeviceBindingPolicy | response | deviceChangePolicy | enum (notAllowed, allowedBeforeFirstUse, otpVerificationRequired, operatorApprovalRequired, supervisorApprovalRequired) |  | deviceBinding (nullable)
AccessService | setDeviceBindingPolicy | response | scopePath | string | yes | ltree of the owning scope node
AccessService | setDeviceBindingPolicy | response | createdAt | string (date-time) |  | (read-only)
AccessService | setDeviceBindingPolicy | response | updatedAt | string (date-time) |  | (read-only)
AccessService | setDeviceBindingPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setDeviceFirmwareStatus | request | status | enum (released, deprecated, withdrawn) | yes
TenancyService | setDeviceFirmwareStatus | request | reason | string |  | Required with deprecated and withdrawn. (max length 500)
TenancyService | setDeviceFirmwareStatus | response | id | string (uuid) |  | (read-only)
TenancyService | setDeviceFirmwareStatus | response | deviceKind | string | yes
TenancyService | setDeviceFirmwareStatus | response | version | string | yes | The release's version as its vendor names it, sent on create (ADAM CR-285 (3), 28 October 2026; CHG-R11TEN-006).
TenancyService | setDeviceFirmwareStatus | response | vendor | string |  | Who built the image, as the device's driver names its maker. (nullable)
TenancyService | setDeviceFirmwareStatus | response | checksumAlgorithm | enum (sha256, sha512) |  | (default sha256)
TenancyService | setDeviceFirmwareStatus | response | releaseNotes | string |  | (nullable)
TenancyService | setDeviceFirmwareStatus | response | artefactAssetId | string (uuid) |  | The uploaded image (an Assets media asset), stored unchecked (ADAM CR-285 (1), 28 October 2026; CHG-R11TEN-006). (nullable)
TenancyService | setDeviceFirmwareStatus | response | checksum | string |  | (nullable)
TenancyService | setDeviceFirmwareStatus | response | minimumPreviousVersion | string |  | Some updates cannot be applied from any starting point. (nullable)
TenancyService | setDeviceFirmwareStatus | response | releasedAt | string (date-time) |  | Set when setDeviceFirmwareStatus first makes the release released. (read-only; nullable)
TenancyService | setDeviceFirmwareStatus | response | installedCount | integer |  | (read-only)
TenancyService | setDeviceFirmwareStatus | response | status | enum (draft, released, deprecated, withdrawn) |  | (default draft; read-only)
TenancyService | setDeviceFirmwareStatus | response | statusReason | string |  | The reason given when the release was deprecated or withdrawn. (read-only; nullable)
TenancyService | setDeviceFirmwareStatus | response | scopePath | string |  | The tenant the release belongs to. (read-only)
TenancyService | setDeviceFirmwareStatus | param (path) | firmwareId | string (uuid) | yes
TenancyService | setDeviceFirmwareStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setDunningPolicy | request | id | string (uuid) |  | (read-only)
OrderService | setDunningPolicy | request | maxAttempts | integer | yes | Capped at eight and defaulted to four. (min 1; max 8; default 4)
OrderService | setDunningPolicy | request | attemptOffsetDays | array of integer |  | Days after the first failure, and the spacing is the part that matters. (default [0, 3, 7, 14])
OrderService | setDunningPolicy | request | minimumHoursBetweenAttempts | integer |  | A floor under the offsets, because a schedule is edited by hand. (default 24)
OrderService | setDunningPolicy | request | retryableDeclineClasses | array of DeclineClass: enum (soft, hard, unknown) |  | soft alone, and widening it is a deliberate act. (default ['soft'])
OrderService | setDunningPolicy | request | notifyGuestOnEachAttempt | boolean |  | False by default. (default False)
OrderService | setDunningPolicy | request | terminalAction | enum (suspendBilling, cancelRenewal) | yes | What happens when the attempts run out, and it deliberately stops short of admission. (default suspendBilling)
OrderService | setDunningPolicy | request | scopePath | string |  | The partition key (ADR-0005).
OrderService | setDunningPolicy | response | id | string (uuid) |  | (read-only)
OrderService | setDunningPolicy | response | maxAttempts | integer | yes | Capped at eight and defaulted to four. (min 1; max 8; default 4)
OrderService | setDunningPolicy | response | attemptOffsetDays | array of integer |  | Days after the first failure, and the spacing is the part that matters. (default [0, 3, 7, 14])
OrderService | setDunningPolicy | response | minimumHoursBetweenAttempts | integer |  | A floor under the offsets, because a schedule is edited by hand. (default 24)
OrderService | setDunningPolicy | response | retryableDeclineClasses | array of DeclineClass: enum (soft, hard, unknown) |  | soft alone, and widening it is a deliberate act. (default ['soft'])
OrderService | setDunningPolicy | response | notifyGuestOnEachAttempt | boolean |  | False by default. (default False)
OrderService | setDunningPolicy | response | terminalAction | enum (suspendBilling, cancelRenewal) | yes | What happens when the attempts run out, and it deliberately stops short of admission. (default suspendBilling)
OrderService | setDunningPolicy | response | scopePath | string |  | The partition key (ADR-0005).
OrderService | setDunningPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setDunningPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setDynamicFieldQuestion | request | formId | string (uuid) | yes
MarketingService | setDynamicFieldQuestion | request | formVersion | integer | yes | (min 1)
MarketingService | setDynamicFieldQuestion | request | key | string | yes | (max length 60; pattern ^[a-zA-Z][a-zA-Z0-9_]*$)
MarketingService | setDynamicFieldQuestion | request | label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setDynamicFieldQuestion | request | helpText | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setDynamicFieldQuestion | request | fieldType | enum (shortText, longText, number, date, yesNo, checkbox, singleSelect, multiSelect, …) | yes
MarketingService | setDynamicFieldQuestion | request | standardField | enum (participantName, dateOfBirth, customerId, bookingReference, ticketNumber, guardianName, guardianRelationship, emergencyContact) |  | Set when the field is one of the reusable standard fields. (nullable)
MarketingService | setDynamicFieldQuestion | request | requirement | enum (required, optional, conditional, readOnly, autoPopulated) | yes | conditional needs conditions; autoPopulated and readOnly need mapsTo.
MarketingService | setDynamicFieldQuestion | request | options | array of object |  | The allowed values of a select, dropdown or multi-select field.
MarketingService | setDynamicFieldQuestion | request | options[].value | string | yes | (max length 100)
MarketingService | setDynamicFieldQuestion | request | options[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setDynamicFieldQuestion | request | validation | object |  | (nullable)
MarketingService | setDynamicFieldQuestion | request | validation.minimum | number |  | (nullable)
MarketingService | setDynamicFieldQuestion | request | validation.maximum | number |  | (nullable)
MarketingService | setDynamicFieldQuestion | request | validation.dateFrom | string (date) |  | (nullable)
MarketingService | setDynamicFieldQuestion | request | validation.dateTo | string (date) |  | (nullable)
MarketingService | setDynamicFieldQuestion | request | validation.pattern | string |  | The required format, as a regular expression. (max length 200; nullable)
MarketingService | setDynamicFieldQuestion | request | validation.maxLength | integer |  | The character limit. (min 1; nullable)
MarketingService | setDynamicFieldQuestion | request | conditions | array of object |  | All must hold (AND).
MarketingService | setDynamicFieldQuestion | request | conditions[].subject | string | yes | Another field's key, or isMinor. (max length 60)
MarketingService | setDynamicFieldQuestion | request | conditions[].operator | enum (equals, notEquals, in, lessThan, greaterThan, isAnswered) | yes
MarketingService | setDynamicFieldQuestion | request | conditions[].value | string |  | (max length 200; nullable)
MarketingService | setDynamicFieldQuestion | request | mapsTo | enum (guestName, guestDateOfBirth, guestEmail, guestMobile, guestAddress, guestId, ticketHolderName, orderReference, …) |  | The existing TICVAI record the field reads from, where the caller may read it. (nullable)
MarketingService | setDynamicFieldQuestion | request | isPersonalData | boolean |  | (default False)
MarketingService | setDynamicFieldQuestion | request | sortOrder | integer |  | (min 0; default 0)
MarketingService | setDynamicFieldQuestion | request | deleted | boolean |  | True removes the field from the draft version. (default False)
MarketingService | setDynamicFieldQuestion | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setDynamicFieldQuestion | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setDynamicFieldQuestion | response | formId | string (uuid) | yes
MarketingService | setDynamicFieldQuestion | response | formVersion | integer | yes | (min 1)
MarketingService | setDynamicFieldQuestion | response | key | string | yes | (max length 60; pattern ^[a-zA-Z][a-zA-Z0-9_]*$)
MarketingService | setDynamicFieldQuestion | response | label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setDynamicFieldQuestion | response | helpText | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setDynamicFieldQuestion | response | fieldType | enum (shortText, longText, number, date, yesNo, checkbox, singleSelect, multiSelect, …) | yes
MarketingService | setDynamicFieldQuestion | response | standardField | enum (participantName, dateOfBirth, customerId, bookingReference, ticketNumber, guardianName, guardianRelationship, emergencyContact) |  | Set when the field is one of the reusable standard fields. (nullable)
MarketingService | setDynamicFieldQuestion | response | requirement | enum (required, optional, conditional, readOnly, autoPopulated) | yes | conditional needs conditions; autoPopulated and readOnly need mapsTo.
MarketingService | setDynamicFieldQuestion | response | options | array of object |  | The allowed values of a select, dropdown or multi-select field.
MarketingService | setDynamicFieldQuestion | response | options[].value | string | yes | (max length 100)
MarketingService | setDynamicFieldQuestion | response | options[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setDynamicFieldQuestion | response | validation | object |  | (nullable)
MarketingService | setDynamicFieldQuestion | response | validation.minimum | number |  | (nullable)
MarketingService | setDynamicFieldQuestion | response | validation.maximum | number |  | (nullable)
MarketingService | setDynamicFieldQuestion | response | validation.dateFrom | string (date) |  | (nullable)
MarketingService | setDynamicFieldQuestion | response | validation.dateTo | string (date) |  | (nullable)
MarketingService | setDynamicFieldQuestion | response | validation.pattern | string |  | The required format, as a regular expression. (max length 200; nullable)
MarketingService | setDynamicFieldQuestion | response | validation.maxLength | integer |  | The character limit. (min 1; nullable)
MarketingService | setDynamicFieldQuestion | response | conditions | array of object |  | All must hold (AND).
MarketingService | setDynamicFieldQuestion | response | conditions[].subject | string | yes | Another field's key, or isMinor. (max length 60)
MarketingService | setDynamicFieldQuestion | response | conditions[].operator | enum (equals, notEquals, in, lessThan, greaterThan, isAnswered) | yes
MarketingService | setDynamicFieldQuestion | response | conditions[].value | string |  | (max length 200; nullable)
MarketingService | setDynamicFieldQuestion | response | mapsTo | enum (guestName, guestDateOfBirth, guestEmail, guestMobile, guestAddress, guestId, ticketHolderName, orderReference, …) |  | The existing TICVAI record the field reads from, where the caller may read it. (nullable)
MarketingService | setDynamicFieldQuestion | response | isPersonalData | boolean |  | (default False)
MarketingService | setDynamicFieldQuestion | response | sortOrder | integer |  | (min 0; default 0)
MarketingService | setDynamicFieldQuestion | response | deleted | boolean |  | True removes the field from the draft version. (default False)
MarketingService | setDynamicFieldQuestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setDynamicFieldQuestion | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setDynamicFieldQuestion | param (path) | formId | string (uuid) | yes | Addresses the item this write creates or replaces.
MarketingService | setDynamicFieldQuestion | param (path) | key | string | yes | Addresses the item this write creates or replaces.
MarketingService | setDynamicFieldQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDynamicPriceRule | request | rule | PricingDynamicPriceRule | yes | Taken from the backend workbook, 20 September.
CatalogueService | setDynamicPriceRule | request | rule.id | string (uuid)
CatalogueService | setDynamicPriceRule | request | rule.pricingRuleCode | string | yes | (max length 100)
CatalogueService | setDynamicPriceRule | request | rule.name | string | yes | (max length 200)
CatalogueService | setDynamicPriceRule | request | rule.productId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.priceListId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.scopePath | string |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.channelId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.priority | integer | yes
CatalogueService | setDynamicPriceRule | request | rule.validFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.validTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.isActive | boolean | yes
CatalogueService | setDynamicPriceRule | request | rule.dynamicPricingStrategyId | string (uuid) |  | The catalogue.dynamic_pricing_strategy a dynamic rule belongs to (29 September, data model DM3). (nullable)
CatalogueService | setDynamicPriceRule | request | rule.ruleType | string |  | Static rules: PricingRuleCommandCenterView.ruleType; dynamic rules: the builder's ruleKind. (max length 40; nullable)
CatalogueService | setDynamicPriceRule | request | rule.inputMetric | string |  | (max length 40; nullable)
CatalogueService | setDynamicPriceRule | request | rule.conditionLogic | enum (all, any) |  | (default all)
CatalogueService | setDynamicPriceRule | request | rule.cooldownMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | request | rule.minimumDurationMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | request | rule.exitThresholdOffset | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.rangeMinPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.rangeMaxPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.isProtected | boolean |  | A protected segment or channel: dynamic adjustments never apply. (default False)
CatalogueService | setDynamicPriceRule | request | conditions | array of PricingDynamicPriceCondition
CatalogueService | setDynamicPriceRule | request | conditions[].actionId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | request | conditions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | request | conditions[].type | string | yes | (max length 50)
CatalogueService | setDynamicPriceRule | request | conditions[].ruleOperator | string | yes | (max length 20)
CatalogueService | setDynamicPriceRule | request | conditions[].valueJson | string | yes
CatalogueService | setDynamicPriceRule | request | conditions[].sequenceNo | integer | yes
CatalogueService | setDynamicPriceRule | request | actions | array of PricingDynamicPriceAction
CatalogueService | setDynamicPriceRule | request | actions[].id | string (uuid)
CatalogueService | setDynamicPriceRule | request | actions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | request | actions[].type | string | yes | (max length 30)
CatalogueService | setDynamicPriceRule | request | actions[].value | number | yes
CatalogueService | setDynamicPriceRule | request | actions[].minPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | actions[].maxPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule | PricingDynamicPriceRule | yes | Taken from the backend workbook, 20 September.
CatalogueService | setDynamicPriceRule | response | rule.id | string (uuid)
CatalogueService | setDynamicPriceRule | response | rule.pricingRuleCode | string | yes | (max length 100)
CatalogueService | setDynamicPriceRule | response | rule.name | string | yes | (max length 200)
CatalogueService | setDynamicPriceRule | response | rule.productId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.priceListId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.scopePath | string |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.channelId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.priority | integer | yes
CatalogueService | setDynamicPriceRule | response | rule.validFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.validTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.isActive | boolean | yes
CatalogueService | setDynamicPriceRule | response | rule.dynamicPricingStrategyId | string (uuid) |  | The catalogue.dynamic_pricing_strategy a dynamic rule belongs to (29 September, data model DM3). (nullable)
CatalogueService | setDynamicPriceRule | response | rule.ruleType | string |  | Static rules: PricingRuleCommandCenterView.ruleType; dynamic rules: the builder's ruleKind. (max length 40; nullable)
CatalogueService | setDynamicPriceRule | response | rule.inputMetric | string |  | (max length 40; nullable)
CatalogueService | setDynamicPriceRule | response | rule.conditionLogic | enum (all, any) |  | (default all)
CatalogueService | setDynamicPriceRule | response | rule.cooldownMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | response | rule.minimumDurationMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | response | rule.exitThresholdOffset | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.rangeMinPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.rangeMaxPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.isProtected | boolean |  | A protected segment or channel: dynamic adjustments never apply. (default False)
CatalogueService | setDynamicPriceRule | response | conditions | array of PricingDynamicPriceCondition
CatalogueService | setDynamicPriceRule | response | conditions[].actionId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | response | conditions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | response | conditions[].type | string | yes | (max length 50)
CatalogueService | setDynamicPriceRule | response | conditions[].ruleOperator | string | yes | (max length 20)
CatalogueService | setDynamicPriceRule | response | conditions[].valueJson | string | yes
CatalogueService | setDynamicPriceRule | response | conditions[].sequenceNo | integer | yes
CatalogueService | setDynamicPriceRule | response | actions | array of PricingDynamicPriceAction
CatalogueService | setDynamicPriceRule | response | actions[].id | string (uuid)
CatalogueService | setDynamicPriceRule | response | actions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | response | actions[].type | string | yes | (max length 30)
CatalogueService | setDynamicPriceRule | response | actions[].value | number | yes
CatalogueService | setDynamicPriceRule | response | actions[].minPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | actions[].maxPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | param (path) | ruleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDynamicPricingGuardrailPolicy | request | id | string (uuid) | yes | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | request | scopeLevel | enum (global, market, venue, strategy, product, event, performance, channel) | yes
CatalogueService | setDynamicPricingGuardrailPolicy | request | scopeId | string (uuid) |  | Null at global. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minimumMarginPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumUpliftPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumReductionPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumSingleChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumDailyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumWeeklyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minimumChangeIntervalMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumChangesPerDay | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minimumInventory | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumOccupancyTriggerPercent | number |  | (min 0; max 100; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | protectedRateTypes | array of enum (contractRates, membershipRates, corporateRates, promotionalLockedRates, regulatoryPrices, complimentaryRates)
CatalogueService | setDynamicPricingGuardrailPolicy | request | isFrozen | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | request | isKillSwitchActive | boolean |  | Stops every automatic change in scope at once. (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | request | automationLevel | enum (advisory, humanInTheLoop, conditionalAutonomous, autonomous) | yes | (default advisory)
CatalogueService | setDynamicPricingGuardrailPolicy | request | authorityTiers | object |  | [{maxAdjustmentPercent, action, confidenceThreshold}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maxAdjustmentPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minAiConfidence | number |  | (min 0; max 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minRevenueUpliftPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | evaluationFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | executionFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | quietPeriodMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | noChangeWindows | object |  | [{anchor, minutesBefore, minutesAfter, clockFrom, clockTo}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | circuitBreakers | object |  | [{trigger, threshold, enabled, tripped}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | requireGuardrailsPassed | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | request | excludeProtectedRates | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | request | requireHealthyForecastData | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | request | safeFailureBehavior | enum (holdLastPrice, returnToBase, freeze, requestReview) |  | (default holdLastPrice)
CatalogueService | setDynamicPricingGuardrailPolicy | request | activeOverride | object |  | {user, reason, overridePrice, start, expiry, returnBehavior}. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | isPaused | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | id | string (uuid) | yes | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | scopeLevel | enum (global, market, venue, strategy, product, event, performance, channel) | yes
CatalogueService | setDynamicPricingGuardrailPolicy | response | scopeId | string (uuid) |  | Null at global. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minimumMarginPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumUpliftPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumReductionPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumSingleChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumDailyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumWeeklyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minimumChangeIntervalMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumChangesPerDay | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minimumInventory | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumOccupancyTriggerPercent | number |  | (min 0; max 100; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | protectedRateTypes | array of enum (contractRates, membershipRates, corporateRates, promotionalLockedRates, regulatoryPrices, complimentaryRates)
CatalogueService | setDynamicPricingGuardrailPolicy | response | isFrozen | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | response | isKillSwitchActive | boolean |  | Stops every automatic change in scope at once. (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | response | automationLevel | enum (advisory, humanInTheLoop, conditionalAutonomous, autonomous) | yes | (default advisory)
CatalogueService | setDynamicPricingGuardrailPolicy | response | authorityTiers | object |  | [{maxAdjustmentPercent, action, confidenceThreshold}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maxAdjustmentPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minAiConfidence | number |  | (min 0; max 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minRevenueUpliftPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | evaluationFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | executionFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | quietPeriodMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | noChangeWindows | object |  | [{anchor, minutesBefore, minutesAfter, clockFrom, clockTo}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | circuitBreakers | object |  | [{trigger, threshold, enabled, tripped}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | requireGuardrailsPassed | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | response | excludeProtectedRates | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | response | requireHealthyForecastData | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | response | safeFailureBehavior | enum (holdLastPrice, returnToBase, freeze, requestReview) |  | (default holdLastPrice)
CatalogueService | setDynamicPricingGuardrailPolicy | response | activeOverride | object |  | {user, reason, overridePrice, start, expiry, returnBehavior}. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | isPaused | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | response | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDynamicPricingStrategy | request | strategyName | string |  | Strategy Name
CatalogueService | setDynamicPricingStrategy | request | strategyCode | string |  | Strategy Code
CatalogueService | setDynamicPricingStrategy | request | description | string |  | Description
CatalogueService | setDynamicPricingStrategy | request | strategyType | enum (demandBased, occupancyBased, availabilityBased, inventoryBased, bookingVelocity, timeToEvent, seasonal, dayOfWeek, …) |  | Strategy Type
CatalogueService | setDynamicPricingStrategy | request | owner | string |  | Owner
CatalogueService | setDynamicPricingStrategy | request | businessUnit | string |  | Business Unit
CatalogueService | setDynamicPricingStrategy | request | market | string |  | Market (nullable)
CatalogueService | setDynamicPricingStrategy | request | venue | string |  | Venue (nullable)
CatalogueService | setDynamicPricingStrategy | request | product | string |  | Product (nullable)
CatalogueService | setDynamicPricingStrategy | request | event | string |  | Event (nullable)
CatalogueService | setDynamicPricingStrategy | request | performances | array of string |  | Performances in scope (one or many)
CatalogueService | setDynamicPricingStrategy | request | timeslots | array of string |  | Timeslots in scope; empty for all
CatalogueService | setDynamicPricingStrategy | request | priceCategories | array of string |  | Price categories in scope; empty for all
CatalogueService | setDynamicPricingStrategy | request | basePriceSource | string |  | Board 1 price-list rate ID the strategy moves from; a strategy never holds its own base amount
CatalogueService | setDynamicPricingStrategy | request | effectiveFrom | string (date-time) |  | Effective from
CatalogueService | setDynamicPricingStrategy | request | effectiveTo | string (date-time) |  | Effective to; empty for open-ended (nullable)
CatalogueService | setDynamicPricingStrategy | request | evaluationFrequency | enum (every15Minutes, every30Minutes, hourly, daily, onInventoryChange, onThresholdTrigger) |  | Evaluation frequency; defaults to hourly (decided 29 September, readiness close-out)
CatalogueService | setDynamicPricingStrategy | request | productFamily | string |  | Product family (for scopeType productFamily) (nullable)
CatalogueService | setDynamicPricingStrategy | request | scopeType | enum (singleProduct, productFamily, event, multiplePerformances, venue, selectedTimeslots, selectedPriceCategories) |  | Scope Assignment (pack p.77)
CatalogueService | setDynamicPricingStrategy | request | combinationMode | enum (independent, combinable, exclusive, fallback) |  | Strategy Combination: independent, combinable with other strategies, exclusive control, or fallback; defaults to independent (decided 29 September, readiness close-out)
CatalogueService | setDynamicPricingStrategy | request | clonedFromStrategyId | string |  | Strategy this one was cloned from (inherits its rules) (nullable)
CatalogueService | setDynamicPricingStrategy | response | strategyName | string |  | Strategy Name
CatalogueService | setDynamicPricingStrategy | response | strategyCode | string |  | Strategy Code
CatalogueService | setDynamicPricingStrategy | response | description | string |  | Description
CatalogueService | setDynamicPricingStrategy | response | strategyType | enum (demandBased, occupancyBased, availabilityBased, inventoryBased, bookingVelocity, timeToEvent, seasonal, dayOfWeek, …) |  | Strategy Type
CatalogueService | setDynamicPricingStrategy | response | owner | string |  | Owner
CatalogueService | setDynamicPricingStrategy | response | businessUnit | string |  | Business Unit
CatalogueService | setDynamicPricingStrategy | response | market | string |  | Market (nullable)
CatalogueService | setDynamicPricingStrategy | response | venue | string |  | Venue (nullable)
CatalogueService | setDynamicPricingStrategy | response | product | string |  | Product (nullable)
CatalogueService | setDynamicPricingStrategy | response | event | string |  | Event (nullable)
CatalogueService | setDynamicPricingStrategy | response | performances | array of string |  | Performances in scope (one or many)
CatalogueService | setDynamicPricingStrategy | response | timeslots | array of string |  | Timeslots in scope; empty for all
CatalogueService | setDynamicPricingStrategy | response | priceCategories | array of string |  | Price categories in scope; empty for all
CatalogueService | setDynamicPricingStrategy | response | basePriceSource | string |  | Board 1 price-list rate ID the strategy moves from; a strategy never holds its own base amount
CatalogueService | setDynamicPricingStrategy | response | effectiveFrom | string (date-time) |  | Effective from
CatalogueService | setDynamicPricingStrategy | response | effectiveTo | string (date-time) |  | Effective to; empty for open-ended (nullable)
CatalogueService | setDynamicPricingStrategy | response | evaluationFrequency | enum (every15Minutes, every30Minutes, hourly, daily, onInventoryChange, onThresholdTrigger) |  | Evaluation frequency; defaults to hourly (decided 29 September, readiness close-out)
CatalogueService | setDynamicPricingStrategy | response | status | string |  | Status: draft, testing, ready, scheduled, active, paused, frozen, expired or retired; draft on create
CatalogueService | setDynamicPricingStrategy | response | productFamily | string |  | Product family (for scopeType productFamily) (nullable)
CatalogueService | setDynamicPricingStrategy | response | scopeType | enum (singleProduct, productFamily, event, multiplePerformances, venue, selectedTimeslots, selectedPriceCategories) |  | Scope Assignment (pack p.77)
CatalogueService | setDynamicPricingStrategy | response | combinationMode | enum (independent, combinable, exclusive, fallback) |  | Strategy Combination: independent, combinable with other strategies, exclusive control, or fallback; defaults to independent (decided 29 September, readiness close-out)
CatalogueService | setDynamicPricingStrategy | response | clonedFromStrategyId | string |  | Strategy this one was cloned from (inherits its rules) (nullable)
CatalogueService | setDynamicPricingStrategy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | setEInvoicingProvider | request | id | string (uuid) |  | (read-only)
LedgerService | setEInvoicingProvider | request | legalEntityId | string (uuid) | yes
LedgerService | setEInvoicingProvider | request | providerName | string | yes | The accredited service provider the client appoints. (max length 200)
LedgerService | setEInvoicingProvider | request | endpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | request | testEndpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | request | credentialRef | string |  | A reference to the secret in the vault; the secret is never stored here. (max length 300; nullable)
LedgerService | setEInvoicingProvider | request | participantId | string |  | The legal entity's Peppol participant identifier. (max length 100; nullable)
LedgerService | setEInvoicingProvider | request | documentFormat | enum (pintAe) |  | (default pintAe)
LedgerService | setEInvoicingProvider | request | mode | enum (disabled, test, live) | yes
LedgerService | setEInvoicingProvider | request | transmitWithinHours | integer |  | (min 1; nullable)
LedgerService | setEInvoicingProvider | request | lastAcceptedTestAt | string (date-time) |  | (read-only; nullable)
LedgerService | setEInvoicingProvider | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | setEInvoicingProvider | response | id | string (uuid) |  | (read-only)
LedgerService | setEInvoicingProvider | response | legalEntityId | string (uuid) | yes
LedgerService | setEInvoicingProvider | response | providerName | string | yes | The accredited service provider the client appoints. (max length 200)
LedgerService | setEInvoicingProvider | response | endpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | response | testEndpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | response | credentialRef | string |  | A reference to the secret in the vault; the secret is never stored here. (max length 300; nullable)
LedgerService | setEInvoicingProvider | response | participantId | string |  | The legal entity's Peppol participant identifier. (max length 100; nullable)
LedgerService | setEInvoicingProvider | response | documentFormat | enum (pintAe) |  | (default pintAe)
LedgerService | setEInvoicingProvider | response | mode | enum (disabled, test, live) | yes
LedgerService | setEInvoicingProvider | response | transmitWithinHours | integer |  | (min 1; nullable)
LedgerService | setEInvoicingProvider | response | lastAcceptedTestAt | string (date-time) |  | (read-only; nullable)
LedgerService | setEInvoicingProvider | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | setEInvoicingProvider | param (path) | providerId | string (uuid) | yes | The record's id (ADAM CR-245).
LedgerService | setEInvoicingProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setEntitlementTemplateBlackoutDates | request | blackoutDates | array of string (date) | yes | The whole list; an empty list clears it.
CatalogueService | setEntitlementTemplateBlackoutDates | request | reason | string |  | (max length 300; nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | setEntitlementTemplateBlackoutDates | response | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | setEntitlementTemplateBlackoutDates | response | code | string | yes | (max length 64)
CatalogueService | setEntitlementTemplateBlackoutDates | response | name | string | yes | (max length 200)
CatalogueService | setEntitlementTemplateBlackoutDates | response | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | setEntitlementTemplateBlackoutDates | response | validFromOffsetDays | integer |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | validForDays | integer |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setEntitlementTemplateBlackoutDates | response | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setEntitlementTemplateBlackoutDates | response | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setEntitlementTemplateBlackoutDates | response | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setEntitlementTemplateBlackoutDates | response | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | validTimeWindows[].from | string
CatalogueService | setEntitlementTemplateBlackoutDates | response | validTimeWindows[].to | string
CatalogueService | setEntitlementTemplateBlackoutDates | response | validTimeWindows[].daysOfWeek | array of string
CatalogueService | setEntitlementTemplateBlackoutDates | response | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | setEntitlementTemplateBlackoutDates | response | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | setEntitlementTemplateBlackoutDates | response | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | setEntitlementTemplateBlackoutDates | response | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | setEntitlementTemplateBlackoutDates | response | reentryAllowed | boolean |  | (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | isTransferable | boolean |  | (default True)
CatalogueService | setEntitlementTemplateBlackoutDates | response | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | setEntitlementTemplateBlackoutDates | response | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | setEntitlementTemplateBlackoutDates | response | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | setEntitlementTemplateBlackoutDates | response | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | setEntitlementTemplateBlackoutDates | response | isActive | boolean
CatalogueService | setEntitlementTemplateBlackoutDates | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setEntitlementTemplateBlackoutDates | param (path) | templateId | string (uuid) | yes
CatalogueService | setEntitlementTemplateBlackoutDates | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setEventLifecycleState | request | state | enum (draft, planned, onSale, live, closed, cancelled, archived) | yes | The state to move to: written to lifecycle_state now, or to scheduled_lifecycle_state while the move waits for its effectiveFrom (ADAM CR-109).
CatalogueService | setEventLifecycleState | request | reason | string |  | Carried on event.lifecycleChanged; kept as scheduledLifecycleReason while a move waits for its effectiveFrom. (max length 500; nullable)
CatalogueService | setEventLifecycleState | request | effectiveFrom | string (date-time) |  | In the future, the move is scheduled and the event lifecycle job applies it then (ADAM CR-109); otherwise it is made now. (nullable)
CatalogueService | setEventLifecycleState | response | id | string (uuid) | yes
CatalogueService | setEventLifecycleState | response | code | string | yes
CatalogueService | setEventLifecycleState | response | name | string | yes
CatalogueService | setEventLifecycleState | response | venueId | string (uuid) | yes
CatalogueService | setEventLifecycleState | response | scopePath | string | yes
CatalogueService | setEventLifecycleState | response | parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | setEventLifecycleState | response | performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | setEventLifecycleState | response | isActive | boolean
CatalogueService | setEventLifecycleState | response | lifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | Where the event is in its lifecycle (4 October 2026, CHG-FXC-003; catalogue.event had nowhere to keep it). (read-only)
CatalogueService | setEventLifecycleState | response | lifecycleStateChangedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | setEventLifecycleState | response | scheduledLifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | A move waiting for its effectiveFrom (ADAM CR-109, option 2; CHG-R10CAT-009): written by setEventLifecycleState when effectiveFrom is in the future, applied and cleared by the event lifecycle job in… (read-only; nullable)
CatalogueService | setEventLifecycleState | response | scheduledLifecycleAt | string (date-time) |  | When the waiting move is applied (the request's effectiveFrom; ADAM CR-109). (read-only; nullable)
CatalogueService | setEventLifecycleState | response | scheduledLifecycleReason | string |  | The reason given with the waiting move, carried on event.lifecycleChanged when it is applied (ADAM CR-109). (max length 500; read-only; nullable)
CatalogueService | setEventLifecycleState | param (path) | eventId | string (uuid) | yes
CatalogueService | setEventLifecycleState | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setExperienceResourceRequirements | request | requirements | array of ResourceRequirement | yes
VenueOpsService | setExperienceResourceRequirements | request | requirements[].id | string (uuid)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].quantity | integer | yes | (default 1)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].mandatory | boolean |  | (default True)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].requiredQualifications | array of string
VenueOpsService | setExperienceResourceRequirements | request | requirements[].requiredAttributes | object
VenueOpsService | setExperienceResourceRequirements | request | requirements[].substituteResourceIds | array of string (uuid)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].scopePath | string
VenueOpsService | setExperienceResourceRequirements | request | requirements[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | setExperienceResourceRequirements | param (path) | experienceId | string (uuid) | yes | The experience's catalogue Product.id (4 October 2026, CHG-FXC-010; BO-877).
VenueOpsService | setExperienceResourceRequirements | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setFaceMatchingVerification | request | profileId | string (uuid) |  | Absent creates a threshold profile
AccessService | setFaceMatchingVerification | request | venueId | string | yes
AccessService | setFaceMatchingVerification | request | accessContext | string | yes | Where the thresholds apply, e.g. (max length 100)
AccessService | setFaceMatchingVerification | request | highConfidenceMin | number | yes | Score at or above which the match is high confidence (allow if every other rule passes) (min 0; max 1)
AccessService | setFaceMatchingVerification | request | reviewRangeMin | number | yes | Score at or above which the match goes to operator review; below it is denied. (min 0; max 1)
AccessService | setFaceMatchingVerification | request | retryQuantity | integer |  | (min 0; max 5; default 2)
AccessService | setFaceMatchingVerification | request | livenessCheck | boolean |  | (default True)
AccessService | setFaceMatchingVerification | request | duplicateFaceCheck | boolean |  | (default True)
AccessService | setFaceMatchingVerification | request | imageQuality | enum (low, medium, high) |  | Minimum image quality accepted (default medium)
AccessService | setFaceMatchingVerification | request | captureTimeout | integer |  | Seconds (min 1; max 60; default 10)
AccessService | setFaceMatchingVerification | request | maskObstructionHandling | enum (deny, operatorReview, fallbackMethod) |  | (default operatorReview)
AccessService | setFaceMatchingVerification | request | operatorFallback | boolean |  | Review-range results go to operator verification (default True)
AccessService | setFaceMatchingVerification | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setFaceMatchingVerification | response | livenessCheck | boolean |  | Liveness check
AccessService | setFaceMatchingVerification | response | duplicateFaceCheck | boolean |  | Duplicate-face check
AccessService | setFaceMatchingVerification | response | imageQuality | enum (low, medium, high) |  | Minimum image quality accepted (decided 29 September, VM close-out)
AccessService | setFaceMatchingVerification | response | captureTimeout | integer |  | Seconds
AccessService | setFaceMatchingVerification | response | maskObstructionHandling | enum (deny, operatorReview, fallbackMethod) |  | What a masked or obstructed face leads to (decided 29 September, VM close-out)
AccessService | setFaceMatchingVerification | response | operatorFallback | boolean |  | Review-range results go to operator verification
AccessService | setFaceMatchingVerification | response | profileId | string
AccessService | setFaceMatchingVerification | response | venueId | string
AccessService | setFaceMatchingVerification | response | accessContext | string |  | Where the thresholds apply, e.g.
AccessService | setFaceMatchingVerification | response | highConfidenceMin | number |  | Score at or above which the match is high confidence (allow if all other rules pass)
AccessService | setFaceMatchingVerification | response | reviewRangeMin | number |  | Score at or above which the match goes to operator review; below it is denied
AccessService | setFaceMatchingVerification | response | retryQuantity | integer
AccessService | setFaceMatchingVerification | param (path) | profileId | string (uuid) | yes | Addresses the item this write creates or replaces.
AccessService | setFaceMatchingVerification | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setFacePassEnrollment | request | venueId | string | yes | Venue this enrolment configuration applies to
AccessService | setFacePassEnrollment | request | enrollmentChannels | array of enum (ticvaiApp, ticketCounter, annualPassCounter, selfServiceKiosk, otherAuthorizedChannel) |  | Channels where Face Pass enrolment is enabled.
AccessService | setFacePassEnrollment | request | accountLoginRequired | boolean |  | Account login required
AccessService | setFacePassEnrollment | request | validTicketPassRequired | boolean |  | Valid ticket/pass required
AccessService | setFacePassEnrollment | request | identityCheckRequired | boolean |  | Identity check required
AccessService | setFacePassEnrollment | request | numberOfCaptureAttempts | integer |  | Number of capture attempts
AccessService | setFacePassEnrollment | request | minimumImageQuality | string |  | minimum image quality
AccessService | setFacePassEnrollment | request | operatorVerification | boolean |  | An operator must verify the capture
AccessService | setFacePassEnrollment | request | enrollmentExpiry | integer |  | Days an enrolment stays valid before re-enrolment is needed
AccessService | setFacePassEnrollment | request | duplicateFaceDetection | boolean |  | Block a face already associated with another annual pass
AccessService | setFacePassEnrollment | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setFacePassEnrollment | response | venueId | string | yes | Venue this enrolment configuration applies to
AccessService | setFacePassEnrollment | response | enrollmentChannels | array of enum (ticvaiApp, ticketCounter, annualPassCounter, selfServiceKiosk, otherAuthorizedChannel) |  | Channels where Face Pass enrolment is enabled.
AccessService | setFacePassEnrollment | response | accountLoginRequired | boolean |  | Account login required
AccessService | setFacePassEnrollment | response | validTicketPassRequired | boolean |  | Valid ticket/pass required
AccessService | setFacePassEnrollment | response | identityCheckRequired | boolean |  | Identity check required
AccessService | setFacePassEnrollment | response | numberOfCaptureAttempts | integer |  | Number of capture attempts
AccessService | setFacePassEnrollment | response | minimumImageQuality | string |  | minimum image quality
AccessService | setFacePassEnrollment | response | operatorVerification | boolean |  | An operator must verify the capture
AccessService | setFacePassEnrollment | response | enrollmentExpiry | integer |  | Days an enrolment stays valid before re-enrolment is needed
AccessService | setFacePassEnrollment | response | duplicateFaceDetection | boolean |  | Block a face already associated with another annual pass
AccessService | setFacePassEnrollment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setFaceTagTemporaryEnrollment | request | profileId | string (uuid) |  | Absent creates a Face Tag profile
AccessService | setFaceTagTemporaryEnrollment | request | venueId | string | yes
AccessService | setFaceTagTemporaryEnrollment | request | name | string | yes | (max length 200)
AccessService | setFaceTagTemporaryEnrollment | request | enrollmentChannels | array of enum (ticketCounter, entryGate) | yes | Where a Face Tag may be captured (min items 1)
AccessService | setFaceTagTemporaryEnrollment | request | bindTo | enum (ticket, visit, temporaryCredential) | yes | What the Face Tag is bound to (default ticket)
AccessService | setFaceTagTemporaryEnrollment | request | deletionTrigger | enum (ticketFullyRedeemed, endOfVisit, ticketExpiration, credentialCancellation, operationalRetentionThreshold) | yes | When the Face Tag is deleted automatically. (default ticketFullyRedeemed)
AccessService | setFaceTagTemporaryEnrollment | request | retentionThresholdHours | integer |  | Used only when deletionTrigger is operationalRetentionThreshold, and then required. (min 1)
AccessService | setFaceTagTemporaryEnrollment | request | consentFormId | string (uuid) |  | The venue's own consent form a Face Tag is captured on (decided 2 October 2026, Chinmay, batch 4, BO-188: "consent first, using a consent form from the venue"; DEC-128, DEC-549; CHG-CSP-018). (nullable)
AccessService | setFaceTagTemporaryEnrollment | request | consentCapture | enum (onScreenAcknowledgement, signedForm) |  | How consent is taken when a Face Tag is captured (3.2.44; added 29 September, build pass). (default onScreenAcknowledgement)
AccessService | setFaceTagTemporaryEnrollment | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setFaceTagTemporaryEnrollment | response | templatesHeldByTicvai | boolean |  | Where TICVAI stores the Face Tag templates, the screen warns the venue that every guest must accept the venue's consent form before capture (decided 2 October 2026, Chinmay, batch 4, BO-188; DEC-128;… (read-only)
AccessService | setFaceTagTemporaryEnrollment | response | consentFormId | string (uuid) |  | The venue's consent form this profile captures on (DEC-128; CHG-CSP-018). (nullable)
AccessService | setFaceTagTemporaryEnrollment | response | enrollmentChannels | array of enum (ticketCounter, entryGate) |  | Where a Face Tag may be captured
AccessService | setFaceTagTemporaryEnrollment | response | bindTo | enum (ticket, visit, temporaryCredential) |  | What the Face Tag is bound to
AccessService | setFaceTagTemporaryEnrollment | response | deletionTrigger | enum (ticketFullyRedeemed, endOfVisit, ticketExpiration, credentialCancellation, operationalRetentionThreshold) |  | When the Face Tag is automatically deleted; default ticketFullyRedeemed
AccessService | setFaceTagTemporaryEnrollment | response | profileId | string
AccessService | setFaceTagTemporaryEnrollment | response | venueId | string
AccessService | setFaceTagTemporaryEnrollment | response | name | string
AccessService | setFaceTagTemporaryEnrollment | response | retentionThresholdHours | integer |  | Used when deletionTrigger is operationalRetentionThreshold.
AccessService | setFaceTagTemporaryEnrollment | response | consentCapture | enum (onScreenAcknowledgement, signedForm) |  | How consent is taken at capture; onScreenAcknowledgement (no form to sign) unless set
AccessService | setFaceTagTemporaryEnrollment | param (path) | profileId | string (uuid) | yes | Addresses the item this write creates or replaces.
AccessService | setFaceTagTemporaryEnrollment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFaqs | request | categories | array of FaqCategory | yes
WhiteLabelService | setFaqs | request | categories[].code | string | yes
WhiteLabelService | setFaqs | request | categories[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setFaqs | request | categories[].sortOrder | integer
WhiteLabelService | setFaqs | request | categories[].entries | array of object | yes
WhiteLabelService | setFaqs | request | categories[].entries[].id | string (uuid) | yes
WhiteLabelService | setFaqs | request | categories[].entries[].question | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setFaqs | request | categories[].entries[].answer | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | setFaqs | request | categories[].entries[].sortOrder | integer
WhiteLabelService | setFaqs | request | categories[].entries[].isPublished | boolean
WhiteLabelService | setFaqs | request | categories[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setFaqs | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFeatureToggles | request | features | array of object | yes
WhiteLabelService | setFeatureToggles | request | features[].featureKey | FeatureKey: enum (digitalCompanionMode, aiConciergeChat, lostAndFound, pushNotifications, socialSharing, multiLanguage, appleWallet, googlePay, …) | yes | The feature toggles a tenant can set — one list for FeatureToggle and the setFeatureToggles body, which took a free string where the response had this enum.
WhiteLabelService | setFeatureToggles | request | features[].isEnabled | boolean | yes
WhiteLabelService | setFeatureToggles | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setFeeDefinition | request | id | string (uuid) | yes | (read-only)
CatalogueService | setFeeDefinition | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setFeeDefinition | request | code | string | yes | (max length 40)
CatalogueService | setFeeDefinition | request | name | string | yes | (max length 200)
CatalogueService | setFeeDefinition | request | description | string |  | (nullable)
CatalogueService | setFeeDefinition | request | feeType | enum (bookingFee, transactionFee, serviceFee, convenienceFee, deliveryFee, handlingFee, modificationFee, reschedulingFee, …) | yes
CatalogueService | setFeeDefinition | request | valueType | enum (fixedAmount, percentage, tiered) | yes
CatalogueService | setFeeDefinition | request | chargeBasis | enum (perTicket, perProduct, perPerson, perOrder, perTransaction, perDay) | yes
CatalogueService | setFeeDefinition | request | amount | object |  | (nullable)
CatalogueService | setFeeDefinition | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setFeeDefinition | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setFeeDefinition | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setFeeDefinition | request | percentage | number |  | (min 0; max 100; nullable)
CatalogueService | setFeeDefinition | request | tiers | object |  | [{fromOrderValue, amount, percentage}] for valueType: tiered. (nullable)
CatalogueService | setFeeDefinition | request | taxTreatment | string |  | How the fee is taxed; a catalogue.tax_rule may refine it. (max length 60; nullable)
CatalogueService | setFeeDefinition | request | refundability | enum (refundable, nonRefundable) |  | (default nonRefundable)
CatalogueService | setFeeDefinition | request | visibility | enum (customerVisible, includedInDisplayPrice, shownSeparately, internalOnly) |  | (default shownSeparately)
CatalogueService | setFeeDefinition | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setFeeDefinition | request | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setFeeDefinition | request | status | object | yes | (default draft)
CatalogueService | setFeeDefinition | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setFeeDefinition | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setFeeDefinition | response | id | string (uuid) | yes | (read-only)
CatalogueService | setFeeDefinition | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setFeeDefinition | response | code | string | yes | (max length 40)
CatalogueService | setFeeDefinition | response | name | string | yes | (max length 200)
CatalogueService | setFeeDefinition | response | description | string |  | (nullable)
CatalogueService | setFeeDefinition | response | feeType | enum (bookingFee, transactionFee, serviceFee, convenienceFee, deliveryFee, handlingFee, modificationFee, reschedulingFee, …) | yes
CatalogueService | setFeeDefinition | response | valueType | enum (fixedAmount, percentage, tiered) | yes
CatalogueService | setFeeDefinition | response | chargeBasis | enum (perTicket, perProduct, perPerson, perOrder, perTransaction, perDay) | yes
CatalogueService | setFeeDefinition | response | amount | object |  | (nullable)
CatalogueService | setFeeDefinition | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setFeeDefinition | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setFeeDefinition | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setFeeDefinition | response | percentage | number |  | (min 0; max 100; nullable)
CatalogueService | setFeeDefinition | response | tiers | object |  | [{fromOrderValue, amount, percentage}] for valueType: tiered. (nullable)
CatalogueService | setFeeDefinition | response | taxTreatment | string |  | How the fee is taxed; a catalogue.tax_rule may refine it. (max length 60; nullable)
CatalogueService | setFeeDefinition | response | refundability | enum (refundable, nonRefundable) |  | (default nonRefundable)
CatalogueService | setFeeDefinition | response | visibility | enum (customerVisible, includedInDisplayPrice, shownSeparately, internalOnly) |  | (default shownSeparately)
CatalogueService | setFeeDefinition | response | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setFeeDefinition | response | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setFeeDefinition | response | status | object | yes | (default draft)
CatalogueService | setFeeDefinition | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setFeeDefinition | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setFeeDefinition | param (path) | feeId | string (uuid) | yes | The record's id (ADAM CR-245).
CatalogueService | setFeeDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setFnbDeliveryPolicy | request | id | string (uuid) |  | (read-only)
FnbService | setFnbDeliveryPolicy | request | outletId | string (uuid) | yes
FnbService | setFnbDeliveryPolicy | request | collectionEnabled | boolean |  | (default True)
FnbService | setFnbDeliveryPolicy | request | deliveryEnabled | boolean |  | (default False)
FnbService | setFnbDeliveryPolicy | request | collectionPoint | string |  | (max length 200; nullable)
FnbService | setFnbDeliveryPolicy | request | collectionHoldMinutes | integer |  | (default 20)
FnbService | setFnbDeliveryPolicy | request | asapCollectionMinutes | integer |  | (default 25)
FnbService | setFnbDeliveryPolicy | request | asapDeliveryMinutes | integer |  | (default 45)
FnbService | setFnbDeliveryPolicy | request | slotMinutes | integer |  | (default 30)
FnbService | setFnbDeliveryPolicy | request | minimumOrder | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | request | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | request | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | request | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | request | deliveryFee | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | request | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | request | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | request | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | request | radiusKm | number |  | (min 0; nullable)
FnbService | setFnbDeliveryPolicy | request | emiratesServed | array of string
FnbService | setFnbDeliveryPolicy | request | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | setFnbDeliveryPolicy | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setFnbDeliveryPolicy | response | id | string (uuid) |  | (read-only)
FnbService | setFnbDeliveryPolicy | response | outletId | string (uuid) | yes
FnbService | setFnbDeliveryPolicy | response | collectionEnabled | boolean |  | (default True)
FnbService | setFnbDeliveryPolicy | response | deliveryEnabled | boolean |  | (default False)
FnbService | setFnbDeliveryPolicy | response | collectionPoint | string |  | (max length 200; nullable)
FnbService | setFnbDeliveryPolicy | response | collectionHoldMinutes | integer |  | (default 20)
FnbService | setFnbDeliveryPolicy | response | asapCollectionMinutes | integer |  | (default 25)
FnbService | setFnbDeliveryPolicy | response | asapDeliveryMinutes | integer |  | (default 45)
FnbService | setFnbDeliveryPolicy | response | slotMinutes | integer |  | (default 30)
FnbService | setFnbDeliveryPolicy | response | minimumOrder | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | response | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | response | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | response | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | response | deliveryFee | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | response | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | response | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | response | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | response | radiusKm | number |  | (min 0; nullable)
FnbService | setFnbDeliveryPolicy | response | emiratesServed | array of string
FnbService | setFnbDeliveryPolicy | response | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | setFnbDeliveryPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setFnbDeliveryPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setFnbDeliveryPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFonts | request | primaryLatin | string | yes
WhiteLabelService | setFonts | request | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | setFonts | request | secondaryLatin | string |  | (nullable)
WhiteLabelService | setFonts | request | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | setFonts | request | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | setFonts | request | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | setFonts | response | primaryLatin | string | yes
WhiteLabelService | setFonts | response | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | setFonts | response | secondaryLatin | string |  | (nullable)
WhiteLabelService | setFonts | response | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | setFonts | response | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | setFonts | response | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | setFonts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFonts | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | setFooter | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | setFooter | request | scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | setFooter | request | columns | array of object
WhiteLabelService | setFooter | request | columns[].heading | string
WhiteLabelService | setFooter | request | columns[].sortOrder | integer |  | The column's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | setFooter | request | columns[].links | array of object |  | The column's links in display order, stored on the column row as one value (R8 blocker WHITE-C24).
WhiteLabelService | setFooter | request | columns[].links[].label | string
WhiteLabelService | setFooter | request | columns[].links[].url | string
WhiteLabelService | setFooter | request | columns[].links[].opensCookiePreferences | boolean |  | (default False)
WhiteLabelService | setFooter | request | legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | setFooter | request | legalLinks.termsUrl | string
WhiteLabelService | setFooter | request | legalLinks.privacyUrl | string
WhiteLabelService | setFooter | request | legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | setFooter | request | legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | setFooter | request | copyrightText | string
WhiteLabelService | setFooter | request | socialLinks | array of object
WhiteLabelService | setFooter | request | socialLinks[].platform | string
WhiteLabelService | setFooter | request | socialLinks[].url | string
WhiteLabelService | setFooter | request | socialLinks[].sortOrder | integer |  | The link's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | setFooter | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | setFooter | response | scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | setFooter | response | columns | array of object
WhiteLabelService | setFooter | response | columns[].heading | string
WhiteLabelService | setFooter | response | columns[].sortOrder | integer |  | The column's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | setFooter | response | columns[].links | array of object |  | The column's links in display order, stored on the column row as one value (R8 blocker WHITE-C24).
WhiteLabelService | setFooter | response | columns[].links[].label | string
WhiteLabelService | setFooter | response | columns[].links[].url | string
WhiteLabelService | setFooter | response | columns[].links[].opensCookiePreferences | boolean |  | (default False)
WhiteLabelService | setFooter | response | legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | setFooter | response | legalLinks.termsUrl | string
WhiteLabelService | setFooter | response | legalLinks.privacyUrl | string
WhiteLabelService | setFooter | response | legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | setFooter | response | legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | setFooter | response | copyrightText | string
WhiteLabelService | setFooter | response | socialLinks | array of object
WhiteLabelService | setFooter | response | socialLinks[].platform | string
WhiteLabelService | setFooter | response | socialLinks[].url | string
WhiteLabelService | setFooter | response | socialLinks[].sortOrder | integer |  | The link's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | setFooter | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setForecastDefinition | request | id | string (uuid) |  | (read-only)
AiService | setForecastDefinition | request | definitionKey | string | yes
AiService | setForecastDefinition | request | name | string
AiService | setForecastDefinition | request | subject | enum (attendance, arrivalPattern, productDemand, timeslotDemand, channelPace, revenue, occupancy, attractionUtilisation, …) | yes
AiService | setForecastDefinition | request | module | object |  | Whose AI this forecast is, and so who publishes it (Chinmay, 2 October, workbook Q3: "the permission holder for that module's AI"; CHG-FUP-004).
AiService | setForecastDefinition | request | grain | enum (hour, day, week, month) | yes
AiService | setForecastDefinition | request | dimensions | array of string |  | Breakdowns forecast directly or reconciled to.
AiService | setForecastDefinition | request | segmentIds | array of string (uuid) |  | The marketing-crm segments customerSegment breaks down by, in priority order where a guest is in several.
AiService | setForecastDefinition | request | horizonDays | integer | yes | (min 1; max 730)
AiService | setForecastDefinition | request | refreshCadence | enum (hourly, daily, weekly)
AiService | setForecastDefinition | request | producer | enum (rule, statistical, model, ensemble) | yes | Which producer is live (design 3.10).
AiService | setForecastDefinition | request | historyWindowMonths | integer |  | How much of the venue's own history the statistical producer reads (18 September minutes, M18-16: "36 months of history"). (min 1; max 60; default 36)
AiService | setForecastDefinition | request | coldStart | object |  | What the forecast stands on before the venue has history (29 September, AI functions review; forecasting book p.27 "New Venue / New Product Problem").
AiService | setForecastDefinition | request | coldStart.strategy | enum (venueSettings, startingPattern, sisterVenue, categoryBaseline, importedHistory) |  | venueSettings uses the onboarding figures with the venue-type pattern; sisterVenue a venue of the same tenant; categoryBaseline a product category's own history; importedHistory means an import cover… (default venueSettings)
AiService | setForecastDefinition | request | coldStart.sisterVenueId | string (uuid) |  | For sisterVenue. (nullable)
AiService | setForecastDefinition | request | coldStart.priorWeightObservations | integer |  | k: how many own observations the prior is worth (4 same weekdays by default). (min 1; max 52; default 4)
AiService | setForecastDefinition | request | coldStart.startingBandPercent | integer |  | The width of the range while the prior carries most of the weight (about +/-40%). (min 5; max 80; default 40)
AiService | setForecastDefinition | request | producerRef | string |  | (read-only)
AiService | setForecastDefinition | request | shadowProducerRef | string |  | Runs alongside and is recorded, never shown (design 3.5). (read-only; nullable)
AiService | setForecastDefinition | request | autoPublish | boolean |  | Publish without approval when the quality gates pass (autonomy L4, design 3.8). (default False)
AiService | setForecastDefinition | request | qualityGates | object |  | Completeness, blocking signals and accuracy-regression thresholds a version must pass to publish. (nullable)
AiService | setForecastDefinition | request | signalKeys | array of string |  | Signal sources this definition may use (ADM-501).
AiService | setForecastDefinition | request | isActive | boolean |  | (default True)
AiService | setForecastDefinition | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setForecastDefinition | response | id | string (uuid) |  | (read-only)
AiService | setForecastDefinition | response | definitionKey | string | yes
AiService | setForecastDefinition | response | name | string
AiService | setForecastDefinition | response | subject | enum (attendance, arrivalPattern, productDemand, timeslotDemand, channelPace, revenue, occupancy, attractionUtilisation, …) | yes
AiService | setForecastDefinition | response | module | object |  | Whose AI this forecast is, and so who publishes it (Chinmay, 2 October, workbook Q3: "the permission holder for that module's AI"; CHG-FUP-004).
AiService | setForecastDefinition | response | grain | enum (hour, day, week, month) | yes
AiService | setForecastDefinition | response | dimensions | array of string |  | Breakdowns forecast directly or reconciled to.
AiService | setForecastDefinition | response | segmentIds | array of string (uuid) |  | The marketing-crm segments customerSegment breaks down by, in priority order where a guest is in several.
AiService | setForecastDefinition | response | horizonDays | integer | yes | (min 1; max 730)
AiService | setForecastDefinition | response | refreshCadence | enum (hourly, daily, weekly)
AiService | setForecastDefinition | response | producer | enum (rule, statistical, model, ensemble) | yes | Which producer is live (design 3.10).
AiService | setForecastDefinition | response | historyWindowMonths | integer |  | How much of the venue's own history the statistical producer reads (18 September minutes, M18-16: "36 months of history"). (min 1; max 60; default 36)
AiService | setForecastDefinition | response | coldStart | object |  | What the forecast stands on before the venue has history (29 September, AI functions review; forecasting book p.27 "New Venue / New Product Problem").
AiService | setForecastDefinition | response | coldStart.strategy | enum (venueSettings, startingPattern, sisterVenue, categoryBaseline, importedHistory) |  | venueSettings uses the onboarding figures with the venue-type pattern; sisterVenue a venue of the same tenant; categoryBaseline a product category's own history; importedHistory means an import cover… (default venueSettings)
AiService | setForecastDefinition | response | coldStart.sisterVenueId | string (uuid) |  | For sisterVenue. (nullable)
AiService | setForecastDefinition | response | coldStart.priorWeightObservations | integer |  | k: how many own observations the prior is worth (4 same weekdays by default). (min 1; max 52; default 4)
AiService | setForecastDefinition | response | coldStart.startingBandPercent | integer |  | The width of the range while the prior carries most of the weight (about +/-40%). (min 5; max 80; default 40)
AiService | setForecastDefinition | response | producerRef | string |  | (read-only)
AiService | setForecastDefinition | response | shadowProducerRef | string |  | Runs alongside and is recorded, never shown (design 3.5). (read-only; nullable)
AiService | setForecastDefinition | response | autoPublish | boolean |  | Publish without approval when the quality gates pass (autonomy L4, design 3.8). (default False)
AiService | setForecastDefinition | response | qualityGates | object |  | Completeness, blocking signals and accuracy-regression thresholds a version must pass to publish. (nullable)
AiService | setForecastDefinition | response | signalKeys | array of string |  | Signal sources this definition may use (ADM-501).
AiService | setForecastDefinition | response | isActive | boolean |  | (default True)
AiService | setForecastDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setForecastDefinition | param (path) | definitionKey | string | yes
AiService | setForecastDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | setFxProvider | request | assignments | array of FxProviderAssignment | yes | At most one per purpose.
LedgerService | setFxProvider | request | assignments[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | setFxProvider | request | assignments[].source | FxRateSource: enum (manual, uaeCentralBank, ecb, openExchangeRates, cardScheme, provider) | yes | Where the rate came from, and which provider specifically.
LedgerService | setFxProvider | request | assignments[].credentialRef | string |  | BYOK — the key lives in the secret store, never here. (nullable)
LedgerService | setFxProvider | request | assignments[].schedule | string |  | Cron in the region timezone. (nullable)
LedgerService | setFxProvider | request | assignments[].scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | setFxProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | setFxRate | request | id | string (uuid) |  | (read-only)
LedgerService | setFxRate | request | fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | request | toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | request | rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | setFxRate | request | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | setFxRate | request | source | object |  | (read-only)
LedgerService | setFxRate | request | effectiveFrom | string (date-time) | yes
LedgerService | setFxRate | request | effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | setFxRate | request | setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | setFxRate | request | note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | setFxRate | request | providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | setFxRate | request | fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | setFxRate | request | chargeable | boolean |  | With venueId, true where a guest may select this currency and pay in it at that venue (tenancy.VenueSettings.chargeCurrencies), false where it is shown as an approximate price only (CHG-FIN-001). (read-only)
LedgerService | setFxRate | response | id | string (uuid) |  | (read-only)
LedgerService | setFxRate | response | fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | response | toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | response | rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | setFxRate | response | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | setFxRate | response | source | object |  | (read-only)
LedgerService | setFxRate | response | effectiveFrom | string (date-time) | yes
LedgerService | setFxRate | response | effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | setFxRate | response | setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | setFxRate | response | note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | setFxRate | response | providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | setFxRate | response | fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | setFxRate | response | chargeable | boolean |  | With venueId, true where a guest may select this currency and pay in it at that venue (tenancy.VenueSettings.chargeCurrencies), false where it is shown as an approximate price only (CHG-FIN-001). (read-only)
LedgerService | setFxRate | param (path) | rateId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
LedgerService | setFxRate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setGateModePolicy | request | id | string (uuid) | yes | (read-only)
AccessService | setGateModePolicy | request | venueId | string (uuid) | yes
AccessService | setGateModePolicy | request | mode | enum (freeFlow, dropArm) | yes | Non-standard operating mode governed (R221 vocabulary)
AccessService | setGateModePolicy | request | whoCanActivate | array of string |  | Roles allowed to activate this mode
AccessService | setGateModePolicy | request | accessPointGroupId | string (uuid) |  | Gate group the policy applies to (access.access_point_group); null for the whole venue (nullable)
AccessService | setGateModePolicy | request | reasonRequired | boolean |  | (default True)
AccessService | setGateModePolicy | request | emergencyCode | string |  | (nullable)
AccessService | setGateModePolicy | request | automaticNotification | boolean |  | (default False)
AccessService | setGateModePolicy | request | createsIncident | boolean |  | Activation creates an incident record (default False)
AccessService | setGateModePolicy | request | scopePath | string | yes | ltree of the owning scope node (ADR-0005) (read-only)
AccessService | setGateModePolicy | request | createdAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | request | updatedAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | response | id | string (uuid) | yes | (read-only)
AccessService | setGateModePolicy | response | venueId | string (uuid) | yes
AccessService | setGateModePolicy | response | mode | enum (freeFlow, dropArm) | yes | Non-standard operating mode governed (R221 vocabulary)
AccessService | setGateModePolicy | response | whoCanActivate | array of string |  | Roles allowed to activate this mode
AccessService | setGateModePolicy | response | accessPointGroupId | string (uuid) |  | Gate group the policy applies to (access.access_point_group); null for the whole venue (nullable)
AccessService | setGateModePolicy | response | reasonRequired | boolean |  | (default True)
AccessService | setGateModePolicy | response | emergencyCode | string |  | (nullable)
AccessService | setGateModePolicy | response | automaticNotification | boolean |  | (default False)
AccessService | setGateModePolicy | response | createsIncident | boolean |  | Activation creates an incident record (default False)
AccessService | setGateModePolicy | response | scopePath | string | yes | ltree of the owning scope node (ADR-0005) (read-only)
AccessService | setGateModePolicy | response | createdAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | response | updatedAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | param (path) | gateModePolicyId | string (uuid) | yes | The record's id (ADAM CR-245).
AccessService | setGateModePolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setGroupPackageDefinition | request | id | string (uuid) |  | (read-only)
CatalogueService | setGroupPackageDefinition | request | productId | string |  | (read-only)
CatalogueService | setGroupPackageDefinition | request | name | string |  | Read from the package's product, not stored here (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009): catalogue.product.name, in the caller's language. (read-only)
CatalogueService | setGroupPackageDefinition | request | unitPrice | object |  | The product's price per participant (pricingBasis perParticipant) or per package, read from the product's current price; not stored here. (read-only)
CatalogueService | setGroupPackageDefinition | request | unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setGroupPackageDefinition | request | unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setGroupPackageDefinition | request | unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setGroupPackageDefinition | request | minimumSize | integer |  | The smallest group the package is sold to; null means one participant. (min 1; nullable)
CatalogueService | setGroupPackageDefinition | request | kind | enum (school, party, corporate, tourOperator, community) | yes | corporate, tourOperator and community are the group types the approved group-booking screens draw beside school and party (CHG-SGU-024; R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009).
CatalogueService | setGroupPackageDefinition | request | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | setGroupPackageDefinition | request | durationMinutes | integer | yes | (min 15)
CatalogueService | setGroupPackageDefinition | request | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | setGroupPackageDefinition | request | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | setGroupPackageDefinition | request | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | setGroupPackageDefinition | request | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | setGroupPackageDefinition | request | includes | array of string
CatalogueService | setGroupPackageDefinition | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setGroupPackageDefinition | response | id | string (uuid) |  | (read-only)
CatalogueService | setGroupPackageDefinition | response | productId | string |  | (read-only)
CatalogueService | setGroupPackageDefinition | response | name | string |  | Read from the package's product, not stored here (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009): catalogue.product.name, in the caller's language. (read-only)
CatalogueService | setGroupPackageDefinition | response | unitPrice | object |  | The product's price per participant (pricingBasis perParticipant) or per package, read from the product's current price; not stored here. (read-only)
CatalogueService | setGroupPackageDefinition | response | unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setGroupPackageDefinition | response | unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setGroupPackageDefinition | response | unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setGroupPackageDefinition | response | minimumSize | integer |  | The smallest group the package is sold to; null means one participant. (min 1; nullable)
CatalogueService | setGroupPackageDefinition | response | kind | enum (school, party, corporate, tourOperator, community) | yes | corporate, tourOperator and community are the group types the approved group-booking screens draw beside school and party (CHG-SGU-024; R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009).
CatalogueService | setGroupPackageDefinition | response | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | setGroupPackageDefinition | response | durationMinutes | integer | yes | (min 15)
CatalogueService | setGroupPackageDefinition | response | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | setGroupPackageDefinition | response | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | setGroupPackageDefinition | response | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | setGroupPackageDefinition | response | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | setGroupPackageDefinition | response | includes | array of string
CatalogueService | setGroupPackageDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setGroupPackageDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setGroupPackageDefinition | param (path) | productId | string | yes
WhiteLabelService | setHeader | request | layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | setHeader | request | showLogo | boolean |  | (default True)
WhiteLabelService | setHeader | request | showMenu | boolean |  | (default True)
WhiteLabelService | setHeader | request | showNotifications | boolean |  | (default True)
WhiteLabelService | setHeader | request | backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setHeader | response | layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | setHeader | response | showLogo | boolean |  | (default True)
WhiteLabelService | setHeader | response | showMenu | boolean |  | (default True)
WhiteLabelService | setHeader | response | showNotifications | boolean |  | (default True)
WhiteLabelService | setHeader | response | backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setHeader | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setHeader | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | setHomepageLayout | request | templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | setHomepageLayout | request | landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | setHomepageLayout | request | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | request | sections | array of object | yes
WhiteLabelService | setHomepageLayout | request | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | request | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | setHomepageLayout | request | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setHomepageLayout | request | sections[].sortOrder | integer | yes
WhiteLabelService | setHomepageLayout | request | sections[].isVisible | boolean | yes
WhiteLabelService | setHomepageLayout | request | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | setHomepageLayout | request | sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | setHomepageLayout | request | sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | setHomepageLayout | request | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | setHomepageLayout | response | templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | setHomepageLayout | response | landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | setHomepageLayout | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | response | sections | array of object | yes
WhiteLabelService | setHomepageLayout | response | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | response | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | setHomepageLayout | response | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setHomepageLayout | response | sections[].sortOrder | integer | yes
WhiteLabelService | setHomepageLayout | response | sections[].isVisible | boolean | yes
WhiteLabelService | setHomepageLayout | response | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | setHomepageLayout | response | sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | setHomepageLayout | response | sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | setHomepageLayout | response | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | setHomepageLayout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setHomepageLayout | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
AiService | setIndexSource | request | id | string (uuid) |  | (read-only)
AiService | setIndexSource | request | table | string | yes | Schema-qualified, e.g.
AiService | setIndexSource | request | contract | string |  | Which contract owns it, for tracing back.
AiService | setIndexSource | request | textFields | array of string | yes | The fields a person would read. (min items 1)
AiService | setIndexSource | request | payloadFields | array of string |  | Carried alongside the vector for filtering, not embedded.
AiService | setIndexSource | request | collectionId | string (uuid) | yes | The knowledge collection the source's entries land in.
AiService | setIndexSource | request | collection | string | yes | The name of the collection's Qdrant alias, set by the server from collectionId and never sent. (read-only)
AiService | setIndexSource | request | scopeLevel | enum (tenant, region, venue) | yes
AiService | setIndexSource | request | kind | enum (product, entitlement, knowledge, faq, report, media) |  | The semanticSearch kind this source feeds (R8 blocker ORDERS-MONEY-C37). (nullable)
AiService | setIndexSource | request | invalidatedBy | array of string |  | Domain events that make an entry stale.
AiService | setIndexSource | request | chunkStrategy | enum (wholeRecord, paragraph, fixedTokens, section, semanticSection, parentChild) |  | Changes what is stored, so it cannot be altered without a reindex.
AiService | setIndexSource | request | parentField | string |  | Which field carries the parent context, where chunkStrategy is parentChild. (nullable)
AiService | setIndexSource | request | isActive | boolean
AiService | setIndexSource | request | entryCount | integer |  | (read-only)
AiService | setIndexSource | request | lastIndexedAt | string (date-time) |  | (read-only; nullable)
AiService | setIndexSource | request | staleCount | integer |  | Records changed since their last embedding. (read-only)
AiService | setIndexSource | response | id | string (uuid) |  | (read-only)
AiService | setIndexSource | response | table | string | yes | Schema-qualified, e.g.
AiService | setIndexSource | response | contract | string |  | Which contract owns it, for tracing back.
AiService | setIndexSource | response | textFields | array of string | yes | The fields a person would read. (min items 1)
AiService | setIndexSource | response | payloadFields | array of string |  | Carried alongside the vector for filtering, not embedded.
AiService | setIndexSource | response | collectionId | string (uuid) | yes | The knowledge collection the source's entries land in.
AiService | setIndexSource | response | collection | string | yes | The name of the collection's Qdrant alias, set by the server from collectionId and never sent. (read-only)
AiService | setIndexSource | response | scopeLevel | enum (tenant, region, venue) | yes
AiService | setIndexSource | response | kind | enum (product, entitlement, knowledge, faq, report, media) |  | The semanticSearch kind this source feeds (R8 blocker ORDERS-MONEY-C37). (nullable)
AiService | setIndexSource | response | invalidatedBy | array of string |  | Domain events that make an entry stale.
AiService | setIndexSource | response | chunkStrategy | enum (wholeRecord, paragraph, fixedTokens, section, semanticSection, parentChild) |  | Changes what is stored, so it cannot be altered without a reindex.
AiService | setIndexSource | response | parentField | string |  | Which field carries the parent context, where chunkStrategy is parentChild. (nullable)
AiService | setIndexSource | response | isActive | boolean
AiService | setIndexSource | response | entryCount | integer |  | (read-only)
AiService | setIndexSource | response | lastIndexedAt | string (date-time) |  | (read-only; nullable)
AiService | setIndexSource | response | staleCount | integer |  | Records changed since their last embedding. (read-only)
AiService | setIndexSource | param (path) | sourceId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
AiService | setIndexSource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | setInventoryKitDefinition | request | kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | request | components | array of InventoryKitComponent | yes
InventoryService | setInventoryKitDefinition | request | components[].kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | request | components[].componentItemId | string (uuid) | yes
InventoryService | setInventoryKitDefinition | request | components[].quantity | number | yes
InventoryService | setInventoryKitDefinition | request | components[].unit | string |  | The component's base unit where omitted. (nullable)
InventoryService | setInventoryKitDefinition | request | components[].scopePath | string |  | The partition key (ADR-0005). (read-only)
InventoryService | setInventoryKitDefinition | response | kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | response | components | array of InventoryKitComponent | yes
InventoryService | setInventoryKitDefinition | response | components[].kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | response | components[].componentItemId | string (uuid) | yes
InventoryService | setInventoryKitDefinition | response | components[].quantity | number | yes
InventoryService | setInventoryKitDefinition | response | components[].unit | string |  | The component's base unit where omitted. (nullable)
InventoryService | setInventoryKitDefinition | response | components[].scopePath | string |  | The partition key (ADR-0005). (read-only)
InventoryService | setInventoryKitDefinition | param (path) | itemId | string (uuid) | yes
InventoryService | setInventoryKitDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setItemAvailability | request | isAvailable | boolean | yes
FnbService | setItemAvailability | request | reason | enum (soldOut, ingredientUnavailable, equipmentDown, seasonal, other) |  | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | setItemAvailability | request | note | string |  | Free text. (max length 500; nullable)
FnbService | setItemAvailability | request | restoreAt | string (date-time) |  | Automatic restore, typically at next service.
FnbService | setItemAvailability | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | setItemAvailability | response | id | string (uuid) | yes
FnbService | setItemAvailability | response | productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | setItemAvailability | response | name | string | yes
FnbService | setItemAvailability | response | description | string |  | (nullable)
FnbService | setItemAvailability | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setItemAvailability | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setItemAvailability | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setItemAvailability | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setItemAvailability | response | dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | setItemAvailability | response | remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | setItemAvailability | response | sortOrder | integer
FnbService | setItemAvailability | response | modifierGroupIds | array of string (uuid)
FnbService | setItemAvailability | response | stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | setItemAvailability | response | menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | setItemAvailability | response | isStockTracked | boolean |  | True where a recipe exists.
FnbService | setItemAvailability | response | isAvailable | boolean | yes
FnbService | setItemAvailability | response | unavailableReason | string |  | (nullable)
FnbService | setItemAvailability | response | restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setItemAvailability | response | preparationMinutes | integer |  | (nullable)
FnbService | setItemAvailability | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setItemAvailability | response | unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | setItemAvailability | param (path) | itemId | string (uuid) | yes
FnbService | setItemAvailability | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setItemAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setKitchenSla | request | outletId | string (uuid) |  | The outlet, from the path. (read-only)
FnbService | setKitchenSla | request | targets | array of object
FnbService | setKitchenSla | request | targets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | setKitchenSla | request | targets[].targetMinutes | integer | yes | (min 1)
FnbService | setKitchenSla | request | targets[].warnAtPercent | integer |  | (default 80)
FnbService | setKitchenSla | request | priorityWeights | object |  | The weight of each signal the board names — age, promise time, table stage, a VIP marker.
FnbService | setKitchenSla | request | priorityWeights.age | integer |  | (min 0)
FnbService | setKitchenSla | request | priorityWeights.targetReadyAt | integer |  | Promise time. (min 0)
FnbService | setKitchenSla | request | priorityWeights.tableStage | integer |  | (min 0)
FnbService | setKitchenSla | request | priorityWeights.vip | integer |  | (min 0)
FnbService | setKitchenSla | response | outletId | string (uuid) |  | The outlet, from the path. (read-only)
FnbService | setKitchenSla | response | targets | array of object
FnbService | setKitchenSla | response | targets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | setKitchenSla | response | targets[].targetMinutes | integer | yes | (min 1)
FnbService | setKitchenSla | response | targets[].warnAtPercent | integer |  | (default 80)
FnbService | setKitchenSla | response | priorityWeights | object |  | The weight of each signal the board names — age, promise time, table stage, a VIP marker.
FnbService | setKitchenSla | response | priorityWeights.age | integer |  | (min 0)
FnbService | setKitchenSla | response | priorityWeights.targetReadyAt | integer |  | Promise time. (min 0)
FnbService | setKitchenSla | response | priorityWeights.tableStage | integer |  | (min 0)
FnbService | setKitchenSla | response | priorityWeights.vip | integer |  | (min 0)
FnbService | setKitchenSla | param (path) | outletId | string (uuid) | yes
FnbService | setKitchenSla | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setKitchenSla | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setKitchenTicketStatus | request | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | setKitchenTicketStatus | request | lineIds | array of string (uuid) |  | Advance specific lines.
FnbService | setKitchenTicketStatus | request | stationId | string (uuid)
FnbService | setKitchenTicketStatus | request | recordedAt | string (date-time) | yes
FnbService | setKitchenTicketStatus | response | id | string (uuid) | yes
FnbService | setKitchenTicketStatus | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | setKitchenTicketStatus | response | orderNumber | string
FnbService | setKitchenTicketStatus | response | outletId | string (uuid) | yes
FnbService | setKitchenTicketStatus | response | tableLabel | string |  | (nullable)
FnbService | setKitchenTicketStatus | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | setKitchenTicketStatus | response | coursing | object |  | BL-131. (nullable)
FnbService | setKitchenTicketStatus | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | setKitchenTicketStatus | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | setKitchenTicketStatus | response | priority | integer |  | Higher fires sooner.
FnbService | setKitchenTicketStatus | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | setKitchenTicketStatus | response | prioritiseReason | string |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines | array of object | yes
FnbService | setKitchenTicketStatus | response | lines[].lineId | string (uuid) | yes
FnbService | setKitchenTicketStatus | response | lines[].name | string | yes
FnbService | setKitchenTicketStatus | response | lines[].quantity | integer | yes
FnbService | setKitchenTicketStatus | response | lines[].modifiers | array of string
FnbService | setKitchenTicketStatus | response | lines[].note | string |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setKitchenTicketStatus | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | setKitchenTicketStatus | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | setKitchenTicketStatus | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | setKitchenTicketStatus | response | lines[].course | integer |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | setKitchenTicketStatus | response | createdAt | string (date-time) | yes
FnbService | setKitchenTicketStatus | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | setKitchenTicketStatus | response | elapsedSeconds | integer
FnbService | setKitchenTicketStatus | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | setKitchenTicketStatus | param (path) | ticketId | string (uuid) | yes
FnbService | setKitchenTicketStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setLanguages | request | languages | array of string | yes | (min items 1)
WhiteLabelService | setLanguages | request | defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | setLanguages | response | languages | array of string | yes | A tenant may add or select interface languages beyond English and Arabic (Chinmay, 2 October, workbook Q145; CHG-CSA-039).
WhiteLabelService | setLanguages | response | defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | setLanguages | response | uiStringCoverage | array of object |  | How complete the interface strings are in each enabled language (CHG-CSA-039). (read-only)
WhiteLabelService | setLanguages | response | uiStringCoverage[].language | string
WhiteLabelService | setLanguages | response | uiStringCoverage[].coveragePercent | number |  | (min 0; max 100)
WhiteLabelService | setLanguages | response | uiStringCoverage[].status | enum (complete, draft, missing)
WhiteLabelService | setLanguages | response | rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | setLanguages | response | translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | setLanguages | response | translationGaps[].language | string
WhiteLabelService | setLanguages | response | translationGaps[].missingCount | integer
WhiteLabelService | setLanguages | response | translationGaps[].areas | array of string |  | The kinds of the missing items, from the closed list contentPages, banners, promoBlocks, faqs, policies (ADAM CR-194).
WhiteLabelService | setLanguages | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setLeaderboardNickname | request | nickname | string | yes | (min length 2; max length 24; pattern ^[\p{L}\p{N}][\p{L}\p{N} _.-]{0,22}[\p{L}\p{N}]$)
MarketingService | setLeaderboardNickname | response | leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | setLeaderboardNickname | response | subjectId | string (uuid) | yes
MarketingService | setLeaderboardNickname | response | programmeId | string (uuid) | yes
MarketingService | setLeaderboardNickname | response | pointsBalance | integer | yes
MarketingService | setLeaderboardNickname | response | lifetimePoints | integer
MarketingService | setLeaderboardNickname | response | tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | setLeaderboardNickname | response | tierCode | string | yes
MarketingService | setLeaderboardNickname | response | tierName | string
MarketingService | setLeaderboardNickname | response | pointsToNextTier | integer |  | (nullable)
MarketingService | setLeaderboardNickname | response | nextExpiryPoints | integer |  | (nullable)
MarketingService | setLeaderboardNickname | response | nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | setLeaderboardNickname | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setLoyaltyRules | request | programmeId | string (uuid) | yes
MarketingService | setLoyaltyRules | request | campaignRules | array of MarketingLoyaltyRule |  | Bonus, multiplier and condition rules, each scoped to a campaign window.
MarketingService | setLoyaltyRules | request | campaignRules[].id | string (uuid)
MarketingService | setLoyaltyRules | request | campaignRules[].campaignId | string (uuid) | yes
MarketingService | setLoyaltyRules | request | campaignRules[].type | string | yes | (max length 30)
MarketingService | setLoyaltyRules | request | campaignRules[].pointsEarningRuleId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].rewardId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].bonusPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].multiplier | number |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].conditionsJson | string |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | request | tiers | array of MarketingProgrammeTier |  | The programme's tiers, in rank order.
MarketingService | setLoyaltyRules | request | tiers[].id | string (uuid) |  | (read-only)
MarketingService | setLoyaltyRules | request | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | setLoyaltyRules | request | tiers[].code | string | yes | (max length 40)
MarketingService | setLoyaltyRules | request | tiers[].name | string | yes | (max length 120)
MarketingService | setLoyaltyRules | request | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | setLoyaltyRules | request | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | setLoyaltyRules | request | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].isActive | boolean |  | (default True)
MarketingService | setLoyaltyRules | request | redemptionRules | array of MarketingPointsRedemptionRule
MarketingService | setLoyaltyRules | request | redemptionRules[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | setLoyaltyRules | request | redemptionRules[].id | string (uuid)
MarketingService | setLoyaltyRules | request | redemptionRules[].loyaltyProgramId | string (uuid) | yes
MarketingService | setLoyaltyRules | request | redemptionRules[].pointRedemptionRuleCode | string | yes | (max length 100)
MarketingService | setLoyaltyRules | request | redemptionRules[].name | string | yes | (max length 200)
MarketingService | setLoyaltyRules | request | redemptionRules[].redemptionType | string | yes | (max length 30)
MarketingService | setLoyaltyRules | request | redemptionRules[].required | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].monetaryValue | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].minimumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].maximumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].productId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].validFrom | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].validTo | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | response | programmeId | string (uuid) | yes
MarketingService | setLoyaltyRules | response | campaignRules | array of MarketingLoyaltyRule |  | Bonus, multiplier and condition rules, each scoped to a campaign window.
MarketingService | setLoyaltyRules | response | campaignRules[].id | string (uuid)
MarketingService | setLoyaltyRules | response | campaignRules[].campaignId | string (uuid) | yes
MarketingService | setLoyaltyRules | response | campaignRules[].type | string | yes | (max length 30)
MarketingService | setLoyaltyRules | response | campaignRules[].pointsEarningRuleId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].rewardId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].bonusPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].multiplier | number |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].conditionsJson | string |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | response | tiers | array of MarketingProgrammeTier |  | The programme's tiers, in rank order.
MarketingService | setLoyaltyRules | response | tiers[].id | string (uuid) |  | (read-only)
MarketingService | setLoyaltyRules | response | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | setLoyaltyRules | response | tiers[].code | string | yes | (max length 40)
MarketingService | setLoyaltyRules | response | tiers[].name | string | yes | (max length 120)
MarketingService | setLoyaltyRules | response | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | setLoyaltyRules | response | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | setLoyaltyRules | response | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].isActive | boolean |  | (default True)
MarketingService | setLoyaltyRules | response | redemptionRules | array of MarketingPointsRedemptionRule
MarketingService | setLoyaltyRules | response | redemptionRules[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | setLoyaltyRules | response | redemptionRules[].id | string (uuid)
MarketingService | setLoyaltyRules | response | redemptionRules[].loyaltyProgramId | string (uuid) | yes
MarketingService | setLoyaltyRules | response | redemptionRules[].pointRedemptionRuleCode | string | yes | (max length 100)
MarketingService | setLoyaltyRules | response | redemptionRules[].name | string | yes | (max length 200)
MarketingService | setLoyaltyRules | response | redemptionRules[].redemptionType | string | yes | (max length 30)
MarketingService | setLoyaltyRules | response | redemptionRules[].required | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].monetaryValue | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].minimumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].maximumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].productId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].validFrom | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].validTo | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | param (path) | programmeId | string (uuid) | yes
MarketingService | setLoyaltyRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setMaintenanceMode | request | isInMaintenance | boolean | yes
WhiteLabelService | setMaintenanceMode | request | message | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | request | expectedBackAt | string (date-time)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.storeUrl | object |  | The store page of the tenant's app for each platform. (nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.storeUrl.ios | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.storeUrl.android | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | setMaintenanceMode | request | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.phone | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.email | string (email) |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.whatsapp | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.address | object |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | setMaintenanceMode | request | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | setMaintenanceMode | request | availabilityMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | response | tenantId | string (uuid) | yes
WhiteLabelService | setMaintenanceMode | response | isPublished | boolean | yes | True once any version has been published.
WhiteLabelService | setMaintenanceMode | response | darkAppModules | array of string |  | The app-modules switched off for this tenant (ADAM CR-164, option A, 18 October 2026; CHG-CRA-005): their keys (for example AM-MARKETING-CRM-P01), from the tenant's release flags. (read-only)
WhiteLabelService | setMaintenanceMode | response | publishedVersion | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | publishedAt | string (date-time) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | draftVersion | string |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | hasUnpublishedChanges | boolean |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | activeModuleCount | integer |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | licensedModuleCount | integer |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | activePageCount | integer |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | isInMaintenance | boolean | yes
WhiteLabelService | setMaintenanceMode | response | maintenanceMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.storeUrl | object |  | The store page of the tenant's app for each platform. (nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.storeUrl.ios | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.storeUrl.android | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | setMaintenanceMode | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.phone | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.address | object |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | setMaintenanceMode | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | setMaintenanceMode | response | availabilityMessage | object |  | What the sold-out or closed screen says (WEB-029). (nullable)
WhiteLabelService | setMaintenanceMode | response | venues | array of object |  | Public: the venues a guest can pick (decided 28 September, audit R267; schema named 29 September, readiness close-out, our build plan). (max items 200)
WhiteLabelService | setMaintenanceMode | response | venues[].venueId | string (uuid) | yes | The venue's scope node (tenancy.OrgUnit.id, level venue): what every guest screen that declares venueId from: session reads once the guest picks it.
WhiteLabelService | setMaintenanceMode | response | venues[].name | string | yes | The venue's name (tenancy.OrgUnit.name). (max length 200)
WhiteLabelService | setMaintenanceMode | response | venues[].contact | object |  | The venue's own contact (address, phone, email), from the venue's settings (tenancy.VenueSettings, read through venueSettingsRecords). (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].contact.phone | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].contact.email | string (email) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].contact.whatsapp | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].contact.address | object |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].city | string |  | Shown under the name so two venues with similar names can be told apart. (max length 120; nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].openingHoursToday | object |  | Today's opening hours in the venue's time zone, from tenancy.VenueSettings opening hours. (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].openingHoursToday.opens | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | setMaintenanceMode | response | venues[].openingHoursToday.closes | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | setMaintenanceMode | response | whatsNew | array of object |  | Public: the guest "what's new" (decided 29 September, rev 3 GAP-B2). (max items 10)
WhiteLabelService | setMaintenanceMode | response | whatsNew[].version | string | yes | The release version.
WhiteLabelService | setMaintenanceMode | response | whatsNew[].publishedAt | string (date-time) | yes | When the release reached the tenant's cell.
WhiteLabelService | setMaintenanceMode | response | whatsNew[].notes | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | response | recentChanges | array of object |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | recentChanges[].area | string
WhiteLabelService | setMaintenanceMode | response | recentChanges[].description | string
WhiteLabelService | setMaintenanceMode | response | recentChanges[].principalId | string (uuid)
WhiteLabelService | setMaintenanceMode | response | recentChanges[].at | string (date-time)
WhiteLabelService | setMaintenanceMode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setMarketingSubscription | request | id | string (uuid) | yes | (read-only)
MarketingService | setMarketingSubscription | request | subjectId | string (uuid) | yes | The guest — from the guest session, or from unsubscribeToken when there is no session. (read-only)
MarketingService | setMarketingSubscription | request | channel | enum (email, sms, push) | yes
MarketingService | setMarketingSubscription | request | listName | string | yes
MarketingService | setMarketingSubscription | request | isSubscribed | boolean | yes
MarketingService | setMarketingSubscription | request | source | string |  | Where the opt-in happened, because a regulator asks.
MarketingService | setMarketingSubscription | request | unsubscribeToken | string |  | Unsubscribe must work without a login.
MarketingService | setMarketingSubscription | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setMarketingSubscription | response | id | string (uuid) | yes | (read-only)
MarketingService | setMarketingSubscription | response | subjectId | string (uuid) | yes | The guest — from the guest session, or from unsubscribeToken when there is no session. (read-only)
MarketingService | setMarketingSubscription | response | channel | enum (email, sms, push) | yes
MarketingService | setMarketingSubscription | response | listName | string | yes
MarketingService | setMarketingSubscription | response | isSubscribed | boolean | yes
MarketingService | setMarketingSubscription | response | source | string |  | Where the opt-in happened, because a regulator asks.
MarketingService | setMarketingSubscription | response | unsubscribeToken | string |  | Unsubscribe must work without a login.
MarketingService | setMarketingSubscription | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setMarketingSubscription | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setMenuItemDailyCount | request | count | integer | yes | Portions for today. (min 0; nullable)
FnbService | setMenuItemDailyCount | response | id | string (uuid) | yes
FnbService | setMenuItemDailyCount | response | productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | setMenuItemDailyCount | response | name | string | yes
FnbService | setMenuItemDailyCount | response | description | string |  | (nullable)
FnbService | setMenuItemDailyCount | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setMenuItemDailyCount | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setMenuItemDailyCount | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setMenuItemDailyCount | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setMenuItemDailyCount | response | dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | setMenuItemDailyCount | response | remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | setMenuItemDailyCount | response | sortOrder | integer
FnbService | setMenuItemDailyCount | response | modifierGroupIds | array of string (uuid)
FnbService | setMenuItemDailyCount | response | stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | setMenuItemDailyCount | response | menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | setMenuItemDailyCount | response | isStockTracked | boolean |  | True where a recipe exists.
FnbService | setMenuItemDailyCount | response | isAvailable | boolean | yes
FnbService | setMenuItemDailyCount | response | unavailableReason | string |  | (nullable)
FnbService | setMenuItemDailyCount | response | restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setMenuItemDailyCount | response | preparationMinutes | integer |  | (nullable)
FnbService | setMenuItemDailyCount | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setMenuItemDailyCount | response | unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | setMenuItemDailyCount | param (path) | itemId | string (uuid) | yes
FnbService | setMenuItemDailyCount | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setMenuItemDailyCount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setMenuSections | request | sections | array of MenuSection | yes
FnbService | setMenuSections | request | sections[].id | string (uuid) |  | (read-only)
FnbService | setMenuSections | request | sections[].code | string | yes
FnbService | setMenuSections | request | sections[].name | string | yes
FnbService | setMenuSections | request | sections[].sortOrder | integer | yes
FnbService | setMenuSections | request | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | setMenuSections | request | sections[].items[].id | string (uuid) | yes
FnbService | setMenuSections | request | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | setMenuSections | request | sections[].items[].name | string | yes
FnbService | setMenuSections | request | sections[].items[].description | string |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setMenuSections | request | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | setMenuSections | request | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | setMenuSections | request | sections[].items[].sortOrder | integer
FnbService | setMenuSections | request | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | setMenuSections | request | sections[].items[].stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | setMenuSections | request | sections[].items[].menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | setMenuSections | request | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | setMenuSections | request | sections[].items[].isAvailable | boolean | yes
FnbService | setMenuSections | request | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setMenuSections | request | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setMenuSections | request | sections[].items[].unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | setMenuSections | response | id | string (uuid) | yes
FnbService | setMenuSections | response | code | string | yes | (max length 64)
FnbService | setMenuSections | response | name | string | yes | (max length 200)
FnbService | setMenuSections | response | outletId | string (uuid) | yes
FnbService | setMenuSections | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | setMenuSections | response | availability.daysOfWeek | array of integer
FnbService | setMenuSections | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | setMenuSections | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | setMenuSections | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | setMenuSections | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | setMenuSections | response | sections | array of MenuSection
FnbService | setMenuSections | response | sections[].id | string (uuid) |  | (read-only)
FnbService | setMenuSections | response | sections[].code | string | yes
FnbService | setMenuSections | response | sections[].name | string | yes
FnbService | setMenuSections | response | sections[].sortOrder | integer | yes
FnbService | setMenuSections | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | setMenuSections | response | sections[].items[].id | string (uuid) | yes
FnbService | setMenuSections | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | setMenuSections | response | sections[].items[].name | string | yes
FnbService | setMenuSections | response | sections[].items[].description | string |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setMenuSections | response | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | setMenuSections | response | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | setMenuSections | response | sections[].items[].sortOrder | integer
FnbService | setMenuSections | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | setMenuSections | response | sections[].items[].stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | setMenuSections | response | sections[].items[].menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | setMenuSections | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | setMenuSections | response | sections[].items[].isAvailable | boolean | yes
FnbService | setMenuSections | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setMenuSections | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setMenuSections | response | sections[].items[].unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | setMenuSections | response | isActive | boolean | yes
FnbService | setMenuSections | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | setMenuSections | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | setMenuSections | param (path) | menuId | string (uuid) | yes
FnbService | setMenuSections | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setMenuSections | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setModuleEnablement | request | modules | array of object | yes
WhiteLabelService | setModuleEnablement | request | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | setModuleEnablement | request | modules[].isEnabled | boolean | yes
WhiteLabelService | setModuleEnablement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setModuleEnablement | param (header) | X-Tenant-Id | string (uuid) |  | Which tenant a call acts in, where one cell holds many tenant databases (ADR-0038; R8 blocker fix, APPROVALS-TENANCY-C44).
PlatformService | setModuleListing | request | currencyCode | string |  | The ISO 4217 currency of the module's price (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored with its currency on the row, since a plat… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | setModuleListing | request | moduleCode | string | yes | Values are ModuleKeys (4 October 2026, CHG-FXC-010; ADM-424): the vocabulary of white-label.ModuleEnablement.moduleKey, so a dependency is checked against what setModuleEnablement switches.
PlatformService | setModuleListing | request | name | string
PlatformService | setModuleListing | request | description | string |  | (nullable)
PlatformService | setModuleListing | request | category | string |  | (nullable)
PlatformService | setModuleListing | request | requiresModules | array of string |  | Values are ModuleKeys (4 October 2026, CHG-FXC-010; ADM-424): the vocabulary of white-label.ModuleEnablement.moduleKey, so a dependency is checked against what setModuleEnablement switches.
PlatformService | setModuleListing | request | incompatibleWithModules | array of string |  | Values are ModuleKeys (4 October 2026, CHG-FXC-010; ADM-424): the vocabulary of white-label.ModuleEnablement.moduleKey, so a dependency is checked against what setModuleEnablement switches.
PlatformService | setModuleListing | request | includedInTiers | array of string
PlatformService | setModuleListing | request | price | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | setModuleListing | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | setModuleListing | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | setModuleListing | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | setModuleListing | request | pricingBasis | enum (included, flatFee, perVenue, perUnit, revenueShare, metered)
PlatformService | setModuleListing | request | meteredMetric | object |  | For metered, what is counted (aiTokens for the AI module). (nullable)
PlatformService | setModuleListing | request | meteredUnitSize | integer |  | For metered, how many units price buys (e.g. (min 1; nullable)
PlatformService | setModuleListing | request | provisioningMinutes | integer |  | (nullable)
PlatformService | setModuleListing | request | requiresProfessionalServices | boolean |  | (default False)
PlatformService | setModuleListing | request | status | enum (available, beta, deprecated, withdrawn)
PlatformService | setModuleListing | response | currencyCode | string |  | The ISO 4217 currency of the module's price (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored with its currency on the row, since a plat… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | setModuleListing | response | moduleCode | string | yes | Values are ModuleKeys (4 October 2026, CHG-FXC-010; ADM-424): the vocabulary of white-label.ModuleEnablement.moduleKey, so a dependency is checked against what setModuleEnablement switches.
PlatformService | setModuleListing | response | name | string
PlatformService | setModuleListing | response | description | string |  | (nullable)
PlatformService | setModuleListing | response | category | string |  | (nullable)
PlatformService | setModuleListing | response | requiresModules | array of string |  | Values are ModuleKeys (4 October 2026, CHG-FXC-010; ADM-424): the vocabulary of white-label.ModuleEnablement.moduleKey, so a dependency is checked against what setModuleEnablement switches.
PlatformService | setModuleListing | response | incompatibleWithModules | array of string |  | Values are ModuleKeys (4 October 2026, CHG-FXC-010; ADM-424): the vocabulary of white-label.ModuleEnablement.moduleKey, so a dependency is checked against what setModuleEnablement switches.
PlatformService | setModuleListing | response | includedInTiers | array of string
PlatformService | setModuleListing | response | price | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | setModuleListing | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | setModuleListing | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | setModuleListing | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | setModuleListing | response | pricingBasis | enum (included, flatFee, perVenue, perUnit, revenueShare, metered)
PlatformService | setModuleListing | response | meteredMetric | object |  | For metered, what is counted (aiTokens for the AI module). (nullable)
PlatformService | setModuleListing | response | meteredUnitSize | integer |  | For metered, how many units price buys (e.g. (min 1; nullable)
PlatformService | setModuleListing | response | provisioningMinutes | integer |  | (nullable)
PlatformService | setModuleListing | response | requiresProfessionalServices | boolean |  | (default False)
PlatformService | setModuleListing | response | status | enum (available, beta, deprecated, withdrawn)
PlatformService | setModuleListing | param (path) | moduleCode | string | yes | Addresses the item this write creates or replaces.
PlatformService | setModuleListing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setNavigation | request | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | request | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | setNavigation | request | items | array of object | yes | (max items 12)
WhiteLabelService | setNavigation | request | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | request | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | request | items[].icon | string
WhiteLabelService | setNavigation | request | items[].target | LinkTarget | yes
WhiteLabelService | setNavigation | request | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | setNavigation | request | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | setNavigation | request | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | setNavigation | request | items[].target.contentPageId | string (uuid)
WhiteLabelService | setNavigation | request | items[].target.productId | string (uuid)
WhiteLabelService | setNavigation | request | items[].target.eventId | string (uuid)
WhiteLabelService | setNavigation | request | items[].target.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | setNavigation | request | items[].target.url | string
WhiteLabelService | setNavigation | request | items[].isVisible | boolean | yes | At most five may be visible when kind is bottomNavigation; the rest overflow.
WhiteLabelService | setNavigation | request | items[].sortOrder | integer | yes
WhiteLabelService | setNavigation | request | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | setNavigation | request | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | setNavigation | request | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | response | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | setNavigation | response | items | array of object | yes | (max items 12)
WhiteLabelService | setNavigation | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | response | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | response | items[].icon | string
WhiteLabelService | setNavigation | response | items[].target | LinkTarget | yes
WhiteLabelService | setNavigation | response | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | setNavigation | response | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | setNavigation | response | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | setNavigation | response | items[].target.contentPageId | string (uuid)
WhiteLabelService | setNavigation | response | items[].target.productId | string (uuid)
WhiteLabelService | setNavigation | response | items[].target.eventId | string (uuid)
WhiteLabelService | setNavigation | response | items[].target.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | setNavigation | response | items[].target.url | string
WhiteLabelService | setNavigation | response | items[].isVisible | boolean | yes | At most five may be visible when kind is bottomNavigation; the rest overflow.
WhiteLabelService | setNavigation | response | items[].sortOrder | integer | yes
WhiteLabelService | setNavigation | response | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | setNavigation | response | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | setNavigation | response | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setNavigation | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
AccessService | setParkingFacility | request | id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | setParkingFacility | request | name | string | yes
AccessService | setParkingFacility | request | venueId | string (uuid) | yes
AccessService | setParkingFacility | request | mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | setParkingFacility | request | capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | setParkingFacility | request | takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | setParkingFacility | request | vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | setParkingFacility | request | vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | request | endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | request | credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | setParkingFacility | request | pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | request | accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | setParkingFacility | request | isActive | boolean
AccessService | setParkingFacility | request | productVariantId | string (uuid) |  | The catalogue variant sold for parking here (4 October 2026, CHG-FXC-010; GST-027, WEB-041): what addCartLine sells when a guest buys parking at this car park. (nullable)
AccessService | setParkingFacility | response | id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | setParkingFacility | response | name | string | yes
AccessService | setParkingFacility | response | venueId | string (uuid) | yes
AccessService | setParkingFacility | response | mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | setParkingFacility | response | capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | setParkingFacility | response | takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | setParkingFacility | response | vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | setParkingFacility | response | vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | response | endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | response | credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | setParkingFacility | response | pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | response | accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | setParkingFacility | response | isActive | boolean
AccessService | setParkingFacility | response | productVariantId | string (uuid) |  | The catalogue variant sold for parking here (4 October 2026, CHG-FXC-010; GST-027, WEB-041): what addCartLine sells when a guest buys parking at this car park. (nullable)
AccessService | setParkingFacility | param (path) | parkingFacilityId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
AccessService | setParkingFacility | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | setPasswordPolicy | request | id | string (uuid) | yes | Assigned by the server. (read-only)
IdentityService | setPasswordPolicy | request | scopePath | string | yes | The partition key (ADR-0005), written by the server from the caller's tenant (x-ticvai-config-scope: tenant). (read-only)
IdentityService | setPasswordPolicy | request | minLength | integer | yes | A tenant may raise the length and never set it below 8 (decided 28 September, audit R126 (7)). (min 8; default 12)
IdentityService | setPasswordPolicy | request | requireBreachCheck | boolean |  | The single most effective rule. (default True)
IdentityService | setPasswordPolicy | request | maxAgeDays | integer |  | Null is the recommended value. (nullable)
IdentityService | setPasswordPolicy | request | recoveryMethods | array of enum (email, sms, securityQuestions, inPersonVerification, supportAssisted) |  | BL-132.
IdentityService | setPasswordPolicy | request | maxConcurrentSessions | integer |  | BL-145. (nullable)
IdentityService | setPasswordPolicy | request | deviceRestriction | object |  | BL-146. (nullable)
IdentityService | setPasswordPolicy | request | deviceRestriction.allowedIpRanges | array of string
IdentityService | setPasswordPolicy | request | deviceRestriction.allowedCountries | array of string
IdentityService | setPasswordPolicy | request | deviceRestriction.requireRegisteredDevice | boolean |  | (default False)
IdentityService | setPasswordPolicy | request | deviceRestriction.onViolation | enum (warn, requireStepUp, block) |  | (default requireStepUp)
IdentityService | setPasswordPolicy | request | lockoutAfterAttempts | integer |  | Wrong passwords before a staff password is locked for lockoutMinutes, counted in PrincipalCredential.failedAttempts (14 October 2026, CHG-CRD-001). (default 10)
IdentityService | setPasswordPolicy | request | lockoutMinutes | integer |  | A temporary lockout, not a permanent one. (default 15)
IdentityService | setPasswordPolicy | request | forceChangeOnFirstLogon | boolean |  | (default True)
IdentityService | setPasswordPolicy | request | reusePreventionCount | integer |  | How many previous passwords a staff member may not reuse — the last 5 unless the tenant sets another (decided 28 September, audit R132). (min 0; max 24; default 5)
IdentityService | setPasswordPolicy | request | pinLength | enum (4, 6, 8) |  | How many digits a staff PIN has, chosen by the tenant from a drop-down (decided by Chinmay, 14 October 2026, ADAM CR-078: "Give those as options that they select as a drop down"; CHG-CRD-002). (default 4)
IdentityService | setPasswordPolicy | request | pinReusePrevention | enum (none, last3, last5) |  | Whether a new PIN may repeat an old one, chosen by the tenant from a drop-down (decided by Chinmay, 14 October 2026, ADAM CR-078; CHG-CRD-002): none lets a PIN be reused, last3 and last5 refuse the c… (default last5)
IdentityService | setPasswordPolicy | request | pinLockoutAfterAttempts | enum (3, 5, 10) |  | Wrong PINs before the PIN is locked, chosen by the tenant from a drop-down (decided by Chinmay, 14 October 2026, ADAM CR-078; CHG-CRD-002). (default 5)
IdentityService | setPasswordPolicy | request | mfaRequiredForPermissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | Step-up rather than blanket MFA. (default ['ROLE_MANAGE', 'LEDGER_APPROVE', 'PLATFORM_TENANT_VIEW', 'PLATFORM_TENANT_MANAGE', 'PLATFORM_TENANT_TERMINATE', 'PLATFORM_TENANT_ACCESS', 'PLATFORM_PLAN_MANAGE', 'PLATFORM_CELL_VIEW', 'PLATFORM_CELL_MANAGE', 'PLATFORM_BILLING_VIEW', 'PLATFORM_BILLING_MANAGE', 'PLATFORM_RELEASE_VIEW', 'PLATFORM_RELEASE_MANAGE', 'PLATFORM_RELEASE_PROMOTE', 'PLATFORM_MIGRATION_VIEW', 'PLATFORM_MIGRATION_APPLY', 'PLATFORM_AI_MANAGE'])
IdentityService | setPasswordPolicy | request | accessTokenMinutes | integer |  | How long a staff access token lives (TokenPair.expiresIn). (min 5; max 60; default 15)
IdentityService | setPasswordPolicy | request | refreshTokenHours | integer |  | How long a staff refresh token lives without use. (min 1; max 24; default 12)
IdentityService | setPasswordPolicy | request | sessionMaxHours | integer |  | The longest a staff session lives (Session.expiresAt). (min 1; max 24; default 12)
IdentityService | setPasswordPolicy | response | id | string (uuid) | yes | Assigned by the server. (read-only)
IdentityService | setPasswordPolicy | response | scopePath | string | yes | The partition key (ADR-0005), written by the server from the caller's tenant (x-ticvai-config-scope: tenant). (read-only)
IdentityService | setPasswordPolicy | response | minLength | integer | yes | A tenant may raise the length and never set it below 8 (decided 28 September, audit R126 (7)). (min 8; default 12)
IdentityService | setPasswordPolicy | response | requireBreachCheck | boolean |  | The single most effective rule. (default True)
IdentityService | setPasswordPolicy | response | maxAgeDays | integer |  | Null is the recommended value. (nullable)
IdentityService | setPasswordPolicy | response | recoveryMethods | array of enum (email, sms, securityQuestions, inPersonVerification, supportAssisted) |  | BL-132.
IdentityService | setPasswordPolicy | response | maxConcurrentSessions | integer |  | BL-145. (nullable)
IdentityService | setPasswordPolicy | response | deviceRestriction | object |  | BL-146. (nullable)
IdentityService | setPasswordPolicy | response | deviceRestriction.allowedIpRanges | array of string
IdentityService | setPasswordPolicy | response | deviceRestriction.allowedCountries | array of string
IdentityService | setPasswordPolicy | response | deviceRestriction.requireRegisteredDevice | boolean |  | (default False)
IdentityService | setPasswordPolicy | response | deviceRestriction.onViolation | enum (warn, requireStepUp, block) |  | (default requireStepUp)
IdentityService | setPasswordPolicy | response | lockoutAfterAttempts | integer |  | Wrong passwords before a staff password is locked for lockoutMinutes, counted in PrincipalCredential.failedAttempts (14 October 2026, CHG-CRD-001). (default 10)
IdentityService | setPasswordPolicy | response | lockoutMinutes | integer |  | A temporary lockout, not a permanent one. (default 15)
IdentityService | setPasswordPolicy | response | forceChangeOnFirstLogon | boolean |  | (default True)
IdentityService | setPasswordPolicy | response | reusePreventionCount | integer |  | How many previous passwords a staff member may not reuse — the last 5 unless the tenant sets another (decided 28 September, audit R132). (min 0; max 24; default 5)
IdentityService | setPasswordPolicy | response | pinLength | enum (4, 6, 8) |  | How many digits a staff PIN has, chosen by the tenant from a drop-down (decided by Chinmay, 14 October 2026, ADAM CR-078: "Give those as options that they select as a drop down"; CHG-CRD-002). (default 4)
IdentityService | setPasswordPolicy | response | pinReusePrevention | enum (none, last3, last5) |  | Whether a new PIN may repeat an old one, chosen by the tenant from a drop-down (decided by Chinmay, 14 October 2026, ADAM CR-078; CHG-CRD-002): none lets a PIN be reused, last3 and last5 refuse the c… (default last5)
IdentityService | setPasswordPolicy | response | pinLockoutAfterAttempts | enum (3, 5, 10) |  | Wrong PINs before the PIN is locked, chosen by the tenant from a drop-down (decided by Chinmay, 14 October 2026, ADAM CR-078; CHG-CRD-002). (default 5)
IdentityService | setPasswordPolicy | response | mfaRequiredForPermissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | Step-up rather than blanket MFA. (default ['ROLE_MANAGE', 'LEDGER_APPROVE', 'PLATFORM_TENANT_VIEW', 'PLATFORM_TENANT_MANAGE', 'PLATFORM_TENANT_TERMINATE', 'PLATFORM_TENANT_ACCESS', 'PLATFORM_PLAN_MANAGE', 'PLATFORM_CELL_VIEW', 'PLATFORM_CELL_MANAGE', 'PLATFORM_BILLING_VIEW', 'PLATFORM_BILLING_MANAGE', 'PLATFORM_RELEASE_VIEW', 'PLATFORM_RELEASE_MANAGE', 'PLATFORM_RELEASE_PROMOTE', 'PLATFORM_MIGRATION_VIEW', 'PLATFORM_MIGRATION_APPLY', 'PLATFORM_AI_MANAGE'])
IdentityService | setPasswordPolicy | response | accessTokenMinutes | integer |  | How long a staff access token lives (TokenPair.expiresIn). (min 5; max 60; default 15)
IdentityService | setPasswordPolicy | response | refreshTokenHours | integer |  | How long a staff refresh token lives without use. (min 1; max 24; default 12)
IdentityService | setPasswordPolicy | response | sessionMaxHours | integer |  | The longest a staff session lives (Session.expiresAt). (min 1; max 24; default 12)
IdentityService | setPasswordPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setPaymentProvider | request | id | string (uuid) | yes
OrderService | setPaymentProvider | request | name | string | yes
OrderService | setPaymentProvider | request | kind | enum (networkInternational, stripe, adyen, checkout, cash, wallet, other) | yes
OrderService | setPaymentProvider | request | supportedMethods | array of enum (card, applePay, googlePay, samsungPay, wallet, bankTransfer, cash, bnpl)
OrderService | setPaymentProvider | request | supportedCurrencies | array of string
OrderService | setPaymentProvider | request | supportsTokenisation | boolean |  | The keystone.
OrderService | setPaymentProvider | request | supportsPartialCapture | boolean |  | (default True)
OrderService | setPaymentProvider | request | acceptedOnChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | BL-115.
OrderService | setPaymentProvider | request | presentmentCurrencies | array of string |  | BL-070.
OrderService | setPaymentProvider | request | supports3ds | boolean |  | (default True)
OrderService | setPaymentProvider | request | terminal | object |  | BL-119. (nullable)
OrderService | setPaymentProvider | request | terminal.emvCertificationRef | string |  | (nullable)
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit | object |  | What a terminal may approve with no connection.
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setPaymentProvider | request | terminal.supportsOfflineApproval | boolean |  | (default False)
OrderService | setPaymentProvider | request | terminal.receiptSignatureRequired | boolean |  | (default False)
OrderService | setPaymentProvider | request | terminal.supportsTipOnTerminal | boolean |  | (default False)
OrderService | setPaymentProvider | request | credentialRef | string |  | A vault reference.
OrderService | setPaymentProvider | request | scopeLevel | enum (tenant, region, venue)
OrderService | setPaymentProvider | request | scopePath | string
OrderService | setPaymentProvider | request | isActive | boolean | yes
OrderService | setPaymentProvider | request | routing | array of PaymentRouting |  | The ordered rules that send payments to this provider.
OrderService | setPaymentProvider | request | routing[].id | string (uuid) | yes
OrderService | setPaymentProvider | request | routing[].priority | integer | yes
OrderService | setPaymentProvider | request | routing[].providerId | string (uuid) | yes
OrderService | setPaymentProvider | request | routing[].conditions | object |  | Match on what is known before the charge — channel, currency, method, issuer country, amount band.
OrderService | setPaymentProvider | request | routing[].conditions.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
OrderService | setPaymentProvider | request | routing[].conditions.currency | string |  | Resolved from the region, not stored (ADR-0018, 24 August). (nullable)
OrderService | setPaymentProvider | request | routing[].conditions.method | string |  | (nullable)
OrderService | setPaymentProvider | request | routing[].conditions.issuerCountry | string |  | (nullable)
OrderService | setPaymentProvider | request | routing[].conditions.minAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setPaymentProvider | request | routing[].conditions.maxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setPaymentProvider | request | routing[].fallbackProviderId | string (uuid) |  | Where this provider declines or is unreachable. (nullable)
OrderService | setPaymentProvider | request | routing[].scopePath | string |  | The partition key (ADR-0005).
OrderService | setPaymentProvider | response | id | string (uuid) | yes
OrderService | setPaymentProvider | response | name | string | yes
OrderService | setPaymentProvider | response | kind | enum (networkInternational, stripe, adyen, checkout, cash, wallet, other) | yes
OrderService | setPaymentProvider | response | supportedMethods | array of enum (card, applePay, googlePay, samsungPay, wallet, bankTransfer, cash, bnpl)
OrderService | setPaymentProvider | response | supportedCurrencies | array of string
OrderService | setPaymentProvider | response | supportsTokenisation | boolean |  | The keystone.
OrderService | setPaymentProvider | response | supportsPartialCapture | boolean |  | (default True)
OrderService | setPaymentProvider | response | acceptedOnChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | BL-115.
OrderService | setPaymentProvider | response | presentmentCurrencies | array of string |  | BL-070.
OrderService | setPaymentProvider | response | supports3ds | boolean |  | (default True)
OrderService | setPaymentProvider | response | terminal | object |  | BL-119. (nullable)
OrderService | setPaymentProvider | response | terminal.emvCertificationRef | string |  | (nullable)
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit | object |  | What a terminal may approve with no connection.
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setPaymentProvider | response | terminal.supportsOfflineApproval | boolean |  | (default False)
OrderService | setPaymentProvider | response | terminal.receiptSignatureRequired | boolean |  | (default False)
OrderService | setPaymentProvider | response | terminal.supportsTipOnTerminal | boolean |  | (default False)
OrderService | setPaymentProvider | response | credentialRef | string |  | A vault reference.
OrderService | setPaymentProvider | response | scopeLevel | enum (tenant, region, venue)
OrderService | setPaymentProvider | response | scopePath | string
OrderService | setPaymentProvider | response | isActive | boolean | yes
OrderService | setPaymentProvider | param (path) | providerId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
OrderService | setPaymentProvider | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setPaymentProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setPlacedResource | request | id | string (uuid) | yes | (read-only)
VenueOpsService | setPlacedResource | request | mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | setPlacedResource | request | resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | setPlacedResource | request | label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | setPlacedResource | request | kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | setPlacedResource | request | zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | setPlacedResource | request | capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | setPlacedResource | request | priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | setPlacedResource | request | variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | setPlacedResource | request | position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | setPlacedResource | request | position.x | number | yes
VenueOpsService | setPlacedResource | request | position.y | number | yes
VenueOpsService | setPlacedResource | request | boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | setPlacedResource | request | boundary[].x | number
VenueOpsService | setPlacedResource | request | boundary[].y | number
VenueOpsService | setPlacedResource | request | isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | setPlacedResource | request | placedResourceId | string (uuid) |  | The placed resource to amend. (nullable)
VenueOpsService | setPlacedResource | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setPlacedResource | response | mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | setPlacedResource | response | resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | setPlacedResource | response | label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | setPlacedResource | response | kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | setPlacedResource | response | zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | setPlacedResource | response | capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | setPlacedResource | response | priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | setPlacedResource | response | variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | setPlacedResource | response | position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | setPlacedResource | response | position.x | number | yes
VenueOpsService | setPlacedResource | response | position.y | number | yes
VenueOpsService | setPlacedResource | response | boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | setPlacedResource | response | boundary[].x | number
VenueOpsService | setPlacedResource | response | boundary[].y | number
VenueOpsService | setPlacedResource | response | isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | setPlacedResource | param (path) | mapId | string (uuid) | yes
VenueOpsService | setPlacedResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setPolicy | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | setPolicy | request | requiresReconsent | boolean | yes | True prompts existing guests to consent again on next launch.
WhiteLabelService | setPolicy | request | effectiveFrom | string (date)
WhiteLabelService | setPolicy | response | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) | yes | The kinds of policy a tenant publishes.
WhiteLabelService | setPolicy | response | title | string |  | Not written by anyone: setPolicy takes no title and the column stays null. (read-only; nullable)
WhiteLabelService | setPolicy | response | version | string | yes | Immutable.
WhiteLabelService | setPolicy | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | setPolicy | response | requiresReconsent | boolean
WhiteLabelService | setPolicy | response | effectiveFrom | string (date) | yes
WhiteLabelService | setPolicy | response | publishedByPrincipalId | string (uuid)
WhiteLabelService | setPolicy | response | publishedAt | string (date-time) | yes
WhiteLabelService | setPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setPolicy | param (path) | policyKind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) | yes
WhiteLabelService | setPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPriceLadderMatrix | request | id | string (uuid) | yes | (read-only)
CatalogueService | setPriceLadderMatrix | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setPriceLadderMatrix | request | dynamicPricingStrategyId | string (uuid) | yes
CatalogueService | setPriceLadderMatrix | request | basePriceSource | string |  | (max length 100; nullable)
CatalogueService | setPriceLadderMatrix | request | adjustmentModel | enum (fixedPriceBands, percentageBands, fixedAmountSteps, derivedBands, continuousRange) | yes
CatalogueService | setPriceLadderMatrix | request | bands | array of object |  | The bands, lowest first (typed 20 October 2026, R8 blocker cause GPS-C32; CHG-R8SPN-028: it was declared an object while every reader and writer used a list, so no valid body could carry it).
CatalogueService | setPriceLadderMatrix | request | bands[].code | string | yes | Band code, e.g. (max length 40)
CatalogueService | setPriceLadderMatrix | request | bands[].price | object |  | Band price (fixed and derived bands) (nullable)
CatalogueService | setPriceLadderMatrix | request | bands[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | request | bands[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | request | bands[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | request | bands[].percent | number |  | Band offset from base in percent (percentage bands) (nullable)
CatalogueService | setPriceLadderMatrix | request | baseBandCode | string |  | (max length 40; nullable)
CatalogueService | setPriceLadderMatrix | request | stepAmount | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | request | stepAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | request | stepAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | request | stepAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | request | minimumPrice | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | request | minimumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | request | minimumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | request | minimumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | request | basePrice | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | request | maximumPrice | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | request | maximumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | request | maximumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | request | maximumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | request | allowUpward | boolean |  | (default True)
CatalogueService | setPriceLadderMatrix | request | allowDownward | boolean |  | (default True)
CatalogueService | setPriceLadderMatrix | request | maxIncreasePercentPerAdjustment | number |  | (nullable)
CatalogueService | setPriceLadderMatrix | request | maxDecreasePercentPerAdjustment | number |  | (nullable)
CatalogueService | setPriceLadderMatrix | request | maximumBandsPerMovement | integer |  | (min 1; nullable)
CatalogueService | setPriceLadderMatrix | request | minimumMinutesBetweenMovements | integer |  | (min 0; nullable)
CatalogueService | setPriceLadderMatrix | request | cooldownMinutes | integer |  | (min 0; nullable)
CatalogueService | setPriceLadderMatrix | request | reversalRule | enum (allowed, afterCooldown, notAllowed) |  | (default afterCooldown)
CatalogueService | setPriceLadderMatrix | request | allowedEndpoints | array of string |  | The governed price endpoints a price may land on, as decimal strings in the venue's currency (e.g.
CatalogueService | setPriceLadderMatrix | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setPriceLadderMatrix | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setPriceLadderMatrix | response | id | string (uuid) | yes | (read-only)
CatalogueService | setPriceLadderMatrix | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setPriceLadderMatrix | response | dynamicPricingStrategyId | string (uuid) | yes
CatalogueService | setPriceLadderMatrix | response | basePriceSource | string |  | (max length 100; nullable)
CatalogueService | setPriceLadderMatrix | response | adjustmentModel | enum (fixedPriceBands, percentageBands, fixedAmountSteps, derivedBands, continuousRange) | yes
CatalogueService | setPriceLadderMatrix | response | bands | array of object |  | The bands, lowest first (typed 20 October 2026, R8 blocker cause GPS-C32; CHG-R8SPN-028: it was declared an object while every reader and writer used a list, so no valid body could carry it).
CatalogueService | setPriceLadderMatrix | response | bands[].code | string | yes | Band code, e.g. (max length 40)
CatalogueService | setPriceLadderMatrix | response | bands[].price | object |  | Band price (fixed and derived bands) (nullable)
CatalogueService | setPriceLadderMatrix | response | bands[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | response | bands[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | response | bands[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | response | bands[].percent | number |  | Band offset from base in percent (percentage bands) (nullable)
CatalogueService | setPriceLadderMatrix | response | baseBandCode | string |  | (max length 40; nullable)
CatalogueService | setPriceLadderMatrix | response | stepAmount | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | response | stepAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | response | stepAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | response | stepAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | response | minimumPrice | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | response | minimumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | response | minimumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | response | minimumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | response | basePrice | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | response | maximumPrice | object |  | (nullable)
CatalogueService | setPriceLadderMatrix | response | maximumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPriceLadderMatrix | response | maximumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPriceLadderMatrix | response | maximumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPriceLadderMatrix | response | allowUpward | boolean |  | (default True)
CatalogueService | setPriceLadderMatrix | response | allowDownward | boolean |  | (default True)
CatalogueService | setPriceLadderMatrix | response | maxIncreasePercentPerAdjustment | number |  | (nullable)
CatalogueService | setPriceLadderMatrix | response | maxDecreasePercentPerAdjustment | number |  | (nullable)
CatalogueService | setPriceLadderMatrix | response | maximumBandsPerMovement | integer |  | (min 1; nullable)
CatalogueService | setPriceLadderMatrix | response | minimumMinutesBetweenMovements | integer |  | (min 0; nullable)
CatalogueService | setPriceLadderMatrix | response | cooldownMinutes | integer |  | (min 0; nullable)
CatalogueService | setPriceLadderMatrix | response | reversalRule | enum (allowed, afterCooldown, notAllowed) |  | (default afterCooldown)
CatalogueService | setPriceLadderMatrix | response | allowedEndpoints | array of string |  | The governed price endpoints a price may land on, as decimal strings in the venue's currency (e.g.
CatalogueService | setPriceLadderMatrix | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setPriceLadderMatrix | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setPriceLadderMatrix | param (path) | strategyId | string (uuid) | yes | The catalogue.dynamic_pricing_strategy id.
CatalogueService | setPriceLadderMatrix | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPrices | request | prices | array of SetPriceRequest | yes | (max items 5000)
CatalogueService | setPrices | request | prices[].variantId | string (uuid) | yes
CatalogueService | setPrices | request | prices[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | setPrices | request | prices[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPrices | request | prices[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPrices | request | prices[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPrices | request | prices[].taxCodeId | string (uuid)
CatalogueService | setPrices | response | applied | integer
CatalogueService | setPrices | param (path) | priceListId | string (uuid) | yes
CatalogueService | setPrices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPrices | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | setPricing | request | venue | string |  | Scope: venue id (nullable)
CatalogueService | setPricing | request | product | string |  | Scope: product id (nullable)
CatalogueService | setPricing | request | event | string |  | Scope: event id (nullable)
CatalogueService | setPricing | request | performance | string |  | Scope: performance id (nullable)
CatalogueService | setPricing | request | timeslot | string |  | Scope: timeslot (nullable)
CatalogueService | setPricing | request | priceCategory | string |  | Scope: price category (nullable)
CatalogueService | setPricing | request | channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) |  | Scope: channel
CatalogueService | setPricing | request | customerSegment | string |  | Scope: customer segment (nullable)
CatalogueService | setPricing | request | dateFrom | string (date) |  | Scope: first date
CatalogueService | setPricing | request | dateTo | string (date) |  | Scope: last date
CatalogueService | setPricing | request | simulationSource | enum (manualPriceChange, dynamicRule, aiRecommendation, newDynamicStrategy, strategyModification, bulkPriceChange) |  | Simulation Source
CatalogueService | setPricing | request | sourceReference | string |  | Id of the rule, recommendation or strategy the simulation came from (nullable)
CatalogueService | setPricing | request | proposedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | request | proposedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | request | proposedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | request | proposedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | request | proposedAdjustmentPercent | number |  | Proposed adjustment, percent (bulk change or strategy) (nullable)
CatalogueService | setPricing | response | expectedDemand | integer |  | Expected Demand
CatalogueService | setPricing | response | expectedConversion | number |  | Expected Conversion, percent
CatalogueService | setPricing | response | expectedAttendance | integer |  | Expected Attendance
CatalogueService | setPricing | response | expectedOccupancy | number |  | Expected Occupancy, percent
CatalogueService | setPricing | response | expectedRevenue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | response | expectedRevenue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | response | expectedRevenue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | response | expectedRevenue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | response | expectedMargin | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | response | expectedMargin.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | response | expectedMargin.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | response | expectedMargin.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | response | expectedSellThrough | number |  | Expected Sell-Through, percent
CatalogueService | setPricing | response | expectedSellOutTime | string (date-time) |  | Expected Sell-Out Time (nullable)
CatalogueService | setPricing | response | averageSellingPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | response | averageSellingPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | response | averageSellingPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | response | averageSellingPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | response | simulationConfidence | number |  | Simulation Confidence, percent
CatalogueService | setPricing | response | dataVolume | integer |  | Data Volume: transactions behind the simulation
CatalogueService | setPricing | response | historicalSimilarity | number |  | Historical Similarity, percent
CatalogueService | setPricing | response | forecastConfidence | number |  | Forecast Confidence, percent
CatalogueService | setPricing | response | elasticityConfidence | number |  | Elasticity Confidence, percent
CatalogueService | setPricing | response | externalSignalQuality | number |  | External Signal Quality, percent
CatalogueService | setPricing | response | simulationId | string |  | Simulation id (saved scenarios keep it)
CatalogueService | setPricing | response | simulationSource | enum (manualPriceChange, dynamicRule, aiRecommendation, newDynamicStrategy, strategyModification, bulkPriceChange) |  | Simulation Source
CatalogueService | setPricing | response | currentPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | response | currentPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | response | currentPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | response | currentPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | response | proposedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | response | proposedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | response | proposedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | response | proposedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | response | baselineRevenue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPricing | response | baselineRevenue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPricing | response | baselineRevenue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPricing | response | baselineRevenue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPricing | response | baselineDemand | integer |  | Current strategy: expected demand
CatalogueService | setPricing | response | baselineOccupancy | number |  | Current strategy: expected occupancy, percent
CatalogueService | setPricing | response | guardrailChecks | array of object |  | Guardrail Check shown before the simulation completes
CatalogueService | setPricing | response | guardrailChecks[].check | enum (commercialGuardrail, contractProtection, priceLadder, approvalThreshold) |  | Guardrail
CatalogueService | setPricing | response | guardrailChecks[].passed | boolean |  | Pass / fail
CatalogueService | setPricing | response | guardrailChecks[].message | string |  | Why it failed, or the approval level required
CatalogueService | setPricing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setPrimaryDomain | response | id | string (uuid) | yes
WhiteLabelService | setPrimaryDomain | response | tenantId | string (uuid) | yes
WhiteLabelService | setPrimaryDomain | response | hostname | string | yes
WhiteLabelService | setPrimaryDomain | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) |  | guestApp is stored as guestWeb: the guest app is served on the guestWeb domain and has no domain of its own (r10 question 4; CHG-R10TEN-020).
WhiteLabelService | setPrimaryDomain | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | setPrimaryDomain | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | setPrimaryDomain | response | verificationToken | string |  | (read-only)
WhiteLabelService | setPrimaryDomain | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | setPrimaryDomain | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | setPrimaryDomain | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | setPrimaryDomain | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | setPrimaryDomain | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | setPrimaryDomain | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | setPrimaryDomain | response | validationExpiresAt | string (date-time) |  | When the validation window ends (ADAM CR-105, option 1; CHG-R10TEN-011): 7 days after claimCustomDomain or regenerateDomainToken issued the token (a proposed default the client can correct). (read-only; nullable)
WhiteLabelService | setPrimaryDomain | response | failureReason | string |  | (nullable)
WhiteLabelService | setPrimaryDomain | response | routing | enum (cname, delegatedSubdomain, apex) |  | How the hostname reaches TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; CHG-CSA-043). (default cname)
WhiteLabelService | setPrimaryDomain | response | dnsRecords | array of object |  | Every record the tenant must publish, with what is observed now (CHG-CSA-043): the TXT _dnsauth record, the CNAME, and CAA or NS where they apply. (read-only)
WhiteLabelService | setPrimaryDomain | response | dnsRecords[].type | enum (TXT, CNAME, CAA, NS) | yes
WhiteLabelService | setPrimaryDomain | response | dnsRecords[].name | string | yes
WhiteLabelService | setPrimaryDomain | response | dnsRecords[].expectedValue | string | yes
WhiteLabelService | setPrimaryDomain | response | dnsRecords[].observedValue | string |  | (nullable)
WhiteLabelService | setPrimaryDomain | response | dnsRecords[].status | enum (ok, missing, wrong) | yes
WhiteLabelService | setPrimaryDomain | response | revalidation | enum (none, pendingRevalidation, timedOut) |  | The two waits CMS-017 shows beside status (CHG-CSA-043). (default none; read-only)
WhiteLabelService | setPrimaryDomain | response | isCnameLost | boolean |  | Takeover warning (CHG-CSA-043). (read-only)
WhiteLabelService | setPrimaryDomain | response | isPrimary | boolean |  | The tenant's primary domain for its kind; the others redirect to it (setPrimaryDomain). (read-only)
WhiteLabelService | setPrimaryDomain | response | readiness | object |  | Per-domain setup a guest needs (CHG-CSA-043): the UAE Pass redirect URI registered for this hostname, the Apple Pay merchant domain verified, and the app links (Apple app-site association, Android as… (read-only)
WhiteLabelService | setPrimaryDomain | response | readiness.uaePassRedirect | enum (ready, pending, notApplicable)
WhiteLabelService | setPrimaryDomain | response | readiness.applePayDomain | enum (ready, pending, notApplicable)
WhiteLabelService | setPrimaryDomain | response | readiness.appLinks | enum (ready, pending, notApplicable)
WhiteLabelService | setPrimaryDomain | param (path) | domainId | string (uuid) | yes
WhiteLabelService | setPrimaryDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductCatalogue | request | channelId | string |  | Channel ID
CatalogueService | setProductCatalogue | request | assignmentMethod | enum (individualProduct, productFamily, productCategory, event, attraction, venueCatalogue, productCollection, entireApprovedCatalogue) |  | Assignment Method (pack p.7)
CatalogueService | setProductCatalogue | request | targetIds | array of string |  | IDs of the products, families, categories, events, attractions, venue catalogues or collections assigned; empty for entireApprovedCatalogue
CatalogueService | setProductCatalogue | request | excludedProductIds | array of string |  | Channel-specific overrides: products excluded from what is inherited (pack p.8, e.g.
CatalogueService | setProductCatalogue | request | enabled | boolean |  | Enable or disable the assignment on the channel
CatalogueService | setProductCatalogue | request | effectiveFrom | string (date) |  | Effective From
CatalogueService | setProductCatalogue | request | effectiveTo | string (date) |  | Effective To; empty for open-ended (nullable)
CatalogueService | setProductCatalogue | response | product | string |  | Product ID
CatalogueService | setProductCatalogue | response | productType | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | setProductCatalogue | response | venue | string |  | Venue ID
CatalogueService | setProductCatalogue | response | status | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived) |  | Status: the product's own lifecycle state in Product Catalogue
CatalogueService | setProductCatalogue | response | validity | string |  | Validity: the product's validity period as set in Product Catalogue, shown for reference
CatalogueService | setProductCatalogue | response | channelStatus | string |  | Channel Status: enabled, disabled or scheduled on this channel (decided 29 September, readiness close-out)
CatalogueService | setProductCatalogue | response | pricingStatus | string |  | Pricing Status: valid, missing or expired for this channel (from ADM-261) (decided 29 September, readiness close-out)
CatalogueService | setProductCatalogue | response | capacityStatus | string |  | Capacity Status: allocated, sharedPool or none for this channel (from ADM-262) (decided 29 September, readiness close-out)
CatalogueService | setProductCatalogue | response | effectiveFrom | string (date) |  | Effective From
CatalogueService | setProductCatalogue | response | effectiveTo | string (date) |  | Effective To; empty for open-ended (nullable)
CatalogueService | setProductCatalogue | response | channelId | string |  | Channel: the configured channel's ID from the Sales Channel Command Center (ADM-258)
CatalogueService | setProductCatalogue | response | assignmentMethod | enum (individualProduct, productFamily, productCategory, event, attraction, venueCatalogue, productCollection, entireApprovedCatalogue) |  | Assignment Method the product came in by (pack p.7)
CatalogueService | setProductCatalogue | response | inheritedFrom | enum (globalChannelCatalogue, venueCatalogue, channelOverride) |  | Inheritance level the assignment comes from (pack p.7-8)
CatalogueService | setProductCatalogue | response | validationIssues | array of object |  | Validation (pack p.8): why this product should not be published on the channel
CatalogueService | setProductCatalogue | response | validationIssues[].code | enum (draftProduct, retiredProduct, missingPricing, missingEntitlement, outsideValidity, unavailableForChannel)
CatalogueService | setProductCatalogue | response | validationIssues[].message | string
CatalogueService | setProductCatalogue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductCategories | request | categories | array of ProductCategory | yes
CatalogueService | setProductCategories | request | categories[].id | string (uuid) | yes
CatalogueService | setProductCategories | request | categories[].name | string | yes
CatalogueService | setProductCategories | request | categories[].code | string |  | Taken from their category tables, 20 September. (max length 64; nullable)
CatalogueService | setProductCategories | request | categories[].nameLocalised | object
CatalogueService | setProductCategories | request | categories[].kind | enum (category, brand, collection, season, department) | yes
CatalogueService | setProductCategories | request | categories[].parentId | string (uuid) |  | One tree, not four. (nullable)
CatalogueService | setProductCategories | request | categories[].scopePath | string |  | Set by the server from the venue the caller acts at; not sent. (read-only)
CatalogueService | setProductCategories | request | categories[].displayOrder | integer |  | (default 100)
CatalogueService | setProductCategories | request | categories[].imageAssetId | string (uuid) |  | (nullable)
CatalogueService | setProductCategories | request | categories[].description | object |  | The short line a guest reads under a category option, e.g. (nullable)
CatalogueService | setProductCategories | request | categories[].bookingFlowId | string (uuid) |  | The booking flow for every product filed here that names none of its own (decided 29 September, W12, BO-115). (nullable)
CatalogueService | setProductCategories | request | categories[].isActive | boolean |  | Deactivated rather than deleted. (default True)
CatalogueService | setProductCategories | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductChannelTexts | request | id | string (uuid) |  | The row's key, set by the server; absent while the product has saved nothing. (read-only)
CatalogueService | setProductChannelTexts | request | productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductChannelTexts | request | posButtonLabel | object |  | The label on the till's sale button (4.10); at most 30 characters per language. (nullable)
CatalogueService | setProductChannelTexts | request | receiptName | object |  | The product's name as printed on the receipt and the ticket, which may differ from the button label (4.10); at most 80 characters per language. (nullable)
CatalogueService | setProductChannelTexts | request | partnerDescription | object |  | What resellers see in the B2B portal and through the API (4.10); at most 4000 characters per language. (nullable)
CatalogueService | setProductChannelTexts | request | webDescription | object |  | The description the website and the guest app show; null uses the product's description (wireframe B1-S06). (nullable)
CatalogueService | setProductChannelTexts | request | kioskLabel | object |  | The label on the kiosk's product tile (wireframe B1-S06); at most 40 characters per language. (nullable)
CatalogueService | setProductChannelTexts | request | visitInstructions | object |  | What the guest is told to do on the day (wireframe B1-S06); at most 2000 characters per language. (nullable)
CatalogueService | setProductChannelTexts | request | termsAndConditions | object |  | The product's own terms (wireframe B1-S06); at most 8000 characters per language. (nullable)
CatalogueService | setProductChannelTexts | request | enabledLanguages | array of string |  | The tenant's enabled languages, ISO 639-1 codes in the tenant's order: the published set, or the draft's before the first publish (white-label LanguageConfig.languages). (read-only)
CatalogueService | setProductChannelTexts | request | missingTranslations | array of object |  | Per enabled language of the tenant, the texts above (and name, description for the product's own) set in some language and not in this one. (read-only)
CatalogueService | setProductChannelTexts | request | missingTranslations[].language | string | yes | (pattern ^[a-z]{2}$)
CatalogueService | setProductChannelTexts | request | missingTranslations[].fields | array of enum (name, description, posButtonLabel, receiptName, partnerDescription, webDescription, kioskLabel, visitInstructions, …) | yes
CatalogueService | setProductChannelTexts | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductChannelTexts | response | id | string (uuid) |  | The row's key, set by the server; absent while the product has saved nothing. (read-only)
CatalogueService | setProductChannelTexts | response | productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductChannelTexts | response | posButtonLabel | object |  | The label on the till's sale button (4.10); at most 30 characters per language. (nullable)
CatalogueService | setProductChannelTexts | response | receiptName | object |  | The product's name as printed on the receipt and the ticket, which may differ from the button label (4.10); at most 80 characters per language. (nullable)
CatalogueService | setProductChannelTexts | response | partnerDescription | object |  | What resellers see in the B2B portal and through the API (4.10); at most 4000 characters per language. (nullable)
CatalogueService | setProductChannelTexts | response | webDescription | object |  | The description the website and the guest app show; null uses the product's description (wireframe B1-S06). (nullable)
CatalogueService | setProductChannelTexts | response | kioskLabel | object |  | The label on the kiosk's product tile (wireframe B1-S06); at most 40 characters per language. (nullable)
CatalogueService | setProductChannelTexts | response | visitInstructions | object |  | What the guest is told to do on the day (wireframe B1-S06); at most 2000 characters per language. (nullable)
CatalogueService | setProductChannelTexts | response | termsAndConditions | object |  | The product's own terms (wireframe B1-S06); at most 8000 characters per language. (nullable)
CatalogueService | setProductChannelTexts | response | enabledLanguages | array of string |  | The tenant's enabled languages, ISO 639-1 codes in the tenant's order: the published set, or the draft's before the first publish (white-label LanguageConfig.languages). (read-only)
CatalogueService | setProductChannelTexts | response | missingTranslations | array of object |  | Per enabled language of the tenant, the texts above (and name, description for the product's own) set in some language and not in this one. (read-only)
CatalogueService | setProductChannelTexts | response | missingTranslations[].language | string | yes | (pattern ^[a-z]{2}$)
CatalogueService | setProductChannelTexts | response | missingTranslations[].fields | array of enum (name, description, posButtonLabel, receiptName, partnerDescription, webDescription, kioskLabel, visitInstructions, …) | yes
CatalogueService | setProductChannelTexts | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductChannelTexts | param (path) | productId | string (uuid) | yes
CatalogueService | setProductChannelTexts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductEligibilityRule | request | id | string (uuid) |  | (read-only)
CatalogueService | setProductEligibilityRule | request | productId | string |  | (read-only)
CatalogueService | setProductEligibilityRule | request | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | request | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | request | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | request | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | request | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | setProductEligibilityRule | request | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | setProductEligibilityRule | request | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | setProductEligibilityRule | request | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | setProductEligibilityRule | request | waiverRequired | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | request | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | setProductEligibilityRule | request | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | request | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | setProductEligibilityRule | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductEligibilityRule | response | id | string (uuid) |  | (read-only)
CatalogueService | setProductEligibilityRule | response | productId | string |  | (read-only)
CatalogueService | setProductEligibilityRule | response | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | response | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | response | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | response | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | response | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | setProductEligibilityRule | response | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | setProductEligibilityRule | response | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | setProductEligibilityRule | response | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | setProductEligibilityRule | response | waiverRequired | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | response | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | setProductEligibilityRule | response | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | response | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | setProductEligibilityRule | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductEligibilityRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductEligibilityRule | param (path) | productId | string | yes
CatalogueService | setProductOwnerForms | request | productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductOwnerForms | request | forms | array of ProductOwnerForm | yes | (max items 2)
CatalogueService | setProductOwnerForms | request | forms[].id | string (uuid) |  | (read-only)
CatalogueService | setProductOwnerForms | request | forms[].productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductOwnerForms | request | forms[].appliesTo | enum (reservationOwner, ticketOwner) | yes | reservationOwner: asked once per sale, of the buyer.
CatalogueService | setProductOwnerForms | request | forms[].formId | string (uuid) | yes | A Marketing form (marketing.form_definition), read through marketing-crm#formDefinitionRecords; not a database reference, because the form is Marketing's.
CatalogueService | setProductOwnerForms | request | forms[].formName | string |  | The form's name, for the product form; null if the form no longer exists. (read-only; nullable)
CatalogueService | setProductOwnerForms | request | forms[].publishedVersion | integer |  | The version a sale made now would ask; null if the form has no published version. (read-only; nullable)
CatalogueService | setProductOwnerForms | request | forms[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductOwnerForms | response | productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductOwnerForms | response | forms | array of ProductOwnerForm | yes | (max items 2)
CatalogueService | setProductOwnerForms | response | forms[].id | string (uuid) |  | (read-only)
CatalogueService | setProductOwnerForms | response | forms[].productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductOwnerForms | response | forms[].appliesTo | enum (reservationOwner, ticketOwner) | yes | reservationOwner: asked once per sale, of the buyer.
CatalogueService | setProductOwnerForms | response | forms[].formId | string (uuid) | yes | A Marketing form (marketing.form_definition), read through marketing-crm#formDefinitionRecords; not a database reference, because the form is Marketing's.
CatalogueService | setProductOwnerForms | response | forms[].formName | string |  | The form's name, for the product form; null if the form no longer exists. (read-only; nullable)
CatalogueService | setProductOwnerForms | response | forms[].publishedVersion | integer |  | The version a sale made now would ask; null if the form has no published version. (read-only; nullable)
CatalogueService | setProductOwnerForms | response | forms[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductOwnerForms | param (path) | productId | string (uuid) | yes
CatalogueService | setProductOwnerForms | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductSalePermissionRules | request | productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductSalePermissionRules | request | rules | array of ProductSalePermissionRule | yes | (max items 200)
CatalogueService | setProductSalePermissionRules | request | rules[].id | string (uuid) |  | (read-only)
CatalogueService | setProductSalePermissionRules | request | rules[].productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductSalePermissionRules | request | rules[].level | SalePermissionLevel: enum (global, venue, salesChannel, workstation, role, principal) | yes | The six levels at which the sale of a product is allowed or denied (16 October 2026 minutes, 4.8, CHG-R8PRD-005), in the package's words: global (every venue of the tenant), venue (the minutes' "site…
CatalogueService | setProductSalePermissionRules | request | rules[].targetId | string (uuid) |  | What the rule names at its level: a venue, a catalogue.sales_channel, a workstation, a role or a principal. (nullable)
CatalogueService | setProductSalePermissionRules | request | rules[].targetName | string |  | The target's name as listSalePermissionTargets gives it, so the rule reads in words; null for global, and for a target that no longer exists. (read-only; nullable)
CatalogueService | setProductSalePermissionRules | request | rules[].effect | enum (ALLOW, DENY) | yes | Resolved as the package resolves grants (permissions.yaml, deny overrides allow); see ProductSalePermissionRuleSet.
CatalogueService | setProductSalePermissionRules | request | rules[].note | string |  | Why the rule exists, for whoever reads it next. (max length 200; nullable)
CatalogueService | setProductSalePermissionRules | request | rules[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductSalePermissionRules | response | productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductSalePermissionRules | response | rules | array of ProductSalePermissionRule | yes | (max items 200)
CatalogueService | setProductSalePermissionRules | response | rules[].id | string (uuid) |  | (read-only)
CatalogueService | setProductSalePermissionRules | response | rules[].productId | string (uuid) |  | From the path. (read-only)
CatalogueService | setProductSalePermissionRules | response | rules[].level | SalePermissionLevel: enum (global, venue, salesChannel, workstation, role, principal) | yes | The six levels at which the sale of a product is allowed or denied (16 October 2026 minutes, 4.8, CHG-R8PRD-005), in the package's words: global (every venue of the tenant), venue (the minutes' "site…
CatalogueService | setProductSalePermissionRules | response | rules[].targetId | string (uuid) |  | What the rule names at its level: a venue, a catalogue.sales_channel, a workstation, a role or a principal. (nullable)
CatalogueService | setProductSalePermissionRules | response | rules[].targetName | string |  | The target's name as listSalePermissionTargets gives it, so the rule reads in words; null for global, and for a target that no longer exists. (read-only; nullable)
CatalogueService | setProductSalePermissionRules | response | rules[].effect | enum (ALLOW, DENY) | yes | Resolved as the package resolves grants (permissions.yaml, deny overrides allow); see ProductSalePermissionRuleSet.
CatalogueService | setProductSalePermissionRules | response | rules[].note | string |  | Why the rule exists, for whoever reads it next. (max length 200; nullable)
CatalogueService | setProductSalePermissionRules | response | rules[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductSalePermissionRules | param (path) | productId | string (uuid) | yes
CatalogueService | setProductSalePermissionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductServicePrice | request | assignmentId | string |  | Assignment ID; empty on create
CatalogueService | setProductServicePrice | request | objectType | enum (ticketProduct, ticketType, admission, event, performance, membership, annualPass, addOn, …) |  | Supported Commercial Objects (p.13): the kind of sellable object being priced
CatalogueService | setProductServicePrice | request | objectIds | array of string |  | The objects assigned; more than one is a Bulk Assignment (25 attraction products -> one price list)
CatalogueService | setProductServicePrice | request | assignmentScope | enum (productLevel, productVariant, ticketType, event, performance, venue) |  | Assignment Scope (p.14): the level at which the assignment holds
CatalogueService | setProductServicePrice | request | scopeRefId | string |  | The variant, ticket type, event, performance or venue the assignment is limited to; empty at product level (nullable)
CatalogueService | setProductServicePrice | request | priceListId | string |  | The price list assigned
CatalogueService | setProductServicePrice | request | categoryRates | array of object |  | Product -> Price List -> Category -> Rate (Assignment Workspace, p.13): which rate of the list serves each category; empty uses every active rate of the list
CatalogueService | setProductServicePrice | request | categoryRates[].priceCategory | string
CatalogueService | setProductServicePrice | request | categoryRates[].rateId | string
CatalogueService | setProductServicePrice | response | assignmentId | string |  | Assignment ID; empty on create
CatalogueService | setProductServicePrice | response | objectType | enum (ticketProduct, ticketType, admission, event, performance, membership, annualPass, addOn, …) |  | Supported Commercial Objects (p.13): the kind of sellable object being priced
CatalogueService | setProductServicePrice | response | objectIds | array of string |  | The objects assigned; more than one is a Bulk Assignment (25 attraction products -> one price list)
CatalogueService | setProductServicePrice | response | assignmentScope | enum (productLevel, productVariant, ticketType, event, performance, venue) |  | Assignment Scope (p.14): the level at which the assignment holds
CatalogueService | setProductServicePrice | response | scopeRefId | string |  | The variant, ticket type, event, performance or venue the assignment is limited to; empty at product level (nullable)
CatalogueService | setProductServicePrice | response | priceListId | string |  | The price list assigned
CatalogueService | setProductServicePrice | response | categoryRates | array of object |  | Product -> Price List -> Category -> Rate (Assignment Workspace, p.13): which rate of the list serves each category; empty uses every active rate of the list
CatalogueService | setProductServicePrice | response | categoryRates[].priceCategory | string
CatalogueService | setProductServicePrice | response | categoryRates[].rateId | string
CatalogueService | setProductServicePrice | response | pricingSource | string |  | Price Source Visibility (p.14): the name shown on the product, e.g.
CatalogueService | setProductServicePrice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPromotionVariants | request | variants | array of PromotionVariant | yes | (min items 2; max items 4)
CatalogueService | setPromotionVariants | request | variants[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | setPromotionVariants | request | variants[].id | string (uuid) |  | (read-only)
CatalogueService | setPromotionVariants | request | variants[].promotionId | string (uuid) |  | Taken from the path. (read-only)
CatalogueService | setPromotionVariants | request | variants[].label | string | yes
CatalogueService | setPromotionVariants | request | variants[].trafficPercent | integer | yes | Share of traffic. (min 0; max 100)
CatalogueService | setPromotionVariants | request | variants[].discountPercent | number
CatalogueService | setPromotionVariants | response | promotionId | string (uuid) | yes
CatalogueService | setPromotionVariants | response | variants | array of PromotionVariant | yes
CatalogueService | setPromotionVariants | response | variants[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | setPromotionVariants | response | variants[].id | string (uuid) |  | (read-only)
CatalogueService | setPromotionVariants | response | variants[].promotionId | string (uuid) |  | Taken from the path. (read-only)
CatalogueService | setPromotionVariants | response | variants[].label | string | yes
CatalogueService | setPromotionVariants | response | variants[].trafficPercent | integer | yes | Share of traffic. (min 0; max 100)
CatalogueService | setPromotionVariants | response | variants[].discountPercent | number
CatalogueService | setPromotionVariants | param (path) | promotionId | string (uuid) | yes
CatalogueService | setPromotionVariants | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setPublishReviewPolicy | request | enabled | boolean | yes | (default False)
WhiteLabelService | setPublishReviewPolicy | request | requiresReviewerOtherThanAuthor | boolean |  | (default True)
WhiteLabelService | setPublishReviewPolicy | request | appliesTo | array of enum (tenantConfig, contentBlocks) |  | What the review covers.
WhiteLabelService | setPublishReviewPolicy | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setPublishReviewPolicy | response | enabled | boolean | yes | (default False)
WhiteLabelService | setPublishReviewPolicy | response | requiresReviewerOtherThanAuthor | boolean |  | (default True)
WhiteLabelService | setPublishReviewPolicy | response | appliesTo | array of enum (tenantConfig, contentBlocks) |  | What the review covers.
WhiteLabelService | setPublishReviewPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setPublishReviewPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setRecipe | request | menuItemId | string (uuid) | yes
FnbService | setRecipe | request | yield | number |  | Portions produced by one execution. (min 0)
FnbService | setRecipe | request | ingredients | array of object | yes | (min items 1)
FnbService | setRecipe | request | ingredients[].inventoryItemId | string (uuid) | yes
FnbService | setRecipe | request | ingredients[].quantity | number | yes | (min 0)
FnbService | setRecipe | request | ingredients[].unit | string | yes
FnbService | setRecipe | request | ingredients[].isOptional | boolean |  | (default False)
FnbService | setRecipe | request | costPerPortion | object |  | Computed, never entered (decided 28 September, audit R125 (9)): the sum of each ingredient quantity at its current inventory cost, divided by yield. (read-only)
FnbService | setRecipe | request | costPerPortion.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setRecipe | request | costPerPortion.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setRecipe | request | costPerPortion.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setRecipe | request | id | string (uuid) |  | The recipe's own id (4 October 2026, CHG-FXC-003; the Sprint 1-2 judging found no operation returned one, so listIngredientSubstitutes, setIngredientSubstitutes and SubstitutionRule.recipeId had noth… (read-only)
FnbService | setRecipe | response | menuItemId | string (uuid) | yes
FnbService | setRecipe | response | yield | number |  | Portions produced by one execution. (min 0)
FnbService | setRecipe | response | ingredients | array of object | yes | (min items 1)
FnbService | setRecipe | response | ingredients[].inventoryItemId | string (uuid) | yes
FnbService | setRecipe | response | ingredients[].quantity | number | yes | (min 0)
FnbService | setRecipe | response | ingredients[].unit | string | yes
FnbService | setRecipe | response | ingredients[].isOptional | boolean |  | (default False)
FnbService | setRecipe | response | costPerPortion | object |  | Computed, never entered (decided 28 September, audit R125 (9)): the sum of each ingredient quantity at its current inventory cost, divided by yield. (read-only)
FnbService | setRecipe | response | costPerPortion.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setRecipe | response | costPerPortion.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setRecipe | response | costPerPortion.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setRecipe | response | id | string (uuid) |  | The recipe's own id (4 October 2026, CHG-FXC-003; the Sprint 1-2 judging found no operation returned one, so listIngredientSubstitutes, setIngredientSubstitutes and SubstitutionRule.recipeId had noth… (read-only)
FnbService | setRecipe | param (path) | recipeId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
FnbService | setRecipe | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setRecipe | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setRefundPolicy | request | id | string (uuid) |  | Added 20 August. (read-only)
OrderService | setRefundPolicy | request | venueId | string (uuid) | yes | The venue in the path. (read-only)
OrderService | setRefundPolicy | request | selfAuthoriseLimit | object | yes | Up to this, a holder of ORDER_REFUND refunds alone.
OrderService | setRefundPolicy | request | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | request | requiresSecondUserAbove | object |  | Above this, a second user — cashier OR supervisor — names themselves as audit control.
OrderService | setRefundPolicy | request | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | request | requiresApprovalAbove | object | yes | Above this, an ORDER_REFUND_APPROVE holder must approve.
OrderService | setRefundPolicy | request | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | request | timeBands | array of object |  | Refundable percentage by time before the performance.
OrderService | setRefundPolicy | request | timeBands[].hoursBefore | integer | yes | (min 0)
OrderService | setRefundPolicy | request | timeBands[].percentage | number | yes | (min 0; max 100)
OrderService | setRefundPolicy | request | timeBands[].refundType | enum (fullRefund, partialRefund, percentageRefund, proRataRefund, originalValueLessFees) |  | The refund type that applies in this band (the values of RefundCalculationPolicyView.refundTypes; ADAM CR-208). (nullable)
OrderService | setRefundPolicy | request | allowPartial | boolean |  | (default True)
OrderService | setRefundPolicy | request | refundWindowDays | integer |  | Days after purchase within which a refund may be made. (min 0; nullable)
OrderService | setRefundPolicy | request | varianceThreshold | object |  | Price variance above this is an exception requiring review rather than a routine posting (CF-38).
OrderService | setRefundPolicy | request | varianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | varianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | varianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
OrderService | setRefundPolicy | response | venueId | string (uuid) | yes | The venue in the path. (read-only)
OrderService | setRefundPolicy | response | selfAuthoriseLimit | object | yes | Up to this, a holder of ORDER_REFUND refunds alone.
OrderService | setRefundPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | requiresSecondUserAbove | object |  | Above this, a second user — cashier OR supervisor — names themselves as audit control.
OrderService | setRefundPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | requiresApprovalAbove | object | yes | Above this, an ORDER_REFUND_APPROVE holder must approve.
OrderService | setRefundPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | timeBands | array of object |  | Refundable percentage by time before the performance.
OrderService | setRefundPolicy | response | timeBands[].hoursBefore | integer | yes | (min 0)
OrderService | setRefundPolicy | response | timeBands[].percentage | number | yes | (min 0; max 100)
OrderService | setRefundPolicy | response | timeBands[].refundType | enum (fullRefund, partialRefund, percentageRefund, proRataRefund, originalValueLessFees) |  | The refund type that applies in this band (the values of RefundCalculationPolicyView.refundTypes; ADAM CR-208). (nullable)
OrderService | setRefundPolicy | response | allowPartial | boolean |  | (default True)
OrderService | setRefundPolicy | response | refundWindowDays | integer |  | Days after purchase within which a refund may be made. (min 0; nullable)
OrderService | setRefundPolicy | response | varianceThreshold | object |  | Price variance above this is an exception requiring review rather than a routine posting (CF-38).
OrderService | setRefundPolicy | response | varianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | varianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | varianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | param (path) | venueId | string (uuid) | yes
OrderService | setRefundPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setRefundPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setResourceLifecycleState | request | state | ResourceLifecycleState: enum (draft, pendingApproval, approved, active, temporarilyUnavailable, underMaintenance, suspended, retired, …) | yes | Board 1.10.
VenueOpsService | setResourceLifecycleState | request | reason | string |  | (nullable)
VenueOpsService | setResourceLifecycleState | request | effectiveFrom | string (date-time) |  | (nullable)
VenueOpsService | setResourceLifecycleState | request | replacementResourceId | string (uuid) |  | (nullable)
VenueOpsService | setResourceLifecycleState | request | disposal | object |  | (nullable)
VenueOpsService | setResourceLifecycleState | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setResourceLifecycleState | response | code | string | yes
VenueOpsService | setResourceLifecycleState | response | name | string | yes
VenueOpsService | setResourceLifecycleState | response | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | setResourceLifecycleState | response | venueId | string (uuid) | yes
VenueOpsService | setResourceLifecycleState | response | scopePath | string
VenueOpsService | setResourceLifecycleState | response | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | setResourceLifecycleState | response | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | setResourceLifecycleState | response | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | setResourceLifecycleState | response | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | setResourceLifecycleState | response | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | setResourceLifecycleState | response | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | setResourceLifecycleState | response | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | setResourceLifecycleState | response | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | setResourceLifecycleState | response | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | setResourceLifecycleState | response | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | setResourceLifecycleState | response | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | setResourceLifecycleState | response | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | setResourceLifecycleState | response | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setResourceLifecycleState | response | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setResourceLifecycleState | response | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setResourceLifecycleState | response | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setResourceLifecycleState | response | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | setResourceLifecycleState | response | isActive | boolean |  | (default True)
VenueOpsService | setResourceLifecycleState | response | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | setResourceLifecycleState | response | lifecycleState | object |  | The lifecycle state setResourceLifecycleState set. (read-only; nullable)
VenueOpsService | setResourceLifecycleState | response | lifecycleEffectiveFrom | string (date-time) |  | When the lifecycle state takes effect (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | setResourceLifecycleState | response | lifecycleReason | string |  | Why the lifecycle state changed (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | setResourceLifecycleState | response | replacementResourceId | string (uuid) |  | The resource that replaces this one, where it was retired for a replacement. (read-only; nullable)
VenueOpsService | setResourceLifecycleState | response | disposal | object |  | How a disposed resource left (setResourceLifecycleState), as given. (read-only; nullable)
VenueOpsService | setResourceLifecycleState | param (path) | resourceId | string (uuid) | yes
VenueOpsService | setResourceLifecycleState | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setResourceSchedule | request | resourceId | string (uuid)
VenueOpsService | setResourceSchedule | request | availabilityMode | enum (alwaysAvailable, scheduled, onRequest)
VenueOpsService | setResourceSchedule | request | windows | array of object
VenueOpsService | setResourceSchedule | request | windows[].daysOfWeek | array of string
VenueOpsService | setResourceSchedule | request | windows[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | request | windows[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | request | windows[].effectiveFrom | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | request | windows[].effectiveTo | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | request | slotMinutes | integer |  | How finely this resource's time can be cut, which is a property of the resource and not of the product sold against it. (nullable)
VenueOpsService | setResourceSchedule | request | minimumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | request | maximumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | request | advanceBookingDays | integer |  | (nullable)
VenueOpsService | setResourceSchedule | request | exceptions | array of object
VenueOpsService | setResourceSchedule | request | exceptions[].date | string (date)
VenueOpsService | setResourceSchedule | request | exceptions[].closed | boolean
VenueOpsService | setResourceSchedule | request | exceptions[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | request | exceptions[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | request | scopePath | string
VenueOpsService | setResourceSchedule | response | resourceId | string (uuid)
VenueOpsService | setResourceSchedule | response | availabilityMode | enum (alwaysAvailable, scheduled, onRequest)
VenueOpsService | setResourceSchedule | response | windows | array of object
VenueOpsService | setResourceSchedule | response | windows[].daysOfWeek | array of string
VenueOpsService | setResourceSchedule | response | windows[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | response | windows[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | response | windows[].effectiveFrom | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | response | windows[].effectiveTo | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | response | slotMinutes | integer |  | How finely this resource's time can be cut, which is a property of the resource and not of the product sold against it. (nullable)
VenueOpsService | setResourceSchedule | response | minimumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | response | maximumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | response | advanceBookingDays | integer |  | (nullable)
VenueOpsService | setResourceSchedule | response | exceptions | array of object
VenueOpsService | setResourceSchedule | response | exceptions[].date | string (date)
VenueOpsService | setResourceSchedule | response | exceptions[].closed | boolean
VenueOpsService | setResourceSchedule | response | exceptions[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | response | exceptions[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | response | scopePath | string
VenueOpsService | setResourceSchedule | param (path) | resourceId | string (uuid) | yes
VenueOpsService | setResourceSchedule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setResourceSchedule | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
RetailService | setReturnPolicy | request | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | setReturnPolicy | request | outletId | string (uuid) | yes
RetailService | setReturnPolicy | request | defaultWindowDays | integer | yes | (min 0)
RetailService | setReturnPolicy | request | requiresReceipt | boolean | yes | (default True)
RetailService | setReturnPolicy | request | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | setReturnPolicy | request | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | setReturnPolicy | request | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | request | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | request | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | request | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | setReturnPolicy | request | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | request | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | request | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | request | requiresApprovalAbove | object |  | Retired (r8, decision R144), so no return raises an approval request.
RetailService | setReturnPolicy | request | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | request | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | request | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | request | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | setReturnPolicy | request | nonReturnableCategoryIds | array of string (uuid)
RetailService | setReturnPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | setReturnPolicy | response | outletId | string (uuid) | yes
RetailService | setReturnPolicy | response | defaultWindowDays | integer | yes | (min 0)
RetailService | setReturnPolicy | response | requiresReceipt | boolean | yes | (default True)
RetailService | setReturnPolicy | response | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | setReturnPolicy | response | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | setReturnPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | response | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | setReturnPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | response | requiresApprovalAbove | object |  | Retired (r8, decision R144), so no return raises an approval request.
RetailService | setReturnPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | response | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | setReturnPolicy | response | nonReturnableCategoryIds | array of string (uuid)
RetailService | setReturnPolicy | param (path) | outletId | string (uuid) | yes
RetailService | setReturnPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setReward | request | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | setReward | request | id | string (uuid)
MarketingService | setReward | request | loyaltyProgramId | string (uuid) | yes
MarketingService | setReward | request | code | string | yes | (max length 100)
MarketingService | setReward | request | name | string | yes | (max length 200)
MarketingService | setReward | request | type | string | yes | (max length 30)
MarketingService | setReward | request | productId | string (uuid) |  | (nullable)
MarketingService | setReward | request | pointsCost | number |  | (nullable)
MarketingService | setReward | request | discountValue | number |  | (nullable)
MarketingService | setReward | request | validityDays | integer |  | (nullable)
MarketingService | setReward | request | isActive | boolean | yes
MarketingService | setReward | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | setReward | response | id | string (uuid)
MarketingService | setReward | response | loyaltyProgramId | string (uuid) | yes
MarketingService | setReward | response | code | string | yes | (max length 100)
MarketingService | setReward | response | name | string | yes | (max length 200)
MarketingService | setReward | response | type | string | yes | (max length 30)
MarketingService | setReward | response | productId | string (uuid) |  | (nullable)
MarketingService | setReward | response | pointsCost | number |  | (nullable)
MarketingService | setReward | response | discountValue | number |  | (nullable)
MarketingService | setReward | response | validityDays | integer |  | (nullable)
MarketingService | setReward | response | isActive | boolean | yes
MarketingService | setReward | param (path) | rewardId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
MarketingService | setReward | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setRolePermissions | request | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
TenancyService | setRolePermissions | request | inheritsFromRoleId | string (uuid) |  | (nullable)
TenancyService | setRolePermissions | response | roleId | string (uuid) | yes
TenancyService | setRolePermissions | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
TenancyService | setRolePermissions | response | inheritsFromRoleId | string (uuid) |  | (nullable)
TenancyService | setRolePermissions | param (path) | roleId | string (uuid) | yes
TenancyService | setRolePermissions | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setRulePriorityConflict | request | orderedRuleIds | array of string |  | The rules in priority order, highest first.
CatalogueService | setRulePriorityConflict | request | resolutionMethod | enum (highestPriorityWins, mostSpecificRuleWins, cumulativeAdjustment, maximumAdjustmentWins, minimumAdjustmentWins, weightedCombination, stopProcessing, customGovernedResolution) |  | How two applicable rules are resolved; the same vocabulary as RulePriorityConflictResolutionDynamicPricingTestConsSummary.resolutionMethod. (default highestPriorityWins)
CatalogueService | setRulePriorityConflict | request | priorityHierarchy | array of enum (commercialProtection, contractMemberProtection, eventSpecificStrategy, inventoryOccupancy, bookingVelocity, timeToEvent, seasonDayTimeslot, basePrice) |  | The priority matrix, highest first; defaults to the pack's order.
CatalogueService | setRulePriorityConflict | request | mode | enum (save, validate, test) | yes | validate checks the order and returns conflicts without saving; test runs testScenario against the order and saves it as a test case; save stores the order and method, refused with 409 while a critic…
CatalogueService | setRulePriorityConflict | request | testScenario | RulePriorityTestScenario |  | A sample booking for the conflict test console (pack p.90), the same inputs as a saved test case.
CatalogueService | setRulePriorityConflict | request | testScenario.caseName | string |  | (max length 120)
CatalogueService | setRulePriorityConflict | request | testScenario.caseType | enum (lowDemand, highDemand, nearSellOut, earlyBird, lastMinute, weekendPeak, memberPurchase, b2bContract, …)
CatalogueService | setRulePriorityConflict | request | testScenario.productId | string (uuid)
CatalogueService | setRulePriorityConflict | request | testScenario.eventId | string (uuid) |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.performanceId | string (uuid) |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.date | string (date)
CatalogueService | setRulePriorityConflict | request | testScenario.timeslot | string |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | setRulePriorityConflict | request | testScenario.customerSegment | string |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | request | testScenario.occupancy | number |  | (min 0; max 100)
CatalogueService | setRulePriorityConflict | request | testScenario.inventory | integer |  | (min 0)
CatalogueService | setRulePriorityConflict | request | testScenario.bookingVelocity | number
CatalogueService | setRulePriorityConflict | request | testScenario.timeToEvent | integer |  | (min 0)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice | object |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | mode | enum (save, validate, test)
CatalogueService | setRulePriorityConflict | response | saved | boolean
CatalogueService | setRulePriorityConflict | response | orderedRuleIds | array of string
CatalogueService | setRulePriorityConflict | response | resolutionMethod | string
CatalogueService | setRulePriorityConflict | response | priorityHierarchy | array of string
CatalogueService | setRulePriorityConflict | response | conflicts | array of object
CatalogueService | setRulePriorityConflict | response | conflicts[].code | enum (contradictoryRules, samePriority, impossibleCondition, overlappingStrategy, circularDependency, missingFallback, guardrailConflict)
CatalogueService | setRulePriorityConflict | response | conflicts[].severity | enum (critical, warning)
CatalogueService | setRulePriorityConflict | response | conflicts[].ruleIds | array of string
CatalogueService | setRulePriorityConflict | response | conflicts[].message | string
CatalogueService | setRulePriorityConflict | response | testResult | object |  | The saved test case with its deterministic result, in test mode. (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.product | string |  | Test input: product
CatalogueService | setRulePriorityConflict | response | testResult.event | string |  | Test input: event (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.performance | string |  | Test input: performance (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.date | string (date) |  | Test input: visit/event date
CatalogueService | setRulePriorityConflict | response | testResult.timeslot | string |  | Test input: timeslot (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.channel | object |  | Test input: channel
CatalogueService | setRulePriorityConflict | response | testResult.customerSegment | string |  | Test input: customer segment
CatalogueService | setRulePriorityConflict | response | testResult.basePrice | object |  | Test input: base price
CatalogueService | setRulePriorityConflict | response | testResult.basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.occupancy | number |  | Test input: occupancy percent
CatalogueService | setRulePriorityConflict | response | testResult.inventory | integer |  | Test input: remaining inventory
CatalogueService | setRulePriorityConflict | response | testResult.bookingVelocity | number |  | Test input: booking velocity, percent against expected pace
CatalogueService | setRulePriorityConflict | response | testResult.timeToEvent | integer |  | Test input: days to event (0 = same day)
CatalogueService | setRulePriorityConflict | response | testResult.calculationPath | array of string |  | Explainability: the complete calculation path, one step per line
CatalogueService | setRulePriorityConflict | response | testResult.testCaseId | string |  | Test case ID
CatalogueService | setRulePriorityConflict | response | testResult.caseName | string |  | Test case name
CatalogueService | setRulePriorityConflict | response | testResult.caseType | enum (lowDemand, highDemand, nearSellOut, earlyBird, lastMinute, weekendPeak, memberPurchase, b2bContract, …) |  | Test case type (pack p.91)
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched | array of object |  | Rules matched
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].ruleId | string |  | Rule
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].ruleName | string |  | Rule name
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].priorityLevel | enum (commercialProtection, contractMemberProtection, eventSpecificStrategy, inventoryOccupancy, bookingVelocity, timeToEvent, seasonDayTimeslot, basePrice) |  | Hierarchy level
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].adjustmentPercent | number |  | Adjustment in percent (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].applied | boolean |  | Applied after resolution
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice | object |  | Raw calculated price
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice | object |  | Nearest allowed band
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.guardrailOutcome | enum (passed, cappedAtMaximum, raisedToMinimum, protectedRateApplied) |  | Guardrail result
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice | object |  | Final dynamic price
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.conflicts | array of object |  | Conflicts met while resolving this case
CatalogueService | setRulePriorityConflict | response | testResult.conflicts[].code | enum (contradictoryRules, samePriority, impossibleCondition, overlappingStrategy, circularDependency, missingFallback, guardrailConflict) |  | Conflict type (pack p.90)
CatalogueService | setRulePriorityConflict | response | testResult.conflicts[].message | string |  | Message
CatalogueService | setRulePriorityConflict | response | testResult.conflicts[].ruleIds | array of string |  | Rules involved
CatalogueService | setRulePriorityConflict | response | testResult.lastRunAt | string (date-time) |  | Last run
CatalogueService | setRulePriorityConflict | response | testResult.passed | boolean |  | Final price matched the expected price saved with the case (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice | object |  | Expected final price for regression (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | savedAt | string (date-time) |  | (nullable)
CatalogueService | setRulePriorityConflict | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setSeatRecommendationRules | request | seatMapId | string (uuid) |  | (nullable)
CatalogueService | setSeatRecommendationRules | request | performanceId | string (uuid) |  | (nullable)
CatalogueService | setSeatRecommendationRules | request | profiles | array of object
CatalogueService | setSeatRecommendationRules | request | profiles[].kind | enum (bestSeat, bestValue, closestToStage, familyTogether, accessible, upgrade)
CatalogueService | setSeatRecommendationRules | request | profiles[].weights | object |  | Sightline, distance, centrality, row, price, availability, aisle proximity, legroom.
CatalogueService | setSeatRecommendationRules | request | profiles[].preferredSectionIds | array of string (uuid)
CatalogueService | setSeatRecommendationRules | request | profiles[].avoidSectionIds | array of string (uuid)
CatalogueService | setSeatRecommendationRules | request | profiles[].contiguityWeight | number |  | (nullable)
CatalogueService | setSeatRecommendationRules | request | reverseRowOrder | boolean |  | Last-row-is-best against first-row-is-best, which the minute names as the worked example and which differs by venue sightline. (default False)
CatalogueService | setSeatRecommendationRules | request | explainToGuest | boolean |  | (default True)
CatalogueService | setSeatRecommendationRules | request | scopePath | string
CatalogueService | setSeatRecommendationRules | response | seatMapId | string (uuid) |  | (nullable)
CatalogueService | setSeatRecommendationRules | response | performanceId | string (uuid) |  | (nullable)
CatalogueService | setSeatRecommendationRules | response | profiles | array of object
CatalogueService | setSeatRecommendationRules | response | profiles[].kind | enum (bestSeat, bestValue, closestToStage, familyTogether, accessible, upgrade)
CatalogueService | setSeatRecommendationRules | response | profiles[].weights | object |  | Sightline, distance, centrality, row, price, availability, aisle proximity, legroom.
CatalogueService | setSeatRecommendationRules | response | profiles[].preferredSectionIds | array of string (uuid)
CatalogueService | setSeatRecommendationRules | response | profiles[].avoidSectionIds | array of string (uuid)
CatalogueService | setSeatRecommendationRules | response | profiles[].contiguityWeight | number |  | (nullable)
CatalogueService | setSeatRecommendationRules | response | reverseRowOrder | boolean |  | Last-row-is-best against first-row-is-best, which the minute names as the worked example and which differs by venue sightline. (default False)
CatalogueService | setSeatRecommendationRules | response | explainToGuest | boolean |  | (default True)
CatalogueService | setSeatRecommendationRules | response | scopePath | string
CatalogueService | setSeatRecommendationRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | setSegregationRules | request | rules | array of SegregationRule | yes
IdentityService | setSegregationRules | request | rules[].id | string (uuid) | yes | Assigned by the server. (read-only)
IdentityService | setSegregationRules | request | rules[].name | string
IdentityService | setSegregationRules | request | rules[].permissionA | string | yes
IdentityService | setSegregationRules | request | rules[].permissionB | string | yes
IdentityService | setSegregationRules | request | rules[].severity | enum (block, requireApproval, warn) | yes | What each severity does (decided 14 October 2026, ADAM CR-079; CHG-IDR-003).
IdentityService | setSegregationRules | request | rules[].rationale | string |  | Why these two conflict, in words an auditor reads.
IdentityService | setSegregationRules | request | rules[].scopeSensitive | boolean |  | Whether the two permissions must overlap in scope to conflict, and this is not scopePath below — that one is the partition key and says where the rule *row* lives (ADR-0005), not where the *conflict*… (default True)
IdentityService | setSegregationRules | request | rules[].allowWithCompensatingControl | boolean |  | A small venue cannot always separate duties, and pretending otherwise means the rule gets disabled entirely. (default False)
IdentityService | setSegregationRules | request | rules[].scopePath | string |  | The partition key (ADR-0005). (read-only)
IdentityService | setSegregationRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | setSemanticModel | request | version | integer |  | Assigned by the server on each publish. (read-only)
ReportingService | setSemanticModel | request | domains | array of object
ReportingService | setSemanticModel | request | domains[].code | string
ReportingService | setSemanticModel | request | domains[].name | string
ReportingService | setSemanticModel | request | domains[].description | string |  | (nullable)
ReportingService | setSemanticModel | request | domains[].datasets | array of object
ReportingService | setSemanticModel | request | domains[].datasets[].code | string
ReportingService | setSemanticModel | request | domains[].datasets[].name | string
ReportingService | setSemanticModel | request | domains[].datasets[].grain | string |  | What one row means.
ReportingService | setSemanticModel | request | domains[].datasets[].fields | array of object
ReportingService | setSemanticModel | request | relationships | array of object
ReportingService | setSemanticModel | request | relationships[].fromDataset | string
ReportingService | setSemanticModel | request | relationships[].toDataset | string
ReportingService | setSemanticModel | request | relationships[].cardinality | enum (oneToOne, oneToMany, manyToOne, manyToMany)
ReportingService | setSemanticModel | request | publishedAt | string (date-time) |  | (read-only; nullable)
ReportingService | setSemanticModel | request | scopePath | string
ReportingService | setSemanticModel | response | version | integer |  | Assigned by the server on each publish. (read-only)
ReportingService | setSemanticModel | response | domains | array of object
ReportingService | setSemanticModel | response | domains[].code | string
ReportingService | setSemanticModel | response | domains[].name | string
ReportingService | setSemanticModel | response | domains[].description | string |  | (nullable)
ReportingService | setSemanticModel | response | domains[].datasets | array of object
ReportingService | setSemanticModel | response | domains[].datasets[].code | string
ReportingService | setSemanticModel | response | domains[].datasets[].name | string
ReportingService | setSemanticModel | response | domains[].datasets[].grain | string |  | What one row means.
ReportingService | setSemanticModel | response | domains[].datasets[].fields | array of object
ReportingService | setSemanticModel | response | relationships | array of object
ReportingService | setSemanticModel | response | relationships[].fromDataset | string
ReportingService | setSemanticModel | response | relationships[].toDataset | string
ReportingService | setSemanticModel | response | relationships[].cardinality | enum (oneToOne, oneToMany, manyToOne, manyToMany)
ReportingService | setSemanticModel | response | publishedAt | string (date-time) |  | (read-only; nullable)
ReportingService | setSemanticModel | response | scopePath | string
ReportingService | setSemanticModel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setSeoMetadata | request | id | string (uuid) | yes | (read-only)
MarketingService | setSeoMetadata | request | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | setSeoMetadata | request | entityId | string (uuid) | yes
MarketingService | setSeoMetadata | request | locale | string
MarketingService | setSeoMetadata | request | title | string |  | (nullable)
MarketingService | setSeoMetadata | request | metaDescription | string |  | (nullable)
MarketingService | setSeoMetadata | request | keywords | array of string
MarketingService | setSeoMetadata | request | canonicalUrl | string |  | (nullable)
MarketingService | setSeoMetadata | request | slug | string |  | 22.11.6. (nullable)
MarketingService | setSeoMetadata | request | hreflang | object |  | 22.11.11.
MarketingService | setSeoMetadata | request | schemaOrgType | string |  | (nullable)
MarketingService | setSeoMetadata | request | openGraph | object
MarketingService | setSeoMetadata | request | isAutoGenerated | boolean |  | 22.11.2. (default True)
MarketingService | setSeoMetadata | request | noIndex | boolean |  | (default False)
MarketingService | setSeoMetadata | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setSeoMetadata | response | id | string (uuid) | yes | (read-only)
MarketingService | setSeoMetadata | response | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | setSeoMetadata | response | entityId | string (uuid) | yes
MarketingService | setSeoMetadata | response | locale | string
MarketingService | setSeoMetadata | response | title | string |  | (nullable)
MarketingService | setSeoMetadata | response | metaDescription | string |  | (nullable)
MarketingService | setSeoMetadata | response | keywords | array of string
MarketingService | setSeoMetadata | response | canonicalUrl | string |  | (nullable)
MarketingService | setSeoMetadata | response | slug | string |  | 22.11.6. (nullable)
MarketingService | setSeoMetadata | response | hreflang | object |  | 22.11.11.
MarketingService | setSeoMetadata | response | schemaOrgType | string |  | (nullable)
MarketingService | setSeoMetadata | response | openGraph | object
MarketingService | setSeoMetadata | response | isAutoGenerated | boolean |  | 22.11.2. (default True)
MarketingService | setSeoMetadata | response | noIndex | boolean |  | (default False)
MarketingService | setSeoMetadata | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setSeoMetadata | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setSiteSetupProgress | request | id | string (uuid) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | request | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | setSiteSetupProgress | request | currentStep | object |  | (nullable)
WhiteLabelService | setSiteSetupProgress | request | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | setSiteSetupProgress | request | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | setSiteSetupProgress | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setSiteSetupProgress | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | response | id | string (uuid) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | response | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | setSiteSetupProgress | response | currentStep | object |  | (nullable)
WhiteLabelService | setSiteSetupProgress | response | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | setSiteSetupProgress | response | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | setSiteSetupProgress | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setSiteSetupProgress | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setStoreAccounts | request | accounts | array of StoreAccount | yes | (max items 2)
WhiteLabelService | setStoreAccounts | request | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | setStoreAccounts | request | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | setStoreAccounts | request | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | setStoreAccounts | request | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | setStoreAccounts | request | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key. (nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].passTypeIdentifier | string |  | The Apple Wallet Pass Type ID (pass.<reverse-domain>), registered in the client's own Apple Developer account, one per brand (Chinmay, 12 October 2026: the client owns the certificate; CHG-R6-033). (pattern ^pass\.[A-Za-z0-9.-]+$; nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].passCertificateSecretRef | string |  | The Pass Type ID certificate, from the client's Apple Developer account. (nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].passCertificatePassword | string (password) |  | The password of the .p12 sent in passCertificateSecretRef. (nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].hasPassCertificate | boolean |  | (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].passCertificateExpiresAt | string (date-time) |  | When the pass certificate expires, read from the certificate when it is stored (CHG-R6-033). (read-only; nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].listing | object |  | The store listing.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.category | string
WhiteLabelService | setStoreAccounts | request | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | setStoreAccounts | request | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | setStoreAccounts | request | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | setStoreAccounts | request | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts | array of StoreAccount | yes
WhiteLabelService | setStoreAccounts | response | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | setStoreAccounts | response | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | setStoreAccounts | response | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | setStoreAccounts | response | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | setStoreAccounts | response | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key. (nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].passTypeIdentifier | string |  | The Apple Wallet Pass Type ID (pass.<reverse-domain>), registered in the client's own Apple Developer account, one per brand (Chinmay, 12 October 2026: the client owns the certificate; CHG-R6-033). (pattern ^pass\.[A-Za-z0-9.-]+$; nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].passCertificateSecretRef | string |  | The Pass Type ID certificate, from the client's Apple Developer account. (nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].passCertificatePassword | string (password) |  | The password of the .p12 sent in passCertificateSecretRef. (nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].hasPassCertificate | boolean |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].passCertificateExpiresAt | string (date-time) |  | When the pass certificate expires, read from the certificate when it is stored (CHG-R6-033). (read-only; nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].listing | object |  | The store listing.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.category | string
WhiteLabelService | setStoreAccounts | response | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | setStoreAccounts | response | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | setStoreAccounts | response | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | setStoreAccounts | response | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setStoreAccounts | response | items | array of object | yes
WhiteLabelService | setStoreAccounts | response | items[].item | enum (appleDunsNumber, appleDeveloperAccount, googlePlayDeveloperAccount, storeListing, appIcons, publishedConfiguration) | yes
WhiteLabelService | setStoreAccounts | response | items[].done | boolean | yes
WhiteLabelService | setStoreAccounts | response | items[].clientOwned | boolean |  | True for the three accounts, which only the client can open.
WhiteLabelService | setStoreAccounts | response | items[].guidance | string |  | What to do next, in the operator's language.
WhiteLabelService | setStoreAccounts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setSubscription | request | planId | string (uuid) | yes
PlatformService | setSubscription | request | planVersion | string |  | Defaults to the current version.
PlatformService | setSubscription | request | effectiveFrom | string (date) |  | Optional, and set by the server if omitted.
PlatformService | setSubscription | request | prorate | boolean |  | An upgrade is always prorated and a downgrade, which starts at renewal, never is (audit R214 (1)). (default True)
PlatformService | setSubscription | request | note | string |  | (max length 500)
PlatformService | setSubscription | response | issuingLegalEntity | enum (ainfiniteAiUae, ainfiniteAiIndia) |  | The TICVAI legal entity that invoices this tenant (the lead, 25 October 2026, r10 round 3, ADAM CR-202; CHG-R10ID-023): Ainfinite AI UAE or Ainfinite AI India.
PlatformService | setSubscription | response | currencyCode | string |  | The ISO 4217 currency of this contract's currentPrice (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored with its currency on the row, si… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | setSubscription | response | tenantId | string (uuid) | yes
PlatformService | setSubscription | response | planId | string (uuid) | yes
PlatformService | setSubscription | response | planName | string
PlatformService | setSubscription | response | planVersion | string | yes
PlatformService | setSubscription | response | status | enum (trial, active, pastDue, cancelled, expired) | yes
PlatformService | setSubscription | response | startsAt | string (date) | yes
PlatformService | setSubscription | response | renewsAt | string (date) |  | (nullable)
PlatformService | setSubscription | response | cancelledAt | string (date) |  | (nullable)
PlatformService | setSubscription | response | scheduledChange | object |  | A downgrade waiting for the next renewal (decided 28 September, audit R214 (1)). (read-only; nullable)
PlatformService | setSubscription | response | scheduledChange.planId | string (uuid)
PlatformService | setSubscription | response | scheduledChange.planVersion | string
PlatformService | setSubscription | response | scheduledChange.effectiveFrom | string (date) |  | Always the renewsAt it was scheduled against.
PlatformService | setSubscription | response | currentPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | setSubscription | response | currentPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | setSubscription | response | currentPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | setSubscription | response | currentPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | setSubscription | response | billingPeriod | string
PlatformService | setSubscription | param (path) | tenantId | string (uuid) | yes
PlatformService | setSubscription | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setSubstitutionRules | request | rules | array of SubstitutionRule | yes
FnbService | setSubstitutionRules | request | rules[].id | string (uuid) | yes
FnbService | setSubstitutionRules | request | rules[].recipeId | string (uuid) | yes | The recipe the rule applies to (decided 28 September, audit R125 (10)).
FnbService | setSubstitutionRules | request | rules[].fromIngredientId | string (uuid) | yes
FnbService | setSubstitutionRules | request | rules[].toIngredientId | string (uuid) | yes
FnbService | setSubstitutionRules | request | rules[].ratio | number |  | Not always one to one. (default 1)
FnbService | setSubstitutionRules | request | rules[].allergensAdded | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setSubstitutionRules | request | rules[].allergensRemoved | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setSubstitutionRules | request | rules[].conditions | array of enum (outOfStock, seasonal, guestRequest, costSaving, always)
FnbService | setSubstitutionRules | request | rules[].requiresApproval | boolean |  | True where the swap changes an allergen. (default False)
FnbService | setSubstitutionRules | request | rules[].isActive | boolean |  | (default True)
FnbService | setSubstitutionRules | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setSubstitutionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setSuggestionProvider | request | assignments | array of SuggestionProviderAssignment | yes | (min items 1)
AiService | setSuggestionProvider | request | assignments[].kind | SuggestionKind: enum (price, replenishment, requisition, demandForecast, prepPlan, menuEngineering, staffing, slaTarget, …) | yes | What is being suggested.
AiService | setSuggestionProvider | request | assignments[].basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | setSuggestionProvider | request | assignments[].producerRef | string | yes | The rule name, or the model id and version — the same value Suggestion.producerRef records on each answer.
AiService | setSuggestionProvider | request | assignments[].shadowProducerRef | string |  | Runs alongside and is recorded, never shown. (nullable)
AiService | setSuggestionProvider | request | assignments[].guardRails | object |  | Bounds the answer must fall within. (nullable)
AiService | setSuggestionProvider | response | assignments | array of SuggestionProviderAssignment | yes
AiService | setSuggestionProvider | response | assignments[].kind | SuggestionKind: enum (price, replenishment, requisition, demandForecast, prepPlan, menuEngineering, staffing, slaTarget, …) | yes | What is being suggested.
AiService | setSuggestionProvider | response | assignments[].basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | setSuggestionProvider | response | assignments[].producerRef | string | yes | The rule name, or the model id and version — the same value Suggestion.producerRef records on each answer.
AiService | setSuggestionProvider | response | assignments[].shadowProducerRef | string |  | Runs alongside and is recorded, never shown. (nullable)
AiService | setSuggestionProvider | response | assignments[].guardRails | object |  | Bounds the answer must fall within. (nullable)
AiService | setSuggestionProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setTableCombinations | request | combinations | array of TableCombination | yes
FnbService | setTableCombinations | request | combinations[].id | string (uuid) |  | (read-only)
FnbService | setTableCombinations | request | combinations[].outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setTableCombinations | request | combinations[].tableIds | array of string (uuid) | yes | (min items 2)
FnbService | setTableCombinations | request | combinations[].combinedCovers | integer | yes | (min 1)
FnbService | setTableCombinations | request | combinations[].setupMinutes | integer |  | (default 5)
FnbService | setTableCombinations | request | combinations[].scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setTableCombinations | response | combinations | array of TableCombination | yes
FnbService | setTableCombinations | response | combinations[].id | string (uuid) |  | (read-only)
FnbService | setTableCombinations | response | combinations[].outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setTableCombinations | response | combinations[].tableIds | array of string (uuid) | yes | (min items 2)
FnbService | setTableCombinations | response | combinations[].combinedCovers | integer | yes | (min 1)
FnbService | setTableCombinations | response | combinations[].setupMinutes | integer |  | (default 5)
FnbService | setTableCombinations | response | combinations[].scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setTableCombinations | param (path) | outletId | string (uuid) | yes
FnbService | setTableCombinations | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setTableCombinations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setTableLayout | request | tables | array of TableLayoutItem | yes
FnbService | setTableLayout | request | tables[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | setTableLayout | request | tables[].id | string (uuid) | yes | The table this item updates, or the id of the table it adds (a UUIDv7 the client makes).
FnbService | setTableLayout | request | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | setTableLayout | request | tables[].capacity | integer | yes | (min 1)
FnbService | setTableLayout | request | tables[].zone | string |  | (nullable)
FnbService | setTableLayout | request | tables[].position | object
FnbService | setTableLayout | request | tables[].position.x | number
FnbService | setTableLayout | request | tables[].position.y | number
FnbService | setTableLayout | request | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | setTableLayout | request | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | setTableLayout | request | tables[].codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | setTableLayout | response | outletId | string (uuid) | yes
FnbService | setTableLayout | response | zones | array of string
FnbService | setTableLayout | response | tables | array of TableState | yes
FnbService | setTableLayout | response | tables[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | setTableLayout | response | tables[].id | string (uuid) | yes | (read-only)
FnbService | setTableLayout | response | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | setTableLayout | response | tables[].capacity | integer | yes | (min 1)
FnbService | setTableLayout | response | tables[].zone | string |  | (nullable)
FnbService | setTableLayout | response | tables[].position | object
FnbService | setTableLayout | response | tables[].position.x | number
FnbService | setTableLayout | response | tables[].position.y | number
FnbService | setTableLayout | response | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | setTableLayout | response | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | setTableLayout | response | tables[].codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | setTableLayout | response | tables[].status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | setTableLayout | response | tables[].visitId | string (uuid) |  | (nullable)
FnbService | setTableLayout | response | tables[].covers | integer |  | (nullable)
FnbService | setTableLayout | response | tables[].seatedAt | string (date-time) |  | (nullable)
FnbService | setTableLayout | response | tables[].serverPrincipalId | string (uuid) |  | (nullable)
FnbService | setTableLayout | response | tables[].billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | setTableLayout | response | tables[].billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setTableLayout | response | tables[].billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setTableLayout | response | tables[].billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setTableLayout | param (path) | outletId | string (uuid) | yes
FnbService | setTableLayout | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setTableLayout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setTheme | request | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | setTheme | request | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | setTheme | request | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | setTheme | request | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | setTheme | request | venueSkins | array of object |  | The guest app skin each venue takes (ADAM CR-280, option B, 28 October 2026; CHG-R11TEN-007): one entry per venue, naming one of the approved app design's skins (handoff/design-tokens/guest-app.yaml,… (default [])
WhiteLabelService | setTheme | request | venueSkins[].venueId | string (uuid) | yes
WhiteLabelService | setTheme | request | venueSkins[].skinKey | GuestAppSkinKey: enum (park, water, stadium, theatre, dining, kids, museum, rooms, …) | yes | The guest app's skins per venue kind, as the approved Mobile App v4 design draws them (handoff/design-tokens/guest-app.yaml skins.byVenueKind; ADAM CR-280, CHG-R11TEN-007).
WhiteLabelService | setTheme | request | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | setTheme | request | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.payButton | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.link | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.badge | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | setTheme | response | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | setTheme | response | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | setTheme | response | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | setTheme | response | venueSkins | array of object |  | The guest app skin each venue takes (ADAM CR-280, option B, 28 October 2026; CHG-R11TEN-007): one entry per venue, naming one of the approved app design's skins (handoff/design-tokens/guest-app.yaml,… (default [])
WhiteLabelService | setTheme | response | venueSkins[].venueId | string (uuid) | yes
WhiteLabelService | setTheme | response | venueSkins[].skinKey | GuestAppSkinKey: enum (park, water, stadium, theatre, dining, kids, museum, rooms, …) | yes | The guest app's skins per venue kind, as the approved Mobile App v4 design draws them (handoff/design-tokens/guest-app.yaml skins.byVenueKind; ADAM CR-280, CHG-R11TEN-007).
WhiteLabelService | setTheme | response | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | setTheme | response | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.payButton | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.link | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.badge | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setTheme | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
OrderService | setTillShiftPolicy | request | id | string (uuid) |  | (read-only)
OrderService | setTillShiftPolicy | request | venueId | string (uuid) | yes
OrderService | setTillShiftPolicy | request | scopePath | string |  | (read-only)
OrderService | setTillShiftPolicy | request | requireOpenApproval | boolean |  | Every shift opens pendingApproval and waits for approveShiftOpen (SHIFT_APPROVE_OPEN). (default False)
OrderService | setTillShiftPolicy | request | openingFloatTolerance | object |  | How far a declared opening float may differ from the box's allocated float before the shift waits for approval (states/shift.yaml, pendingApproval). (nullable)
OrderService | setTillShiftPolicy | request | openingFloatTolerance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setTillShiftPolicy | request | openingFloatTolerance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setTillShiftPolicy | request | openingFloatTolerance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setTillShiftPolicy | request | depositBoxRequired | boolean |  | A shift cannot open without a deposit box (OpenShiftRequest.depositBoxCode); refused 400 otherwise. (default True)
OrderService | setTillShiftPolicy | request | bagNumberRequired | boolean |  | A shift cannot open without a bag number (OpenShiftRequest.bagNumber). (default False)
OrderService | setTillShiftPolicy | request | requireCloseApproval | boolean |  | Every counted shift waits in pendingClosure for approveShiftClose (SHIFT_APPROVE_CLOSE), even within the variance threshold. (default False)
OrderService | setTillShiftPolicy | request | autoCloseAfterHours | integer |  | Hours after which an open or suspended shift nobody closed is closed by the inactivity job as autoClosed and the supervisors are told (states/shift.yaml). (min 1; max 48; default 14; nullable)
OrderService | setTillShiftPolicy | request | noSaleAlertCount | integer |  | No-sales in one shift (recordNoSale) at which the supervisors are alerted on the venue's alerting channel; the count is on POS-020. (min 1; default 10; nullable)
OrderService | setTillShiftPolicy | request | updatedAt | string (date-time) |  | (read-only)
OrderService | setTillShiftPolicy | response | id | string (uuid) |  | (read-only)
OrderService | setTillShiftPolicy | response | venueId | string (uuid) | yes
OrderService | setTillShiftPolicy | response | scopePath | string |  | (read-only)
OrderService | setTillShiftPolicy | response | requireOpenApproval | boolean |  | Every shift opens pendingApproval and waits for approveShiftOpen (SHIFT_APPROVE_OPEN). (default False)
OrderService | setTillShiftPolicy | response | openingFloatTolerance | object |  | How far a declared opening float may differ from the box's allocated float before the shift waits for approval (states/shift.yaml, pendingApproval). (nullable)
OrderService | setTillShiftPolicy | response | openingFloatTolerance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setTillShiftPolicy | response | openingFloatTolerance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setTillShiftPolicy | response | openingFloatTolerance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setTillShiftPolicy | response | depositBoxRequired | boolean |  | A shift cannot open without a deposit box (OpenShiftRequest.depositBoxCode); refused 400 otherwise. (default True)
OrderService | setTillShiftPolicy | response | bagNumberRequired | boolean |  | A shift cannot open without a bag number (OpenShiftRequest.bagNumber). (default False)
OrderService | setTillShiftPolicy | response | requireCloseApproval | boolean |  | Every counted shift waits in pendingClosure for approveShiftClose (SHIFT_APPROVE_CLOSE), even within the variance threshold. (default False)
OrderService | setTillShiftPolicy | response | autoCloseAfterHours | integer |  | Hours after which an open or suspended shift nobody closed is closed by the inactivity job as autoClosed and the supervisors are told (states/shift.yaml). (min 1; max 48; default 14; nullable)
OrderService | setTillShiftPolicy | response | noSaleAlertCount | integer |  | No-sales in one shift (recordNoSale) at which the supervisors are alerted on the venue's alerting channel; the count is on POS-020. (min 1; default 10; nullable)
OrderService | setTillShiftPolicy | response | updatedAt | string (date-time) |  | (read-only)
OrderService | setTillShiftPolicy | param (path) | venueId | string (uuid) | yes
OrderService | setTillShiftPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setTrackingTechnology | request | technologyId | string (uuid) |  | (read-only)
MarketingService | setTrackingTechnology | request | name | string | yes | The cookie, SDK, pixel or storage key as it appears on the device. (max length 200)
MarketingService | setTrackingTechnology | request | provider | string | yes | (max length 150)
MarketingService | setTrackingTechnology | request | domainApplication | string |  | The domain, or the app and version, it was found on. (max length 255; nullable)
MarketingService | setTrackingTechnology | request | technologyType | enum (firstPartyCookie, thirdPartyCookie, mobileSdk, analyticsTracker, advertisingPixel, sessionTechnology, personalisationTechnology, embeddedService, …) | yes
MarketingService | setTrackingTechnology | request | category | enum (strictlyNecessary, functional, analytics, personalisation, marketing, other) |  | Null until an administrator classifies it. (nullable)
MarketingService | setTrackingTechnology | request | otherCategoryLabel | string |  | The organisation-defined category, when category is other. (max length 80; nullable)
MarketingService | setTrackingTechnology | request | purpose | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | request | dataCollected | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | request | durationDays | integer |  | Null for session storage. (min 0; nullable)
MarketingService | setTrackingTechnology | request | isThirdParty | boolean | yes
MarketingService | setTrackingTechnology | request | channels | array of enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | (min items 1)
MarketingService | setTrackingTechnology | request | countries | array of string |  | Empty means every country.
MarketingService | setTrackingTechnology | request | processingPurposeCode | string |  | The DataProcessingPurposeLawfulBasisRegistryView.purposeCode it serves. (nullable)
MarketingService | setTrackingTechnology | request | consentRequired | boolean |  | False only for strictlyNecessary. (default True)
MarketingService | setTrackingTechnology | request | privacyInformation | string |  | What the preference centre tells the guest about it. (max length 1000; nullable)
MarketingService | setTrackingTechnology | request | source | enum (manual, scan) |  | (default manual; read-only)
MarketingService | setTrackingTechnology | request | status | enum (detected, approved, blocked, retired) | yes | detected is treated as blocked until approved.
MarketingService | setTrackingTechnology | request | firstDetectedAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | request | lastSeenAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setTrackingTechnology | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setTrackingTechnology | response | technologyId | string (uuid) |  | (read-only)
MarketingService | setTrackingTechnology | response | name | string | yes | The cookie, SDK, pixel or storage key as it appears on the device. (max length 200)
MarketingService | setTrackingTechnology | response | provider | string | yes | (max length 150)
MarketingService | setTrackingTechnology | response | domainApplication | string |  | The domain, or the app and version, it was found on. (max length 255; nullable)
MarketingService | setTrackingTechnology | response | technologyType | enum (firstPartyCookie, thirdPartyCookie, mobileSdk, analyticsTracker, advertisingPixel, sessionTechnology, personalisationTechnology, embeddedService, …) | yes
MarketingService | setTrackingTechnology | response | category | enum (strictlyNecessary, functional, analytics, personalisation, marketing, other) |  | Null until an administrator classifies it. (nullable)
MarketingService | setTrackingTechnology | response | otherCategoryLabel | string |  | The organisation-defined category, when category is other. (max length 80; nullable)
MarketingService | setTrackingTechnology | response | purpose | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | response | dataCollected | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | response | durationDays | integer |  | Null for session storage. (min 0; nullable)
MarketingService | setTrackingTechnology | response | isThirdParty | boolean | yes
MarketingService | setTrackingTechnology | response | channels | array of enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | (min items 1)
MarketingService | setTrackingTechnology | response | countries | array of string |  | Empty means every country.
MarketingService | setTrackingTechnology | response | processingPurposeCode | string |  | The DataProcessingPurposeLawfulBasisRegistryView.purposeCode it serves. (nullable)
MarketingService | setTrackingTechnology | response | consentRequired | boolean |  | False only for strictlyNecessary. (default True)
MarketingService | setTrackingTechnology | response | privacyInformation | string |  | What the preference centre tells the guest about it. (max length 1000; nullable)
MarketingService | setTrackingTechnology | response | source | enum (manual, scan) |  | (default manual; read-only)
MarketingService | setTrackingTechnology | response | status | enum (detected, approved, blocked, retired) | yes | detected is treated as blocked until approved.
MarketingService | setTrackingTechnology | response | firstDetectedAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | response | lastSeenAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setTrackingTechnology | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setTrackingTechnology | param (path) | technologyId | string (uuid) | yes | The record's id (ADAM CR-245).
MarketingService | setTrackingTechnology | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setTransportFareTable | request | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | setTransportFareTable | request | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | request | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | request | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | request | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | request | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | request | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | request | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | request | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | request | matrix | array of object |  | matrix only.
VenueOpsService | setTransportFareTable | request | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | request | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | request | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | request | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | request | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | request | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | request | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | setTransportFareTable | request | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | setTransportFareTable | request | passengerTypes[].name | LocalisedText | yes
VenueOpsService | setTransportFareTable | request | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | setTransportFareTable | request | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | setTransportFareTable | request | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | request | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | request | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | setTransportFareTable | request | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | setTransportFareTable | request | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | setTransportFareTable | request | effectiveFrom | string (date-time) | yes
VenueOpsService | setTransportFareTable | response | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | setTransportFareTable | response | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | response | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | response | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | response | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | response | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | response | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | response | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | response | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | response | matrix | array of object |  | matrix only.
VenueOpsService | setTransportFareTable | response | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | response | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | response | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | response | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | response | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | setTransportFareTable | response | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | setTransportFareTable | response | passengerTypes[].name | LocalisedText | yes
VenueOpsService | setTransportFareTable | response | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | setTransportFareTable | response | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | setTransportFareTable | response | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | response | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | response | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | setTransportFareTable | response | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | setTransportFareTable | response | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | setTransportFareTable | response | effectiveFrom | string (date-time) | yes
VenueOpsService | setTransportFareTable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | effectiveTo | string (date-time) |  | When the next version takes over; null when none is set (CHG-RUL-012). (read-only; nullable)
VenueOpsService | setTransportFareTable | response | upcoming | object |  | The next version, set and not yet in force (CHG-RUL-012); null when none. (read-only; nullable)
VenueOpsService | setTransportFareTable | response | upcoming.id | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | upcoming.effectiveFrom | string (date-time)
VenueOpsService | setTransportFareTable | param (path) | routeId | string (uuid) | yes
VenueOpsService | setTransportFareTable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setTransportRouteStatus | request | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | setTransportRouteStatus | request | reason | string |  | (max length 500)
VenueOpsService | setTransportRouteStatus | response | venueId | string (uuid) | yes
VenueOpsService | setTransportRouteStatus | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | setTransportRouteStatus | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | setTransportRouteStatus | response | name | LocalisedText | yes
VenueOpsService | setTransportRouteStatus | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | setTransportRouteStatus | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | setTransportRouteStatus | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | setTransportRouteStatus | response | stops | array of RouteStop | yes
VenueOpsService | setTransportRouteStatus | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportRouteStatus | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | setTransportRouteStatus | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | setTransportRouteStatus | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | setTransportRouteStatus | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportRouteStatus | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | setTransportRouteStatus | response | stops[].station | Station
VenueOpsService | setTransportRouteStatus | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | setTransportRouteStatus | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | setTransportRouteStatus | response | stops[].station.name | LocalisedText | yes
VenueOpsService | setTransportRouteStatus | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | setTransportRouteStatus | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | setTransportRouteStatus | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | setTransportRouteStatus | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportRouteStatus | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | setTransportRouteStatus | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportRouteStatus | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | setTransportRouteStatus | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | setTransportRouteStatus | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | setTransportRouteStatus | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | setTransportRouteStatus | response | statusReason | string |  | Why the route's status last changed (setTransportRouteStatus). (max length 500; read-only; nullable)
VenueOpsService | setTransportRouteStatus | param (path) | routeId | string (uuid) | yes
VenueOpsService | setTransportRouteStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setTurnstileMode | request | operatingMode | AccessPointOperatingMode: enum (normal, freeFlow, dropArm, closed, podium, maintenance) | yes | BL-107 and BL-109.
AccessService | setTurnstileMode | request | mode | object |  | Optional narrowing within normal or podium: freeRotation or closed. (nullable)
AccessService | setTurnstileMode | request | reason | string |  | (max length 200)
AccessService | setTurnstileMode | request | effectiveAt | string (date-time) |  | When the change takes effect. (nullable)
AccessService | setTurnstileMode | response | id | string (uuid) | yes
AccessService | setTurnstileMode | response | code | string | yes
AccessService | setTurnstileMode | response | name | string | yes
AccessService | setTurnstileMode | response | venueId | string (uuid) | yes
AccessService | setTurnstileMode | response | accessAreaId | string (uuid) |  | The zone this access point admits to (R8 blocker FOUNDATION-AI-C12, CHG-R8MIG-004): an access.access_area row whose entityType is zone (named for the table it keys, as every key is). (nullable)
AccessService | setTurnstileMode | response | scopePath | string
AccessService | setTurnstileMode | response | externalCredentialSources | object |  | BL-108.
AccessService | setTurnstileMode | response | scanAnomalyRules | object |  | BL-104.
AccessService | setTurnstileMode | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | setTurnstileMode | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | setTurnstileMode | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | setTurnstileMode | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | setTurnstileMode | response | temporaryClosure | object |  | What the access point does while its attraction is temporarily closed (decided 2 October 2026, Chinmay, batch 6 set 9, BO-147: "Deny + reopening time + a virtual-queue return window where enabled"; D… (nullable)
AccessService | setTurnstileMode | response | temporaryClosure.isClosed | boolean |  | (default False)
AccessService | setTurnstileMode | response | temporaryClosure.reason | string |  | Shown to staff; the guest sees "Attraction temporarily closed". (max length 200; nullable)
AccessService | setTurnstileMode | response | temporaryClosure.reopensAt | string (date-time) |  | When it is expected to reopen; shown to the guest when known. (nullable)
AccessService | setTurnstileMode | response | temporaryClosure.offerVirtualQueueReturn | boolean |  | Offer a virtual-queue return window at the denied scan, where the attraction has a queue. (default False)
AccessService | setTurnstileMode | response | temporaryClosure.queueId | string (uuid) |  | The virtual queue the return window is taken in. (nullable)
AccessService | setTurnstileMode | response | antiPassbackEnabled | boolean
AccessService | setTurnstileMode | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | setTurnstileMode | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | setTurnstileMode | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | setTurnstileMode | response | geofence.latitude | number
AccessService | setTurnstileMode | response | geofence.longitude | number
AccessService | setTurnstileMode | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | setTurnstileMode | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setTurnstileMode | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setTurnstileMode | response | isActive | boolean | yes
AccessService | setTurnstileMode | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | setTurnstileMode | response | directionEffectiveAt | string (date-time) |  | When a direction change set by setAccessPointDirection takes effect; held pending until then. (read-only; nullable)
AccessService | setTurnstileMode | response | directionChangeReason | string |  | Why the gate was last turned round (setAccessPointDirection). (max length 200; read-only; nullable)
AccessService | setTurnstileMode | param (path) | accessPointId | string (uuid) | yes
AccessService | setTurnstileMode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setVenueMapArtwork | request | baseAssetId | string (uuid) | yes | The illustrated map (an image asset, PNG or JPG, up to about 12,000 px wide). (nullable)
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment | object |  | Required with an image. (nullable)
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.imageWidthPx | integer | yes | (min 1)
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.imageHeightPx | integer | yes | (min 1)
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.anchors | array of object | yes | (min items 2; max items 4)
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.anchors[].planX | number | yes
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.anchors[].planY | number | yes
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.anchors[].imageX | number | yes
VenueOpsService | setVenueMapArtwork | request | baseImageAlignment.anchors[].imageY | number | yes
VenueOpsService | setVenueMapArtwork | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setVenueMapArtwork | response | name | string | yes
VenueOpsService | setVenueMapArtwork | response | venueId | string (uuid) | yes
VenueOpsService | setVenueMapArtwork | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | setVenueMapArtwork | response | kind | enum (park, floor, zone, parking)
VenueOpsService | setVenueMapArtwork | response | floorLevel | integer |  | (nullable)
VenueOpsService | setVenueMapArtwork | response | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | setVenueMapArtwork | response | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | setVenueMapArtwork | response | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | setVenueMapArtwork | response | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | setVenueMapArtwork | response | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.imageWidthPx | integer
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.imageHeightPx | integer
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.anchors[].planX | number
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.anchors[].planY | number
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.anchors[].imageX | number
VenueOpsService | setVenueMapArtwork | response | baseImageAlignment.anchors[].imageY | number
VenueOpsService | setVenueMapArtwork | response | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | setVenueMapArtwork | response | boundsGeoJson | string |  | (nullable)
VenueOpsService | setVenueMapArtwork | response | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | setVenueMapArtwork | response | modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | setVenueMapArtwork | response | navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | setVenueMapArtwork | response | modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | setVenueMapArtwork | response | modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | setVenueMapArtwork | response | modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | setVenueMapArtwork | response | modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | setVenueMapArtwork | response | modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | setVenueMapArtwork | response | modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints[].label | string | yes
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints[].x | number | yes
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints[].z | number | yes
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints[].lat | number | yes
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints[].lng | number | yes
VenueOpsService | setVenueMapArtwork | response | modelTransform.controlPoints[].residualMetres | number |  | Measured at import. (read-only; nullable)
VenueOpsService | setVenueMapArtwork | response | model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | setVenueMapArtwork | param (path) | mapId | string (uuid) | yes
VenueOpsService | setVenueMapArtwork | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setVenuePoint | request | id | string (uuid) | yes | (read-only)
VenueOpsService | setVenuePoint | request | mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | setVenuePoint | request | kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | setVenuePoint | request | name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | setVenuePoint | request | nameLocalised | object |  | (nullable)
VenueOpsService | setVenuePoint | request | position | object | yes | Drawing coordinates.
VenueOpsService | setVenuePoint | request | position.x | number | yes
VenueOpsService | setVenuePoint | request | position.y | number | yes
VenueOpsService | setVenuePoint | request | outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | setVenuePoint | request | productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | setVenuePoint | request | accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | setVenuePoint | request | isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | setVenuePoint | request | openingHours | string |  | (nullable)
VenueOpsService | setVenuePoint | request | iconRef | string |  | (nullable)
VenueOpsService | setVenuePoint | request | isActive | boolean |  | (default True)
VenueOpsService | setVenuePoint | request | isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | setVenuePoint | request | isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | setVenuePoint | request | description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | request | media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | setVenuePoint | request | media[].assetId | string (uuid) | yes
VenueOpsService | setVenuePoint | request | media[].kind | enum (image, video) | yes
VenueOpsService | setVenuePoint | request | media[].isPrimary | boolean |  | (default False)
VenueOpsService | setVenuePoint | request | media[].altText | string |  | (max length 200; nullable)
VenueOpsService | setVenuePoint | request | featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | request | featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | setVenuePoint | request | featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | setVenuePoint | request | featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | setVenuePoint | request | typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | setVenuePoint | request | interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | setVenuePoint | request | cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | setVenuePoint | request | retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | setVenuePoint | request | pointId | string (uuid) |  | The point to amend. (nullable)
VenueOpsService | setVenuePoint | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setVenuePoint | response | mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | setVenuePoint | response | kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | setVenuePoint | response | name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | setVenuePoint | response | nameLocalised | object |  | (nullable)
VenueOpsService | setVenuePoint | response | position | object | yes | Drawing coordinates.
VenueOpsService | setVenuePoint | response | position.x | number | yes
VenueOpsService | setVenuePoint | response | position.y | number | yes
VenueOpsService | setVenuePoint | response | outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | setVenuePoint | response | productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | setVenuePoint | response | accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | setVenuePoint | response | isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | setVenuePoint | response | openingHours | string |  | (nullable)
VenueOpsService | setVenuePoint | response | iconRef | string |  | (nullable)
VenueOpsService | setVenuePoint | response | isActive | boolean |  | (default True)
VenueOpsService | setVenuePoint | response | isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | setVenuePoint | response | isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | setVenuePoint | response | description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | response | media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | setVenuePoint | response | media[].assetId | string (uuid) | yes
VenueOpsService | setVenuePoint | response | media[].kind | enum (image, video) | yes
VenueOpsService | setVenuePoint | response | media[].isPrimary | boolean |  | (default False)
VenueOpsService | setVenuePoint | response | media[].altText | string |  | (max length 200; nullable)
VenueOpsService | setVenuePoint | response | featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | response | featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | setVenuePoint | response | featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | setVenuePoint | response | featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | setVenuePoint | response | typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | setVenuePoint | response | interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | setVenuePoint | response | cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | setVenuePoint | response | retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | setVenuePoint | param (path) | mapId | string (uuid) | yes
VenueOpsService | setVenuePoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setVenueSettings | request | contact | object |  | How a guest reaches this venue (R8 blocker WHITE-C16, the storage-sat lane's request 5; CHG-R8MIG-011): phone, email, WhatsApp, address and opening-hours prose, one jsonb column, written by the venue… (nullable)
TenancyService | setVenueSettings | request | contact.phone | string |  | (nullable)
TenancyService | setVenueSettings | request | contact.email | string (email) |  | (nullable)
TenancyService | setVenueSettings | request | contact.whatsapp | string |  | (nullable)
TenancyService | setVenueSettings | request | contact.address | object |  | (nullable)
TenancyService | setVenueSettings | request | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
TenancyService | setVenueSettings | request | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setVenueSettings | request | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | setVenueSettings | request | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | setVenueSettings | request | businessDayCutoff | string |  | When the venue's business day closes (Chinmay, 6 October 2026, from the Vivaticket comparison: the business day closes at 12 midnight, with a change request to make the cut-off configurable, default… (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 00:00; nullable)
TenancyService | setVenueSettings | request | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | setVenueSettings | request | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | setVenueSettings | request | supportHours | object |  | CF-100.
TenancyService | setVenueSettings | request | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | setVenueSettings | request | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | setVenueSettings | request | supportHours.windows | array of object
TenancyService | setVenueSettings | request | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | request | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | setVenueSettings | request | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | setVenueSettings | request | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | setVenueSettings | request | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | setVenueSettings | request | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | setVenueSettings | request | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | setVenueSettings | request | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | setVenueSettings | request | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | setVenueSettings | request | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | setVenueSettings | request | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | setVenueSettings | request | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | setVenueSettings | request | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | setVenueSettings | request | biometrics.consentFormId | string (uuid) |  | The venue's own consent form, which every biometric capture is taken on (decided 2 October 2026, Chinmay, batch 4, BO-188: "Consent first, on the venue's consent form"; DEC-128, DEC-549; CHG-CSP-018). (nullable)
TenancyService | setVenueSettings | request | biometrics.templatesHeldByTicvai | boolean |  | True where TICVAI's platform stores this venue's biometric templates (rather than the venue's own on-premises reader estate). (read-only)
TenancyService | setVenueSettings | request | biometrics.allowMinors | boolean |  | Whether this venue enrols minors at all (decided 2 October 2026, Chinmay, critical set 1, BO-187 and CMS-029: "Guardian consent on the venue's form; minor age per country; the venue can switch minors… (default True)
TenancyService | setVenueSettings | request | biometrics.accreditationFaceMatching | object |  | Face matching to find duplicate accreditation applicants, off unless the venue enables it (decided 2 October 2026, Chinmay, critical set 3, BO-631: "Only where the venue enables it, with applicant co… (nullable)
TenancyService | setVenueSettings | request | biometrics.accreditationFaceMatching.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettings | request | biometrics.accreditationFaceMatching.legalSignOffReference | string |  | The venue's own reference for its legal sign-off; the platform records that one was named, by whom and when. (max length 200; nullable)
TenancyService | setVenueSettings | request | biometrics.accreditationFaceMatching.signedOffByPrincipalId | string (uuid) |  | (read-only; nullable)
TenancyService | setVenueSettings | request | biometrics.accreditationFaceMatching.signedOffAt | string (date-time) |  | (read-only; nullable)
TenancyService | setVenueSettings | request | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | setVenueSettings | request | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettings | request | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | setVenueSettings | request | segregatedAccess.schedule | array of object
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | setVenueSettings | request | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | setVenueSettings | request | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | setVenueSettings | request | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | setVenueSettings | request | alerting | object |  | CF-134.
TenancyService | setVenueSettings | request | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | setVenueSettings | request | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | setVenueSettings | request | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | setVenueSettings | request | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | setVenueSettings | request | chargeCurrencies | array of string |  | Which currencies a guest may select and pay in (decided 2 October 2026, Chinmay; CHG-FIN-001; MoM 10 Aug 2026 4.7 option (b), DI-211). (nullable)
TenancyService | setVenueSettings | request | stepMinutes | enum (15, 30, 60) |  | The venue's start-time step for a space sold by the hour (accepted 26 October 2026, Chinmay, ADAM CR-253 option C): the spacing of the start times resources.listProductStartTimes offers (WEB-048, GST… (nullable)
TenancyService | setVenueSettings | request | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | setVenueSettings | request | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | setVenueSettings | request | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | request | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | setVenueSettings | request | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | request | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | request | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | request | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | setVenueSettings | request | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | cashDrawerLimit | Money |  | The most cash a till drawer should hold before some is lifted to the safe (decided 2 October 2026, Chinmay, batch 6 set 3, BO-042: "Add drawer limit setting (warn + offer cash lift)"; DEC-179; CHG-CS… (nullable)
TenancyService | setVenueSettings | request | catalogue | object |  | (nullable)
TenancyService | setVenueSettings | request | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | setVenueSettings | request | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | setVenueSettings | request | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | setVenueSettings | request | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | setVenueSettings | request | inventory | object |  | (nullable)
TenancyService | setVenueSettings | request | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | setVenueSettings | request | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | seating | object |  | (nullable)
TenancyService | setVenueSettings | request | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | setVenueSettings | request | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | setVenueSettings | request | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | setVenueSettings | request | promotions | object |  | (nullable)
TenancyService | setVenueSettings | request | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | fnb | object |  | (nullable)
TenancyService | setVenueSettings | request | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | setVenueSettings | request | fnb.tableReservedLeadMinutes | integer |  | Deprecated (2 October 2026, CHG-CLN-009): fnb.FnbReservationPolicy.reservedLeadMinutes is canonical. (min 0; max 240; default 30; nullable)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | setVenueSettings | request | queue | object |  | (nullable)
TenancyService | setVenueSettings | request | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | setVenueSettings | request | reporting | object |  | (nullable)
TenancyService | setVenueSettings | request | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | setVenueSettings | request | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | setVenueSettings | request | marketing | object |  | (nullable)
TenancyService | setVenueSettings | request | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | setVenueSettings | request | identity | object |  | (nullable)
TenancyService | setVenueSettings | request | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | setVenueSettings | request | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | setVenueSettings | request | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | setVenueSettings | request | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | setVenueSettings | response | contact | object |  | How a guest reaches this venue (R8 blocker WHITE-C16, the storage-sat lane's request 5; CHG-R8MIG-011): phone, email, WhatsApp, address and opening-hours prose, one jsonb column, written by the venue… (nullable)
TenancyService | setVenueSettings | response | contact.phone | string |  | (nullable)
TenancyService | setVenueSettings | response | contact.email | string (email) |  | (nullable)
TenancyService | setVenueSettings | response | contact.whatsapp | string |  | (nullable)
TenancyService | setVenueSettings | response | contact.address | object |  | (nullable)
TenancyService | setVenueSettings | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
TenancyService | setVenueSettings | response | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setVenueSettings | response | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | setVenueSettings | response | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | setVenueSettings | response | businessDayCutoff | string |  | When the venue's business day closes (Chinmay, 6 October 2026, from the Vivaticket comparison: the business day closes at 12 midnight, with a change request to make the cut-off configurable, default… (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 00:00; nullable)
TenancyService | setVenueSettings | response | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | setVenueSettings | response | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | setVenueSettings | response | supportHours | object |  | CF-100.
TenancyService | setVenueSettings | response | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | setVenueSettings | response | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | setVenueSettings | response | supportHours.windows | array of object
TenancyService | setVenueSettings | response | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | response | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | setVenueSettings | response | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | setVenueSettings | response | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | setVenueSettings | response | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | setVenueSettings | response | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | setVenueSettings | response | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | setVenueSettings | response | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | setVenueSettings | response | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | setVenueSettings | response | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | setVenueSettings | response | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | setVenueSettings | response | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | setVenueSettings | response | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | setVenueSettings | response | biometrics.consentFormId | string (uuid) |  | The venue's own consent form, which every biometric capture is taken on (decided 2 October 2026, Chinmay, batch 4, BO-188: "Consent first, on the venue's consent form"; DEC-128, DEC-549; CHG-CSP-018). (nullable)
TenancyService | setVenueSettings | response | biometrics.templatesHeldByTicvai | boolean |  | True where TICVAI's platform stores this venue's biometric templates (rather than the venue's own on-premises reader estate). (read-only)
TenancyService | setVenueSettings | response | biometrics.allowMinors | boolean |  | Whether this venue enrols minors at all (decided 2 October 2026, Chinmay, critical set 1, BO-187 and CMS-029: "Guardian consent on the venue's form; minor age per country; the venue can switch minors… (default True)
TenancyService | setVenueSettings | response | biometrics.accreditationFaceMatching | object |  | Face matching to find duplicate accreditation applicants, off unless the venue enables it (decided 2 October 2026, Chinmay, critical set 3, BO-631: "Only where the venue enables it, with applicant co… (nullable)
TenancyService | setVenueSettings | response | biometrics.accreditationFaceMatching.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettings | response | biometrics.accreditationFaceMatching.legalSignOffReference | string |  | The venue's own reference for its legal sign-off; the platform records that one was named, by whom and when. (max length 200; nullable)
TenancyService | setVenueSettings | response | biometrics.accreditationFaceMatching.signedOffByPrincipalId | string (uuid) |  | (read-only; nullable)
TenancyService | setVenueSettings | response | biometrics.accreditationFaceMatching.signedOffAt | string (date-time) |  | (read-only; nullable)
TenancyService | setVenueSettings | response | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | setVenueSettings | response | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettings | response | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | setVenueSettings | response | segregatedAccess.schedule | array of object
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | setVenueSettings | response | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | setVenueSettings | response | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | setVenueSettings | response | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | setVenueSettings | response | alerting | object |  | CF-134.
TenancyService | setVenueSettings | response | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | setVenueSettings | response | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | setVenueSettings | response | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | setVenueSettings | response | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | setVenueSettings | response | chargeCurrencies | array of string |  | Which currencies a guest may select and pay in (decided 2 October 2026, Chinmay; CHG-FIN-001; MoM 10 Aug 2026 4.7 option (b), DI-211). (nullable)
TenancyService | setVenueSettings | response | stepMinutes | enum (15, 30, 60) |  | The venue's start-time step for a space sold by the hour (accepted 26 October 2026, Chinmay, ADAM CR-253 option C): the spacing of the start times resources.listProductStartTimes offers (WEB-048, GST… (nullable)
TenancyService | setVenueSettings | response | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | setVenueSettings | response | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | setVenueSettings | response | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | response | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | setVenueSettings | response | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | response | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | response | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | response | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | setVenueSettings | response | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | cashDrawerLimit | Money |  | The most cash a till drawer should hold before some is lifted to the safe (decided 2 October 2026, Chinmay, batch 6 set 3, BO-042: "Add drawer limit setting (warn + offer cash lift)"; DEC-179; CHG-CS… (nullable)
TenancyService | setVenueSettings | response | catalogue | object |  | (nullable)
TenancyService | setVenueSettings | response | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | setVenueSettings | response | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | setVenueSettings | response | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | setVenueSettings | response | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | setVenueSettings | response | inventory | object |  | (nullable)
TenancyService | setVenueSettings | response | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | setVenueSettings | response | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | seating | object |  | (nullable)
TenancyService | setVenueSettings | response | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | setVenueSettings | response | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | setVenueSettings | response | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | setVenueSettings | response | promotions | object |  | (nullable)
TenancyService | setVenueSettings | response | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | fnb | object |  | (nullable)
TenancyService | setVenueSettings | response | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | setVenueSettings | response | fnb.tableReservedLeadMinutes | integer |  | Deprecated (2 October 2026, CHG-CLN-009): fnb.FnbReservationPolicy.reservedLeadMinutes is canonical. (min 0; max 240; default 30; nullable)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | setVenueSettings | response | queue | object |  | (nullable)
TenancyService | setVenueSettings | response | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | setVenueSettings | response | reporting | object |  | (nullable)
TenancyService | setVenueSettings | response | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | setVenueSettings | response | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | setVenueSettings | response | marketing | object |  | (nullable)
TenancyService | setVenueSettings | response | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | setVenueSettings | response | identity | object |  | (nullable)
TenancyService | setVenueSettings | response | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | setVenueSettings | response | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | setVenueSettings | response | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | setVenueSettings | response | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | setVenueSettings | param (path) | venueId | string (uuid) | yes
TenancyService | setVenueSettings | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setVenueSettingsDefaults | request | contact | object |  | How a guest reaches this venue (R8 blocker WHITE-C16, the storage-sat lane's request 5; CHG-R8MIG-011): phone, email, WhatsApp, address and opening-hours prose, one jsonb column, written by the venue… (nullable)
TenancyService | setVenueSettingsDefaults | request | contact.phone | string |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | contact.email | string (email) |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | contact.whatsapp | string |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | contact.address | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
TenancyService | setVenueSettingsDefaults | request | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setVenueSettingsDefaults | request | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | setVenueSettingsDefaults | request | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | setVenueSettingsDefaults | request | businessDayCutoff | string |  | When the venue's business day closes (Chinmay, 6 October 2026, from the Vivaticket comparison: the business day closes at 12 midnight, with a change request to make the cut-off configurable, default… (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 00:00; nullable)
TenancyService | setVenueSettingsDefaults | request | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | setVenueSettingsDefaults | request | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | setVenueSettingsDefaults | request | supportHours | object |  | CF-100.
TenancyService | setVenueSettingsDefaults | request | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | setVenueSettingsDefaults | request | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | setVenueSettingsDefaults | request | supportHours.windows | array of object
TenancyService | setVenueSettingsDefaults | request | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettingsDefaults | request | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | setVenueSettingsDefaults | request | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | setVenueSettingsDefaults | request | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | setVenueSettingsDefaults | request | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | setVenueSettingsDefaults | request | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | setVenueSettingsDefaults | request | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | setVenueSettingsDefaults | request | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.consentFormId | string (uuid) |  | The venue's own consent form, which every biometric capture is taken on (decided 2 October 2026, Chinmay, batch 4, BO-188: "Consent first, on the venue's consent form"; DEC-128, DEC-549; CHG-CSP-018). (nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.templatesHeldByTicvai | boolean |  | True where TICVAI's platform stores this venue's biometric templates (rather than the venue's own on-premises reader estate). (read-only)
TenancyService | setVenueSettingsDefaults | request | biometrics.allowMinors | boolean |  | Whether this venue enrols minors at all (decided 2 October 2026, Chinmay, critical set 1, BO-187 and CMS-029: "Guardian consent on the venue's form; minor age per country; the venue can switch minors… (default True)
TenancyService | setVenueSettingsDefaults | request | biometrics.accreditationFaceMatching | object |  | Face matching to find duplicate accreditation applicants, off unless the venue enables it (decided 2 October 2026, Chinmay, critical set 3, BO-631: "Only where the venue enables it, with applicant co… (nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.accreditationFaceMatching.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettingsDefaults | request | biometrics.accreditationFaceMatching.legalSignOffReference | string |  | The venue's own reference for its legal sign-off; the platform records that one was named, by whom and when. (max length 200; nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.accreditationFaceMatching.signedOffByPrincipalId | string (uuid) |  | (read-only; nullable)
TenancyService | setVenueSettingsDefaults | request | biometrics.accreditationFaceMatching.signedOffAt | string (date-time) |  | (read-only; nullable)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.schedule | array of object
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | setVenueSettingsDefaults | request | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | setVenueSettingsDefaults | request | alerting | object |  | CF-134.
TenancyService | setVenueSettingsDefaults | request | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | setVenueSettingsDefaults | request | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | setVenueSettingsDefaults | request | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | setVenueSettingsDefaults | request | chargeCurrencies | array of string |  | Which currencies a guest may select and pay in (decided 2 October 2026, Chinmay; CHG-FIN-001; MoM 10 Aug 2026 4.7 option (b), DI-211). (nullable)
TenancyService | setVenueSettingsDefaults | request | stepMinutes | enum (15, 30, 60) |  | The venue's start-time step for a space sold by the hour (accepted 26 October 2026, Chinmay, ADAM CR-253 option C): the spacing of the start times resources.listProductStartTimes offers (WEB-048, GST… (nullable)
TenancyService | setVenueSettingsDefaults | request | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | setVenueSettingsDefaults | request | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | setVenueSettingsDefaults | request | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettingsDefaults | request | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | setVenueSettingsDefaults | request | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettingsDefaults | request | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettingsDefaults | request | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettingsDefaults | request | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | setVenueSettingsDefaults | request | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | request | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | request | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | request | cashDrawerLimit | Money |  | The most cash a till drawer should hold before some is lifted to the safe (decided 2 October 2026, Chinmay, batch 6 set 3, BO-042: "Add drawer limit setting (warn + offer cash lift)"; DEC-179; CHG-CS… (nullable)
TenancyService | setVenueSettingsDefaults | request | catalogue | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | setVenueSettingsDefaults | request | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | setVenueSettingsDefaults | request | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | setVenueSettingsDefaults | request | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | setVenueSettingsDefaults | request | inventory | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | setVenueSettingsDefaults | request | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | setVenueSettingsDefaults | request | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | setVenueSettingsDefaults | request | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | request | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | request | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | request | seating | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | setVenueSettingsDefaults | request | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | setVenueSettingsDefaults | request | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | setVenueSettingsDefaults | request | promotions | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | setVenueSettingsDefaults | request | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | setVenueSettingsDefaults | request | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | request | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | request | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | request | fnb | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | setVenueSettingsDefaults | request | fnb.tableReservedLeadMinutes | integer |  | Deprecated (2 October 2026, CHG-CLN-009): fnb.FnbReservationPolicy.reservedLeadMinutes is canonical. (min 0; max 240; default 30; nullable)
TenancyService | setVenueSettingsDefaults | request | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | setVenueSettingsDefaults | request | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | request | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | request | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | request | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | setVenueSettingsDefaults | request | queue | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | setVenueSettingsDefaults | request | reporting | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | setVenueSettingsDefaults | request | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | setVenueSettingsDefaults | request | marketing | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | setVenueSettingsDefaults | request | identity | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | request | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | setVenueSettingsDefaults | request | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | setVenueSettingsDefaults | request | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | setVenueSettingsDefaults | request | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | setVenueSettingsDefaults | response | contact | object |  | How a guest reaches this venue (R8 blocker WHITE-C16, the storage-sat lane's request 5; CHG-R8MIG-011): phone, email, WhatsApp, address and opening-hours prose, one jsonb column, written by the venue… (nullable)
TenancyService | setVenueSettingsDefaults | response | contact.phone | string |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | contact.email | string (email) |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | contact.whatsapp | string |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | contact.address | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
TenancyService | setVenueSettingsDefaults | response | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setVenueSettingsDefaults | response | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | setVenueSettingsDefaults | response | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | setVenueSettingsDefaults | response | businessDayCutoff | string |  | When the venue's business day closes (Chinmay, 6 October 2026, from the Vivaticket comparison: the business day closes at 12 midnight, with a change request to make the cut-off configurable, default… (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 00:00; nullable)
TenancyService | setVenueSettingsDefaults | response | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | setVenueSettingsDefaults | response | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | setVenueSettingsDefaults | response | supportHours | object |  | CF-100.
TenancyService | setVenueSettingsDefaults | response | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | setVenueSettingsDefaults | response | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | setVenueSettingsDefaults | response | supportHours.windows | array of object
TenancyService | setVenueSettingsDefaults | response | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettingsDefaults | response | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | setVenueSettingsDefaults | response | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | setVenueSettingsDefaults | response | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | setVenueSettingsDefaults | response | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | setVenueSettingsDefaults | response | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | setVenueSettingsDefaults | response | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | setVenueSettingsDefaults | response | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.consentFormId | string (uuid) |  | The venue's own consent form, which every biometric capture is taken on (decided 2 October 2026, Chinmay, batch 4, BO-188: "Consent first, on the venue's consent form"; DEC-128, DEC-549; CHG-CSP-018). (nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.templatesHeldByTicvai | boolean |  | True where TICVAI's platform stores this venue's biometric templates (rather than the venue's own on-premises reader estate). (read-only)
TenancyService | setVenueSettingsDefaults | response | biometrics.allowMinors | boolean |  | Whether this venue enrols minors at all (decided 2 October 2026, Chinmay, critical set 1, BO-187 and CMS-029: "Guardian consent on the venue's form; minor age per country; the venue can switch minors… (default True)
TenancyService | setVenueSettingsDefaults | response | biometrics.accreditationFaceMatching | object |  | Face matching to find duplicate accreditation applicants, off unless the venue enables it (decided 2 October 2026, Chinmay, critical set 3, BO-631: "Only where the venue enables it, with applicant co… (nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.accreditationFaceMatching.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettingsDefaults | response | biometrics.accreditationFaceMatching.legalSignOffReference | string |  | The venue's own reference for its legal sign-off; the platform records that one was named, by whom and when. (max length 200; nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.accreditationFaceMatching.signedOffByPrincipalId | string (uuid) |  | (read-only; nullable)
TenancyService | setVenueSettingsDefaults | response | biometrics.accreditationFaceMatching.signedOffAt | string (date-time) |  | (read-only; nullable)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.schedule | array of object
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | setVenueSettingsDefaults | response | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | setVenueSettingsDefaults | response | alerting | object |  | CF-134.
TenancyService | setVenueSettingsDefaults | response | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | setVenueSettingsDefaults | response | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | setVenueSettingsDefaults | response | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | setVenueSettingsDefaults | response | chargeCurrencies | array of string |  | Which currencies a guest may select and pay in (decided 2 October 2026, Chinmay; CHG-FIN-001; MoM 10 Aug 2026 4.7 option (b), DI-211). (nullable)
TenancyService | setVenueSettingsDefaults | response | stepMinutes | enum (15, 30, 60) |  | The venue's start-time step for a space sold by the hour (accepted 26 October 2026, Chinmay, ADAM CR-253 option C): the spacing of the start times resources.listProductStartTimes offers (WEB-048, GST… (nullable)
TenancyService | setVenueSettingsDefaults | response | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | setVenueSettingsDefaults | response | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | setVenueSettingsDefaults | response | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettingsDefaults | response | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | setVenueSettingsDefaults | response | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettingsDefaults | response | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettingsDefaults | response | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettingsDefaults | response | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | setVenueSettingsDefaults | response | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | response | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | response | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | response | cashDrawerLimit | Money |  | The most cash a till drawer should hold before some is lifted to the safe (decided 2 October 2026, Chinmay, batch 6 set 3, BO-042: "Add drawer limit setting (warn + offer cash lift)"; DEC-179; CHG-CS… (nullable)
TenancyService | setVenueSettingsDefaults | response | catalogue | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | setVenueSettingsDefaults | response | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | setVenueSettingsDefaults | response | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | setVenueSettingsDefaults | response | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | setVenueSettingsDefaults | response | inventory | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | setVenueSettingsDefaults | response | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | setVenueSettingsDefaults | response | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | setVenueSettingsDefaults | response | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | response | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | response | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | response | seating | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | setVenueSettingsDefaults | response | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | setVenueSettingsDefaults | response | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | setVenueSettingsDefaults | response | promotions | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | setVenueSettingsDefaults | response | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | setVenueSettingsDefaults | response | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | response | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | response | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | response | fnb | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | setVenueSettingsDefaults | response | fnb.tableReservedLeadMinutes | integer |  | Deprecated (2 October 2026, CHG-CLN-009): fnb.FnbReservationPolicy.reservedLeadMinutes is canonical. (min 0; max 240; default 30; nullable)
TenancyService | setVenueSettingsDefaults | response | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | setVenueSettingsDefaults | response | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettingsDefaults | response | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettingsDefaults | response | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettingsDefaults | response | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | setVenueSettingsDefaults | response | queue | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | setVenueSettingsDefaults | response | reporting | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | setVenueSettingsDefaults | response | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | setVenueSettingsDefaults | response | marketing | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | setVenueSettingsDefaults | response | identity | object |  | (nullable)
TenancyService | setVenueSettingsDefaults | response | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | setVenueSettingsDefaults | response | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | setVenueSettingsDefaults | response | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | setVenueSettingsDefaults | response | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | setVenueSettingsDefaults | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setVirtualTicketIdentity | request | venueId | string | yes | Venue this configuration applies to
AccessService | setVirtualTicketIdentity | request | idGenerationPattern | string |  | Virtual Ticket ID format: prefix, suffix and length
AccessService | setVirtualTicketIdentity | request | ticketClassification | string |  | Ticket classification
AccessService | setVirtualTicketIdentity | request | ticketOwnershipModel | string |  | Ticket ownership model
AccessService | setVirtualTicketIdentity | request | holderAssignmentRequirements | string |  | Holder assignment requirements
AccessService | setVirtualTicketIdentity | request | transferabilityReference | string |  | Transferability reference
AccessService | setVirtualTicketIdentity | request | validityModel | string |  | Validity model
AccessService | setVirtualTicketIdentity | request | consumptionModel | string |  | Consumption model
AccessService | setVirtualTicketIdentity | request | entitlementModel | string |  | Entitlement model
AccessService | setVirtualTicketIdentity | request | mediaRequirements | array of string |  | Media types a ticket of this configuration must carry
AccessService | setVirtualTicketIdentity | response | venueId | string | yes | Venue this configuration applies to
AccessService | setVirtualTicketIdentity | response | idGenerationPattern | string |  | Virtual Ticket ID format: prefix, suffix and length
AccessService | setVirtualTicketIdentity | response | ticketClassification | string |  | Ticket classification
AccessService | setVirtualTicketIdentity | response | ticketOwnershipModel | string |  | Ticket ownership model
AccessService | setVirtualTicketIdentity | response | holderAssignmentRequirements | string |  | Holder assignment requirements
AccessService | setVirtualTicketIdentity | response | transferabilityReference | string |  | Transferability reference
AccessService | setVirtualTicketIdentity | response | validityModel | string |  | Validity model
AccessService | setVirtualTicketIdentity | response | consumptionModel | string |  | Consumption model
AccessService | setVirtualTicketIdentity | response | entitlementModel | string |  | Entitlement model
AccessService | setVirtualTicketIdentity | response | mediaRequirements | array of string |  | Media types a ticket of this configuration must carry
AccessService | setVirtualTicketIdentity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setVisitPlanPreset | request | id | string (uuid) | yes | (read-only)
VenueOpsService | setVisitPlanPreset | request | presetKey | string | yes | The key generateVisitPlan.presetKey names. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$)
VenueOpsService | setVisitPlanPreset | request | name | string | yes | (max length 120)
VenueOpsService | setVisitPlanPreset | request | nameLocalised | object |  | (nullable)
VenueOpsService | setVisitPlanPreset | request | description | string |  | (max length 500; nullable)
VenueOpsService | setVisitPlanPreset | request | descriptionLocalised | object |  | (nullable)
VenueOpsService | setVisitPlanPreset | request | pace | enum (packed, balanced, relaxed) | yes
VenueOpsService | setVisitPlanPreset | request | interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | setVisitPlanPreset | request | mustIncludePointIds | array of string (uuid) |  | (max items 10)
VenueOpsService | setVisitPlanPreset | request | isBuiltIn | boolean | yes | True for the six seeded rows; a built-in row can be changed or switched off, never deleted. (read-only)
VenueOpsService | setVisitPlanPreset | request | isActive | boolean | yes | (default True)
VenueOpsService | setVisitPlanPreset | request | sortOrder | integer | yes | The order GST-052 lists the presets in. (min 0)
VenueOpsService | setVisitPlanPreset | request | scopePath | string | yes | The partition key (ADR-0005): the venue the preset belongs to. (read-only)
VenueOpsService | setVisitPlanPreset | request | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | setVisitPlanPreset | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setVisitPlanPreset | response | presetKey | string | yes | The key generateVisitPlan.presetKey names. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$)
VenueOpsService | setVisitPlanPreset | response | name | string | yes | (max length 120)
VenueOpsService | setVisitPlanPreset | response | nameLocalised | object |  | (nullable)
VenueOpsService | setVisitPlanPreset | response | description | string |  | (max length 500; nullable)
VenueOpsService | setVisitPlanPreset | response | descriptionLocalised | object |  | (nullable)
VenueOpsService | setVisitPlanPreset | response | pace | enum (packed, balanced, relaxed) | yes
VenueOpsService | setVisitPlanPreset | response | interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | setVisitPlanPreset | response | mustIncludePointIds | array of string (uuid) |  | (max items 10)
VenueOpsService | setVisitPlanPreset | response | isBuiltIn | boolean | yes | True for the six seeded rows; a built-in row can be changed or switched off, never deleted. (read-only)
VenueOpsService | setVisitPlanPreset | response | isActive | boolean | yes | (default True)
VenueOpsService | setVisitPlanPreset | response | sortOrder | integer | yes | The order GST-052 lists the presets in. (min 0)
VenueOpsService | setVisitPlanPreset | response | scopePath | string | yes | The partition key (ADR-0005): the venue the preset belongs to. (read-only)
VenueOpsService | setVisitPlanPreset | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | setVisitPlanPreset | param (path) | venueId | string (uuid) | yes
VenueOpsService | setVisitPlanPreset | param (path) | presetKey | string | yes
VenueOpsService | setVisitPlanPreset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setVisitReminder | request | id | string (uuid) |  | (read-only)
OrderService | setVisitReminder | request | orderId | string (uuid) |  | (read-only)
OrderService | setVisitReminder | request | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | setVisitReminder | request | enabled | boolean | yes
OrderService | setVisitReminder | request | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | setVisitReminder | request | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | setVisitReminder | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | setVisitReminder | response | id | string (uuid) |  | (read-only)
OrderService | setVisitReminder | response | orderId | string (uuid) |  | (read-only)
OrderService | setVisitReminder | response | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | setVisitReminder | response | enabled | boolean | yes
OrderService | setVisitReminder | response | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | setVisitReminder | response | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | setVisitReminder | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | setVisitReminder | param (path) | orderId | string (uuid) | yes
OrderService | setVisitReminder | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setVisitReminder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setVisualAccessRule | request | decision | enum (allow, deny, referToOperator, overrideEligible) | yes | THEN
AccessService | setVisualAccessRule | request | name | string | yes
AccessService | setVisualAccessRule | request | ruleId | string | yes
AccessService | setVisualAccessRule | request | logic | string |  | Boolean expression combining the conditions with AND / OR / NOT
AccessService | setVisualAccessRule | request | appliesTo | array of string |  | Products or credential types (WHEN)
AccessService | setVisualAccessRule | request | locationIds | array of string |  | Venue, park, zone, attraction or gate IDs (AT)
AccessService | setVisualAccessRule | request | conditions | array of string |  | Conditions (IF), e.g.
AccessService | setVisualAccessRule | request | consequences | array of string |  | Actions performed on the decision, e.g.
AccessService | setVisualAccessRule | response | decision | enum (allow, deny, referToOperator, overrideEligible) | yes | THEN
AccessService | setVisualAccessRule | response | name | string | yes
AccessService | setVisualAccessRule | response | ruleId | string | yes
AccessService | setVisualAccessRule | response | logic | string |  | Boolean expression combining the conditions with AND / OR / NOT
AccessService | setVisualAccessRule | response | appliesTo | array of string |  | Products or credential types (WHEN)
AccessService | setVisualAccessRule | response | locationIds | array of string |  | Venue, park, zone, attraction or gate IDs (AT)
AccessService | setVisualAccessRule | response | conditions | array of string |  | Conditions (IF), e.g.
AccessService | setVisualAccessRule | response | consequences | array of string |  | Actions performed on the decision, e.g.
AccessService | setVisualAccessRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | setWalletAutoReloadSetting | request | walletId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | request | subjectId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | request | enabled | boolean | yes
WalletService | setWalletAutoReloadSetting | request | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | request | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | request | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | request | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | request | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | request | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | request | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | request | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | request | paymentTokenId | string (uuid) |  | (nullable)
WalletService | setWalletAutoReloadSetting | request | maximumPerDay | integer |  | (min 1; nullable)
WalletService | setWalletAutoReloadSetting | request | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | setWalletAutoReloadSetting | request | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | setWalletAutoReloadSetting | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | setWalletAutoReloadSetting | response | walletId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | response | subjectId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | response | enabled | boolean | yes
WalletService | setWalletAutoReloadSetting | response | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | response | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | response | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | response | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | response | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | response | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | response | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | response | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | response | paymentTokenId | string (uuid) |  | (nullable)
WalletService | setWalletAutoReloadSetting | response | maximumPerDay | integer |  | (min 1; nullable)
WalletService | setWalletAutoReloadSetting | response | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | setWalletAutoReloadSetting | response | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | setWalletAutoReloadSetting | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | setWalletAutoReloadSetting | param (path) | walletId | string (uuid) | yes
WalletService | setWalletAutoReloadSetting | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | setWalletAutoReloadSetting | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | setWalletFundingRules | request | walletTypeId | string (uuid) |  | The wallet type these rules are for; null for the venue default. (nullable)
WalletService | setWalletFundingRules | request | minimumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | minimumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | minimumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | minimumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | maximumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | maximumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | maximumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | maximumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | presetAmounts | array of Money
WalletService | setWalletFundingRules | request | presetAmounts[].amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | presetAmounts[].currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | presetAmounts[].scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | allowedChannels | array of string
WalletService | setWalletFundingRules | request | allowedFundingSources | array of enum (card, cash, bankTransfer, voucher, corporateAccount, loyaltyConversion)
WalletService | setWalletFundingRules | request | bonusRules | array of object |  | Board 2.3.
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | bonusRules[].bonusPercent | number |  | (nullable)
WalletService | setWalletFundingRules | request | bonusRules[].bonusCreditTypeId | string (uuid)
WalletService | setWalletFundingRules | request | bonusRules[].validFrom | string (date) |  | (nullable)
WalletService | setWalletFundingRules | request | bonusRules[].validTo | string (date) |  | (nullable)
WalletService | setWalletFundingRules | request | autoReload | object |  | Board 2.5, matrix 4.3.28.
WalletService | setWalletFundingRules | request | autoReload.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | autoReload.reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | autoReload.reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | autoReload.reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | autoReload.reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | autoReload.maximumPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | request | recurringFunding | object |  | Board 2.6, matrix 4.3.29 — *"distinct from auto-reload"*.
WalletService | setWalletFundingRules | request | recurringFunding.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | request | recurringFunding.cadence | enum (daily, weekly, monthly)
WalletService | setWalletFundingRules | request | recurringFunding.amount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | recurringFunding.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | recurringFunding.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | recurringFunding.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | recurringFunding.dayOfWeek | string |  | (nullable)
WalletService | setWalletFundingRules | request | recurringFunding.dayOfMonth | integer |  | (nullable)
WalletService | setWalletFundingRules | request | approvalAboveAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | approvalAboveAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | approvalAboveAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | approvalAboveAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | velocityLimits | object |  | A fraud control, not a commercial one.
WalletService | setWalletFundingRules | request | velocityLimits.maxTransactionsPerHour | integer |  | (nullable)
WalletService | setWalletFundingRules | request | velocityLimits.maxTransactionsPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | scopePath | string
WalletService | setWalletFundingRules | response | walletTypeId | string (uuid) |  | The wallet type these rules are for; null for the venue default. (nullable)
WalletService | setWalletFundingRules | response | minimumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | minimumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | minimumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | minimumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | maximumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | maximumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | maximumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | maximumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | presetAmounts | array of Money
WalletService | setWalletFundingRules | response | presetAmounts[].amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | presetAmounts[].currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | presetAmounts[].scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | allowedChannels | array of string
WalletService | setWalletFundingRules | response | allowedFundingSources | array of enum (card, cash, bankTransfer, voucher, corporateAccount, loyaltyConversion)
WalletService | setWalletFundingRules | response | bonusRules | array of object |  | Board 2.3.
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | bonusRules[].bonusPercent | number |  | (nullable)
WalletService | setWalletFundingRules | response | bonusRules[].bonusCreditTypeId | string (uuid)
WalletService | setWalletFundingRules | response | bonusRules[].validFrom | string (date) |  | (nullable)
WalletService | setWalletFundingRules | response | bonusRules[].validTo | string (date) |  | (nullable)
WalletService | setWalletFundingRules | response | autoReload | object |  | Board 2.5, matrix 4.3.28.
WalletService | setWalletFundingRules | response | autoReload.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | autoReload.reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | autoReload.reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | autoReload.reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | autoReload.reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | autoReload.maximumPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | response | recurringFunding | object |  | Board 2.6, matrix 4.3.29 — *"distinct from auto-reload"*.
WalletService | setWalletFundingRules | response | recurringFunding.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | response | recurringFunding.cadence | enum (daily, weekly, monthly)
WalletService | setWalletFundingRules | response | recurringFunding.amount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | recurringFunding.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | recurringFunding.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | recurringFunding.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | recurringFunding.dayOfWeek | string |  | (nullable)
WalletService | setWalletFundingRules | response | recurringFunding.dayOfMonth | integer |  | (nullable)
WalletService | setWalletFundingRules | response | approvalAboveAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | approvalAboveAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | approvalAboveAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | approvalAboveAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | velocityLimits | object |  | A fraud control, not a commercial one.
WalletService | setWalletFundingRules | response | velocityLimits.maxTransactionsPerHour | integer |  | (nullable)
WalletService | setWalletFundingRules | response | velocityLimits.maxTransactionsPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | scopePath | string
WalletService | setWalletFundingRules | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | setWalletFundingRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | setWalletTransferRules | request | peerToPeerAllowed | boolean |  | (default False)
WalletService | setWalletTransferRules | request | transferableCreditTypeIds | array of string (uuid)
WalletService | setWalletTransferRules | request | maximumPerTransfer | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletTransferRules | request | maximumPerTransfer.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletTransferRules | request | maximumPerTransfer.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletTransferRules | request | maximumPerTransfer.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletTransferRules | request | maximumPerDay | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletTransferRules | request | maximumPerDay.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletTransferRules | request | maximumPerDay.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletTransferRules | request | maximumPerDay.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletTransferRules | request | approvalAboveAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletTransferRules | request | approvalAboveAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletTransferRules | request | approvalAboveAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletTransferRules | request | approvalAboveAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletTransferRules | request | bothPartiesIdentified | boolean |  | (default True)
WalletService | setWalletTransferRules | request | withinSharedWalletOnly | boolean |  | (default False)
WalletService | setWalletTransferRules | request | scopePath | string
WalletService | setWalletTransferRules | response | peerToPeerAllowed | boolean |  | (default False)
WalletService | setWalletTransferRules | response | transferableCreditTypeIds | array of string (uuid)
WalletService | setWalletTransferRules | response | maximumPerTransfer | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletTransferRules | response | maximumPerTransfer.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletTransferRules | response | maximumPerTransfer.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletTransferRules | response | maximumPerTransfer.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletTransferRules | response | maximumPerDay | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletTransferRules | response | maximumPerDay.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletTransferRules | response | maximumPerDay.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletTransferRules | response | maximumPerDay.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletTransferRules | response | approvalAboveAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletTransferRules | response | approvalAboveAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletTransferRules | response | approvalAboveAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletTransferRules | response | approvalAboveAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletTransferRules | response | bothPartiesIdentified | boolean |  | (default True)
WalletService | setWalletTransferRules | response | withinSharedWalletOnly | boolean |  | (default False)
WalletService | setWalletTransferRules | response | scopePath | string
WalletService | setWalletTransferRules | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | setWalletTransferRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | shareEntitlement | request | toSubjectId | string (uuid) | yes
OrderService | shareEntitlement | request | validUntil | string (date-time) |  | (nullable)
OrderService | shareEntitlement | response | id | string (uuid) | yes
OrderService | shareEntitlement | response | entitlementId | string (uuid) | yes
OrderService | shareEntitlement | response | toSubjectId | string (uuid) | yes | The guest it is shared with.
OrderService | shareEntitlement | response | validFrom | string (date-time)
OrderService | shareEntitlement | response | validUntil | string (date-time) |  | Null means until revoked or until the entitlement itself ends. (nullable)
OrderService | shareEntitlement | response | revokedAt | string (date-time) |  | (nullable)
OrderService | shareEntitlement | response | status | enum (active, revoked, expired) | yes
OrderService | shareEntitlement | param (path) | entitlementId | string (uuid) | yes
OrderService | shareEntitlement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | signCorrectiveAction | request | actionTaken | string | yes
FnbService | signCorrectiveAction | request | disposal | enum (none, discarded, reworked, quarantined, returned)
FnbService | signCorrectiveAction | response | id | string (uuid) | yes
FnbService | signCorrectiveAction | response | raisedAt | string (date-time) | yes
FnbService | signCorrectiveAction | response | raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | signCorrectiveAction | response | source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | signCorrectiveAction | response | sourceRef | string (uuid) |  | (nullable)
FnbService | signCorrectiveAction | response | severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | signCorrectiveAction | response | actionTaken | string |  | (nullable)
FnbService | signCorrectiveAction | response | disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | signCorrectiveAction | response | status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | signCorrectiveAction | response | signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | signCorrectiveAction | response | signedAt | string (date-time) |  | (nullable)
FnbService | signCorrectiveAction | response | escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | signCorrectiveAction | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | signCorrectiveAction | param (path) | actionId | string (uuid) | yes
FnbService | signCorrectiveAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | simulateAiGovernancePolicy | request | from | string (date-time) |  | (nullable)
AiService | simulateAiGovernancePolicy | request | to | string (date-time) |  | (nullable)
AiService | simulateAiGovernancePolicy | request | capabilityKeys | array of string
AiService | simulateAiGovernancePolicy | response | evaluated | integer | yes
AiService | simulateAiGovernancePolicy | response | wouldChange | integer
AiService | simulateAiGovernancePolicy | response | byOutcome | object |  | Counts per outcome, current against draft.
AiService | simulateAiGovernancePolicy | response | examples | array of object
AiService | simulateAiGovernancePolicy | response | examples[].decisionRecordId | string (uuid)
AiService | simulateAiGovernancePolicy | response | examples[].current | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) |  | What the governance decision point returns (design 3.8, AIC-166).
AiService | simulateAiGovernancePolicy | response | examples[].draft | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) |  | What the governance decision point returns (design 3.8, AIC-166).
AiService | simulateAiGovernancePolicy | response | examples[].capabilityKey | string
AiService | simulateAiGovernancePolicy | param (path) | versionId | string (uuid) | yes
AiService | simulateAiGovernancePolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | splitBill | request | recordedAt | string (date-time) | yes | Device time of the split (offline-capable).
FnbService | splitBill | request | method | SplitMethod: enum (byAmount, byCovers, byCategory, byLine, bySeat) | yes
FnbService | splitBill | request | parts | integer |  | For byCovers — defaults to the visit's cover count. (min 2)
FnbService | splitBill | request | amounts | array of Money |  | For byAmount.
FnbService | splitBill | request | amounts[].amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | splitBill | request | amounts[].currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | splitBill | request | amounts[].scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | splitBill | request | lineAssignments | array of object |  | For byLine or bySeat.
FnbService | splitBill | request | lineAssignments[].lineId | string | yes
FnbService | splitBill | request | lineAssignments[].partIndex | integer | yes | (min 0)
FnbService | splitBill | request | categoryAssignments | array of object |  | For byCategory — food to one part, beverage to another.
FnbService | splitBill | request | categoryAssignments[].categoryCode | string | yes
FnbService | splitBill | request | categoryAssignments[].partIndex | integer | yes | (min 0)
FnbService | splitBill | response | id | string (uuid) |  | Added 20 August. (read-only)
FnbService | splitBill | response | visitId | string | yes
FnbService | splitBill | response | method | SplitMethod: enum (byAmount, byCovers, byCategory, byLine, bySeat) | yes
FnbService | splitBill | response | subBills | array of object | yes
FnbService | splitBill | response | subBills[].subBillId | string | yes
FnbService | splitBill | response | subBills[].lineIds | array of string
FnbService | splitBill | response | subBills[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | splitBill | response | subBills[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | splitBill | response | subBills[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | splitBill | response | subBills[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | splitBill | response | subBills[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | splitBill | response | subBills[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | splitBill | response | subBills[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | splitBill | response | subBills[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | splitBill | response | subBills[].total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | splitBill | response | subBills[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | splitBill | response | subBills[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | splitBill | response | subBills[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | splitBill | response | subBills[].status | enum (unpaid, paid) | yes
FnbService | splitBill | param (path) | visitId | string (uuid) | yes
FnbService | splitBill | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | stopCampaign | request | reason | string | yes | (min length 3; max length 500)
MarketingService | stopCampaign | response | name | string | yes | (max length 200)
MarketingService | stopCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | stopCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | stopCampaign | response | venueId | string (uuid)
MarketingService | stopCampaign | response | segmentId | string (uuid) | yes
MarketingService | stopCampaign | response | content | CampaignContent | yes
MarketingService | stopCampaign | response | content.templateId | string (uuid) | yes
MarketingService | stopCampaign | response | content.subjectOverride | object
MarketingService | stopCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | stopCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | stopCampaign | response | trigger | CampaignTrigger
MarketingService | stopCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | stopCampaign | response | trigger.delayHours | integer
MarketingService | stopCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | stopCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | stopCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | stopCampaign | response | trigger.conditions[].value | object
MarketingService | stopCampaign | response | trigger.conditions[].values | array of object
MarketingService | stopCampaign | response | scheduledFor | string (date-time)
MarketingService | stopCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | stopCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | stopCampaign | response | sendWindow.startTime | string
MarketingService | stopCampaign | response | sendWindow.endTime | string
MarketingService | stopCampaign | response | sendWindow.timeZone | string
MarketingService | stopCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | stopCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | stopCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | stopCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | stopCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | stopCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | stopCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | stopCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | stopCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | stopCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | stopCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | stopCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | stopCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | stopCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | stopCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | stopCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | stopCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | stopCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | stopCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | stopCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | stopCampaign | response | id | string (uuid) | yes
MarketingService | stopCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | stopCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | stopCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | stopCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | stopCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | stopCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | stopCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | stopCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | stopCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | stopCampaign | response | isPaused | boolean
MarketingService | stopCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | stopCampaign | response | createdAt | string (date-time) | yes
MarketingService | stopCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | stopCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | stopCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | stopCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | stopCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | storePaymentToken | request | providerId | string (uuid) | yes
OrderService | storePaymentToken | request | providerToken | string (password) | yes | The provider's reference to the credential it tokenised, stored field-encrypted as the token row's token (PaymentToken.token, write-only, never returned; CHG-R11FXC-004).
OrderService | storePaymentToken | request | consentPurposeId | string (uuid) | yes
OrderService | storePaymentToken | request | setDefault | boolean |  | True makes the new token the guest's default (PaymentToken.isDefault, the row's is_default), and clears is_default on the guest's other tokens in the same transaction; false stores it with is_default… (default False)
OrderService | storePaymentToken | response | id | string (uuid) | yes
OrderService | storePaymentToken | response | subjectId | string (uuid) | yes
OrderService | storePaymentToken | response | providerId | string (uuid) | yes
OrderService | storePaymentToken | response | token | string (password) | yes | Write-only, never returned.
OrderService | storePaymentToken | response | method | string
OrderService | storePaymentToken | response | maskedIdentifier | string |  | What a guest sees — the last four digits, the card brand.
OrderService | storePaymentToken | response | expiresAt | string (date) |  | (nullable)
OrderService | storePaymentToken | response | revokedAt | string (date-time) |  | When the guest removed it (revokePaymentToken); a removed token is never returned or charged (CHG-R8MIG-022). (read-only; nullable)
OrderService | storePaymentToken | response | isDefault | boolean | yes
OrderService | storePaymentToken | response | consentPurposeId | string (uuid) |  | Storing a card for future use is a purpose a guest consents to, separate from the payment they are making now. (nullable)
OrderService | storePaymentToken | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | submitForm | request | id | string (uuid) | yes | (read-only)
MarketingService | submitForm | request | formId | string (uuid) | yes
MarketingService | submitForm | request | formVersion | integer | yes | The version, not the form.
MarketingService | submitForm | request | subjectId | string (uuid) | yes
MarketingService | submitForm | request | onBehalfOfSubjectId | string (uuid) |  | A guardian signing for a minor, or a group leader for an attendee. (nullable)
MarketingService | submitForm | request | answers | object |  | One entry per answered FormField, keyed by its key.
MarketingService | submitForm | request | signatureAssetId | string (uuid) |  | (nullable)
MarketingService | submitForm | request | submittedAt | string (date-time) | yes | Device time of the acceptance — submitForm is offline-capable, and the time a waiver was signed is the evidence, not the time it synced.
MarketingService | submitForm | request | syncedAt | string (date-time) |  | Server time the submission arrived. (read-only)
MarketingService | submitForm | request | expiresAt | string (date-time) |  | From validForMonths. (read-only; nullable)
MarketingService | submitForm | request | capturedAtChannel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
MarketingService | submitForm | request | ipAddress | string |  | (nullable)
MarketingService | submitForm | request | saleContext | object |  | The sale a capture was made for (products module, 16 October 2026 minutes 4.13; CHG-R8PRD-009, CHG-R8PRD-010): a product's reservation-owner and ticket-owner forms (catalogue getProductOwnerForms) ar… (read-only; nullable)
MarketingService | submitForm | request | saleContext.submissionId | string (uuid) |  | (read-only)
MarketingService | submitForm | request | saleContext.orderId | string (uuid) | yes | The order (Orders' id; not a database reference).
MarketingService | submitForm | request | saleContext.ownerRole | enum (reservationOwner, ticketOwner) | yes
MarketingService | submitForm | request | saleContext.orderLineId | string (uuid) |  | For a ticket owner, the order line whose credential this owner holds; null for the buyer. (nullable)
MarketingService | submitForm | request | saleContext.unitIndex | integer |  | For a ticket owner, which of the line's credentials (1 to the line's quantity); null for the buyer. (min 1; nullable)
MarketingService | submitForm | request | saleContext.scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | submitForm | response | id | string (uuid) | yes | (read-only)
MarketingService | submitForm | response | formId | string (uuid) | yes
MarketingService | submitForm | response | formVersion | integer | yes | The version, not the form.
MarketingService | submitForm | response | subjectId | string (uuid) | yes
MarketingService | submitForm | response | onBehalfOfSubjectId | string (uuid) |  | A guardian signing for a minor, or a group leader for an attendee. (nullable)
MarketingService | submitForm | response | answers | object |  | One entry per answered FormField, keyed by its key.
MarketingService | submitForm | response | signatureAssetId | string (uuid) |  | (nullable)
MarketingService | submitForm | response | submittedAt | string (date-time) | yes | Device time of the acceptance — submitForm is offline-capable, and the time a waiver was signed is the evidence, not the time it synced.
MarketingService | submitForm | response | syncedAt | string (date-time) |  | Server time the submission arrived. (read-only)
MarketingService | submitForm | response | expiresAt | string (date-time) |  | From validForMonths. (read-only; nullable)
MarketingService | submitForm | response | capturedAtChannel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
MarketingService | submitForm | response | ipAddress | string |  | (nullable)
MarketingService | submitForm | response | saleContext | object |  | The sale a capture was made for (products module, 16 October 2026 minutes 4.13; CHG-R8PRD-009, CHG-R8PRD-010): a product's reservation-owner and ticket-owner forms (catalogue getProductOwnerForms) ar… (read-only; nullable)
MarketingService | submitForm | response | saleContext.submissionId | string (uuid) |  | (read-only)
MarketingService | submitForm | response | saleContext.orderId | string (uuid) | yes | The order (Orders' id; not a database reference).
MarketingService | submitForm | response | saleContext.ownerRole | enum (reservationOwner, ticketOwner) | yes
MarketingService | submitForm | response | saleContext.orderLineId | string (uuid) |  | For a ticket owner, the order line whose credential this owner holds; null for the buyer. (nullable)
MarketingService | submitForm | response | saleContext.unitIndex | integer |  | For a ticket owner, which of the line's credentials (1 to the line's quantity); null for the buyer. (min 1; nullable)
MarketingService | submitForm | response | saleContext.scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | submitForm | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | submitReview | request | id | string (uuid) | yes
MarketingService | submitReview | request | subjectId | string (uuid)
MarketingService | submitReview | request | venueId | string (uuid) | yes
MarketingService | submitReview | request | relatedOrderId | string
MarketingService | submitReview | request | rating | integer | yes | (min 1; max 5)
MarketingService | submitReview | request | body | string |  | (max length 5000)
MarketingService | submitReview | request | aspects | array of enum (exhibitions, staff, cleanliness, food, value) |  | Aspect chips — the closed set the description always named.
MarketingService | submitReview | request | recordedAt | string (date-time) | yes
MarketingService | submitReview | response | id | string (uuid) | yes
MarketingService | submitReview | response | subjectId | string (uuid)
MarketingService | submitReview | response | venueId | string (uuid) | yes
MarketingService | submitReview | response | relatedOrderId | string
MarketingService | submitReview | response | rating | integer | yes | (min 1; max 5)
MarketingService | submitReview | response | body | string |  | (max length 5000)
MarketingService | submitReview | response | aspects | array of enum (exhibitions, staff, cleanliness, food, value) |  | Aspect chips — the closed set the description always named.
MarketingService | submitReview | response | recordedAt | string (date-time) | yes
MarketingService | submitReview | response | status | enum (pendingModeration, published, hidden, rejected) | yes
MarketingService | submitReview | response | response | string |  | (nullable)
MarketingService | submitReview | response | responseIsPublic | boolean
MarketingService | submitReview | response | respondedByPrincipalId | string (uuid) |  | (nullable)
MarketingService | submitReview | response | openedCaseId | string |  | Case raised automatically where the rating fell below the venue's threshold. (nullable)
MarketingService | submitReview | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | submitShiftCount | request | countedCash | array of CountedDenominationLine | yes | The cashier's blind count, one line per denomination counted (decided 29 September, readiness close-out; our build plan). (min items 1)
OrderService | submitShiftCount | request | countedCash[].denominationId | string (uuid) | yes | References platform.denomination (Denomination.id) — face value, kind and counting order live there.
OrderService | submitShiftCount | request | countedCash[].count | integer | yes | How many of this note or coin were counted. (min 0; max 100000)
OrderService | submitShiftCount | request | countedCash[].total | object |  | count times the face value, in the denomination's currency.
OrderService | submitShiftCount | request | countedCash[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | submitShiftCount | request | countedCash[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | submitShiftCount | request | countedCash[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | submitShiftCount | request | nonCashDeclared | array of object |  | Declared totals per non-cash tender, for reconciliation against captured payments.
OrderService | submitShiftCount | request | nonCashDeclared[].tender | string | yes
OrderService | submitShiftCount | request | nonCashDeclared[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | submitShiftCount | request | nonCashDeclared[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | submitShiftCount | request | nonCashDeclared[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | submitShiftCount | request | nonCashDeclared[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | submitShiftCount | request | notes | string |  | The cashier's note on the count. (max length 1000)
OrderService | submitShiftCount | request | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | Anything the cashier knows went wrong in the shift (DI-803: till error, unrecorded refund, miscount, other). (nullable)
OrderService | submitShiftCount | request | releaseHeldLeases | boolean |  | Return unsold inventory leases held by this workstation (ADR-0013 C103). (default True)
OrderService | submitShiftCount | request | recordedAt | string (date-time) | yes
OrderService | submitShiftCount | response | shiftId | string (uuid) | yes
OrderService | submitShiftCount | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | submitShiftCount | response | outcome | enum (closed, referredToSupervisor, awaitingCloseApproval) | yes | closed: within the venue's threshold, the shift is closed.
OrderService | submitShiftCount | response | countedAt | string (date-time) | yes
OrderService | submitShiftCount | response | countNumber | integer |  | 1 for the first count of the close, 2 for a recount the supervisor asked for, and so on. (min 1)
OrderService | submitShiftCount | response | varianceReasonRequired | boolean |  | The count found a difference within the threshold and no reason came with it (the client's policy of 6 October 2026, T10.1; CHG-R4-019). (default False)
OrderService | submitShiftCount | param (path) | shiftId | string (uuid) | yes
OrderService | submitShiftCount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | suggestGuidedChoice | request | trigger | enum (manual) |  | (default manual)
AiService | suggestGuidedChoice | request | locales | array of string
AiService | suggestGuidedChoice | response | id | string (uuid) |  | (read-only)
AiService | suggestGuidedChoice | response | venueId | string (uuid) | yes
AiService | suggestGuidedChoice | response | trigger | enum (productsUploaded, mappedProductWithdrawn, productsUncovered, manual) | yes
AiService | suggestGuidedChoice | response | status | enum (running, proposed, noSuggestion, failed, superseded) | yes | (read-only)
AiService | suggestGuidedChoice | response | productCount | integer |  | (min 0; read-only)
AiService | suggestGuidedChoice | response | questions | array of object |  | The questions chosen, in the order asked. (read-only)
AiService | suggestGuidedChoice | response | questions[].attribute | string |  | The catalogue attribute asked about: audience, level, minimum height or age, duration, price band, format, language.
AiService | suggestGuidedChoice | response | questions[].order | integer |  | (min 1)
AiService | suggestGuidedChoice | response | questions[].split | object |  | How evenly it divides the bookable products: products per answer.
AiService | suggestGuidedChoice | response | questions[].droppedBecause | string |  | Set where an attribute was considered and dropped (an answer would leave nothing bookable). (nullable)
AiService | suggestGuidedChoice | response | questions[].answers | array of object
AiService | suggestGuidedChoice | response | questions[].answers[].value | string
AiService | suggestGuidedChoice | response | questions[].answers[].leadsTo | enum (product, category, flow)
AiService | suggestGuidedChoice | response | questions[].answers[].targetRef | string
AiService | suggestGuidedChoice | response | wordingSource | enum (model, attributeNames) |  | Where the text came from. (read-only)
AiService | suggestGuidedChoice | response | modelVersion | string |  | (read-only; nullable)
AiService | suggestGuidedChoice | response | promptTemplateVersion | string |  | (read-only; nullable)
AiService | suggestGuidedChoice | response | guidedChoiceId | string (uuid) |  | The white-label draft GuidedChoice it produced. (read-only; nullable)
AiService | suggestGuidedChoice | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | suggestGuidedChoice | response | createdAt | string (date-time) |  | (read-only)
AiService | suggestGuidedChoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | suggestGuidedChoice | param (path) | venueId | string (uuid) | yes
AiService | suggestGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | suspendShift | request | reason | string |  | (max length 200)
OrderService | suspendShift | request | recordedAt | string (date-time) | yes
OrderService | suspendShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | suspendShift | response | workstationId | string (uuid) | yes
OrderService | suspendShift | response | venueId | string (uuid) | yes
OrderService | suspendShift | response | scopePath | string | yes
OrderService | suspendShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | suspendShift | response | principalDisplayName | string
OrderService | suspendShift | response | incidents | array of object |  | BL-097.
OrderService | suspendShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | suspendShift | response | incidents[].at | string (date-time)
OrderService | suspendShift | response | incidents[].principalId | string (uuid)
OrderService | suspendShift | response | incidents[].note | string |  | (nullable)
OrderService | suspendShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | suspendShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | suspendShift | response | depositBoxCode | string |  | (nullable)
OrderService | suspendShift | response | bagNumber | string |  | (nullable)
OrderService | suspendShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | suspendShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | suspendShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | suspendShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | suspendShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | suspendShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | suspendShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | suspendShift | response | openedAt | string (date-time) | yes
OrderService | suspendShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | suspendShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | suspendShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | suspendShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | suspendShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | suspendShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | suspendShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | suspendShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | suspendShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | suspendShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | suspendShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | suspendShift | response | approvals | array of object
OrderService | suspendShift | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | suspendShift | response | approvals[].principalId | string (uuid) | yes
OrderService | suspendShift | response | approvals[].at | string (date-time) | yes
OrderService | suspendShift | response | approvals[].reason | string
OrderService | suspendShift | param (path) | shiftId | string (uuid) | yes
OrderService | suspendShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | syncOrders | request | deviceId | string (uuid) | yes
OrderService | syncOrders | request | orders | array of OfflineOrder | yes | (min items 1; max items 200)
OrderService | syncOrders | request | orders[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | syncOrders | request | orders[].venueId | string (uuid) | yes
OrderService | syncOrders | request | orders[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
OrderService | syncOrders | request | orders[].shiftId | string (uuid)
OrderService | syncOrders | request | orders[].subjectId | string (uuid) |  | Null for an anonymous sale. (nullable)
OrderService | syncOrders | request | orders[].guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
OrderService | syncOrders | request | orders[].catalogueBundleVersion | string |  | The bundle the client priced from.
OrderService | syncOrders | request | orders[].lines | array of CreateOrderLine | yes | (min items 1)
OrderService | syncOrders | request | orders[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | syncOrders | request | orders[].lines[].variantId | string (uuid) | yes
OrderService | syncOrders | request | orders[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | syncOrders | request | orders[].lines[].performanceId | string (uuid)
OrderService | syncOrders | request | orders[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | syncOrders | request | orders[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | syncOrders | request | orders[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | syncOrders | request | orders[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | syncOrders | request | orders[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | syncOrders | request | orders[].lines[].quantity | integer | yes | (min 1)
OrderService | syncOrders | request | orders[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | syncOrders | request | orders[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | syncOrders | request | orders[].lines[].holderName | string |  | (nullable)
OrderService | syncOrders | request | orders[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | syncOrders | request | orders[].recordedAt | string (date-time) | yes
OrderService | syncOrders | request | orders[].sequence | integer | yes | Monotonic per device. (min 1)
OrderService | syncOrders | request | orders[].payments | array of CreatePaymentRequest | yes
OrderService | syncOrders | request | orders[].payments[].id | string (uuid) | yes | Client-generated UUIDv7 of the payment, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | syncOrders | request | orders[].payments[].orderId | string (uuid) | yes
OrderService | syncOrders | request | orders[].payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | syncOrders | request | orders[].payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | syncOrders | request | orders[].payments[].tenderCurrency | string |  | The currency the guest handed over, where it is not the venue's — becomes Payment.tenderCurrency. (pattern ^[A-Z]{3}$; nullable)
OrderService | syncOrders | request | orders[].payments[].tenderAmount | object |  | What the guest handed over, in tenderCurrency — becomes Payment.tenderAmount, one name for one concept (renamed from tenderedAmount on 26 September).
OrderService | syncOrders | request | orders[].payments[].walletAuthorisationId | string |  | Cross-cell wallet hold, where the guest's home cell is elsewhere. (nullable)
OrderService | syncOrders | request | orders[].payments[].walletHoldId | string (uuid) |  | For a wallet tender, the hold wallet.holdWalletFunds placed (SD-027). (nullable)
OrderService | syncOrders | request | orders[].payments[].returnUrl | string (uri) |  | Where the provider returns the guest after a 3-D Secure challenge or hosted page (SD-034). (nullable)
OrderService | syncOrders | request | orders[].payments[].terminalId | string (uuid) |  | The card terminal to instruct, for a card payment at a till (ECR flow, SD-034). (nullable)
OrderService | syncOrders | request | orders[].payments[].deviceId | string (uuid) |  | (nullable)
OrderService | syncOrders | request | orders[].payments[].recordedAt | string (date-time) | yes
OrderService | syncOrders | response | accepted | integer | yes
OrderService | syncOrders | response | stoppedAtSequence | integer |  | First entry that hit a transient failure (SD-028, 29 September): a refusal on the merits no longer stops the batch. (nullable)
OrderService | syncOrders | response | results | array of object | yes
OrderService | syncOrders | response | results[].id | string (uuid) | yes | The OfflineOrder.id this result is about.
OrderService | syncOrders | response | results[].sequence | integer | yes
OrderService | syncOrders | response | results[].status | enum (accepted, duplicate, rejected, blockedByRejection) | yes | rejected: refused on its merits and quarantined in sync.rejection; the batch continues.
OrderService | syncOrders | response | results[].orderNumber | string |  | (nullable)
OrderService | syncOrders | response | results[].priceVariance | object |  | Posted to the variance account.
OrderService | syncOrders | response | results[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | syncOrders | response | results[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | syncOrders | response | results[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | syncOrders | response | results[].varianceExceedsThreshold | boolean |  | True when review is required per the venue's variance threshold.
OrderService | syncOrders | response | results[].rejectionId | string |  | For a rejected or blockedByRejection entry, the sync.rejection row it was quarantined into (SD-028). (nullable)
OrderService | syncOrders | response | results[].reconcilerFlag | string |  | unitsGone on an accepted entry whose hold had expired before the sync and whose units were no longer free: the sale stands and the order is on the reconciliation queue, nothing refunded (FOUNDATION-A… (nullable)
OrderService | syncOrders | response | results[].error | Problem |  | RFC 9457 problem details.
OrderService | syncOrders | response | results[].error.type | string (uri) | yes | The problem type URI, https://api.ticvai.com/problems/<slug>.
OrderService | syncOrders | response | results[].error.title | string | yes
OrderService | syncOrders | response | results[].error.status | integer | yes
OrderService | syncOrders | response | results[].error.detail | string
OrderService | syncOrders | response | results[].error.instance | string
OrderService | syncOrders | response | results[].error.traceId | string
OrderService | syncOrders | response | results[].error.errors | array of object
OrderService | syncOrders | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | terminateTenant | request | reason | string | yes | (min length 3; max length 1000)
PlatformService | terminateTenant | request | retentionDays | integer | yes | (min 30; max 2555)
PlatformService | terminateTenant | request | confirmTenantCode | string | yes | Must match the tenant's code.
PlatformService | terminateTenant | response | tenantId | string (uuid) | yes
PlatformService | terminateTenant | response | scheduledAt | string (date-time) | yes
PlatformService | terminateTenant | response | retentionUntil | string (date-time) | yes | Cells are destroyed after this.
PlatformService | terminateTenant | response | isReversible | boolean | yes
PlatformService | terminateTenant | response | dataExportUrl | string |  | (nullable)
PlatformService | terminateTenant | response | requestedByPrincipalId | string (uuid)
PlatformService | terminateTenant | param (path) | tenantId | string (uuid) | yes
PlatformService | terminateTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | testAiProvider | request | taskKeys | array of string |  | The tasks to test; absent, every task the provider would serve.
AiService | testAiProvider | response | ok | boolean
AiService | testAiProvider | response | model | string
AiService | testAiProvider | response | latencyMs | integer
AiService | testAiProvider | response | failureReason | enum (invalidKey, expiredKey, quotaExceeded, modelUnavailable, unreachable, residencyRefused) |  | (nullable)
AiService | testAiProvider | response | verifiedAt | string (date-time)
AiService | testAiProvider | response | compatibility | AiProviderCompatibility |  | Whether a provider can serve the tasks it would take, before it takes them (Chinmay, 2 October, contract follow-ups: BYOK accepts any provider, with a compatibility test before activation; CHG-FUP-00…
AiService | testAiProvider | response | compatibility.status | enum (notTested, passed, failed) | yes
AiService | testAiProvider | response | compatibility.testedAt | string (date-time) |  | (nullable)
AiService | testAiProvider | response | compatibility.tasks | array of object
AiService | testAiProvider | response | compatibility.tasks[].taskKey | string | yes
AiService | testAiProvider | response | compatibility.tasks[].tier | string
AiService | testAiProvider | response | compatibility.tasks[].modelName | string |  | The vendor's model the curated map picked for this task and tier; null where the vendor has no curated equivalent, and the task stays on the TICVAI-managed model. (nullable)
AiService | testAiProvider | response | compatibility.tasks[].passed | boolean | yes
AiService | testAiProvider | response | compatibility.tasks[].failedProbes | array of enum (toolCalling, structuredOutput, arabic, contextWindow, latency, residency)
AiService | testAiProvider | param (path) | providerId | string (uuid) | yes
AiService | testAiProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | topUpWallet | request | id | string (uuid) | yes
WalletService | topUpWallet | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | topUpWallet | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | topUpWallet | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | topUpWallet | request | tender | string | yes
WalletService | topUpWallet | request | orderLineId | string (uuid) |  | The top-up line this credits (r8 gate, CHG-R8RW-009): a walletTopUp product line of the paid order, quantity 1, its gross amount amount.
WalletService | topUpWallet | request | paymentId | string (uuid) |  | A captured payment of the top-up line's order (r8 walk fix, CHG-R8WFC-003; CHG-R8RW-009), kept as the credit lot's source reference.
WalletService | topUpWallet | request | bonusAmount | object |  | Promotional bonus on top of the paid amount.
WalletService | topUpWallet | request | bonusAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | topUpWallet | request | bonusAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | request | bonusAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | topUpWallet | request | recordedAt | string (date-time) | yes
WalletService | topUpWallet | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | topUpWallet | response | subjectId | string (uuid) | yes
WalletService | topUpWallet | response | transferRules | object |  | What the venue allows this guest to do with a transfer, read from the venue's WalletTransferRules so a guest screen can hide or limit the action (r8 walk of tickets 28310 and 28345). (read-only; nullable)
WalletService | topUpWallet | response | transferRules.peerToPeerAllowed | boolean
WalletService | topUpWallet | response | transferRules.withinSharedWalletOnly | boolean
WalletService | topUpWallet | response | transferRules.maximumPerTransfer | object |  | (nullable)
WalletService | topUpWallet | response | transferRules.maximumPerTransfer.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | topUpWallet | response | transferRules.maximumPerTransfer.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | response | transferRules.maximumPerTransfer.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | topUpWallet | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | topUpWallet | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | topUpWallet | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | topUpWallet | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | topUpWallet | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | topUpWallet | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | topUpWallet | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | topUpWallet | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | topUpWallet | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | topUpWallet | response | credits[].sourceRef | string |  | (nullable)
WalletService | topUpWallet | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | topUpWallet | response | bonusBalance | object |  | Promotional value.
WalletService | topUpWallet | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | topUpWallet | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | topUpWallet | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | topUpWallet | response | status | enum (active, suspended, closed) | yes
WalletService | topUpWallet | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | topUpWallet | response | expiresAt | string (date-time) |  | (nullable)
WalletService | topUpWallet | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | topUpWallet | param (path) | subjectId | string (uuid) | yes
WalletService | topUpWallet | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | transferOrderTickets | request | ticketIds | array of string (uuid) | yes | The entitlements to hand over. (min items 1)
OrderService | transferOrderTickets | request | recipient | object | yes
OrderService | transferOrderTickets | request | recipient.channel | enum (email, sms, whatsapp) | yes
OrderService | transferOrderTickets | request | recipient.address | string | yes
OrderService | transferOrderTickets | request | message | string |  | (max length 500)
OrderService | transferOrderTickets | response | id | string (uuid) | yes
OrderService | transferOrderTickets | response | orderId | string (uuid) | yes
OrderService | transferOrderTickets | response | ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | transferOrderTickets | response | fromSubjectId | string (uuid)
OrderService | transferOrderTickets | response | toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | transferOrderTickets | response | recipientAddressMasked | string
OrderService | transferOrderTickets | response | status | enum (offered, claimed, expired, cancelled) | yes
OrderService | transferOrderTickets | response | claimUrl | string |  | The link the recipient is sent (R8 blocker fix, ORDERS-MONEY-C12). (nullable)
OrderService | transferOrderTickets | response | claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | transferOrderTickets | response | offeredAt | string (date-time) | yes
OrderService | transferOrderTickets | response | claimedAt | string (date-time) |  | (nullable)
OrderService | transferOrderTickets | response | expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | transferOrderTickets | param (path) | orderId | string (uuid) | yes
OrderService | transferOrderTickets | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | transferTableVisit | request | toPrincipalId | string (uuid) | yes
FnbService | transferTableVisit | request | reason | enum (shiftChange, break, sectionChange, escalation, other) | yes | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | transferTableVisit | request | note | string |  | Free text. (max length 500; nullable)
FnbService | transferTableVisit | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | transferTableVisit | response | id | string (uuid) | yes
FnbService | transferTableVisit | response | tableId | string (uuid) | yes
FnbService | transferTableVisit | response | tableLabel | string
FnbService | transferTableVisit | response | outletId | string (uuid) | yes
FnbService | transferTableVisit | response | covers | integer | yes
FnbService | transferTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | transferTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | transferTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | transferTableVisit | response | orders | array of FnbOrder | yes
FnbService | transferTableVisit | response | orders[].id | string (uuid) | yes
FnbService | transferTableVisit | response | orders[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | transferTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | transferTableVisit | response | orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | transferTableVisit | response | orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | transferTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | transferTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | transferTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | transferTableVisit | response | orders[].lines | array of object | yes
FnbService | transferTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | transferTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | transferTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | transferTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | transferTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | transferTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | transferTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | transferTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | transferTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | transferTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | transferTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | transferTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | transferTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | transferTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | transferTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | transferTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | transferTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | transferTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | transferTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | transferTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | transferTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | transferTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | transferTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | transferTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | transferTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | transferTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | transferTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | transferTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | transferTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | transferTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | transferTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | transferTableVisit | response | orders[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | transferTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | transferTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | transferTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | transferTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | transferTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | transferTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | transferTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | transferTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | transferTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | transferTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | transferTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | transferTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | transferTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | transferTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | transferTableVisit | response | openedAt | string (date-time) | yes
FnbService | transferTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | transferTableVisit | response | serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | transferTableVisit | response | serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | transferTableVisit | response | note | string |  | The server's note on the visit (updateTableVisit). (max length 500; read-only; nullable)
FnbService | transferTableVisit | param (path) | visitId | string (uuid) | yes
FnbService | transferTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | transferWalletBalance | request | toSubjectId | string (uuid) |  | The recipient guest.
WalletService | transferWalletBalance | request | toWalletId | string (uuid) |  | The receiving wallet, named outright.
WalletService | transferWalletBalance | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | transferWalletBalance | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | transferWalletBalance | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | transferWalletBalance | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | transferWalletBalance | request | message | string |  | The sender's note, stored as the reason of both transfer transactions, so the sender's history and the recipient's show it (WalletTransaction.reason; CHG-R11FXC-004). (max length 140; nullable)
WalletService | transferWalletBalance | response | id | string | yes
WalletService | transferWalletBalance | response | walletId | string (uuid) |  | The wallet this movement is on (SD-027, 29 September).
WalletService | transferWalletBalance | response | walletHoldId | string (uuid) |  | The hold a spend settled, where it came through holdWalletFunds. (nullable)
WalletService | transferWalletBalance | response | kind | WalletTransactionKind: enum (topUp, spend, refund, adjustment, bonus, expiry, transfer) | yes
WalletService | transferWalletBalance | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | transferWalletBalance | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | transferWalletBalance | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | transferWalletBalance | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | transferWalletBalance | response | balanceAfter | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | transferWalletBalance | response | balanceAfter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | transferWalletBalance | response | balanceAfter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | transferWalletBalance | response | balanceAfter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | transferWalletBalance | response | orderId | string |  | (nullable)
WalletService | transferWalletBalance | response | venueId | string (uuid) |  | (nullable)
WalletService | transferWalletBalance | response | reason | string |  | (nullable)
WalletService | transferWalletBalance | response | principalId | string (uuid) |  | (nullable)
WalletService | transferWalletBalance | response | recordedAt | string (date-time) | yes
WalletService | transferWalletBalance | param (path) | walletId | string (uuid) | yes
WalletService | transferWalletBalance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | transitionDynamicPricingStrategy | request | action | enum (activate, pause, resume, retire) | yes
CatalogueService | transitionDynamicPricingStrategy | request | reason | string |  | (max length 500; nullable)
CatalogueService | transitionDynamicPricingStrategy | response | id | string (uuid) | yes | (read-only)
CatalogueService | transitionDynamicPricingStrategy | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | transitionDynamicPricingStrategy | response | code | string | yes | (max length 40)
CatalogueService | transitionDynamicPricingStrategy | response | name | string | yes | (max length 200)
CatalogueService | transitionDynamicPricingStrategy | response | description | string |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | strategyType | enum (demandBased, occupancyBased, availabilityBased, inventoryBased, bookingVelocity, timeToEvent, seasonal, dayOfWeek, …) | yes
CatalogueService | transitionDynamicPricingStrategy | response | scopeType | enum (singleProduct, productFamily, event, multiplePerformances, venue, selectedTimeslots, selectedPriceCategories) | yes
CatalogueService | transitionDynamicPricingStrategy | response | venueId | string (uuid) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | productId | string (uuid) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | productFamily | string |  | (max length 100; nullable)
CatalogueService | transitionDynamicPricingStrategy | response | eventId | string (uuid) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | performanceIds | array of string (uuid)
CatalogueService | transitionDynamicPricingStrategy | response | timeslotIds | array of string (uuid)
CatalogueService | transitionDynamicPricingStrategy | response | priceCategoryIds | array of string (uuid)
CatalogueService | transitionDynamicPricingStrategy | response | businessUnit | string |  | (max length 100; nullable)
CatalogueService | transitionDynamicPricingStrategy | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | transitionDynamicPricingStrategy | response | basePriceSource | string |  | The price list or rate the adjustments start from. (max length 100)
CatalogueService | transitionDynamicPricingStrategy | response | evaluationFrequency | enum (every15Minutes, every30Minutes, hourly, daily, onInventoryChange, onThresholdTrigger) |  | (default hourly)
CatalogueService | transitionDynamicPricingStrategy | response | combinationMode | enum (independent, combinable, exclusive, fallback) |  | (default independent)
CatalogueService | transitionDynamicPricingStrategy | response | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | clonedFromStrategyId | string (uuid) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | transitionDynamicPricingStrategy | response | status | enum (draft, active, paused, frozen, expired, retired) | yes | (default draft)
CatalogueService | transitionDynamicPricingStrategy | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | transitionDynamicPricingStrategy | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | transitionDynamicPricingStrategy | param (path) | strategyId | string (uuid) | yes
CatalogueService | transitionDynamicPricingStrategy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | transmitEInvoices | request | legalEntityId | string (uuid) | yes
LedgerService | transmitEInvoices | request | documentIds | array of string (uuid) |  | Tax invoice or credit memo ids.
LedgerService | transmitEInvoices | request | issuedFrom | string (date)
LedgerService | transmitEInvoices | request | issuedTo | string (date)
LedgerService | transmitEInvoices | response | queued | integer
LedgerService | transmitEInvoices | response | skippedAlreadyAccepted | integer
LedgerService | transmitEInvoices | response | transmissions | array of FinEInvoiceTransmission
LedgerService | transmitEInvoices | response | transmissions[].id | string (uuid) | yes
LedgerService | transmitEInvoices | response | transmissions[].documentKind | enum (taxInvoice, creditMemo) | yes
LedgerService | transmitEInvoices | response | transmissions[].documentId | string (uuid) | yes
LedgerService | transmitEInvoices | response | transmissions[].documentNumber | string
LedgerService | transmitEInvoices | response | transmissions[].legalEntityId | string (uuid) | yes
LedgerService | transmitEInvoices | response | transmissions[].providerId | string (uuid) |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].mode | enum (test, live)
LedgerService | transmitEInvoices | response | transmissions[].status | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) | yes | 6.1.1.
LedgerService | transmitEInvoices | response | transmissions[].payloadHash | string |  | SHA-256 of the document as sent, so a resend can be shown to be the same document. (nullable)
LedgerService | transmitEInvoices | response | transmissions[].providerMessageId | string |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].attempt | integer |  | (min 1)
LedgerService | transmitEInvoices | response | transmissions[].errorCodes | array of string
LedgerService | transmitEInvoices | response | transmissions[].errorMessage | string |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].sentAt | string (date-time) |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].answeredAt | string (date-time) |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].createdAt | string (date-time) | yes
LedgerService | transmitEInvoices | response | transmissions[].scopePath | string |  | (read-only)
LedgerService | transmitEInvoices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | unpublishGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | unpublishGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | unpublishGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | unpublishGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | unpublishGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | unpublishGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | unpublishGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | unpublishGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | unpublishGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | unpublishGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | unpublishGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | unpublishGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | unpublishGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | unpublishGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | unpublishGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | unpublishGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | unpublishGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | updateAccessPoint | request | name | string |  | (max length 200)
AccessService | updateAccessPoint | request | direction | Direction: enum (entry, exit, reentry, crossover)
AccessService | updateAccessPoint | request | antiPassbackEnabled | boolean
AccessService | updateAccessPoint | request | requiresExitBeforeReentry | boolean
AccessService | updateAccessPoint | request | isActive | boolean
AccessService | updateAccessPoint | request | driver | string |  | Driver identifier for the controller behind this access point.
AccessService | updateAccessPoint | request | temporaryClosure | object |  | Close or reopen the access point's attraction for a while (AccessPoint.temporaryClosure; DEC-228; CHG-CSP-026). (nullable)
AccessService | updateAccessPoint | request | temporaryClosure.isClosed | boolean
AccessService | updateAccessPoint | request | temporaryClosure.reason | string |  | (max length 200; nullable)
AccessService | updateAccessPoint | request | temporaryClosure.reopensAt | string (date-time) |  | (nullable)
AccessService | updateAccessPoint | request | temporaryClosure.offerVirtualQueueReturn | boolean
AccessService | updateAccessPoint | request | temporaryClosure.queueId | string (uuid) |  | (nullable)
AccessService | updateAccessPoint | response | id | string (uuid) | yes
AccessService | updateAccessPoint | response | code | string | yes
AccessService | updateAccessPoint | response | name | string | yes
AccessService | updateAccessPoint | response | venueId | string (uuid) | yes
AccessService | updateAccessPoint | response | accessAreaId | string (uuid) |  | The zone this access point admits to (R8 blocker FOUNDATION-AI-C12, CHG-R8MIG-004): an access.access_area row whose entityType is zone (named for the table it keys, as every key is). (nullable)
AccessService | updateAccessPoint | response | scopePath | string
AccessService | updateAccessPoint | response | externalCredentialSources | object |  | BL-108.
AccessService | updateAccessPoint | response | scanAnomalyRules | object |  | BL-104.
AccessService | updateAccessPoint | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | updateAccessPoint | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | updateAccessPoint | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | updateAccessPoint | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | updateAccessPoint | response | temporaryClosure | object |  | What the access point does while its attraction is temporarily closed (decided 2 October 2026, Chinmay, batch 6 set 9, BO-147: "Deny + reopening time + a virtual-queue return window where enabled"; D… (nullable)
AccessService | updateAccessPoint | response | temporaryClosure.isClosed | boolean |  | (default False)
AccessService | updateAccessPoint | response | temporaryClosure.reason | string |  | Shown to staff; the guest sees "Attraction temporarily closed". (max length 200; nullable)
AccessService | updateAccessPoint | response | temporaryClosure.reopensAt | string (date-time) |  | When it is expected to reopen; shown to the guest when known. (nullable)
AccessService | updateAccessPoint | response | temporaryClosure.offerVirtualQueueReturn | boolean |  | Offer a virtual-queue return window at the denied scan, where the attraction has a queue. (default False)
AccessService | updateAccessPoint | response | temporaryClosure.queueId | string (uuid) |  | The virtual queue the return window is taken in. (nullable)
AccessService | updateAccessPoint | response | antiPassbackEnabled | boolean
AccessService | updateAccessPoint | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | updateAccessPoint | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | updateAccessPoint | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | updateAccessPoint | response | geofence.latitude | number
AccessService | updateAccessPoint | response | geofence.longitude | number
AccessService | updateAccessPoint | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | updateAccessPoint | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | updateAccessPoint | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | updateAccessPoint | response | isActive | boolean | yes
AccessService | updateAccessPoint | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | updateAccessPoint | response | directionEffectiveAt | string (date-time) |  | When a direction change set by setAccessPointDirection takes effect; held pending until then. (read-only; nullable)
AccessService | updateAccessPoint | response | directionChangeReason | string |  | Why the gate was last turned round (setAccessPointDirection). (max length 200; read-only; nullable)
AccessService | updateAccessPoint | param (path) | accessPointId | string (uuid) | yes
AccessService | updateAccessPoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | updateAdmissionRules | request | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | updateAdmissionRules | request | code | string | yes | (max length 64)
AccessService | updateAdmissionRules | request | perProductRules | object |  | BL-059.
AccessService | updateAdmissionRules | request | name | string | yes | (max length 200)
AccessService | updateAdmissionRules | request | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | updateAdmissionRules | request | closeMinutesAfter | integer | yes
AccessService | updateAdmissionRules | request | maxDurationMinutes | integer |  | (nullable)
AccessService | updateAdmissionRules | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | updateAdmissionRules | request | maxReentries | integer |  | (nullable)
AccessService | updateAdmissionRules | request | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | request | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | updateAdmissionRules | request | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | updateAdmissionRules | request | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | updateAdmissionRules | request | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | updateAdmissionRules | request | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | updateAdmissionRules | request | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | updateAdmissionRules | request | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | updateAdmissionRules | request | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | updateAdmissionRules | request | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | request | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | updateAdmissionRules | request | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | updateAdmissionRules | request | validity.from | string (date)
AccessService | updateAdmissionRules | request | validity.to | string (date) |  | Inclusive.
AccessService | updateAdmissionRules | request | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | updateAdmissionRules | request | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | updateAdmissionRules | request | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | updateAdmissionRules | request | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | updateAdmissionRules | request | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | updateAdmissionRules | request | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | updateAdmissionRules | request | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | updateAdmissionRules | request | crossover.sameDayOnly | boolean |  | (default True)
AccessService | updateAdmissionRules | request | crossover.differentDayAccess | boolean |  | (default False)
AccessService | updateAdmissionRules | request | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | updateAdmissionRules | request | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | request | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | request | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | updateAdmissionRules | request | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | updateAdmissionRules | request | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | updateAdmissionRules | request | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | updateAdmissionRules | request | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | updateAdmissionRules | request | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | updateAdmissionRules | request | scopePath | string |  | The partition key (ADR-0005).
AccessService | updateAdmissionRules | response | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | updateAdmissionRules | response | code | string | yes | (max length 64)
AccessService | updateAdmissionRules | response | perProductRules | object |  | BL-059.
AccessService | updateAdmissionRules | response | name | string | yes | (max length 200)
AccessService | updateAdmissionRules | response | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | updateAdmissionRules | response | closeMinutesAfter | integer | yes
AccessService | updateAdmissionRules | response | maxDurationMinutes | integer |  | (nullable)
AccessService | updateAdmissionRules | response | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | updateAdmissionRules | response | maxReentries | integer |  | (nullable)
AccessService | updateAdmissionRules | response | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | response | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | updateAdmissionRules | response | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | updateAdmissionRules | response | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | updateAdmissionRules | response | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | updateAdmissionRules | response | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | updateAdmissionRules | response | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | updateAdmissionRules | response | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | updateAdmissionRules | response | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | updateAdmissionRules | response | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | response | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | updateAdmissionRules | response | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | updateAdmissionRules | response | validity.from | string (date)
AccessService | updateAdmissionRules | response | validity.to | string (date) |  | Inclusive.
AccessService | updateAdmissionRules | response | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | updateAdmissionRules | response | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | updateAdmissionRules | response | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | updateAdmissionRules | response | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | updateAdmissionRules | response | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | updateAdmissionRules | response | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | updateAdmissionRules | response | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | updateAdmissionRules | response | crossover.sameDayOnly | boolean |  | (default True)
AccessService | updateAdmissionRules | response | crossover.differentDayAccess | boolean |  | (default False)
AccessService | updateAdmissionRules | response | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | updateAdmissionRules | response | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | response | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | response | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | updateAdmissionRules | response | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | updateAdmissionRules | response | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | updateAdmissionRules | response | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | updateAdmissionRules | response | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | updateAdmissionRules | response | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | updateAdmissionRules | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | updateAdmissionRules | param (path) | profileId | string (uuid) | yes
AccessService | updateAdmissionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateBanner | request | title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | request | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | request | imageAssetRef | string (uuid)
WhiteLabelService | updateBanner | request | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | updateBanner | request | linkTarget | LinkTarget
WhiteLabelService | updateBanner | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updateBanner | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updateBanner | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updateBanner | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updateBanner | request | linkTarget.productId | string (uuid)
WhiteLabelService | updateBanner | request | linkTarget.eventId | string (uuid)
WhiteLabelService | updateBanner | request | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | updateBanner | request | linkTarget.url | string
WhiteLabelService | updateBanner | request | startsAt | string (date-time)
WhiteLabelService | updateBanner | request | endsAt | string (date-time) |  | Null runs the banner with no end. (nullable)
WhiteLabelService | updateBanner | request | sortOrder | integer
WhiteLabelService | updateBanner | request | isActive | boolean
WhiteLabelService | updateBanner | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updateBanner | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | response | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | response | imageAssetRef | string (uuid) | yes
WhiteLabelService | updateBanner | response | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | updateBanner | response | linkTarget | LinkTarget
WhiteLabelService | updateBanner | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updateBanner | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updateBanner | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updateBanner | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updateBanner | response | linkTarget.productId | string (uuid)
WhiteLabelService | updateBanner | response | linkTarget.eventId | string (uuid)
WhiteLabelService | updateBanner | response | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | updateBanner | response | linkTarget.url | string
WhiteLabelService | updateBanner | response | startsAt | string (date-time) | yes
WhiteLabelService | updateBanner | response | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | updateBanner | response | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | updateBanner | response | sortOrder | integer
WhiteLabelService | updateBanner | response | isActive | boolean
WhiteLabelService | updateBanner | param (path) | bannerId | string (uuid) | yes
WhiteLabelService | updateBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateBookingFlowDefinition | request | name | string |  | (max length 80)
WhiteLabelService | updateBookingFlowDefinition | request | isDefaultForType | boolean
WhiteLabelService | updateBookingFlowDefinition | request | isEnabled | boolean
WhiteLabelService | updateBookingFlowDefinition | request | steps | array of BookingFlowStep |  | (min items 1; max items 30)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | updateBookingFlowDefinition | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | updateBookingFlowDefinition | request | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | request | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | updateBookingFlowDefinition | request | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | updateBookingFlowDefinition | request | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | updateBookingFlowDefinition | request | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | updateBookingFlowDefinition | request | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | updateBookingFlowDefinition | request | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | updateBookingFlowDefinition | response | id | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | updateBookingFlowDefinition | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | updateBookingFlowDefinition | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | updateBookingFlowDefinition | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | updateBookingFlowDefinition | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | updateBookingFlowDefinition | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | updateBookingFlowDefinition | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | updateBookingFlowDefinition | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | updateBookingFlowDefinition | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | updateBookingFlowDefinition | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | updateBookingFlowDefinition | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | updateBookingFlowDefinition | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | updateBookingFlowDefinition | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | updateBookingFlowDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateBundle | request | name | string |  | (max length 200)
CatalogueService | updateBundle | request | price | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updateBundle | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateBundle | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateBundle | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateBundle | request | validTo | string (date-time)
CatalogueService | updateBundle | request | isActive | boolean
CatalogueService | updateBundle | response | code | string | yes | (max length 64)
CatalogueService | updateBundle | response | name | string | yes | (max length 200)
CatalogueService | updateBundle | response | description | string |  | (max length 1000)
CatalogueService | updateBundle | response | venueId | string (uuid) | yes
CatalogueService | updateBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | updateBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | updateBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | updateBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | updateBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | updateBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | updateBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | updateBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | updateBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | updateBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | updateBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | updateBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | updateBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | updateBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | updateBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | updateBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | updateBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | updateBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | updateBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | updateBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | updateBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | updateBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | updateBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | updateBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | updateBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | updateBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | updateBundle | response | allocation | object | yes | Stored as promotions.allocation_split and promotions.allocation_component, the record of the split; promotions.bundle.allocation is a copy derived from them in the same transaction (ADAM CR-110, opti…
CatalogueService | updateBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | updateBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | updateBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | updateBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | updateBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | updateBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updateBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | updateBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | updateBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | updateBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | updateBundle | response | validFrom | string (date-time)
CatalogueService | updateBundle | response | validTo | string (date-time)
CatalogueService | updateBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | updateBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | updateBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | updateBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | updateBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | updateBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | updateBundle | response | id | string (uuid) | yes
CatalogueService | updateBundle | response | variantId | string (uuid) |  | The catalogue variant a cart line of this bundle names (R8 blocker ORDERS-MONEY-C43, CHG-R8MIG-023): each sold bundle has a catalogue product of kind bundle with one variant, made when the bundle is… (read-only; nullable)
CatalogueService | updateBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price: the list_price captured on each promotions.allocation_component when the bundle was created, not the variants' current prices (ADAM CR-110, option…
CatalogueService | updateBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateBundle | response | savingsPercentage | number
CatalogueService | updateBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | updateBundle | response | isActive | boolean | yes
CatalogueService | updateBundle | param (path) | bundleId | string (uuid) | yes
CatalogueService | updateBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateCampaign | request | name | string |  | (max length 200)
MarketingService | updateCampaign | request | isPaused | boolean
MarketingService | updateCampaign | request | scheduledFor | string (date-time)
MarketingService | updateCampaign | request | content | CampaignContent
MarketingService | updateCampaign | request | content.templateId | string (uuid) | yes
MarketingService | updateCampaign | request | content.subjectOverride | object
MarketingService | updateCampaign | request | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | updateCampaign | request | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | updateCampaign | request | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | updateCampaign | request | variants[].id | string (uuid) |  | (read-only)
MarketingService | updateCampaign | request | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | updateCampaign | request | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | updateCampaign | request | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | updateCampaign | request | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | updateCampaign | request | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | updateCampaign | request | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | updateCampaign | request | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | updateCampaign | request | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | updateCampaign | request | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | updateCampaign | request | abTest | object |  | How the variants are tested. (nullable)
MarketingService | updateCampaign | request | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | updateCampaign | request | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | updateCampaign | request | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | updateCampaign | request | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | updateCampaign | request | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | updateCampaign | request | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | updateCampaign | response | name | string | yes | (max length 200)
MarketingService | updateCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | updateCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | updateCampaign | response | venueId | string (uuid)
MarketingService | updateCampaign | response | segmentId | string (uuid) | yes
MarketingService | updateCampaign | response | content | CampaignContent | yes
MarketingService | updateCampaign | response | content.templateId | string (uuid) | yes
MarketingService | updateCampaign | response | content.subjectOverride | object
MarketingService | updateCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | updateCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | updateCampaign | response | trigger | CampaignTrigger
MarketingService | updateCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | updateCampaign | response | trigger.delayHours | integer
MarketingService | updateCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | updateCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | updateCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | updateCampaign | response | trigger.conditions[].value | object
MarketingService | updateCampaign | response | trigger.conditions[].values | array of object
MarketingService | updateCampaign | response | scheduledFor | string (date-time)
MarketingService | updateCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | updateCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | updateCampaign | response | sendWindow.startTime | string
MarketingService | updateCampaign | response | sendWindow.endTime | string
MarketingService | updateCampaign | response | sendWindow.timeZone | string
MarketingService | updateCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | updateCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | updateCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | updateCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | updateCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | updateCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | updateCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | updateCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | updateCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | updateCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | updateCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | updateCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | updateCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | updateCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | updateCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | updateCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | updateCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | updateCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | updateCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | updateCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | updateCampaign | response | id | string (uuid) | yes
MarketingService | updateCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | updateCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | updateCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | updateCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | updateCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | updateCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | updateCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | updateCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | updateCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | updateCampaign | response | isPaused | boolean
MarketingService | updateCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | updateCampaign | response | createdAt | string (date-time) | yes
MarketingService | updateCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | updateCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | updateCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | updateCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | updateCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | updateCartLine | request | quantity | integer | yes | The new quantity. (min 0)
OrderService | updateCartLine | response | id | string (uuid) | yes
OrderService | updateCartLine | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | updateCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | updateCartLine | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | updateCartLine | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | updateCartLine | response | venueId | string (uuid) | yes
OrderService | updateCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | updateCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | updateCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | updateCartLine | response | lines | array of CartLine | yes
OrderService | updateCartLine | response | lines[].id | string (uuid) | yes
OrderService | updateCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | updateCartLine | response | lines[].productName | string |  | (read-only)
OrderService | updateCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | updateCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | updateCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | updateCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | updateCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | updateCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | updateCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | updateCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | updateCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | updateCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | updateCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | updateCartLine | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | updateCartLine | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | updateCartLine | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | updateCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | updateCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | updateCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | updateCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | updateCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | updateCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | updateCartLine | response | conflicts | array of CartConflict
OrderService | updateCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | updateCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | updateCartLine | response | conflicts[].message | string
OrderService | updateCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | updateCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | updateCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | updateCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | updateCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | updateCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | updateCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | updateCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | updateCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | updateCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | updateCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | updateCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | updateCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | updateCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | updateCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | updateCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | updateCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | updateCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | updateCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | updateCartLine | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | updateCartLine | response | locale | string
OrderService | updateCartLine | response | createdAt | string (date-time)
OrderService | updateCartLine | response | updatedAt | string (date-time)
OrderService | updateCartLine | param (path) | cartId | string (uuid) | yes
OrderService | updateCartLine | param (path) | lineId | string (uuid) | yes
OrderService | updateCartLine | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | updateCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateConsentQuestion | request | text | object |  | The question as the guest reads it, per locale.
MarketingService | updateConsentQuestion | request | helpText | object |  | (nullable)
MarketingService | updateConsentQuestion | request | scope | enum (perPerson, perBooking) |  | A change raises version by one.
MarketingService | updateConsentQuestion | request | required | boolean |  | A change raises version by one.
MarketingService | updateConsentQuestion | request | blockingAnswer | enum (yes, no, none) |  | A change raises version by one.
MarketingService | updateConsentQuestion | request | status | enum (active, retired) |  | retired stops the question being asked and changes no version.
MarketingService | updateConsentQuestion | response | id | string (uuid) | yes | (read-only)
MarketingService | updateConsentQuestion | response | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | updateConsentQuestion | response | text | object | yes | The question as the guest reads it, per locale.
MarketingService | updateConsentQuestion | response | helpText | object |  | (nullable)
MarketingService | updateConsentQuestion | response | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | updateConsentQuestion | response | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | updateConsentQuestion | response | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | updateConsentQuestion | response | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | updateConsentQuestion | response | status | enum (active, retired) | yes | (default active)
MarketingService | updateConsentQuestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | updateConsentQuestion | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateConsentQuestion | param (path) | questionId | string (uuid) | yes
MarketingService | updateConsentQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateContentBlock | request | body | object |  | As ContentBlock.body.
WhiteLabelService | updateContentBlock | request | localeVariants | object |  | As ContentBlock.localeVariants.
WhiteLabelService | updateContentBlock | request | position | integer
WhiteLabelService | updateContentBlock | request | publishAt | string (date-time) |  | (nullable)
WhiteLabelService | updateContentBlock | request | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | updateContentBlock | request | audienceSegmentId | string (uuid) |  | (nullable)
WhiteLabelService | updateContentBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updateContentBlock | response | pageId | string (uuid) |  | (nullable)
WhiteLabelService | updateContentBlock | response | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | updateContentBlock | response | position | integer
WhiteLabelService | updateContentBlock | response | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | updateContentBlock | response | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | updateContentBlock | response | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | updateContentBlock | response | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | updateContentBlock | response | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | updateContentBlock | response | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | updateContentBlock | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | updateContentBlock | response | reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step of publishContentBlock, where the tenant's publish-review policy is on (r8 walk of ticket 27919). (default notRequired; read-only)
WhiteLabelService | updateContentBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updateContentBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateContentBlock | param (path) | blockId | string (uuid) | yes
WhiteLabelService | updateContentPage | request | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | updateContentPage | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateContentPage | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | updateContentPage | request | isEnabled | boolean |  | (default True)
WhiteLabelService | updateContentPage | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | updateContentPage | request | categoryCode | string |  | (nullable)
WhiteLabelService | updateContentPage | request | sortOrder | integer
WhiteLabelService | updateContentPage | request | status | object |  | Only archived is taken — send it to withdraw a published page or abandon a draft (states/content.yaml).
WhiteLabelService | updateContentPage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updateContentPage | response | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | updateContentPage | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateContentPage | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | updateContentPage | response | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | updateContentPage | response | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | updateContentPage | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | updateContentPage | response | categoryCode | string |  | (nullable)
WhiteLabelService | updateContentPage | response | sortOrder | integer
WhiteLabelService | updateContentPage | response | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | updateContentPage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updateContentPage | param (path) | pageId | string (uuid) | yes
WhiteLabelService | updateContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | updateCreditType | request | id | string (uuid)
WalletService | updateCreditType | request | code | string | yes
WalletService | updateCreditType | request | name | string | yes
WalletService | updateCreditType | request | category | enum (cash, refund, bonus, promotional, giftCard, membership, loyalty, ride, …)
WalletService | updateCreditType | request | monetary | boolean |  | Loyalty points are not money. (default True)
WalletService | updateCreditType | request | conversionRate | number |  | (nullable)
WalletService | updateCreditType | request | refundable | boolean |  | Promotional credit is not refundable and cash credit is. (default False)
WalletService | updateCreditType | request | transferable | boolean |  | (default False)
WalletService | updateCreditType | request | expires | boolean |  | (default False)
WalletService | updateCreditType | request | validityDays | integer |  | (nullable)
WalletService | updateCreditType | request | breakageEligible | boolean |  | (default False)
WalletService | updateCreditType | request | ledgerAccountCode | string |  | (nullable)
WalletService | updateCreditType | request | priority | integer |  | (default 0)
WalletService | updateCreditType | request | scopePath | string
WalletService | updateCreditType | request | isActive | boolean |  | (default True)
WalletService | updateCreditType | response | id | string (uuid)
WalletService | updateCreditType | response | code | string | yes
WalletService | updateCreditType | response | name | string | yes
WalletService | updateCreditType | response | category | enum (cash, refund, bonus, promotional, giftCard, membership, loyalty, ride, …)
WalletService | updateCreditType | response | monetary | boolean |  | Loyalty points are not money. (default True)
WalletService | updateCreditType | response | conversionRate | number |  | (nullable)
WalletService | updateCreditType | response | refundable | boolean |  | Promotional credit is not refundable and cash credit is. (default False)
WalletService | updateCreditType | response | transferable | boolean |  | (default False)
WalletService | updateCreditType | response | expires | boolean |  | (default False)
WalletService | updateCreditType | response | validityDays | integer |  | (nullable)
WalletService | updateCreditType | response | breakageEligible | boolean |  | (default False)
WalletService | updateCreditType | response | ledgerAccountCode | string |  | (nullable)
WalletService | updateCreditType | response | priority | integer |  | (default 0)
WalletService | updateCreditType | response | scopePath | string
WalletService | updateCreditType | response | isActive | boolean |  | (default True)
WalletService | updateCreditType | param (path) | creditTypeId | string (uuid) | yes
WalletService | updateCreditType | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | updateCreditType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | updateDashboard | request | name | string | yes | (max length 200)
ReportingService | updateDashboard | request | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | updateDashboard | request | description | string |  | (max length 1000)
ReportingService | updateDashboard | request | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | updateDashboard | request | isShared | boolean |  | (default False)
ReportingService | updateDashboard | request | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | updateDashboard | request | tiles[].id | string (uuid) | yes
ReportingService | updateDashboard | request | tiles[].title | string
ReportingService | updateDashboard | request | tiles[].reportId | string (uuid) | yes
ReportingService | updateDashboard | request | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | updateDashboard | request | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | updateDashboard | request | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | updateDashboard | request | tiles[].position | object | yes
ReportingService | updateDashboard | request | tiles[].position.row | integer | yes
ReportingService | updateDashboard | request | tiles[].position.column | integer | yes
ReportingService | updateDashboard | request | tiles[].position.width | integer | yes
ReportingService | updateDashboard | request | tiles[].position.height | integer | yes
ReportingService | updateDashboard | response | name | string | yes | (max length 200)
ReportingService | updateDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | updateDashboard | response | description | string |  | (max length 1000)
ReportingService | updateDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | updateDashboard | response | isShared | boolean |  | (default False)
ReportingService | updateDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | updateDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | updateDashboard | response | tiles[].title | string
ReportingService | updateDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | updateDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | updateDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | updateDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | updateDashboard | response | tiles[].position | object | yes
ReportingService | updateDashboard | response | tiles[].position.row | integer | yes
ReportingService | updateDashboard | response | tiles[].position.column | integer | yes
ReportingService | updateDashboard | response | tiles[].position.width | integer | yes
ReportingService | updateDashboard | response | tiles[].position.height | integer | yes
ReportingService | updateDashboard | response | id | string (uuid) | yes
ReportingService | updateDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | updateDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | updateDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | updateDashboard | response | createdAt | string (date-time) | yes
ReportingService | updateDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | updateDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | updateDeliveryLocation | request | label | string |  | (max length 200)
FnbService | updateDeliveryLocation | request | zone | string |  | (nullable)
FnbService | updateDeliveryLocation | request | isServiceable | boolean
FnbService | updateDeliveryLocation | request | unserviceableReason | string |  | (nullable)
FnbService | updateDeliveryLocation | request | walkTimeMinutes | integer |  | (min 0; nullable)
FnbService | updateDeliveryLocation | response | id | string (uuid) | yes
FnbService | updateDeliveryLocation | response | venueId | string (uuid) | yes
FnbService | updateDeliveryLocation | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | updateDeliveryLocation | response | label | string | yes | What a runner is told.
FnbService | updateDeliveryLocation | response | zone | string |  | (nullable)
FnbService | updateDeliveryLocation | response | opensAt | string (time) |  | When a collection point opens, local to the venue (r8 walk of ticket 27820). (nullable)
FnbService | updateDeliveryLocation | response | closesAt | string (time) |  | When a collection point closes, local to the venue; retail collectBy defaults to this on the day. (nullable)
FnbService | updateDeliveryLocation | response | tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | updateDeliveryLocation | response | seatId | string |  | Set where the seat is the address. (nullable)
FnbService | updateDeliveryLocation | response | servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | updateDeliveryLocation | response | isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | updateDeliveryLocation | response | unserviceableReason | string |  | (nullable)
FnbService | updateDeliveryLocation | response | walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | updateDeliveryLocation | response | codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | updateDeliveryLocation | param (path) | locationId | string (uuid) | yes
FnbService | updateDeliveryLocation | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | updateDeliveryLocation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateEvent | request | name | string |  | (max length 200)
CatalogueService | updateEvent | request | parentEventId | string (uuid) |  | (nullable)
CatalogueService | updateEvent | request | isActive | boolean
CatalogueService | updateEvent | response | id | string (uuid) | yes
CatalogueService | updateEvent | response | code | string | yes
CatalogueService | updateEvent | response | name | string | yes
CatalogueService | updateEvent | response | venueId | string (uuid) | yes
CatalogueService | updateEvent | response | scopePath | string | yes
CatalogueService | updateEvent | response | parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | updateEvent | response | performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | updateEvent | response | isActive | boolean
CatalogueService | updateEvent | response | lifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | Where the event is in its lifecycle (4 October 2026, CHG-FXC-003; catalogue.event had nowhere to keep it). (read-only)
CatalogueService | updateEvent | response | lifecycleStateChangedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | updateEvent | response | scheduledLifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | A move waiting for its effectiveFrom (ADAM CR-109, option 2; CHG-R10CAT-009): written by setEventLifecycleState when effectiveFrom is in the future, applied and cleared by the event lifecycle job in… (read-only; nullable)
CatalogueService | updateEvent | response | scheduledLifecycleAt | string (date-time) |  | When the waiting move is applied (the request's effectiveFrom; ADAM CR-109). (read-only; nullable)
CatalogueService | updateEvent | response | scheduledLifecycleReason | string |  | The reason given with the waiting move, carried on event.lifecycleChanged when it is applied (ADAM CR-109). (max length 500; read-only; nullable)
CatalogueService | updateEvent | param (path) | eventId | string (uuid) | yes
CatalogueService | updateEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateGuestPreferences | request | id | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | request | subjectId | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | request | seatingPreference | string |  | (max length 200; nullable)
MarketingService | updateGuestPreferences | request | drinkPreferences | array of string
MarketingService | updateGuestPreferences | request | dietary | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | request | accessibility | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | request | preferredChannel | object |  | Stored on the profile (GuestProfile.preferredChannel) — carried here because the preference screen edits it beside the rest.
MarketingService | updateGuestPreferences | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateGuestPreferences | response | id | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | response | subjectId | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | response | seatingPreference | string |  | (max length 200; nullable)
MarketingService | updateGuestPreferences | response | drinkPreferences | array of string
MarketingService | updateGuestPreferences | response | dietary | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | response | accessibility | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | response | preferredChannel | object |  | Stored on the profile (GuestProfile.preferredChannel) — carried here because the preference screen edits it beside the rest.
MarketingService | updateGuestPreferences | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateGuestPreferences | param (path) | subjectId | string (uuid) | yes
MarketingService | updateGuestPreferences | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateGuidedChoice | request | name | string |  | (max length 80)
WhiteLabelService | updateGuidedChoice | request | mode | enum (button, popupOnArrival, off)
WhiteLabelService | updateGuidedChoice | request | showBanner | boolean
WhiteLabelService | updateGuidedChoice | request | behaviour | enum (filter, recommend)
WhiteLabelService | updateGuidedChoice | request | showEverything | boolean
WhiteLabelService | updateGuidedChoice | request | questions | array of object |  | Replaces the whole question list; same shape and bounds as GuidedChoice.questions. (min items 1; max items 4)
WhiteLabelService | updateGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | updateGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | updateGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | updateGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | updateGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | updateGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | updateGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | updateGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | updateGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | updateGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | updateGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | updateGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | updateGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | updateGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | updateGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | updateGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | updateGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | updateGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | updateGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | updateInventoryItem | request | name | string |  | (max length 200)
InventoryService | updateInventoryItem | request | categoryId | string (uuid) |  | Null clears the category (decided 28 September, audit R171). (nullable)
InventoryService | updateInventoryItem | request | reorderPoint | number |  | (min 0)
InventoryService | updateInventoryItem | request | reorderQuantity | number |  | (min 0)
InventoryService | updateInventoryItem | request | parLevel | number |  | (min 0)
InventoryService | updateInventoryItem | request | preferredSupplierId | string (uuid) |  | Null clears the preferred supplier (decided 28 September, audit R171). (nullable)
InventoryService | updateInventoryItem | request | isActive | boolean
InventoryService | updateInventoryItem | request | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) |  | Fixed at item creation.
InventoryService | updateInventoryItem | request | baseUnit | string |  | Changeable only while hasMovements is false; the 409 below is the refusal once it is true.
InventoryService | updateInventoryItem | response | sku | string | yes | Unique within the item's venue, as the 409 says (ADAM CR-068, CHG-DDL-003): an inventory item is something one venue stocks (venueId is required), so two venues of a chain keep their own row for the… (max length 64)
InventoryService | updateInventoryItem | response | barcode | string |  | (max length 128)
InventoryService | updateInventoryItem | response | name | string | yes | (max length 200)
InventoryService | updateInventoryItem | response | venueId | string (uuid) | yes
InventoryService | updateInventoryItem | response | categoryId | string (uuid)
InventoryService | updateInventoryItem | response | baseUnit | string | yes | The unit stock is held in.
InventoryService | updateInventoryItem | response | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | updateInventoryItem | response | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | updateInventoryItem | response | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | updateInventoryItem | response | reorderPoint | number |  | (min 0)
InventoryService | updateInventoryItem | response | reorderQuantity | number |  | (min 0)
InventoryService | updateInventoryItem | response | parLevel | number |  | (min 0)
InventoryService | updateInventoryItem | response | preferredSupplierId | string (uuid)
InventoryService | updateInventoryItem | response | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | updateInventoryItem | response | isPerishable | boolean |  | (default False)
InventoryService | updateInventoryItem | response | shelfLifeDays | integer |  | (nullable)
InventoryService | updateInventoryItem | response | id | string (uuid) | yes
InventoryService | updateInventoryItem | response | onHand | number | yes | Derived from movements.
InventoryService | updateInventoryItem | response | onOrder | number
InventoryService | updateInventoryItem | response | inTransit | number
InventoryService | updateInventoryItem | response | available | number |  | On-hand minus allocated, where allocated is stock reserved for orders (decided 28 September, audit R171).
InventoryService | updateInventoryItem | response | averageCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | updateInventoryItem | response | averageCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | updateInventoryItem | response | averageCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | updateInventoryItem | response | averageCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | updateInventoryItem | response | lastPurchasePrice | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | updateInventoryItem | response | lastPurchasePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | updateInventoryItem | response | lastPurchasePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | updateInventoryItem | response | lastPurchasePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | updateInventoryItem | response | isBelowReorderPoint | boolean
InventoryService | updateInventoryItem | response | hasMovements | boolean |  | True locks costing method and base unit.
InventoryService | updateInventoryItem | response | isActive | boolean | yes
InventoryService | updateInventoryItem | param (path) | itemId | string (uuid) | yes
InventoryService | updateInventoryItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateLoyaltyProgramme | request | name | string |  | (max length 200)
MarketingService | updateLoyaltyProgramme | request | earnRules | array of object |  | Replaces the programme's earning rules; each item as LoyaltyProgramme.earnRules[].
MarketingService | updateLoyaltyProgramme | request | earnRules[].trigger | string | yes
MarketingService | updateLoyaltyProgramme | request | earnRules[].points | number | yes
MarketingService | updateLoyaltyProgramme | request | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …)
MarketingService | updateLoyaltyProgramme | request | earnRules[].multiplier | number
MarketingService | updateLoyaltyProgramme | request | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | updateLoyaltyProgramme | request | isActive | boolean
MarketingService | updateLoyaltyProgramme | response | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | updateLoyaltyProgramme | response | tiers[].id | string (uuid) |  | (read-only)
MarketingService | updateLoyaltyProgramme | response | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | updateLoyaltyProgramme | response | tiers[].code | string | yes | (max length 40)
MarketingService | updateLoyaltyProgramme | response | tiers[].name | string | yes | (max length 120)
MarketingService | updateLoyaltyProgramme | response | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | updateLoyaltyProgramme | response | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | updateLoyaltyProgramme | response | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | updateLoyaltyProgramme | response | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | updateLoyaltyProgramme | response | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | updateLoyaltyProgramme | response | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | updateLoyaltyProgramme | response | tiers[].isActive | boolean |  | (default True)
MarketingService | updateLoyaltyProgramme | response | id | string (uuid) | yes | (read-only)
MarketingService | updateLoyaltyProgramme | response | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | updateLoyaltyProgramme | response | name | string | yes
MarketingService | updateLoyaltyProgramme | response | venueId | string (uuid) |  | (nullable)
MarketingService | updateLoyaltyProgramme | response | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | updateLoyaltyProgramme | response | earnRules | array of object | yes
MarketingService | updateLoyaltyProgramme | response | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | updateLoyaltyProgramme | response | earnRules[].points | number | yes
MarketingService | updateLoyaltyProgramme | response | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | updateLoyaltyProgramme | response | earnRules[].multiplier | number
MarketingService | updateLoyaltyProgramme | response | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | updateLoyaltyProgramme | response | isActive | boolean
MarketingService | updateLoyaltyProgramme | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateLoyaltyProgramme | param (path) | programmeId | string (uuid) | yes
VenueOpsService | updateMediaAsset | request | title | LocalisedText
VenueOpsService | updateMediaAsset | request | description | LocalisedText
VenueOpsService | updateMediaAsset | request | altText | object |  | Accessibility text.
VenueOpsService | updateMediaAsset | request | tags | array of string
VenueOpsService | updateMediaAsset | request | collectionIds | array of string (uuid) |  | Replaces the asset's collection memberships.
VenueOpsService | updateMediaAsset | request | rights | MediaRights |  | Licensing terms.
VenueOpsService | updateMediaAsset | request | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | updateMediaAsset | request | rights.licensor | string |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.licenceReference | string |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.validTo | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | updateMediaAsset | request | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | updateMediaAsset | request | rights.attributionText | string |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | updateMediaAsset | request | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | updateMediaAsset | request | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | updateMediaAsset | request | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | updateMediaAsset | request | status | enum (ready, archived) |  | A lifecycle move from states/media.yaml.
VenueOpsService | updateMediaAsset | response | id | string (uuid) | yes
VenueOpsService | updateMediaAsset | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | updateMediaAsset | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | updateMediaAsset | response | filename | string | yes
VenueOpsService | updateMediaAsset | response | contentType | string | yes
VenueOpsService | updateMediaAsset | response | sizeBytes | integer | yes
VenueOpsService | updateMediaAsset | response | title | LocalisedText
VenueOpsService | updateMediaAsset | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | updateMediaAsset | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | updateMediaAsset | response | width | integer |  | (nullable)
VenueOpsService | updateMediaAsset | response | height | integer |  | (nullable)
VenueOpsService | updateMediaAsset | response | hasTransparency | boolean |  | Whether the image has an alpha channel with any pixel not fully opaque, recorded from the file when the upload completes; null for a file that is not an image (ADAM CR-106, option 1; CHG-R10TEN-012). (read-only; nullable)
VenueOpsService | updateMediaAsset | response | durationSeconds | number |  | (nullable)
VenueOpsService | updateMediaAsset | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | updateMediaAsset | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | updateMediaAsset | response | tags | array of string
VenueOpsService | updateMediaAsset | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | updateMediaAsset | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | updateMediaAsset | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | updateMediaAsset | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | updateMediaAsset | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | updateMediaAsset | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | updateMediaAsset | response | rights.licensor | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | updateMediaAsset | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | updateMediaAsset | response | rights.attributionText | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | updateMediaAsset | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | updateMediaAsset | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | updateMediaAsset | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | updateMediaAsset | response | isRightsExpired | boolean
VenueOpsService | updateMediaAsset | response | version | integer
VenueOpsService | updateMediaAsset | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | updateMediaAsset | response | createdAt | string (date-time) | yes
VenueOpsService | updateMediaAsset | response | extractedText | string |  | The text pulled out of an uploaded document (R8 blocker ORDERS-MONEY-C19): written by the upload's processing job once text extraction finishes (PDF, Word and plain-text kinds), replaced when the fil… (read-only; nullable)
VenueOpsService | updateMediaAsset | response | releasedByPrincipalId | string (uuid) |  | The reviewer who released the asset from quarantined (R8 blocker ORDERS-MONEY-C24, CHG-R8MIG-022); null if it never was. (read-only; nullable)
VenueOpsService | updateMediaAsset | response | releasedAt | string (date-time) |  | When it was released from quarantined. (read-only; nullable)
VenueOpsService | updateMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | updateMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | updateMenu | request | name | string |  | (max length 200)
FnbService | updateMenu | request | availability | MenuAvailability |  | When this menu is in force.
FnbService | updateMenu | request | availability.daysOfWeek | array of integer
FnbService | updateMenu | request | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | request | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | request | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | request | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | request | isActive | boolean
FnbService | updateMenu | response | id | string (uuid) | yes
FnbService | updateMenu | response | code | string | yes | (max length 64)
FnbService | updateMenu | response | name | string | yes | (max length 200)
FnbService | updateMenu | response | outletId | string (uuid) | yes
FnbService | updateMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | updateMenu | response | availability.daysOfWeek | array of integer
FnbService | updateMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | response | sections | array of MenuSection
FnbService | updateMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | updateMenu | response | sections[].code | string | yes
FnbService | updateMenu | response | sections[].name | string | yes
FnbService | updateMenu | response | sections[].sortOrder | integer | yes
FnbService | updateMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | updateMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | updateMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | updateMenu | response | sections[].items[].name | string | yes
FnbService | updateMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | updateMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateMenu | response | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | updateMenu | response | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | updateMenu | response | sections[].items[].sortOrder | integer
FnbService | updateMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | updateMenu | response | sections[].items[].stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | updateMenu | response | sections[].items[].menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | updateMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | updateMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | updateMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | updateMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | updateMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | updateMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | updateMenu | response | sections[].items[].unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | updateMenu | response | isActive | boolean | yes
FnbService | updateMenu | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | updateMenu | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | updateMenu | param (path) | menuId | string (uuid) | yes
FnbService | updateMenu | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | updateMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | updateMerchandise | request | name | string |  | (max length 200)
RetailService | updateMerchandise | request | description | string |  | What the item is, in the guest's words. (nullable)
RetailService | updateMerchandise | request | barcode | string |  | Must stay unique in the venue. (max length 128; nullable)
RetailService | updateMerchandise | request | categoryId | string (uuid)
RetailService | updateMerchandise | request | inventoryItemId | string (uuid) |  | Re-points the stock item a sale depletes. (nullable)
RetailService | updateMerchandise | request | imageAssetRef | string |  | (nullable)
RetailService | updateMerchandise | request | isReturnable | boolean
RetailService | updateMerchandise | request | isDroppable | boolean |  | Whether the item may go to shop-and-drop (R8 blocker APPROVALS-TENANCY-C34).
RetailService | updateMerchandise | request | returnWindowDays | integer |  | (min 0)
RetailService | updateMerchandise | request | requiresSerialNumber | boolean
RetailService | updateMerchandise | request | isActive | boolean
RetailService | updateMerchandise | response | description | string |  | What the item is, in the guest's words.
RetailService | updateMerchandise | response | id | string (uuid) | yes
RetailService | updateMerchandise | response | sku | string | yes | Unique per outlet (ADAM CR-104, CHG-R10ORD-017); lookupMerchandise matches it exactly.
RetailService | updateMerchandise | response | barcode | string |  | Unique per outlet where set (ADAM CR-104; was unique per venue, which the table has no venue column to key); lookupMerchandise matches it exactly and returns one row. (nullable)
RetailService | updateMerchandise | response | name | string | yes
RetailService | updateMerchandise | response | outletId | string (uuid) | yes
RetailService | updateMerchandise | response | categoryId | string (uuid) |  | (nullable)
RetailService | updateMerchandise | response | variantId | string (uuid) | yes | The catalogue variant sold.
RetailService | updateMerchandise | response | inventoryItemId | string (uuid) |  | The stock item depleted on sale. (nullable)
RetailService | updateMerchandise | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | updateMerchandise | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | updateMerchandise | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | updateMerchandise | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | updateMerchandise | response | onHand | number | yes
RetailService | updateMerchandise | response | isReturnable | boolean |  | (default True)
RetailService | updateMerchandise | response | returnWindowDays | integer |  | (nullable)
RetailService | updateMerchandise | response | requiresSerialNumber | boolean |  | (default False)
RetailService | updateMerchandise | response | imageAssetRef | string |  | (nullable)
RetailService | updateMerchandise | response | isActive | boolean | yes
RetailService | updateMerchandise | response | isPublished | boolean |  | Whether a guest or a visitor may see the item (the lead's answer of 25 October 2026 to the r10 lanes' questions, question 22; CHG-R10ORD-025): the flag listMerchandise and lookupMerchandise already n… (default False)
RetailService | updateMerchandise | response | isDroppable | boolean |  | Whether the item may be dropped for later collection (R8 blocker APPROVALS-TENANCY-C34). (default True)
RetailService | updateMerchandise | param (path) | merchandiseId | string (uuid) | yes
RetailService | updateMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateMessageTemplate | request | name | string |  | (max length 200)
MarketingService | updateMessageTemplate | request | subjects | object |  | Per language, as MessageTemplate.subjects.
MarketingService | updateMessageTemplate | request | bodies | object |  | Per language, as MessageTemplate.bodies.
MarketingService | updateMessageTemplate | request | mergeFields | array of string
MarketingService | updateMessageTemplate | request | providerTemplateId | string |  | (nullable)
MarketingService | updateMessageTemplate | response | id | string (uuid) | yes | (read-only)
MarketingService | updateMessageTemplate | response | code | string | yes | (max length 64)
MarketingService | updateMessageTemplate | response | name | string | yes | (max length 200)
MarketingService | updateMessageTemplate | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | updateMessageTemplate | response | subjects | object |  | Per language.
MarketingService | updateMessageTemplate | response | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | updateMessageTemplate | response | mergeFields | array of string
MarketingService | updateMessageTemplate | response | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | updateMessageTemplate | response | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | updateMessageTemplate | response | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | updateMessageTemplate | response | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | updateMessageTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateMessageTemplate | param (path) | templateId | string (uuid) | yes
MarketingService | updateMyProfile | request | displayName | string
MarketingService | updateMyProfile | request | email | string (email)
MarketingService | updateMyProfile | request | phone | string
MarketingService | updateMyProfile | request | preferredLanguage | string
MarketingService | updateMyProfile | request | preferredChannel | enum (email, sms, whatsapp, push, none) |  | none is stored as null on marketing.guest_profile.preferred_channel, and the answer then leaves preferredChannel out (ADAM CR-291, option B; CHG-R11GST-002).
MarketingService | updateMyProfile | request | dietary | array of string |  | Health-adjacent personal data, kept structured rather than as a tag (BL-134).
MarketingService | updateMyProfile | request | accessibility | array of string |  | Same treatment, same reason.
MarketingService | updateMyProfile | response | id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | updateMyProfile | response | subjectId | string (uuid) | yes | Opaque reference.
MarketingService | updateMyProfile | response | displayName | string |  | (nullable)
MarketingService | updateMyProfile | response | email | string |  | (nullable)
MarketingService | updateMyProfile | response | phone | string |  | (nullable)
MarketingService | updateMyProfile | response | preferredLanguage | string |  | (nullable)
MarketingService | updateMyProfile | response | preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) |  | Left out where the guest has no preferred channel: a guest who chose none in updateMyProfile is stored as null and answered without this field (ADAM CR-291, option B; CHG-R11GST-002).
MarketingService | updateMyProfile | response | guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | updateMyProfile | response | tags | array of string
MarketingService | updateMyProfile | response | engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | updateMyProfile | response | engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | updateMyProfile | response | lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | updateMyProfile | response | lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | updateMyProfile | response | lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | updateMyProfile | response | lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | updateMyProfile | response | visitCount | integer
MarketingService | updateMyProfile | response | lastVisitAt | string (date-time) |  | (nullable)
MarketingService | updateMyProfile | response | isActive | boolean | yes
MarketingService | updateMyProfile | response | mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | updateMyProfile | response | mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | updateMyProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateOrgUnit | request | name | string |  | (max length 200)
TenancyService | updateOrgUnit | request | isActive | boolean
TenancyService | updateOrgUnit | response | id | string (uuid) | yes
TenancyService | updateOrgUnit | response | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | updateOrgUnit | response | parentId | string (uuid) |  | (nullable)
TenancyService | updateOrgUnit | response | path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | updateOrgUnit | response | code | string | yes | (max length 64)
TenancyService | updateOrgUnit | response | name | string | yes | (max length 200)
TenancyService | updateOrgUnit | response | isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | updateOrgUnit | response | childCount | integer |  | (min 0)
TenancyService | updateOrgUnit | param (path) | orgUnitId | string (uuid) | yes
TenancyService | updateOrgUnit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateOutlet | request | name | string |  | (max length 200)
TenancyService | updateOutlet | request | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | updateOutlet | request | stockLocationId | string (uuid)
TenancyService | updateOutlet | request | costCenterId | string (uuid)
TenancyService | updateOutlet | request | departmentId | string (uuid) |  | (nullable)
TenancyService | updateOutlet | request | outletType | OutletType: enum (fineDining, casualDining, quickService, coffeeShop, barLounge, foodCourt, buffet, commissary, …) |  | How an F&B or retail outlet trades, which switches features on or off (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-729: "Add both fields: outlet type and department (DI-319)"; DEC-196; CHG-CS…
TenancyService | updateOutlet | request | paymentTiming | OutletPaymentTiming: enum (sendFirst, payFirst) |  | When an F&B order is paid, per outlet (decided 2 October 2026, Chinmay, batch 1, POS-021: "Two configurations: one takes the bill (payment) first, the other sends first and charges after"; DEC-064; C…
TenancyService | updateOutlet | request | orderNumberPrefix | enum (A, B, C, D, E, F, G, H, …) |  | The outlet's one-letter order-number prefix (Outlet.orderNumberPrefix; ADAM CR-293); null clears it. (max length 1; nullable)
TenancyService | updateOutlet | request | admissionContext | OutletAdmissionContext: enum (insideVenue, standalone) |  | Whether an outlet sits behind the admission gate (decided 2 October 2026, Chinmay, batch 1, WEB-036: "Inside the venue, a ticket is needed.
TenancyService | updateOutlet | request | producesForOutletIds | array of string (uuid) |  | Replaces the whole list of outlets this one produces for (CHG-CSP-005).
TenancyService | updateOutlet | request | saleBoardId | string (uuid) |  | (nullable)
TenancyService | updateOutlet | request | openingHours | array of OpeningHoursWindow |  | Replaces the whole weekly pattern.
TenancyService | updateOutlet | request | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | updateOutlet | request | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | request | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | request | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | updateOutlet | request | isActive | boolean
TenancyService | updateOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | updateOutlet | response | code | string | yes | Unique within the venue (409 duplicate-code; ADAM CR-074, CHG-DDL-008): the database holds it with a unique index on (venue_id, code), so two concurrent creates cannot both keep one code. (max length 64)
TenancyService | updateOutlet | response | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | updateOutlet | response | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | updateOutlet | response | venueId | string (uuid) | yes
TenancyService | updateOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | updateOutlet | response | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | updateOutlet | response | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | updateOutlet | response | zone | string |  | (nullable)
TenancyService | updateOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | updateOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | updateOutlet | response | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | updateOutlet | response | orderNumberPrefix | enum (A, B, C, D, E, F, G, H, …) |  | The one letter this outlet's F&B order numbers start with (ADAM CR-293 (2), option A, 29 October 2026; CHG-R11TEN-003): one capital letter A to Z, or null for none. (max length 1; nullable)
TenancyService | updateOutlet | response | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | updateOutlet | response | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | updateOutlet | response | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | updateOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | updateOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | updateOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | response | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | updateOutlet | response | isActive | boolean
TenancyService | updateOutlet | param (path) | outletId | string (uuid) | yes
TenancyService | updateOutlet | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | updateParkingEntitlement | request | plateNumber | string |  | Personal data, under the same rules as ParkingEntitlement.plateNumber.
AccessService | updateParkingEntitlement | request | plateCountry | string |  | (nullable)
AccessService | updateParkingEntitlement | request | status | enum (revoked) |  | The only status a caller may set.
AccessService | updateParkingEntitlement | response | id | string (uuid) |  | (read-only)
AccessService | updateParkingEntitlement | response | facilityId | string (uuid) | yes
AccessService | updateParkingEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | updateParkingEntitlement | response | subjectId | string (uuid) |  | (nullable)
AccessService | updateParkingEntitlement | response | plateNumber | string |  | Required in plateWhitelist mode, meaningless in the others. (nullable)
AccessService | updateParkingEntitlement | response | plateCountry | string |  | (nullable)
AccessService | updateParkingEntitlement | response | mediaCode | string |  | The code presented in none and qrHandoff modes. (nullable)
AccessService | updateParkingEntitlement | response | status | object |  | Server-owned. (read-only)
AccessService | updateParkingEntitlement | response | pushedAt | string (date-time) |  | (read-only; nullable)
AccessService | updateParkingEntitlement | response | pushFailureReason | string |  | (read-only; nullable)
AccessService | updateParkingEntitlement | response | validFrom | string (date-time) | yes
AccessService | updateParkingEntitlement | response | validTo | string (date-time) | yes
AccessService | updateParkingEntitlement | param (path) | entitlementId | string (uuid) | yes
AccessService | updateParkingEntitlement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updatePerformance | request | startsAt | string (date-time)
CatalogueService | updatePerformance | request | endsAt | string (date-time)
CatalogueService | updatePerformance | request | status | enum (scheduled, onSale, suspended)
CatalogueService | updatePerformance | request | admissionRulesId | string (uuid)
CatalogueService | updatePerformance | request | language | string |  | As Performance.language (decided 29 September, rev 3 REV3-17). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | updatePerformance | request | format | string |  | As Performance.format (decided 29 September, rev 3 REV3-17). (max length 40; nullable)
CatalogueService | updatePerformance | request | minutesOnScreen | integer |  | As Performance.minutesOnScreen (DI-167, DI-169; CHG-R4-014). (min 0; max 1440)
CatalogueService | updatePerformance | response | id | string (uuid) | yes
CatalogueService | updatePerformance | response | eventId | string (uuid) | yes
CatalogueService | updatePerformance | response | startsAt | string (date-time) | yes
CatalogueService | updatePerformance | response | endsAt | string (date-time) | yes
CatalogueService | updatePerformance | response | approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | updatePerformance | response | requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | updatePerformance | response | status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | updatePerformance | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | updatePerformance | response | seatMapId | string (uuid) |  | (nullable)
CatalogueService | updatePerformance | response | language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | updatePerformance | response | format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | updatePerformance | response | minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | updatePerformance | param (path) | performanceId | string (uuid) | yes
CatalogueService | updatePerformance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updatePriceList | request | name | string |  | (max length 200)
CatalogueService | updatePriceList | request | validFrom | string (date-time)
CatalogueService | updatePriceList | request | validTo | string (date-time)
CatalogueService | updatePriceList | request | priority | integer
CatalogueService | updatePriceList | request | isActive | boolean
CatalogueService | updatePriceList | request | description | string |  | The price list master fields (data model DM3) are written here since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001); each is optional and means what it means on PriceList. (nullable)
CatalogueService | updatePriceList | request | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …)
CatalogueService | updatePriceList | request | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | request | tags | array of string
CatalogueService | updatePriceList | request | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | request | brand | string |  | (max length 100; nullable)
CatalogueService | updatePriceList | request | businessUnit | string |  | (max length 100; nullable)
CatalogueService | updatePriceList | request | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | updatePriceList | request | marketCode | string |  | (max length 40; nullable)
CatalogueService | updatePriceList | request | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit)
CatalogueService | updatePriceList | request | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | request | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | request | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | request | allowOverrides | boolean
CatalogueService | updatePriceList | request | allowInheritance | boolean
CatalogueService | updatePriceList | request | allowMultipleCurrencies | boolean
CatalogueService | updatePriceList | request | allowProductSpecificRates | boolean
CatalogueService | updatePriceList | response | id | string (uuid) | yes
CatalogueService | updatePriceList | response | code | string | yes
CatalogueService | updatePriceList | response | name | string | yes
CatalogueService | updatePriceList | response | venueId | string (uuid) | yes
CatalogueService | updatePriceList | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | updatePriceList | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | updatePriceList | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | updatePriceList | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | updatePriceList | response | validTo | string (date-time) |  | (nullable)
CatalogueService | updatePriceList | response | priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | updatePriceList | response | description | string |  | Price list master fields (29 September, data model DM3), set with createPriceList and updatePriceList since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001). (nullable)
CatalogueService | updatePriceList | response | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | updatePriceList | response | status | object |  | (default active)
CatalogueService | updatePriceList | response | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | tags | array of string
CatalogueService | updatePriceList | response | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | brand | string |  | (max length 100; nullable)
CatalogueService | updatePriceList | response | businessUnit | string |  | (max length 100; nullable)
CatalogueService | updatePriceList | response | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | updatePriceList | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | updatePriceList | response | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | updatePriceList | response | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | allowOverrides | boolean |  | (default False)
CatalogueService | updatePriceList | response | allowInheritance | boolean |  | (default True)
CatalogueService | updatePriceList | response | allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | updatePriceList | response | allowProductSpecificRates | boolean |  | (default True)
CatalogueService | updatePriceList | response | clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | updatePriceList | param (path) | priceListId | string (uuid) | yes
CatalogueService | updatePriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | updatePrincipal | request | displayName | string |  | (max length 200)
IdentityService | updatePrincipal | request | isActive | boolean
IdentityService | updatePrincipal | request | validTo | string (date-time) |  | (nullable)
IdentityService | updatePrincipal | request | primaryRoleId | string (uuid)
IdentityService | updatePrincipal | response | id | string (uuid) | yes
IdentityService | updatePrincipal | response | username | string | yes
IdentityService | updatePrincipal | response | displayName | string | yes
IdentityService | updatePrincipal | response | isActive | boolean | yes
IdentityService | updatePrincipal | response | validFrom | string (date-time) |  | (nullable)
IdentityService | updatePrincipal | response | validTo | string (date-time) |  | Past this, resolution returns DENY regardless of grants. (nullable)
IdentityService | updatePrincipal | response | primaryRoleId | string (uuid) |  | Determines the landing screen when the principal holds several roles and picks one at login. (nullable)
IdentityService | updatePrincipal | response | roles | array of RoleSummary |  | Read with the principal, never stored on it (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): one item per role the principal holds through a live grant, an identity.delegated_access row with this…
IdentityService | updatePrincipal | response | roles[].id | string (uuid) | yes
IdentityService | updatePrincipal | response | roles[].code | string | yes
IdentityService | updatePrincipal | response | roles[].name | string | yes
IdentityService | updatePrincipal | response | roles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | updatePrincipal | response | roles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | updatePrincipal | response | roles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | updatePrincipal | response | roles[].scope.id | string (uuid) | yes
IdentityService | updatePrincipal | response | roles[].scope.level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | updatePrincipal | response | roles[].scope.path | string | yes | Materialised ltree path.
IdentityService | updatePrincipal | response | roles[].scope.code | string |  | (nullable)
IdentityService | updatePrincipal | response | roles[].scope.name | string |  | (nullable)
IdentityService | updatePrincipal | response | lastLoginAt | string (date-time) |  | (nullable)
IdentityService | updatePrincipal | response | mustChangeCredential | boolean |  | The principal must replace their credential before the session is usable (14 October 2026, CHG-CRD-001, ADAM CR-078; createPrincipal took it and nothing stored it). (default True)
IdentityService | updatePrincipal | response | ssoProviderId | string (uuid) |  | Set when single sign-on provisioned this principal (completeSsoAuthorization, from the tenant's identity.sso_provider; 14 October 2026, CHG-CRD-001). (read-only; nullable)
IdentityService | updatePrincipal | param (path) | principalId | string (uuid) | yes
IdentityService | updatePrincipal | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateProduct | request | familyKey | string |  | The product family across the tenant's venues (decided 29 September, rev 3 REV3-18); see Product.familyKey. (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | updateProduct | request | name | string |  | (max length 200)
CatalogueService | updateProduct | request | description | string
CatalogueService | updateProduct | request | nameLocalised | object |  | See Product.nameLocalised (CHG-R4-011). (nullable)
CatalogueService | updateProduct | request | descriptionLocalised | object |  | See Product.descriptionLocalised (CHG-R4-011). (nullable)
CatalogueService | updateProduct | request | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | updateProduct | request | dataMaskValues | object
CatalogueService | updateProduct | request | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | updateProduct | request | notBookableLabel | object |  | (nullable)
CatalogueService | updateProduct | request | salesContact | object |  | See Product.salesContact (W3, 29 September). (nullable)
CatalogueService | updateProduct | request | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | updateProduct | request | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | updateProduct | request | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | updateProduct | request | bookingFlowId | string (uuid) |  | See Product.bookingFlowId (W8, W12, 29 September). (nullable)
CatalogueService | updateProduct | request | displayTags | array of ProductDisplayTag |  | (max items 6)
CatalogueService | updateProduct | request | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | updateProduct | request | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | updateProduct | request | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | updateProduct | request | media | array of ProductMedia |  | (max items 20)
CatalogueService | updateProduct | request | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | updateProduct | request | media[].kind | enum (image, video) | yes
CatalogueService | updateProduct | request | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | updateProduct | request | media[].displayOrder | integer |  | (default 100)
CatalogueService | updateProduct | request | media[].url | string (uri) |  | The asset's stable CDN address, for a guest card (ADAM CR-221, option A, decided 25 October 2026; CHG-R10CAT-014): the asset library's public address for the asset, set on guest-facing reads (searchC… (read-only; nullable)
CatalogueService | updateProduct | request | media[].thumbnailUrl | string (uri) |  | The asset library's thumbnail address for the asset, on the same reads and with the same rule as url (ADAM CR-221). (read-only; nullable)
CatalogueService | updateProduct | request | media[].altText | object |  | (nullable)
CatalogueService | updateProduct | request | consentQuestionIds | array of string (uuid) |  | (max items 10)
CatalogueService | updateProduct | request | addOnProductIds | array of string (uuid) |  | The kind addOn products of the same venue offered with this product, in display order (Product.addOnProductIds; ADAM CR-252).
CatalogueService | updateProduct | request | requiresTimeWindow | boolean
CatalogueService | updateProduct | response | id | string (uuid) | yes
CatalogueService | updateProduct | response | code | string | yes | (max length 64)
CatalogueService | updateProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | updateProduct | response | name | string | yes | (max length 200)
CatalogueService | updateProduct | response | description | string
CatalogueService | updateProduct | response | nameLocalised | object |  | The product's name in each of the tenant's enabled languages (6 October 2026, CHG-R4-011; the tenant's languages, not the venue's: CHG-R8PRD-009, ADAM CR-213), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | updateProduct | response | descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | updateProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | updateProduct | response | venueId | string (uuid) | yes
CatalogueService | updateProduct | response | scopePath | string | yes
CatalogueService | updateProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | updateProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | updateProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | updateProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | updateProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | updateProduct | response | validTo | string (date-time) |  | The last moment the product's entitlements are valid; null means the same as onSaleTo (ADAM CR-167 as the lead ruled it, 26 October 2026; CHG-R10OPN-003). (nullable)
CatalogueService | updateProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | updateProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | updateProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | updateProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | updateProduct | response | hasVariants | boolean | yes
CatalogueService | updateProduct | response | variantCount | integer
CatalogueService | updateProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | updateProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | updateProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | updateProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | updateProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | updateProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | updateProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | updateProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | updateProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | updateProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | updateProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | updateProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | updateProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | updateProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | updateProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | updateProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | updateProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | updateProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | updateProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | updateProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | updateProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | updateProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | updateProduct | response | media[].url | string (uri) |  | The asset's stable CDN address, for a guest card (ADAM CR-221, option A, decided 25 October 2026; CHG-R10CAT-014): the asset library's public address for the asset, set on guest-facing reads (searchC… (read-only; nullable)
CatalogueService | updateProduct | response | media[].thumbnailUrl | string (uri) |  | The asset library's thumbnail address for the asset, on the same reads and with the same rule as url (ADAM CR-221). (read-only; nullable)
CatalogueService | updateProduct | response | media[].altText | object |  | (nullable)
CatalogueService | updateProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | updateProduct | response | addOnProductIds | array of string (uuid) |  | The add-ons offered with this product, in display order (accepted 26 October 2026, Chinmay, ADAM CR-252 option A): each a kind: addOn product of the same venue (a coffee break, a working lunch, an AV…
CatalogueService | updateProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | updateProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | updateProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | updateProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | updateProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | updateProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | updateProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | updateProduct | response | eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | updateProduct | response | createdAt | string (date-time) | yes | When the product was created (ADAM CR-204, option A, decided 25 October 2026; CHG-R10CAT-007): catalogue.product.created_at, NOT NULL DEFAULT now(), set by the server and never by a request. (read-only)
CatalogueService | updateProduct | response | updatedAt | string (date-time) |  | When the product last changed (ADAM CR-204): set by updateProduct and by every product sub-resource PUT and bulk change that versions the product; null until the first change after creation. (read-only; nullable)
CatalogueService | updateProduct | param (path) | productId | string (uuid) | yes
CatalogueService | updateProduct | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateProduct | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | updateProductVariant | request | name | string |  | (max length 150; nullable)
CatalogueService | updateProductVariant | request | description | object |  | (nullable)
CatalogueService | updateProductVariant | request | barcode | string |  | (max length 64; nullable)
CatalogueService | updateProductVariant | request | isDefault | boolean
CatalogueService | updateProductVariant | request | referencePrice | Money |  | The price the variant's saving is measured against (ProductVariant.referencePrice; ADAM CR-253); null clears it. (nullable)
CatalogueService | updateProductVariant | response | id | string (uuid) | yes
CatalogueService | updateProductVariant | response | listPrice | Money |  | The list price on the caller's channel now, resolved on read from the price lists (listProductVariants; R8 blocker cause GPS-C27, CHG-R8SPN-028). (read-only; nullable)
CatalogueService | updateProductVariant | response | referencePrice | Money |  | The price a saving is measured against (accepted 26 October 2026, Chinmay, ADAM CR-253 option C), set by the back office on the variant (updateProductVariant). (nullable)
CatalogueService | updateProductVariant | response | savingPercent | integer |  | Computed by the server, never in the browser (ADAM CR-253): with a referencePrice and a listPrice below it, the whole percent the list price saves, floor((referencePrice - listPrice) / referencePrice… (read-only; nullable)
CatalogueService | updateProductVariant | response | productId | string (uuid) | yes
CatalogueService | updateProductVariant | response | sku | string | yes
CatalogueService | updateProductVariant | response | axisValues | object | yes
CatalogueService | updateProductVariant | response | name | string |  | Taken from their variant tables, 20 September. (max length 150; nullable)
CatalogueService | updateProductVariant | response | barcode | string |  | Taken from their variant tables, 20 September. (max length 64; nullable)
CatalogueService | updateProductVariant | response | isDefault | boolean |  | Taken from their variant tables. (default False)
CatalogueService | updateProductVariant | response | isActive | boolean | yes | False when retired.
CatalogueService | updateProductVariant | response | description | object |  | Who this ticket type is for and what it includes, shown behind the (i) on each Adult, Child, Senior or Infant row (decided 29 September, 23SEP-6). (nullable)
CatalogueService | updateProductVariant | param (path) | productId | string (uuid) | yes
CatalogueService | updateProductVariant | param (path) | variantId | string (uuid) | yes
CatalogueService | updateProductVariant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updatePromoBlock | request | title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | request | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | request | iconAssetRef | string (uuid)
WhiteLabelService | updatePromoBlock | request | promotionId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget | LinkTarget
WhiteLabelService | updatePromoBlock | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updatePromoBlock | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updatePromoBlock | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updatePromoBlock | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget.productId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget.eventId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | updatePromoBlock | request | linkTarget.url | string
WhiteLabelService | updatePromoBlock | request | startsAt | string (date-time)
WhiteLabelService | updatePromoBlock | request | endsAt | string (date-time)
WhiteLabelService | updatePromoBlock | request | sortOrder | integer
WhiteLabelService | updatePromoBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updatePromoBlock | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | response | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | updatePromoBlock | response | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | updatePromoBlock | response | linkTarget | LinkTarget
WhiteLabelService | updatePromoBlock | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updatePromoBlock | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updatePromoBlock | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updatePromoBlock | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updatePromoBlock | response | linkTarget.productId | string (uuid)
WhiteLabelService | updatePromoBlock | response | linkTarget.eventId | string (uuid)
WhiteLabelService | updatePromoBlock | response | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | updatePromoBlock | response | linkTarget.url | string
WhiteLabelService | updatePromoBlock | response | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | updatePromoBlock | response | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | updatePromoBlock | response | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | updatePromoBlock | response | sortOrder | integer
WhiteLabelService | updatePromoBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updatePromoBlock | param (path) | promoBlockId | string (uuid) | yes
WhiteLabelService | updatePromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updatePromotion | request | name | string |  | (max length 200)
CatalogueService | updatePromotion | request | nameLocalised | object |  | As Promotion.nameLocalised (ADAM CR-231). (nullable)
CatalogueService | updatePromotion | request | descriptionLocalised | object |  | As Promotion.descriptionLocalised (ADAM CR-231). (nullable)
CatalogueService | updatePromotion | request | label | object |  | As Promotion.label (ADAM CR-225). (nullable)
CatalogueService | updatePromotion | request | venues | array of PromotionVenue |  | As Promotion.venues; the whole list, an empty list meaning every venue (ADAM CR-225).
CatalogueService | updatePromotion | request | venues[].venueId | string (uuid) | yes | A venue node of the tenant (checked with tenancy#scopeRecords on write).
CatalogueService | updatePromotion | request | venues[].name | string | yes | The venue's name as the back office gives it for guests. (max length 200)
CatalogueService | updatePromotion | request | venues[].nameLocalised | object |  | The name in each enabled language; falls back to name (ADAM CR-231). (nullable)
CatalogueService | updatePromotion | request | validTo | string (date-time)
CatalogueService | updatePromotion | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | updatePromotion | request | conditions.variantIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.productKinds | array of string
CatalogueService | updatePromotion | request | conditions.categoryIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | updatePromotion | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | updatePromotion | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | updatePromotion | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | updatePromotion | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | updatePromotion | request | conditions.daysOfWeek | array of integer
CatalogueService | updatePromotion | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | updatePromotion | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | updatePromotion | request | conditions.performanceIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | updatePromotion | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | updatePromotion | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | updatePromotion | request | discount | Discount
CatalogueService | updatePromotion | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | updatePromotion | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | updatePromotion | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | updatePromotion | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | updatePromotion | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | updatePromotion | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | updatePromotion | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | updatePromotion | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | updatePromotion | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | updatePromotion | response | code | string | yes | Unique per tenant (6 October 2026, CHG-R4-015; the rule of audit R108 for configuration codes). (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | updatePromotion | response | name | string | yes | (max length 200)
CatalogueService | updatePromotion | response | nameLocalised | object |  | The promotion's name in each of the tenant's enabled languages (ADAM CR-231, option A, decided 25 October 2026; CHG-R10CAT-012), keyed by ISO 639-1 code, as Product.nameLocalised. (nullable)
CatalogueService | updatePromotion | response | description | string |  | (max length 1000)
CatalogueService | updatePromotion | response | descriptionLocalised | object |  | The description in each enabled language, as nameLocalised; falls back to description. (nullable)
CatalogueService | updatePromotion | response | label | object |  | The guest-facing label, the pill on the offer card (BUNDLE, RENTAL, MEMBERSHIP, SEASON, PARKING on WEB-032), per language as nameLocalised (ADAM CR-225 and CR-231, option A, decided 25 October 2026;… (nullable)
CatalogueService | updatePromotion | response | venues | array of PromotionVenue |  | Where a guest may use the offer, as the offer card's venue line shows it (ADAM CR-225, option A, decided 25 October 2026; CHG-R10CAT-012).
CatalogueService | updatePromotion | response | venues[].venueId | string (uuid) | yes | A venue node of the tenant (checked with tenancy#scopeRecords on write).
CatalogueService | updatePromotion | response | venues[].name | string | yes | The venue's name as the back office gives it for guests. (max length 200)
CatalogueService | updatePromotion | response | venues[].nameLocalised | object |  | The name in each enabled language; falls back to name (ADAM CR-231). (nullable)
CatalogueService | updatePromotion | response | venueId | string (uuid) | yes
CatalogueService | updatePromotion | response | discount | Discount | yes
CatalogueService | updatePromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | updatePromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | updatePromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | updatePromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | updatePromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | updatePromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | updatePromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | updatePromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | updatePromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | updatePromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | updatePromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.productKinds | array of string
CatalogueService | updatePromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | updatePromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | updatePromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | updatePromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | updatePromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | updatePromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | updatePromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | updatePromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | updatePromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | updatePromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | updatePromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | updatePromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | updatePromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | updatePromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | updatePromotion | response | validFrom | string (date-time) | yes
CatalogueService | updatePromotion | response | validTo | string (date-time)
CatalogueService | updatePromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | updatePromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | updatePromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | updatePromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | updatePromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | updatePromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | updatePromotion | response | id | string (uuid) | yes
CatalogueService | updatePromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | updatePromotion | response | isPaused | boolean
CatalogueService | updatePromotion | response | redemptionCount | integer
CatalogueService | updatePromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | updatePromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | updatePromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | updatePromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateQueue | request | name | LocalisedText |  | The same locale-to-text map createQueue takes and Queue returns, so an edit form round-trips the name.
VenueOpsService | updateQueue | request | capacityPerCycle | integer |  | (min 1)
VenueOpsService | updateQueue | request | cycleMinutes | number |  | (min 0)
VenueOpsService | updateQueue | request | maxPartySize | integer |  | (min 1)
VenueOpsService | updateQueue | request | returnWindowMinutes | integer |  | (min 1)
VenueOpsService | updateQueue | request | heightRequirementCm | integer |  | (nullable)
VenueOpsService | updateQueue | request | fastPassAllocationPercent | number |  | (min 0; max 100)
VenueOpsService | updateQueue | request | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | updateQueue | request | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | updateQueue | request | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | request | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | request | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | updateQueue | request | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | updateQueue | request | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | updateQueue | request | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | updateQueue | response | code | string | yes | (max length 64)
VenueOpsService | updateQueue | response | name | LocalisedText | yes
VenueOpsService | updateQueue | response | venueId | string (uuid) | yes
VenueOpsService | updateQueue | response | attractionProductId | string (uuid)
VenueOpsService | updateQueue | response | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | updateQueue | response | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | updateQueue | response | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | updateQueue | response | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | updateQueue | response | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | updateQueue | response | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | updateQueue | response | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | updateQueue | response | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | updateQueue | response | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | updateQueue | response | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | updateQueue | response | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | updateQueue | response | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | updateQueue | response | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | updateQueue | response | cycleMinutes | number | yes | (min 0)
VenueOpsService | updateQueue | response | maxPartySize | integer |  | (default 6)
VenueOpsService | updateQueue | response | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | updateQueue | response | heightRequirementCm | integer |  | (nullable)
VenueOpsService | updateQueue | response | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | updateQueue | response | zone | string |  | (nullable)
VenueOpsService | updateQueue | response | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | updateQueue | response | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | updateQueue | response | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | response | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | response | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | updateQueue | response | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | updateQueue | response | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | updateQueue | response | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | updateQueue | response | id | string (uuid) | yes
VenueOpsService | updateQueue | response | status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | updateQueue | response | statusReason | string |  | (nullable)
VenueOpsService | updateQueue | response | waitingPartyCount | integer | yes
VenueOpsService | updateQueue | response | waitingGuestCount | integer
VenueOpsService | updateQueue | response | currentWaitMinutes | integer |  | (nullable)
VenueOpsService | updateQueue | response | waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | updateQueue | response | waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | updateQueue | response | manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | updateQueue | response | manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | updateQueue | response | expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | updateQueue | param (path) | queueId | string (uuid) | yes
VenueOpsService | updateQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateRegionSettings | request | scopePath | string | yes | The partition key (ADR-0005): the path of the region in regionId, set by the server when updateRegionSettings first saves the row, and ignored on input. (read-only)
TenancyService | updateRegionSettings | request | countryCode | string | yes | ISO 3166-1 alpha-2. (pattern ^[A-Z]{2}$)
TenancyService | updateRegionSettings | request | currencyCode | string | yes | (pattern ^[A-Z]{3}$)
TenancyService | updateRegionSettings | request | currencyScale | integer | yes | Decimal places for this region's currency. (min 0; max 4)
TenancyService | updateRegionSettings | request | timeZone | string | yes | IANA zone, e.g.
TenancyService | updateRegionSettings | request | dateFormat | string |  | (default dd/MM/yyyy)
TenancyService | updateRegionSettings | request | numberFormat | string |  | (default #,##0.00)
TenancyService | updateRegionSettings | request | fiscalYearStartMonth | integer | yes | Varies by country. (min 1; max 12)
TenancyService | updateRegionSettings | request | allowedAiResidencies | array of string |  | The region's compliance gate on AI providers (decided 28 September, audit R203; ADR-0009). (default [])
TenancyService | updateRegionSettings | request | aiResidencyClass | enum (uaeOnly, globalAllowed, onPrem) |  | The tenant's AI residency class (decided 2 October 2026, Chinmay, "AI residency: per-tenant residency class"; DEC-539; CHG-CSP-009; amends AI-D02 and ADR-0009 section 1). (default uaeOnly)
TenancyService | updateRegionSettings | request | aiResidencyClassLocked | boolean |  | Set by TICVAI at onboarding for a government, bank or health tenant (DEC-539), which must stay uaeOnly. (default False; read-only)
TenancyService | updateRegionSettings | request | tenantCategory | enum (private, semiGovernment, government, banking, payments, health, difc, adgm) |  | What kind of organisation the tenant is, for AI residency (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 2, and Chinmay's per-tenant residency… (default private; read-only)
TenancyService | updateRegionSettings | request | aiResidencyOptIn | object |  | The evidence a globalAllowed opt-in needs under PDPL Article 23 (DEC-539; CHG-CSP-009): the tenant's references to its vendor contract, its DPIA and the notice guests see. (nullable)
TenancyService | updateRegionSettings | request | aiResidencyOptIn.vendorContractReference | string |  | (max length 200)
TenancyService | updateRegionSettings | request | aiResidencyOptIn.dpiaReference | string |  | (max length 200)
TenancyService | updateRegionSettings | request | aiResidencyOptIn.guestNoticeReference | string |  | (max length 200)
TenancyService | updateRegionSettings | request | aiResidencyOptIn.confirmedByPrincipalId | string (uuid) |  | (read-only)
TenancyService | updateRegionSettings | request | aiResidencyOptIn.confirmedAt | string (date-time) |  | (read-only)
TenancyService | updateRegionSettings | request | localLanguageNameLocales | array of string |  | The languages an outlet name must also be given in, in this country (decided 2 October 2026, Chinmay, batch 2 #26: "English plus the local language where the country needs it"; DEC-031; CHG-CSP-005). (default [])
TenancyService | updateRegionSettings | request | requiredBillingDocuments | array of object |  | Which documents a TICVAI customer's billing entity must upload, in this country (decided 2 October 2026, Chinmay, batch 6 set 7, ADM-411: "Trade licence always; VAT certificate when a TRN is entered;… (default [{'documentType': 'tradeLicence', 'requiredWhen': 'always'}, {'documentType': 'vatCertificate', 'requiredWhen': 'trnEntered'}])
TenancyService | updateRegionSettings | request | requiredBillingDocuments[].documentType | string |  | The document kind, as the subscription contract's PartnerDocument names it (tradeLicence, vatCertificate, ...). (max length 64)
TenancyService | updateRegionSettings | request | requiredBillingDocuments[].requiredWhen | enum (always, trnEntered)
TenancyService | updateRegionSettings | request | minorAgeThreshold | integer |  | The age below which a guest is a minor here, set per country (decided 2 October 2026, Chinmay, critical set 1, BO-187: "Guardian consent on the venue's form; minor age per country"; DEC-237; CHG-CSP-… (min 0; max 21; default 18)
TenancyService | updateRegionSettings | request | placement | Placement |  | Read-only here. (read-only)
TenancyService | updateRegionSettings | request | placement.mode | enum (shared, dedicated, isolated, clientHosted) | yes
TenancyService | updateRegionSettings | request | placement.cellName | string
TenancyService | updateRegionSettings | request | placement.cloudRegion | string
TenancyService | updateRegionSettings | request | cellName | string |  | The cell serving this region. (read-only)
TenancyService | updateRegionSettings | response | scopePath | string | yes | The partition key (ADR-0005): the path of the region in regionId, set by the server when updateRegionSettings first saves the row, and ignored on input. (read-only)
TenancyService | updateRegionSettings | response | countryCode | string | yes | ISO 3166-1 alpha-2. (pattern ^[A-Z]{2}$)
TenancyService | updateRegionSettings | response | currencyCode | string | yes | (pattern ^[A-Z]{3}$)
TenancyService | updateRegionSettings | response | currencyScale | integer | yes | Decimal places for this region's currency. (min 0; max 4)
TenancyService | updateRegionSettings | response | timeZone | string | yes | IANA zone, e.g.
TenancyService | updateRegionSettings | response | dateFormat | string |  | (default dd/MM/yyyy)
TenancyService | updateRegionSettings | response | numberFormat | string |  | (default #,##0.00)
TenancyService | updateRegionSettings | response | fiscalYearStartMonth | integer | yes | Varies by country. (min 1; max 12)
TenancyService | updateRegionSettings | response | allowedAiResidencies | array of string |  | The region's compliance gate on AI providers (decided 28 September, audit R203; ADR-0009). (default [])
TenancyService | updateRegionSettings | response | aiResidencyClass | enum (uaeOnly, globalAllowed, onPrem) |  | The tenant's AI residency class (decided 2 October 2026, Chinmay, "AI residency: per-tenant residency class"; DEC-539; CHG-CSP-009; amends AI-D02 and ADR-0009 section 1). (default uaeOnly)
TenancyService | updateRegionSettings | response | aiResidencyClassLocked | boolean |  | Set by TICVAI at onboarding for a government, bank or health tenant (DEC-539), which must stay uaeOnly. (default False; read-only)
TenancyService | updateRegionSettings | response | tenantCategory | enum (private, semiGovernment, government, banking, payments, health, difc, adgm) |  | What kind of organisation the tenant is, for AI residency (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 2, and Chinmay's per-tenant residency… (default private; read-only)
TenancyService | updateRegionSettings | response | aiResidencyOptIn | object |  | The evidence a globalAllowed opt-in needs under PDPL Article 23 (DEC-539; CHG-CSP-009): the tenant's references to its vendor contract, its DPIA and the notice guests see. (nullable)
TenancyService | updateRegionSettings | response | aiResidencyOptIn.vendorContractReference | string |  | (max length 200)
TenancyService | updateRegionSettings | response | aiResidencyOptIn.dpiaReference | string |  | (max length 200)
TenancyService | updateRegionSettings | response | aiResidencyOptIn.guestNoticeReference | string |  | (max length 200)
TenancyService | updateRegionSettings | response | aiResidencyOptIn.confirmedByPrincipalId | string (uuid) |  | (read-only)
TenancyService | updateRegionSettings | response | aiResidencyOptIn.confirmedAt | string (date-time) |  | (read-only)
TenancyService | updateRegionSettings | response | localLanguageNameLocales | array of string |  | The languages an outlet name must also be given in, in this country (decided 2 October 2026, Chinmay, batch 2 #26: "English plus the local language where the country needs it"; DEC-031; CHG-CSP-005). (default [])
TenancyService | updateRegionSettings | response | requiredBillingDocuments | array of object |  | Which documents a TICVAI customer's billing entity must upload, in this country (decided 2 October 2026, Chinmay, batch 6 set 7, ADM-411: "Trade licence always; VAT certificate when a TRN is entered;… (default [{'documentType': 'tradeLicence', 'requiredWhen': 'always'}, {'documentType': 'vatCertificate', 'requiredWhen': 'trnEntered'}])
TenancyService | updateRegionSettings | response | requiredBillingDocuments[].documentType | string |  | The document kind, as the subscription contract's PartnerDocument names it (tradeLicence, vatCertificate, ...). (max length 64)
TenancyService | updateRegionSettings | response | requiredBillingDocuments[].requiredWhen | enum (always, trnEntered)
TenancyService | updateRegionSettings | response | minorAgeThreshold | integer |  | The age below which a guest is a minor here, set per country (decided 2 October 2026, Chinmay, critical set 1, BO-187: "Guardian consent on the venue's form; minor age per country"; DEC-237; CHG-CSP-… (min 0; max 21; default 18)
TenancyService | updateRegionSettings | response | placement | Placement |  | Read-only here. (read-only)
TenancyService | updateRegionSettings | response | placement.mode | enum (shared, dedicated, isolated, clientHosted) | yes
TenancyService | updateRegionSettings | response | placement.cellName | string
TenancyService | updateRegionSettings | response | placement.cloudRegion | string
TenancyService | updateRegionSettings | response | cellName | string |  | The cell serving this region. (read-only)
TenancyService | updateRegionSettings | param (path) | regionId | string (uuid) | yes
TenancyService | updateRegionSettings | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | updateReport | request | name | string | yes | (max length 200)
ReportingService | updateReport | request | description | string |  | (max length 1000)
ReportingService | updateReport | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | updateReport | request | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | updateReport | request | columns | array of ReportColumn | yes | (min items 1)
ReportingService | updateReport | request | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | request | columns[].field | string | yes
ReportingService | updateReport | request | columns[].label | string
ReportingService | updateReport | request | columns[].aggregation | object |  | (default none)
ReportingService | updateReport | request | columns[].sortOrder | integer
ReportingService | updateReport | request | columns[].sortDirection | enum (asc, desc)
ReportingService | updateReport | request | columns[].format | string |  | (nullable)
ReportingService | updateReport | request | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | updateReport | request | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | updateReport | request | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | updateReport | request | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | updateReport | request | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | updateReport | request | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | updateReport | request | filters | array of ReportFilter
ReportingService | updateReport | request | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | request | filters[].field | string | yes
ReportingService | updateReport | request | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | updateReport | request | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | updateReport | request | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | updateReport | request | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | updateReport | request | groupBy | array of string
ReportingService | updateReport | request | parameters | array of ReportParameter
ReportingService | updateReport | request | parameters[].key | string | yes
ReportingService | updateReport | request | parameters[].label | string | yes
ReportingService | updateReport | request | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | updateReport | request | parameters[].isRequired | boolean | yes
ReportingService | updateReport | request | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | updateReport | request | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | updateReport | request | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | updateReport | response | name | string | yes | (max length 200)
ReportingService | updateReport | response | description | string |  | (max length 1000)
ReportingService | updateReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | updateReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | updateReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | updateReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | response | columns[].field | string | yes
ReportingService | updateReport | response | columns[].label | string
ReportingService | updateReport | response | columns[].aggregation | object |  | (default none)
ReportingService | updateReport | response | columns[].sortOrder | integer
ReportingService | updateReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | updateReport | response | columns[].format | string |  | (nullable)
ReportingService | updateReport | response | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | updateReport | response | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | updateReport | response | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | updateReport | response | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | updateReport | response | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | updateReport | response | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | updateReport | response | filters | array of ReportFilter
ReportingService | updateReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | response | filters[].field | string | yes
ReportingService | updateReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | updateReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | updateReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | updateReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | updateReport | response | groupBy | array of string
ReportingService | updateReport | response | parameters | array of ReportParameter
ReportingService | updateReport | response | parameters[].key | string | yes
ReportingService | updateReport | response | parameters[].label | string | yes
ReportingService | updateReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | updateReport | response | parameters[].isRequired | boolean | yes
ReportingService | updateReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | updateReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | updateReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | updateReport | response | id | string (uuid) | yes
ReportingService | updateReport | response | version | string | yes | The current version.
ReportingService | updateReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | updateReport | response | isRetired | boolean | yes
ReportingService | updateReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | updateReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | updateReport | response | createdAt | string (date-time) | yes
ReportingService | updateReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | updateReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | updateReport | param (path) | reportId | string (uuid) | yes
ReportingService | updateReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateResource | request | id | string (uuid) | yes | (read-only)
VenueOpsService | updateResource | request | code | string | yes
VenueOpsService | updateResource | request | name | string | yes
VenueOpsService | updateResource | request | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | updateResource | request | venueId | string (uuid) | yes
VenueOpsService | updateResource | request | scopePath | string
VenueOpsService | updateResource | request | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | updateResource | request | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | updateResource | request | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | updateResource | request | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | updateResource | request | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | updateResource | request | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | updateResource | request | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | updateResource | request | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | updateResource | request | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | updateResource | request | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | request | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | request | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | updateResource | request | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResource | request | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResource | request | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResource | request | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResource | request | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | updateResource | request | isActive | boolean |  | (default True)
VenueOpsService | updateResource | request | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | updateResource | request | lifecycleState | object |  | The lifecycle state setResourceLifecycleState set. (read-only; nullable)
VenueOpsService | updateResource | request | lifecycleEffectiveFrom | string (date-time) |  | When the lifecycle state takes effect (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | updateResource | request | lifecycleReason | string |  | Why the lifecycle state changed (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | updateResource | request | replacementResourceId | string (uuid) |  | The resource that replaces this one, where it was retired for a replacement. (read-only; nullable)
VenueOpsService | updateResource | request | disposal | object |  | How a disposed resource left (setResourceLifecycleState), as given. (read-only; nullable)
VenueOpsService | updateResource | response | id | string (uuid) | yes | (read-only)
VenueOpsService | updateResource | response | code | string | yes
VenueOpsService | updateResource | response | name | string | yes
VenueOpsService | updateResource | response | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | updateResource | response | venueId | string (uuid) | yes
VenueOpsService | updateResource | response | scopePath | string
VenueOpsService | updateResource | response | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | updateResource | response | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | updateResource | response | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | updateResource | response | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | updateResource | response | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | updateResource | response | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | updateResource | response | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | updateResource | response | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | updateResource | response | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | updateResource | response | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | response | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | response | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | updateResource | response | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResource | response | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResource | response | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResource | response | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResource | response | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | updateResource | response | isActive | boolean |  | (default True)
VenueOpsService | updateResource | response | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | updateResource | response | lifecycleState | object |  | The lifecycle state setResourceLifecycleState set. (read-only; nullable)
VenueOpsService | updateResource | response | lifecycleEffectiveFrom | string (date-time) |  | When the lifecycle state takes effect (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | updateResource | response | lifecycleReason | string |  | Why the lifecycle state changed (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | updateResource | response | replacementResourceId | string (uuid) |  | The resource that replaces this one, where it was retired for a replacement. (read-only; nullable)
VenueOpsService | updateResource | response | disposal | object |  | How a disposed resource left (setResourceLifecycleState), as given. (read-only; nullable)
VenueOpsService | updateResource | param (path) | resourceId | string (uuid) | yes
VenueOpsService | updateResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateResourcePackage | request | id | string (uuid)
VenueOpsService | updateResourcePackage | request | code | string | yes
VenueOpsService | updateResourcePackage | request | name | string | yes
VenueOpsService | updateResourcePackage | request | description | string |  | (nullable)
VenueOpsService | updateResourcePackage | request | applicableVenueIds | array of string (uuid)
VenueOpsService | updateResourcePackage | request | components | array of ResourceRequirement
VenueOpsService | updateResourcePackage | request | components[].id | string (uuid)
VenueOpsService | updateResourcePackage | request | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | request | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | request | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | updateResourcePackage | request | components[].quantity | integer | yes | (default 1)
VenueOpsService | updateResourcePackage | request | components[].mandatory | boolean |  | (default True)
VenueOpsService | updateResourcePackage | request | components[].requiredQualifications | array of string
VenueOpsService | updateResourcePackage | request | components[].requiredAttributes | object
VenueOpsService | updateResourcePackage | request | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | updateResourcePackage | request | components[].scopePath | string
VenueOpsService | updateResourcePackage | request | components[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | updateResourcePackage | request | components[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | updateResourcePackage | request | allocationPriority | integer |  | (default 0)
VenueOpsService | updateResourcePackage | request | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | request | effectiveTo | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | request | minimumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | request | maximumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | request | requiresApproval | boolean |  | (default False)
VenueOpsService | updateResourcePackage | request | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResourcePackage | request | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResourcePackage | request | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResourcePackage | request | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResourcePackage | request | scopePath | string
VenueOpsService | updateResourcePackage | response | id | string (uuid)
VenueOpsService | updateResourcePackage | response | code | string | yes
VenueOpsService | updateResourcePackage | response | name | string | yes
VenueOpsService | updateResourcePackage | response | description | string |  | (nullable)
VenueOpsService | updateResourcePackage | response | applicableVenueIds | array of string (uuid)
VenueOpsService | updateResourcePackage | response | components | array of ResourceRequirement
VenueOpsService | updateResourcePackage | response | components[].id | string (uuid)
VenueOpsService | updateResourcePackage | response | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | response | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | response | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | updateResourcePackage | response | components[].quantity | integer | yes | (default 1)
VenueOpsService | updateResourcePackage | response | components[].mandatory | boolean |  | (default True)
VenueOpsService | updateResourcePackage | response | components[].requiredQualifications | array of string
VenueOpsService | updateResourcePackage | response | components[].requiredAttributes | object
VenueOpsService | updateResourcePackage | response | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | updateResourcePackage | response | components[].scopePath | string
VenueOpsService | updateResourcePackage | response | components[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | updateResourcePackage | response | components[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | updateResourcePackage | response | allocationPriority | integer |  | (default 0)
VenueOpsService | updateResourcePackage | response | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | response | effectiveTo | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | response | minimumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | response | maximumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | response | requiresApproval | boolean |  | (default False)
VenueOpsService | updateResourcePackage | response | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResourcePackage | response | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResourcePackage | response | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResourcePackage | response | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResourcePackage | response | scopePath | string
VenueOpsService | updateResourcePackage | param (path) | packageId | string (uuid) | yes
VenueOpsService | updateResourcePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | updateRole | request | name | string |  | (max length 200)
IdentityService | updateRole | request | description | string |  | (max length 500; nullable)
IdentityService | updateRole | response | id | string (uuid) | yes
IdentityService | updateRole | response | code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | updateRole | response | name | string | yes
IdentityService | updateRole | response | description | string
IdentityService | updateRole | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | updateRole | response | inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | updateRole | response | isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | updateRole | response | presetCode | string |  | The preset this role was started from, for the record only (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): the first of createRole.presetCodes, or null for a role ticked by hand. (max length 64; read-only; nullable)
IdentityService | updateRole | response | principalCount | integer |  | Computed on read, never stored (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): the distinct principals holding this role through a live grant (identity.delegated_access with this role_id, a prin… (read-only)
IdentityService | updateRole | response | grantCount | integer |  | Computed on read, never stored (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): the live grants of this role (the rows principalCount counts, one per grant, so a principal granted the role at two… (read-only)
IdentityService | updateRole | param (path) | roleId | string (uuid) | yes
IdentityService | updateRole | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateRotaAssignment | request | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | updateRotaAssignment | request | labourCost | object |  | Cost at the point of scheduling.
TenancyService | updateRotaAssignment | request | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | updateRotaAssignment | request | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | updateRotaAssignment | request | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | updateRotaAssignment | request | principalId | string (uuid)
TenancyService | updateRotaAssignment | request | venueId | string (uuid)
TenancyService | updateRotaAssignment | request | departmentId | string (uuid) |  | (nullable)
TenancyService | updateRotaAssignment | request | position | string |  | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | updateRotaAssignment | request | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | updateRotaAssignment | request | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | updateRotaAssignment | request | startsAt | string (date-time)
TenancyService | updateRotaAssignment | request | endsAt | string (date-time)
TenancyService | updateRotaAssignment | request | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | updateRotaAssignment | request | breakMinutes | integer |  | (nullable)
TenancyService | updateRotaAssignment | request | note | string |  | (nullable)
TenancyService | updateRotaAssignment | response | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | updateRotaAssignment | response | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | updateRotaAssignment | response | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | updateRotaAssignment | response | labourCost | object |  | Cost at the point of scheduling.
TenancyService | updateRotaAssignment | response | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | updateRotaAssignment | response | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | updateRotaAssignment | response | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | updateRotaAssignment | response | id | string (uuid) |  | (read-only)
TenancyService | updateRotaAssignment | response | principalId | string (uuid) | yes
TenancyService | updateRotaAssignment | response | displayName | string |  | (read-only)
TenancyService | updateRotaAssignment | response | venueId | string (uuid) | yes
TenancyService | updateRotaAssignment | response | departmentId | string (uuid) |  | (nullable)
TenancyService | updateRotaAssignment | response | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | updateRotaAssignment | response | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | updateRotaAssignment | response | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | updateRotaAssignment | response | startsAt | string (date-time) | yes
TenancyService | updateRotaAssignment | response | endsAt | string (date-time) | yes
TenancyService | updateRotaAssignment | response | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | updateRotaAssignment | response | breakMinutes | integer |  | (nullable)
TenancyService | updateRotaAssignment | response | note | string |  | (nullable)
TenancyService | updateRotaAssignment | param (path) | assignmentId | string (uuid) | yes
TenancyService | updateRotaAssignment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateSaleBoard | request | id | string (uuid) | yes | (read-only)
TenancyService | updateSaleBoard | request | code | string | yes | Unique within the venue (as the hand-written r0 table had it). (max length 64)
TenancyService | updateSaleBoard | request | name | string | yes | (max length 200)
TenancyService | updateSaleBoard | request | venueId | string (uuid) | yes
TenancyService | updateSaleBoard | request | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | updateSaleBoard | request | pages | array of object | yes | (min items 1)
TenancyService | updateSaleBoard | request | pages[].name | string | yes
TenancyService | updateSaleBoard | request | pages[].sortOrder | integer | yes
TenancyService | updateSaleBoard | request | pages[].tiles | array of SaleBoardTile | yes
TenancyService | updateSaleBoard | request | pages[].tiles[].position | integer | yes
TenancyService | updateSaleBoard | request | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | updateSaleBoard | request | pages[].tiles[].variantId | string (uuid) |  | The catalogue variant a product tile sells (catalogue.variant). (nullable)
TenancyService | updateSaleBoard | request | pages[].tiles[].categoryId | string (uuid) |  | The catalogue category a category tile opens (catalogue.product_category; ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | updateSaleBoard | request | pages[].tiles[].actionCode | enum (holdSale, recallHeld, applyDiscount, guestLookup, scanMedia, reprintReceipt) |  | The till action an action tile runs (ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | updateSaleBoard | request | pages[].tiles[].label | string
TenancyService | updateSaleBoard | request | pages[].tiles[].colour | string |  | #rrggbb, as the hand-written r0 table held it (char(7); audit R246; CHG-TEN-001). (pattern ^#[0-9A-Fa-f]{6}$; nullable)
TenancyService | updateSaleBoard | request | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | updateSaleBoard | request | isActive | boolean
TenancyService | updateSaleBoard | response | id | string (uuid) | yes | (read-only)
TenancyService | updateSaleBoard | response | code | string | yes | Unique within the venue (as the hand-written r0 table had it). (max length 64)
TenancyService | updateSaleBoard | response | name | string | yes | (max length 200)
TenancyService | updateSaleBoard | response | venueId | string (uuid) | yes
TenancyService | updateSaleBoard | response | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | updateSaleBoard | response | pages | array of object | yes | (min items 1)
TenancyService | updateSaleBoard | response | pages[].name | string | yes
TenancyService | updateSaleBoard | response | pages[].sortOrder | integer | yes
TenancyService | updateSaleBoard | response | pages[].tiles | array of SaleBoardTile | yes
TenancyService | updateSaleBoard | response | pages[].tiles[].position | integer | yes
TenancyService | updateSaleBoard | response | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | updateSaleBoard | response | pages[].tiles[].variantId | string (uuid) |  | The catalogue variant a product tile sells (catalogue.variant). (nullable)
TenancyService | updateSaleBoard | response | pages[].tiles[].categoryId | string (uuid) |  | The catalogue category a category tile opens (catalogue.product_category; ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | updateSaleBoard | response | pages[].tiles[].actionCode | enum (holdSale, recallHeld, applyDiscount, guestLookup, scanMedia, reprintReceipt) |  | The till action an action tile runs (ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | updateSaleBoard | response | pages[].tiles[].label | string
TenancyService | updateSaleBoard | response | pages[].tiles[].colour | string |  | #rrggbb, as the hand-written r0 table held it (char(7); audit R246; CHG-TEN-001). (pattern ^#[0-9A-Fa-f]{6}$; nullable)
TenancyService | updateSaleBoard | response | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | updateSaleBoard | response | isActive | boolean
TenancyService | updateSaleBoard | param (path) | saleBoardId | string (uuid) | yes
TenancyService | updateSaleBoard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateSeatCategory | request | name | string |  | (max length 200)
CatalogueService | updateSeatCategory | request | displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
CatalogueService | updateSeatCategory | request | rank | integer
CatalogueService | updateSeatCategory | request | priceBands | array of SeatPriceBand
CatalogueService | updateSeatCategory | request | priceBands[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | updateSeatCategory | request | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | updateSeatCategory | request | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | updateSeatCategory | request | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | updateSeatCategory | request | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | updateSeatCategory | request | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | updateSeatCategory | request | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | updateSeatCategory | request | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateSeatCategory | request | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateSeatCategory | request | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateSeatCategory | request | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | updateSeatCategory | request | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | updateSeatCategory | request | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | updateSeatCategory | request | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | updateSeatCategory | response | id | string (uuid) | yes
CatalogueService | updateSeatCategory | response | code | string | yes
CatalogueService | updateSeatCategory | response | name | string | yes
CatalogueService | updateSeatCategory | response | venueId | string (uuid) | yes
CatalogueService | updateSeatCategory | response | displayColour | string |  | (nullable)
CatalogueService | updateSeatCategory | response | rank | integer | yes | Ordering for best-seat assignment.
CatalogueService | updateSeatCategory | response | seatCount | integer
CatalogueService | updateSeatCategory | response | priceBands | array of SeatPriceBand |  | What a seat in this category costs, by band (decided 28 September, audit R275 (d), from the BO-1045 pack).
CatalogueService | updateSeatCategory | response | priceBands[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | updateSeatCategory | response | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | updateSeatCategory | response | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | updateSeatCategory | response | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | updateSeatCategory | response | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | updateSeatCategory | response | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | updateSeatCategory | response | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | updateSeatCategory | response | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateSeatCategory | response | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateSeatCategory | response | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateSeatCategory | response | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | updateSeatCategory | response | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | updateSeatCategory | response | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | updateSeatCategory | response | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | updateSeatCategory | param (path) | seatCategoryId | string (uuid) | yes
CatalogueService | updateSeatCategory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateSeatCategory | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
FnbService | updateTableReservation | request | outletId | string (uuid)
FnbService | updateTableReservation | request | subjectId | string (uuid) |  | (nullable)
FnbService | updateTableReservation | request | guestName | string
FnbService | updateTableReservation | request | contactPoint | string
FnbService | updateTableReservation | request | partySize | integer |  | (min 1)
FnbService | updateTableReservation | request | startsAt | string (date-time)
FnbService | updateTableReservation | request | durationMinutes | integer |  | How long the cover is held.
FnbService | updateTableReservation | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | updateTableReservation | request | tables[].reservationId | string (uuid) | yes
FnbService | updateTableReservation | request | tables[].tableId | string (uuid) | yes
FnbService | updateTableReservation | request | tables[].createdAt | string (date-time) | yes
FnbService | updateTableReservation | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | updateTableReservation | request | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | updateTableReservation | request | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | updateTableReservation | request | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | updateTableReservation | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | updateTableReservation | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateTableReservation | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableReservation | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableReservation | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableReservation | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | updateTableReservation | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | updateTableReservation | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | updateTableReservation | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | updateTableReservation | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | updateTableReservation | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | updateTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | updateTableReservation | response | outletId | string (uuid) | yes
FnbService | updateTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | updateTableReservation | response | guestName | string
FnbService | updateTableReservation | response | contactPoint | string
FnbService | updateTableReservation | response | partySize | integer | yes | (min 1)
FnbService | updateTableReservation | response | startsAt | string (date-time) | yes
FnbService | updateTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | updateTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | updateTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | updateTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | updateTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | updateTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | updateTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | updateTableReservation | response | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | updateTableReservation | response | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | updateTableReservation | response | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | updateTableReservation | response | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | updateTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | updateTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | updateTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | updateTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | updateTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | updateTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | updateTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | updateTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | updateTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | updateTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | updateTableReservation | param (path) | reservationId | string (uuid) | yes
FnbService | updateTableReservation | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | updateTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | updateTableVisit | request | covers | integer |  | (min 1)
FnbService | updateTableVisit | request | tableId | string (uuid)
FnbService | updateTableVisit | request | serverPrincipalId | string (uuid)
FnbService | updateTableVisit | request | note | string |  | (max length 500)
FnbService | updateTableVisit | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | updateTableVisit | response | id | string (uuid) | yes
FnbService | updateTableVisit | response | tableId | string (uuid) | yes
FnbService | updateTableVisit | response | tableLabel | string
FnbService | updateTableVisit | response | outletId | string (uuid) | yes
FnbService | updateTableVisit | response | covers | integer | yes
FnbService | updateTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | updateTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | updateTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | updateTableVisit | response | orders | array of FnbOrder | yes
FnbService | updateTableVisit | response | orders[].id | string (uuid) | yes
FnbService | updateTableVisit | response | orders[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | updateTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | updateTableVisit | response | orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | updateTableVisit | response | orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | updateTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | updateTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | updateTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | updateTableVisit | response | orders[].lines | array of object | yes
FnbService | updateTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | updateTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | updateTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | updateTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | updateTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | updateTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | updateTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | updateTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | updateTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | updateTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | updateTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | updateTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | updateTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | updateTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | updateTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | updateTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | updateTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | updateTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | updateTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | updateTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | updateTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | updateTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | updateTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | updateTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | updateTableVisit | response | orders[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | updateTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | updateTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | updateTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | updateTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | updateTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | updateTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | updateTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | updateTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | updateTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableVisit | response | openedAt | string (date-time) | yes
FnbService | updateTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | updateTableVisit | response | serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | updateTableVisit | response | serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | updateTableVisit | response | note | string |  | The server's note on the visit (updateTableVisit). (max length 500; read-only; nullable)
FnbService | updateTableVisit | param (path) | visitId | string (uuid) | yes
FnbService | updateTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | updateTaxCode | request | name | string |  | (max length 200)
LedgerService | updateTaxCode | request | rate | number |  | (min 0; max 100)
LedgerService | updateTaxCode | request | effectiveFrom | string (date) |  | Required with rate, and only meaningful with it.
LedgerService | updateTaxCode | request | isActive | boolean
LedgerService | updateTaxCode | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
LedgerService | updateTaxCode | response | id | string (uuid) | yes
LedgerService | updateTaxCode | response | code | string | yes | (max length 64)
LedgerService | updateTaxCode | response | name | string | yes | (max length 200)
LedgerService | updateTaxCode | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | updateTaxCode | response | appliesTo | array of enum (goods, services, admission, food, accommodation, donation, gratuity, fee) |  | What this code covers, and donation is why the field exists (CF-84).
LedgerService | updateTaxCode | response | rate | number | yes | (min 0; max 100)
LedgerService | updateTaxCode | response | compoundOnTaxCodeId | string (uuid) |  | When set, this tax applies to the base plus the referenced tax, not to the base alone. (nullable)
LedgerService | updateTaxCode | response | isInclusive | boolean |  | True when the displayed price already contains this tax.
LedgerService | updateTaxCode | response | accountId | string (uuid)
LedgerService | updateTaxCode | response | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | updateTaxCode | response | effectiveTo | string (date) |  | A day in the region's time zone, local midnight to local midnight. (nullable)
LedgerService | updateTaxCode | response | isActive | boolean | yes
LedgerService | updateTaxCode | param (path) | taxCodeId | string (uuid) | yes
LedgerService | updateTaxCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | updateTenant | request | name | string |  | (max length 200)
PlatformService | updateTenant | request | billingEmail | string
PlatformService | updateTenant | request | billingAddress | string |  | (max length 500)
PlatformService | updateTenant | request | accountManagerPrincipalId | string (uuid)
PlatformService | updateTenant | response | id | string (uuid) | yes
PlatformService | updateTenant | response | code | string | yes
PlatformService | updateTenant | response | name | string | yes
PlatformService | updateTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | updateTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | updateTenant | response | suspensionReason | string |  | (nullable)
PlatformService | updateTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | updateTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | updateTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | updateTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | updateTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | updateTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | updateTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | updateTenant | response | planVersion | string |  | The version of the plan the tenant is on (with planId, the key of the plan row; R8 blocker APPROVALS-TENANCY-C15, CHG-R8INT-023). (read-only; nullable)
PlatformService | updateTenant | response | planName | string |  | (nullable)
PlatformService | updateTenant | response | cellCount | integer
PlatformService | updateTenant | response | venueCount | integer
PlatformService | updateTenant | response | cellHost | string |  | The host of the tenant's home cell (the host part of Cell.apiEndpoint of the cell that holds the tenant in its home region), derived on read through control.cell_tenant. (read-only; nullable)
PlatformService | updateTenant | response | cellHosts | array of object |  | One entry per region the tenant is in, for a multi-region tenant; the entry with isHome true is cellHost. (read-only)
PlatformService | updateTenant | response | cellHosts[].regionId | string (uuid) | yes
PlatformService | updateTenant | response | cellHosts[].cellId | string (uuid) | yes
PlatformService | updateTenant | response | cellHosts[].host | string | yes
PlatformService | updateTenant | response | cellHosts[].isHome | boolean | yes
PlatformService | updateTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | updateTenant | response | billingEmail | string
PlatformService | updateTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | updateTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | updateTenant | response | createdAt | string (date-time) | yes
PlatformService | updateTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | updateTenant | param (path) | tenantId | string (uuid) | yes
PlatformService | updateTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | updateTicketTemplate | request | name | string |  | (max length 200)
OrderService | updateTicketTemplate | request | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms)
OrderService | updateTicketTemplate | request | isRecyclable | boolean
OrderService | updateTicketTemplate | request | recycleAfterDays | integer |  | (min 0; nullable)
OrderService | updateTicketTemplate | request | appliesToProductKinds | array of string
OrderService | updateTicketTemplate | request | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | updateTicketTemplate | request | selectionPriority | integer
OrderService | updateTicketTemplate | request | layoutRef | string |  | The artwork, as a media-asset reference.
OrderService | updateTicketTemplate | request | localeVariants | object
OrderService | updateTicketTemplate | request | isActive | boolean
OrderService | updateTicketTemplate | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
OrderService | updateTicketTemplate | response | id | string (uuid) | yes
OrderService | updateTicketTemplate | response | name | string | yes
OrderService | updateTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | updateTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | updateTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | updateTicketTemplate | response | appliesToProductKinds | array of string
OrderService | updateTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | updateTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | updateTicketTemplate | response | layoutRef | string
OrderService | updateTicketTemplate | response | localeVariants | object
OrderService | updateTicketTemplate | response | isActive | boolean | yes
OrderService | updateTicketTemplate | param (path) | templateId | string (uuid) | yes
OrderService | updateTicketTemplate | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | updateTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateTransportDeparture | request | seatCapacity | integer |  | (min 1; max 200)
VenueOpsService | updateTransportDeparture | request | vehicleResourceId | string (uuid) |  | (nullable)
VenueOpsService | updateTransportDeparture | request | note | string |  | (max length 500; nullable)
VenueOpsService | updateTransportDeparture | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportDeparture | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportDeparture | response | timetableId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportDeparture | response | performanceId | string (uuid) | yes | The catalogue performance this departure is sold as.
VenueOpsService | updateTransportDeparture | response | serviceDate | string (date) | yes
VenueOpsService | updateTransportDeparture | response | departsAt | string (date-time) | yes | At the route's first stop.
VenueOpsService | updateTransportDeparture | response | status | TransportDepartureStatus: enum (scheduled, onSale, soldOut, departed, cancelled) | yes | Mirrors the catalogue performance behind the departure, in the words a coach operator uses.
VenueOpsService | updateTransportDeparture | response | seatCapacity | integer | yes | (min 1)
VenueOpsService | updateTransportDeparture | response | seatsSold | integer |  | From catalogue availability on read; not stored here. (read-only)
VenueOpsService | updateTransportDeparture | response | vehicleResourceId | string (uuid) |  | (nullable)
VenueOpsService | updateTransportDeparture | response | note | string |  | (nullable)
VenueOpsService | updateTransportDeparture | param (path) | departureId | string (uuid) | yes
VenueOpsService | updateTransportDeparture | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateTransportPassType | request | name | LocalisedText
VenueOpsService | updateTransportPassType | request | description | LocalisedText
VenueOpsService | updateTransportPassType | request | fareMultiplier | number |  | (min 0; max 1000)
VenueOpsService | updateTransportPassType | request | referenceTrips | integer |  | (min 1; max 1000)
VenueOpsService | updateTransportPassType | request | validityDays | integer |  | (min 1; max 366)
VenueOpsService | updateTransportPassType | request | routeIds | array of string (uuid)
VenueOpsService | updateTransportPassType | request | sortOrder | integer |  | (min 0)
VenueOpsService | updateTransportPassType | request | active | boolean
VenueOpsService | updateTransportPassType | response | venueId | string (uuid) | yes
VenueOpsService | updateTransportPassType | response | code | string | yes | (max length 32)
VenueOpsService | updateTransportPassType | response | name | LocalisedText | yes
VenueOpsService | updateTransportPassType | response | description | LocalisedText
VenueOpsService | updateTransportPassType | response | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | updateTransportPassType | response | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | updateTransportPassType | response | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | updateTransportPassType | response | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | updateTransportPassType | response | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | updateTransportPassType | response | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | updateTransportPassType | response | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | updateTransportPassType | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportPassType | response | active | boolean | yes | (default True)
VenueOpsService | updateTransportPassType | response | catalogueProductId | string (uuid) |  | The catalogue openDated product this pass is sold as. (read-only)
VenueOpsService | updateTransportPassType | param (path) | passTypeId | string (uuid) | yes
VenueOpsService | updateTransportPassType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateTransportRoute | request | name | LocalisedText
VenueOpsService | updateTransportRoute | request | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | updateTransportRoute | request | pairedRouteId | string (uuid) |  | (nullable)
VenueOpsService | updateTransportRoute | request | bookingCutoffMinutes | integer |  | (min 0; max 1440)
VenueOpsService | updateTransportRoute | request | stops | array of RouteStopInput |  | (min items 2)
VenueOpsService | updateTransportRoute | request | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | request | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | updateTransportRoute | request | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | request | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | updateTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | updateTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | updateTransportRoute | response | name | LocalisedText | yes
VenueOpsService | updateTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | updateTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | updateTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | updateTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | updateTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | updateTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | updateTransportRoute | response | stops[].station | Station
VenueOpsService | updateTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | updateTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | updateTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | updateTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | updateTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | updateTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | updateTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | updateTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | updateTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | updateTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | updateTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | updateTransportRoute | response | statusReason | string |  | Why the route's status last changed (setTransportRouteStatus). (max length 500; read-only; nullable)
VenueOpsService | updateTransportRoute | param (path) | routeId | string (uuid) | yes
VenueOpsService | updateTransportRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateTransportStation | request | name | LocalisedText
VenueOpsService | updateTransportStation | request | shortName | LocalisedText
VenueOpsService | updateTransportStation | request | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | updateTransportStation | request | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | updateTransportStation | request | active | boolean
VenueOpsService | updateTransportStation | response | venueId | string (uuid) | yes
VenueOpsService | updateTransportStation | response | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | updateTransportStation | response | name | LocalisedText | yes
VenueOpsService | updateTransportStation | response | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | updateTransportStation | response | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | updateTransportStation | response | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | updateTransportStation | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportStation | response | active | boolean | yes | (default True)
VenueOpsService | updateTransportStation | param (path) | stationId | string (uuid) | yes
VenueOpsService | updateTransportStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateVisitPlan | request | baseVersion | integer | yes | (min 1)
VenueOpsService | updateVisitPlan | request | changes | array of object | yes | (min items 1; max items 20)
VenueOpsService | updateVisitPlan | request | changes[].op | enum (swap, remove, add, move, pin, acceptAddOn, declineAddOn, addAddOn, …) | yes
VenueOpsService | updateVisitPlan | request | changes[].itemId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].date | string (date) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].pointId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].startsAt | string (date-time) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].addOnProductId | string (uuid) |  | For addAddOn and removeAddOn (CHG-RUL-009): the add-on product (a catalogue product sold for the item's stop, e.g. (nullable)
VenueOpsService | updateVisitPlan | request | changes[].version | integer |  | For revertTo, the earlier version to restore (undo). (nullable)
VenueOpsService | updateVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | updateVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | updateVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | updateVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | ownership | enum (anonymous, account) |  | anonymous while the plan belongs to a device session (built and changed only; it lapses with the session), account once the guest signed in and the plan moved to their account, where it is saved and… (read-only)
VenueOpsService | updateVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | updateVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | updateVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | updateVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | updateVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | updateVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | updateVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | updateVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | updateVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | updateVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | updateVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | updateVisitPlan | response | inputs.pace | enum (packed, balanced, relaxed) |  | (default relaxed)
VenueOpsService | updateVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | updateVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | updateVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | updateVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | updateVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | updateVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | updateVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | updateVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | updateVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | updateVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | updateVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | response | excluded[].name | string |  | The point's name, worked out on read for the left-out banner (r8 walk of ticket 28693). (nullable)
VenueOpsService | updateVisitPlan | response | excluded[].limit | object |  | The rule that left it out, worked out on read from the product's eligibility rule: for heightRule a minimum or maximum height in centimetres, for ageRule a minimum or maximum age in years. (nullable)
VenueOpsService | updateVisitPlan | response | excluded[].limit.kind | enum (minHeightCm, maxHeightCm, minAge, maxAge)
VenueOpsService | updateVisitPlan | response | excluded[].limit.value | integer |  | (min 0)
VenueOpsService | updateVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | updateVisitPlan | response | estimate | object |  | An estimated total, computed on read from current catalogue prices and stored nowhere (r8 walk of tickets 28693 and 28200; lead decision of 20 October 2026, option A; DI-1098, "with associated costin… (read-only; nullable)
VenueOpsService | updateVisitPlan | response | estimate.total | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateVisitPlan | response | estimate.total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateVisitPlan | response | estimate.total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateVisitPlan | response | estimate.total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateVisitPlan | response | estimate.currency | string | yes
VenueOpsService | updateVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | updateVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | updateVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | updateVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | updateVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | updateVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | updateVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].name | string |  | What the stop is called on the timeline (GST-059, GST-053; r8 walk of ticket 28693): the point's name, or the performance's title for a show, in the request language. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].zoneName | string |  | The name of the zone the stop is in, from the point's zone on the map the plan was laid out on. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | updateVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | updateVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | updateVisitPlan | response | days[].items[].addOnProductIds | array of string (uuid) |  | Add-ons the guest put on this stop with addAddOn (CHG-RUL-009), beside an accepted suggestion, as catalogue product ids. (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | updateVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | updateVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | updateVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | updateVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | updateVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | uploadGuestDocument | request | id | string (uuid) | yes | (read-only)
MarketingService | uploadGuestDocument | request | subjectId | string (uuid) | yes
MarketingService | uploadGuestDocument | request | kind | enum (avatar, idDocument, visa, signedWaiver, medicalNote, accessibilityEvidence, photo, other) | yes
MarketingService | uploadGuestDocument | request | storageRef | string | yes | The stored object's key in the guest-document store, which is deliberately not assets (BL-133).
MarketingService | uploadGuestDocument | request | contentType | string
MarketingService | uploadGuestDocument | request | consentPurposeId | string (uuid)
MarketingService | uploadGuestDocument | request | retainUntil | string (date) | yes | Required, not optional.
MarketingService | uploadGuestDocument | request | uploadedAt | string (date-time) |  | (read-only)
MarketingService | uploadGuestDocument | request | uploadedByPrincipalId | string (uuid) |  | (read-only; nullable)
MarketingService | uploadGuestDocument | response | id | string (uuid) | yes | (read-only)
MarketingService | uploadGuestDocument | response | subjectId | string (uuid) | yes
MarketingService | uploadGuestDocument | response | kind | enum (avatar, idDocument, visa, signedWaiver, medicalNote, accessibilityEvidence, photo, other) | yes
MarketingService | uploadGuestDocument | response | storageRef | string | yes | The stored object's key in the guest-document store, which is deliberately not assets (BL-133).
MarketingService | uploadGuestDocument | response | contentType | string
MarketingService | uploadGuestDocument | response | consentPurposeId | string (uuid)
MarketingService | uploadGuestDocument | response | retainUntil | string (date) | yes | Required, not optional.
MarketingService | uploadGuestDocument | response | uploadedAt | string (date-time) |  | (read-only)
MarketingService | uploadGuestDocument | response | uploadedByPrincipalId | string (uuid) |  | (read-only; nullable)
MarketingService | uploadGuestDocument | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | validateBookingFlow | request | steps | array of BookingFlowStep |  | (max items 30)
WhiteLabelService | validateBookingFlow | request | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | validateBookingFlow | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | validateBookingFlow | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | validateBookingFlow | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | validateBookingFlow | response | valid | boolean | yes
WhiteLabelService | validateBookingFlow | response | problems | array of object | yes
WhiteLabelService | validateBookingFlow | response | problems[].kind | enum (requiredStepDisabled, orderConstraintBroken, conditionNeverHolds, stepNotInType, duplicateStep, unknownStepSetting) | yes
WhiteLabelService | validateBookingFlow | response | problems[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | validateBookingFlow | response | problems[].otherStepKey | object |  | For orderConstraintBroken, the step it must come before or after. (nullable)
WhiteLabelService | validateBookingFlow | response | problems[].message | string | yes
WhiteLabelService | validateBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | validateBookingFlow | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | validateTenantConfig | response | passed | boolean | yes
WhiteLabelService | validateTenantConfig | response | errorCount | integer | yes
WhiteLabelService | validateTenantConfig | response | warningCount | integer | yes
WhiteLabelService | validateTenantConfig | response | findings | array of object | yes
WhiteLabelService | validateTenantConfig | response | findings[].kind | ConfigFindingKind: enum (missingTranslation, navigationTargetsDisabledModule, homepageReferencesMissingContent, contrastFailure, missingRequiredAsset, policyVersionMissing, noVisibleNavigationItems, unlicensedModuleEnabled, …) | yes | The checks validateTenantConfig runs.
WhiteLabelService | validateTenantConfig | response | findings[].severity | enum (error, warning) | yes
WhiteLabelService | validateTenantConfig | response | findings[].message | string | yes
WhiteLabelService | validateTenantConfig | response | findings[].area | string
WhiteLabelService | validateTenantConfig | response | findings[].reference | string |  | (nullable)
WhiteLabelService | validateTenantConfig | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | verifyCustomDomain | response | id | string (uuid) | yes
WhiteLabelService | verifyCustomDomain | response | tenantId | string (uuid) | yes
WhiteLabelService | verifyCustomDomain | response | hostname | string | yes
WhiteLabelService | verifyCustomDomain | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) |  | guestApp is stored as guestWeb: the guest app is served on the guestWeb domain and has no domain of its own (r10 question 4; CHG-R10TEN-020).
WhiteLabelService | verifyCustomDomain | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | verifyCustomDomain | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | verifyCustomDomain | response | verificationToken | string |  | (read-only)
WhiteLabelService | verifyCustomDomain | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | verifyCustomDomain | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | verifyCustomDomain | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | verifyCustomDomain | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | verifyCustomDomain | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | verifyCustomDomain | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | verifyCustomDomain | response | validationExpiresAt | string (date-time) |  | When the validation window ends (ADAM CR-105, option 1; CHG-R10TEN-011): 7 days after claimCustomDomain or regenerateDomainToken issued the token (a proposed default the client can correct). (read-only; nullable)
WhiteLabelService | verifyCustomDomain | response | failureReason | string |  | (nullable)
WhiteLabelService | verifyCustomDomain | response | routing | enum (cname, delegatedSubdomain, apex) |  | How the hostname reaches TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; CHG-CSA-043). (default cname)
WhiteLabelService | verifyCustomDomain | response | dnsRecords | array of object |  | Every record the tenant must publish, with what is observed now (CHG-CSA-043): the TXT _dnsauth record, the CNAME, and CAA or NS where they apply. (read-only)
WhiteLabelService | verifyCustomDomain | response | dnsRecords[].type | enum (TXT, CNAME, CAA, NS) | yes
WhiteLabelService | verifyCustomDomain | response | dnsRecords[].name | string | yes
WhiteLabelService | verifyCustomDomain | response | dnsRecords[].expectedValue | string | yes
WhiteLabelService | verifyCustomDomain | response | dnsRecords[].observedValue | string |  | (nullable)
WhiteLabelService | verifyCustomDomain | response | dnsRecords[].status | enum (ok, missing, wrong) | yes
WhiteLabelService | verifyCustomDomain | response | revalidation | enum (none, pendingRevalidation, timedOut) |  | The two waits CMS-017 shows beside status (CHG-CSA-043). (default none; read-only)
WhiteLabelService | verifyCustomDomain | response | isCnameLost | boolean |  | Takeover warning (CHG-CSA-043). (read-only)
WhiteLabelService | verifyCustomDomain | response | isPrimary | boolean |  | The tenant's primary domain for its kind; the others redirect to it (setPrimaryDomain). (read-only)
WhiteLabelService | verifyCustomDomain | response | readiness | object |  | Per-domain setup a guest needs (CHG-CSA-043): the UAE Pass redirect URI registered for this hostname, the Apple Pay merchant domain verified, and the app links (Apple app-site association, Android as… (read-only)
WhiteLabelService | verifyCustomDomain | response | readiness.uaePassRedirect | enum (ready, pending, notApplicable)
WhiteLabelService | verifyCustomDomain | response | readiness.applePayDomain | enum (ready, pending, notApplicable)
WhiteLabelService | verifyCustomDomain | response | readiness.appLinks | enum (ready, pending, notApplicable)
WhiteLabelService | verifyCustomDomain | param (path) | domainId | string (uuid) | yes
WhiteLabelService | verifyCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | verifyDeveloper | response | id | string (uuid) | yes | (read-only)
PlatformService | verifyDeveloper | response | organisationName | string | yes
PlatformService | verifyDeveloper | response | contactEmail | string (email) | yes | The organisation's contact, who becomes its owner member on registration; unique without case (registerDeveloper 409 developer-already-registered; ADAM CR-098).
PlatformService | verifyDeveloper | response | websiteUrl | string |  | (nullable)
PlatformService | verifyDeveloper | response | countryCode | string
PlatformService | verifyDeveloper | response | partnerId | string (uuid) |  | Where this developer is also a commercial partner. (nullable)
PlatformService | verifyDeveloper | response | status | enum (pending, verified, suspended, closed) | yes | (read-only)
PlatformService | verifyDeveloper | response | verifiedAt | string (date-time) |  | (read-only; nullable)
PlatformService | verifyDeveloper | param (path) | developerId | string (uuid) | yes
PlatformService | verifyDeveloper | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyGuestEmail | request | mode | enum (send, confirm, code) | yes
IdentityService | verifyGuestEmail | request | code | string |  | For code. (pattern ^[0-9]{6}$; nullable)
IdentityService | verifyGuestEmail | request | token | string |  | For confirm. (nullable)
IdentityService | verifyGuestEmail | response | isVerified | boolean
IdentityService | verifyGuestEmail | response | expiresAt | string (date-time) |  | (nullable)
IdentityService | verifyGuestEmail | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyGuestOtp | request | identifier | string | yes
IdentityService | verifyGuestOtp | request | code | string | yes | (min length 4; max length 10)
IdentityService | verifyGuestOtp | request | deviceId | string |  | Send the app's installationId (the value it registers its push token with, marketing-crm registerGuestDevice), so revoking that device signs this session out (endGuestDeviceSessions, CHG-MOD-009).
IdentityService | verifyGuestOtp | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | verifyGuestOtp | response | subjectId | string (uuid) | yes
IdentityService | verifyGuestOtp | response | displayName | string |  | (nullable)
IdentityService | verifyGuestOtp | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | verifyGuestOtp | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | verifyGuestOtp | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | verifyGuestOtp | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | verifyGuestOtp | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | verifyGuestOtp | response | mfaMethods[].id | string (uuid) | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].label | string |  | (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].isActive | boolean | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].isPrimary | boolean
IdentityService | verifyGuestOtp | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | verifyGuestOtp | response | homeCellName | string |  | (nullable)
IdentityService | verifyGuestOtp | response | preferredLanguage | string |  | (nullable)
IdentityService | verifyGuestOtp | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | verifyGuestOtp | response | tokens | object | yes | The new access and refresh tokens; refreshToken returns the next pair.
IdentityService | verifyGuestOtp | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | verifyGuestOtp | response | tokens.refreshToken | string | yes
IdentityService | verifyGuestOtp | response | tokens.expiresIn | integer | yes | Seconds until the access token expires: PasswordPolicy.accessTokenMinutes x 60, 900 by default (15 minutes; proposed, client to correct).
IdentityService | verifyGuestOtp | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyMfaChallenge | request | code | string | yes
IdentityService | verifyMfaChallenge | response | stepUpToken | string |  | Null for a signIn challenge. (nullable)
IdentityService | verifyMfaChallenge | response | expiresAt | string (date-time)
IdentityService | verifyMfaChallenge | response | session | object |  | Only for a signIn challenge, and only where no role selection is still owed. (nullable)
IdentityService | verifyMfaChallenge | response | session.sessionId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.principalId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.roleId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.displayName | string
IdentityService | verifyMfaChallenge | response | session.scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | verifyMfaChallenge | response | session.scope[].id | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | verifyMfaChallenge | response | session.scope[].path | string | yes | Materialised ltree path.
IdentityService | verifyMfaChallenge | response | session.scope[].code | string |  | (nullable)
IdentityService | verifyMfaChallenge | response | session.scope[].name | string |  | (nullable)
IdentityService | verifyMfaChallenge | response | session.effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | verifyMfaChallenge | response | session.permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path, after deny resolution.
IdentityService | verifyMfaChallenge | response | session.permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | verifyMfaChallenge | response | session.permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | verifyMfaChallenge | response | session.saleBoardId | string (uuid) |  | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | verifyMfaChallenge | response | session.workstation | WorkstationContext
IdentityService | verifyMfaChallenge | response | session.workstation.id | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.workstation.code | string | yes
IdentityService | verifyMfaChallenge | response | session.workstation.venueId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.workstation.regionId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | verifyMfaChallenge | response | session.workstation.devices | array of object
IdentityService | verifyMfaChallenge | response | session.workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | verifyMfaChallenge | response | session.workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | verifyMfaChallenge | response | session.workstation.timezone | string
IdentityService | verifyMfaChallenge | response | session.workstation.cellName | string |  | The cell this workstation's region is served from, which is the cell the commerce host answering this request is deployed in (one cell per tenant per region, ADR-0014): the host fills it from its own…
IdentityService | verifyMfaChallenge | response | session.workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | verifyMfaChallenge | response | session.workstation.pinLength | enum (4, 6, 8) |  | The tenant's PasswordPolicy.pinLength, carried to the device (14 October 2026, CHG-CRD-002, ADAM CR-078). (read-only)
IdentityService | verifyMfaChallenge | response | session.availableRoles | array of RoleSummary |  | The roles the principal may choose, one per grant (IDENTITY-C45, CHG-R8SPN-032), resolved on read as LoginResponse.availableRoles is, so EMP-002 can list them on a cold open or after a relaunch (getC… (read-only)
IdentityService | verifyMfaChallenge | response | session.availableRoles[].id | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.availableRoles[].code | string | yes
IdentityService | verifyMfaChallenge | response | session.availableRoles[].name | string | yes
IdentityService | verifyMfaChallenge | response | session.availableRoles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | verifyMfaChallenge | response | session.availableRoles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | verifyMfaChallenge | response | session.availableRoles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | verifyMfaChallenge | response | session.openedAt | string (date-time)
IdentityService | verifyMfaChallenge | response | session.expiresAt | string (date-time) |  | When the session ends at the latest: openedAt plus PasswordPolicy.sessionMaxHours (12 hours by default; proposed, client to correct).
IdentityService | verifyMfaChallenge | param (path) | challengeId | string | yes
IdentityService | verifyMfaChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyMfaEnrolment | request | code | string | yes
IdentityService | verifyMfaEnrolment | response | id | string (uuid) | yes
IdentityService | verifyMfaEnrolment | response | principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | verifyMfaEnrolment | response | subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | verifyMfaEnrolment | response | secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | verifyMfaEnrolment | response | destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | verifyMfaEnrolment | response | pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | verifyMfaEnrolment | response | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | verifyMfaEnrolment | response | label | string |  | (nullable)
IdentityService | verifyMfaEnrolment | response | maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | verifyMfaEnrolment | response | isActive | boolean | yes
IdentityService | verifyMfaEnrolment | response | isPrimary | boolean
IdentityService | verifyMfaEnrolment | response | enrolledAt | string (date-time) | yes
IdentityService | verifyMfaEnrolment | response | lastUsedAt | string (date-time) |  | (nullable)
IdentityService | verifyMfaEnrolment | param (path) | methodId | string (uuid) | yes
IdentityService | verifyMfaEnrolment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | voidOrder | request | id | string (uuid) | yes | Client-generated UUIDv7 of this void, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | voidOrder | request | reason | VoidReason: enum (guestChangedMind, enteredInError, itemUnavailable, qualityIssue, duplicate, other) | yes | The void reason list (decided 28 September, audit R125 (4)): the one list voidOrder takes, and the list fnb.amendFnbOrder and fnb.cancelFnbOrder point to.
OrderService | voidOrder | request | note | string |  | Required when reason is other (audit R222); optional otherwise. (min length 3; max length 500; nullable)
OrderService | voidOrder | request | supervisorStepUp | object |  | The supervisor approving for a cashier without ORDER_VOID (r8 walk fix, CHG-R8WFC-005).
OrderService | voidOrder | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | voidOrder | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | voidOrder | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | voidOrder | request | recordedAt | string (date-time) | yes
OrderService | voidOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | voidOrder | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | voidOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | voidOrder | response | channel | object | yes | Where it came from.
OrderService | voidOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | voidOrder | response | venueId | string (uuid) | yes
OrderService | voidOrder | response | scopePath | string | yes
OrderService | voidOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | voidOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | voidOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | voidOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | voidOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | voidOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | voidOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | voidOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | voidOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | voidOrder | response | droppedPromotions[].name | string
OrderService | voidOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | voidOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | voidOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines | array of OrderLine | yes
OrderService | voidOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | voidOrder | response | lines[].variantId | string (uuid) | yes
OrderService | voidOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | voidOrder | response | lines[].performanceId | string (uuid)
OrderService | voidOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | voidOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | voidOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | voidOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | voidOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | voidOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | voidOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | voidOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | voidOrder | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | voidOrder | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | voidOrder | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | voidOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | voidOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | voidOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | voidOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].holderName | string |  | (nullable)
OrderService | voidOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | voidOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | voidOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | voidOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | voidOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | voidOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | voidOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | voidOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | voidOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | voidOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | voidOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | voidOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | voidOrder | response | payments | array of Payment
OrderService | voidOrder | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | voidOrder | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | voidOrder | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | voidOrder | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | voidOrder | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | voidOrder | response | payments[].id | string (uuid) | yes
OrderService | voidOrder | response | payments[].orderId | string (uuid) | yes
OrderService | voidOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | voidOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | voidOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | voidOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | voidOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | voidOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | voidOrder | response | payments[].providerName | string |  | (nullable)
OrderService | voidOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | voidOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | voidOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | voidOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | voidOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | voidOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | voidOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | voidOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | voidOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | voidOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | voidOrder | response | principalId | string (uuid)
OrderService | voidOrder | response | workstationId | string (uuid)
OrderService | voidOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | voidOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | voidOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | voidOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | voidOrder | response | createdAt | string (date-time) | yes
OrderService | voidOrder | response | recordedAt | string (date-time) | yes
OrderService | voidOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | voidOrder | param (path) | orderId | string (uuid) | yes
OrderService | voidOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | withdrawFromDepositBox | request | id | string (uuid) | yes | Client-generated UUIDv7 of the CashMovement this records.
OrderService | withdrawFromDepositBox | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | request | witnessPrincipalId | string (uuid) | yes | The cashier the cash came from.
OrderService | withdrawFromDepositBox | request | reason | WithdrawalReason: enum (banking, safeDrop, changeOrder, other) |  | Why a supervisor took cash out of a box.
OrderService | withdrawFromDepositBox | request | note | string |  | (max length 300)
OrderService | withdrawFromDepositBox | request | recordedAt | string (date-time) | yes
OrderService | withdrawFromDepositBox | request | witnessStepUp | object |  | The witnessing cashier's countersignature on this device (CHG-RUL-019): principalId is witnessPrincipalId, credential their PIN.
OrderService | withdrawFromDepositBox | request | witnessStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | withdrawFromDepositBox | request | witnessStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | withdrawFromDepositBox | request | witnessStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | withdrawFromDepositBox | response | id | string (uuid) |  | (read-only)
OrderService | withdrawFromDepositBox | response | cashierPrincipalId | string (uuid) | yes
OrderService | withdrawFromDepositBox | response | cashierName | string |  | (read-only)
OrderService | withdrawFromDepositBox | response | venueId | string (uuid) | yes
OrderService | withdrawFromDepositBox | response | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | withdrawFromDepositBox | response | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | withdrawFromDepositBox | response | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | withdrawFromDepositBox | response | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | openingDenominations | array of object |  | 5.8.3.
OrderService | withdrawFromDepositBox | response | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | withdrawFromDepositBox | response | openingDenominations[].count | integer | yes | (min 0)
OrderService | withdrawFromDepositBox | response | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | withdrawFromDepositBox | response | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | withdrawFromDepositBox | response | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not in the box's own currency. (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | expectedTotal | object |  | The figure the box's close count is measured against, filled when the box is counted. (nullable)
OrderService | withdrawFromDepositBox | response | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | variance | object |  | Counted minus expected; negative is short. (nullable)
OrderService | withdrawFromDepositBox | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | withdrawFromDepositBox | response | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | withdrawFromDepositBox | response | closedAt | string (date-time) |  | (nullable)
OrderService | withdrawFromDepositBox | response | recordedAt | string (date-time) |  | When the device made the write (R113; CHG-OFL-003): for an allocation, the same moment as allocatedAt, kept in recorded_at, the column every offline-written table carries for the sync to order replay…
OrderService | withdrawFromDepositBox | param (path) | boxId | string (uuid) | yes
OrderService | withdrawFromDepositBox | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | withdrawTransportTimetable | request | reason | string | yes | (min length 3; max length 500)
VenueOpsService | withdrawTransportTimetable | response | name | string | yes | (max length 120)
VenueOpsService | withdrawTransportTimetable | response | validFrom | string (date) | yes
VenueOpsService | withdrawTransportTimetable | response | validTo | string (date) |  | (nullable)
VenueOpsService | withdrawTransportTimetable | response | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | withdrawTransportTimetable | response | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | withdrawTransportTimetable | response | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | withdrawTransportTimetable | response | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | withdrawTransportTimetable | response | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | withdrawTransportTimetable | response | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | withdrawTransportTimetable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | withdrawTransportTimetable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | withdrawTransportTimetable | response | status | TransportTimetableStatus: enum (draft, published, superseded, withdrawn) | yes
VenueOpsService | withdrawTransportTimetable | response | publishedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | withdrawTransportTimetable | response | releasedThrough | string (date) |  | The last date whose departures have been generated. (read-only; nullable)
VenueOpsService | withdrawTransportTimetable | response | supersededById | string (uuid) |  | (read-only; nullable)
VenueOpsService | withdrawTransportTimetable | param (path) | timetableId | string (uuid) | yes
VenueOpsService | withdrawTransportTimetable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.

## Occupancy
Person | Backend and DevOps tasks | Points
Hrushikant Patkar | 390 | 1515
Pranay Shinde | 214 | 1256
Narayan Gaonkar | 239 | 1247
Deep Khanvilkar | 200 | 667
Sanket Keluskar | 118 | 376
Surendra | 48 | 250
Chinmay Patkar | 112 | 210
New full-stack developer 2 | 13 | 67
New full-stack developer 1 | 12 | 61
Pallavi Sawant | 13 | 39
Pradnya Yeram | 2 | 9
Chitrangi Mestry | 1 | 1
Kalpita Mejari | 1 | 1