## Read me
TICVAI backend build plan: first release (POS, Guest App web and mobile, White Labelling)
Services | 16
Operations (APIs) to build | 786
API schemas they send or return | 515
Tables | 538
Migrations | 34
Backend and DevOps tasks | 1363
Points | 5699
How to read it
Build plan | Every backend and DevOps task. Step 1 can start now; a task at step N waits for at least one task at step N-1. Wave is when the screens need it.
Migrations | One forward-only migration per database schema, in the order they run. Each only references tables created before it; keys that would point forward are added by the last migration.
Tables | Every table the first release reads or writes, plus the tables their foreign keys reach, with the migration that creates each.
Services / APIs / API schemas | What each service builds, every operation to build, and the request and response schemas those operations use, with where each is stored.
Assignees | From docs/active/team.json, balanced by points. Points are relative size (1, 2, 3, 5, 8), not hours.
Generated by tools/build-service-docs.py from the contracts, the delivery slice, the lineage and the DDL in backend/. Re-run it; do not edit this file.

## Build plan
Step | Wave | Key | Parent | Task | Points | Assignee | Service | Depends on | Description
1 | 1 | SETUP-CI | AM-FOUNDATION-SETUP | [DevOps] CI pipelines for the backend and frontend repositories | 3 | Hrushikant Patkar |  |  | CI pipelines for the backend and frontend repositories. In **ticvai-backend** and **ticvai-frontend** (the repositories the setup zip creates). CI is GitLab CI (since 20 October 2026, setup/dependencies.md and ADR-0007; it was GitHub Actions at audit R057). Done when: every merge request runs build, tests and lint in both, a red run blocks the merge, and a failing test on a branch shows in the MR. Tool versions per setup/dependencies.md.
1 | 1 | SETUP-ENV | AM-FOUNDATION-SETUP | [DevOps] Dev and staging environments (Terraform, ADR-0007 infra repository) | 5 | Hrushikant Patkar |  |  | Dev and staging environments (Terraform, ADR-0007 infra repository). In **ticvai-infra** (ADR-0007: one parameterised `cell` module, one tfvars per environment). The provider is Azure in a UAE region, Terraform `azurerm`, with each cell's secrets in its Azure Key Vault (decided 28 September, audit R057). Done when: `terraform plan` and `apply` build dev and staging from nothing, state is remote and locked, and the cell mapping and Azure region are written in the infra README.
2 | 1 | SETUP-CLIENTS | AM-FOUNDATION-SETUP | [DevOps] Publish @ticvai/api-client as a versioned package, generated from ticvai-contracts at each release tag | 3 | Pranay Shinde |  | SETUP-CI | Publish @ticvai/api-client as a versioned package, generated from ticvai-contracts at each release tag. In **ticvai-contracts**, the repository that holds the OpenAPI, the event schemas and the generated clients: `@ticvai/api-client` is generated from `contracts/` by one command at each release tag (the `v*` tag the contracts repository takes when the package releases), checked in GitLab CI, and published as a versioned package to the `ticvai-frontend` group's GitLab package registry (npm). Every app repository depends on it by exact version, **ticvai-guest-web first**, then each repository as its first screen is connected (ADR-0007 amendment; setup/dependencies.md, since 20 October 2026). No frontend repository generates, holds or hand-writes its own client, and there is no per-repository generator (ADAM CR-195). Every FE screen task's "connect to API" sub-task uses this package and waits for it. Done when: every in-release operation has a typed call in the published package, the contracts pipeline fails if the contracts change without a re-generate, ticvai-guest-web builds against the published version, and screen tickets stop stubbing calls.
2 | 1 | SETUP-DB | AM-FOUNDATION-SETUP | [DevOps] PostgreSQL (tenant and control databases) and a forward-only migration runner that applies the MIG epic in order | 5 | Pranay Shinde |  | SETUP-ENV | PostgreSQL (tenant and control databases) and a forward-only migration runner that applies the MIG epic in order. In **ticvai-backend**: `SqlMigrationRunner` (in the starter) applies `db/tenant` and `db/control` - the package's derived DDL - in file order and records each file with its checksum in `platform.schema_version`. The databases run on Azure in the UAE region, connection strings from the cell's Key Vault (audit R057). Done when: both databases exist in dev, the runner applies every MIG file to an empty database, and a second run applies nothing.
2 | 1 | SETUP-OBS | AM-FOUNDATION-SETUP | [DevOps] Logging and monitoring basics | 2 | Hrushikant Patkar |  | SETUP-ENV | Logging and monitoring basics. In **ticvai-infra** (Terraform, in the `cell` module) and **ticvai-backend**: the OpenTelemetry SDK (already referenced by the starter) in each of the five deployables of ADR-0055 (commerce, access, operations, workers and ticvai-ai), exporting traces, metrics and logs over OTLP to an OpenTelemetry Collector in the cell, which writes them to the cell's Log Analytics workspace in Azure UAE North (audit R057; nothing leaves the region). Logs are structured, never concatenated, and carry the trace and correlation ids; they never hold guest names, emails, phone numbers, document numbers, card data or biometric templates, only the opaque subject id (docs/architecture/observability.md; ADR-0009: PII-free by construction, not by filtering). Metrics are Prometheus-compatible. One alert rule to start with (the 5xx rate of each host) goes to an Azure Monitor action group that emails the on-call person (DevOps until a rota exists). Dev and staging only; production is built before the first live tenant. Done when: a request to a dev host can be followed from its log line to its trace by the correlation id; a deliberate 500 on a dev host raises an alert the on-call person receives within five minutes; and a search of a day's dev logs after the seeded test run finds no email address, phone number or card number.
2 | 1 | SETUP-HOSTS | AM-FOUNDATION-SETUP | [BE] Hosts for the deployables on .NET 10: commerce, access, operations and workers, each composing its modules | 3 | Hrushikant Patkar |  | SETUP-CI | Hosts for the deployables on .NET 10: commerce, access, operations and workers, each composing its modules. Builds: `adr ADR-0055`. In **ticvai-backend**, on .NET 10 LTS (decided 30 September; ADR-0055), in the clean-architecture solution the setup zip creates (`TICVAI.Domain`, `TICVAI.Contracts`, `TICVAI.Application`, `TICVAI.Infrastructure`, `TICVAI.Api`; repos/ticvai-docs/setup/backend-patterns.md 3.2). Four hosts: commerce (Identity, Tenancy, Catalogue, Order, Ledger, Wallet), access (Access), operations (F&B, Retail, Inventory, VenueOps, Marketing, WhiteLabel, Reporting, Platform, CrossRegion) and workers (the outbox relay, every module's event consumers, scheduled jobs). **A module is a folder, not an assembly**: `TICVAI.Application/Features/<Module>/` with its controllers in `TICVAI.Api`, so a host composes its modules by registering those folders' services and controllers (there is no `IModule` and no `Ticvai.Modules.*` project; r8 walk fix, CHG-R8WFC-008). ticvai-ai stays the Python service. Done when: each host starts locally with its modules registered and a health endpoint, CI builds one image per host, and moving a module to another host is a change of one registration.
2 | 1 | SETUP-QDRANT | AM-FOUNDATION-SETUP | [BE] Qdrant cluster in dev and staging: 3 nodes, TLS, snapshots, monitoring | 3 | Hrushikant Patkar |  | SETUP-ENV | Qdrant cluster in dev and staging: 3 nodes, TLS, snapshots, monitoring. Builds: `adr ADR-0049`, `adr ADR-0021`. In **ticvai-infra** (Terraform): a self-hosted 3-node Qdrant cluster in Azure UAE North for staging (ADR-0049), pinned to 1.16 or later, with TLS, JWT RBAC on and the signing key in the cell's Key Vault, snapshot storage in the UAE, and monitoring and alerts on node health, disk and latency. Check Qdrant Hybrid Cloud on our own AKS as an alternative before building. Done when: the cluster survives the loss of one node, a snapshot of a test collection restores into a fresh cluster, and a request without a valid token is refused. **Where the install lives** (the lead, 20 October 2026, r8 cause FOUNDATION-AI-C22, option A): the cluster bootstrap is a second Terraform stage in ticvai-infra, run after the cell module against its AKS cluster with the helm and kubernetes providers; it installs cert-manager (certificates from Let's Encrypt), the ingress and the official Qdrant chart on the qdrant node pool, with TLS and JWT RBAC on. The providers, the chart and cert-manager are on the approved list (setup/dependencies.md). Dev has no cluster (laptops, docker compose); this ticket's cluster is staging's (FOUNDATION-AI-C52).
3 | 1 | SETUP-MOCK-API | AM-FOUNDATION-SETUP | [DevOps] Frontend mock API: generated from the published contracts, with the prototypes' sample venues as fixtures | 3 | Pranay Shinde |  | SETUP-CLIENTS | Frontend mock API: generated from the published contracts, with the prototypes' sample venues as fixtures. Builds: `file docs/active/seed-data-proposal.md`. In **ticvai-contracts**, published beside @ticvai/api-client. Why: the lead, Chinmay, 21 October 2026: "I wanna get all of those changes out now.." (CHG-R9UI-001, CHG-R9UI-002); the mock server was the last clause of SETUP-SEED (#27684, Block A week 5) while the screens it serves were built from week 2, so a screen opened in its error state (WEB-007, 21 October). The mock is generated from the same published contracts as the typed client (Prism from the OpenAPI, or MSW handlers generated from it: one command, checked in GitLab CI, published as @ticvai/mock-api on each contracts tag, so it never drifts from the client), every in-release operation answering with its contract's shapes and its listed errors on request (a header or query switch per operation: an error, a delay for loading, an empty list, offline), and fixtures that mirror the client-approved prototypes' sample data: the venues Summit Peaks (theme park), Coastal Aqua (water park), Union Arena (stadium, its fixture and seat map), Grand Playhouse (theatre) and Saffron Table (dining) with their products, prices, performances and seat availability as the guest prototypes show them, and a till with its operators, catalogue and float as the POS terminal shows it, beside SETUP-SEED's reference fixture (two brands, three regions, AED and OMR; docs/active/seed-data-proposal.md). SETUP-SEED (Ready for QA on 21 October 2026) may already serve a mock: start from what it built and make it this. Every frontend screen task whose build sub-task runs against the mock API follows this one. Done when: each frontend repository runs its screens against @ticvai/mock-api with one command; every in-release operation answers with its contract's shape and can be switched to each listed error, a delay, an empty list and offline; the contracts pipeline fails if a contract changes without a new mock; WEB-007 opens on Union Arena's seat map with the mock and no backend.
3 | 1 | MIG-BASELINE | AM-FOUNDATION-DATABASE | [DB] Migration V0001__baseline.sql: schemas, extensions, migration register, RLS helper functions and the monthly partition helpers (ADR-0056) | 3 | Hrushikant Patkar |  | SETUP-DB | Tables: platform.schema_version. Source DDL: backend/tenant/000-schemas.sql, 001-extensions.sql, 002-migration-register.sql, the helper functions at the top of 920-row-level-security.sql and 930-partitioning.sql; the control database's own 000-002. It creates what every later migration assumes (14 October 2026, CHG-TKT-011; audit R056): the schemas (000-schemas.sql), the ltree extension with btree_gist and pgcrypto (001-extensions.sql), the migration register, and the row-level security helpers. Everything else in the MIG epic runs after this. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. The baseline file named in the subject is one you write in our repository; the package keeps no baseline file of its own. It creates the helper functions every later migration calls, copied as they are from the top of 920-row-level-security.sql: platform.current_scope_paths, platform.in_scope, platform.rls_policy_name, platform.apply_scope_rls, platform.apply_shared_scope_rls, platform.venue_in_scope, platform.apply_venue_rls, platform.apply_parent_rls, platform.tenant_root_in_scope, platform.subject_in_scope, platform.apply_tenant_rls, platform.apply_subject_rls; from the top of 930-partitioning.sql: platform.uuidv7_floor, platform.ensure_month_partition, platform.ensure_month_partitions; from backend/tenant/V0102__after_r1_20261013.sql (created by no other file): platform.apply_append_audit_rls; from backend/tenant/V0104__after_r1_20261015.sql (created by no other file): platform.drop_rls_policies, platform.grant_holder, platform.above_scope, platform.apply_split_rls, platform.apply_read_beneath_rls, platform.apply_grant_holder_read_rls, platform.apply_grant_holder_subject_read_rls, platform.apply_parent_split_rls; from backend/tenant/V0105__after_r1_20261018.sql (created by no other file): platform.visible_parent_ids, platform.visible_parent_ids_setup, platform.apply_parent_across_rls, platform.apply_parent_split_across_rls; from backend/tenant/V0108__after_r1_20261020.sql (created by no other file): platform.own_row, platform.apply_own_row_rls, platform.signed_in; from backend/tenant/V0116__after_r1_20261026.sql (created by no other file): platform.apply_append_audit_read_rls, identity.end_principal_sessions; from backend/tenant/V0118__after_r1_20261029.sql (created by no other file): platform.apply_grant_holder_subject_rls (the row-level security of each schema migration calls the platform.apply_* functions, so they come first). Start the file with `SET check_function_bodies = off;`: the SQL-language helpers read platform.scope, which the platform migration creates later, and PostgreSQL checks a function's body against the tables that exist when it is created unless that setting is off (the body is checked when the function first runs instead). Done when the migration for `platform.schema_version` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 1 | MIG-CONTROL | AM-FOUNDATION-DATABASE | [DB] Migration V0002__control.sql: control (19 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE | Control database. Tables: control.api_client, control.api_client_secret, control.api_licence, control.api_version, control.cell_tenant, control.developer_account, control.developer_member, control.integration_listing, control.licence_add_on, control.licence_add_on_limit, control.outbox_relay, control.partner, control.partner_agreement, control.partner_application, control.partner_change_request, control.production_access_request, control.seo_metadata, control.tenant, control.url_redirect. Source DDL: backend/control/010-control.sql and backend/control/V0116__after_r1_20261026.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/control/V0104__after_r1_20261015.sql (control.api_client: column status_reason; control.api_version: column changes; control.tenant: index tenant_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.api_client: foreign key api_client_developer_id_fkey, foreign key api_limit_client_id_fkey (from control.api_limit), foreign key webhook_subscription_client_id_fkey (from control.webhook_subscription); control.cell_tenant: rename column pinned_instance to is_instance_pinned, foreign key cell_tenant_cell_id_fkey, foreign key cell_tenant_instance_id_fkey, foreign key cell_tenant_tenant_id_fkey; control.developer_account: foreign key api_client_developer_id_fkey (from control.api_client), foreign key integration_listing_developer_id_fkey (from control.integration_listing), foreign key production_access_request_developer_id_fkey (from control.production_access_request); control.integration_listing: foreign key integration_listing_developer_id_fkey; control.partner: foreign key partner_allocation_partner_id_fkey (from control.partner_allocation), foreign key partner_billing_profile_partner_id_fkey (from control.partner_billing_profile), foreign key partner_capability_grant_partner_id_fkey (from control.partner_capability_grant), foreign key partner_case_partner_id_fkey (from control.partner_case), foreign key partner_change_request_partner_id_fkey (from control.partner_change_request), foreign key partner_commercial_exception_partner_id_fkey (from control.partner_commercial_exception), foreign key partner_commission_line_partner_id_fkey (from control.partner_commission_line), foreign key partner_commission_rule_partner_id_fkey (from control.partner_commission_rule), foreign key partner_contact_partner_id_fkey (from control.partner_contact), foreign key partner_credit_profile_partner_id_fkey (from control.partner_credit_profile), foreign key partner_distribution_right_partner_id_fkey (from control.partner_distribution_right), foreign key partner_document_partner_id_fkey (from control.partner_document), foreign key partner_rate_partner_id_fkey (from control.partner_rate), foreign key partner_reconciliation_exception_partner_id_fkey (from control.partner_reconciliation_exception), foreign key partner_scope_assignment_partner_id_fkey (from control.partner_scope_assignment), foreign key partner_security_partner_id_fkey (from control.partner_security), foreign key partner_settlement_batch_partner_id_fkey (from control.partner_settlement_batch), foreign key partner_status_history_partner_id_fkey (from control.partner_status_history); control.partner_agreement: rename column renewal_requires_approval to requires_renewal_approval, foreign key partner_allocation_agreement_id_fkey (from control.partner_allocation), foreign key partner_billing_profile_agreement_id_fkey (from control.partner_billing_profile), foreign key partner_commission_line_agreement_id_fkey (from control.partner_commission_line), foreign key partner_commission_rule_agreement_id_fkey (from control.partner_commission_rule), foreign key partner_credit_profile_agreement_id_fkey (from control.partner_credit_profile), foreign key partner_rate_agreement_id_fkey (from control.partner_rate); control.partner_change_request: foreign key partner_change_request_partner_id_fkey, drop index partner_change_request_order_id_idx; control.production_access_request: foreign key production_access_request_developer_id_fkey; control.seo_metadata: rename column no_index to is_excluded_from_index; control.tenant: foreign key cell_tenant_tenant_id_fkey (from control.cell_tenant), foreign key credit_note_tenant_id_fkey (from control.credit_note), foreign key invoice_tenant_id_fkey (from control.invoice), foreign key migration_run_tenant_tenant_id_fkey (from control.migration_run_tenant), foreign key rollout_tenant_tenant_id_fkey (from control.rollout_tenant), foreign key upgrade_schedule_tenant_id_fkey (from control.upgrade_schedule)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0108__after_r1_20261020.sql (control.cell_tenant: column root_scope_path; control.licence_add_on: DROP CONSTRAINT IF EXISTS licence_add_on_module_key_chk, constraint licence_add_on_module_key_chk; control.tenant: column plan_version, DROP CONSTRAINT IF EXISTS tenant_plan_id_when_chk; VALIDATE CONSTRAINT tenant_plan_id_when_chk; DROP CONSTRAINT IF EXISTS tenant_plan_version_when_chk; VALIDATE CONSTRAINT tenant_plan_version_when_chk, constraints tenant_plan_id_when_chk and tenant_plan_version_when_chk, index tenant_plan_id_plan_version_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0109__names_after_r1_20261020.sql (the names the contracts use: control.tenant: foreign key tenant_plan_id_fkey, foreign key tenant_subscription_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0112__after_r1_20261021.sql (control.licence_add_on: columns removed_at, removed_by_principal_id and removal_reason, index licence_add_on_removed_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.developer_account: index developer_account_contact_email_uniq; control.licence_add_on: column currency_code); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Leave out the key cell_tenant_cell_id_fkey** (control.cell_tenant to control.cell): MIG-CONTROL-6 creates control.cell later and adds it. **Leave out the key cell_tenant_instance_id_fkey** (control.cell_tenant to control.cell_instance): MIG-CONTROL-8 creates control.cell_instance later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `control.cell_tenant.root_scope_path`; column changed `control.url_redirect.status_code`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.api_client`, `control.api_client_secret`, `control.api_licence`, `control.api_version`, `control.cell_tenant`, `control.developer_account`, `control.developer_member`, `control.integration_listing` and 11 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 1 | MIG-KERNEL | AM-FOUNDATION-DATABASE | [DB] Migration V0003__kernel.sql: kernel (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE | Tenant database. Tables: kernel.inbox. Source DDL: backend/tenant/010-kernel.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: kernel.inbox: drop index inbox_event_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `kernel.inbox` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 1 | MIG-PARTITIONS | AM-FOUNDATION-DATABASE | [DB] Monthly partitions: create three months ahead, detach what retention has expired | 3 | Hrushikant Patkar |  | MIG-BASELINE SETUP-HOSTS | Monthly partitions: create three months ahead, detach what retention has expired. Builds: `table access.scan_event`, `table kernel.inbox`, `table ledger.journal_line`, `table marketing.message_dispatch`, `table platform.audit_record`, `table platform.outbox`, `adr ADR-0044`, `adr ADR-0047`, `adr ADR-0056`. A job in the workers host that keeps monthly range partitions three months ahead on the time-partitioned tables (access.scan_event, platform.outbox, platform.dead_letter, platform.audit_record, ledger.journal_line, marketing.message_dispatch, kernel.inbox; ADR-0056) in every tenant database, and detaches and archives partitions past their retention (ADR-0047). Source DDL: backend/tenant/930-partitioning.sql (the monthly partitions and default partitions of the time-partitioned tables; its helper functions platform.uuidv7_floor, platform.ensure_month_partition and platform.ensure_month_partitions are already in the baseline, MIG-BASELINE). Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when: a new tenant database has partitions three months ahead, a run with the clock moved forward creates the next month, and an expired partition is detached, not deleted row by row. **Order** (R8 blocker FOUNDATION-AI-C31, CHG-R8MIG-020): it needs the first-release migrations of the tables it partitions (MIG-KERNEL, MIG-PLATFORM, MIG-LEDGER, MIG-ACCESS, MIG-MARKETING) applied first, and creates partitions only for the partitioned tables that exist when it runs, so platform.dead_letter, which MIG-PLATFORM-4 creates later, gets its partitions on the first run after that migration; it is a job in the workers host, not a migration file.
4 | 1 | MIG-PII | AM-FOUNDATION-DATABASE | [DB] Migration V0007__pii.sql: pii (5 tables) | 3 | Hrushikant Patkar | IdentityService | MIG-BASELINE | Tenant database. Tables: pii.subject, pii.subject_biometric, pii.subject_contact, pii.subject_document, pii.subject_identity. Source DDL: backend/tenant/010-pii.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (pii.subject: row-level security apply_grant_holder_read_rls; pii.subject_contact: row-level security apply_grant_holder_subject_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (pii.subject_biometric: row-level security apply_parent_across_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: pii.subject: foreign key face_reenrolment_attempt_subject_id_fkey (from access.face_reenrolment_attempt), foreign key identity_lock_subject_id_fkey (from access.identity_lock), foreign key guest_credential_subject_id_fkey (from identity.guest_credential), foreign key guest_identity_verification_subject_id_fkey (from identity.guest_identity_verification), foreign key communication_policy_decision_subject_id_fkey (from marketing.communication_policy_decision), foreign key guest_note_subject_id_fkey (from marketing.guest_note), foreign key journey_enrollment_subject_id_fkey (from marketing.journey_enrollment), foreign key privacy_action_subject_id_fkey (from marketing.privacy_action), foreign key privacy_request_subject_id_fkey (from marketing.privacy_request), foreign key referral_referrer_subject_id_fkey (from marketing.referral), foreign key subscription_subject_id_fkey (from marketing.subscription), foreign key waiver_requirement_participant_subject_id_fkey (from marketing.waiver_requirement), foreign key group_booking_leader_subject_id_fkey (from orders.group_booking), foreign key guest_credit_account_subject_id_fkey (from orders.guest_credit_account), foreign key resale_listing_seller_subject_id_fkey (from orders.resale_listing), foreign key resale_settlement_seller_subject_id_fkey (from orders.resale_settlement), foreign key subject_erasure_request_id_fkey, foreign key performance_participant_subject_id_fkey (from resources.performance_participant), foreign key shared_wallet_member_subject_id_fkey (from wallet.shared_wallet_member), foreign key wallet_transaction_subject_id_fkey (from wallet.wallet_transaction)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (pii.subject: row-level security apply_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0115__names_after_r1_20261022.sql (the names the contracts use: pii.subject: change foreign key visit_plan_subject_id_fkey (from venuemap.visit_plan)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Create the types the copied DDL names first** (ADAM CR-001): the frozen file types these columns with enum types no package file creates, so before its CREATE TABLE write `CREATE TYPE pii.subject_kind AS ENUM ('guest', 'employee', 'contact', 'applicant');` (pii.subject.kind). The values are the contracts' (handoff/schema-reference.json); a later forward migration turns the column into text with the same CHECK. **Create the types the copied DDL names first** (ADAM CR-001): the frozen file types these columns with enum types no package file creates, so before its CREATE TABLE write `CREATE TYPE pii.contact_kind AS ENUM ('email', 'mobile', 'phone', 'whatsapp', 'postal');` (pii.subject_contact.kind). The values are the contracts' (handoff/schema-reference.json); a later forward migration turns the column into text with the same CHECK. **pii.subject_biometric's row-level security waits for its parent**: its policy reads access.entitlement, which MIG-ACCESS creates later, so leave out its `platform.apply_parent_rls` call here; MIG-ACCESS applies it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `pii.subject.kind`; column changed `pii.subject_contact.kind`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `pii.subject`, `pii.subject_biometric`, `pii.subject_contact`, `pii.subject_document`, `pii.subject_identity` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 1 | MIG-TENANCY | AM-FOUNDATION-DATABASE | [DB] Migration V0004__tenancy.sql: tenancy (5 tables) | 3 | Hrushikant Patkar | TenancyService | MIG-BASELINE | Tenant database. Tables: tenancy.device_assignment, tenancy.device_audit, tenancy.device_firmware, tenancy.device_rollout, tenancy.device_telemetry. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (tenancy.device_rollout: column waves); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: tenancy.device_firmware: foreign key device_rollout_firmware_id_fkey (from tenancy.device_rollout); tenancy.device_rollout: foreign key device_rollout_firmware_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (tenancy.device_assignment: index device_assignment_device_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: tenancy.device_assignment: foreign key device_assignment_device_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (tenancy.device_firmware: row-level security apply_read_beneath_rls; tenancy.device_telemetry: columns sync_backlog and error_count); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (tenancy.device_firmware: index device_firmware_device_kind_version_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0119__names_after_r1_20261029.sql (the names the contracts use: tenancy.device_assignment: drop index device_assignment_device_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `tenancy.device_assignment.device_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `tenancy.device_assignment`, `tenancy.device_audit`, `tenancy.device_firmware`, `tenancy.device_rollout`, `tenancy.device_telemetry` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 1 | MIG-TRANSPORT | AM-FOUNDATION-DATABASE | [DB] Migration V0006__transport.sql: transport (12 tables) | 8 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE | Tenant database. Tables: transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.favourite_route, transport.network_import, transport.pass_type, transport.route, transport.route_stop, transport.station, transport.timetable, transport.timetable_run. Source DDL: backend/tenant/010-transport.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (transport.departure: row-level security apply_parent_rls; transport.fare_matrix_cell: row-level security apply_parent_rls; transport.fare_passenger_type: row-level security apply_parent_rls; transport.fare_table: row-level security apply_parent_rls; transport.network_import: column findings; transport.pass_type: index pass_type_venue_id_code_uniq; transport.route: column status_reason, index route_venue_id_code_uniq; transport.station: index station_venue_id_code_uniq; transport.timetable: row-level security apply_parent_rls; transport.timetable_run: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: transport.departure: foreign key departure_performance_id_fkey, foreign key departure_route_id_fkey, foreign key departure_timetable_id_fkey; transport.fare_matrix_cell: foreign key fare_matrix_cell_from_station_id_fkey, foreign key fare_matrix_cell_to_station_id_fkey; transport.fare_table: foreign key fare_table_route_id_fkey; transport.favourite_route: foreign key favourite_route_venue_id_fkey, foreign key favourite_route_venue_id_from_station_id_fkey, foreign key favourite_route_venue_id_to_station_id_fkey; transport.network_import: foreign key network_import_venue_id_fkey; transport.pass_type: foreign key pass_type_venue_id_fkey; transport.route: foreign key departure_route_id_fkey (from transport.departure), foreign key fare_table_route_id_fkey (from transport.fare_table), foreign key route_venue_id_fkey, foreign key timetable_route_id_fkey (from transport.timetable); transport.route_stop: foreign key route_stop_station_id_fkey; transport.station: foreign key fare_matrix_cell_from_station_id_fkey (from transport.fare_matrix_cell), foreign key fare_matrix_cell_to_station_id_fkey (from transport.fare_matrix_cell), foreign key favourite_route_venue_id_from_station_id_fkey (from transport.favourite_route), foreign key favourite_route_venue_id_to_station_id_fkey (from transport.favourite_route), foreign key route_stop_station_id_fkey (from transport.route_stop), foreign key station_venue_id_fkey; transport.timetable: foreign key departure_timetable_id_fkey (from transport.departure), foreign key timetable_route_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): constraint added `transport.station station_venue_id_id_uniq`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `transport.departure`, `transport.fare_matrix_cell`, `transport.fare_passenger_type`, `transport.fare_table`, `transport.favourite_route`, `transport.network_import`, `transport.pass_type`, `transport.route` and 4 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 1 | DB-READ-VIEWS | AM-FOUNDATION-DATABASE | [BE] Published read views for cross-module reads, generated from the lineage | 5 | Hrushikant Patkar |  | MIG-BASELINE | Published read views for cross-module reads, generated from the lineage. Builds: `adr ADR-0055`, `adr ADR-0016`. A deriver reads handoff/api-data-lineage.json and generates, per owning module, the views other modules may read (894 cross-schema reads on 30 September; ADR-0055), applied by the migrations. Done when: every cross-schema read in the Block A slice goes through a published view, the views regenerate with one command, each exposing exactly the union of its readers' `readColumns` (every pii view a column list, never all columns), and a raw cross-schema read is reported by the lineage check. Spec (4 October, CHG-FXP-005), ADR-0055 rule 2: another module reads a schema only through views its owner publishes (or the owner's in-process query interface), never raw tables; the owner is the schema's module in handoff/service-decomposition.json. Default for the shape: one view per (reader module, owned table) pair the lineage actually reads, in the owner's schema, named `<table>_for_<reader module>`, exposing only the columns the reader's operations read, with SELECT granted to the reader's deployable role (DB-ROLES). The columns are generated, not chosen (14 October, ADAM CR-004, CHG-LIN-001): each lineage entry carries `readColumns` ({table: [columns]}, derived by tools/derive-read-columns.py from the response schemas, the parameters, the join keys and docs/active/read-columns-override.yaml), and a view's columns are the union of `readColumns[table]` over the reader module's operations that read the table. A read with no list keeps every column, except over pii.*: every cross-module read of a pii table has a list (check-read-columns fails one without), so a pii view is always narrow and is never built over all columns. Reads routed `analytical` go to the reporting replica, never the primary (ADR-0016).
4 | 1 | DB-ROLES | AM-FOUNDATION-DATABASE | [BE] One Postgres role per deployable; the AI role read-only | 2 | Hrushikant Patkar |  | MIG-BASELINE | One Postgres role per deployable; the AI role read-only. Builds: `adr ADR-0055`, `adr ADR-0020`. In ticvai-backend, created by the baseline migration (MIG-BASELINE), one PostgreSQL login role per deployable of ADR-0055: commerce, access, operations, workers and ticvai_ai, each reading its password or token from the cell's Key Vault. Each role gets USAGE and SELECT, INSERT, UPDATE, DELETE on the schemas its modules own (the schema owners in handoff/service-decomposition.json; workers runs every module's consumers, the outbox relay and the scheduled jobs, so it gets the schemas those touch), SELECT on the published read views of DB-READ-VIEWS, and nothing else: no CREATE, no ownership, no BYPASSRLS, so FORCE row-level security applies to every host. ticvai_ai writes only the ai schema (and ai.inbox; ADR-0058) and is read-only on the transactional schemas (ADR-0020). The tables are owned by a separate migration role that only SqlMigrationRunner uses. Done when: each host connects with its own role from Key Vault; an INSERT from the ticvai_ai role into a transactional table, and from the commerce role into an operations schema (fnb), are each refused by PostgreSQL; no host role has BYPASSRLS or owns a table (a query on pg_roles and pg_tables in CI shows it); and a host role with no scope set on its session reads no rows from a table under FORCE row-level security. The schemas each role owns (handoff/service-decomposition.json under ADR-0055's five deployables, 4 October, CHG-FXP-005): commerce: identity, pii, platform, workforce, approvals, accreditation, tenancy, kernel, catalogue, pricing, promotions, seating, orders, payments, ledger, wallet; access: access; operations: inventory, fnb, retail, marketing, queue, maintenance, resources, venuemap, assets, games, rental, transport, subscription, whitelabel, reporting, sync (and control, in the control database, ADR-0039); ticvai_ai: ai (and ai.inbox), read-only on the rest; workers: the schemas its consumers, the outbox relay and the scheduled jobs write, which is every module's.
5 | 1 | MIG-GAMES | AM-FOUNDATION-DATABASE | [DB] Migration V0008__games.sql: games (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PII | Tenant database. Tables: games.card, games.credit_ledger. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (games.credit_ledger: columns play_id, reader_id, sequence, credits_used, bonus_credits_used, points_awarded, credits_after, points_after, is_divergence, reconciled_at, recorded_at and synced_at, index credit_ledger_play_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `games.credit_ledger.play_id`; not null `games.credit_ledger.reader_id`; not null `games.credit_ledger.credits_used`; not null `games.credit_ledger.points_awarded`; not null `games.credit_ledger.credits_after`; not null `games.credit_ledger.points_after`; not null `games.credit_ledger.is_divergence`; not null `games.credit_ledger.recorded_at`; not null `games.credit_ledger.synced_at`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `games.card`, `games.credit_ledger` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
5 | 1 | MIG-IDENTITY | AM-FOUNDATION-DATABASE | [DB] Migration V0009__identity.sql: identity (21 tables) | 8 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-PII | Tenant database. Tables: identity.capability_template, identity.delegated_access, identity.guest_credential, identity.mfa_challenge, identity.mfa_method, identity.mfa_recovery_code, identity.otp_challenge, identity.password_policy, identity.platform_staff_grant, identity.principal, identity.principal_credential, identity.principal_credential_history, identity.redirect_host, identity.refresh_token, identity.role, identity.role_permission, identity.segregation_rule, identity.session, identity.sso_provider, identity.subject_data_export, identity.subject_holding. Source DDL: backend/tenant/010-identity.sql and backend/tenant/V0104__after_r1_20261015.sql and backend/tenant/V0116__after_r1_20261026.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (identity.capability_template: row-level security apply_read_beneath_rls; identity.mfa_challenge: columns method_id, action, session_id, code_hash, status, failed_attempts, expires_at, verified_at, consumed_at and voided_at, indexes mfa_challenge_method_id_idx and mfa_challenge_session_id_idx; identity.mfa_recovery_code: columns code_hash, issued_at and used_at; identity.otp_challenge: columns identifier_hash, channel, purpose, code_hash, failed_attempts, attempt_limit, expires_at, resend_after, consumed_at and invalidated_at; identity.password_policy: columns pin_length, pin_reuse_prevention and pin_lockout_after_attempts, row-level security apply_read_beneath_rls; identity.principal: columns must_change_credential and sso_provider_id, constraint principal_sso_provider_id_fkey, indexes principal_sso_provider_id_idx and principal_username_uniq, row-level security apply_grant_holder_read_rls; identity.principal_credential: columns method, credential_hash, set_at, failed_attempts and locked_until, index principal_credential_principal_id_method_uniq; identity.role: index role_code_uniq, row-level security apply_grant_holder_read_rls; identity.role_permission: row-level security apply_parent_split_rls; identity.segregation_rule: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: identity.guest_credential: foreign key guest_credential_subject_id_fkey; identity.password_policy: rename column force_change_on_first_logon to forces_change_on_first_logon; identity.platform_staff_grant: foreign key platform_staff_grant_operator_principal_id_fkey; identity.principal: foreign key configuration_change_changed_by_principal_id_fkey (from access.configuration_change), foreign key gate_mode_change_changed_by_principal_id_fkey (from access.gate_mode_change), foreign key podium_shift_operator_principal_id_fkey (from access.podium_shift), foreign key workflow_intervention_actor_principal_id_fkey (from approvals.workflow_intervention), foreign key change_request_requested_by_principal_id_fkey (from catalogue.change_request), foreign key pricing_recommendation_decision_decided_by_principal_id_fkey (from catalogue.pricing_recommendation_decision), foreign key product_version_published_by_principal_id_fkey (from catalogue.product_version), foreign key rollback_action_requested_by_principal_id_fkey (from catalogue.rollback_action), foreign key platform_staff_grant_operator_principal_id_fkey (from identity.platform_staff_grant), foreign key refresh_token_principal_id_fkey (from identity.refresh_token), foreign key fiscal_period_event_principal_id_fkey (from ledger.fiscal_period_event), foreign key incident_history_principal_id_fkey (from maintenance.incident_history), foreign key agent_service_profile_principal_id_fkey (from marketing.agent_service_profile), foreign key quality_evaluation_agent_principal_id_fkey (from marketing.quality_evaluation), foreign key invitation_offered_by_principal_id_fkey (from orders.invitation), foreign key pos_shift_approval_principal_id_fkey (from orders.pos_shift_approval), foreign key entry_overridden_by_principal_id_fkey (from queue.entry), foreign key natural_language_query_asked_by_principal_id_fkey (from reporting.natural_language_query), foreign key resource_request_raised_by_principal_id_fkey (from resources.resource_request), foreign key membership_product_history_changed_by_principal_id_fkey (from subscription.membership_product_history), foreign key map_version_published_by_principal_id_fkey (from venuemap.map_version), foreign key attendance_amendment_amended_by_principal_id_fkey (from workforce.attendance_amendment), foreign key leave_request_principal_id_fkey (from workforce.leave_request), foreign key shift_swap_from_principal_id_fkey (from workforce.shift_swap), foreign key shift_swap_to_principal_id_fkey (from workforce.shift_swap), foreign key staff_conversation_created_by_principal_id_fkey (from workforce.staff_conversation), foreign key staff_conversation_participant_principal_id_fkey (from workforce.staff_conversation_participant), foreign key staff_message_sender_principal_id_fkey (from workforce.staff_message); identity.refresh_token: foreign key refresh_token_principal_id_fkey; identity.segregation_rule: rename column scope_sensitive to is_scope_sensitive); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (identity.delegated_access: columns granted_by_kind, granted_by_principal_id, granted_by_subject_id and permission, DROP CONSTRAINT IF EXISTS delegated_access_granted_by_principal_id_when_chk; VALIDATE CONSTRAINT delegated_access_granted_by_principal_id_when_chk; DROP CONSTRAINT IF EXISTS delegated_access_granted_by_subject_id_when_chk; VALIDATE CONSTRAINT delegated_access_granted_by_subject_id_when_chk; DROP CONSTRAINT IF EXISTS delegated_access_permission_role_id_one_chk; VALIDATE CONSTRAINT delegated_access_permission_role_id_one_chk, constraints delegated_access_granted_by_principal_id_when_chk, delegated_access_granted_by_subject_id_when_chk, delegated_access_permission_role_id_one_chk and delegated_access_granted_by_subject_id_fkey, index delegated_access_granted_by_subject_id_idx, row-level security apply_split_rls; identity.mfa_challenge: columns principal_id and subject_id, DROP CONSTRAINT IF EXISTS mfa_challenge_principal_id_subject_id_one_chk; VALIDATE CONSTRAINT mfa_challenge_principal_id_subject_id_one_chk, constraints mfa_challenge_principal_id_subject_id_one_chk and mfa_challenge_subject_id_fkey, index mfa_challenge_subject_id_idx, row-level security apply_own_row_rls; identity.mfa_method: columns subject_id, secret, destination and pending_expires_at, DROP CONSTRAINT IF EXISTS mfa_method_principal_id_subject_id_one_chk; VALIDATE CONSTRAINT mfa_method_principal_id_subject_id_one_chk, constraints mfa_method_principal_id_subject_id_one_chk and mfa_method_subject_id_fkey, index mfa_method_subject_id_idx, row-level security apply_own_row_rls; identity.mfa_recovery_code: column subject_id, DROP CONSTRAINT IF EXISTS mfa_recovery_code_principal_id_subject_id_one_chk; VALIDATE CONSTRAINT mfa_recovery_code_principal_id_subject_id_one_chk, constraints mfa_recovery_code_principal_id_subject_id_one_chk and mfa_recovery_code_subject_id_fkey, index mfa_recovery_code_subject_id_idx, row-level security apply_own_row_rls; identity.otp_challenge: column subject_id; identity.password_policy: columns access_token_minutes, refresh_token_hours and session_max_hours; identity.principal: row-level security apply_grant_holder_read_rls; identity.principal_credential: row-level security apply_split_rls; identity.principal_credential_history: row-level security apply_parent_split_rls; identity.role_permission: DROP CONSTRAINT IF EXISTS role_permission_permission_chk; VALIDATE CONSTRAINT role_permission_permission_chk, constraint role_permission_permission_chk; identity.session: columns ended_at, ended_by_principal_id, end_reason and working_venue_id; identity.sso_provider: columns username_claim, display_name_claim, groups_claim, default_home_scope_id and allowed_redirect_uris, constraint sso_provider_default_home_scope_id_fkey, index sso_provider_default_home_scope_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: identity.platform_staff_grant: drop index platform_staff_grant_operator_principal_id_idx, drop foreign key platform_staff_grant_operator_principal_id_fkey; identity.principal: drop foreign key platform_staff_grant_operator_principal_id_fkey (from identity.platform_staff_grant)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (identity.delegated_access: DROP CONSTRAINT IF EXISTS delegated_access_delegation_kind_chk; VALIDATE CONSTRAINT delegated_access_delegation_kind_chk; DROP CONSTRAINT IF EXISTS delegated_access_revoked_by_subject_id_when_chk; VALIDATE CONSTRAINT delegated_access_revoked_by_subject_id_when_chk, constraints delegated_access_delegation_kind_chk, delegated_access_revoked_by_subject_id_when_chk and delegated_access_revoked_by_subject_id_fkey, columns revoked_by_kind and revoked_by_subject_id, index delegated_access_revoked_by_subject_id_idx; identity.refresh_token: columns principal_id and subject_id, DROP CONSTRAINT IF EXISTS refresh_token_principal_id_subject_id_one_chk; VALIDATE CONSTRAINT refresh_token_principal_id_subject_id_one_chk, constraints refresh_token_principal_id_subject_id_one_chk and refresh_token_subject_id_fkey, index refresh_token_subject_id_idx, row-level security apply_subject_rls; identity.role_permission: DROP CONSTRAINT IF EXISTS role_permission_permission_chk; VALIDATE CONSTRAINT role_permission_permission_chk, constraint role_permission_permission_chk; identity.session: DROP CONSTRAINT IF EXISTS session_ended_at_null_chk; VALIDATE CONSTRAINT session_ended_at_null_chk, constraint session_ended_at_null_chk; identity.subject_holding: columns order_number and verified_contact_ref); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `identity.mfa_challenge.action`; not null `identity.mfa_challenge.status`; not null `identity.mfa_challenge.expires_at`; not null `identity.mfa_recovery_code.code_hash`; not null `identity.mfa_recovery_code.issued_at`; not null `identity.otp_challenge.identifier_hash`; not null `identity.otp_challenge.channel`; not null `identity.otp_challenge.purpose`; not null `identity.otp_challenge.code_hash`; not null `identity.otp_challenge.attempt_limit`; not null `identity.otp_challenge.expires_at`; not null `identity.principal_credential.principal_id`; not null `identity.principal_credential.method`; not null `identity.principal_credential.credential_hash`; not null `identity.principal_credential.set_at`; column dropped `identity.role.principal_count`; column dropped `identity.role.grant_count`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `identity.capability_template`, `identity.delegated_access`, `identity.guest_credential`, `identity.mfa_challenge`, `identity.mfa_method`, `identity.mfa_recovery_code`, `identity.otp_challenge`, `identity.password_policy` and 13 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
5 | 1 | MIG-SUBSCRIPTION | AM-FOUNDATION-DATABASE | [DB] Migration V0005__subscription.sql: subscription (5 tables) | 3 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL | Control database. Tables: control.contract, control.module_listing, control.plan, control.plan_limit, control.plan_module. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/control/V0109__names_after_r1_20261020.sql (the names the contracts use: control.contract: foreign key tenant_subscription_id_fkey (from control.tenant); control.plan: foreign key tenant_plan_id_fkey (from control.tenant)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.contract: columns issuing_legal_entity and currency_code; control.module_listing: column currency_code; control.plan: column currency_code); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (control.plan: named subscription.plan in the file, its name before the declared move, index plan_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `subscription.contract`; table dropped `subscription.module_listing`; table dropped `subscription.plan`; table dropped `subscription.plan_limit`; table dropped `subscription.plan_module`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.contract`, `control.module_listing`, `control.plan`, `control.plan_limit`, `control.plan_module` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 1 | MIG-APPROVALS | AM-FOUNDATION-DATABASE | [DB] Migration V0010__approvals.sql: approvals (7 tables) | 5 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: approvals.decision, approvals.delegation, approvals.external_provider, approvals.matrix, approvals.request, approvals.request_approver, approvals.rule. Source DDL: backend/tenant/010-approvals.sql and backend/tenant/V0116__after_r1_20261026.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (approvals.external_provider: index external_provider_code_uniq, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (approvals.matrix: row-level security apply_read_beneath_rls; approvals.rule: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: approvals.decision: rename column used_mfa to did_use_mfa; approvals.external_provider: foreign key external_dispatch_provider_id_fkey (from approvals.external_dispatch); approvals.request: rename column reroute_on_no_approver to reroutes_on_no_approver, foreign key approved_action_execution_approval_request_id_fkey (from approvals.approved_action_execution), foreign key external_dispatch_request_id_fkey (from approvals.external_dispatch), foreign key subject_erasure_request_id_fkey (from pii.subject)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (approvals.decision: columns principal_id, external_approver_ref and external_approver_name, DROP CONSTRAINT IF EXISTS decision_decision_chk; VALIDATE CONSTRAINT decision_decision_chk; DROP CONSTRAINT IF EXISTS decision_principal_id_external_approver_ref_one_chk; VALIDATE CONSTRAINT decision_principal_id_external_approver_ref_one_chk, constraints decision_decision_chk and decision_principal_id_external_approver_ref_one_chk; approvals.matrix: index matrix_kind_scope_path_version_uniq; approvals.request: columns attributes, assignment_note, approval_matrix_id, rule_id and cancel_reason, constraints request_approval_matrix_id_fkey and request_rule_id_fkey, indexes request_approval_matrix_id_idx and request_rule_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (approvals.request: columns requested_by_principal_id and requested_by_subject_id, DROP CONSTRAINT IF EXISTS request_requested_by_principal_id_requested_by_sub_b31f1c6e_chk; VALIDATE CONSTRAINT request_requested_by_principal_id_requested_by_sub_b31f1c6e_chk, constraints request_requested_by_principal_id_requested_by_sub_b31f1c6e_chk and request_requested_by_subject_id_fkey, index request_requested_by_subject_id_idx; approvals.rule: DROP CONSTRAINT IF EXISTS rule_condition_chk, constraint rule_condition_chk, index rule_matrix_id_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `approvals.matrix.version`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.decision`, `approvals.delegation`, `approvals.external_provider`, `approvals.matrix`, `approvals.request`, `approvals.request_approver`, `approvals.rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 1 | MIG-ASSETS | AM-FOUNDATION-DATABASE | [DB] Migration V0013__assets.sql: assets (8 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: assets.asset_version, assets.media_asset, assets.media_collection, assets.media_collection_member, assets.media_fingerprint, assets.media_upload, assets.media_usage, assets.rendition. Source DDL: backend/tenant/010-assets.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (assets.media_collection: index media_collection_name_uniq; assets.media_collection_member: row-level security apply_parent_rls; assets.rendition: column asset_id, constraint rendition_asset_id_fkey, index rendition_asset_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: assets.media_asset: foreign key document_asset_id_fkey (from accreditation.document), foreign key media_collection_member_asset_id_fkey (from assets.media_collection_member), foreign key performance_media_asset_id_fkey (from catalogue.performance_media), foreign key product_media_asset_id_fkey (from catalogue.product_media), foreign key tax_exemption_evidence_asset_id_fkey (from ledger.tax_exemption); assets.media_collection: foreign key media_collection_member_collection_id_fkey (from assets.media_collection_member); assets.media_collection_member: foreign key media_collection_member_asset_id_fkey, foreign key media_collection_member_collection_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (assets.asset_version: columns storage_key and content_type, index asset_version_asset_id_uniq; assets.media_asset: columns extracted_text, released_by_principal_id and released_at, constraint media_asset_released_by_principal_id_fkey, index media_asset_released_by_principal_id_idx; assets.media_usage: DROP CONSTRAINT IF EXISTS media_usage_surface_chk; VALIDATE CONSTRAINT media_usage_surface_chk, constraint media_usage_surface_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (assets.media_asset: column has_transparency); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `assets.media_fingerprint.embedding`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `assets.asset_version`, `assets.media_asset`, `assets.media_collection`, `assets.media_collection_member`, `assets.media_fingerprint`, `assets.media_upload`, `assets.media_usage`, `assets.rendition` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 1 | MIG-REPORTING | AM-FOUNDATION-DATABASE | [DB] Migration V0011__reporting.sql: reporting (15 tables) | 8 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: reporting.alert, reporting.alert_rule, reporting.dashboard, reporting.dashboard_tile, reporting.dashboard_view, reporting.execution, reporting.kpi_definition, reporting.natural_language_query, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter, reporting.schedule, reporting.semantic_model. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (reporting.dashboard_tile: row-level security apply_parent_rls; reporting.kpi_definition: index kpi_definition_code_uniq, row-level security apply_read_beneath_rls; reporting.semantic_model: columns domains and relationships, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: reporting.alert: foreign key alert_rule_id_fkey; reporting.alert_rule: foreign key alert_rule_id_fkey (from reporting.alert); reporting.kpi_definition: rename column higher_is_better to is_higher_better; reporting.natural_language_query: foreign key natural_language_query_asked_by_principal_id_fkey; reporting.schedule: rename column skip_if_empty to skips_if_empty); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (reporting.dashboard: DROP CONSTRAINT IF EXISTS dashboard_module_chk; VALIDATE CONSTRAINT dashboard_module_chk, constraint dashboard_module_chk; reporting.report_definition: DROP CONSTRAINT IF EXISTS report_definition_required_permission_chk; VALIDATE CONSTRAINT report_definition_required_permission_chk, constraint report_definition_required_permission_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: reporting.alert: foreign key alert_item_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (reporting.report_definition: DROP CONSTRAINT IF EXISTS report_definition_required_permission_chk; VALIDATE CONSTRAINT report_definition_required_permission_chk, constraint report_definition_required_permission_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `reporting.alert`, `reporting.alert_rule`, `reporting.dashboard`, `reporting.dashboard_tile`, `reporting.dashboard_view`, `reporting.execution`, `reporting.kpi_definition`, `reporting.natural_language_query` and 7 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 1 | MIG-RESOURCES | AM-FOUNDATION-DATABASE | [DB] Migration V0015__resources.sql: resources (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: resources.booking, resources.resource, resources.resource_block, resources.resource_package, resources.resource_requirement, resources.resource_reservation, resources.resource_schedule. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: resources.resource_reservation: rename table resources.resource_hold to resource_reservation, rename index resource_hold_held_by_principal_id_idx to resource_reservation_held_by_principal_id_idx, rename index resource_hold_map_id_idx to resource_reservation_map_id_idx, rename index resource_hold_scope_path_idx to resource_reservation_scope_path_idx, rename index resource_hold_subject_id_idx to resource_reservation_subject_id_idx, rename constraint resource_hold_status_chk to resource_reservation_status_chk, rename constraint resource_hold_pkey to resource_reservation_pkey, rename policy resource_hold_* to resource_reservation_*); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (resources.booking: column change_reason; resources.resource: columns lifecycle_state, lifecycle_effective_from, lifecycle_reason, replacement_resource_id and disposal, constraint resource_replacement_resource_id_fkey, indexes resource_replacement_resource_id_idx and resource_venue_id_code_uniq; resources.resource_package: index resource_package_code_uniq; resources.resource_schedule: columns windows and exceptions); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: resources.booking: foreign key booking_deposit_authorisation_id_fkey; resources.resource: foreign key resource_block_resource_id_fkey (from resources.resource_block), foreign key resource_cost_resource_id_fkey (from resources.resource_cost), foreign key resource_relation_resource_id_fkey (from resources.resource_relation); resources.resource_block: foreign key resource_block_resource_id_fkey; resources.resource_requirement: drop index resource_requirement_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: resources.resource_reservation: foreign key resource_reservation_map_id_fkey, drop index resource_hold_order_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `resources.booking`, `resources.resource`, `resources.resource_block`, `resources.resource_package`, `resources.resource_requirement`, `resources.resource_reservation`, `resources.resource_schedule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 1 | MIG-SYNC | AM-FOUNDATION-DATABASE | [DB] Migration V0012__sync.sql: sync (1 tables) | 1 | Hrushikant Patkar | CrossRegionService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: sync.rejection. Source DDL: backend/tenant/010-sync.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (sync.rejection: row-level security apply_parent_across_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (sync.rejection: DROP CONSTRAINT IF EXISTS rejection_kind_chk; VALIDATE CONSTRAINT rejection_kind_chk, constraint rejection_kind_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **sync.rejection's row-level security waits for its parent**: its policy reads platform.workstation, which MIG-PLATFORM creates later, so leave out its `platform.apply_parent_rls` call here; MIG-PLATFORM applies it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `sync.rejection` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 1 | MIG-WHITELABEL | AM-FOUNDATION-DATABASE | [DB] Migration V0016__whitelabel.sql: whitelabel (31 tables) | 8 | Hrushikant Patkar | WhiteLabelService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: whitelabel.analytics_provider, whitelabel.app_build, whitelabel.banner, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.content_block, whitelabel.content_page, whitelabel.custom_domain, whitelabel.faq_category, whitelabel.faq_entry, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.policy, whitelabel.promo_block, whitelabel.publish_review_policy, whitelabel.site_package, whitelabel.site_setup_progress, whitelabel.store_account, whitelabel.tenant_config, whitelabel.ui_string_pack. Source DDL: backend/tenant/010-whitelabel.sql and backend/tenant/V0108__after_r1_20261020.sql and backend/tenant/V0116__after_r1_20261026.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (whitelabel.store_account: columns pass_type_identifier, pass_certificate_secret_ref, has_pass_certificate and pass_certificate_expires_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (whitelabel.banner: row-level security apply_grant_holder_read_rls; whitelabel.booking_flow_step: column scope_path, index booking_flow_step_scope_path_idx, row-level security apply_grant_holder_read_rls; whitelabel.config_version: column pending_build_time_changes, row-level security apply_read_beneath_rls; whitelabel.content_page: index content_page_slug_uniq, row-level security apply_read_beneath_rls; whitelabel.homepage_section: row-level security apply_grant_holder_read_rls; whitelabel.promo_block: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: whitelabel.app_build: rename column submit_to_store to submits_to_store; whitelabel.custom_domain: drop index custom_domain_tenant_id_idx; whitelabel.guided_choice: foreign key guided_choice_venue_id_fkey; whitelabel.site_setup_progress: rename column minimum_path_done to is_minimum_path_done); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (whitelabel.analytics_provider: index analytics_provider_venue_id_provider_uniq; whitelabel.booking_flow: DROP CONSTRAINT IF EXISTS booking_flow_flow_type_key_chk, constraint booking_flow_flow_type_key_chk; whitelabel.config_version: columns activation_failed_at and activation_failure, indexes config_version_scope_path_version_uniq and config_version_scope_path_uniq; whitelabel.footer_config_column: columns sort_order and links; whitelabel.footer_config_social_link: column sort_order); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (whitelabel.app_build: index app_build_platform_uniq; whitelabel.custom_domain: column validation_expires_at, indexes custom_domain_hostname_uniq and custom_domain_kind_uniq; whitelabel.site_package: column package_asset_ref); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `control.content_block`; not null `whitelabel.booking_flow_step.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `whitelabel.analytics_provider`, `whitelabel.app_build`, `whitelabel.banner`, `whitelabel.booking_flow`, `whitelabel.booking_flow_step`, `whitelabel.config_version`, `whitelabel.content_block`, `whitelabel.content_page` and 23 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 1 | MIG-AI | AM-FOUNDATION-DATABASE | [DB] Migration V0014__ai.sql: ai (52 tables) | 8 | Hrushikant Patkar | AiService | MIG-ASSETS MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: ai.action_plan, ai.activity, ai.anomaly_detector, ai.answer_feedback, ai.assistant_profile, ai.byok_enablement, ai.capability, ai.capability_maturity, ai.chunk_embedding, ai.conversation, ai.decision_record, ai.eval_run, ai.eval_suite, ai.forecast_accuracy, ai.forecast_definition, ai.forecast_point, ai.forecast_scenario, ai.forecast_version, ai.governance_alert, ai.governance_policy, ai.governance_policy_version, ai.guided_choice_suggestion, ai.history_import, ai.history_observation, ai.inbox, ai.incident, ai.index_entry, ai.index_job, ai.index_source, ai.insight, ai.intervention, ai.knowledge_collection, ai.knowledge_document, ai.knowledge_gap, ai.message, ai.model, ai.operational_requirement, ai.outbox, ai.outbox_sequence, ai.policy, ai.policy_exception, ai.prompt_template, ai.proposed_action, ai.provider, ai.rec_decision, ai.rec_decline, ai.rec_event, ai.release, ai.suggestion, ai.training_run, ai.translation_job, ai.venue_settings. Source DDL: backend/tenant/010-ai.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ai.assistant_profile: row-level security apply_read_beneath_rls; ai.capability: row-level security apply_read_beneath_rls; ai.chunk_embedding: row-level security apply_parent_split_rls; ai.decision_record: column annotations; ai.forecast_scenario: column changes; ai.governance_policy: row-level security apply_read_beneath_rls; ai.governance_policy_version: row-level security apply_read_beneath_rls; ai.guided_choice_suggestion: column questions; ai.history_import: column findings; ai.incident: column containment; ai.index_entry: columns record_key, subject_id, content_hash, chunk_count, embedding_model, point_ids, indexed_at and last_job_id, constraint index_entry_last_job_id_fkey, indexes index_entry_last_job_id_idx and index_entry_source_id_record_key_uniq, row-level security apply_parent_split_rls; ai.index_job: row-level security apply_parent_split_rls; ai.index_source: row-level security apply_parent_split_rls; ai.knowledge_collection: row-level security apply_read_beneath_rls; ai.knowledge_document: row-level security apply_read_beneath_rls; ai.model: column task_fitness, row-level security apply_read_beneath_rls; ai.policy: row-level security apply_read_beneath_rls; ai.policy_exception: row-level security apply_read_beneath_rls; ai.prompt_template: row-level security apply_read_beneath_rls; ai.provider: column fitness_warnings; ai.release: row-level security apply_read_beneath_rls; ai.venue_settings: column opening_hours); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (ai.provider: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ai.byok_enablement: drop index byok_enablement_tenant_id_idx; ai.guided_choice_suggestion: foreign key guided_choice_suggestion_venue_id_fkey; ai.history_import: rename column dry_run to is_dry_run, foreign key history_import_venue_id_fkey; ai.history_observation: foreign key history_observation_venue_id_fkey; ai.model: rename column tool_calling to supports_tool_calling, rename column structured_output to supports_structured_output; ai.policy: rename column cache_answers to caches_answers, rename column guardrail_short_circuit to has_guardrail_short_circuit; ai.proposed_action: rename column interaction_id to activity_id, rename constraint proposed_action_interaction_id_fkey to proposed_action_activity_id_fkey, rename index proposed_action_interaction_id_idx to proposed_action_activity_id_idx; ai.provider: rename column degrade_gracefully to degrades_gracefully; ai.rec_decline: drop index rec_decline_product_id_idx; ai.rec_event: drop index rec_event_order_id_idx, drop index rec_event_product_id_idx; ai.suggestion: foreign key suggestion_outcome_suggestion_id_fkey (from ai.suggestion_outcome)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (ai.activity: column principal_id, DROP CONSTRAINT IF EXISTS activity_principal_id_when_chk; VALIDATE CONSTRAINT activity_principal_id_when_chk; DROP CONSTRAINT IF EXISTS activity_subject_id_when_chk; VALIDATE CONSTRAINT activity_subject_id_when_chk, constraints activity_principal_id_when_chk and activity_subject_id_when_chk; ai.chunk_embedding: column subject_id, index chunk_embedding_subject_id_idx; ai.conversation: columns principal_id, subject_id and profile_key, DROP CONSTRAINT IF EXISTS conversation_module_chk; VALIDATE CONSTRAINT conversation_module_chk; DROP CONSTRAINT IF EXISTS conversation_principal_id_subject_id_one_chk; VALIDATE CONSTRAINT conversation_principal_id_subject_id_one_chk, constraints conversation_module_chk and conversation_principal_id_subject_id_one_chk; ai.decision_record: column hash_version; ai.index_entry: index index_entry_subject_id_idx; ai.index_source: column kind, index index_source_table_name_uniq; ai.policy: column glossary_terms; ai.proposed_action: columns target_kind, target_ref, locale, field_path and draft_text); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: ai.proposed_action: foreign key proposed_action_translation_job_id_fkey; ai.translation_job: foreign key proposed_action_translation_job_id_fkey (from ai.proposed_action)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0110__after_r1_20261020.sql (ai.conversation: index conversation_subject_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (ai.proposed_action: columns confidence, basis, reasoning, distance_metres and map_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (ai.proposed_action: index proposed_action_map_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `ai.forecast_scenario.changes`; not null `ai.index_entry.record_key`; not null `ai.index_entry.content_hash`; not null `ai.index_entry.indexed_at`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.action_plan`, `ai.activity`, `ai.anomaly_detector`, `ai.answer_feedback`, `ai.assistant_profile`, `ai.byok_enablement`, `ai.capability`, `ai.capability_maturity` and 44 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 1 | MIG-PLATFORM | AM-FOUNDATION-DATABASE | [DB] Migration V0017__platform.sql: platform (19 tables) | 8 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: platform.audit_read, platform.audit_record, platform.configuration_profile, platform.denomination, platform.device, platform.idempotency_record, platform.outbox, platform.outlet, platform.outlet_opening_hour, platform.region_settings, platform.sale_board, platform.sale_board_page, platform.sale_board_tile, platform.scope, platform.tenant, platform.venue_settings, platform.workstation, sync.dsar_request, sync.guest_link. Source DDL: backend/tenant/010-platform.sql and backend/tenant/V0104__after_r1_20261015.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (platform.scope: indexes scope_path_uniq, scope_parent_id_idx and scope_tenant_root_uniq; platform.venue_settings: column business_day_cutoff); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: platform.sale_board_tile: rename column page_id to sale_board_page_id; platform.venue_settings: rename column cash_drawer_limit to deposit_box_limit_amount; platform.workstation: rename column cash_drawer_limit to deposit_box_limit_amount; sync.guest_link: move table platform.guest_link to sync); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (platform.audit_record: row-level security apply_append_audit_rls; platform.denomination: column scope_path, index denomination_scope_path_idx, row-level security apply_grant_holder_read_rls; platform.device: column scope_path, indexes device_serial_number_uniq and device_scope_path_idx, row-level security apply_grant_holder_read_rls; platform.outlet: index outlet_venue_id_code_uniq; platform.region_settings: column scope_path, index region_settings_scope_path_idx, row-level security apply_read_beneath_rls; platform.sale_board: index sale_board_venue_id_code_uniq; platform.sale_board_tile: columns position, kind, variant_id, category_id, action_code, label, colour and image_asset_ref, index sale_board_tile_variant_id_idx, row-level security apply_parent_rls; platform.workstation: columns cashier_input_mode and guest_display_content); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (platform.sale_board_tile: DROP CONSTRAINT IF EXISTS sale_board_tile_action_code_when_chk; VALIDATE CONSTRAINT sale_board_tile_action_code_when_chk; DROP CONSTRAINT IF EXISTS sale_board_tile_category_id_when_chk; VALIDATE CONSTRAINT sale_board_tile_category_id_when_chk; DROP CONSTRAINT IF EXISTS sale_board_tile_variant_id_when_chk; VALIDATE CONSTRAINT sale_board_tile_variant_id_when_chk, constraints sale_board_tile_action_code_when_chk, sale_board_tile_category_id_when_chk and sale_board_tile_variant_id_when_chk; platform.venue_settings: column org_unit_id; platform.workstation: column org_unit_id; sync.dsar_request: named platform.dsar_request in the file, its name before the declared move, row-level security apply_parent_across_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105a__names_early_after_r1_20261020.sql (the names the contracts use: sync.dsar_request: move table platform.dsar_request to sync); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: platform.configuration_profile: foreign key profile_deployment_profile_id_fkey (from platform.profile_deployment); platform.denomination: foreign key cash_count_line_denomination_id_fkey (from orders.cash_count_line), foreign key deposit_box_opening_denomination_denomination_id_fkey (from orders.deposit_box_opening_denomination); platform.device: foreign key device_binding_device_id_fkey (from access.device_binding), foreign key reader_device_id_fkey (from games.reader), foreign key kiosk_assist_session_device_id_fkey (from marketing.kiosk_assist_session), foreign key terminal_device_id_fkey (from payments.terminal), foreign key device_tamper_event_device_id_fkey (from tenancy.device_tamper_event); platform.outbox: drop index outbox_event_id_idx, drop index outbox_tenant_id_idx; platform.outlet: foreign key delivery_policy_outlet_id_fkey (from fnb.delivery_policy), foreign key kitchen_sla_outlet_id_fkey (from fnb.kitchen_sla); platform.sale_board_tile: rename constraint sale_board_tile_page_id_fkey to sale_board_tile_sale_board_page_id_fkey, rename index sale_board_tile_page_id_idx to sale_board_tile_sale_board_page_id_idx, create index sale_board_tile_sale_board_page_id_position_uniq; platform.scope: foreign key access_incident_venue_id_fkey (from access.access_incident), foreign key access_map_venue_id_fkey (from access.access_map), foreign key access_point_configuration_venue_id_fkey (from access.access_point_configuration), foreign key access_point_group_venue_id_fkey (from access.access_point_group), foreign key attraction_access_venue_id_fkey (from access.attraction_access), foreign key biometric_audit_event_venue_id_fkey (from access.biometric_audit_event), foreign key biometric_profile_venue_id_fkey (from access.biometric_profile), foreign key branding_profile_scope_id_fkey (from access.branding_profile), foreign key companion_rule_venue_id_fkey (from access.companion_rule), foreign key credential_issuance_retry_policy_venue_id_fkey (from access.credential_issuance_retry_policy), foreign key device_configuration_venue_id_fkey (from access.device_configuration), foreign key device_placement_venue_id_fkey (from access.device_placement), foreign key edge_node_venue_id_fkey (from access.edge_node), foreign key edge_package_venue_id_fkey (from access.edge_package), foreign key face_reenrolment_attempt_venue_id_fkey (from access.face_reenrolment_attempt), foreign key gate_lane_venue_id_fkey (from access.gate_lane), foreign key gate_mode_change_venue_id_fkey (from access.gate_mode_change), foreign key gate_mode_policy_venue_id_fkey (from access.gate_mode_policy), foreign key gate_outcome_profile_venue_id_fkey (from access.gate_outcome_profile), foreign key group_admission_rule_venue_id_fkey (from access.group_admission_rule), foreign key media_compatibility_test_venue_id_fkey (from access.media_compatibility_test), foreign key offline_policy_venue_id_fkey (from access.offline_policy), foreign key operating_calendar_entry_venue_id_fkey (from access.operating_calendar_entry), foreign key podium_venue_id_fkey (from access.podium), foreign key podium_shift_venue_id_fkey (from access.podium_shift), foreign key policy_scope_assignment_scope_id_fkey (from access.policy_scope_assignment), foreign key guided_choice_suggestion_venue_id_fkey (from ai.guided_choice_suggestion), foreign key history_import_venue_id_fkey (from ai.history_import), foreign key history_observation_venue_id_fkey (from ai.history_observation), foreign key waiting_room_setting_venue_id_fkey (from catalogue.waiting_room_setting), foreign key till_shift_policy_venue_id_fkey (from orders.till_shift_policy), foreign key scope_parent_id_fkey, foreign key scope_parent_id_fkey (from platform.scope), foreign key campaign_venue_id_fkey (from promotions.campaign), foreign key promotion_alert_venue_id_fkey (from promotions.promotion_alert), foreign key promotion_audit_venue_id_fkey (from promotions.promotion_audit), foreign key promotion_channel_publication_venue_id_fkey (from promotions.promotion_channel_publication), foreign key promotion_conflict_venue_id_fkey (from promotions.promotion_conflict), foreign key promotion_evaluation_trace_venue_id_fkey (from promotions.promotion_evaluation_trace), foreign key promotion_rule_venue_id_fkey (from promotions.promotion_rule), foreign key stacking_rule_venue_id_fkey (from promotions.stacking_rule), foreign key venue_assignment_primary_venue_id_fkey (from resources.venue_assignment), foreign key favourite_route_venue_id_fkey (from transport.favourite_route), foreign key network_import_venue_id_fkey (from transport.network_import), foreign key pass_type_venue_id_fkey (from transport.pass_type), foreign key route_venue_id_fkey (from transport.route), foreign key station_venue_id_fkey (from transport.station), foreign key visit_plan_venue_id_fkey (from venuemap.visit_plan), foreign key guided_choice_venue_id_fkey (from whitelabel.guided_choice), foreign key labour_budget_venue_id_fkey (from workforce.labour_budget), foreign key staff_conversation_venue_id_fkey (from workforce.staff_conversation)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (platform.audit_read: columns subject_id, read_at, target, filter and record_count, row-level security apply_append_audit_rls; platform.outbox: column occurred_at, index outbox_aggregate_id_sequence_idx; platform.venue_settings: column contact; platform.workstation: columns sale_board and configuration_profile_version, index workstation_configuration_profile_id_configuration_d7f5bd55_idx; sync.dsar_request: column cell_results; sync.guest_link: columns linked_cells and local_subject_id, constraint guest_link_local_subject_id_fkey, index guest_link_local_subject_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: platform.configuration_profile: foreign key workstation_configuration_profile_id_fkey (from platform.workstation); platform.device: foreign key device_assignment_device_id_fkey (from tenancy.device_assignment); platform.workstation: foreign key workstation_configuration_profile_id_fkey, drop index workstation_configuration_profile_id_idx; sync.guest_link: foreign key cross_cell_request_guest_link_id_fkey (from sync.cross_cell_request)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0111__names_after_r1_20261020.sql (the names the contracts use: platform.scope: foreign key bundle_application_venue_id_fkey (from catalogue.bundle_application); platform.workstation: foreign key bundle_application_venue_id_workstation_id_fkey (from catalogue.bundle_application)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (platform.idempotency_record: DROP CONSTRAINT IF EXISTS idempotency_record_status_chk, constraint idempotency_record_status_chk, index idempotency_record_operation_id_idempotency_key_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0115__names_after_r1_20261022.sql (the names the contracts use: platform.configuration_profile: widen primary key configuration_profile_pkey, change foreign key profile_deployment_profile_id_fkey (from platform.profile_deployment), foreign key workstation_configuration_profile_id_fkey (from platform.workstation); platform.workstation: foreign key workstation_configuration_profile_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (platform.audit_read: column org_unit_id, constraint audit_read_org_unit_id_fkey, index audit_read_org_unit_id_idx, row-level security apply_append_audit_read_rls; platform.audit_record: row-level security apply_append_audit_read_rls; platform.configuration_profile: row-level security apply_read_beneath_rls; platform.venue_settings: column step_minutes); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (platform.outlet: column order_number_prefix); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also apply sync.rejection's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through platform.workstation): MIG-SYNC creates sync.rejection before platform.workstation exists. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `platform.audit_read.read_at`; not null `platform.audit_read.target`; not null `platform.denomination.scope_path`; not null `platform.device.scope_path`; column changed `platform.device.status`; not null `platform.outbox.occurred_at`; not null `platform.region_settings.scope_path`; not null `platform.sale_board_tile.sale_board_page_id`; not null `platform.sale_board_tile.position`; not null `platform.sale_board_tile.kind`; column changed `platform.venue_settings.deposit_box_limit_amount`; column retired `platform.venue_settings.org_unit_id`; column changed `platform.workstation.deposit_box_limit_amount`; column retired `platform.workstation.org_unit_id`; not null `sync.dsar_request.cell_results`; not null `sync.guest_link.linked_cells`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `platform.audit_read`, `platform.audit_record`, `platform.configuration_profile`, `platform.denomination`, `platform.device`, `platform.idempotency_record`, `platform.outbox`, `platform.outlet` and 11 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 1 | SETUP-AUTH | AM-FOUNDATION-SETUP | [DevOps] Sign-in working end to end against IdentityService | 5 | Pranay Shinde |  | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Sign-in working end to end against IdentityService. Builds: `operation login`, `operation refreshToken`, `operation logout`, `operation getCurrentSession`. The staff sign-in path of contracts/spine/identity.yaml: `login` issues the session and refresh token, `getCurrentSession` returns the Session with `effectivePermissions` and `permissionsByScope` (the effective permissions the done-when reads), `refreshToken` and `logout` end the loop; the operations themselves are built on their IdentityService tickets, this task wires them through the host. In **ticvai-backend** and **ticvai-frontend**: the identity sign-in operations, `ICurrentPrincipal` and `ITenantContext` filled from the session, signing keys from the cell's Azure Key Vault (audit R057). Done when: a seeded staff member signs in from a web app and an app, gets their effective permissions, and a request without a session gets 401.
8 | 1 | MIG-MAINTENANCE | AM-FOUNDATION-DATABASE | [DB] Migration V0020__maintenance.sql: maintenance (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: maintenance.asset, maintenance.incident, maintenance.inspection, maintenance.inspection_template, maintenance.inspection_template_item, maintenance.work_order. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (maintenance.asset: index asset_venue_id_asset_tag_uniq; maintenance.inspection_template: index inspection_template_code_uniq; maintenance.work_order: columns time_entries and parts); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: maintenance.asset: foreign key asset_document_asset_id_fkey (from maintenance.asset_document), foreign key asset_status_change_asset_id_fkey (from maintenance.asset_status_change), foreign key equipment_assignment_asset_id_fkey (from rental.equipment_assignment); maintenance.incident: rename column first_aid_given to was_first_aid_given, foreign key incident_authority_notification_incident_id_fkey (from maintenance.incident_authority_notification), foreign key incident_history_incident_id_fkey (from maintenance.incident_history), foreign key incident_investigation_note_incident_id_fkey (from maintenance.incident_investigation_note), foreign key incident_involved_party_incident_id_fkey (from maintenance.incident_involved_party), foreign key incident_media_incident_id_fkey (from maintenance.incident_media); maintenance.inspection: foreign key inspection_template_id_fkey; maintenance.inspection_template: foreign key inspection_template_id_fkey (from maintenance.inspection); maintenance.work_order: foreign key vendor_service_request_work_order_id_fkey (from maintenance.vendor_service_request)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `maintenance.asset`, `maintenance.incident`, `maintenance.inspection`, `maintenance.inspection_template`, `maintenance.inspection_template_item`, `maintenance.work_order` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 1 | MIG-SEATING | AM-FOUNDATION-DATABASE | [DB] Migration V0019__seating.sql: seating (11 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-ASSETS MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Tenant database. Tables: seating.accessible, seating.recommendation_rule, seating.seat, seating.seat_block, seating.seat_block_item, seating.seat_category, seating.seat_map, seating.seat_price_band, seating.seat_reservation, seating.seat_reservation_item, seating.section. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (seating.seat: index seat_seat_map_id_section_code_row_label_seat_number_uniq; seating.seat_category: index seat_category_venue_id_code_uniq; seating.seat_price_band: index seat_price_band_seat_category_id_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: seating.recommendation_rule: rename table seating.recommendation_rules to recommendation_rule, rename column explain_to_guest to explains_to_guest, rename column reverse_row_order to reverses_row_order, rename index recommendation_rules_performance_id_idx to recommendation_rule_performance_id_idx, rename index recommendation_rules_scope_path_idx to recommendation_rule_scope_path_idx, rename index recommendation_rules_seat_map_id_idx to recommendation_rule_seat_map_id_idx, rename constraint recommendation_rules_pkey to recommendation_rule_pkey, rename policy recommendation_rules_* to recommendation_rule_*; seating.seat_reservation: rename table seating.seat_hold to seat_reservation, rename index seat_hold_block_id_idx to seat_reservation_block_id_idx, rename index seat_hold_held_by_principal_id_idx to seat_reservation_held_by_principal_id_idx, rename index seat_hold_performance_id_idx to seat_reservation_performance_id_idx, rename index seat_hold_subject_id_idx to seat_reservation_subject_id_idx, rename constraint seat_hold_block_id_fkey to seat_reservation_block_id_fkey, rename constraint seat_hold_held_by_principal_id_fkey to seat_reservation_held_by_principal_id_fkey, rename constraint seat_hold_performance_id_fkey to seat_reservation_performance_id_fkey, rename constraint seat_hold_subject_id_fkey to seat_reservation_subject_id_fkey, rename constraint seat_hold_status_chk to seat_reservation_status_chk, rename constraint seat_hold_pkey to seat_reservation_pkey, rename policy seat_hold_* to seat_reservation_*; seating.seat_reservation_item: rename table seating.seat_hold_item to seat_reservation_item, rename column held_price to gross_amount, rename column hold_id to seat_reservation_id, rename index seat_hold_item_hold_id_idx to seat_reservation_item_seat_reservation_id_idx, rename index seat_hold_item_seat_id_idx to seat_reservation_item_seat_id_idx, rename constraint seat_hold_item_pkey to seat_reservation_item_pkey, rename policy seat_hold_item_* to seat_reservation_item_*); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (seating.accessible: column spaces; seating.seat: column scope_path, indexes seat_seat_map_id_section_code_row_label_seat_number_uniq and seat_scope_path_idx, row-level security apply_grant_holder_read_rls; seating.seat_block_item: row-level security apply_parent_rls; seating.seat_category: index seat_category_venue_id_code_uniq; seating.seat_price_band: column scope_path, indexes seat_price_band_seat_category_id_code_uniq and seat_price_band_scope_path_idx, row-level security apply_grant_holder_read_rls; seating.section: column boundary); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: seating.seat: foreign key seat_block_item_seat_id_fkey (from seating.seat_block_item); seating.seat_block: foreign key seat_block_item_block_id_fkey (from seating.seat_block_item); seating.seat_block_item: foreign key seat_block_item_block_id_fkey, foreign key seat_block_item_seat_id_fkey; seating.seat_map: foreign key seat_pricing_rule_seat_map_id_fkey (from catalogue.seat_pricing_rule); seating.seat_price_band: rename column amount to list_price); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (seating.recommendation_rule: column profiles; seating.seat_reservation: DROP CONSTRAINT IF EXISTS seat_reservation_status_chk; VALIDATE CONSTRAINT seat_reservation_status_chk, constraints seat_reservation_status_chk and seat_reservation_inventory_reservation_id_fkey, column inventory_reservation_id, index seat_reservation_inventory_reservation_id_idx; seating.seat_reservation_item: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: seating.seat: foreign key seat_reservation_item_seat_id_fkey (from seating.seat_reservation_item); seating.seat_reservation: foreign key seat_reservation_item_seat_reservation_id_fkey (from seating.seat_reservation_item); seating.seat_reservation_item: foreign key seat_reservation_item_seat_id_fkey, foreign key seat_reservation_item_seat_reservation_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (seating.accessible: index accessible_seat_map_id_uniq; seating.recommendation_rule: index recommendation_rule_seat_map_id_performance_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **seating.seat_reservation's row-level security waits for its parent**: its policy reads catalogue.performance, which MIG-CATALOGUE creates later, so leave out its `platform.apply_parent_rls` call here; MIG-CATALOGUE applies it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `seating.seat.scope_path`; not null `seating.seat_price_band.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `seating.accessible`, `seating.recommendation_rule`, `seating.seat`, `seating.seat_block`, `seating.seat_block_item`, `seating.seat_category`, `seating.seat_map`, `seating.seat_price_band` and 3 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 1 | MIG-WALLET | AM-FOUNDATION-DATABASE | [DB] Migration V0021__wallet.sql: wallet (21 tables) | 8 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Tenant database. Tables: wallet.accounting_mapping, wallet.authentication_policy, wallet.auto_reload_setting, wallet.balance, wallet.channel_rule, wallet.configuration_version, wallet.configuration_version_snapshot, wallet.consumption_policy, wallet.credit_lot, wallet.credit_type, wallet.fund_reservation, wallet.funding_rule, wallet.gift_card, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rule_set, wallet.transfer_rule, wallet.wallet, wallet.wallet_transaction, wallet.wallet_type. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: wallet.channel_rule: rename table wallet.channel_rules to channel_rule, rename index channel_rules_scope_path_idx to channel_rule_scope_path_idx, rename constraint channel_rules_pkey to channel_rule_pkey, rename policy channel_rules_* to channel_rule_*; wallet.fund_reservation: rename table wallet.hold to fund_reservation, rename column wallet_hold_amount to reserved_amount, rename column wallet_hold_status to status, rename index hold_order_id_idx to fund_reservation_order_id_idx, rename index hold_payment_id_idx to fund_reservation_payment_id_idx, rename index hold_wallet_id_idx to fund_reservation_wallet_id_idx, rename constraint hold_order_id_fkey to fund_reservation_order_id_fkey, rename constraint hold_currency_code_chk to fund_reservation_currency_code_chk, rename constraint hold_wallet_hold_status_chk to fund_reservation_status_chk, rename constraint hold_pkey to fund_reservation_pkey, rename policy hold_* to fund_reservation_*; wallet.funding_rule: rename table wallet.funding_rules to funding_rule, rename index funding_rules_scope_path_idx to funding_rule_scope_path_idx, rename index funding_rules_wallet_type_id_idx to funding_rule_wallet_type_id_idx, rename constraint funding_rules_pkey to funding_rule_pkey, rename policy funding_rules_* to funding_rule_*; wallet.risk_rule_set: rename table wallet.risk_rules to risk_rule_set, rename index risk_rules_scope_path_idx to risk_rule_set_scope_path_idx, rename constraint risk_rules_pkey to risk_rule_set_pkey, rename policy risk_rules_* to risk_rule_set_*; wallet.transfer_rule: rename table wallet.transfer_rules to transfer_rule, rename column within_shared_wallet_only to is_within_shared_wallet_only, rename index transfer_rules_scope_path_idx to transfer_rule_scope_path_idx, rename constraint transfer_rules_pkey to transfer_rule_pkey, rename policy transfer_rules_* to transfer_rule_*); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (wallet.accounting_mapping: column mappings, row-level security apply_read_beneath_rls; wallet.authentication_policy: column tiers; wallet.balance: row-level security apply_grant_holder_read_rls; wallet.configuration_version: column findings; wallet.credit_type: index credit_type_code_uniq, row-level security apply_read_beneath_rls; wallet.gift_card: row-level security apply_grant_holder_subject_read_rls; wallet.reconciliation_source: column sources; wallet.wallet: row-level security apply_grant_holder_subject_read_rls; wallet.wallet_type: index wallet_type_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.balance: foreign key balance_wallet_id_fkey, drop index balance_wallet_balance_id_idx; wallet.credit_lot: foreign key credit_lot_credit_type_id_fkey; wallet.credit_type: foreign key credit_lot_credit_type_id_fkey (from wallet.credit_lot); wallet.gift_card: rename column face_value to face_value_amount, rename column balance to balance_amount; wallet.refund_policy: rename column restore_to_original_lots to restores_to_original_lots, rename column restore_original_expiry to restores_original_expiry; wallet.wallet: rename column balance to balance_amount, foreign key balance_wallet_id_fkey (from wallet.balance), foreign key credential_wallet_id_fkey (from wallet.credential), foreign key dispute_wallet_id_fkey (from wallet.dispute), foreign key exit_settlement_wallet_id_fkey (from wallet.exit_settlement), foreign key restriction_wallet_id_fkey (from wallet.restriction), foreign key shared_wallet_wallet_id_fkey (from wallet.shared_wallet); wallet.wallet_transaction: rename column wallet_hold_id to fund_reservation_id, rename column amount to transaction_amount, rename constraint wallet_transaction_wallet_hold_id_fkey to wallet_transaction_fund_reservation_id_fkey, rename index wallet_transaction_wallet_hold_id_idx to wallet_transaction_fund_reservation_id_idx, foreign key wallet_transaction_subject_id_fkey; wallet.wallet_type: rename column stored_value_capability to supports_stored_value, rename column top_up_capability to supports_top_up, rename column transfer_capability to supports_transfer, rename column refund_capability to supports_refund, rename column gift_card_support to supports_gift_card, rename column voucher_support to supports_voucher, rename column membership_credit_support to supports_membership_credit, rename column wearable_support to supports_wearable, rename column holder_may_differ_from_owner to can_holder_differ_from_owner); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (wallet.configuration_version: index configuration_version_scope_path_version_uniq; wallet.credit_lot: column issued_credits; wallet.fund_reservation: column wallet_hold_id; wallet.funding_rule: columns preset_amounts and bonus_rules, index funding_rule_scope_path_wallet_type_id_uniq; wallet.gift_card: column subject_id, row-level security apply_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: wallet.fund_reservation: foreign key fund_reservation_wallet_id_fkey; wallet.wallet: foreign key fund_reservation_wallet_id_fkey (from wallet.fund_reservation)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0112__after_r1_20261021.sql (wallet.credit_lot: column order_line_id, constraint credit_lot_order_line_id_fkey, index credit_lot_order_line_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (wallet.balance: row-level security apply_grant_holder_read_rls; wallet.wallet: row-level security apply_grant_holder_subject_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `wallet.authentication_policy.tiers`; column retired `wallet.fund_reservation.wallet_hold_id`; not null `wallet.reconciliation_source.sources`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.accounting_mapping`, `wallet.authentication_policy`, `wallet.auto_reload_setting`, `wallet.balance`, `wallet.channel_rule`, `wallet.configuration_version`, `wallet.configuration_version_snapshot`, `wallet.consumption_policy` and 13 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 1 | MIG-WORKFORCE | AM-FOUNDATION-DATABASE | [DB] Migration V0018__workforce.sql: workforce (3 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: workforce.attendance, workforce.attendance_amendment, workforce.rota_assignment. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (workforce.attendance_amendment: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: workforce.attendance: foreign key attendance_amendment_attendance_record_id_fkey (from workforce.attendance_amendment); workforce.attendance_amendment: foreign key attendance_amendment_amended_by_principal_id_fkey, foreign key attendance_amendment_attendance_record_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.attendance`, `workforce.attendance_amendment`, `workforce.rota_assignment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 1 | MIG-CATALOGUE | AM-FOUNDATION-DATABASE | [DB] Migration V0022__catalogue.sql: catalogue (42 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM MIG-SEATING | Tenant database. Tables: catalogue.alternative_code, catalogue.audit_entry, catalogue.channel_capacity, catalogue.channel_envelope, catalogue.demand_forecast, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, catalogue.entitlement_template, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.fee, catalogue.group_package, catalogue.import_job, catalogue.inventory_reservation, catalogue.performance, catalogue.price, catalogue.price_assignment, catalogue.price_execution, catalogue.price_ladder, catalogue.price_list, catalogue.price_resolution_policy, catalogue.pricing_recommendation, catalogue.pricing_recommendation_decision, catalogue.pricing_simulation, catalogue.pricing_test_case, catalogue.product, catalogue.product_category, catalogue.product_channel_assignment, catalogue.product_channel_text, catalogue.product_eligibility_rule, catalogue.product_media, catalogue.product_owner_form, catalogue.product_sale_permission, catalogue.product_version, catalogue.published_bundle, catalogue.rate, catalogue.sales_channel, catalogue.variant, catalogue.waitlist_entry. Source DDL: backend/tenant/010-catalogue.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0101__after_r1_20261006.sql (catalogue.performance: column minutes_on_screen; catalogue.product: columns name_localised and description_localised); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (catalogue.product_media: column product_id, constraint product_media_product_id_fkey, index product_media_product_id_idx; catalogue.sales_channel: column ticket_credential_format); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: catalogue.channel_envelope: rename table catalogue.channel_allocation to channel_envelope, rename column envelope_id to channel_capacity_id, rename column allocation_type to envelope_type, rename index channel_allocation_envelope_id_idx to channel_envelope_channel_capacity_id_idx, rename index channel_allocation_sales_channel_id_idx to channel_envelope_sales_channel_id_idx, rename constraint channel_allocation_envelope_id_fkey to channel_envelope_channel_capacity_id_fkey, rename constraint channel_allocation_channel_chk to channel_envelope_channel_chk, rename constraint channel_allocation_allocation_type_chk to channel_envelope_envelope_type_chk, rename constraint channel_allocation_waitlist_behavior_chk to channel_envelope_waitlist_behavior_chk, rename constraint channel_allocation_pkey to channel_envelope_pkey, rename policy channel_allocation_* to channel_envelope_*; catalogue.inventory_reservation: rename table catalogue.inventory_hold to inventory_reservation, rename index inventory_hold_channel_capacity_id_idx to inventory_reservation_channel_capacity_id_idx, rename index inventory_hold_force_released_by_principal_id_idx to inventory_reservation_force_released_by_principal_id_idx, rename index inventory_hold_holder_cart_id_idx to inventory_reservation_holder_cart_id_idx, rename index inventory_hold_holder_workstation_id_idx to inventory_reservation_holder_workstation_id_idx, rename constraint inventory_hold_channel_capacity_id_fkey to inventory_reservation_channel_capacity_id_fkey, rename constraint inventory_hold_force_released_by_principal_id_fkey to inventory_reservation_force_released_by_principal_id_fkey, rename constraint inventory_hold_holder_workstation_id_fkey to inventory_reservation_holder_workstation_id_fkey, rename constraint inventory_hold_holder_kind_chk to inventory_reservation_holder_kind_chk, rename constraint inventory_hold_status_chk to inventory_reservation_status_chk, rename constraint inventory_hold_pkey to inventory_reservation_pkey, rename policy inventory_hold_* to inventory_reservation_*); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.alternative_code: column scope_path, index alternative_code_scope_path_idx, row-level security apply_grant_holder_read_rls; catalogue.entitlement_template: column valid_time_windows, index entitlement_template_code_uniq; catalogue.event: index event_code_uniq; catalogue.event_registration: column participant_categories; catalogue.event_resource_plan: columns requirements and contractors; catalogue.event_schedule: column performances; catalogue.import_job: column findings; catalogue.price_list: index price_list_code_uniq; catalogue.product: column display_tags, indexes product_code_uniq and product_venue_id_family_key_uniq; catalogue.product_category: index product_category_code_uniq; catalogue.product_media: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (catalogue.dynamic_pricing_control: row-level security apply_read_beneath_rls; catalogue.sales_channel: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.dynamic_pricing_control: rename column exclude_protected_rates to excludes_protected_rates; catalogue.dynamic_pricing_strategy: foreign key price_ladder_dynamic_pricing_strategy_id_fkey (from catalogue.price_ladder); catalogue.entitlement_template: foreign key entitlement_template_id_fkey (from access.entitlement), foreign key plan_benefit_entitlement_template_id_fkey (from catalogue.plan_benefit), foreign key customer_membership_entitlement_template_id_fkey (from identity.customer_membership), foreign key membership_renewal_entitlement_template_id_fkey (from orders.membership_renewal); catalogue.event_registration: rename column capture_per_attendee to captures_per_attendee, foreign key performance_media_event_registration_id_fkey (from catalogue.performance_media); catalogue.event_schedule: rename column duration_is_dynamic to is_duration_dynamic, rename column cascade_overrun to cascades_overrun; catalogue.group_package: foreign key group_package_product_id_fkey; catalogue.performance: foreign key performance_media_performance_id_fkey (from catalogue.performance_media), foreign key performance_participant_performance_id_fkey (from resources.performance_participant), foreign key group_request_performance_id_fkey (from seating.group_request), foreign key hold_pool_performance_id_fkey (from seating.hold_pool), foreign key departure_performance_id_fkey (from transport.departure); catalogue.price: rename column amount to list_price; catalogue.price_assignment: foreign key price_assignment_price_list_id_fkey; catalogue.price_execution: rename column price_inconsistency to has_price_inconsistency; catalogue.price_ladder: foreign key price_ladder_dynamic_pricing_strategy_id_fkey; catalogue.price_list: foreign key price_assignment_price_list_id_fkey (from catalogue.price_assignment), foreign key price_list_version_price_list_id_fkey (from catalogue.price_list_version), foreign key rate_price_list_id_fkey (from catalogue.rate); catalogue.pricing_recommendation: foreign key pricing_recommendation_decision_recommendation_id_fkey (from catalogue.pricing_recommendation_decision); catalogue.pricing_recommendation_decision: foreign key pricing_recommendation_decision_decided_by_principal_id_fkey, foreign key pricing_recommendation_decision_recommendation_id_fkey; catalogue.product: rename column blocked_offline to is_blocked_offline, foreign key verification_method_policy_product_id_fkey (from access.verification_method_policy), foreign key group_package_product_id_fkey (from catalogue.group_package), foreign key lifecycle_action_product_id_fkey (from catalogue.lifecycle_action), foreign key package_pricing_product_id_fkey (from catalogue.package_pricing), foreign key product_channel_assignment_product_id_fkey (from catalogue.product_channel_assignment), foreign key product_eligibility_rule_product_id_fkey (from catalogue.product_eligibility_rule), foreign key product_link_source_product_id_fkey (from catalogue.product_link), foreign key product_recommendation_source_product_id_fkey (from fnb.product_recommendation), foreign key group_ticket_allocation_line_product_id_fkey (from orders.group_ticket_allocation_line), foreign key product_relationship_from_product_id_fkey (from promotions.product_relationship), foreign key product_relationship_to_product_id_fkey (from promotions.product_relationship), foreign key agreement_item_catalogue_product_id_fkey (from rental.agreement_item), foreign key selection_policy_ticket_product_id_fkey (from resources.selection_policy), foreign key product_recommendation_source_product_id_fkey (from retail.product_recommendation); catalogue.product_channel_assignment: foreign key product_channel_assignment_product_id_fkey; catalogue.product_eligibility_rule: rename column refundable_if_ineligible_at_gate to is_refundable_if_ineligible_at_gate, foreign key product_eligibility_rule_product_id_fkey; catalogue.product_media: foreign key product_media_asset_id_fkey; catalogue.product_version: foreign key product_version_published_by_principal_id_fkey; catalogue.rate: foreign key rate_price_category_id_fkey, foreign key rate_price_list_id_fkey; catalogue.sales_channel: foreign key channel_connection_sales_channel_id_fkey (from catalogue.channel_connection), foreign key channel_incident_sales_channel_id_fkey (from catalogue.channel_incident), foreign key channel_sales_rule_sales_channel_id_fkey (from catalogue.channel_sales_rule), foreign key channel_sync_sales_channel_id_fkey (from catalogue.channel_sync); catalogue.variant: foreign key wishlist_item_variant_id_fkey (from marketing.wishlist_item), foreign key reservation_line_variant_id_fkey (from orders.reservation_line), foreign key allocation_component_variant_id_fkey (from promotions.allocation_component), foreign key bundle_choice_option_variant_id_fkey (from promotions.bundle_choice_option), foreign key bundle_component_variant_id_fkey (from promotions.bundle_component)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (catalogue.channel_envelope: row-level security apply_parent_rls; catalogue.group_package: column minimum_size, DROP CONSTRAINT IF EXISTS group_package_kind_chk; VALIDATE CONSTRAINT group_package_kind_chk, constraint group_package_kind_chk; catalogue.product_version: index product_version_product_id_uniq; catalogue.published_bundle: columns published_at and published_by, constraint published_bundle_published_by_fkey, index published_bundle_published_by_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: catalogue.inventory_reservation: foreign key reservation_line_inventory_reservation_id_fkey (from orders.reservation_line)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0112__after_r1_20261021.sql (catalogue.product: DROP CONSTRAINT IF EXISTS product_kind_chk; VALIDATE CONSTRAINT product_kind_chk, constraint product_kind_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (catalogue.alternative_code: index alternative_code_partner_id_code_uniq; catalogue.event: columns scheduled_lifecycle_state, scheduled_lifecycle_at and scheduled_lifecycle_reason; catalogue.group_package: index group_package_product_id_uniq; catalogue.product: columns valid_to, add_on_product_ids, created_at and updated_at; catalogue.product_eligibility_rule: index product_eligibility_rule_product_id_uniq; catalogue.product_version: column snapshot, row-level security apply_parent_rls; catalogue.published_bundle: column note, index published_bundle_venue_id_version_uniq; catalogue.variant: column reference_price); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0117__names_after_r1_20261026.sql (the names the contracts use: catalogue.event: foreign key event_parent_event_id_fkey, foreign key event_parent_event_id_fkey (from catalogue.event)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also apply seating.seat_reservation's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through catalogue.performance): MIG-SEATING creates seating.seat_reservation before catalogue.performance exists. **Leave out the key rate_price_category_id_fkey** (catalogue.rate to catalogue.price_category): MIG-CATALOGUE-8 creates catalogue.price_category later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `catalogue.alternative_code.scope_path`; column changed `catalogue.group_package.product_id`; not null `catalogue.product.created_at`; column changed `catalogue.product_eligibility_rule.product_id`; not null `catalogue.product_media.product_id`; not null `catalogue.product_version.product_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.alternative_code`, `catalogue.audit_entry`, `catalogue.channel_capacity`, `catalogue.channel_envelope`, `catalogue.demand_forecast`, `catalogue.dynamic_pricing_control`, `catalogue.dynamic_pricing_strategy`, `catalogue.entitlement_template` and 34 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 1 | MIG-LEDGER | AM-FOUNDATION-DATABASE | [DB] Migration V0023__ledger.sql: ledger (18 tables) | 8 | Hrushikant Patkar | LedgerService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: ledger.account, ledger.cost_center, ledger.credit_memo, ledger.credit_memo_line, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.fiscal_period, ledger.fx_provider_assignment, ledger.fx_rate, ledger.journal_entry, ledger.journal_line, ledger.legal_entity, ledger.posting, ledger.price_variance, ledger.tax_code, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template. Source DDL: backend/tenant/010-ledger.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (ledger.account: index account_code_uniq; ledger.credit_memo: index credit_memo_credit_memo_number_uniq; ledger.journal_entry: index journal_entry_entry_number_uniq; ledger.tax_code: index tax_code_code_uniq; ledger.tax_invoice: index tax_invoice_invoice_number_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ledger.account: index account_code_uniq, row-level security apply_parent_split_rls; ledger.cost_center: index cost_center_code_uniq; ledger.credit_memo: index credit_memo_credit_memo_number_uniq; ledger.fiscal_period: row-level security apply_parent_split_rls; ledger.journal_entry: column posting_date, index journal_entry_entry_number_uniq, row-level security apply_parent_split_rls; ledger.legal_entity: index legal_entity_code_uniq, row-level security apply_read_beneath_rls; ledger.tax_code: column scope_path, indexes tax_code_code_uniq and tax_code_scope_path_idx, row-level security apply_grant_holder_read_rls; ledger.tax_invoice: index tax_invoice_invoice_number_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ledger.account: rename column balance to balance_amount, foreign key journal_line_account_id_fkey (from ledger.journal_line); ledger.cost_center: foreign key requisition_cost_center_id_fkey (from inventory.requisition); ledger.credit_memo: foreign key credit_memo_legal_entity_id_fkey, foreign key credit_memo_tax_invoice_id_fkey; ledger.einvoice_transmission: foreign key einvoice_transmission_legal_entity_id_fkey, drop index einvoice_transmission_provider_message_id_idx; ledger.einvoicing_provider: foreign key einvoicing_provider_legal_entity_id_fkey, drop index einvoicing_provider_participant_id_idx; ledger.journal_entry: foreign key refund_tax_reversal_entry_id_fkey (from orders.refund), drop index journal_entry_entry_number_uniq; ledger.journal_line: foreign key journal_line_account_id_fkey; ledger.legal_entity: foreign key credit_memo_legal_entity_id_fkey (from ledger.credit_memo), foreign key einvoice_transmission_legal_entity_id_fkey (from ledger.einvoice_transmission), foreign key einvoicing_provider_legal_entity_id_fkey (from ledger.einvoicing_provider), foreign key inter_entity_obligation_from_legal_entity_id_fkey (from ledger.inter_entity_obligation), foreign key inter_entity_obligation_to_legal_entity_id_fkey (from ledger.inter_entity_obligation), foreign key tax_invoice_legal_entity_id_fkey (from ledger.tax_invoice), foreign key tax_invoice_template_legal_entity_id_fkey (from ledger.tax_invoice_template); ledger.price_variance: rename column quoted_price to quoted_amount, rename column server_price to server_amount, rename column variance to variance_amount; ledger.tax_code: foreign key tax_profile_tax_code_id_fkey (from catalogue.tax_profile); ledger.tax_invoice: foreign key credit_memo_tax_invoice_id_fkey (from ledger.credit_memo), foreign key tax_invoice_legal_entity_id_fkey; ledger.tax_invoice_line: rename column unit_price to unit_amount, drop index tax_invoice_line_order_id_idx; ledger.tax_invoice_template: foreign key tax_invoice_template_legal_entity_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (ledger.journal_entry: column legal_entity_id, DROP CONSTRAINT IF EXISTS journal_entry_source_chk; VALIDATE CONSTRAINT journal_entry_source_chk, constraints journal_entry_source_chk and journal_entry_legal_entity_id_fkey, indexes journal_entry_legal_entity_id_idx and journal_entry_legal_entity_id_entry_number_uniq; ledger.posting: DROP CONSTRAINT IF EXISTS posting_source_chk; VALIDATE CONSTRAINT posting_source_chk, constraint posting_source_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `ledger.tax_code.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ledger.account`, `ledger.cost_center`, `ledger.credit_memo`, `ledger.credit_memo_line`, `ledger.einvoice_transmission`, `ledger.einvoicing_provider`, `ledger.fiscal_period`, `ledger.fx_provider_assignment` and 10 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 1 | MIG-INVENTORY | AM-FOUNDATION-DATABASE | [DB] Migration V0024__inventory.sql: inventory (12 tables) | 8 | Hrushikant Patkar | InventoryService | MIG-BASELINE MIG-IDENTITY MIG-LEDGER MIG-PLATFORM | Tenant database. Tables: inventory.goods_receipt, inventory.goods_receipt_line, inventory.inventory_item, inventory.kit_component, inventory.location, inventory.movement, inventory.purchase_order, inventory.requisition, inventory.serialised_item, inventory.stock_batch, inventory.stock_earmark, inventory.supplier. Source DDL: backend/tenant/010-inventory.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: inventory.inventory_item: rename table inventory.item to inventory_item, rename column last_purchase_price to last_purchase_cost_amount, rename index item_preferred_supplier_id_idx to inventory_item_preferred_supplier_id_idx, rename index item_venue_id_idx to inventory_item_venue_id_idx, rename constraint item_preferred_supplier_id_fkey to inventory_item_preferred_supplier_id_fkey, rename constraint item_venue_id_fkey to inventory_item_venue_id_fkey, rename constraint item_barcode_chk to inventory_item_barcode_chk, rename constraint item_costing_method_chk to inventory_item_costing_method_chk, rename constraint item_name_chk to inventory_item_name_chk, rename constraint item_sku_chk to inventory_item_sku_chk, rename constraint item_pkey to inventory_item_pkey, rename policy item_* to inventory_item_*; inventory.stock_earmark: rename table inventory.stock_reservation to stock_earmark, rename index stock_reservation_item_id_idx to stock_earmark_item_id_idx, rename index stock_reservation_location_id_idx to stock_earmark_location_id_idx, rename constraint stock_reservation_source_type_chk to stock_earmark_source_type_chk, rename constraint stock_reservation_status_chk to stock_earmark_status_chk, rename constraint stock_reservation_pkey to stock_earmark_pkey, rename policy stock_reservation_* to stock_earmark_*); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (inventory.location: index location_venue_id_code_uniq; inventory.stock_batch: row-level security apply_grant_holder_read_rls; inventory.supplier: column contacts, index supplier_code_uniq, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: inventory.goods_receipt: foreign key goods_receipt_location_id_fkey; inventory.location: foreign key count_location_id_fkey (from inventory.count), foreign key goods_receipt_location_id_fkey (from inventory.goods_receipt), foreign key movement_location_id_fkey (from inventory.movement), foreign key purchase_order_deliver_to_location_id_fkey (from inventory.purchase_order), foreign key serialised_item_location_id_fkey (from inventory.serialised_item), foreign key transfer_from_location_id_fkey (from inventory.transfer), foreign key transfer_to_location_id_fkey (from inventory.transfer), foreign key location_rule_location_id_fkey (from rental.location_rule); inventory.movement: foreign key movement_location_id_fkey; inventory.purchase_order: foreign key purchase_order_deliver_to_location_id_fkey; inventory.requisition: rename column estimated_total to estimated_amount, foreign key requisition_cost_center_id_fkey; inventory.serialised_item: foreign key serialised_item_location_id_fkey; inventory.supplier: rename column minimum_order_value to minimum_order_amount, foreign key supplier_contract_supplier_id_fkey (from inventory.supplier_contract), foreign key vendor_service_request_supplier_id_fkey (from maintenance.vendor_service_request)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (inventory.inventory_item: index inventory_item_venue_id_sku_uniq; inventory.serialised_item: row-level security apply_parent_rls; inventory.stock_earmark: DROP CONSTRAINT IF EXISTS stock_earmark_source_type_chk; VALIDATE CONSTRAINT stock_earmark_source_type_chk, constraint stock_earmark_source_type_chk, row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: inventory.inventory_item: foreign key ingredient_substitute_from_inventory_item_id_fkey (from fnb.ingredient_substitute), foreign key ingredient_substitute_to_inventory_item_id_fkey (from fnb.ingredient_substitute), foreign key count_line_item_id_fkey (from inventory.count_line), foreign key kit_component_component_item_id_fkey (from inventory.kit_component), foreign key kit_component_kit_item_id_fkey (from inventory.kit_component), foreign key serialised_item_item_id_fkey (from inventory.serialised_item), foreign key stock_earmark_item_id_fkey (from inventory.stock_earmark), foreign key alert_item_id_fkey (from reporting.alert); inventory.kit_component: foreign key kit_component_component_item_id_fkey, foreign key kit_component_kit_item_id_fkey; inventory.location: foreign key stock_earmark_location_id_fkey (from inventory.stock_earmark); inventory.serialised_item: foreign key serialised_item_item_id_fkey; inventory.stock_earmark: foreign key stock_earmark_item_id_fkey, foreign key stock_earmark_location_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `inventory.goods_receipt`, `inventory.goods_receipt_line`, `inventory.inventory_item`, `inventory.kit_component`, `inventory.location`, `inventory.movement`, `inventory.purchase_order`, `inventory.requisition` and 4 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 1 | MIG-PROMOTIONS | AM-FOUNDATION-DATABASE | [DB] Migration V0025__promotions.sql: promotions (16 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE MIG-LEDGER MIG-PII MIG-PLATFORM | Tenant database. Tables: promotions.allocation_component, promotions.allocation_split, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component, promotions.code_assignment, promotions.coupon_campaign, promotions.coupon_code, promotions.coupon_code_batch, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication, promotions.promotion_evaluation_trace, promotions.promotion_rule, promotions.promotion_variant. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0101__after_r1_20261006.sql (promotions.promotion: index promotion_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (promotions.bundle: index bundle_code_uniq; promotions.coupon_campaign: index coupon_campaign_code_uniq; promotions.coupon_code_batch: row-level security apply_parent_rls; promotions.promotion: index promotion_code_uniq; promotions.promotion_variant: column scope_path, index promotion_variant_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: promotions.allocation_component: foreign key allocation_component_variant_id_fkey; promotions.bundle: foreign key bundle_capacity_policy_bundle_id_fkey (from promotions.bundle_capacity_policy); promotions.bundle_choice_option: foreign key bundle_choice_option_variant_id_fkey; promotions.bundle_component: foreign key bundle_component_variant_id_fkey, foreign key partner_bundle_product_bundle_component_id_fkey (from promotions.partner_bundle_product); promotions.code_assignment: foreign key code_assignment_batch_id_fkey; promotions.coupon_campaign: foreign key coupon_code_campaign_id_fkey (from promotions.coupon_code); promotions.coupon_code: foreign key coupon_code_campaign_id_fkey; promotions.coupon_code_batch: foreign key code_assignment_batch_id_fkey (from promotions.code_assignment), foreign key coupon_code_batch_campaign_id_fkey; promotions.promotion: foreign key promotion_audit_venue_id_promotion_id_fkey (from promotions.promotion_audit), foreign key promotion_channel_publication_venue_id_promotion_id_fkey (from promotions.promotion_channel_publication), foreign key promotion_rule_venue_id_promotion_id_fkey (from promotions.promotion_rule), foreign key promotion_variant_promotion_id_fkey (from promotions.promotion_variant), foreign key entry_priority_promotion_id_fkey (from queue.entry); promotions.promotion_audit: foreign key promotion_audit_venue_id_fkey, foreign key promotion_audit_venue_id_promotion_id_fkey; promotions.promotion_channel_publication: foreign key promotion_channel_publication_venue_id_fkey, foreign key promotion_channel_publication_venue_id_promotion_id_fkey; promotions.promotion_evaluation_trace: foreign key promotion_evaluation_trace_venue_id_fkey, foreign key promotion_evaluation_trace_venue_id_order_id_fkey; promotions.promotion_rule: foreign key promotion_rule_venue_id_fkey, foreign key promotion_rule_venue_id_promotion_id_fkey; promotions.promotion_variant: foreign key promotion_variant_promotion_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (promotions.bundle: column variant_id, constraint bundle_variant_id_fkey, index bundle_variant_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (promotions.promotion: columns name_localised, description_localised, label and venues); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **promotions.coupon_code_batch's row-level security waits for its parent**: its policy reads promotions.campaign, which MIG-PROMOTIONS-2 creates later, so leave out its `platform.apply_parent_rls` call here; MIG-PROMOTIONS-2 applies it. **Leave out the key coupon_code_batch_campaign_id_fkey** (promotions.coupon_code_batch to promotions.campaign): MIG-PROMOTIONS-2 creates promotions.campaign later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `promotions.promotion_variant.scope_path`; constraint added `promotions.promotion promotion_venue_id_id_uniq`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.allocation_component`, `promotions.allocation_split`, `promotions.bundle`, `promotions.bundle_choice_group`, `promotions.bundle_choice_option`, `promotions.bundle_component`, `promotions.code_assignment`, `promotions.coupon_campaign` and 8 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 1 | MIG-ORDERS | AM-FOUNDATION-DATABASE | [DB] Migration V0026__orders.sql: orders (44 tables) | 8 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-LEDGER MIG-PII MIG-PLATFORM MIG-PROMOTIONS | Tenant database. Tables: orders.cart, orders.cart_line, orders.cash_count_line, orders.cash_movement, orders.chargeback, orders.deposit, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, orders.fraud_rule, orders.group_booking, orders.group_customer_organisation, orders.group_customer_organisation_contact, orders.group_participant, orders.group_participant_list, orders.group_visit_plan, orders.invitation, orders.no_sale_event, orders.order_event, orders.order_fee, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.payment_link, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, orders.refund, orders.refund_line, orders.refund_payment, orders.refund_policy, orders.refund_policy_time_band, orders.resale_listing, orders.reservation, orders.reservation_line, orders.sales_order, orders.stored_value_authorisation, orders.ticket_template, orders.ticket_template_channel, orders.ticket_transfer, orders.till_shift_policy, orders.visit_reminder, orders.wallet_pass. Source DDL: backend/tenant/010-orders.sql and backend/tenant/V0116__after_r1_20261026.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (orders.pos_shift: column business_date; orders.sales_order: column channel_profile_id, index sales_order_order_number_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: orders.group_customer_organisation: rename table orders.group_customer_organization to group_customer_organisation, rename constraint group_customer_organization_name_chk to group_customer_organisation_name_chk, rename constraint group_customer_organization_organisation_type_chk to group_customer_organisation_organisation_type_chk, rename constraint group_customer_organization_pkey to group_customer_organisation_pkey, rename policy group_customer_organization_* to group_customer_organisation_*; orders.group_customer_organisation_contact: rename table orders.group_customer_organization_contact to group_customer_organisation_contact, rename column group_customer_organization_id to group_customer_organisation_id, rename index group_customer_organization_contact_group_customer_a397067a_idx to group_customer_organisation_contact_group_customer_2ad51596_idx, rename constraint group_customer_organization_contact_group_custome_942e0f58_fkey to group_customer_organisation_contact_group_custome_3b68685a_fkey, rename constraint group_customer_organization_contact_pkey to group_customer_organisation_contact_pkey, rename policy group_customer_organization_contact_* to group_customer_organisation_contact_*); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (orders.deposit_box: column recorded_at; orders.fraud_rule: row-level security apply_read_beneath_rls; orders.group_participant: row-level security apply_parent_rls; orders.group_participant_list: row-level security apply_parent_rls; orders.invitation: column scope_path, index invitation_scope_path_idx, row-level security apply_scope_rls; orders.sales_order: index sales_order_order_number_uniq; orders.ticket_template: column scope_path, index ticket_template_scope_path_idx, row-level security apply_grant_holder_read_rls; orders.ticket_template_channel: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.cart_line: rename column resource_hold_id to resource_reservation_id, rename column inventory_hold_id to inventory_reservation_id, rename constraint cart_line_inventory_hold_id_fkey to cart_line_inventory_reservation_id_fkey, rename index cart_line_resource_hold_id_idx to cart_line_resource_reservation_id_idx, rename index cart_line_inventory_hold_id_idx to cart_line_inventory_reservation_id_idx; orders.cash_count_line: foreign key cash_count_line_denomination_id_fkey; orders.cash_movement: rename column amount to movement_amount; orders.chargeback: foreign key chargeback_evidence_chargeback_id_fkey (from payments.chargeback_evidence); orders.deposit_box: rename column withdrawn_total to withdrawn_amount, rename column expected_total to expected_amount, rename column counted_total to counted_amount, rename column variance to variance_amount; orders.deposit_box_foreign_holding: rename column variance to variance_amount; orders.deposit_box_opening_denomination: foreign key deposit_box_opening_denomination_denomination_id_fkey; orders.group_booking: foreign key group_booking_leader_subject_id_fkey, foreign key group_participant_list_group_booking_id_fkey (from orders.group_participant_list), foreign key group_payment_schedule_group_booking_id_fkey (from orders.group_payment_schedule), foreign key group_ticket_allocation_group_booking_id_fkey (from orders.group_ticket_allocation), foreign key group_ticket_fulfillment_group_booking_id_fkey (from orders.group_ticket_fulfillment); orders.group_participant_list: foreign key group_participant_list_group_booking_id_fkey; orders.invitation: foreign key invitation_offered_by_principal_id_fkey; orders.order_event: foreign key order_event_order_id_fkey; orders.order_line: rename column inventory_hold_id to inventory_reservation_id, rename column resource_hold_id to resource_reservation_id, rename constraint order_line_inventory_hold_id_fkey to order_line_inventory_reservation_id_fkey, rename index order_line_resource_hold_id_idx to order_line_resource_reservation_id_idx, rename index order_line_inventory_hold_id_idx to order_line_inventory_reservation_id_idx, foreign key upgrade_original_order_line_id_fkey (from orders.upgrade), foreign key agreement_item_order_line_id_fkey (from rental.agreement_item); orders.order_line_eligibility: rename column confident_swimmer to is_confident_swimmer; orders.payment: rename column amount to payment_amount; orders.payment_link: rename column release_hold_on_expiry to releases_reservation_on_expiry; orders.pos_shift_approval: foreign key pos_shift_approval_principal_id_fkey; orders.refund: rename column amount to refunded_amount, foreign key refund_tax_reversal_entry_id_fkey; orders.resale_listing: foreign key resale_listing_seller_subject_id_fkey; orders.reservation_line: rename column inventory_hold_id to inventory_reservation_id, rename column resource_hold_id to resource_reservation_id, rename index reservation_line_resource_hold_id_idx to reservation_line_resource_reservation_id_idx, rename index reservation_line_inventory_hold_id_idx to reservation_line_inventory_reservation_id_idx, foreign key reservation_line_variant_id_fkey; orders.sales_order: foreign key case_service_action_order_id_fkey (from marketing.case_service_action), foreign key waiver_requirement_order_id_fkey (from marketing.waiver_requirement), foreign key after_sale_request_order_id_fkey (from orders.after_sale_request), foreign key external_reference_mapping_order_id_fkey (from orders.external_reference_mapping), foreign key order_event_order_id_fkey (from orders.order_event), foreign key order_relationship_order_id_fkey (from orders.order_relationship), foreign key order_relationship_related_order_id_fkey (from orders.order_relationship), foreign key instalment_plan_order_id_fkey (from payments.instalment_plan), foreign key promotion_evaluation_trace_venue_id_order_id_fkey (from promotions.promotion_evaluation_trace); orders.stored_value_authorisation: foreign key booking_deposit_authorisation_id_fkey (from rental.booking), foreign key booking_deposit_authorisation_id_fkey (from resources.booking); orders.till_shift_policy: foreign key till_shift_policy_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (orders.cart: columns session_id and workstation_id; orders.group_booking: column performance_id; orders.order_event: column order_id, DROP CONSTRAINT IF EXISTS order_event_reservation_id_when_chk; VALIDATE CONSTRAINT order_event_reservation_id_when_chk, constraint order_event_reservation_id_when_chk; orders.payment: index payment_provider_reference_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: orders.reservation_line: foreign key reservation_line_inventory_reservation_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0110__after_r1_20261020.sql (orders.cart: indexes cart_session_id_idx and cart_workstation_id_idx; orders.group_booking: index group_booking_performance_id_idx; orders.no_sale_event: column approved_by_principal_id, constraint no_sale_event_approved_by_principal_id_fkey, index no_sale_event_approved_by_principal_id_idx; orders.order_event: columns reason_code, approved_by_principal_id and note, constraint order_event_approved_by_principal_id_fkey, index order_event_approved_by_principal_id_idx; orders.payment: columns tip_amount, tip_source, tip_allocated_to_principal_id, tip_recorded_at and tip_recorded_by_principal_id, constraints payment_tip_allocated_to_principal_id_fkey and payment_tip_recorded_by_principal_id_fkey, indexes payment_tip_allocated_to_principal_id_idx and payment_tip_recorded_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (orders.cart: row-level security apply_split_rls; orders.cart_line: row-level security apply_parent_split_rls; orders.chargeback: row-level security apply_parent_split_rls; orders.deposit: row-level security apply_parent_split_rls; orders.group_booking: row-level security apply_parent_split_rls; orders.group_participant: row-level security apply_parent_split_rls; orders.group_participant_list: row-level security apply_parent_split_rls; orders.order_event: row-level security apply_split_rls; orders.order_fee: row-level security apply_parent_split_rls; orders.order_line: row-level security apply_split_rls; orders.order_line_discount: row-level security apply_parent_split_rls; orders.order_line_eligibility: row-level security apply_parent_split_rls; orders.payment: row-level security apply_parent_split_rls; orders.refund: row-level security apply_parent_split_rls; orders.sales_order: row-level security apply_split_rls; orders.ticket_transfer: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0115__names_after_r1_20261022.sql (the names the contracts use: orders.payment: change foreign key booking_deposit_authorisation_id_fkey (from rental.booking)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (orders.group_booking: column version; orders.payment_link: index payment_link_token_uniq; orders.refund_policy_time_band: column refund_type; orders.stored_value_authorisation: column wallet_hold_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (orders.cart: row-level security apply_split_rls; orders.cart_line: row-level security apply_parent_split_rls; orders.order_event: row-level security apply_split_rls; orders.order_line: row-level security apply_split_rls; orders.sales_order: row-level security apply_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `orders.invitation.scope_path`; not null `orders.ticket_template.scope_path`; statement dropped `orders.payment, orders.payment_tip`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.cart`, `orders.cart_line`, `orders.cash_count_line`, `orders.cash_movement`, `orders.chargeback`, `orders.deposit`, `orders.deposit_box`, `orders.deposit_box_foreign_holding` and 36 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 1 | MIG-ACCESS | AM-FOUNDATION-DATABASE | [DB] Migration V0027__access.sql: access (19 tables) | 8 | Hrushikant Patkar | AccessService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: access.access_incident, access.access_point, access.access_point_group, access.admission_rules, access.biometric_audit_event, access.biometric_profile, access.blacklist, access.configuration_change, access.credential_policy, access.device_binding, access.device_placement, access.entitlement, access.entry_rule_point, access.face_reenrolment_attempt, access.gate_mode_change, access.gate_mode_policy, access.parking_entitlement, access.parking_facility, access.scan_event. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (access.entitlement: column credential_format); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: access.entry_rule_point: rename column admission_profile_id to admission_rules_id); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (access.access_point: columns direction_effective_at and direction_change_reason, index access_point_venue_id_code_uniq; access.admission_rules: index admission_rules_code_uniq; access.configuration_change: column reason; access.entry_rule_point: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.access_incident: foreign key access_incident_venue_id_fkey; access.access_point: rename column vehicle_location_capture to captures_vehicle_location, foreign key access_point_configuration_venue_id_access_point_id_fkey (from access.access_point_configuration), foreign key entry_rule_point_access_point_id_fkey (from access.entry_rule_point), foreign key gate_lane_venue_id_access_point_id_fkey (from access.gate_lane), foreign key gate_mode_change_venue_id_access_point_id_fkey (from access.gate_mode_change); access.access_point_group: foreign key access_point_group_venue_id_fkey; access.admission_rules: rename column same_day_only to is_same_day_only; access.biometric_audit_event: foreign key biometric_audit_event_venue_id_fkey; access.biometric_profile: rename column operator_verification to requires_operator_verification, rename column duplicate_face_check to has_duplicate_face_check, rename column liveness_check to has_liveness_check, rename column operator_fallback to has_operator_fallback, foreign key biometric_profile_venue_id_fkey; access.configuration_change: foreign key configuration_change_changed_by_principal_id_fkey; access.credential_policy: rename column before_first_validation_only to is_before_first_validation_only, rename column return_to_sender to returns_to_sender; access.device_binding: foreign key device_binding_device_id_fkey, foreign key device_binding_entitlement_id_fkey; access.device_placement: foreign key device_placement_venue_id_fkey; access.entitlement: foreign key access_change_new_entitlement_id_fkey (from access.access_change), foreign key access_change_old_entitlement_id_fkey (from access.access_change), foreign key credential_binding_entitlement_id_fkey (from access.credential_binding), foreign key credential_delivery_entitlement_id_fkey (from access.credential_delivery), foreign key credential_event_entitlement_id_fkey (from access.credential_event), foreign key credential_issuance_entitlement_id_fkey (from access.credential_issuance), foreign key credential_sharing_case_entitlement_id_fkey (from access.credential_sharing_case), foreign key device_binding_entitlement_id_fkey (from access.device_binding), foreign key entitlement_template_id_fkey; access.entry_rule_point: rename constraint entry_rule_point_admission_profile_id_fkey to entry_rule_point_admission_rules_id_fkey, rename index entry_rule_point_admission_profile_id_idx to entry_rule_point_admission_rules_id_idx, foreign key entry_rule_point_access_point_id_fkey; access.face_reenrolment_attempt: foreign key face_reenrolment_attempt_subject_id_fkey, foreign key face_reenrolment_attempt_venue_id_fkey; access.gate_mode_change: foreign key gate_mode_change_changed_by_principal_id_fkey, foreign key gate_mode_change_venue_id_access_point_id_fkey, foreign key gate_mode_change_venue_id_fkey; access.gate_mode_policy: rename column automatic_notification to has_automatic_notification, foreign key gate_mode_policy_venue_id_fkey; access.scan_event: rename column ticket_id to entitlement_id, rename constraint scan_event_ticket_id_fkey to scan_event_entitlement_id_fkey, rename index scan_event_ticket_id_idx to scan_event_entitlement_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (access.access_point: column access_area_id, constraint access_point_access_area_id_fkey, index access_point_access_area_id_idx; access.gate_mode_change: columns cancelled_by_principal_id, cancelled_at and cancel_reason, constraint gate_mode_change_cancelled_by_principal_id_fkey, index gate_mode_change_cancelled_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (access.entitlement: columns change_version, media_linked_at and rotation_secret_ciphertext, index entitlement_venue_id_change_version_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also apply pii.subject_biometric's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through access.entitlement): MIG-PII creates pii.subject_biometric before access.entitlement exists. **Leave out the key access_point_access_area_id_fkey** (access.access_point to access.access_area): MIG-ACCESS-2 creates access.access_area later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `access.device_binding.device_id`; not null `access.entitlement.change_version`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.access_incident`, `access.access_point`, `access.access_point_group`, `access.admission_rules`, `access.biometric_audit_event`, `access.biometric_profile`, `access.blacklist`, `access.configuration_change` and 11 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 1 | MIG-MARKETING | AM-FOUNDATION-DATABASE | [DB] Migration V0028__marketing.sql: marketing (56 tables) | 8 | Hrushikant Patkar | MarketingService | MIG-AI MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: marketing.agent_availability, marketing.attribution_touch, marketing.booking_consent_record, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.case, marketing.case_message, marketing.challenge, marketing.challenge_progress, marketing.consent_propagation, marketing.consent_purpose, marketing.consent_purpose_channel, marketing.consent_question, marketing.consent_question_version, marketing.consent_record, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment, marketing.cookie_banner_design, marketing.customer_badge, marketing.device_consent, marketing.device_consent_category, marketing.form_definition, marketing.form_definition_field, marketing.form_submission, marketing.form_submission_sale_link, marketing.guest_device, marketing.guest_document, marketing.guest_preference, marketing.guest_profile, marketing.invitation, marketing.invitation_campaign, marketing.journey, marketing.lost_item, marketing.loyalty_position, marketing.loyalty_programme, marketing.loyalty_rule, marketing.message_dispatch, marketing.message_template, marketing.message_template_version, marketing.points_earning_rule, marketing.points_redemption_rule, marketing.privacy_notice_governance, marketing.programme_tier, marketing.referral, marketing.review, marketing.reward, marketing.segment, marketing.segment_criterion, marketing.subscription, marketing.tracking_technology, marketing.waiver_field_rule, marketing.waiver_requirement, marketing.waiver_requirement_event, marketing.wishlist_item. Source DDL: backend/tenant/010-marketing.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: marketing.wishlist_item: rename column price to list_price); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.agent_availability: row-level security apply_grant_holder_read_rls; marketing.campaign_target: row-level security apply_parent_rls; marketing.case_message: column scope_path, index case_message_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.consent_purpose: row-level security apply_grant_holder_read_rls; marketing.consent_purpose_channel: row-level security apply_grant_holder_read_rls; marketing.consent_question_version: row-level security apply_parent_rls; marketing.consent_record: row-level security apply_grant_holder_subject_read_rls; marketing.cookie_banner_design: columns buttons, links and categories; marketing.customer_badge: row-level security apply_parent_split_rls; marketing.form_submission: row-level security apply_grant_holder_subject_read_rls; marketing.guest_device: column installation_id, indexes guest_device_subject_id_installation_id_uniq and guest_device_subject_id_token_fingerprint_uniq; marketing.guest_document: row-level security apply_grant_holder_subject_read_rls; marketing.guest_preference: row-level security apply_grant_holder_subject_read_rls; marketing.invitation: columns campaign_id, subject_id, token, plus_ones, status and responded_at, constraint invitation_campaign_id_fkey, indexes invitation_subject_id_idx and invitation_campaign_id_idx; marketing.loyalty_programme: index loyalty_programme_code_uniq; marketing.loyalty_rule: row-level security apply_parent_rls; marketing.message_dispatch: row-level security apply_grant_holder_subject_read_rls; marketing.message_template: index message_template_tenant_id_code_uniq, row-level security apply_grant_holder_read_rls; marketing.points_redemption_rule: column scope_path, index points_redemption_rule_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.referral: index referral_code_uniq; marketing.reward: column scope_path, index reward_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.wishlist_item: index wishlist_item_subject_id_variant_id_performance_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (marketing.invitation: columns product_id and offered_by_principal_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.booking_consent_record: drop index booking_consent_record_order_id_idx; marketing.campaign: rename column optimise_channel to optimises_channel, foreign key campaign_target_campaign_id_fkey (from marketing.campaign_target), foreign key loyalty_rule_campaign_id_fkey (from marketing.loyalty_rule); marketing.campaign_target: foreign key campaign_target_campaign_id_fkey; marketing.case: foreign key case_compensation_request_case_id_fkey (from marketing.case_compensation_request), foreign key case_escalation_case_id_fkey (from marketing.case_escalation), foreign key case_internal_request_case_id_fkey (from marketing.case_internal_request), foreign key case_linked_record_case_id_fkey (from marketing.case_linked_record), foreign key case_resolution_case_id_fkey (from marketing.case_resolution); marketing.consent_propagation: foreign key consent_propagation_consent_record_id_fkey; marketing.consent_question: foreign key consent_question_version_question_id_fkey (from marketing.consent_question_version); marketing.consent_question_version: foreign key consent_question_version_question_id_fkey; marketing.consent_record: foreign key consent_propagation_consent_record_id_fkey (from marketing.consent_propagation); marketing.conversation_message: rename column ai_interaction_id to ai_activity_id, rename constraint conversation_message_ai_interaction_id_fkey to conversation_message_ai_activity_id_fkey, rename index conversation_message_ai_interaction_id_idx to conversation_message_ai_activity_id_idx; marketing.cookie_banner_design: rename column reject_is_one_click to is_reject_one_click, rename column record_ip_address to records_ip_address; marketing.customer_badge: foreign key customer_badge_badge_id_fkey; marketing.device_consent: rename column global_privacy_control to honours_global_privacy_control, foreign key consent_identifier_device_consent_id_fkey (from pii.consent_identifier); marketing.form_definition: foreign key waiver_requirement_form_definition_id_fkey (from marketing.waiver_requirement), foreign key waiver_signature_form_definition_id_fkey (from marketing.waiver_signature); marketing.form_submission: foreign key waiver_verification_submission_id_fkey (from marketing.waiver_verification); marketing.guest_device: rename column token_ref to token_ciphertext; marketing.journey: foreign key journey_enrollment_journey_id_fkey (from marketing.journey_enrollment); marketing.loyalty_rule: foreign key loyalty_rule_campaign_id_fkey; marketing.message_template: foreign key message_template_version_message_template_id_fkey (from marketing.message_template_version), foreign key message_trigger_template_id_fkey (from marketing.message_trigger); marketing.message_template_version: foreign key message_template_version_message_template_id_fkey; marketing.programme_tier: foreign key entry_priority_tier_id_fkey (from queue.entry); marketing.referral: foreign key referral_referrer_subject_id_fkey; marketing.review: rename column response_is_public to is_response_public, foreign key review_response_review_id_fkey (from marketing.review_response); marketing.reward: foreign key reward_assignment_reward_id_fkey (from marketing.reward_assignment); marketing.segment: foreign key audience_activation_segment_id_fkey (from marketing.audience_activation); marketing.subscription: foreign key subscription_subject_id_fkey; marketing.waiver_requirement: foreign key waiver_exception_requirement_id_fkey (from marketing.waiver_exception), foreign key waiver_requirement_form_definition_id_fkey, foreign key waiver_requirement_order_id_fkey, foreign key waiver_requirement_participant_subject_id_fkey, foreign key waiver_requirement_event_waiver_requirement_id_fkey (from marketing.waiver_requirement_event), drop index waiver_requirement_product_id_idx; marketing.waiver_requirement_event: foreign key waiver_requirement_event_waiver_requirement_id_fkey; marketing.wishlist_item: foreign key wishlist_item_variant_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (marketing.consent_purpose: DROP CONSTRAINT IF EXISTS consent_purpose_purpose_chk; VALIDATE CONSTRAINT consent_purpose_purpose_chk, constraint consent_purpose_purpose_chk; marketing.consent_record: DROP CONSTRAINT IF EXISTS consent_record_purpose_chk; VALIDATE CONSTRAINT consent_record_purpose_chk, constraint consent_record_purpose_chk; marketing.customer_badge: DROP CONSTRAINT IF EXISTS customer_badge_source_type_chk; DROP CONSTRAINT IF EXISTS customer_badge_status_chk, constraints customer_badge_source_type_chk and customer_badge_status_chk, row-level security apply_split_rls; marketing.form_definition_field: column presentation; marketing.guest_device: DROP CONSTRAINT IF EXISTS guest_device_token_fingerprint_chk, constraint guest_device_token_fingerprint_chk, column pending_session_end_installation_id; marketing.loyalty_position: row-level security apply_split_rls; marketing.loyalty_programme: row-level security apply_split_rls; marketing.points_earning_rule: row-level security apply_split_rls; marketing.programme_tier: row-level security apply_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0110__after_r1_20261020.sql (marketing.form_submission_sale_link: index form_submission_sale_link_order_line_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (marketing.consent_record: row-level security apply_grant_holder_subject_rls; marketing.guest_preference: index guest_preference_subject_id_uniq; marketing.guest_profile: index guest_profile_subject_id_uniq, row-level security apply_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Leave out the key customer_badge_badge_id_fkey** (marketing.customer_badge to marketing.badge): MIG-MARKETING-15 creates marketing.badge later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.case_message.scope_path`; not null `marketing.case_message.case_id`; not null `marketing.cookie_banner_design.categories`; not null `marketing.invitation.campaign_id`; not null `marketing.invitation.token`; not null `marketing.invitation.status`; column retired `marketing.invitation.product_id`; column retired `marketing.invitation.performance_id`; column dropped `marketing.invitation.quantity`; column dropped `marketing.invitation.reason`; column retired `marketing.invitation.offered_by_principal_id`; column retired `marketing.invitation.issued_by_principal_id`; column dropped `marketing.invitation.recipient_name`; column retired `marketing.invitation.cost_center_id`; column dropped `marketing.invitation.issued_at`; not null `marketing.points_redemption_rule.scope_path`; not null `marketing.reward.scope_path`; column changed `marketing.wishlist_item.list_price`; statement dropped `marketing.campaign, marketing.message_delivery`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.agent_availability`, `marketing.attribution_touch`, `marketing.booking_consent_record`, `marketing.campaign`, `marketing.campaign_target`, `marketing.campaign_variant`, `marketing.case`, `marketing.case_message` and 48 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 1 | MIG-ACCESS-2 | AM-FOUNDATION-DATABASE | [DB] Forward migration V1078__access.sql: access for the first release (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE | Tables: access.access_area. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze), pushed before the first release needed it and kept under its pushed key (CHG-R6G-001); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.access_area: rename column support_multi_park_environments to supports_multi_park_environments); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key access_point_access_area_id_fkey here** (access.access_point to access.access_area, guarded): MIG-ACCESS creates access.access_point before access.access_area exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.access_area` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 1 | MIG-FNB | AM-FOUNDATION-DATABASE | [DB] Migration V0029__fnb.sql: fnb (41 tables) | 8 | Hrushikant Patkar | FnbService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-INVENTORY MIG-ORDERS MIG-PII MIG-PLATFORM MIG-SEATING | Tenant database. Tables: fnb.allergen_verdict, fnb.bill_split, fnb.cold_chain_event, fnb.corrective_action, fnb.course_rule, fnb.delivery_location, fnb.delivery_location_outlet, fnb.delivery_policy, fnb.dining_table, fnb.kitchen_exception, fnb.kitchen_sla, fnb.kitchen_station, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.location_session, fnb.menu, fnb.menu_item, fnb.menu_item_modifier, fnb.menu_schedule, fnb.menu_section, fnb.menu_version, fnb.modifier_group, fnb.modifier_option, fnb.order_fulfilment, fnb.production_plan, fnb.production_plan_line, fnb.production_run, fnb.recipe, fnb.recipe_ingredient, fnb.reservation_table, fnb.service_order, fnb.service_order_line, fnb.sold_out_item, fnb.sub_bill, fnb.substitution_rule, fnb.table_combination, fnb.table_reservation, fnb.table_session, fnb.table_visit, fnb.temperature_log, fnb.waitlist_entry. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0103__after_r1_20261013.sql (fnb.production_plan_line: index production_plan_line_item_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (fnb.allergen_verdict: row-level security apply_parent_rls; fnb.cold_chain_event: column scope_path, index cold_chain_event_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.delivery_location: index delivery_location_venue_id_label_uniq; fnb.delivery_location_outlet: row-level security apply_grant_holder_read_rls; fnb.dining_table: column scope_path, indexes dining_table_scope_path_label_uniq and dining_table_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.kitchen_exception: column scope_path, index kitchen_exception_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.kitchen_sla: row-level security apply_parent_rls; fnb.kitchen_station: column scope_path, index kitchen_station_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.menu_item: column unavailable_note, row-level security apply_parent_rls; fnb.menu_item_modifier: row-level security apply_parent_rls; fnb.modifier_group: index modifier_group_scope_path_code_uniq; fnb.production_plan: column scope_path, index production_plan_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.production_plan_line: row-level security apply_parent_split_rls; fnb.reservation_table: row-level security apply_parent_split_rls; fnb.sold_out_item: row-level security apply_parent_rls; fnb.substitution_rule: row-level security apply_parent_rls; fnb.table_visit: column note; fnb.temperature_log: column scope_path, index temperature_log_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (fnb.kitchen_sla: row-level security apply_parent_across_rls; fnb.kitchen_ticket: row-level security apply_parent_across_rls; fnb.menu: row-level security apply_parent_across_rls; fnb.service_order: row-level security apply_parent_across_rls; fnb.table_reservation: row-level security apply_parent_across_rls; fnb.table_session: row-level security apply_parent_across_rls; fnb.table_visit: row-level security apply_parent_across_rls; fnb.waitlist_entry: row-level security apply_parent_across_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: fnb.allergen_verdict: foreign key allergen_verdict_menu_item_id_fkey; fnb.delivery_policy: rename column cutlery_opt_in to is_cutlery_opted_in, foreign key delivery_policy_outlet_id_fkey; fnb.kitchen_sla: foreign key kitchen_sla_outlet_id_fkey; fnb.kitchen_station: foreign key kitchen_routing_rule_default_station_id_fkey (from fnb.kitchen_routing_rule); fnb.kitchen_ticket: foreign key kitchen_ticket_order_id_fkey; fnb.location_session: rename column joined_existing_visit to has_joined_existing_visit; fnb.menu: foreign key menu_schedule_menu_id_fkey (from fnb.menu_schedule), foreign key menu_version_menu_id_fkey (from fnb.menu_version); fnb.menu_item: foreign key allergen_verdict_menu_item_id_fkey (from fnb.allergen_verdict), foreign key combo_slot_option_menu_item_id_fkey (from fnb.combo_slot_option), foreign key menu_item_menu_section_id_fkey, foreign key menu_item_modifier_item_id_fkey (from fnb.menu_item_modifier), foreign key production_plan_line_item_id_fkey (from fnb.production_plan_line), foreign key service_order_line_menu_item_id_fkey (from fnb.service_order_line), foreign key sold_out_item_menu_item_id_fkey (from fnb.sold_out_item); fnb.menu_item_modifier: foreign key menu_item_modifier_group_id_fkey, foreign key menu_item_modifier_item_id_fkey; fnb.menu_schedule: foreign key menu_schedule_menu_id_fkey; fnb.menu_section: foreign key menu_item_menu_section_id_fkey (from fnb.menu_item); fnb.menu_version: foreign key menu_version_menu_id_fkey; fnb.modifier_group: foreign key menu_item_modifier_group_id_fkey (from fnb.menu_item_modifier); fnb.production_plan_line: foreign key production_plan_line_item_id_fkey; fnb.recipe: foreign key substitution_rule_recipe_id_fkey (from fnb.substitution_rule); fnb.recipe_ingredient: foreign key substitution_rule_from_ingredient_id_fkey (from fnb.substitution_rule), foreign key substitution_rule_to_ingredient_id_fkey (from fnb.substitution_rule); fnb.reservation_table: foreign key reservation_table_reservation_id_fkey; fnb.service_order: foreign key kitchen_ticket_order_id_fkey (from fnb.kitchen_ticket); fnb.service_order_line: foreign key service_order_line_menu_item_id_fkey; fnb.sold_out_item: foreign key sold_out_item_menu_item_id_fkey; fnb.sub_bill: foreign key sub_bill_visit_id_fkey; fnb.substitution_rule: foreign key substitution_rule_from_ingredient_id_fkey, foreign key substitution_rule_recipe_id_fkey, foreign key substitution_rule_to_ingredient_id_fkey; fnb.table_reservation: foreign key reservation_table_reservation_id_fkey (from fnb.reservation_table); fnb.table_session: rename column joined_existing_visit to has_joined_existing_visit; fnb.table_visit: foreign key sub_bill_visit_id_fkey (from fnb.sub_bill)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (fnb.delivery_location: columns opens_at and closes_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `fnb.cold_chain_event.scope_path`; not null `fnb.dining_table.scope_path`; not null `fnb.kitchen_exception.scope_path`; not null `fnb.kitchen_station.scope_path`; not null `fnb.menu_item.menu_section_id`; not null `fnb.production_plan.scope_path`; not null `fnb.temperature_log.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.allergen_verdict`, `fnb.bill_split`, `fnb.cold_chain_event`, `fnb.corrective_action`, `fnb.course_rule`, `fnb.delivery_location`, `fnb.delivery_location_outlet`, `fnb.delivery_policy` and 33 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 1 | MIG-PAYMENTS | AM-FOUNDATION-DATABASE | [DB] Migration V0030__payments.sql: payments (8 tables) | 5 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-MARKETING MIG-ORDERS MIG-PII | Tenant database. Tables: payments.dunning_case, payments.dunning_policy, payments.method, payments.payment_attempt, payments.provider, payments.provider_connection, payments.routing_rule, payments.token. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.method: index method_code_uniq; payments.provider_connection: index provider_connection_code_uniq, row-level security apply_read_beneath_rls; payments.routing_rule: column targets; payments.token: row-level security apply_grant_holder_subject_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (payments.provider: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.dunning_case: rename column amount to overdue_amount; payments.method: foreign key eligibility_rule_payment_method_id_fkey (from payments.eligibility_rule), foreign key method_config_payment_method_id_fkey (from payments.method_config); payments.payment_attempt: rename column amount to attempted_amount; payments.provider: rename column supports3ds to supports_3ds, foreign key routing_rule_fallback_provider_id_fkey (from payments.routing_rule), foreign key routing_rule_provider_id_fkey (from payments.routing_rule), foreign key token_provider_id_fkey (from payments.token); payments.routing_rule: foreign key routing_rule_fallback_provider_id_fkey, foreign key routing_rule_provider_id_fkey; payments.token: foreign key token_provider_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (payments.provider_connection: column provider_id, constraint provider_connection_provider_id_fkey, index provider_connection_provider_id_idx; payments.token: column revoked_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (payments.token: row-level security apply_grant_holder_subject_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.dunning_case`, `payments.dunning_policy`, `payments.method`, `payments.payment_attempt`, `payments.provider`, `payments.provider_connection`, `payments.routing_rule`, `payments.token` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 1 | MIG-QUEUE | AM-FOUNDATION-DATABASE | [DB] Migration V0031__queue.sql: queue (4 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-MAINTENANCE MIG-PII MIG-PLATFORM | Tenant database. Tables: queue.entry, queue.queue, queue.queue_operating_window, queue.reading. Source DDL: backend/tenant/010-queue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (queue.entry: index entry_priority_tier_id_idx; queue.queue: index queue_venue_id_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: queue.entry: foreign key entry_overridden_by_principal_id_fkey, foreign key entry_priority_promotion_id_fkey, foreign key entry_priority_tier_id_fkey; queue.queue: rename column accessibility_priority to has_accessibility_priority, foreign key queue_parent_queue_id_fkey, foreign key queue_parent_queue_id_fkey (from queue.queue), drop index queue_fast_pass_id_idx; queue.reading: foreign key reading_feed_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Leave out the key reading_feed_id_fkey** (queue.reading to queue.feed): VM-MIG-QUEUE creates queue.feed later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column dropped `queue.queue.fast_pass_id`; not null `queue.reading.feed_id`; constraint dropped `queue.queue queue_fast_pass_id_fkey`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `queue.entry`, `queue.queue`, `queue.queue_operating_window`, `queue.reading` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 1 | MIG-VENUEMAP | AM-FOUNDATION-DATABASE | [DB] Migration V0033__venuemap.sql: venuemap (9 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-ASSETS MIG-BASELINE MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS MIG-RESOURCES | Tenant database. Tables: venuemap.import_job, venuemap.map, venuemap.map_version, venuemap.path, venuemap.placed_resource, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item, venuemap.visit_plan_preset. Source DDL: backend/tenant/010-venuemap.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (venuemap.import_job: columns scope_path and findings, index import_job_scope_path_idx, row-level security apply_grant_holder_read_rls; venuemap.map_version: row-level security apply_parent_rls; venuemap.path: columns is_closed, expected_reopen_at and closed_note; venuemap.placed_resource: column boundary, row-level security apply_parent_rls; venuemap.point: column media; venuemap.visit_plan: column excluded); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: venuemap.map: foreign key access_map_venue_id_map_id_fkey (from access.access_map), foreign key map_version_map_id_fkey (from venuemap.map_version), foreign key placed_resource_map_id_fkey (from venuemap.placed_resource); venuemap.map_version: foreign key map_version_map_id_fkey, foreign key map_version_published_by_principal_id_fkey; venuemap.path: foreign key path_from_point_id_fkey, foreign key path_restricted_by_point_id_fkey, foreign key path_to_point_id_fkey; venuemap.placed_resource: foreign key placed_resource_map_id_fkey; venuemap.point: foreign key path_from_point_id_fkey (from venuemap.path), foreign key path_restricted_by_point_id_fkey (from venuemap.path), foreign key path_to_point_id_fkey (from venuemap.path); venuemap.visit_plan: foreign key visit_plan_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: venuemap.map: foreign key resource_reservation_map_id_fkey (from resources.resource_reservation)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0115__names_after_r1_20261022.sql (the names the contracts use: venuemap.visit_plan: change foreign key visit_plan_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (venuemap.import_job: columns source_ref, format and created_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `venuemap.import_job.scope_path`; constraint added `venuemap.map map_venue_id_id_uniq`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `venuemap.import_job`, `venuemap.map`, `venuemap.map_version`, `venuemap.path`, `venuemap.placed_resource`, `venuemap.point`, `venuemap.visit_plan`, `venuemap.visit_plan_item` and 1 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 1 | MIG-RETAIL | AM-FOUNDATION-DATABASE | [DB] Migration V0032__retail.sql: retail (10 tables) | 5 | Hrushikant Patkar | RetailService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-FNB MIG-IDENTITY MIG-INVENTORY MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: retail.merchandise, retail.reservation, retail.reservation_line, retail.return, retail.return_line, retail.return_policy, retail.sale, retail.sale_line, retail.shop_and_drop, retail.shop_and_drop_line. Source DDL: backend/tenant/010-retail.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (retail.return_line: row-level security apply_parent_rls; retail.sale: row-level security apply_parent_rls; retail.sale_line: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (retail.merchandise: row-level security apply_parent_across_rls; retail.reservation: row-level security apply_parent_across_rls; retail.return_policy: row-level security apply_parent_across_rls; retail.sale: row-level security apply_parent_across_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: retail.return_policy: rename column self_authorise_limit to self_authorise_limit_amount, rename column requires_second_user_above to second_user_above_amount, rename column requires_approval_above to approval_above_amount; retail.sale_line: rename column unit_price to unit_amount, rename column discount to discount_amount, rename column line_total to gross_amount; retail.shop_and_drop: rename column collection_point_id to collection_location_id, rename constraint shop_and_drop_collection_point_id_fkey to shop_and_drop_collection_location_id_fkey, rename index shop_and_drop_collection_point_id_idx to shop_and_drop_collection_location_id_idx, drop index shop_and_drop_order_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (retail.merchandise: column is_droppable; retail.sale: columns receipt_barcode and cashier_principal_id, constraint sale_cashier_principal_id_fkey, index sale_cashier_principal_id_idx; retail.sale_line: column override_reason); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0110__after_r1_20261020.sql (retail.shop_and_drop: columns disposal_method, disposal_note, disposal_decided_at and disposal_decided_by_principal_id, constraint shop_and_drop_disposal_decided_by_principal_id_fkey, index shop_and_drop_disposal_decided_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0112__after_r1_20261021.sql (retail.sale_line: column order_line_id, index sale_line_order_line_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (retail.merchandise: column is_published, indexes merchandise_outlet_id_barcode_uniq and merchandise_outlet_id_sku_uniq; retail.shop_and_drop: DROP CONSTRAINT IF EXISTS shop_and_drop_drop_reference_chk, constraint shop_and_drop_drop_reference_chk, column collection_note, indexes shop_and_drop_drop_reference_uniq, shop_and_drop_order_id_uniq and shop_and_drop_sale_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `retail.merchandise`, `retail.reservation`, `retail.reservation_line`, `retail.return`, `retail.return_line`, `retail.return_policy`, `retail.sale`, `retail.sale_line` and 2 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 1 | VM-MIG-QUEUE | AM-FOUNDATION-DATABASE | [DB] Forward migration V1051__queue.sql: queue for the first release (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-QUEUE | Tables: queue.feed. Source DDL: backend/tenant/010-queue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze), pushed before the first release needed it and kept under its pushed key (CHG-R6G-001); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: queue.feed: foreign key reading_feed_id_fkey (from queue.reading)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key reading_feed_id_fkey here** (queue.reading to queue.feed, guarded): MIG-QUEUE creates queue.reading before queue.feed exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `queue.feed` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 1 | MIG-FOREIGN-KEYS | AM-FOUNDATION-DATABASE | [DB] Migration V0034__cross_schema_foreign_keys.sql (36 keys) | 3 | Hrushikant Patkar |  | MIG-ACCESS MIG-AI MIG-APPROVALS MIG-ASSETS MIG-CATALOGUE MIG-CONTROL MIG-FNB MIG-GAMES MIG-IDENTITY MIG-INVENTORY MIG-KERNEL MIG-LEDGER MIG-MAINTENANCE MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM MIG-PROMOTIONS MIG-QUEUE MIG-REPORTING MIG-RESOURCES MIG-RETAIL MIG-SEATING MIG-SUBSCRIPTION MIG-SYNC MIG-TENANCY MIG-TRANSPORT MIG-VENUEMAP MIG-WALLET MIG-WHITELABEL MIG-WORKFORCE | Builds: `table ai.policy`, `table ai.provider`, `table assets.media_asset`, `table assets.media_collection`, `table catalogue.entitlement_template`, `table catalogue.performance`, `table catalogue.price`, `table games.card`, `table identity.delegated_access`, `table identity.principal`, `table ledger.price_variance`, `table maintenance.asset`, `table orders.resale_listing`, `table orders.wallet_pass`, `table pii.subject_biometric`, `table platform.outlet`, `table platform.workstation`, `table promotions.coupon_code`, `table reporting.dashboard`, `table resources.booking`, `table resources.resource`, `table seating.seat_block`, `table sync.rejection`, `table transport.network_import`, `table wallet.wallet_transaction`, `table whitelabel.promo_block`, `table whitelabel.tenant_config`, `table workforce.attendance`. The foreign keys that point from a schema into one created after it: ai (2), assets (2), catalogue (3), games (1), identity (3), ledger (2), maintenance (2), orders (2), pii (2), platform (3), promotions (1), reporting (1), resources (2), seating (2), sync (1), transport (1), wallet (3), whitelabel (2), workforce (1). Each is the ALTER TABLE ... ADD CONSTRAINT line of backend/<db>/900-foreign-keys.sql with that constraint name, unchanged (each linked table's record lists its keys with ON DELETE): ai.policy(tenant_id) -> platform.tenant as policy_tenant_id_fkey; ai.provider(region_id) -> platform.scope as provider_region_id_fkey; assets.media_asset(venue_id) -> platform.scope as media_asset_venue_id_fkey; assets.media_collection(venue_id) -> platform.scope as media_collection_venue_id_fkey; catalogue.entitlement_template(admission_rules_id) -> access.admission_rules as entitlement_template_admission_rules_id_fkey; catalogue.performance(admission_rules_id) -> access.admission_rules as performance_admission_rules_id_fkey; catalogue.price(tax_code_id) -> ledger.tax_code as price_tax_code_id_fkey; games.card(venue_id) -> platform.scope as card_venue_id_fkey; identity.delegated_access(scope_id) -> platform.scope as delegated_access_scope_id_fkey; identity.principal(home_scope_id) -> platform.scope as principal_home_scope_id_fkey; ledger.price_variance(order_line_id) -> orders.order_line as price_variance_order_line_id_fkey; ledger.price_variance(venue_id,order_id) -> orders.sales_order as price_variance_venue_id_order_id_fkey; maintenance.asset(supplier_id) -> inventory.supplier as asset_supplier_id_fkey; maintenance.asset(venue_id,linked_access_point_id) -> access.access_point as asset_venue_id_linked_access_point_id_fkey; orders.resale_listing(entitlement_id) -> access.entitlement as resale_listing_entitlement_id_fkey; orders.wallet_pass(entitlement_id) -> access.entitlement as wallet_pass_entitlement_id_fkey; pii.subject_biometric(consent_purpose_id) -> marketing.consent_purpose as subject_biometric_consent_purpose_id_fkey; pii.subject_biometric(entitlement_id) -> access.entitlement as subject_biometric_entitlement_id_fkey; platform.outlet(cost_center_id) -> ledger.cost_center as outlet_cost_center_id_fkey; platform.outlet(venue_id,stock_location_id) -> inventory.location as outlet_venue_id_stock_location_id_fkey; platform.workstation(venue_id,access_point_id) -> access.access_point as workstation_venue_id_access_point_id_fkey; promotions.coupon_code(redeemed_order_id) -> orders.sales_order as coupon_code_redeemed_order_id_fkey; reporting.dashboard(venue_id) -> platform.scope as dashboard_venue_id_fkey; resources.booking(order_id) -> orders.sales_order as booking_order_id_fkey; resources.resource(venue_id) -> platform.scope as resource_venue_id_fkey; seating.seat_block(performance_id) -> catalogue.performance as seat_block_performance_id_fkey; sync.rejection(workstation_id) -> platform.workstation as rejection_workstation_id_fkey; transport.network_import(source_ref) -> assets.media_asset as network_import_source_ref_fkey; wallet.wallet_transaction(order_id) -> orders.sales_order as wallet_transaction_order_id_fkey; whitelabel.promo_block(promotion_id) -> promotions.promotion as promo_block_promotion_id_fkey; whitelabel.tenant_config(tenant_id) -> platform.tenant as tenant_config_tenant_id_fkey; workforce.attendance(access_point_id) -> access.access_point as attendance_access_point_id_fkey. Source DDL: backend/tenant/900-foreign-keys.sql and backend/control/900-foreign-keys.sql (the constraints named here, nothing else from those files). Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when: after every schema migration, this one adds exactly these keys on an empty database and on the previous release's schema, a second run applies nothing, and a row pointing at a missing parent is refused.
7 | 2 | MIG-APPROVALS-4 | AM-FOUNDATION-DATABASE | [DB] Forward migration V1008__approvals.sql: approvals for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-APPROVALS MIG-APPROVALS-2 | Tables: approvals.sla_policy. Source DDL: backend/tenant/010-approvals.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. It also adds the foreign key(s) MIG-APPROVALS-2 (whose file runs before this one) holds into its tables. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (approvals.sla_policy: column reminders, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: approvals.sla_policy: rename column business_hours_only to is_business_hours_only); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.sla_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
3 | 1 | ARCH-TESTS | AM-FOUNDATION-PLATFORM | [BE] Architecture tests for 17 modules: no module references another, and no module's SQL names another's schema | 3 | Pranay Shinde |  | SETUP-HOSTS | Architecture tests for 17 modules: no module references another, and no module's SQL names another's schema. Builds: `adr ADR-0055`, `adr ADR-0028`. Extend `TICVAI.ArchitectureTests` (repos/ticvai-docs/setup/backend-patterns.md 3.2, which already enforces the layer rules: Domain references nothing, Application only Domain and Contracts) to the 17 modules of ADR-0055. A module is a folder, `TICVAI.Application/Features/<Module>/`, not a `Ticvai.Modules.*` assembly (r8 walk fix, CHG-R8WFC-008), so the tests work on namespaces: no type in `Features.<A>` references a type in `Features.<B>` (they share only `TICVAI.Domain` and `TICVAI.Contracts`), and a module's SQL names no other module's schema except through a published read view. Done when: a deliberate cross-module reference and a raw cross-schema query each fail the build in CI.
3 | 1 | KERNEL-ID | AM-FOUNDATION-PLATFORM | [BE] One id type: UUIDv7 from Id.New() in the kernel and in offline-core | 2 | Pranay Shinde |  | SETUP-HOSTS | One id type: UUIDv7 from Id.New() in the kernel and in offline-core. Builds: `adr ADR-0056`. One id type (ADR-0056): `TICVAI.Domain.Identity.Id.New()`, a UUIDv7 `Guid` (RFC 9562) written big-endian so PostgreSQL's uuid order is time order. **The backend repository already has it** (repos/ticvai-docs/setup/backend-patterns.md 3.1: `Guid.NewGuid()` is banned in favour of it; r8 walk fix, CHG-R8WFC-008), so the server side is: confirm the byte order and that no ULID or UUIDv4 is minted anywhere. The offline side is the same generator in each frontend repository whose app creates ids offline (docs/active/frontend-repos.yaml: one GitLab repository per app since 13 October, no shared packages repository), so a till's offline id and a server id sort together. Done when: ids made by the server and by an offline till sort by creation time in PostgreSQL, a .NET-to-TypeScript round-trip test agrees byte for byte, and no ULID string is generated anywhere.
3 | 1 | PLATFORM-MIGRATE | AM-FOUNDATION-PLATFORM | [BE] Migration fan-out across tenant databases, and expand-then-contract changes | 5 | Pranay Shinde |  | SETUP-DB | Migration fan-out across tenant databases, and expand-then-contract changes. Builds: `table control.migration`, `table control.migration_run`, `table control.migration_run_cell`, `table control.migration_run_tenant`, `table control.migration_plan_cell`, `adr ADR-0039`. Apply a migration to every tenant database with progress and resume, and the rule that a schema change ships in two steps so old and new code both run (SD-049). Done when: a column rename reaches three seeded tenant databases with no downtime. Spec (4 October, CHG-FXP-005), ADR-0039 section 3: the fan-out unit is a tenant database and the canary is a tenant inside a canary cell; one `control.migration_run_tenant` row per tenant per run (status, from_version, to_version, error, timings), with `control.migration_run_cell` as the rollup; `control.migration_plan_cell` names all tenants of a cell or a named set. A failed tenant stops its wave and is resumed from its row; tenants already done stay done.
3 | 1 | PLATFORM-OBSERVE | AM-FOUNDATION-PLATFORM | [BE] Observability with tenant and venue on every trace, and the first dashboards | 5 | Pranay Shinde |  | SETUP-OBS | Observability with tenant and venue on every trace, and the first dashboards. Builds: `operation orders#createOrder`, `operation orders#createPayment`, `operation orders#syncOrders`, `operation access#syncScans`, `operation access#validateAccess`. OpenTelemetry attributes for tenant, venue and workstation; dashboards for the sale path and sync; alerts on error rate and latency (SD-048). Done when: a failed POS sale can be found by venue and till within a minute. Spec (4 October, CHG-FXP-005), docs/architecture/observability.md: every log, metric and span carries tenant_id, region_id and venue_id (plus cell, correlation and session id on traces, and workstation on POS metrics), set by the kernel from the resolved session and the workstation. The sale path is the operations linked here (createOrder and createPayment in OrderService, validateAccess in AccessService); sync is syncOrders and syncScans. The first alerts are that document's table, with the threshold, window and severity each row gives (proposed defaults, client to confirm; r8, FOUNDATION-AI-C25): error rate (5xx above 1 percent for 5 minutes; 402 and 409 refusals do not count), latency (p95 above the operation's x-ticvai-latency-budget-ms for 10 minutes), outbox backlog per device (above 1,000 rows or the oldest older than 5 minutes), replication lag per cell (above 30 seconds for 5 minutes), Redis-Postgres capacity divergence and the venue edge heartbeat (missing for 2 minutes), on the stack SETUP-OBS sets up. PgBouncer pool saturation is in that table too but is built by OBS-TENANT-POOL, not here (FOUNDATION-AI-C53).
9 | 1 | PLATFORM-KERNEL | AM-FOUNDATION-PLATFORM | [BE] Request kernel: hostname to tenant routing, per-transaction scope, error model and 429 | 8 | Pranay Shinde |  | SETUP-AUTH SETUP-DB | Request kernel: hostname to tenant routing, per-transaction scope, error model and 429. Builds: `table control.tenant_domain`, `table control.tenant`, `table control.cell_tenant`, `table platform.scope`, `adr ADR-0038`, `adr ADR-0039`, `adr ADR-0005`. In ticvai-backend. Resolve the tenant from the hostname (control-plane routing table, SD-021), open every transaction with the tenant and scope settings the row-level policies read (SD-059), one problem-details error model, and 429 with Retry-After on the hot public operations (SD-043). Done when: two seeded tenants on two hostnames cannot read each other's rows, and a flood test returns 429 instead of 500. Spec (4 October, CHG-FXP-005): the routing table is `control.tenant_domain` (hostname, verified, redirect) in the control database, joined to `control.tenant` and `control.cell_tenant` for the tenant's cell and database (ADR-0038: one database per tenant inside its region's cell; ADR-0039: `control` is a database of its own and `control.cell` has no tenant_id, the relation is `control.cell_tenant`). The row-level policies of backend/tenant/920-row-level-security.sql read two session settings, set with SET LOCAL at the start of every transaction from the resolved session: `ticvai.scope_paths` (the comma-separated ltree scope paths the principal may see; unset or empty means no rows) and `ticvai.subject_id` (the guest's own rows), and `ticvai.principal_id` (the signed-in principal, for the rows that are its own: credentials and second factors). Venues stay partitions of the tenant database (ADR-0005), not databases. **The context before and without a session** (R8 blocker IDENTITY-C48, the lead's option A, 20 October 2026; CHG-R8MIG-007; backend/MIGRATIONS.md "The connection context"): (1) a door or anonymous call (login, the guest sign-ins, listSsoProviders, listActiveSessions with step-up) opens its transaction in an explicit system context (the tenant root path) confined to the identity module's own verification statements, then narrows it with SET LOCAL before any other table is touched: `ticvai.scope_paths` to the resolved principal's paths and `ticvai.principal_id` to the principal, or `ticvai.subject_id` to the guest (scope paths empty); a session-less till call narrows to the till's venue path once the supervisor is verified; (2) a guest reads and writes its own `pii.subject` row and the rows keyed to its subject; (3) a serviceAuth cell-internal call has no user: the tenant comes from the cell token's tid claim, `ticvai.scope_paths` is the tenant root, the calling cell is the audited actor, and its idempotency records are claimed under that context.
10 | 1 | KERNEL-TENANT-LIMITS | AM-FOUNDATION-PLATFORM | [BE] Per-tenant request budgets: a token bucket per tenant and audience, and a load-aware share per replica | 3 | Pranay Shinde |  | PLATFORM-KERNEL | Per-tenant request budgets: a token bucket per tenant and audience, and a load-aware share per replica. Builds: `operation subscription#getPlan`, `adr ADR-0032`, `adr ADR-0064`. ADR-0064 (accepted 1 October), in the kernel middleware of the commerce, access and operations hosts: a token bucket per tenant and audience (guest/public, staff, service, partner) with counts shared through Azure Managed Redis, sustained rate and a 2x burst for 10 seconds from the tenant's plan, asked of Platform with the `subscription#tenantRequestLimits` service query (ADR-0064; the query's rule says what a tenant with no current contract gets), cached per tenant for 60 seconds; one tenant held to 25% of a replica's request slots only while the replica is above 70% of its limit; shedding guest and public first, staff and service last (ADR-0032); 429 with Retry-After and the RateLimit-* headers; if Redis is unavailable each replica falls back to its own in-process buckets (the limit divided by the replica count). Done when: in a test with two tenants on one replica, the busy tenant gets the whole replica while the other is quiet, is held to 25% of the slots once the replica passes 70% while the quiet tenant's requests still succeed, a guest burst never spends a till's staff budget, and stopping Redis leaves requests served under the in-process limits. Contract (4 October, CHG-FXP-005): the plan's limits are `Plan.requestLimits` in contracts/satellite/subscription.yaml, read through the `tenantRequestLimits` query of that contract over Platform's service route, never `subscription#getPlan` (the control database is not the cell's; r8 walk fix, CHG-R8WFC-008); the refusal is the shared `rate-limited` problem (429) of contracts/shared/common.yaml with `Retry-After` and the RateLimit-Limit, RateLimit-Remaining and RateLimit-Reset headers it defines.
10 | 1 | PLATFORM-AUDIT | AM-FOUNDATION-PLATFORM | [BE] Audit interceptor for every write | 3 | Pranay Shinde |  | PLATFORM-KERNEL | Audit interceptor for every write. Builds: `table platform.audit_record`. Who, what, when, tenant and venue for every write, written once by an interceptor rather than per operation (SD-057). Done when: any write in the Block A slice leaves one audit row a support user can read.
10 | 1 | PLATFORM-FLAGS | AM-FOUNDATION-PLATFORM | [BE] Release flags per tenant | 2 | Hrushikant Patkar |  | PLATFORM-KERNEL | Release flags per tenant. Half-built features stay dark per tenant between sprints (SD-051). Spec (default taken 4 October, CHG-FXP-005; for the lead to confirm): flags live in Azure App Configuration in the cell's region, read by every .NET host through Microsoft.FeatureManagement with a tenant targeting filter; a flag's key is an app-module key of the plan (for example `AM-MARKETING-CRM-P01`) and covers that app-module's screens and the operations they bind (their `apis` in screens/*.yaml). Off for a tenant: the apps leave its screens out of that tenant's navigation, and the kernel answers its operations with the shared 404 problem of contracts/shared/common.yaml, as if absent. Done when: with one app-module's flag off for tenant A only, A's guest web no longer shows that module's screens and its operations return 404 for A, while tenant B still sees and calls them; switching it back on restores A within a minute.
10 | 1 | PLATFORM-IDEMPOTENCY | AM-FOUNDATION-PLATFORM | [BE] Durable idempotency: the Idempotency-Key store and middleware | 5 | Pranay Shinde |  | PLATFORM-KERNEL | Durable idempotency: the Idempotency-Key store and middleware. Builds: `table platform.idempotency_record`. Idempotency records in PostgreSQL with Redis as a cache only (SD-024), so a retried payment or sale after a restart returns the first answer. Done when: replaying a createOrder with the same key after a service restart returns the original response and creates nothing.
10 | 1 | PLATFORM-OUTBOX | AM-FOUNDATION-PLATFORM | [BE] Outbox, relay and inbox behind the kernel broker interface, on a local RabbitMQ | 8 | Pranay Shinde |  | PLATFORM-KERNEL SETUP-HOSTS | Outbox, relay and inbox behind the kernel broker interface, on a local RabbitMQ. Builds: `table platform.outbox`, `table kernel.inbox`, `table control.outbox_relay`, `adr ADR-0033`, `adr ADR-0057`, `adr ADR-0058`. The transactional outbox per tenant database; one relay per region in the workers host, with a lease and a polling loop per tenant database, and an inbox per tenant database for exactly-once handling (ADR-0058); modules enqueue through IOutbox inside their own transaction, the relay publishes through IBrokerPublisher and consumers subscribe through IEventSubscriber (ADR-0058 amendment, 1 October); the relay drains a full batch at once and its batch size is configuration (Relay:BatchSize, 1,000 in the flash-sale environment). The broker per ADR-0057 is the client's choice between RabbitMQ and Kafka: build behind the kernel interface on a local RabbitMQ until they answer, with ordering per aggregate by an ordering key and dead letters drained into platform.dead_letter. A relay-lag dashboard and alert per tenant database (SD-030, SD-031, SD-032). Done when: an event written in a transaction reaches its consumer once, survives a relay restart and a redelivery, a poison message lands in platform.dead_letter, and relay lag shows on the dashboard and alerts when unpublished rows are older than 60 seconds.
10 | 1 | PLATFORM-RLS | AM-FOUNDATION-PLATFORM | [BE] Row-level policies without a per-row subquery on hot tables | 3 | Hrushikant Patkar |  | PLATFORM-KERNEL | Row-level policies without a per-row subquery on hot tables. Builds: `table orders.sales_order`, `table access.scan_event`, `table platform.scope`, `adr ADR-0005`, `adr ADR-0044`. Scope predicates read session settings instead of joining per row (SD-016). Done when: the order and scan-event queries keep their plan with policies on, measured with EXPLAIN (ANALYZE) on the seed data before and after (the before is the baseline). Spec (4 October, CHG-FXP-005): the policies are generated in backend/tenant/920-row-level-security.sql by `platform.apply_scope_rls` and its siblings; today each USING clause calls `platform.in_scope(scope_path)`, which unnests `ticvai.scope_paths` for every row. On the hot tables linked here, rewrite the predicate so the planner evaluates the session setting once per statement (an InitPlan over `platform.current_scope_paths()`) instead of per row; the policy names and deny-by-default stay. **No venue partitioning in release 1** (ADR-0044 as amended by ADR-0056, 30 September; r8 walk fix, CHG-R8WFC-008): `orders.sales_order` is not partitioned, and `access.scan_event` is range-partitioned by month on `recorded_at`, so the predicate keeps that time pruning and no `venue_id = ANY(...)` partition pruning is asked for.
11 | 1 | PLATFORM-PAYMENTS | AM-FOUNDATION-PLATFORM | [BE] Payment adapter and signed webhook against the provider's test mode | 8 | Hrushikant Patkar |  | PLATFORM-OUTBOX | Payment adapter and signed webhook against the provider's test mode. Builds: `operation payments#receivePaymentProviderWebhook`, `table payments.provider_event`. The provider adapter, the inbound signed webhook, the provider reference on payments, 3-D Secure redirect states and the card-terminal flow for the POS (SD-034). Done when: an approved, a declined and a 3-D Secure payment each end in the right order state from the webhook alone, with polling only as the fallback. Acceptance of the declined, unknown and reconcile paths waits on the client's payment sandbox credentials: see the client's answer in the Decisions Register. Until the client's sandbox credentials arrive (CLIENT-PAY-SANDBOX), the three outcomes are proven with signed webhook fixtures built from the provider's documented test payloads and a locally generated signing secret (CHG-FXP-006); the run against the provider's test mode follows when they arrive and is the acceptance of those paths.
11 | 1 | PLATFORM-REPUBLISH | AM-FOUNDATION-PLATFORM | [BE] Republish from the outbox by tenant and time range | 3 | Hrushikant Patkar |  | PLATFORM-OUTBOX | Republish from the outbox by tenant and time range. Builds: `operation platform-ops#republishOutbox`, `operation platform-ops#getOutboxRepublish`, `operation platform-ops#listOutboxRepublishes`, `operation platform-ops#cancelOutboxRepublish`, `table control.outbox_republish`, `adr ADR-0058`. The recovery path for a lost broker (ADR-0058 amendment, 1 October; the DR design in ADR-0060 relies on it): republishOutbox, listOutboxRepublishes, getOutboxRepublish and cancelOutboxRepublish in the operations host, carried out by the relay in workers with a keyset cursor over the outbox, published_at left untouched and live batches first; one job per tenant (control.outbox_republish). Done when: after a simulated broker loss, a republish of one tenant's last hour redelivers every event once to each consumer, the inbox drops the duplicates, and a second request for the same tenant while one runs is refused with 409.
11 | 1 | PLATFORM-SAGA-PAID | AM-FOUNDATION-PLATFORM | [BE] Order paid to tickets issued: the saga proven end to end | 5 | Hrushikant Patkar |  | PLATFORM-OUTBOX | Order paid to tickets issued: the saga proven end to end. Builds: `operation orders#createPayment`, `operation catalogue#convertInventoryHold`, `operation access#issueOrderEntitlements`, `table access.entitlement`, `table catalogue.inventory_hold`, `table catalogue.channel_capacity`, `table ledger.journal_entry`, `table ledger.journal_line`, `adr ADR-0055`, `adr ADR-0058`. order.paid consumed by the entitlement owner, tickets issued, the ledger posting once from the event, and holds converted with capacity decremented (SD-026, SD-023). Done when: a web purchase in the sandbox ends with a ticket, one ledger posting and sold capacity reduced, and a replayed event changes nothing. **Until the client's payment sandbox credentials arrive (CLIENT-PAY-SANDBOX)**, 'in the sandbox' is met as PLATFORM-PAYMENTS' module test meets it (CHG-FXP-006): the payment confirmation is a signed webhook built from the provider's documented test payloads with a locally generated signing secret (the lead, 20 October 2026, r8 cause FOUNDATION-AI-C18, option A). The same purchase run against the provider's test mode is a Block A closing check once the credentials arrive, not a condition of this task. Spec (4 October, CHG-FXP-005), from events/order-paid.yaml and events/entitlement-issued.yaml (adam_search order.paid): the payment transaction (createPayment, or the provider webhook) converts the inventory holds (`catalogue#convertInventoryHold`: the hold becomes sold capacity), posts the cash receipt to ledger.journal_entry and ledger.journal_line, and writes `order.paid` to the outbox in the same transaction; AccessService consumes it (`access#issueOrderEntitlements`, idempotency key orderId + lineId; on failure retry, then dead-letter, which pages) and publishes `entitlement.issued`; the orders consumer of that completes the order. A dead-lettered issuance is replayed, never compensated by an automatic refund. ADR-0055: modules in different deployables talk by event; ADR-0058: one relay per region and an inbox per tenant database, so a replayed event is a no-op.
1 | 1 | R8-DB-LOCAL-CHINMAY-PATKAR | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Chinmay Patkar |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-CHITRANGI-MESTRY | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Chitrangi Mestry |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-DEEP-KHANVILKAR | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Deep Khanvilkar |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-KALPITA-MEJARI | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Kalpita Mejari |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-NARAYAN-GAONKAR | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Narayan Gaonkar |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-PALLAVI-SAWANT | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Pallavi Sawant |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-PRADNYA-YERAM | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Pradnya Yeram |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-PRANAY-SHINDE | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Pranay Shinde |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-SANKET-KELUSKAR | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Sanket Keluskar |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-LOCAL-SURENDRA | AM-FOUNDATION-PLATFORM | [BE] r8: bring your local database to r8 (renamed tables, new columns) | 1 | Surendra |  |  | r8: bring your local database to r8 (renamed tables, new columns). Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). How to apply: with psql, file by file in that order, against your own local databases, from the package root: `psql "$TENANT_DB" -v ON_ERROR_STOP=1 -f backend/tenant/V0103a__names_early_after_r1_20261020.sql`, then each of the other tenant files the same way, then the five control files against "$CONTROL_DB". These are the package's files, not ours: each records itself in platform.schema_version, so they are not copied into db/tenant or db/control and not run through SqlMigrationRunner (setup/backend-patterns.md section 3.4); your migrations in our repository stay as they are, and the [DB] ticket that creates a table carries the same change. Tenant V0108 and control V0110 alter tables your database may not have yet: if one stops on `... does not exist`, run that file again with `-v ON_ERROR_STOP=0` and read the errors. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. Then run them all again: the second run changes nothing (for V0108 and V0110, the same lines and nothing else). One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. How to check (in psql, each answers true): `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;` `select to_regclass('wallet.fund_reservation') is not null and to_regclass('wallet.hold') is null;` `select to_regclass('seating.seat_reservation') is not null and to_regclass('seating.seat_hold') is null;` `select to_regclass('sync.guest_link') is not null and to_regclass('platform.guest_link') is null;` (a check whose new and old names are both null is a table your database never had: that is fine), and `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above in the tenant database, and of every control file above in control (an older V0100 to V0102 may be there too). Done when: applied and checked, or, if your local database has none of the tables these files touch, close this task as not needed with a one-line comment saying so.
1 | 1 | R8-DB-SHARED | AM-FOUNDATION-PLATFORM | [BE] r8: apply r8 to the shared database | 3 | Hrushikant Patkar |  |  | r8: apply r8 to the shared database. Builds: `file backend/tenant/V0103a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0105a__names_early_after_r1_20261020.sql`, `file backend/tenant/V0107__names_after_r1_20261019.sql`, `file backend/tenant/V0108__after_r1_20261020.sql`, `file backend/tenant/V0109__names_after_r1_20261020.sql`, `file backend/tenant/V0110__after_r1_20261020.sql`, `file backend/tenant/V0111__names_after_r1_20261020.sql`, `file backend/tenant/V0112__after_r1_20261021.sql`, `file backend/tenant/V0113__after_r1_20261021.sql`, `file backend/tenant/V0114__after_r1_20261022.sql`, `file backend/tenant/V0115__names_after_r1_20261022.sql`, `file backend/control/V0107__names_after_r1_20261019.sql`, `file backend/control/V0108__after_r1_20261020.sql`, `file backend/control/V0109__names_after_r1_20261020.sql`, `file backend/control/V0110__after_r1_20261020.sql`, `file backend/control/V0112__after_r1_20261021.sql`, `file backend/tenant/V0116__after_r1_20261026.sql`, `file backend/tenant/V0117__names_after_r1_20261026.sql`, `file backend/tenant/V0118__after_r1_20261029.sql`, `file backend/tenant/V0119__names_after_r1_20261029.sql`, `file backend/control/V0116__after_r1_20261026.sql`. Why: the lead, 20 October 2026: every developer runs a local database, and r8 changes it. What changed: r8 brings the tenant database to the names the contracts use and adds what the contracts gained since r1. V0103a and V0105a rename 15 tables and move 4 into the sync schema (19 in all), with 20 column renames and the keys, indexes and row-level security policies named for them: catalogue.inventory_hold is now catalogue.inventory_reservation, wallet.hold is wallet.fund_reservation, the wallet *_rules tables are wallet.channel_rule, funding_rule, risk_rule_set and transfer_rule, seating.seat_hold and seat_hold_item are seating.seat_reservation and seat_reservation_item, inventory.item is inventory.inventory_item, inventory.stock_reservation is inventory.stock_earmark, and platform.guest_link, cross_region_entitlement, wallet_authorisation and dsar_request move to sync; columns such as platform.workstation.cash_drawer_limit become deposit_box_limit_amount. V0108 adds 18 tables, 95 columns and their keys and indexes, and widens two CHECKs (inventory.stock_earmark.source_type gains retailReservation, seating.seat_reservation.status gains sold); V0109 adds the foreign keys into the renamed tables, NOT VALID. In the control database V0108 adds 19 tables and 4 columns and V0109 2 keys and an index. Every rename is a guarded block (it does nothing when the old name is not there or the new one already is), so each file can run twice. The files, in this order (every file since r7; apply any of them your database's platform.schema_version does not list yet, in name order, and skip none): tenant database: backend/tenant/V0103a__names_early_after_r1_20261020.sql, backend/tenant/V0105a__names_early_after_r1_20261020.sql, backend/tenant/V0107__names_after_r1_20261019.sql, backend/tenant/V0108__after_r1_20261020.sql, backend/tenant/V0109__names_after_r1_20261020.sql, backend/tenant/V0110__after_r1_20261020.sql, backend/tenant/V0111__names_after_r1_20261020.sql, backend/tenant/V0112__after_r1_20261021.sql, backend/tenant/V0113__after_r1_20261021.sql (r9), backend/tenant/V0114__after_r1_20261022.sql (r9), backend/tenant/V0115__names_after_r1_20261022.sql (r9); control database: backend/control/V0107__names_after_r1_20261019.sql, backend/control/V0108__after_r1_20261020.sql, backend/control/V0109__names_after_r1_20261020.sql, backend/control/V0110__after_r1_20261020.sql, backend/control/V0112__after_r1_20261021.sql. V0107 renames columns, V0110 and V0111 add the columns and keys the r8 fixes added, and V0112 those of the re-walk fixes (wallet.credit_lot.order_line_id, retail.sale_line.order_line_id, the wider product kind and wallet adjustment kind CHECKs; in control, the licence add-on's removal record). The shared database is the one the team works against (Hrushikant Patkar runs it). 0. First run our repository's Migrator to the repository's latest migration on both databases (on 21 October tenant 241 and control 032): the r8 files are written against what the repository builds, and run after it. 1. Backup first: `pg_dump -Fc` of both databases, tenant and control, to a folder on the database server outside the data directory (for example /var/backups/ticvai/r8-20261021/tenant.dump and control.dump), and check each with `pg_restore --list <file> ¦ head`. 2. Apply the r8 files (the eight r8 tenant files on the tenant database, the five control files on the control database) in that order, each as one transaction. Exactly six errors are accepted, all `does not exist`, on a database our team's repository built: in tenant V0108, `relation "marketing.privacy_exception" does not exist` three times (a table the repository has not built yet) and `column "scope_path" does not exist` twice (platform.outbox_sequence keeps the shape our repository's migration 240 gives it, CR-166); in control V0110, `relation "control.onboarding_application" does not exist` once (a table the repository has not built yet). Any other error: write it in a comment here and stop. List the tables of the accepted errors in a comment. One command does it: tools/db/apply-r8.sh in the package, which runs each file as one transaction and retries only tenant V0108 and control V0110 statement by statement, accepting only those six errors. It reads the files from a `sql` folder beside it: copy tools/db/apply-r8.sh and the thirteen r8 files above (all but the files marked r9) into a folder of your own as `apply-r8.sh`, `sql/tenant/<file>.sql` and `sql/control/<file>.sql`, then run `bash apply-r8.sh <host> <user> <tenant_db> <control_db> <log folder>` with PGPASSWORD (and PGPORT if not 5432, PGBIN if psql is not in C:/Program Files/PostgreSQL/18/bin) in the environment. It runs every file twice; the second pass changes nothing. Then apply the files marked r9 in the list above, in name order, each with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each applies with no error either time, every statement in them is guarded. V0113 (r9, CR-166) takes away the scope_path, its index and its scope policy V0108 gave platform.outbox_sequence where V0108 could add them, so the table has the shape our repository's migration 240 gives it (aggregate_id and last_sequence, read, inserted and updated by any connection holding a grant, never deleted); on a database our repository built it changes nothing. V0114 (r9: CR-182, CR-184, CR-191, CR-196) makes platform.idempotency_record unique on (operation_id, idempotency_key) with status completed only (a NOT VALID check: rows already there are not rechecked), re-applies the row-level security of orders.cart, orders.sales_order, orders.order_line and orders.order_event so a guest reads its own cart and orders (staff still by venue or scope) and of the 21 tables under them, and grants commerce SELECT on access.entitlement and access.scan_event where the commerce role exists. V0115 (r9: CR-146) puts five foreign keys in the reference's form: rental.booking's deposit key now points at orders.payment, platform.configuration_profile's primary key is widened (its old key and the keys onto it replaced first) and platform.profile_deployment's key onto it is on (profile_id, version), venuemap.visit_plan's subject key points at pii.subject, and platform.workstation gains its key onto configuration_profile, each added NOT VALID and doing nothing where the key is already the reference's. 3. The hand items of the r8 walk fix (handoff/migration-review.md): three columns are text where the package says numeric(18,4): platform.workstation.deposit_box_limit_amount, platform.venue_settings.deposit_box_limit_amount and marketing.wishlist_item.list_price. For each, first prove every value casts: `select <column> from <table> where <column> is not null and <column> !~ '^\s*-?[0-9]{1,14}(\.[0-9]{1,4})?\s*$';` returns no row (fix or note any row it returns); then `ALTER TABLE <table> ALTER COLUMN <column> TYPE numeric(18,4) USING nullif(trim(<column>), '')::numeric(18,4);`. The 107 NOT NULL rows and the cross-database moves on handoff/migration-review.md (control.content_block to whitelabel.content_block, the subscription tables to control) stay as they are unless you decide otherwise; say in a comment what you did. platform.audit_read: V0108 adds read_at, target, filter and record_count and drops NOT NULL on subject_id; read_at and target stay nullable (the schema reference says NOT NULL: they are two of the 107), and MIG-PLATFORM and VM-MIG-PLATFORM stay blocked on the lead's decision about audit_read (the r8 walk-fix migrations report, section 3). Newer files, added to this task by the plan as each release derives them: backend/tenant/V0116__after_r1_20261026.sql, backend/tenant/V0117__names_after_r1_20261026.sql, backend/tenant/V0118__after_r1_20261029.sql, backend/tenant/V0119__names_after_r1_20261029.sql, backend/control/V0116__after_r1_20261026.sql. Apply each after the files above, in name order, against its own database, with `psql -1 -v ON_ERROR_STOP=1 -f`, twice: each is written to apply as one transaction, twice, on any database (CHG-R9MIG-002), so the second run changes nothing; its header says what it adds. Any error: write it in a comment here and stop. 4. Check on the tenant database, each answers true: `select to_regclass('catalogue.inventory_reservation') is not null and to_regclass('catalogue.inventory_hold') is null;`, the same for wallet.fund_reservation and wallet.hold, seating.seat_reservation and seating.seat_hold, sync.guest_link and platform.guest_link; `select version from platform.schema_version where version like 'V01%' order by version;` lists the number of every tenant file above on tenant, and of every control file above on control (an older V0100 to V0102 may be there too); and `select data_type, numeric_precision, numeric_scale from information_schema.columns where table_name = 'workstation' and column_name = 'deposit_box_limit_amount';` says numeric, 18, 4 (and the same for the other two columns). Done when: every file listed above is in its database's platform.schema_version, the checks pass, and the backup's location is in a comment on this ticket.
11 | 1 | OBS-TENANT-POOL | AM-FOUNDATION-PLATFORM | [BE] Alerts on one tenant's share of its connection pool and on max_connections | 1 | Pranay Shinde |  | KERNEL-TENANT-LIMITS PLATFORM-OBSERVE | Alerts on one tenant's share of its connection pool and on max_connections. Builds: `adr ADR-0032`, `adr ADR-0064`. ADR-0064 item 4: per-tenant pool caps stay, and two alerts watch them: one tenant holding more than 60% of its pool for five minutes, and the instance passing 80% of max_connections; plus a dashboard panel of 429s per tenant and audience from KERNEL-TENANT-LIMITS. Done when: a load run that holds one tenant's pool fires the first alert after five minutes naming the tenant, and opening connections past 80% of max_connections fires the second. Where the numbers come from (4 October, CHG-FXP-005): one tenant's share is the server connections in use for that tenant database, sv_active plus sv_used from PgBouncer's SHOW POOLS, against the database's pool_size from SHOW DATABASES (what ADR-0032 and ADR-0040 say is monitored), with cl_waiting above 0 as a second signal (r8, FOUNDATION-AI-C24); the instance figure is the count of pg_stat_activity against max_connections; both are scraped into the Prometheus-compatible metrics of SETUP-OBS and alert through its Azure Monitor action group, labelled with tenant_id and cell. The pooler is Azure's built-in PgBouncer (r8, FOUNDATION-AI-C53, lead 20 October 2026): Terraform sets pgbouncer.enabled on the Flexible Server (port 6432), and its statistics are read through the admin console on 6432 by a monitoring role with no data access. This alert is the PgBouncer saturation alert of docs/architecture/observability.md: this ticket builds it and its scrape, and PLATFORM-OBSERVE does not build a second one. Thresholds are proposed, client to confirm (that document's alert table).
3 | 1 | OFFLINE-JOURNAL | AM-FOUNDATION-OFFLINE | [BE] Offline journal in packages/offline-core: record, replay and the conflict policies | 8 | Pradnya Yeram |  | SETUP-CLIENTS | Offline journal in packages/offline-core: record, replay and the conflict policies. Builds: `operation orders#createOrder`, `operation orders#createPayment`, `operation shift#createCashMovement`, `operation access#validateAccess`, `operation orders#syncOrders`, `operation access#syncScans`, `adr ADR-0013`, `adr ADR-0022`. In ticvai-frontend packages/offline-core: an append-only journal of sales and scans taken offline, replay on reconnect, and the conflict policies the contracts declare (SD-047). Done when: a POS takes ten cash sales with the network off and all ten reach the server once when it returns. Spec (4 October, CHG-FXP-005): the conflict policies are the `x-ticvai-conflict-policy` of each operation the journal records (linked here): `append` for createOrder, createPayment, createCashMovement and validateAccess (nothing is overwritten, so a replayed entry is a new fact, deduplicated by its idempotency key); `lastWriterWins` only where an operation declares it (holdOrder); `serverWins` for everything else (the server's version stands and the till re-reads). Replay goes through `orders#syncOrders` and `access#syncScans` in journal order, each entry with the idempotency key it was taken with. ADR-0013: the catalogue is read locally on every transaction, online or not, and contended inventory sells only from a lease; ADR-0022: the four policies and why the set is closed. **A cash movement** (r8, FOUNDATION-AI-C13): it replays through shift.createCashMovement with its Idempotency-Key and recordedAt; a 409 shift-not-open or lift-exceeds-float on replay is quarantined through recordSyncRejection with kind cashMovement, as a refused sale is.
10 | 1 | OFFLINE-BUNDLE | AM-FOUNDATION-OFFLINE | [BE] Signed catalogue and entitlement bundles, and the lease client | 8 | Hrushikant Patkar |  | PLATFORM-KERNEL | Signed catalogue and entitlement bundles, and the lease client. Builds: `operation catalogue#getLatestBundle`, `operation catalogue#reportBundleApplied`, `operation catalogue#acquireInventoryHold`, `table catalogue.published_bundle`, `table catalogue.inventory_hold`, `operation access#getOfflinePackage`, `adr ADR-0013`. The signed bundle a till or scanner trades from offline, including entitlements and dynamic access policy for the scanner (SD-052), and the lease each workstation holds (SD-047). Two bundles: the till's signed catalogue bundle (`catalogue#getLatestBundle`, applied whole or not at all and acknowledged with `catalogue#reportBundleApplied`; table catalogue.published_bundle) and the scanner's offline package (`access#getOfflinePackage`). The lease is ADR-0013 section 2: a till holds N units of contended timed capacity for a TTL through `catalogue#acquireInventoryHold` (catalogue.inventory_hold), renewed while the link is up; unsold units return on expiry; seated inventory stays blocked offline (CHG-FXP-005). **Block A takes no standing lease** (ADR-0013 C103; r8, FOUNDATION-AI-C45, GPS-C37): contended timed entry is online-only at the till, and offline the POS-002 sale drawer refuses it and says why (timed entry needs a connection). Done when: offline, a till refuses contended timed entry with that message and sells the rest from its bundle; an offline sale replayed after the hold it relied on expired is accepted and flagged unitsGone for the reconciler, never silently dropped (FOUNDATION-AI-C46); a bundle whose signature does not verify (Ed25519 over contentHash, keys from getBundleSigningKeys with a 7-day grace) is refused whole (FOUNDATION-AI-C14).
11 | 1 | OFFLINE-SYNC | AM-FOUNDATION-OFFLINE | [BE] syncOrders: a result per entry, and a bad entry quarantined instead of blocking the till | 5 | Hrushikant Patkar |  | OFFLINE-BUNDLE | syncOrders: a result per entry, and a bad entry quarantined instead of blocking the till. Builds: `operation orders#syncOrders`, `adr ADR-0022`. Per-entry outcomes, a quarantine a supervisor resolves, and the till carrying on with the rest (SD-028). Done when: one malformed sale in a batch of twenty is quarantined and the other nineteen are accepted.
11 | 1 | POS-KDS-ROUTING | AM-FOUNDATION-OFFLINE | [BE] A POS sale reaches the kitchen: routing online, and the LAN path decision | 8 | Hrushikant Patkar |  | PLATFORM-OUTBOX | A POS sale reaches the kitchen: routing online, and the LAN path decision. Builds: `operation fnb#createFnbOrder`, `table fnb.kitchen_ticket`, `table fnb.kitchen_routing_rule`, `table fnb.kitchen_station`. createFnbOrder from the POS creates the kitchen ticket as the guest order does, routed to the right station (SD-046). The offline LAN path to the Kitchen Display is an ADR decision; this task implements the online path and the stub the decision fills. Done when: a POS sale of a burger and a drink shows on the grill and bar stations. 2 October (Chinmay, DEC-187/189): routing takes category rules with a default/fallback station per outlet; 8 points (was 5). **What prints in Block A** (the lead, 20 October 2026, r8 cause FOUNDATION-AI-C15, option A): DEC-187's kitchen printing is met by prep-sheet printing to the station's printers (printPrepSheet, KitchenStation.printerDeviceIds); the kitchen ticket itself shows on the Kitchen Display and is not printed. Printing each kitchen ticket through a ticket template is a later change, not part of this task.
11 | 1 | SVC-AI-ACTIONS-1 | AM-AI-ENGINE-A | [BE] AiService: overrideAiDecision | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: overrideAiDecision. Spec: handoff/service-docs/backend/AiService.md#group-actions Helper task: Pranay Shinde owns the service and reviews. Done when `ai#overrideAiDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-AI-2 | AM-AI-ENGINE-A | [BE] AiService: setSuggestionProvider, testAiProvider | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSuggestionProvider, testAiProvider. Spec: handoff/service-docs/backend/AiService.md#group-ai Helper task: Pranay Shinde owns the service and reviews. Done when `ai#setSuggestionProvider`, `ai#testAiProvider` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-2 | AM-AI-ENGINE-A | [BE] AiService: getForecastAccuracy, getVenueHistoryImport, importVenueHistory, listForecastVersions | 8 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getForecastAccuracy, getVenueHistoryImport, importVenueHistory, listForecastVersions. Spec: handoff/service-docs/backend/AiService.md#group-forecast. Done when `ai#getForecastAccuracy`, `ai#getVenueHistoryImport`, `ai#importVenueHistory`, `ai#listForecastVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-GOVERNANCE-2 | AM-AI-ENGINE-A | [BE] AiService: getEffectiveAiPolicy, listAiCapabilities, listAiGovernancePolicyVersions, pauseAiCapability | 8 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getEffectiveAiPolicy, listAiCapabilities, listAiGovernancePolicyVersions, pauseAiCapability. Spec: handoff/service-docs/backend/AiService.md#group-governance. Done when `ai#getEffectiveAiPolicy`, `ai#listAiCapabilities`, `ai#listAiGovernancePolicyVersions`, `ai#pauseAiCapability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-RETRIEVAL-2 | AM-AI-ENGINE-A | [BE] AiService: setIndexSource | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setIndexSource. Spec: handoff/service-docs/backend/AiService.md#group-retrieval Helper task: Pranay Shinde owns the service and reviews. Done when `ai#setIndexSource` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-GUESTAUTH-2 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: guestPasswordLogin, guestSocialLogin, guestUaePassLogin, linkGuestCheckout | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: guestPasswordLogin, guestSocialLogin, guestUaePassLogin, linkGuestCheckout. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth. Done when `identity#guestPasswordLogin`, `identity#guestSocialLogin`, `identity#guestUaePassLogin`, `identity#linkGuestCheckout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-IDENTITY-2 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: grantDelegation, listDelegations, login, refreshToken | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: grantDelegation, listDelegations, login, refreshToken. Spec: handoff/service-docs/backend/IdentityService.md#group-identity. Done when `identity#grantDelegation`, `identity#listDelegations`, `identity#login`, `identity#refreshToken` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-MFA-2 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: verifyMfaChallenge, verifyMfaEnrolment | 5 | Sanket Keluskar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: verifyMfaChallenge, verifyMfaEnrolment. Spec: handoff/service-docs/backend/IdentityService.md#group-mfa Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#verifyMfaChallenge`, `identity#verifyMfaEnrolment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-IDENTITY-IDENTITY-4 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: verifyGuestEmail | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: verifyGuestEmail. Spec: handoff/service-docs/backend/IdentityService.md#group-identity Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#verifyGuestEmail` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-ORDER-4 | AM-IDENTITY-SECURITY-P01 | [BE] OrderService: listTicketTransfers, modifyOrder, reprintOrder, rescheduleOrder | 8 | Narayan Gaonkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTicketTransfers, modifyOrder, reprintOrder, rescheduleOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#listTicketTransfers`, `orders#modifyOrder`, `orders#reprintOrder`, `orders#rescheduleOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-CART-2 | AM-IDENTITY-SECURITY-P01 | [BE] OrderService: claimCart, createCart, extendCart, getCart | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PII MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimCart, createCart, extendCart, getCart. Spec: handoff/service-docs/backend/OrderService.md#group-cart. Done when `orders#claimCart`, `orders#createCart`, `orders#extendCart`, `orders#getCart` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDER-2 | AM-IDENTITY-SECURITY-P01 | [BE] OrderService: exchangeOrderLines, getMediaEntitlements, getOrder, getOrderCalendarEvent | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: exchangeOrderLines, getMediaEntitlements, getOrder, getOrderCalendarEvent. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#exchangeOrderLines`, `orders#getMediaEntitlements`, `orders#getOrder`, `orders#getOrderCalendarEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-IDENTITY-IDENTITY-1 | AM-IDENTITY-SECURITY-P02 | [BE] IdentityService: changeOwnCredential, exportSubjectData, forceLogout, getCurrentSession | 8 | Deep Khanvilkar | IdentityService | MIG-APPROVALS MIG-IDENTITY MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: changeOwnCredential, exportSubjectData, forceLogout, getCurrentSession. Spec: handoff/service-docs/backend/IdentityService.md#group-identity. Done when `identity#changeOwnCredential`, `identity#exportSubjectData`, `identity#forceLogout`, `identity#getCurrentSession` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-IDENTITY-IDENTITY-11 | AM-IDENTITY-SECURITY-P02 | [BE] IdentityService: getSubjectDataExport | 1 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-KERNEL SVC-IDENTITY-IDENTITY-1 | Operations: getSubjectDataExport. Spec: handoff/service-docs/backend/IdentityService.md#group-identity Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#getSubjectDataExport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-CART-1 | AM-IDENTITY-SECURITY-P02 | [BE] OrderService: abandonCart, addCartLine, applyCartPromoCode, checkoutCart | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: abandonCart, addCartLine, applyCartPromoCode, checkoutCart. Spec: handoff/service-docs/backend/OrderService.md#group-cart. Done when `orders#abandonCart`, `orders#addCartLine`, `orders#applyCartPromoCode`, `orders#checkoutCart` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CONSENT-4 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: setConsentPurposes, setCookieBannerDesign, setDynamicFieldQuestion, setTrackingTechnology | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setConsentPurposes, setCookieBannerDesign, setDynamicFieldQuestion, setTrackingTechnology. Spec: handoff/service-docs/backend/MarketingService.md#group-consent. Done when `marketing-crm#setConsentPurposes`, `marketing-crm#setCookieBannerDesign`, `marketing-crm#setDynamicFieldQuestion`, `marketing-crm#setTrackingTechnology` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CONSENT-5 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: updateConsentQuestion | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateConsentQuestion. Spec: handoff/service-docs/backend/MarketingService.md#group-consent Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#updateConsentQuestion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-GUEST-1 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: addToWishlist, getWishlist, listGuestDevices, registerGuestDevice | 5 | Deep Khanvilkar | MarketingService | MIG-CATALOGUE MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addToWishlist, getWishlist, listGuestDevices, registerGuestDevice. Spec: handoff/service-docs/backend/MarketingService.md#group-guest. Done when `marketing-crm#addToWishlist`, `marketing-crm#getWishlist`, `marketing-crm#listGuestDevices`, `marketing-crm#registerGuestDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-GUEST-2 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: removeFromWishlist, revokeGuestDevice, searchGuests | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeFromWishlist, revokeGuestDevice, searchGuests. Spec: handoff/service-docs/backend/MarketingService.md#group-guest Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#removeFromWishlist`, `marketing-crm#revokeGuestDevice`, `marketing-crm#searchGuests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-6 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: setAgentAvailability, setSeoMetadata, submitForm, updateGuestPreferences | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAgentAvailability, setSeoMetadata, submitForm, updateGuestPreferences. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#setAgentAvailability`, `marketing-crm#setSeoMetadata`, `marketing-crm#submitForm`, `marketing-crm#updateGuestPreferences` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-7 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: updateMyProfile, uploadGuestDocument | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateMyProfile, uploadGuestDocument. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#updateMyProfile`, `marketing-crm#uploadGuestDocument` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | PRD-W1-FRAME | AM-IDENTITY-SECURITY-P04 | [BE] Products wave 1: back-office frame (working venue and switcher, navigation, dashboard, All products) | 5 | Surendra |  | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PRD-W1-DB SETUP-AUTH | Products wave 1: back-office frame (working venue and switcher, navigation, dashboard, All products). Builds: `operation catalogue#getProductDashboard`, `operation identity#getSessionVenue`, `operation catalogue#listProductAttentionItems`, `operation identity#setSessionVenue`, `operation identity#getCurrentSession`, `operation catalogue#listProductLifecycle`, `operation catalogue#listProducts`, `table identity.session`, `table catalogue.product`, `table catalogue.variant`, `table catalogue.price`, `table catalogue.price_list`. getProductDashboard, getSessionVenue, listProductAttentionItems, setSessionVenue are built by this task, to their contracts at the release tag in ADAM; no other back-end task builds them. Spec: the contracts at the release tag in ADAM (CHG-R8PRD-002 to 011), from the 16 October 2026 minutes (sources/mom/TICVAI_MoM_2026-10-16_TicketingConfig_Wireframes_Plan.md). The back-office screens are held: build the screen from the products wireframe Pallavi Sawant shares (board ids below; its 21 October revision applies the minutes), not from a generated P08 screen. Back end: identity getSessionVenue and setSessionVenue (identity.session.working_venue_id, written with the session registry entry the token's sid names, so services read it from the caller's validated session; sign-in and role selection write it when the session has exactly one venue, fixed by its workstation or the only venue its grants reach), catalogue getProductDashboard and listProductAttentionItems; the screens also use getCurrentSession, listProductLifecycle and listProducts. Screens: the top bar and navigation of every back-office screen, B1-S01 Catalogue Command Center, B1-S02 Ticket Product Directory (All products). Every operation answers as its contract says, with a contract test for each status code and problem type it lists; the permission and venue scope are enforced (row security on scope_path); every write records the audit entry its contract names; paged lists keep their stated order; nothing is written outside the tables listed. Done when: the top bar shows the session's working venue and switches among availableVenues (fixed by a workstation or role: no switcher), refusing venue-not-in-grants, venue-fixed and session-pending, each switch audited, and the back office sends it as venueId on the venue-scoped calls that take one (the wave 1 reads and writes also fall back to it themselves, else venue-required); the navigation is filtered again from permissionsByScope after a switch; the dashboard tiles read countsByLifecycleState and open All products filtered the same way; Products by type reads countsByKind; Needs attention lists listProductAttentionItems in its order (readiness before notice); All products filters by search, status, type, channel, venue and department on listProductLifecycle, paged. The type filter maps the six ticket types of the minutes onto ProductKind (openDated, datedAdmission, timedAdmission, membership, giftCard, addOn) until wave 2.
6 | 2 | VM-MIG-IDENTITY | AM-IDENTITY-SECURITY-P06-BLOCK-A | [DB] Forward migration V1000__identity.sql: identity for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-IDENTITY | Tables: identity.access_decision. Source DDL: backend/tenant/010-identity.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (identity.access_decision: column matched_policies); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `identity.access_decision` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
5 | 3 | MIG-PII-2 | AM-IDENTITY-SECURITY-P06-BLOCK-A-COMPLETION | [DB] Forward migration V1242__pii.sql: pii for Identity & Security · Staff App (Block A completion) (1 tables) | 1 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-PII | Tables: pii.consent_identifier. Source DDL: backend/tenant/010-pii.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: pii.consent_identifier: foreign key consent_identifier_device_consent_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `pii.consent_identifier` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 3 | MIG-IDENTITY-2 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [DB] Forward migration V1001__identity.sql: identity for Identity & Security · Staff App (Block A) (4 tables) | 3 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM VM-MIG-IDENTITY | Tables: identity.guest_identity_verification, identity.guest_verification_policy, identity.principal_external_identity, identity.sso_group_mapping. Source DDL: backend/tenant/010-identity.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: identity.guest_identity_verification: foreign key guest_identity_verification_subject_id_fkey; identity.guest_verification_policy: rename column uae_pass_satisfies_id_document to accepts_uae_pass_as_id_document); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (identity.guest_identity_verification: column selfie_upload_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `identity.guest_identity_verification`, `identity.guest_verification_policy`, `identity.principal_external_identity`, `identity.sso_group_mapping` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-IDENTITY-GUESTAUTH-1 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [BE] IdentityService: deleteGuestAccount, getGuestSession, getMyIdentityVerification, guestLogout | 5 | Deep Khanvilkar | IdentityService | MIG-APPROVALS MIG-IDENTITY MIG-IDENTITY-2 MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: deleteGuestAccount, getGuestSession, getMyIdentityVerification, guestLogout. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#deleteGuestAccount`, `identity#getGuestSession`, `identity#getMyIdentityVerification`, `identity#guestLogout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-GUESTAUTH-3 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [BE] IdentityService: registerGuest, requestGuestOtp, submitGuestIdentityDocument, verifyGuestOtp | 8 | Hrushikant Patkar | IdentityService | MIG-ASSETS MIG-IDENTITY MIG-IDENTITY-2 MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: registerGuest, requestGuestOtp, submitGuestIdentityDocument, verifyGuestOtp. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#registerGuest`, `identity#requestGuestOtp`, `identity#submitGuestIdentityDocument`, `identity#verifyGuestOtp` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-IDENTITY-3 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [BE] IdentityService: selectRole, setGuestVerificationPolicy, setPasswordPolicy, setSegregationRules | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-IDENTITY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: selectRole, setGuestVerificationPolicy, setPasswordPolicy, setSegregationRules. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#selectRole`, `identity#setGuestVerificationPolicy`, `identity#setPasswordPolicy`, `identity#setSegregationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-IDENTITY-12 | AM-IDENTITY-SECURITY-P06-BLOCK-A-COMPLETION | [BE] IdentityService: endGuestDeviceSessions, recordConsentIdentifier, updateGuestSubjectDetails | 3 | Deep Khanvilkar | IdentityService | MIG-PII MIG-PII-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endGuestDeviceSessions, recordConsentIdentifier, updateGuestSubjectDetails. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A completion); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#endGuestDeviceSessions`, `identity#recordConsentIdentifier`, `identity#updateGuestSubjectDetails` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-MFA-1 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [BE] IdentityService: createMfaChallenge, enrolMfaMethod, listMfaMethods, removeMfaMethod | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMfaChallenge, enrolMfaMethod, listMfaMethods, removeMfaMethod. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#createMfaChallenge`, `identity#enrolMfaMethod`, `identity#listMfaMethods`, `identity#removeMfaMethod` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-SSO-1 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [BE] IdentityService: completeSsoAuthorization, listSsoProviders, startSsoAuthorization | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-IDENTITY-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: completeSsoAuthorization, listSsoProviders, startSsoAuthorization. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#completeSsoAuthorization`, `identity#listSsoProviders`, `identity#startSsoAuthorization` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-ADMINISTRATION-1 | AM-IDENTITY-SECURITY-P13 | [BE] IdentityService: createRole, listOwnPlatformStaffGrants, listPrincipals, listRoles | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRole, listOwnPlatformStaffGrants, listPrincipals, listRoles. Spec: handoff/service-docs/backend/IdentityService.md#group-administration Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#createRole`, `identity#listOwnPlatformStaffGrants`, `identity#listPrincipals`, `identity#listRoles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-ADMINISTRATION-2 | AM-IDENTITY-SECURITY-P13 | [BE] IdentityService: openPlatformStaffGrant, setCapabilityTemplate, updatePrincipal, updateRole | 8 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: openPlatformStaffGrant, setCapabilityTemplate, updatePrincipal, updateRole. Spec: handoff/service-docs/backend/IdentityService.md#group-administration. Done when `identity#openPlatformStaffGrant`, `identity#setCapabilityTemplate`, `identity#updatePrincipal`, `identity#updateRole` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-IDENTITY-SESSION-1 | AM-IDENTITY-SECURITY-P04 | [BE] IdentityService: listActiveSessions | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-KERNEL PRD-W1-FRAME SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-MFA-2 | Operations: listActiveSessions. Spec: handoff/service-docs/backend/IdentityService.md#group-session Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#listActiveSessions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 2 | VM-MIG-CONTROL | AM-IDENTITY-SECURITY-P09 | [DB] Forward migration V1003__control.sql: control for Venue Management (2 tables) | 2 | Hrushikant Patkar |  | MIG-CONTROL | Tables: control.webhook_delivery, control.webhook_subscription. Source DDL: backend/control/010-control.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.webhook_delivery: foreign key webhook_delivery_subscription_id_fkey; control.webhook_subscription: foreign key webhook_delivery_subscription_id_fkey (from control.webhook_delivery), foreign key webhook_subscription_client_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0108__after_r1_20261020.sql (control.webhook_delivery: column replay_id, constraint webhook_delivery_replay_id_fkey, index webhook_delivery_replay_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Leave out the key webhook_delivery_replay_id_fkey** (control.webhook_delivery to control.webhook_replay): MIG-CONTROL-21 creates control.webhook_replay later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.webhook_delivery`, `control.webhook_subscription` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-CONTROL-14 | AM-IDENTITY-SECURITY-P09 | [DB] Forward migration V1247__control.sql: control for Identity & Security · TICVAI Console 1 of 5 (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.outbox. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.outbox` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 1 | SVC-WHITELABEL-MODULES-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getFeatureToggles, getModuleEnablement, setFeatureToggles, setLanguages | 3 | Sanket Keluskar | WhiteLabelService | MIG-CONTROL MIG-SUBSCRIPTION MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFeatureToggles, getModuleEnablement, setFeatureToggles, setLanguages. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-modules Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getFeatureToggles`, `white-label#getModuleEnablement`, `white-label#setFeatureToggles`, `white-label#setLanguages` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-OVERVIEW-2 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: recordStorefrontSessionEvents, setAnalyticsProvider, setMaintenanceMode | 5 | Deep Khanvilkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: recordStorefrontSessionEvents, setAnalyticsProvider, setMaintenanceMode. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-overview Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#recordStorefrontSessionEvents`, `white-label#setAnalyticsProvider`, `white-label#setMaintenanceMode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-PUBLISHING-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: createPreview, diffConfigVersion, exportSitePackage, getPublishReviewPolicy | 5 | Deep Khanvilkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createPreview, diffConfigVersion, exportSitePackage, getPublishReviewPolicy. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#createPreview`, `white-label#diffConfigVersion`, `white-label#exportSitePackage`, `white-label#getPublishReviewPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-PUBLISHING-2 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getSitePackage, getSiteSetupProgress, listConfigVersions, publishTenantConfig | 5 | Narayan Gaonkar | WhiteLabelService | MIG-APPROVALS MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getSitePackage, getSiteSetupProgress, listConfigVersions, publishTenantConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getSitePackage`, `white-label#getSiteSetupProgress`, `white-label#listConfigVersions`, `white-label#publishTenantConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-PUBLISHING-3 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: restoreConfigVersion, setPublishReviewPolicy, setSiteSetupProgress, validateTenantConfig | 8 | Narayan Gaonkar | WhiteLabelService | MIG-APPROVALS MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: restoreConfigVersion, setPublishReviewPolicy, setSiteSetupProgress, validateTenantConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing. Done when `white-label#restoreConfigVersion`, `white-label#setPublishReviewPolicy`, `white-label#setSiteSetupProgress`, `white-label#validateTenantConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-THEME-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getFonts, getTheme, setFonts, setTheme | 5 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFonts, getTheme, setFonts, setTheme. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-theme Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getFonts`, `white-label#getTheme`, `white-label#setFonts`, `white-label#setTheme` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-WHITELABEL-WHITELABEL-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: createContentBlock, listContentBlocks, publishContentBlock, setFooter | 8 | Hrushikant Patkar | WhiteLabelService | MIG-APPROVALS MIG-IDENTITY MIG-MARKETING MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createContentBlock, listContentBlocks, publishContentBlock, setFooter. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-whitelabel. Done when `white-label#createContentBlock`, `white-label#listContentBlocks`, `white-label#publishContentBlock`, `white-label#setFooter` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-TENANT-1 | AM-IDENTITY-SECURITY-P09 | [BE] PlatformService: createTenant, listTenants, reactivateTenant, suspendTenant | 8 | Narayan Gaonkar | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTenant, listTenants, reactivateTenant, suspendTenant. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 1 of 5; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#createTenant`, `subscription#listTenants`, `subscription#reactivateTenant`, `subscription#suspendTenant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-DEVICES-1 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: setDeviceAssignment | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeviceAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-devices Helper task: Pranay Shinde owns the service and reviews. Done when `tenancy#setDeviceAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-WORKSTATION-2 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: listDevices, listSaleBoards, updateOutlet, updateSaleBoard | 8 | Sanket Keluskar | TenancyService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDevices, listSaleBoards, updateOutlet, updateSaleBoard. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation. Done when `tenancy#listDevices`, `tenancy#listSaleBoards`, `tenancy#updateOutlet`, `tenancy#updateSaleBoard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-TENANCY-GENERAL-1 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: getDeviceAssignment | 1 | Chinmay Patkar | TenancyService | MIG-TENANCY PLATFORM-KERNEL SVC-TENANCY-DEVICES-1 | Operations: getDeviceAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-general Helper task: Pranay Shinde owns the service and reviews. Done when `tenancy#getDeviceAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-TENANCY-WORKSTATION-1 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: configureWorkstation, createOutlet, createSaleBoard, getOutlet | 8 | Pranay Shinde | TenancyService | MIG-CATALOGUE MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureWorkstation, createOutlet, createSaleBoard, getOutlet. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation. Done when `tenancy#configureWorkstation`, `tenancy#createOutlet`, `tenancy#createSaleBoard`, `tenancy#getOutlet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-1 | AM-TENANCY-VENUES-P04 | [BE] OrderService: acceptShiftVariance, allocateDepositBox, approveShiftOpen, closeShift | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acceptShiftVariance, allocateDepositBox, approveShiftOpen, closeShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#acceptShiftVariance`, `shift#allocateDepositBox`, `shift#approveShiftOpen`, `shift#closeShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-3 | AM-TENANCY-VENUES-P04 | [BE] OrderService: giveShiftVarianceReason, listDenominations, listDepositBoxes, listShifts | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: giveShiftVarianceReason, listDenominations, listDepositBoxes, listShifts. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#giveShiftVarianceReason`, `shift#listDenominations`, `shift#listDepositBoxes`, `shift#listShifts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 2 | VM-MIG-TENANCY | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1073__tenancy.sql: tenancy for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-TENANCY | Tables: tenancy.device_credential. Source DDL: backend/tenant/010-tenancy.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `tenancy.device_credential` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 2 | VM-MIG-PLATFORM | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1002__platform.sql: platform for Venue Management (3 tables) | 2 | Hrushikant Patkar |  | MIG-PLATFORM | Tables: platform.connectivity_policy, platform.offline_policy, platform.profile_deployment. Source DDL: backend/tenant/010-platform.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (platform.profile_deployment: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: platform.profile_deployment: foreign key profile_deployment_profile_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (platform.profile_deployment: index profile_deployment_profile_id_version_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: platform.profile_deployment: drop index profile_deployment_profile_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0115__names_after_r1_20261022.sql (the names the contracts use: platform.profile_deployment: change foreign key profile_deployment_profile_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `platform.connectivity_policy`, `platform.offline_policy`, `platform.profile_deployment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-CONTROL-4 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1074__control.sql: control for Tenancy & Venues · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.tenant_domain. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0104__after_r1_20261015.sql (control.tenant_domain: index tenant_domain_tenant_id_hostname_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0108__after_r1_20261020.sql (control.tenant_domain: DROP CONSTRAINT IF EXISTS tenant_domain_channel_chk; VALIDATE CONSTRAINT tenant_domain_channel_chk, constraint tenant_domain_channel_chk, index tenant_domain_hostname_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0109__names_after_r1_20261020.sql (the names the contracts use: control.tenant_domain: drop index tenant_domain_tenant_id_hostname_uniq); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.tenant_domain: index tenant_domain_tenant_id_channel_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.tenant_domain` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-CONTROL-5 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1085__control.sql: control for Tenancy & Venues · Venue Management (Block A) (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-CONTROL-6 MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.release, control.rollout. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. It also adds the foreign key(s) MIG-CONTROL-6 (whose file runs before this one) holds into its tables: control.migration -> control.release, control.release_component -> control.release. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.rollout: foreign key rollout_cell_rollout_id_fkey (from control.rollout_cell)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0108__after_r1_20261020.sql (control.release: column plan_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also add the key migration_release_id_fkey here** (control.migration to control.release, guarded): MIG-CONTROL-6 creates control.migration before control.release exists. **Also add the key release_component_release_id_fkey here** (control.release_component to control.release, guarded): MIG-CONTROL-6 creates control.release_component before control.release exists. **Also add the key rollout_cell_rollout_id_fkey here** (control.rollout_cell to control.rollout, guarded): MIG-CONTROL-6 creates control.rollout_cell before control.rollout exists. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column retired `control.release.plan_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.release`, `control.rollout` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-TENANCY-2 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1075__tenancy.sql: tenancy for Tenancy & Venues · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-TENANCY VM-MIG-TENANCY | Tables: tenancy.device_tamper_event. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (tenancy.device_tamper_event: column recorded_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: tenancy.device_tamper_event: foreign key device_tamper_event_device_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `tenancy.device_tamper_event` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 3 | MIG-CONTROL-6 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1004__control.sql: control for Tenancy & Venues · Venue Management (Block A) (17 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.cell, control.config_package, control.config_package_application, control.config_package_diff, control.environment, control.migration, control.migration_plan, control.migration_plan_cell, control.migration_run, control.migration_run_cell, control.migration_run_tenant, control.outbox_republish, control.release_component, control.rollout_cell, control.rollout_tenant, control.support_notice, control.upgrade_schedule. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0104__after_r1_20261015.sql (control.migration_run: row-level security apply_parent_rls; control.migration_run_cell: row-level security apply_parent_rls; control.migration_run_tenant: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.cell: foreign key cell_instance_cell_id_fkey (from control.cell_instance), foreign key cell_tenant_cell_id_fkey (from control.cell_tenant), foreign key migration_run_cell_cell_id_fkey (from control.migration_run_cell), foreign key migration_run_tenant_cell_id_fkey (from control.migration_run_tenant), foreign key rollout_tenant_cell_id_fkey (from control.rollout_tenant), foreign key tenant_migration_plan_from_cell_id_fkey (from control.tenant_migration_plan), foreign key tenant_migration_plan_to_cell_id_fkey (from control.tenant_migration_plan); control.migration_plan: foreign key migration_run_plan_id_fkey (from control.migration_run); control.migration_run: foreign key migration_run_plan_id_fkey; control.migration_run_cell: foreign key migration_run_cell_cell_id_fkey; control.migration_run_tenant: foreign key migration_run_tenant_cell_id_fkey, foreign key migration_run_tenant_tenant_id_fkey; control.rollout_cell: foreign key rollout_cell_rollout_id_fkey; control.rollout_tenant: foreign key rollout_tenant_cell_id_fkey, foreign key rollout_tenant_tenant_id_fkey; control.upgrade_schedule: rename column deferred_by_tenant to is_deferred_by_tenant, foreign key upgrade_schedule_tenant_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key cell_tenant_cell_id_fkey here** (control.cell_tenant to control.cell, guarded): MIG-CONTROL creates control.cell_tenant before control.cell exists. **Leave out the key migration_release_id_fkey** (control.migration to control.release): MIG-CONTROL-5 creates control.release later and adds it. **Leave out the key release_component_release_id_fkey** (control.release_component to control.release): MIG-CONTROL-5 creates control.release later and adds it. **Leave out the key rollout_cell_rollout_id_fkey** (control.rollout_cell to control.rollout): MIG-CONTROL-5 creates control.rollout later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `control.outbox_republish.status`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.cell`, `control.config_package`, `control.config_package_application`, `control.config_package_diff`, `control.environment`, `control.migration`, `control.migration_plan`, `control.migration_plan_cell` and 9 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 3 | MIG-PLATFORM-2 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1076__platform.sql: control for Tenancy & Venues · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-CONTROL-6 MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.cell_endpoint. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `platform.cell_endpoint`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.cell_endpoint` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 3 | MIG-PLATFORM-4 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1236__platform.sql: platform for Tenancy & Venues · Venue Management (Block A) (1 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-PLATFORM VM-MIG-PLATFORM | Tables: platform.dead_letter. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (platform.dead_letter: columns event_id, tenant_id, aggregate_type, aggregate_id and sequence); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `platform.dead_letter` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-DEVICES-3 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: listDeviceAuditRecords, listDeviceTamperEvents, recordDeviceTamperEvent | 3 | Pranay Shinde | TenancyService | MIG-PLATFORM MIG-TENANCY MIG-TENANCY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listDeviceAuditRecords, listDeviceTamperEvents, recordDeviceTamperEvent. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#listDeviceAuditRecords`, `tenancy#listDeviceTamperEvents`, `tenancy#recordDeviceTamperEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-TENANCY-4 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: resolveTenantHost, setTenantDomainMapping | 3 | Surendra | TenancyService | MIG-CONTROL MIG-CONTROL-4 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: resolveTenantHost, setTenantDomainMapping. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#resolveTenantHost`, `tenancy#setTenantDomainMapping` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-TENANCY-7 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: requeueDeadLetter | 1 | Deep Khanvilkar | TenancyService | MIG-PLATFORM MIG-PLATFORM-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: requeueDeadLetter. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#requeueDeadLetter` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | VM-TENANCY-TENANCY-1 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: deployConfigurationProfile, getOfflinePolicy, getVenueSettings, listAuditRecords | 8 | Pranay Shinde | TenancyService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PLATFORM | Operations: deployConfigurationProfile, getOfflinePolicy, getVenueSettings, listAuditRecords. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#deployConfigurationProfile`, `tenancy#getOfflinePolicy`, `tenancy#getVenueSettings`, `tenancy#listAuditRecords` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | VM-TENANCY-TENANCY-2 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: setConfigurationProfile, setConnectivityThresholds, setOfflinePolicy | 5 | Sanket Keluskar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PLATFORM | Operations: setConfigurationProfile, setConnectivityThresholds, setOfflinePolicy. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#setConfigurationProfile`, `tenancy#setConnectivityThresholds`, `tenancy#setOfflinePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKSTATION-3 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: recordDeviceHeartbeat | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-TENANCY | Operations: recordDeviceHeartbeat. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#recordDeviceHeartbeat` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-TENANCY-3 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: getConfigurationProfile, getConnectivityPolicy, listCellEndpoints, listProfileDeployments | 3 | Deep Khanvilkar | TenancyService | MIG-PLATFORM MIG-PLATFORM-2 PLATFORM-KERNEL VM-MIG-PLATFORM VM-TENANCY-TENANCY-1 VM-TENANCY-TENANCY-2 | Operations: getConfigurationProfile, getConnectivityPolicy, listCellEndpoints, listProfileDeployments. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#getConfigurationProfile`, `tenancy#getConnectivityPolicy`, `tenancy#listCellEndpoints`, `tenancy#listProfileDeployments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-ORDER-SYNC-1 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] OrderService: resolveSyncRejection | 2 | Chinmay Patkar | OrderService | MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: resolveSyncRejection. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#resolveSyncRejection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CROSSREGION-CROSS-REGION-3 | AM-PLATFORM-OPERATIONS-API-BLOCK-A-COMPLETION | [BE] CrossRegionService: recordSyncRejection, recordSyncRejectionResolution | 3 | Deep Khanvilkar | CrossRegionService | MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordSyncRejection, recordSyncRejectionResolution. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · API only (Block A completion); additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#recordSyncRejection`, `cross-region#recordSyncRejectionResolution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-8 | AM-SUBSCRIPTION-LICENSING-P09 | [DB] Forward migration V1092__control.sql: control for Subscription & Licensing · TICVAI Console 1 of 6 (2 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.cell_instance, control.cell_job. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.cell_instance: foreign key cell_instance_cell_id_fkey, foreign key cell_tenant_instance_id_fkey (from control.cell_tenant)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0108__after_r1_20261020.sql (control.cell_job: column target_tier); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also add the key cell_tenant_instance_id_fkey here** (control.cell_tenant to control.cell_instance, guarded): MIG-CONTROL creates control.cell_tenant before control.cell_instance exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.cell_instance`, `control.cell_job` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-CONTROL-7 | AM-SUBSCRIPTION-LICENSING-P09 | [DB] Forward migration V1090__control.sql: control for Subscription & Licensing · Venue Management 1 of 3 (23 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.burst_environment, control.cell_cluster, control.invoice, control.invoice_number_sequence, control.partner_application_review_task, control.partner_capability_grant, control.partner_case, control.partner_commission_line, control.partner_commission_rule, control.partner_commission_rule_tier, control.partner_contact, control.partner_credit_profile, control.partner_distribution_right, control.partner_document, control.partner_rate, control.partner_reconciliation_exception, control.partner_scope_assignment, control.partner_security, control.partner_settlement_batch, control.platform_tax_rate, control.tenant_migration, control.tenant_migration_plan, control.usage_record. Source DDL: backend/control/010-control.sql and backend/control/V0116__after_r1_20261026.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0104__after_r1_20261015.sql (control.tenant_migration_plan: column blockers); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.cell_cluster: rename column accepting_new_tenants to is_accepting_new_tenants; control.invoice: foreign key credit_note_invoice_id_fkey (from control.credit_note), foreign key invoice_tenant_id_fkey; control.partner_capability_grant: foreign key partner_capability_grant_partner_id_fkey; control.partner_case: foreign key partner_case_partner_id_fkey, drop index partner_case_order_id_idx; control.partner_commission_line: foreign key partner_commission_line_agreement_id_fkey, foreign key partner_commission_line_partner_id_fkey, drop index partner_commission_line_order_id_idx, drop index partner_commission_line_product_id_idx; control.partner_commission_rule: foreign key partner_commission_rule_agreement_id_fkey, foreign key partner_commission_rule_partner_id_fkey, drop index partner_commission_rule_product_id_idx; control.partner_contact: foreign key partner_contact_partner_id_fkey; control.partner_credit_profile: foreign key partner_credit_profile_agreement_id_fkey, foreign key partner_credit_profile_partner_id_fkey; control.partner_distribution_right: foreign key partner_distribution_right_partner_id_fkey; control.partner_document: foreign key partner_document_partner_id_fkey; control.partner_rate: rename column seasonal_rate to is_seasonal_rate, foreign key partner_rate_agreement_id_fkey, foreign key partner_rate_partner_id_fkey, drop index partner_rate_product_id_idx; control.partner_reconciliation_exception: foreign key partner_reconciliation_exception_partner_id_fkey, drop index partner_reconciliation_exception_order_id_idx; control.partner_scope_assignment: rename column seasonal_scope to is_seasonal_scope, foreign key partner_scope_assignment_partner_id_fkey; control.partner_security: foreign key partner_security_partner_id_fkey; control.partner_settlement_batch: foreign key partner_settlement_batch_partner_id_fkey; control.tenant_migration_plan: foreign key tenant_migration_plan_from_cell_id_fkey, foreign key tenant_migration_plan_to_cell_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.invoice: columns invoice_number, issuing_legal_entity and currency_code, index invoice_tenant_id_period_start_period_end_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `control.invoice.currency_code`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.burst_environment`, `control.cell_cluster`, `control.invoice`, `control.invoice_number_sequence`, `control.partner_application_review_task`, `control.partner_capability_grant`, `control.partner_case`, `control.partner_commission_line` and 15 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 1 | SVC-PLATFORM-LICENSING-1 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: addLicenceAddOn, getTenantLicences | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addLicenceAddOn, getTenantLicences. Spec: handoff/service-docs/backend/PlatformService.md#group-licensing Helper task: Narayan Gaonkar owns the service and reviews. Done when `subscription#addLicenceAddOn`, `subscription#getTenantLicences` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: listModuleCatalogue, setModuleListing, setSubscription | 5 | Sanket Keluskar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listModuleCatalogue, setModuleListing, setSubscription. Spec: handoff/service-docs/backend/PlatformService.md#group-subscription Helper task: Narayan Gaonkar owns the service and reviews. Done when `subscription#listModuleCatalogue`, `subscription#setModuleListing`, `subscription#setSubscription` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-MODULES-2 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] WhiteLabelService: setModuleEnablement | 2 | Chinmay Patkar | WhiteLabelService | MIG-CONTROL MIG-SUBSCRIPTION MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setModuleEnablement. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-modules Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#setModuleEnablement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-5 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: updateCellTier | 1 | Pranay Shinde | PlatformService | MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateCellTier. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#updateCellTier` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-3 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: cancelDecommission, decommissionCell, getCell, getCellCapacity | 5 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelDecommission, decommissionCell, getCell, getCellCapacity. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#cancelDecommission`, `subscription#decommissionCell`, `subscription#getCell`, `subscription#getCellCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 1 | VM-MIG-APPROVALS | AM-APPROVALS-P04 | [DB] Forward migration V1005__approvals.sql: approvals for the first release (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE | Tables: approvals.escalation. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze), pushed before the first release needed it and kept under its pushed key (CHG-R6G-001); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (approvals.escalation: columns escalated_at, reason, from_level, to_level, was_automatic, escalated_by_principal_id and added_approver_principal_id, indexes escalation_added_approver_principal_id_idx and escalation_escalated_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `approvals.escalation.escalated_at`; not null `approvals.escalation.to_level`; not null `approvals.escalation.was_automatic`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.escalation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 1 | SVC-TENANCY-APPROVALS-1 | AM-APPROVALS-P04 | [BE] TenancyService: approveMatrixMultiLevel, approveRoleAuthorityDelegation | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveMatrixMultiLevel, approveRoleAuthorityDelegation. Spec: handoff/service-docs/backend/TenancyService.md#group-approvals Helper task: Pranay Shinde owns the service and reviews. Done when `approvals#approveMatrixMultiLevel`, `approvals#approveRoleAuthorityDelegation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-TENANCY-REQUEST-1 | AM-APPROVALS-P04 | [BE] TenancyService: createApprovalRequest, decideApprovalRequest, evaluateApprovalRequirement, listApprovalRequests | 8 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-APPROVALS | Operations: createApprovalRequest, decideApprovalRequest, evaluateApprovalRequirement, listApprovalRequests. Spec: handoff/service-docs/backend/TenancyService.md#group-request. Done when `approvals#createApprovalRequest`, `approvals#decideApprovalRequest`, `approvals#evaluateApprovalRequirement`, `approvals#listApprovalRequests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-CARD-1 | AM-APPROVALS-P04 | [BE] WalletService: loadGameCredits | 5 | Sanket Keluskar | WalletService | MIG-GAMES MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: loadGameCredits. Spec: handoff/service-docs/backend/WalletService.md#group-card Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#loadGameCredits` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-RETAIL-2 | AM-APPROVALS-P04 | [BE] WalletService: transferWalletBalance | 3 | Sanket Keluskar | WalletService | MIG-PII MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferWalletBalance. Spec: handoff/service-docs/backend/WalletService.md#group-retail Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#transferWalletBalance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-WALLET-1 | AM-APPROVALS-P04 | [BE] WalletService: getWallet, listWalletTransactions, publishWalletConfiguration, restoreWalletConfigurationVersion | 8 | Pranay Shinde | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWallet, listWalletTransactions, publishWalletConfiguration, restoreWalletConfigurationVersion. Spec: handoff/service-docs/backend/WalletService.md#group-wallet. Done when `wallet#getWallet`, `wallet#listWalletTransactions`, `wallet#publishWalletConfiguration`, `wallet#restoreWalletConfigurationVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-WALLET-7 | AM-APPROVALS-P04 | [BE] WalletService: createCreditType, setWalletTransferRules, updateCreditType | 5 | Deep Khanvilkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCreditType, setWalletTransferRules, updateCreditType. Spec: handoff/service-docs/backend/WalletService.md#group-wallet Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#createCreditType`, `wallet#setWalletTransferRules`, `wallet#updateCreditType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-4 | AM-APPROVALS-P04 | [BE] OrderService: openShift, recordNoSale, rejectShiftVariance, reopenShift | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: openShift, recordNoSale, rejectShiftVariance, reopenShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#openShift`, `shift#recordNoSale`, `shift#rejectShiftVariance`, `shift#reopenShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-FLOOR-1 | AM-APPROVALS-P04 | [BE] RetailService: collectShopAndDrop, createShopAndDrop, lookupMerchandise, lookupShopAndDrop | 5 | Deep Khanvilkar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: collectShopAndDrop, createShopAndDrop, lookupMerchandise, lookupShopAndDrop. Spec: handoff/service-docs/backend/RetailService.md#group-floor. Done when `retail#collectShopAndDrop`, `retail#createShopAndDrop`, `retail#lookupMerchandise`, `retail#lookupShopAndDrop` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-FLOOR-2 | AM-APPROVALS-P04 | [BE] RetailService: reserveMerchandise | 2 | Chinmay Patkar | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: reserveMerchandise. Spec: handoff/service-docs/backend/RetailService.md#group-floor Helper task: Hrushikant Patkar owns the service and reviews. Done when `retail#reserveMerchandise` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-MERCHANDISE-1 | AM-APPROVALS-P04 | [BE] RetailService: createMerchandise, listMerchandise, updateMerchandise | 5 | Pranay Shinde | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMerchandise, listMerchandise, updateMerchandise. Spec: handoff/service-docs/backend/RetailService.md#group-merchandise. Done when `retail#createMerchandise`, `retail#listMerchandise`, `retail#updateMerchandise` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-RETURN-1 | AM-APPROVALS-P04 | [BE] RetailService: createRetailReturn, getReturnPolicy, lookupRetailSale, setReturnPolicy | 8 | Pranay Shinde | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailReturn, getReturnPolicy, lookupRetailSale, setReturnPolicy. Spec: handoff/service-docs/backend/RetailService.md#group-return. Done when `retail#createRetailReturn`, `retail#getReturnPolicy`, `retail#lookupRetailSale`, `retail#setReturnPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-SALE-1 | AM-APPROVALS-P04 | [BE] RetailService: createRetailSale, getRetailSale, listRetailSales, reprintReceipt | 8 | Pranay Shinde | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailSale, getRetailSale, listRetailSales, reprintReceipt. Spec: handoff/service-docs/backend/RetailService.md#group-sale. Done when `retail#createRetailSale`, `retail#getRetailSale`, `retail#listRetailSales`, `retail#reprintReceipt` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 2 | VM-MIG-AI | AM-APPROVALS-P08-BLOCK-A | [DB] Forward migration V1006__ai.sql: ai for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-AI | Tables: ai.approval_request_score. Source DDL: backend/tenant/010-ai.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ai.approval_request_score: column signals); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.approval_request_score` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 3 | MIG-APPROVALS-5 | AM-APPROVALS-P08-BLOCK-A | [DB] Forward migration V1009__approvals.sql: approvals for Approvals · Venue Management (Block A) (3 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-BASELINE | Tables: approvals.automation_execution, approvals.external_dispatch, approvals.step_up_policy. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (approvals.step_up_policy: row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: approvals.automation_execution: foreign key automation_execution_automation_id_fkey; approvals.external_dispatch: foreign key external_dispatch_provider_id_fkey, foreign key external_dispatch_request_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (approvals.external_dispatch: column requester_reference); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Leave out the key automation_execution_automation_id_fkey** (approvals.automation_execution to approvals.automation): MIG-APPROVALS-6 creates approvals.automation later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.automation_execution`, `approvals.external_dispatch`, `approvals.step_up_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 3 | MIG-APPROVALS-6 | AM-APPROVALS-P08-BLOCK-A | [DB] Forward migration V1099__approvals.sql: approvals for Approvals · Venue Management (Block A) (12 tables) | 8 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-BASELINE | Tables: approvals.approved_action_execution, approvals.automation, approvals.business_rule, approvals.control_policy, approvals.decision_record, approvals.decision_table, approvals.decision_table_row, approvals.workflow_exception, approvals.workflow_instance, approvals.workflow_intervention, approvals.workflow_step_execution, approvals.workflow_trigger. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (approvals.control_policy: row-level security apply_read_beneath_rls; approvals.decision_record: column policy_versions); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: approvals.approved_action_execution: foreign key approved_action_execution_approval_request_id_fkey; approvals.automation: foreign key automation_execution_automation_id_fkey (from approvals.automation_execution); approvals.workflow_exception: foreign key workflow_exception_workflow_instance_id_fkey; approvals.workflow_instance: foreign key workflow_exception_workflow_instance_id_fkey (from approvals.workflow_exception), foreign key workflow_instance_workflow_definition_id_fkey, foreign key workflow_instance_workflow_version_id_fkey, foreign key workflow_intervention_workflow_instance_id_fkey (from approvals.workflow_intervention), foreign key workflow_step_execution_workflow_instance_id_fkey (from approvals.workflow_step_execution), drop index workflow_instance_current_node_id_idx; approvals.workflow_intervention: foreign key workflow_intervention_actor_principal_id_fkey, foreign key workflow_intervention_workflow_instance_id_fkey, drop index workflow_intervention_alternative_node_id_idx; approvals.workflow_step_execution: foreign key workflow_step_execution_workflow_instance_id_fkey; approvals.workflow_trigger: foreign key workflow_trigger_workflow_definition_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key automation_execution_automation_id_fkey here** (approvals.automation_execution to approvals.automation, guarded): MIG-APPROVALS-5 creates approvals.automation_execution before approvals.automation exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.approved_action_execution`, `approvals.automation`, `approvals.business_rule`, `approvals.control_policy`, `approvals.decision_record`, `approvals.decision_table`, `approvals.decision_table_row`, `approvals.workflow_exception` and 4 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-TENANCY-REQUEST-1 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: escalateApprovalRequest, getApprovalRequest, resubmitApprovalRequest, withdrawApprovalRequest | 8 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-APPROVALS | Operations beyond the first release: escalateApprovalRequest, getApprovalRequest, resubmitApprovalRequest, withdrawApprovalRequest. Additive to TenancyService; its first-release owner (Pranay Shinde) reviews. Done when `approvals#escalateApprovalRequest`, `approvals#getApprovalRequest`, `approvals#resubmitApprovalRequest`, `approvals#withdrawApprovalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-4 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: approveUnifiedDecision, listAutomationExecutions | 3 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-5 MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: approveUnifiedDecision, listAutomationExecutions. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#approveUnifiedDecision`, `approvals#listAutomationExecutions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-2 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: assignApprovalRequest, cancelApprovalRequest, recordExternalApprovalDecision, reopenApprovalRequest | 8 | Narayan Gaonkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-5 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-APPROVALS | Operations: assignApprovalRequest, cancelApprovalRequest, recordExternalApprovalDecision, reopenApprovalRequest. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#assignApprovalRequest`, `approvals#cancelApprovalRequest`, `approvals#recordExternalApprovalDecision`, `approvals#reopenApprovalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-3 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: submitApprovalRequest | 3 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-APPROVALS | Operations: submitApprovalRequest. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#submitApprovalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-6 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: recordApprovedActionOutcome | 1 | Deep Khanvilkar | TenancyService | MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordApprovedActionOutcome. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#recordApprovedActionOutcome` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-AI-RISK-1 | AM-APPROVALS-P08-BLOCK-A | [BE] AiService: getApprovalRequestScore | 1 | Chinmay Patkar | AiService | PLATFORM-KERNEL VM-MIG-AI | Operations beyond the first release: getApprovalRequestScore. Additive to AiService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `ai#getApprovalRequestScore` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PUBLICAPI-12 | AM-PUBLIC-API-P14-BLOCK-A | [BE] PlatformService: verifyDeveloper | 1 | Chinmay Patkar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: verifyDeveloper. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi Helper task: Narayan Gaonkar owns the service and reviews. Done when `public-api#verifyDeveloper` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-21 | AM-PUBLIC-API-API-BLOCK-A-COMPLETION | [DB] Forward migration V1248__control.sql: control for Public API · API only (Block A completion) (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.webhook_replay. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.webhook_replay: columns tenant_id and failure_reason, constraint webhook_replay_tenant_id_fkey, index webhook_replay_tenant_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also add the key webhook_delivery_replay_id_fkey here** (control.webhook_delivery to control.webhook_replay, guarded): VM-MIG-CONTROL creates control.webhook_delivery before control.webhook_replay exists. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `control.webhook_replay.tenant_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.webhook_replay` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-9 | AM-PUBLIC-API-API-BLOCK-A-COMPLETION | [BE] PlatformService: replayEvents | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL-21 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations: replayEvents. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · API only (Block A completion); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#replayEvents` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ASSET-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: deleteMediaAsset, getMediaAsset, replaceMediaAsset, searchMedia | 8 | Narayan Gaonkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteMediaAsset, getMediaAsset, replaceMediaAsset, searchMedia. Spec: handoff/service-docs/backend/VenueOpsService.md#group-asset. Done when `assets#deleteMediaAsset`, `assets#getMediaAsset`, `assets#replaceMediaAsset`, `assets#searchMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ASSET-2 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: updateMediaAsset | 3 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateMediaAsset. Spec: handoff/service-docs/backend/VenueOpsService.md#group-asset Helper task: Narayan Gaonkar owns the service and reviews. Done when `assets#updateMediaAsset` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-COLLECTION-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: createCollection, listCollections | 2 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCollection, listCollections. Spec: handoff/service-docs/backend/VenueOpsService.md#group-collection Helper task: Narayan Gaonkar owns the service and reviews. Done when `assets#createCollection`, `assets#listCollections` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-UPLOAD-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: completeUpload, createUpload | 5 | Narayan Gaonkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: completeUpload, createUpload. Spec: handoff/service-docs/backend/VenueOpsService.md#group-upload Helper task: Narayan Gaonkar owns the service and reviews. Done when `assets#completeUpload`, `assets#createUpload` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-VENUEOPS-RIGHTS-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: getExpiringRights | 1 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-KERNEL SVC-VENUEOPS-ASSET-1 SVC-VENUEOPS-ASSET-2 SVC-VENUEOPS-UPLOAD-1 | Operations: getExpiringRights. Spec: handoff/service-docs/backend/VenueOpsService.md#group-rights Helper task: Narayan Gaonkar owns the service and reviews. Done when `assets#getExpiringRights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-AI-RETRIEVAL-1 | AM-DIGITAL-ASSETS-P13 | [BE] AiService: createKnowledgeCollection, ingestKnowledgeDocument, reindexSource, semanticSearch | 8 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS MIG-CATALOGUE MIG-FNB MIG-MAINTENANCE MIG-MARKETING MIG-REPORTING MIG-RETAIL MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createKnowledgeCollection, ingestKnowledgeDocument, reindexSource, semanticSearch. Spec: handoff/service-docs/backend/AiService.md#group-retrieval. Done when `ai#createKnowledgeCollection`, `ai#ingestKnowledgeDocument`, `ai#reindexSource`, `ai#semanticSearch` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-1 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: createBanner, createContentPage, createGuidedChoice, createPromoBlock | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBanner, createContentPage, createGuidedChoice, createPromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#createBanner`, `white-label#createContentPage`, `white-label#createGuidedChoice`, `white-label#createPromoBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-2 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: deleteBanner, deleteContentPage, deleteGuidedChoice, deletePromoBlock | 5 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteBanner, deleteContentPage, deleteGuidedChoice, deletePromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#deleteBanner`, `white-label#deleteContentPage`, `white-label#deleteGuidedChoice`, `white-label#deletePromoBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-5 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: listPublishedPolicies, proposeGuidedChoice, publishGuidedChoice, setFaqs | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPublishedPolicies, proposeGuidedChoice, publishGuidedChoice, setFaqs. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#listPublishedPolicies`, `white-label#proposeGuidedChoice`, `white-label#publishGuidedChoice`, `white-label#setFaqs` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-6 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: setPolicy, unpublishGuidedChoice, updateBanner, updateContentPage | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPolicy, unpublishGuidedChoice, updateBanner, updateContentPage. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#setPolicy`, `white-label#unpublishGuidedChoice`, `white-label#updateBanner`, `white-label#updateContentPage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-7 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: updateGuidedChoice, updatePromoBlock | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateGuidedChoice, updatePromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#updateGuidedChoice`, `white-label#updatePromoBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-WHITELABEL-CONTENT-4 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: listPolicies, listPromoBlocks, listPublishedContentPages, listPublishedFaqs | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-6 SVC-WHITELABEL-CONTENT-7 | Operations: listPolicies, listPromoBlocks, listPublishedContentPages, listPublishedFaqs. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#listPolicies`, `white-label#listPromoBlocks`, `white-label#listPublishedContentPages`, `white-label#listPublishedFaqs` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-CATALOGUE-2 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: listProductCategories, searchCatalogue, setProductCategories | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductCategories, searchCatalogue, setProductCategories. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#listProductCategories`, `catalogue#searchCatalogue`, `catalogue#setProductCategories` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: createEntitlementTemplate, setEntitlementTemplateBlackoutDates | 5 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createEntitlementTemplate, setEntitlementTemplateBlackoutDates. Spec: handoff/service-docs/backend/CatalogueService.md#group-entitlement Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createEntitlementTemplate`, `catalogue#setEntitlementTemplateBlackoutDates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-PRODUCT-3 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: resolveProductByCode, setAlternativeCodes, setGroupPackageDefinition, setProductEligibilityRule | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveProductByCode, setAlternativeCodes, setGroupPackageDefinition, setProductEligibilityRule. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#resolveProductByCode`, `catalogue#setAlternativeCodes`, `catalogue#setGroupPackageDefinition`, `catalogue#setProductEligibilityRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-PRODUCT-4 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: updateProduct, updateProductVariant | 5 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateProduct, updateProductVariant. Spec: handoff/service-docs/backend/CatalogueService.md#group-product. Done when `catalogue#updateProduct`, `catalogue#updateProductVariant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-BUNDLE-2 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: publishBundle, updateBundle | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishBundle, updateBundle. Spec: handoff/service-docs/backend/CatalogueService.md#group-bundle. Done when `catalogue#publishBundle`, `promotions#updateBundle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-4 | AM-WHITE-LABEL-P01 | [BE] AccessService: revokeFacePass, setAccessPointGroup, setBiometricVerificationProfile, setBleBeaconGeofence | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: revokeFacePass, setAccessPointGroup, setBiometricVerificationProfile, setBleBeaconGeofence. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#revokeFacePass`, `access#setAccessPointGroup`, `access#setBiometricVerificationProfile`, `access#setBleBeaconGeofence` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-6 | AM-WHITE-LABEL-P01 | [BE] AccessService: setFaceTagTemporaryEnrollment, setGateModePolicy, setParkingFacility, setVirtualTicketIdentity | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setFaceTagTemporaryEnrollment, setGateModePolicy, setParkingFacility, setVirtualTicketIdentity. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#setFaceTagTemporaryEnrollment`, `access#setGateModePolicy`, `access#setParkingFacility`, `access#setVirtualTicketIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-7 | AM-WHITE-LABEL-P01 | [BE] AccessService: setVisualAccessRule, updateParkingEntitlement | 3 | Sanket Keluskar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setVisualAccessRule, updateParkingEntitlement. Spec: handoff/service-docs/backend/AccessService.md#group-access Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#setVisualAccessRule`, `access#updateParkingEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESSPOINT-1 | AM-WHITE-LABEL-P01 | [BE] AccessService: addBlacklistEntry, createAccessPoint, createAdmissionRules, setAccessPointDirection | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addBlacklistEntry, createAccessPoint, createAdmissionRules, setAccessPointDirection. Spec: handoff/service-docs/backend/AccessService.md#group-accesspoint. Done when `access#addBlacklistEntry`, `access#createAccessPoint`, `access#createAdmissionRules`, `access#setAccessPointDirection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESSPOINT-2 | AM-WHITE-LABEL-P01 | [BE] AccessService: setAccessPointGeofence, setTurnstileMode, updateAccessPoint, updateAdmissionRules | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessPointGeofence, setTurnstileMode, updateAccessPoint, updateAdmissionRules. Spec: handoff/service-docs/backend/AccessService.md#group-accesspoint. Done when `access#setAccessPointGeofence`, `access#setTurnstileMode`, `access#updateAccessPoint`, `access#updateAdmissionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-CATALOGUE-CATALOGUE-1 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: bulkChangePrices, cloneProduct, commitCatalogueImport, getMyMemberships | 8 | Narayan Gaonkar | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bulkChangePrices, cloneProduct, commitCatalogueImport, getMyMemberships. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue. Done when `catalogue#bulkChangePrices`, `catalogue#cloneProduct`, `catalogue#commitCatalogueImport`, `catalogue#getMyMemberships` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDER-1 | AM-WHITE-LABEL-P01 | [BE] OrderService: appendEntitlementToMedia, applyManualDiscount, claimTicketTransfer, createOrder | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: appendEntitlementToMedia, applyManualDiscount, claimTicketTransfer, createOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#appendEntitlementToMedia`, `orders#applyManualDiscount`, `orders#claimTicketTransfer`, `orders#createOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDER-5 | AM-WHITE-LABEL-P01 | [BE] OrderService: resumeOrder, setVisitReminder, transferOrderTickets, voidOrder | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: resumeOrder, setVisitReminder, transferOrderTickets, voidOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#resumeOrder`, `orders#setVisitReminder`, `orders#transferOrderTickets`, `orders#voidOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDERS-4 | AM-WHITE-LABEL-P01 | [BE] OrderService: previewProductTickets, recordGroupCheckIn, reissueEntitlement, requestGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: previewProductTickets, recordGroupCheckIn, reissueEntitlement, requestGroupBooking. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#previewProductTickets`, `orders#recordGroupCheckIn`, `orders#reissueEntitlement`, `orders#requestGroupBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-ORDERS-3 | AM-WHITE-LABEL-P01 | [BE] OrderService: listBillingStatements, listMyOrders, listPaymentTokens, payByLink | 8 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listBillingStatements, listMyOrders, listPaymentTokens, payByLink. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#listBillingStatements`, `orders#listMyOrders`, `orders#listPaymentTokens`, `orders#payByLink` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-ORDERS-5 | AM-WHITE-LABEL-P01 | [BE] OrderService: setPaymentProvider, shareEntitlement, storePaymentToken, updateTicketTemplate | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setPaymentProvider, shareEntitlement, storePaymentToken, updateTicketTemplate. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#setPaymentProvider`, `orders#shareEntitlement`, `orders#storePaymentToken`, `orders#updateTicketTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | PRD-W1-CATEGORIES-TAGS | AM-WHITE-LABEL-P01 | [BE] Products wave 1: categories and tags as master data, back end and screens | 5 | Sanket Keluskar |  | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PRD-W1-DB | Products wave 1: categories and tags as master data, back end and screens. Builds: `operation catalogue#listProductCategoryUsage`, `operation catalogue#listProductTags`, `operation catalogue#setProductClassification`, `operation catalogue#setProductTagDefinition`, `operation catalogue#listProductCategories`, `operation catalogue#setProductCategories`, `table catalogue.product_category`, `table catalogue.product_tag`, `table catalogue.product`. listProductCategoryUsage, listProductTags, setProductClassification, setProductTagDefinition are built by this task, to their contracts at the release tag in ADAM; no other back-end task builds them. Spec: the contracts at the release tag in ADAM (CHG-R8PRD-002 to 011), from the 16 October 2026 minutes (sources/mom/TICVAI_MoM_2026-10-16_TicketingConfig_Wireframes_Plan.md). The back-office screens are held: build the screen from the products wireframe Pallavi Sawant shares (board ids below; its 21 October revision applies the minutes), not from a generated P08 screen. Back end in CatalogueService: listProductCategoryUsage, listProductTags, setProductTagDefinition, setProductClassification (listProductCategories and setProductCategories exist). Screens: B1-S05 Category & Hierarchy Manager, the new Tags screen of the Setup Library, the category drop-down and tag picker of B1-S04 Identity & Classification (the rest of B1-S04 is wave 2), the tag line of B11-S04. Every operation answers as its contract says, with a contract test for each status code and problem type it lists; the permission and venue scope are enforced (row security on scope_path); every write records the audit entry its contract names; paged lists keep their stated order; nothing is written outside the tables listed. Done when: the category manager shows each category's product counts (archived counted apart) and refuses dropping a used category; tags are listed, created, replaced and deactivated, with duplicate-code (unique in the venue, ignoring case) and tag-code-in-use (a product or a Help me choose answer carries it) refused; setProductClassification writes category_id and segment_tags, versions the product as updateProduct does, and refuses unknown-category, inactive-category, unknown-tag, inactive-tag and product-archived; listProducts with segmentTag finds the products a tag was given; the venue-scoped reads and the tag write take venueId, else the working venue, refusing venue-required and venue-not-in-grants.
15 | 1 | SVC-CATALOGUE-PRODUCT-2 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: listAlternativeCodes, listGroupPackages, listProductVariants, listProducts | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-5 SVC-WHITELABEL-CONTENT-7 | Operations: listAlternativeCodes, listGroupPackages, listProductVariants, listProducts. Spec: handoff/service-docs/backend/CatalogueService.md#group-product. Done when `catalogue#listAlternativeCodes`, `catalogue#listGroupPackages`, `catalogue#listProductVariants`, `catalogue#listProducts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-3 | AM-WHITE-LABEL-P02 | [BE] MarketingService: getMyProfile, getSeoMetadata, getWaiverStatus, handoverToAgent | 8 | Pranay Shinde | MarketingService | MIG-ACCESS MIG-CATALOGUE MIG-CONTROL MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getMyProfile, getSeoMetadata, getWaiverStatus, handoverToAgent. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#getMyProfile`, `marketing-crm#getSeoMetadata`, `marketing-crm#getWaiverStatus`, `marketing-crm#handoverToAgent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-5 | AM-WHITE-LABEL-P02 | [BE] MarketingService: redeemLoyaltyPoints, replyToMyCase, respondToInvitation, sendConversationMessage | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: redeemLoyaltyPoints, replyToMyCase, respondToInvitation, sendConversationMessage. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#redeemLoyaltyPoints`, `marketing-crm#replyToMyCase`, `marketing-crm#respondToInvitation`, `marketing-crm#sendConversationMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-MARKETING-MARKETING-4 | AM-WHITE-LABEL-P02 | [BE] MarketingService: identifyGuest, listMyCases, raiseMyCase, recordLostItem | 8 | Pranay Shinde | MarketingService | MIG-ACCESS MIG-MARKETING MIG-PII MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: identifyGuest, listMyCases, raiseMyCase, recordLostItem. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#identifyGuest`, `marketing-crm#listMyCases`, `marketing-crm#raiseMyCase`, `marketing-crm#recordLostItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 1 | SVC-WHITELABEL-CONTENT-8 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: previewGuidedChoice | 1 | Chinmay Patkar | WhiteLabelService | MIG-BASELINE PLATFORM-KERNEL | Operations: previewGuidedChoice. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#previewGuidedChoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-SCOPE-1 | AM-WHITE-LABEL-P13 | [BE] TenancyService: createOrgUnit, listOrgUnits, updateOrgUnit | 3 | Sanket Keluskar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createOrgUnit, listOrgUnits, updateOrgUnit. Spec: handoff/service-docs/backend/TenancyService.md#group-scope Helper task: Pranay Shinde owns the service and reviews. Done when `tenancy#createOrgUnit`, `tenancy#listOrgUnits`, `tenancy#updateOrgUnit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getAppBuild, getStoreAccounts, listAppBuilds, requestAppBuild | 5 | Deep Khanvilkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getAppBuild, getStoreAccounts, listAppBuilds, requestAppBuild. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-apppublishing Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getAppBuild`, `white-label#getStoreAccounts`, `white-label#listAppBuilds`, `white-label#requestAppBuild` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-APPPUBLISHING-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: setStoreAccounts | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setStoreAccounts. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-apppublishing Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#setStoreAccounts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: createBookingFlowDefinition, deleteBookingFlow, getBookingFlow, getPublishedBookingFlow | 8 | Hrushikant Patkar | WhiteLabelService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBookingFlowDefinition, deleteBookingFlow, getBookingFlow, getPublishedBookingFlow. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-bookingflows. Done when `white-label#createBookingFlowDefinition`, `white-label#deleteBookingFlow`, `white-label#getBookingFlow`, `white-label#getPublishedBookingFlow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: listBookingFlowTypes, listBookingFlows, updateBookingFlowDefinition, validateBookingFlow | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBookingFlowTypes, listBookingFlows, updateBookingFlowDefinition, validateBookingFlow. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-bookingflows. Done when `white-label#listBookingFlowTypes`, `white-label#listBookingFlows`, `white-label#updateBookingFlowDefinition`, `white-label#validateBookingFlow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BRAND-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getAppIcons, getBrandIdentity, setAppIcons, setBrandIdentity | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAppIcons, getBrandIdentity, setAppIcons, setBrandIdentity. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-brand Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getAppIcons`, `white-label#getBrandIdentity`, `white-label#setAppIcons`, `white-label#setBrandIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BRANDING-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getBookingFlowConfig, setBookingFlowConfig | 5 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBookingFlowConfig, setBookingFlowConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-branding Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getBookingFlowConfig`, `white-label#setBookingFlowConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-HOMEPAGE-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getHomepageLayout, listLandingPageTemplates, setHomepageLayout | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getHomepageLayout, listLandingPageTemplates, setHomepageLayout. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-homepage Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#getHomepageLayout`, `white-label#listLandingPageTemplates`, `white-label#setHomepageLayout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-NAVIGATION-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: buildDeepLink, getDeepLinkScheme, getNavigation, setHeader | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: buildDeepLink, getDeepLinkScheme, getNavigation, setHeader. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-navigation Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#buildDeepLink`, `white-label#getDeepLinkScheme`, `white-label#getNavigation`, `white-label#setHeader` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-NAVIGATION-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: setNavigation | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setNavigation. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-navigation Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#setNavigation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-WHITELABEL-OVERVIEW-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getPublishedTenantConfig, getTenantAppStatus, getTenantConfig, listAnalyticsProviders | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-BOOKINGFLOWS-1 SVC-WHITELABEL-BOOKINGFLOWS-2 SVC-WHITELABEL-BRAND-1 SVC-WHITELABEL-BRANDING-1 SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-6 SVC-WHITELABEL-HOMEPAGE-1 SVC-WHITELABEL-MODULES-1 SVC-WHITELABEL-MODULES-2 SVC-WHITELABEL-NAVIGATION-1 SVC-WHITELABEL-NAVIGATION-2 SVC-WHITELABEL-OVERVIEW-2 SVC-WHITELABEL-PUBLISHING-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-PUBLISHING-3 SVC-WHITELABEL-THEME-1 SVC-WHITELABEL-WHITELABEL-1 | Operations: getPublishedTenantConfig, getTenantAppStatus, getTenantConfig, listAnalyticsProviders. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-overview. Done when `white-label#getPublishedTenantConfig`, `white-label#getTenantAppStatus`, `white-label#getTenantConfig`, `white-label#listAnalyticsProviders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: claimCustomDomain, getPlatformSubdomain, listCustomDomains, regenerateDomainToken | 5 | Deep Khanvilkar | WhiteLabelService | MIG-CONTROL MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: claimCustomDomain, getPlatformSubdomain, listCustomDomains, regenerateDomainToken. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-white-label Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#claimCustomDomain`, `white-label#getPlatformSubdomain`, `white-label#listCustomDomains`, `white-label#regenerateDomainToken` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: relinquishCustomDomain, setPrimaryDomain, verifyCustomDomain | 5 | Deep Khanvilkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: relinquishCustomDomain, setPrimaryDomain, verifyCustomDomain. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-white-label Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#relinquishCustomDomain`, `white-label#setPrimaryDomain`, `white-label#verifyCustomDomain` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-WHITELABEL-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: updateContentBlock | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateContentBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-whitelabel Helper task: Hrushikant Patkar owns the service and reviews. Done when `white-label#updateContentBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-WHITELABEL-CONTENT-3 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getPublishedGuidedChoice, listBanners, listContentPages, listGuidedChoices | 8 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-5 SVC-WHITELABEL-CONTENT-6 SVC-WHITELABEL-CONTENT-7 SVC-WHITELABEL-PUBLISHING-2 | Operations: getPublishedGuidedChoice, listBanners, listContentPages, listGuidedChoices. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#getPublishedGuidedChoice`, `white-label#listBanners`, `white-label#listContentPages`, `white-label#listGuidedChoices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENT-2 | AM-WHITE-LABEL-P13 | [BE] CatalogueService: getWaitingRoomPosition, listEvents, listPerformances, updateEvent | 5 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingRoomPosition, listEvents, listPerformances, updateEvent. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#getWaitingRoomPosition`, `catalogue#listEvents`, `catalogue#listPerformances`, `catalogue#updateEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-ASSIST-1 | AM-WHITE-LABEL-P13 | [BE] AiService: createAiConversation, listAiConversations, sendAiMessage | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAiConversation, listAiConversations, sendAiMessage. Spec: handoff/service-docs/backend/AiService.md#group-assist Helper task: Pranay Shinde owns the service and reviews. Done when `ai#createAiConversation`, `ai#listAiConversations`, `ai#sendAiMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-CONFIGURE-1 | AM-WHITE-LABEL-P13 | [BE] AiService: getGuidedChoiceSuggestion, suggestGuidedChoice | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGuidedChoiceSuggestion, suggestGuidedChoice. Spec: handoff/service-docs/backend/AiService.md#group-configure Helper task: Pranay Shinde owns the service and reviews. Done when `ai#getGuidedChoiceSuggestion`, `ai#suggestGuidedChoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-GOVERNANCE-1 | AM-WHITE-LABEL-P13 | [BE] AiService: createAiGovernancePolicyDraft, decideProposedAction, evaluateAiGovernance, getAiUsage | 8 | Narayan Gaonkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAiGovernancePolicyDraft, decideProposedAction, evaluateAiGovernance, getAiUsage. Spec: handoff/service-docs/backend/AiService.md#group-governance. Done when `ai#createAiGovernancePolicyDraft`, `ai#decideProposedAction`, `ai#evaluateAiGovernance`, `ai#getAiUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-AI-GENERATE-1 | AM-WHITE-LABEL-P13 | [BE] AiService: proposeMarketingContent | 3 | Sanket Keluskar | AiService | MIG-AI MIG-CATALOGUE MIG-MARKETING MIG-PROMOTIONS MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeMarketingContent. Spec: handoff/service-docs/backend/AiService.md#group-generate Helper task: Pranay Shinde owns the service and reviews. Done when `ai#proposeMarketingContent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-AI-AI-1 | AM-WHITE-LABEL-P13 | [BE] AiService: getTranslationProposals, proposeTranslations, proposeVenueLabels, requestSuggestion | 8 | Pranay Shinde | AiService | MIG-AI MIG-FNB MIG-INVENTORY MIG-MARKETING MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getTranslationProposals, proposeTranslations, proposeVenueLabels, requestSuggestion. Spec: handoff/service-docs/backend/AiService.md#group-ai. Done when `ai#getTranslationProposals`, `ai#proposeTranslations`, `ai#proposeVenueLabels`, `ai#requestSuggestion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-AI-GOVERNANCE-4 | AM-WHITE-LABEL-P13 | [BE] AiService: listProposedActions | 1 | Narayan Gaonkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-AI-1 SVC-AI-ASSIST-1 SVC-AI-GENERATE-1 SVC-AI-GOVERNANCE-1 | Operations: listProposedActions. Spec: handoff/service-docs/backend/AiService.md#group-governance Helper task: Pranay Shinde owns the service and reviews. Done when `ai#listProposedActions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-DELEGATION-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: createApprovalDelegation | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createApprovalDelegation. Spec: handoff/service-docs/backend/TenancyService.md#group-delegation Helper task: Pranay Shinde owns the service and reviews. Done when `approvals#createApprovalDelegation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-IDENTITY-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: setRolePermissions | 2 | Chinmay Patkar | TenancyService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRolePermissions. Spec: handoff/service-docs/backend/TenancyService.md#group-identity Helper task: Pranay Shinde owns the service and reviews. Done when `tenancy#setRolePermissions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-MATRIX-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: setApprovalExternalProvider, setApprovalMatrix | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalExternalProvider, setApprovalMatrix. Spec: handoff/service-docs/backend/TenancyService.md#group-matrix Helper task: Pranay Shinde owns the service and reviews. Done when `approvals#setApprovalExternalProvider`, `approvals#setApprovalMatrix` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-TENANCY-TENANCY-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: getWorkstationHealth, setVenueSettings, setVenueSettingsDefaults | 5 | Deep Khanvilkar | TenancyService | MIG-ACCESS MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWorkstationHealth, setVenueSettings, setVenueSettingsDefaults. Spec: handoff/service-docs/backend/TenancyService.md#group-tenancy. Done when `tenancy#getWorkstationHealth`, `tenancy#setVenueSettings`, `tenancy#setVenueSettingsDefaults` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-9 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] FnbService: setCourseRules, setKitchenSla, setSubstitutionRules, setTableCombinations | 5 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCourseRules, setKitchenSla, setSubstitutionRules, setTableCombinations. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#setCourseRules`, `fnb#setKitchenSla`, `fnb#setSubstitutionRules`, `fnb#setTableCombinations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 2 | VM-MIG-WORKFORCE | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [DB] Forward migration V1036__workforce.sql: workforce for Venue Management (6 tables) | 3 | Hrushikant Patkar |  | MIG-WORKFORCE | Tables: workforce.announcement, workforce.announcement_receipt, workforce.employee, workforce.job_title, workforce.shift, workforce.work_assignment. Source DDL: backend/tenant/010-workforce.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: workforce.employee: foreign key employment_employee_id_fkey (from workforce.employment), foreign key leave_balance_employee_id_fkey (from workforce.leave_balance), foreign key work_assignment_employee_id_fkey (from workforce.work_assignment), drop index employee_tenant_id_idx; workforce.job_title: foreign key work_assignment_job_title_id_fkey (from workforce.work_assignment), drop index job_title_tenant_id_idx; workforce.shift: drop index shift_tenant_id_idx; workforce.work_assignment: foreign key work_assignment_employee_id_fkey, foreign key work_assignment_job_title_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.announcement`, `workforce.announcement_receipt`, `workforce.employee`, `workforce.job_title`, `workforce.shift`, `workforce.work_assignment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 3 | MIG-IDENTITY-3 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [DB] Forward migration V1058__identity.sql: identity for Identity & Security · Venue Management (12 tables) | 8 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-IDENTITY VM-MIG-IDENTITY | Tables: identity.access_override, identity.access_review_campaign, identity.access_review_item, identity.authorisation_policy, identity.authorisation_policy_version, identity.authz_audit, identity.benefit_usage, identity.customer_membership, identity.membership_history, identity.module, identity.module_access, identity.permission. Source DDL: backend/tenant/010-identity.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (identity.authorisation_policy: column status_reason, index authorisation_policy_code_uniq; identity.authz_audit: row-level security apply_append_audit_rls; identity.benefit_usage: column recorded_at, row-level security apply_parent_split_rls; identity.customer_membership: row-level security apply_parent_rls; identity.membership_history: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: identity.access_review_campaign: rename column prefill_from_findings to prefills_from_findings; identity.benefit_usage: foreign key benefit_usage_customer_membership_id_fkey, foreign key benefit_usage_membership_benefit_id_fkey; identity.customer_membership: foreign key benefit_usage_customer_membership_id_fkey (from identity.benefit_usage), foreign key customer_membership_entitlement_template_id_fkey, foreign key membership_history_customer_membership_id_fkey (from identity.membership_history), foreign key membership_renewal_customer_membership_id_fkey (from orders.membership_renewal); identity.membership_history: foreign key membership_history_customer_membership_id_fkey; identity.module: foreign key permission_module_id_fkey (from identity.permission); identity.permission: foreign key permission_module_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **identity.benefit_usage's row-level security waits for its parent**: its policy reads catalogue.membership_benefit, which MIG-CATALOGUE-5 creates later, so leave out its `platform.apply_parent_rls` call here; MIG-CATALOGUE-5 applies it. **Also apply orders.membership_renewal's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through identity.customer_membership): MIG-ORDERS-2 creates orders.membership_renewal before identity.customer_membership exists. **Leave out the key benefit_usage_membership_benefit_id_fkey** (identity.benefit_usage to catalogue.membership_benefit): MIG-CATALOGUE-5 creates catalogue.membership_benefit later and adds it. **Also add the key membership_renewal_customer_membership_id_fkey here** (orders.membership_renewal to identity.customer_membership, guarded): MIG-ORDERS-2 creates orders.membership_renewal before identity.customer_membership exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `identity.access_override`, `identity.access_review_campaign`, `identity.access_review_item`, `identity.authorisation_policy`, `identity.authorisation_policy_version`, `identity.authz_audit`, `identity.benefit_usage`, `identity.customer_membership` and 4 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-IDENTITY-ADMINISTRATION-1 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: createPrincipal, getPrincipal, listPlatformStaffGrants, resetPrincipalCredential | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: createPrincipal, getPrincipal, listPlatformStaffGrants, resetPrincipalCredential. Additive to IdentityService; its first-release owner (Hrushikant Patkar) reviews. Done when `identity#createPrincipal`, `identity#getPrincipal`, `identity#listPlatformStaffGrants`, `identity#resetPrincipalCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-TENANCY-MATRIX-1 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalMatrices | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS PLATFORM-KERNEL SVC-TENANCY-APPROVALS-1 SVC-TENANCY-MATRIX-1 SVC-WHITELABEL-PUBLISHING-3 | Operations beyond the first release: listApprovalMatrices. Additive to TenancyService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `approvals#listApprovalMatrices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-DELEGATION-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalDelegations, revokeApprovalDelegation | 2 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listApprovalDelegations, revokeApprovalDelegation. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listApprovalDelegations`, `approvals#revokeApprovalDelegation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | VM-TENANCY-DEVICES-1 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: createDeviceFirmware, getDeviceFirmware, issueDeviceCredential, listDeviceFirmware | 5 | Deep Khanvilkar | TenancyService | MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-TENANCY | Operations: createDeviceFirmware, getDeviceFirmware, issueDeviceCredential, listDeviceFirmware. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#createDeviceFirmware`, `tenancy#getDeviceFirmware`, `tenancy#issueDeviceCredential`, `tenancy#listDeviceFirmware` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | VM-TENANCY-DEVICES-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: revokeDeviceCredential, rollbackDeviceFirmware, setDeviceFirmwareStatus, startDeviceFirmwareRollout | 8 | Pranay Shinde | TenancyService | MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-TENANCY | Operations: revokeDeviceCredential, rollbackDeviceFirmware, setDeviceFirmwareStatus, startDeviceFirmwareRollout. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#revokeDeviceCredential`, `tenancy#rollbackDeviceFirmware`, `tenancy#setDeviceFirmwareStatus`, `tenancy#startDeviceFirmwareRollout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-MATRIX-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalExternalProviders, listStepUpPolicies, setStepUpPolicy | 3 | Narayan Gaonkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listApprovalExternalProviders, listStepUpPolicies, setStepUpPolicy. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listApprovalExternalProviders`, `approvals#listStepUpPolicies`, `approvals#setStepUpPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-IDENTITY-IDENTITY-10 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: getGuestVerificationPolicy, getPasswordPolicy | 2 | Pranay Shinde | IdentityService | MIG-IDENTITY MIG-IDENTITY-2 PLATFORM-KERNEL SVC-IDENTITY-IDENTITY-3 | Operations: getGuestVerificationPolicy, getPasswordPolicy. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#getGuestVerificationPolicy`, `identity#getPasswordPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-REQUEST-5 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalExternalDispatches | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS-5 PLATFORM-KERNEL SVC-TENANCY-REQUEST-2 | Operations: listApprovalExternalDispatches. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listApprovalExternalDispatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-SCOPE-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: getOrgUnit | 1 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-SCOPE-1 | Operations: getOrgUnit. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#getOrgUnit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-TENANCY-6 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: getVenueSettingsDefaults | 2 | Surendra | TenancyService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-TENANCY-1 | Operations: getVenueSettingsDefaults. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#getVenueSettingsDefaults` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PLAN-1 | AM-SETUP-PLATFORM-FOUNDATION-P09 | [BE] PlatformService: createPlan, createPlanVersion | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPlan, createPlanVersion. Spec: handoff/service-docs/backend/PlatformService.md#group-plan Helper task: Narayan Gaonkar owns the service and reviews. Done when `subscription#createPlan`, `subscription#createPlanVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-TENANT-2 | AM-SETUP-PLATFORM-FOUNDATION-P09 | [BE] PlatformService: terminateTenant, updateTenant | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: terminateTenant, updateTenant. Spec: handoff/service-docs/backend/PlatformService.md#group-tenant Helper task: Narayan Gaonkar owns the service and reviews. Done when `subscription#terminateTenant`, `subscription#updateTenant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [DB] Forward migration V1065__control.sql: control for Identity & Security · TICVAI Console 5 of 5 (3 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.billing_entity, control.onboarding_application, control.venue_type_template. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0110__after_r1_20261020.sql (control.onboarding_application: index onboarding_application_requested_plan_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.billing_entity: column billing_currency); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.billing_entity`, `control.onboarding_application`, `control.venue_type_template` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 3 | MIG-CONTROL-9 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [DB] Forward migration V1098__control.sql: control for Subscription & Licensing · Venue Management 1 of 3 (3 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-CONTROL-7 MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.credit_note, control.credit_note_line, control.invoice_line. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.credit_note: foreign key credit_note_invoice_id_fkey, foreign key credit_note_tenant_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.credit_note: column currency_code); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `control.credit_note.invoice_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.credit_note`, `control.credit_note_line`, `control.invoice_line` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-IDENTITY-SSO-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] IdentityService: getSsoConfig, setSsoConfig | 3 | Pranay Shinde | IdentityService | MIG-IDENTITY MIG-IDENTITY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getSsoConfig, setSsoConfig. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#getSsoConfig`, `identity#setSsoConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-BILLING-6 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: generateInvoice, listSubscriptionInvoices | 5 | Surendra | PlatformService | MIG-CONTROL-2 MIG-CONTROL-7 MIG-CONTROL-9 MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: generateInvoice, listSubscriptionInvoices. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#generateInvoice`, `subscription#listSubscriptionInvoices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-6 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: provisionCell | 2 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: provisionCell. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#provisionCell` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-CELL-4 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: getCellHealth, listCellJobs, listCells, listTenantCells | 5 | Narayan Gaonkar | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-KERNEL SVC-PLATFORM-CELL-3 SVC-PLATFORM-CELL-5 SVC-PLATFORM-CELL-6 | Operations: getCellHealth, listCellJobs, listCells, listTenantCells. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getCellHealth`, `subscription#listCellJobs`, `subscription#listCells`, `subscription#listTenantCells` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-TENANT-3 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: getTenant | 2 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-CELL-3 SVC-PLATFORM-CELL-6 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-1 SVC-PLATFORM-TENANT-2 | Operations: getTenant. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getTenant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-LICENSING-3 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: removeLicenceAddOn | 1 | Narayan Gaonkar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeLicenceAddOn. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#removeLicenceAddOn` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-LICENSING-2 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: getEntitlementUsage | 1 | Deep Khanvilkar | PlatformService | MIG-CONTROL MIG-CONTROL-7 PLATFORM-KERNEL SVC-PLATFORM-LICENSING-1 SVC-PLATFORM-LICENSING-3 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-1 SVC-PLATFORM-TENANT-2 | Operations: getEntitlementUsage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getEntitlementUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-METERING-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: getUsageMetering | 1 | Pranay Shinde | PlatformService | MIG-CONTROL-7 MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-2 | Operations: getUsageMetering. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getUsageMetering` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-PLAN-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: getPlan, listPlans | 2 | Narayan Gaonkar | PlatformService | MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-PLAN-1 | Operations: getPlan, listPlans. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getPlan`, `subscription#listPlans` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-19 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: getSubscription, previewSubscriptionChange | 3 | Narayan Gaonkar | PlatformService | MIG-PLATFORM MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-PLAN-1 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-2 | Operations: getSubscription, previewSubscriptionChange. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getSubscription`, `subscription#previewSubscriptionChange` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-ORDERS-7 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] OrderService: listPaymentProviders | 1 | Narayan Gaonkar | OrderService | MIG-PAYMENTS PLATFORM-KERNEL SVC-ORDER-ORDERS-5 | Operations: listPaymentProviders. Spec: contracts (orders) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listPaymentProviders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PUBLICAPI-2 | AM-SETUP-PLATFORM-FOUNDATION-P14 | [BE] PlatformService: registerDeveloper, rotateApiCredential, setApiClientStatus, setApiLicensing | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: registerDeveloper, rotateApiCredential, setApiClientStatus, setApiLicensing. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi Helper task: Narayan Gaonkar owns the service and reviews. Done when `public-api#registerDeveloper`, `public-api#rotateApiCredential`, `public-api#setApiClientStatus`, `public-api#setApiLicensing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PUBLICAPI-3 | AM-SETUP-PLATFORM-FOUNDATION-P14 | [BE] PlatformService: setDeveloperMembers | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeveloperMembers. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi Helper task: Narayan Gaonkar owns the service and reviews. Done when `public-api#setDeveloperMembers` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-PLATFORM-PUBLICAPI-1 | AM-SETUP-PLATFORM-FOUNDATION-P14 | [BE] PlatformService: certifyIntegration, createApiClient, decideProductionAccess, deprecateApiVersion | 8 | Narayan Gaonkar | PlatformService | MIG-CONTROL MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: certifyIntegration, createApiClient, decideProductionAccess, deprecateApiVersion. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi. Done when `public-api#certifyIntegration`, `public-api#createApiClient`, `public-api#decideProductionAccess`, `public-api#deprecateApiVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-PLATFORM-PUBLICAPI-7 | AM-PUBLIC-API-P14-BLOCK-A | [BE] PlatformService: listApiScopes, listApiVersions | 2 | Pranay Shinde | PlatformService | MIG-CONTROL PLATFORM-KERNEL SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-PUBLICAPI-2 | Operations: listApiScopes, listApiVersions. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Developer Portal (Block A); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#listApiScopes`, `public-api#listApiVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-13 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [DB] Forward migration V1181__control.sql: control for Platform Foundation · Developer Portal (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.api_anomaly_rule, control.api_limit. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.api_limit: foreign key api_limit_client_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.api_anomaly_rule`, `control.api_limit` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-PLATFORM-PUBLICAPI-1 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: createWebhookSubscription, listApiClients, listWebhookDeliveries, listWebhookSubscriptions | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations beyond the first release: createWebhookSubscription, listApiClients, listWebhookDeliveries, listWebhookSubscriptions. Additive to PlatformService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `public-api#createWebhookSubscription`, `public-api#listApiClients`, `public-api#listWebhookDeliveries`, `public-api#listWebhookSubscriptions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-10 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: listDeveloperMembers, listIntegrationListings, listProductionAccessRequests, requestProductionAccess | 5 | Surendra | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDeveloperMembers, listIntegrationListings, listProductionAccessRequests, requestProductionAccess. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Platform Foundation · Developer Portal (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#listDeveloperMembers`, `public-api#listIntegrationListings`, `public-api#listProductionAccessRequests`, `public-api#requestProductionAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-11 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: revokeApiCredential, setApiAnomalyRule, setApiQuota | 5 | Narayan Gaonkar | PlatformService | MIG-CONTROL MIG-CONTROL-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: revokeApiCredential, setApiAnomalyRule, setApiQuota. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Platform Foundation · Developer Portal (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#revokeApiCredential`, `public-api#setApiAnomalyRule`, `public-api#setApiQuota` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-GENERAL-1 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: getDeveloperAccount, listApiAnomalyRules, listApiLicences, listApiQuotas | 3 | Narayan Gaonkar | PlatformService | MIG-CONTROL MIG-CONTROL-13 PLATFORM-KERNEL SVC-PLATFORM-PUBLICAPI-11 SVC-PLATFORM-PUBLICAPI-12 SVC-PLATFORM-PUBLICAPI-2 SVC-PLATFORM-PUBLICAPI-3 | Operations: getDeveloperAccount, listApiAnomalyRules, listApiLicences, listApiQuotas. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Platform Foundation · Developer Portal (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#getDeveloperAccount`, `public-api#listApiAnomalyRules`, `public-api#listApiLicences`, `public-api#listApiQuotas` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 1 | MIG-CATALOGUE-11 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [DB] Forward migration V1126__catalogue.sql: catalogue for the first release (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE | Tables: catalogue.channel_connection, catalogue.channel_sales_rule. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze), pushed before the first release needed it and kept under its pushed key (CHG-R6G-001); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.channel_connection: foreign key channel_connection_sales_channel_id_fkey; catalogue.channel_sales_rule: foreign key channel_sales_rule_sales_channel_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.channel_connection`, `catalogue.channel_sales_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 1 | MIG-PRICING-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [DB] Forward migration V1112__pricing.sql: pricing for the first release (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE | Tables: pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule. Source DDL: backend/tenant/010-pricing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze), pushed before the first release needed it and kept under its pushed key (CHG-R6G-001); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (pricing.dynamic_price_action: row-level security apply_parent_rls; pricing.dynamic_price_condition: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: pricing.dynamic_price_action: foreign key dynamic_price_action_dynamic_price_rule_id_fkey; pricing.dynamic_price_condition: foreign key dynamic_price_condition_dynamic_price_rule_id_fkey; pricing.dynamic_price_rule: foreign key dynamic_price_action_dynamic_price_rule_id_fkey (from pricing.dynamic_price_action), foreign key dynamic_price_condition_dynamic_price_rule_id_fkey (from pricing.dynamic_price_condition)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `pricing.dynamic_price_action`, `pricing.dynamic_price_condition`, `pricing.dynamic_price_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 1 | SETUP-SEED | AM-FOUNDATION-SETUP | [DevOps] Seed data: the reference fixture (two brands, three regions, AED and OMR) every test runs against | 5 | Pranay Shinde |  | MIG-ACCESS MIG-ACCESS-2 MIG-AI MIG-APPROVALS MIG-ASSETS MIG-BASELINE MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CONTROL MIG-FNB MIG-FOREIGN-KEYS MIG-GAMES MIG-IDENTITY MIG-INVENTORY MIG-KERNEL MIG-LEDGER MIG-MAINTENANCE MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM MIG-PRICING-2 MIG-PROMOTIONS MIG-QUEUE MIG-REPORTING MIG-RESOURCES MIG-RETAIL MIG-SEATING MIG-SUBSCRIPTION MIG-SYNC MIG-TENANCY MIG-TRANSPORT MIG-VENUEMAP MIG-WALLET MIG-WHITELABEL MIG-WORKFORCE VM-MIG-APPROVALS VM-MIG-QUEUE | Seed data: the reference fixture (two brands, three regions, AED and OMR) every test runs against. In **ticvai-backend** `db/seed`: the reference fixture quality-gates 8 requires - two brands, three regions across two countries, AED and OMR - with products, prices, events, tills, staff, roles and denominations, so apps can be built before the Back Office setup screens exist. The denominations and roles seed from docs/active/seed-data-proposal.md (proposed, client to correct - audit R229). The frontend mock API is SETUP-MOCK-API's (since 21 October 2026): it mirrors this fixture's reference data beside the prototypes' sample venues. Done when: it loads on a migrated database and integration tests run against it.
11 | 1 | SVC-CATALOGUE-CATEGORY-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createSeatCategory, updateSeatCategory | 5 | Chinmay Patkar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatCategory, updateSeatCategory. Spec: handoff/service-docs/backend/CatalogueService.md#group-category Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#createSeatCategory`, `seating#updateSeatCategory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-DRAFTED-24 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setBookingVelocityTime, setDemandOccupancyAvailability, setDynamicPricingStrategy | 8 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBookingVelocityTime, setDemandOccupancyAvailability, setDynamicPricingStrategy. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted. Done when `catalogue#setBookingVelocityTime`, `catalogue#setDemandOccupancyAvailability`, `catalogue#setDynamicPricingStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-DRAFTED-33 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: publishChannelReadinessValidation, setChannelFeePayment | 3 | Surendra | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishChannelReadinessValidation, setChannelFeePayment. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#publishChannelReadinessValidation`, `catalogue#setChannelFeePayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-DRAFTED-45 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setProductServicePrice | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setProductServicePrice. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#setProductServicePrice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENT-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createEvent, createPerformances, enterWaitingRoom, getPerformance | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createEvent, createPerformances, enterWaitingRoom, getPerformance. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createEvent`, `catalogue#createPerformances`, `catalogue#enterWaitingRoom`, `catalogue#getPerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENT-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: updatePerformance | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updatePerformance. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#updatePerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENTS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: cloneEvent, setEventLifecycleState | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cloneEvent, setEventLifecycleState. Spec: handoff/service-docs/backend/CatalogueService.md#group-events Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#cloneEvent`, `catalogue#setEventLifecycleState` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-PRICING-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: copyPriceList, createPriceList, setPrices, updatePriceList | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: copyPriceList, createPriceList, setPrices, updatePriceList. Spec: handoff/service-docs/backend/CatalogueService.md#group-pricing. Done when `catalogue#copyPriceList`, `catalogue#createPriceList`, `catalogue#setPrices`, `catalogue#updatePriceList` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-SEATING-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setAccessibleSeating, setSeatRecommendationRules | 3 | Sanket Keluskar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessibleSeating, setSeatRecommendationRules. Spec: handoff/service-docs/backend/CatalogueService.md#group-seating Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#setAccessibleSeating`, `seating#setSeatRecommendationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-SEATMAP-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: editSeatMapStructure | 3 | Sanket Keluskar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: editSeatMapStructure. Spec: handoff/service-docs/backend/CatalogueService.md#group-seatmap Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#editSeatMapStructure` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-DRAFTED-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setCodeDistributionManager | 2 | Pranay Shinde | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCodeDistributionManager. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#setCodeDistributionManager` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-PROMOTION-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: analysePromotionConflicts, createPromotion, getPromotion, getPromotionUsage | 5 | Narayan Gaonkar | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: analysePromotionConflicts, createPromotion, getPromotion, getPromotionUsage. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion. Done when `promotions#analysePromotionConflicts`, `promotions#createPromotion`, `promotions#getPromotion`, `promotions#getPromotionUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-PROMOTION-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: listPromotions, publishPromotion, updatePromotion | 8 | Deep Khanvilkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPromotions, publishPromotion, updatePromotion. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion. Done when `promotions#listPromotions`, `promotions#publishPromotion`, `promotions#updatePromotion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-PROMOTIONS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setPromotionVariants | 2 | Chinmay Patkar | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPromotionVariants. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotions Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#setPromotionVariants` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDERS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] OrderService: getGroupBooking, getPaymentLink, importTicketTemplate, issueWalletPass | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGroupBooking, getPaymentLink, importTicketTemplate, issueWalletPass. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#getGroupBooking`, `orders#getPaymentLink`, `orders#importTicketTemplate`, `orders#issueWalletPass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-ORDERS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] OrderService: cloneTicketTemplate, createResaleListing, createTicketTemplate, getBillingStatement | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cloneTicketTemplate, createResaleListing, createTicketTemplate, getBillingStatement. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#cloneTicketTemplate`, `orders#createResaleListing`, `orders#createTicketTemplate`, `orders#getBillingStatement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] WalletService: setWalletFundingRules, setWalletRefundPolicy, topUpWallet | 8 | Pranay Shinde | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setWalletFundingRules, setWalletRefundPolicy, topUpWallet. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#setWalletFundingRules`, `wallet#setWalletRefundPolicy`, `wallet#topUpWallet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-BUNDLE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createBundle, getBundle, getLatestBundle, listCatalogueBundles | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-FNB MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBundle, getBundle, getLatestBundle, listCatalogueBundles. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createBundle`, `promotions#getBundle`, `catalogue#getLatestBundle`, `catalogue#listCatalogueBundles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-DEPARTURE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: getNextTransportDeparture, searchTransportDepartures, updateTransportDeparture | 5 | Sanket Keluskar | VenueOpsService | MIG-CATALOGUE MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getNextTransportDeparture, searchTransportDepartures, updateTransportDeparture. Spec: handoff/service-docs/backend/VenueOpsService.md#group-departure Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#getNextTransportDeparture`, `transport#searchTransportDepartures`, `transport#updateTransportDeparture` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-FARE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: getTransportFareTable, quoteTransportFare, setTransportFareTable | 8 | Narayan Gaonkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getTransportFareTable, quoteTransportFare, setTransportFareTable. Spec: handoff/service-docs/backend/VenueOpsService.md#group-fare. Done when `transport#getTransportFareTable`, `transport#quoteTransportFare`, `transport#setTransportFareTable` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-NETWORKIMPORT-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: applyTransportNetworkImport, importTransportNetwork | 5 | Narayan Gaonkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyTransportNetworkImport, importTransportNetwork. Spec: handoff/service-docs/backend/VenueOpsService.md#group-networkimport Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#applyTransportNetworkImport`, `transport#importTransportNetwork` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-PASS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportPassType, listTransportPassOffers, updateTransportPassType | 5 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportPassType, listTransportPassOffers, updateTransportPassType. Spec: handoff/service-docs/backend/VenueOpsService.md#group-pass Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#createTransportPassType`, `transport#listTransportPassOffers`, `transport#updateTransportPassType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ROUTE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: setTransportRouteStatus, updateTransportRoute | 5 | Chinmay Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTransportRouteStatus, updateTransportRoute. Spec: handoff/service-docs/backend/VenueOpsService.md#group-route Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#setTransportRouteStatus`, `transport#updateTransportRoute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-STATION-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportStation, listTransportStations, updateTransportStation | 5 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportStation, listTransportStations, updateTransportStation. Spec: handoff/service-docs/backend/VenueOpsService.md#group-station Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#createTransportStation`, `transport#listTransportStations`, `transport#updateTransportStation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-TIMETABLE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportTimetable, publishTransportTimetable, withdrawTransportTimetable | 5 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportTimetable, publishTransportTimetable, withdrawTransportTimetable. Spec: handoff/service-docs/backend/VenueOpsService.md#group-timetable Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#createTransportTimetable`, `transport#publishTransportTimetable`, `transport#withdrawTransportTimetable` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VENUEMAP-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createVenueMap, getVenueMap, getVenueMapGraph, importVenueGeometry | 8 | Narayan Gaonkar | VenueOpsService | MIG-ASSETS MIG-PLATFORM MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVenueMap, getVenueMap, getVenueMapGraph, importVenueGeometry. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap. Done when `venue-map#createVenueMap`, `venue-map#getVenueMap`, `venue-map#getVenueMapGraph`, `venue-map#importVenueGeometry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VENUEMAP-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: listBookableVenueMaps, publishVenueMap, setPlacedResource, setVenueMapArtwork | 8 | Narayan Gaonkar | VenueOpsService | MIG-ASSETS MIG-PLATFORM MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBookableVenueMaps, publishVenueMap, setPlacedResource, setVenueMapArtwork. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap. Done when `venue-map#listBookableVenueMaps`, `venue-map#publishVenueMap`, `venue-map#setPlacedResource`, `venue-map#setVenueMapArtwork` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VENUEMAP-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: setVenuePoint | 3 | Sanket Keluskar | VenueOpsService | MIG-ACCESS MIG-ASSETS MIG-CATALOGUE MIG-PLATFORM MIG-PROMOTIONS MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setVenuePoint. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap Helper task: Narayan Gaonkar owns the service and reviews. Done when `venue-map#setVenuePoint` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-ROUTE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportRoute, getTransportRoute, getTransportRouteMap, listTransportRoutes | 8 | Narayan Gaonkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportRoute, getTransportRoute, getTransportRouteMap, listTransportRoutes. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `transport#createTransportRoute`, `transport#getTransportRoute`, `transport#getTransportRouteMap`, `transport#listTransportRoutes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 2 | VM-MIG-CATALOGUE | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1088__catalogue.sql: catalogue for Venue Management (3 tables) | 2 | Hrushikant Patkar |  | MIG-CATALOGUE | Tables: catalogue.bundle_application, catalogue.donation_campaign, catalogue.performance_template. Source DDL: backend/tenant/010-catalogue.sql and backend/tenant/V0108__after_r1_20261020.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.donation_campaign: column fixed_amounts; catalogue.performance_template: column bands); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0110__after_r1_20261020.sql (catalogue.bundle_application: indexes bundle_application_venue_id_idx and bundle_application_workstation_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0111__names_after_r1_20261020.sql (the names the contracts use: catalogue.bundle_application: foreign key bundle_application_venue_id_fkey, foreign key bundle_application_venue_id_workstation_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.bundle_application`, `catalogue.donation_campaign`, `catalogue.performance_template` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 2 | VM-MIG-PROMOTIONS | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1017__promotions.sql: promotions for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-PROMOTIONS | Tables: promotions.upsell_rule, promotions.voucher. Source DDL: backend/tenant/010-promotions.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (promotions.upsell_rule: column scope_path, index upsell_rule_scope_path_idx, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **promotions.voucher's row-level security waits for its parent**: its policy reads promotions.voucher_batch, which MIG-PROMOTIONS-2 creates later, so leave out its `platform.apply_parent_rls` call here; MIG-PROMOTIONS-2 applies it. **Leave out the key voucher_batch_id_fkey** (promotions.voucher to promotions.voucher_batch): MIG-PROMOTIONS-2 creates promotions.voucher_batch later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `promotions.upsell_rule.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.upsell_rule`, `promotions.voucher` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 2 | VM-CATALOGUE-UPSELL-1 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] CatalogueService: createUpsellRule, deleteUpsellRule, listUpsellRules | 3 | Sanket Keluskar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations beyond the first release: createUpsellRule, deleteUpsellRule, listUpsellRules. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#createUpsellRule`, `promotions#deleteUpsellRule`, `promotions#listUpsellRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-MIG-ACCESS | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1019__access.sql: access for Venue Management (10 tables) | 5 | Hrushikant Patkar |  | MIG-ACCESS | Tables: access.access_change, access.accreditation_credential, access.credential_binding, access.credential_event, access.dynamic_policy, access.dynamic_policy_version, access.media_replacement_policy, access.media_template, access.media_type, access.policy_scope_assignment. Source DDL: backend/tenant/010-access.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: access.access_change: rename column old_access_id to old_entitlement_id); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (access.access_change: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (access.policy_scope_assignment: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.access_change: rename column new_access_id to new_entitlement_id, rename index access_change_new_access_id_idx to access_change_new_entitlement_id_idx, rename index access_change_old_access_id_idx to access_change_old_entitlement_id_idx, foreign key access_change_new_entitlement_id_fkey, foreign key access_change_old_entitlement_id_fkey; access.accreditation_credential: foreign key accreditation_credential_holder_id_fkey; access.credential_binding: foreign key credential_binding_entitlement_id_fkey, foreign key credential_binding_media_type_id_fkey; access.credential_event: foreign key credential_event_entitlement_id_fkey; access.dynamic_policy: foreign key dynamic_policy_version_dynamic_policy_id_fkey (from access.dynamic_policy_version), foreign key policy_scope_assignment_dynamic_policy_id_fkey (from access.policy_scope_assignment); access.dynamic_policy_version: foreign key dynamic_policy_version_dynamic_policy_id_fkey; access.media_replacement_policy: rename column supervisor_approval to requires_supervisor_approval, rename column identity_verification to requires_identity_verification, rename column reason_mandatory to requires_reason; access.media_template: foreign key media_template_version_media_template_id_fkey (from access.media_template_version), drop index media_template_product_id_idx; access.media_type: rename column temporary_media to is_temporary_media, rename column one_time_use to is_one_time_use, rename column automatic_expiration to has_automatic_expiration, foreign key credential_binding_media_type_id_fkey (from access.credential_binding), foreign key credential_issuance_media_type_id_fkey (from access.credential_issuance), foreign key media_compatibility_test_media_type_id_fkey (from access.media_compatibility_test); access.policy_scope_assignment: foreign key policy_scope_assignment_dynamic_policy_id_fkey, foreign key policy_scope_assignment_scope_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Leave out the key accreditation_credential_holder_id_fkey** (access.accreditation_credential to accreditation.holder): VM-MIG-ACCREDITATION creates accreditation.holder later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.access_change`, `access.accreditation_credential`, `access.credential_binding`, `access.credential_event`, `access.dynamic_policy`, `access.dynamic_policy_version`, `access.media_replacement_policy`, `access.media_template` and 2 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 2 | VM-MIG-FNB | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1033__fnb.sql: fnb for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-FNB | Tables: fnb.kitchen_routing_rule, fnb.waste_approval_policy. Source DDL: backend/tenant/010-fnb.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: fnb.kitchen_routing_rule: foreign key kitchen_routing_rule_default_station_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.kitchen_routing_rule`, `fnb.waste_approval_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
4 | 3 | MIG-SUBSCRIPTION-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1084__subscription.sql: subscription for Subscription & Licensing · Venue Management 1 of 3 (8 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE | Tables: subscription.membership_eligibility_rule, subscription.membership_entitlement, subscription.membership_household_policy, subscription.membership_household_policy_role_limit, subscription.membership_product, subscription.membership_product_history, subscription.membership_renewal_policy, subscription.membership_usage_policy. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: subscription.membership_eligibility_rule: foreign key membership_eligibility_rule_membership_product_id_fkey; subscription.membership_entitlement: foreign key membership_entitlement_membership_product_id_fkey, drop index membership_entitlement_pricing_rule_id_idx; subscription.membership_household_policy: rename column eligibility_revalidation to requires_eligibility_revalidation, foreign key membership_household_policy_membership_product_id_fkey; subscription.membership_product: rename column promotional_pricing_eligibility to is_eligible_for_promotional_pricing, rename column separate_purchase_and_activation_rules to has_separate_purchase_and_activation_rules, foreign key membership_eligibility_rule_membership_product_id_fkey (from subscription.membership_eligibility_rule), foreign key membership_entitlement_membership_product_id_fkey (from subscription.membership_entitlement), foreign key membership_household_policy_membership_product_id_fkey (from subscription.membership_household_policy), foreign key membership_product_history_membership_product_id_fkey (from subscription.membership_product_history), foreign key membership_renewal_policy_membership_product_id_fkey (from subscription.membership_renewal_policy), foreign key membership_usage_policy_membership_product_id_fkey (from subscription.membership_usage_policy); subscription.membership_product_history: foreign key membership_product_history_changed_by_principal_id_fkey, foreign key membership_product_history_membership_product_id_fkey; subscription.membership_renewal_policy: foreign key membership_renewal_policy_membership_product_id_fkey; subscription.membership_usage_policy: foreign key membership_usage_policy_membership_product_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: subscription.membership_renewal_policy: drop index membership_renewal_policy_cancellation_policy_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `subscription.membership_eligibility_rule`, `subscription.membership_entitlement`, `subscription.membership_household_policy`, `subscription.membership_household_policy_role_limit`, `subscription.membership_product`, `subscription.membership_product_history`, `subscription.membership_renewal_policy`, `subscription.membership_usage_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-CONTROL-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1072__control.sql: control for Identity & Security · Partner Portal (6 tables) | 5 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.channel_listing, control.partner_allocation, control.partner_booking_limit, control.partner_commercial_exception, control.partner_status_history, control.partner_user. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.partner_allocation: foreign key partner_allocation_agreement_id_fkey, foreign key partner_allocation_partner_id_fkey, drop index partner_allocation_product_id_idx; control.partner_commercial_exception: foreign key partner_commercial_exception_partner_id_fkey; control.partner_status_history: foreign key partner_status_history_partner_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.channel_listing`, `control.partner_allocation`, `control.partner_booking_limit`, `control.partner_commercial_exception`, `control.partner_status_history`, `control.partner_user` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 3 | MIG-AI-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1010__ai.sql: ai for Identity & Security · TICVAI Console 3 of 5 (5 tables) | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.action_step, ai.blueprint, ai.blueprint_decision, ai.config_session, ai.config_source. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ai.config_source: column scope_path, index config_source_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `ai.config_source.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.action_step`, `ai.blueprint`, `ai.blueprint_decision`, `ai.config_session`, `ai.config_source` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 3 | MIG-AI-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1011__ai.sql: ai for Identity & Security · TICVAI Console 3 of 5 (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.tool. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ai.tool: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ai.tool: rename column validate_only to is_validation_only); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.tool` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 3 | MIG-SEATING-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1111__seating.sql: seating for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (2 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-SEATING | Tables: seating.seating_rules, seating.section_row. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: seating.seating_rules: rename column prevent_orphan_seats to prevents_orphan_seats); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `seating.seating_rules`, `seating.section_row` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-10 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1237__catalogue.sql: catalogue for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.demand_signal, catalogue.signal_registry. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.signal_registry: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.demand_signal`, `catalogue.signal_registry` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-12 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1238__catalogue.sql: catalogue for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.channel_incident, catalogue.channel_sync. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.channel_incident: column resolution_note); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.channel_incident: foreign key channel_incident_sales_channel_id_fkey; catalogue.channel_sync: foreign key channel_sync_sales_channel_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.channel_incident`, `catalogue.channel_sync` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1091__catalogue.sql: catalogue for Subscription & Licensing · Venue Management 1 of 3 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.membership_programme, catalogue.plan_benefit. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.membership_programme: column scope_path, index membership_programme_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.plan_benefit: foreign key plan_benefit_entitlement_template_id_fkey, foreign key plan_benefit_membership_benefit_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Leave out the key plan_benefit_membership_benefit_id_fkey** (catalogue.plan_benefit to catalogue.membership_benefit): MIG-CATALOGUE-5 creates catalogue.membership_benefit later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `catalogue.membership_programme.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.membership_programme`, `catalogue.plan_benefit` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1239__catalogue.sql: catalogue for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.package_pricing, catalogue.rollback_action, catalogue.variant_dimension. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.variant_dimension: column values); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.package_pricing: foreign key package_pricing_product_id_fkey; catalogue.rollback_action: foreign key rollback_action_requested_by_principal_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `catalogue.variant_dimension.values`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.package_pricing`, `catalogue.rollback_action`, `catalogue.variant_dimension` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1118__catalogue.sql: catalogue for Identity & Security · TICVAI Console 3 of 5 (5 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.event_change_treatment_policy, catalogue.membership_benefit, catalogue.seat_pricing_rule, catalogue.tax_profile, catalogue.waiting_room_setting. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.membership_benefit: column scope_path, index membership_benefit_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.membership_benefit: foreign key plan_benefit_membership_benefit_id_fkey (from catalogue.plan_benefit), foreign key benefit_usage_membership_benefit_id_fkey (from identity.benefit_usage); catalogue.seat_pricing_rule: foreign key seat_pricing_rule_seat_map_id_fkey; catalogue.tax_profile: foreign key tax_profile_tax_code_id_fkey; catalogue.waiting_room_setting: foreign key waiting_room_setting_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also apply identity.benefit_usage's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through catalogue.membership_benefit): MIG-IDENTITY-3 creates identity.benefit_usage before catalogue.membership_benefit exists. **Also add the key benefit_usage_membership_benefit_id_fkey here** (identity.benefit_usage to catalogue.membership_benefit, guarded): MIG-IDENTITY-3 creates identity.benefit_usage before catalogue.membership_benefit exists. **Also add the key plan_benefit_membership_benefit_id_fkey here** (catalogue.plan_benefit to catalogue.membership_benefit, guarded): MIG-CATALOGUE-2 creates catalogue.plan_benefit before catalogue.membership_benefit exists. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `catalogue.membership_benefit.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.event_change_treatment_policy`, `catalogue.membership_benefit`, `catalogue.seat_pricing_rule`, `catalogue.tax_profile`, `catalogue.waiting_room_setting` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1119__catalogue.sql: catalogue for Identity & Security · TICVAI Console 3 of 5 (6 tables) | 5 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.calculation_profile, catalogue.calculation_step, catalogue.fee_rule, catalogue.pricing_experiment, catalogue.rounding_profile, catalogue.tax_rule. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.rounding_profile: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.pricing_experiment: rename column statistical_significance to is_statistically_significant); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.calculation_profile`, `catalogue.calculation_step`, `catalogue.fee_rule`, `catalogue.pricing_experiment`, `catalogue.rounding_profile`, `catalogue.tax_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-7 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1120__catalogue.sql: catalogue for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (10 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.ai_catalogue_session, catalogue.ai_finding, catalogue.change_request, catalogue.change_request_line, catalogue.configuration_template, catalogue.lifecycle_action, catalogue.lifecycle_workflow, catalogue.price_list_version, catalogue.pricing_publication, catalogue.product_link. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.change_request: foreign key change_request_requested_by_principal_id_fkey, foreign key pricing_publication_change_request_id_fkey (from catalogue.pricing_publication); catalogue.lifecycle_action: rename column pre_action_validation to requires_pre_action_validation, foreign key lifecycle_action_product_id_fkey; catalogue.price_list_version: foreign key price_list_version_price_list_id_fkey; catalogue.pricing_publication: foreign key pricing_publication_change_request_id_fkey; catalogue.product_link: foreign key product_link_source_product_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.ai_catalogue_session`, `catalogue.ai_finding`, `catalogue.change_request`, `catalogue.change_request_line`, `catalogue.configuration_template`, `catalogue.lifecycle_action`, `catalogue.lifecycle_workflow`, `catalogue.price_list_version` and 2 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 3 | MIG-PROMOTIONS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1114__promotions.sql: promotions for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (4 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PLATFORM MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.campaign, promotions.campaign_budget, promotions.stacking_rule, promotions.voucher_batch. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (promotions.campaign: index campaign_venue_id_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: promotions.campaign: foreign key campaign_venue_id_fkey, foreign key coupon_code_batch_campaign_id_fkey (from promotions.coupon_code_batch); promotions.stacking_rule: foreign key stacking_rule_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also apply promotions.coupon_code_batch's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through promotions.campaign): MIG-PROMOTIONS creates promotions.coupon_code_batch before promotions.campaign exists. **Also apply promotions.voucher's row-level security here** (its `platform.apply_parent_rls` call, 920-row-level-security.sql, through promotions.voucher_batch): VM-MIG-PROMOTIONS creates promotions.voucher before promotions.voucher_batch exists. **Also add the key coupon_code_batch_campaign_id_fkey here** (promotions.coupon_code_batch to promotions.campaign, guarded): MIG-PROMOTIONS creates promotions.coupon_code_batch before promotions.campaign exists. **Also add the key voucher_batch_id_fkey here** (promotions.voucher to promotions.voucher_batch, guarded): VM-MIG-PROMOTIONS creates promotions.voucher before promotions.voucher_batch exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.campaign`, `promotions.campaign_budget`, `promotions.stacking_rule`, `promotions.voucher_batch` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-ACCESS-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1115__access.sql: access for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.companion_rule. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.companion_rule: foreign key companion_rule_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.companion_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-FNB-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1117__fnb.sql: fnb for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.combo, fnb.combo_slot, fnb.combo_slot_option. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (fnb.combo: column scope_path, index combo_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.combo_slot: column scope_path, index combo_slot_scope_path_idx, row-level security apply_grant_holder_read_rls; fnb.combo_slot_option: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: fnb.combo_slot_option: foreign key combo_slot_option_menu_item_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `fnb.combo.scope_path`; not null `fnb.combo_slot.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.combo`, `fnb.combo_slot`, `fnb.combo_slot_option` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-20 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] PlatformService: listChannelListings, setChannelListing | 3 | Pranay Shinde | PlatformService | MIG-CATALOGUE MIG-CONTROL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listChannelListings, setChannelListing. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listChannelListings`, `subscription#setChannelListing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-21 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] PlatformService: setMembershipCommercialConfig | 2 | Chinmay Patkar | PlatformService | MIG-CATALOGUE MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMembershipCommercialConfig. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setMembershipCommercialConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-PLATFORM-DRAFTED-16 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] PlatformService: listMembershipCommercialPricing, listMembershipFreezeSuspension, setMembershipEntitlementAdmission | 5 | Deep Khanvilkar | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listMembershipCommercialPricing, listMembershipFreezeSuspension, setMembershipEntitlementAdmission. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listMembershipCommercialPricing`, `subscription#listMembershipFreezeSuspension`, `subscription#setMembershipEntitlementAdmission` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CAPACITY-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createChannelCapacity, getChannelAllocations, listChannelCapacities, relinquishChannelAllocation | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: createChannelCapacity, getChannelAllocations, listChannelCapacities, relinquishChannelAllocation. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createChannelCapacity`, `catalogue#getChannelAllocations`, `catalogue#listChannelCapacities`, `catalogue#relinquishChannelAllocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CAPACITY-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setChannelAllocations, updateChannelCapacity | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setChannelAllocations, updateChannelCapacity. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#setChannelAllocations`, `catalogue#updateChannelCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CATALOGUE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createDonationCampaign, listDonationCampaigns, listWaitlistEntries, offerWaitlistCapacity | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: createDonationCampaign, listDonationCampaigns, listWaitlistEntries, offerWaitlistCapacity. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createDonationCampaign`, `catalogue#listDonationCampaigns`, `catalogue#listWaitlistEntries`, `catalogue#offerWaitlistCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-CATALOGUE-PRODUCT-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: transitionProductLifecycle | 3 | Narayan Gaonkar | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: transitionProductLifecycle. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#transitionProductLifecycle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-ACCESS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] AccessService: listCredentialReplacementReissue, replaceCredential, setPdfPrintablePos | 5 | Sanket Keluskar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations beyond the first release: listCredentialReplacementReissue, replaceCredential, setPdfPrintablePos. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredentialReplacementReissue`, `access#replaceCredential`, `access#setPdfPrintablePos` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-CATALOGUE-DRAFTED-50 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getChannelAvailability | 1 | Narayan Gaonkar | CatalogueService | MIG-BASELINE PLATFORM-KERNEL | Operations: getChannelAvailability. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getChannelAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-DRAFTED-25 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createChannelProfile, createLiveDynamicPrice, decidePricingRecommendation, listAutomationPolicyAutonomous | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createChannelProfile, createLiveDynamicPrice, decidePricingRecommendation, listAutomationPolicyAutonomous. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#createChannelProfile`, `catalogue#createLiveDynamicPrice`, `catalogue#decidePricingRecommendation`, `catalogue#listAutomationPolicyAutonomous` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-CATALOGUE-PRICING-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listPrices | 1 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-DRAFTED-25 | Operations beyond the first release: listPrices. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#listPrices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATMAP-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createSeatMap, getSeatMap, updateSeatMap | 8 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatMap, getSeatMap, updateSeatMap. Spec: contracts (seating) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#createSeatMap`, `seating#getSeatMap`, `seating#updateSeatMap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-11 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: cancelPricingRollback, setCurrencyRoundingRule, setFeeDefinition, setPriceCalculationPolicy | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cancelPricingRollback, setCurrencyRoundingRule, setFeeDefinition, setPriceCalculationPolicy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#cancelPricingRollback`, `catalogue#setCurrencyRoundingRule`, `catalogue#setFeeDefinition`, `catalogue#setPriceCalculationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-12 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setDemandSignalConfiguration, setDynamicPricingGuardrailPolicy, setPriceLadderMatrix, transitionDynamicPricingStrategy | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-PLATFORM MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setDemandSignalConfiguration, setDynamicPricingGuardrailPolicy, setPriceLadderMatrix, transitionDynamicPricingStrategy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setDemandSignalConfiguration`, `catalogue#setDynamicPricingGuardrailPolicy`, `catalogue#setPriceLadderMatrix`, `catalogue#transitionDynamicPricingStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-14 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: retryChannelIncident, setChannelConnectionConfiguration, setChannelSalesRule, setChannelSyncSetting | 8 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: retryChannelIncident, setChannelConnectionConfiguration, setChannelSalesRule, setChannelSyncSetting. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#retryChannelIncident`, `catalogue#setChannelConnectionConfiguration`, `catalogue#setChannelSalesRule`, `catalogue#setChannelSyncSetting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-15 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: testChannelConnection, updateChannelIncident | 3 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: testChannelConnection, updateChannelIncident. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#testChannelConnection`, `catalogue#updateChannelIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: importProductCatalogue, listDynamicPriceRules, listProductVersions, restoreProductVersion | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: importProductCatalogue, listDynamicPriceRules, listProductVersions, restoreProductVersion. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#importProductCatalogue`, `catalogue#listDynamicPriceRules`, `catalogue#listProductVersions`, `catalogue#restoreProductVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setDynamicPriceRule, setPackagePricingDefinition | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDynamicPriceRule, setPackagePricingDefinition. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setDynamicPriceRule`, `catalogue#setPackagePricingDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATEGORY-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listSeatCategories | 1 | Narayan Gaonkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 | Operations: listSeatCategories. Spec: contracts (seating) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#listSeatCategories` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-COUPON-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: assignCoupon, listCouponCampaigns, listCouponCodes, voidCouponCode | 8 | Pranay Shinde | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignCoupon, listCouponCampaigns, listCouponCodes, voidCouponCode. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#assignCoupon`, `promotions#listCouponCampaigns`, `promotions#listCouponCodes`, `promotions#voidCouponCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-COUPON-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createCouponCampaign, generateCouponCodes, getCouponCode | 8 | Narayan Gaonkar | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCouponCampaign, generateCouponCodes, getCouponCode. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createCouponCampaign`, `promotions#generateCouponCodes`, `promotions#getCouponCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-ENTITLEMENT-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listEntitlementTemplates | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-ENTITLEMENT-1 | Operations: listEntitlementTemplates. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listEntitlementTemplates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-PRODUCT-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createProduct, setProductAttributes | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createProduct, setProductAttributes. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#createProduct`, `catalogue#setProductAttributes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-SEATING-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getAccessibleSeating, getSeatRecommendationRules | 2 | Deep Khanvilkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-SEATING-1 | Operations: getAccessibleSeating, getSeatRecommendationRules. Spec: contracts (seating) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getAccessibleSeating`, `seating#getSeatRecommendationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WALLET-WALLET-11 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] WalletService: getWalletTransferRules | 1 | Pranay Shinde | WalletService | MIG-WALLET PLATFORM-KERNEL SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-7 | Operations: getWalletTransferRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#getWalletTransferRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WALLET-WALLET-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] WalletService: listCreditTypes | 1 | Narayan Gaonkar | WalletService | MIG-WALLET PLATFORM-KERNEL SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-7 | Operations: listCreditTypes. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#listCreditTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-GENERAL-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getPackagePricingDefinition, getProductAttributes | 2 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE-4 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-PRODUCT-5 | Operations: getPackagePricingDefinition, getProductAttributes. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getPackagePricingDefinition`, `catalogue#getProductAttributes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-PROMOTIONS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: simulatePromotion, voidVoucher | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations: simulatePromotion, voidVoucher. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#simulatePromotion`, `promotions#voidVoucher` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-CATALOGUE-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: assessProductChange, bulkUpdateCatalogueProducts, getCatalogueImportJob, getDynamicPriceRule | 8 | Pranay Shinde | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assessProductChange, bulkUpdateCatalogueProducts, getCatalogueImportJob, getDynamicPriceRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#assessProductChange`, `catalogue#bulkUpdateCatalogueProducts`, `catalogue#getCatalogueImportJob`, `catalogue#getDynamicPriceRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-10 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: publishActivationScheduler, publishChannelAvailability, setCatalogueReview, setLifecycleStatuWorkflow | 8 | Pranay Shinde | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-CATALOGUE-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishActivationScheduler, publishChannelAvailability, setCatalogueReview, setLifecycleStatuWorkflow. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#publishActivationScheduler`, `catalogue#publishChannelAvailability`, `catalogue#setCatalogueReview`, `catalogue#setLifecycleStatuWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-34 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listGovernanceRiskLaunch, listRulePriorityConflict, setRulePriorityConflict | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PRICING-2 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listGovernanceRiskLaunch, listRulePriorityConflict, setRulePriorityConflict. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listGovernanceRiskLaunch`, `catalogue#listRulePriorityConflict`, `catalogue#setRulePriorityConflict` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setPromotionStackingRule | 2 | Pranay Shinde | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPromotionStackingRule. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#setPromotionStackingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-PROMOTION-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: endPromotion, listCommercialCampaigns, pausePromotion, unschedulePromotion | 5 | Narayan Gaonkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: endPromotion, listCommercialCampaigns, pausePromotion, unschedulePromotion. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#endPromotion`, `promotions#listCommercialCampaigns`, `promotions#pausePromotion`, `promotions#unschedulePromotion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-VOUCHER-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createVoucherBatch, listVoucherBatches | 3 | Sanket Keluskar | CatalogueService | MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVoucherBatch, listVoucherBatches. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createVoucherBatch`, `promotions#listVoucherBatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-PRICING-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getPriceList, listPriceLists | 3 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-PRICING-1 | Operations: getPriceList, listPriceLists. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getPriceList`, `catalogue#listPriceLists` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-9 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] AccessService: archiveMediaTemplate, listGuestCompanionEligibility, listMediaDesign | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: archiveMediaTemplate, listGuestCompanionEligibility, listMediaDesign. Spec: contracts (access) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#archiveMediaTemplate`, `access#listGuestCompanionEligibility`, `access#listMediaDesign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-TIMETABLE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: listTransportTimetables, updateTransportTimetable | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTransportTimetables, updateTransportTimetable. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `transport#listTransportTimetables`, `transport#updateTransportTimetable` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-DEPARTURE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: listTransportRouteDepartures | 1 | Chinmay Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-DEPARTURE-1 SVC-VENUEOPS-TIMETABLE-1 | Operations: listTransportRouteDepartures. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `transport#listTransportRouteDepartures` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-NETWORKIMPORT-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: getTransportNetworkImport | 1 | Narayan Gaonkar | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-NETWORKIMPORT-1 | Operations: getTransportNetworkImport. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `transport#getTransportNetworkImport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-PASS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: listTransportPassTypes | 1 | Narayan Gaonkar | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-PASS-1 | Operations: listTransportPassTypes. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `transport#listTransportPassTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-11 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] FnbService: createCombo, setComboSlots | 5 | Surendra | FnbService | MIG-CATALOGUE MIG-FNB MIG-FNB-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCombo, setComboSlots. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#createCombo`, `fnb#setComboSlots` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-FNB-GENERAL-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] FnbService: listCombos | 1 | Chinmay Patkar | FnbService | MIG-FNB-2 PLATFORM-KERNEL SVC-FNB-FNB-11 | Operations: listCombos. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#listCombos` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-AI-GENERATE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] AiService: generateConfiguration | 3 | Narayan Gaonkar | AiService | MIG-AI MIG-AI-2 MIG-AI-3 MIG-CATALOGUE MIG-CATALOGUE-4 MIG-MARKETING MIG-PLATFORM MIG-PROMOTIONS MIG-SEATING MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: generateConfiguration. Spec: contracts (ai) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#generateConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-EVALUATION-1 | AM-TICKETING-P01 | [BE] CatalogueService: evaluatePromotions | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: evaluatePromotions. Spec: handoff/service-docs/backend/CatalogueService.md#group-evaluation Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#evaluatePromotions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SYNC-1 | AM-TICKETING-P01 | [BE] OrderService: listSyncRejections, syncOrders | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PLATFORM MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listSyncRejections, syncOrders. Spec: handoff/service-docs/backend/OrderService.md#group-sync. Done when `orders#listSyncRejections`, `orders#syncOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-CART-3 | AM-TICKETING-P01 | [BE] OrderService: removeCartLine, updateCartLine | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeCartLine, updateCartLine. Spec: handoff/service-docs/backend/OrderService.md#group-cart. Done when `orders#removeCartLine`, `orders#updateCartLine` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-CATALOGUE-PRODUCT-1 | AM-TICKETING-P01 | [BE] CatalogueService: checkBookingEligibility, getGroupPackageDefinition, getProduct, getProductEligibilityRule | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 | Operations: checkBookingEligibility, getGroupPackageDefinition, getProduct, getProductEligibilityRule. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#checkBookingEligibility`, `catalogue#getGroupPackageDefinition`, `catalogue#getProduct`, `catalogue#getProductEligibilityRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-PAYMENT-1 | AM-TICKETING-P01 | [BE] OrderService: addTip, capturePayment, createPayment, inquirePaymentStatus | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: addTip, capturePayment, createPayment, inquirePaymentStatus. Spec: handoff/service-docs/backend/OrderService.md#group-payment Acceptance of the declined, unknown and reconcile paths waits on the client's payment sandbox credentials: see the client's answer in the Decisions Register. Done when `orders#addTip`, `orders#capturePayment`, `orders#createPayment`, `orders#inquirePaymentStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | PRD-W1-LANGUAGES | AM-TICKETING-P01 | [BE] Products wave 1: translatable product texts per channel in the tenant's languages, back end and screens | 3 | Surendra |  | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PRD-W1-DB | Products wave 1: translatable product texts per channel in the tenant's languages, back end and screens. Builds: `operation catalogue#getProductChannelTexts`, `operation catalogue#setProductChannelTexts`, `operation catalogue#getProduct`, `operation catalogue#updateProduct`, `operation white-label#setLanguages`, `operation white-label#getTenantConfig`, `table catalogue.product_channel_text`, `table catalogue.product`. getProductChannelTexts, setProductChannelTexts are built by this task, to their contracts at the release tag in ADAM; no other back-end task builds them. Spec: the contracts at the release tag in ADAM (CHG-R8PRD-002 to 011), from the 16 October 2026 minutes (sources/mom/TICVAI_MoM_2026-10-16_TicketingConfig_Wireframes_Plan.md). The back-office screens are held: build the screen from the products wireframe Pallavi Sawant shares (board ids below; its 21 October revision applies the minutes), not from a generated P08 screen. Back end in CatalogueService: getProductChannelTexts, setProductChannelTexts, reading the tenant's languages only through white-label#tenantLanguageRecords; the product's own name and description per language through getProduct and updateProduct. The languages themselves are the tenant's (white-label setLanguages and getTenantConfig, which exist; the tenant's languages count, published, or the draft before the first publish): no venue list. Screens: the languages entry of the Setup Library, read-only for a venue's product administrator with a link to the tenant's language setting (setLanguages needs TENANT_CONFIGURE at tenant scope), B1-S06 Content & Localization (one block per enabled language and the channel-specific section), the preview of B1-S09. Every operation answers as its contract says, with a contract test for each status code and problem type it lists; the permission and venue scope are enforced (row security on scope_path); every write records the audit entry its contract names; paged lists keep their stated order; nothing is written outside the tables listed. Done when: channel texts save per language within their limits, refuse language-not-enabled and product-archived, and are versioned as updateProduct does; missingTranslations drives the per-language status; the preview shows the POS button label, receipt name and B2B description separately per language.
11 | 1 | PRD-W1-OWNER-FORMS | AM-TICKETING-P01 | [BE] Products wave 1: reservation-owner and ticket-owner forms linked to a product, back end and screens | 5 | Sanket Keluskar |  | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PRD-W1-DB | Products wave 1: reservation-owner and ticket-owner forms linked to a product, back end and screens. Builds: `operation catalogue#getProductOwnerForms`, `operation catalogue#listOwnerFormCandidates`, `operation marketing-crm#recordSaleOwnerAnswers`, `operation catalogue#setProductOwnerForms`, `operation marketing-crm#createForm`, `operation marketing-crm#getForm`, `operation marketing-crm#submitForm`, `table catalogue.product_owner_form`, `table marketing.form_submission_sale_link`. getProductOwnerForms, listOwnerFormCandidates, recordSaleOwnerAnswers, setProductOwnerForms are built by this task, to their contracts at the release tag in ADAM; no other back-end task builds them. Spec: the contracts at the release tag in ADAM (CHG-R8PRD-002 to 011), from the 16 October 2026 minutes (sources/mom/TICVAI_MoM_2026-10-16_TicketingConfig_Wireframes_Plan.md). The back-office screens are held: build the screen from the products wireframe Pallavi Sawant shares (board ids below; its 21 October revision applies the minutes), not from a generated P08 screen. Back end in CatalogueService: getProductOwnerForms, setProductOwnerForms, listOwnerFormCandidates, reading Marketing's forms only through marketing-crm#formDefinitionRecords. In MarketingService, additive and reviewed by its owner: FormField.presentation (dropDown, radio, checkBoxes) through createForm and getForm, and recordSaleOwnerAnswers (the service write the Orders service calls; FormSubmission.saleContext read-only on submitForm). Screens: the owner-form picker of B2-S10 Ownership & Assignment Model only. No Forms screen is built here: the venue draws the data mask (text, drop-down, radio, check box, each field marked personal data or not) and publishes it in Marketing's own form screens, by staff holding MARKETING_VIEW and MARKETING_MANAGE (publishing is Marketing's, with its own second approver); the Setup Library links there, and the product administrator only picks a published form. Every operation answers as its contract says, with a contract test for each status code and problem type it lists; the permission and venue scope are enforced (row security on scope_path); every write records the audit entry its contract names; paged lists keep their stated order; nothing is written outside the tables listed. Done when: a product links at most one reservation-owner and one ticket-owner form, each a published dataCapture or registration form of its venue (unknown-form, form-kind-not-allowed, form-not-published and product-archived refused), versioned as updateProduct does; the picker lists only those forms to a caller holding PRODUCT_CONFIGURE; a select drawn as radio or drop-down and a multiSelect drawn as check boxes store the same answers as before. recordSaleOwnerAnswers takes the order's venue from Orders, checks the order, its buyer, the line and unit, the form's venue and the subject through its declared reads, keeps one submission per owner slot and refuses a second (owner-answers-already-recorded). Asking the forms at sale and calling recordSaleOwnerAnswers is not in this task (orders).
11 | 1 | PRD-W1-SALE-PERMISSIONS | AM-TICKETING-P01 | [BE] Products wave 1: who can sell a product, back end | 5 | Sanket Keluskar |  | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PRD-W1-DB | Products wave 1: who can sell a product, back end. Builds: `operation catalogue#checkProductSalePermission`, `operation catalogue#getProductSalePermissionRules`, `operation catalogue#listSalePermissionTargets`, `operation catalogue#setProductSalePermissionRules`, `table catalogue.product_sale_permission`, `table catalogue.sales_channel`, `table catalogue.product`. checkProductSalePermission, getProductSalePermissionRules, listSalePermissionTargets, setProductSalePermissionRules are built by this task, to their contracts at the release tag in ADAM; no other back-end task builds them. Spec: the contracts at the release tag in ADAM (CHG-R8PRD-002 to 011), from the 16 October 2026 minutes (sources/mom/TICVAI_MoM_2026-10-16_TicketingConfig_Wireframes_Plan.md). Back end in CatalogueService: getProductSalePermissionRules, setProductSalePermissionRules, checkProductSalePermission, listSalePermissionTargets, reading other modules only through their declared queries (tenancy#activeVenues, tenancy#workstationRecords, identity#roleRecords, identity#principalRecords, identity#delegatedAccessRecords). Serves the Who can sell section of B1-S04 and B7-S07 (PRD-W1-SALE-PERMISSIONS-UI). Every operation answers as its contract says, with a contract test for each status code and problem type it lists; the permission and venue scope are enforced (row security on scope_path); every write records the audit entry its contract names; paged lists keep their stated order; nothing is written outside the tables listed. Done when: a rule set saves whole and a rule sent again with its level and target keeps its id; validation, no-allow-rule, global-deny, unknown-sale-permission-target (a new or changed rule naming anything listSalePermissionTargets does not offer for the product; unchanged rules are kept as they are), sale-permission-self-grant (adding an ALLOW for, or lifting a DENY on, the caller or the caller's role) and product-archived are refused; a change takes effect at once in every state but archived, as updateProduct does, versioned and audited; listSalePermissionTargets with productId lists that product's venue; checkProductSalePermission resolves deny over allow (any matching DENY denies, else any matching ALLOW allows, else denied; no rules sells as before), with tests for the contract's example; and a test shows admin rights per venue with the existing grants: a principal granted PRODUCT_CONFIGURE at venue A's scope path (createDelegatedAccess) changes venue A's products and is refused at venue B, while a grant at the tenant's path reaches both. Enforcing the rules at sale is not in this task.
12 | 1 | PRD-W1-SALE-PERMISSIONS-UI | AM-FOUNDATION-PLATFORM | [BE] Products wave 1: who can sell a product, screens | 3 | Surendra |  | PRD-W1-FRAME PRD-W1-SALE-PERMISSIONS | Products wave 1: who can sell a product, screens. Builds: `table catalogue.product_sale_permission`, `table catalogue.sales_channel`, `table catalogue.product`. Spec: the contracts at the release tag in ADAM (CHG-R8PRD-002 to 011), from the 16 October 2026 minutes (sources/mom/TICVAI_MoM_2026-10-16_TicketingConfig_Wireframes_Plan.md). The back-office screens are held: build the screen from the products wireframe Pallavi Sawant shares (board ids below; its 21 October revision applies the minutes), not from a generated P08 screen. Screens on the operations of PRD-W1-SALE-PERMISSIONS: the Who can sell section of B1-S04 Identity & Classification (it replaces Venue scope) and B7-S07 Channel Restrictions. Done when: the rules table edits level (everyone, venue, sales channel, workstation, role, staff member), target (picked from listSalePermissionTargets), allow or deny and note, saves the whole set and shows its one-line summary and that a deny always wins; Test a sale calls checkProductSalePermission with a venue, channel, workstation, role and staff member and shows the deciding rule; every refusal (self-grant, no allow, a deny for everyone) is shown in plain words. The target pickers call listSalePermissionTargets with the product's id.
11 | 1 | SVC-VENUEOPS-RESOURCES-3 | AM-TICKETING-P01 | [BE] VenueOpsService: getResourceHold, listProductStartTimes, releaseResourceBlock, relinquishResourceHold | 3 | Sanket Keluskar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getResourceHold, listProductStartTimes, releaseResourceBlock, relinquishResourceHold. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources Helper task: Narayan Gaonkar owns the service and reviews. Done when `resources#getResourceHold`, `resources#listProductStartTimes`, `resources#releaseResourceBlock`, `resources#relinquishResourceHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VISITPLAN-1 | AM-TICKETING-P01 | [BE] VenueOpsService: bookVisitPlan, generateVisitPlan, getVisitPlan, listVisitPlanAlternatives | 8 | Narayan Gaonkar | VenueOpsService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bookVisitPlan, generateVisitPlan, getVisitPlan, listVisitPlanAlternatives. Spec: handoff/service-docs/backend/VenueOpsService.md#group-visitplan. Done when `venue-map#bookVisitPlan`, `venue-map#generateVisitPlan`, `venue-map#getVisitPlan`, `venue-map#listVisitPlanAlternatives` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-CATALOGUE-CAPACITY-1 | AM-TICKETING-P01 | [BE] CatalogueService: getAvailability | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 | Operations: getAvailability. Spec: handoff/service-docs/backend/CatalogueService.md#group-capacity Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#getAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-CATALOGUE-BUNDLE-5 | AM-TICKETING-P02 | [BE] CatalogueService: getGuestBundle | 2 | Chinmay Patkar | CatalogueService | MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-2 | Operations: getGuestBundle. Spec: handoff/service-docs/backend/CatalogueService.md#group-bundle Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#getGuestBundle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-LEASE-2 | AM-TICKETING-P05-BLOCK-A | [BE] CatalogueService: relinquishInventoryHold | 2 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: relinquishInventoryHold. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Kiosk (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#relinquishInventoryHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-EVENT-1 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: cancelPerformance, getEvent | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: cancelPerformance, getEvent. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#cancelPerformance`, `catalogue#getEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-CATALOGUE-BUNDLE-7 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getBundleSigningKeys | 1 | Deep Khanvilkar | CatalogueService | MIG-BASELINE PLATFORM-KERNEL | Operations: getBundleSigningKeys. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getBundleSigningKeys` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-LEASE-1 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: acquireInventoryHold, convertInventoryHold, listInventoryHolds | 8 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acquireInventoryHold, convertInventoryHold, listInventoryHolds. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#acquireInventoryHold`, `catalogue#convertInventoryHold`, `catalogue#listInventoryHolds` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-LEASE-3 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: renewInventoryHold | 2 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: renewInventoryHold. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#renewInventoryHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-5 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: listProductApprovalWorkflows, listSeatPricingRules, listTaxProfiles, setSeatPricingRule | 8 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductApprovalWorkflows, listSeatPricingRules, listTaxProfiles, setSeatPricingRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listProductApprovalWorkflows`, `catalogue#listSeatPricingRules`, `catalogue#listTaxProfiles`, `catalogue#setSeatPricingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENT-4 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getWaitingRoomStatus, setWaitingRoomSetting | 3 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingRoomStatus, setWaitingRoomSetting. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getWaitingRoomStatus`, `catalogue#setWaitingRoomSetting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-2 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getEventChangeTreatmentPolicy, setEventChangeTreatmentPolicy | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getEventChangeTreatmentPolicy, setEventChangeTreatmentPolicy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getEventChangeTreatmentPolicy`, `catalogue#setEventChangeTreatmentPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-CATALOGUE-7 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getPlanBenefits, joinWaitlist, leaveWaitlist, listGuestMemberships | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getPlanBenefits, joinWaitlist, leaveWaitlist, listGuestMemberships. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getPlanBenefits`, `catalogue#joinWaitlist`, `catalogue#leaveWaitlist`, `catalogue#listGuestMemberships` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-DRAFTED-29 | AM-TICKETING-P08-BLOCK-A-COMPLETION | [BE] CatalogueService: setChannelPricingCommercial, setPricing, setPricingExperiment, setProductCatalogue | 8 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setChannelPricingCommercial, setPricing, setPricingExperiment, setProductCatalogue. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A completion); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setChannelPricingCommercial`, `catalogue#setPricing`, `catalogue#setPricingExperiment`, `catalogue#setProductCatalogue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-21 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listChannelCustomerSegment, listCompetitorPricingMarket, listDynamicPriceBand, listDynamicPricingAutomation | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-PRICING-2 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listChannelCustomerSegment, listCompetitorPricingMarket, listDynamicPriceBand, listDynamicPricingAutomation. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannelCustomerSegment`, `catalogue#listCompetitorPricingMarket`, `catalogue#listDynamicPriceBand`, `catalogue#listDynamicPricingAutomation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-ORDERS-8 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: listTicketTemplates, printTicketProof | 3 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-5 VM-CATALOGUE-PRODUCT-1 | Operations: listTicketTemplates, printTicketProof. Spec: contracts (orders) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listTicketTemplates`, `orders#printTicketProof` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-CATALOGUE-8 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: listMembershipBenefits, listMembershipProgrammes | 1 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE-2 MIG-CATALOGUE-5 PLATFORM-KERNEL | Operations: listMembershipBenefits, listMembershipProgrammes. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listMembershipBenefits`, `catalogue#listMembershipProgrammes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 1 | SVC-CATALOGUE-COUPON-4 | AM-PRICING-PROMOTIONS-P02 | [BE] CatalogueService: getGuestCouponCode | 2 | Deep Khanvilkar | CatalogueService | MIG-BASELINE PLATFORM-KERNEL | Operations: getGuestCouponCode. Spec: handoff/service-docs/backend/CatalogueService.md#group-coupon Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#getGuestCouponCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-HOLD-1 | AM-SEATING-MAPS-P01 | [BE] CatalogueService: createSeatHold, extendSeatHold, getSeatHold, relinquishSeatHold | 5 | Narayan Gaonkar | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createSeatHold, extendSeatHold, getSeatHold, relinquishSeatHold. Spec: handoff/service-docs/backend/CatalogueService.md#group-hold Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#createSeatHold`, `seating#extendSeatHold`, `seating#getSeatHold`, `seating#relinquishSeatHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-AVAILABILITY-1 | AM-SEATING-MAPS-P01 | [BE] CatalogueService: getSeatAvailability | 2 | Chinmay Patkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-SEATMAP-1 | Operations: getSeatAvailability. Spec: handoff/service-docs/backend/CatalogueService.md#group-availability Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#getSeatAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-RECOMMENDATION-1 | AM-SEATING-MAPS-P01 | [BE] CatalogueService: recommendSeats | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 | Operations: recommendSeats. Spec: handoff/service-docs/backend/CatalogueService.md#group-recommendation Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#recommendSeats` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-QUEUE-1 | AM-SEATING-MAPS-P01 | [BE] VenueOpsService: createQueue, listQueues, updateQueue | 8 | Narayan Gaonkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createQueue, listQueues, updateQueue. Spec: handoff/service-docs/backend/VenueOpsService.md#group-queue. Done when `queue#createQueue`, `queue#listQueues`, `queue#updateQueue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VISITPLAN-2 | AM-SEATING-MAPS-P01 | [BE] VenueOpsService: updateVisitPlan | 3 | Sanket Keluskar | VenueOpsService | MIG-CATALOGUE MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateVisitPlan. Spec: handoff/service-docs/backend/VenueOpsService.md#group-visitplan Helper task: Narayan Gaonkar owns the service and reviews. Done when `venue-map#updateVisitPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-RESOURCES-2 | AM-SEATING-MAPS-P02 | [BE] VenueOpsService: createResourcePackage, extendResourceHold, getMapResourceAvailability, getResourceAvailability | 8 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResourcePackage, extendResourceHold, getMapResourceAvailability, getResourceAvailability. Spec: contracts (resources) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#createResourcePackage`, `resources#extendResourceHold`, `resources#getMapResourceAvailability`, `resources#getResourceAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-VENUEMAP-1 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: setPathClosure | 2 | Chinmay Patkar | VenueOpsService | MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setPathClosure. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `venue-map#setPathClosure` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-VENUEMAP-5 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: acceptVenueLabelProposals, acceptWalkwayProposals, getVenueMapImportJob, getVenueNavigationFile | 8 | Pranay Shinde | VenueOpsService | MIG-AI MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: acceptVenueLabelProposals, acceptWalkwayProposals, getVenueMapImportJob, getVenueNavigationFile. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `venue-map#acceptVenueLabelProposals`, `venue-map#acceptWalkwayProposals`, `venue-map#getVenueMapImportJob`, `venue-map#getVenueNavigationFile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-VISITPLAN-3 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: getVisitPlannerOptions, listMyVisitPlans, setVisitPlanPreset | 8 | Narayan Gaonkar | VenueOpsService | MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getVisitPlannerOptions, listMyVisitPlans, setVisitPlanPreset. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `venue-map#getVisitPlannerOptions`, `venue-map#listMyVisitPlans`, `venue-map#setVisitPlanPreset` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-VENUEMAP-6 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: listVenueMaps, validateVenueMapGraph | 2 | Narayan Gaonkar | VenueOpsService | MIG-VENUEMAP PLATFORM-KERNEL SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-VENUEOPS-VENUEMAP-1 | Operations: listVenueMaps, validateVenueMapGraph. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `venue-map#listVenueMaps`, `venue-map#validateVenueMapGraph` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-VISITPLAN-4 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: listVisitPlanPresets | 1 | Narayan Gaonkar | VenueOpsService | MIG-VENUEMAP PLATFORM-KERNEL SVC-VENUEOPS-VISITPLAN-3 | Operations: listVisitPlanPresets. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `venue-map#listVisitPlanPresets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-AI-AI-3 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] AiService: proposeWalkways | 2 | Surendra | AiService | MIG-AI MIG-ASSETS MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeWalkways. Spec: contracts (ai) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#proposeWalkways` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-RESERVATION-1 | AM-ORDERS-RESERVATIONS-P01 | [BE] OrderService: cancelReservation, convertReservation, createReservation, extendReservation | 8 | Sanket Keluskar | OrderService | MIG-ORDERS MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelReservation, convertReservation, createReservation, extendReservation. Spec: handoff/service-docs/backend/OrderService.md#group-reservation. Done when `orders#cancelReservation`, `orders#convertReservation`, `orders#createReservation`, `orders#extendReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-DUNNING-1 | AM-ORDERS-RESERVATIONS-P01 | [BE] OrderService: listMyPaymentIssues, retryMyDunningPayment | 3 | Sanket Keluskar | OrderService | MIG-ORDERS MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listMyPaymentIssues, retryMyDunningPayment. Spec: handoff/service-docs/backend/OrderService.md#group-dunning Helper task: Pranay Shinde owns the service and reviews. Done when `payments#listMyPaymentIssues`, `payments#retryMyDunningPayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ORDER-ORDERS-10 | AM-ORDERS-RESERVATIONS-P01 | [BE] OrderService: listOwnGroupBookings, listOwnResaleListings | 3 | Sanket Keluskar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-4 | Operations: listOwnGroupBookings, listOwnResaleListings. Spec: handoff/service-docs/backend/OrderService.md#group-orders Helper task: Pranay Shinde owns the service and reviews. Done when `orders#listOwnGroupBookings`, `orders#listOwnResaleListings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ORDER-RESERVATION-2 | AM-ORDERS-RESERVATIONS-P01 | [BE] OrderService: getReservation, listReservations | 3 | Sanket Keluskar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-ORDERS-3 SVC-ORDER-RESERVATION-1 | Operations: getReservation, listReservations. Spec: handoff/service-docs/backend/OrderService.md#group-reservation Helper task: Pranay Shinde owns the service and reviews. Done when `orders#getReservation`, `orders#listReservations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-10 | AM-ORDERS-RESERVATIONS-P01 | [BE] FnbService: signCorrectiveAction, transferTableVisit, updateTableReservation | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: signCorrectiveAction, transferTableVisit, updateTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#signCorrectiveAction`, `fnb#transferTableVisit`, `fnb#updateTableReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-4 | AM-ORDERS-RESERVATIONS-P01 | [BE] FnbService: leaveRestaurantWaitlist, list86Events, listMyTableReservations, listTableCombinations | 5 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: leaveRestaurantWaitlist, list86Events, listMyTableReservations, listTableCombinations. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#leaveRestaurantWaitlist`, `fnb#list86Events`, `fnb#listMyTableReservations`, `fnb#listTableCombinations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-ORDER-3 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: getOrderStatement, getVisitReminder, holdOrder, listOrders | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getOrderStatement, getVisitReminder, holdOrder, listOrders. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#getOrderStatement`, `orders#getVisitReminder`, `orders#holdOrder`, `orders#listOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-REFUND-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: createRefund, createRefundRequest, listOrderRefunds | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createRefund, createRefundRequest, listOrderRefunds. Spec: handoff/service-docs/backend/OrderService.md#group-refund. Done when `orders#createRefund`, `orders#createRefundRequest`, `orders#listOrderRefunds` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-REFUND-3 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: listOwnRefundRequests | 2 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-REFUND-1 | Operations: listOwnRefundRequests. Spec: handoff/service-docs/backend/OrderService.md#group-refund Helper task: Pranay Shinde owns the service and reviews. Done when `orders#listOwnRefundRequests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-GUESTORDERING-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: claimLocationSession, createDeliveryLocation, createGuestFnbOrder, getFnbDeliveryPolicy | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: claimLocationSession, createDeliveryLocation, createGuestFnbOrder, getFnbDeliveryPolicy. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#claimLocationSession`, `fnb#createDeliveryLocation`, `fnb#createGuestFnbOrder`, `fnb#getFnbDeliveryPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-GUESTORDERING-3 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: listDeliveryLocations, listDiningOutlets, listFulfilmentSlots, recordOrderHandover | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDeliveryLocations, listDiningOutlets, listFulfilmentSlots, recordOrderHandover. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#listDeliveryLocations`, `fnb#listDiningOutlets`, `fnb#listFulfilmentSlots`, `fnb#recordOrderHandover` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-GUESTORDERING-4 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: setDeliveryLocationOutletMapping, setFnbDeliveryPolicy, updateDeliveryLocation | 5 | Sanket Keluskar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeliveryLocationOutletMapping, setFnbDeliveryPolicy, updateDeliveryLocation. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#setDeliveryLocationOutletMapping`, `fnb#setFnbDeliveryPolicy`, `fnb#updateDeliveryLocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-KITCHEN-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: listKitchenStations, listKitchenTickets, prioritiseKitchenTicket, setKitchenTicketStatus | 8 | Deep Khanvilkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listKitchenStations, listKitchenTickets, prioritiseKitchenTicket, setKitchenTicketStatus. Spec: handoff/service-docs/backend/FnbService.md#group-kitchen. Done when `fnb#listKitchenStations`, `fnb#listKitchenTickets`, `fnb#prioritiseKitchenTicket`, `fnb#setKitchenTicketStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-MODIFIER-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: createModifierGroup | 2 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createModifierGroup. Spec: handoff/service-docs/backend/FnbService.md#group-modifier Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#createModifierGroup` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-ORDER-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: createFnbOrder, getFnbOrder, listFnbOrders | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createFnbOrder, getFnbOrder, listFnbOrders. Spec: handoff/service-docs/backend/FnbService.md#group-order. Done when `fnb#createFnbOrder`, `fnb#getFnbOrder`, `fnb#listFnbOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-SERVICE-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: acceptFnbOrder, cancelFnbOrder | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acceptFnbOrder, cancelFnbOrder. Spec: handoff/service-docs/backend/FnbService.md#group-service. Done when `fnb#acceptFnbOrder`, `fnb#cancelFnbOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-TABLE-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: clearTable, getTableMap, getTableVisit, openTableVisit | 8 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: clearTable, getTableMap, getTableVisit, openTableVisit. Spec: handoff/service-docs/backend/FnbService.md#group-table. Done when `fnb#clearTable`, `fnb#getTableMap`, `fnb#getTableVisit`, `fnb#openTableVisit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-TABLE-2 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: setTableLayout, updateTableVisit | 5 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTableLayout, updateTableVisit. Spec: handoff/service-docs/backend/FnbService.md#group-table. Done when `fnb#setTableLayout`, `fnb#updateTableVisit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-RECOMMEND-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] AiService: decideRecommendations, recordRecommendationEvents | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideRecommendations, recordRecommendationEvents. Spec: handoff/service-docs/backend/AiService.md#group-recommend Helper task: Pranay Shinde owns the service and reviews. Done when `ai#decideRecommendations`, `ai#recordRecommendationEvents` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-LEDGER-TAX-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] LedgerService: createTaxCode, getTaxDocumentRendition, getTaxInvoice, issueCreditMemo | 8 | Narayan Gaonkar | LedgerService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createTaxCode, getTaxDocumentRendition, getTaxInvoice, issueCreditMemo. Spec: handoff/service-docs/backend/LedgerService.md#group-tax. Done when `finance#createTaxCode`, `finance#getTaxDocumentRendition`, `finance#getTaxInvoice`, `finance#issueCreditMemo` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-LEDGER-TAX-2 | AM-ORDERS-RESERVATIONS-P04 | [BE] LedgerService: issueTaxInvoice, listCreditMemos, listTaxInvoices, setEInvoicingProvider | 8 | Narayan Gaonkar | LedgerService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: issueTaxInvoice, listCreditMemos, listTaxInvoices, setEInvoicingProvider. Spec: handoff/service-docs/backend/LedgerService.md#group-tax. Done when `finance#issueTaxInvoice`, `finance#listCreditMemos`, `finance#listTaxInvoices`, `finance#setEInvoicingProvider` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-CARD-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] VenueOpsService: getGameCard, issueGameCard | 3 | Sanket Keluskar | VenueOpsService | MIG-GAMES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGameCard, issueGameCard. Spec: handoff/service-docs/backend/VenueOpsService.md#group-card Helper task: Narayan Gaonkar owns the service and reviews. Done when `games#getGameCard`, `games#issueGameCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-INVENTORY-ITEM-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] InventoryService: createInventoryItem, setInventoryKitDefinition, updateInventoryItem | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createInventoryItem, setInventoryKitDefinition, updateInventoryItem. Spec: handoff/service-docs/backend/InventoryService.md#group-item Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#createInventoryItem`, `inventory#setInventoryKitDefinition`, `inventory#updateInventoryItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-INVENTORY-INVENTORY-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] InventoryService: listSerialisedItems | 2 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations: listSerialisedItems. Spec: handoff/service-docs/backend/InventoryService.md#group-inventory Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#listSerialisedItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-LOYALTY-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] MarketingService: awardBadge, createLoyaltyProgramme, getGuestLoyalty, listCustomerBadges | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: awardBadge, createLoyaltyProgramme, getGuestLoyalty, listCustomerBadges. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty. Done when `marketing-crm#awardBadge`, `marketing-crm#createLoyaltyProgramme`, `marketing-crm#getGuestLoyalty`, `marketing-crm#listCustomerBadges` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-MIG-LEDGER | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1016__ledger.sql: ledger for Venue Management (7 tables) | 3 | Hrushikant Patkar |  | MIG-LEDGER | Tables: ledger.account_mapping, ledger.deposit, ledger.event_budget, ledger.fiscal_period_event, ledger.recognition_schedule, ledger.settlement, ledger.settlement_exception. Source DDL: backend/tenant/010-ledger.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ledger.deposit: row-level security apply_grant_holder_subject_read_rls; ledger.event_budget: column cost_lines; ledger.fiscal_period_event: row-level security apply_parent_split_rls; ledger.recognition_schedule: column scope_path, index recognition_schedule_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ledger.fiscal_period_event: foreign key fiscal_period_event_principal_id_fkey; ledger.recognition_schedule: rename column revalidate_on_validity_change to revalidates_on_validity_change); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (ledger.account_mapping: column scope_path, index account_mapping_scope_path_idx, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `ledger.account_mapping.scope_path`; not null `ledger.recognition_schedule.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ledger.account_mapping`, `ledger.deposit`, `ledger.event_budget`, `ledger.fiscal_period_event`, `ledger.recognition_schedule`, `ledger.settlement`, `ledger.settlement_exception` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 2 | VM-MIG-ORDERS | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1018__orders.sql: orders for Venue Management (6 tables) | 5 | Hrushikant Patkar |  | MIG-ORDERS | Tables: orders.after_sale_policy, orders.after_sale_request, orders.chargeback_evidence, orders.chargeback_investigation_log, orders.group_quote, orders.refund_batch. Source DDL: backend/tenant/010-orders.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.after_sale_policy: rename column void_same_business_day_only to is_void_same_business_day_only, rename column void_before_settlement_only to is_void_before_settlement_only, rename column void_before_ticket_use_only to is_void_before_ticket_use_only, rename column void_before_fiscal_closure_only to is_void_before_fiscal_closure_only, rename column void_dual_authorisation to requires_void_dual_authorisation, drop index after_sale_policy_product_id_idx; orders.after_sale_request: foreign key after_sale_request_order_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (orders.chargeback_evidence: row-level security apply_parent_split_rls; orders.chargeback_investigation_log: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Leave out the key group_quote_enquiry_id_fkey** (orders.group_quote to orders.group_enquiry): MIG-ORDERS-18 creates orders.group_enquiry later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.after_sale_policy`, `orders.after_sale_request`, `orders.chargeback_evidence`, `orders.chargeback_investigation_log`, `orders.group_quote`, `orders.refund_batch` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | MIG-ORDERS-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1127__orders.sql: orders for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.discount. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (orders.discount: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.discount` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 2 | VM-MIG-PAYMENTS | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1020__payments.sql: payments for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-PAYMENTS | Tables: payments.provider_cost. Source DDL: backend/tenant/010-payments.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.provider_cost: rename column amount to cost_amount); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.provider_cost` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1139__payments.sql: payments for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (5 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.instalment, payments.instalment_plan, payments.instalment_policy, payments.mixed_tender_rules, payments.payment_terms. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.instalment_policy: row-level security apply_read_beneath_rls; payments.mixed_tender_rules: column allowed_combinations); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.instalment: rename column amount to due_amount; payments.instalment_plan: rename column total to gross_amount, rename column paid_to_date to paid_amount, foreign key instalment_plan_order_id_fkey; payments.instalment_policy: rename column minimum_order_value to minimum_order_amount, rename column instalment_fee to instalment_fee_amount); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.instalment`, `payments.instalment_plan`, `payments.instalment_policy`, `payments.mixed_tender_rules`, `payments.payment_terms` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 3 | SVC-ORDER-PAYMENTS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: createInstalmentPlan, createPaymentProviderConnection, listInstalmentPlans, setDunningPolicy | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-4 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createInstalmentPlan, createPaymentProviderConnection, listInstalmentPlans, setDunningPolicy. Spec: contracts (payments) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#createInstalmentPlan`, `payments#createPaymentProviderConnection`, `payments#listInstalmentPlans`, `payments#setDunningPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: resolveDunningCase, setB2bPaymentTerms, setMixedTenderRules | 5 | Pranay Shinde | OrderService | MIG-PAYMENTS MIG-PAYMENTS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveDunningCase, setB2bPaymentTerms, setMixedTenderRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#resolveDunningCase`, `payments#setB2bPaymentTerms`, `payments#setMixedTenderRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-5 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1027__orders.sql: orders for Orders & Reservations · Staff App (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.order_relationship. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.order_relationship: foreign key order_relationship_order_id_fkey, foreign key order_relationship_related_order_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.order_relationship` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | MIG-ORDERS-6 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1028__orders.sql: orders for Orders & Reservations · Venue Management (Block A) (5 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-IDENTITY MIG-LEDGER MIG-ORDERS VM-MIG-ORDERS | Tables: orders.b2b_credit, orders.credit_override, orders.guest_credit_account, orders.invitation_allowance, orders.refund_calculation_policy. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (orders.invitation_allowance: column scope_path, index invitation_allowance_scope_path_idx, row-level security apply_grant_holder_read_rls; orders.refund_calculation_policy: column scope_path, index refund_calculation_policy_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.guest_credit_account: foreign key guest_credit_account_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `orders.invitation_allowance.scope_path`; not null `orders.refund_calculation_policy.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.b2b_credit`, `orders.credit_override`, `orders.guest_credit_account`, `orders.invitation_allowance`, `orders.refund_calculation_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | MIG-ORDERS-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1025__orders.sql: orders for Subscription & Licensing · Venue Management 2 of 3 (3 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.membership_activation_action, orders.membership_migration, orders.membership_renewal. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (orders.membership_activation_action: row-level security apply_grant_holder_subject_read_rls; orders.membership_migration: column scope_path, index membership_migration_scope_path_idx, row-level security apply_grant_holder_read_rls; orders.membership_renewal: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.membership_migration: rename column pro_rata to is_pro_rata; orders.membership_renewal: foreign key membership_renewal_customer_membership_id_fkey, foreign key membership_renewal_entitlement_template_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **orders.membership_renewal's row-level security waits for its parent**: its policy reads identity.customer_membership, which MIG-IDENTITY-3 creates later, so leave out its `platform.apply_parent_rls` call here; MIG-IDENTITY-3 applies it. **Leave out the key membership_renewal_customer_membership_id_fkey** (orders.membership_renewal to identity.customer_membership): MIG-IDENTITY-3 creates identity.customer_membership later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `orders.membership_migration.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.membership_activation_action`, `orders.membership_migration`, `orders.membership_renewal` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 2 | VM-LEDGER-FINANCE-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] LedgerService: settleDeposit, validateRecognitionSchedules | 3 | Sanket Keluskar | LedgerService | MIG-CATALOGUE MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: settleDeposit, validateRecognitionSchedules. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#settleDeposit`, `finance#validateRecognitionSchedules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-LEDGER-SETTLEMENT-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] LedgerService: resolveSettlementException | 2 | Chinmay Patkar | LedgerService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: resolveSettlementException. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#resolveSettlementException` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-ORDER-SHIFT-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: closeDepositBoxes, getShift | 5 | Deep Khanvilkar | OrderService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: closeDepositBoxes, getShift. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `shift#closeDepositBoxes`, `shift#getShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-ORDERS-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: getChargebackAnalytics, listDeposits, recordChargeback, recordChargebackOutcome | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-LEDGER VM-MIG-ORDERS | Operations beyond the first release: getChargebackAnalytics, listDeposits, recordChargeback, recordChargebackOutcome. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `orders#getChargebackAnalytics`, `orders#listDeposits`, `orders#recordChargeback`, `orders#recordChargebackOutcome` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-REFUND-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: approveRefund, createBulkRefund | 5 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations beyond the first release: approveRefund, createBulkRefund. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `orders#approveRefund`, `orders#createBulkRefund` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-LEDGER-SETTLEMENT-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] LedgerService: getSettlement, ingestSettlementFile, listSettlementExceptions, listSettlements | 8 | Narayan Gaonkar | LedgerService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER VM-MIG-PAYMENTS | Operations beyond the first release: getSettlement, ingestSettlementFile, listSettlementExceptions, listSettlements. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Done when `finance#getSettlement`, `finance#ingestSettlementFile`, `finance#listSettlementExceptions`, `finance#listSettlements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-ORDER-ORDERS-21 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: attachGuestCheckoutOrders | 1 | Narayan Gaonkar | OrderService | MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: attachGuestCheckoutOrders. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#attachGuestCheckoutOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ORDER-ORDERS-14 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: revokeEntitlementShare | 2 | Surendra | OrderService | MIG-ACCESS MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: revokeEntitlementShare. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#revokeEntitlementShare` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-IDENTITY-ADMINISTRATION-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: suggestRoleAssignment | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 VM-IDENTITY-ADMINISTRATION-1 VM-MIG-IDENTITY VM-MIG-WORKFORCE | Operations beyond the first release: suggestRoleAssignment. Additive to IdentityService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#suggestRoleAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-IDENTITY-ADMINISTRATION-9 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: listAccessReviewCampaigns, listAccessReviewItems, listCapabilityTemplates, listPermissionFindings | 5 | Surendra | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-IDENTITY-3 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 VM-IDENTITY-ADMINISTRATION-1 VM-MIG-IDENTITY | Operations: listAccessReviewCampaigns, listAccessReviewItems, listCapabilityTemplates, listPermissionFindings. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#listAccessReviewCampaigns`, `identity#listAccessReviewItems`, `identity#listCapabilityTemplates`, `identity#listPermissionFindings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-IDENTITY-ADMINISTRATION-10 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: resolvePermissions | 1 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 SVC-TENANCY-SCOPE-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: resolvePermissions. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#resolvePermissions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-IDENTITY-IDENTITY-7 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: listModules, listSegregationRules, listSegregationViolations | 2 | Sanket Keluskar | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-IDENTITY-3 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: listModules, listSegregationRules, listSegregationViolations. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#listModules`, `identity#listSegregationRules`, `identity#listSegregationViolations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-B2B-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: overrideCreditLimit, setB2bCreditLimit | 5 | Pranay Shinde | OrderService | MIG-ORDERS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: overrideCreditLimit, setB2bCreditLimit. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#overrideCreditLimit`, `orders#setB2bCreditLimit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: setOrderAmendment, setOrderDetailTransaction | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-3 MIG-ORDERS-5 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: setOrderAmendment, setOrderDetailTransaction. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setOrderAmendment`, `orders#setOrderDetailTransaction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-12 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: convertToTermProduct, issueInvitation, listInvitationAllowances, listMembershipRenewals | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-ORDERS-2 MIG-ORDERS-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: convertToTermProduct, issueInvitation, listInvitationAllowances, listMembershipRenewals. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#convertToTermProduct`, `orders#issueInvitation`, `orders#listInvitationAllowances`, `orders#listMembershipRenewals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-27 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listLearningModelPerformance, listPriceElasticityRevenue, listPricingRecommendationExplainability, listRecommendationReviewDecision | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-PRODUCT-1 | Operations: listLearningModelPerformance, listPriceElasticityRevenue, listPricingRecommendationExplainability, listRecommendationReviewDecision. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listLearningModelPerformance`, `catalogue#listPriceElasticityRevenue`, `catalogue#listPricingRecommendationExplainability`, `catalogue#listRecommendationReviewDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-22 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listDynamicPricingGuardrail, listInternalDemandBooking, listMarketTourismHoliday, listNearbyEventExhibition | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listDynamicPricingGuardrail, listInternalDemandBooking, listMarketTourismHoliday, listNearbyEventExhibition. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listDynamicPricingGuardrail`, `catalogue#listInternalDemandBooking`, `catalogue#listMarketTourismHoliday`, `catalogue#listNearbyEventExhibition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-26 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listChannelSaleRule, listChannelSaleSchedule, listDynamicPricingPerformance, listInventoryCapacityChannel | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-7 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listChannelSaleRule, listChannelSaleSchedule, listDynamicPricingPerformance, listInventoryCapacityChannel. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannelSaleRule`, `catalogue#listChannelSaleSchedule`, `catalogue#listDynamicPricingPerformance`, `catalogue#listInventoryCapacityChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-30 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listChannel, listChannel2, listChannelAllocationRebalancing, listChannelConnectionIntegration | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listChannel, listChannel2, listChannelAllocationRebalancing, listChannelConnectionIntegration. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannel`, `catalogue#listChannel2`, `catalogue#listChannelAllocationRebalancing`, `catalogue#listChannelConnectionIntegration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-13 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: listOrderDiscounts, listOrderFees, openGuestCreditAccount, pushWalletPassUpdate | 5 | Narayan Gaonkar | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-3 MIG-ORDERS-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOrderDiscounts, listOrderFees, openGuestCreditAccount, pushWalletPassUpdate. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listOrderDiscounts`, `orders#listOrderFees`, `orders#openGuestCreditAccount`, `orders#pushWalletPassUpdate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-20 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: revokePaymentToken | 1 | Pranay Shinde | OrderService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: revokePaymentToken. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#revokePaymentToken` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-9 | AM-PAYMENTS-P08-BLOCK-A-COMPLETION | [DB] Forward migration V1071__payments.sql: payments for Payments · Venue Management (Block A completion) (4 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.chargeback_evidence, payments.credit_account, payments.matching_rules, payments.merchant_account. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.chargeback_evidence: column documents); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.chargeback_evidence: foreign key chargeback_evidence_chargeback_id_fkey; payments.credit_account: rename column over_limit to is_over_limit; payments.matching_rules: rename column net_of_fees to is_net_of_fees; payments.merchant_account: foreign key external_reference_mapping_merchant_id_fkey (from orders.external_reference_mapping)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.chargeback_evidence`, `payments.credit_account`, `payments.matching_rules`, `payments.merchant_account` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 3 | SVC-ORDER-PAYMENTS-2 | AM-PAYMENTS-P08-BLOCK-A-COMPLETION | [BE] OrderService: setInstalmentPolicy | 2 | Chinmay Patkar | OrderService | MIG-PAYMENTS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setInstalmentPolicy. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management (Block A completion); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setInstalmentPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: getB2bPaymentTerms, getDunningPolicy, getInstalmentPolicy, listDunningCases | 3 | Pranay Shinde | OrderService | MIG-PAYMENTS MIG-PAYMENTS-4 PLATFORM-KERNEL SVC-ORDER-DUNNING-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-2 SVC-ORDER-PAYMENTS-6 | Operations: getB2bPaymentTerms, getDunningPolicy, getInstalmentPolicy, listDunningCases. Spec: contracts (payments) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#getB2bPaymentTerms`, `payments#getDunningPolicy`, `payments#getInstalmentPolicy`, `payments#listDunningCases` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-11 | AM-PAYMENTS-P08-BLOCK-A-COMPLETION | [BE] OrderService: listB2bCreditAccounts | 1 | Hrushikant Patkar | OrderService | MIG-PAYMENTS-9 PLATFORM-KERNEL | Operations: listB2bCreditAccounts. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management (Block A completion); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listB2bCreditAccounts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-7 | AM-PAYMENTS-API-BLOCK-A | [DB] Forward migration V1030__payments.sql: payments for Payments · Venue Management 1 of 3 (5 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.currency_rule, payments.eligibility_rule, payments.failover_policy, payments.fee_rule, payments.provider_event. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.fee_rule: column scope_path, index fee_rule_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.eligibility_rule: foreign key eligibility_rule_payment_method_id_fkey; payments.failover_policy: rename column failover_to_next_provider to fails_over_to_next_provider); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (payments.currency_rule: column payment_policy_id; payments.eligibility_rule: column payment_policy_id; payments.fee_rule: column payment_policy_id; payments.provider_event: column provider_connection_id, constraint provider_event_provider_connection_id_fkey, index provider_event_provider_connection_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column retired `payments.currency_rule.payment_policy_id`; column retired `payments.eligibility_rule.payment_policy_id`; not null `payments.fee_rule.scope_path`; column retired `payments.fee_rule.payment_policy_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.currency_rule`, `payments.eligibility_rule`, `payments.failover_policy`, `payments.fee_rule`, `payments.provider_event` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-10 | AM-PAYMENTS-API-BLOCK-A | [DB] Forward migration V1182__payments.sql: payments for Payments · API only (Block A) (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.method_config. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.method_config: foreign key method_config_payment_method_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (payments.method_config: column payment_policy_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column retired `payments.method_config.payment_policy_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.method_config` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 3 | SVC-ORDER-PAYMENTS-17 | AM-PAYMENTS-API-BLOCK-A | [BE] OrderService: listPaymentMethods, listPaymentProviderConnections, setPaymentRules, simulatePaymentConfiguration | 5 | Deep Khanvilkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-10 MIG-PAYMENTS-7 MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPaymentMethods, listPaymentProviderConnections, setPaymentRules, simulatePaymentConfiguration. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · API only (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listPaymentMethods`, `payments#listPaymentProviderConnections`, `payments#setPaymentRules`, `payments#simulatePaymentConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-18 | AM-PAYMENTS-API-BLOCK-A | [BE] OrderService: testPaymentProviderConnection | 1 | Narayan Gaonkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: testPaymentProviderConnection. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · API only (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#testPaymentProviderConnection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 1 | SVC-WALLET-GIFTCARD-1 | AM-WALLET-CASHLESS-P01 | [BE] WalletService: getGiftCard | 1 | Chinmay Patkar | WalletService | MIG-WALLET PLATFORM-KERNEL | Operations: getGiftCard. Spec: handoff/service-docs/backend/WalletService.md#group-giftcard Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#getGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 2 | VM-MIG-WALLET | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [DB] Forward migration V1081__wallet.sql: wallet for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-WALLET | Tables: wallet.adjustment. Source DDL: backend/tenant/010-wallet.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.adjustment: rename column amount to adjustment_amount); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0112__after_r1_20261021.sql (wallet.adjustment: DROP CONSTRAINT IF EXISTS adjustment_kind_chk; VALIDATE CONSTRAINT adjustment_kind_chk, constraint adjustment_kind_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.adjustment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | MIG-WALLET-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1128__wallet.sql: wallet for Public API · Venue Management (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.risk_rule. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.risk_rule: rename column risk_rules_id to risk_rule_set_id, rename constraint risk_rule_risk_rules_id_fkey to risk_rule_risk_rule_set_id_fkey, rename index risk_rule_risk_rules_id_idx to risk_rule_risk_rule_set_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (wallet.risk_rule: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.risk_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] WalletService: listWalletConfigurationVersions, listWalletTypes, setWalletRiskRuleStatus | 3 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listWalletConfigurationVersions, listWalletTypes, setWalletRiskRuleStatus. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#listWalletConfigurationVersions`, `wallet#listWalletTypes`, `wallet#setWalletRiskRuleStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-3 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [DB] Forward migration V1145__wallet.sql: wallet for Wallet & Cashless · Venue Management (Block A completion) (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.dispute. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.dispute: rename column amount to disputed_amount, foreign key dispute_wallet_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.dispute` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-WALLET-WALLET-1 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: expireCreditLots, listCreditLots | 3 | Sanket Keluskar | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-WALLET | Operations beyond the first release: expireCreditLots, listCreditLots. Additive to WalletService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#expireCreditLots`, `wallet#listCreditLots` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-WALLET-WALLET-12 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: getWalletMovementSummary, getWalletPreCloseChecks | 1 | Narayan Gaonkar | WalletService | MIG-BASELINE PLATFORM-KERNEL | Operations: getWalletMovementSummary, getWalletPreCloseChecks. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management (Block A completion); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#getWalletMovementSummary`, `wallet#getWalletPreCloseChecks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-8 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: captureWalletHold, holdWalletFunds, listWalletDisputes, releaseWalletHold | 8 | Pranay Shinde | WalletService | MIG-PLATFORM MIG-WALLET MIG-WALLET-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: captureWalletHold, holdWalletFunds, listWalletDisputes, releaseWalletHold. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management (Block A completion); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#captureWalletHold`, `wallet#holdWalletFunds`, `wallet#listWalletDisputes`, `wallet#releaseWalletHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-9 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: resolveWalletDispute, setWalletIntegrationMapping, withdrawWalletDispute | 5 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveWalletDispute, setWalletIntegrationMapping, withdrawWalletDispute. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management (Block A completion); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#resolveWalletDispute`, `wallet#setWalletIntegrationMapping`, `wallet#withdrawWalletDispute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WALLET-WALLET-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] WalletService: diffWalletConfigurationVersion, getWalletFundingRules, getWalletRefundPolicy, getWalletRiskRules | 5 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-2 PLATFORM-KERNEL SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-5 SVC-WALLET-WALLET-7 SVC-WALLET-WALLET-9 | Operations: diffWalletConfigurationVersion, getWalletFundingRules, getWalletRefundPolicy, getWalletRiskRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#diffWalletConfigurationVersion`, `wallet#getWalletFundingRules`, `wallet#getWalletRefundPolicy`, `wallet#getWalletRiskRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-10 | AM-WALLET-CASHLESS-API-BLOCK-A | [DB] Forward migration V1240__wallet.sql: wallet for Wallet & Cashless · API only (Block A) (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.exit_settlement. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.exit_settlement: rename column amount to settled_amount, foreign key exit_settlement_wallet_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.exit_settlement` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-14 | AM-WALLET-CASHLESS-API-BLOCK-A | [DB] Forward migration V1211__payments.sql: payments for Payments · Venue Management 2 of 3 (3 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.authentication_policy, payments.hosted_checkout, payments.stored_forward. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.stored_forward: rename column amount to transaction_amount); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.authentication_policy`, `payments.hosted_checkout`, `payments.stored_forward` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 3 | SVC-WALLET-RETAIL-1 | AM-WALLET-CASHLESS-API-BLOCK-A | [BE] WalletService: getWalletAutoReloadSetting, getWalletExitBalance, setWalletAutoReloadSetting, settleWalletAtExit | 8 | Pranay Shinde | WalletService | MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-14 MIG-PLATFORM MIG-WALLET MIG-WALLET-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getWalletAutoReloadSetting, getWalletExitBalance, setWalletAutoReloadSetting, settleWalletAtExit. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · API only (Block A); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#getWalletAutoReloadSetting`, `wallet#getWalletExitBalance`, `wallet#setWalletAutoReloadSetting`, `wallet#settleWalletAtExit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-2 | AM-ADMISSION-ACCESS-P01 | [BE] AccessService: enrolFaceTag, getEntitlement, getEntitlementCredential, getEntitlementHistory | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: enrolFaceTag, getEntitlement, getEntitlementCredential, getEntitlementHistory. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#enrolFaceTag`, `access#getEntitlement`, `access#getEntitlementCredential`, `access#getEntitlementHistory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ACCESS-GENERAL-1 | AM-ADMISSION-ACCESS-P01 | [BE] AccessService: getParkingEntitlement | 1 | Chinmay Patkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-7 | Operations: getParkingEntitlement. Spec: handoff/service-docs/backend/AccessService.md#group-general Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#getParkingEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-1 | AM-ADMISSION-ACCESS-P02 | [BE] AccessService: approveManualOverrideSupervisor, bindCredentialDevice, deleteAccessPointGroup, enrolFacePass | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: approveManualOverrideSupervisor, bindCredentialDevice, deleteAccessPointGroup, enrolFacePass. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#approveManualOverrideSupervisor`, `access#bindCredentialDevice`, `access#deleteAccessPointGroup`, `access#enrolFacePass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-MARKETING-CONSENT-2 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: getGuestConsents, listConsentAnswers, listConsentPurposes, listConsentQuestions | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 | Operations: getGuestConsents, listConsentAnswers, listConsentPurposes, listConsentQuestions. Spec: handoff/service-docs/backend/MarketingService.md#group-consent. Done when `marketing-crm#getGuestConsents`, `marketing-crm#listConsentAnswers`, `marketing-crm#listConsentPurposes`, `marketing-crm#listConsentQuestions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ACCESS-ACCESS-3 | AM-WHITE-LABEL-P01 | [BE] AccessService: getFacePassEnrolment, listEntitlements, listMyEntitlements, listParkingFacilities | 8 | Pranay Shinde | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-PII PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-PRODUCT-4 SVC-IDENTITY-IDENTITY-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 | Operations: getFacePassEnrolment, listEntitlements, listMyEntitlements, listParkingFacilities. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#getFacePassEnrolment`, `access#listEntitlements`, `access#listMyEntitlements`, `access#listParkingFacilities` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ORDER-DRAFTED-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] OrderService: listGroupArrivalCheck | 1 | Chinmay Patkar | OrderService | MIG-ACCESS MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 | Operations: listGroupArrivalCheck. Spec: handoff/service-docs/backend/OrderService.md#group-drafted Helper task: Pranay Shinde owns the service and reviews. Done when `orders#listGroupArrivalCheck` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-PLATFORM-3 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [DB] Forward migration V1241__sync.sql: sync for Platform Operations · Scanner (2 tables) | 2 | Hrushikant Patkar | CrossRegionService | MIG-ACCESS MIG-BASELINE MIG-ORDERS MIG-PLATFORM MIG-SYNC MIG-WALLET | Tables: sync.cross_region_entitlement, sync.wallet_authorisation. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: sync.cross_region_entitlement: move table platform.cross_region_entitlement to sync, rename column ticket_id to entitlement_id, rename index cross_region_entitlement_ticket_id_idx to cross_region_entitlement_entitlement_id_idx, rename constraint cross_region_entitlement_ticket_id_fkey to cross_region_entitlement_entitlement_id_fkey; sync.wallet_authorisation: move table platform.wallet_authorisation to sync, rename column wallet_hold_id to fund_reservation_id, rename index wallet_authorisation_wallet_hold_id_idx to wallet_authorisation_fund_reservation_id_idx, rename constraint wallet_authorisation_wallet_hold_id_fkey to wallet_authorisation_fund_reservation_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (sync.wallet_authorisation: column share_percentage); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: sync.wallet_authorisation: drop index wallet_authorisation_authorisation_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `sync.cross_region_entitlement`, `sync.wallet_authorisation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 2 | VM-ACCESS-SYNC-1 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] AccessService: getOfflinePackage, listScans, syncScans | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-PLATFORM MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations beyond the first release: getOfflinePackage, listScans, syncScans. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Done when `access#getOfflinePackage`, `access#listScans`, `access#syncScans` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-VALIDATION-1 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] AccessService: lookupTicket, overrideAccess, validateAccess, validateGroupAccess | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations beyond the first release: lookupTicket, overrideAccess, validateAccess, validateGroupAccess. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Done when `access#lookupTicket`, `access#overrideAccess`, `access#validateAccess`, `access#validateGroupAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-REDEMPTION-2 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] CrossRegionService: consumeCrossRegionEntitlement | 2 | Deep Khanvilkar | CrossRegionService | MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: consumeCrossRegionEntitlement. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Admission & Access · Scanner (Block A); additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#consumeCrossRegionEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
4 | 2 | VM-MIG-ACCREDITATION | AM-ADMISSION-ACCESS-P08-BLOCK-A | [DB] Forward migration V1041__accreditation.sql: accreditation for Venue Management (4 tables) | 3 | Hrushikant Patkar |  | MIG-BASELINE | Tables: accreditation.application, accreditation.credential, accreditation.holder, accreditation.validity. Source DDL: backend/tenant/010-accreditation.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (accreditation.holder: columns status_effective_from and status_review_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: accreditation.application: foreign key application_programme_id_fkey; accreditation.credential: foreign key credential_holder_id_fkey, foreign key mobile_credential_delivery_credential_id_fkey (from accreditation.mobile_credential_delivery); accreditation.holder: foreign key accreditation_credential_holder_id_fkey (from access.accreditation_credential), foreign key credential_holder_id_fkey (from accreditation.credential); accreditation.validity: rename column renewal_requires_reverification to requires_renewal_reverification); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key accreditation_credential_holder_id_fkey here** (access.accreditation_credential to accreditation.holder, guarded): VM-MIG-ACCESS creates access.accreditation_credential before accreditation.holder exists. **Leave out the key application_programme_id_fkey** (accreditation.application to accreditation.programme): MIG-ACCREDITATION-4 creates accreditation.programme later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.application`, `accreditation.credential`, `accreditation.holder`, `accreditation.validity` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
5 | 3 | MIG-ACCREDITATION-3 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [DB] Forward migration V1043__accreditation.sql: accreditation for Ticketing · Venue Management 8 of 8 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.access_profile. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.access_profile` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
5 | 3 | MIG-ACCREDITATION-4 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [DB] Forward migration V1044__accreditation.sql: accreditation for Admission & Access · Scanner (Block A) (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.holder_access, accreditation.programme. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (accreditation.programme: column categories, index programme_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: accreditation.programme: foreign key application_programme_id_fkey (from accreditation.application)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key application_programme_id_fkey here** (accreditation.application to accreditation.programme, guarded): VM-MIG-ACCREDITATION creates accreditation.application before accreditation.programme exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.holder_access`, `accreditation.programme` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 2 | VM-MIG-REPORTING | AM-ADMISSION-ACCESS-P08-BLOCK-A | [DB] Forward migration V1048__reporting.sql: reporting for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-REPORTING | Tables: reporting.kpi_target, reporting.schedule_recipient. Source DDL: backend/tenant/010-reporting.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `reporting.kpi_target`, `reporting.schedule_recipient` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-ACCESS-5 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [DB] Forward migration V1148__access.sql: access for Admission & Access · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.hardware_certification. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.hardware_certification: foreign key hardware_certification_model_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Leave out the key hardware_certification_model_id_fkey** (access.hardware_certification to access.hardware_model): MIG-ACCESS-8 creates access.hardware_model later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.hardware_certification` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 2 | VM-ORDER-ORDERS-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] OrderService: assignChargeback, authoriseStoredValue, captureStoredValue, createGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PII MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS VM-MIG-PROMOTIONS | Operations beyond the first release: assignChargeback, authoriseStoredValue, captureStoredValue, createGroupBooking. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `orders#assignChargeback`, `orders#authoriseStoredValue`, `orders#captureStoredValue`, `orders#createGroupBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-ORDERS-3 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] OrderService: relinquishStoredValue, updateGroupBooking | 3 | Sanket Keluskar | OrderService | MIG-ORDERS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations beyond the first release: relinquishStoredValue, updateGroupBooking. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#relinquishStoredValue`, `orders#updateGroupBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-ACCESSPOINT-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: listAccessPoints | 2 | Chinmay Patkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 | Operations beyond the first release: listAccessPoints. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#listAccessPoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 2 | VM-ACCESS-GENERAL-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A-COMPLETION | [BE] AccessService: getPdfPrintablePos | 1 | Chinmay Patkar | AccessService | PLATFORM-KERNEL SVC-ACCESS-ACCESS-9 VM-ACCESS-ACCESS-1 VM-MIG-ACCESS | Operations beyond the first release: getPdfPrintablePos. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#getPdfPrintablePos` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-VALIDATION-2 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: issueOrderEntitlements | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: issueOrderEntitlements. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#issueOrderEntitlements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-VALIDATION-3 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: recordQueueRedemptionUse | 1 | Narayan Gaonkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordQueueRedemptionUse. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#recordQueueRedemptionUse` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-18 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listFeeSurcharge, listFeeWaiverTax, listPriceCalculationSequence, listPricingChangeImpact | 8 | New full-stack developer 2 | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listFeeSurcharge, listFeeWaiverTax, listPriceCalculationSequence, listPricingChangeImpact. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listFeeSurcharge`, `catalogue#listFeeWaiverTax`, `catalogue#listPriceCalculationSequence`, `catalogue#listPricingChangeImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-11 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: createParkingEntitlement, getHardwareModelCertification, listAccessChanges, listEntryExitRule | 5 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-5 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: createParkingEntitlement, getHardwareModelCertification, listAccessChanges, listEntryExitRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#createParkingEntitlement`, `access#getHardwareModelCertification`, `access#listAccessChanges`, `access#listEntryExitRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-12 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: listEntryTemporaryExit, setHardwareModelCertification, setVirtualTicketCredential, verifyIdentity | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-5 MIG-CATALOGUE MIG-ORDERS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listEntryTemporaryExit, setHardwareModelCertification, setVirtualTicketCredential, verifyIdentity. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listEntryTemporaryExit`, `access#setHardwareModelCertification`, `access#setVirtualTicketCredential`, `access#verifyIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-RETAIL-RETAIL-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] RetailService: disposeShopAndDrop | 2 | Sanket Keluskar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: disposeShopAndDrop. Additive to RetailService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `retail#disposeShopAndDrop` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-FNB-MENU-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] FnbService: getMenu, setMenuItemDailyCount | 3 | Sanket Keluskar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getMenu, setMenuItemDailyCount. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#getMenu`, `fnb#setMenuItemDailyCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-LEDGER-1 | AM-FINANCE-TAX-P01 | [BE] LedgerService: listFxRates, setFxRate | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listFxRates, setFxRate. Spec: handoff/service-docs/backend/LedgerService.md#group-ledger Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#listFxRates`, `finance#setFxRate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-LEDGER-2 | AM-FINANCE-TAX-P08-BLOCK-A | [DB] Forward migration V1032__ledger.sql: ledger for Finance & Tax · Venue Management (Block A) (2 tables) | 2 | Hrushikant Patkar | LedgerService | MIG-ACCESS MIG-BASELINE MIG-LEDGER MIG-ORDERS VM-MIG-LEDGER | Tables: ledger.inter_entity_obligation, ledger.tax_exemption. Source DDL: backend/tenant/010-ledger.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ledger.inter_entity_obligation: row-level security apply_parent_split_rls; ledger.tax_exemption: column scope_path, index tax_exemption_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ledger.inter_entity_obligation: foreign key inter_entity_obligation_from_legal_entity_id_fkey, foreign key inter_entity_obligation_to_legal_entity_id_fkey; ledger.tax_exemption: rename column evidence_document_id to evidence_asset_id, rename index tax_exemption_evidence_document_id_idx to tax_exemption_evidence_asset_id_idx, foreign key tax_exemption_evidence_asset_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `ledger.tax_exemption.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ledger.inter_entity_obligation`, `ledger.tax_exemption` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 2 | VM-LEDGER-LEDGER-1 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: abandonPeriodClose, beginPeriodClose, getTrialBalance, listLedgerEntries | 5 | Deep Khanvilkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: abandonPeriodClose, beginPeriodClose, getTrialBalance, listLedgerEntries. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Done when `finance#abandonPeriodClose`, `finance#beginPeriodClose`, `finance#getTrialBalance`, `finance#listLedgerEntries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-FINANCE-3 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: disputeObligation, recordWriteOff, resolveObligationDispute | 8 | Pranay Shinde | LedgerService | MIG-CONTROL MIG-LEDGER MIG-LEDGER-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: disputeObligation, recordWriteOff, resolveObligationDispute. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#disputeObligation`, `finance#recordWriteOff`, `finance#resolveObligationDispute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-LEDGER-3 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: listInterEntityObligations, postOrderRevenue, runFxRevaluation | 8 | Surendra | LedgerService | MIG-LEDGER MIG-LEDGER-2 MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listInterEntityObligations, postOrderRevenue, runFxRevaluation. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#listInterEntityObligations`, `finance#postOrderRevenue`, `finance#runFxRevaluation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-TAX-4 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: calculateTax, recordEInvoiceTransmissionStatus | 5 | Deep Khanvilkar | LedgerService | MIG-CATALOGUE-5 MIG-LEDGER MIG-LEDGER-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: calculateTax, recordEInvoiceTransmissionStatus. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#calculateTax`, `finance#recordEInvoiceTransmissionStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-LEDGER-FISCAL-1 | AM-FINANCE-TAX-API-BLOCK-A-COMPLETION | [BE] LedgerService: closeFiscalPeriod, listFiscalPeriods | 5 | Sanket Keluskar | LedgerService | MIG-APPROVALS MIG-LEDGER MIG-ORDERS MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX SVC-WALLET-WALLET-12 VM-MIG-LEDGER | Operations beyond the first release: closeFiscalPeriod, listFiscalPeriods. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Done when `finance#closeFiscalPeriod`, `finance#listFiscalPeriods` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-LEDGER-RECOGNITION-1 | AM-FINANCE-TAX-API-BLOCK-A-COMPLETION | [BE] LedgerService: createRecognitionSchedule, getDeferredRevenue, listRecognitionSchedules, runRecognition | 8 | Narayan Gaonkar | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: createRecognitionSchedule, getDeferredRevenue, listRecognitionSchedules, runRecognition. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Done when `finance#createRecognitionSchedule`, `finance#getDeferredRevenue`, `finance#listRecognitionSchedules`, `finance#runRecognition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-LEDGER-FINANCE-5 | AM-FINANCE-TAX-API-BLOCK-A-COMPLETION | [BE] LedgerService: getUnifiedReconciliation | 2 | Narayan Gaonkar | LedgerService | MIG-LEDGER MIG-ORDERS MIG-WALLET PLATFORM-KERNEL SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-8 VM-LEDGER-FINANCE-1 VM-LEDGER-RECOGNITION-1 VM-LEDGER-SETTLEMENT-1 VM-MIG-LEDGER VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 VM-WALLET-WALLET-1 | Operations: getUnifiedReconciliation. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · API only (Block A completion); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#getUnifiedReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-ROTA-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] TenancyService: createRotaAssignment, listRotaAssignments, updateRotaAssignment | 8 | Pranay Shinde | TenancyService | MIG-IDENTITY MIG-PLATFORM MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRotaAssignment, listRotaAssignments, updateRotaAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-rota. Done when `workforce#createRotaAssignment`, `workforce#listRotaAssignments`, `workforce#updateRotaAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-5 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] AccessService: setCredentialActivationDisplay, setDeviceBindingPolicy, setFaceMatchingVerification, setFacePassEnrollment | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCredentialActivationDisplay, setDeviceBindingPolicy, setFaceMatchingVerification, setFacePassEnrollment. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#setCredentialActivationDisplay`, `access#setDeviceBindingPolicy`, `access#setFaceMatchingVerification`, `access#setFacePassEnrollment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-INSPECTION-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: createInspectionTemplate | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createInspectionTemplate. Spec: handoff/service-docs/backend/VenueOpsService.md#group-inspection Helper task: Narayan Gaonkar owns the service and reviews. Done when `maintenance#createInspectionTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-RESOURCES-4 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: setExperienceResourceRequirements, setResourceLifecycleState, setResourceSchedule, updateResource | 8 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setExperienceResourceRequirements, setResourceLifecycleState, setResourceSchedule, updateResource. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources. Done when `resources#setExperienceResourceRequirements`, `resources#setResourceLifecycleState`, `resources#setResourceSchedule`, `resources#updateResource` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-RESOURCES-5 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: updateResourcePackage | 3 | Sanket Keluskar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateResourcePackage. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources Helper task: Narayan Gaonkar owns the service and reviews. Done when `resources#updateResourcePackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-RESOURCES-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: cloneResource, createResource, createResourceBlock, createResourceHold | 8 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cloneResource, createResource, createResourceBlock, createResourceHold. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources. Done when `resources#cloneResource`, `resources#createResource`, `resources#createResourceBlock`, `resources#createResourceHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-VENUEOPS-FEED-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: configureQueueFeed, getQueueFeedHealth, listQueueFeeds, testQueueFeed | 5 | Narayan Gaonkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-QUEUE | Operations: configureQueueFeed, getQueueFeedHealth, listQueueFeeds, testQueueFeed. Spec: contracts (queue) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `queue#configureQueueFeed`, `queue#getQueueFeedHealth`, `queue#listQueueFeeds`, `queue#testQueueFeed` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 2 | VM-MIG-RESOURCES | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1015__resources.sql: resources for Venue Management (3 tables) | 2 | Hrushikant Patkar |  | MIG-RESOURCES | Tables: resources.performance_participant, resources.qualification, resources.selection_policy. Source DDL: backend/tenant/010-resources.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (resources.performance_participant: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (resources.performance_participant: row-level security apply_parent_across_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: resources.performance_participant: foreign key performance_participant_performance_id_fkey, foreign key performance_participant_subject_id_fkey; resources.selection_policy: rename column ticket_type_id to ticket_product_id, rename index selection_policy_ticket_type_id_idx to selection_policy_ticket_product_id_idx, foreign key selection_policy_ticket_product_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `resources.performance_participant`, `resources.qualification`, `resources.selection_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 2 | VM-MIG-MAINTENANCE | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1037__maintenance.sql: maintenance for Venue Management (9 tables) | 5 | Hrushikant Patkar |  | MIG-MAINTENANCE | Tables: maintenance.asset_document, maintenance.asset_status_change, maintenance.incident_authority_notification, maintenance.incident_history, maintenance.incident_investigation_note, maintenance.incident_involved_party, maintenance.preventive_plan, maintenance.priority_scoring_model, maintenance.vendor_service_request. Source DDL: backend/tenant/010-maintenance.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (maintenance.asset_document: row-level security apply_parent_rls; maintenance.asset_status_change: row-level security apply_parent_rls; maintenance.incident_authority_notification: row-level security apply_parent_rls; maintenance.incident_history: row-level security apply_parent_rls; maintenance.incident_investigation_note: row-level security apply_parent_rls; maintenance.incident_involved_party: row-level security apply_parent_rls; maintenance.priority_scoring_model: column bands); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: maintenance.asset_document: foreign key asset_document_asset_id_fkey; maintenance.asset_status_change: foreign key asset_status_change_asset_id_fkey; maintenance.incident_authority_notification: foreign key incident_authority_notification_incident_id_fkey; maintenance.incident_history: foreign key incident_history_incident_id_fkey, foreign key incident_history_principal_id_fkey; maintenance.incident_investigation_note: foreign key incident_investigation_note_incident_id_fkey; maintenance.incident_involved_party: foreign key incident_involved_party_incident_id_fkey; maintenance.vendor_service_request: foreign key vendor_service_request_supplier_id_fkey, foreign key vendor_service_request_work_order_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `maintenance.priority_scoring_model.bands`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `maintenance.asset_document`, `maintenance.asset_status_change`, `maintenance.incident_authority_notification`, `maintenance.incident_history`, `maintenance.incident_investigation_note`, `maintenance.incident_involved_party`, `maintenance.preventive_plan`, `maintenance.priority_scoring_model` and 1 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
8 | 3 | MIG-RESOURCES-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1161__resources.sql: resources for Venue Operations · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.resource_type. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (resources.resource_type: index resource_type_code_uniq, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `resources.resource_type` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | MIG-MAINTENANCE-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1134__maintenance.sql: maintenance for Venue Operations · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-MAINTENANCE VM-MIG-MAINTENANCE | Tables: maintenance.inspection_item. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `maintenance.inspection_item` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-INSPECTION-2 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: listInspectionTemplates, listInspections, submitInspection | 5 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE MIG-MAINTENANCE-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listInspectionTemplates, listInspections, submitInspection. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#listInspectionTemplates`, `maintenance#listInspections`, `maintenance#submitInspection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WORKFORCE-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1059__workforce.sql: workforce for Venue Operations · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.shift_swap. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: workforce.shift_swap: foreign key shift_swap_from_principal_id_fkey, foreign key shift_swap_to_principal_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.shift_swap` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-ACCESS-8 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1150__access.sql: access for Admission & Access · Venue Management 3 of 8 (6 tables) | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_point_configuration, access.device_configuration, access.edge_node, access.edge_package, access.gate_outcome_profile, access.hardware_model. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (access.hardware_model: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.access_point_configuration: foreign key access_point_configuration_venue_id_access_point_id_fkey, foreign key access_point_configuration_venue_id_fkey; access.device_configuration: rename column offline_capability to supports_offline, rename column biometric_capability to supports_biometric, foreign key device_configuration_venue_id_fkey; access.edge_node: foreign key edge_node_venue_id_fkey; access.edge_package: rename column signature_valid to is_signature_valid, rename column package_complete to is_package_complete, rename column version_valid to is_version_valid, foreign key edge_package_venue_id_fkey; access.gate_outcome_profile: foreign key gate_outcome_profile_venue_id_fkey; access.hardware_model: rename column offline_capability to supports_offline, rename column screen_capability to supports_screen, rename column sound_capability to supports_sound, rename column light_capability to supports_light, rename column relay_controller_support to supports_relay_controller, rename column payment_capability to supports_payment, foreign key hardware_certification_model_id_fkey (from access.hardware_certification)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key hardware_certification_model_id_fkey here** (access.hardware_certification to access.hardware_model, guarded): MIG-ACCESS-5 creates access.hardware_certification before access.hardware_model exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.access_point_configuration`, `access.device_configuration`, `access.edge_node`, `access.edge_package`, `access.gate_outcome_profile`, `access.hardware_model` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ROTA-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] TenancyService: requestShiftSwap | 2 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-IDENTITY MIG-WORKFORCE MIG-WORKFORCE-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestShiftSwap. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#requestShiftSwap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-ACCESS-58 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: cancelGateModeChange, listAccessLocationGrouping, listCredentialActivationDisplay, listDeviceBindingSession | 5 | Sanket Keluskar | AccessService | MIG-ACCESS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelGateModeChange, listAccessLocationGrouping, listCredentialActivationDisplay, listDeviceBindingSession. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#cancelGateModeChange`, `access#listAccessLocationGrouping`, `access#listCredentialActivationDisplay`, `access#listDeviceBindingSession` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-ACCESSPOINT-3 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: getAccessPoint, listAdmissionRules, listBlacklist, removeBlacklistEntry | 8 | Pranay Shinde | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAccessPoint, listAdmissionRules, listBlacklist, removeBlacklistEntry. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getAccessPoint`, `access#listAdmissionRules`, `access#listBlacklist`, `access#removeBlacklistEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-60 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: listLiveGateMode, listVisualAccessRules, releaseCredentialDevice, setEntryRulePoints | 5 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listLiveGateMode, listVisualAccessRules, releaseCredentialDevice, setEntryRulePoints. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listLiveGateMode`, `access#listVisualAccessRules`, `access#releaseCredentialDevice`, `access#setEntryRulePoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-59 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: listEntryRulePoints, listFaceMatchingVerification, listFaceTagTemporary, listGateModeFree | 3 | Narayan Gaonkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-7 | Operations: listEntryRulePoints, listFaceMatchingVerification, listFaceTagTemporary, listGateModeFree. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listEntryRulePoints`, `access#listFaceMatchingVerification`, `access#listFaceTagTemporary`, `access#listGateModeFree` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-GENERAL-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: getBiometricVerificationProfile, getBleBeaconGeofence, getFacePassEnrollmentConfiguration, getVirtualTicketIdentity | 3 | Narayan Gaonkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 | Operations: getBiometricVerificationProfile, getBleBeaconGeofence, getFacePassEnrollmentConfiguration, getVirtualTicketIdentity. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getBiometricVerificationProfile`, `access#getBleBeaconGeofence`, `access#getFacePassEnrollmentConfiguration`, `access#getVirtualTicketIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-FINANCE-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] LedgerService: ingestFxRates, setFxProvider | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: ingestFxRates, setFxProvider. Spec: handoff/service-docs/backend/LedgerService.md#group-finance Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#ingestFxRates`, `finance#setFxProvider` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-FISCAL-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] LedgerService: createLegalEntity | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createLegalEntity. Spec: handoff/service-docs/backend/LedgerService.md#group-fiscal Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#createLegalEntity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-TAX-3 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] LedgerService: transmitEInvoices, updateTaxCode | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: transmitEInvoices, updateTaxCode. Spec: handoff/service-docs/backend/LedgerService.md#group-tax Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#transmitEInvoices`, `finance#updateTaxCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-CATALOGUE-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] ReportingService: createReport, deleteReport, getReport, listReports | 8 | Narayan Gaonkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createReport, deleteReport, getReport, listReports. Spec: handoff/service-docs/backend/ReportingService.md#group-catalogue. Done when `reporting#createReport`, `reporting#deleteReport`, `reporting#getReport`, `reporting#listReports` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-CATALOGUE-2 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] ReportingService: updateReport | 3 | Sanket Keluskar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateReport. Spec: handoff/service-docs/backend/ReportingService.md#group-catalogue Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#updateReport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-LEDGER-VARIANCE-1 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listPriceVariances, reviewPriceVariance | 3 | Deep Khanvilkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPriceVariances, reviewPriceVariance. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#listPriceVariances`, `finance#reviewPriceVariance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-56 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] CatalogueService: listCalculationValidationReconciliation, setTaxProfileJurisdiction | 3 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-5 MIG-CATALOGUE-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCalculationValidationReconciliation, setTaxProfileJurisdiction. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listCalculationValidationReconciliation`, `catalogue#setTaxProfileJurisdiction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listDemandBookingCurve, listDynamicPricingStrategy, listRevenue, simulatePriceBreakdownCalculation | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-5 MIG-CATALOGUE-6 MIG-ORDERS MIG-PRICING-2 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listDemandBookingCurve, listDynamicPricingStrategy, listRevenue, simulatePriceBreakdownCalculation. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listDemandBookingCurve`, `catalogue#listDynamicPricingStrategy`, `catalogue#listRevenue`, `catalogue#simulatePriceBreakdownCalculation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-LEDGER-ACCOUNTS-1 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: createAccount, createCostCenter, getAccount, listAccountMappings | 5 | New full-stack developer 1 | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: createAccount, createCostCenter, getAccount, listAccountMappings. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#createAccount`, `finance#createCostCenter`, `finance#getAccount`, `finance#listAccountMappings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-LEDGER-ACCOUNTS-2 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listAccounts, listCostCenters, setAccountMappings, updateAccount | 5 | Pranay Shinde | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: listAccounts, listCostCenters, setAccountMappings, updateAccount. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#listAccounts`, `finance#listCostCenters`, `finance#setAccountMappings`, `finance#updateAccount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-LEDGER-FISCAL-2 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listLegalEntities | 1 | Narayan Gaonkar | LedgerService | MIG-LEDGER PLATFORM-KERNEL SVC-LEDGER-FISCAL-1 | Operations: listLegalEntities. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#listLegalEntities` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-GENERAL-2 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] CatalogueService: getTaxProfileJurisdiction | 1 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE-5 PLATFORM-KERNEL SVC-CATALOGUE-DRAFTED-56 | Operations: getTaxProfileJurisdiction. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getTaxProfileJurisdiction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-TAX-5 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: createTaxExemption, listEInvoiceTransmissions, listEInvoicingProviders, listTaxCodes | 5 | Surendra | LedgerService | MIG-LEDGER MIG-LEDGER-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTaxExemption, listEInvoiceTransmissions, listEInvoicingProviders, listTaxCodes. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#createTaxExemption`, `finance#listEInvoiceTransmissions`, `finance#listEInvoicingProviders`, `finance#listTaxCodes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-TAX-6 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listTaxExemptions, listTaxInvoiceTemplates, setTaxInvoiceTemplate, verifyTaxExemption | 8 | Surendra | LedgerService | MIG-LEDGER MIG-LEDGER-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTaxExemptions, listTaxInvoiceTemplates, setTaxInvoiceTemplate, verifyTaxExemption. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#listTaxExemptions`, `finance#listTaxInvoiceTemplates`, `finance#setTaxInvoiceTemplate`, `finance#verifyTaxExemption` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-DASHBOARD-2 | AM-SETUP-FINANCE-INSIGHTS-P16 | [BE] ReportingService: updateDashboard | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateDashboard. Spec: handoff/service-docs/backend/ReportingService.md#group-dashboard Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#updateDashboard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-REPORTING-2 | AM-SETUP-FINANCE-INSIGHTS-P16 | [BE] ReportingService: setSemanticModel | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSemanticModel. Spec: handoff/service-docs/backend/ReportingService.md#group-reporting Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#setSemanticModel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-FAVOURITE-1 | AM-TRANSPORT-P01 | [BE] VenueOpsService: deleteFavouriteRoute, listMyFavouriteRoutes, saveFavouriteRoute | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteFavouriteRoute, listMyFavouriteRoutes, saveFavouriteRoute. Spec: handoff/service-docs/backend/VenueOpsService.md#group-favourite Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#deleteFavouriteRoute`, `transport#listMyFavouriteRoutes`, `transport#saveFavouriteRoute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-VENUEOPS-GENERAL-1 | AM-TRANSPORT-P02 | [BE] VenueOpsService: getTransportDeparture | 1 | Chinmay Patkar | VenueOpsService | MIG-CATALOGUE MIG-TRANSPORT PLATFORM-KERNEL SVC-CATALOGUE-EVENTS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-DEPARTURE-1 SVC-VENUEOPS-FARE-1 SVC-VENUEOPS-NETWORKIMPORT-1 SVC-VENUEOPS-ROUTE-2 SVC-VENUEOPS-STATION-1 SVC-VENUEOPS-TIMETABLE-1 | Operations: getTransportDeparture. Spec: handoff/service-docs/backend/VenueOpsService.md#group-general Helper task: Narayan Gaonkar owns the service and reviews. Done when `transport#getTransportDeparture` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-1 | AM-FOOD-BEVERAGE-P01 | [BE] FnbService: attachModifierGroup, buildProductionPlan, chaseStation, createTableReservation | 8 | Narayan Gaonkar | FnbService | MIG-AI MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: attachModifierGroup, buildProductionPlan, chaseStation, createTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#attachModifierGroup`, `fnb#buildProductionPlan`, `fnb#chaseStation`, `fnb#createTableReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-3 | AM-FOOD-BEVERAGE-P01 | [BE] FnbService: getHaccpStatus, getKitchenSla, holdCourse, joinRestaurantWaitlist | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getHaccpStatus, getKitchenSla, holdCourse, joinRestaurantWaitlist. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#getHaccpStatus`, `fnb#getKitchenSla`, `fnb#holdCourse`, `fnb#joinRestaurantWaitlist` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-CASH-1 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: createCashMovement, listCashMovements | 5 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCashMovement, listCashMovements. Spec: handoff/service-docs/backend/OrderService.md#group-cash. Done when `shift#createCashMovement`, `shift#listCashMovements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-5 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: resumeShift, setDenominations, setTillShiftPolicy, submitShiftCount | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: resumeShift, setDenominations, setTillShiftPolicy, submitShiftCount. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#resumeShift`, `shift#setDenominations`, `shift#setTillShiftPolicy`, `shift#submitShiftCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-6 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: suspendShift, withdrawFromDepositBox | 8 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: suspendShift, withdrawFromDepositBox. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#suspendShift`, `shift#withdrawFromDepositBox` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-SHIFT-2 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: getCurrentShift, getShiftCountLines, getTillShiftPolicy, getWorkstationShift | 8 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-CASH-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 | Operations: getCurrentShift, getShiftCountLines, getTillShiftPolicy, getWorkstationShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#getCurrentShift`, `shift#getShiftCountLines`, `shift#getTillShiftPolicy`, `shift#getWorkstationShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-BILL-1 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: closeTableVisit, getBill, splitBill | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeTableVisit, getBill, splitBill. Spec: handoff/service-docs/backend/FnbService.md#group-bill. Done when `fnb#closeTableVisit`, `fnb#getBill`, `fnb#splitBill` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-2 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: createTableReservationForGuest, escalateCorrectiveAction, fireCourse, getCourseRules | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTableReservationForGuest, escalateCorrectiveAction, fireCourse, getCourseRules. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#createTableReservationForGuest`, `fnb#escalateCorrectiveAction`, `fnb#fireCourse`, `fnb#getCourseRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-5 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: listTableReservations, logColdChain, logKitchenException, logTemperature | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTableReservations, logColdChain, logKitchenException, logTemperature. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#listTableReservations`, `fnb#logColdChain`, `fnb#logKitchenException`, `fnb#logTemperature` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-6 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: markOrderCollected, notifyServer, printOrderLabel, publishMenu | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-IDENTITY MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: markOrderCollected, notifyServer, printOrderLabel, publishMenu. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#markOrderCollected`, `fnb#notifyServer`, `fnb#printOrderLabel`, `fnb#publishMenu` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-8 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: requestBill, rollbackMenu, scheduleMenuPublish, seatTableReservation | 8 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestBill, rollbackMenu, scheduleMenuPublish, seatTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#requestBill`, `fnb#rollbackMenu`, `fnb#scheduleMenuPublish`, `fnb#seatTableReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-MENU-1 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: createMenu, setItemAvailability, setMenuSections, updateMenu | 8 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMenu, setItemAvailability, setMenuSections, updateMenu. Spec: handoff/service-docs/backend/FnbService.md#group-menu. Done when `fnb#createMenu`, `fnb#setItemAvailability`, `fnb#setMenuSections`, `fnb#updateMenu` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-7 | AM-FOOD-BEVERAGE-P15 | [BE] FnbService: rebalanceStationLoad, recallKitchenTicket, refireItem, releaseProductionPlan | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rebalanceStationLoad, recallKitchenTicket, refireItem, releaseProductionPlan. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#rebalanceStationLoad`, `fnb#recallKitchenTicket`, `fnb#refireItem`, `fnb#releaseProductionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-FNB-GUESTORDERING-2 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: getGuestBill, getGuestMenu, getGuestOrderStatus, listBookableOutlets | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-ORDERS PLATFORM-KERNEL SVC-FNB-BILL-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 | Operations: getGuestBill, getGuestMenu, getGuestOrderStatus, listBookableOutlets. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#getGuestBill`, `fnb#getGuestMenu`, `fnb#getGuestOrderStatus`, `fnb#listBookableOutlets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-INVENTORY-MOVEMENT-1 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] InventoryService: createStockMovement, listStockMovements | 3 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: createStockMovement, listStockMovements. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#createStockMovement`, `inventory#listStockMovements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-FNB-PRODUCTION-1 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: getWasteApprovalPolicy, listRecipes, recordWaste, setWasteApprovalPolicy | 5 | Narayan Gaonkar | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB | Operations beyond the first release: getWasteApprovalPolicy, listRecipes, recordWaste, setWasteApprovalPolicy. Additive to FnbService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#getWasteApprovalPolicy`, `fnb#listRecipes`, `fnb#recordWaste`, `fnb#setWasteApprovalPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-12 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: compItem, listCorrectiveActions, moveTableVisit, quoteWaitTime | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: compItem, listCorrectiveActions, moveTableVisit, quoteWaitTime. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#compItem`, `fnb#listCorrectiveActions`, `fnb#moveTableVisit`, `fnb#quoteWaitTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-48 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listBundleCombo, listPackageBundleAdd, listPromotionLifecycleStatus | 3 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-PRODUCT-1 | Operations: listBundleCombo, listPackageBundleAdd, listPromotionLifecycleStatus. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleCombo`, `catalogue#listPackageBundleAdd`, `promotions#listPromotionLifecycleStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-ORDER-DRAFTED-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: listPaymentReconciliationException, listTicketReissueFulfillment | 2 | Chinmay Patkar | OrderService | MIG-ACCESS MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-LEDGER VM-MIG-ORDERS | Operations beyond the first release: listPaymentReconciliationException, listTicketReissueFulfillment. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#listPaymentReconciliationException`, `orders#listTicketReissueFulfillment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-13 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: reassignServer, setServiceStage, transferOrderItems | 8 | Surendra | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: reassignServer, setServiceStage, transferOrderItems. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#reassignServer`, `fnb#setServiceStage`, `fnb#transferOrderItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-TABLE-3 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: mergeTableVisits | 3 | Surendra | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: mergeTableVisits. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#mergeTableVisits` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-FNB-3 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [DB] Forward migration V1034__fnb.sql: fnb for Food & Beverage · Staff App (1 tables) | 1 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.reservation_policy. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (fnb.reservation_policy: column turn_time_bands); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.reservation_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-FNB-4 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [DB] Forward migration V1035__fnb.sql: fnb for Food & Beverage · Venue Management (Block A) (3 tables) | 2 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.ingredient_substitute, fnb.prep_sheet_template, fnb.product_recommendation. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: fnb.product_recommendation: foreign key product_recommendation_source_product_id_fkey, drop index product_recommendation_target_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (fnb.ingredient_substitute: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: fnb.ingredient_substitute: foreign key ingredient_substitute_from_inventory_item_id_fkey, foreign key ingredient_substitute_to_inventory_item_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.ingredient_substitute`, `fnb.prep_sheet_template`, `fnb.product_recommendation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | VM-TENANCY-WORKSTATION-1 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] TenancyService: getWorkstation, listOutlets, listWorkstations, registerDevice | 8 | Pranay Shinde | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWorkstation, listOutlets, listWorkstations, registerDevice. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#getWorkstation`, `tenancy#listOutlets`, `tenancy#listWorkstations`, `tenancy#registerDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-ORDER-SHIFT-7 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] OrderService: adjustDepositBoxFloat, approveShiftClose | 5 | Narayan Gaonkar | OrderService | MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: adjustDepositBoxFloat, approveShiftClose. Spec: contracts (shift) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `shift#adjustDepositBoxFloat`, `shift#approveShiftClose` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-LEDGER-REPORTING-2 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: getForeignTenderReport | 1 | Deep Khanvilkar | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-KERNEL SVC-LEDGER-FINANCE-1 SVC-LEDGER-LEDGER-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SHIFT-7 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 | Operations: getForeignTenderReport. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#getForeignTenderReport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-FNB-ORDER-1 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: amendFnbOrder | 3 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: amendFnbOrder. Additive to FnbService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#amendFnbOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-16 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: applyMenuActions, closeCorrectiveAction, createTable, getAllergenVerification | 5 | Narayan Gaonkar | FnbService | MIG-CATALOGUE MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyMenuActions, closeCorrectiveAction, createTable, getAllergenVerification. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#applyMenuActions`, `fnb#closeCorrectiveAction`, `fnb#createTable`, `fnb#getAllergenVerification` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-FNB-GENERAL-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listSubstitutionRules | 1 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-KERNEL SVC-FNB-FNB-9 | Operations: listSubstitutionRules. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#listSubstitutionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-FNB-MODIFIER-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listModifierGroups | 1 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-KERNEL SVC-FNB-MODIFIER-1 | Operations: listModifierGroups. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#listModifierGroups` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-17 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listFnbRecommendations, listIngredientSubstitutes, recordCorrectiveAction, sendOrderNotification | 5 | Pranay Shinde | FnbService | MIG-FNB MIG-FNB-4 MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listFnbRecommendations, listIngredientSubstitutes, recordCorrectiveAction, sendOrderNotification. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#listFnbRecommendations`, `fnb#listIngredientSubstitutes`, `fnb#recordCorrectiveAction`, `fnb#sendOrderNotification` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-18 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: setFnbReservationPolicy, setIngredientSubstitutes, updateTable, verifyAllergens | 5 | Surendra | FnbService | MIG-FNB MIG-FNB-3 MIG-FNB-4 MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setFnbReservationPolicy, setIngredientSubstitutes, updateTable, verifyAllergens. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#setFnbReservationPolicy`, `fnb#setIngredientSubstitutes`, `fnb#updateTable`, `fnb#verifyAllergens` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-PRODUCTION-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: getPrepSheetTemplate, setPrepSheetTemplate | 2 | Sanket Keluskar | FnbService | MIG-FNB-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getPrepSheetTemplate, setPrepSheetTemplate. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#getPrepSheetTemplate`, `fnb#setPrepSheetTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
4 | 2 | VM-MIG-RENTAL | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [DB] Forward migration V1014__rental.sql: rental for Venue Management (2 tables) | 2 | Hrushikant Patkar |  | MIG-BASELINE | Tables: rental.booking, rental.participant. Source DDL: backend/tenant/010-rental.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (rental.booking: column change_reason; rental.participant: column scope_path, index participant_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: rental.booking: foreign key booking_deposit_authorisation_id_fkey, foreign key booking_product_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0115__names_after_r1_20261022.sql (the names the contracts use: rental.booking: change foreign key booking_deposit_authorisation_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Leave out the key booking_product_id_fkey** (rental.booking to rental.product): MIG-RENTAL-2 creates rental.product later and adds it. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `rental.participant.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `rental.booking`, `rental.participant` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-RESOURCES-2 | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [BE] VenueOpsService: getResourceBooking, getResourceQualifications, listResources, reorderPerformanceManifest | 3 | Deep Khanvilkar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: getResourceBooking, getResourceQualifications, listResources, reorderPerformanceManifest. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `resources#getResourceBooking`, `resources#getResourceQualifications`, `resources#listResources`, `resources#reorderPerformanceManifest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-VENUEOPS-RESOURCES-1 | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [BE] VenueOpsService: bookResource, checkInResource, checkOutResource, getPerformanceManifest | 8 | Narayan Gaonkar | VenueOpsService | MIG-MARKETING MIG-ORDERS MIG-PII MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: bookResource, checkInResource, checkOutResource, getPerformanceManifest. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `resources#bookResource`, `resources#checkInResource`, `resources#checkOutResource`, `resources#getPerformanceManifest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-RESOURCES-6 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] VenueOpsService: getExperienceResourceRequirements, getResource, getResourceSchedule, listResourceBlocks | 3 | Pranay Shinde | VenueOpsService | MIG-RESOURCES PLATFORM-KERNEL SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-2 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-RESOURCES-5 VM-VENUEOPS-RESOURCES-1 | Operations: getExperienceResourceRequirements, getResource, getResourceSchedule, listResourceBlocks. Spec: contracts (resources) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#getExperienceResourceRequirements`, `resources#getResource`, `resources#getResourceSchedule`, `resources#listResourceBlocks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-RESOURCES-7 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] VenueOpsService: listResourcePackages, suggestResources | 1 | Deep Khanvilkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-2 PLATFORM-KERNEL SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-2 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-RESOURCES-5 VM-VENUEOPS-RESOURCES-1 | Operations: listResourcePackages, suggestResources. Spec: contracts (resources) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#listResourcePackages`, `resources#suggestResources` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-RENTAL-1 | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [BE] VenueOpsService: getRentalBooking | 2 | Chinmay Patkar | VenueOpsService | PLATFORM-KERNEL VM-MIG-RENTAL | Operations beyond the first release: getRentalBooking. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `rental#getRentalBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-TENANCY-ATTENDANCE-1 | AM-WORKFORCE-P04 | [BE] TenancyService: recordAttendance | 2 | Chinmay Patkar | TenancyService | MIG-ACCESS MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordAttendance. Spec: handoff/service-docs/backend/TenancyService.md#group-attendance Helper task: Pranay Shinde owns the service and reviews. Done when `workforce#recordAttendance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-MAINTENANCE-4 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [DB] Forward migration V1165__maintenance.sql: maintenance for Maintenance & Safety · Staff App (Block A) (2 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-BASELINE MIG-MAINTENANCE VM-MIG-MAINTENANCE | Tables: maintenance.incident_media, maintenance.work_order_attachment. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (maintenance.incident_media: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: maintenance.incident_media: foreign key incident_media_incident_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `maintenance.incident_media`, `maintenance.work_order_attachment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-INCIDENT-1 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: getIncident, listIncidents, recordAuthorityNotification, reportIncident | 8 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: getIncident, listIncidents, recordAuthorityNotification, reportIncident. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#getIncident`, `maintenance#listIncidents`, `maintenance#recordAuthorityNotification`, `maintenance#reportIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-INCIDENT-2 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: updateIncident | 3 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: updateIncident. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `maintenance#updateIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-WORKORDER-2 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: listVendorServiceRequests, listWorkOrders, suggestWorkOrderAssignee, updateVendorServiceRequest | 8 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE VM-MIG-RESOURCES VM-MIG-WORKFORCE | Operations beyond the first release: listVendorServiceRequests, listWorkOrders, suggestWorkOrderAssignee, updateVendorServiceRequest. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#listVendorServiceRequests`, `maintenance#listWorkOrders`, `maintenance#suggestWorkOrderAssignee`, `maintenance#updateVendorServiceRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-VENUEOPS-MAINTENANCE-1 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: closeWorkOrder, pauseWorkOrder, rejectWorkOrder | 8 | Narayan Gaonkar | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: closeWorkOrder, pauseWorkOrder, rejectWorkOrder. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#closeWorkOrder`, `maintenance#pauseWorkOrder`, `maintenance#rejectWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-VENUEOPS-WORKORDER-1 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: completeWorkOrder, createVendorServiceRequest, createWorkOrder, getWorkOrder | 8 | Narayan Gaonkar | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-MAINTENANCE | Operations beyond the first release: completeWorkOrder, createVendorServiceRequest, createWorkOrder, getWorkOrder. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#completeWorkOrder`, `maintenance#createVendorServiceRequest`, `maintenance#createWorkOrder`, `maintenance#getWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-INCIDENT-3 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: addIncidentPerson, uploadIncidentMedia | 3 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations: addIncidentPerson, uploadIncidentMedia. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#addIncidentPerson`, `maintenance#uploadIncidentMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-MAINTENANCE-2 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: acceptWorkOrder, attachWorkOrderEvidence, resumeWorkOrder, startWorkOrder | 8 | Narayan Gaonkar | VenueOpsService | MIG-ASSETS MIG-MAINTENANCE MIG-MAINTENANCE-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: acceptWorkOrder, attachWorkOrderEvidence, resumeWorkOrder, startWorkOrder. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#acceptWorkOrder`, `maintenance#attachWorkOrderEvidence`, `maintenance#resumeWorkOrder`, `maintenance#startWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-INVENTORY-INVENTORY-3 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] InventoryService: createStockReservation, listStockReservations, releaseStockReservation | 3 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createStockReservation, listStockReservations, releaseStockReservation. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to InventoryService, whose first-release owner (Narayan Gaonkar) reviews. Done when `inventory#createStockReservation`, `inventory#listStockReservations`, `inventory#releaseStockReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-WORKORDER-4 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: recordWorkOrderParts, recordWorkOrderTime | 8 | Pranay Shinde | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordWorkOrderParts, recordWorkOrderTime. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#recordWorkOrderParts`, `maintenance#recordWorkOrderTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-ASSET-1 | AM-MAINTENANCE-SAFETY-P08-BLOCK-A | [BE] VenueOpsService: createAsset, getAsset, getAssetHistory, listAssets | 8 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: createAsset, getAsset, getAssetHistory, listAssets. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#createAsset`, `maintenance#getAsset`, `maintenance#getAssetHistory`, `maintenance#listAssets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-ASSET-2 | AM-MAINTENANCE-SAFETY-P08-BLOCK-A | [BE] VenueOpsService: lookupAsset, setAssetStatus, updateAsset | 8 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: lookupAsset, setAssetStatus, updateAsset. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#lookupAsset`, `maintenance#setAssetStatus`, `maintenance#updateAsset` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-WORKORDER-3 | AM-MAINTENANCE-SAFETY-P08-BLOCK-A | [BE] VenueOpsService: updateWorkOrder, verifyWorkOrder | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: updateWorkOrder, verifyWorkOrder. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `maintenance#updateWorkOrder`, `maintenance#verifyWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 2 | VM-MIG-GAMES | AM-GAMES-RIDES-P08-BLOCK-A | [DB] Forward migration V1039__games.sql: games for Venue Management (5 tables) | 3 | Hrushikant Patkar |  | MIG-GAMES | Tables: games.game, games.operational_config, games.play, games.pricing, games.reader_profile. Source DDL: backend/tenant/010-games.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (games.game: index game_venue_id_code_uniq; games.operational_config: column operating_hours; games.play: column scope_path, index play_scope_path_idx, row-level security apply_grant_holder_read_rls; games.pricing: columns group_pricing, peak_pricing and calendar_exceptions); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: games.game: foreign key pricing_exception_game_id_fkey (from games.pricing_exception)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `games.play.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `games.game`, `games.operational_config`, `games.play`, `games.pricing`, `games.reader_profile` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
7 | 3 | MIG-GAMES-2 | AM-GAMES-RIDES-P08-BLOCK-A | [DB] Forward migration V1040__games.sql: games for Games & Rides · Venue Management (Block A) (3 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES VM-MIG-GAMES | Tables: games.authorisation, games.reader, games.reader_sync_status. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (games.authorisation: column trace); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: games.authorisation: rename column decided_offline to was_decided_offline; games.reader: foreign key reader_device_id_fkey, foreign key reader_sync_status_reader_id_fkey (from games.reader_sync_status); games.reader_sync_status: foreign key reader_sync_status_reader_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `games.authorisation`, `games.reader`, `games.reader_sync_status` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-GAME-1 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: cloneGame, createGame, listGames, updateGame | 8 | Pranay Shinde | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations beyond the first release: cloneGame, createGame, listGames, updateGame. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Done when `games#cloneGame`, `games#createGame`, `games#listGames`, `games#updateGame` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-CARD-2 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: transferGameCard | 1 | Deep Khanvilkar | VenueOpsService | MIG-GAMES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferGameCard. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#transferGameCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-1 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: authoriseGameplay, reportReaderQueue | 3 | Pranay Shinde | VenueOpsService | MIG-GAMES-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: authoriseGameplay, reportReaderQueue. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#authoriseGameplay`, `games#reportReaderQueue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-PLAY-1 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: recordGamePlay, syncGamePlays | 5 | Pranay Shinde | VenueOpsService | MIG-GAMES MIG-GAMES-2 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: recordGamePlay, syncGamePlays. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#recordGamePlay`, `games#syncGamePlays` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-ENTRY-1 | AM-VIRTUAL-QUEUE-P01 | [BE] VenueOpsService: getWaitingGuest, joinQueue, leaveQueue | 5 | Narayan Gaonkar | VenueOpsService | MIG-MARKETING MIG-PROMOTIONS MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingGuest, joinQueue, leaveQueue. Spec: handoff/service-docs/backend/VenueOpsService.md#group-entry. Done when `queue#getWaitingGuest`, `queue#joinQueue`, `queue#leaveQueue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-VENUEOPS-WAITTIME-1 | AM-WHITE-LABEL-P02 | [BE] VenueOpsService: getWaitTimes | 1 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-KERNEL SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-QUEUE-1 | Operations: getWaitTimes. Spec: handoff/service-docs/backend/VenueOpsService.md#group-waittime Helper task: Narayan Gaonkar owns the service and reviews. Done when `queue#getWaitTimes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-QUEUE-1 | AM-VIRTUAL-QUEUE-P06-BLOCK-A | [BE] VenueOpsService: getQueue, setQueueStatus | 5 | Narayan Gaonkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: getQueue, setQueueStatus. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `queue#getQueue`, `queue#setQueueStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-WAITTIME-1 | AM-VIRTUAL-QUEUE-P06-BLOCK-A | [BE] VenueOpsService: setWaitTime | 2 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setWaitTime. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `queue#setWaitTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-ENTRY-1 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: callNextParties, listQueueEntries | 3 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: callNextParties, listQueueEntries. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `queue#callNextParties`, `queue#listQueueEntries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-ENTRY-2 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: listMyWaitingGuests, overrideWaitingGuest, redeemWaitingGuest | 5 | Surendra | VenueOpsService | MIG-PLATFORM MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listMyWaitingGuests, overrideWaitingGuest, redeemWaitingGuest. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `queue#listMyWaitingGuests`, `queue#overrideWaitingGuest`, `queue#redeemWaitingGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-ENTRY-3 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: resolveCalledWaitingGuest | 2 | Pallavi Sawant | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveCalledWaitingGuest. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `queue#resolveCalledWaitingGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-FEED-2 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: submitQueueReading | 1 | Deep Khanvilkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-QUEUE | Operations: submitQueueReading. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `queue#submitQueueReading` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-VENUEOPS-SIGNAGE-1 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: getSignageQueueBoard, getSignageQueueCalls | 3 | Hrushikant Patkar | VenueOpsService | MIG-QUEUE PLATFORM-KERNEL SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-ENTRY-2 SVC-VENUEOPS-ENTRY-3 SVC-VENUEOPS-FEED-2 SVC-VENUEOPS-QUEUE-1 VM-VENUEOPS-ENTRY-1 VM-VENUEOPS-FEED-1 VM-VENUEOPS-QUEUE-1 VM-VENUEOPS-WAITTIME-1 | Operations: getSignageQueueBoard, getSignageQueueCalls. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `queue#getSignageQueueBoard`, `queue#getSignageQueueCalls` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-INVENTORY-RECEIPT-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06 | [BE] InventoryService: createGoodsReceipt, rejectReceivedGoods | 5 | Pranay Shinde | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createGoodsReceipt, rejectReceivedGoods. Spec: handoff/service-docs/backend/InventoryService.md#group-receipt Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#createGoodsReceipt`, `inventory#rejectReceivedGoods` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-MIG-INVENTORY | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06-REST | [DB] Forward migration V1049__inventory.sql: inventory for Venue Management (9 tables) | 5 | Hrushikant Patkar |  | MIG-INVENTORY | Tables: inventory.count, inventory.count_line, inventory.purchase_order_line, inventory.quotation, inventory.quotation_line, inventory.requisition_line, inventory.supplier_contract, inventory.transfer, inventory.transfer_line. Source DDL: backend/tenant/010-inventory.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (inventory.count: row-level security apply_parent_rls; inventory.quotation_line: row-level security apply_parent_rls; inventory.supplier_contract: index supplier_contract_number_uniq, row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: inventory.count: foreign key count_location_id_fkey; inventory.supplier_contract: foreign key supplier_contract_supplier_id_fkey; inventory.transfer: foreign key transfer_from_location_id_fkey, foreign key transfer_to_location_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (inventory.count_line: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: inventory.count_line: foreign key count_line_item_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `inventory.count`, `inventory.count_line`, `inventory.purchase_order_line`, `inventory.quotation`, `inventory.quotation_line`, `inventory.requisition_line`, `inventory.supplier_contract`, `inventory.transfer` and 1 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 2 | VM-INVENTORY-TRANSFER-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] InventoryService: closeTransferShort, createStockTransfer, listStockTransfers, receiveStockTransfer | 8 | Pranay Shinde | InventoryService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: closeTransferShort, createStockTransfer, listStockTransfers, receiveStockTransfer. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#closeTransferShort`, `inventory#createStockTransfer`, `inventory#listStockTransfers`, `inventory#receiveStockTransfer` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-PURCHASEORDER-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06-REST | [BE] InventoryService: cancelPurchaseOrder, createPurchaseOrder, getPurchaseOrder, listPurchaseOrders | 8 | Pranay Shinde | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: cancelPurchaseOrder, createPurchaseOrder, getPurchaseOrder, listPurchaseOrders. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#cancelPurchaseOrder`, `inventory#createPurchaseOrder`, `inventory#getPurchaseOrder`, `inventory#listPurchaseOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-INVENTORY-INVENTORY-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06-REST | [BE] InventoryService: getStockTransfer, updateRequisitionLines, updateSupplier | 8 | Pranay Shinde | InventoryService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: getStockTransfer, updateRequisitionLines, updateSupplier. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#getStockTransfer`, `inventory#updateRequisitionLines`, `inventory#updateSupplier` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-REGION-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08 | [BE] TenancyService: getRegionSettings, updateRegionSettings | 5 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getRegionSettings, updateRegionSettings. Spec: handoff/service-docs/backend/TenancyService.md#group-region Helper task: Pranay Shinde owns the service and reviews. Done when `tenancy#getRegionSettings`, `tenancy#updateRegionSettings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-POLICY-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08 | [BE] OrderService: setRefundPolicy | 3 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRefundPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-policy Helper task: Pranay Shinde owns the service and reviews. Done when `orders#setRefundPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-POLICY-2 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: getGuestRefundPolicy | 1 | Sanket Keluskar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-POLICY-1 | Operations: getGuestRefundPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-policy Helper task: Pranay Shinde owns the service and reviews. Done when `orders#getGuestRefundPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-POLICY-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: getRefundPolicy | 2 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-POLICY-1 | Operations beyond the first release: getRefundPolicy. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#getRefundPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-REFUND-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: simulateRefund | 2 | Surendra | OrderService | MIG-ORDERS MIG-ORDERS-6 PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 VM-ORDER-REFUND-1 | Operations: simulateRefund. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#simulateRefund` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-PRODUCTION-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08 | [BE] FnbService: setRecipe | 3 | Chinmay Patkar | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRecipe. Spec: handoff/service-docs/backend/FnbService.md#group-production Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#setRecipe` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-EXECUTION-1 | AM-APPROVALS-P04 | [BE] ReportingService: runReport | 1 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-7 | Operations: runReport. Spec: handoff/service-docs/backend/ReportingService.md#group-execution Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#runReport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-REPORTING-1 | AM-APPROVALS-P04 | [BE] ReportingService: createKpi, deleteDashboard, listAlerts, setAlertRule | 5 | Deep Khanvilkar | ReportingService | MIG-IDENTITY MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-7 | Operations: createKpi, deleteDashboard, listAlerts, setAlertRule. Spec: handoff/service-docs/backend/ReportingService.md#group-reporting Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#createKpi`, `reporting#deleteDashboard`, `reporting#listAlerts`, `reporting#setAlertRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-NATURALLANGUAGE-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] ReportingService: askReportingQuestion, saveNaturalLanguageQuery | 8 | Pranay Shinde | ReportingService | MIG-AI MIG-PLATFORM MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-7 | Operations: askReportingQuestion, saveNaturalLanguageQuery. Spec: handoff/service-docs/backend/ReportingService.md#group-naturallanguage. Done when `reporting#askReportingQuestion`, `reporting#saveNaturalLanguageQuery` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-DASHBOARD-1 | AM-SETUP-FINANCE-INSIGHTS-P16 | [BE] ReportingService: createDashboard, getDashboard, listDashboards, recordDashboardView | 5 | Hrushikant Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-7 | Operations: createDashboard, getDashboard, listDashboards, recordDashboardView. Spec: handoff/service-docs/backend/ReportingService.md#group-dashboard Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#createDashboard`, `reporting#getDashboard`, `reporting#listDashboards`, `reporting#recordDashboardView` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-REPORTING-4 | AM-SETUP-FINANCE-INSIGHTS-P16-REST | [BE] ReportingService: getSemanticModel, listKpis | 2 | Narayan Gaonkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-REPORTING-1 SVC-REPORTING-REPORTING-2 | Operations: getSemanticModel, listKpis. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Finance & Insights · Analytics (setup, the rest of the screens); additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#getSemanticModel`, `reporting#listKpis` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-FNB-MENU-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listMenuSchedules, listMenuVersions, listMenus | 3 | Narayan Gaonkar | FnbService | MIG-FNB PLATFORM-KERNEL SVC-FNB-FNB-1 SVC-FNB-FNB-16 SVC-FNB-FNB-6 SVC-FNB-FNB-8 SVC-FNB-MENU-1 SVC-FNB-PRODUCTION-1 VM-FNB-MENU-1 | Operations: listMenuSchedules, listMenuVersions, listMenus. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#listMenuSchedules`, `fnb#listMenuVersions`, `fnb#listMenus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-FNB-9 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [DB] Forward migration V1254__fnb.sql: fnb for Food, Beverage & Retail · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.temperature_checkpoint. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.temperature_checkpoint` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 2 | SVC-FNB-PRODUCTION-3 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: printPrepSheet | 1 | Deep Khanvilkar | FnbService | MIG-BASELINE PLATFORM-KERNEL | Operations beyond the first release: printPrepSheet. Additive to FnbService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#printPrepSheet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-ITEM-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: listInventoryItems | 2 | Chinmay Patkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations beyond the first release: listInventoryItems. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#listInventoryItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-INVENTORY-STOCK-2 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: createStockLocation | 1 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createStockLocation. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to InventoryService, whose first-release owner (Narayan Gaonkar) reviews. Done when `inventory#createStockLocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-INVENTORY-ITEM-2 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: getInventoryItem, getInventoryKitDefinition, lookupInventoryItem | 5 | Surendra | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations: getInventoryItem, getInventoryKitDefinition, lookupInventoryItem. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to InventoryService, whose first-release owner (Narayan Gaonkar) reviews. Done when `inventory#getInventoryItem`, `inventory#getInventoryKitDefinition`, `inventory#lookupInventoryItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-20 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: completeProductionRun, listProductionPlans, planProductionRun | 5 | Narayan Gaonkar | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: completeProductionRun, listProductionPlans, planProductionRun. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#completeProductionRun`, `fnb#listProductionPlans`, `fnb#planProductionRun` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 2 | VM-INVENTORY-STOCK-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: getStockPositions, getStockValuation, listStockLocations | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-LEDGER PLATFORM-KERNEL SVC-FNB-FNB-20 SVC-FNB-FNB-7 SVC-INVENTORY-INVENTORY-3 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-STOCK-2 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-RETAIL-FLOOR-2 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-VENUEOPS-WORKORDER-4 VM-FNB-PRODUCTION-1 VM-INVENTORY-MOVEMENT-1 | Operations beyond the first release: getStockPositions, getStockValuation, listStockLocations. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#getStockPositions`, `inventory#getStockValuation`, `inventory#listStockLocations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-FNB-FNB-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: enterCountLine, getProductionRun, listProductionRuns, listTemperatureCheckpoints | 8 | Narayan Gaonkar | FnbService | MIG-FNB MIG-FNB-9 MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations: enterCountLine, getProductionRun, listProductionRuns, listTemperatureCheckpoints. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#enterCountLine`, `fnb#getProductionRun`, `fnb#listProductionRuns`, `fnb#listTemperatureCheckpoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-28 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: setTemperatureCheckpoint | 2 | Narayan Gaonkar | FnbService | MIG-FNB-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTemperatureCheckpoint. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#setTemperatureCheckpoint` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-REPORTING-REPORTING-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] ReportingService: acknowledgeAlert, getKpiValues, getSupplierPerformance | 5 | Sanket Keluskar | ReportingService | MIG-ACCESS MIG-FNB MIG-INVENTORY MIG-LEDGER MIG-MARKETING MIG-ORDERS MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-11 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-58 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-9 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-7 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENT-4 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-EVENTS-2 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-PROMOTIONS-2 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-CATALOGUE-SEATMAP-2 SVC-CATALOGUE-VOUCHER-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-11 SVC-FNB-FNB-12 SVC-FNB-FNB-13 SVC-FNB-FNB-16 SVC-FNB-FNB-17 SVC-FNB-FNB-18 SVC-FNB-FNB-2 SVC-FNB-FNB-20 SVC-FNB-FNB-28 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-PRODUCTION-2 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-FNB-TABLE-3 SVC-INVENTORY-INVENTORY-3 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-INVENTORY-STOCK-2 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-LEDGER-3 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-LEDGER-TAX-4 SVC-LEDGER-TAX-5 SVC-LEDGER-TAX-6 SVC-LEDGER-VARIANCE-1 SVC-ORDER-B2B-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-20 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-2 SVC-ORDER-PAYMENTS-6 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SHIFT-7 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-5 SVC-WALLET-WALLET-7 SVC-WALLET-WALLET-8 SVC-WALLET-WALLET-9 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-FNB-FNB-1 VM-FNB-MENU-1 VM-FNB-ORDER-1 VM-FNB-PRODUCTION-1 VM-INVENTORY-INVENTORY-1 VM-INVENTORY-MOVEMENT-1 VM-INVENTORY-PURCHASEORDER-1 VM-INVENTORY-TRANSFER-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-1 VM-LEDGER-RECOGNITION-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-ACCREDITATION VM-MIG-REPORTING VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 VM-ORDER-SYNC-1 VM-RETAIL-RETAIL-1 VM-WALLET-WALLET-1 | Operations beyond the first release: acknowledgeAlert, getKpiValues, getSupplierPerformance. Additive to ReportingService; its first-release owner (Pranay Shinde) reviews. Done when `reporting#acknowledgeAlert`, `reporting#getKpiValues`, `reporting#getSupplierPerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-FEEDBACK-1 | AM-MARKETING-CRM-P01 | [BE] MarketingService: submitReview | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: submitReview. Spec: handoff/service-docs/backend/MarketingService.md#group-feedback Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#submitReview` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-LOYALTY-2 | AM-MARKETING-CRM-P01 | [BE] MarketingService: listLeaderboard, listLoyaltyProgrammes, listRewards, setLeaderboardNickname | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listLeaderboard, listLoyaltyProgrammes, listRewards, setLeaderboardNickname. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty. Done when `marketing-crm#listLeaderboard`, `marketing-crm#listLoyaltyProgrammes`, `marketing-crm#listRewards`, `marketing-crm#setLeaderboardNickname` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-1 | AM-MARKETING-CRM-P01 | [BE] MarketingService: createChallenge, createForm, createInvitationCampaign, createReferral | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createChallenge, createForm, createInvitationCampaign, createReferral. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#createChallenge`, `marketing-crm#createForm`, `marketing-crm#createInvitationCampaign`, `marketing-crm#createReferral` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-2 | AM-MARKETING-CRM-P01 | [BE] MarketingService: createUrlRedirect, getForm, getLoyaltyPosition, getMyChallenges | 5 | Deep Khanvilkar | MarketingService | MIG-CONTROL MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createUrlRedirect, getForm, getLoyaltyPosition, getMyChallenges. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#createUrlRedirect`, `marketing-crm#getForm`, `marketing-crm#getLoyaltyPosition`, `marketing-crm#getMyChallenges` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MESSAGE-1 | AM-MARKETING-CRM-P01 | [BE] MarketingService: createMessageTemplate, listMyNotifications, markMyNotificationsRead, updateMessageTemplate | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMessageTemplate, listMyNotifications, markMyNotificationsRead, updateMessageTemplate. Spec: handoff/service-docs/backend/MarketingService.md#group-message. Done when `marketing-crm#createMessageTemplate`, `marketing-crm#listMyNotifications`, `marketing-crm#markMyNotificationsRead`, `marketing-crm#updateMessageTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-MARKETING-MARKETING-8 | AM-MARKETING-CRM-P02 | [BE] MarketingService: getMyCase | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 | Operations: getMyCase. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#getMyCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-MIG-MARKETING | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1052__marketing.sql: marketing for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-MARKETING | Tables: marketing.journey_step. Source DDL: backend/tenant/010-marketing.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.journey_step: foreign key journey_enrollment_step_id_fkey (from marketing.journey_enrollment)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.journey_step` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
6 | 3 | MIG-TENANCY-3 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1077__tenancy.sql: tenancy for Tenancy & Venues · Venue Management 2 of 3 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-TENANCY VM-MIG-TENANCY | Tables: tenancy.data_retention_setting. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (tenancy.data_retention_setting: index data_retention_setting_data_class_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `tenancy.data_retention_setting` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-6 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1054__marketing.sql: marketing for Marketing & CRM · Venue Management (Block A) (29 tables) | 8 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-IDENTITY MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.agent_service_profile, marketing.business_event, marketing.case_internal_request, marketing.case_linked_record, marketing.case_resolution, marketing.case_routing_rule, marketing.communication_routing_rule, marketing.consent_record_channel, marketing.contact_automation, marketing.guest_extra_field, marketing.guest_extra_option, marketing.guest_extra_value, marketing.guest_match_policy, marketing.guest_relationship, marketing.message_trigger, marketing.message_trigger_condition, marketing.privacy_request_deadline, marketing.privacy_request_type, marketing.quality_evaluation, marketing.reward_assignment, marketing.sla_policy, marketing.suppression, marketing.tracking_technology_catalogue, marketing.waiver_association, marketing.waiver_exception, marketing.waiver_form_layout, marketing.waiver_master, marketing.waiver_trigger_rule, marketing.waiver_version_control. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.communication_routing_rule: column providers; marketing.consent_record_channel: row-level security apply_grant_holder_read_rls; marketing.guest_extra_option: column scope_path, index guest_extra_option_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.guest_extra_value: column scope_path, index guest_extra_value_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.privacy_request_type: column stages; marketing.quality_evaluation: columns criteria, ai_findings and coaching_actions; marketing.reward_assignment: row-level security apply_parent_split_rls; marketing.suppression: row-level security apply_read_beneath_rls; marketing.tracking_technology_catalogue: row-level security apply_read_beneath_rls; marketing.waiver_form_layout: column sections; marketing.waiver_trigger_rule: columns eligibility and reminders; marketing.waiver_version_control: column history); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.agent_service_profile: foreign key agent_service_profile_principal_id_fkey; marketing.case_internal_request: foreign key case_internal_request_case_id_fkey; marketing.case_linked_record: foreign key case_linked_record_case_id_fkey; marketing.case_resolution: foreign key case_resolution_case_id_fkey; marketing.case_routing_rule: rename column respect_sla_capability to respects_sla_capability, rename column sticky_ownership to has_sticky_ownership; marketing.communication_routing_rule: rename column skip_unhealthy_providers to skips_unhealthy_providers, rename column cost_aware to is_cost_aware; marketing.contact_automation: rename column kill_switch to is_kill_switch_engaged; marketing.guest_extra_field: drop index guest_extra_field_tenant_id_idx; marketing.guest_match_policy: rename column offer_at_checkout to offers_at_checkout; marketing.guest_relationship: rename column shared_benefits to has_shared_benefits; marketing.message_trigger: foreign key message_trigger_template_id_fkey, foreign key message_trigger_condition_message_trigger_id_fkey (from marketing.message_trigger_condition); marketing.message_trigger_condition: foreign key message_trigger_condition_message_trigger_id_fkey; marketing.quality_evaluation: rename column sla_met to is_sla_met, foreign key quality_evaluation_agent_principal_id_fkey; marketing.reward_assignment: foreign key reward_assignment_reward_id_fkey; marketing.sla_policy: rename column business_hours_only to is_business_hours_only; marketing.waiver_exception: foreign key waiver_exception_requirement_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.communication_routing_rule.providers`; not null `marketing.guest_extra_option.scope_path`; not null `marketing.guest_extra_value.scope_path`; not null `marketing.privacy_request_type.stages`; not null `marketing.quality_evaluation.criteria`; not null `marketing.waiver_form_layout.sections`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.agent_service_profile`, `marketing.business_event`, `marketing.case_internal_request`, `marketing.case_linked_record`, `marketing.case_resolution`, `marketing.case_routing_rule`, `marketing.communication_routing_rule`, `marketing.consent_record_channel` and 21 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-2 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1062__marketing.sql: marketing for Identity & Security · Venue Management (4 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING MIG-ORDERS MIG-PII VM-MIG-MARKETING | Tables: marketing.guest_note, marketing.loyalty_points, marketing.touch_point, marketing.waiver_signature. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0103a__names_early_after_r1_20261020.sql (the names the contracts use: marketing.waiver_signature: rename column template_id to form_definition_id); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.loyalty_points: column scope_path, index loyalty_points_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.touch_point: row-level security apply_grant_holder_subject_read_rls; marketing.waiver_signature: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.guest_note: rename column visible_to_server to is_visible_to_server, foreign key guest_note_subject_id_fkey; marketing.waiver_signature: rename index waiver_signature_template_id_idx to waiver_signature_form_definition_id_idx, foreign key waiver_signature_form_definition_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.loyalty_points.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.guest_note`, `marketing.loyalty_points`, `marketing.touch_point`, `marketing.waiver_signature` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-3 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1082__marketing.sql: marketing for Tenancy & Venues · Venue Management 2 of 3 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.legal_hold, marketing.privacy_action, marketing.privacy_audit_event, marketing.retention_policy, marketing.retention_run. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.privacy_action: column system_results; marketing.privacy_audit_event: row-level security apply_grant_holder_subject_read_rls; marketing.retention_policy: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.legal_hold: drop index legal_hold_hold_id_idx; marketing.privacy_action: foreign key privacy_action_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (marketing.privacy_audit_event: DROP CONSTRAINT IF EXISTS privacy_audit_event_source_chk; VALIDATE CONSTRAINT privacy_audit_event_source_chk, constraint privacy_audit_event_source_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.legal_hold`, `marketing.privacy_action`, `marketing.privacy_audit_event`, `marketing.retention_policy`, `marketing.retention_run` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-MARKETING-CAMPAIGN-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: pauseCampaign, unscheduleCampaign | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: pauseCampaign, unscheduleCampaign. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#pauseCampaign`, `marketing-crm#unscheduleCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-CONSENT-3 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listPublishedTrackingTechnologies, recordConsent, recordConsentAnswers, recordDeviceConsent | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PII-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPublishedTrackingTechnologies, recordConsent, recordConsentAnswers, recordDeviceConsent. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listPublishedTrackingTechnologies`, `marketing-crm#recordConsent`, `marketing-crm#recordConsentAnswers`, `marketing-crm#recordDeviceConsent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-CONSENT-1 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: claimDeviceConsent, createConsentQuestion, getCookieConsentRuntime, getDeviceConsentHistory | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: claimDeviceConsent, createConsentQuestion, getCookieConsentRuntime, getDeviceConsentHistory. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#claimDeviceConsent`, `marketing-crm#createConsentQuestion`, `marketing-crm#getCookieConsentRuntime`, `marketing-crm#getDeviceConsentHistory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MESSAGE-3 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: notifyPerformanceHolders | 1 | Pallavi Sawant | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: notifyPerformanceHolders. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#notifyPerformanceHolders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-1 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: getCaseInvestigationResolution, listIntelligentRoutingSkills, setAgentServiceProfile, setCaseInternalRequest | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCaseInvestigationResolution, listIntelligentRoutingSkills, setAgentServiceProfile, setCaseInternalRequest. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getCaseInvestigationResolution`, `marketing-crm#listIntelligentRoutingSkills`, `marketing-crm#setAgentServiceProfile`, `marketing-crm#setCaseInternalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setCaseResolution, setContactAutomation, setQualityEvaluation | 8 | Surendra | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCaseResolution, setContactAutomation, setQualityEvaluation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setCaseResolution`, `marketing-crm#setContactAutomation`, `marketing-crm#setQualityEvaluation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-6 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: actOnWaiverRequirements, getDigitalWaiverForm, getSuppressionList, getWaiverTesting | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnWaiverRequirements, getDigitalWaiverForm, getSuppressionList, getWaiverTesting. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#actOnWaiverRequirements`, `marketing-crm#getDigitalWaiverForm`, `marketing-crm#getSuppressionList`, `marketing-crm#getWaiverTesting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-7 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: recordCheckoutConsents, setPrivacyAction, setPrivacyRequestTypes, setTrackingTechnologyCatalogueEntry | 8 | Surendra | MarketingService | MIG-MARKETING MIG-MARKETING-3 MIG-MARKETING-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordCheckoutConsents, setPrivacyAction, setPrivacyRequestTypes, setTrackingTechnologyCatalogueEntry. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#recordCheckoutConsents`, `marketing-crm#setPrivacyAction`, `marketing-crm#setPrivacyRequestTypes`, `marketing-crm#setTrackingTechnologyCatalogueEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-8 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setWaiverAssociation, setWaiverException, setWaiverTemplateMaster, setWaiverTriggerRule | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWaiverAssociation, setWaiverException, setWaiverTemplateMaster, setWaiverTriggerRule. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setWaiverAssociation`, `marketing-crm#setWaiverException`, `marketing-crm#setWaiverTemplateMaster`, `marketing-crm#setWaiverTriggerRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-3 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setDataRetentionPolicy | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING-3 MIG-TENANCY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDataRetentionPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setDataRetentionPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-4 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: issueReward, listLoyaltyPointEntries, listRewardAssignments | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING-2 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueReward, listLoyaltyPointEntries, listRewardAssignments. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#issueReward`, `marketing-crm#listLoyaltyPointEntries`, `marketing-crm#listRewardAssignments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-11 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: accrueLoyaltyPoints, getGuestExtraValues, listGuestExtraFields, listMessageDispatches | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: accrueLoyaltyPoints, getGuestExtraValues, listGuestExtraFields, listMessageDispatches. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#accrueLoyaltyPoints`, `marketing-crm#getGuestExtraValues`, `marketing-crm#listGuestExtraFields`, `marketing-crm#listMessageDispatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-12 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listSlaPolicies, listWaiverSignatures, recordTouchPoint, setGuestExtraValues | 5 | Surendra | MarketingService | MIG-MARKETING MIG-MARKETING-2 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listSlaPolicies, listWaiverSignatures, recordTouchPoint, setGuestExtraValues. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listSlaPolicies`, `marketing-crm#listWaiverSignatures`, `marketing-crm#recordTouchPoint`, `marketing-crm#setGuestExtraValues` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MESSAGE-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setBusinessEventMapping, setCommunicationRoutingRule | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBusinessEventMapping, setCommunicationRoutingRule. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setBusinessEventMapping`, `marketing-crm#setCommunicationRoutingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-10 | AM-MARKETING-CRM-P12-BLOCK-A | [DB] Forward migration V1060__marketing.sql: marketing for Marketing & CRM · Venue Management 4 of 5 (4 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.case_escalation, marketing.feedback_classification, marketing.review_response, marketing.waiver_verification. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.review_response: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.case_escalation: foreign key case_escalation_case_id_fkey; marketing.review_response: foreign key review_response_review_id_fkey; marketing.waiver_verification: rename column participant_match to is_participant_match, rename column booking_match to is_order_match, rename column guardian_relationship_present to is_guardian_relationship_present, rename column required_evidence_present to is_required_evidence_present, foreign key waiver_verification_submission_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.case_escalation`, `marketing.feedback_classification`, `marketing.review_response`, `marketing.waiver_verification` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-MARKETING-CASE-8 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: listCases, reopenCase, updateCase | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCases, reopenCase, updateCase. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCases`, `marketing-crm#reopenCase`, `marketing-crm#updateCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MARKETING-18 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: claimConversation, closeConversation, getConversation, listConversations | 8 | Narayan Gaonkar | MarketingService | MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimConversation, closeConversation, getConversation, listConversations. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#claimConversation`, `marketing-crm#closeConversation`, `marketing-crm#getConversation`, `marketing-crm#listConversations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MARKETING-19 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: transferConversation | 2 | Narayan Gaonkar | MarketingService | MIG-IDENTITY MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferConversation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#transferConversation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-7 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: addCaseMessage, createCase, escalateCase, getCase | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addCaseMessage, createCase, escalateCase, getCase. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#addCaseMessage`, `marketing-crm#createCase`, `marketing-crm#escalateCase`, `marketing-crm#getCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-9 | AM-MARKETING-CRM-API-BLOCK-A-COMPLETION | [DB] Forward migration V1056__marketing.sql: marketing for Marketing & CRM · Venue Management 3 of 5 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.case_category, marketing.case_service_action, marketing.communication_provider, marketing.message_dispatch_attempt, marketing.service_queue. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.message_dispatch_attempt: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.case_service_action: foreign key case_service_action_order_id_fkey; marketing.communication_provider: foreign key message_dispatch_attempt_communication_provider_id_fkey (from marketing.message_dispatch_attempt), foreign key sender_identity_provider_id_fkey (from marketing.sender_identity); marketing.message_dispatch_attempt: foreign key message_dispatch_attempt_communication_provider_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.case_category`, `marketing.case_service_action`, `marketing.communication_provider`, `marketing.message_dispatch_attempt`, `marketing.service_queue` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-20 | AM-MARKETING-CRM-API-BLOCK-A-COMPLETION | [DB] Forward migration V1226__marketing.sql: marketing for Marketing & CRM · Venue Management 5 of 5 (3 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.communication_policy_decision, marketing.sender_identity, marketing.waiver_signatory_rule. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.waiver_signatory_rule: column guardian_threshold_by_country); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.communication_policy_decision: rename column email_preference to prefers_email, rename column sms_preference to prefers_sms, rename column whatsapp_preference to prefers_whatsapp, rename column push_preference to prefers_push, foreign key communication_policy_decision_subject_id_fkey; marketing.sender_identity: foreign key sender_identity_provider_id_fkey; marketing.waiver_signatory_rule: rename column capture_relationship to captures_relationship, rename column guardian_signs_for_each_minor to requires_guardian_signature_per_minor); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.communication_policy_decision`, `marketing.sender_identity`, `marketing.waiver_signatory_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-MARKETING-MESSAGE-9 | AM-MARKETING-CRM-API-BLOCK-A-COMPLETION | [BE] MarketingService: sendTransactionalMessage | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-20 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: sendTransactionalMessage. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · API only (Block A completion); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#sendTransactionalMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-KNOWLEDGE-1 | AM-AI-P01 | [BE] AiService: configureAssistantProfile, recordAnswerFeedback | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAssistantProfile, recordAnswerFeedback. Spec: handoff/service-docs/backend/AiService.md#group-knowledge Helper task: Pranay Shinde owns the service and reviews. Done when `ai#configureAssistantProfile`, `ai#recordAnswerFeedback` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-INSIGHTS-1 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] AiService: decideAiInsight, explainMetricChange | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideAiInsight, explainMetricChange. Spec: handoff/service-docs/backend/AiService.md#group-insights Helper task: Pranay Shinde owns the service and reviews. Done when `ai#decideAiInsight`, `ai#explainMetricChange` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CAMPAIGN-1 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] MarketingService: createCampaign, launchCampaign, stopCampaign, updateCampaign | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCampaign, launchCampaign, stopCampaign, updateCampaign. Spec: handoff/service-docs/backend/MarketingService.md#group-campaign. Done when `marketing-crm#createCampaign`, `marketing-crm#launchCampaign`, `marketing-crm#stopCampaign`, `marketing-crm#updateCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-LOYALTY-3 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] MarketingService: setLoyaltyRules, setReward, updateLoyaltyProgramme | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLoyaltyRules, setReward, updateLoyaltyProgramme. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty. Done when `marketing-crm#setLoyaltyRules`, `marketing-crm#setReward`, `marketing-crm#updateLoyaltyProgramme` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-SEGMENT-1 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] MarketingService: createSegment | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSegment. Spec: handoff/service-docs/backend/MarketingService.md#group-segment Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#createSegment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-SEGMENT-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listSegmentMembers | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 | Operations: listSegmentMembers. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listSegmentMembers` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-5 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [DB] Forward migration V1053__marketing.sql: marketing for Marketing & CRM · Kiosk (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PLATFORM VM-MIG-MARKETING | Tables: marketing.kiosk_assist_session. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.kiosk_assist_session: column actions_taken, index kiosk_assist_session_device_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.kiosk_assist_session: foreign key kiosk_assist_session_device_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.kiosk_assist_session` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-15 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [DB] Forward migration V1173__marketing.sql: marketing for Customer & Marketing · Venue Management (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.badge, marketing.loyalty_campaign, marketing.message_delivery. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.badge: column scope_path, index badge_scope_path_idx, row-level security apply_grant_holder_read_rls; marketing.loyalty_campaign: column scope_path, index loyalty_campaign_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.badge: foreign key customer_badge_badge_id_fkey (from marketing.customer_badge)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (marketing.badge: row-level security apply_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also add the key customer_badge_badge_id_fkey here** (marketing.customer_badge to marketing.badge, guarded): MIG-MARKETING creates marketing.customer_badge before marketing.badge exists. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.badge.scope_path`; not null `marketing.loyalty_campaign.scope_path`; table dropped `marketing.message_delivery`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.badge`, `marketing.loyalty_campaign`, `marketing.message_delivery` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-17 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] TenancyService: listAccreditationProgrammes, updateAccreditationProgramme | 3 | Sanket Keluskar | TenancyService | MIG-ACCREDITATION-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAccreditationProgrammes, updateAccreditationProgramme. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#listAccreditationProgrammes`, `accreditation#updateAccreditationProgramme` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-ACCREDITATION-3 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] TenancyService: verifyAccreditationCredential | 1 | Narayan Gaonkar | TenancyService | MIG-ACCREDITATION-3 MIG-ACCREDITATION-4 PLATFORM-KERNEL SVC-TENANCY-ACCREDITATION-17 VM-MIG-ACCREDITATION | Operations: verifyAccreditationCredential. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Admission & Access · Scanner (Block A); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#verifyAccreditationCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-MARKETING-SEGMENT-1 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: listSegments | 1 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-SEGMENT-1 | Operations beyond the first release: listSegments. Additive to MarketingService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#listSegments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-INSIGHTS-3 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] AiService: listMarketingRecommendations | 1 | Sanket Keluskar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-INSIGHTS-1 | Operations: listMarketingRecommendations. Spec: contracts (ai) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listMarketingRecommendations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-CAMPAIGN-3 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: getCampaign, getCampaignPerformance, testSendCampaign | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCampaign, getCampaignPerformance, testSendCampaign. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getCampaign`, `marketing-crm#getCampaignPerformance`, `marketing-crm#testSendCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-MARKETING-CAMPAIGN-1 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listCampaigns | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CAMPAIGN-2 SVC-MARKETING-CAMPAIGN-3 SVC-MARKETING-SEGMENT-1 | Operations beyond the first release: listCampaigns. Additive to MarketingService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#listCampaigns` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MARKETING-20 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: activateChallenge, getChallenge, listChallenges, listForms | 5 | Surendra | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: activateChallenge, getChallenge, listChallenges, listForms. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#activateChallenge`, `marketing-crm#getChallenge`, `marketing-crm#listChallenges`, `marketing-crm#listForms` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-MARKETING-MESSAGE-7 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: listMessageTemplates | 1 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-MESSAGE-1 | Operations: listMessageTemplates. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listMessageTemplates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-7 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: setLoyaltyCampaign | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLoyaltyCampaign. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setLoyaltyCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-6 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: getLoyaltyRules, listBadges, listLoyaltyCampaigns, setBadge | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getLoyaltyRules, listBadges, listLoyaltyCampaigns, setBadge. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getLoyaltyRules`, `marketing-crm#listBadges`, `marketing-crm#listLoyaltyCampaigns`, `marketing-crm#setBadge` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-21 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: setCallDisposition, startKioskAssist | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING MIG-MARKETING-5 MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCallDisposition, startKioskAssist. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setCallDisposition`, `marketing-crm#startKioskAssist` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-GUEST-4 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: getGuestProfile | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-LOYALTY-2 SVC-MARKETING-MARKETING-11 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 | Operations: getGuestProfile. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getGuestProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-SEGMENT-4 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: previewSegmentDraft | 1 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 SVC-ORDER-CART-1 | Operations: previewSegmentDraft. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#previewSegmentDraft` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-16 | AM-SETUP-CUSTOMER-MARKETING-P13-REST | [DB] Forward migration V1174__marketing.sql: marketing for Customer & Marketing · CMS (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.cookie_scan_finding, marketing.cookie_scan_policy, marketing.cookie_scan_run. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (marketing.cookie_scan_policy: DROP CONSTRAINT IF EXISTS cookie_scan_policy_frequency_chk, constraint cookie_scan_policy_frequency_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.cookie_scan_finding`, `marketing.cookie_scan_policy`, `marketing.cookie_scan_run` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CONSENT-24 | AM-SETUP-CUSTOMER-MARKETING-P13-REST | [BE] MarketingService: listCookieTrackingDigital, listTrackingTechnologyCatalogue, recordCookieScan, setCookieScanPolicy | 8 | Surendra | MarketingService | MIG-MARKETING MIG-MARKETING-16 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCookieTrackingDigital, listTrackingTechnologyCatalogue, recordCookieScan, setCookieScanPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · CMS (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCookieTrackingDigital`, `marketing-crm#listTrackingTechnologyCatalogue`, `marketing-crm#recordCookieScan`, `marketing-crm#setCookieScanPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-23 | AM-SETUP-CUSTOMER-MARKETING-P13-REST | [BE] MarketingService: listCookieBannerPreference, listCookieScanFindings, listCookieScanPolicies, listCookieScans | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-16 PLATFORM-KERNEL SVC-MARKETING-CONSENT-24 SVC-MARKETING-CONSENT-4 | Operations: listCookieBannerPreference, listCookieScanFindings, listCookieScanPolicies, listCookieScans. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · CMS (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCookieBannerPreference`, `marketing-crm#listCookieScanFindings`, `marketing-crm#listCookieScanPolicies`, `marketing-crm#listCookieScans` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CASE-12 | AM-SETUP-CUSTOMER-MARKETING-P12-REST | [BE] MarketingService: listAgentWorkloadAvailability | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-KERNEL SVC-MARKETING-CASE-1 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-19 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-3 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 | Operations: listAgentWorkloadAvailability. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Support Console (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listAgentWorkloadAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-CONFIG-2 | AM-SETUP-AI-INTELLIGENCE-P08 | [BE] AiService: setAiPolicy | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiPolicy. Spec: handoff/service-docs/backend/AiService.md#group-config Helper task: Pranay Shinde owns the service and reviews. Done when `ai#setAiPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-1 | AM-SETUP-AI-INTELLIGENCE-P08 | [BE] AiService: createForecastScenario, decideOperationalRequirement, getAiVenueSettings, getForecast | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createForecastScenario, decideOperationalRequirement, getAiVenueSettings, getForecast. Spec: handoff/service-docs/backend/AiService.md#group-forecast. Done when `ai#createForecastScenario`, `ai#decideOperationalRequirement`, `ai#getAiVenueSettings`, `ai#getForecast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-10 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1184__ai.sql: ai for AI & Intelligence · Venue Management (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.index_failure, ai.spend_ceiling. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.index_failure`, `ai.spend_ceiling` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-6 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1185__workforce.sql: workforce for AI & Intelligence · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.forecast_requirement. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.forecast_requirement` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-3 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1162__workforce.sql: workforce for Resources & Capacity · Venue Management 2 of 4 (4 tables) | 3 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.field_ownership, workforce.integration_source, workforce.staffing_rules, workforce.training_record. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (workforce.training_record: row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: workforce.integration_source: foreign key sync_conflict_source_id_fkey (from workforce.sync_conflict), foreign key sync_run_source_id_fkey (from workforce.sync_run)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.field_ownership`, `workforce.integration_source`, `workforce.staffing_rules`, `workforce.training_record` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-5 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1164__workforce.sql: workforce for Workforce · Venue Management 1 of 2 (9 tables) | 5 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-PLATFORM MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.labour_budget, workforce.leave_balance, workforce.leave_request, workforce.leave_type, workforce.open_shift, workforce.position_requirement, workforce.shift_template, workforce.sync_conflict, workforce.sync_run. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (workforce.shift_template: column breaks); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: workforce.labour_budget: foreign key labour_budget_venue_id_fkey; workforce.leave_balance: foreign key leave_balance_employee_id_fkey, foreign key leave_balance_type_id_fkey; workforce.leave_request: rename column half_day to is_half_day, foreign key leave_request_principal_id_fkey; workforce.leave_type: foreign key leave_balance_type_id_fkey (from workforce.leave_balance), drop index leave_type_tenant_id_idx; workforce.sync_conflict: foreign key sync_conflict_source_id_fkey; workforce.sync_run: foreign key sync_run_source_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.labour_budget`, `workforce.leave_balance`, `workforce.leave_request`, `workforce.leave_type`, `workforce.open_shift`, `workforce.position_requirement`, `workforce.shift_template`, `workforce.sync_conflict` and 1 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-17 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1187__marketing.sql: marketing for AI & Intelligence · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.service_copilot_config. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (marketing.service_copilot_config: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.service_copilot_config: rename column reply_in_customer_language to replies_in_customer_language); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.service_copilot_config` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-TENANCY-WORKFORCE-9 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] TenancyService: getStaffingCoverage | 1 | Narayan Gaonkar | TenancyService | MIG-WORKFORCE MIG-WORKFORCE-3 MIG-WORKFORCE-5 MIG-WORKFORCE-6 PLATFORM-KERNEL SVC-TENANCY-ROTA-1 | Operations: getStaffingCoverage. Spec: contracts (workforce) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#getStaffingCoverage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIG-3 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: getAiSpendCeiling, setAiSpendCeiling | 2 | Narayan Gaonkar | AiService | MIG-AI-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAiSpendCeiling, setAiSpendCeiling. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#getAiSpendCeiling`, `ai#setAiSpendCeiling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-KNOWLEDGE-2 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: listAssistantProfiles, listKnowledgeGaps | 2 | Narayan Gaonkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-ASSIST-1 SVC-AI-KNOWLEDGE-1 | Operations: listAssistantProfiles, listKnowledgeGaps. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAssistantProfiles`, `ai#listKnowledgeGaps` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-13 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] MarketingService: setCustomerServiceCopilot | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCustomerServiceCopilot. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setCustomerServiceCopilot` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-AI-RETRIEVAL-4 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: listIndexFailures, listKnowledgeCollections | 1 | Chinmay Patkar | AiService | MIG-AI MIG-AI-10 PLATFORM-KERNEL SVC-AI-RETRIEVAL-1 | Operations: listIndexFailures, listKnowledgeCollections. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listIndexFailures`, `ai#listKnowledgeCollections` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-GENERAL-1 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] MarketingService: getCustomerServiceCopilot | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-17 PLATFORM-KERNEL SVC-MARKETING-CASE-13 | Operations: getCustomerServiceCopilot. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getCustomerServiceCopilot` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-CONFIG-1 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: getAiByokEnablement, getAiPolicy, listAiProviders, setAiByokEnablement | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAiByokEnablement, getAiPolicy, listAiProviders, setAiByokEnablement. Spec: handoff/service-docs/backend/AiService.md#group-config Helper task: Pranay Shinde owns the service and reviews. Done when `ai#getAiByokEnablement`, `ai#getAiPolicy`, `ai#listAiProviders`, `ai#setAiByokEnablement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-3 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: listOperationalRequirements, listVenueHistoryImports, publishForecastVersion, runForecast | 8 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOperationalRequirements, listVenueHistoryImports, publishForecastVersion, runForecast. Spec: handoff/service-docs/backend/AiService.md#group-forecast. Done when `ai#listOperationalRequirements`, `ai#listVenueHistoryImports`, `ai#publishForecastVersion`, `ai#runForecast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-4 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: setAiVenueSettings, setForecastDefinition | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiVenueSettings, setForecastDefinition. Spec: handoff/service-docs/backend/AiService.md#group-forecast Helper task: Pranay Shinde owns the service and reviews. Done when `ai#setAiVenueSettings`, `ai#setForecastDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-GOVERNANCE-3 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: publishAiGovernancePolicy, revokeAiPolicyException, simulateAiGovernancePolicy | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishAiGovernancePolicy, revokeAiPolicyException, simulateAiGovernancePolicy. Spec: handoff/service-docs/backend/AiService.md#group-governance Helper task: Pranay Shinde owns the service and reviews. Done when `ai#publishAiGovernancePolicy`, `ai#revokeAiPolicyException`, `ai#simulateAiGovernancePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-MODELS-1 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: listAiEvaluations, listAiTrainingRuns, promoteAiRelease, publishPromptTemplate | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAiEvaluations, listAiTrainingRuns, promoteAiRelease, publishPromptTemplate. Spec: handoff/service-docs/backend/AiService.md#group-models. Done when `ai#listAiEvaluations`, `ai#listAiTrainingRuns`, `ai#promoteAiRelease`, `ai#publishPromptTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-MODELS-2 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: rollbackAiRelease, runAiEvaluation, setAiModel | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rollbackAiRelease, runAiEvaluation, setAiModel. Spec: handoff/service-docs/backend/AiService.md#group-models. Done when `ai#rollbackAiRelease`, `ai#runAiEvaluation`, `ai#setAiModel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-FORECAST-7 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: listForecastDefinitions | 1 | Narayan Gaonkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-FORECAST-4 SVC-AI-MODELS-1 SVC-AI-MODELS-2 | Operations: listForecastDefinitions. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listForecastDefinitions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-MONITORING-1 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: containAiIncident, listAiGovernanceAlerts, listAiIncidents, openAiIncident | 8 | Narayan Gaonkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: containAiIncident, listAiGovernanceAlerts, listAiIncidents, openAiIncident. Spec: handoff/service-docs/backend/AiService.md#group-monitoring. Done when `ai#containAiIncident`, `ai#listAiGovernanceAlerts`, `ai#listAiIncidents`, `ai#openAiIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-11 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [DB] Forward migration V1188__ai.sql: ai for AI & Intelligence · TICVAI Console (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.forecast_export. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.forecast_export` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-AI-FORECAST-8 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: exportForecastVersion | 2 | Sanket Keluskar | AiService | MIG-AI MIG-AI-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: exportForecastVersion. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#exportForecastVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-MONITORING-5 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: closeAiIncident | 2 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeAiIncident. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#closeAiIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-ACTIONS-7 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: listAiTools | 1 | Narayan Gaonkar | AiService | MIG-AI-3 PLATFORM-KERNEL | Operations: listAiTools. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAiTools` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-MODELS-3 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: listAiModels, listPromptTemplates | 3 | Narayan Gaonkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-MODELS-1 SVC-AI-MODELS-2 | Operations: listAiModels, listPromptTemplates. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAiModels`, `ai#listPromptTemplates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-NATURALLANGUAGE-2 | AM-REPORTING-P08-BLOCK-A | [BE] ReportingService: runSemanticQuery | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-CATALOGUE-1 SVC-REPORTING-CATALOGUE-2 SVC-REPORTING-NATURALLANGUAGE-1 SVC-REPORTING-REPORTING-1 SVC-REPORTING-REPORTING-2 | Operations: runSemanticQuery. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management (Block A); additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#runSemanticQuery` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-REPORTING-6 | AM-REPORTING-P08-BLOCK-A | [BE] ReportingService: getServiceSummary, listAlertRules | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-REPORTING-1 | Operations: getServiceSummary, listAlertRules. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management (Block A); additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#getServiceSummary`, `reporting#listAlertRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-INSIGHTS-4 | AM-REPORTING-P16-BLOCK-A | [BE] AiService: listAiInsights | 2 | Sanket Keluskar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-INSIGHTS-1 | Operations: listAiInsights. Spec: contracts (ai) at the release tag, served by ADAM. Built for Reporting · Analytics (Block A); additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAiInsights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-DASHBOARD-3 | AM-REPORTING-P16-BLOCK-A | [BE] ReportingService: getCommandCentre | 1 | Narayan Gaonkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-DASHBOARD-1 SVC-REPORTING-DASHBOARD-2 SVC-REPORTING-REPORTING-1 | Operations: getCommandCentre. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics (Block A); additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#getCommandCentre` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-REPORTING-SCHEDULE-1 | AM-REPORTING-API-BLOCK-A-COMPLETION | [BE] ReportingService: createReportSchedule | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-11 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-58 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-9 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-7 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENT-4 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-EVENTS-2 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-PROMOTIONS-2 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-CATALOGUE-SEATMAP-2 SVC-CATALOGUE-VOUCHER-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-11 SVC-FNB-FNB-12 SVC-FNB-FNB-13 SVC-FNB-FNB-16 SVC-FNB-FNB-17 SVC-FNB-FNB-18 SVC-FNB-FNB-2 SVC-FNB-FNB-20 SVC-FNB-FNB-28 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-PRODUCTION-2 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-FNB-TABLE-3 SVC-INVENTORY-INVENTORY-3 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-INVENTORY-STOCK-2 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-LEDGER-3 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-LEDGER-TAX-4 SVC-LEDGER-TAX-5 SVC-LEDGER-TAX-6 SVC-LEDGER-VARIANCE-1 SVC-ORDER-B2B-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-20 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-2 SVC-ORDER-PAYMENTS-6 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SHIFT-7 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-5 SVC-WALLET-WALLET-7 SVC-WALLET-WALLET-8 SVC-WALLET-WALLET-9 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-FNB-FNB-1 VM-FNB-MENU-1 VM-FNB-ORDER-1 VM-FNB-PRODUCTION-1 VM-INVENTORY-INVENTORY-1 VM-INVENTORY-MOVEMENT-1 VM-INVENTORY-PURCHASEORDER-1 VM-INVENTORY-TRANSFER-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-1 VM-LEDGER-RECOGNITION-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-REPORTING VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 VM-ORDER-SYNC-1 VM-RETAIL-RETAIL-1 VM-WALLET-WALLET-1 | Operations beyond the first release: createReportSchedule. Additive to ReportingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#createReportSchedule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-SCHEDULE-2 | AM-REPORTING-API-BLOCK-A-COMPLETION | [BE] ReportingService: deleteReportSchedule, listReportSchedules, updateReportSchedule | 5 | Surendra | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-REPORTING | Operations: deleteReportSchedule, listReportSchedules, updateReportSchedule. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · API only (Block A completion); additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#deleteReportSchedule`, `reporting#listReportSchedules`, `reporting#updateReportSchedule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | EDGE-WAITING-ROOM | AM-FOUNDATION-API-PLATFORM | [BE] The on-sale waiting room: Redis positions, the cached page, the release controller, admission tokens | 8 | Narayan Gaonkar |  | KERNEL-TENANT-LIMITS PLATFORM-KERNEL | The on-sale waiting room: Redis positions, the cached page, the release controller, admission tokens. Builds: `operation catalogue#enterWaitingRoom`, `operation catalogue#getWaitingRoomPosition`, `operation catalogue#setWaitingRoomSetting`, `adr ADR-0064`, `adr ADR-0066`. ADR-0066 (accepted 1 October; B1, or Block A if an on-sale is booked in Block A): enterWaitingRoom gives a position from a Redis counter with no database write; the static branded waiting page is served from Front Door's cache and polls getWaitingRoomPosition; a release controller admits guests per second from the health of commerce (latency and the 429 rate, ADR-0064); an admitted guest gets a short-lived signed token (tenant, performance, expiry, unique id; key in Key Vault) that middleware checks by signature, with no database read, on addCartLine and acquireInventoryHold from guest channels only (till, kiosk and workstation holds are exempt, amendment of 1 October); activation follows the performance's onSaleFrom/onSaleTo or setWaitingRoomSetting. Done when: with the room on, a guest cart hold without a token is refused 403 admission-required, one with a valid token succeeds, a forged or expired token or one for another performance is refused, a till hold needs no token, and the release rate drops when commerce latency rises.
12 | 3 | EDGE-WAITING-ROOM-LOAD | AM-FOUNDATION-API-PLATFORM | [BE] Load test the waiting room at 50,000 arrivals in the burst environment | 3 | Narayan Gaonkar |  | EDGE-WAITING-ROOM | Load test the waiting room at 50,000 arrivals in the burst environment. Builds: `adr ADR-0035`, `adr ADR-0066`. ADR-0066 item 4 as amended on 6 October (the client's sizing benchmarks, CHG-R4-017), before the first large sale: 50,000 simultaneous arrivals in the opening seconds against a burst environment (ADR-0035) with the waiting room on, the sale behind the room held at 3,000 concurrent B2C users and then stepped above it to show the benchmark is not a limit (docs/active/block-test-strategy.md, Load scenarios), recording position latency, the Front Door cache hit rate, the release rate the controller holds, commerce p95 and 429s, and the relay lag while admitted guests buy (ADR-0058 amendment: 3,500 events a second). Done when: all 50,000 get a position without a database write, admitted guests buy with commerce p95 inside its target at 3,000 concurrent and above, no cart hold succeeds without a token, and the results are recorded against the sizing figures.
11 | 3 | SVC-IDENTITY-IDENTITY-5 | AM-IDENTITY-SECURITY-P06 | [BE] IdentityService: logout | 2 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: logout. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#logout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-2 | AM-IDENTITY-SECURITY-P08 | [DB] Forward migration V1007__approvals.sql: approvals for Identity & Security · Venue Management (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE | Tables: approvals.workflow_definition, approvals.workflow_version. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: approvals.workflow_definition: foreign key workflow_instance_workflow_definition_id_fkey (from approvals.workflow_instance), foreign key workflow_trigger_workflow_definition_id_fkey (from approvals.workflow_trigger), foreign key workflow_version_workflow_definition_id_fkey (from approvals.workflow_version); approvals.workflow_version: foreign key workflow_instance_workflow_version_id_fkey (from approvals.workflow_instance), foreign key workflow_version_workflow_definition_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.workflow_definition`, `approvals.workflow_version` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-IDENTITY-SESSION-1 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: revokeAllSessions | 1 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: revokeAllSessions. Additive to IdentityService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `identity#revokeAllSessions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-TENANCY-WORKFORCE-1 | AM-IDENTITY-SECURITY-P08 | [BE] TenancyService: listJobTitles, listWorkAssignments, setJobTitle, setWorkAssignment | 5 | Deep Khanvilkar | TenancyService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: listJobTitles, listWorkAssignments, setJobTitle, setWorkAssignment. Additive to TenancyService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `workforce#listJobTitles`, `workforce#listWorkAssignments`, `workforce#setJobTitle`, `workforce#setWorkAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-IDENTITY-IDENTITY-16 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: listStepUpSupervisors | 1 | Narayan Gaonkar | IdentityService | MIG-BASELINE PLATFORM-KERNEL | Operations: listStepUpSupervisors. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#listStepUpSupervisors` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-3 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: createAccessReviewCampaign, createAuthorisationPolicy, createEmergencyAccessOverride, decideAccessReviewItem | 8 | Surendra | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-IDENTITY VM-MIG-WORKFORCE | Operations: createAccessReviewCampaign, createAuthorisationPolicy, createEmergencyAccessOverride, decideAccessReviewItem. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#createAccessReviewCampaign`, `identity#createAuthorisationPolicy`, `identity#createEmergencyAccessOverride`, `identity#decideAccessReviewItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-4 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: evaluateAccess, getAuthorisationPolicy, getAuthorisationPolicyBundle, getPrincipalModuleAccess | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-IDENTITY | Operations: evaluateAccess, getAuthorisationPolicy, getAuthorisationPolicyBundle, getPrincipalModuleAccess. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#evaluateAccess`, `identity#getAuthorisationPolicy`, `identity#getAuthorisationPolicyBundle`, `identity#getPrincipalModuleAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-6 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: listAuthorisationPolicyTemplates, listModuleCapabilities, restoreAuthorisationPolicyVersion, setAuthorisationPolicyState | 5 | Surendra | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAuthorisationPolicyTemplates, listModuleCapabilities, restoreAuthorisationPolicyVersion, setAuthorisationPolicyState. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#listAuthorisationPolicyTemplates`, `identity#listModuleCapabilities`, `identity#restoreAuthorisationPolicyVersion`, `identity#setAuthorisationPolicyState` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-7 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: setPrincipalModuleAccess, simulateAuthorisationPolicy, updateAuthorisationPolicy | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-IDENTITY | Operations: setPrincipalModuleAccess, simulateAuthorisationPolicy, updateAuthorisationPolicy. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#setPrincipalModuleAccess`, `identity#simulateAuthorisationPolicy`, `identity#updateAuthorisationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-IDENTITY-15 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: verifySupervisorStepUp | 1 | Narayan Gaonkar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: verifySupervisorStepUp. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#verifySupervisorStepUp` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-IDENTITY-6 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: decideGuestIdentityVerification, getMembership, listCustomerMemberships, listGuestIdentityVerifications | 5 | Surendra | IdentityService | MIG-IDENTITY-2 MIG-IDENTITY-3 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideGuestIdentityVerification, getMembership, listCustomerMemberships, listGuestIdentityVerifications. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#decideGuestIdentityVerification`, `identity#getMembership`, `identity#listCustomerMemberships`, `identity#listGuestIdentityVerifications` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-2 | AM-IDENTITY-SECURITY-P08 | [BE] TenancyService: approveVersioningGovernance | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveVersioningGovernance. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#approveVersioningGovernance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-IDENTITY-ADMINISTRATION-5 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: listAccessDecisions, listAuthorisationPolicies, listAuthorisationPolicyEffectiveness, listAuthorisationPolicyHistory | 3 | Deep Khanvilkar | IdentityService | MIG-IDENTITY-3 PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-3 SVC-IDENTITY-ADMINISTRATION-4 SVC-IDENTITY-ADMINISTRATION-6 SVC-IDENTITY-ADMINISTRATION-7 VM-MIG-IDENTITY | Operations: listAccessDecisions, listAuthorisationPolicies, listAuthorisationPolicyEffectiveness, listAuthorisationPolicyHistory. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#listAccessDecisions`, `identity#listAuthorisationPolicies`, `identity#listAuthorisationPolicyEffectiveness`, `identity#listAuthorisationPolicyHistory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-MARKETING-MARKETING-2 | AM-IDENTITY-SECURITY-P08 | [BE] MarketingService: matchLostItem | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: matchLostItem. Additive to MarketingService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `marketing-crm#matchLostItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-REPORTING-2 | AM-IDENTITY-SECURITY-P16 | [DB] Forward migration V1063__reporting.sql: reporting for Identity & Security · Analytics (1 tables) | 1 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.analytics_governance_policy. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `reporting.analytics_governance_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 3 | SVC-REPORTING-REPORTING-3 | AM-IDENTITY-SECURITY-P16 | [BE] ReportingService: getAnalyticsGovernancePolicy | 1 | Narayan Gaonkar | ReportingService | MIG-REPORTING-2 PLATFORM-KERNEL | Operations: getAnalyticsGovernancePolicy. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Identity & Security · Analytics; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#getAnalyticsGovernancePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-IDENTITY-IDENTITY-8 | AM-IDENTITY-SECURITY-P09-2 | [BE] IdentityService: listPermissions | 1 | Chinmay Patkar | IdentityService | MIG-IDENTITY-3 PLATFORM-KERNEL | Operations: listPermissions. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 5; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#listPermissions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-SESSION-2 | AM-IDENTITY-SECURITY-P09-2 | [BE] IdentityService: endOwnSession, listOwnSessions | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endOwnSession, listOwnSessions. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 5; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#endOwnSession`, `identity#listOwnSessions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-AI-GOVERNANCE-5 | AM-IDENTITY-SECURITY-P09-2 | [BE] AiService: listAiInteractions | 2 | Pranay Shinde | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-AI-1 SVC-AI-AI-2 SVC-AI-AI-3 SVC-AI-ASSIST-1 SVC-AI-CONFIGURE-1 SVC-AI-GENERATE-1 SVC-AI-GENERATE-2 SVC-AI-GOVERNANCE-1 SVC-AI-INSIGHTS-1 SVC-AI-RETRIEVAL-1 SVC-REPORTING-NATURALLANGUAGE-1 | Operations: listAiInteractions. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAiInteractions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-2 | AM-IDENTITY-SECURITY-P09-3 | [DB] Forward migration V1070__payments.sql: payments for Identity & Security · TICVAI Console 3 of 5 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.reconciliation_source. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.reconciliation_source: rename column alert_if_missing to alerts_if_missing); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.reconciliation_source` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
18 | 3 | SVC-ORDER-PAYMENTS-3 | AM-IDENTITY-SECURITY-P09-3 | [BE] OrderService: listReconciliationSources | 1 | Narayan Gaonkar | OrderService | MIG-PAYMENTS-2 PLATFORM-KERNEL | Operations: listReconciliationSources. Spec: contracts (payments) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 5; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listReconciliationSources` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-ACTIONS-3 | AM-IDENTITY-SECURITY-P09-3 | [BE] AiService: simulateActionPlan | 2 | Pallavi Sawant | AiService | MIG-AI MIG-AI-2 MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#simulateActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIGURE-2 | AM-IDENTITY-SECURITY-P09-3 | [BE] AiService: decideBlueprintRecommendation, getConfigurationBlueprint | 3 | Pallavi Sawant | AiService | MIG-AI-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideBlueprintRecommendation, getConfigurationBlueprint. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#decideBlueprintRecommendation`, `ai#getConfigurationBlueprint` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-FORECAST-5 | AM-IDENTITY-SECURITY-P09-3 | [BE] AiService: compareForecastScenarios | 1 | Pallavi Sawant | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-FORECAST-1 SVC-AI-FORECAST-3 | Operations: compareForecastScenarios. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#compareForecastScenarios` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-AI-ACTIONS-2 | AM-IDENTITY-SECURITY-P09-3 | [BE] AiService: getActionPlan | 2 | Chinmay Patkar | AiService | MIG-AI MIG-AI-2 PLATFORM-KERNEL SVC-AI-ACTIONS-3 SVC-AI-GENERATE-2 SVC-AI-GOVERNANCE-1 SVC-AI-GOVERNANCE-2 | Operations: getActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#getActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-4 | AM-IDENTITY-SECURITY-P09-4 | [DB] Forward migration V1243__ai.sql: ai for Identity & Security · TICVAI Console 4 of 5 (2 tables) | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.evidence_package, ai.risk_register. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.evidence_package`, `ai.risk_register` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-AI-AUDIT-2 | AM-IDENTITY-SECURITY-P09-4 | [BE] AiService: exportAiEvidencePackage | 1 | Pranay Shinde | AiService | MIG-AI MIG-AI-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: exportAiEvidencePackage. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 4 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#exportAiEvidencePackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-MONITORING-2 | AM-IDENTITY-SECURITY-P09-4 | [BE] AiService: listAiRiskRegister, setAiRiskRegisterEntry | 3 | Hrushikant Patkar | AiService | MIG-AI-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAiRiskRegister, setAiRiskRegisterEntry. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 4 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAiRiskRegister`, `ai#setAiRiskRegisterEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-AI-AUDIT-1 | AM-IDENTITY-SECURITY-P09-4 | [BE] AiService: getAiDecisionTrace, searchAiDecisions | 5 | Narayan Gaonkar | AiService | MIG-AI MIG-AI-2 PLATFORM-KERNEL SVC-AI-ACTIONS-1 SVC-AI-ACTIONS-3 SVC-AI-AI-1 SVC-AI-AI-2 SVC-AI-AI-3 SVC-AI-ASSIST-1 SVC-AI-CONFIGURE-1 SVC-AI-FORECAST-1 SVC-AI-FORECAST-3 SVC-AI-GENERATE-1 SVC-AI-GENERATE-2 SVC-AI-GOVERNANCE-1 SVC-AI-GOVERNANCE-2 SVC-AI-GOVERNANCE-3 SVC-AI-INSIGHTS-1 SVC-AI-MODELS-1 SVC-AI-MODELS-2 SVC-AI-MONITORING-1 SVC-AI-RECOMMEND-1 SVC-AI-RETRIEVAL-1 SVC-REPORTING-NATURALLANGUAGE-1 | Operations: getAiDecisionTrace, searchAiDecisions. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 4 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#getAiDecisionTrace`, `ai#searchAiDecisions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-IDENTITY-PROSPECTAUTH-1 | AM-IDENTITY-SECURITY-P09-5 | [BE] IdentityService: startProspectSignup, verifyProspectSignupCode | 2 | Narayan Gaonkar | IdentityService | MIG-BASELINE PLATFORM-KERNEL | Operations: startProspectSignup, verifyProspectSignupCode. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 5 of 5; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#startProspectSignup`, `identity#verifyProspectSignupCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-2 | AM-IDENTITY-SECURITY-P09-5 | [BE] PlatformService: submitOnboardingApplication | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-2 MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: submitOnboardingApplication. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 5 of 5; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#submitOnboardingApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-8 | AM-IDENTITY-SECURITY-P10 | [BE] IdentityService: createDelegatedAccess, deleteDelegatedAccess, listDelegatedAccess | 5 | Sanket Keluskar | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createDelegatedAccess, deleteDelegatedAccess, listDelegatedAccess. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Partner Portal; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#createDelegatedAccess`, `identity#deleteDelegatedAccess`, `identity#listDelegatedAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-DRAFTED-1 | AM-IDENTITY-SECURITY-P10 | [BE] PlatformService: approveBookingLimitCommercial, approvePartnerStatuLifecycle | 8 | Narayan Gaonkar | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-3 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveBookingLimitCommercial, approvePartnerStatuLifecycle. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Identity & Security · Partner Portal; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#approveBookingLimitCommercial`, `subscription#approvePartnerStatuLifecycle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ACCESS-ACCESS-10 | AM-TENANCY-VENUES-P08 | [BE] AccessService: setAccessAreaCapacity | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessAreaCapacity. Spec: contracts (access) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 1 of 3; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setAccessAreaCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-8 | AM-TENANCY-VENUES-P08 | [BE] AccessService: listVenueParkAccess | 1 | New full-stack developer 2 | AccessService | MIG-ACCESS-2 PLATFORM-KERNEL SVC-ACCESS-ACCESS-10 | Operations: listVenueParkAccess. Spec: contracts (access) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 1 of 3; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVenueParkAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-3 | AM-TENANCY-VENUES-P08-2 | [DB] Forward migration V1080__payments.sql: payments for Tenancy & Venues · Venue Management 2 of 3 (3 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.terminal, payments.terminal_certification, payments.terminal_certification_level3. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.terminal_certification: row-level security apply_read_beneath_rls; payments.terminal_certification_level3: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: payments.terminal: foreign key terminal_device_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.terminal`, `payments.terminal_certification`, `payments.terminal_certification_level3` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-DEVICES-4 | AM-TENANCY-VENUES-P08-2 | [BE] TenancyService: enrolDevice, getDeviceTelemetry | 3 | Sanket Keluskar | TenancyService | MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: enrolDevice, getDeviceTelemetry. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#enrolDevice`, `tenancy#getDeviceTelemetry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-TENANCY-5 | AM-TENANCY-VENUES-P08-2 | [BE] TenancyService: listDataRetentionSettings, setDataRetentionSetting | 3 | Pranay Shinde | TenancyService | MIG-TENANCY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDataRetentionSettings, setDataRetentionSetting. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#listDataRetentionSettings`, `tenancy#setDataRetentionSetting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-4 | AM-TENANCY-VENUES-P08-2 | [BE] OrderService: setPaymentTerminalConfiguration | 2 | Chinmay Patkar | OrderService | MIG-PAYMENTS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentTerminalConfiguration. Spec: contracts (payments) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setPaymentTerminalConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-2 | AM-TENANCY-VENUES-P08-2 | [BE] MarketingService: runDataRetention | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: runDataRetention. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#runDataRetention` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-3 | AM-TENANCY-VENUES-P08-3 | [DB] Forward migration V1083__approvals.sql: approvals for Tenancy & Venues · Venue Management 3 of 3 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-BASELINE | Tables: approvals.retention_policy. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: approvals.retention_policy: rename column retain_signatures to retains_signatures, rename column retain_attachments to retains_attachments); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.retention_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-3 | AM-TENANCY-VENUES-P08-3 | [BE] TenancyService: setApprovalRetentionPolicy | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalRetentionPolicy. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 3 of 3; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#setApprovalRetentionPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-SUBSCRIPTION-2 | AM-TENANCY-VENUES-P09 | [DB] Forward migration V1057__subscription.sql: control for Tenancy & Venues · TICVAI Console (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.go_live_readiness. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (control.go_live_readiness: named subscription.go_live_readiness in the file, its name before the declared move, column groups); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `subscription.go_live_readiness`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.go_live_readiness` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-3 | AM-TENANCY-VENUES-P09 | [BE] PlatformService: runGoLiveValidation | 1 | Sanket Keluskar | PlatformService | MIG-SUBSCRIPTION-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: runGoLiveValidation. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Tenancy & Venues · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#runGoLiveValidation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-SYNC-2 | AM-PLATFORM-OPERATIONS-P07 | [DB] Forward migration V1086__sync.sql: sync for Platform Operations · Scanner (2 tables) | 2 | Hrushikant Patkar | CrossRegionService | MIG-BASELINE MIG-PLATFORM MIG-SYNC | Tables: sync.cell_connection, sync.cross_cell_request. Source DDL: backend/tenant/010-sync.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0109__names_after_r1_20261020.sql (the names the contracts use: sync.cross_cell_request: foreign key cross_cell_request_guest_link_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `sync.cell_connection`, `sync.cross_cell_request` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-PLATFORM-OPS-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] PlatformService: skipRolloutCell | 2 | Pranay Shinde | PlatformService | MIG-CONTROL-5 MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: skipRolloutCell. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#skipRolloutCell` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-CROSSREGION-CROSS-REGION-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: listCellConnections, listCrossCellRequests | 2 | Chinmay Patkar | CrossRegionService | MIG-SYNC-2 PLATFORM-KERNEL | Operations: listCellConnections, listCrossCellRequests. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#listCellConnections`, `cross-region#listCrossCellRequests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CROSSREGION-DSAR-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: createDsarRequest, getDsarRequest | 2 | Surendra | CrossRegionService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createDsarRequest, getDsarRequest. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#createDsarRequest`, `cross-region#getDsarRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CROSSREGION-GUESTLINK-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: createGuestLink, getGuestLink, resolveGuestLink, revokeGuestLink | 5 | Deep Khanvilkar | CrossRegionService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createGuestLink, getGuestLink, resolveGuestLink, revokeGuestLink. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#createGuestLink`, `cross-region#getGuestLink`, `cross-region#resolveGuestLink`, `cross-region#revokeGuestLink` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-REDEMPTION-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: getCrossRegionEntitlement, propagateCrossRegionEntitlement, reconcileRedemptions, revokeCrossRegionEntitlement | 5 | Surendra | CrossRegionService | MIG-ACCESS MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCrossRegionEntitlement, propagateCrossRegionEntitlement, reconcileRedemptions, revokeCrossRegionEntitlement. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#getCrossRegionEntitlement`, `cross-region#propagateCrossRegionEntitlement`, `cross-region#reconcileRedemptions`, `cross-region#revokeCrossRegionEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-WALLET-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: authoriseWalletSpend, captureWalletAuthorisation, getWalletAllocation, relinquishWalletAuthorisation | 8 | Pranay Shinde | CrossRegionService | MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: authoriseWalletSpend, captureWalletAuthorisation, getWalletAllocation, relinquishWalletAuthorisation. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#authoriseWalletSpend`, `cross-region#captureWalletAuthorisation`, `cross-region#getWalletAllocation`, `cross-region#relinquishWalletAuthorisation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-WALLET-2 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: setWalletAllocationPolicy | 2 | Chinmay Patkar | CrossRegionService | MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletAllocationPolicy. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#setWalletAllocationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-ENVIRONMENT-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: listEnvironments, registerEnvironment | 2 | Sanket Keluskar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listEnvironments, registerEnvironment. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#listEnvironments`, `platform-ops#registerEnvironment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-MIGRATION-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: applyConfigPackage, applyMigration, diffConfigPackage, exportConfigPackage | 5 | Narayan Gaonkar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyConfigPackage, applyMigration, diffConfigPackage, exportConfigPackage. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#applyConfigPackage`, `platform-ops#applyMigration`, `platform-ops#diffConfigPackage`, `platform-ops#exportConfigPackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-MIGRATION-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: getMigrationRun, getVersionSkew, listMigrations, planMigration | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getMigrationRun, getVersionSkew, listMigrations, planMigration. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#getMigrationRun`, `platform-ops#getVersionSkew`, `platform-ops#listMigrations`, `platform-ops#planMigration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-MIGRATION-3 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: rollbackMigrationRun | 2 | Chinmay Patkar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rollbackMigrationRun. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#rollbackMigrationRun` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-NOTICE-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: listSupportNotices, listUpgradeSchedules, publishSupportNotice, scheduleTenantUpgrade | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listSupportNotices, listUpgradeSchedules, publishSupportNotice, scheduleTenantUpgrade. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#listSupportNotices`, `platform-ops#listUpgradeSchedules`, `platform-ops#publishSupportNotice`, `platform-ops#scheduleTenantUpgrade` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PLATFORM-OPS-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: cancelOutboxRepublish, getOutboxRepublish, listDeadLetters, listOutboxRepublishes | 5 | Pranay Shinde | PlatformService | MIG-CONTROL-6 MIG-PLATFORM MIG-PLATFORM-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelOutboxRepublish, getOutboxRepublish, listDeadLetters, listOutboxRepublishes. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#cancelOutboxRepublish`, `platform-ops#getOutboxRepublish`, `platform-ops#listDeadLetters`, `platform-ops#listOutboxRepublishes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PLATFORM-OPS-3 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: replayDeadLetter, republishOutbox | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-6 MIG-PLATFORM MIG-PLATFORM-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: replayDeadLetter, republishOutbox. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#replayDeadLetter`, `platform-ops#republishOutbox` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-RELEASE-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: createRelease, getRelease, getReleaseReadiness, listReleases | 5 | Surendra | PlatformService | MIG-CONTROL-5 MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRelease, getRelease, getReleaseReadiness, listReleases. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#createRelease`, `platform-ops#getRelease`, `platform-ops#getReleaseReadiness`, `platform-ops#listReleases` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-RELEASE-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: promoteRelease, rejectRelease, withdrawRelease | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: promoteRelease, rejectRelease, withdrawRelease. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#promoteRelease`, `platform-ops#rejectRelease`, `platform-ops#withdrawRelease` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-ROLLOUT-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: getRollout, listRollouts, pauseRollout, rollbackRollout | 8 | Pranay Shinde | PlatformService | MIG-CONTROL-5 MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getRollout, listRollouts, pauseRollout, rollbackRollout. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#getRollout`, `platform-ops#listRollouts`, `platform-ops#pauseRollout`, `platform-ops#rollbackRollout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-ROLLOUT-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: startRollout | 1 | Chinmay Patkar | PlatformService | MIG-CONTROL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: startRollout. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `platform-ops#startRollout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-SUBSCRIPTION-1 | AM-SUBSCRIPTION-LICENSING-P08 | [DB] Forward migration V1249__control.sql: control for Subscription & Licensing · Venue Management 1 of 3 (2 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.tier_allowance, control.tier_module. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: control.tier_allowance: change named subscription.tier_allowance in the file, its name before the declared move, drop index tier_allowance_tier_id_idx; control.tier_module: change named subscription.tier_module in the file, its name before the declared move, drop index tier_module_tier_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `subscription.tier_allowance`; table dropped `subscription.tier_module`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.tier_allowance`, `control.tier_module` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-BILLING-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: resolveInvoiceDispute | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveInvoiceDispute. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#resolveInvoiceDispute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-BILLING-7 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: issueInvoice, listPlatformTaxRates, setPlatformTaxRate | 5 | Pallavi Sawant | PlatformService | MIG-CONTROL-7 MIG-CONTROL-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueInvoice, listPlatformTaxRates, setPlatformTaxRate. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#issueInvoice`, `subscription#listPlatformTaxRates`, `subscription#setPlatformTaxRate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: executeTenantMigration, launchCellCluster, listCellClusters, listTenantMigrations | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: executeTenantMigration, launchCellCluster, listCellClusters, listTenantMigrations. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#executeTenantMigration`, `subscription#launchCellCluster`, `subscription#listCellClusters`, `subscription#listTenantMigrations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-DRAFTED-5 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: setFamilyHouseholdDependent, setMembershipEligibilityQualification, setMembershipProductTier, setValidityActivationExpiry | 8 | Pranay Shinde | PlatformService | MIG-CATALOGUE MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setFamilyHouseholdDependent, setMembershipEligibilityQualification, setMembershipProductTier, setValidityActivationExpiry. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setFamilyHouseholdDependent`, `subscription#setMembershipEligibilityQualification`, `subscription#setMembershipProductTier`, `subscription#setValidityActivationExpiry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-METERING-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: recordUsage | 2 | Sanket Keluskar | PlatformService | MIG-AI MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordUsage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#recordUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-4 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: actOnPartnerCommissionLine, actOnPartnerReconciliationException, actOnPartnerSettlementBatch, cancelSubscription | 8 | Surendra | PlatformService | MIG-CONTROL MIG-CONTROL-7 MIG-IDENTITY MIG-LEDGER MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnPartnerCommissionLine, actOnPartnerReconciliationException, actOnPartnerSettlementBatch, cancelSubscription. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#actOnPartnerCommissionLine`, `subscription#actOnPartnerReconciliationException`, `subscription#actOnPartnerSettlementBatch`, `subscription#cancelSubscription` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-8 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: setPartnerCapabilityGrants, setPartnerCommissionRules, setPartnerCreditProfile, setPartnerDistributionRights | 8 | Narayan Gaonkar | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPartnerCapabilityGrants, setPartnerCommissionRules, setPartnerCreditProfile, setPartnerDistributionRights. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setPartnerCapabilityGrants`, `subscription#setPartnerCommissionRules`, `subscription#setPartnerCreditProfile`, `subscription#setPartnerDistributionRights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-9 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: setPartnerSecurity, setPlanTiers, updatePartnerAgreement | 8 | Surendra | PlatformService | MIG-CONTROL MIG-CONTROL-7 MIG-LEDGER MIG-SUBSCRIPTION-1 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPartnerSecurity, setPlanTiers, updatePartnerAgreement. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setPartnerSecurity`, `subscription#setPlanTiers`, `subscription#updatePartnerAgreement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-CELL-2 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: planTenantMigration, rollbackTenantMigration | 3 | Chinmay Patkar | PlatformService | MIG-CONTROL-7 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: planTenantMigration, rollbackTenantMigration. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#planTenantMigration`, `subscription#rollbackTenantMigration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-5 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: createPartnerAgreement, decommissionBurstEnvironment, drainBurstEnvironment, exportPartnerInvoice | 8 | Surendra | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createPartnerAgreement, decommissionBurstEnvironment, drainBurstEnvironment, exportPartnerInvoice. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#createPartnerAgreement`, `subscription#decommissionBurstEnvironment`, `subscription#drainBurstEnvironment`, `subscription#exportPartnerInvoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-6 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: getPlanTiers, listBurstEnvironments, listPartnerUsers, reconcileBurstEnvironment | 5 | Narayan Gaonkar | PlatformService | MIG-CATALOGUE MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-ORDERS MIG-PLATFORM MIG-SUBSCRIPTION-1 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getPlanTiers, listBurstEnvironments, listPartnerUsers, reconcileBurstEnvironment. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getPlanTiers`, `subscription#listBurstEnvironments`, `subscription#listPartnerUsers`, `subscription#reconcileBurstEnvironment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-7 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: registerPartner, requestBurstEnvironment, setMembershipUsagePolicy, setPartnerAllocations | 8 | Pranay Shinde | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-6 MIG-CONTROL-7 MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: registerPartner, requestBurstEnvironment, setMembershipUsagePolicy, setPartnerAllocations. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#registerPartner`, `subscription#requestBurstEnvironment`, `subscription#setMembershipUsagePolicy`, `subscription#setPartnerAllocations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-PLATFORM-DRAFTED-2 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: approveMembershipProductValidation, listCommercialAllocationQuota, listCommissionCalculationSettlement, listCommissionMarginIncentive | 8 | Surendra | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveMembershipProductValidation, listCommercialAllocationQuota, listCommissionCalculationSettlement, listCommissionMarginIncentive. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#approveMembershipProductValidation`, `subscription#listCommercialAllocationQuota`, `subscription#listCommissionCalculationSettlement`, `subscription#listCommissionMarginIncentive` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-LEDGER-LEDGER-2 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] LedgerService: rejectJournal, reopenPeriod | 5 | Deep Khanvilkar | LedgerService | MIG-APPROVALS MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: rejectJournal, reopenPeriod. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Done when `finance#rejectJournal`, `finance#reopenPeriod` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-3 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] CatalogueService: setMembershipProgramme, setPlanBenefits | 2 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMembershipProgramme, setPlanBenefits. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setMembershipProgramme`, `catalogue#setPlanBenefits` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-IDENTITY-9 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] IdentityService: recordBenefitUsage | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordBenefitUsage. Spec: contracts (identity) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to IdentityService, whose first-release owner (Hrushikant Patkar) reviews. Done when `identity#recordBenefitUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-10 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: getGoLiveReadiness | 1 | Narayan Gaonkar | PlatformService | MIG-SUBSCRIPTION-2 PLATFORM-KERNEL SVC-PLATFORM-SUBSCRIPTION-3 | Operations: getGoLiveReadiness. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getGoLiveReadiness` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-PLATFORM-DRAFTED-8 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: setMemberMembershipAccount, setRenewalAutoMembership | 5 | Deep Khanvilkar | PlatformService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMemberMembershipAccount, setRenewalAutoMembership. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setMemberMembershipAccount`, `subscription#setRenewalAutoMembership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-6 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] OrderService: migrateMembership, renewMembership, resolveMembershipActivation | 5 | Surendra | OrderService | MIG-ORDERS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: migrateMembership, renewMembership, resolveMembershipActivation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#migrateMembership`, `orders#renewMembership`, `orders#resolveMembershipActivation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-SUBSCRIPTION-4 | AM-SUBSCRIPTION-LICENSING-P09-2 | [DB] Forward migration V1089__subscription.sql: control for Subscription & Licensing · TICVAI Console 2 of 6 (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.licensing_model, control.vsi_assessment. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.licensing_model: column currency_code); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (control.licensing_model: named subscription.licensing_model in the file, its name before the declared move, column overage_pricing); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `subscription.licensing_model`; table dropped `subscription.vsi_assessment`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.licensing_model`, `control.vsi_assessment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-11 | AM-SUBSCRIPTION-LICENSING-P09-2 | [BE] PlatformService: getBillingReconciliation, scoreVsiAssessment | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-2 MIG-CONTROL-7 MIG-CONTROL-9 MIG-SUBSCRIPTION MIG-SUBSCRIPTION-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBillingReconciliation, scoreVsiAssessment. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 2 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getBillingReconciliation`, `subscription#scoreVsiAssessment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-SUBSCRIPTION-5 | AM-SUBSCRIPTION-LICENSING-P09-3 | [DB] Forward migration V1094__subscription.sql: control for Subscription & Licensing · TICVAI Console 3 of 6 (3 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.capacity_pack, control.enforcement_policy, control.vsi_model. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0116__after_r1_20261026.sql (control.capacity_pack: column currency_code); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (control.enforcement_policy: named subscription.enforcement_policy in the file, its name before the declared move, column thresholds; control.vsi_model: named subscription.vsi_model in the file, its name before the declared move, columns factors and tiers); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: control.capacity_pack: change named subscription.capacity_pack in the file, its name before the declared move, drop index capacity_pack_tenant_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `subscription.capacity_pack`; table dropped `subscription.enforcement_policy`; table dropped `subscription.vsi_model`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.capacity_pack`, `control.enforcement_policy`, `control.vsi_model` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-13 | AM-SUBSCRIPTION-LICENSING-P09-3 | [BE] PlatformService: setLicensingModel, setVsiModel, simulateCommercialPackage | 5 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION MIG-SUBSCRIPTION-1 MIG-SUBSCRIPTION-4 MIG-SUBSCRIPTION-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLicensingModel, setVsiModel, simulateCommercialPackage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 3 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setLicensingModel`, `subscription#setVsiModel`, `subscription#simulateCommercialPackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-SUBSCRIPTION-6 | AM-SUBSCRIPTION-LICENSING-P09-4 | [DB] Forward migration V1095__subscription.sql: control for Subscription & Licensing · TICVAI Console 4 of 6 (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.trial_config. Source DDL: backend/control/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): table dropped `subscription.trial_config`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.trial_config` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-BILLING-3 | AM-SUBSCRIPTION-LICENSING-P09-4 | [BE] PlatformService: getBillingEntity, setBillingEntity | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBillingEntity, setBillingEntity. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 4 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getBillingEntity`, `subscription#setBillingEntity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-31 | AM-SUBSCRIPTION-LICENSING-P09-2 | [BE] PlatformService: getCommercialMetrics | 1 | Pranay Shinde | PlatformService | MIG-CONTROL-2 PLATFORM-KERNEL SVC-PLATFORM-BILLING-3 SVC-PLATFORM-SUBSCRIPTION-2 | Operations: getCommercialMetrics. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 2 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getCommercialMetrics` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-DRAFTED-9 | AM-SUBSCRIPTION-LICENSING-P09-4 | [BE] PlatformService: setAgreementContractTerm | 3 | Sanket Keluskar | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-7 MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAgreementContractTerm. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 4 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setAgreementContractTerm` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-14 | AM-SUBSCRIPTION-LICENSING-P09-4 | [BE] PlatformService: addCapacityPack, setTrialConfiguration | 3 | Sanket Keluskar | PlatformService | MIG-SUBSCRIPTION-5 MIG-SUBSCRIPTION-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addCapacityPack, setTrialConfiguration. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 4 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#addCapacityPack`, `subscription#setTrialConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-15 | AM-SUBSCRIPTION-LICENSING-P09-5 | [BE] PlatformService: listVenueTypeTemplates, setLicenceEnforcementPolicy, settleAiUsage | 3 | Sanket Keluskar | PlatformService | MIG-AI MIG-CONTROL-2 MIG-CONTROL-7 MIG-SUBSCRIPTION MIG-SUBSCRIPTION-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listVenueTypeTemplates, setLicenceEnforcementPolicy, settleAiUsage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 5 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listVenueTypeTemplates`, `subscription#setLicenceEnforcementPolicy`, `subscription#settleAiUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-12 | AM-SUBSCRIPTION-LICENSING-P09-3 | [BE] PlatformService: getLicenceEnforcement, getPlanRecommendations, getVsiModel, listLicensingModels | 5 | Narayan Gaonkar | PlatformService | MIG-CONTROL MIG-CONTROL-7 MIG-SUBSCRIPTION MIG-SUBSCRIPTION-1 MIG-SUBSCRIPTION-4 MIG-SUBSCRIPTION-5 PLATFORM-KERNEL SVC-PLATFORM-LICENSING-1 SVC-PLATFORM-LICENSING-3 SVC-PLATFORM-METERING-1 SVC-PLATFORM-PLAN-1 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-SUBSCRIPTION-13 SVC-PLATFORM-SUBSCRIPTION-14 SVC-PLATFORM-SUBSCRIPTION-15 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-2 | Operations: getLicenceEnforcement, getPlanRecommendations, getVsiModel, listLicensingModels. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 3 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getLicenceEnforcement`, `subscription#getPlanRecommendations`, `subscription#getVsiModel`, `subscription#listLicensingModels` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-BILLING-4 | AM-SUBSCRIPTION-LICENSING-P09-6 | [BE] PlatformService: issueCreditNote, recordInvoicePayment | 5 | Sanket Keluskar | PlatformService | MIG-CONTROL-7 MIG-CONTROL-9 MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueCreditNote, recordInvoicePayment. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 6 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#issueCreditNote`, `subscription#recordInvoicePayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-BILLING-5 | AM-SUBSCRIPTION-LICENSING-P09-6 | [BE] PlatformService: cancelInvoice, disputeInvoice | 2 | Narayan Gaonkar | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelInvoice, disputeInvoice. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 6 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#cancelInvoice`, `subscription#disputeInvoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-BILLING-2 | AM-SUBSCRIPTION-LICENSING-P09-6 | [BE] PlatformService: listCreditNotes | 2 | Narayan Gaonkar | PlatformService | MIG-CONTROL-9 PLATFORM-KERNEL SVC-PLATFORM-BILLING-4 | Operations: listCreditNotes. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 6 of 6; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listCreditNotes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-10 | AM-SUBSCRIPTION-LICENSING-P10 | [DB] Forward migration V1107__control.sql: control for Subscription & Licensing · Partner Portal 1 of 2 (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.partner_billing_profile, control.partner_rate_volume_band. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/control/V0107__names_after_r1_20261019.sql (the names the contracts use: control.partner_billing_profile: rename column consolidated_billing to has_consolidated_billing, foreign key partner_billing_profile_agreement_id_fkey, foreign key partner_billing_profile_partner_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.partner_billing_profile`, `control.partner_rate_volume_band` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-16 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: actOnPartnerApplicationReview, createPartnerUser, setPartnerContact | 8 | Surendra | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnPartnerApplicationReview, createPartnerUser, setPartnerContact. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#actOnPartnerApplicationReview`, `subscription#createPartnerUser`, `subscription#setPartnerContact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-DRAFTED-12 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: listPartnerProfileReadiness, setPartnerBrandVenue, setPartnerProfileOrganization, setPartnerRateNet | 8 | Narayan Gaonkar | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-10 MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPartnerProfileReadiness, setPartnerBrandVenue, setPartnerProfileOrganization, setPartnerRateNet. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listPartnerProfileReadiness`, `subscription#setPartnerBrandVenue`, `subscription#setPartnerProfileOrganization`, `subscription#setPartnerRateNet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-DRAFTED-13 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: setPaymentTermBilling | 3 | Deep Khanvilkar | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-10 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentTermBilling. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#setPaymentTermBilling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-17 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: actOnPartnerCase, createPartnerCase, createPartnerChangeRequest, getCommissionStatement | 8 | Narayan Gaonkar | PlatformService | MIG-APPROVALS MIG-APPROVALS-4 MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnPartnerCase, createPartnerCase, createPartnerChangeRequest, getCommissionStatement. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#actOnPartnerCase`, `subscription#createPartnerCase`, `subscription#createPartnerChangeRequest`, `subscription#getCommissionStatement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-PLATFORM-SUBSCRIPTION-18 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: listPartnerAgreements | 1 | Chinmay Patkar | PlatformService | MIG-CONTROL PLATFORM-KERNEL SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-REQUEST-1 | Operations: listPartnerAgreements. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listPartnerAgreements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-LEASE-1 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] CatalogueService: forceReleaseInventoryHold | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: forceReleaseInventoryHold. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#forceReleaseInventoryHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-2 | AM-APPROVALS-P08 | [DB] Forward migration V1042__accreditation.sql: accreditation for Approvals · Venue Management 1 of 5 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.audit. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.audit` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
9 | 3 | MIG-SEATING-2 | AM-APPROVALS-P08 | [DB] Forward migration V1100__seating.sql: seating for Approvals · Venue Management 1 of 5 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-SEATING | Tables: seating.hold_pool. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: seating.hold_pool: foreign key hold_pool_hold_type_id_fkey, foreign key hold_pool_performance_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `seating.hold_pool` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-5 | AM-APPROVALS-P08 | [BE] TenancyService: actOnWorkflowInstance, listConditionDecisionLogic, listRuleWorkflow, listWorkflow | 8 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-5 MIG-APPROVALS-6 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: actOnWorkflowInstance, listConditionDecisionLogic, listRuleWorkflow, listWorkflow. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#actOnWorkflowInstance`, `approvals#listConditionDecisionLogic`, `approvals#listRuleWorkflow`, `approvals#listWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-6 | AM-APPROVALS-P08 | [BE] TenancyService: listWorkflowInstanceProcess, setTriggerActionCross, setVisualBusinessRule, setVisualWorkflow | 8 | Surendra | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-6 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: listWorkflowInstanceProcess, setTriggerActionCross, setVisualBusinessRule, setVisualWorkflow. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listWorkflowInstanceProcess`, `approvals#setTriggerActionCross`, `approvals#setVisualBusinessRule`, `approvals#setVisualWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-7 | AM-APPROVALS-P08 | [BE] TenancyService: simulateWorkflowTestingImpact | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateWorkflowTestingImpact. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#simulateWorkflowTestingImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-ACCREDITATION-1 | AM-APPROVALS-P08 | [BE] TenancyService: listAccreditationAudit | 1 | Sanket Keluskar | TenancyService | MIG-ACCREDITATION-2 PLATFORM-KERNEL | Operations: listAccreditationAudit. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#listAccreditationAudit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-ANALYTICS-1 | AM-APPROVALS-P08 | [BE] TenancyService: getApprovalAnalytics | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-MIG-APPROVALS VM-TENANCY-REQUEST-1 | Operations: getApprovalAnalytics. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#getApprovalAnalytics` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-SEATING-2 | AM-APPROVALS-P08 | [BE] CatalogueService: listSeatHoldPools | 1 | Chinmay Patkar | CatalogueService | MIG-SEATING-2 PLATFORM-KERNEL | Operations: listSeatHoldPools. Spec: contracts (seating) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#listSeatHoldPools` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-3 | AM-APPROVALS-P08-2 | [DB] Forward migration V1104__catalogue.sql: catalogue for Approvals · Venue Management 2 of 5 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.approval_policy. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.approval_policy: rename column creator_cannot_give_final_approval to is_creator_barred_from_final_approval); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.approval_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-8 | AM-APPROVALS-P08-2 | [BE] TenancyService: createAutomationAutonomouAction, listCrossModuleOrchestration, listProcessAutomationOpportunity, listWorkflowAutonomouGovernance | 5 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-5 MIG-APPROVALS-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: createAutomationAutonomouAction, listCrossModuleOrchestration, listProcessAutomationOpportunity, listWorkflowAutonomouGovernance. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 2 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#createAutomationAutonomouAction`, `approvals#listCrossModuleOrchestration`, `approvals#listProcessAutomationOpportunity`, `approvals#listWorkflowAutonomouGovernance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-2 | AM-APPROVALS-P08-2 | [BE] CatalogueService: approveWorkflow | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveWorkflow. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Approvals · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#approveWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-7 | AM-APPROVALS-P08-3 | [DB] Forward migration V1103__approvals.sql: approvals for Approvals · Venue Management 3 of 5 (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-BASELINE | Tables: approvals.evidence_package, approvals.signature. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.evidence_package`, `approvals.signature` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | SVC-PLATFORM-PUBLICAPI-4 | AM-APPROVALS-P08-3 | [BE] PlatformService: listWebhookEventTypes | 1 | Sanket Keluskar | PlatformService | MIG-BASELINE PLATFORM-KERNEL | Operations: listWebhookEventTypes. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Approvals · Venue Management 3 of 5; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#listWebhookEventTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-10 | AM-APPROVALS-P08-3 | [BE] TenancyService: createApprovalEvidencePackage, getApprovalRecord, listApprovalControlPolicies, listSlaEscalationBottleneck | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-6 MIG-APPROVALS-7 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: createApprovalEvidencePackage, getApprovalRecord, listApprovalControlPolicies, listSlaEscalationBottleneck. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 3 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#createApprovalEvidencePackage`, `approvals#getApprovalRecord`, `approvals#listApprovalControlPolicies`, `approvals#listSlaEscalationBottleneck` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-11 | AM-APPROVALS-P08-3 | [BE] TenancyService: setApprovalControlPolicy | 2 | Sanket Keluskar | TenancyService | MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalControlPolicy. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 3 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#setApprovalControlPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-12 | AM-APPROVALS-P08-4 | [BE] TenancyService: listSlaEscalationReminder, signApprovalDecision | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-APPROVALS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listSlaEscalationReminder, signApprovalDecision. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 4 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listSlaEscalationReminder`, `approvals#signApprovalDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-8 | AM-APPROVALS-P08-5 | [DB] Forward migration V1105__approvals.sql: approvals for Approvals · Venue Management 5 of 5 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-BASELINE | Tables: approvals.approver_availability. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `approvals.approver_availability` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-13 | AM-APPROVALS-P08-5 | [BE] TenancyService: setApprovalSlaPolicy, setApproverAvailability | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS-4 MIG-APPROVALS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalSlaPolicy, setApproverAvailability. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 5 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#setApprovalSlaPolicy`, `approvals#setApproverAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-14 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: listPartnerCancellationRefund, listPartnerDisputeCase, listPartnerPerformanceScorecard, listPartnerRelationship | 8 | Surendra | PlatformService | MIG-APPROVALS MIG-APPROVALS-4 MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-ORDERS PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-20 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-13 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-ORDER-REFUND-1 VM-TENANCY-REQUEST-1 | Operations: listPartnerCancellationRefund, listPartnerDisputeCase, listPartnerPerformanceScorecard, listPartnerRelationship. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listPartnerCancellationRefund`, `subscription#listPartnerDisputeCase`, `subscription#listPartnerPerformanceScorecard`, `subscription#listPartnerRelationship` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-4 | AM-APPROVALS-P08-5 | [BE] TenancyService: listApprovedActionExecutions, resolveApprovedActionExecution | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listApprovedActionExecutions, resolveApprovedActionExecution. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 5 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listApprovedActionExecutions`, `approvals#resolveApprovedActionExecution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-APPROVALS-9 | AM-APPROVALS-P08-2 | [BE] TenancyService: listWorkflowExceptionFailure, listWorkflowProcessPerformance | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-5 MIG-APPROVALS-6 PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-1 SVC-TENANCY-APPROVALS-13 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-APPROVALS-6 SVC-TENANCY-DELEGATION-1 SVC-TENANCY-DELEGATION-2 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-REQUEST-4 SVC-TENANCY-REQUEST-6 SVC-TENANCY-ROTA-2 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-MIG-APPROVALS VM-TENANCY-REQUEST-1 | Operations: listWorkflowExceptionFailure, listWorkflowProcessPerformance. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 2 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `approvals#listWorkflowExceptionFailure`, `approvals#listWorkflowProcessPerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-5 | AM-PUBLIC-API-P08 | [BE] PlatformService: getApiUsage, issueApiToken, testWebhookSubscription | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations: getApiUsage, issueApiToken, testWebhookSubscription. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Venue Management; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#getApiUsage`, `public-api#issueApiToken`, `public-api#testWebhookSubscription` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-10 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: listCommercialAgreement, listCommercialAgreementHealth, listPartner, listPartner2 | 8 | Pranay Shinde | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-1 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-PUBLICAPI-11 SVC-PLATFORM-PUBLICAPI-2 SVC-PLATFORM-PUBLICAPI-5 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-20 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-MIG-CONTROL VM-ORDER-ORDERS-2 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 VM-TENANCY-REQUEST-1 | Operations: listCommercialAgreement, listCommercialAgreementHealth, listPartner, listPartner2. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listCommercialAgreement`, `subscription#listCommercialAgreementHealth`, `subscription#listPartner`, `subscription#listPartner2` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-3 | AM-PUBLIC-API-P08 | [BE] WalletService: setWalletRiskRules | 2 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletRiskRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Public API · Venue Management; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#setWalletRiskRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-11 | AM-PUBLIC-API-P09 | [DB] Forward migration V1108__control.sql: control for Public API · TICVAI Console (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.api_anomaly. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.api_anomaly` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | SVC-PLATFORM-PUBLICAPI-6 | AM-PUBLIC-API-P09 | [BE] PlatformService: listApiAnomalies | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL-11 PLATFORM-KERNEL | Operations: listApiAnomalies. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · TICVAI Console; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#listApiAnomalies` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-12 | AM-PUBLIC-API-P14 | [DB] Forward migration V1189__control.sql: control for Public API · Developer Portal (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL MIG-SUBSCRIPTION VM-MIG-CONTROL | Tables: control.sandbox. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `control.sandbox` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys and indexes; no row-level security, which the control database does not have (backend/MIGRATIONS.md)); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-8 | AM-PUBLIC-API-P14 | [BE] PlatformService: createSandbox, listSandboxes, resetSandbox, submitIntegrationListing | 5 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSandbox, listSandboxes, resetSandbox, submitIntegrationListing. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Developer Portal; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#createSandbox`, `public-api#listSandboxes`, `public-api#resetSandbox`, `public-api#submitIntegrationListing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-PLATFORM-PUBLICAPI-14 | AM-PUBLIC-API-P08 | [BE] PlatformService: listMarketplaceListings | 1 | Narayan Gaonkar | PlatformService | MIG-CONTROL PLATFORM-KERNEL SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-PUBLICAPI-8 | Operations: listMarketplaceListings. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Venue Management; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `public-api#listMarketplaceListings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, checked by the operation's permission and tenant check (the control database has no row-level security: only the control plane's role reaches it, backend/MIGRATIONS.md); unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-ASSETS-2 | AM-DIGITAL-ASSETS-P13-2 | [DB] Forward migration V1109__assets.sql: assets for Digital Assets · CMS 2 of 4 (6 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-BASELINE | Tables: assets.audit, assets.distribution_channel, assets.guest_upload, assets.share, assets.tag, assets.taxonomy. Source DDL: backend/tenant/010-assets.sql and backend/tenant/V0108__after_r1_20261020.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (assets.distribution_channel: row-level security apply_read_beneath_rls; assets.taxonomy: columns categories, fields and keyword_vocabularies, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: assets.distribution_channel: rename column signed_urls to uses_signed_urls); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `assets.audit`, `assets.distribution_channel`, `assets.guest_upload`, `assets.share`, `assets.tag`, `assets.taxonomy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-ASSETS-1 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: analyseMediaAsset, bulkUpdateMediaAssets, findSimilarMediaAssets, getMediaDistribution | 5 | New full-stack developer 2 | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: analyseMediaAsset, bulkUpdateMediaAssets, findSimilarMediaAssets, getMediaDistribution. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `assets#analyseMediaAsset`, `assets#bulkUpdateMediaAssets`, `assets#findSimilarMediaAssets`, `assets#getMediaDistribution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-ASSETS-3 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: requestMediaRendition, setMediaAssetTags, setMediaTaxonomy | 5 | Surendra | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestMediaRendition, setMediaAssetTags, setMediaTaxonomy. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `assets#requestMediaRendition`, `assets#setMediaAssetTags`, `assets#setMediaTaxonomy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-UPLOAD-2 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: completeGuestUpload, createGuestUpload | 3 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: completeGuestUpload, createGuestUpload. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `assets#completeGuestUpload`, `assets#createGuestUpload` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-ASSETS-3 | AM-DIGITAL-ASSETS-P13-3 | [DB] Forward migration V1110__assets.sql: assets for Digital Assets · CMS 3 of 4 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-BASELINE | Tables: assets.approval. Source DDL: backend/tenant/010-assets.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `assets.approval` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-ASSETS-5 | AM-DIGITAL-ASSETS-P13-3 | [BE] VenueOpsService: setMediaDistributionChannels | 1 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMediaDistributionChannels. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `assets#setMediaDistributionChannels` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-ASSETS-4 | AM-DIGITAL-ASSETS-P13-3 | [BE] VenueOpsService: createMediaShare, listMediaAssetAudit, setMediaAssetApproval, setMediaAssetRights | 5 | Narayan Gaonkar | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 MIG-ASSETS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMediaShare, listMediaAssetAudit, setMediaAssetApproval, setMediaAssetRights. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `assets#createMediaShare`, `assets#listMediaAssetAudit`, `assets#setMediaAssetApproval`, `assets#setMediaAssetRights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-ASSETS-2 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: getMediaTaxonomy, getMediaUsageAnalytics, listMediaAssetVersions, listMediaRenditions | 3 | New full-stack developer 1 | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 PLATFORM-KERNEL SVC-VENUEOPS-ASSET-1 SVC-VENUEOPS-ASSET-2 SVC-VENUEOPS-ASSETS-1 SVC-VENUEOPS-ASSETS-3 SVC-VENUEOPS-ASSETS-4 SVC-VENUEOPS-UPLOAD-1 | Operations: getMediaTaxonomy, getMediaUsageAnalytics, listMediaAssetVersions, listMediaRenditions. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `assets#getMediaTaxonomy`, `assets#getMediaUsageAnalytics`, `assets#listMediaAssetVersions`, `assets#listMediaRenditions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-WHITELABEL-PUBLISHING-4 | AM-WHITE-LABEL-P08 | [BE] WhiteLabelService: getPreview | 1 | Pranay Shinde | WhiteLabelService | MIG-BASELINE PLATFORM-KERNEL | Operations: getPreview. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Venue Management; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#getPreview` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WHITELABEL-OVERVIEW-3 | AM-WHITE-LABEL-P08 | [BE] WhiteLabelService: getStorefrontInsights | 2 | New full-stack developer 1 | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-OVERVIEW-2 | Operations: getStorefrontInsights. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Venue Management; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#getStorefrontInsights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-BUNDLE-1 | AM-TICKETING-P06 | [BE] CatalogueService: reportBundleApplied | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: reportBundleApplied. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#reportBundleApplied` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CATALOGUE-2 | AM-TICKETING-P08 | [BE] CatalogueService: updateDonationCampaign | 2 | Chinmay Patkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: updateDonationCampaign. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#updateDonationCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-EVENTS-1 | AM-TICKETING-P08 | [BE] CatalogueService: listPerformanceTemplates, setPerformanceTemplate | 2 | Chinmay Patkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: listPerformanceTemplates, setPerformanceTemplate. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#listPerformanceTemplates`, `catalogue#setPerformanceTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-DRAFTED-11 | AM-TICKETING-P08-2 | [BE] CatalogueService: setProductContextOwnership | 2 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setProductContextOwnership. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setProductContextOwnership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-4 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: listMembershipUsageVisit, listPartnerAccessRole, listPartnerReconciliationException, listTerritoryMarketDistribution | 8 | New full-stack developer 1 | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-20 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-CATALOGUE-PRODUCT-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 VM-TENANCY-REQUEST-1 | Operations: listMembershipUsageVisit, listPartnerAccessRole, listPartnerReconciliationException, listTerritoryMarketDistribution. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listMembershipUsageVisit`, `subscription#listPartnerAccessRole`, `subscription#listPartnerReconciliationException`, `subscription#listTerritoryMarketDistribution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-11 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: listPartnerContactUser, listPartnerDocumentationCompliance, listPartnerOnboardingApplication, listPartnerOrderBooking | 8 | New full-stack developer 2 | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-SSO-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-TENANCY-REQUEST-1 | Operations: listPartnerContactUser, listPartnerDocumentationCompliance, listPartnerOnboardingApplication, listPartnerOrderBooking. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listPartnerContactUser`, `subscription#listPartnerDocumentationCompliance`, `subscription#listPartnerOnboardingApplication`, `subscription#listPartnerOrderBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-15 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: listPartnerStatementAccount, listReservationHoldRelease | 5 | Pranay Shinde | PlatformService | MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-REQUEST-1 SVC-WALLET-RETAIL-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 VM-LEDGER-FINANCE-1 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 | Operations: listPartnerStatementAccount, listReservationHoldRelease. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listPartnerStatementAccount`, `subscription#listReservationHoldRelease` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-9 | AM-TICKETING-P08-2 | [BE] CatalogueService: decideCatalogueAiFinding, requestPricingRollback, setConfigurationTemplate, setProductLinks | 8 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: decideCatalogueAiFinding, requestPricingRollback, setConfigurationTemplate, setProductLinks. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#decideCatalogueAiFinding`, `catalogue#requestPricingRollback`, `catalogue#setConfigurationTemplate`, `catalogue#setProductLinks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-7 | AM-TICKETING-P08-2 | [BE] CatalogueService: approveReviewDecision, listChangeImpactAnalysis, listChangePropagationDependency, listGovernanceRiskMonitoring | 5 | Surendra | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveReviewDecision, listChangeImpactAnalysis, listChangePropagationDependency, listGovernanceRiskMonitoring. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#approveReviewDecision`, `catalogue#listChangeImpactAnalysis`, `catalogue#listChangePropagationDependency`, `catalogue#listGovernanceRiskMonitoring` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-8 | AM-TICKETING-P08-3 | [DB] Forward migration V1121__catalogue.sql: catalogue for Ticketing · Venue Management 3 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.price_category, catalogue.pricing_market. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.price_category: row-level security apply_read_beneath_rls; catalogue.pricing_market: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.price_category: foreign key rate_price_category_id_fkey (from catalogue.rate)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key rate_price_category_id_fkey here** (catalogue.rate to catalogue.price_category, guarded): MIG-CATALOGUE creates catalogue.rate before catalogue.price_category exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.price_category`, `catalogue.pricing_market` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-10 | AM-TICKETING-P08-3 | [BE] CatalogueService: setMarketPricingConfiguration, setPriceCategoryRateType | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-6 MIG-CATALOGUE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMarketPricingConfiguration, setPriceCategoryRateType. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setMarketPricingConfiguration`, `catalogue#setPriceCategoryRateType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-16 | AM-TICKETING-P08-3 | [BE] CatalogueService: setPriceHierarchyInheritance, setTaxRuleTreatment, testPricingRule | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-5 MIG-CATALOGUE-6 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPriceHierarchyInheritance, setTaxRuleTreatment, testPricingRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setPriceHierarchyInheritance`, `catalogue#setTaxRuleTreatment`, `catalogue#testPricingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-13 | AM-TICKETING-P08-3 | [BE] CatalogueService: listCustomerSegmentProfile, listEffectiveDateSeason, listLocationVenueEvent, listMarketVenueCurrency | 5 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-6 MIG-CATALOGUE-8 MIG-PRICING-2 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listCustomerSegmentProfile, listEffectiveDateSeason, listLocationVenueEvent, listMarketVenueCurrency. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listCustomerSegmentProfile`, `catalogue#listEffectiveDateSeason`, `catalogue#listLocationVenueEvent`, `catalogue#listMarketVenueCurrency` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-14 | AM-TICKETING-P08-3 | [BE] CatalogueService: listMembershipLoyaltyPricing, listPriceCategoryRate, listPriceListTemplate, listPricingRule | 5 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-7 MIG-CATALOGUE-8 MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-PRICING-1 | Operations: listMembershipLoyaltyPricing, listPriceCategoryRate, listPriceListTemplate, listPricingRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listMembershipLoyaltyPricing`, `catalogue#listPriceCategoryRate`, `catalogue#listPriceListTemplate`, `catalogue#listPricingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-15 | AM-TICKETING-P08-3 | [BE] CatalogueService: listPricingRulePriority, listQuantityGroupVolume, listResidencyNationalityMarket, listTimeslotPerformanceTime | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-PRICING-2 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listPricingRulePriority, listQuantityGroupVolume, listResidencyNationalityMarket, listTimeslotPerformanceTime. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listPricingRulePriority`, `catalogue#listQuantityGroupVolume`, `catalogue#listResidencyNationalityMarket`, `catalogue#listTimeslotPerformanceTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-9 | AM-TICKETING-P08-4 | [DB] Forward migration V1122__catalogue.sql: catalogue for Ticketing · Venue Management 4 of 8 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.pricing_publication_target. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.pricing_publication_target` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-DRAFTED-17 | AM-TICKETING-P08-4 | [BE] CatalogueService: approvePricingWorkflowAuthority, decidePricingChangeRequest, listBulkPricingUpdate, listCurrencyPrecisionRounding | 8 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: approvePricingWorkflowAuthority, decidePricingChangeRequest, listBulkPricingUpdate, listCurrencyPrecisionRounding. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#approvePricingWorkflowAuthority`, `catalogue#decidePricingChangeRequest`, `catalogue#listBulkPricingUpdate`, `catalogue#listCurrencyPrecisionRounding` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-20 | AM-TICKETING-P08-4 | [BE] CatalogueService: publishPricingEffectiveDate, setFeeApplicabilityCharging, setPricingChangeRequest, submitPricingChangeRequest | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-CATALOGUE-9 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: publishPricingEffectiveDate, setFeeApplicabilityCharging, setPricingChangeRequest, submitPricingChangeRequest. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#publishPricingEffectiveDate`, `catalogue#setFeeApplicabilityCharging`, `catalogue#setPricingChangeRequest`, `catalogue#submitPricingChangeRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-46 | AM-IDENTITY-SECURITY-P09-3 | [BE] CatalogueService: listTaxFeeCalculation | 2 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-5 MIG-CATALOGUE-6 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listTaxFeeCalculation. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listTaxFeeCalculation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-8 | AM-TICKETING-P08-2 | [BE] CatalogueService: listProductDuplicationTemplate, listProductGovernance, listProductImportExport, listProductLifecycle | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-7 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS PRD-W1-LANGUAGES PRD-W1-OWNER-FORMS PRD-W1-SALE-PERMISSIONS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listProductDuplicationTemplate, listProductGovernance, listProductImportExport, listProductLifecycle. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listProductDuplicationTemplate`, `catalogue#listProductGovernance`, `catalogue#listProductImportExport`, `catalogue#listProductLifecycle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-19 | AM-TICKETING-P08-4 | [BE] CatalogueService: listPricingDistributionSynchronization, listPricingGovernance, listPricingRollbackEmergency, listPricingVersionBaseline | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-7 MIG-CATALOGUE-9 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-PRICING-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-BUNDLE-1 | Operations: listPricingDistributionSynchronization, listPricingGovernance, listPricingRollbackEmergency, listPricingVersionBaseline. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listPricingDistributionSynchronization`, `catalogue#listPricingGovernance`, `catalogue#listPricingRollbackEmergency`, `catalogue#listPricingVersionBaseline` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-13 | AM-TICKETING-P08-5 | [BE] CatalogueService: setSignalRegistryPolicy | 3 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSignalRegistryPolicy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setSignalRegistryPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-23 | AM-TICKETING-P08-5 | [BE] CatalogueService: listPricing, listPricingCompliance, listSeasonalCalendarDay, listWeatherDemandImpact | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-ORDERS MIG-PRICING-2 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS PRD-W1-LANGUAGES PRD-W1-OWNER-FORMS PRD-W1-SALE-PERMISSIONS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-PRODUCT-1 | Operations: listPricing, listPricingCompliance, listSeasonalCalendarDay, listWeatherDemandImpact. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listPricing`, `catalogue#listPricingCompliance`, `catalogue#listSeasonalCalendarDay`, `catalogue#listWeatherDemandImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-31 | AM-TICKETING-P08-6 | [BE] CatalogueService: listChannelExceptionIncident, listChannelGovernanceSla, listChannelLogTransaction, listChannelPerformanceCommercial | 8 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS PRD-W1-LANGUAGES PRD-W1-OWNER-FORMS PRD-W1-SALE-PERMISSIONS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listChannelExceptionIncident, listChannelGovernanceSla, listChannelLogTransaction, listChannelPerformanceCommercial. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannelExceptionIncident`, `catalogue#listChannelGovernanceSla`, `catalogue#listChannelLogTransaction`, `catalogue#listChannelPerformanceCommercial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-32 | AM-TICKETING-P08-6 | [BE] CatalogueService: listCustomerEligibilityRule, listProductPriceAvailability, listRealTimeAvailability, listRealTimeChannel | 5 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-PROMOTIONS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listCustomerEligibilityRule, listProductPriceAvailability, listRealTimeAvailability, listRealTimeChannel. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listCustomerEligibilityRule`, `catalogue#listProductPriceAvailability`, `promotions#listRealTimeAvailability`, `catalogue#listRealTimeChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-28 | AM-TICKETING-P08-6 | [BE] CatalogueService: listRevenueDemandImpact, listSaleChannel, listScenarioModelingWhat, listSignalDataQuality | 8 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-11 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listRevenueDemandImpact, listSaleChannel, listScenarioModelingWhat, listSignalDataQuality. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listRevenueDemandImpact`, `catalogue#listSaleChannel`, `catalogue#listScenarioModelingWhat`, `catalogue#listSignalDataQuality` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-13 | AM-TICKETING-P08-7 | [DB] Forward migration V1130__catalogue.sql: catalogue for Ticketing · Venue Management 7 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE MIG-PLATFORM PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.event_type, catalogue.space. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (catalogue.event_type: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.event_type: rename column ticket_names_date to is_ticket_dated, rename column multi_day to is_multi_day; catalogue.space: drop index space_venue_map_zone_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.event_type`, `catalogue.space` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-14 | AM-TICKETING-P08-7 | [DB] Forward migration V1190__catalogue.sql: catalogue for Ticketing · Venue Management 7 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.event_reschedule, catalogue.prepaid_minutes. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.event_reschedule: rename column refund_fees to refunds_fees; catalogue.prepaid_minutes: rename column band_multipliers_apply to applies_band_multipliers, rename column transferable_within_household to is_transferable_within_household); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.event_reschedule`, `catalogue.prepaid_minutes` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | MIG-ORDERS-4 | AM-TICKETING-P08-7 | [DB] Forward migration V1026__orders.sql: orders for Ticketing · Venue Management 7 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.member_exception. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (orders.member_exception: column scope_path, index member_exception_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `orders.member_exception.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.member_exception` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-CATALOGUE-ENTITLEMENT-5 | AM-TICKETING-P08-7 | [BE] CatalogueService: archiveEntitlementTemplate, getEntitlementTemplate, updateEntitlementTemplate | 8 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: archiveEntitlementTemplate, getEntitlementTemplate, updateEntitlementTemplate. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#archiveEntitlementTemplate`, `catalogue#getEntitlementTemplate`, `catalogue#updateEntitlementTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-5 | AM-TICKETING-P08-7 | [BE] CatalogueService: rescheduleEvent, setEventCapacityProfile, setEventRegistration, setPrepaidMinutePackage | 8 | Narayan Gaonkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rescheduleEvent, setEventCapacityProfile, setEventRegistration, setPrepaidMinutePackage. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#rescheduleEvent`, `catalogue#setEventCapacityProfile`, `catalogue#setEventRegistration`, `catalogue#setPrepaidMinutePackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-6 | AM-TICKETING-P08-7 | [BE] CatalogueService: setSpace | 2 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSpace. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setSpace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-CATALOGUE-16 | AM-TICKETING-P08-7 | [BE] CatalogueService: freezeEntitlement, reinstateEntitlement, setMembershipBenefit | 8 | New full-stack developer 2 | CatalogueService | MIG-ACCESS MIG-CATALOGUE-5 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: freezeEntitlement, reinstateEntitlement, setMembershipBenefit. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#freezeEntitlement`, `catalogue#reinstateEntitlement`, `catalogue#setMembershipBenefit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-9 | AM-TICKETING-P08-2 | [BE] CatalogueService: listProductRetirementSuspension, listProductTrailChange, listRollbackRecovery, listScheduledLifecycleActions | 5 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-4 MIG-CATALOGUE-5 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS PRD-W1-LANGUAGES PRD-W1-OWNER-FORMS PRD-W1-SALE-PERMISSIONS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-PRODUCT-1 | Operations: listProductRetirementSuspension, listProductTrailChange, listRollbackRecovery, listScheduledLifecycleActions. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listProductRetirementSuspension`, `catalogue#listProductTrailChange`, `catalogue#listRollbackRecovery`, `catalogue#listScheduledLifecycleActions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-ENTITLEMENT-3 | AM-TICKETING-P08-7 | [BE] CatalogueService: suspendEntitlement | 2 | Deep Khanvilkar | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: suspendEntitlement. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#suspendEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-GUESTS-1 | AM-IDENTITY-SECURITY-P08 | [BE] MarketingService: getGuestTimeline | 1 | Deep Khanvilkar | MarketingService | MIG-ACCESS MIG-MARKETING MIG-MARKETING-2 MIG-ORDERS PLATFORM-KERNEL PRD-W1-OWNER-FORMS SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-FNB-FNB-17 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-CONSENT-6 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-MARKETING-12 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-19 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-3 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-9 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-MARKETING-MARKETING-2 | Operations: getGuestTimeline. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getGuestTimeline` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-3 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: listCreditLimitExposure, listDepositGuaranteeFinancial, listMemberExceptionOverride, listMembershipAnnualPass | 8 | New full-stack developer 2 | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-2 MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-SSO-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-BILLING-3 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-16 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-8 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-2 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 VM-TENANCY-REQUEST-1 | Operations: listCreditLimitExposure, listDepositGuaranteeFinancial, listMemberExceptionOverride, listMembershipAnnualPass. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listCreditLimitExposure`, `subscription#listDepositGuaranteeFinancial`, `subscription#listMemberExceptionOverride`, `subscription#listMembershipAnnualPass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-6 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: getMembershipProductValidation, listMember, listMemberLifecycleCase, listMembershipActivationCredential | 8 | Narayan Gaonkar | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-SSO-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-16 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-8 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-TENANT-1 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-WHITELABEL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-2 VM-ORDER-REFUND-1 VM-TENANCY-REQUEST-1 | Operations: getMembershipProductValidation, listMember, listMemberLifecycleCase, listMembershipActivationCredential. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#getMembershipProductValidation`, `subscription#listMember`, `subscription#listMemberLifecycleCase`, `subscription#listMembershipActivationCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-7 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: listMembershipRenewalRetention, listMembershipUpgradeDowngrade, listRenewalAuto, listVisitAdmissionEntitlement | 8 | Surendra | PlatformService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-16 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-8 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-ORDER-REFUND-1 | Operations: listMembershipRenewalRetention, listMembershipUpgradeDowngrade, listRenewalAuto, listVisitAdmissionEntitlement. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Narayan Gaonkar) reviews. Done when `subscription#listMembershipRenewalRetention`, `subscription#listMembershipUpgradeDowngrade`, `subscription#listRenewalAuto`, `subscription#listVisitAdmissionEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-9 | AM-TICKETING-P08-7 | [BE] OrderService: createMemberException | 1 | Deep Khanvilkar | OrderService | MIG-ORDERS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMemberException. Spec: contracts (orders) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createMemberException` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-15 | AM-TICKETING-P08-8 | [DB] Forward migration V1244__catalogue.sql: catalogue for Ticketing · Venue Management 8 of 8 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE PRD-W1-DB VM-MIG-CATALOGUE | Tables: catalogue.performance_media. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: catalogue.performance_media: rename column participant_id to event_registration_id, rename index performance_media_participant_id_idx to performance_media_event_registration_id_idx, foreign key performance_media_asset_id_fkey, foreign key performance_media_event_registration_id_fkey, foreign key performance_media_performance_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `catalogue.performance_media` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 3 | SVC-TENANCY-ACCREDITATION-2 | AM-TICKETING-P08-8 | [BE] TenancyService: listAccessProfiles | 1 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-3 PLATFORM-KERNEL | Operations: listAccessProfiles. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 8; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#listAccessProfiles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-4 | AM-TICKETING-P08-8 | [BE] CatalogueService: setEventResourcePlan, setEventSchedule, setEventType | 5 | Surendra | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setEventResourcePlan, setEventSchedule, setEventType. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setEventResourcePlan`, `catalogue#setEventSchedule`, `catalogue#setEventType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-EVENTS-3 | AM-TICKETING-P08-7 | [BE] CatalogueService: estimateEventResourceCost, getEventResourcePlan, listEventTypes, listSpaces | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-13 PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-EVENTS-4 SVC-CATALOGUE-EVENTS-6 | Operations: estimateEventResourceCost, getEventResourcePlan, listEventTypes, listSpaces. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#estimateEventResourceCost`, `catalogue#getEventResourcePlan`, `catalogue#listEventTypes`, `catalogue#listSpaces` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-7 | AM-TICKETING-P08-8 | [BE] CatalogueService: assignPerformanceMedia | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignPerformanceMedia. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#assignPerformanceMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-PROMOTIONS-3 | AM-PRICING-PROMOTIONS-P08 | [DB] Forward migration V1124__promotions.sql: promotions for Pricing & Promotions · Venue Management 1 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-ORDERS MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.promotion_alert, promotions.recommendation_outcome. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (promotions.recommendation_outcome: column recorded_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: promotions.promotion_alert: foreign key promotion_alert_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.promotion_alert`, `promotions.recommendation_outcome` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-ALLOCATION-1 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listAllocationSplits, previewAllocationSplit | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAllocationSplits, previewAllocationSplit. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listAllocationSplits`, `promotions#previewAllocationSplit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-12 | AM-TICKETING-P08-3 | [BE] CatalogueService: listBundlePricingCommercial, listChannelBasedPricing, listCommercialPricing, listCommercialPricingStructure | 5 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-8 MIG-PRICING-2 MIG-PROMOTIONS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-45 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listBundlePricingCommercial, listChannelBasedPricing, listCommercialPricing, listCommercialPricingStructure. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundlePricingCommercial`, `catalogue#listChannelBasedPricing`, `catalogue#listCommercialPricing`, `catalogue#listCommercialPricingStructure` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-COUPON-3 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: getCouponCodeBatch | 1 | Deep Khanvilkar | CatalogueService | MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-COUPON-1 | Operations: getCouponCodeBatch. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getCouponCodeBatch` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-VOUCHER-2 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: redeemVoucher | 1 | Deep Khanvilkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations: redeemVoucher. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#redeemVoucher` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-PROMOTION-4 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: createCommercialCampaign, updateCommercialCampaign | 5 | Deep Khanvilkar | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCommercialCampaign, updateCommercialCampaign. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createCommercialCampaign`, `promotions#updateCommercialCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-36 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listCustomerMembershipSegment, listDiscountLimitGuardrail, listPaymentMethodBank, listPercentageFixedDiscount | 3 | Hrushikant Patkar | CatalogueService | MIG-MARKETING MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-LOYALTY-1 SVC-MARKETING-LOYALTY-3 SVC-MARKETING-SEGMENT-1 | Operations: listCustomerMembershipSegment, listDiscountLimitGuardrail, listPaymentMethodBank, listPercentageFixedDiscount. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCustomerMembershipSegment`, `promotions#listDiscountLimitGuardrail`, `promotions#listPaymentMethodBank`, `promotions#listPercentageFixedDiscount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-39 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listUniqueCodeGeneration, listUsageCapacityFrequency, listVolumeBulkTier, setRuleTestRecommendation | 3 | Surendra | CatalogueService | MIG-CATALOGUE MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 VM-CATALOGUE-PRODUCT-1 | Operations: listUniqueCodeGeneration, listUsageCapacityFrequency, listVolumeBulkTier, setRuleTestRecommendation. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listUniqueCodeGeneration`, `promotions#listUsageCapacityFrequency`, `promotions#listVolumeBulkTier`, `promotions#setRuleTestRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-UPSELL-2 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: getUpsellSuggestions | 2 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-MIG-PROMOTIONS | Operations: getUpsellSuggestions. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getUpsellSuggestions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-BUNDLE-3 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listBundles | 2 | New full-stack developer 2 | CatalogueService | MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 | Operations: listBundles. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-35 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listCampaignCalendarTimeline, listCampaignPromotionPerformance, listCartTransactionThreshold, listCodeEligibilityRestriction | 3 | New full-stack developer 1 | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listCampaignCalendarTimeline, listCampaignPromotionPerformance, listCartTransactionThreshold, listCodeEligibilityRestriction. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCampaignCalendarTimeline`, `promotions#listCampaignPromotionPerformance`, `promotions#listCartTransactionThreshold`, `promotions#listCodeEligibilityRestriction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-38 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listPromotionHealthPerformance, listPromotionPerformance, listSpecialPriceGuest, listTimeBasedSeasonal | 3 | New full-stack developer 2 | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listPromotionHealthPerformance, listPromotionPerformance, listSpecialPriceGuest, listTimeBasedSeasonal. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionHealthPerformance`, `promotions#listPromotionPerformance`, `promotions#listSpecialPriceGuest`, `promotions#listTimeBasedSeasonal` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-PROMOTIONS-3 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: getRecommendations | 1 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PROMOTIONS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: getRecommendations. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getRecommendations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-PROMOTIONS-4 | AM-PRICING-PROMOTIONS-P08-2 | [DB] Forward migration V1131__promotions.sql: promotions for Pricing & Promotions · Venue Management 2 of 8 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.partner_bundle_product. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (promotions.partner_bundle_product: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: promotions.partner_bundle_product: foreign key partner_bundle_product_bundle_component_id_fkey, drop index partner_bundle_product_external_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `promotions.partner_bundle_product.connection_status`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.partner_bundle_product` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-BUNDLE-4 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listBundlePartnerProductMappings, setBundlePartnerProductMappings | 5 | Hrushikant Patkar | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBundlePartnerProductMappings, setBundlePartnerProductMappings. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundlePartnerProductMappings`, `promotions#setBundlePartnerProductMappings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-40 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listAdvancedOffer, listAdvancedOfferGuardrail, listBundleAvailabilityCapacity, listBundleValidityScheduling | 3 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listAdvancedOffer, listAdvancedOfferGuardrail, listBundleAvailabilityCapacity, listBundleValidityScheduling. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listAdvancedOffer`, `promotions#listAdvancedOfferGuardrail`, `promotions#listBundleAvailabilityCapacity`, `promotions#listBundleValidityScheduling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-41 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listCheapestLowestValue, listCodeSecurityFraud, listComponentInventoryAvailability, listDynamicBundle | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-LEASE-1 | Operations: listCheapestLowestValue, listCodeSecurityFraud, listComponentInventoryAvailability, listDynamicBundle. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCheapestLowestValue`, `promotions#listCodeSecurityFraud`, `promotions#listComponentInventoryAvailability`, `promotions#listDynamicBundle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-42 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listDynamicBundle2, listDynamicBundleRule, listMultiBuyQuantity, listOfferBasketTrace | 2 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listDynamicBundle2, listDynamicBundleRule, listMultiBuyQuantity, listOfferBasketTrace. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listDynamicBundle2`, `promotions#listDynamicBundleRule`, `promotions#listMultiBuyQuantity`, `promotions#listOfferBasketTrace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-44 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listRewardSelectionSubstitution, listValidityDateTime, simulateBundlePreviewRecommendation | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listRewardSelectionSubstitution, listValidityDateTime, simulateBundlePreviewRecommendation. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listRewardSelectionSubstitution`, `promotions#listValidityDateTime`, `promotions#simulateBundlePreviewRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-PROMOTIONS-8 | AM-PRICING-PROMOTIONS-P08-3 | [DB] Forward migration V1200__promotions.sql: promotions for Pricing & Promotions · Venue Management 3 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.bundle_capacity_policy, promotions.promotion_conflict. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: promotions.bundle_capacity_policy: foreign key bundle_capacity_policy_bundle_id_fkey; promotions.promotion_conflict: foreign key promotion_conflict_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.bundle_capacity_policy`, `promotions.promotion_conflict` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-BUNDLE-10 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listBundleCapacityPolicies, setBundleCapacityPolicy | 3 | Hrushikant Patkar | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBundleCapacityPolicies, setBundleCapacityPolicy. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleCapacityPolicies`, `promotions#setBundleCapacityPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-37 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listPromotionActivityVersion, listPromotionAlertException, listPromotionCampaign, listPromotionChannel | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-10 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-BUNDLE-4 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 | Operations: listPromotionActivityVersion, listPromotionAlertException, listPromotionCampaign, listPromotionChannel. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionActivityVersion`, `promotions#listPromotionAlertException`, `promotions#listPromotionCampaign`, `promotions#listPromotionChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-43 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listPartnerExternalProduct, listRedemption, listRedemptionCodeLookup, listRevenueAllocationCost | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-4 PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-10 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-BUNDLE-4 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listPartnerExternalProduct, listRedemption, listRedemptionCodeLookup, listRevenueAllocationCost. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPartnerExternalProduct`, `promotions#listRedemption`, `promotions#listRedemptionCodeLookup`, `promotions#listRevenueAllocationCost` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-82 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listCrmCustomerSegment, listDynamicComponentSubstitution, listMembershipLoyaltyGuest, listPartnerPaymentEligibility | 3 | Pallavi Sawant | CatalogueService | MIG-MARKETING MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-LOYALTY-1 SVC-MARKETING-LOYALTY-2 SVC-MARKETING-LOYALTY-3 SVC-MARKETING-MARKETING-11 SVC-MARKETING-MARKETING-5 SVC-MARKETING-SEGMENT-1 | Operations: listCrmCustomerSegment, listDynamicComponentSubstitution, listMembershipLoyaltyGuest, listPartnerPaymentEligibility. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCrmCustomerSegment`, `promotions#listDynamicComponentSubstitution`, `promotions#listMembershipLoyaltyGuest`, `promotions#listPartnerPaymentEligibility` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-83 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listPromotionPriorityHierarchy, listStackingConflict, listTargetingConflictFrequency, listTargetingEligibility | 3 | Hrushikant Patkar | CatalogueService | MIG-MARKETING MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 | Operations: listPromotionPriorityHierarchy, listStackingConflict, listTargetingConflictFrequency, listTargetingEligibility. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionPriorityHierarchy`, `promotions#listStackingConflict`, `promotions#listTargetingConflictFrequency`, `promotions#listTargetingEligibility` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-80 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listAudienceDiscoveryTargeting, listAudiencePreviewReach, listBehavioralTransactionTargeting, listBundleAvailabilityChannel | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-10 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listAudienceDiscoveryTargeting, listAudiencePreviewReach, listBehavioralTransactionTargeting, listBundleAvailabilityChannel. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listAudienceDiscoveryTargeting`, `promotions#listAudiencePreviewReach`, `promotions#listBehavioralTransactionTargeting`, `promotions#listBundleAvailabilityChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-81 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listBundleAvailabilityForecast, listBundleSellabilityDependency, listCapacityPoolReservation, listContextLocationChannel | 3 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-10 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-LEASE-1 | Operations: listBundleAvailabilityForecast, listBundleSellabilityDependency, listCapacityPoolReservation, listContextLocationChannel. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleAvailabilityForecast`, `promotions#listBundleSellabilityDependency`, `promotions#listCapacityPoolReservation`, `promotions#listContextLocationChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | DEVICE-BOCA-FGL | AM-DEVICES-BOCA | [BE] BOCA ticket and wristband printing: FGL driver behind the ticketPrinter port | 8 | Hrushikant Patkar |  | PLATFORM-KERNEL SVC-ORDER-ORDER-4 SVC-ORDER-ORDERS-5 SVC-ORDER-ORDERS-8 | BOCA ticket and wristband printing: FGL driver behind the ticketPrinter port. Builds: `adr ADR-0015`. In the device app (ADR-0015 Tier A; the client confirmed BOCA and sent its documents on 5 October 2026, sources/client/2026-10-05-allam-boca-printer.md; CHG-R4-002). Implement the ticketPrinter port of handoff/integration-register.md for BOCA in FGL: render a ticket or wristband from the ticket designer's layout (updateTicketTemplate, listTicketTemplates; the same layout printTicketProof previews) to FGL: text, fonts including Arabic (as a bitmap where FGL needs it), barcode and QR, the logo bitmap and the cut; printer status and errors (paper out, jam, offline) reported so the kiosk shows KSK-010 Print failure and the POS its reprint path (reprintOrder, POS-026); reprint; and a virtual (emulated) BOCA printer for the tests and CI. RFID encoding on the BOCA Lemur is built behind a flag, off, until the client confirms its scope (Decisions Register, pending). The hardware validation runs on the real unit when it reaches the India office. Done when: a kiosk sale and a POS sale print a ticket and a wristband from the designer layout on the emulator with the same output as the designer's print preview, print failures reach KSK-010 and POS-026, and the hardware check is listed as pending the device.
7 | 3 | MIG-WHITELABEL-2 | AM-WHITE-LABEL-KIOSK | [DB] Forward migration V1199__whitelabel.sql: whitelabel for White Label · Kiosk customisation (5 tables) | 3 | Hrushikant Patkar | WhiteLabelService | MIG-BASELINE MIG-WHITELABEL | Tables: whitelabel.kiosk_assignment, whitelabel.kiosk_config, whitelabel.kiosk_config_attract_slide, whitelabel.kiosk_config_start_tile, whitelabel.kiosk_config_version. Source DDL: backend/tenant/V0100__after_r1_20261006.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0101__after_r1_20261006.sql (whitelabel.kiosk_assignment: indexes kiosk_assignment_assigned_by_principal_id_idx, kiosk_assignment_kiosk_config_id_idx, kiosk_assignment_venue_id_idx and kiosk_assignment_workstation_id_idx; whitelabel.kiosk_config: index kiosk_config_venue_id_idx; whitelabel.kiosk_config_attract_slide: index kiosk_config_attract_slide_kiosk_config_id_idx; whitelabel.kiosk_config_start_tile: index kiosk_config_start_tile_kiosk_config_id_idx; whitelabel.kiosk_config_version: indexes kiosk_config_version_kiosk_config_id_idx and kiosk_config_version_published_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: whitelabel.kiosk_config: foreign key kiosk_config_version_kiosk_config_id_fkey (from whitelabel.kiosk_config_version); whitelabel.kiosk_config_version: foreign key kiosk_config_version_kiosk_config_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (whitelabel.kiosk_config_version: indexes kiosk_config_version_kiosk_config_id_version_number_uniq and kiosk_config_version_kiosk_config_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `whitelabel.kiosk_assignment`, `whitelabel.kiosk_config`, `whitelabel.kiosk_config_attract_slide`, `whitelabel.kiosk_config_start_tile`, `whitelabel.kiosk_config_version` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WHITELABEL-KIOSK-1 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: assignKiosk, createKioskConfig, deleteKioskConfig, getKioskConfig | 8 | Hrushikant Patkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignKiosk, createKioskConfig, deleteKioskConfig, getKioskConfig. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#assignKiosk`, `white-label#createKioskConfig`, `white-label#deleteKioskConfig`, `white-label#getKioskConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WHITELABEL-KIOSK-3 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: listKioskConfigs, publishKioskConfigs, restoreKioskConfigVersion, setKioskOutOfService | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listKioskConfigs, publishKioskConfigs, restoreKioskConfigVersion, setKioskOutOfService. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#listKioskConfigs`, `white-label#publishKioskConfigs`, `white-label#restoreKioskConfigVersion`, `white-label#setKioskOutOfService` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WHITELABEL-KIOSK-4 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: updateKioskConfig | 3 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateKioskConfig. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#updateKioskConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-WHITELABEL-KIOSK-2 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: getKioskConfigValidation, getPublishedKioskConfig, listKioskAssignments, listKioskConfigVersions | 5 | Hrushikant Patkar | WhiteLabelService | MIG-CATALOGUE MIG-WHITELABEL MIG-WHITELABEL-2 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-WHITELABEL-BOOKINGFLOWS-1 SVC-WHITELABEL-BOOKINGFLOWS-2 SVC-WHITELABEL-KIOSK-1 SVC-WHITELABEL-KIOSK-3 SVC-WHITELABEL-KIOSK-4 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-PUBLISHING-3 VM-CATALOGUE-PRODUCT-1 | Operations: getKioskConfigValidation, getPublishedKioskConfig, listKioskAssignments, listKioskConfigVersions. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#getKioskConfigValidation`, `white-label#getPublishedKioskConfig`, `white-label#listKioskAssignments`, `white-label#listKioskConfigVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-91 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: listPromotionExclusionCompatibility, listRedemptionDiscountExposure, listThresholdActionAutomatic, setCampaignBudgetFinancial | 5 | Pallavi Sawant | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPromotionExclusionCompatibility, listRedemptionDiscountExposure, listThresholdActionAutomatic, setCampaignBudgetFinancial. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionExclusionCompatibility`, `promotions#listRedemptionDiscountExposure`, `promotions#listThresholdActionAutomatic`, `promotions#setCampaignBudgetFinancial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-88 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: approveCampaignWorkflow, approveDecision, listBestOfferCustomer, listBudgetConsumptionForecast | 5 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-91 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 | Operations: approveCampaignWorkflow, approveDecision, listBestOfferCustomer, listBudgetConsumptionForecast. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#approveCampaignWorkflow`, `promotions#approveDecision`, `promotions#listBestOfferCustomer`, `promotions#listBudgetConsumptionForecast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-PROMOTIONS-10 | AM-PRICING-PROMOTIONS-P08-5 | [DB] Forward migration V1253__promotions.sql: promotions for Pricing & Promotions · Venue Management 5 of 8 (4 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.product_relationship, promotions.recommendation_experiment, promotions.recommendation_strategy, promotions.recommendation_suppression. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (promotions.recommendation_experiment: column variants, index recommendation_experiment_code_uniq; promotions.recommendation_strategy: index recommendation_strategy_code_uniq; promotions.recommendation_suppression: column hard_exclusions); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: promotions.product_relationship: foreign key product_relationship_from_product_id_fkey, foreign key product_relationship_to_product_id_fkey; promotions.recommendation_strategy: rename column exclude_in_basket to excludes_in_basket); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `promotions.recommendation_experiment.variants`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `promotions.product_relationship`, `promotions.recommendation_experiment`, `promotions.recommendation_strategy`, `promotions.recommendation_suppression` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-1 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: createRecommendationStrategy, getRecommendationPerformance, listProductRelationships, listRecommendationStrategies | 5 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS-10 MIG-PROMOTIONS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createRecommendationStrategy, getRecommendationPerformance, listProductRelationships, listRecommendationStrategies. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createRecommendationStrategy`, `promotions#getRecommendationPerformance`, `promotions#listProductRelationships`, `promotions#listRecommendationStrategies` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-2 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: setProductRelationships, setRecommendationSuppression, updateRecommendationStrategy | 5 | Hrushikant Patkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setProductRelationships, setRecommendationSuppression, updateRecommendationStrategy. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#setProductRelationships`, `promotions#setRecommendationSuppression`, `promotions#updateRecommendationStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-3 | AM-PRICING-PROMOTIONS-P08-6 | [BE] CatalogueService: getProductAffinity, simulateRecommendationStrategy | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-PROMOTIONS-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getProductAffinity, simulateRecommendationStrategy. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 6 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getProductAffinity`, `promotions#simulateRecommendationStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RENTAL-2 | AM-PRICING-PROMOTIONS-P08-8 | [DB] Forward migration V1021__rental.sql: rental for Pricing & Promotions · Venue Management 8 of 8 (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PLATFORM VM-MIG-RENTAL | Tables: rental.availability_rules, rental.blackout, rental.duration_rules, rental.equipment_assignment, rental.inventory_model, rental.location_rule, rental.product. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (rental.availability_rules: columns operating_windows and product_id, constraint availability_rules_product_id_fkey, indexes availability_rules_product_id_idx and availability_rules_product_id_uniq; rental.duration_rules: column product_id, constraint duration_rules_product_id_fkey, indexes duration_rules_product_id_idx and duration_rules_product_id_uniq; rental.equipment_assignment: column booking_id, constraint equipment_assignment_booking_id_fkey, index equipment_assignment_booking_id_idx; rental.inventory_model: columns components and product_id, constraint inventory_model_product_id_fkey, indexes inventory_model_product_id_idx and inventory_model_product_id_uniq; rental.location_rule: column product_id, constraint location_rule_product_id_fkey, index location_rule_product_id_idx; rental.product: index product_tenant_id_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: rental.availability_rules: rename column release_on_payment_failure to releases_on_payment_failure; rental.equipment_assignment: rename column assigned_manually to is_assigned_manually, foreign key equipment_assignment_asset_id_fkey; rental.inventory_model: rename column assignment_required_at_checkout to requires_assignment_at_checkout; rental.location_rule: foreign key location_rule_location_id_fkey; rental.product: foreign key booking_product_id_fkey (from rental.booking), foreign key quote_product_id_fkey (from rental.quote)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key booking_product_id_fkey here** (rental.booking to rental.product, guarded): VM-MIG-RENTAL creates rental.booking before rental.product exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `rental.availability_rules`, `rental.blackout`, `rental.duration_rules`, `rental.equipment_assignment`, `rental.inventory_model`, `rental.location_rule`, `rental.product` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | MIG-MARKETING-8 | AM-PRICING-PROMOTIONS-P08-8 | [DB] Forward migration V1169__marketing.sql: marketing for Pricing & Promotions · Venue Management 8 of 8 (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.audience_list. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.audience_list: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.audience_list` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-4 | AM-PRICING-PROMOTIONS-P08-8 | [BE] CatalogueService: concludeRecommendationExperiment, createRecommendationExperiment, listRecommendationExperiments | 5 | Hrushikant Patkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: concludeRecommendationExperiment, createRecommendationExperiment, listRecommendationExperiments. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 8 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#concludeRecommendationExperiment`, `promotions#createRecommendationExperiment`, `promotions#listRecommendationExperiments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-RENTAL-2 | AM-PRICING-PROMOTIONS-P08-8 | [BE] VenueOpsService: getRentalAvailability | 1 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE MIG-RENTAL-2 PLATFORM-KERNEL VM-MIG-RENTAL VM-VENUEOPS-ASSET-1 VM-VENUEOPS-ASSET-2 | Operations: getRentalAvailability. Spec: contracts (rental) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 8 of 8; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#getRentalAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-AI-GENERATE-4 | AM-PRICING-PROMOTIONS-P08-8 | [BE] AiService: proposeLookalikeSegment | 2 | Pallavi Sawant | AiService | MIG-AI MIG-MARKETING MIG-MARKETING-8 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeLookalikeSegment. Spec: contracts (ai) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 8 of 8; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#proposeLookalikeSegment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-VENUEOPS-VENUEMAP-4 | AM-SEATING-MAPS-P06 | [BE] VenueOpsService: getVenueMapLive | 1 | Pranay Shinde | VenueOpsService | MIG-ACCESS MIG-QUEUE MIG-VENUEMAP PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-ENTRY-2 SVC-VENUEOPS-ENTRY-3 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-VENUEOPS-ENTRY-1 VM-VENUEOPS-VENUEMAP-1 | Operations: getVenueMapLive. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Staff App; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `venue-map#getVenueMapLive` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-SEATING-6 | AM-SEATING-MAPS-P08 | [DB] Forward migration V1068__seating.sql: seating for Seating & Maps · Venue Management 1 of 5 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-SEATING | Tables: seating.hold_type, seating.seat_rules. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: seating.hold_type: rename column visible_to_guest to is_visible_to_guest, foreign key hold_pool_hold_type_id_fkey (from seating.hold_pool)); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `seating.hold_type`, `seating.seat_rules` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-CATALOGUE-SEATING-6 | AM-SEATING-MAPS-P08 | [BE] CatalogueService: createSeatHoldPool, getSeatRules, listSeatHoldTypes, releaseSeatHoldPool | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING-2 MIG-SEATING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatHoldPool, getSeatRules, listSeatHoldTypes, releaseSeatHoldPool. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 1 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#createSeatHoldPool`, `seating#getSeatRules`, `seating#listSeatHoldTypes`, `seating#releaseSeatHoldPool` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-7 | AM-SEATING-MAPS-P08 | [BE] CatalogueService: setSeatHoldType, setSeatRules, validateSeatCompliance | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-3 MIG-SEATING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSeatHoldType, setSeatRules, validateSeatCompliance. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 1 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#setSeatHoldType`, `seating#setSeatRules`, `seating#validateSeatCompliance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-SEATING-7 | AM-SEATING-MAPS-P08-2 | [DB] Forward migration V1202__seating.sql: seating for Seating & Maps · Venue Management 2 of 5 (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-ORDERS MIG-SEATING | Tables: seating.group_request, seating.group_request_participant, seating.reassignment. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: seating.group_request: foreign key group_request_performance_id_fkey; seating.reassignment: rename column refund_issued to is_refund_issued); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `seating.group_request`, `seating.group_request_participant`, `seating.reassignment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 3 | SVC-LEDGER-FINANCE-2 | AM-SEATING-MAPS-P08-2 | [BE] LedgerService: recordDeposit | 2 | Pranay Shinde | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: recordDeposit. Spec: contracts (finance) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#recordDeposit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-SEATING-8 | AM-SEATING-MAPS-P08-2 | [BE] CatalogueService: allocateGroupSeats, createGroupSeatRequest, listGroupSeatRequests, reassignSeats | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-3 MIG-SEATING-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: allocateGroupSeats, createGroupSeatRequest, listGroupSeatRequests, reassignSeats. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#allocateGroupSeats`, `seating#createGroupSeatRequest`, `seating#listGroupSeatRequests`, `seating#reassignSeats` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-SEATING-9 | AM-SEATING-MAPS-P08-2 | [BE] CatalogueService: setGroupSeatRoster | 1 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGroupSeatRoster. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#setGroupSeatRoster` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-SEATING-8 | AM-SEATING-MAPS-P08-3 | [DB] Forward migration V1203__seating.sql: seating for Seating & Maps · Venue Management 3 of 5 (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PLATFORM MIG-SEATING | Tables: seating.import_job, seating.seat_map_template, seating.zone. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `seating.import_job`, `seating.seat_map_template`, `seating.zone` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
12 | 3 | SVC-TENANCY-TENANCY-12 | AM-SEATING-MAPS-P08-3 | [BE] TenancyService: listConfigurationProfiles | 1 | Pranay Shinde | TenancyService | MIG-PLATFORM PLATFORM-KERNEL VM-TENANCY-TENANCY-2 | Operations: listConfigurationProfiles. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#listConfigurationProfiles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-IMPORT-1 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: getImportJob, importSeatGeometry, importSeatManifest | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getImportJob, importSeatGeometry, importSeatManifest. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getImportJob`, `seating#importSeatGeometry`, `seating#importSeatManifest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-10 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: getSeatMapImport, importSeatMap, setMapZones | 5 | Hrushikant Patkar | CatalogueService | MIG-ASSETS MIG-SEATING MIG-SEATING-3 MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getSeatMapImport, importSeatMap, setMapZones. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getSeatMapImport`, `seating#importSeatMap`, `seating#setMapZones` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATMAP-5 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: cloneSeatMap, createSeatMapTemplate, listSeatMapTemplates, listSeatMaps | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cloneSeatMap, createSeatMapTemplate, listSeatMapTemplates, listSeatMaps. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#cloneSeatMap`, `seating#createSeatMapTemplate`, `seating#listSeatMapTemplates`, `seating#listSeatMaps` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATMAP-6 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: publishSeatMap, updateSeats, validateSeatMap | 5 | Pranay Shinde | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: publishSeatMap, updateSeats, validateSeatMap. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#publishSeatMap`, `seating#updateSeats`, `seating#validateSeatMap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-AI-CONFIGURE-4 | AM-SEATING-MAPS-P08-3 | [BE] AiService: proposeSeatMapChanges | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-AI-2 MIG-AI-3 MIG-ORDERS MIG-SEATING MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeSeatMapChanges. Spec: contracts (ai) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#proposeSeatMapChanges` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-AI-RECOMMEND-2 | AM-PRICING-PROMOTIONS-P08-7 | [BE] AiService: explainRecommendationDecision | 1 | Hrushikant Patkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-ACTIONS-1 SVC-AI-ASSIST-1 SVC-AI-CONFIGURE-1 SVC-AI-CONFIGURE-4 SVC-AI-FORECAST-1 SVC-AI-FORECAST-3 SVC-AI-GENERATE-1 SVC-AI-GENERATE-2 SVC-AI-GENERATE-4 SVC-AI-GOVERNANCE-1 SVC-AI-GOVERNANCE-2 SVC-AI-GOVERNANCE-3 SVC-AI-MODELS-1 SVC-AI-MODELS-2 SVC-AI-MONITORING-1 SVC-AI-RECOMMEND-1 | Operations: explainRecommendationDecision. Spec: contracts (ai) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 7 of 8; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#explainRecommendationDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-BLOCK-1 | AM-SEATING-MAPS-P08-4 | [BE] CatalogueService: createSeatBlock, listSeatBlocks | 3 | Narayan Gaonkar | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createSeatBlock, listSeatBlocks. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 4 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#createSeatBlock`, `seating#listSeatBlocks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-IMPORT-2 | AM-SEATING-MAPS-P08-4 | [BE] CatalogueService: commitImportJob | 2 | Hrushikant Patkar | CatalogueService | MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: commitImportJob. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 4 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#commitImportJob` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-11 | AM-SEATING-MAPS-P08-4 | [BE] CatalogueService: copySeatMapSection, diffSeatMapVersions, getSeatInventory | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-2 MIG-SEATING-3 MIG-SEATING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: copySeatMapSection, diffSeatMapVersions, getSeatInventory. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 4 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#copySeatMapSection`, `seating#diffSeatMapVersions`, `seating#getSeatInventory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-RULES-1 | AM-SEATING-MAPS-P08-5 | [BE] CatalogueService: getSeatingRules, setSeatingRules | 3 | Hrushikant Patkar | CatalogueService | MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getSeatingRules, setSeatingRules. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 5 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getSeatingRules`, `seating#setSeatingRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-12 | AM-SEATING-MAPS-P08-5 | [BE] CatalogueService: assignSeats, getSeatReconciliation | 2 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-SEATING MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignSeats, getSeatReconciliation. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 5 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#assignSeats`, `seating#getSeatReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-SEATMAP-4 | AM-SEATING-MAPS-P08-2 | [BE] CatalogueService: listSeats | 1 | Surendra | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-SEATING-12 SVC-CATALOGUE-SEATMAP-1 | Operations: listSeats. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#listSeats` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-BLOCK-2 | AM-SEATING-MAPS-P10 | [BE] CatalogueService: allocateBlockedSeats, relinquishSeatBlock | 3 | Narayan Gaonkar | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: allocateBlockedSeats, relinquishSeatBlock. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Partner Portal; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#allocateBlockedSeats`, `seating#relinquishSeatBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-6 | AM-ORDERS-RESERVATIONS-P06 | [DB] Forward migration V1250__access.sql: access for Orders & Reservations · Staff App (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.media_binding_rule. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.media_binding_rule: drop index media_binding_rule_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.media_binding_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | SVC-ORDER-ORDERS-19 | AM-ORDERS-RESERVATIONS-P06 | [BE] OrderService: splitOrder | 2 | Hrushikant Patkar | OrderService | MIG-ORDERS MIG-ORDERS-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: splitOrder. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Staff App; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#splitOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-14 | AM-ORDERS-RESERVATIONS-P06 | [BE] AccessService: setMediaBindingActivation | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setMediaBindingActivation. Spec: contracts (access) at the release tag, served by ADAM. Built for Orders & Reservations · Staff App; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setMediaBindingActivation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-12 | AM-ORDERS-RESERVATIONS-P08 | [DB] Forward migration V1143__orders.sql: orders for Orders & Reservations · Venue Management 1 of 8 (4 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-CATALOGUE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.resale_eligibility_rule, orders.resale_fee_policy, orders.resale_marketplace_config, orders.resale_settlement. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.resale_eligibility_rule: rename column resale_immediately_after_purchase to allows_resale_immediately_after_purchase, rename column original_purchaser_only to is_original_purchaser_only, drop index resale_eligibility_rule_product_id_idx; orders.resale_fee_policy: rename column fees_shown_to_seller to shows_fees_to_seller; orders.resale_marketplace_config: rename column seller_can_edit_price to can_seller_edit_price; orders.resale_settlement: foreign key resale_settlement_seller_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.resale_eligibility_rule`, `orders.resale_fee_policy`, `orders.resale_marketplace_config`, `orders.resale_settlement` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-5 | AM-ORDERS-RESERVATIONS-P08 | [BE] OrderService: setResaleEligibilityRule | 2 | Hrushikant Patkar | OrderService | MIG-ORDERS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResaleEligibilityRule. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 1 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setResaleEligibilityRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-13 | AM-ORDERS-RESERVATIONS-P08-2 | [DB] Forward migration V1192__orders.sql: orders for Orders & Reservations · Venue Management 2 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.resale_recommendation. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.resale_recommendation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-6 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: approveListingModeration, createListingSeller, listBuyerPurchaseResale, listCapacityInventoryReconciliation | 8 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveListingModeration, createListingSeller, listBuyerPurchaseResale, listCapacityInventoryReconciliation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#approveListingModeration`, `orders#createListingSeller`, `orders#listBuyerPurchaseResale`, `orders#listCapacityInventoryReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-9 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: listResalePricingPrice, listSellerSettlementPayout, listTicketOwnershipTransfer, setResaleMarketplaceRecommendation | 3 | Narayan Gaonkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-ORDERS-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listResalePricingPrice, listSellerSettlementPayout, listTicketOwnershipTransfer, setResaleMarketplaceRecommendation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listResalePricingPrice`, `orders#listSellerSettlementPayout`, `orders#listTicketOwnershipTransfer`, `orders#setResaleMarketplaceRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-23 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: getResaleFeePolicy, holdResaleSettlement, releaseResaleSettlementHold, setResaleFeePolicy | 8 | Hrushikant Patkar | OrderService | MIG-ORDERS-12 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getResaleFeePolicy, holdResaleSettlement, releaseResaleSettlementHold, setResaleFeePolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getResaleFeePolicy`, `orders#holdResaleSettlement`, `orders#releaseResaleSettlementHold`, `orders#setResaleFeePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-24 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: setResaleMarketplaceConfig | 2 | Narayan Gaonkar | OrderService | MIG-ORDERS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResaleMarketplaceConfig. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setResaleMarketplaceConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-ORDERS-22 | AM-ORDERS-RESERVATIONS-P08 | [BE] OrderService: getResaleMarketplaceConfig | 2 | Narayan Gaonkar | OrderService | MIG-ORDERS-12 PLATFORM-KERNEL SVC-ORDER-ORDERS-24 | Operations: getResaleMarketplaceConfig. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 1 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getResaleMarketplaceConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-14 | AM-ORDERS-RESERVATIONS-P08-3 | [DB] Forward migration V1204__orders.sql: orders for Orders & Reservations · Venue Management 3 of 8 (2 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.upgrade, orders.upgrade_rule. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.upgrade: foreign key upgrade_original_order_line_id_fkey; orders.upgrade_rule: rename column exclude_fees_from_credit to excludes_fees_from_credit); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (orders.upgrade: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.upgrade`, `orders.upgrade_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-13 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: setProRataResidual, setUpgradeConversionPath | 3 | Narayan Gaonkar | OrderService | MIG-CATALOGUE MIG-ORDERS-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setProRataResidual, setUpgradeConversionPath. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setProRataResidual`, `orders#setUpgradeConversionPath` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-15 | AM-ORDERS-RESERVATIONS-P08-4 | [DB] Forward migration V1205__orders.sql: orders for Orders & Reservations · Venue Management 4 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.payment_allocation_rule. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.payment_allocation_rule: drop index payment_allocation_rule_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.payment_allocation_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-11 | AM-ORDERS-RESERVATIONS-P08-4 | [DB] Forward migration V1206__payments.sql: payments for Orders & Reservations · Venue Management 4 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.risk_rules. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.risk_rules: columns rules and lists); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.risk_rules` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-14 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: createUpgradeCredentialRegeneration, listBulkGroupAssisted, listOrderPaymentDetail, listPersonTypeProduct | 5 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: createUpgradeCredentialRegeneration, listBulkGroupAssisted, listOrderPaymentDetail, listPersonTypeProduct. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createUpgradeCredentialRegeneration`, `orders#listBulkGroupAssisted`, `orders#listOrderPaymentDetail`, `orders#listPersonTypeProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-25 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: cancelPaymentLink, createPaymentLink, listFraudRules, listPaymentAllocationRules | 5 | Narayan Gaonkar | OrderService | MIG-MARKETING MIG-ORDERS MIG-ORDERS-15 MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelPaymentLink, createPaymentLink, listFraudRules, listPaymentAllocationRules. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#cancelPaymentLink`, `orders#createPaymentLink`, `orders#listFraudRules`, `orders#listPaymentAllocationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-26 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: listUpgrades, resendPaymentLink, setFraudRules, voidPayment | 8 | Hrushikant Patkar | OrderService | MIG-MARKETING MIG-ORDERS MIG-ORDERS-14 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listUpgrades, resendPaymentLink, setFraudRules, voidPayment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listUpgrades`, `orders#resendPaymentLink`, `orders#setFraudRules`, `orders#voidPayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-DRAFTED-15 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: listUpgradeException, listVoidReversalSame, setMultiPaymentSplit | 3 | Narayan Gaonkar | OrderService | MIG-IDENTITY MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-15 MIG-PAYMENTS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: listUpgradeException, listVoidReversalSame, setMultiPaymentSplit. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listUpgradeException`, `orders#listVoidReversalSame`, `orders#setMultiPaymentSplit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-9 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: setPaymentRiskRules | 2 | Narayan Gaonkar | OrderService | MIG-PAYMENTS-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentRiskRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setPaymentRiskRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-16 | AM-ORDERS-RESERVATIONS-P08-5 | [DB] Forward migration V1207__orders.sql: orders for Orders & Reservations · Venue Management 5 of 8 (3 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.order_source_channel, orders.reservation_hold_policy, orders.status_transition_rule. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.reservation_hold_policy: rename column extension_requires_approval to requires_extension_approval, drop index reservation_hold_policy_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.order_source_channel`, `orders.reservation_hold_policy`, `orders.status_transition_rule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-ORDER-ORDERS-27 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: listChargebacks, respondToChargeback | 5 | Narayan Gaonkar | OrderService | MIG-ACCESS MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ORDERS | Operations: listChargebacks, respondToChargeback. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listChargebacks`, `orders#respondToChargeback` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-16 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: createOrderSourceChannel, listCapacityReservationInventory, listOrderLifecycleTimeline, listOrderLineProduct | 5 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-16 MIG-ORDERS-3 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createOrderSourceChannel, listCapacityReservationInventory, listOrderLifecycleTimeline, listOrderLineProduct. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createOrderSourceChannel`, `orders#listCapacityReservationInventory`, `orders#listOrderLifecycleTimeline`, `orders#listOrderLineProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-17 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: listOrderReservation, listReservationConfirmationExpiry, setCustomerGuestAccount, setOrderReservationStatus | 8 | Narayan Gaonkar | OrderService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-16 MIG-ORDERS-2 MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listOrderReservation, listReservationConfirmationExpiry, setCustomerGuestAccount, setOrderReservationStatus. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listOrderReservation`, `orders#listReservationConfirmationExpiry`, `orders#setCustomerGuestAccount`, `orders#setOrderReservationStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-18 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: setReservationHoldPolicy | 2 | Hrushikant Patkar | OrderService | MIG-ORDERS-16 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setReservationHoldPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setReservationHoldPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-CART-4 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: listAbandonedCarts | 1 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-VENUEOPS-VISITPLAN-1 | Operations: listAbandonedCarts. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listAbandonedCarts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-17 | AM-ORDERS-RESERVATIONS-P08-6 | [DB] Forward migration V1208__orders.sql: orders for Orders & Reservations · Venue Management 6 of 8 (5 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.after_sale_policy_window, orders.deposit_policy, orders.external_reference_mapping, orders.group_payment_milestone, orders.group_payment_schedule. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (orders.group_payment_milestone: row-level security apply_parent_rls; orders.group_payment_schedule: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.external_reference_mapping: foreign key external_reference_mapping_merchant_id_fkey, foreign key external_reference_mapping_order_id_fkey; orders.group_payment_schedule: foreign key group_payment_schedule_group_booking_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (orders.group_payment_milestone: row-level security apply_parent_split_rls; orders.group_payment_schedule: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `orders.external_reference_mapping.merchant_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.after_sale_policy_window`, `orders.deposit_policy`, `orders.external_reference_mapping`, `orders.group_payment_milestone`, `orders.group_payment_schedule` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-12 | AM-ORDERS-RESERVATIONS-P08-6 | [DB] Forward migration V1209__payments.sql: payments for Orders & Reservations · Venue Management 6 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.deposit_activity. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (payments.deposit_activity: column scope_path, index deposit_activity_scope_path_idx, row-level security apply_grant_holder_read_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `payments.deposit_activity.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `payments.deposit_activity` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-ORDER-ORDERS-29 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: voidEntitlement | 3 | Narayan Gaonkar | OrderService | MIG-ACCESS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: voidEntitlement. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#voidEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-19 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: approveExceptionServiceRecovery, listAmendmentAfterSale, listAmendmentAfterSale2, listDepositPartialPayment | 3 | Hrushikant Patkar | OrderService | MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-17 MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: approveExceptionServiceRecovery, listAmendmentAfterSale, listAmendmentAfterSale2, listDepositPartialPayment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#approveExceptionServiceRecovery`, `orders#listAmendmentAfterSale`, `orders#listAmendmentAfterSale2`, `orders#listDepositPartialPayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-21 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: setAmendmentEligibilityPolicy, setCancellationPartialPolicy | 5 | Hrushikant Patkar | OrderService | MIG-ORDERS MIG-ORDERS-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: setAmendmentEligibilityPolicy, setCancellationPartialPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setAmendmentEligibilityPolicy`, `orders#setCancellationPartialPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDER-6 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: getDepositPolicy, setDepositPolicy | 5 | Hrushikant Patkar | OrderService | MIG-ORDERS-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getDepositPolicy, setDepositPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getDepositPolicy`, `orders#setDepositPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-28 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: cleanupFailedPayment, listExternalReferenceMappings, mergeOrders, recordExternalReference | 8 | Narayan Gaonkar | OrderService | MIG-LEDGER MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-5 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cleanupFailedPayment, listExternalReferenceMappings, mergeOrders, recordExternalReference. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#cleanupFailedPayment`, `orders#listExternalReferenceMappings`, `orders#mergeOrders`, `orders#recordExternalReference` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-89 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: listCampaignExperimentTest, listCampaignFinancialCommercial, listCampaignGovernanceBudget, listConflict | 3 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-91 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listCampaignExperimentTest, listCampaignFinancialCommercial, listCampaignGovernanceBudget, listConflict. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCampaignExperimentTest`, `promotions#listCampaignFinancialCommercial`, `promotions#listCampaignGovernanceBudget`, `promotions#listConflict` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-90 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: listConflictDetectionResolution, listDiscountCalculationApplication, listDiscountCapMaximum, listPromotionDecisionTrace | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listConflictDetectionResolution, listDiscountCalculationApplication, listDiscountCapMaximum, listPromotionDecisionTrace. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listConflictDetectionResolution`, `promotions#listDiscountCalculationApplication`, `promotions#listDiscountCapMaximum`, `promotions#listPromotionDecisionTrace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-93 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: listIncrementalityAttributionCannibalization, listNextBestAction, listRedemptionConversionFunnel, listUpsellCrossSell | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-10 MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-UPSELL-1 VM-MIG-PROMOTIONS | Operations: listIncrementalityAttributionCannibalization, listNextBestAction, listRedemptionConversionFunnel, listUpsellCrossSell. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listIncrementalityAttributionCannibalization`, `promotions#listNextBestAction`, `promotions#listRedemptionConversionFunnel`, `promotions#listUpsellCrossSell` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-92 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: listBundleBogoAdvanced, listCustomerSegmentChannel, listDiscountMarginProfitability, listExecutivePromotionReporting | 3 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-91 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listBundleBogoAdvanced, listCustomerSegmentChannel, listDiscountMarginProfitability, listExecutivePromotionReporting. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleBogoAdvanced`, `promotions#listCustomerSegmentChannel`, `promotions#listDiscountMarginProfitability`, `promotions#listExecutivePromotionReporting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-POLICY-3 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: setRefundCalculationPolicy | 1 | Narayan Gaonkar | OrderService | MIG-ORDERS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRefundCalculationPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setRefundCalculationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-10 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: listDepositActivity, recordDepositActivity | 2 | Narayan Gaonkar | OrderService | MIG-PAYMENTS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDepositActivity, recordDepositActivity. Spec: contracts (payments) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listDepositActivity`, `payments#recordDepositActivity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-18 | AM-ORDERS-RESERVATIONS-P08-7 | [DB] Forward migration V1210__orders.sql: orders for Orders & Reservations · Venue Management 7 of 8 (6 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.group_enquiry, orders.group_quote_line, orders.group_task, orders.group_ticket_allocation, orders.group_ticket_allocation_line, orders.group_ticket_fulfillment. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (orders.group_enquiry: column scope_path, index group_enquiry_scope_path_idx, row-level security apply_grant_holder_read_rls; orders.group_ticket_allocation: row-level security apply_parent_rls; orders.group_ticket_allocation_line: row-level security apply_parent_rls; orders.group_ticket_fulfillment: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: orders.group_quote_line: drop index group_quote_line_product_id_idx; orders.group_ticket_allocation: rename column keep_group_together to keeps_group_together, rename column vip_allocation to is_vip, foreign key group_ticket_allocation_group_booking_id_fkey; orders.group_ticket_allocation_line: foreign key group_ticket_allocation_line_product_id_fkey; orders.group_ticket_fulfillment: foreign key group_ticket_fulfillment_group_booking_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0114__after_r1_20261022.sql (orders.group_ticket_allocation: row-level security apply_parent_split_rls; orders.group_ticket_allocation_line: row-level security apply_parent_split_rls; orders.group_ticket_fulfillment: row-level security apply_parent_split_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Also add the key group_quote_enquiry_id_fkey here** (orders.group_quote to orders.group_enquiry, guarded): VM-MIG-ORDERS creates orders.group_quote before orders.group_enquiry exists. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `orders.group_enquiry.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `orders.group_enquiry`, `orders.group_quote_line`, `orders.group_task`, `orders.group_ticket_allocation`, `orders.group_ticket_allocation_line`, `orders.group_ticket_fulfillment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 3 | SVC-ORDER-ORDERS-31 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: setParticipantGuestList | 2 | Narayan Gaonkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setParticipantGuestList. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setParticipantGuestList` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-22 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: approveGroupDiscountException, listFinancialTraceability, listGroupBooking, listGroupBookingReconciliation | 5 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 MIG-ORDERS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: approveGroupDiscountException, listFinancialTraceability, listGroupBooking, listGroupBookingReconciliation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#approveGroupDiscountException`, `orders#listFinancialTraceability`, `orders#listGroupBooking`, `orders#listGroupBookingReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-25 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: listParticipantGuestList, listQuoteBookingConversion, listQuoteRevisionNegotiation, setGroupBookingHandover | 5 | Narayan Gaonkar | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: listParticipantGuestList, listQuoteBookingConversion, listQuoteRevisionNegotiation, setGroupBookingHandover. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listParticipantGuestList`, `orders#listQuoteBookingConversion`, `orders#listQuoteRevisionNegotiation`, `orders#setGroupBookingHandover` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-26 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: setGroupOperationalPlanning, setGroupPackageExperience, setGroupQuotationProposal | 8 | Hrushikant Patkar | OrderService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: setGroupOperationalPlanning, setGroupPackageExperience, setGroupQuotationProposal. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setGroupOperationalPlanning`, `orders#setGroupPackageExperience`, `orders#setGroupQuotationProposal` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-30 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: createGroupEnquiry, setGroupCustomerOrganization, setGroupPaymentSchedule, setGroupTicketAllocation | 8 | Narayan Gaonkar | OrderService | MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createGroupEnquiry, setGroupCustomerOrganization, setGroupPaymentSchedule, setGroupTicketAllocation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createGroupEnquiry`, `orders#setGroupCustomerOrganization`, `orders#setGroupPaymentSchedule`, `orders#setGroupTicketAllocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-32 | AM-ORDERS-RESERVATIONS-P08-8 | [BE] OrderService: setGroupTicketFulfillment | 1 | Deep Khanvilkar | OrderService | MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGroupTicketFulfillment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 8 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setGroupTicketFulfillment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-B2B-3 | AM-ORDERS-RESERVATIONS-P10 | [BE] OrderService: getB2bCredit | 2 | Deep Khanvilkar | OrderService | MIG-ORDERS-6 PLATFORM-KERNEL SVC-ORDER-B2B-1 | Operations: getB2bCredit. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Partner Portal; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getB2bCredit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-PAYMENTS-14 | AM-PAYMENTS-P08 | [BE] OrderService: updatePaymentMethod | 2 | Pranay Shinde | OrderService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updatePaymentMethod. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 1 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#updatePaymentMethod` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-12 | AM-PAYMENTS-P08 | [BE] OrderService: createPaymentMethod, getPaymentPerformance, getPaymentProviderHealth, getPaymentRules | 5 | Narayan Gaonkar | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPaymentMethod, getPaymentPerformance, getPaymentProviderHealth, getPaymentRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 1 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#createPaymentMethod`, `payments#getPaymentPerformance`, `payments#getPaymentProviderHealth`, `payments#getPaymentRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-13 | AM-PAYMENTS-P08 | [BE] OrderService: listPaymentRoutingRules, receivePaymentProviderWebhook, setPaymentFailoverPolicy, setPaymentRoutingRules | 8 | Hrushikant Patkar | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPaymentRoutingRules, receivePaymentProviderWebhook, setPaymentFailoverPolicy, setPaymentRoutingRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 1 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listPaymentRoutingRules`, `payments#receivePaymentProviderWebhook`, `payments#setPaymentFailoverPolicy`, `payments#setPaymentRoutingRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-20 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: listExternalPaymentPartner, listOrderSplitMerge, listRelatedOrderTransaction, setAfterSaleFinancial | 3 | Deep Khanvilkar | OrderService | MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-17 MIG-ORDERS-3 MIG-ORDERS-5 PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-19 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-LEDGER-SETTLEMENT-1 VM-MIG-LEDGER VM-MIG-ORDERS VM-ORDER-REFUND-1 | Operations: listExternalPaymentPartner, listOrderSplitMerge, listRelatedOrderTransaction, setAfterSaleFinancial. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listExternalPaymentPartner`, `orders#listOrderSplitMerge`, `orders#listRelatedOrderTransaction`, `orders#setAfterSaleFinancial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-23 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: listGroupCustomerOrganization, listGroupEnquiryOpportunity, listGroupPaymentDeposit, listGroupRequirementAvailability | 3 | Hrushikant Patkar | OrderService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDER-6 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-30 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 SVC-WALLET-RETAIL-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listGroupCustomerOrganization, listGroupEnquiryOpportunity, listGroupPaymentDeposit, listGroupRequirementAvailability. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listGroupCustomerOrganization`, `orders#listGroupEnquiryOpportunity`, `orders#listGroupPaymentDeposit`, `orders#listGroupRequirementAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-16 | AM-PAYMENTS-P08-2 | [BE] OrderService: listStoredForwardTransactions, recordPaymentTerminalCertification, setHostedCheckoutConfiguration, setPaymentAuthenticationPolicy | 5 | Narayan Gaonkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-14 MIG-PAYMENTS-3 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listStoredForwardTransactions, recordPaymentTerminalCertification, setHostedCheckoutConfiguration, setPaymentAuthenticationPolicy. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listStoredForwardTransactions`, `payments#recordPaymentTerminalCertification`, `payments#setHostedCheckoutConfiguration`, `payments#setPaymentAuthenticationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-15 | AM-PAYMENTS-P08-2 | [BE] OrderService: getMixedTenderRules, getPaymentProviderEconomics, listPaymentTerminalCertifications, listPaymentTerminals | 3 | Narayan Gaonkar | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-3 MIG-PAYMENTS-4 MIG-PAYMENTS-7 PLATFORM-KERNEL SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-27 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-16 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-4 SVC-ORDER-PAYMENTS-6 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-LEDGER-SETTLEMENT-1 VM-MIG-LEDGER VM-MIG-PAYMENTS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 | Operations: getMixedTenderRules, getPaymentProviderEconomics, listPaymentTerminalCertifications, listPaymentTerminals. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#getMixedTenderRules`, `payments#getPaymentProviderEconomics`, `payments#listPaymentTerminalCertifications`, `payments#listPaymentTerminals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-19 | AM-PAYMENTS-P08-2 | [BE] OrderService: simulatePaymentRouting | 1 | Deep Khanvilkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-7 PLATFORM-KERNEL SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-12 SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-14 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 | Operations: simulatePaymentRouting. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#simulatePaymentRouting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-6 | AM-PAYMENTS-P08-3 | [DB] Forward migration V1175__ai.sql: ai for Payments · Venue Management 3 of 3 (3 tables) | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.risk_assessment, ai.risk_case, ai.risk_strategy. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (ai.risk_case: column entities; ai.risk_strategy: column outcome_map); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ai.risk_assessment: rename column fell_back to did_fall_back, drop index risk_assessment_order_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.risk_assessment`, `ai.risk_case`, `ai.risk_strategy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-13 | AM-PAYMENTS-P08-3 | [BE] WalletService: getCreditConsumptionPolicy, setWalletChannelRules | 2 | Pranay Shinde | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCreditConsumptionPolicy, setWalletChannelRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#getCreditConsumptionPolicy`, `wallet#setWalletChannelRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-20 | AM-PAYMENTS-P08-3 | [BE] OrderService: createB2bCreditAccount, listMerchantAccounts, setMerchantAccount, setReconciliationMatchingRules | 5 | Hrushikant Patkar | OrderService | MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createB2bCreditAccount, listMerchantAccounts, setMerchantAccount, setReconciliationMatchingRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#createB2bCreditAccount`, `payments#listMerchantAccounts`, `payments#setMerchantAccount`, `payments#setReconciliationMatchingRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-21 | AM-PAYMENTS-P08-3 | [BE] OrderService: setReconciliationSource, submitChargebackEvidence | 3 | Narayan Gaonkar | OrderService | MIG-PAYMENTS-2 MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setReconciliationSource, submitChargebackEvidence. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setReconciliationSource`, `payments#submitChargebackEvidence` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-28 | AM-PAYMENTS-P08-3 | [BE] OrderService: listPaymentOrderFinancial | 1 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-LEDGER VM-ORDER-REFUND-1 | Operations: listPaymentOrderFinancial. Spec: contracts (orders) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listPaymentOrderFinancial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-2 | AM-PAYMENTS-P08-3 | [BE] AiService: backtestRiskStrategy | 2 | Deep Khanvilkar | AiService | MIG-AI-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: backtestRiskStrategy. Spec: contracts (ai) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#backtestRiskStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-6 | AM-WALLET-CASHLESS-P08 | [DB] Forward migration V1194__wallet.sql: wallet for Wallet & Cashless · Venue Management 1 of 7 (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.credit_eligibility. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.credit_eligibility` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WALLET-CARD-2 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: adjustGameCard | 3 | Hrushikant Patkar | WalletService | MIG-GAMES MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: adjustGameCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#adjustGameCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-GIFTCARD-2 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: blockGiftCard | 1 | Narayan Gaonkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: blockGiftCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#blockGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-RETAIL-3 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: closeWallet, reinstateWallet, suspendWallet | 5 | Narayan Gaonkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeWallet, reinstateWallet, suspendWallet. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#closeWallet`, `wallet#reinstateWallet`, `wallet#suspendWallet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-14 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: adjustWallet, createWalletType, getWalletLiability, listWalletHolds | 8 | Hrushikant Patkar | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: adjustWallet, createWalletType, getWalletLiability, listWalletHolds. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#adjustWallet`, `wallet#createWalletType`, `wallet#getWalletLiability`, `wallet#listWalletHolds` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-15 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: setCreditEligibilityRules | 2 | Deep Khanvilkar | WalletService | MIG-WALLET-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCreditEligibilityRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#setCreditEligibilityRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-7 | AM-WALLET-CASHLESS-P08-2 | [DB] Forward migration V1197__wallet.sql: wallet for Wallet & Cashless · Venue Management 2 of 7 (3 tables) | 2 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.credential, wallet.shared_wallet, wallet.shared_wallet_member. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (wallet.credential: column recorded_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.credential: foreign key credential_wallet_id_fkey; wallet.shared_wallet: foreign key shared_wallet_wallet_id_fkey; wallet.shared_wallet_member: foreign key shared_wallet_member_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.credential`, `wallet.shared_wallet`, `wallet.shared_wallet_member` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-16 | AM-WALLET-CASHLESS-P08-2 | [BE] WalletService: linkWalletCredential, listSharedWallets, reverseWalletFunding, setSharedWalletMembers | 5 | Pranay Shinde | WalletService | MIG-WALLET-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WALLET | Operations: linkWalletCredential, listSharedWallets, reverseWalletFunding, setSharedWalletMembers. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 2 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#linkWalletCredential`, `wallet#listSharedWallets`, `wallet#reverseWalletFunding`, `wallet#setSharedWalletMembers` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-17 | AM-WALLET-CASHLESS-P08-2 | [BE] WalletService: updateWalletType | 2 | Narayan Gaonkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateWalletType. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 2 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#updateWalletType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-18 | AM-WALLET-CASHLESS-P08-3 | [BE] WalletService: createSharedWallet, getWalletBalance, getWalletReconciliation, setCreditConsumptionPolicy | 5 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSharedWallet, getWalletBalance, getWalletReconciliation, setCreditConsumptionPolicy. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 3 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#createSharedWallet`, `wallet#getWalletBalance`, `wallet#getWalletReconciliation`, `wallet#setCreditConsumptionPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-WALLET-WALLET-19 | AM-WALLET-CASHLESS-P08-3 | [BE] WalletService: simulateCreditConsumption | 2 | Deep Khanvilkar | WalletService | MIG-WALLET MIG-WALLET-6 PLATFORM-KERNEL SVC-WALLET-CARD-1 SVC-WALLET-CARD-2 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-RETAIL-3 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-14 SVC-WALLET-WALLET-15 SVC-WALLET-WALLET-18 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-7 VM-WALLET-WALLET-1 | Operations: simulateCreditConsumption. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 3 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#simulateCreditConsumption` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-8 | AM-WALLET-CASHLESS-P08-4 | [DB] Forward migration V1212__wallet.sql: wallet for Wallet & Cashless · Venue Management 4 of 7 (2 tables) | 2 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.gift_card_product, wallet.voucher_type. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (wallet.gift_card_product: column denominations; wallet.voucher_type: index voucher_type_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.voucher_type: rename column single_use to is_single_use); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.gift_card_product`, `wallet.voucher_type` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WALLET-GIFTCARD-3 | AM-WALLET-CASHLESS-P08-4 | [BE] WalletService: issueGiftCard | 2 | Deep Khanvilkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueGiftCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 4 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#issueGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-RETAIL-4 | AM-WALLET-CASHLESS-P08-4 | [BE] WalletService: activateGiftCard, redeemGiftCard | 3 | Narayan Gaonkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: activateGiftCard, redeemGiftCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 4 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#activateGiftCard`, `wallet#redeemGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-20 | AM-WALLET-CASHLESS-P08-4 | [BE] WalletService: createVoucherType, listVoucherTypes, setGiftCardProduct | 5 | Pranay Shinde | WalletService | MIG-WALLET-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVoucherType, listVoucherTypes, setGiftCardProduct. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 4 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#createVoucherType`, `wallet#listVoucherTypes`, `wallet#setGiftCardProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-21 | AM-WALLET-CASHLESS-P08-5 | [BE] WalletService: setWalletAuthenticationPolicy | 1 | Narayan Gaonkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletAuthenticationPolicy. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 5 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#setWalletAuthenticationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-9 | AM-WALLET-CASHLESS-P08-6 | [DB] Forward migration V1213__wallet.sql: wallet for Wallet & Cashless · Venue Management 6 of 7 (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.restriction. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: wallet.restriction: foreign key restriction_wallet_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `wallet.restriction` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-22 | AM-WALLET-CASHLESS-P08-6 | [BE] WalletService: raiseWalletDispute, setWalletAccountingMapping, setWalletReconciliationSources, setWalletRestriction | 5 | Hrushikant Patkar | WalletService | MIG-WALLET MIG-WALLET-3 MIG-WALLET-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: raiseWalletDispute, setWalletAccountingMapping, setWalletReconciliationSources, setWalletRestriction. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 6 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#raiseWalletDispute`, `wallet#setWalletAccountingMapping`, `wallet#setWalletReconciliationSources`, `wallet#setWalletRestriction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-7 | AM-ADMISSION-ACCESS-P07 | [DB] Forward migration V1149__access.sql: access for Admission & Access · Scanner (2 tables) | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE MIG-PLATFORM VM-MIG-ACCESS | Tables: access.podium, access.podium_shift. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.podium: foreign key podium_venue_id_fkey; access.podium_shift: foreign key podium_shift_operator_principal_id_fkey, foreign key podium_shift_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.podium`, `access.podium_shift` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-15 | AM-ADMISSION-ACCESS-P07 | [BE] AccessService: endPodiumShift, startPodiumShift | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endPodiumShift, startPodiumShift. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Scanner; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#endPodiumShift`, `access#startPodiumShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | ACC-RULE-EVAL | AM-ADMISSION-ACCESS-P07 | [BE] One admission rule format, two evaluators: .NET and TypeScript proven equal by shared test vectors | 8 | Narayan Gaonkar |  | OFFLINE-BUNDLE | One admission rule format, two evaluators: .NET and TypeScript proven equal by shared test vectors. Builds: `operation access#validateAccess`, `operation access#getOfflinePackage`, `table access.dynamic_policy`, `adr ADR-0068`. ADR-0068 (accepted 1 October; B1, with the scanner): the closed JSON rule format (AdmissionRule, AdmissionCondition; conditionRule on access.dynamic_policy versions) evaluated by validateAccess online in .NET and by the gate offline in TypeScript (packages/offline-core) against the same active policy version that getOfflinePackage carries; each scan_event records the policy version that decided it. Done when: one set of test vectors runs in CI against both evaluators and they agree on every vector, a rule the format cannot express is refused when the policy is saved, and an offline scan and an online scan of the same credential under the same policy version give the same decision.
15 | 3 | MIG-ACCESS-10 | AM-ADMISSION-ACCESS-P08 | [DB] Forward migration V1251__access.sql: access for Admission & Access · Venue Management 1 of 8 (10 tables) | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_map, access.attraction_access, access.configuration_version, access.consumption_rule, access.gate_lane, access.group_admission_rule, access.hardware_deployment, access.journey_sequence_rule, access.offline_policy, access.operating_calendar_entry. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.access_map: foreign key access_map_venue_id_fkey, foreign key access_map_venue_id_map_id_fkey; access.attraction_access: rename column fast_pass_support to supports_fast_pass, rename column adult_companion_requirement to requires_adult_companion, rename column membership_access to has_membership_access, rename column vip_access to has_vip_access, rename column biometric_requirement to requires_biometric, foreign key attraction_access_venue_id_fkey, drop index attraction_access_attraction_id_idx; access.consumption_rule: rename column one_per_attraction to is_one_per_attraction; access.gate_lane: rename column re_entry to allows_re_entry, foreign key gate_lane_venue_id_access_point_id_fkey, foreign key gate_lane_venue_id_fkey; access.group_admission_rule: foreign key group_admission_rule_venue_id_fkey; access.offline_policy: rename column automatic_switch to has_automatic_switch, foreign key offline_policy_venue_id_fkey; access.operating_calendar_entry: rename column attraction_validation to requires_attraction_validation, foreign key operating_calendar_entry_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `access.access_map.map_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.access_map`, `access.attraction_access`, `access.configuration_version`, `access.consumption_rule`, `access.gate_lane`, `access.group_admission_rule`, `access.hardware_deployment`, `access.journey_sequence_rule` and 2 more applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-18 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: deleteJourneySequenceRule, deleteOperatingCalendarEntry, listAccess, listAccessRule | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteJourneySequenceRule, deleteOperatingCalendarEntry, listAccess, listAccessRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deleteJourneySequenceRule`, `access#deleteOperatingCalendarEntry`, `access#listAccess`, `access#listAccessRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-20 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: listOperatingCalendarSpecial, publishRuleConflictCheck, publishTopologyValidation, rollbackConfigurationVersion | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-2 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOperatingCalendarSpecial, publishRuleConflictCheck, publishTopologyValidation, rollbackConfigurationVersion. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listOperatingCalendarSpecial`, `access#publishRuleConflictCheck`, `access#publishTopologyValidation`, `access#rollbackConfigurationVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-21 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: setAccessAreaZone, setAccessGraphicalMap, setAttractionAccess, setEntitlementConsumption | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-2 MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessAreaZone, setAccessGraphicalMap, setAttractionAccess, setEntitlementConsumption. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setAccessAreaZone`, `access#setAccessGraphicalMap`, `access#setAttractionAccess`, `access#setEntitlementConsumption` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-22 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: setGateLane, setJourneySequenceRule, setOperatingCalendarEntry | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGateLane, setJourneySequenceRule, setOperatingCalendarEntry. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setGateLane`, `access#setJourneySequenceRule`, `access#setOperatingCalendarEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-11 | AM-ADMISSION-ACCESS-P08-2 | [DB] Forward migration V1152__access.sql: access for Admission & Access · Venue Management 2 of 8 (7 tables) | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.credential_event_propagation_rule, access.credential_security_profile, access.external_credential_integration, access.media_compatibility_test, access.media_encoding_profile, access.security_alert, access.verification_method_policy. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (access.verification_method_policy: column credential_format_override); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (access.security_alert: column note); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.credential_security_profile: rename column offline_ready to is_offline_ready; access.media_compatibility_test: foreign key media_compatibility_test_media_type_id_fkey, foreign key media_compatibility_test_venue_id_fkey; access.media_encoding_profile: rename column offline_capability to supports_offline; access.verification_method_policy: rename column lock_on_first_successful_access to locks_on_first_successful_access, foreign key verification_method_policy_product_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.credential_event_propagation_rule`, `access.credential_security_profile`, `access.external_credential_integration`, `access.media_compatibility_test`, `access.media_encoding_profile`, `access.security_alert`, `access.verification_method_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-27 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listVirtualCredentialMedia, publishMediaCompatibilityTesting, reviewFaceReenrolment, setCredentialEventPropagationRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-11 MIG-CATALOGUE MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations: listVirtualCredentialMedia, publishMediaCompatibilityTesting, reviewFaceReenrolment, setCredentialEventPropagationRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVirtualCredentialMedia`, `access#publishMediaCompatibilityTesting`, `access#reviewFaceReenrolment`, `access#setCredentialEventPropagationRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-28 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: setDynamicSecurityProfile, setEmbeddedEntitlementPayload, setGateOfflinePolicy, setHotelWalletExternal | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDynamicSecurityProfile, setEmbeddedEntitlementPayload, setGateOfflinePolicy, setHotelWalletExternal. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setDynamicSecurityProfile`, `access#setEmbeddedEntitlementPayload`, `access#setGateOfflinePolicy`, `access#setHotelWalletExternal` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-29 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: setMediaIssuanceEncoding, setMediaTypeTechnology, setRfidNfc, setVerificationMethodPolicy | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setMediaIssuanceEncoding, setMediaTypeTechnology, setRfidNfc, setVerificationMethodPolicy. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setMediaIssuanceEncoding`, `access#setMediaTypeTechnology`, `access#setRfidNfc`, `access#setVerificationMethodPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-DEVICES-9 | AM-ADMISSION-ACCESS-P08-3 | [BE] TenancyService: approveDevice | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveDevice. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#approveDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-32 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: listOfflineEdge, listOfflineEntitlementUsage, listPhysicalDeviceRegistration, placeAccessDevice | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-2 MIG-ACCESS-8 MIG-CATALOGUE MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOfflineEdge, listOfflineEntitlementUsage, listPhysicalDeviceRegistration, placeAccessDevice. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listOfflineEdge`, `access#listOfflineEntitlementUsage`, `access#listPhysicalDeviceRegistration`, `access#placeAccessDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-33 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: publishHardwareDeployment, setDeviceSoftwareContent, setEdgeNodeLocal, setHandheldMobileAccess | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishHardwareDeployment, setDeviceSoftwareContent, setEdgeNodeLocal, setHandheldMobileAccess. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#publishHardwareDeployment`, `access#setDeviceSoftwareContent`, `access#setEdgeNodeLocal`, `access#setHandheldMobileAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-34 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: setHardwareModel, setReaderScannerPeripheral, setTurnstileLaneBehavior, setValidationOutcomeGuest | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setHardwareModel, setReaderScannerPeripheral, setTurnstileLaneBehavior, setValidationOutcomeGuest. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setHardwareModel`, `access#setReaderScannerPeripheral`, `access#setTurnstileLaneBehavior`, `access#setValidationOutcomeGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-35 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: simulateBiometricConfiguration, updateAccessDevicePlacement | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateBiometricConfiguration, updateAccessDevicePlacement. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#simulateBiometricConfiguration`, `access#updateAccessDevicePlacement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-30 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: listBiometric, listBiometricValidationGate, listConnectivityFailureDegraded, listDeviceGate | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-8 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-20 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-32 SVC-ACCESS-ACCESS-33 SVC-ACCESS-ACCESS-34 SVC-ACCESS-ACCESS-35 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 | Operations: listBiometric, listBiometricValidationGate, listConnectivityFailureDegraded, listDeviceGate. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listBiometric`, `access#listBiometricValidationGate`, `access#listConnectivityFailureDegraded`, `access#listDeviceGate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-31 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: listDeviceTypeHardware, listEdgePackageData, listHardwareCompatibilityHealth, listOfflineCredentialRevocation | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-8 PLATFORM-KERNEL SVC-ACCESS-ACCESS-20 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-32 SVC-ACCESS-ACCESS-33 SVC-ACCESS-ACCESS-34 SVC-ACCESS-ACCESS-35 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-3 VM-ACCESS-ACCESS-1 VM-MIG-ACCESS | Operations: listDeviceTypeHardware, listEdgePackageData, listHardwareCompatibilityHealth, listOfflineCredentialRevocation. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listDeviceTypeHardware`, `access#listEdgePackageData`, `access#listHardwareCompatibilityHealth`, `access#listOfflineCredentialRevocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-13 | AM-ADMISSION-ACCESS-P08-4 | [DB] Forward migration V1252__access.sql: access for Admission & Access · Venue Management 4 of 8 (5 tables) | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.fast_pass_profile, access.identity_lock, access.journey_profile, access.reason_code, access.security_investigation. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (access.reason_code: index reason_code_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.fast_pass_profile: rename column one_per_ride to is_one_per_ride; access.identity_lock: foreign key identity_lock_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.fast_pass_profile`, `access.identity_lock`, `access.journey_profile`, `access.reason_code`, `access.security_investigation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-36 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: deletePodium, deleteReasonCode, listCredentialDisableBlacklist, listEdgeSecurityDeployment | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-11 MIG-ACCESS-13 MIG-ACCESS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deletePodium, deleteReasonCode, listCredentialDisableBlacklist, listEdgeSecurityDeployment. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deletePodium`, `access#deleteReasonCode`, `access#listCredentialDisableBlacklist`, `access#listEdgeSecurityDeployment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-40 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listValidationExceptionReason, lockIdentity, releaseIdentityLock, setFastPassProfile | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listValidationExceptionReason, lockIdentity, releaseIdentityLock, setFastPassProfile. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listValidationExceptionReason`, `access#lockIdentity`, `access#releaseIdentityLock`, `access#setFastPassProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-41 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: setGroupAdmissionProfile, setGuestCompanionEligibility, setJourneyProfile, setPodium | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-13 MIG-ACCESS-3 MIG-ACCESS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGroupAdmissionProfile, setGuestCompanionEligibility, setJourneyProfile, setPodium. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setGroupAdmissionProfile`, `access#setGuestCompanionEligibility`, `access#setJourneyProfile`, `access#setPodium` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-19 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: listAccessValidityTime, listAntiPassbackJourney, listEntitlementConsumption, listGroupAdmissionQuantity | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-CATALOGUE PLATFORM-KERNEL SVC-ACCESS-ACCESS-18 SVC-ACCESS-ACCESS-21 SVC-ACCESS-ACCESS-22 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-5 | Operations: listAccessValidityTime, listAntiPassbackJourney, listEntitlementConsumption, listGroupAdmissionQuantity. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listAccessValidityTime`, `access#listAntiPassbackJourney`, `access#listEntitlementConsumption`, `access#listGroupAdmissionQuantity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-42 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: setReasonCode, simulateGuestJourney, simulateOfflineResilienceTesting, updateSecurityAlert | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-13 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setReasonCode, simulateGuestJourney, simulateOfflineResilienceTesting, updateSecurityAlert. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setReasonCode`, `access#simulateGuestJourney`, `access#simulateOfflineResilienceTesting`, `access#updateSecurityAlert` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-14 | AM-ADMISSION-ACCESS-P08-5 | [DB] Forward migration V1215__access.sql: access for Admission & Access · Venue Management 5 of 8 (5 tables) | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_attribute, access.credential_sharing_case, access.fraud_rule, access.policy_evaluation_setting, access.risk_scoring_config. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.credential_sharing_case: foreign key credential_sharing_case_entitlement_id_fkey; access.fraud_rule: rename column offline_availability to is_offline_available); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.access_attribute`, `access.credential_sharing_case`, `access.fraud_rule`, `access.policy_evaluation_setting`, `access.risk_scoring_config` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-7 | AM-ADMISSION-ACCESS-P08-5 | [BE] TenancyService: setAccessProfile | 2 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessProfile. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#setAccessProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-47 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: rollbackAccessPolicy, setAccessAttributeCatalog, setContextTimeEvent, setFraudDetectionRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: rollbackAccessPolicy, setAccessAttributeCatalog, setContextTimeEvent, setFraudDetectionRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#rollbackAccessPolicy`, `access#setAccessAttributeCatalog`, `access#setContextTimeEvent`, `access#setFraudDetectionRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-48 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: setOperationalIncidentException, setPolicyEvaluationSetting, setPolicyScopeHierarchy, setRelationshipFraudRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setOperationalIncidentException, setPolicyEvaluationSetting, setPolicyScopeHierarchy, setRelationshipFraudRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setOperationalIncidentException`, `access#setPolicyEvaluationSetting`, `access#setPolicyScopeHierarchy`, `access#setRelationshipFraudRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-49 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: setSecurityInvestigationEvidence, setVisualDynamicPolicy, simulatePolicyConflictImpact | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-13 MIG-ACCESS-14 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setSecurityInvestigationEvidence, setVisualDynamicPolicy, simulatePolicyConflictImpact. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setSecurityInvestigationEvidence`, `access#setVisualDynamicPolicy`, `access#simulatePolicyConflictImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-45 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: listFraudDetectionRule, listIdentityMembershipAccreditation, listPolicyEvaluationArchitecture, listPolicyScopeHierarchy | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS-14 PLATFORM-KERNEL SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-49 VM-MIG-ACCESS | Operations: listFraudDetectionRule, listIdentityMembershipAccreditation, listPolicyEvaluationArchitecture, listPolicyScopeHierarchy. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listFraudDetectionRule`, `access#listIdentityMembershipAccreditation`, `access#listPolicyEvaluationArchitecture`, `access#listPolicyScopeHierarchy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-15 | AM-ADMISSION-ACCESS-P08-6 | [DB] Forward migration V1216__access.sql: access for Admission & Access · Venue Management 6 of 8 (4 tables) | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.credential_exception, access.credential_issuance, access.security_playbook, access.ticket_status_transition. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.credential_issuance: foreign key credential_issuance_entitlement_id_fkey, foreign key credential_issuance_media_type_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.credential_exception`, `access.credential_issuance`, `access.security_playbook`, `access.ticket_status_transition` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-50 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: deleteMediaBindingRule, listAccessExecutiveInsight, listAccessMonitoring, listAccessRiskScoring | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 MIG-ACCESS-6 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteMediaBindingRule, listAccessExecutiveInsight, listAccessMonitoring, listAccessRiskScoring. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deleteMediaBindingRule`, `access#listAccessExecutiveInsight`, `access#listAccessMonitoring`, `access#listAccessRiskScoring` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-54 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listVirtualTicketStatus, setMediaBindingRule, setRealTimeSecurity, setRiskScoringConfig | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 MIG-ACCESS-15 MIG-ACCESS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listVirtualTicketStatus, setMediaBindingRule, setRealTimeSecurity, setRiskScoringConfig. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVirtualTicketStatus`, `access#setMediaBindingRule`, `access#setRealTimeSecurity`, `access#setRiskScoringConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-55 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: setTicketStatusTransition | 2 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTicketStatusTransition. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setTicketStatusTransition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-16 | AM-ADMISSION-ACCESS-P08-7 | [DB] Forward migration V1217__access.sql: access for Admission & Access · Venue Management 7 of 8 (5 tables) | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.branding_profile, access.credential_delivery, access.credential_issuance_retry_policy, access.dynamic_field, access.media_template_version. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: access.branding_profile: foreign key branding_profile_scope_id_fkey; access.credential_delivery: foreign key credential_delivery_entitlement_id_fkey; access.credential_issuance_retry_policy: rename column automatic_retry to has_automatic_retry, foreign key credential_issuance_retry_policy_venue_id_fkey; access.media_template_version: rename column controlled_rollout to has_controlled_rollout, foreign key media_template_version_media_template_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): column changed `access.branding_profile.scope_id`; column changed `access.credential_issuance_retry_policy.venue_id`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `access.branding_profile`, `access.credential_delivery`, `access.credential_issuance_retry_policy`, `access.dynamic_field`, `access.media_template_version` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 3 | SVC-ACCESS-ACCESS-64 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: setMediaReplacementRevocation, setRfidNfcCard | 5 | Narayan Gaonkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setMediaReplacementRevocation, setRfidNfcCard. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setMediaReplacementRevocation`, `access#setRfidNfcCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-56 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: approveMultiMediaPreview, deliverCredential, getCredentialIssuanceRetryPolicy, listBrandingLocalizationTemplate | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-16 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: approveMultiMediaPreview, deliverCredential, getCredentialIssuanceRetryPolicy, listBrandingLocalizationTemplate. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#approveMultiMediaPreview`, `access#deliverCredential`, `access#getCredentialIssuanceRetryPolicy`, `access#listBrandingLocalizationTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-61 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: listMediaActivationPriority, listMediaReplacementRevocation, listVirtualTicketArchitecture, resolveCredentialException | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-15 MIG-ACCESS-16 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listMediaActivationPriority, listMediaReplacementRevocation, listVirtualTicketArchitecture, resolveCredentialException. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listMediaActivationPriority`, `access#listMediaReplacementRevocation`, `access#listVirtualTicketArchitecture`, `access#resolveCredentialException` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-ORDERS-18 | AM-PRICING-PROMOTIONS-P08-6 | [BE] OrderService: quoteUpgrade | 2 | Narayan Gaonkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 | Operations: quoteUpgrade. Spec: contracts (orders) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#quoteUpgrade` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-DRAFTED-4 | AM-ORDERS-RESERVATIONS-P08 | [BE] OrderService: listOfficialResaleMarketplace, listResaleMarketplace, listResalePolicyMarketplace, listTicketResaleMarketplace | 5 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listOfficialResaleMarketplace, listResaleMarketplace, listResalePolicyMarketplace, listTicketResaleMarketplace. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 1 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listOfficialResaleMarketplace`, `orders#listResaleMarketplace`, `orders#listResalePolicyMarketplace`, `orders#listTicketResaleMarketplace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-7 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: listCredentialRevocationRegeneration, listFeeSellerProceed, listListingLifecycleExpiry, listResale | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-12 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-ORDER-REFUND-1 | Operations: listCredentialRevocationRegeneration, listFeeSellerProceed, listListingLifecycleExpiry, listResale. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listCredentialRevocationRegeneration`, `orders#listFeeSellerProceed`, `orders#listListingLifecycleExpiry`, `orders#listResale` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-8 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: listResale2, listResaleFeeCommission, listResaleFraudDuplicate, listResaleInventoryAvailability | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-ORDER-REFUND-1 | Operations: listResale2, listResaleFeeCommission, listResaleFraudDuplicate, listResaleInventoryAvailability. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listResale2`, `orders#listResaleFeeCommission`, `orders#listResaleFraudDuplicate`, `orders#listResaleInventoryAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-DRAFTED-12 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: listUpgradeEligibilityQualification, listUpgradeFinancialTreatment, listUpgradeTimingUsage, listWhiteLabelMarketplace | 3 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-ORDERS-14 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-13 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 | Operations: listUpgradeEligibilityQualification, listUpgradeFinancialTreatment, listUpgradeTimingUsage, listWhiteLabelMarketplace. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listUpgradeEligibilityQualification`, `orders#listUpgradeFinancialTreatment`, `orders#listUpgradeTimingUsage`, `orders#listWhiteLabelMarketplace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-10 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: listBuyerCheckoutInventory, listCreateListingResale, listResaleConfirmationOwnership, listResaleEligibilityTicket | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-5 SVC-ORDER-DRAFTED-6 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 | Operations: listBuyerCheckoutInventory, listCreateListingResale, listResaleConfirmationOwnership, listResaleEligibilityTicket. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listBuyerCheckoutInventory`, `orders#listCreateListingResale`, `orders#listResaleConfirmationOwnership`, `orders#listResaleEligibilityTicket` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-11 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: listResaleListingSeller, listResaleOwnership, listResaleTicketDetail, listUpgradeConversion | 5 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-ORDERS-14 PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-13 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listResaleListingSeller, listResaleOwnership, listResaleTicketDetail, listUpgradeConversion. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listResaleListingSeller`, `orders#listResaleOwnership`, `orders#listResaleTicketDetail`, `orders#listUpgradeConversion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-24 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: listGroupSale, listGroupSale2, listGroupTicketSeat, listOrderFinancialReconciliation | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 MIG-ORDERS-3 MIG-PAYMENTS PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-22 SVC-ORDER-DRAFTED-26 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-30 SVC-ORDER-ORDERS-31 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-6 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-LEDGER VM-MIG-ORDERS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 | Operations: listGroupSale, listGroupSale2, listGroupTicketSeat, listOrderFinancialReconciliation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listGroupSale`, `orders#listGroupSale2`, `orders#listGroupTicketSeat`, `orders#listOrderFinancialReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-23 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: getFaceReenrolmentImages, listBiometricAccess, listCredentialRevocationLifecycle, listCredentialSecurity | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: getFaceReenrolmentImages, listBiometricAccess, listCredentialRevocationLifecycle, listCredentialSecurity. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getFaceReenrolmentImages`, `access#listBiometricAccess`, `access#listCredentialRevocationLifecycle`, `access#listCredentialSecurity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-24 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listCredentialSecurityOperational, listCredentialTransferRebinding, listDigitalCredentialSecurity, listExternalPartnerCredential | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-CATALOGUE MIG-IDENTITY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-SSO-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-IDENTITY-ADMINISTRATION-1 VM-MIG-ACCESS | Operations: listCredentialSecurityOperational, listCredentialTransferRebinding, listDigitalCredentialSecurity, listExternalPartnerCredential. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredentialSecurityOperational`, `access#listCredentialTransferRebinding`, `access#listDigitalCredentialSecurity`, `access#listExternalPartnerCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-25 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listFaceChangeEnrollment, listHotelWalletExternal, listMediaCredential, listMediaIssuanceEncoding | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listFaceChangeEnrollment, listHotelWalletExternal, listMediaCredential, listMediaIssuanceEncoding. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listFaceChangeEnrollment`, `access#listHotelWalletExternal`, `access#listMediaCredential`, `access#listMediaIssuanceEncoding` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-26 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listMediaSwapReplacement, listMediaTypeTechnology, listOfflineCryptographicValidation, listVerificationMethodSelection | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-11 PLATFORM-KERNEL SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-MIG-ACCESS | Operations: listMediaSwapReplacement, listMediaTypeTechnology, listOfflineCryptographicValidation, listVerificationMethodSelection. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listMediaSwapReplacement`, `access#listMediaTypeTechnology`, `access#listOfflineCryptographicValidation`, `access#listVerificationMethodSelection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-37 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listFamilyChildPod, listFastPassAttraction, listGroupAttendancePartial, listGroupLeaderFast | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-13 MIG-ACCESS-3 MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-IDENTITY-SSO-1 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: listFamilyChildPod, listFastPassAttraction, listGroupAttendancePartial, listGroupLeaderFast. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listFamilyChildPod`, `access#listFastPassAttraction`, `access#listGroupAttendancePartial`, `access#listGroupLeaderFast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-38 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listGuestJourney, listLiveAccess, listMultiParkCrossover, listMultiParkCrossover2 | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-13 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 | Operations: listGuestJourney, listLiveAccess, listMultiParkCrossover, listMultiParkCrossover2. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listGuestJourney`, `access#listLiveAccess`, `access#listMultiParkCrossover`, `access#listMultiParkCrossover2` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-39 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listPodiumConsole, listReconnectionSynchronizationConflict, listSpecialEventFree, listTicketCredentialInvestigation | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-10 MIG-ACCESS-7 MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-SYNC PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-15 SVC-ACCESS-ACCESS-18 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-22 SVC-ACCESS-ACCESS-36 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CROSSREGION-CROSS-REGION-3 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-IDENTITY-SSO-1 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-PLAY-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-IDENTITY-ADMINISTRATION-1 VM-ORDER-SYNC-1 | Operations: listPodiumConsole, listReconnectionSynchronizationConflict, listSpecialEventFree, listTicketCredentialInvestigation. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listPodiumConsole`, `access#listReconnectionSynchronizationConflict`, `access#listSpecialEventFree`, `access#listTicketCredentialInvestigation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-43 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: getAccessRiskScore, listAccessAttributeCatalog, listAccessSecurityFraud, listAuthorizationGovernanceTemporary | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-13 MIG-ACCESS-14 MIG-IDENTITY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-42 SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-49 SVC-ACCESS-ACCESS-54 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-ADMINISTRATION-3 SVC-IDENTITY-ADMINISTRATION-8 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-SSO-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: getAccessRiskScore, listAccessAttributeCatalog, listAccessSecurityFraud, listAuthorizationGovernanceTemporary. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getAccessRiskScore`, `access#listAccessAttributeCatalog`, `access#listAccessSecurityFraud`, `access#listAuthorizationGovernanceTemporary` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-44 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: listBiometricIdentityIntegrity, listCredentialSharingConcurrent, listDynamicAccessPolicy, listDynamicPolicyEffectiveness | 5 | Pranay Shinde | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-14 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-42 SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-49 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listBiometricIdentityIntegrity, listCredentialSharingConcurrent, listDynamicAccessPolicy, listDynamicPolicyEffectiveness. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listBiometricIdentityIntegrity`, `access#listCredentialSharingConcurrent`, `access#listDynamicAccessPolicy`, `access#listDynamicPolicyEffectiveness` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-46 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: listQueueThroughputLane, listRelationshipCompanionFraud, listShiftHandoverSummary, listUnifiedIdentityCredential | 5 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-13 MIG-ACCESS-14 MIG-ACCESS-7 MIG-IDENTITY MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-15 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-58 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-IDENTITY-SSO-1 SVC-MARKETING-MARKETING-7 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: listQueueThroughputLane, listRelationshipCompanionFraud, listShiftHandoverSummary, listUnifiedIdentityCredential. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listQueueThroughputLane`, `access#listRelationshipCompanionFraud`, `access#listShiftHandoverSummary`, `access#listUnifiedIdentityCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-51 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listAttendanceAdmission, listCredentialIdentityToken, listEntryExitCrossover, listGraphicalAccessMap | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-CATALOGUE MIG-ORDERS MIG-VENUEMAP PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-MIG-ACCESS VM-VENUEOPS-VENUEMAP-1 | Operations: listAttendanceAdmission, listCredentialIdentityToken, listEntryExitCrossover, listGraphicalAccessMap. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listAttendanceAdmission`, `access#listCredentialIdentityToken`, `access#listEntryExitCrossover`, `access#listGraphicalAccessMap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-52 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listGuestDwellTime, listLiveVenueOccupancy, listMediaTypeCredential, listMultiMediaBinding | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-2 MIG-ACCESS-6 MIG-CATALOGUE MIG-VENUEMAP PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-10 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-21 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-50 SVC-ACCESS-ACCESS-54 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listGuestDwellTime, listLiveVenueOccupancy, listMediaTypeCredential, listMultiMediaBinding. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listGuestDwellTime`, `access#listLiveVenueOccupancy`, `access#listMediaTypeCredential`, `access#listMultiMediaBinding` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-62 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: retryCredentialGeneration, setAppleWalletPass, setBrandingLocalizationTemplate, setCredentialIssuanceRetryPolicy | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-15 MIG-ACCESS-16 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: retryCredentialGeneration, setAppleWalletPass, setBrandingLocalizationTemplate, setCredentialIssuanceRetryPolicy. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#retryCredentialGeneration`, `access#setAppleWalletPass`, `access#setBrandingLocalizationTemplate`, `access#setCredentialIssuanceRetryPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-53 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listSecurityDetectionGovernance, listThroughputQueueValidation, listValidationOutcomeRejection, listVirtualTicket | 8 | Pranay Shinde | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-13 MIG-ACCESS-14 MIG-ACCESS-15 MIG-CATALOGUE MIG-ORDERS MIG-PII PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-42 SVC-ACCESS-ACCESS-49 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-62 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-MIG-ACCESS | Operations: listSecurityDetectionGovernance, listThroughputQueueValidation, listValidationOutcomeRejection, listVirtualTicket. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listSecurityDetectionGovernance`, `access#listThroughputQueueValidation`, `access#listValidationOutcomeRejection`, `access#listVirtualTicket` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-63 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: setDigitalBarcodeTicket, setDigitalCardMembership, setDynamicFieldData, setGoogleWalletPass | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-16 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setDigitalBarcodeTicket, setDigitalCardMembership, setDynamicFieldData, setGoogleWalletPass. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setDigitalBarcodeTicket`, `access#setDigitalCardMembership`, `access#setDynamicFieldData`, `access#setGoogleWalletPass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-57 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: listCredential, listCredentialDeliveryDistribution, listCredentialGenerationIssuance, listEntitlementCrossMedia | 8 | Narayan Gaonkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-15 MIG-ACCESS-16 MIG-CATALOGUE MIG-PII PLATFORM-KERNEL PRD-W1-CATEGORIES-TAGS SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-62 SVC-ACCESS-ACCESS-63 SVC-ACCESS-ACCESS-64 SVC-ACCESS-ACCESS-9 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-MIG-ACCESS | Operations: listCredential, listCredentialDeliveryDistribution, listCredentialGenerationIssuance, listEntitlementCrossMedia. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredential`, `access#listCredentialDeliveryDistribution`, `access#listCredentialGenerationIssuance`, `access#listEntitlementCrossMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-65 | AM-ADMISSION-ACCESS-P08-8 | [BE] AccessService: listCredentialUsageCross, listFailedGenerationDelivery, listTicketMedia | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-15 MIG-ACCESS-16 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-62 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listCredentialUsageCross, listFailedGenerationDelivery, listTicketMedia. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 8 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredentialUsageCross`, `access#listFailedGenerationDelivery`, `access#listTicketMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-LEDGER-JOURNAL-1 | AM-FINANCE-TAX-P08 | [BE] LedgerService: approveJournalEntry, createJournalEntry, getJournalEntry, listJournalEntries | 8 | Hrushikant Patkar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: approveJournalEntry, createJournalEntry, getJournalEntry, listJournalEntries. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Done when `finance#approveJournalEntry`, `finance#createJournalEntry`, `finance#getJournalEntry`, `finance#listJournalEntries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-LEDGER-JOURNAL-2 | AM-FINANCE-TAX-P08 | [BE] LedgerService: reverseJournalEntry | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: reverseJournalEntry. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#reverseJournalEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-FINANCE-6 | AM-FINANCE-TAX-P08 | [BE] LedgerService: recordSettlement | 2 | Deep Khanvilkar | LedgerService | MIG-LEDGER MIG-LEDGER-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordSettlement. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management; additive to LedgerService, whose first-release owner (Hrushikant Patkar) reviews. Done when `finance#recordSettlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-LEDGER-REPORTING-1 | AM-FINANCE-TAX-P08 | [BE] LedgerService: getFinancialReport, getVatReturn | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-KERNEL SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-LEDGER-FINANCE-2 SVC-LEDGER-FINANCE-3 SVC-LEDGER-FINANCE-6 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-3 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-3 SVC-ORDER-ORDERS-27 SVC-ORDER-ORDERS-28 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-REFUND-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-JOURNAL-1 VM-LEDGER-JOURNAL-2 VM-LEDGER-LEDGER-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-MIG-LEDGER VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 | Operations beyond the first release: getFinancialReport, getVatReturn. Additive to LedgerService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `finance#getFinancialReport`, `finance#getVatReturn` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-22 | AM-FOOD-BEVERAGE-P06 | [BE] FnbService: setSectionLayout | 1 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSectionLayout. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App; additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#setSectionLayout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-21 | AM-FOOD-BEVERAGE-P06 | [BE] FnbService: getFnbReservationPolicy, notifyWaitlistParty, resolveBookingConflict, sendBookingConfirmation | 5 | Narayan Gaonkar | FnbService | MIG-FNB MIG-FNB-3 MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFnbReservationPolicy, notifyWaitlistParty, resolveBookingConflict, sendBookingConfirmation. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App; additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#getFnbReservationPolicy`, `fnb#notifyWaitlistParty`, `fnb#resolveBookingConflict`, `fnb#sendBookingConfirmation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-27 | AM-ORDERS-RESERVATIONS-P08-8 | [BE] OrderService: listGroupAmendmentCancellation, listGroupTicketFulfillment | 2 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-MARKETING MIG-ORDERS MIG-ORDERS-18 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-FNB-FNB-12 SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-6 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-9 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-19 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-31 SVC-ORDER-ORDERS-32 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-MIG-ORDERS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 | Operations: listGroupAmendmentCancellation, listGroupTicketFulfillment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 8 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listGroupAmendmentCancellation`, `orders#listGroupTicketFulfillment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-MARKETING-9 | AM-FOOD-BEVERAGE-P06 | [BE] MarketingService: matchGuest | 1 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 | Operations: matchGuest. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Food & Beverage · Staff App; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#matchGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-FNB-8 | AM-FOOD-BEVERAGE-P08 | [DB] Forward migration V1218__fnb.sql: fnb for Food & Beverage · Venue Management (2 tables) | 2 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.outlet_template, fnb.service_charge_policy. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (fnb.outlet_template: index outlet_template_scope_path_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: fnb.service_charge_policy: rename column included_in_display_price to is_included_in_display_price, rename column shown_separately to is_shown_separately); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `fnb.outlet_template`, `fnb.service_charge_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 2 | VM-INVENTORY-COUNT-1 | AM-FOOD-BEVERAGE-P08 | [BE] InventoryService: cancelStockCount, getCountVariance, listStockCounts, postStockCount | 8 | Narayan Gaonkar | InventoryService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-INVENTORY | Operations beyond the first release: cancelStockCount, getCountVariance, listStockCounts, postStockCount. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#cancelStockCount`, `inventory#getCountVariance`, `inventory#listStockCounts`, `inventory#postStockCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-FNB-KITCHEN-1 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: getKitchenRoutingRules, setKitchenRoutingRules, setKitchenStations | 5 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB | Operations beyond the first release: getKitchenRoutingRules, setKitchenRoutingRules, setKitchenStations. Additive to FnbService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#getKitchenRoutingRules`, `fnb#setKitchenRoutingRules`, `fnb#setKitchenStations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-26 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: getFnbServiceChargePolicy, setFnbServiceChargePolicy | 3 | Hrushikant Patkar | FnbService | MIG-FNB-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFnbServiceChargePolicy, setFnbServiceChargePolicy. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management; additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#getFnbServiceChargePolicy`, `fnb#setFnbServiceChargePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-OUTLET-1 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: listOutletTemplates, setOutletTemplate | 3 | Pranay Shinde | FnbService | MIG-FNB-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOutletTemplates, setOutletTemplate. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management; additive to FnbService, whose first-release owner (Narayan Gaonkar) reviews. Done when `fnb#listOutletTemplates`, `fnb#setOutletTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-RETAIL-RETAIL-2 | AM-RETAIL-P06 | [BE] RetailService: cancelMerchandiseReservation, collectMerchandiseReservation | 3 | Narayan Gaonkar | RetailService | MIG-INVENTORY MIG-PLATFORM MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelMerchandiseReservation, collectMerchandiseReservation. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Staff App; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#cancelMerchandiseReservation`, `retail#collectMerchandiseReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-RETAIL-FLOOR-3 | AM-RETAIL-P06 | [BE] RetailService: getOutletStock | 1 | Pallavi Sawant | RetailService | MIG-PLATFORM MIG-RETAIL PLATFORM-KERNEL SVC-RETAIL-MERCHANDISE-1 SVC-TENANCY-WORKSTATION-1 SVC-TENANCY-WORKSTATION-2 | Operations: getOutletStock. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Staff App; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#getOutletStock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-RETAIL-2 | AM-RETAIL-P08 | [DB] Forward migration V1158__retail.sql: retail for Retail · Venue Management (2 tables) | 2 | Hrushikant Patkar | RetailService | MIG-BASELINE MIG-RETAIL | Tables: retail.exchange, retail.product_recommendation. Source DDL: backend/tenant/010-retail.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (retail.exchange: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0105__after_r1_20261018.sql (retail.exchange: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: retail.exchange: rename column returned_value to returned_amount, rename column replacement_value to replacement_amount, rename column difference to difference_amount; retail.product_recommendation: foreign key product_recommendation_source_product_id_fkey, drop index product_recommendation_target_product_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `retail.exchange`, `retail.product_recommendation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 3 | SVC-RETAIL-RETAIL-3 | AM-RETAIL-P08 | [BE] RetailService: listRetailRecommendations | 1 | Hrushikant Patkar | RetailService | MIG-RETAIL-2 PLATFORM-KERNEL | Operations: listRetailRecommendations. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Venue Management; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#listRetailRecommendations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-RETAIL-RETURN-2 | AM-RETAIL-P08 | [BE] RetailService: createRetailExchange, listRetailReturns | 3 | Hrushikant Patkar | RetailService | MIG-RETAIL MIG-RETAIL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailExchange, listRetailReturns. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Venue Management; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#createRetailExchange`, `retail#listRetailReturns` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RENTAL-3 | AM-RENTALS-P06 | [DB] Forward migration V1022__rental.sql: rental for Rentals · Staff App 1 of 2 (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PLATFORM VM-MIG-RENTAL | Tables: rental.deposit_policy, rental.incident, rental.inspection, rental.inspection_item, rental.pricing_profile, rental.quote. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (rental.incident: column recorded_at; rental.inspection: columns checklist, recorded_at and booking_id, constraint inspection_booking_id_fkey, index inspection_booking_id_idx; rental.inspection_item: row-level security apply_parent_rls; rental.pricing_profile: columns duration_tiers and calendar_rules, index pricing_profile_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: rental.deposit_policy: rename column inspection_required_before_release to requires_inspection_before_release; rental.inspection: foreign key inspection_item_rental_inspection_id_fkey (from rental.inspection_item); rental.inspection_item: foreign key inspection_item_rental_agreement_item_id_fkey, foreign key inspection_item_rental_inspection_id_fkey; rental.quote: foreign key quote_product_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Leave out the key inspection_item_rental_agreement_item_id_fkey** (rental.inspection_item to rental.agreement_item): MIG-RENTAL-5 creates rental.agreement_item later and adds it. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `rental.deposit_policy`, `rental.incident`, `rental.inspection`, `rental.inspection_item`, `rental.pricing_profile`, `rental.quote` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RENTAL-3 | AM-RENTALS-P06 | [BE] VenueOpsService: assignRentalEquipment, checkOutRental, extendRental, listOverdueRentals | 8 | Hrushikant Patkar | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: assignRentalEquipment, checkOutRental, extendRental, listOverdueRentals. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 1 of 2; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#assignRentalEquipment`, `rental#checkOutRental`, `rental#extendRental`, `rental#listOverdueRentals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RENTAL-4 | AM-RENTALS-P06 | [BE] VenueOpsService: listRentalBookings, quoteRentalPrice, recordRentalInspection, reportRentalIncident | 8 | Pranay Shinde | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: listRentalBookings, quoteRentalPrice, recordRentalInspection, reportRentalIncident. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 1 of 2; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#listRentalBookings`, `rental#quoteRentalPrice`, `rental#recordRentalInspection`, `rental#reportRentalIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RENTAL-5 | AM-RENTALS-P06 | [BE] VenueOpsService: swapRentalEquipment | 2 | Deep Khanvilkar | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: swapRentalEquipment. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 1 of 2; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#swapRentalEquipment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-RENTAL-4 | AM-RENTALS-P06-2 | [DB] Forward migration V1159__rental.sql: rental for Rentals · Staff App 2 of 2 (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE VM-MIG-RENTAL | Tables: rental.damage_assessment, rental.settlement. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (rental.damage_assessment: column booking_id, constraint damage_assessment_booking_id_fkey, index damage_assessment_booking_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `rental.damage_assessment`, `rental.settlement` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RENTAL-6 | AM-RENTALS-P06-2 | [BE] VenueOpsService: assessRentalDamage, returnRental | 5 | Hrushikant Patkar | VenueOpsService | MIG-RENTAL-3 MIG-RENTAL-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assessRentalDamage, returnRental. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 2 of 2; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#assessRentalDamage`, `rental#returnRental` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-MAINTENANCE-5 | AM-RENTALS-P08 | [DB] Forward migration V1219__maintenance.sql: maintenance for Rentals · Venue Management 1 of 5 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-MAINTENANCE VM-MIG-MAINTENANCE | Tables: maintenance.asset_category. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (maintenance.asset_category: index asset_category_code_uniq, row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `maintenance.asset_category` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 3 | MIG-RENTAL-5 | AM-RENTALS-P08 | [DB] Forward migration V1135__rental.sql: rental for Rentals · Venue Management 1 of 5 (5 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-ORDERS MIG-PLATFORM VM-MIG-RENTAL | Tables: rental.agreement, rental.agreement_item, rental.agreement_rules, rental.fee_policy, rental.operational_rules. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (rental.agreement_rules: column product_id, constraint agreement_rules_product_id_fkey, indexes agreement_rules_product_id_idx and agreement_rules_product_id_uniq; rental.fee_policy: column late_fee_tiers; rental.operational_rules: column product_id, constraint operational_rules_product_id_fkey, indexes operational_rules_product_id_idx and operational_rules_product_id_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: rental.agreement: foreign key agreement_item_rental_agreement_id_fkey (from rental.agreement_item); rental.agreement_item: rename column stock_reservation_id to stock_earmark_id, rename index agreement_item_stock_reservation_id_idx to agreement_item_stock_earmark_id_idx, foreign key agreement_item_catalogue_product_id_fkey, foreign key agreement_item_order_line_id_fkey, foreign key agreement_item_rental_agreement_id_fkey, foreign key inspection_item_rental_agreement_item_id_fkey (from rental.inspection_item); rental.agreement_rules: rename column guardian_signature_for_minor to requires_guardian_signature_for_minor); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Also add the key inspection_item_rental_agreement_item_id_fkey here** (rental.inspection_item to rental.agreement_item, guarded): MIG-RENTAL-3 creates rental.inspection_item before rental.agreement_item exists. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `rental.agreement`, `rental.agreement_item`, `rental.agreement_rules`, `rental.fee_policy`, `rental.operational_rules` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-VENUEOPS-RENTAL-10 | AM-RENTALS-P08 | [BE] VenueOpsService: setRentalAvailabilityRules, setRentalDurationRules, setRentalInventoryModel, setRentalOperationalRules | 8 | Narayan Gaonkar | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRentalAvailabilityRules, setRentalDurationRules, setRentalInventoryModel, setRentalOperationalRules. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#setRentalAvailabilityRules`, `rental#setRentalDurationRules`, `rental#setRentalInventoryModel`, `rental#setRentalOperationalRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-11 | AM-RENTALS-P08 | [BE] VenueOpsService: setRentalProductLocations, updateRentalProduct, validateRentalProduct | 3 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-3 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRentalProductLocations, updateRentalProduct, validateRentalProduct. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#setRentalProductLocations`, `rental#updateRentalProduct`, `rental#validateRentalProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-7 | AM-RENTALS-P08 | [BE] VenueOpsService: createRentalAgreement, createRentalBlackout, createRentalCategory, createRentalProduct | 8 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRentalAgreement, createRentalBlackout, createRentalCategory, createRentalProduct. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#createRentalAgreement`, `rental#createRentalBlackout`, `rental#createRentalCategory`, `rental#createRentalProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-8 | AM-RENTALS-P08 | [BE] VenueOpsService: getRentalAgreement, getRentalProduct, importRentalCatalogue, listRentalAgreements | 5 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getRentalAgreement, getRentalProduct, importRentalCatalogue, listRentalAgreements. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#getRentalAgreement`, `rental#getRentalProduct`, `rental#importRentalCatalogue`, `rental#listRentalAgreements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-9 | AM-RENTALS-P08 | [BE] VenueOpsService: listRentalCategories, listRentalProducts, publishRentalProduct, setRentalAgreementRequirements | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listRentalCategories, listRentalProducts, publishRentalProduct, setRentalAgreementRequirements. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#listRentalCategories`, `rental#listRentalProducts`, `rental#publishRentalProduct`, `rental#setRentalAgreementRequirements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-RENTAL-6 | AM-RENTALS-P08-2 | [DB] Forward migration V1160__rental.sql: rental for Rentals · Venue Management 2 of 5 (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE VM-MIG-RENTAL | Tables: rental.agreement_signature, rental.override. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `rental.agreement_signature`, `rental.override` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RENTAL-12 | AM-RENTALS-P08-2 | [BE] VenueOpsService: createRentalBooking, createRentalPricingProfile, explainRentalPrice, listRentalPricingProfiles | 8 | Pranay Shinde | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: createRentalBooking, createRentalPricingProfile, explainRentalPrice, listRentalPricingProfiles. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 2 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#createRentalBooking`, `rental#createRentalPricingProfile`, `rental#explainRentalPrice`, `rental#listRentalPricingProfiles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-13 | AM-RENTALS-P08-2 | [BE] VenueOpsService: requestRentalCommercialOverride, setRentalDepositPolicy, setRentalFeePolicy, signRentalAgreement | 8 | Narayan Gaonkar | VenueOpsService | MIG-RENTAL-3 MIG-RENTAL-5 MIG-RENTAL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: requestRentalCommercialOverride, setRentalDepositPolicy, setRentalFeePolicy, signRentalAgreement. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 2 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#requestRentalCommercialOverride`, `rental#setRentalDepositPolicy`, `rental#setRentalFeePolicy`, `rental#signRentalAgreement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-14 | AM-RENTALS-P08-2 | [BE] VenueOpsService: simulateRentalPricing, updateRentalBooking, updateRentalPricingProfile | 8 | Pranay Shinde | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: simulateRentalPricing, updateRentalBooking, updateRentalPricingProfile. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 2 of 5; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `rental#simulateRentalPricing`, `rental#updateRentalBooking`, `rental#updateRentalPricingProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-INVENTORY-2 | AM-INVENTORY-P06 | [DB] Forward migration V1050__inventory.sql: inventory for Inventory · Staff App (1 tables) | 1 | Hrushikant Patkar | InventoryService | MIG-BASELINE MIG-INVENTORY VM-MIG-INVENTORY | Tables: inventory.daily_count_list. Source DDL: backend/tenant/010-inventory.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `inventory.daily_count_list` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 2 | VM-FNB-FNB-2 | AM-INVENTORY-P06 | [BE] FnbService: requestRecount | 1 | Chinmay Patkar | FnbService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: requestRecount. Additive to FnbService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `fnb#requestRecount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-COUNT-2 | AM-INVENTORY-P06 | [BE] InventoryService: recountStockCount, startStockCount, submitCountLines | 8 | Narayan Gaonkar | InventoryService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: recountStockCount, startStockCount, submitCountLines. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#recountStockCount`, `inventory#startStockCount`, `inventory#submitCountLines` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-REQUISITION-1 | AM-INVENTORY-P06 | [BE] InventoryService: approveRequisition, createRequisition, getSuggestedRequisitions, listRequisitions | 8 | Narayan Gaonkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: approveRequisition, createRequisition, getSuggestedRequisitions, listRequisitions. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#approveRequisition`, `inventory#createRequisition`, `inventory#getSuggestedRequisitions`, `inventory#listRequisitions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-INVENTORY-INVENTORY-2 | AM-INVENTORY-P06 | [BE] InventoryService: setDailyCount | 1 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-INVENTORY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDailyCount. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Inventory · Staff App; additive to InventoryService, whose first-release owner (Narayan Gaonkar) reviews. Done when `inventory#setDailyCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-INVENTORY-COUNT-3 | AM-INVENTORY-P06 | [BE] InventoryService: listStockCountLines | 1 | Deep Khanvilkar | InventoryService | PLATFORM-KERNEL VM-FNB-FNB-1 VM-FNB-FNB-2 VM-INVENTORY-COUNT-1 VM-INVENTORY-COUNT-2 VM-MIG-INVENTORY | Operations: listStockCountLines. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Inventory · Staff App; additive to InventoryService, whose first-release owner (Narayan Gaonkar) reviews. Done when `inventory#listStockCountLines` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-PROCUREMENT-1 | AM-INVENTORY-P08 | [BE] InventoryService: acknowledgePurchaseOrder, cancelRequisition, closePurchaseOrderShort, sendPurchaseOrder | 8 | Narayan Gaonkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: acknowledgePurchaseOrder, cancelRequisition, closePurchaseOrderShort, sendPurchaseOrder. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#acknowledgePurchaseOrder`, `inventory#cancelRequisition`, `inventory#closePurchaseOrderShort`, `inventory#sendPurchaseOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-RECEIPT-1 | AM-INVENTORY-P08 | [BE] InventoryService: listGoodsReceipts | 1 | Chinmay Patkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-RECEIPT-1 | Operations beyond the first release: listGoodsReceipts. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#listGoodsReceipts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-SUPPLIER-1 | AM-INVENTORY-P08 | [BE] InventoryService: compareQuotations, createSupplier, createSupplierContract, listSupplierContracts | 8 | Narayan Gaonkar | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: compareQuotations, createSupplier, createSupplierContract, listSupplierContracts. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Done when `inventory#compareQuotations`, `inventory#createSupplier`, `inventory#createSupplierContract`, `inventory#listSupplierContracts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-SUPPLIER-2 | AM-INVENTORY-P08 | [BE] InventoryService: listSuppliers, recordQuotation, updateSupplierContract | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: listSuppliers, recordQuotation, updateSupplierContract. Additive to InventoryService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `inventory#listSuppliers`, `inventory#recordQuotation`, `inventory#updateSupplierContract` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-8 | AM-ACCREDITATION-P08 | [DB] Forward migration V1220__accreditation.sql: accreditation for Accreditation · Venue Management 1 of 4 (4 tables) | 3 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.document, accreditation.identity_conflict, accreditation.notification_rules, accreditation.requirements. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (accreditation.notification_rules: column rules; accreditation.requirements: column rows); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: accreditation.document: foreign key document_asset_id_fkey; accreditation.identity_conflict: rename column differing_access to has_differing_access); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.document`, `accreditation.identity_conflict`, `accreditation.notification_rules`, `accreditation.requirements` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-10 | AM-ACCREDITATION-P08 | [BE] TenancyService: listAccreditationHolders, listAccreditationIdentityConflicts, resolveIdentityConflict, setAccreditationRequirements | 8 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: listAccreditationHolders, listAccreditationIdentityConflicts, resolveIdentityConflict, setAccreditationRequirements. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#listAccreditationHolders`, `accreditation#listAccreditationIdentityConflicts`, `accreditation#resolveIdentityConflict`, `accreditation#setAccreditationRequirements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-11 | AM-ACCREDITATION-P08 | [BE] TenancyService: submitAccreditationApplication, submitAccreditationDocument, updateAccreditationApplication, updateAccreditationHolder | 8 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: submitAccreditationApplication, submitAccreditationDocument, updateAccreditationApplication, updateAccreditationHolder. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#submitAccreditationApplication`, `accreditation#submitAccreditationDocument`, `accreditation#updateAccreditationApplication`, `accreditation#updateAccreditationHolder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-12 | AM-ACCREDITATION-P08 | [BE] TenancyService: verifyAccreditationDocument, withdrawAccreditationApplication | 3 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: verifyAccreditationDocument, withdrawAccreditationApplication. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#verifyAccreditationDocument`, `accreditation#withdrawAccreditationApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-8 | AM-ACCREDITATION-P08 | [BE] TenancyService: cloneAccreditationProgramme, createAccreditationApplication, createAccreditationProgramme, decideAccreditationApplication | 8 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-2 MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: cloneAccreditationProgramme, createAccreditationApplication, createAccreditationProgramme, decideAccreditationApplication. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#cloneAccreditationProgramme`, `accreditation#createAccreditationApplication`, `accreditation#createAccreditationProgramme`, `accreditation#decideAccreditationApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-9 | AM-ACCREDITATION-P08-2 | [DB] Forward migration V1221__accreditation.sql: accreditation for Accreditation · Venue Management 2 of 4 (3 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.badge_template, accreditation.mobile_credential_delivery, accreditation.print_job. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (accreditation.print_job: column failures); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: accreditation.mobile_credential_delivery: foreign key mobile_credential_delivery_credential_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.badge_template`, `accreditation.mobile_credential_delivery`, `accreditation.print_job` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-13 | AM-ACCREDITATION-P08-2 | [BE] TenancyService: createBadgePrintJob, deliverAccreditationCredential, getAccreditationApplication, issueAccreditationCredential | 8 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-9 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: createBadgePrintJob, deliverAccreditationCredential, getAccreditationApplication, issueAccreditationCredential. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#createBadgePrintJob`, `accreditation#deliverAccreditationCredential`, `accreditation#getAccreditationApplication`, `accreditation#issueAccreditationCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-14 | AM-ACCREDITATION-P08-2 | [BE] TenancyService: listBadgePrintJobs, listBadgeTemplates, replaceAccreditationCredential, resubmitAccreditationApplication | 5 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-ACCREDITATION-9 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: listBadgePrintJobs, listBadgeTemplates, replaceAccreditationCredential, resubmitAccreditationApplication. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#listBadgePrintJobs`, `accreditation#listBadgeTemplates`, `accreditation#replaceAccreditationCredential`, `accreditation#resubmitAccreditationApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-15 | AM-ACCREDITATION-P08-2 | [BE] TenancyService: setBadgeTemplate, setHolderAccess | 3 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBadgeTemplate, setHolderAccess. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#setBadgeTemplate`, `accreditation#setHolderAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-10 | AM-ACCREDITATION-P08-3 | [DB] Forward migration V1222__accreditation.sql: accreditation for Accreditation · Venue Management 3 of 4 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.data_export. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `accreditation.data_export` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-16 | AM-ACCREDITATION-P08-3 | [BE] TenancyService: exportAccreditationData, getAccreditationExport, getAccreditationValidity, importAccreditationHolders | 5 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-10 MIG-ACCREDITATION-2 MIG-ACCREDITATION-3 MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: exportAccreditationData, getAccreditationExport, getAccreditationValidity, importAccreditationHolders. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 3 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#exportAccreditationData`, `accreditation#getAccreditationExport`, `accreditation#getAccreditationValidity`, `accreditation#importAccreditationHolders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-18 | AM-ACCREDITATION-P08-3 | [BE] TenancyService: listAccreditationAccessActivity, listAccreditationExports, previewAccessImpact, renewAccreditation | 5 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-10 MIG-ACCREDITATION-2 MIG-ACCREDITATION-3 MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: listAccreditationAccessActivity, listAccreditationExports, previewAccessImpact, renewAccreditation. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 3 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#listAccreditationAccessActivity`, `accreditation#listAccreditationExports`, `accreditation#previewAccessImpact`, `accreditation#renewAccreditation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-19 | AM-ACCREDITATION-P08-3 | [BE] TenancyService: setAccreditationNotificationRules, setAccreditationStatus, setAccreditationValidity | 5 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-2 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: setAccreditationNotificationRules, setAccreditationStatus, setAccreditationValidity. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 3 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#setAccreditationNotificationRules`, `accreditation#setAccreditationStatus`, `accreditation#setAccreditationValidity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-ACCREDITATION-9 | AM-ACCREDITATION-P08 | [BE] TenancyService: getAccreditationHolder, listAccreditationApplications, listAccreditationCredentials, listAccreditationDocuments | 3 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-8 PLATFORM-KERNEL SVC-TENANCY-ACCREDITATION-10 SVC-TENANCY-ACCREDITATION-11 SVC-TENANCY-ACCREDITATION-12 SVC-TENANCY-ACCREDITATION-13 SVC-TENANCY-ACCREDITATION-14 SVC-TENANCY-ACCREDITATION-16 SVC-TENANCY-ACCREDITATION-18 SVC-TENANCY-ACCREDITATION-19 SVC-TENANCY-ACCREDITATION-8 VM-MIG-ACCREDITATION | Operations: getAccreditationHolder, listAccreditationApplications, listAccreditationCredentials, listAccreditationDocuments. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#getAccreditationHolder`, `accreditation#listAccreditationApplications`, `accreditation#listAccreditationCredentials`, `accreditation#listAccreditationDocuments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-20 | AM-ACCREDITATION-P11 | [BE] TenancyService: issueMyAccreditationWalletPass, listMyAccreditationApplications, listMyAccreditationCredentials | 5 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: issueMyAccreditationWalletPass, listMyAccreditationApplications, listMyAccreditationCredentials. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Accreditation Web; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `accreditation#issueMyAccreditationWalletPass`, `accreditation#listMyAccreditationApplications`, `accreditation#listMyAccreditationCredentials` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | ACC-UAEPASS-ICP | AM-ACCREDITATION-API-PLATFORM | [BE] Identity verification for accreditation: UAE Pass and ICP | 8 | Pranay Shinde |  | PLATFORM-KERNEL | Identity verification for accreditation: UAE Pass and ICP. 2 October (Chinmay, DEC-457): UAE Pass sign-in/verification and ICP (Federal Authority for Identity, Citizenship, Customs and Port Security) document checks for accreditation applicants, alongside manual review. Needs client access to both (external dependencies register). Done when: an applicant verified through UAE Pass shows the verified identity on the reviewer workspace, and an ICP check result is recorded on the application.
8 | 3 | MIG-RESOURCES-4 | AM-RESOURCES-CAPACITY-P08 | [DB] Forward migration V1195__resources.sql: resources for Resources & Capacity · Venue Management 1 of 4 (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PLATFORM MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.attribute_definition, resources.resource_audit, resources.resource_category, resources.resource_dependency, resources.resource_relation, resources.venue_assignment. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (resources.attribute_definition: index attribute_definition_code_uniq, row-level security apply_read_beneath_rls; resources.resource_category: index resource_category_code_uniq, row-level security apply_read_beneath_rls; resources.venue_assignment: column resource_id, constraint venue_assignment_resource_id_fkey, index venue_assignment_resource_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: resources.resource_relation: foreign key resource_relation_resource_id_fkey; resources.venue_assignment: rename column shared_pool to is_shared_across_venues, foreign key venue_assignment_primary_venue_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `resources.attribute_definition`, `resources.resource_audit`, `resources.resource_category`, `resources.resource_dependency`, `resources.resource_relation`, `resources.venue_assignment` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-RESOURCES-3 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: setResourceQualifications | 2 | Chinmay Patkar | VenueOpsService | MIG-IDENTITY MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: setResourceQualifications. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `resources#setResourceQualifications` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-WORK-1 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: cancelWorkOrder | 3 | Sanket Keluskar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: cancelWorkOrder. Additive to VenueOpsService; its first-release owner (Narayan Gaonkar) reviews. Helper task: Narayan Gaonkar owns the service and reviews. Done when `maintenance#cancelWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-11 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: listResourceAttributes, listResourceCategories, listResourceTypes, setResourceDependencies | 3 | Deep Khanvilkar | VenueOpsService | MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listResourceAttributes, listResourceCategories, listResourceTypes, setResourceDependencies. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#listResourceAttributes`, `resources#listResourceCategories`, `resources#listResourceTypes`, `resources#setResourceDependencies` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-12 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: setResourceHierarchy, setResourceVenueAssignment, updateResourceCategory, updateResourceType | 8 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResourceHierarchy, setResourceVenueAssignment, updateResourceCategory, updateResourceType. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#setResourceHierarchy`, `resources#setResourceVenueAssignment`, `resources#updateResourceCategory`, `resources#updateResourceType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-9 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: createResourceAttribute, createResourceCategory, createResourceType, getResourceAuditTrail | 5 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResourceAttribute, createResourceCategory, createResourceType, getResourceAuditTrail. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#createResourceAttribute`, `resources#createResourceCategory`, `resources#createResourceType`, `resources#getResourceAuditTrail` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RESOURCES-5 | AM-RESOURCES-CAPACITY-P08-2 | [DB] Forward migration V1198__resources.sql: resources for Resources & Capacity · Venue Management 2 of 4 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.allocation_policy. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: resources.allocation_policy: rename column respect_resource_priority to respects_resource_priority); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `resources.allocation_policy` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-TENANCY-WORKFORCE-2 | AM-RESOURCES-CAPACITY-P08-2 | [BE] TenancyService: listIntegrationSources, setFieldOwnership, validateWorkforceCompliance | 2 | Deep Khanvilkar | TenancyService | MIG-IDENTITY MIG-WORKFORCE MIG-WORKFORCE-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: listIntegrationSources, setFieldOwnership, validateWorkforceCompliance. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#listIntegrationSources`, `workforce#setFieldOwnership`, `workforce#validateWorkforceCompliance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-13 | AM-RESOURCES-CAPACITY-P08-2 | [BE] VenueOpsService: allocateResources, cancelResourceBooking, getResourceAllocationPolicy, listResourceBookings | 5 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-4 MIG-RESOURCES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: allocateResources, cancelResourceBooking, getResourceAllocationPolicy, listResourceBookings. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#allocateResources`, `resources#cancelResourceBooking`, `resources#getResourceAllocationPolicy`, `resources#listResourceBookings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-14 | AM-RESOURCES-CAPACITY-P08-2 | [BE] VenueOpsService: replaceResourceAllocation, setResourceAllocationPolicy, setResourceSelectionPolicy, updateResourceBooking | 5 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-2 MIG-RESOURCES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations: replaceResourceAllocation, setResourceAllocationPolicy, setResourceSelectionPolicy, updateResourceBooking. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#replaceResourceAllocation`, `resources#setResourceAllocationPolicy`, `resources#setResourceSelectionPolicy`, `resources#updateResourceBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RESOURCES-6 | AM-RESOURCES-CAPACITY-P08-3 | [DB] Forward migration V1223__resources.sql: resources for Resources & Capacity · Venue Management 3 of 4 (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.resource_cost, resources.resource_request. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: resources.resource_cost: foreign key resource_cost_resource_id_fkey; resources.resource_request: foreign key resource_request_raised_by_principal_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `resources.resource_cost`, `resources.resource_request` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RESOURCES-15 | AM-RESOURCES-CAPACITY-P08-3 | [BE] VenueOpsService: createResourceCost, deleteResourceCost, getResourceCostAnalytics, listResourceCosts | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-RESOURCES-4 MIG-RESOURCES-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResourceCost, deleteResourceCost, getResourceCostAnalytics, listResourceCosts. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#createResourceCost`, `resources#deleteResourceCost`, `resources#getResourceCostAnalytics`, `resources#listResourceCosts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-16 | AM-RESOURCES-CAPACITY-P08-3 | [BE] VenueOpsService: raiseResourceRequest, setResourceBookingProgress | 3 | Narayan Gaonkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: raiseResourceRequest, setResourceBookingProgress. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#raiseResourceRequest`, `resources#setResourceBookingProgress` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-RESOURCES-10 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: getResourceCalendar, getResourceDependencies, getResourceHierarchy, getResourceUtilisation | 3 | Narayan Gaonkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-KERNEL SVC-VENUEOPS-MAINTENANCE-2 SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-11 SVC-VENUEOPS-RESOURCES-12 SVC-VENUEOPS-RESOURCES-13 SVC-VENUEOPS-RESOURCES-14 SVC-VENUEOPS-RESOURCES-16 SVC-VENUEOPS-RESOURCES-2 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-RESOURCES-9 SVC-VENUEOPS-WORKORDER-4 VM-VENUEOPS-MAINTENANCE-1 VM-VENUEOPS-RESOURCES-1 VM-VENUEOPS-WORK-1 VM-VENUEOPS-WORKORDER-1 VM-VENUEOPS-WORKORDER-3 | Operations: getResourceCalendar, getResourceDependencies, getResourceHierarchy, getResourceUtilisation. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `resources#getResourceCalendar`, `resources#getResourceDependencies`, `resources#getResourceHierarchy`, `resources#getResourceUtilisation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WORKFORCE-8 | AM-WORKFORCE-P06 | [DB] Forward migration V1224__workforce.sql: workforce for Workforce · Staff App (4 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.employment, workforce.staff_conversation, workforce.staff_conversation_participant, workforce.staff_message. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (workforce.staff_conversation_participant: row-level security apply_parent_rls; workforce.staff_message: row-level security apply_parent_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: workforce.employment: foreign key employment_employee_id_fkey; workforce.staff_conversation: foreign key staff_conversation_created_by_principal_id_fkey, foreign key staff_conversation_venue_id_fkey, foreign key staff_conversation_participant_staff_conversation_id_fkey (from workforce.staff_conversation_participant), foreign key staff_message_staff_conversation_id_fkey (from workforce.staff_message); workforce.staff_conversation_participant: foreign key staff_conversation_participant_principal_id_fkey, foreign key staff_conversation_participant_staff_conversation_id_fkey; workforce.staff_message: foreign key staff_message_sender_principal_id_fkey, foreign key staff_message_staff_conversation_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `workforce.employment`, `workforce.staff_conversation`, `workforce.staff_conversation_participant`, `workforce.staff_message` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 2 | VM-TENANCY-ANNOUNCEMENTS-1 | AM-WORKFORCE-P06 | [BE] TenancyService: getAnnouncementReach, listAnnouncements, publishAnnouncement | 5 | Deep Khanvilkar | TenancyService | MIG-IDENTITY MIG-PLATFORM MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: getAnnouncementReach, listAnnouncements, publishAnnouncement. Additive to TenancyService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `workforce#getAnnouncementReach`, `workforce#listAnnouncements`, `workforce#publishAnnouncement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-TENANCY-ATTENDANCE-1 | AM-WORKFORCE-P06 | [BE] TenancyService: amendAttendance, listAttendance | 2 | Chinmay Patkar | TenancyService | MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: amendAttendance, listAttendance. Additive to TenancyService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `workforce#amendAttendance`, `workforce#listAttendance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ANNOUNCEMENTS-2 | AM-WORKFORCE-P06 | [BE] TenancyService: acknowledgeAnnouncement, listStaffConversations, listStaffMessages, markStaffConversationRead | 8 | Pranay Shinde | TenancyService | MIG-WORKFORCE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: acknowledgeAnnouncement, listStaffConversations, listStaffMessages, markStaffConversationRead. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Staff App; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#acknowledgeAnnouncement`, `workforce#listStaffConversations`, `workforce#listStaffMessages`, `workforce#markStaffConversationRead` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ANNOUNCEMENTS-3 | AM-WORKFORCE-P06 | [BE] TenancyService: sendStaffMessage | 2 | Pranay Shinde | TenancyService | MIG-WORKFORCE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: sendStaffMessage. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Staff App; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#sendStaffMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKFORCE-6 | AM-WORKFORCE-P08 | [BE] TenancyService: listShiftTemplates, listSyncConflicts, listSyncRuns, requestLeave | 5 | Pranay Shinde | TenancyService | MIG-WORKFORCE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listShiftTemplates, listSyncConflicts, listSyncRuns, requestLeave. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#listShiftTemplates`, `workforce#listSyncConflicts`, `workforce#listSyncRuns`, `workforce#requestLeave` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKFORCE-7 | AM-WORKFORCE-P08 | [BE] TenancyService: resolveSyncConflict, setIntegrationSource, setLabourBudget, setLeaveType | 5 | Pranay Shinde | TenancyService | MIG-WORKFORCE-3 MIG-WORKFORCE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveSyncConflict, setIntegrationSource, setLabourBudget, setLeaveType. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#resolveSyncConflict`, `workforce#setIntegrationSource`, `workforce#setLabourBudget`, `workforce#setLeaveType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKFORCE-8 | AM-WORKFORCE-P08 | [BE] TenancyService: setShiftPattern, setShiftTemplate, setStaffingRules, startSync | 8 | Pranay Shinde | TenancyService | MIG-WORKFORCE-3 MIG-WORKFORCE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: setShiftPattern, setShiftTemplate, setStaffingRules, startSync. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#setShiftPattern`, `workforce#setShiftTemplate`, `workforce#setStaffingRules`, `workforce#startSync` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-WORKFORCE-3 | AM-WORKFORCE-P08 | [BE] TenancyService: broadcastToGuests, claimOpenShift, getEmployee, getFieldOwnership | 8 | Pranay Shinde | TenancyService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-VENUEMAP MIG-WORKFORCE-3 MIG-WORKFORCE-5 MIG-WORKFORCE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: broadcastToGuests, claimOpenShift, getEmployee, getFieldOwnership. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#broadcastToGuests`, `workforce#claimOpenShift`, `workforce#getEmployee`, `workforce#getFieldOwnership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-WORKFORCE-4 | AM-WORKFORCE-P08 | [BE] TenancyService: getLabourCost, listEmployees, listLabourBudgets, listLeaveBalances | 3 | Deep Khanvilkar | TenancyService | MIG-WORKFORCE MIG-WORKFORCE-5 PLATFORM-KERNEL SVC-TENANCY-ATTENDANCE-1 SVC-TENANCY-ROTA-1 SVC-TENANCY-WORKFORCE-7 SVC-TENANCY-WORKFORCE-8 VM-MIG-WORKFORCE VM-TENANCY-ATTENDANCE-1 VM-TENANCY-WORKFORCE-1 | Operations: getLabourCost, listEmployees, listLabourBudgets, listLeaveBalances. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#getLabourCost`, `workforce#listEmployees`, `workforce#listLabourBudgets`, `workforce#listLeaveBalances` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-TENANCY-WORKFORCE-5 | AM-WORKFORCE-P08 | [BE] TenancyService: listLeaveRequests, listLeaveTypes, listOpenShifts, listShiftPatterns | 3 | Pranay Shinde | TenancyService | MIG-WORKFORCE-5 PLATFORM-KERNEL SVC-TENANCY-WORKFORCE-3 SVC-TENANCY-WORKFORCE-6 SVC-TENANCY-WORKFORCE-7 SVC-TENANCY-WORKFORCE-8 VM-MIG-WORKFORCE | Operations: listLeaveRequests, listLeaveTypes, listOpenShifts, listShiftPatterns. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `workforce#listLeaveRequests`, `workforce#listLeaveTypes`, `workforce#listOpenShifts`, `workforce#listShiftPatterns` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-PLANNED-2 | AM-MAINTENANCE-SAFETY-P08 | [BE] VenueOpsService: createMaintenancePlan, listMaintenancePlans, updateMaintenancePlan | 5 | Narayan Gaonkar | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations: createMaintenancePlan, listMaintenancePlans, updateMaintenancePlan. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Venue Management 1 of 2; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#createMaintenancePlan`, `maintenance#listMaintenancePlans`, `maintenance#updateMaintenancePlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-PLANNED-1 | AM-RESOURCES-CAPACITY-P08-3 | [BE] VenueOpsService: getDueMaintenance | 1 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-KERNEL SVC-VENUEOPS-PLANNED-2 SVC-VENUEOPS-RENTAL-8 VM-MIG-MAINTENANCE VM-VENUEOPS-ASSET-1 VM-VENUEOPS-ASSET-2 | Operations: getDueMaintenance. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#getDueMaintenance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-WORKORDER-6 | AM-MAINTENANCE-SAFETY-P08 | [BE] VenueOpsService: getWorkOrderPriorityPolicy, setWorkOrderPriorityPolicy | 3 | Narayan Gaonkar | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations: getWorkOrderPriorityPolicy, setWorkOrderPriorityPolicy. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Venue Management 1 of 2; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `maintenance#getWorkOrderPriorityPolicy`, `maintenance#setWorkOrderPriorityPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-GAMES-4 | AM-GAMES-RIDES-P08 | [DB] Forward migration V1167__games.sql: games for Games & Rides · Venue Management 1 of 4 (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES VM-MIG-GAMES | Tables: games.attraction_type, games.entitlement, games.gameplay_transaction, games.pricing_exception, games.reader_deployment, games.redemption_rules, games.validation_rules. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (games.attraction_type: row-level security apply_read_beneath_rls; games.entitlement: index entitlement_code_uniq; games.reader_deployment: column scope_path, index reader_deployment_scope_path_idx, row-level security apply_grant_holder_read_rls; games.redemption_rules: column earn_rules); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: games.gameplay_transaction: rename column decided_offline to was_decided_offline; games.pricing_exception: foreign key pricing_exception_game_id_fkey; games.redemption_rules: rename column tickets_expire to has_expiring_tickets); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `games.reader_deployment.scope_path`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `games.attraction_type`, `games.entitlement`, `games.gameplay_transaction`, `games.pricing_exception`, `games.reader_deployment`, `games.redemption_rules`, `games.validation_rules` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-TENANCY-WORKSTATION-6 | AM-GAMES-RIDES-P08 | [BE] TenancyService: getDevice | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-DEVICES-4 SVC-TENANCY-DEVICES-9 SVC-TENANCY-WORKSTATION-1 SVC-TENANCY-WORKSTATION-3 VM-TENANCY-WORKSTATION-1 | Operations: getDevice. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Pranay Shinde) reviews. Done when `tenancy#getDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-3 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: cloneReaderConfiguration, getGamePricing, getGameplayValidationRules, listAttractionTypes | 3 | Narayan Gaonkar | VenueOpsService | MIG-GAMES-2 MIG-GAMES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: cloneReaderConfiguration, getGamePricing, getGameplayValidationRules, listAttractionTypes. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#cloneReaderConfiguration`, `games#getGamePricing`, `games#getGameplayValidationRules`, `games#listAttractionTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-4 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: listGameEntitlements, listGameplayTransactions, listReaders, setAttractionType | 3 | Narayan Gaonkar | VenueOpsService | MIG-GAMES-2 MIG-GAMES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listGameEntitlements, listGameplayTransactions, listReaders, setAttractionType. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#listGameEntitlements`, `games#listGameplayTransactions`, `games#listReaders`, `games#setAttractionType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-5 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: setGameOperationalConfiguration, setReaderConfiguration, setReaderProfile, simulateGameplayAuthorisation | 8 | Narayan Gaonkar | VenueOpsService | MIG-CATALOGUE MIG-GAMES-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: setGameOperationalConfiguration, setReaderConfiguration, setReaderProfile, simulateGameplayAuthorisation. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#setGameOperationalConfiguration`, `games#setReaderConfiguration`, `games#setReaderProfile`, `games#simulateGameplayAuthorisation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-7 | AM-GAMES-RIDES-P08-2 | [BE] VenueOpsService: createGameEntitlement, setGamePricing, setGameplayValidationRules | 5 | Narayan Gaonkar | VenueOpsService | MIG-GAMES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: createGameEntitlement, setGamePricing, setGameplayValidationRules. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 2 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#createGameEntitlement`, `games#setGamePricing`, `games#setGameplayValidationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-GAMES-5 | AM-GAMES-RIDES-P08-3 | [DB] Forward migration V1168__games.sql: games for Games & Rides · Venue Management 3 of 4 (5 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES MIG-IDENTITY MIG-PLATFORM MIG-RETAIL VM-MIG-GAMES | Tables: games.card_expiry_rules, games.prize, games.prize_cost, games.redemption, games.redemption_line. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: games.card_expiry_rules: rename column extend_on_recharge to extends_on_recharge); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `games.card_expiry_rules`, `games.prize`, `games.prize_cost`, `games.redemption`, `games.redemption_line` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
17 | 3 | SVC-VENUEOPS-GAMES-8 | AM-GAMES-RIDES-P08-3 | [BE] VenueOpsService: setGameCardExpiryRules, setGameCardLifecycle, setPrizeCost, setRedemptionRules | 5 | Narayan Gaonkar | VenueOpsService | MIG-GAMES MIG-GAMES-4 MIG-GAMES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGameCardExpiryRules, setGameCardLifecycle, setPrizeCost, setRedemptionRules. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#setGameCardExpiryRules`, `games#setGameCardLifecycle`, `games#setPrizeCost`, `games#setRedemptionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-VENUEOPS-PRIZE-1 | AM-GAMES-RIDES-P08-3 | [BE] VenueOpsService: createPrize, listPrizes, lookupPrize, redeemPrize | 8 | Hrushikant Patkar | VenueOpsService | MIG-GAMES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPrize, listPrizes, lookupPrize, redeemPrize. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#createPrize`, `games#listPrizes`, `games#lookupPrize`, `games#redeemPrize` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-GAMES-6 | AM-GAMES-RIDES-P08-4 | [DB] Forward migration V1225__games.sql: games for Games & Rides · Venue Management 4 of 4 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES VM-MIG-GAMES | Tables: games.kiosk_config. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `games.kiosk_config` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-GAMES-9 | AM-GAMES-RIDES-P08-4 | [BE] VenueOpsService: deployReaderConfiguration, getGameEligibility, getGameplaySyncStatus, setGameKioskConfiguration | 3 | Deep Khanvilkar | VenueOpsService | MIG-GAMES MIG-GAMES-2 MIG-GAMES-4 MIG-GAMES-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: deployReaderConfiguration, getGameEligibility, getGameplaySyncStatus, setGameKioskConfiguration. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 4 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#deployReaderConfiguration`, `games#getGameEligibility`, `games#getGameplaySyncStatus`, `games#setGameKioskConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-VENUEOPS-GAMES-6 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: testReader, validateGameConfiguration | 2 | Deep Khanvilkar | VenueOpsService | MIG-GAMES MIG-GAMES-2 MIG-GAMES-4 PLATFORM-KERNEL SVC-VENUEOPS-CARD-1 SVC-VENUEOPS-CARD-2 SVC-VENUEOPS-GAMES-3 SVC-VENUEOPS-GAMES-5 SVC-VENUEOPS-GAMES-7 SVC-VENUEOPS-GAMES-8 SVC-VENUEOPS-GAMES-9 SVC-WALLET-CARD-1 SVC-WALLET-CARD-2 VM-MIG-GAMES VM-VENUEOPS-GAME-1 | Operations: testReader, validateGameConfiguration. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Narayan Gaonkar) reviews. Done when `games#testReader`, `games#validateGameConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-10 | AM-MARKETING-CRM-P05 | [BE] MarketingService: endKioskAssist | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endKioskAssist. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Kiosk; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#endKioskAssist` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-13 | AM-MARKETING-CRM-P06 | [BE] MarketingService: addGuestNote, mergeGuests | 3 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-2 MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: addGuestNote, mergeGuests. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Staff App; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#addGuestNote`, `marketing-crm#mergeGuests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-13 | AM-MARKETING-CRM-P08 | [DB] Forward migration V1171__marketing.sql: marketing for Marketing & CRM · Venue Management 1 of 5 (5 tables) | 5 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.duplicate_candidate, marketing.guest_attribute_model, marketing.identity_rules, marketing.privacy_exception, marketing.privacy_request. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.duplicate_candidate: column conflicts; marketing.guest_attribute_model: columns field_groups, attributes and identifiers; marketing.identity_rules: columns matchers and survivorship); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.privacy_request: rename column at_risk to is_at_risk, foreign key privacy_export_package_request_id_fkey (from marketing.privacy_export_package), foreign key privacy_request_subject_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Source DDL after r1: backend/tenant/V0108__after_r1_20261020.sql (marketing.privacy_exception: DROP CONSTRAINT IF EXISTS privacy_exception_system_chk; VALIDATE CONSTRAINT privacy_exception_system_chk, constraint privacy_exception_system_chk); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0116__after_r1_20261026.sql (marketing.privacy_request: column approval_request_id); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0118__after_r1_20261029.sql (marketing.privacy_request: index privacy_request_approval_request_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.duplicate_candidate`, `marketing.guest_attribute_model`, `marketing.identity_rules`, `marketing.privacy_exception`, `marketing.privacy_request` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
15 | 2 | VM-MARKETING-MARKETING-1 | AM-MARKETING-CRM-P08 | [BE] MarketingService: createJourney, getLostItemMatches, listJourneys, listLostItems | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MARKETING | Operations beyond the first release: createJourney, getLostItemMatches, listJourneys, listLostItems. Additive to MarketingService; its first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#createJourney`, `marketing-crm#getLostItemMatches`, `marketing-crm#listJourneys`, `marketing-crm#listLostItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-GUEST-3 | AM-MARKETING-CRM-P08 | [BE] MarketingService: mergeGuestProfiles, updateGuestProfile | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: mergeGuestProfiles, updateGuestProfile. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#mergeGuestProfiles`, `marketing-crm#updateGuestProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-7 | AM-MARKETING-CRM-P08 | [BE] MarketingService: decideDuplicateCandidate, getGuestAttributeModel, getGuestIntelligence, getGuestMatchPolicy | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-2 MIG-MARKETING-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideDuplicateCandidate, getGuestAttributeModel, getGuestIntelligence, getGuestMatchPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#decideDuplicateCandidate`, `marketing-crm#getGuestAttributeModel`, `marketing-crm#getGuestIntelligence`, `marketing-crm#getGuestMatchPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-8 | AM-MARKETING-CRM-P08 | [BE] MarketingService: getGuestRelationships, getIdentityResolutionRules, listDuplicateCandidates, setGuestAttributeModel | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING-13 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGuestRelationships, getIdentityResolutionRules, listDuplicateCandidates, setGuestAttributeModel. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getGuestRelationships`, `marketing-crm#getIdentityResolutionRules`, `marketing-crm#listDuplicateCandidates`, `marketing-crm#setGuestAttributeModel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-9 | AM-MARKETING-CRM-P08 | [BE] MarketingService: setGuestMatchPolicy, setGuestRelationships, setIdentityResolutionRules | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING-13 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGuestMatchPolicy, setGuestRelationships, setIdentityResolutionRules. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setGuestMatchPolicy`, `marketing-crm#setGuestRelationships`, `marketing-crm#setIdentityResolutionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-8 | AM-MARKETING-CRM-P08 | [BE] MarketingService: adjustLoyaltyPoints | 2 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: adjustLoyaltyPoints. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#adjustLoyaltyPoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-16 | AM-MARKETING-CRM-P08 | [BE] MarketingService: setGuestExtraFields | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGuestExtraFields. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setGuestExtraFields` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-14 | AM-MARKETING-CRM-P08-2 | [DB] Forward migration V1172__marketing.sql: marketing for Marketing & CRM · Venue Management 2 of 5 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.audience_activation, marketing.communication_preference_type, marketing.journey_enrollment, marketing.privacy_export_package, marketing.privacy_incident. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.privacy_export_package: columns identifiers, results and corrections; marketing.privacy_incident: row-level security apply_read_beneath_rls); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.audience_activation: rename column enforce_consent to enforces_consent, foreign key audience_activation_segment_id_fkey; marketing.journey_enrollment: foreign key journey_enrollment_journey_id_fkey, foreign key journey_enrollment_step_id_fkey, foreign key journey_enrollment_subject_id_fkey; marketing.privacy_export_package: foreign key privacy_export_package_request_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.privacy_export_package.results`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.audience_activation`, `marketing.communication_preference_type`, `marketing.journey_enrollment`, `marketing.privacy_export_package`, `marketing.privacy_incident` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
14 | 3 | SVC-MARKETING-SEGMENT-5 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: previewSegment | 1 | Narayan Gaonkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: previewSegment. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#previewSegment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-12 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: listDataSubjectCustomer, listPrivacy, listPrivacyEvidenceCompliance, setCommunicationPreferenceMarketing | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-14 MIG-MARKETING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDataSubjectCustomer, listPrivacy, listPrivacyEvidenceCompliance, setCommunicationPreferenceMarketing. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listDataSubjectCustomer`, `marketing-crm#listPrivacy`, `marketing-crm#listPrivacyEvidenceCompliance`, `marketing-crm#setCommunicationPreferenceMarketing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-13 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: setDataDiscoveryAccess, setPrivacyRequest | 5 | Hrushikant Patkar | MarketingService | MIG-MARKETING-13 MIG-MARKETING-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDataDiscoveryAccess, setPrivacyRequest. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setDataDiscoveryAccess`, `marketing-crm#setPrivacyRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-10 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: activateAudience, getAudienceOverlap, importAudienceList, listAudienceActivations | 5 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-14 MIG-MARKETING-6 MIG-MARKETING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: activateAudience, getAudienceOverlap, importAudienceList, listAudienceActivations. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#activateAudience`, `marketing-crm#getAudienceOverlap`, `marketing-crm#importAudienceList`, `marketing-crm#listAudienceActivations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-17 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: activateJourney, getJourneyPerformance, listMessageTriggers, recordPrivacyIncident | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-14 MIG-MARKETING-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MARKETING | Operations: activateJourney, getJourneyPerformance, listMessageTriggers, recordPrivacyIncident. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#activateJourney`, `marketing-crm#getJourneyPerformance`, `marketing-crm#listMessageTriggers`, `marketing-crm#recordPrivacyIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-22 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: setMessageTrigger | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMessageTrigger. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setMessageTrigger` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-GUESTS-11 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: listAudienceLists | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-8 PLATFORM-KERNEL SVC-MARKETING-GUESTS-10 | Operations: listAudienceLists. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listAudienceLists` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-9 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: setIntelligentRoutingSkill, setOrderBookingTicket, setServiceQueueDefinition | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setIntelligentRoutingSkill, setOrderBookingTicket, setServiceQueueDefinition. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setIntelligentRoutingSkill`, `marketing-crm#setOrderBookingTicket`, `marketing-crm#setServiceQueueDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-14 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: addSuppression | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addSuppression. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#addSuppression` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-23 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: retryMessageDispatch | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: retryMessageDispatch. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#retryMessageDispatch` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-MESSAGE-5 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: listSystemTransactionalTemplate | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-KERNEL SVC-MARKETING-MARKETING-22 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-2 | Operations: listSystemTransactionalTemplate. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listSystemTransactionalTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-10 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: listEscalationCriticalCase, listServiceRootCause, listSlaPolicyService, setCaseCategoryDefinition | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-6 MIG-MARKETING-9 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listEscalationCriticalCase, listServiceRootCause, listSlaPolicyService, setCaseCategoryDefinition. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listEscalationCriticalCase`, `marketing-crm#listServiceRootCause`, `marketing-crm#listSlaPolicyService`, `marketing-crm#setCaseCategoryDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-FEEDBACK-2 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: listCustomerSatisfactionFeedback, listReviews, respondToReview | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCustomerSatisfactionFeedback, listReviews, respondToReview. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCustomerSatisfactionFeedback`, `marketing-crm#listReviews`, `marketing-crm#respondToReview` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-24 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: setSlaPolicy | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSlaPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setSlaPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-18 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: setDigitalWaiverForm, setSignatorySignatureGuardian, setWaiverVerificationValidation | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-20 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDigitalWaiverForm, setSignatorySignatureGuardian, setWaiverVerificationValidation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setDigitalWaiverForm`, `marketing-crm#setSignatorySignatureGuardian`, `marketing-crm#setWaiverVerificationValidation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-15 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: listWaiver | 3 | Narayan Gaonkar | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-2 MIG-MARKETING-6 MIG-ORDERS PLATFORM-KERNEL PRD-W1-OWNER-FORMS SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-FNB-FNB-12 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-8 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-6 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-EVENT-1 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listWaiver. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listWaiver` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MESSAGE-6 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: listBusinessEventNotification, listDeliveryCommunicationPlatform, setChannelProvider, setSenderIdentityDomain | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-20 MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBusinessEventNotification, listDeliveryCommunicationPlatform, setChannelProvider, setSenderIdentityDomain. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listBusinessEventNotification`, `marketing-crm#listDeliveryCommunicationPlatform`, `marketing-crm#setChannelProvider`, `marketing-crm#setSenderIdentityDomain` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-MESSAGE-4 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: listCommunicationService, listDeliveryQueueFailure, listProviderHealthUsage, listRoutingPriorityThrottling | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-KERNEL SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-6 SVC-MARKETING-MARKETING-22 SVC-MARKETING-MARKETING-23 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-2 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-6 SVC-MARKETING-MESSAGE-9 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-PLATFORM-PUBLICAPI-1 SVC-TENANCY-WORKFORCE-3 | Operations: listCommunicationService, listDeliveryQueueFailure, listProviderHealthUsage, listRoutingPriorityThrottling. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCommunicationService`, `marketing-crm#listDeliveryQueueFailure`, `marketing-crm#listProviderHealthUsage`, `marketing-crm#listRoutingPriorityThrottling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-CONSENT-16 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: getSignatorySignatureGuardian, listComplianceEvidenceWaiver, listConsentPreferenceCommunication, listMinorGuardianGroup | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-2 MIG-MARKETING-20 MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL PRD-W1-OWNER-FORMS SVC-ACCESS-ACCESS-1 SVC-FNB-FNB-12 SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-14 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-7 SVC-MARKETING-CONSENT-8 SVC-MARKETING-GUESTS-9 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-13 SVC-MARKETING-MARKETING-23 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-9 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-TENANCY-WORKFORCE-3 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: getSignatorySignatureGuardian, listComplianceEvidenceWaiver, listConsentPreferenceCommunication, listMinorGuardianGroup. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getSignatorySignatureGuardian`, `marketing-crm#listComplianceEvidenceWaiver`, `marketing-crm#listConsentPreferenceCommunication`, `marketing-crm#listMinorGuardianGroup` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-22 | AM-MARKETING-CRM-P13-2 | [DB] Forward migration V1228__marketing.sql: marketing for Marketing & CRM · CMS 2 of 4 (4 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.consent_capture_point, marketing.minor_privacy_rule, marketing.privacy_change_set, marketing.processing_purpose. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.consent_capture_point: column steps; marketing.privacy_change_set: column items); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.consent_capture_point: rename column skip_if_current_version_accepted to skips_if_current_version_accepted; marketing.minor_privacy_rule: rename column restrict_marketing to restricts_marketing, rename column restrict_tracking to restricts_tracking, rename column restrict_personalisation to restricts_personalisation; marketing.processing_purpose: rename column data_controller_applicable_organization to data_controller_applicable_organisation, rename constraint processing_purpose_data_controller_applicable_organization_chk to processing_purpose_data_controller_applicable_organisation_chk); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.consent_capture_point.steps`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.consent_capture_point`, `marketing.minor_privacy_rule`, `marketing.privacy_change_set`, `marketing.processing_purpose` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CONSENT-19 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: approvePrivacyTesting, listConsentEvidenceWithdrawal, listCustomerPrivacyConsent, listDataProcessingPurpose | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-22 MIG-MARKETING-3 MIG-MARKETING-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approvePrivacyTesting, listConsentEvidenceWithdrawal, listCustomerPrivacyConsent, listDataProcessingPurpose. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#approvePrivacyTesting`, `marketing-crm#listConsentEvidenceWithdrawal`, `marketing-crm#listCustomerPrivacyConsent`, `marketing-crm#listDataProcessingPurpose` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-21 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: listPrivacyConsent, listPrivacyNoticePolicy, setConsentCapturePoint, setDataProcessingPurpose | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-14 MIG-MARKETING-22 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPrivacyConsent, listPrivacyNoticePolicy, setConsentCapturePoint, setDataProcessingPurpose. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listPrivacyConsent`, `marketing-crm#listPrivacyNoticePolicy`, `marketing-crm#setConsentCapturePoint`, `marketing-crm#setDataProcessingPurpose` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-22 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: setLegalHold, setMinorGuardianAge, setPrivacyComplianceException, setPrivacyNoticePolicyGovernance | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-22 MIG-MARKETING-3 MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLegalHold, setMinorGuardianAge, setPrivacyComplianceException, setPrivacyNoticePolicyGovernance. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#setLegalHold`, `marketing-crm#setMinorGuardianAge`, `marketing-crm#setPrivacyComplianceException`, `marketing-crm#setPrivacyNoticePolicyGovernance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-11 | AM-MARKETING-CRM-P08 | [BE] MarketingService: getConsentHistory, listPrivacyCompliance | 3 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-3 MIG-MARKETING-6 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-13 SVC-MARKETING-CONSENT-22 SVC-MARKETING-CONSENT-24 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-7 SVC-MARKETING-GUESTS-2 SVC-MARKETING-GUESTS-3 SVC-MARKETING-MARKETING-6 SVC-MARKETING-SEGMENT-1 SVC-MARKETING-SEGMENT-5 SVC-ORDER-CART-1 | Operations: getConsentHistory, listPrivacyCompliance. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getConsentHistory`, `marketing-crm#listPrivacyCompliance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-20 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: listDataRetentionExpiry, listDeletionAnonymizationRestriction, listDeviceConsents, listPrivacyComplianceExceptions | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-3 PLATFORM-KERNEL SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-22 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-GUESTS-2 | Operations: listDataRetentionExpiry, listDeletionAnonymizationRestriction, listDeviceConsents, listPrivacyComplianceExceptions. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listDataRetentionExpiry`, `marketing-crm#listDeletionAnonymizationRestriction`, `marketing-crm#listDeviceConsents`, `marketing-crm#listPrivacyComplianceExceptions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-23 | AM-MARKETING-CRM-P13-3 | [DB] Forward migration V1229__marketing.sql: marketing for Marketing & CRM · CMS 3 of 4 (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.waiver_localisation. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (marketing.waiver_localisation: column languages); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. **Changes no file writes, for this migration to write** (handoff/migration-review.md, where each row says what to write; CHG-R8MIG-013): not null `marketing.waiver_localisation.languages`. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.waiver_localisation` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CONSENT-25 | AM-MARKETING-CRM-P13-3 | [BE] MarketingService: approveWaiverTesting, getLocalizationBrandingCustomer, listDigitalSigningCollection, listDynamicFieldQuestion | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-23 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveWaiverTesting, getLocalizationBrandingCustomer, listDigitalSigningCollection, listDynamicFieldQuestion. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 3 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#approveWaiverTesting`, `marketing-crm#getLocalizationBrandingCustomer`, `marketing-crm#listDigitalSigningCollection`, `marketing-crm#listDynamicFieldQuestion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-17 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: listParticipantWaiverStatus, listVersioningEffectiveDate, listWaiverTemplateMaster, listWaiverTriggerEligibility | 8 | Hrushikant Patkar | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-2 MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL PRD-W1-OWNER-FORMS SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-25 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-8 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-13 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-EVENT-1 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listParticipantWaiverStatus, listVersioningEffectiveDate, listWaiverTemplateMaster, listWaiverTriggerEligibility. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listParticipantWaiverStatus`, `marketing-crm#listVersioningEffectiveDate`, `marketing-crm#listWaiverTemplateMaster`, `marketing-crm#listWaiverTriggerEligibility` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-26 | AM-MARKETING-CRM-P13-3 | [BE] MarketingService: listProductEventExperience, listWaiverConsent, listWaiverVerificationQueue, setLocalizationBrandingCustomer | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-2 MIG-MARKETING-23 MIG-MARKETING-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductEventExperience, listWaiverConsent, listWaiverVerificationQueue, setLocalizationBrandingCustomer. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 3 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listProductEventExperience`, `marketing-crm#listWaiverConsent`, `marketing-crm#listWaiverVerificationQueue`, `marketing-crm#setLocalizationBrandingCustomer` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-CONSENT-27 | AM-MARKETING-CRM-P13-4 | [BE] MarketingService: listMissingExpiredInvalid, listSiteWaiverException, listWaiverComplianceOperational, listWaiverComplianceRisk | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-20 MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL PRD-W1-OWNER-FORMS SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-FNB-FNB-12 SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-25 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-8 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-13 SVC-MARKETING-MARKETING-23 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-9 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-TENANCY-WORKFORCE-3 VM-CATALOGUE-EVENT-1 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listMissingExpiredInvalid, listSiteWaiverException, listWaiverComplianceOperational, listWaiverComplianceRisk. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 4 of 4; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listMissingExpiredInvalid`, `marketing-crm#listSiteWaiverException`, `marketing-crm#listWaiverComplianceOperational`, `marketing-crm#listWaiverComplianceRisk` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-24 | AM-MARKETING-CRM-P12 | [DB] Forward migration V1245__marketing.sql: marketing for Marketing & CRM · Support Console 1 of 2 (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.case_compensation_request. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: marketing.case_compensation_request: foreign key case_compensation_request_case_id_fkey, drop index case_compensation_request_order_id_idx); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `marketing.case_compensation_request` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CASE-15 | AM-MARKETING-CRM-P12 | [BE] MarketingService: createCaseClassificationIntelligent, listCaseResolutionClosure, listContact, listCustomerService | 8 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-24 MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCaseClassificationIntelligent, listCaseResolutionClosure, listContact, listCustomerService. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console 1 of 2; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#createCaseClassificationIntelligent`, `marketing-crm#listCaseResolutionClosure`, `marketing-crm#listContact`, `marketing-crm#listCustomerService` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CASE-5 | AM-MARKETING-CRM-P08 | [BE] MarketingService: listCustomerServiceProfile | 3 | Deep Khanvilkar | MarketingService | MIG-ACCESS MIG-MARKETING MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-ACCESS-VALIDATION-3 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-12 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CASE-15 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-14 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-GUEST-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-LOYALTY-2 SVC-MARKETING-LOYALTY-8 SVC-MARKETING-MARKETING-11 SVC-MARKETING-MARKETING-13 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-19 SVC-ORDER-ORDERS-21 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-MARKETING-MARKETING-2 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listCustomerServiceProfile. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCustomerServiceProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-CASE-6 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: listCaseCategories, listQualityAgentEvaluation, listServiceQueues, listUnifiedInteractionCommunication | 5 | Narayan Gaonkar | MarketingService | MIG-MARKETING MIG-MARKETING-5 MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-KERNEL SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CASE-10 SVC-MARKETING-CASE-15 SVC-MARKETING-CASE-2 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-CASE-9 SVC-MARKETING-CONSENT-6 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-MARKETING-10 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-19 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-23 SVC-MARKETING-MARKETING-3 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-9 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-PLATFORM-PUBLICAPI-1 SVC-TENANCY-WORKFORCE-3 VM-MARKETING-MARKETING-2 | Operations: listCaseCategories, listQualityAgentEvaluation, listServiceQueues, listUnifiedInteractionCommunication. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listCaseCategories`, `marketing-crm#listQualityAgentEvaluation`, `marketing-crm#listServiceQueues`, `marketing-crm#listUnifiedInteractionCommunication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-16 | AM-MARKETING-CRM-P12 | [BE] MarketingService: listEscalationCollaborationInternal, setCaseInvestigationResolution, setRefundCompensationService | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING-24 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listEscalationCollaborationInternal, setCaseInvestigationResolution, setRefundCompensationService. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console 1 of 2; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listEscalationCollaborationInternal`, `marketing-crm#setCaseInvestigationResolution`, `marketing-crm#setRefundCompensationService` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CASE-17 | AM-MARKETING-CRM-P12-2 | [BE] MarketingService: listContactAutomation | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-KERNEL SVC-MARKETING-CASE-2 | Operations: listContactAutomation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console 2 of 2; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#listContactAutomation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-MESSAGE-8 | AM-MARKETING-CRM-P10 | [BE] MarketingService: getMessageStatus | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-6 SVC-MARKETING-MARKETING-23 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-9 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-PLATFORM-PUBLICAPI-1 SVC-TENANCY-WORKFORCE-3 | Operations: getMessageStatus. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Partner Portal; additive to MarketingService, whose first-release owner (Narayan Gaonkar) reviews. Done when `marketing-crm#getMessageStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-7 | AM-AI-P08 | [DB] Forward migration V1176__ai.sql: ai for AI · Venue Management 1 of 2 (6 tables) | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.case_action, ai.case_evidence, ai.entity_risk, ai.layout_draft, ai.risk_alert, ai.risk_edge. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.case_action`, `ai.case_evidence`, `ai.entity_risk`, `ai.layout_draft`, `ai.risk_alert`, `ai.risk_edge` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-AI-ACTIONS-4 | AM-AI-P08 | [BE] AiService: setAiTool | 2 | Deep Khanvilkar | AiService | MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiTool. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#setAiTool` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIGURE-5 | AM-AI-P08 | [BE] AiService: runGuidedChoiceSuggestionJob | 2 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: runGuidedChoiceSuggestionJob. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#runGuidedChoiceSuggestionJob` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-GENERATE-5 | AM-AI-P08 | [BE] AiService: generateVenueLayout | 2 | Deep Khanvilkar | AiService | MIG-AI MIG-AI-7 MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: generateVenueLayout. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#generateVenueLayout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RETRIEVAL-3 | AM-AI-P08 | [BE] AiService: listIndexJobs, listIndexSources, removeIndexEntry | 3 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listIndexJobs, listIndexSources, removeIndexEntry. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listIndexJobs`, `ai#listIndexSources`, `ai#removeIndexEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-3 | AM-AI-P08 | [BE] AiService: addRiskCaseEvidence, closeRiskCase, configureRiskStrategy, createRiskCase | 8 | Pranay Shinde | AiService | MIG-AI MIG-AI-6 MIG-AI-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addRiskCaseEvidence, closeRiskCase, configureRiskStrategy, createRiskCase. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#addRiskCaseEvidence`, `ai#closeRiskCase`, `ai#configureRiskStrategy`, `ai#createRiskCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-4 | AM-AI-P08 | [BE] AiService: decideRiskAlert, expandRiskNetwork, getEntityRisk, getRiskCase | 8 | Pranay Shinde | AiService | MIG-AI-6 MIG-AI-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideRiskAlert, expandRiskNetwork, getEntityRisk, getRiskCase. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#decideRiskAlert`, `ai#expandRiskNetwork`, `ai#getEntityRisk`, `ai#getRiskCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-5 | AM-AI-P08 | [BE] AiService: listRiskAlerts, proposeRiskAction, scoreApprovalRequest, scoreTransactionRisk | 8 | Pranay Shinde | AiService | MIG-AI MIG-AI-2 MIG-AI-3 MIG-AI-6 MIG-AI-7 MIG-APPROVALS MIG-APPROVALS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-AI | Operations: listRiskAlerts, proposeRiskAction, scoreApprovalRequest, scoreTransactionRisk. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listRiskAlerts`, `ai#proposeRiskAction`, `ai#scoreApprovalRequest`, `ai#scoreTransactionRisk` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-RECOMMEND-3 | AM-AI-P08 | [BE] AiService: getCustomerRecommendationProfile, simulateRecommendationDecision | 3 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-RECOMMEND-1 | Operations: getCustomerRecommendationProfile, simulateRecommendationDecision. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#getCustomerRecommendationProfile`, `ai#simulateRecommendationDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-8 | AM-AI-P16 | [DB] Forward migration V1066__ai.sql: ai for AI · Analytics (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.suggestion_outcome. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: ai.suggestion_outcome: foreign key suggestion_outcome_suggestion_id_fkey); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.suggestion_outcome` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-AI-AI-5 | AM-AI-P16 | [BE] AiService: recordSuggestionOutcome | 1 | Deep Khanvilkar | AiService | MIG-AI MIG-AI-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordSuggestionOutcome. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#recordSuggestionOutcome` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-REPORTING-8 | AM-AI-P16 | [BE] ReportingService: setAnalyticsGovernancePolicy | 2 | Deep Khanvilkar | ReportingService | MIG-REPORTING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAnalyticsGovernancePolicy. Spec: contracts (reporting) at the release tag, served by ADAM. Built for AI · Analytics; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#setAnalyticsGovernancePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WHITELABEL-CONTENT-9 | AM-AI-P12 | [BE] WhiteLabelService: listFaqs | 1 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-5 | Operations: listFaqs. Spec: contracts (white-label) at the release tag, served by ADAM. Built for AI · Support Console; additive to WhiteLabelService, whose first-release owner (Hrushikant Patkar) reviews. Done when `white-label#listFaqs` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-9 | AM-AI-P09 | [DB] Forward migration V1067__ai.sql: ai for AI · TICVAI Console 1 of 4 (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.signal_source. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.signal_source` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-AI-CONFIGURE-6 | AM-AI-P09 | [BE] AiService: answerConfigurationQuestion, attachConfigurationSource, listConfigurationSessions, listConfigurationSources | 8 | Pranay Shinde | AiService | MIG-AI MIG-AI-2 MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: answerConfigurationQuestion, attachConfigurationSource, listConfigurationSessions, listConfigurationSources. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 1 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#answerConfigurationQuestion`, `ai#attachConfigurationSource`, `ai#listConfigurationSessions`, `ai#listConfigurationSources` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIGURE-7 | AM-AI-P09 | [BE] AiService: startConfigurationSession | 2 | Deep Khanvilkar | AiService | MIG-AI MIG-AI-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: startConfigurationSession. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 1 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#startConfigurationSession` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-FORECAST-9 | AM-AI-P09 | [BE] AiService: configureForecastSignalSource, listForecastSignals | 2 | Deep Khanvilkar | AiService | MIG-AI-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureForecastSignalSource, listForecastSignals. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 1 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#configureForecastSignalSource`, `ai#listForecastSignals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-INSIGHTS-5 | AM-AI-P09 | [BE] AiService: configureAnomalyDetector | 2 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAnomalyDetector. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 1 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#configureAnomalyDetector` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-INSIGHTS-2 | AM-AI-P16 | [BE] AiService: listAnomalyDetectors | 1 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-INSIGHTS-1 SVC-AI-INSIGHTS-5 | Operations: listAnomalyDetectors. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAnomalyDetectors` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-ACTIONS-5 | AM-AI-P09-2 | [BE] AiService: cancelActionPlan, pauseActionPlan | 5 | Pranay Shinde | AiService | MIG-AI MIG-AI-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelActionPlan, pauseActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 2 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#cancelActionPlan`, `ai#pauseActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIGURE-8 | AM-AI-P09-2 | [BE] AiService: buildConfigurationPlan | 3 | Pranay Shinde | AiService | MIG-AI MIG-AI-2 MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: buildConfigurationPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 2 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#buildConfigurationPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-ACTIONS-6 | AM-AI-P09-3 | [BE] AiService: resumeActionPlan, retryActionStep, rollbackActionPlan | 8 | Pranay Shinde | AiService | MIG-AI MIG-AI-2 MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resumeActionPlan, retryActionStep, rollbackActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 3 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#resumeActionPlan`, `ai#retryActionStep`, `ai#rollbackActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-GOVERNANCE-7 | AM-AI-P09-3 | [BE] AiService: configureAiCapability, createAiPolicyException, resumeAiCapability | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAiCapability, createAiPolicyException, resumeAiCapability. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 3 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#configureAiCapability`, `ai#createAiPolicyException`, `ai#resumeAiCapability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-MONITORING-4 | AM-AI-P16 | [BE] AiService: listAiCapabilityMaturity | 1 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-FORECAST-2 SVC-AI-GOVERNANCE-2 SVC-AI-GOVERNANCE-7 SVC-AI-MONITORING-1 | Operations: listAiCapabilityMaturity. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#listAiCapabilityMaturity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-12 | AM-AI-P09-4 | [DB] Forward migration V1246__ai.sql: ai for AI · TICVAI Console 4 of 4 (2 tables) | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.control, ai.control_test. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `ai.control`, `ai.control_test` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-AI-AUDIT-3 | AM-AI-P09-4 | [BE] AiService: replayAiDecision | 1 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: replayAiDecision. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 4 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#replayAiDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-MONITORING-6 | AM-AI-P09-4 | [BE] AiService: decideAiGovernanceAlert, listAiCapabilityHealth, listAiControls, runAiControlTest | 5 | Pranay Shinde | AiService | MIG-AI MIG-AI-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideAiGovernanceAlert, listAiCapabilityHealth, listAiControls, runAiControlTest. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 4 of 4; additive to AiService, whose first-release owner (Pranay Shinde) reviews. Done when `ai#decideAiGovernanceAlert`, `ai#listAiCapabilityHealth`, `ai#listAiControls`, `ai#runAiControlTest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-1 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 1) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-2 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 2) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-3 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 3) | 8 | Narayan Gaonkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-4 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 4) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-5 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 5) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-6 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 6) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-7 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 7) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-8 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 8) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-9 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 9) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-1 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 1) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-10 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 10) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-11 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 11) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-12 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 12) | 8 | Narayan Gaonkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-2 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 2) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-3 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 3) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-4 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 4) | 8 | Narayan Gaonkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-5 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 5) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-6 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 6) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-7 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 7) | 8 | Narayan Gaonkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-8 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 8) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-9 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 9) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-1 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 1) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-2 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 2) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-3 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 3) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-4 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 4) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-5 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 5) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-6 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 6) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
8 | 3 | MIG-REPORTING-4 | AM-REPORTING-P08 | [DB] Forward migration V1177__reporting.sql: reporting for Reporting · Venue Management 1 of 2 (1 tables) | 1 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-IDENTITY MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.export. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `reporting.export` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
10 | 3 | SVC-ACCESS-ACCESS-69 | AM-REPORTING-P08 | [BE] AccessService: listAccessReportScheduled | 1 | Deep Khanvilkar | AccessService | MIG-BASELINE PLATFORM-KERNEL | Operations: listAccessReportScheduled. Spec: contracts (access) at the release tag, served by ADAM. Built for Reporting · Venue Management 1 of 2; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listAccessReportScheduled` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-EXPORT-1 | AM-REPORTING-P08 | [BE] ReportingService: exportReportResult, getReportExport | 2 | Deep Khanvilkar | ReportingService | MIG-REPORTING-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: exportReportResult, getReportExport. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management 1 of 2; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#exportReportResult`, `reporting#getReportExport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-REPORTING-5 | AM-REPORTING-P08-2 | [DB] Forward migration V1178__reporting.sql: reporting for Reporting · Venue Management 2 of 2 (2 tables) | 2 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.pipeline, reporting.site_normalisation_basis. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `reporting.pipeline`, `reporting.site_normalisation_basis` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
13 | 3 | SVC-INVENTORY-INVENTORY-5 | AM-REPORTING-P16 | [BE] InventoryService: listExpiringBatches | 2 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations: listExpiringBatches. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Reporting · Analytics 1 of 4; additive to InventoryService, whose first-release owner (Narayan Gaonkar) reviews. Done when `inventory#listExpiringBatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-REPORTING-CATALOGUE-3 | AM-REPORTING-P16-2 | [BE] ReportingService: listReportFields | 1 | Pranay Shinde | ReportingService | MIG-BASELINE PLATFORM-KERNEL | Operations: listReportFields. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 2 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#listReportFields` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-EXECUTION-2 | AM-REPORTING-P16-2 | [BE] ReportingService: cancelReportExecution | 1 | Pranay Shinde | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelReportExecution. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 2 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#cancelReportExecution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-REPORTING-EXECUTION-1 | AM-MARKETING-CRM-P08 | [BE] ReportingService: getReportExecution, listReportExecutions | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-EXECUTION-1 SVC-REPORTING-EXECUTION-2 | Operations beyond the first release: getReportExecution, listReportExecutions. Additive to ReportingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `reporting#getReportExecution`, `reporting#listReportExecutions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-REPORTING-11 | AM-REPORTING-P16-2 | [BE] ReportingService: listSeededReports, listSiteNormalisationBases, setKpiTargets | 3 | Deep Khanvilkar | ReportingService | MIG-REPORTING MIG-REPORTING-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-REPORTING | Operations: listSeededReports, listSiteNormalisationBases, setKpiTargets. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 2 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#listSeededReports`, `reporting#listSiteNormalisationBases`, `reporting#setKpiTargets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-REPORTING-6 | AM-REPORTING-P16-3 | [DB] Forward migration V1179__reporting.sql: reporting for Reporting · Analytics 3 of 4 (3 tables) | 2 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.anomaly, reporting.delivery, reporting.subscription. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0104__after_r1_20261015.sql (reporting.anomaly: column candidate_causes; reporting.subscription: column recipients); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0107__names_after_r1_20261019.sql (the names the contracts use: reporting.delivery: rename column contained_personal_data to did_contain_personal_data); the files above create these tables with the names they had at r1, so this migration copies the blocks of that file that name its tables, after its tables are created (each block is guarded and does nothing when its table, key or index is not there). A key between this migration's table and one a later migration creates is copied by both, and takes effect in the later one. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. **Safe to run twice**: write every ALTER TABLE ... ADD CONSTRAINT copied from the package guarded, either preceded by `ALTER TABLE ... DROP CONSTRAINT IF EXISTS <name>;` or inside `DO $$ BEGIN IF NOT EXISTS (SELECT 1 FROM pg_constraint WHERE conname = '<name>' AND conrelid = '<schema.table>'::regclass) THEN ALTER TABLE ... ADD CONSTRAINT ...; END IF; END $$;` (the package's 900-foreign-keys.sql lines are written unguarded and fail a second run as they are). Do not copy the `INSERT INTO platform.schema_version ...` statement at the end of a package after-r1 file: SqlMigrationRunner records this migration in platform.schema_version itself. Done when the migration for `reporting.anomaly`, `reporting.delivery`, `reporting.subscription` applies on a copy of the database at the previous state, a second run applies nothing (it is safe to run twice: every ADD CONSTRAINT copied from the package is written guarded), and `node .claude/scripts/db-ticket.mjs <ticket>` says MATCH (columns, keys, indexes, row-level security); every migration from an empty database runs once a day and in the merge-request pipeline; and a peer has reviewed it.
11 | 3 | SVC-REPORTING-REPORTING-12 | AM-REPORTING-P16-3 | [BE] ReportingService: createReportSubscription, getAnalyticsUsage, listAnalyticsAnomalies, listReportDeliveries | 3 | Deep Khanvilkar | ReportingService | MIG-REPORTING MIG-REPORTING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createReportSubscription, getAnalyticsUsage, listAnalyticsAnomalies, listReportDeliveries. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 3 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#createReportSubscription`, `reporting#getAnalyticsUsage`, `reporting#listAnalyticsAnomalies`, `reporting#listReportDeliveries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-REPORTING-REPORTING-13 | AM-REPORTING-P16-3 | [BE] ReportingService: listReportSubscriptions | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING-6 PLATFORM-KERNEL SVC-REPORTING-REPORTING-12 | Operations: listReportSubscriptions. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 3 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#listReportSubscriptions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-EXECUTION-3 | AM-REPORTING-P16-3 | [BE] ReportingService: getReportResult | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-EXECUTION-1 SVC-REPORTING-EXECUTION-2 | Operations: getReportResult. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 3 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#getReportResult` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-REPORTING-14 | AM-REPORTING-P16-4 | [BE] ReportingService: setSiteNormalisationBasis | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSiteNormalisationBasis. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 4 of 4; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#setSiteNormalisationBasis` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-REPORTING-10 | AM-REPORTING-P08-2 | [BE] ReportingService: getAnalyticsBenchmark, listAnalyticsPipelines | 2 | Deep Khanvilkar | ReportingService | MIG-ACCESS MIG-REPORTING MIG-REPORTING-5 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-REPORTING-REPORTING-1 SVC-REPORTING-REPORTING-11 SVC-REPORTING-REPORTING-14 SVC-REPORTING-REPORTING-2 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-REPORTING | Operations: getAnalyticsBenchmark, listAnalyticsPipelines. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management 2 of 2; additive to ReportingService, whose first-release owner (Pranay Shinde) reviews. Done when `reporting#getAnalyticsBenchmark`, `reporting#listAnalyticsPipelines` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
1 | 3 | TEST-SAME-NUMBERS | AM-REPORTING-API-PLATFORM | [BE] Same numbers test: till, back-office and Analytics reports agree | 3 | Narayan Gaonkar |  |  | Same numbers test: till, back-office and Analytics reports agree. Builds: `screen POS-008`. 2 October (Chinmay, DEC-559, prevention of CHG-FIN-006): an automated comparison of the same measure (takings, gross sales, net revenue, refunds) for the same period and scope on the till report (POS-008), the back-office report and the Analytics (P16) dashboard; fails when they differ. Done when: the test runs in CI against the seeded demo tenant.

## Migrations
Order | Task | Migration file | Database | Schema | Tables | Columns | References (created earlier or deferred) | Assignee | Points | Owning service
0 | MIG-BASELINE | V0001__baseline.sql | both | (baseline) | 0 | 0 |  | Hrushikant Patkar | 3
1 | MIG-CONTROL | V0002__control.sql | control | control | 19 | 304 |  | Hrushikant Patkar | 8 | PlatformService
2 | MIG-KERNEL | V0003__kernel.sql | tenant | kernel | 1 | 3 |  | Hrushikant Patkar | 1 | TenancyService
3 | MIG-TENANCY | V0004__tenancy.sql | tenant | tenancy | 5 | 63 |  | Hrushikant Patkar | 3 | TenancyService
4 | MIG-SUBSCRIPTION | V0005__subscription.sql | control | subscription | 5 | 58 | control | Hrushikant Patkar | 3 | PlatformService
5 | MIG-TRANSPORT | V0006__transport.sql | tenant | transport | 12 | 111 | assets | Hrushikant Patkar | 8 | VenueOpsService
6 | MIG-PII | V0007__pii.sql | tenant | pii | 5 | 54 | access, marketing | Hrushikant Patkar | 3 | IdentityService
7 | MIG-GAMES | V0008__games.sql | tenant | games | 2 | 29 | pii, platform | Hrushikant Patkar | 2 | VenueOpsService
8 | MIG-IDENTITY | V0009__identity.sql | tenant | identity | 21 | 229 | pii, platform | Hrushikant Patkar | 8 | IdentityService
9 | MIG-APPROVALS | V0010__approvals.sql | tenant | approvals | 7 | 121 | identity, pii | Hrushikant Patkar | 5 | TenancyService
10 | MIG-REPORTING | V0011__reporting.sql | tenant | reporting | 15 | 162 | identity, platform | Hrushikant Patkar | 8 | ReportingService
11 | MIG-SYNC | V0012__sync.sql | tenant | sync | 1 | 11 | identity, platform | Hrushikant Patkar | 1 | CrossRegionService
12 | MIG-ASSETS | V0013__assets.sql | tenant | assets | 8 | 91 | identity, platform | Hrushikant Patkar | 5 | VenueOpsService
13 | MIG-AI | V0014__ai.sql | tenant | ai | 52 | 775 | assets, identity, pii, platform | Hrushikant Patkar | 8 | AiService
14 | MIG-RESOURCES | V0015__resources.sql | tenant | resources | 7 | 97 | identity, orders, pii, platform | Hrushikant Patkar | 5 | VenueOpsService
15 | MIG-WHITELABEL | V0016__whitelabel.sql | tenant | whitelabel | 31 | 298 | identity, platform, promotions | Hrushikant Patkar | 8 | WhiteLabelService
16 | MIG-PLATFORM | V0017__platform.sql | tenant | platform | 19 | 245 | access, approvals, identity, inventory, ledger, pii | Hrushikant Patkar | 8 | TenancyService
17 | MIG-WORKFORCE | V0018__workforce.sql | tenant | workforce | 3 | 39 | access, identity, platform | Hrushikant Patkar | 2 | TenancyService
18 | MIG-SEATING | V0019__seating.sql | tenant | seating | 11 | 95 | assets, catalogue, identity, pii, platform | Hrushikant Patkar | 8 | CatalogueService
19 | MIG-MAINTENANCE | V0020__maintenance.sql | tenant | maintenance | 6 | 150 | access, identity, inventory, platform | Hrushikant Patkar | 5 | VenueOpsService
20 | MIG-WALLET | V0021__wallet.sql | tenant | wallet | 21 | 199 | identity, orders, pii, platform | Hrushikant Patkar | 8 | WalletService
21 | MIG-CATALOGUE | V0022__catalogue.sql | tenant | catalogue | 42 | 762 | access, identity, ledger, pii, platform, seating | Hrushikant Patkar | 8 | CatalogueService
22 | MIG-LEDGER | V0023__ledger.sql | tenant | ledger | 18 | 274 | catalogue, identity, orders, platform | Hrushikant Patkar | 8 | LedgerService
23 | MIG-INVENTORY | V0024__inventory.sql | tenant | inventory | 12 | 173 | identity, ledger, platform | Hrushikant Patkar | 8 | InventoryService
24 | MIG-PROMOTIONS | V0025__promotions.sql | tenant | promotions | 16 | 188 | catalogue, ledger, orders, pii, platform | Hrushikant Patkar | 8 | CatalogueService
25 | MIG-ORDERS | V0026__orders.sql | tenant | orders | 44 | 547 | access, catalogue, identity, ledger, pii, platform, promotions | Hrushikant Patkar | 8 | OrderService
26 | MIG-ACCESS | V0027__access.sql | tenant | access | 19 | 335 | catalogue, identity, orders, pii, platform | Hrushikant Patkar | 8 | AccessService
27 | MIG-MARKETING | V0028__marketing.sql | tenant | marketing | 56 | 694 | ai, catalogue, identity, ledger, orders, pii, platform | Hrushikant Patkar | 8 | MarketingService
28 | MIG-FNB | V0029__fnb.sql | tenant | fnb | 41 | 407 | access, catalogue, identity, inventory, orders, pii, platform, seating | Hrushikant Patkar | 8 | FnbService
29 | MIG-PAYMENTS | V0030__payments.sql | tenant | payments | 8 | 105 | marketing, orders, pii | Hrushikant Patkar | 5 | OrderService
30 | MIG-QUEUE | V0031__queue.sql | tenant | queue | 4 | 77 | access, catalogue, maintenance, pii, platform | Hrushikant Patkar | 3 | VenueOpsService
31 | MIG-RETAIL | V0032__retail.sql | tenant | retail | 10 | 121 | access, catalogue, fnb, identity, inventory, orders, pii, platform | Hrushikant Patkar | 5 | RetailService
32 | MIG-VENUEMAP | V0033__venuemap.sql | tenant | venuemap | 9 | 143 | access, assets, catalogue, marketing, orders, platform, promotions, resources | Hrushikant Patkar | 5 | VenueOpsService
33 | MIG-FOREIGN-KEYS | V0034__cross_schema_foreign_keys.sql | tenant | (cross-schema) | 0 | 0 |  | Hrushikant Patkar | 3

## Tables
Migration | Table | Database | Columns | Row-level security | Partitioned by month | Operations reading | Operations writing | Foreign keys to | Why it is in the release | Owning service | Source DDL
MIG-CONTROL | control.api_client | control | 15 | none |  | 5 | 4 | control.integration_listing | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.api_client_secret | control | 7 | none |  | 0 | 2 | control.api_client | used by the first release | PlatformService | backend/control/V0116__after_r1_20261026.sql
MIG-CONTROL | control.api_licence | control | 9 | none |  | 2 | 1 | control.tenant | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.api_version | control | 10 | none |  | 2 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.cell_tenant | control | 11 | none |  | 0 | 0 |  | referenced by control.outbox_relay | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.developer_account | control | 8 | none |  | 4 | 3 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.developer_member | control | 7 | none |  | 1 | 2 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.integration_listing | control | 12 | none |  | 3 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.licence_add_on | control | 11 | none |  | 4 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.licence_add_on_limit | control | 6 | none |  | 2 | 1 | control.licence_add_on | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.outbox_relay | control | 6 | none |  | 0 | 0 | control.cell_tenant | kernel machinery: the relay lease per tenant database (ADR-0058; PLATFORM-OUTBOX) | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner | control | 28 | scope_path |  | 0 | 0 |  | referenced by control.partner_agreement | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_agreement | control | 53 | scope_path |  | 0 | 1 | control.partner | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_application | control | 31 | scope_path |  | 0 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_change_request | control | 28 | scope_path |  | 0 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.production_access_request | control | 14 | none |  | 1 | 1 | control.api_client, control.integration_listing | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.seo_metadata | control | 15 | scope_path |  | 2 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.tenant | control | 24 | none |  | 10 | 4 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.url_redirect | control | 9 | scope_path |  | 1 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-KERNEL | kernel.inbox | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) | yes | 0 | 0 |  | kernel machinery: the inbox per tenant database (ADR-0058; PLATFORM-OUTBOX, MIG-PARTITIONS) | TenancyService | backend/tenant/010-kernel.sql
MIG-TENANCY | tenancy.device_assignment | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-TENANCY | tenancy.device_audit | tenant | 11 | scope_path |  | 0 | 1 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-TENANCY | tenancy.device_firmware | tenant | 14 | none |  | 3 | 2 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-TENANCY | tenancy.device_rollout | tenant | 11 | scope_path |  | 1 | 1 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-TENANCY | tenancy.device_telemetry | tenant | 15 | scope_path |  | 1 | 0 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-SUBSCRIPTION | control.contract | control | 14 | none |  | 5 | 2 | control.plan, control.tenant | used by the first release | PlatformService | backend/control/V0108__after_r1_20261020.sql
MIG-SUBSCRIPTION | control.module_listing | control | 16 | none |  | 2 | 1 |  | used by the first release | PlatformService | backend/control/V0108__after_r1_20261020.sql
MIG-SUBSCRIPTION | control.plan | control | 17 | none |  | 6 | 2 | control.tenant | used by the first release | PlatformService | backend/control/V0108__after_r1_20261020.sql
MIG-SUBSCRIPTION | control.plan_limit | control | 7 | none |  | 2 | 2 | control.plan | used by the first release | PlatformService | backend/control/V0108__after_r1_20261020.sql
MIG-SUBSCRIPTION | control.plan_module | control | 4 | none |  | 2 | 2 | control.plan | used by the first release | PlatformService | backend/control/V0108__after_r1_20261020.sql
MIG-TRANSPORT | transport.departure | tenant | 10 | through its owner |  | 5 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_matrix_cell | tenant | 5 | through its owner |  | 7 | 1 | transport.fare_table | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_passenger_type | tenant | 11 | through its owner |  | 6 | 1 | transport.fare_table | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_table | tenant | 7 | through its owner |  | 8 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.favourite_route | tenant | 9 | venue_id |  | 3 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.network_import | tenant | 11 | venue_id |  | 2 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.pass_type | tenant | 14 | venue_id |  | 4 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.route | tenant | 13 | venue_id |  | 11 | 4 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.route_stop | tenant | 7 | through its owner |  | 10 | 3 | transport.route | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.station | tenant | 8 | venue_id |  | 12 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.timetable | tenant | 12 | through its owner |  | 7 | 4 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.timetable_run | tenant | 4 | through its owner |  | 3 | 2 | transport.timetable | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-PII | pii.subject | tenant | 13 | none |  | 20 | 6 |  | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_biometric | tenant | 15 | none |  | 4 | 3 | access.entitlement, marketing.consent_purpose, pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_contact | tenant | 10 | none |  | 6 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_document | tenant | 10 | subject |  | 0 | 1 | pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_identity | tenant | 6 | subject |  | 2 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/V0108__after_r1_20261020.sql
MIG-GAMES | games.card | tenant | 15 | venue_id |  | 3 | 2 | pii.subject, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-games.sql
MIG-GAMES | games.credit_ledger | tenant | 14 | through its owner |  | 1 | 0 | games.card | used by the first release | VenueOpsService | backend/tenant/010-games.sql
MIG-IDENTITY | identity.capability_template | tenant | 9 | none |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.delegated_access | tenant | 25 | none |  | 17 | 2 | identity.principal, identity.role, pii.subject, platform.scope | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.guest_credential | tenant | 6 | subject |  | 1 | 2 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_challenge | tenant | 13 | none |  | 2 | 2 | identity.principal, pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_method | tenant | 13 | none |  | 11 | 2 | identity.principal, pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_recovery_code | tenant | 6 | none |  | 2 | 2 | identity.principal, pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.otp_challenge | tenant | 12 | subject |  | 3 | 4 | pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.password_policy | tenant | 19 | none |  | 8 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.platform_staff_grant | tenant | 9 | scope_path |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal | tenant | 11 | none |  | 25 | 2 | identity.role, identity.sso_provider, platform.scope | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal_credential | tenant | 7 | none |  | 3 | 3 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal_credential_history | tenant | 4 | none |  | 1 | 1 | identity.principal_credential | used by the first release | IdentityService | backend/tenant/V0104__after_r1_20261015.sql
MIG-IDENTITY | identity.redirect_host | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 |  | used by the first release | IdentityService | backend/tenant/V0116__after_r1_20261026.sql
MIG-IDENTITY | identity.refresh_token | tenant | 11 | subject |  | 1 | 3 | pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.role | tenant | 9 | none |  | 11 | 2 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.role_permission | tenant | 6 | none |  | 7 | 2 | identity.role | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.segregation_rule | tenant | 9 | none |  | 3 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.session | tenant | 16 | venue_id |  | 7 | 7 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.sso_provider | tenant | 17 | scope_path |  | 0 | 0 | platform.scope | referenced by identity.principal | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.subject_data_export | tenant | 9 | subject |  | 1 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/V0116__after_r1_20261026.sql
MIG-IDENTITY | identity.subject_holding | tenant | 12 | subject |  | 3 | 0 | pii.subject | used by the first release | IdentityService | backend/tenant/V0104__after_r1_20261015.sql
MIG-APPROVALS | approvals.decision | tenant | 15 | through its owner |  | 3 | 1 | approvals.request, identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.delegation | tenant | 13 | scope_path |  | 6 | 2 | identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
VM-MIG-APPROVALS | approvals.escalation | tenant | 9 | through its owner |  | 3 | 1 | approvals.request | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.external_provider | tenant | 16 | none |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.matrix | tenant | 6 | none |  | 8 | 3 |  | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.request | tenant | 36 | scope_path |  | 3 | 6 | approvals.matrix, approvals.rule, identity.principal, pii.subject | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.request_approver | tenant | 5 | through its owner |  | 3 | 2 | approvals.request, identity.principal | used by the first release | TenancyService | backend/tenant/V0116__after_r1_20261026.sql
MIG-APPROVALS | approvals.rule | tenant | 30 | none |  | 7 | 2 | approvals.matrix | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-REPORTING | reporting.alert | tenant | 18 | scope_path |  | 1 | 0 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.alert_rule | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard | tenant | 10 | venue_id |  | 6 | 3 | identity.principal, platform.scope | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard_tile | tenant | 8 | through its owner |  | 5 | 2 | reporting.dashboard, reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard_view | tenant | 5 | venue_id |  | 0 | 1 | identity.principal, reporting.dashboard | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.execution | tenant | 15 | through its owner |  | 1 | 1 | identity.principal, reporting.report_definition, reporting.schedule | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.kpi_definition | tenant | 12 | none |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.natural_language_query | tenant | 9 | scope_path |  | 1 | 2 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_column | tenant | 14 | through its owner |  | 7 | 4 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_definition | tenant | 16 | scope_path |  | 8 | 4 | identity.principal | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_definition_version | tenant | 7 | scope_path |  | 1 | 2 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_filter | tenant | 7 | through its owner |  | 7 | 4 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_parameter | tenant | 7 | through its owner |  | 6 | 3 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.schedule | tenant | 15 | through its owner |  | 0 | 0 | identity.principal, reporting.report_definition | referenced by reporting.execution | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.semantic_model | tenant | 6 | none |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-SYNC | sync.rejection | tenant | 11 | none |  | 1 | 1 | identity.principal, platform.workstation | used by the first release | CrossRegionService | backend/tenant/010-sync.sql
MIG-ASSETS | assets.asset_version | tenant | 13 | scope_path |  | 1 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_asset | tenant | 29 | venue_id |  | 14 | 4 | identity.principal, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_collection | tenant | 7 | venue_id |  | 4 | 1 | assets.media_asset, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_collection_member | tenant | 5 | through its owner |  | 3 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_fingerprint | tenant | 7 | scope_path |  | 0 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_upload | tenant | 12 | venue_id |  | 3 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_usage | tenant | 7 | through its owner |  | 5 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.rendition | tenant | 11 | scope_path |  | 1 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-AI | ai.action_plan | tenant | 19 | scope_path |  | 2 | 2 | ai.action_plan, ai.proposed_action, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.activity | tenant | 25 | scope_path |  | 1 | 12 | ai.conversation, identity.principal, pii.subject | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.anomaly_detector | tenant | 14 | scope_path |  | 0 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.answer_feedback | tenant | 11 | scope_path |  | 1 | 1 | ai.conversation, ai.message, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.assistant_profile | tenant | 14 | none |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.byok_enablement | tenant | 11 | scope_path |  | 3 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.capability | tenant | 18 | none |  | 6 | 2 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.capability_maturity | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.chunk_embedding | tenant | 13 | none |  | 4 | 2 | ai.chunk_embedding, ai.knowledge_document | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.conversation | tenant | 10 | scope_path |  | 3 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.decision_record | tenant | 27 | scope_path |  | 2 | 15 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.eval_run | tenant | 14 | scope_path |  | 4 | 1 | ai.eval_suite, ai.release, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.eval_suite | tenant | 9 | scope_path |  | 2 | 0 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_accuracy | tenant | 13 | scope_path |  | 1 | 0 | ai.forecast_definition, ai.forecast_version | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_definition | tenant | 20 | scope_path |  | 6 | 3 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_point | tenant | 12 | scope_path |  | 3 | 2 | ai.forecast_scenario, ai.forecast_version | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_scenario | tenant | 9 | scope_path |  | 1 | 1 | ai.forecast_version, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_version | tenant | 18 | scope_path |  | 7 | 2 | ai.forecast_definition, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_alert | tenant | 14 | scope_path |  | 3 | 2 | ai.incident, ai.release, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_policy | tenant | 9 | none |  | 3 | 2 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_policy_version | tenant | 12 | none |  | 7 | 3 | ai.governance_policy, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.guided_choice_suggestion | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.history_import | tenant | 19 | scope_path |  | 3 | 1 | assets.media_asset, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.history_observation | tenant | 10 | scope_path |  | 2 | 1 | ai.history_import | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.inbox | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) | yes | 0 | 0 |  | kernel machinery: the AI consumers' inbox, since only AI writes AI tables (ADR-0058, ADR-0020) | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.incident | tenant | 20 | scope_path |  | 3 | 2 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_entry | tenant | 10 | none |  | 0 | 1 | ai.index_job, ai.index_source | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_job | tenant | 14 | none |  | 1 | 1 | ai.index_source | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_source | tenant | 16 | none |  | 2 | 1 | ai.knowledge_collection | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.insight | tenant | 22 | scope_path |  | 3 | 2 | ai.anomaly_detector, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.intervention | tenant | 11 | scope_path |  | 1 | 3 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_collection | tenant | 12 | none |  | 4 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_document | tenant | 11 | none |  | 3 | 1 | ai.knowledge_collection | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_gap | tenant | 13 | scope_path |  | 0 | 2 | ai.knowledge_collection, ai.knowledge_document, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.message | tenant | 15 | through its owner |  | 2 | 1 | ai.conversation, ai.proposed_action | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.model | tenant | 20 | none |  | 3 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.operational_requirement | tenant | 17 | scope_path |  | 3 | 2 | ai.forecast_version, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.outbox | tenant | 16 | scope_path | yes | 0 | 1 |  | used by the first release | AiService | backend/tenant/V0108__after_r1_20261020.sql
MIG-AI | ai.outbox_sequence | tenant | 3 | scope_path |  | 0 | 0 |  | kernel machinery: the per-aggregate sequence of ai.outbox (ADR-0058) | AiService | backend/tenant/V0108__after_r1_20261020.sql
MIG-AI | ai.policy | tenant | 33 | none |  | 15 | 4 | platform.tenant | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.policy_exception | tenant | 13 | none |  | 3 | 2 | ai.governance_policy, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.prompt_template | tenant | 13 | none |  | 3 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.proposed_action | tenant | 29 | scope_path |  | 4 | 5 | ai.action_plan, ai.activity, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.provider | tenant | 28 | none |  | 10 | 1 | ai.model, platform.scope | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_decision | tenant | 19 | scope_path |  | 1 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_decline | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_event | tenant | 11 | scope_path |  | 0 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.release | tenant | 18 | none |  | 7 | 5 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.suggestion | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.training_run | tenant | 17 | scope_path |  | 1 | 0 | ai.eval_run, ai.release | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.translation_job | tenant | 10 | scope_path |  | 0 | 1 | identity.principal | used by the first release | AiService | backend/tenant/V0108__after_r1_20261020.sql
MIG-AI | ai.venue_settings | tenant | 15 | scope_path |  | 4 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-RESOURCES | resources.booking | tenant | 17 | through its owner |  | 3 | 0 | orders.sales_order, pii.subject, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource | tenant | 22 | scope_path |  | 7 | 4 | identity.principal, platform.scope, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_block | tenant | 8 | scope_path |  | 5 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_package | tenant | 13 | scope_path |  | 2 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_requirement | tenant | 12 | scope_path |  | 4 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_reservation | tenant | 15 | scope_path |  | 6 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_schedule | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-WHITELABEL | whitelabel.analytics_provider | tenant | 13 | scope_path |  | 4 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.app_build | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.banner | tenant | 12 | none |  | 5 | 3 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.booking_flow | tenant | 10 | scope_path |  | 15 | 4 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.booking_flow_step | tenant | 8 | none |  | 10 | 4 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.config_version | tenant | 16 | none |  | 15 | 1 | identity.principal | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.content_block | tenant | 13 | scope_path |  | 4 | 3 |  | used by the first release | WhiteLabelService | backend/tenant/V0108__after_r1_20261020.sql
MIG-WHITELABEL | whitelabel.content_page | tenant | 11 | none |  | 10 | 4 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.custom_domain | tenant | 18 | tenant root (one tenant per database; no tenant_id by design) |  | 8 | 5 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.faq_category | tenant | 5 | scope_path |  | 1 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.faq_entry | tenant | 6 | through its owner |  | 3 | 1 | whitelabel.faq_category | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.feature_toggle | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config | tenant | 4 | scope_path |  | 5 | 2 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config_column | tenant | 5 | through its owner |  | 4 | 1 | whitelabel.footer_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config_social_link | tenant | 5 | through its owner |  | 4 | 1 | whitelabel.footer_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice | tenant | 13 | venue_id |  | 8 | 6 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice_answer | tenant | 12 | through its owner |  | 10 | 4 | whitelabel.guided_choice, whitelabel.guided_choice_question | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice_question | tenant | 5 | through its owner |  | 8 | 4 | whitelabel.guided_choice | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.homepage_layout | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 7 | 2 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.homepage_section | tenant | 10 | none |  | 9 | 2 | whitelabel.content_page, whitelabel.homepage_layout | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.module_enablement | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 8 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.navigation_config | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 7 | 2 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.navigation_item | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 7 | 2 | whitelabel.navigation_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.policy | tenant | 10 | scope_path |  | 4 | 1 | identity.principal | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.promo_block | tenant | 11 | none |  | 6 | 3 | promotions.promotion | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.publish_review_policy | tenant | 5 | scope_path |  | 5 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.site_package | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.site_setup_progress | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.store_account | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.tenant_config | tenant | 27 | tenant root (one tenant per database; no tenant_id by design) |  | 26 | 13 | platform.tenant, whitelabel.footer_config, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.navigation_config, whitelabel.navigation_item | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.ui_string_pack | tenant | 5 | scope_path |  | 1 | 0 |  | used by the first release | WhiteLabelService | backend/tenant/V0116__after_r1_20261026.sql
MIG-PLATFORM | platform.audit_read | tenant | 8 | none |  | 0 | 1 | identity.principal, pii.subject, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.audit_record | tenant | 8 | none | yes | 1 | 5 | identity.principal, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.configuration_profile | tenant | 9 | none |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.denomination | tenant | 8 | none |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.device | tenant | 42 | none |  | 5 | 1 | platform.workstation | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.idempotency_record | tenant | 11 | scope_path |  | 0 | 6 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outbox | tenant | 16 | scope_path | yes | 0 | 70 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outlet | tenant | 17 | venue_id |  | 11 | 2 | inventory.location, ledger.cost_center, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outlet_opening_hour | tenant | 4 | through its owner |  | 3 | 2 | platform.outlet | used by the first release | TenancyService | backend/tenant/V0104__after_r1_20261015.sql
MIG-PLATFORM | platform.region_settings | tenant | 20 | none |  | 8 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board | tenant | 6 | venue_id |  | 4 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board_page | tenant | 4 | through its owner |  | 3 | 2 | platform.sale_board | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board_tile | tenant | 10 | through its owner |  | 3 | 2 | platform.sale_board_page | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.scope | tenant | 8 | none |  | 11 | 2 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.tenant | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 | platform.scope | referenced by marketing.message_template | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.venue_settings | tenant | 34 | venue_id |  | 5 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.workstation | tenant | 23 | scope_path |  | 7 | 1 | access.access_point, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | sync.dsar_request | tenant | 8 | none |  | 0 | 0 | approvals.request, sync.guest_link | built by MIG-PLATFORM as platform.dsar_request, before a declared move (CHG-TKT-013) | CrossRegionService | backend/tenant/010-platform.sql
MIG-PLATFORM | sync.guest_link | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 |  | built by MIG-PLATFORM as platform.guest_link, before a declared move (CHG-TKT-013) | CrossRegionService | backend/tenant/010-platform.sql
MIG-WORKFORCE | workforce.attendance | tenant | 15 | venue_id |  | 1 | 1 | access.access_point, identity.principal, platform.scope, workforce.rota_assignment | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-WORKFORCE | workforce.attendance_amendment | tenant | 7 | through its owner |  | 1 | 0 |  | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-WORKFORCE | workforce.rota_assignment | tenant | 17 | venue_id |  | 4 | 2 | identity.principal, platform.scope, platform.workstation | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-SEATING | seating.accessible | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.recommendation_rule | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat | tenant | 12 | none |  | 2 | 1 | seating.seat_map | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_block | tenant | 10 | scope_path |  | 0 | 0 | catalogue.performance, identity.principal | referenced by seating.seat_reservation | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_block_item | tenant | 4 | through its owner |  | 1 | 0 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_category | tenant | 7 | venue_id |  | 4 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_map | tenant | 12 | venue_id |  | 1 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_price_band | tenant | 11 | none |  | 3 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_reservation | tenant | 13 | through its owner |  | 6 | 4 | catalogue.performance, identity.principal, pii.subject, seating.seat_block | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_reservation_item | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.section | tenant | 8 | scope_path |  | 0 | 1 | assets.media_asset | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-MAINTENANCE | maintenance.asset | tenant | 30 | venue_id |  | 0 | 0 | access.access_point, inventory.supplier, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.incident | tenant | 28 | venue_id |  | 0 | 0 | identity.principal, maintenance.asset, maintenance.work_order, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection | tenant | 14 | venue_id |  | 0 | 0 | identity.principal, maintenance.asset, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection_template | tenant | 9 | venue_id |  | 2 | 1 | platform.scope | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection_template_item | tenant | 11 | through its owner |  | 1 | 1 | maintenance.inspection_template | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.work_order | tenant | 58 | venue_id |  | 1 | 0 | identity.principal, maintenance.asset, maintenance.incident, maintenance.inspection, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-WALLET | wallet.accounting_mapping | tenant | 4 | none |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.authentication_policy | tenant | 3 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.auto_reload_setting | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.balance | tenant | 9 | none |  | 3 | 3 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.channel_rule | tenant | 10 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.configuration_version | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.configuration_version_snapshot | tenant | 6 | scope_path |  | 1 | 1 | wallet.configuration_version | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.consumption_policy | tenant | 7 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.credit_lot | tenant | 14 | scope_path |  | 4 | 3 | orders.order_line, wallet.wallet | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.credit_type | tenant | 15 | none |  | 4 | 3 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.fund_reservation | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 | orders.sales_order | referenced by wallet.wallet_transaction | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.funding_rule | tenant | 13 | scope_path |  | 3 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.gift_card | tenant | 11 | none |  | 1 | 0 | pii.subject | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.integration_mapping | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.reconciliation_source | tenant | 3 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.refund_policy | tenant | 8 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.risk_rule_set | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.transfer_rule | tenant | 9 | scope_path |  | 3 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet | tenant | 9 | none |  | 6 | 3 | pii.subject | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet_transaction | tenant | 12 | venue_id |  | 2 | 3 | identity.principal, orders.sales_order, platform.scope, wallet.fund_reservation, wallet.wallet | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet_type | tenant | 25 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-CATALOGUE | catalogue.alternative_code | tenant | 8 | none |  | 2 | 1 | catalogue.product, catalogue.variant | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.audit_entry | tenant | 28 | scope_path |  | 0 | 23 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.channel_capacity | tenant | 12 | through its owner |  | 14 | 5 | catalogue.performance, seating.seat_category | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE-11 | catalogue.channel_connection | tenant | 23 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.channel_envelope | tenant | 19 | through its owner |  | 2 | 1 | catalogue.channel_capacity | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE-11 | catalogue.channel_sales_rule | tenant | 50 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.demand_forecast | tenant | 27 | scope_path |  | 1 | 0 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.dynamic_pricing_control | tenant | 39 | none |  | 7 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.dynamic_pricing_strategy | tenant | 26 | scope_path |  | 7 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.entitlement_template | tenant | 33 | scope_path |  | 8 | 2 | access.admission_rules | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event | tenant | 13 | scope_path |  | 9 | 4 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_capacity_profile | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_registration | tenant | 8 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_resource_plan | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_schedule | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.fee | tenant | 19 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.group_package | tenant | 12 | scope_path |  | 4 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.import_job | tenant | 26 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.inventory_reservation | tenant | 18 | through its owner |  | 7 | 9 | catalogue.channel_capacity, identity.principal, platform.workstation | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.performance | tenant | 12 | through its owner |  | 17 | 4 | access.admission_rules, catalogue.event, seating.seat_map | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price | tenant | 5 | through its owner |  | 8 | 2 | catalogue.price_list, catalogue.variant, ledger.tax_code | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_assignment | tenant | 26 | scope_path |  | 6 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_execution | tenant | 20 | scope_path |  | 0 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_ladder | tenant | 22 | scope_path |  | 4 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_list | tenant | 28 | venue_id |  | 16 | 5 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_resolution_policy | tenant | 11 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.pricing_recommendation | tenant | 34 | scope_path |  | 3 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.pricing_recommendation_decision | tenant | 13 | scope_path |  | 2 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.pricing_simulation | tenant | 35 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.pricing_test_case | tenant | 14 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product | tenant | 49 | scope_path |  | 41 | 7 | catalogue.entitlement_template, platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_category | tenant | 12 | scope_path |  | 6 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_channel_assignment | tenant | 17 | scope_path |  | 3 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_channel_text | tenant | 10 | scope_path |  | 2 | 1 | catalogue.product | used by the first release | CatalogueService | backend/tenant/V0108__after_r1_20261020.sql
MIG-CATALOGUE | catalogue.product_eligibility_rule | tenant | 15 | scope_path |  | 8 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_media | tenant | 7 | through its owner |  | 7 | 2 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_owner_form | tenant | 5 | scope_path |  | 2 | 1 | catalogue.product | used by the first release | CatalogueService | backend/tenant/V0108__after_r1_20261020.sql
MIG-CATALOGUE | catalogue.product_sale_permission | tenant | 7 | scope_path |  | 2 | 1 | catalogue.product | used by the first release | CatalogueService | backend/tenant/V0108__after_r1_20261020.sql
MIG-CATALOGUE | catalogue.product_version | tenant | 10 | through its owner |  | 0 | 5 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.published_bundle | tenant | 13 | venue_id |  | 2 | 1 | identity.principal, platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.rate | tenant | 17 | scope_path |  | 1 | 0 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.sales_channel | tenant | 46 | none |  | 8 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.variant | tenant | 10 | through its owner |  | 16 | 4 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.waitlist_entry | tenant | 11 | through its owner |  | 2 | 2 | catalogue.performance, catalogue.variant, pii.subject | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-LEDGER | ledger.account | tenant | 15 | none |  | 0 | 0 | ledger.legal_entity | referenced by inventory.supplier | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.cost_center | tenant | 6 | venue_id |  | 0 | 0 | platform.scope | referenced by orders.invitation | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.credit_memo | tenant | 30 | scope_path |  | 5 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.credit_memo_line | tenant | 10 | through its owner |  | 3 | 1 | ledger.credit_memo | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.einvoice_transmission | tenant | 17 | scope_path |  | 3 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.einvoicing_provider | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fiscal_period | tenant | 9 | none |  | 0 | 0 | identity.principal, ledger.legal_entity | referenced by ledger.journal_entry | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fx_provider_assignment | tenant | 6 | scope_path |  | 1 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fx_rate | tenant | 13 | through its owner |  | 7 | 2 | platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.journal_entry | tenant | 22 | none |  | 0 | 3 | identity.principal, ledger.fiscal_period, ledger.legal_entity | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.journal_line | tenant | 9 | venue_id | yes | 0 | 2 | ledger.journal_entry, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.legal_entity | tenant | 11 | none |  | 3 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.posting | tenant | 12 | venue_id |  | 1 | 1 | ledger.account, ledger.cost_center, ledger.journal_entry, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.price_variance | tenant | 15 | venue_id |  | 0 | 1 | catalogue.variant, identity.principal, ledger.journal_entry, orders.order_line, orders.sales_order, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_code | tenant | 13 | none |  | 3 | 2 | ledger.account | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice | tenant | 39 | scope_path |  | 6 | 2 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice_line | tenant | 17 | through its owner |  | 6 | 2 | ledger.tax_invoice | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice_template | tenant | 18 | scope_path |  | 2 | 2 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-INVENTORY | inventory.goods_receipt | tenant | 11 | through its owner |  | 3 | 2 | identity.principal, inventory.purchase_order, ledger.journal_entry | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.goods_receipt_line | tenant | 11 | through its owner |  | 2 | 2 | inventory.goods_receipt, inventory.inventory_item | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.inventory_item | tenant | 26 | venue_id |  | 6 | 3 | inventory.supplier, platform.scope | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.kit_component | tenant | 6 | scope_path |  | 3 | 1 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.location | tenant | 7 | venue_id |  | 0 | 0 | platform.scope | referenced by inventory.stock_batch | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.movement | tenant | 17 | through its owner |  | 4 | 3 | identity.principal, inventory.inventory_item, ledger.cost_center, ledger.journal_entry | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.purchase_order | tenant | 29 | scope_path |  | 0 | 0 | identity.principal, inventory.requisition, inventory.supplier, platform.scope | referenced by inventory.goods_receipt | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.requisition | tenant | 20 | venue_id |  | 0 | 0 | identity.principal, platform.scope | referenced by inventory.purchase_order | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.serialised_item | tenant | 9 | through its owner |  | 1 | 0 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.stock_batch | tenant | 10 | none |  | 2 | 0 | inventory.inventory_item, inventory.location, inventory.supplier | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.stock_earmark | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.supplier | tenant | 17 | none |  | 0 | 0 | ledger.account | referenced by inventory.purchase_order | InventoryService | backend/tenant/010-inventory.sql
MIG-PROMOTIONS | promotions.allocation_component | tenant | 9 | venue_id |  | 2 | 2 | ledger.account, ledger.legal_entity, platform.scope, promotions.allocation_split | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.allocation_split | tenant | 4 | through its owner |  | 0 | 1 | promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle | tenant | 21 | venue_id |  | 5 | 2 | catalogue.variant, platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_choice_group | tenant | 6 | through its owner |  | 3 | 1 | promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_choice_option | tenant | 5 | through its owner |  | 3 | 1 | promotions.bundle_choice_group | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_component | tenant | 13 | venue_id |  | 3 | 2 | platform.scope, promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.code_assignment | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_campaign | tenant | 14 | venue_id |  | 3 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_code | tenant | 17 | scope_path |  | 3 | 2 | orders.sales_order, pii.subject | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_code_batch | tenant | 11 | through its owner |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion | tenant | 28 | venue_id |  | 13 | 4 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_audit | tenant | 14 | venue_id |  | 0 | 9 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_channel_publication | tenant | 9 | venue_id |  | 2 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_evaluation_trace | tenant | 9 | venue_id |  | 0 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_rule | tenant | 13 | venue_id |  | 1 | 0 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_variant | tenant | 6 | none |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-ORDERS | orders.cart | tenant | 20 | none |  | 11 | 8 | pii.subject, platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cart_line | tenant | 21 | none |  | 10 | 6 | catalogue.inventory_reservation, catalogue.performance, catalogue.variant, orders.cart | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cash_count_line | tenant | 11 | through its owner |  | 6 | 4 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cash_movement | tenant | 13 | through its owner |  | 5 | 3 | identity.principal, orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.chargeback | tenant | 16 | none |  | 1 | 0 | orders.payment | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit | tenant | 16 | none |  | 0 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box | tenant | 16 | venue_id |  | 5 | 3 | identity.principal, orders.pos_shift, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box_foreign_holding | tenant | 7 | through its owner |  | 3 | 2 | orders.deposit_box | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box_opening_denomination | tenant | 4 | through its owner |  | 3 | 2 | orders.deposit_box | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.fraud_rule | tenant | 12 | none |  | 3 | 0 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_booking | tenant | 23 | none |  | 5 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_customer_organisation | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 |  | referenced by orders.group_customer_organisation_contact | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_customer_organisation_contact | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 | orders.group_customer_organisation | referenced by orders.group_visit_plan | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_participant | tenant | 7 | none |  | 1 | 0 | orders.group_participant_list | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_participant_list | tenant | 5 | none |  | 0 | 0 |  | referenced by orders.group_participant | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_visit_plan | tenant | 27 | scope_path |  | 2 | 1 | orders.group_booking, orders.group_customer_organisation_contact | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.invitation | tenant | 13 | scope_path |  | 1 | 0 | catalogue.performance, catalogue.product, ledger.cost_center | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.no_sale_event | tenant | 9 | through its owner |  | 1 | 1 | identity.principal, orders.pos_shift, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_event | tenant | 19 | none |  | 2 | 16 | identity.principal | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_fee | tenant | 11 | none |  | 1 | 0 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line | tenant | 23 | none |  | 19 | 12 | catalogue.inventory_reservation, catalogue.performance, catalogue.variant, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line_discount | tenant | 6 | none |  | 12 | 3 | orders.order_line, promotions.promotion | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line_eligibility | tenant | 7 | none |  | 12 | 1 | orders.order_line | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.payment | tenant | 23 | none |  | 27 | 15 | identity.principal, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.payment_link | tenant | 14 | scope_path |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift | tenant | 31 | scope_path |  | 13 | 10 | identity.principal, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift_approval | tenant | 6 | through its owner |  | 12 | 3 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift_incident | tenant | 6 | through its owner |  | 12 | 2 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund | tenant | 20 | none |  | 8 | 2 | identity.principal, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund_line | tenant | 5 | none |  | 3 | 1 | orders.order_line, orders.refund | used by the first release | OrderService | backend/tenant/V0116__after_r1_20261026.sql
MIG-ORDERS | orders.refund_payment | tenant | 5 | none |  | 3 | 1 | orders.payment, orders.refund | used by the first release | OrderService | backend/tenant/V0116__after_r1_20261026.sql
MIG-ORDERS | orders.refund_policy | tenant | 8 | venue_id |  | 6 | 1 | platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund_policy_time_band | tenant | 5 | through its owner |  | 1 | 1 | orders.refund_policy | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.resale_listing | tenant | 16 | scope_path |  | 2 | 1 | access.entitlement | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.reservation | tenant | 7 | venue_id |  | 7 | 4 | orders.sales_order, platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.reservation_line | tenant | 14 | through its owner |  | 4 | 1 | orders.reservation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.sales_order | tenant | 26 | none |  | 32 | 15 | identity.principal, orders.pos_shift, pii.subject, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.stored_value_authorisation | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_template | tenant | 11 | none |  | 5 | 4 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_template_channel | tenant | 3 | none |  | 4 | 3 | orders.ticket_template | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_transfer | tenant | 12 | none |  | 3 | 2 | orders.sales_order, pii.subject | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.till_shift_policy | tenant | 11 | scope_path |  | 4 | 1 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.visit_reminder | tenant | 7 | scope_path |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.wallet_pass | tenant | 9 | scope_path |  | 1 | 1 | access.entitlement | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ACCESS-2 | access.access_area | tenant | 28 | scope_path |  | 0 | 0 |  | referenced by access.access_point | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_incident | tenant | 12 | scope_path |  | 0 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_point | tenant | 21 | scope_path |  | 12 | 6 | access.access_area, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_point_group | tenant | 8 | scope_path |  | 4 | 2 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.admission_rules | tenant | 21 | scope_path |  | 4 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.biometric_audit_event | tenant | 18 | scope_path |  | 0 | 2 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.biometric_profile | tenant | 37 | scope_path |  | 6 | 4 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.blacklist | tenant | 10 | scope_path |  | 2 | 1 | identity.principal | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.configuration_change | tenant | 12 | scope_path |  | 0 | 19 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.credential_policy | tenant | 32 | scope_path |  | 4 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.device_binding | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.device_placement | tenant | 18 | scope_path |  | 1 | 1 | platform.device | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.entitlement | tenant | 34 | scope_path |  | 19 | 7 | catalogue.product, orders.sales_order, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.entry_rule_point | tenant | 5 | through its owner |  | 1 | 1 | access.admission_rules | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.face_reenrolment_attempt | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.gate_mode_change | tenant | 16 | scope_path |  | 2 | 2 | identity.principal | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.gate_mode_policy | tenant | 12 | scope_path |  | 3 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.parking_entitlement | tenant | 12 | subject |  | 2 | 1 | access.parking_facility, orders.sales_order, pii.subject | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.parking_facility | tenant | 14 | venue_id |  | 2 | 1 | platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.scan_event | tenant | 23 | scope_path | yes | 4 | 1 | access.access_point, access.entitlement, identity.principal, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-MARKETING | marketing.agent_availability | tenant | 7 | none |  | 2 | 1 | identity.principal | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.attribution_touch | tenant | 8 | through its owner |  | 2 | 0 | marketing.campaign, marketing.journey, orders.sales_order, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.booking_consent_record | tenant | 20 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign | tenant | 22 | venue_id |  | 5 | 4 | identity.principal, marketing.segment, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign_target | tenant | 7 | through its owner |  | 0 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign_variant | tenant | 10 | scope_path |  | 4 | 2 | marketing.campaign | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.case | tenant | 23 | venue_id |  | 6 | 3 | identity.principal, orders.sales_order, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.case_message | tenant | 12 | none |  | 2 | 1 | identity.principal, marketing.case | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.challenge | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.challenge_progress | tenant | 9 | through its owner |  | 1 | 0 | marketing.challenge, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_propagation | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_purpose | tenant | 8 | none |  | 3 | 1 | platform.tenant | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_purpose_channel | tenant | 3 | none |  | 2 | 1 | marketing.consent_purpose | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_question | tenant | 11 | scope_path |  | 12 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_question_version | tenant | 6 | through its owner |  | 11 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_record | tenant | 11 | none |  | 9 | 5 | identity.principal, orders.sales_order, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation | tenant | 21 | venue_id |  | 2 | 2 | identity.principal, marketing.case, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation_message | tenant | 8 | through its owner |  | 2 | 2 | ai.activity, marketing.conversation | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation_message_attachment | tenant | 4 | through its owner |  | 2 | 1 | marketing.conversation_message | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.cookie_banner_design | tenant | 21 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.customer_badge | tenant | 9 | none |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.device_consent | tenant | 16 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.device_consent_category | tenant | 4 | through its owner |  | 2 | 0 | marketing.device_consent | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_definition | tenant | 16 | scope_path |  | 4 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_definition_field | tenant | 24 | scope_path |  | 3 | 2 | marketing.form_definition | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_submission | tenant | 12 | none |  | 3 | 1 | pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_submission_sale_link | tenant | 7 | scope_path |  | 1 | 1 | marketing.form_submission | used by the first release | MarketingService | backend/tenant/V0108__after_r1_20261020.sql
MIG-MARKETING | marketing.guest_device | tenant | 16 | subject |  | 3 | 2 | pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_document | tenant | 9 | none |  | 2 | 1 | marketing.consent_purpose, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_preference | tenant | 7 | none |  | 2 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_profile | tenant | 23 | none |  | 9 | 3 | marketing.loyalty_position, marketing.segment, pii.subject, sync.guest_link | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.invitation | tenant | 19 | scope_path |  | 1 | 1 | catalogue.performance, catalogue.product, ledger.cost_center, marketing.invitation_campaign | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.invitation_campaign | tenant | 11 | scope_path |  | 2 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.journey | tenant | 9 | scope_path |  | 0 | 0 |  | referenced by marketing.attribution_touch | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.lost_item | tenant | 17 | venue_id |  | 1 | 1 | platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_position | tenant | 12 | none |  | 7 | 2 | marketing.loyalty_programme, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_programme | tenant | 7 | none |  | 6 | 2 | ledger.account, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_rule | tenant | 9 | through its owner |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_dispatch | tenant | 18 | none | yes | 2 | 5 | marketing.campaign, marketing.campaign_variant, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_template | tenant | 12 | none |  | 4 | 2 | platform.tenant | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_template_version | tenant | 16 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.points_earning_rule | tenant | 6 | none |  | 3 | 2 | marketing.loyalty_programme | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.points_redemption_rule | tenant | 14 | none |  | 1 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.privacy_notice_governance | tenant | 14 | scope_path |  | 0 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.programme_tier | tenant | 11 | none |  | 4 | 2 | marketing.loyalty_programme | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.referral | tenant | 10 | scope_path |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.review | tenant | 13 | venue_id |  | 1 | 1 | identity.principal, marketing.case, orders.sales_order, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.reward | tenant | 11 | none |  | 2 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.segment | tenant | 14 | venue_id |  | 3 | 1 | platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.segment_criterion | tenant | 6 | through its owner |  | 4 | 4 | marketing.segment | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.subscription | tenant | 8 | subject |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.tracking_technology | tenant | 23 | scope_path |  | 3 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.waiver_field_rule | tenant | 5 | through its owner |  | 1 | 1 | marketing.form_definition_field | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.waiver_requirement | tenant | 30 | scope_path |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.waiver_requirement_event | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.wishlist_item | tenant | 12 | subject |  | 3 | 2 | catalogue.performance, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-FNB | fnb.allergen_verdict | tenant | 9 | through its owner |  | 0 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.bill_split | tenant | 3 | through its owner |  | 1 | 1 | fnb.table_visit | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.cold_chain_event | tenant | 10 | none |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.corrective_action | tenant | 13 | scope_path |  | 4 | 4 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.course_rule | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_location | tenant | 14 | venue_id |  | 7 | 2 | fnb.dining_table, platform.scope, seating.seat | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_location_outlet | tenant | 3 | none |  | 2 | 2 | fnb.delivery_location, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_policy | tenant | 16 | scope_path |  | 4 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.dining_table | tenant | 10 | none |  | 10 | 3 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_exception | tenant | 10 | none |  | 1 | 2 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_sla | tenant | 3 | none |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_station | tenant | 11 | none |  | 5 | 1 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_ticket | tenant | 16 | none |  | 22 | 9 | identity.principal, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_ticket_line | tenant | 14 | through its owner |  | 19 | 3 | fnb.kitchen_station, fnb.kitchen_ticket | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.location_session | tenant | 10 | venue_id |  | 2 | 1 | fnb.delivery_location, fnb.table_visit, pii.subject, platform.outlet, platform.scope | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu | tenant | 8 | none |  | 7 | 6 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_item | tenant | 18 | through its owner |  | 15 | 7 | catalogue.variant, fnb.kitchen_station | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_item_modifier | tenant | 5 | through its owner |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_schedule | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_section | tenant | 5 | through its owner |  | 5 | 3 | fnb.menu | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_version | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.modifier_group | tenant | 6 | scope_path |  | 4 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.modifier_option | tenant | 7 | through its owner |  | 2 | 1 | fnb.modifier_group | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.order_fulfilment | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_plan | tenant | 7 | none |  | 3 | 2 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_plan_line | tenant | 7 | none |  | 2 | 1 | fnb.production_plan | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_run | tenant | 11 | through its owner |  | 0 | 1 | fnb.recipe | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.recipe | tenant | 4 | through its owner |  | 2 | 1 | fnb.menu_item | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.recipe_ingredient | tenant | 6 | through its owner |  | 1 | 1 | fnb.recipe, inventory.inventory_item | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.reservation_table | tenant | 4 | none |  | 6 | 4 | fnb.dining_table | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.service_order | tenant | 17 | none |  | 17 | 9 | fnb.kitchen_ticket, fnb.table_visit, orders.sales_order, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.service_order_line | tenant | 12 | through its owner |  | 12 | 1 | access.entitlement, fnb.service_order | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.sold_out_item | tenant | 10 | through its owner |  | 1 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.sub_bill | tenant | 11 | through its owner |  | 1 | 1 | fnb.bill_split | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.substitution_rule | tenant | 10 | through its owner |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_combination | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_reservation | tenant | 24 | none |  | 6 | 4 | fnb.table_visit, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_session | tenant | 9 | none |  | 2 | 1 | fnb.dining_table, fnb.table_visit, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_visit | tenant | 17 | none |  | 11 | 8 | fnb.dining_table, identity.principal, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.temperature_log | tenant | 12 | none |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.waitlist_entry | tenant | 11 | none |  | 3 | 2 | pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-PAYMENTS | payments.dunning_case | tenant | 14 | scope_path |  | 4 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.dunning_policy | tenant | 8 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.method | tenant | 16 | scope_path |  | 0 | 0 |  | referenced by payments.payment_attempt | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.payment_attempt | tenant | 19 | scope_path |  | 0 | 3 | orders.payment, orders.sales_order, payments.method, payments.provider_connection | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.provider | tenant | 15 | none |  | 3 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.provider_connection | tenant | 13 | none |  | 3 | 1 | payments.provider | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.routing_rule | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.token | tenant | 10 | none |  | 3 | 1 | marketing.consent_purpose, pii.subject | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-QUEUE | queue.entry | tenant | 25 | through its owner |  | 4 | 2 | access.entitlement, pii.subject, queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
VM-MIG-QUEUE | queue.feed | tenant | 7 | through its owner |  | 2 | 1 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.queue | tenant | 40 | venue_id |  | 6 | 2 | access.access_point, catalogue.product, maintenance.asset, platform.scope, queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.queue_operating_window | tenant | 4 | through its owner |  | 3 | 1 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.reading | tenant | 8 | through its owner |  | 5 | 0 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-RETAIL | retail.merchandise | tenant | 18 | none |  | 8 | 2 | catalogue.variant, inventory.inventory_item, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.reservation | tenant | 8 | none |  | 1 | 1 | pii.subject, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.reservation_line | tenant | 5 | through its owner |  | 1 | 1 | retail.merchandise, retail.reservation | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return | tenant | 14 | through its owner |  | 1 | 1 | identity.principal, orders.refund, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return_line | tenant | 9 | through its owner |  | 1 | 1 | retail.merchandise, retail.return | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return_policy | tenant | 10 | none |  | 3 | 1 | platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.sale | tenant | 15 | none |  | 8 | 2 | identity.principal, orders.pos_shift, orders.sales_order, pii.subject, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.sale_line | tenant | 15 | through its owner |  | 7 | 1 | retail.merchandise, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.shop_and_drop | tenant | 20 | venue_id |  | 3 | 2 | access.entitlement, fnb.delivery_location, identity.principal, pii.subject, platform.scope, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.shop_and_drop_line | tenant | 7 | through its owner |  | 3 | 2 | retail.merchandise, retail.shop_and_drop | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-VENUEMAP | venuemap.import_job | tenant | 19 | none |  | 2 | 1 | venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.map | tenant | 19 | scope_path |  | 11 | 3 | assets.media_asset, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.map_version | tenant | 10 | through its owner |  | 2 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.path | tenant | 13 | through its owner |  | 6 | 1 | venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.placed_resource | tenant | 12 | through its owner |  | 6 | 1 | catalogue.variant, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.point | tenant | 22 | through its owner |  | 10 | 2 | access.access_point, catalogue.product, platform.outlet, venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan | tenant | 15 | scope_path |  | 6 | 3 | marketing.guest_profile, orders.cart | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan_item | tenant | 19 | through its owner |  | 6 | 2 | catalogue.performance, catalogue.product, promotions.bundle, venuemap.point, venuemap.visit_plan | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan_preset | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/V0108__after_r1_20261020.sql
MIG-PRICING-2 | pricing.dynamic_price_action | tenant | 7 | through its owner |  | 4 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-pricing.sql
MIG-PRICING-2 | pricing.dynamic_price_condition | tenant | 8 | through its owner |  | 4 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-pricing.sql
MIG-PRICING-2 | pricing.dynamic_price_rule | tenant | 21 | scope_path |  | 6 | 4 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-pricing.sql

## Services
Service | Owner | Tier | Operations in release | All operations | Tables it owns in release | Points | If down
AccessService | Hrushikant Patkar | commerce | 35 | 259 | 20 | 68 | Down means the gates stop. Runs at the edge with a local decision cache.
AiService | Pranay Shinde | engagement | 66 | 146 | 52 | 125 | Down degrades suggestions and the concierge. Nothing that takes money depends on it.
CatalogueService | Hrushikant Patkar | commerce | 95 | 470 | 74 | 128 | A bad publish reaches every workstation. Versioned and rollback-able for that reason.
FnbService | Narayan Gaonkar | operations | 79 | 138 | 41 | 155 | Down means the kitchen falls back to paper. Offline-capable by design.
IdentityService | Hrushikant Patkar | foundation | 37 | 102 | 26 | 47 | A restart is an outage everywhere. Deploys go out first and alone.
InventoryService | Narayan Gaonkar | operations | 7 | 59 | 12 | 12 | Down blocks receiving and counting; selling continues from the till's cache.
LedgerService | Hrushikant Patkar | commerce | 15 | 72 | 18 | 27 | Correctness over availability. A ledger that is briefly unavailable is recoverable; one that is briefly wrong is not.
MarketingService | Narayan Gaonkar | engagement | 73 | 280 | 56 | 111 | Down stops campaigns and guest lookup. Neither stops trading.
OrderService | Pranay Shinde | commerce | 99 | 305 | 52 | 205 | Down means no sales. Highest availability target in the platform.
PlatformService | Narayan Gaonkar | platform | 21 | 234 | 24 | 31 | Down blocks provisioning and the developer API. Trading is unaffected.
ReportingService | Pranay Shinde | platform | 18 | 51 | 15 | 34 | Down stops dashboards. Nothing operational depends on it.
RetailService | Hrushikant Patkar | operations | 16 | 25 | 10 | 28 | Down means the shop stops; the gates and the restaurant do not.
TenancyService | Pranay Shinde | foundation | 37 | 214 | 34 | 64 | Same as identity — nothing runs without a scope.
VenueOpsService | Narayan Gaonkar | operations | 80 | 298 | 49 | 132 | Down degrades venue operations. Selling and admitting continue.
WalletService | Pranay Shinde | commerce | 14 | 71 | 21 | 22 | It holds a liability owed to a customer. A wallet that double-spends is a financial loss, not a bug report. Deduction order across credit lots is FEFO and is decided here, once, rather than per caller.
WhiteLabelService | Hrushikant Patkar | platform | 94 | 110 | 31 | 148 | Down freezes the current published config. Guests see the last good version.

## APIs
Service | Group | Operation | Method | Path | Request schema | Response schema | Permission | Part | Wave | Task | Reads | Writes | Summary
AccessService | access | approveManualOverrideSupervisor | PUT | /manual-override-supervisor | ManualOverrideSupervisorApprovalInput | ManualOverrideSupervisorApprovalView | ACCESS_OVERRIDE | setup | 1 | SVC-ACCESS-ACCESS-1 | access.access_point, access.scan_event, cache:idempotency, identity.principal | access.scan_event, cache:idempotency | Manual Override & Supervisor Approval
AccessService | access | bindCredentialDevice | POST | /my/credentials/{credentialId}/device-bindings | CredentialDeviceBindingInput | AccessDeviceBinding |  | core | 1 | SVC-ACCESS-ACCESS-1 | access.credential_policy, access.device_binding, access.entitlement, cache:idempotency | access.device_binding, cache:idempotency | Bind my credential to this device
AccessService | access | deleteAccessPointGroup | DELETE | /access-point-groups/{groupId} |  |  | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-1 | access.access_point_group, access.gate_mode_policy, cache:idempotency | access.access_point_group, access.configuration_change, cache:idempotency | Delete an access-point group
AccessService | access | enrolFacePass | POST | /face-pass/enrolments |  | FacePassEnrolment | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-1 | access.biometric_profile, access.face_reenrolment_attempt, cache:idempotency, marketing.consent_record, pii.subject, pii.subject_biometric | access.biometric_audit_event, access.face_reenrolment_attempt, cache:idempotency, marketing.consent_record, pii.subject_biometric, platform.outbox | Register a facial profile against an entitlement
AccessService | access | enrolFaceTag | POST | /face-tag/enrolments |  | FacePassEnrolment | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-2 | access.biometric_profile, cache:idempotency, pii.subject_biometric | cache:idempotency, pii.subject_biometric, platform.outbox | Capture a same-visit facial model, deleted when the ticket is fully redeemed
AccessService | access | getEntitlement | GET | /entitlements/{entitlementId} |  | Entitlement | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement, catalogue.entitlement_template, identity.delegated_access |  | One entitlement, with what remains on it
AccessService | access | getEntitlementCredential | GET | /entitlements/{entitlementId}/credential |  | object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement | access.entitlement | The thing that gets scanned
AccessService | access | getEntitlementHistory | GET | /entitlements/{entitlementId}/history |  | array of object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement, access.scan_event |  | Every scan, freeze, share and reissue against it
AccessService | access | getFacePassEnrolment | GET | /face-pass/enrolments/{enrolmentId} |  | FacePassEnrolment | GUEST_VIEW | core | 1 | SVC-ACCESS-ACCESS-3 | pii.subject_biometric |  | Whether a pass has a face registered, and when
AccessService | access | listEntitlements | GET | /my/entitlements/all |  | object |  | core | 1 | SVC-ACCESS-ACCESS-3 | access.admission_rules, access.entitlement, catalogue.product |  | Every entitlement this guest holds, including expired
AccessService | access | listMyEntitlements | GET | /guests/me/entitlements |  | object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-3 | access.entitlement, catalogue.entitlement_template, catalogue.product, identity.delegated_access |  | Every ticket, pass and membership this guest holds
AccessService | access | listParkingFacilities | GET | /parking-facilities |  | object | PARKING_CONFIGURE | core | 1 | SVC-ACCESS-ACCESS-3 | access.parking_facility |  | Car parks at a venue, and how each integrates
AccessService | access | revokeFacePass | DELETE | /face-pass/enrolments/{enrolmentId} |  |  | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-4 | cache:idempotency, pii.subject_biometric | access.biometric_audit_event, cache:idempotency, pii.subject_biometric, platform.outbox | Remove a facial profile
AccessService | access | setAccessPointGroup | PUT | /access-point-groups/{groupId} | AccessAccessPointGroup | AccessAccessPointGroup | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.access_point_group, cache:idempotency | access.access_point_group, access.configuration_change, cache:idempotency | Create or replace an access-point group
AccessService | access | setBiometricVerificationProfile | PUT | /biometric-verification-profile | BiometricVerificationProfileBuilderInput | BiometricVerificationProfileBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Biometric Verification Profile Builder
AccessService | access | setBleBeaconGeofence | PUT | /ble-beacon-geofence | BleBeaconGeofenceConfigurationInput | BleBeaconGeofenceConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.device_placement, cache:idempotency | access.access_point, access.configuration_change, access.device_placement, cache:idempotency | BLE Beacon & Geofence Configuration
AccessService | access | setCredentialActivationDisplay | PUT | /credential-activation-display/{credentialPolicyId} | CredentialActivationDisplayRulesInput | CredentialActivationDisplayRulesView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Save a credential activation and display rule
AccessService | access | setDeviceBindingPolicy | PUT | /device-binding-policy | DeviceBindingPolicyInput | AccessCredentialPolicy | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Set the device binding policy of a venue
AccessService | access | setFaceMatchingVerification | PUT | /face-matching-verification/{profileId} | FaceMatchingVerificationThresholdsInput | FaceMatchingVerificationThresholdsView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Save face matching and verification thresholds
AccessService | access | setFacePassEnrollment | PUT | /face-pass-enrollment | FacePassEnrollmentConfigurationInput | FacePassEnrollmentConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Face Pass Enrollment Configuration
AccessService | access | setFaceTagTemporaryEnrollment | PUT | /face-tag-temporary/{profileId} | FaceTagTemporaryEnrollmentInput | FaceTagTemporaryEnrollmentView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Save a Face Tag profile
AccessService | access | setGateModePolicy | PUT | /gate-mode-policies/{gateModePolicyId} | AccessGateModePolicy | AccessGateModePolicy | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.access_point_group, access.gate_mode_policy, cache:idempotency | access.configuration_change, access.gate_mode_policy, cache:idempotency | Set a policy for a non-standard gate mode
AccessService | access | setParkingFacility | PUT | /parking-facilities/{parkingFacilityId} | ParkingFacility | ParkingFacility | PARKING_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.parking_facility, cache:idempotency | access.configuration_change, access.parking_facility, cache:idempotency | Configure a car park and its integration
AccessService | access | setVirtualTicketIdentity | PUT | /virtual-ticket-identity | VirtualTicketIdentityMasterRecordConfigurationInput | VirtualTicketIdentityMasterRecordConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Virtual Ticket Identity & Master Record Configuration
AccessService | access | setVisualAccessRule | PUT | /visual-access-rule | VisualAccessRuleBuilderInput | VisualAccessRuleBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-7 | access.admission_rules, access.entry_rule_point, cache:idempotency | access.admission_rules, access.configuration_change, access.entry_rule_point, cache:idempotency | Visual Access Rule Builder
AccessService | access | updateParkingEntitlement | PATCH | /parking-entitlements/{entitlementId} | UpdateParkingEntitlementRequest | ParkingEntitlement |  | core | 1 | SVC-ACCESS-ACCESS-7 | access.parking_entitlement, cache:idempotency | access.parking_entitlement, cache:idempotency | Change the plate, or revoke
AccessService | accessPoint | addBlacklistEntry | POST | /blacklist |  | BlacklistEntry | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.blacklist, cache:idempotency | access.blacklist, cache:idempotency | Blacklist a media code
AccessService | accessPoint | createAccessPoint | POST | /access-points | CreateAccessPointRequest | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Create an access point
AccessService | accessPoint | createAdmissionRules | POST | /admission-rules | AdmissionRules | AdmissionRules | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.admission_rules, cache:idempotency | access.admission_rules, access.configuration_change, cache:idempotency | Create an admission profile
AccessService | accessPoint | setAccessPointDirection | PUT | /access-points/{accessPointId}/direction |  | AccessPoint | ACCESS_DIRECTION_SET | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.access_point, access.gate_mode_change, cache:idempotency | access.access_point, access.configuration_change, access.gate_mode_change, cache:idempotency | Switch a gate's direction live
AccessService | accessPoint | setAccessPointGeofence | PUT | /access-points/{accessPointId}/geofence | AccessPointGeofence | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Set a geofence for handheld validation
AccessService | accessPoint | setTurnstileMode | PUT | /access-points/{accessPointId}/mode |  | AccessPoint | TURNSTILE_MODE_SET | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, access.access_point_group, access.gate_mode_change, access.gate_mode_policy, cache:idempotency | access.access_incident, access.access_point, access.gate_mode_change, cache:idempotency | Set the operating mode of an access point
AccessService | accessPoint | updateAccessPoint | PATCH | /access-points/{accessPointId} |  | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Update an access point
AccessService | accessPoint | updateAdmissionRules | PUT | /admission-rules/{profileId} | AdmissionRules | AdmissionRules | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.admission_rules, cache:idempotency | access.admission_rules, access.configuration_change, cache:idempotency | Update an admission profile
AccessService | general | getParkingEntitlement | GET | /parking-entitlements/{entitlementId} |  | ParkingEntitlement |  | core | 1 | SVC-ACCESS-GENERAL-1 | access.parking_entitlement |  | One of the guest's parking entitlements
AiService | actions | overrideAiDecision | POST | /decision-records/{decisionRecordId}/override |  | AiIntervention | AI_APPROVE | core | 1 | SVC-AI-ACTIONS-1 | ai.decision_record, ai.intervention, cache:idempotency | ai.decision_record, ai.intervention, cache:idempotency | Override an AI decision
AiService | ai | getTranslationProposals | GET | /ai/translate/{translationJobId} |  | TranslationProposals | TENANT_CONFIGURE | core | 1 | SVC-AI-AI-1 | ai.proposed_action |  | Follow a translation job
AiService | ai | proposeTranslations | POST | /ai/translate |  | TranslationProposals | TENANT_CONFIGURE | core | 1 | SVC-AI-AI-1 | ai.policy, ai.provider, cache:idempotency, marketing.message_template, marketing.message_template_version | ai.activity, ai.proposed_action, ai.translation_job, cache:idempotency | Fill translation gaps with a first pass, for a human to edit
AiService | ai | proposeVenueLabels | POST | /ai/venue-map/{mapId}/propose-labels |  | array of VenueLabelProposal | VENUE_MAP_MANAGE | core | 1 | SVC-AI-AI-1 | ai.policy, ai.provider, cache:idempotency, qdrant:knowledge, venuemap.import_job, venuemap.point | ai.activity, ai.proposed_action, cache:idempotency | Suggest what each extracted shape is
AiService | ai | requestSuggestion | POST | /ai/suggestions |  | Suggestion | AI_USE | core | 1 | SVC-AI-AI-1 | ai.capability_maturity, ai.forecast_point, ai.forecast_version, ai.history_observation, ai.insight, ai.operational_requirement, ai.policy, ai.provider, ai.rec_decline, ai.release, ai.suggestion, ai.venue_settings, cache:idempotency, cache:rec-candidates, fnb.production_plan, inventory.movement, inventory.stock_batch, marketing.attribution_touch, marketing.segment, queue.queue, queue.reading, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | ai.activity, ai.suggestion, cache:idempotency | Ask for an answer, however it is currently produced
AiService | ai | setSuggestionProvider | PUT | /ai/suggestion-providers |  | object | AI_CONFIGURE | setup | 1 | SVC-AI-AI-2 | ai.policy, ai.provider, ai.release, cache:idempotency | ai.policy, cache:idempotency, cache:resolution | Point a question at a rule, a model, or both
AiService | ai | testAiProvider | POST | /ai-providers/{providerId}/test |  | object | AI_CONFIGURE | core | 1 | SVC-AI-AI-2 | ai.byok_enablement, ai.model, ai.provider, cache:idempotency | ai.activity, ai.provider, cache:idempotency | Check the key works before anyone relies on it
AiService | assist | createAiConversation | POST | /conversations |  | AiConversation | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.conversation, cache:idempotency | ai.conversation, cache:idempotency | Open a conversation
AiService | assist | listAiConversations | GET | /conversations |  | object | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.conversation |  | A principal's conversation history
AiService | assist | sendAiMessage | POST | /conversations/{conversationId}/messages |  | AiMessage | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.assistant_profile, ai.capability, ai.chunk_embedding, ai.conversation, ai.knowledge_document, ai.message, ai.policy, ai.proposed_action, ai.provider, cache:answer, cache:idempotency, qdrant:knowledge | ai.activity, ai.decision_record, ai.knowledge_gap, ai.message, ai.proposed_action, cache:answer, cache:idempotency, qdrant:knowledge | Ask
AiService | config | getAiByokEnablement | GET | /tenants/{tenantId}/byok |  | AiByokEnablement | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.byok_enablement |  | Whether a tenant may bring its own key
AiService | config | getAiPolicy | GET | /policy |  | AiPolicy | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.policy |  | What the assistant may do here
AiService | config | listAiProviders | GET | /providers |  | array of AiProvider | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.provider |  | Configured providers and their order
AiService | config | setAiByokEnablement | PUT | /tenants/{tenantId}/byok | AiByokEnablement | AiByokEnablement | PLATFORM_AI_MANAGE | setup | 1 | SVC-AI-CONFIG-1 | ai.byok_enablement, cache:idempotency | ai.byok_enablement, cache:idempotency | Enable or disable bring-your-own-key for a tenant (platform)
AiService | config | setAiPolicy | PUT | /policy | AiPolicy | AiPolicy | AI_CONFIGURE | setup | 1 | SVC-AI-CONFIG-2 | ai.policy, cache:idempotency | ai.policy, cache:idempotency | Set the policy
AiService | configure | getGuidedChoiceSuggestion | GET | /guided-choice-suggestions/{suggestionId} |  | AiGuidedChoiceSuggestion | AI_USE | core | 1 | SVC-AI-CONFIGURE-1 | ai.guided_choice_suggestion |  | The reasons behind a Help me choose suggestion
AiService | configure | suggestGuidedChoice | POST | /venues/{venueId}/guided-choice-suggestions |  | AiGuidedChoiceSuggestion | AI_USE | core | 1 | SVC-AI-CONFIGURE-1 | ai.guided_choice_suggestion, ai.policy, ai.prompt_template, cache:idempotency | ai.activity, ai.decision_record, ai.guided_choice_suggestion, cache:idempotency | Suggest a Help me choose set-up from the venue's catalogue
AiService | forecast | createForecastScenario | POST | /forecast-scenarios | AiForecastScenario | AiForecastScenario | AI_USE | setup | 1 | SVC-AI-FORECAST-1 | ai.forecast_point, ai.forecast_scenario, ai.forecast_version, cache:idempotency | ai.forecast_point, ai.forecast_scenario, cache:idempotency | Run a what-if
AiService | forecast | decideOperationalRequirement | POST | /operational-requirements/{requirementId}/decide |  | AiOperationalRequirement | AI_USE | setup | 1 | SVC-AI-FORECAST-1 | ai.operational_requirement, cache:idempotency | ai.decision_record, ai.operational_requirement, cache:idempotency | Accept, modify or reject a requirement
AiService | forecast | getAiVenueSettings | GET | /venues/{venueId}/ai-settings |  | AiVenueSettings | AI_USE | core | 1 | SVC-AI-FORECAST-1 | ai.venue_settings |  | The venue AI profile the baselines stand on
AiService | forecast | getForecast | GET | /forecasts |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-1 | ai.forecast_definition, ai.forecast_point, ai.forecast_version |  | Forecast values
AiService | forecast | getForecastAccuracy | GET | /forecast-accuracy |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.forecast_accuracy, ai.forecast_definition |  | Measured forecast accuracy
AiService | forecast | getVenueHistoryImport | GET | /history-imports/{importId} |  | AiHistoryImport | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.history_import |  | One history import, with its findings
AiService | forecast | importVenueHistory | POST | /venues/{venueId}/history-imports |  | AiHistoryImport | AI_CONFIGURE | core | 1 | SVC-AI-FORECAST-2 | ai.history_import, assets.media_asset, cache:idempotency | ai.capability_maturity, ai.history_import, ai.history_observation, cache:idempotency | Import the venue's own historical exports for the AI baselines
AiService | forecast | listForecastVersions | GET | /forecast-versions |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.forecast_definition, ai.forecast_version |  | Forecast versions
AiService | forecast | listOperationalRequirements | GET | /operational-requirements |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-3 | ai.forecast_version, ai.operational_requirement |  | Requirements derived from the forecast
AiService | forecast | listVenueHistoryImports | GET | /venues/{venueId}/history-imports |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-3 | ai.history_import |  | The venue's history imports
AiService | forecast | publishForecastVersion | POST | /forecast-versions/{versionId}/publish |  | AiForecastVersion | AI_USE | setup | 1 | SVC-AI-FORECAST-3 | ai.forecast_definition, ai.forecast_version, cache:idempotency | ai.decision_record, ai.forecast_version, ai.operational_requirement, cache:idempotency | Publish a forecast version
AiService | forecast | runForecast | POST | /forecast-definitions/{definitionKey}/runs |  | AiForecastVersion | AI_CONFIGURE | setup | 1 | SVC-AI-FORECAST-3 | ai.forecast_definition, ai.forecast_version, ai.history_observation, ai.venue_settings, cache:idempotency | ai.forecast_point, ai.forecast_version, cache:idempotency | Run a forecast now
AiService | forecast | setAiVenueSettings | PUT | /venues/{venueId}/ai-settings | AiVenueSettings | AiVenueSettings | AI_CONFIGURE | core | 1 | SVC-AI-FORECAST-4 | ai.venue_settings, cache:idempotency | ai.venue_settings, cache:idempotency | Set the venue AI profile
AiService | forecast | setForecastDefinition | PUT | /forecast-definitions/{definitionKey} | AiForecastDefinition | AiForecastDefinition | AI_CONFIGURE | setup | 1 | SVC-AI-FORECAST-4 | ai.forecast_definition, cache:idempotency | ai.forecast_definition, cache:idempotency | Define a forecast
AiService | generate | proposeMarketingContent | POST | /ai/content-drafts |  | AiContentDraftSet | AI_USE | core | 1 | SVC-AI-GENERATE-1 | ai.capability, ai.governance_policy_version, ai.policy, ai.prompt_template, ai.provider, cache:idempotency, catalogue.event, catalogue.product, marketing.campaign, marketing.message_template, promotions.promotion, whitelabel.banner, whitelabel.content_page, whitelabel.homepage_section, whitelabel.promo_block | ai.activity, ai.decision_record, ai.proposed_action, cache:idempotency | Draft marketing content for a person to edit and apply
AiService | governance | createAiGovernancePolicyDraft | POST | /governance/policy-drafts |  | AiGovernancePolicyVersion | AI_CONFIGURE | setup | 1 | SVC-AI-GOVERNANCE-1 | ai.governance_policy, ai.governance_policy_version, cache:idempotency | ai.governance_policy, ai.governance_policy_version, cache:idempotency | Draft a governance policy, or a new version of one
AiService | governance | decideProposedAction | POST | /proposed-actions/{actionId}/decide |  | ProposedAction | AI_USE | core | 1 | SVC-AI-GOVERNANCE-1 | ai.action_plan, ai.proposed_action, cache:idempotency | ai.action_plan, ai.activity, ai.decision_record, ai.proposed_action, cache:idempotency | Approve or reject a proposal
AiService | governance | evaluateAiGovernance | POST | /governance/evaluate |  | AiGovernanceDecision |  | core | 1 | SVC-AI-GOVERNANCE-1 | ai.capability, ai.governance_policy_version, ai.policy, ai.policy_exception, cache:governance-policy, cache:idempotency | ai.decision_record, cache:idempotency | Ask the governance decision point (service callers)
AiService | governance | getAiUsage | GET | /usage |  | AiUsageReport | AI_AUDIT_VIEW | core | 1 | SVC-AI-GOVERNANCE-1 | ai.activity, ai.model |  | Usage, cost and performance
AiService | governance | getEffectiveAiPolicy | GET | /governance/effective-policy |  | AiEffectivePolicy | AI_USE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.capability, ai.governance_policy, ai.governance_policy_version, ai.policy, ai.policy_exception |  | The policy in force for a capability at a scope
AiService | governance | listAiCapabilities | GET | /governance/capabilities |  | object | AI_USE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.capability |  | The capability registry
AiService | governance | listAiGovernancePolicyVersions | GET | /governance/policy-versions |  | object | AI_USE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.governance_policy, ai.governance_policy_version |  | Governance policies and their versions
AiService | governance | listProposedActions | GET | /proposed-actions |  | array of ProposedAction | AI_USE | core | 1 | SVC-AI-GOVERNANCE-4 | ai.proposed_action |  | What the assistant has proposed and nobody has decided
AiService | governance | pauseAiCapability | POST | /governance/capabilities/{capabilityKey}/pause |  | AiCapabilityRegistration | AI_CONFIGURE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.action_plan, ai.capability, cache:idempotency | ai.action_plan, ai.capability, ai.decision_record, ai.intervention, ai.outbox, cache:idempotency | Stop a capability now
AiService | governance | publishAiGovernancePolicy | POST | /governance/policy-versions/{versionId}/publish |  | AiGovernancePolicyVersion | AI_APPROVE | setup | 1 | SVC-AI-GOVERNANCE-3 | ai.governance_policy_version, cache:idempotency | ai.decision_record, ai.governance_policy, ai.governance_policy_version, cache:governance-policy, cache:idempotency | Publish a simulated policy version
AiService | governance | revokeAiPolicyException | POST | /governance/policy-exceptions/{exceptionId}/revoke |  | AiPolicyException | AI_APPROVE | core | 1 | SVC-AI-GOVERNANCE-3 | ai.policy_exception, cache:idempotency | ai.decision_record, ai.policy_exception, cache:idempotency | End an exception before it expires
AiService | governance | simulateAiGovernancePolicy | POST | /governance/policy-versions/{versionId}/simulate |  | AiPolicySimulation | AI_CONFIGURE | setup | 1 | SVC-AI-GOVERNANCE-3 | ai.decision_record, ai.governance_policy_version, cache:idempotency | ai.governance_policy_version, cache:idempotency | Test a draft policy before it is published
AiService | insights | decideAiInsight | POST | /insights/{insightId}/decide |  | AiInsight | AI_USE | setup | 1 | SVC-AI-INSIGHTS-1 | ai.insight, cache:idempotency | ai.anomaly_detector, ai.insight, cache:idempotency | Review, accept, reject or mark an insight actioned
AiService | insights | explainMetricChange | POST | /insights/explain-metric-change |  | AiMetricChangeExplanation | AI_USE | setup | 1 | SVC-AI-INSIGHTS-1 | ai.insight, ai.policy, cache:idempotency | ai.activity, ai.insight, cache:idempotency | Why did this metric change
AiService | knowledge | configureAssistantProfile | PUT | /assistant-profiles/{profileKey} | AiAssistantProfile | AiAssistantProfile | AI_CONFIGURE | setup | 1 | SVC-AI-KNOWLEDGE-1 | ai.assistant_profile, ai.policy, cache:idempotency | ai.assistant_profile, cache:idempotency | Define an assistant profile
AiService | knowledge | recordAnswerFeedback | POST | /messages/{messageId}/feedback |  | AiAnswerFeedback | AI_USE | core | 1 | SVC-AI-KNOWLEDGE-1 | ai.answer_feedback, ai.message, cache:idempotency | ai.answer_feedback, ai.knowledge_gap, cache:idempotency | Say whether an answer helped
AiService | models | listAiEvaluations | GET | /evaluations |  | object | AI_USE | core | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.eval_suite |  | Evaluation runs
AiService | models | listAiTrainingRuns | GET | /training-runs |  | object | AI_USE | core | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.release, ai.training_run |  | The per-tenant training and backtest runs
AiService | models | promoteAiRelease | POST | /releases/{releaseId}/promote |  | AiRelease | AI_USE | setup | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.governance_alert, ai.release, cache:idempotency | ai.decision_record, ai.forecast_definition, ai.governance_alert, ai.policy, ai.release, cache:idempotency | Promote a release to its next stage (a person)
AiService | models | publishPromptTemplate | POST | /prompt-templates/{templateKey}/versions |  | AiPromptTemplate | AI_APPROVE | setup | 1 | SVC-AI-MODELS-1 | ai.prompt_template, cache:idempotency | ai.prompt_template, ai.release, cache:idempotency | Publish a prompt template version
AiService | models | rollbackAiRelease | POST | /releases/{releaseId}/rollback |  | AiRelease | AI_APPROVE | setup | 1 | SVC-AI-MODELS-2 | ai.release, cache:idempotency | ai.decision_record, ai.forecast_definition, ai.policy, ai.release, cache:idempotency | Roll a release back
AiService | models | runAiEvaluation | POST | /evaluations |  | AiEvaluationRun | AI_CONFIGURE | setup | 1 | SVC-AI-MODELS-2 | ai.eval_run, ai.eval_suite, ai.release, cache:idempotency | ai.eval_run, ai.release, cache:idempotency | Evaluate a candidate
AiService | models | setAiModel | PUT | /models/{modelId} | AiModel | AiModel | PLATFORM_AI_MANAGE | setup | 1 | SVC-AI-MODELS-2 | ai.model, cache:idempotency | ai.model, cache:idempotency | Add or change a platform model (platform)
AiService | monitoring | containAiIncident | POST | /incidents/{incidentId}/contain |  | AiIncident | AI_APPROVE | setup | 1 | SVC-AI-MONITORING-1 | ai.incident, cache:idempotency | ai.capability, ai.decision_record, ai.incident, ai.intervention, ai.policy_exception, ai.release, cache:idempotency | Contain an incident
AiService | monitoring | listAiGovernanceAlerts | GET | /governance-alerts |  | object | AI_USE | core | 1 | SVC-AI-MONITORING-1 | ai.governance_alert |  | Governance alerts
AiService | monitoring | listAiIncidents | GET | /incidents |  | object | AI_USE | core | 1 | SVC-AI-MONITORING-1 | ai.incident |  | AI incidents
AiService | monitoring | openAiIncident | POST | /incidents |  | AiIncident | AI_CONFIGURE | core | 1 | SVC-AI-MONITORING-1 | ai.governance_alert, ai.incident, cache:idempotency | ai.governance_alert, ai.incident, cache:idempotency | Open an AI incident
AiService | recommend | decideRecommendations | POST | /recommendations/decide |  | AiRecommendationResult | AI_USE | core | 1 | SVC-AI-RECOMMEND-1 | ai.rec_decline, ai.release, cache:idempotency, cache:rec-candidates, cache:rec-features | ai.decision_record, ai.rec_decision, cache:idempotency | Fill a recommendation slot
AiService | recommend | recordRecommendationEvents | POST | /recommendations/events |  |  | AI_USE | core | 1 | SVC-AI-RECOMMEND-1 | ai.rec_decision, cache:idempotency | ai.rec_decline, ai.rec_event, cache:idempotency | Report what happened to recommended items
AiService | retrieval | createKnowledgeCollection | POST | /collections | KnowledgeCollection | KnowledgeCollection | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, cache:idempotency, qdrant:knowledge | ai.knowledge_collection, cache:idempotency, qdrant:knowledge | Create a collection
AiService | retrieval | ingestKnowledgeDocument | POST | /collections/{collectionId}/documents | KnowledgeDocument | KnowledgeDocument | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, ai.knowledge_document, cache:embedding, cache:idempotency, qdrant:knowledge | ai.chunk_embedding, ai.knowledge_document, cache:embedding, cache:idempotency, qdrant:knowledge | Add a document
AiService | retrieval | reindexSource | POST | /index-sources/{sourceId}/reindex |  | IndexJob | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.index_job, ai.index_source, assets.media_asset, cache:embedding, cache:idempotency, catalogue.entitlement_template, catalogue.product, fnb.menu_item, maintenance.inspection_template, marketing.case, reporting.report_definition, retail.merchandise, whitelabel.content_page, whitelabel.faq_entry, whitelabel.policy | ai.chunk_embedding, ai.index_entry, ai.index_job, cache:embedding, cache:idempotency, qdrant:knowledge | Rebuild a source
AiService | retrieval | semanticSearch | POST | /search |  | array of SearchResult | AI_USE | core | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, ai.knowledge_document, assets.media_asset, cache:answer, cache:idempotency, catalogue.product, qdrant:knowledge | ai.activity, cache:answer, cache:idempotency, qdrant:knowledge | Search meaning, not words
AiService | retrieval | setIndexSource | PUT | /index-sources/{sourceId} | IndexSource | IndexSource | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-2 | ai.index_source, ai.knowledge_collection, cache:idempotency | ai.index_source, cache:idempotency | Declare a source indexed
CatalogueService | availability | getSeatAvailability | GET | /performances/{performanceId}/seat-availability |  | SeatAvailability | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-AVAILABILITY-1 | seating.seat, seating.seat_category, seating.seat_reservation |  | Seat status for a performance
CatalogueService | bundle | createBundle | POST | /bundles | CreateBundleRequest | Bundle | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, fnb.menu_item, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component, promotions.promotion_audit | Create a bundle
CatalogueService | bundle | getGuestBundle | GET | /guest-bundles/{bundleId} |  | GuestBundle |  | core | 1 | SVC-CATALOGUE-BUNDLE-5 | promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component |  | What a guest is shown of a bundle
CatalogueService | bundle | getLatestBundle | GET | /catalogue/bundles/latest |  | CatalogueBundle | PRODUCT_VIEW | core | 1 |  | catalogue.published_bundle |  | Pull the current bundle for this workstation's venue
CatalogueService | bundle | publishBundle | POST | /catalogue/bundles |  | BundleSummary | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-2 | cache:idempotency, catalogue.price, catalogue.price_list, catalogue.product, catalogue.published_bundle, catalogue.variant, platform.sale_board_for_catalogue, platform.sale_board_page_for_catalogue, platform.sale_board_tile_for_catalogue | cache:idempotency, catalogue.published_bundle | Compute, sign and publish a catalogue bundle
CatalogueService | bundle | updateBundle | PATCH | /bundles/{bundleId} |  | Bundle | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-2 | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component | cache:idempotency, catalogue.product, catalogue.variant, promotions.allocation_component, promotions.allocation_split, promotions.bundle, promotions.bundle_component, promotions.promotion_audit | Amend a bundle
CatalogueService | capacity | getAvailability | GET | /availability |  | PerformanceAvailabilityPage | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CAPACITY-1 | catalogue.channel_capacity, catalogue.inventory_reservation, catalogue.performance |  | Live remaining capacity
CatalogueService | catalogue | bulkChangePrices | POST | /products/bulk-price |  | BulkPriceResult | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.price_list, catalogue.product | cache:idempotency, catalogue.price_list, catalogue.product_version | Reprice a category or a whole catalogue
CatalogueService | catalogue | cloneProduct | POST | /products/{productId}/clone |  | Product | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.product, catalogue.product_media, catalogue.variant | cache:idempotency, catalogue.product, catalogue.product_media, catalogue.variant | Copy a product as a new draft
CatalogueService | catalogue | commitCatalogueImport | POST | /products/import/{jobId}/commit |  | CatalogueImportJob | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.import_job | cache:idempotency, catalogue.import_job, catalogue.product, catalogue.variant | Apply a parsed catalogue import
CatalogueService | catalogue | getMyMemberships | GET | /guests/me/memberships |  | array of GuestMembership | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CATALOGUE-1 | access.entitlement, catalogue.product, marketing.loyalty_position |  | A guest's own memberships, benefits and history
CatalogueService | catalogue | joinWaitlist | POST | /waitlist-entries | WaitlistEntry | WaitlistEntry |  | core | 1 |  | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.waitlist_entry | cache:idempotency, catalogue.waitlist_entry | Ask to be told if capacity frees up
CatalogueService | catalogue | leaveWaitlist | DELETE | /waitlist-entries/{entryId} |  |  |  | core | 1 |  | cache:idempotency, catalogue.waitlist_entry | cache:idempotency, catalogue.waitlist_entry | Stop waiting
CatalogueService | catalogue | listProductCategories | GET | /product-categories |  | array of ProductCategoryNode | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | catalogue.product, catalogue.product_category |  | The merchandise hierarchy — categories, brands, collections
CatalogueService | catalogue | searchCatalogue | GET | /search |  | array of object |  | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | catalogue.event, catalogue.product, catalogue.product_eligibility_rule, catalogue.product_media, catalogue.variant, whitelabel.guided_choice_answer |  | Find something by name
CatalogueService | catalogue | setChannelConnectionConfiguration | PUT | /channel-connections/{connectionId} | ChannelConnection | ChannelConnection | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.channel_connection, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.channel_connection | Create or update a channel connection
CatalogueService | catalogue | setChannelSalesRule | PUT | /channel-sales-rules/{ruleId} | ChannelSalesRule | ChannelSalesRule | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.channel_sales_rule, catalogue.product, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.channel_sales_rule | Create or replace a channel sales window, limit or eligibility rule
CatalogueService | catalogue | setDynamicPriceRule | PUT | /pricing/dynamic-rules/{ruleId} | DynamicPriceRuleDetail | DynamicPriceRuleDetail | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | Replace a rule, its conditions and its actions
CatalogueService | catalogue | setDynamicPricingGuardrailPolicy | PUT | /dynamic-pricing-controls | DynamicPricingControl | DynamicPricingControl | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy | cache:idempotency, catalogue.audit_entry, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, platform.outbox | Set the guardrails and automation level of dynamic pricing at one scope
CatalogueService | catalogue | setFeeDefinition | PUT | /fees/{feeId} | PricingFee | PricingFee | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.fee | cache:idempotency, catalogue.audit_entry, catalogue.fee | Create or update a fee or surcharge
CatalogueService | catalogue | setPriceLadderMatrix | PUT | /dynamic-pricing-strategies/{strategyId}/price-ladder | PriceLadder | PriceLadder | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, catalogue.price_ladder | cache:idempotency, catalogue.audit_entry, catalogue.price_ladder | Set a strategy's price ladder
CatalogueService | catalogue | setProductCategories | PUT | /product-categories |  | array of ProductCategory | PRODUCT_CONFIGURE | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | cache:idempotency, catalogue.product, catalogue.product_category, whitelabel.booking_flow | cache:idempotency, catalogue.product_category | Define the hierarchy, in the order a guest sees it
CatalogueService | catalogue | transitionDynamicPricingStrategy | POST | /dynamic-pricing-strategies/{strategyId}/lifecycle |  | DynamicPricingStrategy | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, catalogue.price_ladder, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, catalogue.dynamic_pricing_strategy | Activate, pause, resume or retire a dynamic pricing strategy
CatalogueService | category | createSeatCategory | POST | /seat-categories |  | SeatCategory | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATEGORY-1 | cache:idempotency, seating.seat_category, seating.seat_price_band | cache:idempotency, seating.seat_category, seating.seat_price_band | Create a seat category
CatalogueService | category | updateSeatCategory | PATCH | /seat-categories/{seatCategoryId} |  | SeatCategory | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATEGORY-1 | cache:idempotency, seating.seat_category, seating.seat_price_band | cache:idempotency, seating.seat_price_band | Rename, re-rank or re-price a seat category
CatalogueService | coupon | createCouponCampaign | POST | /coupon-campaigns | CreateCouponCampaignRequest | CouponCampaign | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, promotions.coupon_campaign | cache:idempotency, promotions.coupon_campaign, promotions.promotion_audit | Create a coupon campaign
CatalogueService | coupon | generateCouponCodes | POST | /coupon-campaigns/{campaignId}/codes |  | object | PRICE_CONFIGURE | setup | 1 |  | cache:idempotency, promotions.coupon_campaign | cache:idempotency, promotions.coupon_code, promotions.coupon_code_batch, promotions.promotion_audit | Generate codes in bulk
CatalogueService | coupon | getGuestCouponCode | GET | /guest-coupon-codes/{code} |  | GuestCouponCode |  | core | 1 | SVC-CATALOGUE-COUPON-4 |  |  | What a guest is told about a coupon code
CatalogueService | drafted | createChannelProfile | POST | /channel-profile | ChannelCreationProfileConfigurationInput | ChannelCreationProfileConfigurationView | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.sales_channel | Channel Creation & Profile Configuration
CatalogueService | drafted | createLiveDynamicPrice | POST | /live-dynamic-price | LiveDynamicPriceExecutionDeploymentMonitorInput | LiveDynamicPriceExecutionDeploymentMonitorView | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, catalogue.price, catalogue.price_ladder, catalogue.pricing_recommendation, catalogue.pricing_recommendation_decision, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, catalogue.price, catalogue.price_execution, catalogue.pricing_recommendation_decision, platform.outbox | Live Dynamic Price Execution & Deployment Monitor
CatalogueService | drafted | decidePricingRecommendation | POST | /recommendation-review-decision/{recommendationId}/decision | PricingRecommendationDecisionInput | PricingRecommendationDecision | AI_APPROVE | setup | 1 |  | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.pricing_recommendation, catalogue.pricing_recommendation_decision | cache:idempotency, catalogue.audit_entry, catalogue.pricing_recommendation, catalogue.pricing_recommendation_decision, platform.outbox | Record a human decision on an AI pricing recommendation
CatalogueService | drafted | publishChannelAvailability | PUT | /channel-availability | ChannelPublicationAvailabilityInput | ChannelPublicationAvailabilityView | PRODUCT_CONFIGURE | setup | 1 |  | access.entitlement, cache:idempotency, catalogue.product, catalogue.product_channel_assignment, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.product, catalogue.product_channel_assignment | Channel Publication & Availability
CatalogueService | drafted | publishChannelReadinessValidation | PUT | /channel-readiness-validation | ChannelPublicationReadinessAiValidationInput | ChannelPublicationReadinessAiValidationView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-33 | cache:idempotency, catalogue.channel_capacity, catalogue.channel_connection, catalogue.channel_envelope, catalogue.channel_sales_rule, catalogue.price_assignment, catalogue.price_list, catalogue.product, catalogue.product_channel_assignment, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.sales_channel | Channel Publication, Readiness & AI Validation
CatalogueService | drafted | setBookingVelocityTime | PUT | /booking-velocity-time | BookingVelocityTimeToEventRuleBuilderInput | BookingVelocityTimeToEventRuleBuilderView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-24 | cache:idempotency, catalogue.dynamic_pricing_strategy, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | Booking Velocity & Time-to-Event Rule Builder
CatalogueService | drafted | setChannelFeePayment | PUT | /channel-fee-payment | ChannelFeesPaymentFulfillmentConfigurationInput | ChannelFeesPaymentFulfillmentConfigurationView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-33 | cache:idempotency, catalogue.fee, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.sales_channel | Channel Fees, Payment & Fulfillment Configuration
CatalogueService | drafted | setChannelPricingCommercial | PUT | /channel-pricing-commercial | ChannelPricingCommercialProfileAssignmentInput | ChannelPricingCommercialProfileAssignmentView | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.price_assignment, catalogue.price_list, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.price_assignment | Channel Pricing & Commercial Profile Assignment
CatalogueService | drafted | setCodeDistributionManager | PUT | /code-distribution-manager | CodeDistributionAssignmentManagerInput | CodeDistributionAssignmentManagerView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-1 | cache:idempotency, promotions.code_assignment, promotions.coupon_code, promotions.coupon_code_batch | cache:idempotency, promotions.code_assignment, promotions.coupon_code, promotions.promotion_audit | Code Distribution & Assignment Manager
CatalogueService | drafted | setDemandOccupancyAvailability | PUT | /demand-occupancy-availability | DemandOccupancyAvailabilityRuleBuilderInput | DemandOccupancyAvailabilityRuleBuilderView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-24 | cache:idempotency, catalogue.dynamic_pricing_strategy, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | Demand, Occupancy & Availability Rule Builder
CatalogueService | drafted | setDynamicPricingStrategy | PUT | /dynamic-pricing-strategy-2 | DynamicPricingStrategyBuilderInput | DynamicPricingStrategyBuilderView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-24 | cache:idempotency, catalogue.dynamic_pricing_strategy, catalogue.price, catalogue.price_list | cache:idempotency, catalogue.audit_entry, catalogue.dynamic_pricing_strategy | Dynamic Pricing Strategy Builder
CatalogueService | drafted | setPricing | PUT | /pricing-2 | PricingSimulationStudioInput | PricingSimulationStudioView | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.channel_capacity, catalogue.demand_forecast, catalogue.dynamic_pricing_control, catalogue.performance, catalogue.price, catalogue.price_ladder, catalogue.pricing_recommendation, catalogue.pricing_simulation, orders.sales_order | cache:idempotency, catalogue.pricing_recommendation, catalogue.pricing_simulation | Pricing Simulation Studio
CatalogueService | drafted | setProductCatalogue | PUT | /product-catalogue | ProductCatalogueAssignmentInput | ProductCatalogueAssignmentView | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.price_list, catalogue.product, catalogue.product_channel_assignment, catalogue.sales_channel | cache:idempotency, catalogue.audit_entry, catalogue.product, catalogue.product_channel_assignment | Product & Catalogue Assignment
CatalogueService | drafted | setProductServicePrice | PUT | /product-service-price | ProductServicePriceAssignmentInput | ProductServicePriceAssignmentView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-45 | cache:idempotency, catalogue.price_assignment, catalogue.price_list, catalogue.product, catalogue.rate, catalogue.variant | cache:idempotency, catalogue.audit_entry, catalogue.price_assignment | Product & Service Price Assignment
CatalogueService | drafted | setRulePriorityConflict | PUT | /rule-priority-conflict | RulePriorityConflictInput | RulePriorityConflictView | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.price_resolution_policy, catalogue.pricing_test_case, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, catalogue.price_resolution_policy, catalogue.pricing_test_case, pricing.dynamic_price_rule | Reorder, validate, test or save the pricing rule priority
CatalogueService | entitlement | createEntitlementTemplate | POST | /entitlement-templates | EntitlementTemplate | EntitlementTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | cache:idempotency, catalogue.entitlement_template | cache:idempotency, catalogue.entitlement_template | Create an entitlement template
CatalogueService | entitlement | setEntitlementTemplateBlackoutDates | PUT | /entitlement-templates/{templateId}/blackout-dates |  | EntitlementTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | cache:idempotency, catalogue.entitlement_template | cache:idempotency, catalogue.audit_entry, catalogue.entitlement_template | Set the dates a product's entitlement does not admit
CatalogueService | evaluation | evaluatePromotions | POST | /promotions/evaluate | EvaluatePromotionsRequest | PromotionEvaluation | PRICE_VIEW | core | 1 | SVC-CATALOGUE-EVALUATION-1 | cache:idempotency, catalogue.price_list, promotions.coupon_code, promotions.promotion, promotions.promotion_rule | cache:idempotency, promotions.promotion_evaluation_trace | Evaluate promotions against a cart
CatalogueService | event | createEvent | POST | /events | CreateEventRequest | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-1 | cache:idempotency, catalogue.event | cache:idempotency, catalogue.event | Create an event
CatalogueService | event | createPerformances | POST | /events/{eventId}/performances | CreatePerformancesRequest | object | PERFORMANCE_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-1 | cache:idempotency, catalogue.performance | cache:idempotency, catalogue.performance | Create performances, singly or by schedule
CatalogueService | event | enterWaitingRoom | POST | /performances/{performanceId}/waiting-room/entries |  | WaitingRoomEntry |  | core | 1 | SVC-CATALOGUE-EVENT-1 | cache:idempotency | cache:idempotency | Join the on-sale waiting room for a performance
CatalogueService | event | getPerformance | GET | /performances/{performanceId} |  | Performance | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-1 | catalogue.performance |  | Read a performance
CatalogueService | event | getWaitingRoomPosition | GET | /performances/{performanceId}/waiting-room/entries/{waitingEntryId} |  | WaitingRoomEntry |  | core | 1 | SVC-CATALOGUE-EVENT-2 |  |  | Where a waiting guest is, and the admission token once admitted
CatalogueService | event | listEvents | GET | /events |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-2 | catalogue.event |  | List events
CatalogueService | event | listPerformances | GET | /events/{eventId}/performances |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-2 | catalogue.performance, catalogue.product, catalogue.product_category |  | List performances of an event
CatalogueService | event | updateEvent | PATCH | /events/{eventId} |  | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-2 | cache:idempotency, catalogue.event | cache:idempotency, catalogue.event | Amend an event
CatalogueService | event | updatePerformance | PATCH | /performances/{performanceId} |  | Performance | PERFORMANCE_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-3 | cache:idempotency, catalogue.performance | cache:idempotency, catalogue.performance | Amend a performance
CatalogueService | events | cloneEvent | POST | /events/{eventId}/clone | CloneEventRequest | object | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENTS-1 | cache:idempotency, catalogue.channel_capacity, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance, catalogue.price_assignment | cache:idempotency, catalogue.channel_capacity, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance, catalogue.price_assignment | Copy an event, choosing what comes with it
CatalogueService | events | setEventLifecycleState | POST | /events/{eventId}/lifecycle |  | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENTS-1 | cache:idempotency, catalogue.channel_capacity, catalogue.event, catalogue.event_capacity_profile, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance, catalogue.price, catalogue.price_list, catalogue.product, catalogue.variant | cache:idempotency, catalogue.event, catalogue.performance, platform.outbox | Draft, planned, on sale, live, closed, cancelled
CatalogueService | hold | createSeatHold | POST | /seat-holds | CreateSeatHoldRequest | SeatHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_reservation | cache:idempotency, platform.outbox, seating.seat_reservation | Hold specific seats
CatalogueService | hold | extendSeatHold | POST | /seat-holds/{holdId}/extend |  | SeatHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_reservation | cache:idempotency, seating.seat_reservation | Extend a hold
CatalogueService | hold | getSeatHold | GET | /seat-holds/{holdId} |  | SeatHold | ORDER_VIEW | core | 1 | SVC-CATALOGUE-HOLD-1 | seating.seat_reservation |  | Read a hold
CatalogueService | hold | relinquishSeatHold | DELETE | /seat-holds/{holdId} |  |  | ORDER_CREATE | core | 1 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_reservation | cache:idempotency, platform.outbox, seating.seat_reservation | Release a hold
CatalogueService | lease | convertInventoryHold | POST | /inventory-holds/{inventoryHoldId}/convert |  | InventoryHold |  | setup | 1 |  | cache:idempotency, catalogue.channel_capacity, catalogue.channel_envelope, catalogue.inventory_reservation | cache:idempotency, catalogue.channel_capacity, catalogue.channel_envelope, catalogue.inventory_reservation, platform.outbox, seating.seat_reservation, seating.seat_reservation_item | Turn a paid hold into sold units
CatalogueService | pricing | copyPriceList | POST | /price-lists/{priceListId}/copy |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Copy a price list, optionally with an adjustment
CatalogueService | pricing | createPriceList | POST | /price-lists | CreatePriceListRequest | PriceList | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Create a price list
CatalogueService | pricing | setPrices | PUT | /price-lists/{priceListId}/prices |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, cache:resolution, catalogue.price_list | Set prices in bulk
CatalogueService | pricing | updatePriceList | PATCH | /price-lists/{priceListId} |  | PriceList | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Amend a price list
CatalogueService | product | checkBookingEligibility | POST | /eligibility-checks | EligibilityCheckRequest | EligibilityCheckResult | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | cache:idempotency, catalogue.product, catalogue.product_eligibility_rule | cache:idempotency | Can this party take part
CatalogueService | product | getGroupPackageDefinition | GET | /products/{productId}/group-package |  | GroupPackageDefinition | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.group_package |  | A school-trip format or party package
CatalogueService | product | getProduct | GET | /products/{productId} |  | Product | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product, catalogue.product_media |  | Read a product
CatalogueService | product | getProductEligibilityRule | GET | /products/{productId}/eligibility-rule |  | ProductEligibilityRule | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product_eligibility_rule |  | Who may take part: age, height, supervision
CatalogueService | product | listAlternativeCodes | GET | /products/{productId}/alternative-codes |  | array of AlternativeCode | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.alternative_code |  | External identifiers for a product
CatalogueService | product | listGroupPackages | GET | /group-packages |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.group_package |  | The school-trip formats or party packages on offer
CatalogueService | product | listProductVariants | GET | /products/{productId}/variants |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.variant |  | List generated variants
CatalogueService | product | listProducts | GET | /products |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.product, catalogue.product_category, catalogue.product_eligibility_rule, catalogue.product_media, whitelabel.guided_choice_answer |  | List products
CatalogueService | product | resolveProductByCode | GET | /products/resolve |  | ProductVariant | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-3 | catalogue.variant |  | Resolve a partner code to a product
CatalogueService | product | setAlternativeCodes | PUT | /products/{productId}/alternative-codes |  | array of AlternativeCode | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | cache:idempotency, catalogue.alternative_code | cache:idempotency, catalogue.alternative_code | Set external identifiers
CatalogueService | product | setGroupPackageDefinition | PUT | /products/{productId}/group-package | GroupPackageDefinition | GroupPackageDefinition | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | cache:idempotency, catalogue.group_package | cache:idempotency, catalogue.group_package | Define a school-trip format or party package
CatalogueService | product | setProductChannelTexts | PUT | /products/{productId}/channel-texts | ProductChannelTexts | ProductChannelTexts | PRODUCT_CONFIGURE | setup | 1 | PRD-W1-LANGUAGES | cache:idempotency, catalogue.product_channel_text | cache:idempotency, catalogue.audit_entry, catalogue.product_channel_text, catalogue.product_version | Set the product's texts per sales channel
CatalogueService | product | setProductEligibilityRule | PUT | /products/{productId}/eligibility-rule | ProductEligibilityRule | ProductEligibilityRule | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | cache:idempotency, catalogue.product_eligibility_rule | cache:idempotency, catalogue.product_eligibility_rule | Set age, height and supervision limits
CatalogueService | product | setProductOwnerForms | PUT | /products/{productId}/owner-forms | ProductOwnerFormSet | ProductOwnerFormSet | PRODUCT_CONFIGURE | setup | 1 | PRD-W1-OWNER-FORMS | cache:idempotency, catalogue.product_owner_form | cache:idempotency, catalogue.audit_entry, catalogue.product_owner_form, catalogue.product_version | Link a product to the forms its sale asks
CatalogueService | product | setProductSalePermissionRules | PUT | /products/{productId}/sale-permission-rules | ProductSalePermissionRuleSet | ProductSalePermissionRuleSet | PRODUCT_CONFIGURE | setup | 1 | PRD-W1-SALE-PERMISSIONS | cache:idempotency, catalogue.product_sale_permission | cache:idempotency, catalogue.audit_entry, catalogue.product_sale_permission, catalogue.product_version | Set who can sell this product
CatalogueService | product | updateProduct | PATCH | /products/{productId} | UpdateProductRequest | Product | PRODUCT_CONFIGURE | core | 1 | SVC-CATALOGUE-PRODUCT-4 | cache:idempotency, catalogue.product, catalogue.product_channel_text, catalogue.product_media, catalogue.product_owner_form, catalogue.product_sale_permission, whitelabel.booking_flow | cache:idempotency, catalogue.product, catalogue.product_media, catalogue.product_version | Update a product
CatalogueService | product | updateProductVariant | PATCH | /products/{productId}/variants/{variantId} |  | ProductVariant | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-4 | cache:idempotency, catalogue.variant | cache:idempotency, catalogue.variant | Describe a variant
CatalogueService | promotion | analysePromotionConflicts | GET | /promotions/{promotionId}/conflicts |  | ConflictAnalysis | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Analyse stacking against live promotions
CatalogueService | promotion | createPromotion | POST | /promotions | CreatePromotionRequest | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-1 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Create a promotion
CatalogueService | promotion | getPromotion | GET | /promotions/{promotionId} |  | Promotion or GuestPromotion | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Read a promotion
CatalogueService | promotion | getPromotionUsage | GET | /promotions/{promotionId}/usage |  | PromotionUsage | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Redemption count and discount given
CatalogueService | promotion | listPromotions | GET | /promotions |  | object | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-2 | promotions.promotion |  | List promotions
CatalogueService | promotion | publishPromotion | POST | /promotions/{promotionId}/publish |  | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-2 | cache:idempotency, promotions.promotion, promotions.promotion_channel_publication | cache:idempotency, platform.outbox, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication | Publish a promotion
CatalogueService | promotion | updatePromotion | PATCH | /promotions/{promotionId} |  | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-2 | cache:idempotency, promotions.promotion, promotions.promotion_channel_publication | cache:idempotency, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication | Amend a promotion
CatalogueService | promotions | setPromotionVariants | PUT | /promotions/{promotionId}/variants |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTIONS-1 | cache:idempotency, promotions.promotion, promotions.promotion_variant | cache:idempotency, promotions.promotion, promotions.promotion_audit, promotions.promotion_variant | A/B test two versions against each other
CatalogueService | recommendation | recommendSeats | POST | /performances/{performanceId}/seat-recommendations | SeatRecommendationRequest | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-RECOMMENDATION-1 | cache:idempotency, catalogue.performance, seating.accessible, seating.recommendation_rule, seating.seat, seating.seat_block_item, seating.seat_category, seating.seat_price_band, seating.seat_reservation, seating.seat_reservation_item | cache:idempotency | Recommend seats for a party
CatalogueService | seatMap | editSeatMapStructure | PATCH | /seat-maps/{seatMapId}/structure |  | object | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-SEATMAP-1 | cache:idempotency, seating.seat_map | cache:idempotency, seating.seat, seating.seat_map, seating.section | Build a seat map by hand
CatalogueService | seating | setAccessibleSeating | PUT | /accessible-seating | AccessibleSeating | AccessibleSeating | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-SEATING-1 | cache:idempotency, seating.accessible | cache:idempotency, seating.accessible | Define accessible seats, routes and eligibility
CatalogueService | seating | setSeatRecommendationRules | PUT | /seat-recommendation-rules | SeatRecommendationRules | SeatRecommendationRules | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-SEATING-1 | cache:idempotency, seating.recommendation_rule | cache:idempotency, seating.recommendation_rule | Scoring for best seat, best value, closest, family and accessible
FnbService | bill | closeTableVisit | POST | /table-visits/{visitId}/close |  | object | ORDER_CREATE | core | 1 | SVC-FNB-BILL-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Settle and close a visit
FnbService | bill | getBill | GET | /table-visits/{visitId}/bill |  | Bill | ORDER_VIEW | core | 1 | SVC-FNB-BILL-1 | fnb.service_order, fnb.table_session, orders.payment |  | Bill for a visit
FnbService | bill | splitBill | POST | /table-visits/{visitId}/bill/split | SplitBillRequest | BillSplit | ORDER_MODIFY | core | 1 | SVC-FNB-BILL-1 | cache:idempotency, fnb.bill_split, fnb.sub_bill | cache:idempotency, fnb.bill_split, fnb.sub_bill | Split a bill
FnbService | fnb | attachModifierGroup | PUT | /menu-items/{menuItemId}/modifier-groups |  | MenuItem | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-1 | cache:idempotency, fnb.menu_item, fnb.modifier_group | cache:idempotency, cache:resolution, fnb.menu_item, fnb.menu_item_modifier | Give an item its choices
FnbService | fnb | buildProductionPlan | POST | /production-plans | ProductionPlan | ProductionPlan | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-1 | ai.suggestion, cache:idempotency, fnb.menu_item, fnb.menu_item_modifier, fnb.production_plan, fnb.production_plan_line, fnb.recipe | cache:idempotency, fnb.production_plan, fnb.production_plan_line | Turn a forecast into a prep list
FnbService | fnb | chaseStation | POST | /kitchen-stations/{stationId}/chase |  |  | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-1 | cache:idempotency, fnb.kitchen_station, fnb.kitchen_ticket | cache:idempotency, fnb.kitchen_exception | The pass asks a station where an item is
FnbService | fnb | createTableReservation | POST | /table-reservations | TableReservation | TableReservation |  | core | 1 | SVC-FNB-FNB-1 | cache:idempotency, fnb.dining_table, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Book a table in advance
FnbService | fnb | createTableReservationForGuest | POST | /outlets/{outletId}/table-reservations | TableReservation | TableReservation | ORDER_CREATE | core | 1 | SVC-FNB-FNB-2 | cache:idempotency, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Book a table for a guest (staff)
FnbService | fnb | escalateCorrectiveAction | POST | /food-safety/corrective-actions/{actionId}/escalate |  | CorrectiveAction | INCIDENT_MANAGE | setup | 1 | SVC-FNB-FNB-2 | cache:idempotency, fnb.corrective_action, identity.principal | cache:idempotency, fnb.corrective_action | Escalate a finding
FnbService | fnb | fireCourse | POST | /kitchen-tickets/{ticketId}/fire |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Send a held course to the pass
FnbService | fnb | getCourseRules | GET | /outlets/{outletId}/course-rules |  | CourseRules | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-2 | fnb.course_rule |  | How this outlet courses by default (read)
FnbService | fnb | getHaccpStatus | GET | /food-safety/status |  | object | INCIDENT_VIEW | core | 1 | SVC-FNB-FNB-3 | fnb.cold_chain_event, fnb.corrective_action, fnb.temperature_log |  | Where this venue stands, right now
FnbService | fnb | getKitchenSla | GET | /outlets/{outletId}/kitchen-sla |  | KitchenSla | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-3 | fnb.kitchen_sla |  | How long a ticket may sit before it is late (read)
FnbService | fnb | holdCourse | POST | /kitchen-tickets/{ticketId}/hold |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-3 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Stop a course going out
FnbService | fnb | joinRestaurantWaitlist | POST | /waitlist | RestaurantWaitlist | RestaurantWaitlist | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-3 | cache:idempotency, fnb.dining_table, fnb.waitlist_entry, platform.outlet | cache:idempotency, fnb.waitlist_entry | Add a party to an outlet's waitlist
FnbService | fnb | leaveRestaurantWaitlist | POST | /waitlist/{entryId}/leave |  | RestaurantWaitlist | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-4 | cache:idempotency, fnb.waitlist_entry | cache:idempotency, fnb.waitlist_entry | Take a party off an outlet's waitlist
FnbService | fnb | list86Events | GET | /outlets/{outletId}/86-events |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-4 | fnb.menu_item, fnb.sold_out_item |  | What came off the menu today, when, and for how long
FnbService | fnb | listMyTableReservations | GET | /me/table-reservations |  | object |  | core | 1 | SVC-FNB-FNB-4 | fnb.reservation_table, fnb.table_reservation, fnb.waitlist_entry |  | The guest's own table bookings and waitlist places
FnbService | fnb | listTableCombinations | GET | /outlets/{outletId}/table-combinations |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-4 | fnb.table_combination |  | The outlet's table combinations
FnbService | fnb | listTableReservations | GET | /table-reservations |  | object | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-5 | fnb.dining_table, fnb.reservation_table, fnb.table_reservation |  | Bookings for a service period
FnbService | fnb | logColdChain | POST | /food-safety/cold-chain | ColdChainEvent | ColdChainEvent | INCIDENT_REPORT | setup | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.cold_chain_event, inventory.goods_receipt | cache:idempotency, fnb.cold_chain_event, fnb.corrective_action | The temperature a delivery arrived at, and what was decided
FnbService | fnb | logKitchenException | POST | /kitchen-exceptions |  | KitchenException | INCIDENT_REPORT | core | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.kitchen_exception, fnb.kitchen_station | cache:idempotency, fnb.kitchen_exception | Something went wrong that is not a refire
FnbService | fnb | logTemperature | POST | /food-safety/temperature-logs | TemperatureLog | object | INCIDENT_REPORT | setup | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.corrective_action, fnb.temperature_log, platform.scope | cache:idempotency, fnb.corrective_action, fnb.temperature_log | Record a temperature check, in range or not
FnbService | fnb | markOrderCollected | POST | /orders/{orderId}/collected |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.kitchen_ticket, fnb.service_order | The guest took it
FnbService | fnb | notifyServer | POST | /table-visits/{visitId}/notify-server |  |  | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.table_visit, identity.principal | cache:idempotency, marketing.message_dispatch | The kitchen calls the server to the pass
FnbService | fnb | printOrderLabel | POST | /kitchen-tickets/{ticketId}/label |  | OrderLabel | ORDER_VIEW | core | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.kitchen_ticket | cache:idempotency | A label for the bag
FnbService | fnb | publishMenu | POST | /menus/{menuId}/publish |  | MenuVersion | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section, fnb.menu_version | cache:idempotency, cache:resolution, fnb.menu | Make the draft live, now or on a date
FnbService | fnb | rebalanceStationLoad | POST | /kitchen-stations/rebalance | StationRebalance | StationRebalance | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.kitchen_station | cache:idempotency, cache:resolution, fnb.kitchen_station | Move work between stations mid-service
FnbService | fnb | recallKitchenTicket | POST | /kitchen-tickets/{ticketId}/recall |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Bring back a ticket that was bumped by mistake
FnbService | fnb | refireItem | POST | /kitchen-tickets/{ticketId}/refire |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket_line, inventory.movement | Make it again
FnbService | fnb | releaseProductionPlan | POST | /production-plans/{planId}/release |  | ProductionPlan | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.production_plan, fnb.production_plan_line | cache:idempotency, fnb.production_plan, fnb.production_run | Make the plan real
FnbService | fnb | requestBill | POST | /table-visits/{visitId}/request-bill |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.table_visit | The party asked to pay
FnbService | fnb | rollbackMenu | POST | /menus/{menuId}/rollback |  | MenuVersion | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section, fnb.menu_version | cache:idempotency, cache:resolution, fnb.menu, fnb.menu_version | Put the previous version back
FnbService | fnb | scheduleMenuPublish | POST | /menus/{menuId}/schedule |  | MenuSchedule | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.menu, fnb.menu_schedule | cache:idempotency, cache:resolution, fnb.menu, fnb.menu_schedule | Publish it on a date, not now
FnbService | fnb | seatTableReservation | POST | /table-reservations/{reservationId}/seat |  | TableReservation | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.dining_table, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation, fnb.table_session, fnb.table_visit | The party arrived and has been sat down
FnbService | fnb | setCourseRules | PUT | /outlets/{outletId}/course-rules | CourseRules | CourseRules | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.course_rule | cache:idempotency, cache:resolution, fnb.course_rule | How this outlet courses by default
FnbService | fnb | setKitchenSla | PUT | /outlets/{outletId}/kitchen-sla | KitchenSla | KitchenSla | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.kitchen_sla | cache:idempotency, cache:resolution, fnb.kitchen_sla | How long a ticket may sit before it is late
FnbService | fnb | setSubstitutionRules | PUT | /substitution-rules |  | array of SubstitutionRule | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.substitution_rule | cache:idempotency, cache:resolution, fnb.substitution_rule | What may replace what
FnbService | fnb | setTableCombinations | PUT | /outlets/{outletId}/table-combinations |  | object | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.dining_table, fnb.table_combination | cache:idempotency, cache:resolution, fnb.dining_table, fnb.table_combination | Which tables can be pushed together, and to what capacity
FnbService | fnb | signCorrectiveAction | POST | /food-safety/corrective-actions/{actionId}/sign |  | CorrectiveAction | INCIDENT_MANAGE | setup | 1 | SVC-FNB-FNB-10 | cache:idempotency, fnb.corrective_action, identity.principal | cache:idempotency, fnb.corrective_action | Say what was done, and put a name to it
FnbService | fnb | transferTableVisit | POST | /table-visits/{visitId}/transfer |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-10 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit, identity.principal | cache:idempotency, fnb.table_visit | Move a check to another server
FnbService | fnb | updateTableReservation | PATCH | /table-reservations/{reservationId} | UpdateTableReservationRequest | TableReservation |  | core | 1 | SVC-FNB-FNB-10 | cache:idempotency, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Change or cancel a booking
FnbService | guestOrdering | claimLocationSession | POST | /location-sessions |  | LocationSession |  | core | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_location, fnb.dining_table, fnb.location_session, fnb.table_visit | cache:idempotency, fnb.location_session, fnb.table_visit | Tell the platform where the guest is
FnbService | guestOrdering | createDeliveryLocation | POST | /delivery-locations |  | DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_location, fnb.dining_table, platform.outlet | cache:idempotency, fnb.delivery_location, fnb.delivery_location_outlet | Add a place food can be delivered to
FnbService | guestOrdering | createGuestFnbOrder | POST | /guest-orders | CreateGuestOrderRequest | GuestOrderResult |  | core | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_policy, fnb.location_session, fnb.menu_item, fnb.menu_item_modifier, inventory.movement | cache:idempotency, fnb.kitchen_ticket, fnb.order_fulfilment, fnb.service_order, platform.outbox | A guest orders food
FnbService | guestOrdering | getFnbDeliveryPolicy | GET | /fnb-delivery-policy |  | FnbDeliveryPolicy | PRODUCT_VIEW | core | 1 | SVC-FNB-GUESTORDERING-1 | fnb.delivery_policy |  | How an outlet does takeaway and delivery
FnbService | guestOrdering | getGuestBill | GET | /table-sessions/{sessionId}/bill |  | Bill |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.service_order, fnb.table_session, orders.payment |  | The bill for the guest's table
FnbService | guestOrdering | getGuestMenu | GET | /outlets/{outletId}/guest-menu |  | GuestMenu |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.modifier_group, fnb.modifier_option |  | The menu a guest sees
FnbService | guestOrdering | getGuestOrderStatus | GET | /guest-orders/{orderId} |  | GuestOrderStatus |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.delivery_location, fnb.kitchen_ticket, fnb.service_order |  | Track an order
FnbService | guestOrdering | listBookableOutlets | GET | /venues/{venueId}/bookable-outlets |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-2 |  |  | The restaurants a guest can book a table at
FnbService | guestOrdering | listDeliveryLocations | GET | /venues/{venueId}/delivery-locations |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-3 | fnb.delivery_location, fnb.delivery_location_outlet |  | Where an order can be delivered
FnbService | guestOrdering | listDiningOutlets | GET | /venues/{venueId}/dining |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-3 | fnb.menu, fnb.service_order, platform.outlet |  | Where a guest can eat, right now
FnbService | guestOrdering | listFulfilmentSlots | GET | /outlets/{outletId}/fulfilment-slots |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-3 | fnb.delivery_policy, platform.outlet |  | Collection times or delivery windows still open
FnbService | guestOrdering | recordOrderHandover | POST | /guest-orders/{orderId}/delivery |  | GuestOrderStatus | ORDER_MODIFY | core | 1 | SVC-FNB-GUESTORDERING-3 | cache:idempotency, fnb.delivery_location, fnb.delivery_location_outlet, fnb.service_order | cache:idempotency, fnb.service_order | Record that an order reached the guest
FnbService | guestOrdering | setDeliveryLocationOutletMapping | PUT | /venues/{venueId}/delivery-location-outlets |  | array of DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_location, platform.outlet | cache:idempotency, cache:resolution, fnb.delivery_location_outlet | Set which outlets deliver to which delivery locations
FnbService | guestOrdering | setFnbDeliveryPolicy | PUT | /fnb-delivery-policy | FnbDeliveryPolicy | FnbDeliveryPolicy | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_policy | cache:idempotency, fnb.delivery_policy | Set takeaway and delivery rules
FnbService | guestOrdering | updateDeliveryLocation | PATCH | /delivery-locations/{locationId} |  | DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_location | cache:idempotency, fnb.delivery_location | Rename a delivery location, or take it out of service
FnbService | kitchen | listKitchenStations | GET | /kitchen/stations |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-KITCHEN-1 | fnb.kitchen_station |  | List preparation stations and their routing
FnbService | kitchen | listKitchenTickets | GET | /kitchen/tickets |  | object | ORDER_VIEW | core | 1 | SVC-FNB-KITCHEN-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line |  | Kitchen ticket queue
FnbService | kitchen | prioritiseKitchenTicket | POST | /kitchen/tickets/{ticketId}/prioritise |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-KITCHEN-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Move a ticket up the queue
FnbService | kitchen | setKitchenTicketStatus | PUT | /kitchen/tickets/{ticketId}/status |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-KITCHEN-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket, platform.outbox | Advance a kitchen ticket
FnbService | menu | createMenu | POST | /menus | CreateMenuRequest | Menu | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Create a menu
FnbService | menu | setItemAvailability | PUT | /menu-items/{itemId}/availability |  | MenuItem | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu_item | cache:idempotency, fnb.menu_item | Mark an item available or eighty-sixed
FnbService | menu | setMenuItemDailyCount | PUT | /menu-items/{itemId}/daily-count |  | MenuItem | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, fnb.menu_item | cache:idempotency, fnb.menu_item, fnb.sold_out_item | Set today's count for a dish
FnbService | menu | setMenuSections | PUT | /menus/{menuId}/sections |  | Menu | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Set menu sections and their item ordering
FnbService | menu | updateMenu | PATCH | /menus/{menuId} |  | Menu | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Amend a menu
FnbService | modifier | createModifierGroup | POST | /modifier-groups | ModifierGroup | ModifierGroup | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MODIFIER-1 | cache:idempotency, fnb.modifier_group, fnb.modifier_option | cache:idempotency, fnb.modifier_group, fnb.modifier_option | Create a modifier group
FnbService | order | createFnbOrder | POST | /fnb-orders | CreateFnbOrderRequest | FnbOrder | ORDER_CREATE | core | 1 | SVC-FNB-ORDER-1 | cache:idempotency, fnb.kitchen_station, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.menu_item, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, platform.idempotency_record, platform.outbox | Place an F&B order
FnbService | order | getFnbOrder | GET | /fnb-orders/{orderId} |  | FnbOrder | ORDER_VIEW | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line |  | Read an F&B order
FnbService | order | listFnbOrders | GET | /fnb-orders |  | object | ORDER_VIEW | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line |  | List F&B orders
FnbService | production | setRecipe | PUT | /recipes/{recipeId} | Recipe | Recipe | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-PRODUCTION-1 | cache:idempotency, fnb.menu_item, fnb.modifier_group, fnb.recipe, fnb.recipe_ingredient, fnb.substitution_rule, inventory.inventory_item | cache:idempotency, fnb.allergen_verdict, fnb.menu_item, fnb.recipe, fnb.recipe_ingredient | Define a recipe for a menu item
FnbService | service | acceptFnbOrder | POST | /fnb-orders/{orderId}/accept |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-SERVICE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, platform.outbox | The outlet takes the order
FnbService | service | cancelFnbOrder | POST | /fnb-orders/{orderId}/cancel |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-SERVICE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.service_order | Cancel an order
FnbService | table | clearTable | POST | /tables/{tableId}/clear |  | TableState | ORDER_MODIFY | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.dining_table, fnb.table_visit | cache:idempotency, fnb.dining_table, fnb.table_visit | Mark a table cleared and free
FnbService | table | getTableMap | GET | /outlets/{outletId}/tables |  | TableMap | ORDER_VIEW | core | 1 | SVC-FNB-TABLE-1 | fnb.dining_table, fnb.table_visit |  | Table map with live state
FnbService | table | getTableVisit | GET | /table-visits/{visitId} |  | TableVisit | ORDER_VIEW | core | 1 | SVC-FNB-TABLE-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit |  | Read a visit with all its orders
FnbService | table | openTableVisit | POST | /table-visits | OpenTableVisitRequest | TableVisit | ORDER_CREATE | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Seat a party and open a visit
FnbService | table | setTableLayout | PUT | /outlets/{outletId}/tables |  | TableMap | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-TABLE-2 | cache:idempotency, fnb.dining_table, fnb.table_visit | cache:idempotency, fnb.dining_table | Configure the table layout
FnbService | table | updateTableVisit | PATCH | /table-visits/{visitId} |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-TABLE-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Amend covers, move table, or reassign server
IdentityService | administration | createRole | POST | /roles |  | Role | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-1 | cache:idempotency, identity.capability_template, identity.role, identity.role_permission, identity.segregation_rule | cache:idempotency, cache:resolution, identity.role, identity.role_permission, platform.audit_record | Create a role
IdentityService | administration | listOwnPlatformStaffGrants | GET | /platform-staff-grants/mine |  | object | PLATFORM_TENANT_ACCESS | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.platform_staff_grant |  | The calling platform operator's own grants into this tenant
IdentityService | administration | listPrincipals | GET | /principals |  | object | USER_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.delegated_access, identity.principal, identity.role, platform.scope |  | List principals
IdentityService | administration | listRoles | GET | /roles |  | object | ROLE_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.delegated_access, identity.role, identity.role_permission |  | List roles
IdentityService | administration | openPlatformStaffGrant | POST | /platform-staff-grants |  | PlatformStaffGrant | PLATFORM_TENANT_ACCESS | core | 1 | SVC-IDENTITY-ADMINISTRATION-2 | cache:idempotency, identity.platform_staff_grant | cache:idempotency, identity.platform_staff_grant | A platform operator opens a time-boxed grant into this tenant
IdentityService | administration | setCapabilityTemplate | PUT | /capability-templates/{capabilityTemplateId} | CapabilityTemplate | CapabilityTemplate | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-2 | cache:idempotency, identity.capability_template | cache:idempotency, identity.capability_template | Save a tick-set under a name
IdentityService | administration | updatePrincipal | PATCH | /principals/{principalId} |  | Principal | USER_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-2 | cache:idempotency, identity.delegated_access, identity.principal, identity.role | cache:idempotency, identity.principal, identity.refresh_token, identity.session | Update or deactivate a principal
IdentityService | administration | updateRole | PATCH | /roles/{roleId} |  | Role | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-2 | cache:idempotency, identity.role | cache:idempotency, identity.role | Rename a role or change its description
IdentityService | guestAuth | deleteGuestAccount | DELETE | /auth/guest/account |  | object |  | core | 1 |  | cache:idempotency, identity.subject_holding, pii.subject | approvals.request, cache:idempotency, identity.subject_data_export, pii.subject, platform.outbox | Self-service account deletion
IdentityService | guestAuth | getGuestSession | GET | /auth/guest/session |  | GuestSessionView |  | core | 1 |  | identity.guest_session, identity.mfa_method, pii.subject |  | Read the current guest session
IdentityService | guestAuth | guestLogout | DELETE | /auth/guest/session |  |  |  | core | 1 |  | cache:idempotency, identity.guest_session | cache:idempotency, identity.guest_session | End a guest session
IdentityService | guestAuth | guestPasswordLogin | POST | /auth/guest/password |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.guest_credential, identity.mfa_method, identity.password_policy, pii.subject_contact | cache:idempotency, identity.guest_credential, identity.guest_session, platform.outbox | Sign in with an email or mobile and a password
IdentityService | guestAuth | guestSocialLogin | POST | /auth/guest/social |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.mfa_method, pii.subject_contact, pii.subject_identity | cache:idempotency, identity.guest_session, pii.subject, pii.subject_identity, platform.outbox | Sign in with Apple or Google
IdentityService | guestAuth | guestUaePassLogin | POST | /auth/guest/uae-pass |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.mfa_method, identity.redirect_host, pii.subject_contact, pii.subject_identity | cache:idempotency, identity.guest_session, pii.subject, pii.subject_document, pii.subject_identity, platform.outbox | Sign in with a national identity provider
IdentityService | guestAuth | linkGuestCheckout | POST | /auth/guest/link-checkout |  | object |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.subject_holding | cache:idempotency, platform.outbox | Attach a guest checkout to an account
IdentityService | guestAuth | registerGuest | POST | /auth/guest/register | RegisterGuestRequest | GuestSession |  | core | 1 |  | cache:idempotency, identity.mfa_method, pii.subject | cache:idempotency, identity.guest_credential, identity.guest_session, identity.otp_challenge, pii.subject, pii.subject_contact, platform.outbox | Create a guest account
IdentityService | guestAuth | requestGuestOtp | POST | /auth/guest/otp |  | object |  | core | 1 |  | cache:idempotency, identity.otp_challenge, pii.subject_contact | cache:idempotency, identity.otp_challenge, platform.outbox | Request a one-time code
IdentityService | guestAuth | verifyGuestOtp | POST | /auth/guest/otp/verify |  | GuestSession |  | core | 1 |  | cache:idempotency, identity.mfa_method, identity.otp_challenge, pii.subject_contact | cache:idempotency, identity.guest_session, identity.otp_challenge, pii.subject_contact, platform.outbox | Verify a one-time code and issue a session
IdentityService | identity | changeOwnCredential | POST | /auth/credential | ChangeCredentialRequest |  |  | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.password_policy, identity.principal, identity.principal_credential, identity.principal_credential_history | cache:idempotency, identity.principal, identity.principal_credential, identity.principal_credential_history, identity.session | Change the caller's own password or PIN
IdentityService | identity | exportSubjectData | POST | /guests/{subjectId}/data-export |  | object | GUEST_VIEW_PII | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.subject_holding, marketing.consent_record, marketing.form_submission, marketing.guest_document, marketing.guest_profile, pii.subject | approvals.request, cache:idempotency, identity.subject_data_export, platform.outbox | Everything the platform holds about one guest
IdentityService | identity | forceLogout | POST | /auth/sessions/{sessionId}/force-logout |  |  | SESSION_FORCE_LOGOUT | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.delegated_access, identity.password_policy, identity.principal, identity.principal_credential, identity.role_permission, identity.session, platform.workstation | cache:idempotency, identity.principal_credential, identity.session | Supervisor termination of an abandoned session
IdentityService | identity | getCurrentSession | GET | /auth/session |  | Session |  | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:resolution, identity.delegated_access, identity.password_policy, identity.principal, identity.role, identity.role_permission, identity.session | cache:resolution | Current session and effective permissions
IdentityService | identity | getSubjectDataExport | GET | /guests/{subjectId}/data-export/{requestId} |  | SubjectDataExportStatus | GUEST_VIEW_PII | core | 1 | SVC-IDENTITY-IDENTITY-11 | identity.subject_data_export |  | Where a guest's data export has got to, and its download link
IdentityService | identity | grantDelegation | POST | /guests/{subjectId}/delegations |  | DelegatedAccess | GUEST_MANAGE | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.delegated_access, pii.subject | cache:idempotency, identity.delegated_access | Let one guest act for another
IdentityService | identity | listDelegations | GET | /guests/{subjectId}/delegations |  | object | GUEST_VIEW | core | 1 | SVC-IDENTITY-IDENTITY-2 | identity.delegated_access, pii.subject |  | Who may act for this guest, and for whom they may act
IdentityService | identity | login | POST | /auth/login | LoginRequest | LoginResponse |  | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.delegated_access, identity.mfa_method, identity.password_policy, identity.principal, identity.principal_credential, identity.role, identity.role_permission | cache:idempotency, identity.principal_credential, identity.refresh_token, identity.session, platform.outbox | Authenticate and open a session
IdentityService | identity | refreshToken | POST | /auth/refresh |  | TokenPair |  | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.refresh_token, identity.session | cache:idempotency, identity.refresh_token, identity.session | Rotate the access token
IdentityService | identity | selectRole | POST | /auth/select-role |  | Session |  | core | 1 |  | cache:idempotency, identity.delegated_access, identity.password_policy, identity.role, identity.role_permission, identity.session | cache:idempotency, identity.session | Choose a role for a multi-role session
IdentityService | identity | setPasswordPolicy | PUT | /password-policy | PasswordPolicy | PasswordPolicy | TENANT_CONFIGURE | setup | 1 |  | cache:idempotency, identity.password_policy | cache:idempotency, identity.password_policy | Length, breach check, lockout and step-up
IdentityService | identity | setSegregationRules | PUT | /segregation-rules |  | array of SegregationRule | ROLE_MANAGE | setup | 1 |  | cache:idempotency, identity.delegated_access, identity.segregation_rule | cache:idempotency, identity.segregation_rule | Which permissions may not be held together
IdentityService | identity | verifyGuestEmail | POST | /auth/guest/verify-email |  | object |  | core | 1 | SVC-IDENTITY-IDENTITY-4 | cache:idempotency, identity.otp_challenge, pii.subject, pii.subject_contact | cache:idempotency, identity.otp_challenge, marketing.message_dispatch, pii.subject | Send a verification link, or consume one
IdentityService | mfa | createMfaChallenge | POST | /auth/mfa/challenge |  | object |  | core | 1 |  | cache:idempotency, identity.mfa_challenge, identity.mfa_method, identity.session | cache:idempotency, identity.mfa_challenge | Second factor at staff sign-in, and step-up for a sensitive action
IdentityService | mfa | enrolMfaMethod | POST | /auth/mfa/methods |  | MfaEnrolment |  | core | 1 |  | cache:idempotency, identity.mfa_recovery_code, identity.principal | cache:idempotency, identity.mfa_method, identity.mfa_recovery_code | Enrol an MFA method
IdentityService | mfa | listMfaMethods | GET | /auth/mfa/methods |  | array of MfaMethod |  | core | 1 |  | identity.mfa_method |  | Enrolled MFA methods
IdentityService | mfa | verifyMfaChallenge | POST | /auth/mfa/challenge/{challengeId}/verify |  | object |  | core | 1 | SVC-IDENTITY-MFA-2 | cache:idempotency, identity.mfa_challenge, identity.mfa_method, identity.mfa_recovery_code, identity.password_policy, identity.session | cache:idempotency, identity.mfa_challenge, identity.mfa_recovery_code, identity.session, platform.outbox | Complete a sign-in or step-up challenge
IdentityService | mfa | verifyMfaEnrolment | POST | /auth/mfa/methods/{methodId} |  | MfaMethod |  | core | 1 | SVC-IDENTITY-MFA-2 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_method | Complete enrolment
IdentityService | session | listActiveSessions | GET | /auth/sessions |  | object | SESSION_FORCE_LOGOUT | core | 1 | SVC-IDENTITY-SESSION-1 | identity.principal, identity.role, identity.session |  | List active sessions
InventoryService | inventory | bulkUpdateProducts | POST | /products/bulk |  | object | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.price, catalogue.product, inventory.inventory_item | cache:idempotency, cache:resolution, catalogue.price, catalogue.product, inventory.inventory_item | Change many products at once, with a preview
InventoryService | inventory | listSerialisedItems | GET | /serialised-items |  | object | PRODUCT_VIEW | core | 1 | SVC-INVENTORY-INVENTORY-1 | inventory.inventory_item, inventory.serialised_item, inventory.stock_batch |  | Where each individual item is
InventoryService | item | createInventoryItem | POST | /inventory-items | CreateInventoryItemRequest | InventoryItem | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.inventory_item | cache:idempotency, inventory.inventory_item | Create an inventory item
InventoryService | item | setInventoryKitDefinition | PUT | /inventory-items/{itemId}/kit-definition | InventoryKitDefinition | InventoryKitDefinition | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.inventory_item, inventory.kit_component, inventory.movement | cache:idempotency, cache:resolution, inventory.kit_component | Make an item a kit of other stocked items
InventoryService | item | updateInventoryItem | PATCH | /inventory-items/{itemId} |  | InventoryItem | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.inventory_item | cache:idempotency, inventory.inventory_item | Amend an item
InventoryService | receipt | createGoodsReceipt | POST | /goods-receipts | CreateGoodsReceiptRequest | GoodsReceipt | PROCUREMENT_RECEIVE | setup | 1 | SVC-INVENTORY-RECEIPT-1 | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line, platform.outbox | Receive goods against a purchase order
InventoryService | receipt | rejectReceivedGoods | POST | /goods-receipts/{receiptId}/reject |  | GoodsReceipt | PROCUREMENT_RECEIVE | setup | 1 | SVC-INVENTORY-RECEIPT-1 | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | Reject received goods
LedgerService | finance | ingestFxRates | POST | /fx-rates/ingest |  | object | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-FINANCE-1 | cache:idempotency, ledger.fx_rate, platform.region_settings | cache:idempotency, ledger.fx_rate | Pull rates from the configured provider
LedgerService | finance | setFxProvider | PUT | /fx-rates/providers |  | array of FxProviderAssignment | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-FINANCE-1 | cache:idempotency, ledger.fx_provider_assignment, platform.region_settings | cache:idempotency, ledger.fx_provider_assignment, platform.region_settings | Which provider serves which purpose
LedgerService | fiscal | createLegalEntity | POST | /legal-entities | LegalEntity | LegalEntity | ACCOUNT_CONFIGURE | setup | 1 | SVC-LEDGER-FISCAL-1 | cache:idempotency, ledger.legal_entity | cache:idempotency, ledger.legal_entity | Create a legal entity
LedgerService | ledger | listFxRates | GET | /fx-rates |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-LEDGER-1 | ledger.fx_rate |  | The rates in force
LedgerService | ledger | setFxRate | PUT | /fx-rates/{rateId} | FxRate | FxRate | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-LEDGER-1 | cache:idempotency, ledger.fx_rate | cache:idempotency, ledger.fx_rate | Set a rate
LedgerService | tax | createTaxCode | POST | /tax-codes | CreateTaxCodeRequest | TaxCode | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-1 | cache:idempotency, ledger.tax_code | cache:idempotency, ledger.tax_code | Create a tax code
LedgerService | tax | getTaxDocumentRendition | GET | /tax-documents/{documentId}/rendition |  | FinTaxDocumentRendition | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-1 | ledger.credit_memo, ledger.tax_invoice |  | The PDF of a tax invoice or credit memo, in a language
LedgerService | tax | getTaxInvoice | GET | /tax-invoices/{invoiceId} |  | FinTaxInvoice | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-1 | ledger.credit_memo, ledger.einvoice_transmission, ledger.tax_invoice, ledger.tax_invoice_line |  | One tax invoice, with its lines, VAT per rate and credit memos
LedgerService | tax | issueCreditMemo | POST | /tax-invoices/{invoiceId}/credit-memos | FinIssueCreditMemoRequest | FinCreditMemo | LEDGER_POST | core | 1 | SVC-LEDGER-TAX-1 | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, orders.refund | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, platform.audit_record, platform.outbox | Credit all or part of a tax invoice
LedgerService | tax | issueTaxInvoice | POST | /tax-invoices | FinIssueTaxInvoiceRequest | FinTaxInvoice | LEDGER_POST | core | 1 | SVC-LEDGER-TAX-2 | cache:idempotency, ledger.legal_entity, ledger.tax_code, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, orders.order_line, orders.payment, orders.sales_order | cache:idempotency, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, platform.audit_record, platform.outbox | Issue a tax invoice for one or more paid orders
LedgerService | tax | listCreditMemos | GET | /credit-memos |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-2 | ledger.credit_memo, ledger.credit_memo_line |  | Credit memos issued, newest first
LedgerService | tax | listTaxInvoices | GET | /tax-invoices |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-2 | ledger.tax_invoice, ledger.tax_invoice_line |  | Tax invoices issued, newest first
LedgerService | tax | setEInvoicingProvider | PUT | /e-invoicing/providers/{providerId} | FinEInvoicingProvider | FinEInvoicingProvider | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-2 | cache:idempotency, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.legal_entity | cache:idempotency, cache:resolution, ledger.einvoicing_provider, platform.audit_record | Connect a legal entity to its accredited e-invoicing service provider
LedgerService | tax | transmitEInvoices | POST | /e-invoicing/transmissions |  | object | LEDGER_POST | setup | 1 | SVC-LEDGER-TAX-3 | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.tax_invoice, ledger.tax_invoice_line | cache:idempotency, ledger.einvoice_transmission, platform.outbox | Send issued tax documents to the e-invoicing provider
LedgerService | tax | updateTaxCode | PATCH | /tax-codes/{taxCodeId} |  | TaxCode | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-3 | cache:idempotency, ledger.tax_code | cache:idempotency, ledger.tax_code | Amend a tax code
MarketingService | campaign | createCampaign | POST | /campaigns | CreateCampaignRequest | Campaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.segment_criterion | Create a campaign
MarketingService | campaign | launchCampaign | POST | /campaigns/{campaignId}/launch |  | LaunchResult | MARKETING_SEND | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.attribution_touch, marketing.campaign, marketing.campaign_variant | cache:idempotency, marketing.campaign, marketing.message_dispatch | Launch or schedule a campaign
MarketingService | campaign | stopCampaign | POST | /campaigns/{campaignId}/stop |  | Campaign | MARKETING_SEND | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.segment_criterion | Stop a campaign mid-send
MarketingService | campaign | updateCampaign | PATCH | /campaigns/{campaignId} |  | Campaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.segment_criterion | Amend, pause or resume a campaign
MarketingService | consent | claimDeviceConsent | POST | /guests/{subjectId}/consents/claim-device | ClaimDeviceConsentRequest | ConsentState |  | core | 1 |  | cache:idempotency, marketing.consent_record, marketing.device_consent, marketing.device_consent_category, marketing.guest_profile, marketing.tracking_technology | cache:idempotency, marketing.consent_propagation, marketing.consent_record, marketing.device_consent, platform.outbox | Attach a browser's cookie decision to the guest who turned out to own it
MarketingService | consent | createConsentQuestion | POST | /consent-questions | CreateConsentQuestionRequest | ConsentQuestion | GUEST_MANAGE | core | 1 |  | cache:idempotency, marketing.consent_question, marketing.consent_question_version | cache:idempotency, marketing.consent_question, marketing.consent_question_version | Define a consent question
MarketingService | consent | getCookieConsentRuntime | GET | /storefront/cookie-consent |  | CookieConsentRuntime |  | core | 1 |  | marketing.cookie_banner_design, marketing.device_consent, marketing.device_consent_category, marketing.tracking_technology |  | What the page must show and what it may load
MarketingService | consent | getGuestConsents | GET | /guests/{subjectId}/consents |  | ConsentState | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.consent_purpose, marketing.consent_record, pii.subject |  | Read a guest's consent state
MarketingService | consent | listConsentAnswers | GET | /consent-answers |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.booking_consent_record |  | The consent records given at booking
MarketingService | consent | listConsentPurposes | GET | /consent-purposes |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | cache:resolution, marketing.consent_purpose, marketing.consent_purpose_channel | cache:resolution | Configured consent purposes
MarketingService | consent | listConsentQuestions | GET | /consent-questions |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.consent_question, marketing.consent_question_version |  | The consent questions a venue asks at booking
MarketingService | consent | recordConsent | POST | /guests/{subjectId}/consents | RecordConsentRequest | ConsentState | GUEST_MANAGE | core | 1 |  | cache:idempotency, marketing.consent_record, marketing.guest_profile | cache:idempotency, marketing.consent_propagation, marketing.consent_record, marketing.guest_profile | Record a consent decision
MarketingService | consent | recordConsentAnswers | POST | /consent-answers | RecordConsentAnswersRequest | object | ORDER_CREATE | core | 1 |  | cache:idempotency, marketing.booking_consent_record | cache:idempotency, marketing.booking_consent_record | Answer the consent questions a booking asks
MarketingService | consent | setConsentPurposes | PUT | /consent-purposes |  | array of ConsentPurposeConfig | GUEST_MANAGE | core | 1 | SVC-MARKETING-CONSENT-4 | cache:idempotency, marketing.consent_purpose, marketing.consent_purpose_channel | cache:idempotency, cache:resolution, marketing.consent_purpose, marketing.consent_purpose_channel | Configure consent purposes
MarketingService | consent | setCookieBannerDesign | PUT | /cookie-banner-preference/{bannerDesignId} | CookieBannerPreferenceCenterDesignerView | CookieBannerPreferenceCenterDesignerView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | cache:idempotency, marketing.cookie_banner_design | cache:idempotency, marketing.cookie_banner_design | Save a cookie banner design as a new version
MarketingService | consent | setDynamicFieldQuestion | PUT | /dynamic-field-question/{formId}/{key} | DynamicFieldsQuestionsConditionalLogicView | DynamicFieldsQuestionsConditionalLogicView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | cache:idempotency, marketing.form_definition_field, marketing.waiver_field_rule | cache:idempotency, marketing.form_definition_field, marketing.waiver_field_rule | Create, change or remove one field of a draft waiver version
MarketingService | consent | setTrackingTechnology | PUT | /cookie-tracking-digital/{technologyId} | CookieTrackingDigitalTechnologyRegistryView | CookieTrackingDigitalTechnologyRegistryView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | cache:idempotency, marketing.tracking_technology | cache:idempotency, marketing.tracking_technology | Add, classify or retire a tracking technology
MarketingService | consent | updateConsentQuestion | PATCH | /consent-questions/{questionId} | UpdateConsentQuestionRequest | ConsentQuestion | GUEST_MANAGE | core | 1 | SVC-MARKETING-CONSENT-5 | cache:idempotency, marketing.consent_question, marketing.consent_question_version | cache:idempotency, marketing.consent_question, marketing.consent_question_version | Reword, re-scope or retire a consent question
MarketingService | feedback | submitReview | POST | /reviews | SubmitReviewRequest | Review |  | core | 1 | SVC-MARKETING-FEEDBACK-1 | cache:idempotency, marketing.case, marketing.review | cache:idempotency, marketing.case, marketing.review | Submit a review
MarketingService | guest | addToWishlist | POST | /guests/{subjectId}/wishlist |  | Wishlist |  | core | 1 | SVC-MARKETING-GUEST-1 | cache:idempotency, catalogue.performance, catalogue.price, catalogue.price_assignment, catalogue.price_list, catalogue.product, catalogue.product_media, catalogue.variant, marketing.wishlist_item | cache:idempotency, marketing.wishlist_item | Save an item
MarketingService | guest | getWishlist | GET | /guests/{subjectId}/wishlist |  | Wishlist |  | core | 1 | SVC-MARKETING-GUEST-1 | catalogue.performance, catalogue.price, catalogue.price_assignment, catalogue.price_list, catalogue.product, catalogue.product_media, catalogue.variant, marketing.wishlist_item |  | Read a guest's saved items
MarketingService | guest | listGuestDevices | GET | /guests/{subjectId}/devices |  | object |  | core | 1 | SVC-MARKETING-GUEST-1 | marketing.guest_device |  | A guest's registered devices
MarketingService | guest | registerGuestDevice | POST | /guests/{subjectId}/devices |  | GuestDevice |  | core | 1 | SVC-MARKETING-GUEST-1 | cache:idempotency, marketing.guest_device | cache:idempotency, marketing.guest_device | Register a device for push
MarketingService | guest | removeFromWishlist | DELETE | /guests/{subjectId}/wishlist/{itemId} |  |  |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.wishlist_item | cache:idempotency, marketing.wishlist_item | Remove a saved item
MarketingService | guest | revokeGuestDevice | DELETE | /guests/{subjectId}/devices/{deviceId} |  |  |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.guest_device | cache:idempotency, identity.guest_session, marketing.guest_device | Revoke a device registration
MarketingService | guest | searchGuests | GET | /guests |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-GUEST-2 | marketing.consent_record, marketing.guest_profile |  | Search guest profiles
MarketingService | loyalty | awardBadge | POST | /customers/{customerId}/badges | MarketingCustomerBadge | MarketingCustomerBadge | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-1 | cache:idempotency, marketing.customer_badge | cache:idempotency, marketing.customer_badge | Award a badge
MarketingService | loyalty | createLoyaltyProgramme | POST | /loyalty/programmes | LoyaltyProgramme | LoyaltyProgramme | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-1 | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | Create a loyalty programme
MarketingService | loyalty | getGuestLoyalty | GET | /guests/{subjectId}/loyalty |  | LoyaltyPosition | GUEST_VIEW | core | 1 | SVC-MARKETING-LOYALTY-1 | marketing.loyalty_position |  | A guest's loyalty position
MarketingService | loyalty | listCustomerBadges | GET | /customers/{customerId}/badges |  | object | MARKETING_VIEW | core | 1 | SVC-MARKETING-LOYALTY-1 | marketing.customer_badge |  | Badges a guest holds
MarketingService | loyalty | listLeaderboard | GET | /loyalty/leaderboard |  | object |  | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.loyalty_position |  | Standings, by nickname
MarketingService | loyalty | listLoyaltyProgrammes | GET | /loyalty/programmes |  | object | MARKETING_VIEW | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier |  | List loyalty programmes
MarketingService | loyalty | listRewards | GET | /loyalty/rewards |  | object | MARKETING_VIEW | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.reward |  | What points can be turned into
MarketingService | loyalty | setLeaderboardNickname | PUT | /loyalty/leaderboard-nickname |  | LoyaltyPosition |  | core | 1 | SVC-MARKETING-LOYALTY-2 | cache:idempotency, marketing.loyalty_position | cache:idempotency, marketing.loyalty_position | Choose the name shown on the board
MarketingService | loyalty | setLoyaltyRules | PUT | /loyalty/programmes/{programmeId}/rules | LoyaltyRuleSet | LoyaltyRuleSet | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-3 | cache:idempotency, marketing.loyalty_rule, marketing.points_redemption_rule, marketing.programme_tier | cache:idempotency, marketing.loyalty_rule, marketing.points_redemption_rule, marketing.programme_tier | Replace a programme's rules as one set
MarketingService | loyalty | setReward | PUT | /loyalty/rewards/{rewardId} | MarketingReward | MarketingReward | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-3 | cache:idempotency, marketing.reward | cache:idempotency, marketing.reward | Define a reward and its points cost
MarketingService | loyalty | updateLoyaltyProgramme | PATCH | /loyalty/programmes/{programmeId} |  | LoyaltyProgramme | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-3 | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule | Change a loyalty programme
MarketingService | marketing | createChallenge | POST | /challenges | Challenge | Challenge | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.event, marketing.challenge, marketing.loyalty_programme | cache:idempotency, marketing.challenge | Define a challenge, mission or streak
MarketingService | marketing | createForm | POST | /forms | FormDefinition | FormDefinition | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.product, marketing.form_definition, marketing.form_definition_field | cache:idempotency, marketing.form_definition, marketing.form_definition_field | Define a waiver, survey or capture form
MarketingService | marketing | createInvitationCampaign | POST | /invitation-campaigns | InvitationCampaign | InvitationCampaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.event, catalogue.product, marketing.invitation_campaign | cache:idempotency, marketing.invitation_campaign | A quota-bounded, addressed invitation
MarketingService | marketing | createReferral | POST | /referrals | Referral | Referral | MARKETING_MANAGE | core | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, marketing.guest_profile, marketing.referral, promotions.promotion | cache:idempotency, marketing.referral | Issue a referral code
MarketingService | marketing | createUrlRedirect | POST | /seo-redirects | UrlRedirect | UrlRedirect | MARKETING_MANAGE | core | 1 | SVC-MARKETING-MARKETING-2 | cache:idempotency, control.url_redirect | cache:idempotency, cache:resolution, control.url_redirect | 301, 302 and custom redirects
MarketingService | marketing | getForm | GET | /forms/{formId} |  | FormDefinition | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.form_definition, marketing.form_definition_field |  | One form, to fill in or to edit
MarketingService | marketing | getGuestConversation | GET | /my/conversations/{conversationId} |  | GuestConversation |  | core | 1 | AI-ENGINE-CONCIERGE |  |  | The guest's own handed-over conversation, with the agent's replies and the queue position
MarketingService | marketing | getLoyaltyPosition | GET | /loyalty/position |  | object |  | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.loyalty_programme |  | A guest's points, tier and what is within reach
MarketingService | marketing | getMarketingSubscription | GET | /marketing-subscriptions |  | array of MarketingSubscription | MARKETING_VIEW | core | 1 |  | marketing.subscription |  | What this guest has opted into
MarketingService | marketing | getMyCase | GET | /my/cases/{caseId} |  | CaseDetail |  | core | 1 | SVC-MARKETING-MARKETING-8 | marketing.case, marketing.case_message |  | One case the guest raised, with its thread
MarketingService | marketing | getMyChallenges | GET | /guests/me/challenges |  | array of object | MARKETING_VIEW | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.challenge, marketing.challenge_progress |  | Active challenges and how far along I am
MarketingService | marketing | getMyProfile | GET | /guests/me/profile |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | marketing.guest_preference, marketing.guest_profile |  | A guest reading their own details
MarketingService | marketing | getSeoMetadata | GET | /seo-metadata |  | SeoMetadata | MARKETING_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | control.seo_metadata |  | The metadata in force for one page
MarketingService | marketing | getWaiverStatus | GET | /guests/{subjectId}/waiver-status |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | access.entitlement, catalogue.product, marketing.form_definition, marketing.form_submission |  | Whether this guest may be issued a ticket that requires a waiver
MarketingService | marketing | handoverToAgent | POST | /conversations/{conversationId}/handover |  | Conversation |  | core | 1 | SVC-MARKETING-MARKETING-3 | cache:idempotency, marketing.agent_availability, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | cache:idempotency, marketing.conversation, platform.outbox | Pass an assistant conversation to a person
MarketingService | marketing | identifyGuest | POST | /guests/identify |  | GuestIdentification | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-4 | access.blacklist, access.entitlement, cache:idempotency, marketing.guest_profile, marketing.loyalty_position, pii.subject | cache:idempotency | Resolve any identifier to a guest
MarketingService | marketing | listMyCases | GET | /my/cases |  | object |  | core | 1 | SVC-MARKETING-MARKETING-4 | marketing.case, pii.subject |  | The cases this guest raised
MarketingService | marketing | raiseMyCase | POST | /my/cases |  | Case |  | core | 1 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.case | cache:idempotency, marketing.case | Report something — lost property, a complaint, a question
MarketingService | marketing | recordLostItem | POST | /lost-items | LostItem | LostItem | CASE_MANAGE | core | 1 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.lost_item, pii.subject, venuemap.point | cache:idempotency, marketing.lost_item | Report something lost, or hand something in
MarketingService | marketing | redeemLoyaltyPoints | POST | /loyalty/redemptions |  | LoyaltyPosition | LOYALTY_REDEEM | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.loyalty_position, marketing.loyalty_programme | cache:idempotency, marketing.loyalty_position, orders.stored_value_authorisation | Spend points
MarketingService | marketing | replyToMyCase | POST | /my/cases/{caseId}/messages |  | CaseDetail |  | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.case, marketing.case_message | cache:idempotency, marketing.case, marketing.case_message | Reply on a case the guest raised
MarketingService | marketing | respondToInvitation | POST | /invitations/{token}/respond |  | CampaignInvitation | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.invitation, marketing.invitation_campaign, orders.invitation | cache:idempotency, marketing.invitation | Accept or decline
MarketingService | marketing | sendConversationMessage | POST | /conversations/{conversationId}/messages |  | ConversationMessage | CASE_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | cache:idempotency, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | Say something, as a guest or an agent
MarketingService | marketing | sendGuestConversationMessage | POST | /my/conversations/{conversationId}/messages |  | GuestConversationMessage |  | core | 1 | AI-ENGINE-CONCIERGE | cache:idempotency | cache:idempotency, marketing.conversation_message | Write to the agent, as the guest, in the guest's own handed-over conversation
MarketingService | marketing | setAgentAvailability | PUT | /agent-availability |  | AgentAvailability | CASE_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, identity.principal, marketing.agent_availability | cache:idempotency, marketing.agent_availability | An agent goes available, away or offline
MarketingService | marketing | setMarketingSubscription | PUT | /marketing-subscriptions | MarketingSubscription | MarketingSubscription | MARKETING_VIEW | core | 1 |  | cache:idempotency, marketing.subscription | cache:idempotency, marketing.subscription | Subscribe or unsubscribe
MarketingService | marketing | setSeoMetadata | PUT | /seo-metadata | SeoMetadata | SeoMetadata | MARKETING_MANAGE | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, catalogue.product, control.seo_metadata | cache:idempotency, cache:resolution, control.seo_metadata | Titles, descriptions, canonicals and hreflang
MarketingService | marketing | submitForm | POST | /form-submissions | FormSubmission | FormSubmission | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, marketing.consent_record, marketing.form_definition, marketing.form_submission, marketing.form_submission_sale_link, marketing.waiver_requirement, pii.subject | cache:idempotency, marketing.consent_record, marketing.form_submission, marketing.form_submission_sale_link, marketing.waiver_requirement, marketing.waiver_requirement_event | Sign a waiver, answer a survey, capture details
MarketingService | marketing | updateGuestPreferences | PUT | /guests/{subjectId}/preferences | GuestPreferences | GuestPreferences | GUEST_MANAGE | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, marketing.guest_preference, marketing.guest_profile | cache:idempotency, marketing.guest_preference, marketing.guest_profile | The things a regular should not have to say twice
MarketingService | marketing | updateMyProfile | PATCH | /guests/me/profile |  | GuestProfile | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-7 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_preference, marketing.guest_profile, pii.subject | A guest correcting their own details
MarketingService | marketing | uploadGuestDocument | POST | /guest-documents | GuestDocument | GuestDocument | GUEST_VIEW_PII | setup | 1 | SVC-MARKETING-MARKETING-7 | cache:idempotency, marketing.consent_record, marketing.guest_document, pii.subject | cache:idempotency, marketing.guest_document | Store a guest photo, ID or signed document
MarketingService | message | createMessageTemplate | POST | /message-templates | MessageTemplate | MessageTemplate | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_template | cache:idempotency, marketing.message_template, marketing.message_template_version | Create a message template
MarketingService | message | listMyNotifications | GET | /me/notifications |  | object |  | core | 1 | SVC-MARKETING-MESSAGE-1 | marketing.message_dispatch |  | The signed-in guest's notification feed
MarketingService | message | markMyNotificationsRead | POST | /me/notifications/read |  | object |  | core | 1 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_dispatch | cache:idempotency, marketing.message_dispatch | Mark the signed-in guest's notifications read
MarketingService | message | updateMessageTemplate | PATCH | /message-templates/{templateId} |  | MessageTemplate | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_template | cache:idempotency, marketing.message_template, marketing.message_template_version | Change a message template
MarketingService | segment | createSegment | POST | /segments | CreateSegmentRequest | Segment | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-SEGMENT-1 | cache:idempotency, marketing.segment, marketing.segment_criterion | cache:idempotency, marketing.segment, marketing.segment_criterion | Create a segment
OrderService | cart | abandonCart | DELETE | /carts/{cartId} |  |  |  | core | 1 | SVC-ORDER-CART-1 | cache:idempotency, orders.cart | cache:idempotency, catalogue.inventory_reservation, orders.cart | Empty it deliberately
OrderService | cart | addCartLine | POST | /carts/{cartId}/lines | AddCartLineRequest | Cart |  | core | 1 | SVC-ORDER-CART-1 | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.product, catalogue.variant, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, orders.cart, orders.cart_line, platform.idempotency_record | Add a line to the cart
OrderService | cart | applyCartPromoCode | POST | /carts/{cartId}/promo-codes | ApplyCartPromoCodeRequest | Cart |  | core | 1 | SVC-ORDER-CART-1 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, promotions.coupon_campaign, promotions.coupon_code | cache:idempotency, orders.cart, orders.cart_line | Apply a promo code to the cart
OrderService | cart | checkoutCart | POST | /carts/{cartId}/checkout |  | Order |  | core | 1 | SVC-ORDER-CART-1 | cache:idempotency, catalogue.inventory_reservation, marketing.consent_question, orders.cart, orders.cart_line, orders.fraud_rule, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, marketing.consent_record, orders.cart, orders.deposit, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.sales_order, platform.idempotency_record, platform.outbox | Turn the cart into an order
OrderService | cart | claimCart | POST | /carts/{cartId}/claim |  | CartMergeResult |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, pii.subject | cache:idempotency, orders.cart, orders.cart_line | Attach an anonymous cart to a guest
OrderService | cart | createCart | POST | /carts |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, pii.subject, platform.scope | cache:idempotency, orders.cart | Start a cart
OrderService | cart | extendCart | POST | /carts/{cartId}/extend |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, catalogue.inventory_reservation, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_reservation, orders.cart | Give the guest more time
OrderService | cart | getCart | GET | /carts/{cartId} |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | catalogue.channel_capacity, catalogue.inventory_reservation, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, promotions.promotion |  | The cart, priced and checked, right now
OrderService | cart | removeCartLine | DELETE | /carts/{cartId}/lines/{lineId} |  | Cart |  | core | 1 | SVC-ORDER-CART-3 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_reservation, orders.cart_line | Take something out
OrderService | cart | updateCartLine | PATCH | /carts/{cartId}/lines/{lineId} |  | Cart |  | core | 1 | SVC-ORDER-CART-3 | cache:idempotency, catalogue.channel_capacity, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_reservation, orders.cart_line | Change a quantity
OrderService | cash | createCashMovement | POST | /shifts/{shiftId}/cash-movements | CreateCashMovementRequest | CashMovement | CASH_LIFT | core | 1 | SVC-ORDER-CASH-1 | cache:idempotency, orders.cash_count_line, orders.cash_movement | cache:idempotency, orders.cash_count_line, orders.cash_movement | Record a cash lift or add
OrderService | cash | listCashMovements | GET | /shifts/{shiftId}/cash-movements |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-CASH-1 | orders.cash_count_line, orders.cash_movement |  | Lifts, adds and the opening float
OrderService | drafted | listGroupArrivalCheck | GET | /group-arrival-check |  | array of GroupArrivalCheckInAdmissionOperationsView | ORDER_VIEW | core | 1 | SVC-ORDER-DRAFTED-1 | access.entitlement, access.scan_event, orders.group_booking, orders.group_participant, orders.group_visit_plan |  | Group Arrival, Check-In & Admission Operations
OrderService | dunning | listMyPaymentIssues | GET | /guests/me/payment-issues |  | object |  | core | 1 | SVC-ORDER-DUNNING-1 | payments.dunning_case |  | A guest's own failed recurring payments
OrderService | dunning | retryMyDunningPayment | POST | /dunning-cases/{caseId}/retry | RetryDunningPaymentRequest | DunningCase |  | core | 1 | SVC-ORDER-DUNNING-1 | cache:idempotency, orders.payment, payments.dunning_case, payments.dunning_policy | cache:idempotency, orders.payment, payments.dunning_case | Retry a declined membership payment now
OrderService | order | appendEntitlementToMedia | POST | /media/{mediaCode}/entitlements | AppendEntitlementRequest | AppendEntitlementResult | ORDER_CREATE | core | 1 | SVC-ORDER-ORDER-1 | access.entitlement, cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | access.entitlement, cache:idempotency, orders.order_line, orders.payment, orders.sales_order, platform.outbox | Add something to a ticket the guest already holds
OrderService | order | applyManualDiscount | POST | /orders/{orderId}/discounts | ManualDiscountRequest | Order | ORDER_DISCOUNT | core | 1 | SVC-ORDER-ORDER-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_line, orders.order_line_discount, orders.payment, orders.sales_order | Apply a discount a cashier chose
OrderService | order | claimTicketTransfer | POST | /ticket-transfers/{transferId}/claim |  | TicketTransfer |  | core | 1 | SVC-ORDER-ORDER-1 | access.entitlement, cache:idempotency, orders.ticket_transfer | access.entitlement, cache:idempotency, orders.ticket_transfer, platform.outbox | Claim transferred tickets
OrderService | order | createOrder | POST | /orders | CreateOrderRequest | Order | ORDER_CREATE | core | 1 | SVC-ORDER-ORDER-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, platform.outbox, promotions.promotion_evaluation_trace | Create an order
OrderService | order | exchangeOrderLines | POST | /orders/{orderId}/exchanges | ExchangeOrderRequest | OrderExchangeResult | ORDER_EXCHANGE | core | 1 | SVC-ORDER-ORDER-2 | cache:idempotency, orders.order_line, orders.refund, orders.refund_policy, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.sales_order, platform.outbox | Exchange lines for different products or dates
OrderService | order | getMediaEntitlements | GET | /media/{mediaCode}/entitlements |  | MediaEntitlements | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | access.entitlement, access.scan_event, catalogue.entitlement_template, orders.sales_order, pii.subject |  | What is already on this media
OrderService | order | getOrder | GET | /orders/{orderId} |  | Order | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order |  | Read an order
OrderService | order | getOrderCalendarEvent | GET | /orders/{orderId}/calendar-event |  | string | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | orders.order_event, orders.order_line, orders.sales_order, platform.scope |  | The visit as a calendar entry
OrderService | order | getOrderStatement | GET | /orders/{orderId}/statement |  | OrderStatement | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | ledger.posting, orders.chargeback, orders.order_event, orders.order_fee, orders.payment, orders.refund, orders.sales_order |  | Full financial history of an order
OrderService | order | getVisitReminder | GET | /orders/{orderId}/reminder |  | VisitReminder | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | orders.sales_order, orders.visit_reminder |  | The guest's reminder for this booking
OrderService | order | holdOrder | POST | /orders/{orderId}/hold |  | Order | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-3 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Park a sale and free the till
OrderService | order | listOrders | GET | /orders |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | orders.order_line, orders.payment, orders.sales_order |  | List orders
OrderService | order | listTicketTransfers | GET | /ticket-transfers |  | object |  | core | 1 | SVC-ORDER-ORDER-4 | orders.ticket_transfer |  | The ticket transfers this guest sent or received
OrderService | order | modifyOrder | POST | /orders/{orderId}/modify | ModifyOrderRequest | OrderModificationResult | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.refund, orders.refund_policy, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Add or remove lines on an existing order
OrderService | order | reprintOrder | POST | /orders/{orderId}/reprints |  | object | ORDER_REPRINT | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.order_line, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.sales_order | Reprint or resend tickets
OrderService | order | rescheduleOrder | POST | /orders/{orderId}/reschedule |  | OrderExchangeResult | ORDER_RESCHEDULE | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.order_line, orders.refund, orders.refund_policy, orders.sales_order | cache:idempotency, orders.order_event, orders.sales_order | Move an order to another performance
OrderService | order | resumeOrder | POST | /orders/{orderId}/resume |  | OrderResumeResult | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-5 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Bring a parked sale back to a till
OrderService | order | setVisitReminder | PUT | /orders/{orderId}/reminder | VisitReminder | VisitReminder | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-5 | cache:idempotency, orders.visit_reminder | cache:idempotency, orders.visit_reminder | Turn a visit reminder on or off
OrderService | order | transferOrderTickets | POST | /orders/{orderId}/transfer |  | TicketTransfer |  | core | 1 | SVC-ORDER-ORDER-5 | access.entitlement, cache:idempotency, orders.ticket_transfer | access.entitlement, cache:idempotency, orders.ticket_transfer, platform.outbox | Transfer tickets to another guest
OrderService | order | voidOrder | POST | /orders/{orderId}/voids |  | Order | ORDER_VOID | core | 1 | SVC-ORDER-ORDER-5 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, platform.outbox | Void an order
OrderService | orders | cloneTicketTemplate | POST | /ticket-templates/{templateId}/clone | CloneTicketTemplateInput | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-1 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | Create a ticket template from an existing one
OrderService | orders | createResaleListing | POST | /resale-listings | CreateResaleListingRequest | ResaleListing | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-1 | access.entitlement, cache:idempotency, catalogue.entitlement_template, orders.resale_listing, orders.sales_order | cache:idempotency, orders.resale_listing, platform.outbox | List an entitlement for resale
OrderService | orders | createTicketTemplate | POST | /ticket-templates | TicketTemplateRequest | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-1 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | Create a ticket template
OrderService | orders | getBillingStatement | GET | /billing-statements/{statementId} |  | BillingStatement | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-1 | ledger.tax_invoice_line, orders.payment, orders.sales_order, payments.dunning_case |  | One statement, with its lines
OrderService | orders | getGroupBooking | GET | /group-bookings/{groupBookingId} |  | GroupBooking | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | orders.group_booking, orders.sales_order, pii.subject |  | A group, its leader and its name-capture duty
OrderService | orders | getPaymentLink | GET | /payment-links/{token} |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment_link, orders.reservation, orders.sales_order, platform.scope |  | What a guest holding a link is being asked to pay for
OrderService | orders | importTicketTemplate | POST | /ticket-templates/imports | TicketTemplateImportInput | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-2 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | Import a ticket template definition
OrderService | orders | issueWalletPass | POST | /wallet-passes |  | WalletPass | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | access.entitlement, cache:idempotency, orders.ticket_template, orders.wallet_pass | cache:idempotency, orders.wallet_pass | Generate an Apple or Google wallet pass
OrderService | orders | listBillingStatements | GET | /billing-statements |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-3 | orders.payment, orders.sales_order, payments.dunning_case |  | What was charged, when, and against which agreement
OrderService | orders | listMyOrders | GET | /my/orders |  | object |  | core | 1 | SVC-ORDER-ORDERS-3 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order, pii.subject |  | The orders this guest placed
OrderService | orders | listOwnGroupBookings | GET | /group-booking-requests |  | object |  | core | 1 | SVC-ORDER-ORDERS-10 | orders.group_booking |  | The group bookings the caller asked for
OrderService | orders | listOwnResaleListings | GET | /resale-listings |  | object |  | core | 1 | SVC-ORDER-ORDERS-10 | orders.resale_listing |  | The caller's own resale listings
OrderService | orders | listPaymentTokens | GET | /payment-tokens |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-3 | payments.token |  | A guest's saved payment methods
OrderService | orders | payByLink | POST | /payment-links/{token}/pay |  | object | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-3 | cache:idempotency, orders.payment_link, orders.reservation, orders.sales_order, payments.provider | access.entitlement, cache:idempotency, orders.payment, orders.payment_link, orders.reservation, orders.sales_order, payments.payment_attempt, platform.outbox | Pay for a booking taken at a till
OrderService | orders | previewProductTickets | GET | /products/{productId}/ticket-previews |  | array of TicketProof | PRODUCT_VIEW | core | 1 | SVC-ORDER-ORDERS-4 |  |  | Preview a product's PDF ticket and wallet passes
OrderService | orders | recordGroupCheckIn | POST | /group-bookings/{groupBookingId}/check-in | GroupCheckInRequest | GroupVisitPlan | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDERS-4 | cache:idempotency, orders.group_booking, orders.group_visit_plan | cache:idempotency, orders.group_visit_plan, orders.order_event | Record a group's arrival at the venue
OrderService | orders | reissueEntitlement | POST | /entitlements/{entitlementId}/reissue |  | ReissuedEntitlement | ORDER_EXCHANGE | core | 1 | SVC-ORDER-ORDERS-4 | access.entitlement, cache:idempotency, catalogue.product | access.entitlement, cache:idempotency, platform.outbox | Zero-value reissue of an expired entitlement for a later date
OrderService | orders | requestGroupBooking | POST | /group-booking-requests | GroupBookingRequest | GroupBooking |  | core | 1 | SVC-ORDER-ORDERS-4 | cache:idempotency, catalogue.group_package, catalogue.product, orders.group_booking | cache:idempotency, orders.group_booking, orders.sales_order | Ask for a school trip or a birthday party
OrderService | orders | setPaymentProvider | PUT | /payment-providers/{providerId} | SetPaymentProviderRequest | PaymentProvider | TENANT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-5 | cache:idempotency, payments.provider | cache:idempotency, payments.provider, payments.routing_rule | Configure a gateway and its routing
OrderService | orders | shareEntitlement | POST | /entitlements/{entitlementId}/share |  | EntitlementShare | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDERS-5 | access.entitlement, cache:idempotency, catalogue.entitlement_template, identity.delegated_access | access.entitlement, cache:idempotency, identity.delegated_access, platform.outbox | Let somebody else use this, without giving it away
OrderService | orders | storePaymentToken | POST | /payment-tokens |  | PaymentToken | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-5 | cache:idempotency, marketing.consent_record, payments.provider, payments.token | cache:idempotency, payments.token, platform.outbox | Save a payment method for future use
OrderService | orders | updateTicketTemplate | PATCH | /ticket-templates/{templateId} | TicketTemplateRequest | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-5 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template | Change or retire a ticket template
OrderService | payment | addTip | POST | /payments/{paymentId}/tip |  | Payment | ORDER_MODIFY | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, orders.payment | cache:idempotency, orders.payment | Record a tip against a payment
OrderService | payment | capturePayment | POST | /payments/{paymentId}/capture |  | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, ledger.fx_rate, orders.payment, payments.provider_connection | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_reservation, ledger.journal_entry, ledger.journal_line, orders.order_event, orders.payment, payments.payment_attempt, platform.idempotency_record, platform.outbox | Capture a previously authorised payment
OrderService | payment | createPayment | POST | /payments | CreatePaymentRequest | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, catalogue.inventory_reservation, ledger.fx_rate, orders.order_line, orders.payment, orders.sales_order, payments.provider_connection | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_reservation, ledger.journal_entry, ledger.journal_line, orders.order_event, orders.payment, payments.payment_attempt, platform.idempotency_record, platform.outbox | Take a payment against an order
OrderService | payment | inquirePaymentStatus | POST | /payments/{paymentId}/inquiry |  | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, orders.payment | cache:idempotency, orders.payment, platform.outbox | Ask the provider what actually happened
OrderService | payments | createPaymentProviderConnection | POST | /payment-providers | PaymentProviderConnection | PaymentProviderConnection | PAYMENT_PROVIDER_MANAGE | setup | 1 |  | cache:idempotency, payments.provider_connection | cache:idempotency, payments.provider_connection | Connect a provider
OrderService | payments | setDunningPolicy | PUT | /dunning-policy | DunningPolicy | DunningPolicy | PAYMENT_CONFIGURE | setup | 1 |  | cache:idempotency, payments.dunning_policy | cache:idempotency, payments.dunning_policy | Set the retry schedule and what happens when it runs out
OrderService | policy | getGuestRefundPolicy | GET | /venues/{venueId}/guest-refund-policy |  | GuestRefundPolicy |  | core | 1 | SVC-ORDER-POLICY-2 | orders.refund_policy |  | What a guest is told about refunds at a venue
OrderService | policy | setRefundPolicy | PUT | /venues/{venueId}/refund-policy | RefundPolicy | RefundPolicy | REGION_CONFIGURE | setup | 1 | SVC-ORDER-POLICY-1 | cache:idempotency, orders.refund_policy, orders.refund_policy_time_band | cache:idempotency, cache:resolution, orders.refund_policy, orders.refund_policy_time_band | Set a venue's refund policy
OrderService | refund | createRefund | POST | /orders/{orderId}/refunds | CreateRefundRequest | Refund | ORDER_REFUND | core | 1 | SVC-ORDER-REFUND-1 | cache:idempotency, orders.fraud_rule, orders.payment, orders.refund, orders.refund_line, orders.refund_payment, orders.sales_order | cache:idempotency, ledger.journal_entry, ledger.posting, orders.order_event, orders.refund, orders.refund_line, orders.refund_payment, platform.outbox | Refund an order, wholly or in part
OrderService | refund | createRefundRequest | POST | /refund-requests |  | object |  | core | 1 | SVC-ORDER-REFUND-1 | cache:idempotency, orders.fraud_rule, orders.refund_policy, orders.sales_order | cache:idempotency, orders.refund | Guest-initiated refund request
OrderService | refund | listOrderRefunds | GET | /orders/{orderId}/refunds |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-REFUND-1 | orders.refund, orders.refund_line, orders.refund_payment |  | List refunds against an order
OrderService | refund | listOwnRefundRequests | GET | /refund-requests |  | object |  | core | 1 | SVC-ORDER-REFUND-3 | orders.refund, orders.refund_line, orders.refund_payment |  | The caller's own refund requests
OrderService | reservation | cancelReservation | DELETE | /reservations/{reservationId} |  |  | ORDER_CANCEL | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation | cache:idempotency, orders.order_event, orders.reservation | Cancel a reservation
OrderService | reservation | convertReservation | POST | /reservations/{reservationId}/convert |  | Order | ORDER_CREATE | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, promotions.promotion_evaluation_trace | Convert a reservation into an order
OrderService | reservation | createReservation | POST | /reservations | CreateReservationRequest | Reservation | ORDER_CREATE | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation, orders.reservation_line | cache:idempotency, orders.order_event, orders.reservation, orders.reservation_line | Hold without payment
OrderService | reservation | extendReservation | POST | /reservations/{reservationId}/extend |  | Reservation | ORDER_CREATE | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation, orders.reservation_line | cache:idempotency, orders.order_event, orders.reservation | Extend a reservation
OrderService | reservation | getReservation | GET | /reservations/{reservationId} |  | Reservation | ORDER_VIEW | core | 1 | SVC-ORDER-RESERVATION-2 | orders.reservation, orders.reservation_line |  | Read a reservation
OrderService | reservation | listReservations | GET | /reservations |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-RESERVATION-2 | orders.reservation, orders.reservation_line |  | List reservations
OrderService | shift | acceptShiftVariance | POST | /shifts/{shiftId}/accept-variance |  | Shift | OVERSHORT_ACCEPT | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.deposit_box, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.deposit_box, orders.pos_shift, orders.pos_shift_approval, platform.outbox | Accept an over/short beyond the threshold
OrderService | shift | allocateDepositBox | POST | /deposit-boxes | CreateDepositBoxRequest | DepositBox | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, identity.principal, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, platform.workstation | cache:idempotency, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | Give a cashier a box and a float
OrderService | shift | approveShiftOpen | POST | /shifts/{shiftId}/approve-open |  | Shift | SHIFT_APPROVE_OPEN | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift, orders.pos_shift_approval | Approve a shift opening outside tolerance
OrderService | shift | closeShift | POST | /shifts/{shiftId}/close |  | ShiftCloseResult | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, ledger.fx_rate, orders.cash_count_line, orders.cash_movement, orders.payment, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, orders.sales_order, orders.till_shift_policy, platform.venue_settings | cache:idempotency, orders.cash_count_line, orders.pos_shift, platform.outbox | Blind close-out
OrderService | shift | getCurrentShift | GET | /shifts/current |  | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-2 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | The open or suspended shift on the session's workstation
OrderService | shift | getShiftCountLines | GET | /shifts/{shiftId}/count-lines |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-2 | orders.cash_count_line |  | The denomination breakdown of a shift's counts
OrderService | shift | getTillShiftPolicy | GET | /venues/{venueId}/till-shift-policy |  | TillShiftPolicy | SCOPE_VIEW | core | 1 | SVC-ORDER-SHIFT-2 | orders.till_shift_policy |  | The rules every till in the venue opens and closes to
OrderService | shift | getWorkstationShift | GET | /shifts/current/overview |  | Shift | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-2 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | Read the open or suspended shift on the session's workstation, without the right to open one
OrderService | shift | giveShiftVarianceReason | POST | /shifts/{shiftId}/variance-reason | ShiftVarianceReasonRequest | ShiftCountReceipt | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-3 | cache:idempotency | cache:idempotency, orders.pos_shift, platform.outbox | Give the reason for a difference within the threshold, and close the shift
OrderService | shift | listDenominations | GET | /denominations |  | array of Denomination | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | platform.denomination, platform.region_settings |  | The notes and coins a till counts
OrderService | shift | listDepositBoxes | GET | /deposit-boxes |  | object | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | identity.principal, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, orders.payment |  | Cash boxes and who holds them
OrderService | shift | listShifts | GET | /shifts |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-3 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | List shifts
OrderService | shift | openShift | POST | /shifts | OpenShiftRequest | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, identity.principal, orders.cash_count_line, orders.cash_movement, orders.deposit_box, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, orders.till_shift_policy, platform.venue_settings, platform.workstation | cache:idempotency, orders.cash_count_line, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.outbox | Open a shift
OrderService | shift | recordNoSale | POST | /shifts/{shiftId}/no-sale |  | NoSaleEvent | CASH_NO_SALE | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.no_sale_event | cache:idempotency, orders.no_sale_event | Open the Deposit Box without a sale
OrderService | shift | rejectShiftVariance | POST | /shifts/{shiftId}/reject-variance |  | Shift | OVERSHORT_ACCEPT | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift, orders.pos_shift_incident | Send a counted shift back for a recount
OrderService | shift | reopenShift | POST | /shifts/{shiftId}/reopen |  | Shift | SHIFT_REOPEN | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Reopen a shift closed in error
OrderService | shift | resumeShift | POST | /shifts/{shiftId}/resume |  | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Resume a suspended shift
OrderService | shift | setDenominations | PUT | /denominations | SetDenominationsRequest | array of Denomination | REGION_CONFIGURE | setup | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, platform.denomination | cache:idempotency, platform.denomination | Set the notes and coins a region's tills count
OrderService | shift | setTillShiftPolicy | PUT | /venues/{venueId}/till-shift-policy | TillShiftPolicy | TillShiftPolicy | WORKSTATION_CONFIGURE | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, orders.till_shift_policy | cache:idempotency, orders.till_shift_policy | Set the rules every till in the venue opens and closes to
OrderService | shift | submitShiftCount | POST | /shifts/{shiftId}/count | CloseShiftRequest | ShiftCountReceipt | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, ledger.fx_rate, orders.cash_count_line, orders.cash_movement, orders.payment, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.venue_settings | cache:idempotency, orders.cash_count_line, orders.pos_shift, platform.outbox | The cashier's blind count, closing their own shift
OrderService | shift | suspendShift | POST | /shifts/{shiftId}/suspend |  | Shift | SHIFT_SUSPEND | core | 1 | SVC-ORDER-SHIFT-6 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Suspend a shift so another user can log in
OrderService | shift | withdrawFromDepositBox | POST | /deposit-boxes/{boxId}/withdraw |  | DepositBox | CASH_LIFT | core | 1 | SVC-ORDER-SHIFT-6 | cache:idempotency, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | cache:idempotency, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | A supervisor takes cash out mid-shift
OrderService | sync | listSyncRejections | GET | /sync/rejections |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-SYNC-1 | sync.rejection |  | Entries the server refused
OrderService | sync | syncOrders | POST | /sync/orders |  | OrderSyncResult | ORDER_CREATE | core | 1 | SVC-ORDER-SYNC-1 | cache:idempotency, catalogue.inventory_reservation, catalogue.price_list, catalogue.variant, orders.sales_order | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_reservation, ledger.price_variance, orders.order_line, orders.order_line_discount, orders.payment, orders.sales_order, platform.idempotency_record, platform.outbox, sync.rejection | Replay orders recorded offline
PlatformService | licensing | addLicenceAddOn | POST | /tenants/{tenantId}/licences/add-ons | LicenceAddOn | LicencePosition | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-LICENSING-1 | cache:idempotency, control.licence_add_on, control.licence_add_on_limit, control.tenant | cache:idempotency, control.licence_add_on, control.licence_add_on_limit | License a module outside the plan
PlatformService | licensing | getTenantLicences | GET | /tenants/{tenantId}/licences |  | LicencePosition | PLATFORM_TENANT_VIEW | core | 1 | SVC-PLATFORM-LICENSING-1 | control.contract, control.licence_add_on, control.licence_add_on_limit, control.plan, control.tenant |  | What a tenant is licensed to use
PlatformService | plan | createPlan | POST | /plans | CreatePlanRequest | Plan | PLATFORM_PLAN_MANAGE | setup | 1 | SVC-PLATFORM-PLAN-1 | cache:idempotency, control.plan, control.plan_limit, control.plan_module, control.tenant | cache:idempotency, control.plan, control.plan_limit, control.plan_module | Create a subscription plan
PlatformService | plan | createPlanVersion | POST | /plans/{planId} | CreatePlanRequest | Plan | PLATFORM_PLAN_MANAGE | setup | 1 | SVC-PLATFORM-PLAN-1 | cache:idempotency, control.plan, control.plan_limit, control.plan_module, control.tenant | cache:idempotency, control.plan, control.plan_limit, control.plan_module | Publish a new version of a plan
PlatformService | publicApi | certifyIntegration | POST | /listings/{listingId}/certify |  | IntegrationListing | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_version, control.integration_listing | cache:idempotency, control.integration_listing | Approve, reject or revoke a certification
PlatformService | publicApi | createApiClient | POST | /api-clients | ApiClient | object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_client, control.api_licence, control.developer_account, control.integration_listing | cache:idempotency, control.api_client, control.api_client_secret | Create a client with scopes and an environment
PlatformService | publicApi | decideProductionAccess | POST | /production-access-requests/{requestId}/decide |  | ProductionAccessRequest | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.integration_listing, control.production_access_request | cache:idempotency, control.api_client, control.production_access_request | Approve or reject production access
PlatformService | publicApi | deprecateApiVersion | POST | /api-versions/{version}/deprecate |  | ApiVersion | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_client, control.api_version | cache:idempotency, control.api_version, marketing.message_dispatch | Announce a sunset date and notify subscribers
PlatformService | publicApi | registerDeveloper | POST | /developers | CreateDeveloperAccountRequest | DeveloperAccount |  | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.developer_account | cache:idempotency, control.developer_account, control.developer_member | Register a developer or organisation
PlatformService | publicApi | rotateApiCredential | POST | /api-clients/{clientId}/credentials |  | object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_client | cache:idempotency, control.api_client, control.api_client_secret | Issue a new secret, with an overlap window
PlatformService | publicApi | setApiClientStatus | POST | /api-clients/{clientId}/status |  | ApiClient | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_client | cache:idempotency, control.api_client | Suspend or reactivate an integration, reversibly
PlatformService | publicApi | setApiLicensing | PUT | /api-licensing/{licenceId} | ApiLicence | ApiLicence | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_licence, control.tenant | cache:idempotency, cache:resolution, control.api_licence | Which API modules a tenant has licensed, and on what terms
PlatformService | publicApi | setDeveloperMembers | PUT | /developers/{developerId}/members |  | array of DeveloperMember | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-3 | cache:idempotency, control.developer_account, control.developer_member | cache:idempotency, control.developer_account, control.developer_member | Who at this organisation may do what
PlatformService | publicApi | verifyDeveloper | POST | /developers/{developerId}/verify |  | DeveloperAccount | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-12 | cache:idempotency, control.developer_account | cache:idempotency, control.developer_account | Verify a registered developer organisation
PlatformService | subscription | listModuleCatalogue | GET | /module-catalogue |  | array of ModuleListing | PLATFORM_PLAN_MANAGE | core | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | control.module_listing |  | Modules, their dependencies and their commercial treatment
PlatformService | subscription | setModuleListing | PUT | /module-catalogue/{moduleCode} | ModuleListing | ModuleListing | PLATFORM_PLAN_MANAGE | setup | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | cache:idempotency, control.module_listing | cache:idempotency, control.module_listing | Define a module's dependencies, incompatibilities and price
PlatformService | subscription | setSubscription | PUT | /tenants/{tenantId}/subscription | SetSubscriptionRequest | Subscription | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | cache:idempotency, control.contract, control.plan | cache:idempotency, control.contract, control.tenant | Assign or change a subscription
PlatformService | tenant | createTenant | POST | /tenants | CreateTenantRequest | Tenant | PLATFORM_TENANT_MANAGE | setup | 1 |  | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Create a tenant
PlatformService | tenant | listTenants | GET | /tenants |  | object | PLATFORM_TENANT_VIEW | core | 1 |  | control.tenant |  | List tenants
PlatformService | tenant | terminateTenant | POST | /tenants/{tenantId}/terminate |  | TerminationSchedule | PLATFORM_TENANT_TERMINATE | setup | 1 | SVC-PLATFORM-TENANT-2 | cache:idempotency, control.contract, control.tenant | cache:idempotency, control.contract, control.tenant | Begin termination
PlatformService | tenant | updateTenant | PATCH | /tenants/{tenantId} |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-TENANT-2 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Amend tenant details
ReportingService | catalogue | createReport | POST | /reports | CreateReportRequest | ReportDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-CATALOGUE-1 | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter | Create a custom report definition
ReportingService | catalogue | deleteReport | DELETE | /reports/{reportId} |  |  | REPORT_MANAGE | setup | 1 | SVC-REPORTING-CATALOGUE-1 | cache:idempotency, reporting.report_definition | cache:idempotency, reporting.report_definition | Retire a report definition
ReportingService | catalogue | getReport | GET | /reports/{reportId} |  | ReportDefinition | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-CATALOGUE-1 | reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter |  | Read a report definition
ReportingService | catalogue | listReports | GET | /reports |  | object | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-CATALOGUE-1 | reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter |  | List available report definitions
ReportingService | catalogue | updateReport | PUT | /reports/{reportId} | CreateReportRequest | ReportDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-CATALOGUE-2 | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter | Publish a new version of a definition
ReportingService | dashboard | createDashboard | POST | /dashboards | CreateDashboardRequest | Dashboard | REPORT_MANAGE | setup | 1 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | Create a dashboard
ReportingService | dashboard | getDashboard | GET | /dashboards/{dashboardId} |  | DashboardData | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-DASHBOARD-1 | reporting.dashboard, reporting.dashboard_tile |  | Read a dashboard with tile data
ReportingService | dashboard | listDashboards | GET | /dashboards |  | array of Dashboard | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-DASHBOARD-1 | reporting.dashboard, reporting.dashboard_tile |  | List dashboards
ReportingService | dashboard | recordDashboardView | POST | /dashboards/{dashboardId}/views |  |  | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard | cache:idempotency, reporting.dashboard_view | Record that a dashboard was opened
ReportingService | dashboard | updateDashboard | PUT | /dashboards/{dashboardId} | CreateDashboardRequest | Dashboard | REPORT_MANAGE | setup | 1 | SVC-REPORTING-DASHBOARD-2 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | Update a dashboard
ReportingService | execution | runReport | POST | /reports/{reportId}/run | RunReportRequest | ReportResult | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-EXECUTION-1 | cache:idempotency, reporting.execution, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.execution | Run a report
ReportingService | naturalLanguage | askReportingQuestion | POST | /reports/ask |  | NaturalLanguageAnswer | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-NATURALLANGUAGE-1 | ai.policy, ai.provider, cache:idempotency, reporting.kpi_definition, reporting.natural_language_query, reporting.report_column, reporting.report_filter, reporting.semantic_model | ai.activity, cache:idempotency, platform.outbox, reporting.natural_language_query, reporting.report_column, reporting.report_filter | Natural-language reporting query
ReportingService | naturalLanguage | saveNaturalLanguageQuery | POST | /reports/ask/{conversationId}/save |  | ReportDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-NATURALLANGUAGE-1 | ai.policy, ai.provider, cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | ai.activity, cache:idempotency, platform.outbox, reporting.natural_language_query, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | Save a natural-language answer as a report definition
ReportingService | reporting | createKpi | POST | /kpis | KpiDefinition | KpiDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | cache:idempotency, reporting.kpi_definition | cache:idempotency, reporting.kpi_definition | Define a KPI once, for everywhere
ReportingService | reporting | deleteDashboard | DELETE | /dashboards/{dashboardId} |  |  | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard | Archive a dashboard
ReportingService | reporting | listAlerts | GET | /alerts |  | array of Alert | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-REPORTING-1 | reporting.alert, reporting.alert_rule |  | What is currently wrong
ReportingService | reporting | setAlertRule | PUT | /alert-rules/{alertRuleId} | AlertRule | AlertRule | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | cache:idempotency, identity.role, reporting.alert_rule | cache:idempotency, reporting.alert_rule | Watch a metric and tell somebody
ReportingService | reporting | setSemanticModel | PUT | /semantic-model | SemanticModel | SemanticModel | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-2 | cache:idempotency, reporting.semantic_model | cache:idempotency, reporting.semantic_model | Publish the catalogue
RetailService | floor | collectShopAndDrop | POST | /shop-and-drop/{dropId}/collect |  | ShopAndDrop | ORDER_MODIFY | core | 1 | SVC-RETAIL-FLOOR-1 | cache:idempotency, retail.shop_and_drop, retail.shop_and_drop_line | cache:idempotency, retail.shop_and_drop, retail.shop_and_drop_line | Hand the goods over
RetailService | floor | createShopAndDrop | POST | /shop-and-drop |  | ShopAndDrop | ORDER_CREATE | core | 1 | SVC-RETAIL-FLOOR-1 | cache:idempotency, retail.sale, retail.sale_line, retail.shop_and_drop, retail.shop_and_drop_line | cache:idempotency, retail.shop_and_drop, retail.shop_and_drop_line | Buy now, collect on the way out
RetailService | floor | lookupMerchandise | GET | /merchandise/lookup |  | PriceCheck | PRODUCT_VIEW | core | 1 | SVC-RETAIL-FLOOR-1 | retail.merchandise |  | Price and stock check by barcode
RetailService | floor | lookupShopAndDrop | GET | /shop-and-drop/lookup |  | array of ShopAndDrop | ORDER_VIEW | core | 1 | SVC-RETAIL-FLOOR-1 | retail.sale, retail.sale_line, retail.shop_and_drop, retail.shop_and_drop_line |  | Find a guest's dropped goods
RetailService | floor | reserveMerchandise | POST | /outlets/{outletId}/reserve |  | MerchandiseReservation | ORDER_CREATE | core | 1 | SVC-RETAIL-FLOOR-2 | cache:idempotency, inventory.movement, inventory.stock_earmark, retail.merchandise, retail.reservation, retail.reservation_line | cache:idempotency, inventory.stock_earmark, retail.reservation, retail.reservation_line | Reserve an item for collection
RetailService | merchandise | createMerchandise | POST | /merchandise | CreateMerchandiseRequest | MerchandiseItem | PRODUCT_CONFIGURE | setup | 1 | SVC-RETAIL-MERCHANDISE-1 | cache:idempotency, retail.merchandise | cache:idempotency, retail.merchandise | Create a merchandise item
RetailService | merchandise | listMerchandise | GET | /merchandise |  | object | PRODUCT_VIEW | core | 1 | SVC-RETAIL-MERCHANDISE-1 | retail.merchandise |  | List merchandise
RetailService | merchandise | updateMerchandise | PATCH | /merchandise/{merchandiseId} |  | MerchandiseItem | PRODUCT_CONFIGURE | setup | 1 | SVC-RETAIL-MERCHANDISE-1 | cache:idempotency, retail.merchandise | cache:idempotency, retail.merchandise | Amend a merchandise item
RetailService | return | createRetailReturn | POST | /retail-returns | CreateRetailReturnRequest | RetailReturn | ORDER_REFUND | core | 1 | SVC-RETAIL-RETURN-1 | cache:idempotency, inventory.kit_component, retail.merchandise, retail.return, retail.return_line, retail.return_policy, retail.sale, retail.sale_line | cache:idempotency, inventory.movement, retail.return, retail.return_line | Accept a return
RetailService | return | getReturnPolicy | GET | /outlets/{outletId}/return-policy |  | ReturnPolicy | ORDER_VIEW | core | 1 | SVC-RETAIL-RETURN-1 | cache:resolution, retail.return_policy | cache:resolution | Read the retail return policy
RetailService | return | lookupRetailSale | GET | /retail-sales/lookup |  | object | ORDER_VIEW | core | 1 | SVC-RETAIL-RETURN-1 | retail.sale, retail.sale_line |  | Find a sale from a receipt
RetailService | return | setReturnPolicy | PUT | /outlets/{outletId}/return-policy | ReturnPolicy | ReturnPolicy | REGION_CONFIGURE | setup | 1 | SVC-RETAIL-RETURN-1 | cache:idempotency, retail.return_policy | cache:idempotency, cache:resolution, retail.return_policy | Set the retail return policy
RetailService | sale | createRetailSale | POST | /retail-sales | CreateRetailSaleRequest | RetailSale | ORDER_CREATE | core | 1 | SVC-RETAIL-SALE-1 | cache:idempotency, inventory.kit_component, retail.merchandise, retail.sale, retail.sale_line | cache:idempotency, inventory.movement, retail.sale, retail.sale_line | Sell merchandise
RetailService | sale | getRetailSale | GET | /retail-sales/{saleId} |  | RetailSale | ORDER_VIEW | core | 1 | SVC-RETAIL-SALE-1 | retail.sale, retail.sale_line |  | Read a retail sale
RetailService | sale | listRetailSales | GET | /retail-sales |  | object | ORDER_VIEW | core | 1 | SVC-RETAIL-SALE-1 | retail.sale, retail.sale_line |  | List retail sales
RetailService | sale | reprintReceipt | POST | /retail-sales/{saleId}/reprint |  | object | ORDER_REPRINT | core | 1 | SVC-RETAIL-SALE-1 | cache:idempotency, retail.sale | cache:idempotency, retail.sale | Reprint or resend a receipt
TenancyService | approvals | approveMatrixMultiLevel | PUT | /matrix-multi-level | ApprovalMatrixMultiLevelApprovalConfigurationInput | ApprovalMatrixMultiLevelApprovalConfigurationView | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-APPROVALS-1 | approvals.matrix, approvals.rule, cache:idempotency | approvals.matrix, approvals.rule, cache:idempotency | Approval Matrix & Multi-Level Approval Configuration
TenancyService | approvals | approveRoleAuthorityDelegation | PUT | /role-authority-delegation | RolesAuthorityDelegationApprovalLimitsInput | RolesAuthorityDelegationApprovalLimitsView | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-APPROVALS-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, identity.principal | approvals.delegation, cache:idempotency | Roles, Authority, Delegation & Approval Limits
TenancyService | attendance | recordAttendance | POST | /attendance/clock |  | AttendanceRecord | ATTENDANCE_RECORD | core | 1 | SVC-TENANCY-ATTENDANCE-1 | access.access_point, cache:idempotency, workforce.attendance, workforce.attendance_amendment, workforce.rota_assignment | cache:idempotency, workforce.attendance | Clock in, clock out, or take a break
TenancyService | delegation | createApprovalDelegation | POST | /delegations | ApprovalDelegation | ApprovalDelegation | APPROVAL_DECIDE | setup | 1 | SVC-TENANCY-DELEGATION-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, identity.principal | approvals.delegation, cache:idempotency | Delegate approval authority
TenancyService | devices | createDeviceFirmware | POST | /device-firmware | DeviceFirmware | DeviceFirmware | DEVICE_MANAGE | setup | 1 |  | cache:idempotency, tenancy.device_firmware | cache:idempotency, tenancy.device_firmware | Register a firmware or software release before it is deployed
TenancyService | devices | setDeviceAssignment | PUT | /devices/{deviceId}/assignment | DeviceAssignment | DeviceAssignment | DEVICE_MANAGE | core | 1 | SVC-TENANCY-DEVICES-1 | cache:idempotency, platform.device, tenancy.device_assignment | cache:idempotency, tenancy.device_assignment | Who owns it, who holds it, and where it is
TenancyService | devices | setDeviceFirmwareStatus | POST | /device-firmware/{firmwareId}/status |  | DeviceFirmware | DEVICE_MANAGE | setup | 1 |  | cache:idempotency, tenancy.device_firmware, tenancy.device_rollout | cache:idempotency, platform.outbox, tenancy.device_audit, tenancy.device_firmware, tenancy.device_rollout | Release, deprecate or withdraw a firmware release
TenancyService | general | getDeviceAssignment | GET | /devices/{deviceId}/assignment |  | DeviceAssignment | DEVICE_VIEW | core | 1 | SVC-TENANCY-GENERAL-1 | tenancy.device_assignment |  | Where a device is assigned
TenancyService | identity | setRolePermissions | PUT | /roles/{roleId}/permissions |  | object | ROLE_MANAGE | setup | 1 | SVC-TENANCY-IDENTITY-1 | cache:idempotency, identity.role, identity.role_permission, identity.segregation_rule | cache:idempotency, cache:resolution, identity.role_permission, platform.audit_record | What this role may do
TenancyService | matrix | setApprovalExternalProvider | PUT | /approval-external-providers/{externalProviderId} | ApprovalExternalProvider | ApprovalExternalProvider | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-MATRIX-1 | approvals.external_provider, cache:idempotency, control.api_client | approvals.external_provider, cache:idempotency | Register a third-party workflow system as an approver
TenancyService | matrix | setApprovalMatrix | PUT | /approval-matrices/{matrixId} | ApprovalMatrix | ApprovalMatrix | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-MATRIX-1 | approvals.external_provider, approvals.matrix, approvals.rule, cache:idempotency | approvals.matrix, approvals.rule, cache:idempotency | Configure what requires approval
TenancyService | region | getRegionSettings | GET | /regions/{regionId}/settings |  | RegionSettings | SCOPE_VIEW | core | 1 | SVC-TENANCY-REGION-1 | cache:resolution, platform.region_settings | cache:resolution | Read region settings
TenancyService | region | updateRegionSettings | PUT | /regions/{regionId}/settings | RegionSettings | RegionSettings | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-REGION-1 | cache:idempotency, platform.region_settings | cache:idempotency, cache:resolution, platform.region_settings | Update region settings
TenancyService | request | createApprovalRequest | POST | /approval-requests | CreateApprovalRequest | ApprovalRequest | APPROVAL_REQUEST | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.delegation, approvals.escalation, approvals.matrix, approvals.request, approvals.request_approver, approvals.rule, cache:idempotency, identity.principal | approvals.escalation, approvals.request, approvals.request_approver, cache:idempotency | Raise a request
TenancyService | request | decideApprovalRequest | POST | /approval-requests/{requestId}/decide |  | ApprovalRequest | APPROVAL_DECIDE | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.delegation, approvals.escalation, approvals.matrix, approvals.request, approvals.request_approver, approvals.rule, cache:idempotency, identity.principal | approvals.decision, approvals.request, approvals.request_approver, cache:idempotency, control.partner_agreement, control.partner_application, control.partner_change_request, marketing.privacy_notice_governance, platform.outbox | Approve, reject, return or ask for information
TenancyService | request | evaluateApprovalRequirement | POST | /approval-requests/evaluate |  | ApprovalRequirement | APPROVAL_VIEW | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, platform.scope | cache:idempotency | Does this need approval, and from whom
TenancyService | request | listApprovalRequests | GET | /approval-requests |  | object | APPROVAL_VIEW | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.delegation, approvals.escalation, approvals.matrix, approvals.request, approvals.request_approver |  | Requests awaiting a decision, or already decided
TenancyService | rota | createRotaAssignment | POST | /rota-assignments | RotaAssignment | RotaAssignment | WORKFORCE_MANAGE | setup | 1 | SVC-TENANCY-ROTA-1 | cache:idempotency, identity.delegated_access, identity.principal, platform.workstation, workforce.rota_assignment | cache:idempotency, workforce.rota_assignment | Put someone on the rota
TenancyService | rota | listRotaAssignments | GET | /rota-assignments |  | object | WORKFORCE_VIEW | core | 1 | SVC-TENANCY-ROTA-1 | identity.principal, workforce.rota_assignment |  | The rota
TenancyService | rota | updateRotaAssignment | PATCH | /rota-assignments/{assignmentId} | UpdateRotaAssignmentRequest | RotaAssignment | WORKFORCE_MANAGE | setup | 1 | SVC-TENANCY-ROTA-1 | cache:idempotency, workforce.rota_assignment | cache:idempotency, workforce.rota_assignment | Move or cancel an assignment
TenancyService | scope | createOrgUnit | POST | /org-units | CreateScopeNodeRequest | OrgUnit | SCOPE_MANAGE | setup | 1 | SVC-TENANCY-SCOPE-1 | cache:idempotency, platform.scope | cache:idempotency, cache:resolution, platform.scope | Create a scope node
TenancyService | scope | listOrgUnits | GET | /org-units |  | object | SCOPE_VIEW | core | 1 | SVC-TENANCY-SCOPE-1 | cache:resolution, platform.scope | cache:resolution | List scope nodes visible to the session
TenancyService | scope | updateOrgUnit | PATCH | /org-units/{orgUnitId} |  | OrgUnit | SCOPE_MANAGE | setup | 1 | SVC-TENANCY-SCOPE-1 | cache:idempotency, platform.scope | cache:idempotency, cache:resolution, platform.scope | Rename or deactivate a scope node
TenancyService | tenancy | getWorkstationHealth | GET | /workstations/{workstationId}/health |  | object | DEVICE_VIEW | core | 1 | SVC-TENANCY-TENANCY-1 | platform.configuration_profile, platform.device, platform.workstation, tenancy.device_firmware, tenancy.device_telemetry |  | A score a manager can sort by, and what is dragging it down
TenancyService | tenancy | listAuditRecords | GET | /audit-records |  | object | AUDIT_VIEW | core | 1 |  | cache:idempotency, identity.principal, platform.audit_record, platform.scope | platform.audit_read | Who did what, where, and when
TenancyService | tenancy | setConfigurationProfile | PUT | /configuration-profiles/{profileId} | SetConfigurationProfileRequest | ConfigurationProfile | TENANT_CONFIGURE | setup | 1 |  | cache:idempotency, platform.configuration_profile | cache:idempotency, cache:resolution, platform.configuration_profile | What a class of workstation is configured to be
TenancyService | tenancy | setVenueSettings | PUT | /venues/{venueId}/settings | VenueSettings | VenueSettings | TENANT_CONFIGURE | setup | 1 | SVC-TENANCY-TENANCY-1 | access.access_point, cache:idempotency, platform.venue_settings | cache:idempotency, cache:resolution, platform.venue_settings | Set support hours, quiet hours, segregated access and alerting
TenancyService | tenancy | setVenueSettingsDefaults | PUT | /venue-settings-defaults | VenueSettings | VenueSettings | TENANT_CONFIGURE | setup | 1 | SVC-TENANCY-TENANCY-1 | cache:idempotency, platform.venue_settings | cache:idempotency, platform.venue_settings | Set the tenant's default for every venue setting
TenancyService | workstation | configureWorkstation | PUT | /workstations/{workstationId} | ConfigureWorkstationRequest | Workstation | WORKSTATION_CONFIGURE | core | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, orders.pos_shift, platform.device, platform.outlet, platform.region_settings, platform.sale_board, platform.workstation | cache:idempotency, platform.device, platform.workstation | Configure a workstation
TenancyService | workstation | createOutlet | POST | /outlets | Outlet | Outlet | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.outlet, platform.outlet_opening_hour, platform.region_settings | cache:idempotency, platform.outlet, platform.outlet_opening_hour | Create an outlet
TenancyService | workstation | createSaleBoard | POST | /sale-boards | SaleBoard | SaleBoard | WORKSTATION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, catalogue.product, catalogue.variant, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | cache:idempotency, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | Create a sale board
TenancyService | workstation | getOutlet | GET | /outlets/{outletId} |  | Outlet | SCOPE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-1 | platform.outlet, platform.outlet_opening_hour |  | Read an outlet
TenancyService | workstation | getWorkstation | GET | /workstations/{workstationId} |  | Workstation | SCOPE_VIEW | core | 1 |  | platform.device, platform.workstation |  | Read a workstation
TenancyService | workstation | listDevices | GET | /devices |  | object | DEVICE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.device |  | List registered devices
TenancyService | workstation | listSaleBoards | GET | /sale-boards |  | array of SaleBoard | SCOPE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.sale_board, platform.sale_board_page, platform.sale_board_tile |  | List sale boards
TenancyService | workstation | updateOutlet | PATCH | /outlets/{outletId} |  | Outlet | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-2 | cache:idempotency, platform.outlet, platform.outlet_opening_hour, platform.region_settings | cache:idempotency, platform.outlet, platform.outlet_opening_hour | Amend an outlet
TenancyService | workstation | updateSaleBoard | PUT | /sale-boards/{saleBoardId} | SaleBoard | SaleBoard | WORKSTATION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-2 | cache:idempotency, catalogue.product, catalogue.variant, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | cache:idempotency, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | Update a sale board
VenueOpsService | asset | deleteMediaAsset | DELETE | /media/{mediaId} |  |  | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, assets.media_usage, cache:idempotency | assets.media_asset, assets.media_usage, cache:idempotency | Delete an asset
VenueOpsService | asset | getMediaAsset | GET | /media/{mediaId} |  | MediaAssetDetail | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.asset_version, assets.media_asset, assets.media_collection, assets.media_collection_member, assets.media_usage, assets.rendition |  | Read an asset with derivatives and usage
VenueOpsService | asset | replaceMediaAsset | POST | /media/{mediaId}/replace |  | MediaReplaceResult | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, assets.media_upload, assets.media_usage, cache:idempotency | assets.asset_version, assets.media_asset, assets.media_fingerprint, assets.media_upload, cache:idempotency | Replace the file behind an asset
VenueOpsService | asset | searchMedia | GET | /media |  | object | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, assets.media_collection_member |  | Search the asset library
VenueOpsService | asset | updateMediaAsset | PATCH | /media/{mediaId} |  | MediaAsset | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-ASSET-2 | assets.media_asset, assets.media_collection, assets.media_usage, cache:idempotency | assets.media_asset, assets.media_collection_member, cache:idempotency | Amend metadata, tags or rights
VenueOpsService | card | getGameCard | GET | /game-cards/{cardCode} |  | GameCard | WALLET_VIEW | core | 1 | SVC-VENUEOPS-CARD-1 | games.card, games.credit_ledger |  | Read a card's balances
VenueOpsService | card | issueGameCard | POST | /game-cards | IssueGameCardRequest | GameCard | ORDER_CREATE | core | 1 | SVC-VENUEOPS-CARD-1 | cache:idempotency, games.card | cache:idempotency, games.card | Issue or activate a game card
VenueOpsService | collection | createCollection | POST | /media/collections |  | Collection | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-COLLECTION-1 | assets.media_collection, cache:idempotency | assets.media_collection, assets.media_collection_member, cache:idempotency | Create a collection
VenueOpsService | collection | listCollections | GET | /media/collections |  | array of Collection | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-COLLECTION-1 | assets.media_collection, assets.media_collection_member |  | List collections
VenueOpsService | departure | getNextTransportDeparture | GET | /transport/departures/next |  | DepartureOffer |  | core | 1 | SVC-VENUEOPS-DEPARTURE-1 | catalogue.channel_capacity, transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | Next Available Trip
VenueOpsService | departure | searchTransportDepartures | GET | /transport/departures |  | object |  | core | 1 | SVC-VENUEOPS-DEPARTURE-1 | catalogue.channel_capacity, transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | Search Trips — departures between two stations on a date
VenueOpsService | departure | updateTransportDeparture | PATCH | /transport/departures/{departureId} |  | Departure | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-DEPARTURE-1 | cache:idempotency, transport.departure | cache:idempotency, transport.departure | Change a departure's coach or capacity
VenueOpsService | entry | getWaitingGuest | GET | /waiting-guests/{entryId} |  | WaitingGuest |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | queue.entry |  | Read a queue entry
VenueOpsService | entry | joinQueue | POST | /waiting-guests | JoinQueueRequest | WaitingGuest |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | cache:idempotency, marketing.loyalty_position, promotions.promotion, queue.entry, queue.queue | cache:idempotency, queue.entry | Join a virtual queue
VenueOpsService | entry | leaveQueue | DELETE | /waiting-guests/{entryId} |  |  |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | cache:idempotency, queue.entry | cache:idempotency, queue.entry | Leave a queue
VenueOpsService | fare | getTransportFareTable | GET | /transport/routes/{routeId}/fare-table |  | FareTable |  | core | 1 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table |  | A route's fares and passenger types
VenueOpsService | fare | quoteTransportFare | POST | /transport/fare-quotes | FareQuoteRequest | FareQuote |  | core | 1 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.pass_type, transport.route_stop |  | Price a one-way trip or a pass for a party
VenueOpsService | fare | setTransportFareTable | PUT | /transport/routes/{routeId}/fare-table | SetFareTableRequest | FareTable | TRANSPORT_PRICE | setup | 1 | SVC-VENUEOPS-FARE-1 | cache:idempotency, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route | cache:idempotency, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table | Set a route's fares and passenger types
VenueOpsService | favourite | deleteFavouriteRoute | DELETE | /transport/favourite-routes/{favouriteId} |  |  |  | core | 1 | SVC-VENUEOPS-FAVOURITE-1 | cache:idempotency, transport.favourite_route | cache:idempotency, transport.favourite_route | Remove a saved route
VenueOpsService | favourite | listMyFavouriteRoutes | GET | /transport/favourite-routes |  | object |  | core | 1 | SVC-VENUEOPS-FAVOURITE-1 | transport.favourite_route |  | The caller's saved routes
VenueOpsService | favourite | saveFavouriteRoute | POST | /transport/favourite-routes |  | FavouriteRoute |  | core | 1 | SVC-VENUEOPS-FAVOURITE-1 | cache:idempotency, transport.favourite_route, transport.station | cache:idempotency, transport.favourite_route | Save route
VenueOpsService | feed | configureQueueFeed | PUT | /queue-feeds/{feedId} | QueueFeed | QueueFeed | QUEUE_MANAGE | setup | 1 |  | cache:idempotency, queue.feed | cache:idempotency, queue.feed | Configure a sensor feed
VenueOpsService | feed | listQueueFeeds | GET | /queue-feeds |  | array of QueueFeed | QUEUE_MANAGE | core | 1 |  | queue.feed |  | List configured sensor feeds
VenueOpsService | general | getTransportDeparture | GET | /transport/departures/{departureId} |  | DepartureOffer |  | core | 1 | SVC-VENUEOPS-GENERAL-1 | catalogue.channel_capacity, transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | One departure, as a guest books it
VenueOpsService | inspection | createInspectionTemplate | POST | /inspection-templates | InspectionTemplate | InspectionTemplate | INSPECTION_MANAGE | setup | 1 | SVC-VENUEOPS-INSPECTION-1 | cache:idempotency, maintenance.inspection_template, maintenance.inspection_template_item | cache:idempotency, maintenance.inspection_template, maintenance.inspection_template_item | Create an inspection template
VenueOpsService | networkImport | applyTransportNetworkImport | POST | /transport/network-imports/{importId}/apply |  | TransportNetworkImport | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-NETWORKIMPORT-1 | cache:idempotency, transport.network_import | cache:idempotency, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable, transport.timetable_run | Apply a previewed import to the network
VenueOpsService | networkImport | importTransportNetwork | POST | /transport/network-imports | ImportTransportNetworkRequest | TransportNetworkImport | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-NETWORKIMPORT-1 | cache:idempotency, transport.network_import | cache:idempotency, transport.network_import | Read a network file into a preview
VenueOpsService | pass | createTransportPassType | POST | /transport/pass-types | CreatePassTypeRequest | PassType | TRANSPORT_PRICE | setup | 1 | SVC-VENUEOPS-PASS-1 | cache:idempotency, transport.pass_type | cache:idempotency, transport.pass_type | Define a multi-trip or unlimited pass
VenueOpsService | pass | listTransportPassOffers | GET | /transport/pass-offers |  | object |  | core | 1 | SVC-VENUEOPS-PASS-1 | transport.fare_matrix_cell, transport.fare_table, transport.pass_type, transport.route, transport.route_stop |  | Multi-trip passes for a pair of stations, priced, with the saving
VenueOpsService | pass | updateTransportPassType | PATCH | /transport/pass-types/{passTypeId} |  | PassType | TRANSPORT_PRICE | setup | 1 | SVC-VENUEOPS-PASS-1 | cache:idempotency, transport.pass_type | cache:idempotency, transport.pass_type | Amend or retire a pass type
VenueOpsService | queue | createQueue | POST | /queues | CreateQueueRequest | Queue | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-QUEUE-1 | cache:idempotency, queue.queue, queue.queue_operating_window | cache:idempotency, queue.queue, queue.queue_operating_window | Create a queue
VenueOpsService | queue | listQueues | GET | /queues |  | object | QUEUE_VIEW | core | 1 | SVC-VENUEOPS-QUEUE-1 | queue.queue, queue.queue_operating_window |  | List queues
VenueOpsService | queue | updateQueue | PATCH | /queues/{queueId} |  | Queue | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-QUEUE-1 | cache:idempotency, queue.queue, queue.queue_operating_window | cache:idempotency, queue.queue | Amend queue configuration
VenueOpsService | resources | cloneResource | POST | /resources/{resourceId}/clone |  | array of Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-1 | cache:idempotency, resources.resource | cache:idempotency, resources.resource | Copy a resource and its configuration into new ones
VenueOpsService | resources | createResource | POST | /resources | Resource | Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-1 | cache:idempotency, resources.resource | cache:idempotency, resources.resource | Define a bookable resource
VenueOpsService | resources | createResourceBlock | POST | /resource-blocks | ResourceBlock | ResourceBlock | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-1 | cache:idempotency, resources.resource_block | cache:idempotency, resources.resource_block | Take a resource out of service for a window, with a reason
VenueOpsService | resources | createResourceHold | POST | /resource-holds | CreateResourceHoldRequest | ResourceHold | ORDER_CREATE | core | 1 | SVC-VENUEOPS-RESOURCES-1 | cache:idempotency, resources.booking, resources.resource, resources.resource_block, resources.resource_reservation, venuemap.map, venuemap.placed_resource | cache:idempotency, resources.resource_reservation | Hold a specific resource picked on the map
VenueOpsService | resources | createResourcePackage | POST | /resource-packages | ResourcePackage | ResourcePackage | RESOURCE_CONFIGURE | setup | 1 |  | cache:idempotency, resources.resource_package, resources.resource_requirement | cache:idempotency, resources.resource_package, resources.resource_requirement | Define a reusable combination
VenueOpsService | resources | extendResourceHold | POST | /resource-holds/{holdId}/extend |  | ResourceHold | ORDER_CREATE | core | 1 |  | cache:idempotency, resources.resource_reservation | cache:idempotency, resources.resource_reservation | Extend a resource hold
VenueOpsService | resources | getMapResourceAvailability | GET | /resource-availability |  | MapResourceAvailability | RESOURCE_VIEW | core | 1 |  | maintenance.work_order, resources.booking, resources.resource, resources.resource_block, resources.resource_reservation, venuemap.map, venuemap.map_version, venuemap.placed_resource |  | Every bookable resource on a venue map, free or taken, in one call
VenueOpsService | resources | getResourceHold | GET | /resource-holds/{holdId} |  | ResourceHold | ORDER_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-3 | resources.resource_reservation |  | Read a resource hold
VenueOpsService | resources | listProductStartTimes | GET | /resource-start-times |  | object | RESOURCE_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-3 | resources.booking, resources.resource, resources.resource_block, resources.resource_requirement, resources.resource_reservation, resources.resource_schedule |  | Start times a space sold by the hour can be booked at, for one length on one day
VenueOpsService | resources | releaseResourceBlock | DELETE | /resource-blocks/{blockId} |  |  | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-3 | cache:idempotency, resources.resource_block | cache:idempotency, resources.resource_block | Put it back into service
VenueOpsService | resources | relinquishResourceHold | DELETE | /resource-holds/{holdId} |  |  | ORDER_CREATE | core | 1 | SVC-VENUEOPS-RESOURCES-3 | cache:idempotency, resources.resource_reservation | cache:idempotency, resources.resource_reservation | Give up a resource hold
VenueOpsService | resources | setExperienceResourceRequirements | PUT | /experiences/{experienceId}/resource-requirements |  | array of ResourceRequirement | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | cache:idempotency, resources.resource_requirement | cache:idempotency, resources.resource_requirement | Bind resource requirements to an experience
VenueOpsService | resources | setResourceLifecycleState | POST | /resources/{resourceId}/state |  | Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | cache:idempotency, resources.resource | cache:idempotency, resources.resource | Move a resource through its lifecycle, with a reason
VenueOpsService | resources | setResourceSchedule | PUT | /resources/{resourceId}/schedule | ResourceSchedule | ResourceSchedule | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | cache:idempotency, resources.resource_schedule | cache:idempotency, resources.resource_schedule | Operating hours, working pattern and bookable slots
VenueOpsService | resources | updateResource | PUT | /resources/{resourceId} | Resource | Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | cache:idempotency, resources.resource | cache:idempotency, resources.resource | Change a resource
VenueOpsService | resources | updateResourcePackage | PUT | /resource-packages/{packageId} | ResourcePackage | ResourcePackage | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-5 | cache:idempotency, resources.resource_package, resources.resource_requirement | cache:idempotency, resources.resource_package, resources.resource_requirement | Change a combination
VenueOpsService | rights | getExpiringRights | GET | /media/rights-expiring |  | array of ExpiringMedia | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-RIGHTS-1 | assets.media_asset, assets.media_usage |  | Assets whose licence is expiring or expired
VenueOpsService | route | createTransportRoute | POST | /transport/routes | CreateTransportRouteRequest | TransportRoute | TRANSPORT_MANAGE | setup | 1 |  | cache:idempotency, transport.route, transport.route_stop, transport.station | cache:idempotency, transport.route, transport.route_stop | Define a route with its ordered stops
VenueOpsService | route | getTransportRouteMap | GET | /transport/routes/{routeId}/map |  | RouteMap |  | core | 1 |  | transport.route, transport.route_stop, transport.station |  | The route drawn for a map, with the journey highlighted
VenueOpsService | route | listTransportRoutes | GET | /transport/routes |  | object |  | core | 1 |  | transport.route, transport.route_stop, transport.station |  | Routes, optionally those serving a pair of stations
VenueOpsService | route | setTransportRouteStatus | PUT | /transport/routes/{routeId}/status |  | TransportRoute | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-ROUTE-2 | cache:idempotency, transport.departure, transport.fare_table, transport.route, transport.route_stop, transport.station | cache:idempotency, transport.route | Activate, suspend or retire a route
VenueOpsService | route | updateTransportRoute | PATCH | /transport/routes/{routeId} |  | TransportRoute | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-ROUTE-2 | cache:idempotency, transport.route, transport.route_stop, transport.station, transport.timetable | cache:idempotency, transport.route, transport.route_stop | Amend a route
VenueOpsService | station | createTransportStation | POST | /transport/stations | CreateStationRequest | Station | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-STATION-1 | cache:idempotency, transport.station | cache:idempotency, transport.station | Add a station
VenueOpsService | station | listTransportStations | GET | /transport/stations |  | object |  | core | 1 | SVC-VENUEOPS-STATION-1 | transport.station |  | Stations of a venue's transport network
VenueOpsService | station | updateTransportStation | PATCH | /transport/stations/{stationId} |  | Station | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-STATION-1 | cache:idempotency, transport.station | cache:idempotency, transport.station | Amend or deactivate a station
VenueOpsService | timetable | createTransportTimetable | POST | /transport/routes/{routeId}/timetables | CreateTimetableRequest | Timetable | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-TIMETABLE-1 | cache:idempotency, transport.route, transport.timetable, transport.timetable_run | cache:idempotency, transport.timetable, transport.timetable_run | Draft a timetable for a route
VenueOpsService | timetable | publishTransportTimetable | POST | /transport/timetables/{timetableId}/publish |  | Timetable | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-TIMETABLE-1 | cache:idempotency, transport.timetable, transport.timetable_run | cache:idempotency, transport.departure, transport.timetable | Publish a timetable and release its departures
VenueOpsService | timetable | withdrawTransportTimetable | POST | /transport/timetables/{timetableId}/withdraw |  | Timetable | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-TIMETABLE-1 | cache:idempotency, transport.timetable, transport.timetable_run | cache:idempotency, transport.timetable | Withdraw a published timetable
VenueOpsService | upload | completeUpload | POST | /media/uploads/{uploadId}/complete |  | MediaAsset | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-UPLOAD-1 | assets.media_asset, assets.media_upload, cache:idempotency | assets.asset_version, assets.media_asset, assets.media_collection_member, assets.media_fingerprint, assets.media_upload, assets.rendition, cache:idempotency | Confirm an upload and create the asset
VenueOpsService | upload | createUpload | POST | /media/uploads |  | UploadTicket | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-UPLOAD-1 | assets.media_upload, cache:idempotency | assets.media_upload, cache:idempotency | Request a signed upload URL
VenueOpsService | venueMap | createVenueMap | POST | /venue-maps | VenueMap | VenueMap | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-1 | assets.media_asset, cache:idempotency, platform.scope, venuemap.map | cache:idempotency, venuemap.map | Start a map
VenueOpsService | venueMap | getVenueMap | GET | /venue-maps/{mapId} |  | VenueMapDetail | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-1 | assets.media_asset, venuemap.map, venuemap.path, venuemap.placed_resource, venuemap.point |  | A map with its points and paths
VenueOpsService | venueMap | getVenueMapGraph | GET | /venue-maps/{mapId}/graph |  | VenueMapGraph | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-1 | cache:resolution, venuemap.map, venuemap.path, venuemap.point | cache:resolution | The navigation graph, ready to route over
VenueOpsService | venueMap | importVenueGeometry | POST | /venue-maps/{mapId}/import |  | VenueMapImportJob | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-1 | cache:idempotency, venuemap.import_job, venuemap.map | cache:idempotency, venuemap.import_job, venuemap.path, venuemap.point | Read a drawing into shapes
VenueOpsService | venueMap | listBookableVenueMaps | GET | /bookable-venue-maps |  | BookableVenueMaps | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-2 | venuemap.map, venuemap.map_version, venuemap.placed_resource |  | The published maps of a venue that carry bookable spots
VenueOpsService | venueMap | publishVenueMap | POST | /venue-maps/{mapId}/publish |  | VenueMap | VENUE_MAP_PUBLISH | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | assets.media_asset, cache:idempotency, platform.outlet, venuemap.map, venuemap.path, venuemap.placed_resource, venuemap.point | cache:idempotency, cache:resolution, venuemap.map, venuemap.map_version | Make the draft the one guests see
VenueOpsService | venueMap | setPlacedResource | POST | /venue-maps/{mapId}/resources | SetPlacedResourceRequest | PlacedResource | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | cache:idempotency, venuemap.placed_resource | cache:idempotency, venuemap.placed_resource | Place or amend a bookable resource on the map
VenueOpsService | venueMap | setVenueMapArtwork | POST | /venue-maps/{mapId}/artwork |  | VenueMap | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | cache:idempotency, venuemap.map | cache:idempotency, venuemap.map | Set the illustrated map guests see, and how it lines up with the plan
VenueOpsService | venueMap | setVenuePoint | POST | /venue-maps/{mapId}/points | SetVenuePointRequest | VenuePoint | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-3 | access.access_point, assets.media_asset, cache:idempotency, catalogue.product, platform.outlet, promotions.bundle, venuemap.map, venuemap.point | cache:idempotency, venuemap.point | Place or amend a point of interest
VenueOpsService | visitPlan | bookVisitPlan | POST | /visit-plans/{planId}/booking |  | VisitPlanBooking |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.product, catalogue.variant, orders.cart, orders.cart_line, promotions.bundle, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, catalogue.inventory_reservation, orders.cart, orders.cart_line, venuemap.visit_plan | Book this plan — turn it into cart lines
VenueOpsService | visitPlan | generateVisitPlan | POST | /visit-plans | VisitPlanRequest | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | cache:idempotency, catalogue.performance, catalogue.product, catalogue.product_eligibility_rule, catalogue.variant, queue.reading, venuemap.map, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, venuemap.visit_plan, venuemap.visit_plan_item | Build a visit plan from the party, the dates and what they like
VenueOpsService | visitPlan | getVisitPlan | GET | /visit-plans/{planId} |  | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | venuemap.visit_plan, venuemap.visit_plan_item |  | A visit plan, at its current version or an earlier one
VenueOpsService | visitPlan | getVisitPlannerOptions | GET | /venues/{venueId}/visit-planner-options |  | VisitPlannerOptions | VENUE_MAP_VIEW | core | 1 |  | venuemap.visit_plan_preset |  | What a guest can choose from when planning a visit
VenueOpsService | visitPlan | listVisitPlanAlternatives | GET | /visit-plans/{planId}/items/{itemId}/alternatives |  | object |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | catalogue.performance, catalogue.product, catalogue.product_eligibility_rule, queue.reading, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item |  | What could take this item's place
VenueOpsService | visitPlan | setVisitPlanPreset | PUT | /venues/{venueId}/visit-plan-presets/{presetKey} | VisitPlanPreset | VisitPlanPreset | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, venuemap.visit_plan_preset | cache:idempotency, venuemap.visit_plan_preset | Add or replace one of a venue's ready-made day plans
VenueOpsService | visitPlan | updateVisitPlan | PUT | /visit-plans/{planId} | VisitPlanUpdate | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-2 | cache:idempotency, catalogue.performance, catalogue.product_eligibility_rule, queue.reading, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, venuemap.visit_plan, venuemap.visit_plan_item | Swap, remove, add, move or undo, as a new version
VenueOpsService | waitTime | getWaitTimes | GET | /queues/wait-times |  | array of WaitTime |  | core | 1 | SVC-VENUEOPS-WAITTIME-1 | queue.entry, queue.queue, queue.reading |  | Wait times across a venue
WalletService | card | loadGameCredits | POST | /game-cards/{cardCode}/load |  | Wallet | WALLET_OPERATE | core | 1 | SVC-WALLET-CARD-1 | cache:idempotency, games.card, wallet.balance, wallet.credit_lot, wallet.wallet | cache:idempotency, games.card, platform.outbox, wallet.balance, wallet.credit_lot, wallet.wallet, wallet.wallet_transaction | Load credits onto a card
WalletService | giftCard | getGiftCard | GET | /gift-cards/{cardCode} |  | GiftCard | WALLET_VIEW | core | 1 | SVC-WALLET-GIFTCARD-1 | wallet.gift_card |  | Check a gift card balance
WalletService | retail | getWalletAutoReloadSetting | GET | /wallets/{walletId}/auto-reload |  | WalletAutoReloadSetting | WALLET_VIEW | core | 1 |  | wallet.auto_reload_setting, wallet.wallet |  | A wallet's own auto top-up, if the holder set one
WalletService | retail | setWalletAutoReloadSetting | PUT | /wallets/{walletId}/auto-reload | WalletAutoReloadSetting | WalletAutoReloadSetting | WALLET_OPERATE | core | 1 |  | cache:idempotency, payments.token, wallet.auto_reload_setting, wallet.funding_rule, wallet.wallet | cache:idempotency, cache:resolution, wallet.auto_reload_setting | Top the wallet up automatically from a stored card when it runs low
WalletService | retail | transferWalletBalance | POST | /wallets/{walletId}/transfer |  | WalletTransaction | WALLET_OPERATE | core | 1 | SVC-WALLET-RETAIL-2 | cache:idempotency, pii.subject, wallet.balance, wallet.credit_lot, wallet.credit_type, wallet.transfer_rule, wallet.wallet, wallet.wallet_transaction | cache:idempotency, wallet.balance, wallet.credit_lot, wallet.wallet, wallet.wallet_transaction | Send balance to another guest
WalletService | wallet | createCreditType | POST | /credit-types | CreditType | CreditType | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-7 | cache:idempotency, wallet.credit_type | cache:idempotency, wallet.credit_type | Define a kind of credit, without a release
WalletService | wallet | getWallet | GET | /wallets/{subjectId} |  | Wallet | WALLET_VIEW | core | 1 | SVC-WALLET-WALLET-1 | wallet.credit_lot, wallet.wallet |  | Read a guest wallet
WalletService | wallet | listWalletTransactions | GET | /wallets/{subjectId}/transactions |  | object | WALLET_VIEW | core | 1 | SVC-WALLET-WALLET-1 | wallet.wallet_transaction |  | Wallet transaction history
WalletService | wallet | publishWalletConfiguration | POST | /wallet-configuration/publish |  | WalletConfigurationVersion | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-1 | cache:idempotency, wallet.accounting_mapping, wallet.authentication_policy, wallet.channel_rule, wallet.configuration_version, wallet.consumption_policy, wallet.credit_type, wallet.funding_rule, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rule_set, wallet.transfer_rule, wallet.wallet_type | cache:idempotency, wallet.configuration_version, wallet.configuration_version_snapshot | Validate and publish the wallet configuration as a version
WalletService | wallet | restoreWalletConfigurationVersion | POST | /wallet-configuration/versions/{version}/restore |  | WalletConfigurationVersion | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-1 | cache:idempotency, wallet.configuration_version, wallet.configuration_version_snapshot | cache:idempotency, wallet.accounting_mapping, wallet.authentication_policy, wallet.channel_rule, wallet.consumption_policy, wallet.credit_type, wallet.funding_rule, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rule_set, wallet.transfer_rule, wallet.wallet_type | Put a previous wallet configuration back as the working draft
WalletService | wallet | setWalletFundingRules | PUT | /wallet-funding-rules | WalletFundingRules | WalletFundingRules | WALLET_CONFIGURE | setup | 1 |  | cache:idempotency, wallet.funding_rule | cache:idempotency, wallet.funding_rule | Amounts, channels, bonuses, limits and velocity
WalletService | wallet | setWalletTransferRules | PUT | /wallet-transfer-rules | WalletTransferRules | WalletTransferRules | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-7 | cache:idempotency, wallet.transfer_rule | cache:idempotency, wallet.transfer_rule | Whether guests may move money to each other, and on what terms
WalletService | wallet | topUpWallet | POST | /wallets/{subjectId}/top-ups |  | Wallet | WALLET_OPERATE | core | 1 |  | cache:idempotency, wallet.balance, wallet.credit_lot, wallet.wallet | cache:idempotency, platform.outbox, wallet.balance, wallet.credit_lot, wallet.wallet, wallet.wallet_transaction | Add value to a wallet
WalletService | wallet | updateCreditType | PUT | /credit-types/{creditTypeId} | CreditType | CreditType | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-7 | cache:idempotency, wallet.credit_type | cache:idempotency, wallet.credit_type | Change a kind of credit
WhiteLabelService | appPublishing | getAppBuild | GET | /tenant-config/app-builds/{appBuildId} |  | AppBuild | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build |  | One app build, with its package and store status
WhiteLabelService | appPublishing | getStoreAccounts | GET | /tenant-config/store-accounts |  | StorePublishingChecklist | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.config_version, whitelabel.store_account, whitelabel.tenant_config |  | The client's store accounts and the publishing checklist
WhiteLabelService | appPublishing | listAppBuilds | GET | /tenant-config/app-builds |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build |  | The tenant's app builds, newest first
WhiteLabelService | appPublishing | requestAppBuild | POST | /tenant-config/app-builds |  | AppBuild | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | cache:idempotency, whitelabel.app_build, whitelabel.config_version, whitelabel.store_account | cache:idempotency, platform.outbox, whitelabel.app_build | Build the branded app for a store
WhiteLabelService | appPublishing | setStoreAccounts | PUT | /tenant-config/store-accounts |  | StorePublishingChecklist | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-2 | cache:idempotency, whitelabel.store_account | cache:idempotency, whitelabel.store_account | Record the client's own Apple and Google store accounts and listings
WhiteLabelService | bookingFlows | createBookingFlowDefinition | POST | /venues/{venueId}/booking-flows | BookingFlow | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Pick a booking flow for a venue
WhiteLabelService | bookingFlows | deleteBookingFlow | DELETE | /booking-flows/{bookingFlowId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | cache:idempotency, catalogue.product, catalogue.product_category, whitelabel.booking_flow | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Remove a booking flow from a venue
WhiteLabelService | bookingFlows | getBookingFlow | GET | /booking-flows/{bookingFlowId} |  | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | whitelabel.booking_flow, whitelabel.booking_flow_step |  | Read one of a venue's booking flows, every step included
WhiteLabelService | bookingFlows | getPublishedBookingFlow | GET | /venues/{venueId}/booking-flow |  | BookingFlow |  | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | catalogue.product, catalogue.product_category, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version |  | The published booking flow a product or category books through
WhiteLabelService | bookingFlows | listBookingFlowTypes | GET | /booking-flow-types |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 |  |  | The booking flow types a venue can pick from, with their steps
WhiteLabelService | bookingFlows | listBookingFlows | GET | /venues/{venueId}/booking-flows |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step |  | A venue's booking flows, in the working draft
WhiteLabelService | bookingFlows | updateBookingFlowDefinition | PATCH | /booking-flows/{bookingFlowId} |  | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Reorder a flow's steps, switch optional steps, change its settings
WhiteLabelService | bookingFlows | validateBookingFlow | POST | /booking-flows/{bookingFlowId}/validate |  | BookingFlowValidation | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow_step | Check a flow against its type
WhiteLabelService | brand | getAppIcons | GET | /tenant-config/app-icons |  | AppIcons | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | whitelabel.tenant_config |  | Read app icon set
WhiteLabelService | brand | getBrandIdentity | GET | /tenant-config/brand |  | BrandIdentity | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | whitelabel.tenant_config |  | Read brand identity
WhiteLabelService | brand | setAppIcons | PUT | /tenant-config/app-icons |  | AppIcons | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set app icons
WhiteLabelService | brand | setBrandIdentity | PUT | /tenant-config/brand | BrandIdentity | BrandIdentity | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set logo, favicon and splash
WhiteLabelService | branding | getBookingFlowConfig | GET | /tenant-config/booking-flow |  | BookingFlowConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRANDING-1 | whitelabel.tenant_config |  | How the guest booking flow looks and steps
WhiteLabelService | branding | setBookingFlowConfig | PUT | /tenant-config/booking-flow | BookingFlowConfig | BookingFlowConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRANDING-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.tenant_config | Set how the guest booking flow looks and steps
WhiteLabelService | content | createBanner | POST | /tenant-config/banners | Banner | Banner | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.banner | cache:idempotency, whitelabel.banner | Create a banner
WhiteLabelService | content | createContentPage | POST | /tenant-config/pages | ContentPage | ContentPage | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.content_page | cache:idempotency, whitelabel.content_page | Create a content page
WhiteLabelService | content | createGuidedChoice | POST | /venues/{venueId}/guided-choices | GuidedChoice | GuidedChoice | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Set up Help me choose for a venue
WhiteLabelService | content | createPromoBlock | POST | /tenant-config/promo-blocks | PromoBlock | PromoBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Create a promotional block
WhiteLabelService | content | deleteBanner | DELETE | /tenant-config/banners/{bannerId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.banner, whitelabel.tenant_config | Delete a banner
WhiteLabelService | content | deleteContentPage | DELETE | /tenant-config/pages/{pageId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.content_page, whitelabel.tenant_config | Delete a content page
WhiteLabelService | content | deleteGuidedChoice | DELETE | /guided-choices/{guidedChoiceId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Delete a Help me choose set-up, or dismiss a suggestion
WhiteLabelService | content | deletePromoBlock | DELETE | /tenant-config/promo-blocks/{promoBlockId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Delete a promotional block
WhiteLabelService | content | getPublishedGuidedChoice | GET | /venues/{venueId}/guided-choice |  | GuidedChoice |  | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | The venue's published Help me choose
WhiteLabelService | content | listBanners | GET | /tenant-config/banners |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.banner |  | List banners
WhiteLabelService | content | listContentPages | GET | /tenant-config/pages |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.content_page |  | List custom content pages
WhiteLabelService | content | listGuidedChoices | GET | /venues/{venueId}/guided-choices |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | List a venue's Help me choose set-ups
WhiteLabelService | content | listPolicies | GET | /tenant-config/policies |  | array of Policy | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-4 | whitelabel.policy |  | List legal policies
WhiteLabelService | content | listPromoBlocks | GET | /tenant-config/promo-blocks |  | array of PromoBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-4 | whitelabel.promo_block |  | List promotional blocks
WhiteLabelService | content | listPublishedContentPages | GET | /storefront/pages |  | object |  | core | 1 | SVC-WHITELABEL-CONTENT-4 |  |  | The live content pages, readable before sign-in
WhiteLabelService | content | listPublishedFaqs | GET | /storefront/faqs |  | array of PublishedFaqCategory |  | core | 1 | SVC-WHITELABEL-CONTENT-4 |  |  | The published FAQs, readable before sign-in
WhiteLabelService | content | listPublishedPolicies | GET | /storefront/policies |  | array of PublishedPolicy |  | core | 1 | SVC-WHITELABEL-CONTENT-5 |  |  | The tenant's current legal policies, readable before sign-in
WhiteLabelService | content | previewGuidedChoice | POST | /venues/{venueId}/guided-choice-previews | GuidedChoicePreviewRequest | GuidedChoicePreview | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-8 |  |  | What a draft Help me choose leaves, combination by combination
WhiteLabelService | content | proposeGuidedChoice | POST | /venues/{venueId}/guided-choice-suggestions |  | GuidedChoice |  | core | 1 | SVC-WHITELABEL-CONTENT-5 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Record an AI-proposed Help me choose set-up for review
WhiteLabelService | content | publishGuidedChoice | POST | /guided-choices/{guidedChoiceId}/publish |  | GuidedChoice | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-CONTENT-5 | cache:idempotency, whitelabel.booking_flow, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice | Publish a Help me choose set-up to guests
WhiteLabelService | content | setFaqs | PUT | /tenant-config/faqs |  | array of FaqCategory | TENANT_CONFIGURE | setup | 1 | SVC-WHITELABEL-CONTENT-5 | cache:idempotency, whitelabel.faq_category, whitelabel.faq_entry | cache:idempotency, whitelabel.faq_category, whitelabel.faq_entry | Set FAQ categories and entries
WhiteLabelService | content | setPolicy | PUT | /tenant-config/policies/{policyKind} |  | Policy | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.policy | cache:idempotency, whitelabel.policy | Publish a policy version
WhiteLabelService | content | unpublishGuidedChoice | POST | /guided-choices/{guidedChoiceId}/unpublish |  | GuidedChoice | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice | Take a Help me choose set-up off the guest app
WhiteLabelService | content | updateBanner | PATCH | /tenant-config/banners/{bannerId} |  | Banner | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.banner | cache:idempotency, whitelabel.banner | Amend or activate a banner
WhiteLabelService | content | updateContentPage | PUT | /tenant-config/pages/{pageId} | UpdateContentPageRequest | ContentPage | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.content_page | cache:idempotency, whitelabel.content_page | Amend a content page
WhiteLabelService | content | updateGuidedChoice | PATCH | /guided-choices/{guidedChoiceId} |  | GuidedChoice | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-7 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Edit a Help me choose set-up, or review a suggestion
WhiteLabelService | content | updatePromoBlock | PATCH | /tenant-config/promo-blocks/{promoBlockId} |  | PromoBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-7 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Amend a promotional block
WhiteLabelService | homepage | getHomepageLayout | GET | /tenant-config/homepage |  | HomepageLayout | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-HOMEPAGE-1 | whitelabel.homepage_layout, whitelabel.homepage_section |  | Read homepage layout
WhiteLabelService | homepage | listLandingPageTemplates | GET | /landing-page-templates |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-HOMEPAGE-1 | whitelabel.homepage_layout, whitelabel.homepage_section |  | The landing-page templates TICVAI provides
WhiteLabelService | homepage | setHomepageLayout | PUT | /tenant-config/homepage | HomepageLayout | HomepageLayout | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-HOMEPAGE-1 | cache:idempotency, whitelabel.homepage_layout, whitelabel.homepage_section | cache:idempotency, whitelabel.homepage_layout, whitelabel.homepage_section | Set homepage section order
WhiteLabelService | modules | getFeatureToggles | GET | /tenant-config/features |  | array of FeatureToggle | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:resolution, whitelabel.feature_toggle | cache:resolution | Read tenant feature toggles
WhiteLabelService | modules | getModuleEnablement | GET | /tenant-config/modules |  | array of ModuleEnablement | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:resolution, control.contract, control.licence_add_on, control.plan, whitelabel.module_enablement | cache:resolution | Read module enablement
WhiteLabelService | modules | setFeatureToggles | PUT | /tenant-config/features |  | array of FeatureToggle | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:idempotency, whitelabel.feature_toggle | cache:idempotency, cache:resolution, whitelabel.feature_toggle | Set feature toggles
WhiteLabelService | modules | setLanguages | PUT | /tenant-config/languages |  | LanguageConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:idempotency, whitelabel.banner, whitelabel.content_page, whitelabel.faq_entry, whitelabel.policy, whitelabel.promo_block, whitelabel.tenant_config, whitelabel.ui_string_pack | cache:idempotency, whitelabel.tenant_config | Set enabled languages and default
WhiteLabelService | modules | setModuleEnablement | PUT | /tenant-config/modules |  | array of ModuleEnablement | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-2 | cache:idempotency, control.contract, control.licence_add_on, control.plan, whitelabel.module_enablement, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.module_enablement, whitelabel.tenant_config | Enable or disable modules
WhiteLabelService | navigation | buildDeepLink | POST | /deep-links |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 | whitelabel.config_version, whitelabel.custom_domain |  | Build a deep link to a target
WhiteLabelService | navigation | getDeepLinkScheme | GET | /deep-links |  | DeepLinkScheme | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 | whitelabel.config_version, whitelabel.custom_domain |  | The published deep-link scheme
WhiteLabelService | navigation | getNavigation | GET | /tenant-config/navigation |  | NavigationConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 | cache:resolution, whitelabel.navigation_config, whitelabel.navigation_item | cache:resolution | Read navigation
WhiteLabelService | navigation | setHeader | PUT | /tenant-config/header | HeaderConfig | HeaderConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Configure the header
WhiteLabelService | navigation | setNavigation | PUT | /tenant-config/navigation | NavigationConfig | NavigationConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-2 | cache:idempotency, whitelabel.navigation_config, whitelabel.navigation_item | cache:idempotency, cache:resolution, whitelabel.navigation_config, whitelabel.navigation_item | Set main and overflow navigation
WhiteLabelService | overview | getPublishedTenantConfig | GET | /storefront/tenant-config |  | PublishedTenantConfig |  | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.analytics_provider, whitelabel.config_version, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.tenant_config |  | The published guest-facing configuration, before anyone signs in
WhiteLabelService | overview | getTenantAppStatus | GET | /tenant-config/status |  | TenantAppStatus |  | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.config_version, whitelabel.content_page, whitelabel.module_enablement, whitelabel.tenant_config |  | App status and recent changes
WhiteLabelService | overview | getTenantConfig | GET | /tenant-config |  | TenantConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.tenant_config |  | Full working configuration
WhiteLabelService | overview | listAnalyticsProviders | GET | /tenant-config/analytics-providers |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.analytics_provider |  | The analytics platforms the storefront and app report to
WhiteLabelService | overview | recordStorefrontSessionEvents | POST | /storefront/session-events | WhiteLabelStorefrontSessionBatch |  |  | core | 1 | SVC-WHITELABEL-OVERVIEW-2 |  | platform.outbox | Report a batch of browsing behaviour for fraud prevention, hashed and without personal data
WhiteLabelService | overview | setAnalyticsProvider | PUT | /tenant-config/analytics-providers/{analyticsProviderId} | StorefrontAnalyticsProvider | StorefrontAnalyticsProvider | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency, whitelabel.analytics_provider | cache:idempotency, whitelabel.analytics_provider | Connect the storefront and app to an analytics platform
WhiteLabelService | overview | setMaintenanceMode | PUT | /tenant-config/status |  | TenantAppStatus | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency, whitelabel.content_page, whitelabel.module_enablement, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Enable or clear maintenance mode, and set the live app status
WhiteLabelService | publishing | createPreview | POST | /tenant-config/preview |  | Preview | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, platform.outbox, whitelabel.tenant_config | Generate a preview link
WhiteLabelService | publishing | diffConfigVersion | GET | /tenant-config/versions/{version}/diff |  | ConfigDiff | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.config_version, whitelabel.tenant_config |  | Compare a version against the working draft
WhiteLabelService | publishing | exportSitePackage | POST | /site-package |  | SitePackage | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | cache:idempotency, whitelabel.config_version, whitelabel.site_package | cache:idempotency, platform.outbox, whitelabel.site_package | Generate a site package (self-hosted)
WhiteLabelService | publishing | getPublishReviewPolicy | GET | /publish-review-policy |  | PublishReviewPolicy | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.publish_review_policy |  | Whether publishing needs a review
WhiteLabelService | publishing | getSitePackage | GET | /site-package/{packageId} |  | SitePackage | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.site_package |  | A site package and its download link
WhiteLabelService | publishing | getSiteSetupProgress | GET | /tenant-config/site-setup |  | SiteSetupProgress | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.booking_flow, whitelabel.config_version, whitelabel.site_setup_progress, whitelabel.tenant_config |  | Where the tenant is in the Site Builder
WhiteLabelService | publishing | listConfigVersions | GET | /tenant-config/versions |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.config_version |  | Version history
WhiteLabelService | publishing | publishTenantConfig | POST | /tenant-config/publish |  | ConfigVersion | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | cache:idempotency, whitelabel.analytics_provider, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.content_page, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.publish_review_policy, whitelabel.tenant_config | approvals.request, cache:idempotency, platform.outbox, whitelabel.config_version, whitelabel.content_page | Publish the working draft
WhiteLabelService | publishing | restoreConfigVersion | POST | /tenant-config/versions/{version}/restore |  | TenantConfig | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.booking_flow, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.tenant_config | Restore a previous version
WhiteLabelService | publishing | setPublishReviewPolicy | PUT | /publish-review-policy | PublishReviewPolicy | PublishReviewPolicy | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | cache:idempotency, whitelabel.publish_review_policy | approvals.matrix, cache:idempotency, whitelabel.publish_review_policy | Switch the publish review step on or off
WhiteLabelService | publishing | setSiteSetupProgress | PUT | /tenant-config/site-setup | SiteSetupProgress | SiteSetupProgress | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | cache:idempotency, whitelabel.config_version, whitelabel.site_setup_progress | cache:idempotency, whitelabel.site_setup_progress | Save the Site Builder's progress
WhiteLabelService | publishing | validateTenantConfig | POST | /tenant-config/validate |  | ConfigValidationReport | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.content_page, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.publish_review_policy, whitelabel.tenant_config | cache:idempotency | Validate the working draft
WhiteLabelService | theme | getFonts | GET | /tenant-config/fonts |  | FontConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | whitelabel.tenant_config |  | Read font configuration
WhiteLabelService | theme | getTheme | GET | /tenant-config/theme |  | Theme | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | cache:resolution, whitelabel.tenant_config | cache:resolution | Read colour theme
WhiteLabelService | theme | setFonts | PUT | /tenant-config/fonts | FontConfig | FontConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set fonts
WhiteLabelService | theme | setTheme | PUT | /tenant-config/theme | Theme | Theme | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.tenant_config | Set colour theme
WhiteLabelService | white-label | claimCustomDomain | POST | /tenant-domains |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | cache:idempotency, control.tenant, whitelabel.custom_domain | cache:idempotency, platform.outbox, whitelabel.custom_domain | Claim a domain and get a verification token
WhiteLabelService | white-label | getPlatformSubdomain | GET | /platform-subdomain |  | PlatformSubdomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 |  |  | The tenant's platform subdomain
WhiteLabelService | white-label | listCustomDomains | GET | /tenant-domains |  | array of CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | whitelabel.custom_domain |  | The domains this tenant has claimed
WhiteLabelService | white-label | regenerateDomainToken | POST | /tenant-domains/{domainId}/token |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | cache:idempotency, whitelabel.custom_domain | cache:idempotency, platform.outbox, whitelabel.custom_domain | Issue a new validation token
WhiteLabelService | white-label | relinquishCustomDomain | DELETE | /tenant-domains/{domainId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | cache:idempotency, whitelabel.custom_domain | cache:idempotency, platform.outbox, whitelabel.custom_domain | Give the domain up
WhiteLabelService | white-label | setPrimaryDomain | POST | /tenant-domains/{domainId}/primary |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | cache:idempotency, whitelabel.custom_domain | cache:idempotency, platform.outbox, whitelabel.custom_domain | Make a domain the primary one
WhiteLabelService | white-label | verifyCustomDomain | POST | /tenant-domains/{domainId}/verify |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | cache:idempotency, whitelabel.custom_domain | cache:idempotency, platform.outbox, whitelabel.custom_domain | Check the record and issue the certificate
WhiteLabelService | whiteLabel | createContentBlock | POST | /content-blocks | ContentBlock | ContentBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, marketing.segment, whitelabel.content_block | cache:idempotency, whitelabel.content_block | Author a block of content
WhiteLabelService | whiteLabel | listContentBlocks | GET | /content-blocks |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | whitelabel.content_block |  | The content blocks of a page
WhiteLabelService | whiteLabel | publishContentBlock | POST | /content-blocks/{blockId}/publish |  | ContentBlock | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, identity.principal, whitelabel.content_block, whitelabel.publish_review_policy | approvals.request, cache:idempotency, cache:resolution, whitelabel.content_block | Publish now, or schedule it
WhiteLabelService | whiteLabel | setFooter | PUT | /footer | FooterConfig | FooterConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link | cache:idempotency, cache:resolution, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link | Footer columns, legal links and social
WhiteLabelService | whiteLabel | updateContentBlock | PATCH | /content-blocks/{blockId} |  | ContentBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-2 | cache:idempotency, whitelabel.content_block | cache:idempotency, whitelabel.content_block | Change a draft content block

## API schemas
Contract | Schema | Fields | Stored as | Used as request | Used as response | Operations | Description
access | AccessAccessPointGroup | 8 | access.access_point_group | 1 | 1 | setAccessPointGroup | A named group of access points in one venue (e.g.
access | AccessCredentialPolicy | 32 | access.credential_policy | 0 | 1 | setDeviceBindingPolicy | One credential policy of one kind for a venue - activation and display rule, transfer policy, Virtual Ticket identity configuration or device binding policy; merges the proposed credential_display_ru…
access | AccessDeviceBinding | 15 | access.device_binding | 0 | 1 | bindCredentialDevice | One guest device bound to a credential, with its registration, last activation and security status; the binding policy in force is a deviceBinding row of access.credential_policy (declared 29 Septemb…
access | AccessGateModePolicy | 12 | access.gate_mode_policy | 1 | 1 | setGateModePolicy | One policy for a non-standard gate mode (free spin or count only as freeFlow, emergency as dropArm): who may activate it, on which gate group, whether a reason is required, emergency code, notificati…
access | AccessPoint | 21 | access.access_point | 0 | 5 | createAccessPoint, setAccessPointDirection, setAccessPointGeofence, setTurnstileMode, updateAccessPoint
access | AccessPointGeofence | 5 |  | 1 | 0 | setAccessPointGeofence | Where a handheld may validate for one access point, and what happens outside it.
access | AdmissionRules | 21 | access.admission_rules | 2 | 2 | createAdmissionRules, updateAdmissionRules
access | BiometricVerificationProfileBuilderInput | 11 | none — request only; applied to `access.biometric_profile` (with `access.configuration_change`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setBiometricVerificationProfile | What Biometric Verification Profile Builder submits.
access | BiometricVerificationProfileBuilderView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setBiometricVerificationProfile | What Biometric Verification Profile Builder displays.
access | BlacklistEntry | 9 | access.blacklist | 0 | 1 | addBlacklistEntry
access | BleBeaconGeofenceConfigurationInput | 13 | none — request only; applied to `access.access_point` (with `access.configuration_change`, `access.device_placement`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setBleBeaconGeofence | What BLE Beacon & Geofence Configuration submits.
access | BleBeaconGeofenceConfigurationView | 13 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setBleBeaconGeofence | What BLE Beacon & Geofence Configuration displays.
access | CreateAccessPointRequest | 7 |  | 1 | 0 | createAccessPoint
access | CredentialActivationDisplayRulesInput | 6 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setCredentialActivationDisplay | What Credential Activation & Display Rules submits (decided 29 September, VM close-out).
access | CredentialActivationDisplayRulesView | 5 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setCredentialActivationDisplay | What Credential Activation & Display Rules displays.
access | CredentialDeviceBindingInput | 5 | none — request only; written as access.device_binding (declared 29 September, writers pass) | 1 | 0 | bindCredentialDevice
access | DeviceBindingPolicyInput | 4 | none — request only; written as the deviceBinding row of access.credential_policy (declared 29 September, writers pass) | 1 | 0 | setDeviceBindingPolicy
access | Entitlement | 40 | access.entitlement | 0 | 1 | getEntitlement | What a guest actually holds.
access | FaceMatchingVerificationThresholdsInput | 13 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setFaceMatchingVerification | What Face Matching & Verification Thresholds submits (decided 29 September, VM close-out).
access | FaceMatchingVerificationThresholdsView | 12 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFaceMatchingVerification | What Face Matching & Verification Thresholds displays.
access | FacePassEnrollmentConfigurationInput | 11 | none — request only; applied to `access.biometric_profile` (with `access.configuration_change`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setFacePassEnrollment | What Face Pass Enrollment Configuration submits.
access | FacePassEnrollmentConfigurationView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFacePassEnrollment | What Face Pass Enrollment Configuration displays.
access | FacePassEnrolment | 15 | pii.subject_biometric | 0 | 3 | enrolFacePass, enrolFaceTag, getFacePassEnrolment | 3.2.43.
access | FaceTagTemporaryEnrollmentInput | 10 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setFaceTagTemporaryEnrollment | What Face Tag Temporary Enrollment submits (decided 29 September, VM close-out).
access | FaceTagTemporaryEnrollmentView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFaceTagTemporaryEnrollment | What Face Tag Temporary Enrollment displays.
access | ManualOverrideSupervisorApprovalInput | 7 | none — request only; applied to `access.scan_event`, the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | approveManualOverrideSupervisor | What Manual Override & Supervisor Approval submits.
access | ManualOverrideSupervisorApprovalView | 7 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | approveManualOverrideSupervisor | What Manual Override & Supervisor Approval displays.
access | ParkingEntitlement | 12 | access.parking_entitlement | 0 | 2 | getParkingEntitlement, updateParkingEntitlement | Issued at payment of an order that contains a parking product (decided 28 September, audit R166).
access | ParkingFacility | 14 | access.parking_facility | 1 | 1 | setParkingFacility
access | UpdateParkingEntitlementRequest | 3 | none — request only; applied to access.parking_entitlement | 1 | 0 | updateParkingEntitlement | The body of updateParkingEntitlement: only what changes.
access | VirtualTicketIdentityMasterRecordConfigurationInput | 10 | none — request only; applied to `access.credential_policy` (with `access.configuration_change`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setVirtualTicketIdentity | What Virtual Ticket Identity & Master Record Configuration submits.
access | VirtualTicketIdentityMasterRecordConfigurationView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVirtualTicketIdentity | What Virtual Ticket Identity & Master Record Configuration displays.
access | VisualAccessRuleBuilderInput | 8 | none — request only; applied to `access.admission_rules` (with `access.configuration_change`, `access.entry_rule_point`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setVisualAccessRule | What Visual Access Rule Builder submits.
access | VisualAccessRuleBuilderView | 8 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVisualAccessRule | What Visual Access Rule Builder displays.
ai | AiAnswerFeedback | 11 | ai.answer_feedback | 0 | 1 | recordAnswerFeedback | What a person thought of an answer (AIC-062).
ai | AiAssistantProfile | 14 | ai.assistant_profile | 1 | 1 | configureAssistantProfile | One assistant runtime, many profiles (design 5.10, C5; AIC-069..080).
ai | AiByokEnablement | 11 | ai.byok_enablement | 1 | 2 | getAiByokEnablement, setAiByokEnablement | Whether a tenant may bring its own model key (decided 29 September, design 8 on 5.9).
ai | AiCapabilityRegistration | 18 | ai.capability | 0 | 1 | pauseAiCapability | An entry in the capability registry (design 3.1 Registry, AIC-144, AIC-145; ADM-520).
ai | AiContentDraftSet | 4 | none — each draft is an ai.proposed_action row (kind content); proposedActionId is its id | 0 | 1 | proposeMarketingContent | What proposeMarketingContent drafted: one entry per variant per locale.
ai | AiConversation | 10 | ai.conversation | 0 | 1 | createAiConversation
ai | AiEffectivePolicy | 8 | none — resolved from published policy versions, exceptions and ai.policy | 0 | 1 | getEffectiveAiPolicy | The policy in force for a capability at a scope (AIC-153, AIC-165; ADM-525, ADM-528): the intersection of the capability, governance policy and the tenant or venue AI policy, with where each part cam…
ai | AiEvaluationRun | 14 | ai.eval_run | 0 | 1 | runAiEvaluation | One evaluation of a candidate against its baseline: offline golden set, backtest or shadow comparison.
ai | AiForecastDefinition | 20 | ai.forecast_definition | 1 | 1 | setForecastDefinition | What is forecast, at what grain, for what horizon, how often and by which producer (design 3.1 Forecast, 5.2; ADM-500).
ai | AiForecastScenario | 9 | ai.forecast_scenario | 1 | 1 | createForecastScenario | A what-if against a published version (ADM-507, ADM-517, BO-931).
ai | AiForecastVersion | 18 | ai.forecast_version | 0 | 2 | publishForecastVersion, runForecast | An immutable forecast version (AIP-032): producer, model version, data cut-off, horizon and status.
ai | AiGovernanceDecision | 7 | none — computed; a block also writes ai.decision_record | 0 | 1 | evaluateAiGovernance | The governance decision point's answer (design 3.8, AIC-166): outcome, policy version, conditions, required approvals and an explanation.
ai | AiGovernancePolicyVersion | 12 | ai.governance_policy_version | 0 | 2 | createAiGovernancePolicyDraft, publishAiGovernancePolicy | One version of a governance policy.
ai | AiGuidedChoiceSuggestion | 13 | ai.guided_choice_suggestion | 0 | 2 | getGuidedChoiceSuggestion, suggestGuidedChoice | One Help me choose suggestion for a venue (design 3.11, decided 29 September; C7 at autonomy "suggest").
ai | AiHistoryImport | 19 | ai.history_import | 0 | 2 | getVenueHistoryImport, importVenueHistory | One import of a venue's own history (29 September, AI functions review).
ai | AiIncident | 20 | ai.incident | 0 | 2 | containAiIncident, openAiIncident | An AI governance incident (ADM-556): detection, containment, investigation, remediation and closure.
ai | AiInsight | 22 | ai.insight | 0 | 1 | decideAiInsight | An insight with a lifecycle (AIP-181): new, reviewed, accepted or rejected, actioned, measured.
ai | AiIntervention | 11 | ai.intervention | 0 | 1 | overrideAiDecision | A person stepping in (AIC-187, ADM-535, ADM-536): an override, pause, resume, stop, retry or rollback, with the original AI decision and the human one side by side.
ai | AiMessage | 15 | ai.message | 0 | 1 | sendAiMessage
ai | AiMetricChangeExplanation | 9 | none — computed; written as an ai.insight of kind rootCause when kept | 0 | 1 | explainMetricChange | Why a metric changed (AIP-176..180, ANL-056): drivers with their contribution, computed from the semantic layer.
ai | AiModel | 20 | ai.model | 1 | 1 | setAiModel | The model catalogue (design 3.1 Registry, 3.3; AIC-013, AIC-026).
ai | AiOperationalRequirement | 17 | ai.operational_requirement | 0 | 1 | decideOperationalRequirement | A requirement derived from a forecast version (design 2.2 C step 6, AIP-067): staff, POS, gates, F&B, stock or resources, computed with the tenant's productivity standards.
ai | AiPolicy | 32 | ai.policy | 1 | 2 | getAiPolicy, setAiPolicy
ai | AiPolicyException | 13 | ai.policy_exception | 0 | 1 | revokeAiPolicyException | A temporary, recorded exception to a governance policy (AIC-162, ADM-526): an expiry, an approver and compensating controls.
ai | AiPolicySimulation | 4 | none — computed; summary kept on ai.governance_policy_version.simulationSummary | 0 | 1 | simulateAiGovernancePolicy | What a draft policy version would have decided over recorded decisions and the test cases (ADM-527).
ai | AiPromptTemplate | 13 | ai.prompt_template | 0 | 1 | publishPromptTemplate | The prompt registry (design 3.1 Registry, AIC-022).
ai | AiProvider | 27 | ai.provider | 0 | 1 | listAiProviders
ai | AiRecommendationResult | 5 | none — written as ai.rec_decision after the response | 0 | 1 | decideRecommendations | The recommendation slot's content (design 2.2 A).
ai | AiRelease | 18 | ai.release | 0 | 2 | promoteAiRelease, rollbackAiRelease | The release pointer per capability and tenant (design 3.5): draft, offline evaluation, shadow, canary, production, monitored.
ai | AiUsageReport | 7 | none — aggregated from ai.activity | 0 | 1 | getAiUsage
ai | AiVenueSettings | 15 | ai.venue_settings | 1 | 2 | getAiVenueSettings, setAiVenueSettings | The venue AI profile (29 September, AI functions review): the figures a venue gives at onboarding so every data-driven answer is useful before it has history.
ai | IndexJob | 14 | ai.index_job | 0 | 1 | reindexSource
ai | IndexSource | 16 | ai.index_source | 1 | 1 | setIndexSource | One declaration per indexed table (table is unique; the id is the identity).
ai | KnowledgeCollection | 12 | ai.knowledge_collection | 1 | 1 | createKnowledgeCollection
ai | KnowledgeDocument | 13 | ai.knowledge_document | 1 | 1 | ingestKnowledgeDocument
ai | ProposedAction | 29 | ai.proposed_action | 0 | 2 | decideProposedAction, listProposedActions
ai | SearchResult | 10 | none — computed | 0 | 1 | semanticSearch
ai | Suggestion | 13 | ai.suggestion | 0 | 1 | requestSuggestion | One answer to one question, with its reasoning and its confidence.
ai | TranslationProposals | 4 | none — each draft is an ai.proposed_action row (one per block and language), applied to the block only when an operator saves it through the block's own write (ADR-0020); CHG-FXC-004 | 0 | 2 | getTranslationProposals, proposeTranslations | What proposeTranslations drafted.
ai | VenueLabelProposal | 8 | none — each proposal is an ai.proposed_action row; proposalId is its id | 0 | 1 | proposeVenueLabels | 1.4.24.
approvals | ApprovalDelegation | 13 | approvals.delegation | 1 | 1 | createApprovalDelegation
approvals | ApprovalExternalProvider | 16 | approvals.external_provider | 1 | 1 | setApprovalExternalProvider | 11.1.65 (29 September, build pass).
approvals | ApprovalMatrix | 7 | approvals.matrix | 1 | 1 | setApprovalMatrix | Which matrix routes a request, and which version of it (ADAM CR-102, option 1, accepted 15 October 2026; CHG-R10ID-015).
approvals | ApprovalMatrixMultiLevelApprovalConfigurationInput | 19 | none — request only; written as one approvals.rule row (ApprovalRule) of the approvals.matrix for the kind and scope it names, field by field in approveMatrixMultiLevel (CHG-FXC-005) | 1 | 0 | approveMatrixMultiLevel | What Approval Matrix & Multi-Level Approval Configuration submits.
approvals | ApprovalMatrixMultiLevelApprovalConfigurationView | 19 | none — projection over approvals state, assembled at read time from tables that already exist | 0 | 1 | approveMatrixMultiLevel | What Approval Matrix & Multi-Level Approval Configuration displays.
approvals | ApprovalRequest | 40 | approvals.request + approvals.escalation + approvals.request_approver | 0 | 2 | createApprovalRequest, decideApprovalRequest
approvals | ApprovalRequirement | 6 | none — computed | 0 | 1 | evaluateApprovalRequirement | The answer to "does this need approval", returned before the action.
approvals | CreateApprovalRequest | 11 | none — request only | 1 | 0 | createApprovalRequest
approvals | RolesAuthorityDelegationApprovalLimitsInput | 19 | none — request only; written as one approvals.delegation row (ApprovalDelegation), field by field in approveRoleAuthorityDelegation (CHG-FXC-005) | 1 | 0 | approveRoleAuthorityDelegation | What Roles, Authority, Delegation & Approval Limits submits.
approvals | RolesAuthorityDelegationApprovalLimitsView | 19 | none — projection over approvals state, assembled at read time from tables that already exist | 0 | 1 | approveRoleAuthorityDelegation | What Roles, Authority, Delegation & Approval Limits displays.
assets | Collection | 7 | assets.media_collection | 0 | 2 | createCollection, listCollections
assets | ExpiringMedia | 9 | none — computed | 0 | 1 | getExpiringRights
assets | MediaAsset | 29 | assets.media_asset | 0 | 2 | completeUpload, updateMediaAsset
assets | MediaAssetDetail | 33 | assets.media_asset | 0 | 1 | getMediaAsset
assets | MediaReplaceResult | 4 | none — computed | 0 | 1 | replaceMediaAsset
assets | UploadTicket | 12 | assets.media_upload | 0 | 1 | createUpload
catalogue | AlternativeCode | 6 | catalogue.alternative_code | 0 | 2 | listAlternativeCodes, setAlternativeCodes
catalogue | BookingVelocityTimeToEventRuleBuilderInput | 12 | none — request only; applied to `pricing.dynamic_price_action` (with `catalogue.audit_entry`, `pricing.dynamic_price_condition`, `pricing.dynamic_price_rule`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setBookingVelocityTime | What Booking Velocity & Time-to-Event Rule Builder submits.
catalogue | BookingVelocityTimeToEventRuleBuilderView | 12 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setBookingVelocityTime | What Booking Velocity & Time-to-Event Rule Builder displays.
catalogue | BulkPriceResult | 4 |  | 0 | 1 | bulkChangePrices | 2.9.9.
catalogue | BundleSummary | 10 | none — projection over bundle | 0 | 1 | publishBundle | One published catalogue bundle — the signed snapshot terminals pull (ADR-0013).
catalogue | CatalogueBundle | 12 | catalogue.published_bundle | 0 | 1 | getLatestBundle
catalogue | CatalogueImportJob | 26 | catalogue.import_job | 0 | 1 | commitCatalogueImport | 1.4.2.
catalogue | ChannelConnection | 23 | catalogue.channel_connection | 1 | 1 | setChannelConnectionConfiguration | How TICVAI technically reaches a channel (29 September, data model DM3).
catalogue | ChannelCreationProfileConfigurationInput | 28 | none — request only; applied to `catalogue.sales_channel` (with `catalogue.audit_entry`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | createChannelProfile | What Channel Creation & Profile Configuration submits.
catalogue | ChannelCreationProfileConfigurationView | 31 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | createChannelProfile | What Channel Creation & Profile Configuration displays.
catalogue | ChannelFeesPaymentFulfillmentConfigurationInput | 6 | none — request only; applied to `catalogue.sales_channel` (with `catalogue.audit_entry`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setChannelFeePayment | What Channel Fees, Payment & Fulfillment Configuration submits.
catalogue | ChannelFeesPaymentFulfillmentConfigurationView | 6 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setChannelFeePayment | What Channel Fees, Payment & Fulfillment Configuration displays.
catalogue | ChannelPricingCommercialProfileAssignmentInput | 18 | none — request only; applied to `catalogue.price_assignment` (with `catalogue.audit_entry`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setChannelPricingCommercial | What Channel Pricing & Commercial Profile Assignment submits.
catalogue | ChannelPricingCommercialProfileAssignmentView | 19 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setChannelPricingCommercial | What Channel Pricing & Commercial Profile Assignment displays.
catalogue | ChannelPublicationAvailabilityInput | 2 | none — request only; applied to `catalogue.product` (with `catalogue.audit_entry`, `catalogue.product_channel_assignment`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | publishChannelAvailability | What Channel Publication & Availability submits.
catalogue | ChannelPublicationAvailabilityView | 5 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | publishChannelAvailability | What Channel Publication & Availability displays.
catalogue | ChannelPublicationReadinessAiValidationInput | 6 | none — request only; applied to `catalogue.sales_channel` (with `catalogue.audit_entry`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | publishChannelReadinessValidation | What Channel Publication, Readiness & AI Validation submits.
catalogue | ChannelPublicationReadinessAiValidationView | 8 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | publishChannelReadinessValidation | What Channel Publication, Readiness & AI Validation displays.
catalogue | ChannelSalesRule | 50 | catalogue.channel_sales_rule | 1 | 1 | setChannelSalesRule | When, how much and to whom a channel may sell (29 September, data model DM3).
catalogue | CloneEventRequest | 4 | none — request only | 1 | 0 | cloneEvent | The body of cloneEvent.
catalogue | CreateEventRequest | 4 |  | 1 | 0 | createEvent
catalogue | CreatePerformancesRequest | 9 |  | 1 | 0 | createPerformances
catalogue | CreatePriceListRequest | 24 |  | 1 | 0 | createPriceList
catalogue | DemandOccupancyAvailabilityRuleBuilderInput | 12 | none — request only; applied to `pricing.dynamic_price_action` (with `catalogue.audit_entry`, `pricing.dynamic_price_condition`, `pricing.dynamic_price_rule`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setDemandOccupancyAvailability | What Demand, Occupancy & Availability Rule Builder submits.
catalogue | DemandOccupancyAvailabilityRuleBuilderView | 12 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setDemandOccupancyAvailability | What Demand, Occupancy & Availability Rule Builder displays.
catalogue | DynamicPriceRuleDetail | 3 | none — composed from a rule, its conditions and its actions | 1 | 1 | setDynamicPriceRule | A rule is unreadable without both halves.
catalogue | DynamicPricingControl | 39 | catalogue.dynamic_pricing_control | 1 | 1 | setDynamicPricingGuardrailPolicy | The limits and the autonomy of dynamic pricing at one scope (29 September, data model DM3).
catalogue | DynamicPricingStrategy | 26 | catalogue.dynamic_pricing_strategy | 0 | 1 | transitionDynamicPricingStrategy | A dynamic pricing strategy: what it prices, from which base and how often (29 September, data model DM3).
catalogue | DynamicPricingStrategyBuilderInput | 21 | none — request only; applied to `catalogue.dynamic_pricing_strategy` (with `catalogue.audit_entry`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setDynamicPricingStrategy | What Dynamic Pricing Strategy Builder submits.
catalogue | DynamicPricingStrategyBuilderView | 22 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setDynamicPricingStrategy | What Dynamic Pricing Strategy Builder displays.
catalogue | EligibilityCheckRequest | 2 |  | 1 | 0 | checkBookingEligibility | Request only.
catalogue | EligibilityCheckResult | 3 | none — computed per request | 0 | 1 | checkBookingEligibility
catalogue | EntitlementTemplate | 33 | catalogue.entitlement_template | 1 | 2 | createEntitlementTemplate, setEntitlementTemplateBlackoutDates
catalogue | Event | 13 | catalogue.event | 0 | 3 | createEvent, setEventLifecycleState, updateEvent
catalogue | GroupPackageDefinition | 14 | catalogue.group_package | 1 | 2 | getGroupPackageDefinition, setGroupPackageDefinition
catalogue | GuestMembership | 11 |  | 0 | 1 | getMyMemberships | 19.2.26 to 19.2.28.
catalogue | InventoryHold | 18 | catalogue.inventory_reservation | 0 | 1 | convertInventoryHold
catalogue | LiveDynamicPriceExecutionDeploymentMonitorInput | 11 | none — request only; applied to `catalogue.price` (with `catalogue.audit_entry`, `catalogue.price_execution`, `catalogue.pricing_recommendation_decision`, `platform.outbox`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | createLiveDynamicPrice | What Live Dynamic Price Execution & Deployment Monitor submits.
catalogue | LiveDynamicPriceExecutionDeploymentMonitorView | 15 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | createLiveDynamicPrice | What Live Dynamic Price Execution & Deployment Monitor displays.
catalogue | Performance | 12 | catalogue.performance | 0 | 2 | getPerformance, updatePerformance
catalogue | PerformanceAvailabilityPage | 3 | none — computed on read | 0 | 1 | getAvailability | The getAvailability answer (named 29 September, rev 3 REV3-1).
catalogue | PriceLadder | 22 | catalogue.price_ladder | 1 | 1 | setPriceLadderMatrix | The bands a dynamic price may move between, and how fast (29 September, data model DM3).
catalogue | PriceList | 30 | catalogue.price_list | 0 | 2 | createPriceList, updatePriceList
catalogue | PricingFee | 19 | catalogue.fee | 1 | 1 | setFeeDefinition | The fee and surcharge library (29 September, data model DM3).
catalogue | PricingRecommendationDecision | 13 | catalogue.pricing_recommendation_decision | 0 | 1 | decidePricingRecommendation | One human decision on one AI pricing recommendation (decided 29 September, readiness close-out).
catalogue | PricingRecommendationDecisionInput | 5 | none — request only | 1 | 0 | decidePricingRecommendation | What decidePricingRecommendation takes (decided 29 September, readiness close-out).
catalogue | PricingSimulationStudioInput | 14 | none — request only; applied to `catalogue.pricing_recommendation` (with `catalogue.pricing_simulation`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setPricing | What Pricing Simulation Studio submits.
catalogue | PricingSimulationStudioView | 23 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setPricing | What Pricing Simulation Studio displays.
catalogue | Product | 50 | catalogue.product + catalogue.product_media | 0 | 3 | cloneProduct, getProduct, updateProduct
catalogue | ProductCatalogueAssignmentInput | 7 | none — request only; applied to `catalogue.product` (with `catalogue.audit_entry`, `catalogue.product_channel_assignment`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setProductCatalogue | What Product & Catalogue Assignment submits.
catalogue | ProductCatalogueAssignmentView | 14 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setProductCatalogue | What Product & Catalogue Assignment displays.
catalogue | ProductCategory | 12 | catalogue.product_category | 0 | 1 | setProductCategories | Retail Board 2 of the client's design set, 20 August.
catalogue | ProductCategoryNode | 13 | none — projection over catalogue.product_category | 0 | 1 | listProductCategories | One node of the tree listProductCategories returns.
catalogue | ProductChannelTexts | 12 | catalogue.product_channel_text | 1 | 1 | setProductChannelTexts | The product's text per sales channel, per language (16 October 2026 minutes, 4.9 and 4.10, CHG-R8PRD-003).
catalogue | ProductEligibilityRule | 15 | catalogue.product_eligibility_rule | 1 | 2 | getProductEligibilityRule, setProductEligibilityRule | Participation limits for one product.
catalogue | ProductOwnerFormSet | 2 | none — the product's rows of catalogue.product_owner_form | 1 | 1 | setProductOwnerForms | The forms a product links, at most one per appliesTo (CHG-R8PRD-009).
catalogue | ProductSalePermissionRuleSet | 2 | none — the product's rows of catalogue.product_sale_permission | 1 | 1 | setProductSalePermissionRules | Who can sell one product, and how the rules decide (16 October 2026 minutes, 4.8, CHG-R8PRD-005 as corrected by CHG-R8PRD-009).
catalogue | ProductServicePriceAssignmentInput | 7 | none — request only; applied to `catalogue.price_assignment` (with `catalogue.audit_entry`), the table its operation writes (CHG-STO-021); a field with no column there is a working input of the screen and is not kept | 1 | 0 | setProductServicePrice | What Product & Service Price Assignment submits.
catalogue | ProductServicePriceAssignmentView | 8 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setProductServicePrice | What Product & Service Price Assignment displays.
catalogue | ProductVariant | 12 | catalogue.variant | 0 | 2 | resolveProductByCode, updateProductVariant
catalogue | RulePriorityConflictInput | 5 | none — request only; the saved hierarchy and test cases are the rows listRulePriorityConflict reads | 1 | 0 | setRulePriorityConflict | What setRulePriorityConflict takes (decided 29 September, readiness close-out; VM close-out for BO-441 Reorder, Validate, Test, Save).
catalogue | RulePriorityConflictView | 8 | none — projection over the saved priority order and test cases | 0 | 1 | setRulePriorityConflict | What setRulePriorityConflict returns: the order in force, the conflicts it has and, in test mode, the result.
catalogue | UpdateProductRequest | 16 |  | 1 | 0 | updateProduct
catalogue | WaitingRoomEntry | 8 | none — transient, held in the room's Redis counters and never in a table | 0 | 2 | enterWaitingRoom, getWaitingRoomPosition | One guest's place in a performance's waiting room (ADR-0066).
catalogue | WaitlistEntry | 11 | catalogue.waitlist_entry | 1 | 1 | joinWaitlist
finance | CreateTaxCodeRequest | 8 |  | 1 | 0 | createTaxCode
finance | FinCreditMemo | 31 | ledger.credit_memo + ledger.credit_memo_line | 0 | 1 | issueCreditMemo | 5.7.94.
finance | FinEInvoicingProvider | 12 | ledger.einvoicing_provider | 1 | 1 | setEInvoicingProvider | 6.1.1.
finance | FinIssueCreditMemoRequest | 6 | none — request only | 1 | 0 | issueCreditMemo
finance | FinIssueTaxInvoiceRequest | 6 | none — request only | 1 | 0 | issueTaxInvoice
finance | FinTaxDocumentRendition | 7 | none — a signed link to the stored PDF | 0 | 1 | getTaxDocumentRendition
finance | FinTaxInvoice | 41 | ledger.tax_invoice + ledger.tax_invoice_line | 0 | 2 | getTaxInvoice, issueTaxInvoice | 5.7.93, 5.10.3.
finance | FxProviderAssignment | 5 | ledger.fx_provider_assignment | 0 | 1 | setFxProvider | Which provider serves one FX purpose in one region, as setFxProvider sets it and ingestFxRates reads it.
finance | FxRate | 13 | ledger.fx_rate | 1 | 1 | setFxRate | Also the setFxRate body.
finance | LegalEntity | 11 | ledger.legal_entity | 1 | 1 | createLegalEntity | Also the createLegalEntity body.
finance | TaxCode | 13 | ledger.tax_code | 0 | 2 | createTaxCode, updateTaxCode
fnb | Bill | 8 | none — computed from visit orders | 0 | 2 | getBill, getGuestBill
fnb | BillSplit | 4 | fnb.bill_split + fnb.sub_bill | 0 | 1 | splitBill
fnb | ColdChainEvent | 10 | fnb.cold_chain_event | 1 | 1 | logColdChain | Board 5G.
fnb | CorrectiveAction | 13 | fnb.corrective_action | 0 | 2 | escalateCorrectiveAction, signCorrectiveAction | What was done about a finding, and who signed it.
fnb | CourseRules | 6 | fnb.course_rule | 1 | 2 | getCourseRules, setCourseRules | An outlet's coursing default.
fnb | CreateFnbOrderRequest | 7 | none — request only | 1 | 0 | createFnbOrder
fnb | CreateGuestOrderRequest | 8 |  | 1 | 0 | createGuestFnbOrder
fnb | CreateMenuRequest | 4 | none — request only | 1 | 0 | createMenu
fnb | DeliveryLocation | 14 | fnb.delivery_location | 0 | 3 | createDeliveryLocation, setDeliveryLocationOutletMapping, updateDeliveryLocation
fnb | FnbDeliveryPolicy | 16 | fnb.delivery_policy | 1 | 2 | getFnbDeliveryPolicy, setFnbDeliveryPolicy
fnb | FnbOrder | 19 | fnb.service_order + fnb.service_order_line | 0 | 5 | acceptFnbOrder, cancelFnbOrder, createFnbOrder, getFnbOrder, markOrderCollected
fnb | GuestMenu | 7 | none — projection over fnb.menu, fnb.menu_item and availability | 0 | 1 | getGuestMenu
fnb | GuestOrderResult | 9 | none — projection over fnb_order | 0 | 1 | createGuestFnbOrder
fnb | GuestOrderStatus | 6 | none — projection over kitchen_ticket | 0 | 2 | getGuestOrderStatus, recordOrderHandover
fnb | KitchenException | 10 | fnb.kitchen_exception | 0 | 1 | logKitchenException | Board 3, 24 August.
fnb | KitchenSla | 3 | fnb.kitchen_sla | 1 | 2 | getKitchenSla, setKitchenSla | How long a ticket may sit, per service mode, and what pushes it up the rail (setKitchenSla).
fnb | KitchenTicket | 17 | fnb.kitchen_ticket + fnb.kitchen_ticket_line | 0 | 6 | fireCourse, holdCourse, prioritiseKitchenTicket, recallKitchenTicket, refireItem, setKitchenTicketStatus
fnb | LocationSession | 9 | fnb.location_session | 0 | 1 | claimLocationSession
fnb | Menu | 9 | fnb.menu | 0 | 3 | createMenu, setMenuSections, updateMenu
fnb | MenuItem | 18 | fnb.menu_item | 0 | 3 | attachModifierGroup, setItemAvailability, setMenuItemDailyCount
fnb | MenuSchedule | 9 | fnb.menu_schedule | 0 | 1 | scheduleMenuPublish | A publish dated for later (scheduleMenuPublish, or publishMenu with an effectiveAt).
fnb | MenuVersion | 13 | fnb.menu_version | 0 | 2 | publishMenu, rollbackMenu | One published state of a menu, kept.
fnb | ModifierGroup | 7 | fnb.modifier_group + fnb.modifier_option | 1 | 1 | createModifierGroup | An F&B modifier is a choice added to a dish at the moment of ordering — *no onions*, *extra cheese*, *cooked medium*.
fnb | OpenTableVisitRequest | 6 | none — request only | 1 | 0 | openTableVisit
fnb | OrderLabel | 8 | none — rendered from the kitchen ticket and its order | 0 | 1 | printOrderLabel | What goes on the bag (printOrderLabel).
fnb | ProductionPlan | 8 | fnb.production_plan + fnb.production_plan_line | 1 | 2 | buildProductionPlan, releaseProductionPlan | Board 2M.
fnb | Recipe | 5 | fnb.recipe + fnb.recipe_ingredient | 1 | 1 | setRecipe
fnb | RestaurantWaitlist | 11 | fnb.waitlist_entry | 1 | 2 | joinRestaurantWaitlist, leaveRestaurantWaitlist | BL-130.
fnb | SplitBillRequest | 6 | none — request only | 1 | 0 | splitBill
fnb | StationRebalance | 2 |  | 1 | 1 | rebalanceStationLoad | A temporary move of work between stations (rebalanceStationLoad).
fnb | SubstitutionRule | 10 | fnb.substitution_rule | 0 | 1 | setSubstitutionRules | Board 2L, 24 August.
fnb | TableMap | 3 | none — projection | 0 | 2 | getTableMap, setTableLayout
fnb | TableReservation | 19 | fnb.table_reservation | 2 | 4 | createTableReservation, createTableReservationForGuest, seatTableReservation, updateTableReservation
fnb | TableState | 15 | none — projection over table and visit | 0 | 1 | clearTable
fnb | TableVisit | 18 | fnb.table_visit | 0 | 5 | getTableVisit, openTableVisit, requestBill, transferTableVisit, updateTableVisit
fnb | TemperatureLog | 12 | fnb.temperature_log | 1 | 0 | logTemperature | Board 5J of the client F&B pack, 20 August.
fnb | UpdateTableReservationRequest | 13 | none — request only; a partial update of fnb.table_reservation | 1 | 0 | updateTableReservation | A partial update of TableReservation (the CR-089 pattern; CHG-SHP-008): updateTableReservation sends only what changes, and a field left out keeps its stored value.
games | GameCard | 15 | games.card | 0 | 2 | getGameCard, issueGameCard
games | IssueGameCardRequest | 7 | none — request only | 1 | 0 | issueGameCard
identity | CapabilityTemplate | 9 | identity.capability_template | 1 | 1 | setCapabilityTemplate | 3.3.23, BL-110.
identity | ChangeCredentialRequest | 3 |  | 1 | 0 | changeOwnCredential | Request only.
identity | DelegatedAccess | 25 | identity.delegated_access | 0 | 1 | grantDelegation
identity | GuestSession | 11 | none — Redis session registry | 0 | 5 | guestPasswordLogin, guestSocialLogin, guestUaePassLogin, registerGuest, verifyGuestOtp | A guest sign-in's answer: the session and its new tokens (registerGuest, verifyGuestOtp, guestPasswordLogin, guestSocialLogin, guestUaePassLogin).
identity | GuestSessionView | 10 | none — Redis session registry | 0 | 1 | getGuestSession | The guest session as getGuestSession reads it: no tokens (accepted 15 October 2026, ADAM CR-100; CHG-R10ID-009; BC-482).
identity | LoginRequest | 5 |  | 1 | 0 | login | workstationId is required for a device door and absent from a browser door (CHG-DOOR-001, 2 October 2026).
identity | LoginResponse | 10 | none — computed | 0 | 1 | login
identity | MfaEnrolment | 7 | none — transient | 0 | 1 | enrolMfaMethod
identity | MfaMethod | 13 | identity.mfa_method | 0 | 2 | listMfaMethods, verifyMfaEnrolment | A second factor a principal or a guest has enrolled (R8 blockers IDENTITY-C12 and IDENTITY-C34, CHG-R8MIG-007).
identity | PasswordPolicy | 19 | identity.password_policy | 1 | 1 | setPasswordPolicy | BL-144.
identity | PlatformStaffGrant | 9 | identity.platform_staff_grant | 0 | 1 | openPlatformStaffGrant | One platform operator's time-boxed access into this tenant (decided 28 September, audit R098).
identity | Principal | 11 | identity.principal | 0 | 1 | updatePrincipal
identity | RegisterGuestRequest | 6 |  | 1 | 0 | registerGuest
identity | Role | 10 | identity.role | 0 | 2 | createRole, updateRole
identity | SegregationRule | 9 | identity.segregation_rule | 0 | 1 | setSegregationRules | BL-147, 3.3.31 and 11.1.24.
identity | Session | 12 |  | 0 | 2 | getCurrentSession, selectRole
identity | SubjectDataExportStatus | 10 | none — computed from identity.subject_data_export | 0 | 1 | getSubjectDataExport | Where a guest's data export has got to, and the link to download it (ADAM CR-101; CHG-R10ID-016), the answer of getSubjectDataExport.
identity | TokenPair | 3 | none — transient | 0 | 1 | refreshToken
inventory | CreateGoodsReceiptRequest | 6 | none — request only | 1 | 0 | createGoodsReceipt
inventory | CreateInventoryItemRequest | 16 | none — request only | 1 | 0 | createInventoryItem
inventory | GoodsReceipt | 12 | inventory.goods_receipt + inventory.goods_receipt_line | 0 | 2 | createGoodsReceipt, rejectReceivedGoods
inventory | InventoryItem | 26 | inventory.inventory_item | 0 | 2 | createInventoryItem, updateInventoryItem
inventory | InventoryKitDefinition | 2 | none — composed of the item's inventory.kit_component rows | 1 | 1 | setInventoryKitDefinition | 4.4.20.
maintenance | InspectionTemplate | 10 | maintenance.inspection_template + maintenance.inspection_template_item | 1 | 1 | createInspectionTemplate
marketing-crm | AgentAvailability | 7 | marketing.agent_availability | 0 | 1 | setAgentAvailability
marketing-crm | Campaign | 24 | marketing.campaign | 0 | 3 | createCampaign, stopCampaign, updateCampaign
marketing-crm | CampaignInvitation | 10 | marketing.invitation | 0 | 1 | respondToInvitation | Addressed and tokenised.
marketing-crm | Case | 23 | marketing.case | 0 | 1 | raiseMyCase
marketing-crm | CaseDetail | 26 | marketing.case | 0 | 2 | getMyCase, replyToMyCase
marketing-crm | Challenge | 14 | marketing.challenge | 1 | 1 | createChallenge | BL-022, CF-137.
marketing-crm | ClaimDeviceConsentRequest | 1 | none — request only | 1 | 0 | claimDeviceConsent
marketing-crm | ConsentPurposeConfig | 8 | marketing.consent_purpose + marketing.consent_purpose_channel | 0 | 1 | setConsentPurposes
marketing-crm | ConsentQuestion | 11 | marketing.consent_question + marketing.consent_question_version | 0 | 2 | createConsentQuestion, updateConsentQuestion | A venue-defined consent question asked at booking (decided 29 September, rev 3 REV3-26).
marketing-crm | ConsentState | 2 | none — projection over consent_record | 0 | 3 | claimDeviceConsent, getGuestConsents, recordConsent
marketing-crm | Conversation | 22 | marketing.conversation | 0 | 1 | handoverToAgent | 22.8.
marketing-crm | ConversationMessage | 8 | marketing.conversation_message + marketing.conversation_message_attachment | 0 | 1 | sendConversationMessage
marketing-crm | CookieBannerPreferenceCenterDesignerView | 21 | marketing.cookie_banner_design | 1 | 1 | setCookieBannerDesign | One version of a cookie banner and preference-centre design (pack 17.1.6).
marketing-crm | CookieConsentRuntime | 6 | none — assembled at read time from marketing.cookie_banner_design, marketing.tracking_technology and marketing.device_consent | 0 | 1 | getCookieConsentRuntime | What getCookieConsentRuntime gives the storefront tag loader and the app SDK gate (2.6.52, 2.6.58).
marketing-crm | CookieTrackingDigitalTechnologyRegistryView | 22 | marketing.tracking_technology | 1 | 1 | setTrackingTechnology | One governed tracking technology (pack 17.1.5 Registry Fields; BL-073 §4a).
marketing-crm | CreateCampaignRequest | 14 | none — request only | 1 | 0 | createCampaign
marketing-crm | CreateConsentQuestionRequest | 6 | none — request only; applied to marketing.consent_question and marketing.consent_question_version | 1 | 0 | createConsentQuestion | The body of createConsentQuestion (ADAM CR-089, CHG-CNS-001).
marketing-crm | CreateSegmentRequest | 11 | none — request only | 1 | 0 | createSegment
marketing-crm | DynamicFieldsQuestionsConditionalLogicView | 17 | marketing.form_definition_field + marketing.waiver_field_rule | 1 | 1 | setDynamicFieldQuestion | One field of a waiver version (pack 11.1.4).
marketing-crm | FormDefinition | 17 | marketing.form_definition + marketing.form_definition_field | 1 | 2 | createForm, getForm | CF-129, CL-04.
marketing-crm | FormSubmission | 13 | marketing.form_submission | 1 | 1 | submitForm | The acceptance record, and it is evidence.
marketing-crm | GuestConversation | 5 | none — a guest view of marketing.conversation and its guest-visible messages | 0 | 1 | getGuestConversation | A handed-over conversation as the guest sees it (getGuestConversation; Chinmay, 3 October 2026, Pattern 4; CHG-GCF-004).
marketing-crm | GuestConversationMessage | 5 | none — a guest view of marketing.conversation_message | 0 | 1 | sendGuestConversationMessage | One message as the guest sees it.
marketing-crm | GuestDevice | 16 | marketing.guest_device | 0 | 1 | registerGuestDevice
marketing-crm | GuestDocument | 9 | marketing.guest_document | 1 | 1 | uploadGuestDocument | BL-133.
marketing-crm | GuestIdentification | 7 |  | 0 | 1 | identifyGuest | The answer to "who is this" at a till, resolved from any identifier.
marketing-crm | GuestPreferences | 8 | marketing.guest_preference | 1 | 1 | updateGuestPreferences | What the guest likes, kept apart from what they permit (consent) and from who they are (the profile).
marketing-crm | GuestProfile | 17 | marketing.guest_profile | 0 | 1 | updateMyProfile
marketing-crm | InvitationCampaign | 11 | marketing.invitation_campaign | 1 | 1 | createInvitationCampaign | BL-150.
marketing-crm | LaunchResult | 5 | none — computed | 0 | 1 | launchCampaign
marketing-crm | LostItem | 17 | marketing.lost_item | 1 | 1 | recordLostItem | BL-021.
marketing-crm | LoyaltyPosition | 11 | marketing.loyalty_position | 0 | 3 | getGuestLoyalty, redeemLoyaltyPoints, setLeaderboardNickname
marketing-crm | LoyaltyProgramme | 9 | marketing.loyalty_programme + marketing.points_earning_rule + marketing.programme_tier | 1 | 2 | createLoyaltyProgramme, updateLoyaltyProgramme
marketing-crm | LoyaltyRuleSet | 4 | none — composed from the rule tables of one programme | 1 | 1 | setLoyaltyRules | Every rule a programme runs on, read and written as one thing.
marketing-crm | MarketingCustomerBadge | 9 | marketing.customer_badge | 1 | 1 | awardBadge | Taken from the backend workbook, 20 September.
marketing-crm | MarketingReward | 11 | marketing.reward | 1 | 1 | setReward | Taken from the backend workbook, 20 September.
marketing-crm | MarketingSubscription | 8 | marketing.subscription | 1 | 2 | getMarketingSubscription, setMarketingSubscription | Drafted 4 September.
marketing-crm | MessageTemplate | 11 | marketing.message_template | 1 | 2 | createMessageTemplate, updateMessageTemplate
marketing-crm | RecordConsentAnswersRequest | 4 | none — request only | 1 | 0 | recordConsentAnswers
marketing-crm | RecordConsentRequest | 6 | none — request only | 1 | 0 | recordConsent
marketing-crm | Referral | 10 | marketing.referral | 1 | 1 | createReferral | BL-034.
marketing-crm | Review | 13 | marketing.review | 0 | 1 | submitReview
marketing-crm | Segment | 15 | marketing.segment + marketing.segment_criterion | 0 | 1 | createSegment
marketing-crm | SeoMetadata | 15 | control.seo_metadata | 1 | 2 | getSeoMetadata, setSeoMetadata | 22.11.1 to 22.11.12, CF-137.
marketing-crm | SubmitReviewRequest | 8 | none — request only | 1 | 0 | submitReview
marketing-crm | UpdateConsentQuestionRequest | 6 | none — request only; applied to marketing.consent_question and marketing.consent_question_version | 1 | 0 | updateConsentQuestion | The body of updateConsentQuestion: only what changes (ADAM CR-089, CHG-CNS-001).
marketing-crm | UrlRedirect | 9 | control.url_redirect | 1 | 1 | createUrlRedirect | 22.11.7.
marketing-crm | Wishlist | 2 | none — wrapper. The items are the table, keyed by subject | 0 | 2 | addToWishlist, getWishlist
orders | AddCartLineRequest | 10 | none — request only | 1 | 0 | addCartLine
orders | AppendEntitlementRequest | 5 | none — request only | 1 | 0 | appendEntitlementToMedia
orders | AppendEntitlementResult | 3 | none — computed | 0 | 1 | appendEntitlementToMedia
orders | ApplyCartPromoCodeRequest | 1 | none — request only | 1 | 0 | applyCartPromoCode
orders | BillingStatement | 11 | none — computed from orders.payment and payments.dunning_case | 0 | 1 | getBillingStatement | 2.14.19-2.14.23, 5.7.96, BL-100.
orders | Cart | 24 | orders.cart | 0 | 7 | addCartLine, applyCartPromoCode, createCart, extendCart, getCart, removeCartLine, updateCartLine
orders | CartMergeResult | 3 | none — computed | 0 | 1 | claimCart
orders | CloneTicketTemplateInput | 4 | none — request only | 1 | 0 | cloneTicketTemplate | What cloneTicketTemplate takes (decided 29 September, readiness close-out).
orders | CreateOrderRequest | 9 |  | 1 | 0 | createOrder
orders | CreatePaymentRequest | 12 |  | 1 | 0 | createPayment
orders | CreateRefundRequest | 8 |  | 1 | 0 | createRefund
orders | CreateResaleListingRequest | 3 | none — request only | 1 | 0 | createResaleListing | Request only; persisted as ResaleListing.
orders | CreateReservationRequest | 5 |  | 1 | 0 | createReservation
orders | EntitlementShare | 7 | none — a view of the identity.delegated_access row shareEntitlement writes | 0 | 1 | shareEntitlement | A second person's right to present an entitlement the owner still holds.
orders | ExchangeOrderRequest | 6 |  | 1 | 0 | exchangeOrderLines
orders | GroupArrivalCheckInAdmissionOperationsView | 17 | none — projection over orders state, assembled at read time from tables that already exist | 0 | 1 | listGroupArrivalCheck | What Group Arrival, Check-In & Admission Operations displays.
orders | GroupBooking | 23 | orders.group_booking | 0 | 2 | getGroupBooking, requestGroupBooking | BL-028.
orders | GroupBookingRequest | 11 |  | 1 | 0 | requestGroupBooking | Request only.
orders | GroupCheckInRequest | 6 | none — request only; lands in the check-in columns of `orders.group_visit_plan` | 1 | 0 | recordGroupCheckIn | What the group check-in desk records (BO-280).
orders | GroupVisitPlan | 27 | orders.group_visit_plan | 0 | 1 | recordGroupCheckIn | The day-of-visit record for one group booking: the operational plan, the sales-to-operations handover, and the group check-in (DM5, 29 September: data model for the agreed operations; MoM 31 Aug 4.7-…
orders | GuestRefundPolicy | 4 | none — guest projection of RefundPolicy | 0 | 1 | getGuestRefundPolicy | What getGuestRefundPolicy returns (R8 blocker ORDERS-MONEY-C26): how much of a ticket comes back and until when, and nothing about who authorises a refund.
orders | ManualDiscountRequest | 8 | none — request only | 1 | 0 | applyManualDiscount
orders | MediaEntitlements | 7 | none — projection over entitlement and scan history | 0 | 1 | getMediaEntitlements | Derived from the entitlements on the code, with no media table (ADAM CR-196, decided 21 October 2026, the derivation its recommendation names; CHG-R9CR-005).
orders | ModifyOrderRequest | 5 |  | 1 | 0 | modifyOrder
orders | Order | 32 | orders.sales_order + orders.order_line | 0 | 7 | applyManualDiscount, checkoutCart, convertReservation, createOrder, getOrder, holdOrder, voidOrder
orders | OrderExchangeResult | 8 | none — computed | 0 | 2 | exchangeOrderLines, rescheduleOrder
orders | OrderModificationResult | 7 | none — computed | 0 | 1 | modifyOrder
orders | OrderResumeResult | 3 | none — computed | 0 | 1 | resumeOrder
orders | OrderStatement | 8 | none — computed from order, payment, refund and ledger | 0 | 1 | getOrderStatement
orders | OrderSyncResult | 3 | none — computed | 0 | 1 | syncOrders
orders | Payment | 24 | orders.payment | 0 | 4 | addTip, capturePayment, createPayment, inquirePaymentStatus
orders | PaymentProvider | 15 | payments.provider | 0 | 1 | setPaymentProvider | BL-116, CF-131.
orders | PaymentToken | 10 | payments.token | 0 | 1 | storePaymentToken | BL-116.
orders | Refund | 22 | orders.refund + orders.refund_line + orders.refund_payment | 0 | 1 | createRefund
orders | RefundPolicy | 9 | orders.refund_policy + orders.refund_policy_time_band | 1 | 1 | setRefundPolicy | Venue-configured.
orders | ReissuedEntitlement | 5 | none — computed; both entitlements live in access.entitlement | 0 | 1 | reissueEntitlement | The zero-value reissue — the old entitlement voided, the new one issued, and the reason that links them.
orders | ResaleListing | 16 | orders.resale_listing | 0 | 1 | createResaleListing | BL-060.
orders | Reservation | 8 | orders.reservation + orders.reservation_line | 0 | 3 | createReservation, extendReservation, getReservation | An unpaid hold, not a booking.
orders | SetPaymentProviderRequest | 16 | none — request only; the provider lands in payments.provider and its rules in payments.routing_rule | 1 | 0 | setPaymentProvider | Request only.
orders | TicketProof | 5 | none — rendered on request, nothing is stored | 0 | 1 | previewProductTickets | A sample ticket from a template, marked as a proof on the artefact itself so it cannot be presented at a gate.
orders | TicketTemplate | 12 | orders.ticket_template + orders.ticket_template_channel | 0 | 4 | cloneTicketTemplate, createTicketTemplate, importTicketTemplate, updateTicketTemplate | BL-102.
orders | TicketTemplateImportInput | 3 | none — request only | 1 | 0 | importTicketTemplate | What importTicketTemplate takes (decided 29 September, readiness close-out).
orders | TicketTemplateRequest | 10 |  | 2 | 0 | createTicketTemplate, updateTicketTemplate | Request only; persisted as TicketTemplate.
orders | TicketTransfer | 12 | orders.ticket_transfer | 0 | 2 | claimTicketTransfer, transferOrderTickets
orders | VisitReminder | 7 | orders.visit_reminder | 1 | 2 | getVisitReminder, setVisitReminder | One reminder per booking, set by the guest.
orders | WalletPass | 10 | orders.wallet_pass | 0 | 1 | issueWalletPass | BL-029.
payments | DunningCase | 14 | payments.dunning_case | 0 | 1 | retryMyDunningPayment | BL-100.
payments | DunningPolicy | 8 | payments.dunning_policy | 1 | 1 | setDunningPolicy | 2.14.19-2.14.23, BL-100.
payments | PaymentProviderConnection | 13 | payments.provider_connection | 1 | 1 | createPaymentProviderConnection | Boards 2.2 and 2.4.
payments | RetryDunningPaymentRequest | 1 |  | 1 | 0 | retryMyDunningPayment | Request only.
promotions | Bundle | 23 | promotions.bundle + promotions.bundle_component | 0 | 2 | createBundle, updateBundle
promotions | CodeDistributionAssignmentManagerInput | 5 | none — request only; stored as one promotions.code_assignment row (CouponCodeAssignment) and the coupon codes it assigns (CHG-FXC-005) | 1 | 0 | setCodeDistributionManager | What Code Distribution & Assignment Manager submits.
promotions | CodeDistributionAssignmentManagerView | 12 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setCodeDistributionManager | What Code Distribution & Assignment Manager displays.
promotions | ConflictAnalysis | 3 | none — computed | 0 | 1 | analysePromotionConflicts
promotions | CouponCampaign | 14 | promotions.coupon_campaign | 0 | 1 | createCouponCampaign
promotions | CreateBundleRequest | 17 | none — request only | 1 | 0 | createBundle
promotions | CreateCouponCampaignRequest | 10 | none — request only | 1 | 0 | createCouponCampaign
promotions | CreatePromotionRequest | 21 | none — request only | 1 | 0 | createPromotion
promotions | EvaluatePromotionsRequest | 8 | none — request only | 1 | 0 | evaluatePromotions
promotions | GuestBundle | 11 | none — guest projection of promotions.bundle and its components | 0 | 1 | getGuestBundle | What a guest may see of a bundle (R8 blocker ORDERS-MONEY-C32), as GuestPromotion is for a promotion: never the allocation, owner, campaign, code or whether it has been sold.
promotions | GuestCouponCode | 7 | none — guest projection of promotions.coupon_code and its campaign | 0 | 1 | getGuestCouponCode | What a guest may see of a coupon code (R8 blocker ORDERS-MONEY-C32), as GuestPromotion is for a promotion: never the campaign, batch, assignee, assignment, redemption counts or the order it was redee…
promotions | Promotion | 28 | promotions.promotion | 0 | 3 | createPromotion, publishPromotion, updatePromotion
promotions | PromotionEvaluation | 4 | none — computed | 0 | 1 | evaluatePromotions
promotions | PromotionUsage | 7 | none — aggregated from ledger and orders | 0 | 1 | getPromotionUsage
public-api | ApiClient | 15 | control.api_client | 1 | 1 | createApiClient, setApiClientStatus | CF-135a.
public-api | ApiLicence | 9 | control.api_licence | 1 | 1 | setApiLicensing | 13.3.24, decision D5.
public-api | ApiVersion | 9 | control.api_version | 0 | 1 | deprecateApiVersion | 13.1.31 to 13.1.35, ADR-0026.
public-api | CreateDeveloperAccountRequest | 5 | none — request only; stored as control.developer_account (DeveloperAccount) and its owner control.developer_member | 1 | 0 | registerDeveloper | What registerDeveloper takes (ADAM CR-098, accepted for r10; CHG-R10ID-011): the organisation and its contact, never the read-only id, status or verifiedAt, which the server sets.
public-api | DeveloperAccount | 8 | control.developer_account | 0 | 2 | registerDeveloper, verifyDeveloper | 13.1.6 to 13.1.9.
public-api | DeveloperMember | 7 | control.developer_member | 0 | 1 | setDeveloperMembers | One person at a developer organisation (setDeveloperMembers, 4 October 2026, CHG-FXC-005).
public-api | IntegrationListing | 12 | control.integration_listing | 0 | 1 | certifyIntegration | 13.1.50, decision D1.
public-api | ProductionAccessRequest | 14 | control.production_access_request | 0 | 1 | decideProductionAccess | A developer's request for production keys (17 September minutes, M17-06): sandbox, then certification, then production.
queue | CreateQueueRequest | 20 | none — request only | 1 | 0 | createQueue
queue | JoinQueueRequest | 8 | none — request only | 1 | 0 | joinQueue
queue | Queue | 31 | queue.queue + queue.queue_operating_window | 0 | 2 | createQueue, updateQueue
queue | QueueFeed | 8 | queue.feed | 1 | 2 | configureQueueFeed, listQueueFeeds
queue | WaitTime | 11 | none — computed from readings and throughput | 0 | 1 | getWaitTimes
queue | WaitingGuest | 25 | queue.entry | 0 | 2 | getWaitingGuest, joinQueue
reporting | Alert | 18 | reporting.alert | 0 | 1 | listAlerts | A raised alert.
reporting | AlertRule | 13 | reporting.alert_rule | 1 | 1 | setAlertRule | BL-152, CF-134.
reporting | CreateDashboardRequest | 6 | none — request only | 2 | 0 | createDashboard, updateDashboard
reporting | CreateReportRequest | 10 | none — request only | 2 | 0 | createReport, updateReport
reporting | Dashboard | 11 | reporting.dashboard + reporting.dashboard_tile | 0 | 3 | createDashboard, listDashboards, updateDashboard
reporting | DashboardData | 12 | none — computed | 0 | 1 | getDashboard
reporting | KpiDefinition | 12 | reporting.kpi_definition | 1 | 1 | createKpi | BI boards 2.5 and 10.2.
reporting | NaturalLanguageAnswer | 13 | none — computed | 0 | 1 | askReportingQuestion
reporting | ReportDefinition | 19 | reporting.report_definition + reporting.report_column + reporting.report_filter | 0 | 4 | createReport, getReport, saveNaturalLanguageQuery, updateReport
reporting | ReportResult | 8 | none — result set, cached in object storage | 0 | 1 | runReport
reporting | RunReportRequest | 5 | none — request only | 1 | 0 | runReport
reporting | SemanticModel | 5 | reporting.semantic_model | 1 | 1 | setSemanticModel | BI boards 3.3 and 10.6.
resources | CreateResourceHoldRequest | 8 | none — request only | 1 | 0 | createResourceHold
resources | MapResourceAvailability | 7 | none — computed from placed resources, bookings, holds and blocks | 0 | 1 | getMapResourceAvailability | What getMapResourceAvailability returns: every placed resource on one map, for one window, in one answer (rev 3 REV3-15).
resources | Resource | 22 | resources.resource | 2 | 4 | cloneResource, createResource, setResourceLifecycleState, updateResource | A specific object, not a quantity of interchangeable ones.
resources | ResourceBlock | 8 | resources.resource_block | 1 | 1 | createResourceBlock | Board 2.07.
resources | ResourceHold | 15 | resources.resource_reservation | 0 | 3 | createResourceHold, extendResourceHold, getResourceHold | A guest's pick on the map, held while they pay (decided 29 September, rev 3 REV3-15).
resources | ResourcePackage | 14 | resources.resource_package | 2 | 2 | createResourcePackage, updateResourcePackage | Board 1.08.
resources | ResourceRequirement | 12 | resources.resource_requirement | 0 | 1 | setExperienceResourceRequirements | A type and a quantity, never a named resource.
resources | ResourceSchedule | 9 | resources.resource_schedule | 1 | 1 | setResourceSchedule | Boards 2.03 and 2.04.
retail | CreateMerchandiseRequest | 14 | none — request only | 1 | 0 | createMerchandise
retail | CreateRetailReturnRequest | 7 | none — request only | 1 | 0 | createRetailReturn
retail | CreateRetailSaleRequest | 8 | none — request only | 1 | 0 | createRetailSale
retail | MerchandiseItem | 18 | retail.merchandise | 0 | 2 | createMerchandise, updateMerchandise
retail | MerchandiseReservation | 9 | retail.reservation + retail.reservation_line | 0 | 1 | reserveMerchandise
retail | PriceCheck | 10 | none — computed | 0 | 1 | lookupMerchandise
retail | RetailReturn | 15 | retail.return + retail.return_line | 0 | 1 | createRetailReturn
retail | RetailSale | 16 | retail.sale + retail.sale_line | 0 | 2 | createRetailSale, getRetailSale
retail | ReturnPolicy | 10 | retail.return_policy | 1 | 2 | getReturnPolicy, setReturnPolicy
retail | ShopAndDrop | 20 | retail.shop_and_drop + retail.shop_and_drop_line | 0 | 3 | collectShopAndDrop, createShopAndDrop, lookupShopAndDrop
seating | AccessibleSeating | 5 | seating.accessible | 1 | 1 | setAccessibleSeating | Boards 7.6 to 7.8.
seating | CreateSeatHoldRequest | 7 | none — request only | 1 | 0 | createSeatHold | Seats or a standing zone, exactly one (r8, GPS-C38): seatIds holds named seats; zoneId with quantity holds places in a standing zone (a zone has no seats), refused 409 zone-unavailable when the zone…
seating | SeatAvailability | 11 | none — computed from seat, hold and block | 0 | 1 | getSeatAvailability
seating | SeatCategory | 8 | seating.seat_category | 0 | 2 | createSeatCategory, updateSeatCategory
seating | SeatHold | 12 | seating.seat_reservation | 0 | 3 | createSeatHold, extendSeatHold, getSeatHold
seating | SeatRecommendationRequest | 6 | none — request only | 1 | 0 | recommendSeats
seating | SeatRecommendationRules | 6 | seating.recommendation_rule | 1 | 1 | setSeatRecommendationRules | Board 9, and the 21 August minute: *"best-seat ranking… must be configurable per seat map/event."* Five kinds, one scoring model — five algorithms would eventually contradict each other.
shift | CashMovement | 14 | orders.cash_movement | 0 | 1 | createCashMovement
shift | CloseShiftRequest | 6 |  | 1 | 0 | submitShiftCount
shift | CreateCashMovementRequest | 7 |  | 1 | 0 | createCashMovement
shift | CreateDepositBoxRequest | 19 | none — request only; allocateDepositBox writes it as orders.deposit_box with its orders.deposit_box_opening_denomination rows, and answers with DepositBox | 1 | 0 | allocateDepositBox | What allocateDepositBox takes (R8 blocker fix, APPROVALS-TENANCY-C25).
shift | Denomination | 8 | platform.denomination | 0 | 2 | listDenominations, setDenominations | Raised in review by Tanmay: denominations belong in a table, not in JSON.
shift | DepositBox | 19 | orders.deposit_box + orders.deposit_box_opening_denomination + orders.deposit_box_foreign_holding | 0 | 2 | allocateDepositBox, withdrawFromDepositBox | 5.8.
shift | NoSaleEvent | 9 | orders.no_sale_event | 0 | 1 | recordNoSale
shift | OpenShiftRequest | 5 |  | 1 | 0 | openShift
shift | SetDenominationsRequest | 3 |  | 1 | 0 | setDenominations | Request only.
shift | Shift | 36 | orders.pos_shift + orders.pos_shift_approval + orders.pos_shift_incident | 0 | 9 | acceptShiftVariance, approveShiftOpen, getCurrentShift, getWorkstationShift, openShift, rejectShiftVariance, reopenShift, resumeShift, suspendShift | approvals and incidents are child rows (26 September, pull audit R099): orders.pos_shift_approval and orders.pos_shift_incident, one row per item, keyed to the shift.
shift | ShiftCloseResult | 7 | none — computed | 0 | 1 | closeShift
shift | ShiftCountReceipt | 6 | none — computed | 0 | 2 | giveShiftVarianceReason, submitShiftCount | What submitShiftCount returns to the cashier: what happens next, never the figure (CHG-FIN-003).
shift | ShiftVarianceReasonRequest | 2 | orders.pos_shift | 1 | 0 | giveShiftVarianceReason | The reason for a difference within the threshold, given after the blind count is locked (giveShiftVarianceReason; the client's policy of 6 October 2026, T10.1; CHG-R4-019).
shift | TillShiftPolicy | 11 | orders.till_shift_policy | 1 | 2 | getTillShiftPolicy, setTillShiftPolicy | The venue's opening, closing and exception rules for every till (CHG-CSP-020; POS-019; DI-309).
subscription | CreatePlanRequest | 14 | none — request only | 2 | 0 | createPlan, createPlanVersion
subscription | CreateTenantRequest | 6 | none — request only | 1 | 0 | createTenant
subscription | LicenceAddOn | 11 | control.licence_add_on + control.licence_add_on_limit | 1 | 0 | addLicenceAddOn | Belongs to the tenant, not the plan.
subscription | LicencePosition | 5 | none — union of the tenant's plan (control.tenant.plan_id -> control.plan_module, control.plan_limit) and its add-ons (control.licence_add_on, control.licence_add_on_limit by tenant_id) | 0 | 2 | addLicenceAddOn, getTenantLicences
subscription | ModuleListing | 15 | control.module_listing | 1 | 2 | listModuleCatalogue, setModuleListing | Board 4.6.
subscription | Plan | 19 | control.plan + control.plan_module + control.plan_limit | 0 | 2 | createPlan, createPlanVersion | A plan's modules and limits are rows, keyed on plan_id.
subscription | SetSubscriptionRequest | 5 | none — request only | 1 | 0 | setSubscription
subscription | Subscription | 13 | control.contract | 0 | 1 | setSubscription
subscription | Tenant | 25 | control.tenant | 0 | 2 | createTenant, updateTenant
subscription | TerminationSchedule | 6 | none — projection of control.tenant's termination columns (termination_scheduled_at, termination_retention_until, termination_requested_by_principal_id); isReversible is computed from the retention date | 0 | 1 | terminateTenant
tenancy | ConfigurationProfile | 9 | platform.configuration_profile | 0 | 1 | setConfigurationProfile | Board 1 of the client's POS design set, 20 August.
tenancy | ConfigureWorkstationRequest | 14 |  | 1 | 0 | configureWorkstation
tenancy | CreateScopeNodeRequest | 4 |  | 1 | 0 | createOrgUnit
tenancy | DeviceAssignment | 11 | tenancy.device_assignment | 1 | 2 | getDeviceAssignment, setDeviceAssignment | 16.2.9 to 16.2.11.
tenancy | DeviceFirmware | 14 | tenancy.device_firmware | 1 | 2 | createDeviceFirmware, setDeviceFirmwareStatus | 16.6.30 and 16.6.32.
tenancy | OrgUnit | 8 | platform.scope | 0 | 2 | createOrgUnit, updateOrgUnit
tenancy | Outlet | 18 | platform.outlet + platform.outlet_opening_hour | 1 | 3 | createOutlet, getOutlet, updateOutlet
tenancy | RegionSettings | 18 | platform.region_settings | 1 | 2 | getRegionSettings, updateRegionSettings
tenancy | SaleBoard | 7 | platform.sale_board + platform.sale_board_page + platform.sale_board_tile | 2 | 3 | createSaleBoard, listSaleBoards, updateSaleBoard | A board is stored as three tables (decided 14 October 2026, Chinmay, ADAM CR-080; CHG-TEN-001): the board (platform.sale_board), one row per page (pages[], platform.sale_board_page, keyed to the boar…
tenancy | SetConfigurationProfileRequest | 9 | none — request only | 1 | 0 | setConfigurationProfile | What setConfigurationProfile is sent (r11 gate, check-contract-shapes C-REQUEST-SERVER-FIELDS, R079; started ticket #30825; CHG-R11FXC-001).
tenancy | VenueSettings | 33 | platform.venue_settings | 2 | 2 | setVenueSettings, setVenueSettingsDefaults | Venue-level operational configuration that no other level can answer.
tenancy | Workstation | 26 | platform.workstation | 0 | 2 | configureWorkstation, getWorkstation
transport | CreatePassTypeRequest | 11 | none — request only | 1 | 0 | createTransportPassType
transport | CreateStationRequest | 6 | none — request only | 1 | 0 | createTransportStation
transport | CreateTimetableRequest | 7 | none — request only | 1 | 0 | createTransportTimetable
transport | CreateTransportRouteRequest | 8 | none — request only | 1 | 0 | createTransportRoute
transport | Departure | 11 | transport.departure | 0 | 1 | updateTransportDeparture
transport | DepartureOffer | 12 | none — projection | 0 | 2 | getNextTransportDeparture, getTransportDeparture
transport | FareQuote | 7 | none — computed | 0 | 1 | quoteTransportFare
transport | FareQuoteRequest | 7 | none — request only | 1 | 0 | quoteTransportFare
transport | FareTable | 10 | transport.fare_table + transport.fare_passenger_type + transport.fare_matrix_cell | 0 | 2 | getTransportFareTable, setTransportFareTable
transport | FavouriteRoute | 10 | transport.favourite_route | 0 | 1 | saveFavouriteRoute | Unique per guest, venue and ordered pair of stations.
transport | ImportTransportNetworkRequest | 3 | none — request only | 1 | 0 | importTransportNetwork
transport | PassType | 14 | transport.pass_type | 0 | 2 | createTransportPassType, updateTransportPassType
transport | RouteMap | 6 | none — projection | 0 | 1 | getTransportRouteMap
transport | SetFareTableRequest | 6 | none — request only | 1 | 0 | setTransportFareTable
transport | Station | 8 | transport.station | 0 | 2 | createTransportStation, updateTransportStation
transport | Timetable | 13 | transport.timetable + transport.timetable_run | 0 | 3 | createTransportTimetable, publishTransportTimetable, withdrawTransportTimetable
transport | TransportNetworkImport | 11 | transport.network_import | 0 | 2 | applyTransportNetworkImport, importTransportNetwork
transport | TransportRoute | 14 | transport.route + transport.route_stop | 0 | 3 | createTransportRoute, setTransportRouteStatus, updateTransportRoute
venue-map | BookableVenueMaps | 2 |  | 0 | 1 | listBookableVenueMaps | What listBookableVenueMaps returns: the published maps of one venue that carry bookable spots (decided 29 September, readiness close-out).
venue-map | PlacedResource | 12 | venuemap.placed_resource | 0 | 1 | setPlacedResource | A bookable resource where it stands on the map (decided 29 September, rev 3 REV3-15 and GAP-C2): cabana B09 on the Beach, 15 guests, Large.
venue-map | SetPlacedResourceRequest | 13 |  | 1 | 0 | setPlacedResource | What setPlacedResource takes: a PlacedResource without its server-owned fields.
venue-map | SetVenuePointRequest | 23 |  | 1 | 0 | setVenuePoint | What setVenuePoint takes: a VenuePoint without its server-owned fields, plus the point to amend.
venue-map | VenueMap | 19 | venuemap.map | 1 | 3 | createVenueMap, publishVenueMap, setVenueMapArtwork | A park map, or a floor plan.
venue-map | VenueMapDetail | 6 |  | 0 | 1 | getVenueMap | 19.2.55.
venue-map | VenueMapGraph | 6 |  | 0 | 1 | getVenueMapGraph | 19.2.56.
venue-map | VenueMapImportJob | 19 | venuemap.import_job | 0 | 1 | importVenueGeometry | Two-phase, following seating.ImportJob, and carrying its lesson: a job that finds nothing is not a successful job.
venue-map | VenuePoint | 22 | venuemap.point | 0 | 1 | setVenuePoint | 19.2.57 to 19.2.60.
venue-map | VisitPlan | 18 | venuemap.visit_plan | 0 | 3 | generateVisitPlan, getVisitPlan, updateVisitPlan | A guest's visit plan (29 September, MOB-6): the Plan tab.
venue-map | VisitPlanBooking | 5 | none — computed; the lines are orders.cart_line rows | 0 | 1 | bookVisitPlan | What bookVisitPlan returns (29 September, MOB-6): the cart handoff.
venue-map | VisitPlanPreset | 14 | venuemap.visit_plan_preset | 1 | 1 | setVisitPlanPreset | A ready-made day plan a venue offers (GST-052 Suggested Itineraries; R8 blocker GPS-C21, the lead's answer of 20 October 2026: venue-defined presets in a table, the six built-in ones as seed).
venue-map | VisitPlanRequest | 13 | none — request only; kept as `inputs` on venuemap.visit_plan | 1 | 0 | generateVisitPlan | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
venue-map | VisitPlanUpdate | 2 | none — request only; lands as a new version of venuemap.visit_plan_item rows | 1 | 0 | updateVisitPlan | What updateVisitPlan takes (29 September, MOB-6).
venue-map | VisitPlannerOptions | 6 | none — assembled on read from venuemap.visit_plan_preset, the published points and Promotions' bundles | 0 | 1 | getVisitPlannerOptions | What the visit planner offers at one venue (getVisitPlannerOptions; R8 blocker GPS-C21).
wallet | CreditType | 15 | wallet.credit_type | 2 | 2 | createCreditType, updateCreditType | Board 1.6.
wallet | GiftCard | 10 | wallet.gift_card | 0 | 1 | getGiftCard
wallet | Wallet | 11 | wallet.wallet + wallet.credit_lot | 0 | 3 | getWallet, loadGameCredits, topUpWallet
wallet | WalletAutoReloadSetting | 10 | wallet.auto_reload_setting | 1 | 2 | getWalletAutoReloadSetting, setWalletAutoReloadSetting | 4.2.17, 4.3.28.
wallet | WalletConfigurationVersion | 6 | wallet.configuration_version | 0 | 2 | publishWalletConfiguration, restoreWalletConfigurationVersion | Boards 1.10 and 10.8.
wallet | WalletFundingRules | 12 | wallet.funding_rule | 1 | 1 | setWalletFundingRules | Board 2, which is the 27 August minute one screen for one.
wallet | WalletTransaction | 11 | wallet.wallet_transaction | 0 | 1 | transferWalletBalance
wallet | WalletTransferRules | 8 | wallet.transfer_rule | 1 | 1 | setWalletTransferRules | Boards 7.2 and 7.3.
white-label | AppBuild | 15 | whitelabel.app_build | 0 | 2 | getAppBuild, requestAppBuild | One build of the tenant's branded app (decided 24 September, M24-08).
white-label | AppIcons | 5 | none — embedded in tenant_config | 0 | 2 | getAppIcons, setAppIcons
white-label | Banner | 11 | whitelabel.banner | 1 | 2 | createBanner, updateBanner
white-label | BookingFlow | 11 | whitelabel.booking_flow | 1 | 4 | createBookingFlowDefinition, getBookingFlow, getPublishedBookingFlow, updateBookingFlowDefinition | A venue's booking flow (decided 29 September, W12: operators pick their flows, see which steps are required, set their own order).
white-label | BookingFlowConfig | 29 | none — embedded in tenant_config | 1 | 2 | getBookingFlowConfig, setBookingFlowConfig | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
white-label | BookingFlowValidation | 2 | none — computed | 0 | 1 | validateBookingFlow
white-label | BrandIdentity | 12 | none — embedded in tenant_config | 1 | 2 | getBrandIdentity, setBrandIdentity | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload).
white-label | ConfigDiff | 4 | none — computed | 0 | 1 | diffConfigVersion
white-label | ConfigValidationReport | 4 | none — computed | 0 | 1 | validateTenantConfig
white-label | ConfigVersion | 15 | whitelabel.config_version | 0 | 1 | publishTenantConfig
white-label | ContentBlock | 13 | whitelabel.content_block | 1 | 3 | createContentBlock, publishContentBlock, updateContentBlock | BL-172.
white-label | ContentPage | 11 | whitelabel.content_page | 1 | 2 | createContentPage, updateContentPage
white-label | CustomDomain | 18 | whitelabel.custom_domain | 0 | 5 | claimCustomDomain, listCustomDomains, regenerateDomainToken, setPrimaryDomain, verifyCustomDomain | 24 August.
white-label | DeepLinkScheme | 3 | none — derived from the primary domain and the published configuration | 0 | 1 | getDeepLinkScheme | The URL patterns a tenant's own site uses to link into the storefront and the app (CHG-CSA-037).
white-label | FaqCategory | 5 | whitelabel.faq_category + whitelabel.faq_entry | 0 | 1 | setFaqs
white-label | FeatureToggle | 5 | whitelabel.feature_toggle | 0 | 2 | getFeatureToggles, setFeatureToggles
white-label | FontConfig | 6 | none — embedded in tenant_config | 1 | 2 | getFonts, setFonts
white-label | FooterConfig | 6 | whitelabel.footer_config + whitelabel.footer_config_column + whitelabel.footer_config_social_link | 1 | 1 | setFooter | BL-002.
white-label | GuidedChoice | 14 | whitelabel.guided_choice + whitelabel.guided_choice_question + whitelabel.guided_choice_answer | 1 | 6 | createGuidedChoice, getPublishedGuidedChoice, proposeGuidedChoice, publishGuidedChoice, unpublishGuidedChoice, updateGuidedChoice | Help me choose (decided 29 September, rev 3 REV3-11).
white-label | GuidedChoicePreview | 1 | none — computed on read | 0 | 1 | previewGuidedChoice | One row per combination of answers a guest can give (at most the product of the questions' answer counts, four questions of a few answers each), in question order (r8, WHITE-C26).
white-label | GuidedChoicePreviewRequest | 2 | none — request only | 1 | 0 | previewGuidedChoice | What previewGuidedChoice takes: a draft set-up's behaviour and questions, in GuidedChoice's shape, saved or not (r8, WHITE-C26).
white-label | HeaderConfig | 5 | none — embedded in tenant_config | 1 | 1 | setHeader
white-label | HomepageLayout | 4 | whitelabel.homepage_layout + whitelabel.homepage_section | 1 | 2 | getHomepageLayout, setHomepageLayout | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
white-label | LanguageConfig | 5 | none — embedded in tenant_config | 0 | 1 | setLanguages
white-label | ModuleEnablement | 5 | whitelabel.module_enablement | 0 | 2 | getModuleEnablement, setModuleEnablement
white-label | NavigationConfig | 4 | whitelabel.navigation_config + whitelabel.navigation_item | 1 | 2 | getNavigation, setNavigation | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
white-label | PlatformSubdomain | 4 | none — derived from the tenant's slug and its cell | 0 | 1 | getPlatformSubdomain | Every tenant's own address on TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; DI-283; CHG-CSA-043).
white-label | Policy | 9 | whitelabel.policy | 0 | 2 | listPolicies, setPolicy
white-label | Preview | 7 | none — short-lived, cache only | 0 | 1 | createPreview
white-label | PromoBlock | 11 | whitelabel.promo_block | 1 | 3 | createPromoBlock, listPromoBlocks, updatePromoBlock
white-label | PublishReviewPolicy | 4 | whitelabel.publish_review_policy | 1 | 2 | getPublishReviewPolicy, setPublishReviewPolicy | Whether publishing goes through a review step (CHG-CSA-042).
white-label | PublishedFaqCategory | 4 | none — a public projection of whitelabel.faq_category + whitelabel.faq_entry | 0 | 1 | listPublishedFaqs | One FAQ category with its published entries only (listPublishedFaqs).
white-label | PublishedPolicy | 6 | none — a public projection of whitelabel.policy | 0 | 1 | listPublishedPolicies | The current version of one policy as a guest reads it (listPublishedPolicies).
white-label | PublishedTenantConfig | 31 | none — computed from the current ConfigVersion snapshot and the live status on whitelabel.tenant_config | 0 | 1 | getPublishedTenantConfig | The public view of the tenant's configuration (getPublishedTenantConfig, decided 2 October, GFIX-1).
white-label | SitePackage | 10 | whitelabel.site_package | 0 | 2 | exportSitePackage, getSitePackage | A self-hosting package of one published version (exportSitePackage, CHG-CSA-038).
white-label | SiteSetupProgress | 7 | whitelabel.site_setup_progress | 1 | 2 | getSiteSetupProgress, setSiteSetupProgress | The Site Builder's saved progress, one row per tenant (decided 29 September, W12 and M24-05).
white-label | StorePublishingChecklist | 2 | none — computed | 0 | 2 | getStoreAccounts, setStoreAccounts
white-label | StorefrontAnalyticsProvider | 13 | whitelabel.analytics_provider | 1 | 1 | setAnalyticsProvider | One analytics platform the storefront or app reports to (22.10.29, 29 September build).
white-label | TenantAppStatus | 20 | none — computed | 0 | 2 | getTenantAppStatus, setMaintenanceMode | Computed on read.
white-label | TenantConfig | 28 | whitelabel.tenant_config | 0 | 2 | getTenantConfig, restoreConfigVersion | The tenant's working draft, one row per tenant (see the header).
white-label | Theme | 11 | none — embedded in tenant_config | 1 | 2 | getTheme, setTheme
white-label | UpdateContentPageRequest | 8 | none — request only; the fields land on whitelabel.content_page | 1 | 0 | updateContentPage | The body of updateContentPage: the fields a tenant edits.
white-label | WhiteLabelStorefrontSessionBatch | 8 | none — request only; published as storefront.sessionEvent through platform.outbox | 1 | 0 | recordStorefrontSessionEvents | One beacon from the storefront or guest-app runtime (8.3.40; decided 29 September, build pass, group G2).
workforce | AttendanceRecord | 16 | workforce.attendance | 0 | 1 | recordAttendance
workforce | RotaAssignment | 17 | workforce.rota_assignment | 1 | 2 | createRotaAssignment, updateRotaAssignment
workforce | UpdateRotaAssignmentRequest | 13 | none — request only; a partial update of workforce.rota_assignment | 1 | 0 | updateRotaAssignment | A partial update of RotaAssignment (the CR-089 pattern; CHG-SHP-008): updateRotaAssignment sends only what changes, and a field left out keeps its stored value.

## Fields
Service | Operation | Where | Field | Type | Required | Notes
OrderService | abandonCart | param (path) | cartId | string (uuid) | yes
OrderService | abandonCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | acceptFnbOrder | request | estimatedReadyAt | string (date-time)
FnbService | acceptFnbOrder | request | stationId | string (uuid)
FnbService | acceptFnbOrder | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | acceptFnbOrder | response | id | string (uuid) | yes
FnbService | acceptFnbOrder | response | orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | acceptFnbOrder | response | outletId | string (uuid) | yes
FnbService | acceptFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | acceptFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | acceptFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | acceptFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | acceptFnbOrder | response | lines | array of object | yes
FnbService | acceptFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | acceptFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | acceptFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | acceptFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | acceptFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | acceptFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | acceptFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | acceptFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | acceptFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | acceptFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | acceptFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | acceptFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | acceptFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | acceptFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | acceptFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | acceptFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | acceptFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | acceptFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | acceptFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | acceptFnbOrder | response | createdAt | string (date-time) | yes
FnbService | acceptFnbOrder | response | recordedAt | string (date-time)
FnbService | acceptFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | acceptFnbOrder | param (path) | orderId | string (uuid) | yes
FnbService | acceptFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | acceptShiftVariance | request | reason | string | yes | Retained for audit. (min length 3; max length 500)
OrderService | acceptShiftVariance | request | supervisorStepUp | object |  | The supervisor accepting, signing on this device (CHG-RUL-019).
OrderService | acceptShiftVariance | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | acceptShiftVariance | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | acceptShiftVariance | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | acceptShiftVariance | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | acceptShiftVariance | response | workstationId | string (uuid) | yes
OrderService | acceptShiftVariance | response | venueId | string (uuid) | yes
OrderService | acceptShiftVariance | response | scopePath | string | yes
OrderService | acceptShiftVariance | response | principalId | string (uuid) | yes | Who opened it.
OrderService | acceptShiftVariance | response | principalDisplayName | string
OrderService | acceptShiftVariance | response | incidents | array of object |  | BL-097.
OrderService | acceptShiftVariance | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | acceptShiftVariance | response | incidents[].at | string (date-time)
OrderService | acceptShiftVariance | response | incidents[].principalId | string (uuid)
OrderService | acceptShiftVariance | response | incidents[].note | string |  | (nullable)
OrderService | acceptShiftVariance | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | acceptShiftVariance | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | acceptShiftVariance | response | depositBoxCode | string |  | (nullable)
OrderService | acceptShiftVariance | response | bagNumber | string |  | (nullable)
OrderService | acceptShiftVariance | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | acceptShiftVariance | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | acceptShiftVariance | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | acceptShiftVariance | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | acceptShiftVariance | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | acceptShiftVariance | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | acceptShiftVariance | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | acceptShiftVariance | response | openedAt | string (date-time) | yes
OrderService | acceptShiftVariance | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | acceptShiftVariance | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | acceptShiftVariance | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | acceptShiftVariance | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | acceptShiftVariance | response | closedAt | string (date-time) |  | (nullable)
OrderService | acceptShiftVariance | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | acceptShiftVariance | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | acceptShiftVariance | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | acceptShiftVariance | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | acceptShiftVariance | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | acceptShiftVariance | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | acceptShiftVariance | response | approvals | array of object
OrderService | acceptShiftVariance | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | acceptShiftVariance | response | approvals[].principalId | string (uuid) | yes
OrderService | acceptShiftVariance | response | approvals[].at | string (date-time) | yes
OrderService | acceptShiftVariance | response | approvals[].reason | string
OrderService | acceptShiftVariance | param (path) | shiftId | string (uuid) | yes
OrderService | acceptShiftVariance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | addBlacklistEntry | request | mediaCode | string | yes | (max length 256)
AccessService | addBlacklistEntry | request | reason | string | yes | (min length 3; max length 500)
AccessService | addBlacklistEntry | request | expiresAt | string (date-time)
AccessService | addBlacklistEntry | request | listType | enum (blacklist, whitelist) |  | A whitelist entry waits for a second approver (DEC-254; CHG-CSP-031). (default blacklist)
AccessService | addBlacklistEntry | request | disableScope | enum (entireCredential, venueAccess, attractionAccess, reEntry, fastPass, specificEntitlement) |  | What the entry disables (BlacklistEntry.disableScope). (default entireCredential)
AccessService | addBlacklistEntry | response | mediaCode | string | yes | Unique within the tenant (decided 28 September, audit R108): one entry per code, compared exactly: it is what a gate reads off the media, an opaque external id (common.yaml, the uniqueness rule).
AccessService | addBlacklistEntry | response | reason | string | yes
AccessService | addBlacklistEntry | response | addedAt | string (date-time) | yes
AccessService | addBlacklistEntry | response | addedByPrincipalId | string (uuid) | yes
AccessService | addBlacklistEntry | response | expiresAt | string (date-time) |  | (nullable)
AccessService | addBlacklistEntry | response | listType | enum (blacklist, whitelist) |  | A blacklist entry refuses the media; a whitelist entry is an approved exception to a restriction (added 29 September, data-model close-out DM1). (default blacklist)
AccessService | addBlacklistEntry | response | disableScope | enum (entireCredential, venueAccess, attractionAccess, reEntry, fastPass, specificEntitlement) |  | What the entry disables (added 29 September, data-model close-out DM1). (default entireCredential)
AccessService | addBlacklistEntry | response | distributedTo | array of enum (centralPlatform, venueEdge, onlineGates, offlineRevocationPackage) |  | Where the restriction has been distributed so far, as listCredentialDisableBlacklist returns it (added 29 September, data-model close-out DM1).
AccessService | addBlacklistEntry | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | addBlacklistEntry | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addCartLine | request | variantId | string (uuid) | yes
OrderService | addCartLine | request | quantity | integer | yes | (min 1)
OrderService | addCartLine | request | performanceId | string (uuid)
OrderService | addCartLine | request | bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | addCartLine | request | bookedWindow.startsAt | string (date-time) | yes
OrderService | addCartLine | request | bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | addCartLine | request | recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | addCartLine | request | tableReservationId | string (uuid) |  | A table deposit line (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation in awaitingDeposit this pays for, sent with variantId set to the booking's deposit.variantId and quantity 1. (nullable)
OrderService | addCartLine | request | seatIds | array of string (uuid) |  | At most VenueSettings.seating.maxSeatsPerGuestOrder seats per booking on a guest channel (default 10, bounds 1 to 50, decided 29 September, rev 3 REV3-7); at most 10 per sale on staff and POS (audit… (max items 50)
OrderService | addCartLine | request | resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant and quantity is 1. (nullable)
OrderService | addCartLine | request | parentLineId | string (uuid) |  | For an add-on attaching to a ticket already in the cart. (nullable)
OrderService | addCartLine | request | attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | addCartLine | request | attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | addCartLine | request | attributes.transport.routeId | string (uuid) | yes | The transport.TransportRoute.
OrderService | addCartLine | request | attributes.transport.fromStationId | string (uuid) | yes | Boarding station, a stop of the route.
OrderService | addCartLine | request | attributes.transport.toStationId | string (uuid) | yes | Alighting station, a later stop of the route.
OrderService | addCartLine | request | attributes.transport.passengerTypeCode | string |  | The fare table's passenger type (adult, child, ...). (pattern ^[a-z][a-zA-Z0-9]{0,31}$; nullable)
OrderService | addCartLine | request | attributes.transport.passTypeId | string (uuid) |  | Pass purchase only. (nullable)
OrderService | addCartLine | request | attributes.transport.passEntitlementId | string (uuid) |  | A seat reserved with a pass already owned. (nullable)
OrderService | addCartLine | request | attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | addCartLine | request | attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | addCartLine | request | attributes.parking.plate | object | yes
OrderService | addCartLine | request | attributes.parking.validFrom | string (date-time) | yes
OrderService | addCartLine | request | attributes.parking.validTo | string (date-time) | yes
OrderService | addCartLine | request | attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | addCartLine | request | attributes.bundle.bundleId | string (uuid) | yes
OrderService | addCartLine | request | attributes.bundle.choices | array of object
OrderService | addCartLine | response | id | string (uuid) | yes
OrderService | addCartLine | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | addCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | addCartLine | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | addCartLine | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | addCartLine | response | venueId | string (uuid) | yes
OrderService | addCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | addCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | addCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | addCartLine | response | lines | array of CartLine | yes
OrderService | addCartLine | response | lines[].id | string (uuid) | yes
OrderService | addCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | addCartLine | response | lines[].productName | string |  | (read-only)
OrderService | addCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | addCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | addCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | addCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | addCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | addCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | addCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | addCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | addCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | addCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | addCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | addCartLine | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | addCartLine | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | addCartLine | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | addCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | addCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | addCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | addCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | addCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | addCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | addCartLine | response | conflicts | array of CartConflict
OrderService | addCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | addCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | addCartLine | response | conflicts[].message | string
OrderService | addCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | addCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | addCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | addCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | addCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | addCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | addCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | addCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | addCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | addCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | addCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | addCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | addCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | addCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | addCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | addCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | addCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | addCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | addCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | addCartLine | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | addCartLine | response | locale | string
OrderService | addCartLine | response | createdAt | string (date-time)
OrderService | addCartLine | response | updatedAt | string (date-time)
OrderService | addCartLine | param (path) | cartId | string (uuid) | yes
OrderService | addCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addCartLine | param (header) | X-Admission-Token | string |  | The on-sale waiting room's admission token (ADR-0066, accepted 1 October).
PlatformService | addLicenceAddOn | request | currencyCode | string |  | The ISO 4217 currency of the add-on's price (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored with its currency on the row, since a plat… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | tenantId | string (uuid) |  | The tenant the add-on was sold to — the tenantId in the path, never the body. (read-only)
PlatformService | addLicenceAddOn | request | moduleKey | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
PlatformService | addLicenceAddOn | request | limitOverrides | array of EntitlementLimit
PlatformService | addLicenceAddOn | request | limitOverrides[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | addLicenceAddOn | request | limitOverrides[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageAllowed | boolean |  | (default False)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | request | price | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | request | validFrom | string (date)
PlatformService | addLicenceAddOn | request | validTo | string (date) |  | (nullable)
PlatformService | addLicenceAddOn | request | note | string |  | (max length 500)
PlatformService | addLicenceAddOn | request | removedAt | string (date-time) |  | When removeLicenceAddOn ended the add-on (r8 re-walk, CHG-R8RW-003); null while it is in force. (read-only; nullable)
PlatformService | addLicenceAddOn | request | removedByPrincipalId | string (uuid) |  | Who removed it (the caller of removeLicenceAddOn); null while it is in force. (read-only; nullable)
PlatformService | addLicenceAddOn | request | removalReason | string |  | Why it was removed (removeLicenceAddOn's reason); null while it is in force. (max length 500; read-only; nullable)
PlatformService | addLicenceAddOn | response | poweredByRemovable | boolean |  | Whether the tenant's licence lets it switch "Powered by TICVAI" off (Chinmay, 2 October, workbook Q160 and the pre-apply round; CHG-CSA-036). (default False; read-only)
PlatformService | addLicenceAddOn | response | tenantId | string (uuid) | yes
PlatformService | addLicenceAddOn | response | planId | string (uuid) |  | (nullable)
PlatformService | addLicenceAddOn | response | licensedModules | array of object | yes | Union of plan modules and add-ons.
PlatformService | addLicenceAddOn | response | licensedModules[].moduleKey | string | yes
PlatformService | addLicenceAddOn | response | licensedModules[].displayName | string
PlatformService | addLicenceAddOn | response | licensedModules[].source | enum (plan, addOn) | yes
PlatformService | addLicenceAddOn | response | licensedModules[].validTo | string (date) |  | (nullable)
PlatformService | addLicenceAddOn | response | limits | array of EntitlementLimit | yes
PlatformService | addLicenceAddOn | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | addLicenceAddOn | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | addLicenceAddOn | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | param (path) | tenantId | string (uuid) | yes
PlatformService | addLicenceAddOn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addTip | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | addTip | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | request | source | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) | yes | serviceCharge is not a tip and is separated deliberately — it is revenue in most jurisdictions, and pooling it with tips is how a payroll dispute starts.
OrderService | addTip | request | allocateToPrincipalId | string (uuid) |  | Where the venue allocates rather than pools.
OrderService | addTip | request | recordedAt | string (date-time) | yes
OrderService | addTip | response | tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | addTip | response | tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | addTip | response | tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | addTip | response | tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | addTip | response | tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | addTip | response | id | string (uuid) | yes
OrderService | addTip | response | orderId | string (uuid) | yes
OrderService | addTip | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | addTip | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | addTip | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | addTip | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | addTip | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | addTip | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | addTip | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addTip | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | addTip | response | providerName | string |  | (nullable)
OrderService | addTip | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | addTip | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | addTip | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | addTip | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | addTip | response | nextAction.kind | enum (redirect, terminal)
OrderService | addTip | response | nextAction.url | string (uri) |  | (nullable)
OrderService | addTip | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | addTip | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | addTip | response | recordedAt | string (date-time) | yes
OrderService | addTip | response | syncedAt | string (date-time) |  | (nullable)
OrderService | addTip | param (path) | paymentId | string (uuid) | yes
OrderService | addTip | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | addToWishlist | request | variantId | string (uuid) | yes
MarketingService | addToWishlist | request | performanceId | string (uuid) |  | Saving a specific date rather than the product generally. (nullable)
MarketingService | addToWishlist | request | note | string |  | (max length 200)
MarketingService | addToWishlist | response | subjectId | string (uuid) | yes
MarketingService | addToWishlist | response | items | array of WishlistItem | yes | Newest first: ordered by addedAt descending, id as the tiebreak (CHG-MKT-002).
MarketingService | addToWishlist | response | items[].id | string (uuid) | yes
MarketingService | addToWishlist | response | items[].subjectId | string (uuid) | yes | The guest who saved it. (read-only)
MarketingService | addToWishlist | response | items[].variantId | string (uuid) | yes
MarketingService | addToWishlist | response | items[].productName | string |  | Catalogue's, not Marketing's.
MarketingService | addToWishlist | response | items[].performanceId | string (uuid) |  | (nullable)
MarketingService | addToWishlist | response | items[].performanceStartsAt | string (date-time) |  | The saved performance's start, from Catalogue's variantListingFacts; null for a date-less entry. (nullable)
MarketingService | addToWishlist | response | items[].price | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | addToWishlist | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | addToWishlist | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | addToWishlist | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | addToWishlist | response | items[].imageAssetRef | string |  | The product's primary media, from Catalogue's variantListingFacts. (nullable)
MarketingService | addToWishlist | response | items[].isAvailable | boolean | yes | False where the product has been withdrawn or the performance has passed.
MarketingService | addToWishlist | response | items[].unavailableReason | string |  | Why isAvailable is false, in Catalogue's words (variantListingFacts.reason), or performancePassed; null when available. (nullable)
MarketingService | addToWishlist | response | items[].note | string |  | (nullable)
MarketingService | addToWishlist | response | items[].addedAt | string (date-time) | yes
MarketingService | addToWishlist | param (path) | subjectId | string (uuid) | yes
MarketingService | addToWishlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | allocateDepositBox | request | id | string (uuid) |  | (read-only)
OrderService | allocateDepositBox | request | cashierPrincipalId | string (uuid) | yes
OrderService | allocateDepositBox | request | cashierName | string |  | (read-only)
OrderService | allocateDepositBox | request | venueId | string (uuid) | yes
OrderService | allocateDepositBox | request | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | allocateDepositBox | request | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | allocateDepositBox | request | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | allocateDepositBox | request | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | openingDenominations | array of object |  | 5.8.3.
OrderService | allocateDepositBox | request | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | allocateDepositBox | request | openingDenominations[].count | integer | yes | (min 0)
OrderService | allocateDepositBox | request | withdrawnTotal | withdrawnTotal |  | Reduces the expected close figure. (read-only)
OrderService | allocateDepositBox | request | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | allocateDepositBox | request | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | allocateDepositBox | request | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not in the box's own currency. (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | expectedTotal | expectedTotal |  | The figure the box's close count is measured against, filled when the box is counted. (nullable)
OrderService | allocateDepositBox | request | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | variance | variance |  | Counted minus expected; negative is short. (nullable)
OrderService | allocateDepositBox | request | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | allocateDepositBox | request | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | allocateDepositBox | request | closedAt | string (date-time) |  | (nullable)
OrderService | allocateDepositBox | request | recordedAt | string (date-time) |  | When the device made the write (R113; CHG-OFL-003): for an allocation, the same moment as allocatedAt, kept in recorded_at, the column every offline-written table carries for the sync to order replay…
OrderService | allocateDepositBox | response | id | string (uuid) |  | (read-only)
OrderService | allocateDepositBox | response | cashierPrincipalId | string (uuid) | yes
OrderService | allocateDepositBox | response | cashierName | string |  | (read-only)
OrderService | allocateDepositBox | response | venueId | string (uuid) | yes
OrderService | allocateDepositBox | response | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | allocateDepositBox | response | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | allocateDepositBox | response | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | allocateDepositBox | response | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | openingDenominations | array of object |  | 5.8.3.
OrderService | allocateDepositBox | response | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | allocateDepositBox | response | openingDenominations[].count | integer | yes | (min 0)
OrderService | allocateDepositBox | response | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | allocateDepositBox | response | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | allocateDepositBox | response | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | allocateDepositBox | response | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not in the box's own currency. (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | expectedTotal | object |  | The figure the box's close count is measured against, filled when the box is counted. (nullable)
OrderService | allocateDepositBox | response | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | variance | object |  | Counted minus expected; negative is short. (nullable)
OrderService | allocateDepositBox | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | allocateDepositBox | response | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | allocateDepositBox | response | closedAt | string (date-time) |  | (nullable)
OrderService | allocateDepositBox | response | recordedAt | string (date-time) |  | When the device made the write (R113; CHG-OFL-003): for an allocation, the same moment as allocatedAt, kept in recorded_at, the column every offline-written table carries for the sync to order replay…
OrderService | allocateDepositBox | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | analysePromotionConflicts | response | promotionId | string (uuid) | yes
CatalogueService | analysePromotionConflicts | response | conflicts | array of object | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].otherPromotionId | string (uuid) | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].otherPromotionCode | string | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].overlap | enum (products, period, channel, full) | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].combinedDiscount | number | yes | Combined percentage where both apply to the same line.
CatalogueService | analysePromotionConflicts | response | conflicts[].isBlocking | boolean |  | True where the combination would produce a line price of zero or below (decided 28 September, audit R101).
CatalogueService | analysePromotionConflicts | response | conflicts[].isNearZero | boolean |  | True where the combination leaves a net line price above zero but below the venue setting promotions.nearZeroLinePrice (proposed AED 1.00; decided 28 September, audit R096 (5)).
CatalogueService | analysePromotionConflicts | response | worstCaseDiscount | number | yes | Largest combined discount any single line could receive.
CatalogueService | analysePromotionConflicts | param (path) | promotionId | string (uuid) | yes
OrderService | appendEntitlementToMedia | request | id | string (uuid) | yes | Client-generated UUIDv7 of the new order this creates, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | appendEntitlementToMedia | request | lines | array of object | yes | (min items 1)
OrderService | appendEntitlementToMedia | request | lines[].variantId | string (uuid) | yes
OrderService | appendEntitlementToMedia | request | lines[].quantity | integer | yes | (min 1)
OrderService | appendEntitlementToMedia | request | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | request | paymentMethod | enum (card, cash, wallet, giftCard, chargeToAccount)
OrderService | appendEntitlementToMedia | request | note | string |  | (max length 300)
OrderService | appendEntitlementToMedia | request | recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order | object | yes | A new order.
OrderService | appendEntitlementToMedia | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | appendEntitlementToMedia | response | order.orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | appendEntitlementToMedia | response | order.channel | object | yes | Where it came from.
OrderService | appendEntitlementToMedia | response | order.channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.venueId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.scopePath | string | yes
OrderService | appendEntitlementToMedia | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | appendEntitlementToMedia | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | appendEntitlementToMedia | response | order.chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].name | string
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.lines | array of OrderLine | yes
OrderService | appendEntitlementToMedia | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | appendEntitlementToMedia | response | order.lines[].variantId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].performanceId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | appendEntitlementToMedia | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | appendEntitlementToMedia | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | appendEntitlementToMedia | response | order.lines[].holderName | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | appendEntitlementToMedia | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | appendEntitlementToMedia | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | appendEntitlementToMedia | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | appendEntitlementToMedia | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | appendEntitlementToMedia | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | appendEntitlementToMedia | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | appendEntitlementToMedia | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | appendEntitlementToMedia | response | order.payments | array of Payment
OrderService | appendEntitlementToMedia | response | order.payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].id | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].orderId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | appendEntitlementToMedia | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | appendEntitlementToMedia | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].providerName | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.principalId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.workstationId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.createdAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media | object | yes | The full set now on the media, so the cashier can say what the QR does.
OrderService | appendEntitlementToMedia | response | media.mediaCode | string | yes
OrderService | appendEntitlementToMedia | response | media.mediaKind | enum (qr, wristband, card, nfc, mobilePass) |  | From the entitlements' credentialFormat (CR-196): platformSignedQr, staticQr or null (which is platformSignedQr, CHG-R6-031) is qr, and rfidCard is card.
OrderService | appendEntitlementToMedia | response | media.subjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.isValid | boolean | yes | True when at least one entitlement on the code counts (see the schema's description).
OrderService | appendEntitlementToMedia | response | media.invalidReason | string |  | Null while isValid. (nullable)
OrderService | appendEntitlementToMedia | response | media.canAcceptMore | boolean |  | False where the media has been surrendered, expired or blocked.
OrderService | appendEntitlementToMedia | response | media.entitlements | array of object | yes
OrderService | appendEntitlementToMedia | response | media.entitlements[].entitlementId | string (uuid)
OrderService | appendEntitlementToMedia | response | media.entitlements[].name | string
OrderService | appendEntitlementToMedia | response | media.entitlements[].kind | enum (admission, locker, fnb, retail, parking, rental, experience, membership) |  | The product's kind (catalogue.Product.kind, read through catalogue#productRecords by the entitlement's productId), mapped onto these values (ADAM CR-226, option A; Chinmay, 25 October 2026; CHG-R10OR…
OrderService | appendEntitlementToMedia | response | media.entitlements[].orderId | string (uuid)
OrderService | appendEntitlementToMedia | response | media.entitlements[].addedAt | string (date-time) |  | When the entitlement was put on this media: access.entitlement.media_linked_at, written when the media code is set or rotated (ADAM CR-226).
OrderService | appendEntitlementToMedia | response | media.entitlements[].status | object |  | Replaced isRedeemed on 17 August.
OrderService | appendEntitlementToMedia | response | media.entitlements[].entriesUsed | integer
OrderService | appendEntitlementToMedia | response | media.entitlements[].entriesAllowed | integer |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].redeemedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].transferredToSubjectId | string (uuid) |  | The subjectId of the entitlement whose supersedesEntitlementId names this one with issuedVia transfer (ADAM CR-226), read through access#entitlementRecords; null when it was not transferred. (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].validTo | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | addedEntitlementIds | array of string (uuid)
OrderService | appendEntitlementToMedia | param (path) | mediaCode | string | yes | The QR, wristband or card the guest is already carrying.
OrderService | appendEntitlementToMedia | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | applyCartPromoCode | request | code | string | yes | The code as the guest typed it. (min length 1; max length 100)
OrderService | applyCartPromoCode | response | id | string (uuid) | yes
OrderService | applyCartPromoCode | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | applyCartPromoCode | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | applyCartPromoCode | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | applyCartPromoCode | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | applyCartPromoCode | response | venueId | string (uuid) | yes
OrderService | applyCartPromoCode | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | applyCartPromoCode | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | applyCartPromoCode | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | applyCartPromoCode | response | lines | array of CartLine | yes
OrderService | applyCartPromoCode | response | lines[].id | string (uuid) | yes
OrderService | applyCartPromoCode | response | lines[].variantId | string (uuid) | yes
OrderService | applyCartPromoCode | response | lines[].productName | string |  | (read-only)
OrderService | applyCartPromoCode | response | lines[].quantity | integer | yes | (min 1)
OrderService | applyCartPromoCode | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | applyCartPromoCode | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | applyCartPromoCode | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | applyCartPromoCode | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | applyCartPromoCode | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | applyCartPromoCode | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | applyCartPromoCode | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | applyCartPromoCode | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | applyCartPromoCode | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | applyCartPromoCode | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | applyCartPromoCode | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | applyCartPromoCode | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | applyCartPromoCode | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | applyCartPromoCode | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | applyCartPromoCode | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | applyCartPromoCode | response | conflicts | array of CartConflict
OrderService | applyCartPromoCode | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | applyCartPromoCode | response | conflicts[].lineIds | array of string (uuid)
OrderService | applyCartPromoCode | response | conflicts[].message | string
OrderService | applyCartPromoCode | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | applyCartPromoCode | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | applyCartPromoCode | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | applyCartPromoCode | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | applyCartPromoCode | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | applyCartPromoCode | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | applyCartPromoCode | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | applyCartPromoCode | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | applyCartPromoCode | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | applyCartPromoCode | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | applyCartPromoCode | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | applyCartPromoCode | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | applyCartPromoCode | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | applyCartPromoCode | response | extensionsUsed | integer |  | (read-only)
OrderService | applyCartPromoCode | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | applyCartPromoCode | response | locale | string
OrderService | applyCartPromoCode | response | createdAt | string (date-time)
OrderService | applyCartPromoCode | response | updatedAt | string (date-time)
OrderService | applyCartPromoCode | param (path) | cartId | string (uuid) | yes
OrderService | applyCartPromoCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | applyManualDiscount | request | id | string (uuid) | yes | Client-generated UUIDv7 of this discount, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | applyManualDiscount | request | lineId | string (uuid) |  | Omit to discount the order rather than a line. (nullable)
OrderService | applyManualDiscount | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | request | percentage | number |  | (min 0; max 100)
OrderService | applyManualDiscount | request | reason | string | yes | Required, and free text rather than a code list. (min length 3; max length 300)
OrderService | applyManualDiscount | request | reasonCode | string |  | Optional alongside the free text, where the venue maintains a list. (nullable)
OrderService | applyManualDiscount | request | approverPrincipalId | string (uuid) |  | Required above the venue threshold. (nullable)
OrderService | applyManualDiscount | request | recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | applyManualDiscount | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | applyManualDiscount | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | applyManualDiscount | response | channel | object | yes | Where it came from.
OrderService | applyManualDiscount | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | applyManualDiscount | response | venueId | string (uuid) | yes
OrderService | applyManualDiscount | response | scopePath | string | yes
OrderService | applyManualDiscount | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | applyManualDiscount | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | applyManualDiscount | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | applyManualDiscount | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | applyManualDiscount | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | applyManualDiscount | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | applyManualDiscount | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | applyManualDiscount | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | applyManualDiscount | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | applyManualDiscount | response | droppedPromotions[].name | string
OrderService | applyManualDiscount | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | applyManualDiscount | response | totalPriceVariance | object |  | Sum across lines.
OrderService | applyManualDiscount | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines | array of OrderLine | yes
OrderService | applyManualDiscount | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | applyManualDiscount | response | lines[].variantId | string (uuid) | yes
OrderService | applyManualDiscount | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | applyManualDiscount | response | lines[].performanceId | string (uuid)
OrderService | applyManualDiscount | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | applyManualDiscount | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | applyManualDiscount | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | applyManualDiscount | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | applyManualDiscount | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | applyManualDiscount | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | applyManualDiscount | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | applyManualDiscount | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | applyManualDiscount | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | applyManualDiscount | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | applyManualDiscount | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | applyManualDiscount | response | lines[].quantity | integer | yes | (min 1)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].holderName | string |  | (nullable)
OrderService | applyManualDiscount | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | applyManualDiscount | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | applyManualDiscount | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | applyManualDiscount | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | applyManualDiscount | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | applyManualDiscount | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | applyManualDiscount | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | applyManualDiscount | response | lines[].discounts[].id | string (uuid) | yes
OrderService | applyManualDiscount | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | applyManualDiscount | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | applyManualDiscount | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | applyManualDiscount | response | payments | array of Payment
OrderService | applyManualDiscount | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].id | string (uuid) | yes
OrderService | applyManualDiscount | response | payments[].orderId | string (uuid) | yes
OrderService | applyManualDiscount | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | applyManualDiscount | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | applyManualDiscount | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | applyManualDiscount | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | applyManualDiscount | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | applyManualDiscount | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | applyManualDiscount | response | payments[].providerName | string |  | (nullable)
OrderService | applyManualDiscount | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | applyManualDiscount | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | applyManualDiscount | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | principalId | string (uuid)
OrderService | applyManualDiscount | response | workstationId | string (uuid)
OrderService | applyManualDiscount | response | shiftId | string (uuid) |  | (nullable)
OrderService | applyManualDiscount | response | subjectId | string (uuid) |  | (nullable)
OrderService | applyManualDiscount | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | applyManualDiscount | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | applyManualDiscount | response | createdAt | string (date-time) | yes
OrderService | applyManualDiscount | response | recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | syncedAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | param (path) | orderId | string (uuid) | yes
OrderService | applyManualDiscount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | applyTransportNetworkImport | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | applyTransportNetworkImport | response | venueId | string (uuid) | yes | (read-only)
VenueOpsService | applyTransportNetworkImport | response | format | enum (csvBundle, gtfs) | yes
VenueOpsService | applyTransportNetworkImport | response | sourceRef | string (uuid) | yes
VenueOpsService | applyTransportNetworkImport | response | status | TransportNetworkImportStatus: enum (validating, previewReady, failed, applied, expired) | yes | validating → previewReady or failed; previewReady → applied, or expired after 7 days unapplied (proposed, client to correct).
VenueOpsService | applyTransportNetworkImport | response | preview | object |  | What applying would write. (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | response | preview.stationsToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.stationsToUpdate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.routesToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.routesToUpdate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.stopsToWrite | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.timetablesToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | findings | array of TransportNetworkImportFinding |  | (max items 1000; read-only)
VenueOpsService | applyTransportNetworkImport | response | findings[].code | enum (nothingFound, fileMissing, headerMismatch, stationCodeDuplicate, stationCoordinatesMissing, routeCodeDuplicate, routeStopUnknownStation, routeOffsetsNotIncreasing, …) | yes | stationCoordinatesMissing is a warning (the station is listed and left off the map); routeActiveStopsChanged is a warning (those stops are skipped); every other code is an error and blocks the apply.
VenueOpsService | applyTransportNetworkImport | response | findings[].severity | enum (error, warning) | yes
VenueOpsService | applyTransportNetworkImport | response | findings[].file | string |  | e.g. (nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].row | integer |  | (min 1; nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].reference | string |  | The station (nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].message | string | yes | (max length 500)
VenueOpsService | applyTransportNetworkImport | response | createdBy | string (uuid) |  | (read-only)
VenueOpsService | applyTransportNetworkImport | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | applyTransportNetworkImport | response | appliedBy | string (uuid) |  | (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | response | appliedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | param (path) | importId | string (uuid) | yes
VenueOpsService | applyTransportNetworkImport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | approveManualOverrideSupervisor | request | supervisorId | string | yes | Approving supervisor.
AccessService | approveManualOverrideSupervisor | request | scanId | string | yes | The denied scan being overridden, and the key of this write (x-ticvai-body-key).
AccessService | approveManualOverrideSupervisor | request | selectType | enum (guestService, ticketingError, operationalException, managementAuthorization, technicalFailure, eventException, other) | yes | Override reason category.
AccessService | approveManualOverrideSupervisor | request | reasonNote | string |  | Free-text justification, stored after the category in override_reason (see selectType).
AccessService | approveManualOverrideSupervisor | request | accessPointId | string |  | Gate
AccessService | approveManualOverrideSupervisor | request | deviceId | string |  | Device
AccessService | approveManualOverrideSupervisor | request | originalDecision | string |  | Original validation decision, read only and never rewritten.
AccessService | approveManualOverrideSupervisor | response | supervisorId | string | yes | Approving supervisor
AccessService | approveManualOverrideSupervisor | response | scanId | string | yes | The denied scan being overridden
AccessService | approveManualOverrideSupervisor | response | selectType | enum (guestService, ticketingError, operationalException, managementAuthorization, technicalFailure, eventException, other) | yes | Override reason category
AccessService | approveManualOverrideSupervisor | response | reasonNote | string |  | Free-text justification
AccessService | approveManualOverrideSupervisor | response | accessPointId | string |  | Gate
AccessService | approveManualOverrideSupervisor | response | deviceId | string |  | Device
AccessService | approveManualOverrideSupervisor | response | originalDecision | string |  | Original validation decision, read only and never rewritten
AccessService | approveManualOverrideSupervisor | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | approveMatrixMultiLevel | request | code | string | yes | Stable rule code the PUT upserts by
TenancyService | approveMatrixMultiLevel | request | approvalMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) | yes | How approvers at this rule combine
TenancyService | approveMatrixMultiLevel | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveMatrixMultiLevel | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveMatrixMultiLevel | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveMatrixMultiLevel | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveMatrixMultiLevel | request | percentage | number |  | Percentage
TenancyService | approveMatrixMultiLevel | request | module | string |  | Required by the server.
TenancyService | approveMatrixMultiLevel | request | product | string |  | Product
TenancyService | approveMatrixMultiLevel | request | venue | string |  | Venue.
TenancyService | approveMatrixMultiLevel | request | department | string |  | Department
TenancyService | approveMatrixMultiLevel | request | customerType | string |  | Customer Type
TenancyService | approveMatrixMultiLevel | request | risk | string |  | Risk
TenancyService | approveMatrixMultiLevel | request | exceptionType | string |  | Exception Type
TenancyService | approveMatrixMultiLevel | request | legalEntity | string |  | Legal Entity
TenancyService | approveMatrixMultiLevel | request | minimumApprovals | integer |  | N in N-of-M: approvals needed from the approver group
TenancyService | approveMatrixMultiLevel | request | rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this level does
TenancyService | approveMatrixMultiLevel | request | requestChanges | boolean |  | Approvers may return the request for changes
TenancyService | approveMatrixMultiLevel | request | delegate | boolean |  | Approvers may delegate
TenancyService | approveMatrixMultiLevel | request | reassign | boolean |  | The request may be reassigned
TenancyService | approveMatrixMultiLevel | request | skipConditions | string |  | Skip Conditions
TenancyService | approveMatrixMultiLevel | request | requiredApproverRole | string |  | Role that must always approve, e.g.
TenancyService | approveMatrixMultiLevel | response | code | string | yes | Stable rule code the PUT upserts by
TenancyService | approveMatrixMultiLevel | response | approvalMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) | yes | How approvers at this rule combine
TenancyService | approveMatrixMultiLevel | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveMatrixMultiLevel | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveMatrixMultiLevel | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveMatrixMultiLevel | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveMatrixMultiLevel | response | percentage | number |  | Percentage
TenancyService | approveMatrixMultiLevel | response | module | string |  | Module
TenancyService | approveMatrixMultiLevel | response | product | string |  | Product
TenancyService | approveMatrixMultiLevel | response | venue | string |  | Venue
TenancyService | approveMatrixMultiLevel | response | department | string |  | Department
TenancyService | approveMatrixMultiLevel | response | customerType | string |  | Customer Type
TenancyService | approveMatrixMultiLevel | response | risk | string |  | Risk
TenancyService | approveMatrixMultiLevel | response | exceptionType | string |  | Exception Type
TenancyService | approveMatrixMultiLevel | response | legalEntity | string |  | Legal Entity
TenancyService | approveMatrixMultiLevel | response | minimumApprovals | integer |  | N in N-of-M: approvals needed from the approver group
TenancyService | approveMatrixMultiLevel | response | rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this level does
TenancyService | approveMatrixMultiLevel | response | requestChanges | boolean |  | Approvers may return the request for changes
TenancyService | approveMatrixMultiLevel | response | delegate | boolean |  | Approvers may delegate
TenancyService | approveMatrixMultiLevel | response | reassign | boolean |  | The request may be reassigned
TenancyService | approveMatrixMultiLevel | response | skipConditions | string |  | Skip Conditions
TenancyService | approveMatrixMultiLevel | response | requiredApproverRole | string |  | Role that must always approve, e.g.
TenancyService | approveMatrixMultiLevel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | approveRoleAuthorityDelegation | request | user | string |  | User
TenancyService | approveRoleAuthorityDelegation | request | role | string |  | Role
TenancyService | approveRoleAuthorityDelegation | request | position | string |  | Position
TenancyService | approveRoleAuthorityDelegation | request | department | string |  | Department
TenancyService | approveRoleAuthorityDelegation | request | venue | string |  | Venue
TenancyService | approveRoleAuthorityDelegation | request | businessUnit | string |  | Business Unit.
TenancyService | approveRoleAuthorityDelegation | request | legalEntity | string |  | Legal Entity.
TenancyService | approveRoleAuthorityDelegation | request | region | string |  | Region
TenancyService | approveRoleAuthorityDelegation | request | delegator | string | yes | Delegator
TenancyService | approveRoleAuthorityDelegation | request | delegate | string | yes | Delegate
TenancyService | approveRoleAuthorityDelegation | request | scope | string |  | Scope
TenancyService | approveRoleAuthorityDelegation | request | start | string (date-time) | yes | Delegation start
TenancyService | approveRoleAuthorityDelegation | request | end | string (date-time) | yes | Delegation end
TenancyService | approveRoleAuthorityDelegation | request | reason | string |  | Reason
TenancyService | approveRoleAuthorityDelegation | request | delegationType | enum (leave, travel, vacancy, eventOperations) |  | Why temporary authority is granted
TenancyService | approveRoleAuthorityDelegation | request | requiredRole | string |  | Required role
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveRoleAuthorityDelegation | request | requestKind | string |  | What the authority limit covers, e.g.
TenancyService | approveRoleAuthorityDelegation | request | authorityPercentage | number |  | Percentage limit where the authority is a percentage, e.g.
TenancyService | approveRoleAuthorityDelegation | response | user | string |  | User
TenancyService | approveRoleAuthorityDelegation | response | role | string |  | Role
TenancyService | approveRoleAuthorityDelegation | response | position | string |  | Position
TenancyService | approveRoleAuthorityDelegation | response | department | string |  | Department
TenancyService | approveRoleAuthorityDelegation | response | venue | string |  | Venue
TenancyService | approveRoleAuthorityDelegation | response | businessUnit | string |  | Business Unit
TenancyService | approveRoleAuthorityDelegation | response | legalEntity | string |  | Legal Entity
TenancyService | approveRoleAuthorityDelegation | response | region | string |  | Region
TenancyService | approveRoleAuthorityDelegation | response | delegator | string | yes | Delegator
TenancyService | approveRoleAuthorityDelegation | response | delegate | string | yes | Delegate
TenancyService | approveRoleAuthorityDelegation | response | scope | string |  | Scope
TenancyService | approveRoleAuthorityDelegation | response | start | string (date-time) | yes | Delegation start
TenancyService | approveRoleAuthorityDelegation | response | end | string (date-time) | yes | Delegation end
TenancyService | approveRoleAuthorityDelegation | response | reason | string |  | Reason
TenancyService | approveRoleAuthorityDelegation | response | delegationType | enum (leave, travel, vacancy, eventOperations) |  | Why temporary authority is granted
TenancyService | approveRoleAuthorityDelegation | response | requiredRole | string |  | Required role
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveRoleAuthorityDelegation | response | requestKind | string |  | What the authority limit covers, e.g.
TenancyService | approveRoleAuthorityDelegation | response | authorityPercentage | number |  | Percentage limit where the authority is a percentage, e.g.
TenancyService | approveRoleAuthorityDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | approveShiftOpen | request | reason | string | yes | (min length 3; max length 300)
OrderService | approveShiftOpen | request | supervisorStepUp | object |  | The supervisor approving, signing on this device (ADAM CR-200).
OrderService | approveShiftOpen | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | approveShiftOpen | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | approveShiftOpen | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | approveShiftOpen | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | approveShiftOpen | response | workstationId | string (uuid) | yes
OrderService | approveShiftOpen | response | venueId | string (uuid) | yes
OrderService | approveShiftOpen | response | scopePath | string | yes
OrderService | approveShiftOpen | response | principalId | string (uuid) | yes | Who opened it.
OrderService | approveShiftOpen | response | principalDisplayName | string
OrderService | approveShiftOpen | response | incidents | array of object |  | BL-097.
OrderService | approveShiftOpen | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | approveShiftOpen | response | incidents[].at | string (date-time)
OrderService | approveShiftOpen | response | incidents[].principalId | string (uuid)
OrderService | approveShiftOpen | response | incidents[].note | string |  | (nullable)
OrderService | approveShiftOpen | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | approveShiftOpen | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | approveShiftOpen | response | depositBoxCode | string |  | (nullable)
OrderService | approveShiftOpen | response | bagNumber | string |  | (nullable)
OrderService | approveShiftOpen | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | approveShiftOpen | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | approveShiftOpen | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | approveShiftOpen | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | approveShiftOpen | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | approveShiftOpen | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | approveShiftOpen | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | approveShiftOpen | response | openedAt | string (date-time) | yes
OrderService | approveShiftOpen | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | approveShiftOpen | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | approveShiftOpen | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | approveShiftOpen | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | approveShiftOpen | response | closedAt | string (date-time) |  | (nullable)
OrderService | approveShiftOpen | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | approveShiftOpen | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | approveShiftOpen | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | approveShiftOpen | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | approveShiftOpen | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | approveShiftOpen | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | approveShiftOpen | response | approvals | array of object
OrderService | approveShiftOpen | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | approveShiftOpen | response | approvals[].principalId | string (uuid) | yes
OrderService | approveShiftOpen | response | approvals[].at | string (date-time) | yes
OrderService | approveShiftOpen | response | approvals[].reason | string
OrderService | approveShiftOpen | param (path) | shiftId | string (uuid) | yes
OrderService | approveShiftOpen | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | askReportingQuestion | request | question | string | yes | (min length 3; max length 1000)
ReportingService | askReportingQuestion | request | conversationId | string |  | Continue a prior exchange for follow-up questions.
ReportingService | askReportingQuestion | request | venueId | string (uuid) |  | Narrows the answer to one venue.
ReportingService | askReportingQuestion | response | conversationId | string | yes
ReportingService | askReportingQuestion | response | question | string | yes
ReportingService | askReportingQuestion | response | interpretation | string | yes | What the question was understood to mean, in plain language.
ReportingService | askReportingQuestion | response | semanticSpec | object |  | What the model returned instead of SQL (design 2.2 E, 5.7): metric, dimensions, filters, period, comparison, as validated against the semantic model. (nullable)
ReportingService | askReportingQuestion | response | semanticSpec.metric | string | yes | A measure field code in the SemanticModel, or a KpiDefinition.code.
ReportingService | askReportingQuestion | response | semanticSpec.dimensions | array of string |  | Field codes to group by. (max items 5)
ReportingService | askReportingQuestion | response | semanticSpec.filters | array of object
ReportingService | askReportingQuestion | response | semanticSpec.filters[].field | string | yes | A SemanticModel field code.
ReportingService | askReportingQuestion | response | semanticSpec.filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, isNull, …) | yes
ReportingService | askReportingQuestion | response | semanticSpec.filters[].values | array of object |  | Open on purpose; typed by the field.
ReportingService | askReportingQuestion | response | semanticSpec.period | string | yes | ISO 8601 interval in the venue's time zone, e.g.
ReportingService | askReportingQuestion | response | semanticSpec.comparison | enum (previousPeriod, samePeriodLastYear, target, benchmark) |  | As getKpiValues compareTo. (nullable)
ReportingService | askReportingQuestion | response | semanticSpec.semanticModelVersion | integer |  | The SemanticModel.version the spec was validated and compiled against. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery | object |  | The query the spec compiled to: data source, columns, filters, grouping, and the compiled SQL in compiledSql. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) |  | What a report may be built over.
ReportingService | askReportingQuestion | response | generatedQuery.columns | array of ReportColumn
ReportingService | askReportingQuestion | response | generatedQuery.columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].field | string | yes
ReportingService | askReportingQuestion | response | generatedQuery.columns[].label | string
ReportingService | askReportingQuestion | response | generatedQuery.columns[].aggregation | object |  | (default none)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].sortOrder | integer
ReportingService | askReportingQuestion | response | generatedQuery.columns[].sortDirection | enum (asc, desc)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].format | string |  | (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | askReportingQuestion | response | generatedQuery.filters | array of ReportFilter
ReportingService | askReportingQuestion | response | generatedQuery.filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery.filters[].field | string | yes
ReportingService | askReportingQuestion | response | generatedQuery.filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | askReportingQuestion | response | generatedQuery.filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | askReportingQuestion | response | generatedQuery.filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | askReportingQuestion | response | generatedQuery.filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | askReportingQuestion | response | generatedQuery.groupBy | array of string
ReportingService | askReportingQuestion | response | generatedQuery.compiledSql | string |  | The SQL the semantic spec compiled to, exactly as run on the analytical replica (29 September, design 5.7). (nullable)
ReportingService | askReportingQuestion | response | result | object | yes | Null when the question is outside the semantic model. (nullable)
ReportingService | askReportingQuestion | response | result.executionId | string | yes
ReportingService | askReportingQuestion | response | result.columns | array of object | yes
ReportingService | askReportingQuestion | response | result.columns[].key | string
ReportingService | askReportingQuestion | response | result.columns[].label | string
ReportingService | askReportingQuestion | response | result.columns[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …)
ReportingService | askReportingQuestion | response | result.rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | askReportingQuestion | response | result.totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | askReportingQuestion | response | result.rowCount | integer
ReportingService | askReportingQuestion | response | result.nextCursor | string |  | (nullable)
ReportingService | askReportingQuestion | response | result.generatedAt | string (date-time)
ReportingService | askReportingQuestion | response | result.dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | askReportingQuestion | response | dataAsOf | string (date-time) |  | Replica position the answer was read at, the result's dataAsOf, stated beside the answer so a figure that moved is not argued about. (nullable)
ReportingService | askReportingQuestion | response | reliability | ReportingAnswerReliability: enum (grounded, partial, conflictingSources, insufficientEvidence) | yes | How far an analytics answer can be relied on (decided 29 September, AI system design 5.6): a category, never a bare percentage.
ReportingService | askReportingQuestion | response | unavailableReason | object |  | Set only when reliability is insufficientEvidence because the question is outside the semantic model ("not available yet"); names which part is not modelled. (nullable)
ReportingService | askReportingQuestion | response | confidence | number |  | Superseded by reliability on 29 September (design 5.6, never a bare percentage for analytics). (min 0; max 1)
ReportingService | askReportingQuestion | response | suggestedFollowUps | array of string
ReportingService | askReportingQuestion | response | modelVersion | string
ReportingService | askReportingQuestion | response | tokensUsed | integer
ReportingService | askReportingQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | attachModifierGroup | request | groupIds | array of string (uuid) | yes
FnbService | attachModifierGroup | response | id | string (uuid) | yes
FnbService | attachModifierGroup | response | productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | attachModifierGroup | response | name | string | yes
FnbService | attachModifierGroup | response | description | string |  | (nullable)
FnbService | attachModifierGroup | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | attachModifierGroup | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | attachModifierGroup | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | attachModifierGroup | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | attachModifierGroup | response | dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | attachModifierGroup | response | remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | attachModifierGroup | response | sortOrder | integer
FnbService | attachModifierGroup | response | modifierGroupIds | array of string (uuid)
FnbService | attachModifierGroup | response | stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | attachModifierGroup | response | menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | attachModifierGroup | response | isStockTracked | boolean |  | True where a recipe exists.
FnbService | attachModifierGroup | response | isAvailable | boolean | yes
FnbService | attachModifierGroup | response | unavailableReason | string |  | (nullable)
FnbService | attachModifierGroup | response | restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | attachModifierGroup | response | preparationMinutes | integer |  | (nullable)
FnbService | attachModifierGroup | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | attachModifierGroup | response | unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | attachModifierGroup | param (path) | menuItemId | string (uuid) | yes
FnbService | attachModifierGroup | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | attachModifierGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | awardBadge | request | id | string (uuid)
MarketingService | awardBadge | request | customerId | string (uuid) | yes
MarketingService | awardBadge | request | badgeId | string (uuid) | yes
MarketingService | awardBadge | request | challengeId | string (uuid) |  | (nullable)
MarketingService | awardBadge | request | sourceType | enum (challenge, purchase, manager) |  | Why the badge was awarded (R8 blocker ORDERS-MONEY-C14): challenge (a completed challenge, challengeId set), purchase (sourceReferenceId the order), manager (awarded by hand, as BO-826 does). (max length 30; nullable)
MarketingService | awardBadge | request | sourceReferenceId | string (uuid) |  | (nullable)
MarketingService | awardBadge | request | awardedAt | string (date-time) | yes
MarketingService | awardBadge | request | expiresAt | string (date-time) |  | (nullable)
MarketingService | awardBadge | request | status | enum (awarded, expired, revoked) | yes | Written by the server, never sent (R8 blocker ORDERS-MONEY-C14). (max length 20; read-only)
MarketingService | awardBadge | response | id | string (uuid)
MarketingService | awardBadge | response | customerId | string (uuid) | yes
MarketingService | awardBadge | response | badgeId | string (uuid) | yes
MarketingService | awardBadge | response | challengeId | string (uuid) |  | (nullable)
MarketingService | awardBadge | response | sourceType | enum (challenge, purchase, manager) |  | Why the badge was awarded (R8 blocker ORDERS-MONEY-C14): challenge (a completed challenge, challengeId set), purchase (sourceReferenceId the order), manager (awarded by hand, as BO-826 does). (max length 30; nullable)
MarketingService | awardBadge | response | sourceReferenceId | string (uuid) |  | (nullable)
MarketingService | awardBadge | response | awardedAt | string (date-time) | yes
MarketingService | awardBadge | response | expiresAt | string (date-time) |  | (nullable)
MarketingService | awardBadge | response | status | enum (awarded, expired, revoked) | yes | Written by the server, never sent (R8 blocker ORDERS-MONEY-C14). (max length 20; read-only)
MarketingService | awardBadge | param (path) | customerId | string (uuid) | yes
MarketingService | awardBadge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | bindCredentialDevice | request | deviceId | string | yes | The app's stable device identifier (max length 128)
AccessService | bindCredentialDevice | request | deviceReference | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | request | appInstallationId | string |  | (max length 128; nullable)
AccessService | bindCredentialDevice | request | os | string |  | (max length 64; nullable)
AccessService | bindCredentialDevice | request | otp | string |  | Verified one-time code, where the policy is otpVerificationRequired and this is a device change (max length 12; nullable)
AccessService | bindCredentialDevice | response | id | string (uuid) | yes
AccessService | bindCredentialDevice | response | subjectId | string (uuid) |  | The guest (pii.subject) (nullable)
AccessService | bindCredentialDevice | response | entitlementId | string (uuid) | yes
AccessService | bindCredentialDevice | response | credentialBindingId | string (uuid) |  | (nullable)
AccessService | bindCredentialDevice | response | deviceId | string | yes | (max length 200)
AccessService | bindCredentialDevice | response | deviceReference | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | response | appInstallationId | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | response | os | string |  | (max length 50; nullable)
AccessService | bindCredentialDevice | response | registeredAt | string (date-time) | yes
AccessService | bindCredentialDevice | response | lastActivatedAt | string (date-time) |  | (nullable)
AccessService | bindCredentialDevice | response | lastKnownVenueId | string (uuid) |  | (nullable)
AccessService | bindCredentialDevice | response | securityStatus | enum (normal, suspicious, blocked) | yes | (default normal)
AccessService | bindCredentialDevice | response | deactivatedAt | string (date-time) |  | Set when the binding is removed (deactivation, or a transfer of the credential) (nullable)
AccessService | bindCredentialDevice | response | scopePath | string | yes | ltree of the owning scope node
AccessService | bindCredentialDevice | response | updatedAt | string (date-time) |  | (read-only)
AccessService | bindCredentialDevice | param (path) | credentialId | string (uuid) | yes | The Virtual Ticket (access.entitlement.id); decided 29 September, writers pass
AccessService | bindCredentialDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | bookVisitPlan | request | baseVersion | integer | yes | The version the guest is looking at. (min 1)
VenueOpsService | bookVisitPlan | request | cartId | string (uuid) |  | The guest's open cart. (nullable)
VenueOpsService | bookVisitPlan | request | itemIds | array of string (uuid) |  | Only these items.
VenueOpsService | bookVisitPlan | request | includeAddOns | boolean |  | Also add the add-ons the guest accepted on the plan (VisitPlanItem.addOnAccepted). (default True)
VenueOpsService | bookVisitPlan | response | planId | string (uuid) | yes
VenueOpsService | bookVisitPlan | response | cartId | string (uuid) | yes
VenueOpsService | bookVisitPlan | response | added | array of object | yes
VenueOpsService | bookVisitPlan | response | added[].itemId | string (uuid)
VenueOpsService | bookVisitPlan | response | added[].cartLineId | string (uuid)
VenueOpsService | bookVisitPlan | response | added[].leaseExpiresAt | string (date-time) |  | (nullable)
VenueOpsService | bookVisitPlan | response | notAdded | array of object | yes | Items that could not be added, with the addCartLine refusal each met.
VenueOpsService | bookVisitPlan | response | notAdded[].itemId | string (uuid)
VenueOpsService | bookVisitPlan | response | notAdded[].reason | string |  | The orders CartProblem code, e.g.
VenueOpsService | bookVisitPlan | response | freeItems | integer |  | Stops that need nothing bought.
VenueOpsService | bookVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | bookVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | buildDeepLink | request | target | LinkTarget | yes
WhiteLabelService | buildDeepLink | request | target.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | buildDeepLink | request | target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | buildDeepLink | request | target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | buildDeepLink | request | target.contentPageId | string (uuid)
WhiteLabelService | buildDeepLink | request | target.productId | string (uuid)
WhiteLabelService | buildDeepLink | request | target.eventId | string (uuid)
WhiteLabelService | buildDeepLink | request | target.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | buildDeepLink | request | target.url | string
WhiteLabelService | buildDeepLink | request | utm | object |  | Campaign tags appended to the link, e.g.
WhiteLabelService | buildDeepLink | response | url | string | yes
WhiteLabelService | buildDeepLink | response | appLink | string |  | The universal or app link that opens the app where installed. (nullable)
FnbService | buildProductionPlan | request | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | buildProductionPlan | request | id | string (uuid) | yes | (read-only)
FnbService | buildProductionPlan | request | outletId | string (uuid)
FnbService | buildProductionPlan | request | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone; a business date, closing at the venue's businessDayCutoff (tenancy VenueSettings, default 00:00; CHG-R6-032).
FnbService | buildProductionPlan | request | status | enum (draft, released, superseded, cancelled) | yes | (read-only)
FnbService | buildProductionPlan | request | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | buildProductionPlan | request | lines | array of object | yes
FnbService | buildProductionPlan | request | lines[].itemId | string (uuid) | yes
FnbService | buildProductionPlan | request | lines[].suggestedQuantity | number |  | (nullable)
FnbService | buildProductionPlan | request | lines[].plannedQuantity | number | yes
FnbService | buildProductionPlan | request | lines[].uom | string
FnbService | buildProductionPlan | request | lines[].stationId | string (uuid) |  | (nullable)
FnbService | buildProductionPlan | request | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | buildProductionPlan | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | buildProductionPlan | response | id | string (uuid) | yes | (read-only)
FnbService | buildProductionPlan | response | outletId | string (uuid)
FnbService | buildProductionPlan | response | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone; a business date, closing at the venue's businessDayCutoff (tenancy VenueSettings, default 00:00; CHG-R6-032).
FnbService | buildProductionPlan | response | status | enum (draft, released, superseded, cancelled) | yes | (read-only)
FnbService | buildProductionPlan | response | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | buildProductionPlan | response | lines | array of object | yes
FnbService | buildProductionPlan | response | lines[].itemId | string (uuid) | yes
FnbService | buildProductionPlan | response | lines[].suggestedQuantity | number |  | (nullable)
FnbService | buildProductionPlan | response | lines[].plannedQuantity | number | yes
FnbService | buildProductionPlan | response | lines[].uom | string
FnbService | buildProductionPlan | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | buildProductionPlan | response | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | buildProductionPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | bulkChangePrices | request | dryRun | boolean |  | (default True)
CatalogueService | bulkChangePrices | request | selection | object | yes | A selection, not a list of ids.
CatalogueService | bulkChangePrices | request | selection.categoryId | string (uuid) |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.productKind | string |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.priceListId | string (uuid) |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | bulkChangePrices | request | adjustment | object | yes
CatalogueService | bulkChangePrices | request | adjustment.mode | enum (percentage, absolute, setTo) | yes
CatalogueService | bulkChangePrices | request | adjustment.value | string | yes | A decimal string, never a float (naming-and-style 5.1). (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | bulkChangePrices | request | adjustment.roundTo | string |  | An increment in the region's currency, as a decimal string (0.5, 5). (pattern ^\d+(\.\d{1,4})?$; nullable)
CatalogueService | bulkChangePrices | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | bulkChangePrices | response | applied | boolean | yes
CatalogueService | bulkChangePrices | response | productsMatched | integer | yes
CatalogueService | bulkChangePrices | response | pricesChanged | integer
CatalogueService | bulkChangePrices | response | skipped | array of object |  | Products the selection matched and the adjustment could not touch — a fixed-price bundle, a partner net rate, a product in an open period.
CatalogueService | bulkChangePrices | response | skipped[].productId | string (uuid)
CatalogueService | bulkChangePrices | response | skipped[].reason | string
CatalogueService | bulkChangePrices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | bulkUpdateProducts | request | previewOnly | boolean |  | (default True)
InventoryService | bulkUpdateProducts | request | selector | object | yes
InventoryService | bulkUpdateProducts | request | changes | object | yes
InventoryService | bulkUpdateProducts | response | matched | integer
InventoryService | bulkUpdateProducts | response | succeeded | integer
InventoryService | bulkUpdateProducts | response | failed | integer
InventoryService | bulkUpdateProducts | response | failures | array of object |  | One entry per product the change was refused for.
InventoryService | bulkUpdateProducts | response | failures[].productId | string (uuid) | yes
InventoryService | bulkUpdateProducts | response | failures[].code | string | yes | The validation rule the product failed, as in Problem.errors[].code.
InventoryService | bulkUpdateProducts | response | failures[].message | string
InventoryService | bulkUpdateProducts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | cancelFnbOrder | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | cancelFnbOrder | request | reason | enum (outletRefused, guestCancelled, itemUnavailable, tooLong, error) | yes
FnbService | cancelFnbOrder | request | note | string |  | (max length 300)
FnbService | cancelFnbOrder | request | recordWaste | boolean |  | Where preparation had started.
FnbService | cancelFnbOrder | response | id | string (uuid) | yes
FnbService | cancelFnbOrder | response | orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | cancelFnbOrder | response | outletId | string (uuid) | yes
FnbService | cancelFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | cancelFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | cancelFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | cancelFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | cancelFnbOrder | response | lines | array of object | yes
FnbService | cancelFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | cancelFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | cancelFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | cancelFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | cancelFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | cancelFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | cancelFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | cancelFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | cancelFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | cancelFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | cancelFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | cancelFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | cancelFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | cancelFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | cancelFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | cancelFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | cancelFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | cancelFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | cancelFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | cancelFnbOrder | response | createdAt | string (date-time) | yes
FnbService | cancelFnbOrder | response | recordedAt | string (date-time)
FnbService | cancelFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | cancelFnbOrder | param (path) | orderId | string (uuid) | yes
FnbService | cancelFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | cancelReservation | param (path) | reservationId | string (uuid) | yes
OrderService | cancelReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | capturePayment | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | capturePayment | response | tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | capturePayment | response | tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | capturePayment | response | tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | capturePayment | response | tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | capturePayment | response | id | string (uuid) | yes
OrderService | capturePayment | response | orderId | string (uuid) | yes
OrderService | capturePayment | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | capturePayment | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | capturePayment | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | capturePayment | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | capturePayment | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | capturePayment | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | capturePayment | response | providerName | string |  | (nullable)
OrderService | capturePayment | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | capturePayment | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | capturePayment | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | capturePayment | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | capturePayment | response | nextAction.kind | enum (redirect, terminal)
OrderService | capturePayment | response | nextAction.url | string (uri) |  | (nullable)
OrderService | capturePayment | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | capturePayment | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | capturePayment | response | recordedAt | string (date-time) | yes
OrderService | capturePayment | response | syncedAt | string (date-time) |  | (nullable)
OrderService | capturePayment | param (path) | paymentId | string (uuid) | yes
OrderService | capturePayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | certifyIntegration | request | decision | enum (certify, reject, revoke) | yes
PlatformService | certifyIntegration | request | certifiedUntil | string (date) |  | (nullable)
PlatformService | certifyIntegration | request | notes | string |  | (nullable)
PlatformService | certifyIntegration | response | id | string (uuid) | yes | (read-only)
PlatformService | certifyIntegration | response | developerId | string (uuid) | yes
PlatformService | certifyIntegration | response | name | string | yes
PlatformService | certifyIntegration | response | category | enum (crm, marketing, accounting, hotel, transport, analytics, accessibility, other) | yes
PlatformService | certifyIntegration | response | description | string
PlatformService | certifyIntegration | response | integrationUrl | string
PlatformService | certifyIntegration | response | requiredScopes | array of string
PlatformService | certifyIntegration | response | status | enum (draft, submitted, inReview, certified, rejected, revoked, delisted) | yes | (read-only)
PlatformService | certifyIntegration | response | certifiedUntil | string (date) |  | Certification expires. (read-only; nullable)
PlatformService | certifyIntegration | response | certifiedAgainstVersion | string |  | (read-only; nullable)
PlatformService | certifyIntegration | response | listingFeeModel | enum (none, flat, revenueShare) |  | (nullable)
PlatformService | certifyIntegration | response | visibility | enum (public, private) |  | private: certified for production access and never shown in the marketplace (17 September minutes, M17-06). (default public)
PlatformService | certifyIntegration | param (path) | listingId | string (uuid) | yes
PlatformService | certifyIntegration | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | changeOwnCredential | request | method | enum (password, pin) | yes | Which credential is being changed (PrincipalCredential.method).
IdentityService | changeOwnCredential | request | currentCredential | string | yes | Compared with the current credentialHash and never stored. (max length 512)
IdentityService | changeOwnCredential | request | newCredential | string | yes | Stored as the new credentialHash (a PHC string, ADR-0071); the replaced hash moves to identity.principal_credential_history. (max length 512)
IdentityService | changeOwnCredential | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | chaseStation | request | ticketId | string (uuid) | yes
FnbService | chaseStation | request | lineId | string (uuid) |  | (nullable)
FnbService | chaseStation | request | recordedAt | string (date-time) | yes | Device time of the chase.
FnbService | chaseStation | param (path) | stationId | string (uuid) | yes
FnbService | chaseStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | checkBookingEligibility | request | productIds | array of string | yes | (min items 1)
CatalogueService | checkBookingEligibility | request | party | array of EligibilityDeclaration | yes | (min items 1)
CatalogueService | checkBookingEligibility | request | party[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
CatalogueService | checkBookingEligibility | request | party[].ageYears | integer |  | (nullable)
CatalogueService | checkBookingEligibility | request | party[].heightBandIndex | integer |  | Which band of the rule's heightBandsCm, counting from 0. (nullable)
CatalogueService | checkBookingEligibility | request | party[].confidentSwimmer | boolean |  | Superseded by the consent record for the product's swim consent question (decided 29 September, rev 3 REV3-26); see ProductEligibilityRule.swimAbility. (nullable)
CatalogueService | checkBookingEligibility | request | party[].guardianSigned | boolean |  | (default False)
CatalogueService | checkBookingEligibility | response | eligible | boolean | yes
CatalogueService | checkBookingEligibility | response | guests | array of object
CatalogueService | checkBookingEligibility | response | guests[].index | integer
CatalogueService | checkBookingEligibility | response | guests[].eligible | boolean
CatalogueService | checkBookingEligibility | response | guests[].reasons | array of enum (tooYoung, tooOld, tooShort, tooTall, needsAdult, needsGuardianSignature, needsSwimmer)
CatalogueService | checkBookingEligibility | response | waiverRequired | boolean
CatalogueService | checkBookingEligibility | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | checkoutCart | request | subjectId | string (uuid) |  | The guest the order is for.
OrderService | checkoutCart | request | chargeCurrency | string |  | The currency the guest selected to pay in (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; nullable)
OrderService | checkoutCart | request | marketingConsents | array of object |  | Marketing opt-ins given at checkout (29 September, M18-15).
OrderService | checkoutCart | request | marketingConsents[].channel | enum (email, sms, whatsapp, push) | yes
OrderService | checkoutCart | request | marketingConsents[].purpose | string | yes | The consent purpose code (marketing ConsentPurpose), for example marketing. (max length 60)
OrderService | checkoutCart | request | marketingConsents[].granted | boolean | yes | True only when the guest ticked it.
OrderService | checkoutCart | request | marketingConsents[].noticeVersion | string |  | The version of the consent notice shown. (max length 40)
OrderService | checkoutCart | request | attendees | array of object |  | The named holder for each cart line that needs one.
OrderService | checkoutCart | request | attendees[].lineId | string (uuid) | yes | A CartLine.id in this cart.
OrderService | checkoutCart | request | attendees[].holderName | string | yes
OrderService | checkoutCart | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | checkoutCart | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | checkoutCart | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | checkoutCart | response | channel | object | yes | Where it came from.
OrderService | checkoutCart | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | checkoutCart | response | venueId | string (uuid) | yes
OrderService | checkoutCart | response | scopePath | string | yes
OrderService | checkoutCart | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | checkoutCart | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | checkoutCart | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | checkoutCart | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | checkoutCart | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | checkoutCart | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | checkoutCart | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | checkoutCart | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | checkoutCart | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | checkoutCart | response | droppedPromotions[].name | string
OrderService | checkoutCart | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | checkoutCart | response | totalPriceVariance | object |  | Sum across lines.
OrderService | checkoutCart | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines | array of OrderLine | yes
OrderService | checkoutCart | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | checkoutCart | response | lines[].variantId | string (uuid) | yes
OrderService | checkoutCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | checkoutCart | response | lines[].performanceId | string (uuid)
OrderService | checkoutCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | checkoutCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | checkoutCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | checkoutCart | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | checkoutCart | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | checkoutCart | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | checkoutCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | checkoutCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | checkoutCart | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | checkoutCart | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | checkoutCart | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | checkoutCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | checkoutCart | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | checkoutCart | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].holderName | string |  | (nullable)
OrderService | checkoutCart | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | checkoutCart | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | checkoutCart | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | checkoutCart | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | checkoutCart | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | checkoutCart | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | checkoutCart | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | checkoutCart | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | checkoutCart | response | lines[].discounts[].id | string (uuid) | yes
OrderService | checkoutCart | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | checkoutCart | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | checkoutCart | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | checkoutCart | response | payments | array of Payment
OrderService | checkoutCart | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | checkoutCart | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | checkoutCart | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | checkoutCart | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | checkoutCart | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | checkoutCart | response | payments[].id | string (uuid) | yes
OrderService | checkoutCart | response | payments[].orderId | string (uuid) | yes
OrderService | checkoutCart | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | checkoutCart | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | checkoutCart | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | checkoutCart | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | checkoutCart | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | checkoutCart | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | checkoutCart | response | payments[].providerName | string |  | (nullable)
OrderService | checkoutCart | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | checkoutCart | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | checkoutCart | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | checkoutCart | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | checkoutCart | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | checkoutCart | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | checkoutCart | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | payments[].recordedAt | string (date-time) | yes
OrderService | checkoutCart | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | principalId | string (uuid)
OrderService | checkoutCart | response | workstationId | string (uuid)
OrderService | checkoutCart | response | shiftId | string (uuid) |  | (nullable)
OrderService | checkoutCart | response | subjectId | string (uuid) |  | (nullable)
OrderService | checkoutCart | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | checkoutCart | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | checkoutCart | response | createdAt | string (date-time) | yes
OrderService | checkoutCart | response | recordedAt | string (date-time) | yes
OrderService | checkoutCart | response | syncedAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | param (path) | cartId | string (uuid) | yes
OrderService | checkoutCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | checkoutCart | param (header) | X-Device-Id | string (uuid) |  | The device a guest app or browser is (ADAM CR-191, option A, decided 21 October 2026; CHG-R9CR-004): the client UUIDv7 the app mints once per installation and keeps, the same value it sends as create…
OrderService | claimCart | request | cartToken | string |  | The anonymous cart's token, as the device that built it holds it (CHG-R8MIG-021).
OrderService | claimCart | response | cart | Cart | yes
OrderService | claimCart | response | cart.id | string (uuid) | yes
OrderService | claimCart | response | cart.anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | claimCart | response | cart.token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | claimCart | response | cart.sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | claimCart | response | cart.workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | claimCart | response | cart.venueId | string (uuid) | yes
OrderService | claimCart | response | cart.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | claimCart | response | cart.subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | claimCart | response | cart.status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | claimCart | response | cart.lines | array of CartLine | yes
OrderService | claimCart | response | cart.lines[].id | string (uuid) | yes
OrderService | claimCart | response | cart.lines[].variantId | string (uuid) | yes
OrderService | claimCart | response | cart.lines[].productName | string |  | (read-only)
OrderService | claimCart | response | cart.lines[].quantity | integer | yes | (min 1)
OrderService | claimCart | response | cart.lines[].performanceId | string (uuid) |  | (nullable)
OrderService | claimCart | response | cart.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | claimCart | response | cart.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | claimCart | response | cart.lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | claimCart | response | cart.lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | claimCart | response | cart.lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | claimCart | response | cart.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | claimCart | response | cart.lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | claimCart | response | cart.lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | claimCart | response | cart.lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | claimCart | response | cart.lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | claimCart | response | cart.lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | claimCart | response | cart.lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | claimCart | response | cart.conflicts | array of CartConflict
OrderService | claimCart | response | cart.conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | claimCart | response | cart.conflicts[].lineIds | array of string (uuid)
OrderService | claimCart | response | cart.conflicts[].message | string
OrderService | claimCart | response | cart.conflicts[].isBlocking | boolean |  | Most are not.
OrderService | claimCart | response | cart.consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | claimCart | response | cart.consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | claimCart | response | cart.consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | claimCart | response | cart.consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | claimCart | response | cart.consentQuestions[].helpText | object |  | (nullable)
OrderService | claimCart | response | cart.consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | claimCart | response | cart.consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | claimCart | response | cart.consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | claimCart | response | cart.consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | claimCart | response | cart.consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | claimCart | response | cart.consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | claimCart | response | cart.consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | claimCart | response | cart.consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | claimCart | response | cart.consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | claimCart | response | cart.subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | claimCart | response | cart.couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | claimCart | response | cart.expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | claimCart | response | cart.extensionsUsed | integer |  | (read-only)
OrderService | claimCart | response | cart.maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | claimCart | response | cart.locale | string
OrderService | claimCart | response | cart.createdAt | string (date-time)
OrderService | claimCart | response | cart.updatedAt | string (date-time)
OrderService | claimCart | response | mergedLineCount | integer
OrderService | claimCart | response | droppedLines | array of object |  | Reported, never silent.
OrderService | claimCart | response | droppedLines[].productName | string
OrderService | claimCart | response | droppedLines[].reason | enum (noCapacity, expired, notSellableOnChannel, duplicate)
OrderService | claimCart | param (path) | cartId | string (uuid) | yes
OrderService | claimCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | claimCustomDomain | request | hostname | string | yes
WhiteLabelService | claimCustomDomain | request | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) | yes
WhiteLabelService | claimCustomDomain | request | verificationMethod | enum (dnsTxt, cname, httpFile) |  | (default dnsTxt)
WhiteLabelService | claimCustomDomain | request | routing | enum (cname, delegatedSubdomain, apex) |  | How the hostname reaches TICVAI (CustomDomain.routing); apex is the only way to claim a bare domain (ADAM CR-105). (default cname)
WhiteLabelService | claimCustomDomain | response | id | string (uuid) | yes
WhiteLabelService | claimCustomDomain | response | tenantId | string (uuid) | yes
WhiteLabelService | claimCustomDomain | response | hostname | string | yes
WhiteLabelService | claimCustomDomain | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) |  | guestApp is stored as guestWeb: the guest app is served on the guestWeb domain and has no domain of its own (r10 question 4; CHG-R10TEN-020).
WhiteLabelService | claimCustomDomain | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | claimCustomDomain | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | claimCustomDomain | response | verificationToken | string |  | (read-only)
WhiteLabelService | claimCustomDomain | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | claimCustomDomain | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | claimCustomDomain | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | claimCustomDomain | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | claimCustomDomain | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | claimCustomDomain | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | claimCustomDomain | response | validationExpiresAt | string (date-time) |  | When the validation window ends (ADAM CR-105, option 1; CHG-R10TEN-011): 7 days after claimCustomDomain or regenerateDomainToken issued the token (a proposed default the client can correct). (read-only; nullable)
WhiteLabelService | claimCustomDomain | response | failureReason | string |  | (nullable)
WhiteLabelService | claimCustomDomain | response | routing | enum (cname, delegatedSubdomain, apex) |  | How the hostname reaches TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; CHG-CSA-043). (default cname)
WhiteLabelService | claimCustomDomain | response | dnsRecords | array of object |  | Every record the tenant must publish, with what is observed now (CHG-CSA-043): the TXT _dnsauth record, the CNAME, and CAA or NS where they apply. (read-only)
WhiteLabelService | claimCustomDomain | response | dnsRecords[].type | enum (TXT, CNAME, CAA, NS) | yes
WhiteLabelService | claimCustomDomain | response | dnsRecords[].name | string | yes
WhiteLabelService | claimCustomDomain | response | dnsRecords[].expectedValue | string | yes
WhiteLabelService | claimCustomDomain | response | dnsRecords[].observedValue | string |  | (nullable)
WhiteLabelService | claimCustomDomain | response | dnsRecords[].status | enum (ok, missing, wrong) | yes
WhiteLabelService | claimCustomDomain | response | revalidation | enum (none, pendingRevalidation, timedOut) |  | The two waits CMS-017 shows beside status (CHG-CSA-043). (default none; read-only)
WhiteLabelService | claimCustomDomain | response | isCnameLost | boolean |  | Takeover warning (CHG-CSA-043). (read-only)
WhiteLabelService | claimCustomDomain | response | isPrimary | boolean |  | The tenant's primary domain for its kind; the others redirect to it (setPrimaryDomain). (read-only)
WhiteLabelService | claimCustomDomain | response | readiness | object |  | Per-domain setup a guest needs (CHG-CSA-043): the UAE Pass redirect URI registered for this hostname, the Apple Pay merchant domain verified, and the app links (Apple app-site association, Android as… (read-only)
WhiteLabelService | claimCustomDomain | response | readiness.uaePassRedirect | enum (ready, pending, notApplicable)
WhiteLabelService | claimCustomDomain | response | readiness.applePayDomain | enum (ready, pending, notApplicable)
WhiteLabelService | claimCustomDomain | response | readiness.appLinks | enum (ready, pending, notApplicable)
WhiteLabelService | claimCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | claimDeviceConsent | request | consentKey | string | yes | (max length 64)
MarketingService | claimDeviceConsent | response | subjectId | string (uuid) | yes
MarketingService | claimDeviceConsent | response | purposes | array of object | yes
MarketingService | claimDeviceConsent | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment) | yes | storedPaymentCredential (a card saved for later, storePaymentToken) and facePassEnrolment (a face enrolled for entry, enrolFacePass) are purposes of their own (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-…
MarketingService | claimDeviceConsent | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | claimDeviceConsent | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | claimDeviceConsent | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | claimDeviceConsent | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | claimDeviceConsent | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | claimDeviceConsent | param (path) | subjectId | string (uuid) | yes
MarketingService | claimDeviceConsent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | claimLocationSession | request | locationCode | string |  | From the QR or NFC tag.
FnbService | claimLocationSession | request | seatReference | object |  | For seated venues where the seat is the address and there is no code to scan.
FnbService | claimLocationSession | request | seatReference.performanceId | string (uuid)
FnbService | claimLocationSession | request | seatReference.seatId | string
FnbService | claimLocationSession | request | partySize | integer |  | (min 1)
FnbService | claimLocationSession | response | id | string (uuid) | yes
FnbService | claimLocationSession | response | locationId | string (uuid) | yes
FnbService | claimLocationSession | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | claimLocationSession | response | label | string | yes
FnbService | claimLocationSession | response | outletId | string (uuid) |  | The outlet serving this location. (nullable)
FnbService | claimLocationSession | response | visitId | string (uuid) |  | The table visit this session orders onto, where the location is a table. (nullable)
FnbService | claimLocationSession | response | joinedExistingVisit | boolean
FnbService | claimLocationSession | response | subjectId | string (uuid)
FnbService | claimLocationSession | response | expiresAt | string (date-time) | yes | Sessions expire so a guest who leaves cannot order to a lounger now occupied by someone else.
FnbService | claimLocationSession | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | claimTicketTransfer | request | claimToken | string | yes | The token carried in the claim link, checked against TicketTransfer.claimToken.
OrderService | claimTicketTransfer | response | id | string (uuid) | yes
OrderService | claimTicketTransfer | response | orderId | string (uuid) | yes
OrderService | claimTicketTransfer | response | ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | claimTicketTransfer | response | fromSubjectId | string (uuid)
OrderService | claimTicketTransfer | response | toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | claimTicketTransfer | response | recipientAddressMasked | string
OrderService | claimTicketTransfer | response | status | enum (offered, claimed, expired, cancelled) | yes
OrderService | claimTicketTransfer | response | claimUrl | string |  | The link the recipient is sent (R8 blocker fix, ORDERS-MONEY-C12). (nullable)
OrderService | claimTicketTransfer | response | claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | claimTicketTransfer | response | offeredAt | string (date-time) | yes
OrderService | claimTicketTransfer | response | claimedAt | string (date-time) |  | (nullable)
OrderService | claimTicketTransfer | response | expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | claimTicketTransfer | param (path) | transferId | string (uuid) | yes
OrderService | claimTicketTransfer | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | clearTable | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | clearTable | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | clearTable | response | id | string (uuid) | yes | (read-only)
FnbService | clearTable | response | label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | clearTable | response | capacity | integer | yes | (min 1)
FnbService | clearTable | response | zone | string |  | (nullable)
FnbService | clearTable | response | position | object
FnbService | clearTable | response | position.x | number
FnbService | clearTable | response | position.y | number
FnbService | clearTable | response | shape | enum (round, square, rectangle, booth, bar)
FnbService | clearTable | response | isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | clearTable | response | codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | clearTable | response | status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | clearTable | response | visitId | string (uuid) |  | (nullable)
FnbService | clearTable | response | covers | integer |  | (nullable)
FnbService | clearTable | response | seatedAt | string (date-time) |  | (nullable)
FnbService | clearTable | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | clearTable | response | billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | clearTable | response | billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | clearTable | response | billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | clearTable | response | billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | clearTable | param (path) | tableId | string (uuid) | yes
FnbService | clearTable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | cloneEvent | request | include | array of enum (schedule, pricing, seatMap, capacityProfile, resourceRequirements, staffPlan, registrationForm, accessRules)
CatalogueService | cloneEvent | request | shiftDatesByDays | integer |  | (nullable)
CatalogueService | cloneEvent | request | newName | string |  | (nullable)
CatalogueService | cloneEvent | request | newCode | string |  | The copy's event code (6 October 2026, CHG-R4-016). (max length 64; nullable)
CatalogueService | cloneEvent | response | eventId | string (uuid)
CatalogueService | cloneEvent | response | code | string |  | The copy's event code, as sent in newCode or as the server chose it (CHG-R4-016).
CatalogueService | cloneEvent | param (path) | eventId | string (uuid) | yes
CatalogueService | cloneEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | cloneProduct | request | code | string | yes
CatalogueService | cloneProduct | request | name | string | yes
CatalogueService | cloneProduct | request | includeVariants | boolean |  | (default True)
CatalogueService | cloneProduct | request | includePrices | boolean |  | (default False)
CatalogueService | cloneProduct | response | id | string (uuid) | yes
CatalogueService | cloneProduct | response | code | string | yes | (max length 64)
CatalogueService | cloneProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | cloneProduct | response | name | string | yes | (max length 200)
CatalogueService | cloneProduct | response | description | string
CatalogueService | cloneProduct | response | nameLocalised | object |  | The product's name in each of the tenant's enabled languages (6 October 2026, CHG-R4-011; the tenant's languages, not the venue's: CHG-R8PRD-009, ADAM CR-213), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | cloneProduct | response | descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | cloneProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | cloneProduct | response | venueId | string (uuid) | yes
CatalogueService | cloneProduct | response | scopePath | string | yes
CatalogueService | cloneProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | cloneProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | cloneProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | cloneProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | cloneProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | cloneProduct | response | validTo | string (date-time) |  | The last moment the product's entitlements are valid; null means the same as onSaleTo (ADAM CR-167 as the lead ruled it, 26 October 2026; CHG-R10OPN-003). (nullable)
CatalogueService | cloneProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | cloneProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | cloneProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | cloneProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | cloneProduct | response | hasVariants | boolean | yes
CatalogueService | cloneProduct | response | variantCount | integer
CatalogueService | cloneProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | cloneProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | cloneProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | cloneProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | cloneProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | cloneProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | cloneProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | cloneProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | cloneProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | cloneProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | cloneProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | cloneProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | cloneProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | cloneProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | cloneProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | cloneProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | cloneProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | cloneProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | cloneProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | cloneProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | cloneProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | cloneProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | cloneProduct | response | media[].url | string (uri) |  | The asset's stable CDN address, for a guest card (ADAM CR-221, option A, decided 25 October 2026; CHG-R10CAT-014): the asset library's public address for the asset, set on guest-facing reads (searchC… (read-only; nullable)
CatalogueService | cloneProduct | response | media[].thumbnailUrl | string (uri) |  | The asset library's thumbnail address for the asset, on the same reads and with the same rule as url (ADAM CR-221). (read-only; nullable)
CatalogueService | cloneProduct | response | media[].altText | object |  | (nullable)
CatalogueService | cloneProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | cloneProduct | response | addOnProductIds | array of string (uuid) |  | The add-ons offered with this product, in display order (accepted 26 October 2026, Chinmay, ADAM CR-252 option A): each a kind: addOn product of the same venue (a coffee break, a working lunch, an AV…
CatalogueService | cloneProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | cloneProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | cloneProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | cloneProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | cloneProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | cloneProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | cloneProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | cloneProduct | response | eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | cloneProduct | response | createdAt | string (date-time) | yes | When the product was created (ADAM CR-204, option A, decided 25 October 2026; CHG-R10CAT-007): catalogue.product.created_at, NOT NULL DEFAULT now(), set by the server and never by a request. (read-only)
CatalogueService | cloneProduct | response | updatedAt | string (date-time) |  | When the product last changed (ADAM CR-204): set by updateProduct and by every product sub-resource PUT and bulk change that versions the product; null until the first change after creation. (read-only; nullable)
CatalogueService | cloneProduct | param (path) | productId | string (uuid) | yes
CatalogueService | cloneProduct | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | cloneResource | request | count | integer |  | Forty strollers in one act. (default 1)
VenueOpsService | cloneResource | request | codePattern | string |  | (nullable)
VenueOpsService | cloneResource | param (path) | resourceId | string (uuid) | yes
VenueOpsService | cloneResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | cloneTicketTemplate | request | name | string | yes | (max length 120)
OrderService | cloneTicketTemplate | request | source | enum (existingTemplate, venueTemplate, productTemplate) | yes | What the template in the path is (decided 29 September, readiness close-out).
OrderService | cloneTicketTemplate | request | venueId | string (uuid) |  | The venue whose template is copied. (nullable)
OrderService | cloneTicketTemplate | request | productId | string (uuid) |  | The product the template issues for. (nullable)
OrderService | cloneTicketTemplate | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
OrderService | cloneTicketTemplate | response | id | string (uuid) | yes
OrderService | cloneTicketTemplate | response | name | string | yes
OrderService | cloneTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | cloneTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | cloneTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | cloneTicketTemplate | response | appliesToProductKinds | array of string
OrderService | cloneTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | cloneTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | cloneTicketTemplate | response | layoutRef | string
OrderService | cloneTicketTemplate | response | localeVariants | object
OrderService | cloneTicketTemplate | response | isActive | boolean | yes
OrderService | cloneTicketTemplate | param (path) | templateId | string (uuid) | yes
OrderService | cloneTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeShift | request | countedCash | array of CountedDenominationLine | yes | The cashier's blind count, one line per denomination counted (decided 29 September, readiness close-out; our build plan). (min items 1)
OrderService | closeShift | request | countedCash[].denominationId | string (uuid) | yes | References platform.denomination (Denomination.id) — face value, kind and counting order live there.
OrderService | closeShift | request | countedCash[].count | integer | yes | How many of this note or coin were counted. (min 0; max 100000)
OrderService | closeShift | request | countedCash[].total | object |  | count times the face value, in the denomination's currency.
OrderService | closeShift | request | countedCash[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | request | countedCash[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | request | countedCash[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | request | nonCashDeclared | array of object |  | Declared totals per non-cash tender, for reconciliation against captured payments.
OrderService | closeShift | request | nonCashDeclared[].tender | string | yes
OrderService | closeShift | request | nonCashDeclared[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | request | nonCashDeclared[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | request | nonCashDeclared[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | request | nonCashDeclared[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | request | notes | string |  | The cashier's note on the count. (max length 1000)
OrderService | closeShift | request | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | Anything the cashier knows went wrong in the shift (DI-803: till error, unrecorded refund, miscount, other). (nullable)
OrderService | closeShift | request | releaseHeldLeases | boolean |  | Return unsold inventory leases held by this workstation (ADR-0013 C103). (default True)
OrderService | closeShift | request | recordedAt | string (date-time) | yes
OrderService | closeShift | request | supervisorStepUp | object |  | The supervisor closing the shift, signing on this device (CHG-RUL-019).
OrderService | closeShift | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
OrderService | closeShift | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
OrderService | closeShift | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | closeShift | response | shift | Shift | yes | approvals and incidents are child rows (26 September, pull audit R099): orders.pos_shift_approval and orders.pos_shift_incident, one row per item, keyed to the shift.
OrderService | closeShift | response | shift.id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeShift | response | shift.workstationId | string (uuid) | yes
OrderService | closeShift | response | shift.venueId | string (uuid) | yes
OrderService | closeShift | response | shift.scopePath | string | yes
OrderService | closeShift | response | shift.principalId | string (uuid) | yes | Who opened it.
OrderService | closeShift | response | shift.principalDisplayName | string
OrderService | closeShift | response | shift.incidents | array of object |  | BL-097.
OrderService | closeShift | response | shift.incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | closeShift | response | shift.incidents[].at | string (date-time)
OrderService | closeShift | response | shift.incidents[].principalId | string (uuid)
OrderService | closeShift | response | shift.incidents[].note | string |  | (nullable)
OrderService | closeShift | response | shift.status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | closeShift | response | shift.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | closeShift | response | shift.depositBoxCode | string |  | (nullable)
OrderService | closeShift | response | shift.bagNumber | string |  | (nullable)
OrderService | closeShift | response | shift.openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | closeShift | response | shift.expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | closeShift | response | shift.countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | closeShift | response | shift.variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | closeShift | response | shift.cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | closeShift | response | shift.varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | closeShift | response | shift.heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | closeShift | response | shift.openedAt | string (date-time) | yes
OrderService | closeShift | response | shift.businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | closeShift | response | shift.recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | closeShift | response | shift.suspendedAt | string (date-time) |  | (nullable)
OrderService | closeShift | response | shift.suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | closeShift | response | shift.closedAt | string (date-time) |  | (nullable)
OrderService | closeShift | response | shift.closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | closeShift | response | shift.recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | closeShift | response | shift.recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | closeShift | response | shift.recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | closeShift | response | shift.countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | closeShift | response | shift.syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | closeShift | response | shift.approvals | array of object
OrderService | closeShift | response | shift.approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | closeShift | response | shift.approvals[].principalId | string (uuid) | yes
OrderService | closeShift | response | shift.approvals[].at | string (date-time) | yes
OrderService | closeShift | response | shift.approvals[].reason | string
OrderService | closeShift | response | expectedCash | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | countedCash | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | variance | object | yes | Counted minus expected.
OrderService | closeShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | requiresAcceptance | boolean | yes | True when the variance exceeds the venue's shiftVarianceThreshold (audit R094).
OrderService | closeShift | response | varianceReasonRequired | boolean |  | True when the variance is non-zero and within the threshold and the body gave no cashierReason: the shift is held in pendingClosure until giveShiftVarianceReason or approveShiftClose records a reason… (default False)
OrderService | closeShift | response | nonCashVariances | array of object
OrderService | closeShift | response | nonCashVariances[].tender | string | yes
OrderService | closeShift | response | nonCashVariances[].declared | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].declared.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].declared.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].declared.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | nonCashVariances[].captured | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].captured.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].captured.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].captured.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | nonCashVariances[].variance | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | param (path) | shiftId | string (uuid) | yes
OrderService | closeShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | closeTableVisit | request | payments | array of object | yes | Empty only at a payFirst outlet with nothing left to pay (CHG-RUL-001). (min items 0)
FnbService | closeTableVisit | request | payments[].subBillId | string |  | The sub-bill this payment settles. (nullable)
FnbService | closeTableVisit | request | payments[].tender | string | yes
FnbService | closeTableVisit | request | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | request | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | request | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | request | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | request | gratuity | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | request | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | request | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | request | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit | TableVisit | yes
FnbService | closeTableVisit | response | visit.id | string (uuid) | yes
FnbService | closeTableVisit | response | visit.tableId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.tableLabel | string
FnbService | closeTableVisit | response | visit.outletId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.covers | integer | yes
FnbService | closeTableVisit | response | visit.status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | closeTableVisit | response | visit.serverPrincipalId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.subjectId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders | array of FnbOrder | yes
FnbService | closeTableVisit | response | visit.orders[].id | string (uuid) | yes
FnbService | closeTableVisit | response | visit.orders[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | closeTableVisit | response | visit.orders[].outletId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | closeTableVisit | response | visit.orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | closeTableVisit | response | visit.orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | closeTableVisit | response | visit.orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | closeTableVisit | response | visit.orders[].lines | array of object | yes
FnbService | closeTableVisit | response | visit.orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | closeTableVisit | response | visit.orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | closeTableVisit | response | visit.orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | closeTableVisit | response | visit.orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].createdAt | string (date-time) | yes
FnbService | closeTableVisit | response | visit.orders[].recordedAt | string (date-time)
FnbService | closeTableVisit | response | visit.orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.mergedFromVisitIds | array of string (uuid)
FnbService | closeTableVisit | response | visit.runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | response | visit.runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | response | visit.runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit.gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | closeTableVisit | response | visit.gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | response | visit.gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | response | visit.gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit.openedAt | string (date-time) | yes
FnbService | closeTableVisit | response | visit.closedAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | closeTableVisit | response | visit.serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | closeTableVisit | response | visit.note | string |  | The server's note on the visit (updateTableVisit). (max length 500; read-only; nullable)
FnbService | closeTableVisit | response | orderIds | array of string | yes
FnbService | closeTableVisit | param (path) | visitId | string (uuid) | yes
FnbService | closeTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | collectShopAndDrop | request | lineIds | array of string |  | Lines collected in full.
RetailService | collectShopAndDrop | request | lines | array of object |  | What is handed over, per line (R8 blocker APPROVALS-TENANCY-C34): each line's collectedQuantity grows by quantity, never past the line's quantity (a larger one is 400).
RetailService | collectShopAndDrop | request | lines[].lineId | string | yes
RetailService | collectShopAndDrop | request | lines[].quantity | integer | yes | (min 1)
RetailService | collectShopAndDrop | request | verifiedBy | enum (entitlementScan, receipt, dropReference, staffOverride)
RetailService | collectShopAndDrop | request | note | string |  | Kept on the drop as collectionNote (ADAM CR-104). (max length 500)
RetailService | collectShopAndDrop | request | recordedAt | string (date-time) | yes | When the device recorded the handover; kept as collectedAt (ADAM CR-104).
RetailService | collectShopAndDrop | response | disposalMethod | enum (donated, destroyed, returnedToStock, heldLonger) |  | What disposeShopAndDrop decided for an uncollected item; null until it is called. (read-only; nullable)
RetailService | collectShopAndDrop | response | disposalNote | string |  | The note sent with that decision; null when none was sent. (max length 300; read-only; nullable)
RetailService | collectShopAndDrop | response | disposalDecidedAt | string (date-time) |  | When the decision was recorded (the server's time). (read-only; nullable)
RetailService | collectShopAndDrop | response | disposalDecidedByPrincipalId | string (uuid) |  | Who authorised it, the caller, from the session ("recorded with who authorised it"). (read-only; nullable)
RetailService | collectShopAndDrop | response | id | string | yes
RetailService | collectShopAndDrop | response | dropReference | string | yes | Short and readable. (max length 32; read-only)
RetailService | collectShopAndDrop | response | saleId | string |  | The till sale. (nullable)
RetailService | collectShopAndDrop | response | orderId | string (uuid) |  | The paid online order that created this collection (audit R236). (nullable)
RetailService | collectShopAndDrop | response | entitlementId | string |  | The ticket that claims these goods. (nullable)
RetailService | collectShopAndDrop | response | subjectId | string (uuid) |  | The guest the goods are for, set at the drop from the sale's subjectId or, for an online order, the order's buyer; null when the sale named no guest (R8 blocker APPROVALS-TENANCY-C34). (nullable)
RetailService | collectShopAndDrop | response | collectionPointId | string (uuid) | yes
RetailService | collectShopAndDrop | response | collectionPointName | string
RetailService | collectShopAndDrop | response | status | enum (awaitingCollection, partiallyCollected, collected, uncollected, disposed) | yes
RetailService | collectShopAndDrop | response | lines | array of object
RetailService | collectShopAndDrop | response | lines[].lineId | string
RetailService | collectShopAndDrop | response | lines[].merchandiseId | string (uuid)
RetailService | collectShopAndDrop | response | lines[].name | string
RetailService | collectShopAndDrop | response | lines[].quantity | integer
RetailService | collectShopAndDrop | response | lines[].collectedQuantity | integer
RetailService | collectShopAndDrop | response | droppedAt | string (date-time)
RetailService | collectShopAndDrop | response | collectBy | string (date-time) | yes
RetailService | collectShopAndDrop | response | collectedAt | string (date-time) |  | (nullable)
RetailService | collectShopAndDrop | response | collectedByPrincipalId | string (uuid) |  | (nullable)
RetailService | collectShopAndDrop | response | verifiedBy | string |  | (nullable)
RetailService | collectShopAndDrop | response | collectionNote | string |  | The note given with the latest collectShopAndDrop (ADAM CR-104, CHG-R10ORD-017); null when none was given. (max length 500; nullable)
RetailService | collectShopAndDrop | param (path) | dropId | string (uuid) | yes
RetailService | collectShopAndDrop | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | commitCatalogueImport | response | id | string (uuid) | yes
CatalogueService | commitCatalogueImport | response | status | enum (parsing, previewReady, committing, committed, failed) | yes
CatalogueService | commitCatalogueImport | response | outcome | enum (parsed, parsedWithFindings, nothingFound, unreadable)
CatalogueService | commitCatalogueImport | response | parsedCount | integer | yes
CatalogueService | commitCatalogueImport | response | createCount | integer
CatalogueService | commitCatalogueImport | response | updateCount | integer
CatalogueService | commitCatalogueImport | response | findings | array of object |  | What an operator sees before committing — missing prices, duplicate codes, unknown categories, codes that do not match the tenant's schema.
CatalogueService | commitCatalogueImport | response | findings[].row | integer
CatalogueService | commitCatalogueImport | response | findings[].severity | enum (error, warning)
CatalogueService | commitCatalogueImport | response | findings[].message | string
CatalogueService | commitCatalogueImport | response | scopePath | string |  | The partition key (ADR-0005).
CatalogueService | commitCatalogueImport | response | jobKind | enum (productImport, environmentTransfer, pricingBulkUpdate, pricingImport) |  | One job table for every catalogue bulk operation (29 September, data model DM3): product import (the original use), environment transfer (ADM-124) and bulk pricing update or import (ADM-080). (default productImport)
CatalogueService | commitCatalogueImport | response | direction | enum (export, import, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | sourceEnvironment | enum (development, sandbox, uat, staging, production, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | targetEnvironment | enum (development, sandbox, uat, staging, production, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | productIds | array of string (uuid)
CatalogueService | commitCatalogueImport | response | components | array of string |  | Transfer components, per ProductImportExportEnvironmentTransferView.components.
CatalogueService | commitCatalogueImport | response | referenceMappings | object |  | [{kind, sourceRef, targetRef}]. (nullable)
CatalogueService | commitCatalogueImport | response | missingReferences | array of string
CatalogueService | commitCatalogueImport | response | fileId | string (uuid) |  | (nullable)
CatalogueService | commitCatalogueImport | response | sourceFormat | string |  | (max length 40; nullable)
CatalogueService | commitCatalogueImport | response | columnMappings | object |  | [{sourceColumn, targetField, suggestedByAi, confirmed}]. (nullable)
CatalogueService | commitCatalogueImport | response | parameters | object |  | Bulk pricing: {selectBy, selectionValues, operation, adjustmentPercent, adjustmentAmount, targetCurrency, effectivePeriodFrom, effectivePeriodTo}. (nullable)
CatalogueService | commitCatalogueImport | response | warningCount | integer |  | (default 0)
CatalogueService | commitCatalogueImport | response | errorCount | integer |  | (default 0)
CatalogueService | commitCatalogueImport | response | changeRequestId | string (uuid) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | response | requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | commitCatalogueImport | response | completedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | param (path) | jobId | string (uuid) | yes
CatalogueService | commitCatalogueImport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | completeUpload | request | title | LocalisedText
VenueOpsService | completeUpload | request | altText | LocalisedText
VenueOpsService | completeUpload | request | tags | array of string
VenueOpsService | completeUpload | request | collectionIds | array of string (uuid)
VenueOpsService | completeUpload | request | rights | MediaRights |  | Licensing terms.
VenueOpsService | completeUpload | request | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | completeUpload | request | rights.licensor | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.licenceReference | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | completeUpload | request | rights.validTo | string (date) |  | (nullable)
VenueOpsService | completeUpload | request | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | completeUpload | request | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | completeUpload | request | rights.attributionText | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | completeUpload | request | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | completeUpload | request | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | completeUpload | request | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | id | string (uuid) | yes
VenueOpsService | completeUpload | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | completeUpload | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | completeUpload | response | filename | string | yes
VenueOpsService | completeUpload | response | contentType | string | yes
VenueOpsService | completeUpload | response | sizeBytes | integer | yes
VenueOpsService | completeUpload | response | title | LocalisedText
VenueOpsService | completeUpload | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | completeUpload | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | completeUpload | response | width | integer |  | (nullable)
VenueOpsService | completeUpload | response | height | integer |  | (nullable)
VenueOpsService | completeUpload | response | hasTransparency | boolean |  | Whether the image has an alpha channel with any pixel not fully opaque, recorded from the file when the upload completes; null for a file that is not an image (ADAM CR-106, option 1; CHG-R10TEN-012). (read-only; nullable)
VenueOpsService | completeUpload | response | durationSeconds | number |  | (nullable)
VenueOpsService | completeUpload | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | completeUpload | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | completeUpload | response | tags | array of string
VenueOpsService | completeUpload | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | completeUpload | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | completeUpload | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | completeUpload | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | completeUpload | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | completeUpload | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | completeUpload | response | rights.licensor | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | completeUpload | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | completeUpload | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | completeUpload | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | completeUpload | response | rights.attributionText | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | completeUpload | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | completeUpload | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | completeUpload | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | isRightsExpired | boolean
VenueOpsService | completeUpload | response | version | integer
VenueOpsService | completeUpload | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | completeUpload | response | createdAt | string (date-time) | yes
VenueOpsService | completeUpload | response | extractedText | string |  | The text pulled out of an uploaded document (R8 blocker ORDERS-MONEY-C19): written by the upload's processing job once text extraction finishes (PDF, Word and plain-text kinds), replaced when the fil… (read-only; nullable)
VenueOpsService | completeUpload | response | releasedByPrincipalId | string (uuid) |  | The reviewer who released the asset from quarantined (R8 blocker ORDERS-MONEY-C24, CHG-R8MIG-022); null if it never was. (read-only; nullable)
VenueOpsService | completeUpload | response | releasedAt | string (date-time) |  | When it was released from quarantined. (read-only; nullable)
VenueOpsService | completeUpload | param (path) | uploadId | string (uuid) | yes
VenueOpsService | completeUpload | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | configureAssistantProfile | request | id | string (uuid) |  | (read-only)
AiService | configureAssistantProfile | request | profileKey | string | yes
AiService | configureAssistantProfile | request | name | string
AiService | configureAssistantProfile | request | audience | enum (staff, guest, support) | yes
AiService | configureAssistantProfile | request | roleIds | array of string (uuid)
AiService | configureAssistantProfile | request | module | object |  | (nullable)
AiService | configureAssistantProfile | request | collectionIds | array of string (uuid) |  | Knowledge collections it retrieves from.
AiService | configureAssistantProfile | request | toolKeys | array of string |  | Registered tools it may propose (an assistant only reads; a change request goes to the configuration assistant, AIC-078).
AiService | configureAssistantProfile | request | modelTask | string |  | The gateway task, e.g.
AiService | configureAssistantProfile | request | guestCapabilityScope | array of string |  | For a guest profile: the same values as AiPolicy.guestCapabilityScope, narrowed.
AiService | configureAssistantProfile | request | locales | array of string
AiService | configureAssistantProfile | request | handoverTarget | string |  | Where "ask a person" goes: a support queue or a staff role. (nullable)
AiService | configureAssistantProfile | request | isActive | boolean |  | (default True)
AiService | configureAssistantProfile | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAssistantProfile | response | id | string (uuid) |  | (read-only)
AiService | configureAssistantProfile | response | profileKey | string | yes
AiService | configureAssistantProfile | response | name | string
AiService | configureAssistantProfile | response | audience | enum (staff, guest, support) | yes
AiService | configureAssistantProfile | response | roleIds | array of string (uuid)
AiService | configureAssistantProfile | response | module | object |  | (nullable)
AiService | configureAssistantProfile | response | collectionIds | array of string (uuid) |  | Knowledge collections it retrieves from.
AiService | configureAssistantProfile | response | toolKeys | array of string |  | Registered tools it may propose (an assistant only reads; a change request goes to the configuration assistant, AIC-078).
AiService | configureAssistantProfile | response | modelTask | string |  | The gateway task, e.g.
AiService | configureAssistantProfile | response | guestCapabilityScope | array of string |  | For a guest profile: the same values as AiPolicy.guestCapabilityScope, narrowed.
AiService | configureAssistantProfile | response | locales | array of string
AiService | configureAssistantProfile | response | handoverTarget | string |  | Where "ask a person" goes: a support queue or a staff role. (nullable)
AiService | configureAssistantProfile | response | isActive | boolean |  | (default True)
AiService | configureAssistantProfile | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAssistantProfile | param (path) | profileKey | string | yes
AiService | configureAssistantProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | configureQueueFeed | request | id | string (uuid) | yes | (read-only)
VenueOpsService | configureQueueFeed | request | queueId | string (uuid) | yes
VenueOpsService | configureQueueFeed | request | adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) | yes | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | request | adaptorName | string |  | Named vendor where adaptor is vendorAdaptor. (nullable)
VenueOpsService | configureQueueFeed | request | credentialsRef | string |  | Key vault reference. (nullable)
VenueOpsService | configureQueueFeed | request | expectedIntervalSeconds | integer |  | Beyond this without a reading, the feed is considered quiet. (default 60)
VenueOpsService | configureQueueFeed | request | isEnabled | boolean | yes
VenueOpsService | configureQueueFeed | request | health | object |  | Whether the feed is currently reporting, computed on read — what listQueueFeeds promises per row. (read-only)
VenueOpsService | configureQueueFeed | request | health.feedId | string (uuid) | yes
VenueOpsService | configureQueueFeed | request | health.adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) |  | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | request | health.isHealthy | boolean | yes | Healthy means the last reading arrived within the feed's expected interval (decided 28 September, audit R106 (1)): lastReadingAt is no older than expectedIntervalSeconds.
VenueOpsService | configureQueueFeed | request | health.isQuiet | boolean | yes | No reading within the expected interval.
VenueOpsService | configureQueueFeed | request | health.lastReadingAt | string (date-time) |  | (nullable)
VenueOpsService | configureQueueFeed | request | health.expectedIntervalSeconds | integer |  | The feed's expectedIntervalSeconds — the interval isQuiet is judged against, returned here so a health panel does not need the feed row as well.
VenueOpsService | configureQueueFeed | request | health.readingsLastHour | integer
VenueOpsService | configureQueueFeed | request | health.discardedLastHour | integer |  | Out-of-order readings rejected in the last hour — rows of queue.reading for this feed with disposition: discardedOutOfOrder.
VenueOpsService | configureQueueFeed | response | id | string (uuid) | yes | (read-only)
VenueOpsService | configureQueueFeed | response | queueId | string (uuid) | yes
VenueOpsService | configureQueueFeed | response | adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) | yes | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | response | adaptorName | string |  | Named vendor where adaptor is vendorAdaptor. (nullable)
VenueOpsService | configureQueueFeed | response | credentialsRef | string |  | Key vault reference. (nullable)
VenueOpsService | configureQueueFeed | response | expectedIntervalSeconds | integer |  | Beyond this without a reading, the feed is considered quiet. (default 60)
VenueOpsService | configureQueueFeed | response | isEnabled | boolean | yes
VenueOpsService | configureQueueFeed | response | health | object |  | Whether the feed is currently reporting, computed on read — what listQueueFeeds promises per row. (read-only)
VenueOpsService | configureQueueFeed | response | health.feedId | string (uuid) | yes
VenueOpsService | configureQueueFeed | response | health.adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) |  | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | response | health.isHealthy | boolean | yes | Healthy means the last reading arrived within the feed's expected interval (decided 28 September, audit R106 (1)): lastReadingAt is no older than expectedIntervalSeconds.
VenueOpsService | configureQueueFeed | response | health.isQuiet | boolean | yes | No reading within the expected interval.
VenueOpsService | configureQueueFeed | response | health.lastReadingAt | string (date-time) |  | (nullable)
VenueOpsService | configureQueueFeed | response | health.expectedIntervalSeconds | integer |  | The feed's expectedIntervalSeconds — the interval isQuiet is judged against, returned here so a health panel does not need the feed row as well.
VenueOpsService | configureQueueFeed | response | health.readingsLastHour | integer
VenueOpsService | configureQueueFeed | response | health.discardedLastHour | integer |  | Out-of-order readings rejected in the last hour — rows of queue.reading for this feed with disposition: discardedOutOfOrder.
VenueOpsService | configureQueueFeed | param (path) | feedId | string (uuid) | yes | Addresses the item this write creates or replaces: its id.
VenueOpsService | configureQueueFeed | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | configureWorkstation | request | cashierInputMode | enum (keyboard, touch, scanner, hybrid) |  | BL-061. (default hybrid)
TenancyService | configureWorkstation | request | guestDisplayContent | array of enum (lineItems, total, loyaltyBalance, promotions, branding, upsell, queuePosition) |  | What the guest-facing screen shows while a sale is in progress. (default ['lineItems'])
TenancyService | configureWorkstation | request | loadedMediaStockId | string (uuid) |  | Deprecated: not stored until BL-095 (the media stock record, on the printer device, waits on the BOCA stock answer; ADAM CR-082, CHG-TEN-003). (nullable)
TenancyService | configureWorkstation | request | mediaStockRemaining | integer |  | Deprecated: not stored until BL-095 (the media stock record, on the printer device, waits on the BOCA stock answer; ADAM CR-082, CHG-TEN-003). (read-only; nullable)
TenancyService | configureWorkstation | request | name | string | yes | (max length 200)
TenancyService | configureWorkstation | request | saleBoardId | string (uuid) |  | This till's own layout, overriding its outlet's (DEC-183; CHG-CSP-006). (nullable)
TenancyService | configureWorkstation | request | outletId | string (uuid) |  | The outlet this till stands in (CHG-CSP-006). (nullable)
TenancyService | configureWorkstation | request | cashDrawerLimit | Money |  | This till's drawer limit; null inherits VenueSettings.cashDrawerLimit (DEC-179; CHG-CSP-016). (nullable)
TenancyService | configureWorkstation | request | departmentId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | accessPointId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | devices | array of DeviceBinding
TenancyService | configureWorkstation | request | devices[].deviceId | string (uuid) |  | The registered device (CR-155): the platform.device row's own id.
TenancyService | configureWorkstation | request | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | configureWorkstation | request | devices[].driver | string | yes | Driver identifier.
TenancyService | configureWorkstation | request | devices[].identifier | string |  | Serial
TenancyService | configureWorkstation | request | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | configureWorkstation | request | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | configureWorkstation | request | edgeNodeId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | isActive | boolean |  | (default True)
TenancyService | configureWorkstation | response | id | string (uuid) | yes
TenancyService | configureWorkstation | response | code | string | yes | (max length 64)
TenancyService | configureWorkstation | response | name | string | yes | (max length 200)
TenancyService | configureWorkstation | response | venueId | string (uuid) | yes
TenancyService | configureWorkstation | response | regionId | string (uuid) | yes
TenancyService | configureWorkstation | response | departmentId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | response | outletId | string (uuid) |  | The outlet this till stands in (CHG-CSP-006). (nullable)
TenancyService | configureWorkstation | response | scopePath | string | yes
TenancyService | configureWorkstation | response | saleBoard | object | yes | Determines which front end loads.
TenancyService | configureWorkstation | response | saleBoard.id | string (uuid) | yes
TenancyService | configureWorkstation | response | saleBoard.kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | configureWorkstation | response | saleBoard.name | string
TenancyService | configureWorkstation | response | saleBoardSource | enum (outlet, workstation) |  | Where saleBoard came from (decided 2 October 2026, Chinmay, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006): outlet when the till uses its outlet's layout, workstation when this til… (read-only)
TenancyService | configureWorkstation | response | cashDrawerLimit | Money |  | This till's drawer limit, overriding the venue's (VenueSettings.cashDrawerLimit; DEC-179; CHG-CSP-016). (nullable)
TenancyService | configureWorkstation | response | cashierInputMode | enum (keyboard, touch, scanner, hybrid) |  | BL-061. (default hybrid)
TenancyService | configureWorkstation | response | guestDisplayContent | array of enum (lineItems, total, loyaltyBalance, promotions, branding, upsell, queuePosition) |  | BL-061. (default ['lineItems'])
TenancyService | configureWorkstation | response | accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator. (nullable)
TenancyService | configureWorkstation | response | devices | array of DeviceBinding
TenancyService | configureWorkstation | response | devices[].deviceId | string (uuid) |  | The registered device (CR-155): the platform.device row's own id.
TenancyService | configureWorkstation | response | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | configureWorkstation | response | devices[].driver | string | yes | Driver identifier.
TenancyService | configureWorkstation | response | devices[].identifier | string |  | Serial
TenancyService | configureWorkstation | response | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | configureWorkstation | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
TenancyService | configureWorkstation | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
TenancyService | configureWorkstation | response | timeZone | string | yes
TenancyService | configureWorkstation | response | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | configureWorkstation | response | edgeNodeId | string (uuid) |  | Present when deploymentProfile is venueEdge. (nullable)
TenancyService | configureWorkstation | response | healthScore | integer |  | Board 1 of the client's POS set. (min 0; max 100; read-only; nullable)
TenancyService | configureWorkstation | response | configurationProfileId | string (uuid) |  | Which profile this workstation runs, and at which version. (nullable)
TenancyService | configureWorkstation | response | configurationProfileVersion | integer |  | The version of configurationProfileId this workstation runs, written when a deployment reaches it; null with no profile (R8 blocker APPROVALS-TENANCY-C08, CHG-R8MIG-019). (read-only; nullable)
TenancyService | configureWorkstation | response | catalogueState | CatalogueState |  | The workstation's local catalogue position.
TenancyService | configureWorkstation | response | catalogueState.appliedBundleVersion | string | yes
TenancyService | configureWorkstation | response | catalogueState.appliedAt | string (date-time) | yes
TenancyService | configureWorkstation | response | catalogueState.staleAfter | string (date-time) | yes | Beyond this the terminal refuses to trade.
TenancyService | configureWorkstation | response | catalogueState.isStale | boolean | yes
TenancyService | configureWorkstation | response | catalogueState.pendingBundleVersion | string |  | Published but not yet applied. (nullable)
TenancyService | configureWorkstation | response | offlineCapable | boolean |  | Derived from deploymentProfile.
TenancyService | configureWorkstation | response | isActive | boolean
TenancyService | configureWorkstation | param (path) | workstationId | string (uuid) | yes
TenancyService | configureWorkstation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | containAiIncident | request | actions | array of object | yes | (min items 1)
AiService | containAiIncident | request | actions[].action | enum (pauseCapability, rollbackRelease, revokeException, disableTool) | yes
AiService | containAiIncident | request | actions[].targetRef | string | yes
AiService | containAiIncident | request | note | string |  | (max length 1000; nullable)
AiService | containAiIncident | response | id | string (uuid) |  | (read-only)
AiService | containAiIncident | response | reference | string | yes | (read-only)
AiService | containAiIncident | response | title | string | yes
AiService | containAiIncident | response | kind | enum (governance, operational, both)
AiService | containAiIncident | response | severity | enum (low, medium, high, critical) | yes
AiService | containAiIncident | response | status | enum (open, contained, investigating, remediating, closed) | yes | (read-only)
AiService | containAiIncident | response | capabilityKeys | array of string
AiService | containAiIncident | response | alertIds | array of string (uuid)
AiService | containAiIncident | response | operationalIncidentRef | string |  | The linked operational incident, where both apply (AIC-250). (nullable)
AiService | containAiIncident | response | containment | array of object |  | (read-only)
AiService | containAiIncident | response | containment[].action | string
AiService | containAiIncident | response | containment[].targetRef | string
AiService | containAiIncident | response | containment[].at | string (date-time)
AiService | containAiIncident | response | containment[].byPrincipalId | string (uuid)
AiService | containAiIncident | response | rootCause | string |  | (nullable)
AiService | containAiIncident | response | remediation | string |  | (nullable)
AiService | containAiIncident | response | impact | string |  | The post-incident review's impact (closeAiIncident, CHG-CSA-045). (nullable)
AiService | containAiIncident | response | controlFailure | string |  | (nullable)
AiService | containAiIncident | response | lessonsLearned | string |  | (nullable)
AiService | containAiIncident | response | ownerPrincipalId | string (uuid) |  | (nullable)
AiService | containAiIncident | response | openedAt | string (date-time) |  | (read-only)
AiService | containAiIncident | response | containedAt | string (date-time) |  | (read-only; nullable)
AiService | containAiIncident | response | closedAt | string (date-time) |  | (read-only; nullable)
AiService | containAiIncident | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | containAiIncident | param (path) | incidentId | string (uuid) | yes
AiService | containAiIncident | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | convertInventoryHold | request | orderId | string (uuid) | yes | The paid order the units are sold to.
CatalogueService | convertInventoryHold | request | units | integer |  | Units sold, when fewer than the hold grants (a line reduced before payment). (min 1)
CatalogueService | convertInventoryHold | response | id | string | yes
CatalogueService | convertInventoryHold | response | channelCapacityId | string (uuid) | yes
CatalogueService | convertInventoryHold | response | holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | convertInventoryHold | response | holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | convertInventoryHold | response | holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | convertInventoryHold | response | convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | convertInventoryHold | response | convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | convertInventoryHold | response | parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | convertInventoryHold | response | requestedUnits | integer
CatalogueService | convertInventoryHold | response | channel | object |  | Allocation this lease draws from.
CatalogueService | convertInventoryHold | response | grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | convertInventoryHold | response | consumedUnits | integer | yes
CatalogueService | convertInventoryHold | response | status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | convertInventoryHold | response | acquiredAt | string (date-time) | yes
CatalogueService | convertInventoryHold | response | expiresAt | string (date-time) | yes
CatalogueService | convertInventoryHold | response | releasedAt | string (date-time) |  | (nullable)
CatalogueService | convertInventoryHold | response | forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | convertInventoryHold | response | forceReleaseReason | string |  | (nullable)
CatalogueService | convertInventoryHold | param (path) | inventoryHoldId | string (uuid) | yes
CatalogueService | convertInventoryHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | convertReservation | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | convertReservation | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | convertReservation | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | convertReservation | response | channel | object | yes | Where it came from.
OrderService | convertReservation | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | convertReservation | response | venueId | string (uuid) | yes
OrderService | convertReservation | response | scopePath | string | yes
OrderService | convertReservation | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | convertReservation | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | convertReservation | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | convertReservation | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | convertReservation | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | convertReservation | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | convertReservation | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | convertReservation | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | convertReservation | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | convertReservation | response | droppedPromotions[].name | string
OrderService | convertReservation | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | convertReservation | response | totalPriceVariance | object |  | Sum across lines.
OrderService | convertReservation | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines | array of OrderLine | yes
OrderService | convertReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | convertReservation | response | lines[].variantId | string (uuid) | yes
OrderService | convertReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | convertReservation | response | lines[].performanceId | string (uuid)
OrderService | convertReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | convertReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | convertReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | convertReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | convertReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | convertReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | convertReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | convertReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | convertReservation | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | convertReservation | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | convertReservation | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | convertReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | convertReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | convertReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | convertReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].holderName | string |  | (nullable)
OrderService | convertReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | convertReservation | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | convertReservation | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | convertReservation | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | convertReservation | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | convertReservation | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | convertReservation | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | convertReservation | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | convertReservation | response | lines[].discounts[].id | string (uuid) | yes
OrderService | convertReservation | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | convertReservation | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | convertReservation | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | convertReservation | response | payments | array of Payment
OrderService | convertReservation | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | convertReservation | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | convertReservation | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | convertReservation | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | convertReservation | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | convertReservation | response | payments[].id | string (uuid) | yes
OrderService | convertReservation | response | payments[].orderId | string (uuid) | yes
OrderService | convertReservation | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | convertReservation | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | convertReservation | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | convertReservation | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | convertReservation | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | convertReservation | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | convertReservation | response | payments[].providerName | string |  | (nullable)
OrderService | convertReservation | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | convertReservation | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | convertReservation | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | convertReservation | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | convertReservation | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | convertReservation | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | convertReservation | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | convertReservation | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | convertReservation | response | payments[].recordedAt | string (date-time) | yes
OrderService | convertReservation | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | convertReservation | response | principalId | string (uuid)
OrderService | convertReservation | response | workstationId | string (uuid)
OrderService | convertReservation | response | shiftId | string (uuid) |  | (nullable)
OrderService | convertReservation | response | subjectId | string (uuid) |  | (nullable)
OrderService | convertReservation | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | convertReservation | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | convertReservation | response | createdAt | string (date-time) | yes
OrderService | convertReservation | response | recordedAt | string (date-time) | yes
OrderService | convertReservation | response | syncedAt | string (date-time) |  | (nullable)
OrderService | convertReservation | param (path) | reservationId | string (uuid) | yes
OrderService | convertReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | copyPriceList | request | code | string | yes | (max length 64)
CatalogueService | copyPriceList | request | name | string | yes | (max length 200)
CatalogueService | copyPriceList | request | adjustmentPercent | number |  | Applied to every copied price.
CatalogueService | copyPriceList | request | roundTo | string |  | Round adjusted prices to this increment, e.g. (pattern ^\d+(\.\d{1,4})?$)
CatalogueService | copyPriceList | request | validFrom | string (date-time)
CatalogueService | copyPriceList | request | validTo | string (date-time)
CatalogueService | copyPriceList | response | priceList | PriceList
CatalogueService | copyPriceList | response | priceList.id | string (uuid) | yes
CatalogueService | copyPriceList | response | priceList.code | string | yes
CatalogueService | copyPriceList | response | priceList.name | string | yes
CatalogueService | copyPriceList | response | priceList.venueId | string (uuid) | yes
CatalogueService | copyPriceList | response | priceList.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | copyPriceList | response | priceList.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | copyPriceList | response | priceList.channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | copyPriceList | response | priceList.validFrom | string (date-time) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.validTo | string (date-time) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | copyPriceList | response | priceList.description | string |  | Price list master fields (29 September, data model DM3), set with createPriceList and updatePriceList since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001). (nullable)
CatalogueService | copyPriceList | response | priceList.priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | copyPriceList | response | priceList.status | object |  | (default active)
CatalogueService | copyPriceList | response | priceList.ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.tags | array of string
CatalogueService | copyPriceList | response | priceList.legalEntityId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.brand | string |  | (max length 100; nullable)
CatalogueService | copyPriceList | response | priceList.businessUnit | string |  | (max length 100; nullable)
CatalogueService | copyPriceList | response | priceList.countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | copyPriceList | response | priceList.marketCode | string |  | (max length 40; nullable)
CatalogueService | copyPriceList | response | priceList.scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | copyPriceList | response | priceList.defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.allowOverrides | boolean |  | (default False)
CatalogueService | copyPriceList | response | priceList.allowInheritance | boolean |  | (default True)
CatalogueService | copyPriceList | response | priceList.allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | copyPriceList | response | priceList.allowProductSpecificRates | boolean |  | (default True)
CatalogueService | copyPriceList | response | priceList.clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | copyPriceList | response | copiedPriceCount | integer
CatalogueService | copyPriceList | param (path) | priceListId | string (uuid) | yes
CatalogueService | copyPriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | createAccessPoint | request | code | string | yes | (max length 64)
AccessService | createAccessPoint | request | name | string | yes | (max length 200)
AccessService | createAccessPoint | request | venueId | string (uuid) | yes
AccessService | createAccessPoint | request | direction | Direction: enum (entry, exit, reentry, crossover) | yes
AccessService | createAccessPoint | request | antiPassbackEnabled | boolean |  | (default False)
AccessService | createAccessPoint | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAccessPoint | request | driver | string
AccessService | createAccessPoint | response | id | string (uuid) | yes
AccessService | createAccessPoint | response | code | string | yes
AccessService | createAccessPoint | response | name | string | yes
AccessService | createAccessPoint | response | venueId | string (uuid) | yes
AccessService | createAccessPoint | response | accessAreaId | string (uuid) |  | The zone this access point admits to (R8 blocker FOUNDATION-AI-C12, CHG-R8MIG-004): an access.access_area row whose entityType is zone (named for the table it keys, as every key is). (nullable)
AccessService | createAccessPoint | response | scopePath | string
AccessService | createAccessPoint | response | externalCredentialSources | object |  | BL-108.
AccessService | createAccessPoint | response | scanAnomalyRules | object |  | BL-104.
AccessService | createAccessPoint | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | createAccessPoint | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | createAccessPoint | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | createAccessPoint | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | createAccessPoint | response | temporaryClosure | object |  | What the access point does while its attraction is temporarily closed (decided 2 October 2026, Chinmay, batch 6 set 9, BO-147: "Deny + reopening time + a virtual-queue return window where enabled"; D… (nullable)
AccessService | createAccessPoint | response | temporaryClosure.isClosed | boolean |  | (default False)
AccessService | createAccessPoint | response | temporaryClosure.reason | string |  | Shown to staff; the guest sees "Attraction temporarily closed". (max length 200; nullable)
AccessService | createAccessPoint | response | temporaryClosure.reopensAt | string (date-time) |  | When it is expected to reopen; shown to the guest when known. (nullable)
AccessService | createAccessPoint | response | temporaryClosure.offerVirtualQueueReturn | boolean |  | Offer a virtual-queue return window at the denied scan, where the attraction has a queue. (default False)
AccessService | createAccessPoint | response | temporaryClosure.queueId | string (uuid) |  | The virtual queue the return window is taken in. (nullable)
AccessService | createAccessPoint | response | antiPassbackEnabled | boolean
AccessService | createAccessPoint | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | createAccessPoint | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | createAccessPoint | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | createAccessPoint | response | geofence.latitude | number
AccessService | createAccessPoint | response | geofence.longitude | number
AccessService | createAccessPoint | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | createAccessPoint | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | createAccessPoint | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | createAccessPoint | response | isActive | boolean | yes
AccessService | createAccessPoint | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | createAccessPoint | response | directionEffectiveAt | string (date-time) |  | When a direction change set by setAccessPointDirection takes effect; held pending until then. (read-only; nullable)
AccessService | createAccessPoint | response | directionChangeReason | string |  | Why the gate was last turned round (setAccessPointDirection). (max length 200; read-only; nullable)
AccessService | createAccessPoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | createAdmissionRules | request | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | createAdmissionRules | request | code | string | yes | (max length 64)
AccessService | createAdmissionRules | request | perProductRules | object |  | BL-059.
AccessService | createAdmissionRules | request | name | string | yes | (max length 200)
AccessService | createAdmissionRules | request | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | createAdmissionRules | request | closeMinutesAfter | integer | yes
AccessService | createAdmissionRules | request | maxDurationMinutes | integer |  | (nullable)
AccessService | createAdmissionRules | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAdmissionRules | request | maxReentries | integer |  | (nullable)
AccessService | createAdmissionRules | request | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | createAdmissionRules | request | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | createAdmissionRules | request | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | createAdmissionRules | request | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | createAdmissionRules | request | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | createAdmissionRules | request | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | createAdmissionRules | request | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | createAdmissionRules | request | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | createAdmissionRules | request | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | createAdmissionRules | request | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | createAdmissionRules | request | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | createAdmissionRules | request | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | createAdmissionRules | request | validity.from | string (date)
AccessService | createAdmissionRules | request | validity.to | string (date) |  | Inclusive.
AccessService | createAdmissionRules | request | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | createAdmissionRules | request | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | createAdmissionRules | request | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | createAdmissionRules | request | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | createAdmissionRules | request | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | createAdmissionRules | request | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | createAdmissionRules | request | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | createAdmissionRules | request | crossover.sameDayOnly | boolean |  | (default True)
AccessService | createAdmissionRules | request | crossover.differentDayAccess | boolean |  | (default False)
AccessService | createAdmissionRules | request | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | createAdmissionRules | request | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | request | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | request | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | createAdmissionRules | request | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | createAdmissionRules | request | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | createAdmissionRules | request | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | createAdmissionRules | request | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | createAdmissionRules | request | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | createAdmissionRules | request | scopePath | string |  | The partition key (ADR-0005).
AccessService | createAdmissionRules | response | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | createAdmissionRules | response | code | string | yes | (max length 64)
AccessService | createAdmissionRules | response | perProductRules | object |  | BL-059.
AccessService | createAdmissionRules | response | name | string | yes | (max length 200)
AccessService | createAdmissionRules | response | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | createAdmissionRules | response | closeMinutesAfter | integer | yes
AccessService | createAdmissionRules | response | maxDurationMinutes | integer |  | (nullable)
AccessService | createAdmissionRules | response | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAdmissionRules | response | maxReentries | integer |  | (nullable)
AccessService | createAdmissionRules | response | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | createAdmissionRules | response | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | createAdmissionRules | response | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | createAdmissionRules | response | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | createAdmissionRules | response | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | createAdmissionRules | response | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | createAdmissionRules | response | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | createAdmissionRules | response | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | createAdmissionRules | response | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | createAdmissionRules | response | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | createAdmissionRules | response | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | createAdmissionRules | response | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | createAdmissionRules | response | validity.from | string (date)
AccessService | createAdmissionRules | response | validity.to | string (date) |  | Inclusive.
AccessService | createAdmissionRules | response | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | createAdmissionRules | response | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | createAdmissionRules | response | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | createAdmissionRules | response | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | createAdmissionRules | response | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | createAdmissionRules | response | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | createAdmissionRules | response | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | createAdmissionRules | response | crossover.sameDayOnly | boolean |  | (default True)
AccessService | createAdmissionRules | response | crossover.differentDayAccess | boolean |  | (default False)
AccessService | createAdmissionRules | response | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | createAdmissionRules | response | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | response | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | response | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | createAdmissionRules | response | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | createAdmissionRules | response | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | createAdmissionRules | response | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | createAdmissionRules | response | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | createAdmissionRules | response | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | createAdmissionRules | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | createAdmissionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiConversation | request | module | object | yes | Which part of the platform the conversation is about (8.4.1).
AiService | createAiConversation | request | locale | string |  | 8.4.3.
AiService | createAiConversation | request | profileKey | string |  | The assistant profile to run the conversation under (configureAssistantProfile), e.g.
AiService | createAiConversation | response | id | string (uuid) | yes
AiService | createAiConversation | response | principalId | string (uuid) | yes | The staff member who opened the conversation; null when a guest opened it (subjectId). (nullable)
AiService | createAiConversation | response | subjectId | string (uuid) |  | The guest who opened the conversation (a guest is not a principal); null for staff. (nullable)
AiService | createAiConversation | response | profileKey | string |  | The assistant profile the conversation runs under (configureAssistantProfile), as createAiConversation set it; null for the module's default profile (R8 blocker WHITE-C27). (nullable)
AiService | createAiConversation | response | scopePath | string
AiService | createAiConversation | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
AiService | createAiConversation | response | locale | string
AiService | createAiConversation | response | messageCount | integer
AiService | createAiConversation | response | startedAt | string (date-time) | yes
AiService | createAiConversation | response | lastMessageAt | string (date-time)
AiService | createAiConversation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiGovernancePolicyDraft | request | policyId | string (uuid) |  | An existing policy to draft the next version of. (nullable)
AiService | createAiGovernancePolicyDraft | request | policyKey | string |  | Required for a new policy. (nullable)
AiService | createAiGovernancePolicyDraft | request | name | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | request | kind | enum (action, data, scope, autonomy, approval, environment) |  | (nullable)
AiService | createAiGovernancePolicyDraft | request | capabilityKeys | array of string
AiService | createAiGovernancePolicyDraft | request | rules | array of AiGovernanceRule | yes | (min items 1)
AiService | createAiGovernancePolicyDraft | request | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | createAiGovernancePolicyDraft | request | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | createAiGovernancePolicyDraft | request | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | createAiGovernancePolicyDraft | request | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | createAiGovernancePolicyDraft | request | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | createAiGovernancePolicyDraft | request | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | createAiGovernancePolicyDraft | request | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | createAiGovernancePolicyDraft | request | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | createAiGovernancePolicyDraft | request | changeNote | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | response | id | string (uuid) |  | (read-only)
AiService | createAiGovernancePolicyDraft | response | policyId | string (uuid) | yes
AiService | createAiGovernancePolicyDraft | response | version | integer | yes | (min 1)
AiService | createAiGovernancePolicyDraft | response | status | enum (draft, simulated, published, superseded) | yes
AiService | createAiGovernancePolicyDraft | response | rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | createAiGovernancePolicyDraft | response | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | createAiGovernancePolicyDraft | response | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | createAiGovernancePolicyDraft | response | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | createAiGovernancePolicyDraft | response | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | createAiGovernancePolicyDraft | response | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | createAiGovernancePolicyDraft | response | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | createAiGovernancePolicyDraft | response | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | createAiGovernancePolicyDraft | response | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | createAiGovernancePolicyDraft | response | changeNote | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | response | simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | createAiGovernancePolicyDraft | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | supersededAt | string (date-time) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createAiGovernancePolicyDraft | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createApiClient | request | id | string (uuid) | yes | (read-only)
PlatformService | createApiClient | request | developerId | string (uuid) | yes
PlatformService | createApiClient | request | name | string | yes
PlatformService | createApiClient | request | clientId | string |  | (read-only)
PlatformService | createApiClient | request | environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | createApiClient | request | scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | createApiClient | request | issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | createApiClient | request | certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | createApiClient | request | credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | createApiClient | request | expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | createApiClient | request | allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | createApiClient | request | ipAllowList | array of string |  | 13.1.38.
PlatformService | createApiClient | request | status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | createApiClient | request | lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | createApiClient | request | statusReason | string |  | Why the client was suspended (setApiClientStatus). (max length 500; read-only; nullable)
PlatformService | createApiClient | response | client | ApiClient |  | CF-135a.
PlatformService | createApiClient | response | client.id | string (uuid) | yes | (read-only)
PlatformService | createApiClient | response | client.developerId | string (uuid) | yes
PlatformService | createApiClient | response | client.name | string | yes
PlatformService | createApiClient | response | client.clientId | string |  | (read-only)
PlatformService | createApiClient | response | client.environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | createApiClient | response | client.scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | createApiClient | response | client.issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | createApiClient | response | client.certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | createApiClient | response | client.credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | createApiClient | response | client.expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | createApiClient | response | client.allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | createApiClient | response | client.ipAllowList | array of string |  | 13.1.38.
PlatformService | createApiClient | response | client.status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | createApiClient | response | client.lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | createApiClient | response | client.statusReason | string |  | Why the client was suspended (setApiClientStatus). (max length 500; read-only; nullable)
PlatformService | createApiClient | response | clientSecret | string (password)
PlatformService | createApiClient | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createApprovalDelegation | request | id | string (uuid) |  | (read-only)
TenancyService | createApprovalDelegation | request | delegatorPrincipalId | string (uuid) | yes | A principal id (identity.Principal.id).
TenancyService | createApprovalDelegation | request | delegatePrincipalId | string (uuid) | yes | A principal id, resolved to a name the same way as delegatorPrincipalId.
TenancyService | createApprovalDelegation | request | kinds | array of ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) |  | Absent means everything the delegator may approve.
TenancyService | createApprovalDelegation | request | maxAmount | object |  | A delegate may be given less authority than the delegator, never more.
TenancyService | createApprovalDelegation | request | maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalDelegation | request | maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalDelegation | request | maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalDelegation | request | from | string (date-time) | yes
TenancyService | createApprovalDelegation | request | to | string (date-time) | yes | Required.
TenancyService | createApprovalDelegation | request | reason | string
TenancyService | createApprovalDelegation | request | isActive | boolean |  | (read-only)
TenancyService | createApprovalDelegation | request | scopePath | string |  | The partition key (ADR-0005).
TenancyService | createApprovalDelegation | request | delegationType | string |  | The composite screen's delegationType (planned absence, temporary cover ...), for display and reporting; the engine treats every delegation alike (4 October 2026, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | request | maxPercentage | number |  | A percentage cap beside maxAmount (the composite's authorityPercentage, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | request | requiredRoleId | string (uuid) |  | A role the delegate must hold for the delegation to act (the composite's requiredRole); checked when the delegate decides, refused with 409 at creation where the delegate does not hold it (CHG-FXC-00… (nullable)
TenancyService | createApprovalDelegation | response | id | string (uuid) |  | (read-only)
TenancyService | createApprovalDelegation | response | delegatorPrincipalId | string (uuid) | yes | A principal id (identity.Principal.id).
TenancyService | createApprovalDelegation | response | delegatePrincipalId | string (uuid) | yes | A principal id, resolved to a name the same way as delegatorPrincipalId.
TenancyService | createApprovalDelegation | response | kinds | array of ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) |  | Absent means everything the delegator may approve.
TenancyService | createApprovalDelegation | response | maxAmount | object |  | A delegate may be given less authority than the delegator, never more.
TenancyService | createApprovalDelegation | response | maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalDelegation | response | maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalDelegation | response | maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalDelegation | response | from | string (date-time) | yes
TenancyService | createApprovalDelegation | response | to | string (date-time) | yes | Required.
TenancyService | createApprovalDelegation | response | reason | string
TenancyService | createApprovalDelegation | response | isActive | boolean |  | (read-only)
TenancyService | createApprovalDelegation | response | scopePath | string |  | The partition key (ADR-0005).
TenancyService | createApprovalDelegation | response | delegationType | string |  | The composite screen's delegationType (planned absence, temporary cover ...), for display and reporting; the engine treats every delegation alike (4 October 2026, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | response | maxPercentage | number |  | A percentage cap beside maxAmount (the composite's authorityPercentage, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | response | requiredRoleId | string (uuid) |  | A role the delegate must hold for the delegation to act (the composite's requiredRole); checked when the delegate decides, refused with 409 at creation where the delegate does not hold it (CHG-FXC-00… (nullable)
TenancyService | createApprovalDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createApprovalRequest | request | id | string (uuid) | yes
TenancyService | createApprovalRequest | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | createApprovalRequest | request | subjectContract | string | yes | Which contract owns the thing being approved.
TenancyService | createApprovalRequest | request | subjectType | string | yes
TenancyService | createApprovalRequest | request | subjectId | string | yes | A reference, never a copy.
TenancyService | createApprovalRequest | request | scopePath | string | yes
TenancyService | createApprovalRequest | request | summary | string | yes | What the approver sees in their queue before opening it. (max length 300)
TenancyService | createApprovalRequest | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | createApprovalRequest | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalRequest | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalRequest | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalRequest | request | attributes | object
TenancyService | createApprovalRequest | request | justification | string |  | (max length 1000)
TenancyService | createApprovalRequest | request | isDraft | boolean |  | True saves the request at draft without routing it; submitApprovalRequest sends it later (decided 28 September, audit R129). (default False)
TenancyService | createApprovalRequest | response | id | string | yes
TenancyService | createApprovalRequest | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | createApprovalRequest | response | rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | createApprovalRequest | response | outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | createApprovalRequest | response | allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | createApprovalRequest | response | reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | createApprovalRequest | response | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | createApprovalRequest | response | subjectContract | string
TenancyService | createApprovalRequest | response | subjectType | string
TenancyService | createApprovalRequest | response | subjectId | string
TenancyService | createApprovalRequest | response | scopePath | string
TenancyService | createApprovalRequest | response | summary | string
TenancyService | createApprovalRequest | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | createApprovalRequest | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalRequest | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalRequest | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalRequest | response | attributes | object |  | The attributes the raising contract sent (CreateApprovalRequest.attributes), stored as given (ADAM CR-172, fix round 3; CHG-CRA-005). (read-only; nullable)
TenancyService | createApprovalRequest | response | justification | string |  | (nullable)
TenancyService | createApprovalRequest | response | requestedByPrincipalId | string (uuid) |  | The principal who raised the request, or for whom the raising contract raised it. (nullable)
TenancyService | createApprovalRequest | response | requestedBySubjectId | string (uuid) |  | The guest who raised the request (ADAM CR-101; CHG-R10ID-016), set by the server from the guest session; null for a request a principal raised. (read-only; nullable)
TenancyService | createApprovalRequest | response | matrixVersion | integer
TenancyService | createApprovalRequest | response | mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | createApprovalRequest | response | currentLevel | integer
TenancyService | createApprovalRequest | response | totalLevels | integer
TenancyService | createApprovalRequest | response | approvers | array of object |  | The approver chain, fixed when the request is routed (ADAM CR-102, option 1, accepted 15 October 2026; CHG-R10ID-015). (read-only)
TenancyService | createApprovalRequest | response | approvers[].level | integer | yes | The level of the chain this approver decides at. (min 1)
TenancyService | createApprovalRequest | response | approvers[].principalId | string (uuid) | yes | The approver, a principal of the tenant.
TenancyService | createApprovalRequest | response | approvers[].isDelegate | boolean | yes | True when the approver stands in for another through an ApprovalDelegation in force at routing.
TenancyService | createApprovalRequest | response | pendingApprovers | array of object |  | The rows of approvers at currentLevel who have not decided yet, with their names; derived, not stored (CHG-R10ID-015).
TenancyService | createApprovalRequest | response | pendingApprovers[].principalId | string (uuid)
TenancyService | createApprovalRequest | response | pendingApprovers[].displayName | string
TenancyService | createApprovalRequest | response | pendingApprovers[].isDelegate | boolean
TenancyService | createApprovalRequest | response | decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | createApprovalRequest | response | decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | createApprovalRequest | response | decisions[].level | integer | yes
TenancyService | createApprovalRequest | response | decisions[].principalId | string (uuid) |  | The approver; null when an external workflow system decided (externalApproverRef set). (nullable)
TenancyService | createApprovalRequest | response | decisions[].externalApproverRef | string |  | Who decided in the external provider's system, as it named them (recordExternalApprovalDecision); null for an internal approver (CHG-R8MIG-009). (nullable)
TenancyService | createApprovalRequest | response | decisions[].externalApproverName | string |  | The external approver's display name, where the provider sent one (CHG-R8MIG-009). (max length 200; nullable)
TenancyService | createApprovalRequest | response | decisions[].displayName | string
TenancyService | createApprovalRequest | response | decisions[].isDelegate | boolean
TenancyService | createApprovalRequest | response | decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].decision | enum (approve, reject, return, requestInformation) | yes | return and requestInformation are stored as decisions too, their comment in comment (decideApprovalRequest; CHG-R8MIG-009).
TenancyService | createApprovalRequest | response | decisions[].comment | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].reason | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].usedMfa | boolean
TenancyService | createApprovalRequest | response | decisions[].signatureRef | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].decidedAt | string (date-time) | yes
TenancyService | createApprovalRequest | response | escalations | array of object |  | 11.1.48.
TenancyService | createApprovalRequest | response | escalations[].at | string (date-time) | yes
TenancyService | createApprovalRequest | response | escalations[].reason | string |  | The requester's or approver's reason; for an automatic escalation, the SLA rule that fired. (max length 300)
TenancyService | createApprovalRequest | response | escalations[].fromLevel | integer
TenancyService | createApprovalRequest | response | escalations[].toLevel | integer | yes
TenancyService | createApprovalRequest | response | escalations[].wasAutomatic | boolean | yes
TenancyService | createApprovalRequest | response | escalations[].escalatedByPrincipalId | string (uuid) |  | Who escalated it by hand (escalateApprovalRequest's caller); null for an automatic one. (nullable)
TenancyService | createApprovalRequest | response | escalations[].addedApproverPrincipalId | string (uuid) |  | The approver the escalation added at toLevel; the original approver stays in the chain. (nullable)
TenancyService | createApprovalRequest | response | resubmittedFromId | string |  | (nullable)
TenancyService | createApprovalRequest | response | reopenedFromId | string |  | (nullable)
TenancyService | createApprovalRequest | response | slaDueAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | slaBreached | boolean
TenancyService | createApprovalRequest | response | expiresAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | assignedToPrincipalId | string (uuid) |  | Who claimed or was assigned the request in a shared queue (assignApprovalRequest; DI-723; CHG-CSP-042). (read-only; nullable)
TenancyService | createApprovalRequest | response | assignedToDepartmentId | string (uuid) |  | The department queue it was assigned to, where it went to a department rather than a person (CHG-CSP-042). (read-only; nullable)
TenancyService | createApprovalRequest | response | assignedAt | string (date-time) |  | (read-only; nullable)
TenancyService | createApprovalRequest | response | assignmentNote | string |  | The note assignApprovalRequest was given, kept with the assignment (R8 blocker APPROVALS-TENANCY-C02, CHG-R8MIG-009). (max length 500; read-only; nullable)
TenancyService | createApprovalRequest | response | approvalMatrixId | string (uuid) |  | The matrix routing chose at submit (with matrixVersion), so a decision is checked against the matrix the request was routed by (CHG-R8MIG-009). (read-only; nullable)
TenancyService | createApprovalRequest | response | ruleId | string (uuid) |  | The matrix rule that matched on kind, scope, amount and attributes (CHG-R8MIG-009). (read-only; nullable)
TenancyService | createApprovalRequest | response | cancelReason | string |  | Why the request was cancelled, as cancelApprovalRequest was given it (CHG-R8MIG-009). (max length 500; read-only; nullable)
TenancyService | createApprovalRequest | response | requestedAt | string (date-time) | yes
TenancyService | createApprovalRequest | response | completedAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | createApprovalRequest | response | aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | createApprovalRequest | response | aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | createApprovalRequest | response | aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion.action | enum (escalate, addBackupApprover, none)
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion.reason | string |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | createApprovalRequest | response | aiAssessment.signals[].code | string
TenancyService | createApprovalRequest | response | aiAssessment.signals[].contribution | number
TenancyService | createApprovalRequest | response | aiAssessment.signals[].detail | string |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | createApprovalRequest | response | aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | createApprovalRequest | response | aiAssessment.assessedAt | string (date-time)
TenancyService | createApprovalRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createBanner | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createBanner | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | request | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | request | imageAssetRef | string (uuid) | yes
WhiteLabelService | createBanner | request | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | createBanner | request | linkTarget | LinkTarget
WhiteLabelService | createBanner | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createBanner | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createBanner | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createBanner | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.productId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.eventId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | createBanner | request | linkTarget.url | string
WhiteLabelService | createBanner | request | startsAt | string (date-time) | yes
WhiteLabelService | createBanner | request | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createBanner | request | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | createBanner | request | sortOrder | integer
WhiteLabelService | createBanner | request | isActive | boolean
WhiteLabelService | createBanner | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createBanner | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | response | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | response | imageAssetRef | string (uuid) | yes
WhiteLabelService | createBanner | response | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | createBanner | response | linkTarget | LinkTarget
WhiteLabelService | createBanner | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createBanner | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createBanner | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createBanner | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.productId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.eventId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | createBanner | response | linkTarget.url | string
WhiteLabelService | createBanner | response | startsAt | string (date-time) | yes
WhiteLabelService | createBanner | response | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createBanner | response | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | createBanner | response | sortOrder | integer
WhiteLabelService | createBanner | response | isActive | boolean
WhiteLabelService | createBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createBookingFlowDefinition | request | id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | createBookingFlowDefinition | request | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | createBookingFlowDefinition | request | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | createBookingFlowDefinition | request | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | createBookingFlowDefinition | request | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | createBookingFlowDefinition | request | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | createBookingFlowDefinition | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createBookingFlowDefinition | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | createBookingFlowDefinition | request | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | request | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | createBookingFlowDefinition | request | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | createBookingFlowDefinition | request | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | createBookingFlowDefinition | request | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | createBookingFlowDefinition | request | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | createBookingFlowDefinition | request | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | createBookingFlowDefinition | request | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createBookingFlowDefinition | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | createBookingFlowDefinition | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | createBookingFlowDefinition | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | createBookingFlowDefinition | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | createBookingFlowDefinition | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | createBookingFlowDefinition | response | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | createBookingFlowDefinition | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createBookingFlowDefinition | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | createBookingFlowDefinition | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | createBookingFlowDefinition | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | createBookingFlowDefinition | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | createBookingFlowDefinition | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | createBookingFlowDefinition | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | createBookingFlowDefinition | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | createBookingFlowDefinition | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createBookingFlowDefinition | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | param (path) | venueId | string (uuid) | yes
WhiteLabelService | createBookingFlowDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createBundle | request | code | string | yes | (max length 64)
CatalogueService | createBundle | request | name | string | yes | (max length 200)
CatalogueService | createBundle | request | description | string |  | (max length 1000)
CatalogueService | createBundle | request | venueId | string (uuid) | yes
CatalogueService | createBundle | request | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | createBundle | request | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | request | components | array of BundleComponent | yes | (min items 0)
CatalogueService | createBundle | request | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | request | components[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | createBundle | request | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | createBundle | request | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | createBundle | request | components[].quantity | integer | yes | (min 1)
CatalogueService | createBundle | request | components[].isOptional | boolean |  | (default False)
CatalogueService | createBundle | request | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | createBundle | request | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | createBundle | request | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | createBundle | request | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | createBundle | request | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | createBundle | request | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | createBundle | request | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | request | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | createBundle | request | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | createBundle | request | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | createBundle | request | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | createBundle | request | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | request | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | createBundle | request | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | createBundle | request | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | createBundle | request | allocation | object | yes | Stored as promotions.allocation_split and promotions.allocation_component, the record of the split; promotions.bundle.allocation is a copy derived from them in the same transaction (ADAM CR-110, opti…
CatalogueService | createBundle | request | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | createBundle | request | allocation.components | array of AllocationComponent | yes
CatalogueService | createBundle | request | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | request | allocation.components[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | createBundle | request | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | request | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | createBundle | request | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | createBundle | request | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | createBundle | request | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | createBundle | request | validFrom | string (date-time)
CatalogueService | createBundle | request | validTo | string (date-time)
CatalogueService | createBundle | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | createBundle | request | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | createBundle | request | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | createBundle | request | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | createBundle | request | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | createBundle | request | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | createBundle | response | code | string | yes | (max length 64)
CatalogueService | createBundle | response | name | string | yes | (max length 200)
CatalogueService | createBundle | response | description | string |  | (max length 1000)
CatalogueService | createBundle | response | venueId | string (uuid) | yes
CatalogueService | createBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | createBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | createBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | createBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | createBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | createBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | createBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | createBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | createBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | createBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | createBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | createBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | createBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | createBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | createBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | createBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | createBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | createBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | createBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | createBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | createBundle | response | allocation | object | yes | Stored as promotions.allocation_split and promotions.allocation_component, the record of the split; promotions.bundle.allocation is a copy derived from them in the same transaction (ADAM CR-110, opti…
CatalogueService | createBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | createBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | createBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | createBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | createBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | createBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | createBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | createBundle | response | validFrom | string (date-time)
CatalogueService | createBundle | response | validTo | string (date-time)
CatalogueService | createBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | createBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | createBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | createBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | createBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | createBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | createBundle | response | id | string (uuid) | yes
CatalogueService | createBundle | response | variantId | string (uuid) |  | The catalogue variant a cart line of this bundle names (R8 blocker ORDERS-MONEY-C43, CHG-R8MIG-023): each sold bundle has a catalogue product of kind bundle with one variant, made when the bundle is… (read-only; nullable)
CatalogueService | createBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price: the list_price captured on each promotions.allocation_component when the bundle was created, not the variants' current prices (ADAM CR-110, option…
CatalogueService | createBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | response | savingsPercentage | number
CatalogueService | createBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | createBundle | response | isActive | boolean | yes
CatalogueService | createBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createCampaign | request | name | string | yes | (max length 200)
MarketingService | createCampaign | request | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | createCampaign | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCampaign | request | venueId | string (uuid)
MarketingService | createCampaign | request | segmentId | string (uuid) | yes
MarketingService | createCampaign | request | content | CampaignContent | yes
MarketingService | createCampaign | request | content.templateId | string (uuid) | yes
MarketingService | createCampaign | request | content.subjectOverride | object
MarketingService | createCampaign | request | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | createCampaign | request | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | createCampaign | request | trigger | CampaignTrigger
MarketingService | createCampaign | request | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | createCampaign | request | trigger.delayHours | integer
MarketingService | createCampaign | request | trigger.conditions | array of SegmentCriterion
MarketingService | createCampaign | request | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createCampaign | request | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createCampaign | request | trigger.conditions[].value | object
MarketingService | createCampaign | request | trigger.conditions[].values | array of object
MarketingService | createCampaign | request | scheduledFor | string (date-time)
MarketingService | createCampaign | request | consentPurpose | object |  | (default marketing)
MarketingService | createCampaign | request | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | createCampaign | request | sendWindow.startTime | string
MarketingService | createCampaign | request | sendWindow.endTime | string
MarketingService | createCampaign | request | sendWindow.timeZone | string
MarketingService | createCampaign | request | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | createCampaign | request | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | createCampaign | request | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | createCampaign | request | variants[].id | string (uuid) |  | (read-only)
MarketingService | createCampaign | request | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | createCampaign | request | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | createCampaign | request | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | createCampaign | request | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | createCampaign | request | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | createCampaign | request | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | createCampaign | request | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | createCampaign | request | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | createCampaign | request | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | createCampaign | request | abTest | object |  | How the variants are tested. (nullable)
MarketingService | createCampaign | request | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | createCampaign | request | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | createCampaign | request | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | createCampaign | request | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | createCampaign | request | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | createCampaign | request | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | createCampaign | response | name | string | yes | (max length 200)
MarketingService | createCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | createCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCampaign | response | venueId | string (uuid)
MarketingService | createCampaign | response | segmentId | string (uuid) | yes
MarketingService | createCampaign | response | content | CampaignContent | yes
MarketingService | createCampaign | response | content.templateId | string (uuid) | yes
MarketingService | createCampaign | response | content.subjectOverride | object
MarketingService | createCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | createCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | createCampaign | response | trigger | CampaignTrigger
MarketingService | createCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | createCampaign | response | trigger.delayHours | integer
MarketingService | createCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | createCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createCampaign | response | trigger.conditions[].value | object
MarketingService | createCampaign | response | trigger.conditions[].values | array of object
MarketingService | createCampaign | response | scheduledFor | string (date-time)
MarketingService | createCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | createCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | createCampaign | response | sendWindow.startTime | string
MarketingService | createCampaign | response | sendWindow.endTime | string
MarketingService | createCampaign | response | sendWindow.timeZone | string
MarketingService | createCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | createCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | createCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | createCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | createCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | createCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | createCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | createCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | createCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | createCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | createCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | createCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | createCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | createCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | createCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | createCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | createCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | createCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | createCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | createCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | createCampaign | response | id | string (uuid) | yes
MarketingService | createCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | createCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | createCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | createCampaign | response | isPaused | boolean
MarketingService | createCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | createCampaign | response | createdAt | string (date-time) | yes
MarketingService | createCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | createCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | createCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | createCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCart | request | venueId | string (uuid) | yes
OrderService | createCart | request | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | createCart | request | subjectId | string (uuid) |  | (nullable)
OrderService | createCart | request | locale | string
OrderService | createCart | request | deviceId | string (uuid) |  | The device the anonymous session is bound to (ADAM CR-183, option A; CHG-R9CR-002): a client UUIDv7 the app mints once per installation and keeps. (nullable)
OrderService | createCart | response | id | string (uuid) | yes
OrderService | createCart | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | createCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | createCart | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | createCart | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | createCart | response | venueId | string (uuid) | yes
OrderService | createCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | createCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | createCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | createCart | response | lines | array of CartLine | yes
OrderService | createCart | response | lines[].id | string (uuid) | yes
OrderService | createCart | response | lines[].variantId | string (uuid) | yes
OrderService | createCart | response | lines[].productName | string |  | (read-only)
OrderService | createCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | createCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | createCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | createCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | createCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | createCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createCart | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | createCart | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | createCart | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | createCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | createCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | createCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | createCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | createCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | createCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | createCart | response | conflicts | array of CartConflict
OrderService | createCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | createCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | createCart | response | conflicts[].message | string
OrderService | createCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | createCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | createCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | createCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | createCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | createCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | createCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | createCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | createCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | createCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | createCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | createCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | createCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | createCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | createCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | createCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | createCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | createCart | response | extensionsUsed | integer |  | (read-only)
OrderService | createCart | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | createCart | response | locale | string
OrderService | createCart | response | createdAt | string (date-time)
OrderService | createCart | response | updatedAt | string (date-time)
OrderService | createCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | request | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | request | kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | createCashMovement | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | request | denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | createCashMovement | request | denominations[].id | string (uuid)
OrderService | createCashMovement | request | denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | createCashMovement | request | denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | createCashMovement | request | denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | createCashMovement | request | denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | createCashMovement | request | denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | createCashMovement | request | denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | createCashMovement | request | denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | request | denominations[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | request | denominations[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | request | denominations[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | request | denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | createCashMovement | request | denominations[].countedAt | string (date-time)
OrderService | createCashMovement | request | denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | createCashMovement | request | reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | createCashMovement | request | reason | string |  | (max length 500)
OrderService | createCashMovement | request | recordedAt | string (date-time) | yes
OrderService | createCashMovement | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | response | kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | createCashMovement | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | response | denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | createCashMovement | response | denominations[].id | string (uuid)
OrderService | createCashMovement | response | denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | createCashMovement | response | denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | createCashMovement | response | denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | createCashMovement | response | denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | createCashMovement | response | denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | createCashMovement | response | denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | createCashMovement | response | denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | response | denominations[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | response | denominations[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | response | denominations[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | response | denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | createCashMovement | response | denominations[].countedAt | string (date-time)
OrderService | createCashMovement | response | denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | createCashMovement | response | reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | createCashMovement | response | reason | string |  | (max length 500)
OrderService | createCashMovement | response | recordedAt | string (date-time) | yes
OrderService | createCashMovement | response | shiftId | string (uuid) | yes
OrderService | createCashMovement | response | depositBoxId | string (uuid) |  | The box the cash moved in or out of. (nullable)
OrderService | createCashMovement | response | witnessPrincipalId | string (uuid) |  | The cashier who countersigned a withdrawal. (nullable)
OrderService | createCashMovement | response | withdrawalReason | object |  | (nullable)
OrderService | createCashMovement | response | authorisedByPrincipalId | string (uuid) | yes | The principal who authorised the movement, recorded for audit.
OrderService | createCashMovement | response | sequence | integer | yes | Monotonic within the shift.
OrderService | createCashMovement | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createCashMovement | param (path) | shiftId | string (uuid) | yes
OrderService | createCashMovement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createChallenge | request | id | string (uuid) | yes | (read-only)
MarketingService | createChallenge | request | name | string | yes
MarketingService | createChallenge | request | kind | enum (visit, spend, ride, collection, streak, referral, survey, social, …) | yes | What an entrant does to progress.
MarketingService | createChallenge | request | scope | enum (individual, family, group, team) |  | 22.6.7 and 22.6.8. (default individual)
MarketingService | createChallenge | request | goal | object | yes | What completes it.
MarketingService | createChallenge | request | goal.metric | string
MarketingService | createChallenge | request | goal.target | number
MarketingService | createChallenge | request | goal.withinDays | integer |  | (nullable)
MarketingService | createChallenge | request | eventId | string (uuid) |  | (nullable)
MarketingService | createChallenge | request | rewardKind | enum (badge, loyaltyPoints, walletCredit, voucher, entitlement, none) |  | 22.6.13.
MarketingService | createChallenge | request | rewardValue | integer |  | Points, for rewardKind: loyaltyPoints only. (min 1; nullable)
MarketingService | createChallenge | request | rewardAmount | object |  | The credit, for rewardKind: walletCredit only. (nullable)
MarketingService | createChallenge | request | rewardAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createChallenge | request | rewardAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createChallenge | request | rewardAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createChallenge | request | badgeAssetId | string (uuid) |  | (nullable)
MarketingService | createChallenge | request | startsAt | string (date-time)
MarketingService | createChallenge | request | endsAt | string (date-time) |  | (nullable)
MarketingService | createChallenge | request | status | enum (draft, active, paused, ended, archived) | yes | (read-only)
MarketingService | createChallenge | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createChallenge | response | id | string (uuid) | yes | (read-only)
MarketingService | createChallenge | response | name | string | yes
MarketingService | createChallenge | response | kind | enum (visit, spend, ride, collection, streak, referral, survey, social, …) | yes | What an entrant does to progress.
MarketingService | createChallenge | response | scope | enum (individual, family, group, team) |  | 22.6.7 and 22.6.8. (default individual)
MarketingService | createChallenge | response | goal | object | yes | What completes it.
MarketingService | createChallenge | response | goal.metric | string
MarketingService | createChallenge | response | goal.target | number
MarketingService | createChallenge | response | goal.withinDays | integer |  | (nullable)
MarketingService | createChallenge | response | eventId | string (uuid) |  | (nullable)
MarketingService | createChallenge | response | rewardKind | enum (badge, loyaltyPoints, walletCredit, voucher, entitlement, none) |  | 22.6.13.
MarketingService | createChallenge | response | rewardValue | integer |  | Points, for rewardKind: loyaltyPoints only. (min 1; nullable)
MarketingService | createChallenge | response | rewardAmount | object |  | The credit, for rewardKind: walletCredit only. (nullable)
MarketingService | createChallenge | response | rewardAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createChallenge | response | rewardAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createChallenge | response | rewardAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createChallenge | response | badgeAssetId | string (uuid) |  | (nullable)
MarketingService | createChallenge | response | startsAt | string (date-time)
MarketingService | createChallenge | response | endsAt | string (date-time) |  | (nullable)
MarketingService | createChallenge | response | status | enum (draft, active, paused, ended, archived) | yes | (read-only)
MarketingService | createChallenge | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createChannelProfile | request | channelName | string |  | Channel Name (internal) (max length 120)
CatalogueService | createChannelProfile | request | channelCode | string |  | Channel Code: unique within the tenant, 2-20 upper-case letters, digits or hyphens (decided 29 September, readiness close-out) (pattern ^[A-Z0-9-]{2,20}$)
CatalogueService | createChannelProfile | request | channelType | enum (b2cWeb, b2cMobileApp, pos, mobilePos, flyingPos, kiosk, callCentre, b2bPortal, …) |  | Channel Type (pack p.3-4 Channel Types).
CatalogueService | createChannelProfile | request | internalDescription | string |  | Internal Description
CatalogueService | createChannelProfile | request | customerFacingName | string |  | Customer-Facing Name (max length 120)
CatalogueService | createChannelProfile | request | brand | string |  | Brand ID
CatalogueService | createChannelProfile | request | businessUnit | string |  | Business Unit ID
CatalogueService | createChannelProfile | request | country | string |  | Country: ISO 3166-1 alpha-2 (pattern ^[A-Z]{2}$)
CatalogueService | createChannelProfile | request | market | string |  | Market (a configured market code)
CatalogueService | createChannelProfile | request | currency | string |  | Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | createChannelProfile | request | timeZone | string |  | Time Zone: IANA name, e.g.
CatalogueService | createChannelProfile | request | owner | string |  | Owner (user ID)
CatalogueService | createChannelProfile | request | responsibleDepartment | string |  | Responsible Department
CatalogueService | createChannelProfile | request | venue | string |  | Venue ID: required for the POS types (pack p.6) and when scopeLevel is venue (nullable)
CatalogueService | createChannelProfile | request | workstationGroups | array of string |  | Workstation groups (IDs) that may sell on a POS-type channel (pack p.6)
CatalogueService | createChannelProfile | request | cashierAccess | array of string |  | Cashier access: role IDs allowed to sell on a POS-type channel (pack p.6)
CatalogueService | createChannelProfile | request | webstore | string |  | Webstore ID for a B2C-type channel (pack p.6) (nullable)
CatalogueService | createChannelProfile | request | domainBrand | string |  | Domain/brand: the storefront domain for a B2C-type channel (pack p.6) (nullable)
CatalogueService | createChannelProfile | request | digitalCustomerJourney | string |  | Digital customer journey: the checkout journey template ID for a B2C-type channel (pack p.6) (nullable)
CatalogueService | createChannelProfile | request | partner | string |  | Partner ID for an OTA, reseller or partner channel (pack p.6); the partner record lives in B2B/OTA (nullable)
CatalogueService | createChannelProfile | request | apiConnection | string |  | API connection: the connector ID from ADM-269 for an OTA/API channel (pack p.6); the external platform is named as data on the connector (nullable)
CatalogueService | createChannelProfile | request | commercialOwner | string |  | Commercial Owner (user ID)
CatalogueService | createChannelProfile | request | operationalOwner | string |  | Operational Owner (user ID)
CatalogueService | createChannelProfile | request | technicalOwner | string |  | Technical Owner (user ID)
CatalogueService | createChannelProfile | request | financeOwner | string |  | Finance Owner (user ID)
CatalogueService | createChannelProfile | request | scopeLevel | enum (global, country, region, venue, attraction, event, location, businessUnit) |  | Operational Scope level (pack p.6)
CatalogueService | createChannelProfile | request | scopeId | string |  | ID of the scoped item (country code, region, venue, attraction, event, location or business unit); empty for global (nullable)
CatalogueService | createChannelProfile | request | salesChannel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | createChannelProfile | response | channelName | string |  | Channel Name (internal) (max length 120)
CatalogueService | createChannelProfile | response | channelCode | string |  | Channel Code: unique within the tenant, 2-20 upper-case letters, digits or hyphens (decided 29 September, readiness close-out) (pattern ^[A-Z0-9-]{2,20}$)
CatalogueService | createChannelProfile | response | channelType | enum (b2cWeb, b2cMobileApp, pos, mobilePos, flyingPos, kiosk, callCentre, b2bPortal, …) |  | Channel Type (pack p.3-4 Channel Types).
CatalogueService | createChannelProfile | response | internalDescription | string |  | Internal Description
CatalogueService | createChannelProfile | response | customerFacingName | string |  | Customer-Facing Name (max length 120)
CatalogueService | createChannelProfile | response | tenant | string |  | Tenant
CatalogueService | createChannelProfile | response | brand | string |  | Brand ID
CatalogueService | createChannelProfile | response | businessUnit | string |  | Business Unit ID
CatalogueService | createChannelProfile | response | country | string |  | Country: ISO 3166-1 alpha-2 (pattern ^[A-Z]{2}$)
CatalogueService | createChannelProfile | response | market | string |  | Market (a configured market code)
CatalogueService | createChannelProfile | response | currency | string |  | Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | createChannelProfile | response | timeZone | string |  | Time Zone: IANA name, e.g.
CatalogueService | createChannelProfile | response | owner | string |  | Owner (user ID)
CatalogueService | createChannelProfile | response | responsibleDepartment | string |  | Responsible Department
CatalogueService | createChannelProfile | response | venue | string |  | Venue ID: required for the POS types (pack p.6) and when scopeLevel is venue (nullable)
CatalogueService | createChannelProfile | response | workstationGroups | array of string |  | Workstation groups (IDs) that may sell on a POS-type channel (pack p.6)
CatalogueService | createChannelProfile | response | cashierAccess | array of string |  | Cashier access: role IDs allowed to sell on a POS-type channel (pack p.6)
CatalogueService | createChannelProfile | response | webstore | string |  | Webstore ID for a B2C-type channel (pack p.6) (nullable)
CatalogueService | createChannelProfile | response | domainBrand | string |  | Domain/brand: the storefront domain for a B2C-type channel (pack p.6) (nullable)
CatalogueService | createChannelProfile | response | digitalCustomerJourney | string |  | Digital customer journey: the checkout journey template ID for a B2C-type channel (pack p.6) (nullable)
CatalogueService | createChannelProfile | response | partner | string |  | Partner ID for an OTA, reseller or partner channel (pack p.6); the partner record lives in B2B/OTA (nullable)
CatalogueService | createChannelProfile | response | apiConnection | string |  | API connection: the connector ID from ADM-269 for an OTA/API channel (pack p.6); the external platform is named as data on the connector (nullable)
CatalogueService | createChannelProfile | response | commercialOwner | string |  | Commercial Owner (user ID)
CatalogueService | createChannelProfile | response | operationalOwner | string |  | Operational Owner (user ID)
CatalogueService | createChannelProfile | response | technicalOwner | string |  | Technical Owner (user ID)
CatalogueService | createChannelProfile | response | financeOwner | string |  | Finance Owner (user ID)
CatalogueService | createChannelProfile | response | scopeLevel | enum (global, country, region, venue, attraction, event, location, businessUnit) |  | Operational Scope level (pack p.6)
CatalogueService | createChannelProfile | response | scopeId | string |  | ID of the scoped item (country code, region, venue, attraction, event, location or business unit); empty for global (nullable)
CatalogueService | createChannelProfile | response | salesChannel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | createChannelProfile | response | channelId | string |  | Channel ID, assigned by TICVAI (read-only)
CatalogueService | createChannelProfile | response | status | string |  | Status: draft, configuration, validation, approved, scheduled, active, suspended, disabled or archived (the pack's suggested lifecycle, p.5); a new channel starts in draft (read-only)
CatalogueService | createChannelProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createCollection | request | name | string | yes | (max length 200)
VenueOpsService | createCollection | request | description | string |  | (max length 1000)
VenueOpsService | createCollection | request | venueId | string (uuid)
VenueOpsService | createCollection | request | parentCollectionId | string (uuid)
VenueOpsService | createCollection | response | id | string (uuid) | yes
VenueOpsService | createCollection | response | name | string | yes | Unique per tenant (decided 28 September, audit R108).
VenueOpsService | createCollection | response | description | string |  | (nullable)
VenueOpsService | createCollection | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | response | parentCollectionId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | response | assetCount | integer | yes
VenueOpsService | createCollection | response | coverAssetId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createConsentQuestion | request | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | createConsentQuestion | request | text | object | yes | The question as the guest reads it, per locale.
MarketingService | createConsentQuestion | request | helpText | object |  | (nullable)
MarketingService | createConsentQuestion | request | scope | enum (perPerson, perBooking) |  | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | createConsentQuestion | request | required | boolean |  | Checkout waits until it is answered. (default True)
MarketingService | createConsentQuestion | request | blockingAnswer | enum (yes, no, none) |  | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | createConsentQuestion | response | id | string (uuid) | yes | (read-only)
MarketingService | createConsentQuestion | response | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | createConsentQuestion | response | text | object | yes | The question as the guest reads it, per locale.
MarketingService | createConsentQuestion | response | helpText | object |  | (nullable)
MarketingService | createConsentQuestion | response | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | createConsentQuestion | response | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | createConsentQuestion | response | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | createConsentQuestion | response | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | createConsentQuestion | response | status | enum (active, retired) | yes | (default active)
MarketingService | createConsentQuestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createConsentQuestion | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | createConsentQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentBlock | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentBlock | request | pageId | string (uuid) |  | (nullable)
WhiteLabelService | createContentBlock | request | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | createContentBlock | request | position | integer
WhiteLabelService | createContentBlock | request | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | createContentBlock | request | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | createContentBlock | request | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | createContentBlock | request | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | createContentBlock | request | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | createContentBlock | request | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | createContentBlock | request | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | createContentBlock | request | reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step of publishContentBlock, where the tenant's publish-review policy is on (r8 walk of ticket 27919). (default notRequired; read-only)
WhiteLabelService | createContentBlock | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentBlock | response | pageId | string (uuid) |  | (nullable)
WhiteLabelService | createContentBlock | response | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | createContentBlock | response | position | integer
WhiteLabelService | createContentBlock | response | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | createContentBlock | response | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | createContentBlock | response | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | createContentBlock | response | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | createContentBlock | response | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | createContentBlock | response | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | createContentBlock | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | createContentBlock | response | reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step of publishContentBlock, where the tenant's publish-review policy is on (r8 walk of ticket 27919). (default notRequired; read-only)
WhiteLabelService | createContentBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentPage | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentPage | request | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | createContentPage | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createContentPage | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | createContentPage | request | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | createContentPage | request | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | createContentPage | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createContentPage | request | categoryCode | string |  | (nullable)
WhiteLabelService | createContentPage | request | sortOrder | integer
WhiteLabelService | createContentPage | request | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | createContentPage | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentPage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentPage | response | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | createContentPage | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createContentPage | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | createContentPage | response | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | createContentPage | response | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | createContentPage | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createContentPage | response | categoryCode | string |  | (nullable)
WhiteLabelService | createContentPage | response | sortOrder | integer
WhiteLabelService | createContentPage | response | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | createContentPage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentPage | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | createCouponCampaign | request | code | string | yes | (max length 64)
CatalogueService | createCouponCampaign | request | name | string | yes | (max length 200)
CatalogueService | createCouponCampaign | request | venueId | string (uuid) | yes
CatalogueService | createCouponCampaign | request | discount | Discount | yes
CatalogueService | createCouponCampaign | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createCouponCampaign | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createCouponCampaign | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createCouponCampaign | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createCouponCampaign | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createCouponCampaign | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createCouponCampaign | request | conditions.variantIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.productKinds | array of string
CatalogueService | createCouponCampaign | request | conditions.categoryIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createCouponCampaign | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createCouponCampaign | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createCouponCampaign | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createCouponCampaign | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createCouponCampaign | request | conditions.daysOfWeek | array of integer
CatalogueService | createCouponCampaign | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createCouponCampaign | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createCouponCampaign | request | conditions.performanceIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createCouponCampaign | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createCouponCampaign | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createCouponCampaign | request | isSingleUse | boolean |  | True generates individually redeemable codes. (default True)
CatalogueService | createCouponCampaign | request | maxRedemptionsPerCode | integer |  | (default 1)
CatalogueService | createCouponCampaign | request | validFrom | string (date-time) | yes
CatalogueService | createCouponCampaign | request | validTo | string (date-time)
CatalogueService | createCouponCampaign | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the codes are issued under, as the Coupon & Promo Code Builder names it. (nullable)
CatalogueService | createCouponCampaign | response | code | string | yes | (max length 64)
CatalogueService | createCouponCampaign | response | name | string | yes | (max length 200)
CatalogueService | createCouponCampaign | response | venueId | string (uuid) | yes
CatalogueService | createCouponCampaign | response | discount | Discount | yes
CatalogueService | createCouponCampaign | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createCouponCampaign | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createCouponCampaign | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createCouponCampaign | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createCouponCampaign | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createCouponCampaign | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createCouponCampaign | response | conditions.variantIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.productKinds | array of string
CatalogueService | createCouponCampaign | response | conditions.categoryIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createCouponCampaign | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createCouponCampaign | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createCouponCampaign | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createCouponCampaign | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createCouponCampaign | response | conditions.daysOfWeek | array of integer
CatalogueService | createCouponCampaign | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createCouponCampaign | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createCouponCampaign | response | conditions.performanceIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createCouponCampaign | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createCouponCampaign | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createCouponCampaign | response | isSingleUse | boolean |  | True generates individually redeemable codes. (default True)
CatalogueService | createCouponCampaign | response | maxRedemptionsPerCode | integer |  | (default 1)
CatalogueService | createCouponCampaign | response | validFrom | string (date-time) | yes
CatalogueService | createCouponCampaign | response | validTo | string (date-time)
CatalogueService | createCouponCampaign | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the codes are issued under, as the Coupon & Promo Code Builder names it. (nullable)
CatalogueService | createCouponCampaign | response | id | string (uuid) | yes
CatalogueService | createCouponCampaign | response | generatedCount | integer | yes
CatalogueService | createCouponCampaign | response | redeemedCount | integer | yes
CatalogueService | createCouponCampaign | response | isActive | boolean
CatalogueService | createCouponCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | createCreditType | request | id | string (uuid)
WalletService | createCreditType | request | code | string | yes
WalletService | createCreditType | request | name | string | yes
WalletService | createCreditType | request | category | enum (cash, refund, bonus, promotional, giftCard, membership, loyalty, ride, …)
WalletService | createCreditType | request | monetary | boolean |  | Loyalty points are not money. (default True)
WalletService | createCreditType | request | conversionRate | number |  | (nullable)
WalletService | createCreditType | request | refundable | boolean |  | Promotional credit is not refundable and cash credit is. (default False)
WalletService | createCreditType | request | transferable | boolean |  | (default False)
WalletService | createCreditType | request | expires | boolean |  | (default False)
WalletService | createCreditType | request | validityDays | integer |  | (nullable)
WalletService | createCreditType | request | breakageEligible | boolean |  | (default False)
WalletService | createCreditType | request | ledgerAccountCode | string |  | (nullable)
WalletService | createCreditType | request | priority | integer |  | (default 0)
WalletService | createCreditType | request | scopePath | string
WalletService | createCreditType | request | isActive | boolean |  | (default True)
WalletService | createCreditType | response | id | string (uuid)
WalletService | createCreditType | response | code | string | yes
WalletService | createCreditType | response | name | string | yes
WalletService | createCreditType | response | category | enum (cash, refund, bonus, promotional, giftCard, membership, loyalty, ride, …)
WalletService | createCreditType | response | monetary | boolean |  | Loyalty points are not money. (default True)
WalletService | createCreditType | response | conversionRate | number |  | (nullable)
WalletService | createCreditType | response | refundable | boolean |  | Promotional credit is not refundable and cash credit is. (default False)
WalletService | createCreditType | response | transferable | boolean |  | (default False)
WalletService | createCreditType | response | expires | boolean |  | (default False)
WalletService | createCreditType | response | validityDays | integer |  | (nullable)
WalletService | createCreditType | response | breakageEligible | boolean |  | (default False)
WalletService | createCreditType | response | ledgerAccountCode | string |  | (nullable)
WalletService | createCreditType | response | priority | integer |  | (default 0)
WalletService | createCreditType | response | scopePath | string
WalletService | createCreditType | response | isActive | boolean |  | (default True)
WalletService | createCreditType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createDashboard | request | name | string | yes | (max length 200)
ReportingService | createDashboard | request | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | createDashboard | request | description | string |  | (max length 1000)
ReportingService | createDashboard | request | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | createDashboard | request | isShared | boolean |  | (default False)
ReportingService | createDashboard | request | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | createDashboard | request | tiles[].id | string (uuid) | yes
ReportingService | createDashboard | request | tiles[].title | string
ReportingService | createDashboard | request | tiles[].reportId | string (uuid) | yes
ReportingService | createDashboard | request | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | createDashboard | request | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | createDashboard | request | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | createDashboard | request | tiles[].position | object | yes
ReportingService | createDashboard | request | tiles[].position.row | integer | yes
ReportingService | createDashboard | request | tiles[].position.column | integer | yes
ReportingService | createDashboard | request | tiles[].position.width | integer | yes
ReportingService | createDashboard | request | tiles[].position.height | integer | yes
ReportingService | createDashboard | response | name | string | yes | (max length 200)
ReportingService | createDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | createDashboard | response | description | string |  | (max length 1000)
ReportingService | createDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | createDashboard | response | isShared | boolean |  | (default False)
ReportingService | createDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | createDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | createDashboard | response | tiles[].title | string
ReportingService | createDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | createDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | createDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | createDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | createDashboard | response | tiles[].position | object | yes
ReportingService | createDashboard | response | tiles[].position.row | integer | yes
ReportingService | createDashboard | response | tiles[].position.column | integer | yes
ReportingService | createDashboard | response | tiles[].position.width | integer | yes
ReportingService | createDashboard | response | tiles[].position.height | integer | yes
ReportingService | createDashboard | response | id | string (uuid) | yes
ReportingService | createDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | createDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | createDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | createDashboard | response | createdAt | string (date-time) | yes
ReportingService | createDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createDeliveryLocation | request | venueId | string (uuid) | yes
FnbService | createDeliveryLocation | request | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | createDeliveryLocation | request | label | string | yes | (max length 200)
FnbService | createDeliveryLocation | request | zone | string |  | (nullable)
FnbService | createDeliveryLocation | request | tableId | string (uuid) |  | (nullable)
FnbService | createDeliveryLocation | request | seatId | string |  | (nullable)
FnbService | createDeliveryLocation | request | servingOutletIds | array of string (uuid)
FnbService | createDeliveryLocation | request | walkTimeMinutes | integer |  | (min 0; nullable)
FnbService | createDeliveryLocation | response | id | string (uuid) | yes
FnbService | createDeliveryLocation | response | venueId | string (uuid) | yes
FnbService | createDeliveryLocation | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | createDeliveryLocation | response | label | string | yes | What a runner is told.
FnbService | createDeliveryLocation | response | zone | string |  | (nullable)
FnbService | createDeliveryLocation | response | opensAt | string (time) |  | When a collection point opens, local to the venue (r8 walk of ticket 27820). (nullable)
FnbService | createDeliveryLocation | response | closesAt | string (time) |  | When a collection point closes, local to the venue; retail collectBy defaults to this on the day. (nullable)
FnbService | createDeliveryLocation | response | tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | createDeliveryLocation | response | seatId | string |  | Set where the seat is the address. (nullable)
FnbService | createDeliveryLocation | response | servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | createDeliveryLocation | response | isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | createDeliveryLocation | response | unserviceableReason | string |  | (nullable)
FnbService | createDeliveryLocation | response | walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | createDeliveryLocation | response | codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | createDeliveryLocation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createDeviceFirmware | request | id | string (uuid) |  | (read-only)
TenancyService | createDeviceFirmware | request | deviceKind | string | yes
TenancyService | createDeviceFirmware | request | version | string | yes | The release's version as its vendor names it, sent on create (ADAM CR-285 (3), 28 October 2026; CHG-R11TEN-006).
TenancyService | createDeviceFirmware | request | vendor | string |  | Who built the image, as the device's driver names its maker. (nullable)
TenancyService | createDeviceFirmware | request | checksumAlgorithm | enum (sha256, sha512) |  | (default sha256)
TenancyService | createDeviceFirmware | request | releaseNotes | string |  | (nullable)
TenancyService | createDeviceFirmware | request | artefactAssetId | string (uuid) |  | The uploaded image (an Assets media asset), stored unchecked (ADAM CR-285 (1), 28 October 2026; CHG-R11TEN-006). (nullable)
TenancyService | createDeviceFirmware | request | checksum | string |  | (nullable)
TenancyService | createDeviceFirmware | request | minimumPreviousVersion | string |  | Some updates cannot be applied from any starting point. (nullable)
TenancyService | createDeviceFirmware | request | releasedAt | string (date-time) |  | Set when setDeviceFirmwareStatus first makes the release released. (read-only; nullable)
TenancyService | createDeviceFirmware | request | installedCount | integer |  | (read-only)
TenancyService | createDeviceFirmware | request | status | enum (draft, released, deprecated, withdrawn) |  | (default draft; read-only)
TenancyService | createDeviceFirmware | request | statusReason | string |  | The reason given when the release was deprecated or withdrawn. (read-only; nullable)
TenancyService | createDeviceFirmware | request | scopePath | string |  | The tenant the release belongs to. (read-only)
TenancyService | createDeviceFirmware | response | id | string (uuid) |  | (read-only)
TenancyService | createDeviceFirmware | response | deviceKind | string | yes
TenancyService | createDeviceFirmware | response | version | string | yes | The release's version as its vendor names it, sent on create (ADAM CR-285 (3), 28 October 2026; CHG-R11TEN-006).
TenancyService | createDeviceFirmware | response | vendor | string |  | Who built the image, as the device's driver names its maker. (nullable)
TenancyService | createDeviceFirmware | response | checksumAlgorithm | enum (sha256, sha512) |  | (default sha256)
TenancyService | createDeviceFirmware | response | releaseNotes | string |  | (nullable)
TenancyService | createDeviceFirmware | response | artefactAssetId | string (uuid) |  | The uploaded image (an Assets media asset), stored unchecked (ADAM CR-285 (1), 28 October 2026; CHG-R11TEN-006). (nullable)
TenancyService | createDeviceFirmware | response | checksum | string |  | (nullable)
TenancyService | createDeviceFirmware | response | minimumPreviousVersion | string |  | Some updates cannot be applied from any starting point. (nullable)
TenancyService | createDeviceFirmware | response | releasedAt | string (date-time) |  | Set when setDeviceFirmwareStatus first makes the release released. (read-only; nullable)
TenancyService | createDeviceFirmware | response | installedCount | integer |  | (read-only)
TenancyService | createDeviceFirmware | response | status | enum (draft, released, deprecated, withdrawn) |  | (default draft; read-only)
TenancyService | createDeviceFirmware | response | statusReason | string |  | The reason given when the release was deprecated or withdrawn. (read-only; nullable)
TenancyService | createDeviceFirmware | response | scopePath | string |  | The tenant the release belongs to. (read-only)
TenancyService | createDeviceFirmware | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createEntitlementTemplate | request | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | createEntitlementTemplate | request | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | createEntitlementTemplate | request | code | string | yes | (max length 64)
CatalogueService | createEntitlementTemplate | request | name | string | yes | (max length 200)
CatalogueService | createEntitlementTemplate | request | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | createEntitlementTemplate | request | validFromOffsetDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | validForDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | createEntitlementTemplate | request | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | createEntitlementTemplate | request | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createEntitlementTemplate | request | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createEntitlementTemplate | request | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createEntitlementTemplate | request | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createEntitlementTemplate | request | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].from | string
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].to | string
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].daysOfWeek | array of string
CatalogueService | createEntitlementTemplate | request | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | createEntitlementTemplate | request | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | createEntitlementTemplate | request | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | createEntitlementTemplate | request | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | createEntitlementTemplate | request | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | createEntitlementTemplate | request | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | createEntitlementTemplate | request | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | createEntitlementTemplate | request | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | createEntitlementTemplate | request | reentryAllowed | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | createEntitlementTemplate | request | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | createEntitlementTemplate | request | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createEntitlementTemplate | request | isTransferable | boolean |  | (default True)
CatalogueService | createEntitlementTemplate | request | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | createEntitlementTemplate | request | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | createEntitlementTemplate | request | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | createEntitlementTemplate | request | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | createEntitlementTemplate | request | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | createEntitlementTemplate | request | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | createEntitlementTemplate | request | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | createEntitlementTemplate | request | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | createEntitlementTemplate | request | isActive | boolean
CatalogueService | createEntitlementTemplate | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | createEntitlementTemplate | response | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | createEntitlementTemplate | response | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | createEntitlementTemplate | response | code | string | yes | (max length 64)
CatalogueService | createEntitlementTemplate | response | name | string | yes | (max length 200)
CatalogueService | createEntitlementTemplate | response | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | createEntitlementTemplate | response | validFromOffsetDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | validForDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | createEntitlementTemplate | response | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | createEntitlementTemplate | response | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createEntitlementTemplate | response | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createEntitlementTemplate | response | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createEntitlementTemplate | response | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createEntitlementTemplate | response | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].from | string
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].to | string
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].daysOfWeek | array of string
CatalogueService | createEntitlementTemplate | response | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | createEntitlementTemplate | response | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | createEntitlementTemplate | response | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | createEntitlementTemplate | response | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | createEntitlementTemplate | response | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | createEntitlementTemplate | response | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | createEntitlementTemplate | response | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | createEntitlementTemplate | response | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | createEntitlementTemplate | response | reentryAllowed | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | createEntitlementTemplate | response | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | createEntitlementTemplate | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createEntitlementTemplate | response | isTransferable | boolean |  | (default True)
CatalogueService | createEntitlementTemplate | response | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | createEntitlementTemplate | response | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | createEntitlementTemplate | response | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | createEntitlementTemplate | response | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | createEntitlementTemplate | response | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | createEntitlementTemplate | response | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | createEntitlementTemplate | response | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | createEntitlementTemplate | response | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | createEntitlementTemplate | response | isActive | boolean
CatalogueService | createEntitlementTemplate | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | createEntitlementTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createEvent | request | code | string | yes | Unique per tenant (decided 28 September, audit R108). (max length 64)
CatalogueService | createEvent | request | name | string | yes | (max length 200)
CatalogueService | createEvent | request | venueId | string (uuid) | yes
CatalogueService | createEvent | request | parentEventId | string (uuid)
CatalogueService | createEvent | response | id | string (uuid) | yes
CatalogueService | createEvent | response | code | string | yes
CatalogueService | createEvent | response | name | string | yes
CatalogueService | createEvent | response | venueId | string (uuid) | yes
CatalogueService | createEvent | response | scopePath | string | yes
CatalogueService | createEvent | response | parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | createEvent | response | performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | createEvent | response | isActive | boolean
CatalogueService | createEvent | response | lifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | Where the event is in its lifecycle (4 October 2026, CHG-FXC-003; catalogue.event had nowhere to keep it). (read-only)
CatalogueService | createEvent | response | lifecycleStateChangedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | createEvent | response | scheduledLifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | A move waiting for its effectiveFrom (ADAM CR-109, option 2; CHG-R10CAT-009): written by setEventLifecycleState when effectiveFrom is in the future, applied and cleared by the event lifecycle job in… (read-only; nullable)
CatalogueService | createEvent | response | scheduledLifecycleAt | string (date-time) |  | When the waiting move is applied (the request's effectiveFrom; ADAM CR-109). (read-only; nullable)
CatalogueService | createEvent | response | scheduledLifecycleReason | string |  | The reason given with the waiting move, carried on event.lifecycleChanged when it is applied (ADAM CR-109). (max length 500; read-only; nullable)
CatalogueService | createEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createFnbOrder | request | id | string (uuid) | yes
FnbService | createFnbOrder | request | outletId | string (uuid) | yes
FnbService | createFnbOrder | request | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | createFnbOrder | request | tableVisitId | string (uuid) |  | Required for table service. (nullable)
FnbService | createFnbOrder | request | lines | array of CreateFnbOrderLine | yes | (min items 1)
FnbService | createFnbOrder | request | lines[].id | string (uuid) | yes
FnbService | createFnbOrder | request | lines[].menuItemId | string (uuid) | yes
FnbService | createFnbOrder | request | lines[].quantity | integer | yes | (min 1)
FnbService | createFnbOrder | request | lines[].modifierOptionIds | array of string (uuid)
FnbService | createFnbOrder | request | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createFnbOrder | request | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | createFnbOrder | request | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | createFnbOrder | request | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | createFnbOrder | request | salesOrderId | string (uuid) |  | The orders.sales_order this F&B order fulfils (SD-046, 29 September). (nullable)
FnbService | createFnbOrder | request | recordedAt | string (date-time) | yes
FnbService | createFnbOrder | response | id | string (uuid) | yes
FnbService | createFnbOrder | response | orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | createFnbOrder | response | outletId | string (uuid) | yes
FnbService | createFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | createFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | createFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | createFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | createFnbOrder | response | lines | array of object | yes
FnbService | createFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | createFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | createFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | createFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | createFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | createFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | createFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | createFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | createFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | createFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | createFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | createFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | createFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | createFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | createFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | createFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | createFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | createFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | createFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | createFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | createFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | createFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | response | createdAt | string (date-time) | yes
FnbService | createFnbOrder | response | recordedAt | string (date-time)
FnbService | createFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createForecastScenario | request | id | string (uuid) |  | (read-only)
AiService | createForecastScenario | request | name | string
AiService | createForecastScenario | request | baseVersionId | string (uuid) | yes
AiService | createForecastScenario | request | changes | array of object | yes | (min items 1)
AiService | createForecastScenario | request | changes[].lever | enum (price, capacity, openingHours, weather, event, marketing, staffing, closure) | yes
AiService | createForecastScenario | request | changes[].target | string |  | (nullable)
AiService | createForecastScenario | request | changes[].value | object |  | (nullable)
AiService | createForecastScenario | request | status | enum (computing, ready, failed) |  | (read-only)
AiService | createForecastScenario | request | result | object |  | Deltas against the base version by subject and period. (read-only; nullable)
AiService | createForecastScenario | request | createdByPrincipalId | string (uuid) |  | (read-only)
AiService | createForecastScenario | request | createdAt | string (date-time) |  | (read-only)
AiService | createForecastScenario | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createForecastScenario | response | id | string (uuid) |  | (read-only)
AiService | createForecastScenario | response | name | string
AiService | createForecastScenario | response | baseVersionId | string (uuid) | yes
AiService | createForecastScenario | response | changes | array of object | yes | (min items 1)
AiService | createForecastScenario | response | changes[].lever | enum (price, capacity, openingHours, weather, event, marketing, staffing, closure) | yes
AiService | createForecastScenario | response | changes[].target | string |  | (nullable)
AiService | createForecastScenario | response | changes[].value | object |  | (nullable)
AiService | createForecastScenario | response | status | enum (computing, ready, failed) |  | (read-only)
AiService | createForecastScenario | response | result | object |  | Deltas against the base version by subject and period. (read-only; nullable)
AiService | createForecastScenario | response | createdByPrincipalId | string (uuid) |  | (read-only)
AiService | createForecastScenario | response | createdAt | string (date-time) |  | (read-only)
AiService | createForecastScenario | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createForecastScenario | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createForm | request | id | string (uuid) | yes | (read-only)
MarketingService | createForm | request | name | string | yes
MarketingService | createForm | request | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | createForm | request | consentPurposes | array of enum (facePass, faceTag, marketing, photography, waiver) |  | What a consentForm consents to (Chinmay, 2 October, batch 4; follows BO-188: biometric capture needs consent on the venue's own form; CHG-CSA-026).
MarketingService | createForm | request | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | createForm | request | fields | array of FormField
MarketingService | createForm | request | fields[].key | string | yes
MarketingService | createForm | request | fields[].label | string | yes
MarketingService | createForm | request | fields[].labelLocalised | object
MarketingService | createForm | request | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | createForm | request | fields[].options | array of string
MarketingService | createForm | request | fields[].isRequired | boolean |  | (default False)
MarketingService | createForm | request | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | createForm | request | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | createForm | request | fields[].showWhen | object |  | (nullable)
MarketingService | createForm | request | fields[].showWhen.field | string
MarketingService | createForm | request | fields[].showWhen.equals | string
MarketingService | createForm | request | fields[].presentation | enum (dropDown, radio, checkBoxes) |  | How a choice is drawn (products module, 16 October 2026 minutes 4.13: the data mask's field types are text, drop-down, radio and check box; CHG-R8PRD-009). (nullable)
MarketingService | createForm | request | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | createForm | request | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | createForm | request | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | createForm | request | appliesToProductIds | array of string (uuid)
MarketingService | createForm | request | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | createForm | request | minimumAge | integer |  | (nullable)
MarketingService | createForm | request | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | createForm | request | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | createForm | request | legalReviewedBy | string |  | (nullable)
MarketingService | createForm | request | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | createForm | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createForm | response | id | string (uuid) | yes | (read-only)
MarketingService | createForm | response | name | string | yes
MarketingService | createForm | response | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | createForm | response | consentPurposes | array of enum (facePass, faceTag, marketing, photography, waiver) |  | What a consentForm consents to (Chinmay, 2 October, batch 4; follows BO-188: biometric capture needs consent on the venue's own form; CHG-CSA-026).
MarketingService | createForm | response | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | createForm | response | fields | array of FormField
MarketingService | createForm | response | fields[].key | string | yes
MarketingService | createForm | response | fields[].label | string | yes
MarketingService | createForm | response | fields[].labelLocalised | object
MarketingService | createForm | response | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | createForm | response | fields[].options | array of string
MarketingService | createForm | response | fields[].isRequired | boolean |  | (default False)
MarketingService | createForm | response | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | createForm | response | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | createForm | response | fields[].showWhen | object |  | (nullable)
MarketingService | createForm | response | fields[].showWhen.field | string
MarketingService | createForm | response | fields[].showWhen.equals | string
MarketingService | createForm | response | fields[].presentation | enum (dropDown, radio, checkBoxes) |  | How a choice is drawn (products module, 16 October 2026 minutes 4.13: the data mask's field types are text, drop-down, radio and check box; CHG-R8PRD-009). (nullable)
MarketingService | createForm | response | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | createForm | response | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | createForm | response | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | createForm | response | appliesToProductIds | array of string (uuid)
MarketingService | createForm | response | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | createForm | response | minimumAge | integer |  | (nullable)
MarketingService | createForm | response | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | createForm | response | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | createForm | response | legalReviewedBy | string |  | (nullable)
MarketingService | createForm | response | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | createForm | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createForm | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | createGoodsReceipt | request | id | string (uuid) | yes
InventoryService | createGoodsReceipt | request | purchaseOrderId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | locationId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | deliveryNoteReference | string |  | (max length 128)
InventoryService | createGoodsReceipt | request | lines | array of object | yes | (min items 1)
InventoryService | createGoodsReceipt | request | lines[].itemId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | lines[].receivedQuantity | number | yes | (min 0)
InventoryService | createGoodsReceipt | request | lines[].unit | string
InventoryService | createGoodsReceipt | request | lines[].batchNumber | string |  | (max length 64)
InventoryService | createGoodsReceipt | request | lines[].expiryDate | string (date) |  | Required for perishable items.
InventoryService | createGoodsReceipt | request | lines[].note | string |  | (max length 200)
InventoryService | createGoodsReceipt | request | recordedAt | string (date-time) | yes
InventoryService | createGoodsReceipt | response | id | string (uuid) | yes
InventoryService | createGoodsReceipt | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152), e.g. (read-only)
InventoryService | createGoodsReceipt | response | purchaseOrderId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | locationId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | deliveryNoteReference | string |  | (nullable)
InventoryService | createGoodsReceipt | response | lines | array of object | yes
InventoryService | createGoodsReceipt | response | lines[].lineId | string (uuid) |  | One batch or expiry line of the receipt. (read-only)
InventoryService | createGoodsReceipt | response | lines[].itemId | string (uuid)
InventoryService | createGoodsReceipt | response | lines[].itemName | string
InventoryService | createGoodsReceipt | response | lines[].orderedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].receivedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].rejectedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].batchNumber | string |  | (nullable)
InventoryService | createGoodsReceipt | response | lines[].expiryDate | string (date) |  | (nullable)
InventoryService | createGoodsReceipt | response | lines[].unitCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createGoodsReceipt | response | lines[].unitCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createGoodsReceipt | response | lines[].unitCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createGoodsReceipt | response | lines[].unitCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createGoodsReceipt | response | totalValue | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createGoodsReceipt | response | totalValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createGoodsReceipt | response | totalValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createGoodsReceipt | response | totalValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createGoodsReceipt | response | receivedByPrincipalId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | journalEntryId | string |  | The accrual the supplier invoice will later match against. (nullable)
InventoryService | createGoodsReceipt | response | createdAt | string (date-time) | yes
InventoryService | createGoodsReceipt | response | recordedAt | string (date-time)
InventoryService | createGoodsReceipt | response | syncedAt | string (date-time) |  | (nullable)
InventoryService | createGoodsReceipt | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createGuestFnbOrder | request | id | string (uuid) | yes
FnbService | createGuestFnbOrder | request | locationSessionId | string (uuid) |  | From claimLocationSession. (nullable)
FnbService | createGuestFnbOrder | request | outletId | string (uuid) |  | Required for collection. (nullable)
FnbService | createGuestFnbOrder | request | fulfilment | object |  | Required for takeaway and address delivery; refused with 422 when it breaks the outlet's FnbDeliveryPolicy. (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.id | string (uuid) |  | (read-only)
FnbService | createGuestFnbOrder | request | fulfilment.orderId | string (uuid) |  | The guest order this fulfils (FnbOrder.id). (read-only)
FnbService | createGuestFnbOrder | request | fulfilment.mode | enum (collection, delivery, inVenue) | yes | collection from a counter, delivery to an address outside the venue, inVenue to a table, seat, cabana or named location (the location session).
FnbService | createGuestFnbOrder | request | fulfilment.collectionAt | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.windowStart | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.windowEnd | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress | object |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.building | string |  | (max length 200)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.unit | string |  | (max length 60; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.emirate | string |  | (max length 60)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.directions | string |  | (max length 500; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee | object |  | (read-only; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | request | fulfilment.cutlery | boolean |  | (default False)
FnbService | createGuestFnbOrder | request | fulfilment.scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | createGuestFnbOrder | request | lines | array of CreateGuestOrderLine | yes | (min items 1)
FnbService | createGuestFnbOrder | request | lines[].id | string (uuid) | yes
FnbService | createGuestFnbOrder | request | lines[].menuItemId | string (uuid) | yes
FnbService | createGuestFnbOrder | request | lines[].quantity | integer | yes | (min 1; max 20)
FnbService | createGuestFnbOrder | request | lines[].modifierOptionIds | array of string (uuid)
FnbService | createGuestFnbOrder | request | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createGuestFnbOrder | request | quotedTotal | object | yes | What the guest was shown.
FnbService | createGuestFnbOrder | request | quotedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | request | quotedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | request | quotedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | request | paymentMethod | enum (card, wallet, roomCharge, addToTab)
FnbService | createGuestFnbOrder | request | recordedAt | string (date-time) | yes
FnbService | createGuestFnbOrder | response | orderId | string | yes
FnbService | createGuestFnbOrder | response | orderNumber | string | yes | Short and readable.
FnbService | createGuestFnbOrder | response | fulfilment | enum (collect, deliverToLocation, tableService, deliverToAddress) |  | How the order reaches the guest, in the request's terms: collect is GuestOrderFulfilment.mode collection; deliverToAddress is delivery; inVenue is tableService where the location session is a table a…
FnbService | createGuestFnbOrder | response | deliveryLabel | string |  | Where it is going, as a runner would read it. (nullable)
FnbService | createGuestFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | createGuestFnbOrder | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createGuestFnbOrder | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | response | collectionPoint | string |  | (nullable)
FnbService | createGuestFnbOrder | response | tableLabel | string |  | (nullable)
FnbService | createGuestFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createGuidedChoice | request | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | createGuidedChoice | request | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | createGuidedChoice | request | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | createGuidedChoice | request | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | createGuidedChoice | request | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | createGuidedChoice | request | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | createGuidedChoice | request | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | createGuidedChoice | request | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | request | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | createGuidedChoice | request | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | request | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | request | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | createGuidedChoice | request | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | createGuidedChoice | request | status | object | yes | (read-only)
WhiteLabelService | createGuidedChoice | request | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | createGuidedChoice | request | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | createGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | createGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | createGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | createGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | createGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | createGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | createGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | createGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | createGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | createGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | createGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | createGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | createGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createInspectionTemplate | request | instructions | string |  | The procedure itself.
VenueOpsService | createInspectionTemplate | request | id | string (uuid) | yes | (read-only)
VenueOpsService | createInspectionTemplate | request | code | string | yes | (max length 64)
VenueOpsService | createInspectionTemplate | request | name | string | yes | (max length 200)
VenueOpsService | createInspectionTemplate | request | venueId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | request | appliesToAssetCategoryId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | request | frequency | enum (preOpening, postClosing, daily, weekly, monthly, annual, adHoc)
VenueOpsService | createInspectionTemplate | request | items | array of object | yes | (min items 1)
VenueOpsService | createInspectionTemplate | request | items[].key | string | yes
VenueOpsService | createInspectionTemplate | request | items[].label | string | yes
VenueOpsService | createInspectionTemplate | request | items[].kind | InspectionItemKind: enum (passFail, yesNo, numeric, text, photo, signature) | yes
VenueOpsService | createInspectionTemplate | request | items[].isRequired | boolean | yes
VenueOpsService | createInspectionTemplate | request | items[].isSafetyCritical | boolean |  | A failed safety-critical item blocks the inspection from passing and cannot be overridden by completing the rest. (default False)
VenueOpsService | createInspectionTemplate | request | items[].requiresPhotoOnFail | boolean |  | (default True)
VenueOpsService | createInspectionTemplate | request | items[].minValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | request | items[].maxValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | request | items[].guidance | string |  | (nullable)
VenueOpsService | createInspectionTemplate | request | retentionYears | integer |  | Compliance inspections are retained alongside the financial trail. (default 7)
VenueOpsService | createInspectionTemplate | request | isActive | boolean
VenueOpsService | createInspectionTemplate | response | instructions | string |  | The procedure itself.
VenueOpsService | createInspectionTemplate | response | id | string (uuid) | yes | (read-only)
VenueOpsService | createInspectionTemplate | response | code | string | yes | (max length 64)
VenueOpsService | createInspectionTemplate | response | name | string | yes | (max length 200)
VenueOpsService | createInspectionTemplate | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | response | appliesToAssetCategoryId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | response | frequency | enum (preOpening, postClosing, daily, weekly, monthly, annual, adHoc)
VenueOpsService | createInspectionTemplate | response | items | array of object | yes | (min items 1)
VenueOpsService | createInspectionTemplate | response | items[].key | string | yes
VenueOpsService | createInspectionTemplate | response | items[].label | string | yes
VenueOpsService | createInspectionTemplate | response | items[].kind | InspectionItemKind: enum (passFail, yesNo, numeric, text, photo, signature) | yes
VenueOpsService | createInspectionTemplate | response | items[].isRequired | boolean | yes
VenueOpsService | createInspectionTemplate | response | items[].isSafetyCritical | boolean |  | A failed safety-critical item blocks the inspection from passing and cannot be overridden by completing the rest. (default False)
VenueOpsService | createInspectionTemplate | response | items[].requiresPhotoOnFail | boolean |  | (default True)
VenueOpsService | createInspectionTemplate | response | items[].minValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | response | items[].maxValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | response | items[].guidance | string |  | (nullable)
VenueOpsService | createInspectionTemplate | response | retentionYears | integer |  | Compliance inspections are retained alongside the financial trail. (default 7)
VenueOpsService | createInspectionTemplate | response | isActive | boolean
VenueOpsService | createInspectionTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | createInventoryItem | request | sku | string | yes | Unique within the item's venue, as the 409 says (ADAM CR-068, CHG-DDL-003): an inventory item is something one venue stocks (venueId is required), so two venues of a chain keep their own row for the… (max length 64)
InventoryService | createInventoryItem | request | barcode | string |  | (max length 128)
InventoryService | createInventoryItem | request | name | string | yes | (max length 200)
InventoryService | createInventoryItem | request | venueId | string (uuid) | yes
InventoryService | createInventoryItem | request | categoryId | string (uuid)
InventoryService | createInventoryItem | request | baseUnit | string | yes | The unit stock is held in.
InventoryService | createInventoryItem | request | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | createInventoryItem | request | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | createInventoryItem | request | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | createInventoryItem | request | reorderPoint | number |  | (min 0)
InventoryService | createInventoryItem | request | reorderQuantity | number |  | (min 0)
InventoryService | createInventoryItem | request | parLevel | number |  | (min 0)
InventoryService | createInventoryItem | request | preferredSupplierId | string (uuid)
InventoryService | createInventoryItem | request | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | createInventoryItem | request | isPerishable | boolean |  | (default False)
InventoryService | createInventoryItem | request | shelfLifeDays | integer |  | (nullable)
InventoryService | createInventoryItem | response | sku | string | yes | Unique within the item's venue, as the 409 says (ADAM CR-068, CHG-DDL-003): an inventory item is something one venue stocks (venueId is required), so two venues of a chain keep their own row for the… (max length 64)
InventoryService | createInventoryItem | response | barcode | string |  | (max length 128)
InventoryService | createInventoryItem | response | name | string | yes | (max length 200)
InventoryService | createInventoryItem | response | venueId | string (uuid) | yes
InventoryService | createInventoryItem | response | categoryId | string (uuid)
InventoryService | createInventoryItem | response | baseUnit | string | yes | The unit stock is held in.
InventoryService | createInventoryItem | response | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | createInventoryItem | response | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | createInventoryItem | response | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | createInventoryItem | response | reorderPoint | number |  | (min 0)
InventoryService | createInventoryItem | response | reorderQuantity | number |  | (min 0)
InventoryService | createInventoryItem | response | parLevel | number |  | (min 0)
InventoryService | createInventoryItem | response | preferredSupplierId | string (uuid)
InventoryService | createInventoryItem | response | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | createInventoryItem | response | isPerishable | boolean |  | (default False)
InventoryService | createInventoryItem | response | shelfLifeDays | integer |  | (nullable)
InventoryService | createInventoryItem | response | id | string (uuid) | yes
InventoryService | createInventoryItem | response | onHand | number | yes | Derived from movements.
InventoryService | createInventoryItem | response | onOrder | number
InventoryService | createInventoryItem | response | inTransit | number
InventoryService | createInventoryItem | response | available | number |  | On-hand minus allocated, where allocated is stock reserved for orders (decided 28 September, audit R171).
InventoryService | createInventoryItem | response | averageCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createInventoryItem | response | averageCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createInventoryItem | response | averageCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createInventoryItem | response | averageCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createInventoryItem | response | lastPurchasePrice | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createInventoryItem | response | lastPurchasePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createInventoryItem | response | lastPurchasePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createInventoryItem | response | lastPurchasePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createInventoryItem | response | isBelowReorderPoint | boolean
InventoryService | createInventoryItem | response | hasMovements | boolean |  | True locks costing method and base unit.
InventoryService | createInventoryItem | response | isActive | boolean | yes
InventoryService | createInventoryItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createInvitationCampaign | request | id | string (uuid) | yes | (read-only)
MarketingService | createInvitationCampaign | request | name | string | yes
MarketingService | createInvitationCampaign | request | eventId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | request | productId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | request | quota | integer | yes | Places held, not invitations sent.
MarketingService | createInvitationCampaign | request | overInvitePercent | number |  | How many more may be invited than there are places. (default 0)
MarketingService | createInvitationCampaign | request | issuedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | request | acceptedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | request | respondByAt | string (date-time) |  | (nullable)
MarketingService | createInvitationCampaign | request | status | enum (draft, open, closed, cancelled) | yes | (read-only)
MarketingService | createInvitationCampaign | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createInvitationCampaign | response | id | string (uuid) | yes | (read-only)
MarketingService | createInvitationCampaign | response | name | string | yes
MarketingService | createInvitationCampaign | response | eventId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | response | productId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | response | quota | integer | yes | Places held, not invitations sent.
MarketingService | createInvitationCampaign | response | overInvitePercent | number |  | How many more may be invited than there are places. (default 0)
MarketingService | createInvitationCampaign | response | issuedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | response | acceptedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | response | respondByAt | string (date-time) |  | (nullable)
MarketingService | createInvitationCampaign | response | status | enum (draft, open, closed, cancelled) | yes | (read-only)
MarketingService | createInvitationCampaign | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createInvitationCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createKnowledgeCollection | request | id | string (uuid) |  | (read-only)
AiService | createKnowledgeCollection | request | name | string | yes
AiService | createKnowledgeCollection | request | description | string
AiService | createKnowledgeCollection | request | scopeLevel | enum (tenant, region, venue) | yes
AiService | createKnowledgeCollection | request | scopePath | string |  | The node the collection belongs to (R8 blocker ORDERS-MONEY-C36).
AiService | createKnowledgeCollection | request | documentCount | integer |  | (read-only)
AiService | createKnowledgeCollection | request | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | createKnowledgeCollection | request | retrieval | enum (dense, hybrid) |  | Set at creation and not changeable. (default hybrid)
AiService | createKnowledgeCollection | request | sparseModel | string |  | The sparse signal, where retrieval is hybrid. (nullable)
AiService | createKnowledgeCollection | request | idfScope | enum (shard, tenant, venue) |  | Which population the sparse score measures rarity against (ADR-0021). (default tenant)
AiService | createKnowledgeCollection | request | embeddingModel | string |  | This is what decides how many collections exist (ADR-0021). (read-only)
AiService | createKnowledgeCollection | request | isActive | boolean
AiService | createKnowledgeCollection | response | id | string (uuid) |  | (read-only)
AiService | createKnowledgeCollection | response | name | string | yes
AiService | createKnowledgeCollection | response | description | string
AiService | createKnowledgeCollection | response | scopeLevel | enum (tenant, region, venue) | yes
AiService | createKnowledgeCollection | response | scopePath | string |  | The node the collection belongs to (R8 blocker ORDERS-MONEY-C36).
AiService | createKnowledgeCollection | response | documentCount | integer |  | (read-only)
AiService | createKnowledgeCollection | response | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | createKnowledgeCollection | response | retrieval | enum (dense, hybrid) |  | Set at creation and not changeable. (default hybrid)
AiService | createKnowledgeCollection | response | sparseModel | string |  | The sparse signal, where retrieval is hybrid. (nullable)
AiService | createKnowledgeCollection | response | idfScope | enum (shard, tenant, venue) |  | Which population the sparse score measures rarity against (ADR-0021). (default tenant)
AiService | createKnowledgeCollection | response | embeddingModel | string |  | This is what decides how many collections exist (ADR-0021). (read-only)
AiService | createKnowledgeCollection | response | isActive | boolean
AiService | createKnowledgeCollection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createKpi | request | id | string (uuid)
ReportingService | createKpi | request | code | string | yes | takings and admissions are seeded for every tenant as system KPIs (decided 28 September, audit R283), and the five accreditation KPIs for every tenant with the accreditation module (29 September, bui…
ReportingService | createKpi | request | name | string | yes
ReportingService | createKpi | request | description | string |  | (nullable)
ReportingService | createKpi | request | domain | string |  | (nullable)
ReportingService | createKpi | request | formula | string |  | Expressed against the semantic model, not against tables.
ReportingService | createKpi | request | unit | enum (currency, count, percentage, duration, ratio, score)
ReportingService | createKpi | request | higherIsBetter | boolean |  | Refund rate and revenue both go up. (default True)
ReportingService | createKpi | request | defaultPeriod | string |  | (nullable)
ReportingService | createKpi | request | owner | string (uuid) |  | (nullable)
ReportingService | createKpi | request | scopePath | string
ReportingService | createKpi | request | isActive | boolean |  | (default True)
ReportingService | createKpi | response | id | string (uuid)
ReportingService | createKpi | response | code | string | yes | takings and admissions are seeded for every tenant as system KPIs (decided 28 September, audit R283), and the five accreditation KPIs for every tenant with the accreditation module (29 September, bui…
ReportingService | createKpi | response | name | string | yes
ReportingService | createKpi | response | description | string |  | (nullable)
ReportingService | createKpi | response | domain | string |  | (nullable)
ReportingService | createKpi | response | formula | string |  | Expressed against the semantic model, not against tables.
ReportingService | createKpi | response | unit | enum (currency, count, percentage, duration, ratio, score)
ReportingService | createKpi | response | higherIsBetter | boolean |  | Refund rate and revenue both go up. (default True)
ReportingService | createKpi | response | defaultPeriod | string |  | (nullable)
ReportingService | createKpi | response | owner | string (uuid) |  | (nullable)
ReportingService | createKpi | response | scopePath | string
ReportingService | createKpi | response | isActive | boolean |  | (default True)
ReportingService | createKpi | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createLegalEntity | request | id | string (uuid) | yes | (read-only)
LedgerService | createLegalEntity | request | code | string | yes | (max length 64)
LedgerService | createLegalEntity | request | name | string | yes | (max length 200)
LedgerService | createLegalEntity | request | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createLegalEntity | request | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | createLegalEntity | request | currencyScale | integer | yes | (min 0; max 4)
LedgerService | createLegalEntity | request | taxRegistrationNumber | string |  | (nullable)
LedgerService | createLegalEntity | request | fiscalYearStartMonth | integer | yes | (min 1; max 12)
LedgerService | createLegalEntity | request | regionIds | array of string (uuid)
LedgerService | createLegalEntity | request | isActive | boolean
LedgerService | createLegalEntity | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | createLegalEntity | response | id | string (uuid) | yes | (read-only)
LedgerService | createLegalEntity | response | code | string | yes | (max length 64)
LedgerService | createLegalEntity | response | name | string | yes | (max length 200)
LedgerService | createLegalEntity | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createLegalEntity | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | createLegalEntity | response | currencyScale | integer | yes | (min 0; max 4)
LedgerService | createLegalEntity | response | taxRegistrationNumber | string |  | (nullable)
LedgerService | createLegalEntity | response | fiscalYearStartMonth | integer | yes | (min 1; max 12)
LedgerService | createLegalEntity | response | regionIds | array of string (uuid)
LedgerService | createLegalEntity | response | isActive | boolean
LedgerService | createLegalEntity | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | createLegalEntity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createLiveDynamicPrice | request | product | string |  | Product id
CatalogueService | createLiveDynamicPrice | request | event | string |  | Event id (nullable)
CatalogueService | createLiveDynamicPrice | request | newPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createLiveDynamicPrice | request | newPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createLiveDynamicPrice | request | newPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createLiveDynamicPrice | request | newPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createLiveDynamicPrice | request | strategy | string |  | Strategy id (nullable)
CatalogueService | createLiveDynamicPrice | request | aiRecommendation | string |  | Recommendation id (nullable)
CatalogueService | createLiveDynamicPrice | request | approval | string |  | Approval reference; required unless the automation policy permits automatic execution (nullable)
CatalogueService | createLiveDynamicPrice | request | executionSource | enum (manual, humanApproved, scheduled, conditionalAutonomous, autonomous) |  | Execution Source
CatalogueService | createLiveDynamicPrice | request | performance | string |  | Performance id (nullable)
CatalogueService | createLiveDynamicPrice | request | trigger | string |  | Trigger (nullable)
CatalogueService | createLiveDynamicPrice | request | channels | array of enum (b2c, mobileApp, pos, kiosk, callCenter, b2b, reseller, ota, …) |  | Channels to deploy to; default all channels the product is sold on (decided 29 September, readiness close-out)
CatalogueService | createLiveDynamicPrice | request | scheduledFor | string (date-time) |  | Execute at; empty = now (nullable)
CatalogueService | createLiveDynamicPrice | response | timestamp | string (date-time) |  | Timestamp
CatalogueService | createLiveDynamicPrice | response | product | string |  | Product id
CatalogueService | createLiveDynamicPrice | response | event | string |  | Event id (nullable)
CatalogueService | createLiveDynamicPrice | response | previousPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createLiveDynamicPrice | response | previousPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createLiveDynamicPrice | response | previousPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createLiveDynamicPrice | response | previousPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createLiveDynamicPrice | response | newPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createLiveDynamicPrice | response | newPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createLiveDynamicPrice | response | newPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createLiveDynamicPrice | response | newPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createLiveDynamicPrice | response | strategy | string |  | Strategy id (nullable)
CatalogueService | createLiveDynamicPrice | response | aiRecommendation | string |  | Recommendation id the change came from (nullable)
CatalogueService | createLiveDynamicPrice | response | approval | string |  | Approval reference; empty only for policy-permitted automatic execution (nullable)
CatalogueService | createLiveDynamicPrice | response | executionSource | enum (manual, humanApproved, scheduled, conditionalAutonomous, autonomous) |  | Execution Source
CatalogueService | createLiveDynamicPrice | response | status | string |  | Status: queued, processing, live, partial, failed or rolledBack
CatalogueService | createLiveDynamicPrice | response | executionId | string |  | Execution id
CatalogueService | createLiveDynamicPrice | response | trigger | string |  | Trigger, e.g. (nullable)
CatalogueService | createLiveDynamicPrice | response | aiConfidence | number |  | AI confidence at execution, percent
CatalogueService | createLiveDynamicPrice | response | channelDeployments | array of object |  | Channel Deployment
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].channel | enum (b2c, mobileApp, pos, kiosk, callCenter, b2b, reseller, ota, …) |  | Channel
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].price | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].consistent | boolean |  | Channel shows the new price
CatalogueService | createLiveDynamicPrice | response | channelDeployments[].deploymentStatus | string |  | queued, processing, live, failed or rolledBack
CatalogueService | createLiveDynamicPrice | response | priceInconsistency | boolean |  | Price inconsistency detected across channels
CatalogueService | createLiveDynamicPrice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createLoyaltyProgramme | request | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | createLoyaltyProgramme | request | tiers[].id | string (uuid) |  | (read-only)
MarketingService | createLoyaltyProgramme | request | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | request | tiers[].code | string | yes | (max length 40)
MarketingService | createLoyaltyProgramme | request | tiers[].name | string | yes | (max length 120)
MarketingService | createLoyaltyProgramme | request | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | createLoyaltyProgramme | request | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | createLoyaltyProgramme | request | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].isActive | boolean |  | (default True)
MarketingService | createLoyaltyProgramme | request | id | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | request | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | createLoyaltyProgramme | request | name | string | yes
MarketingService | createLoyaltyProgramme | request | venueId | string (uuid) |  | (nullable)
MarketingService | createLoyaltyProgramme | request | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | createLoyaltyProgramme | request | earnRules | array of object | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].points | number | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | createLoyaltyProgramme | request | earnRules[].multiplier | number
MarketingService | createLoyaltyProgramme | request | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | createLoyaltyProgramme | request | isActive | boolean
MarketingService | createLoyaltyProgramme | response | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | createLoyaltyProgramme | response | tiers[].id | string (uuid) |  | (read-only)
MarketingService | createLoyaltyProgramme | response | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | response | tiers[].code | string | yes | (max length 40)
MarketingService | createLoyaltyProgramme | response | tiers[].name | string | yes | (max length 120)
MarketingService | createLoyaltyProgramme | response | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | createLoyaltyProgramme | response | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | createLoyaltyProgramme | response | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].isActive | boolean |  | (default True)
MarketingService | createLoyaltyProgramme | response | id | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | response | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | createLoyaltyProgramme | response | name | string | yes
MarketingService | createLoyaltyProgramme | response | venueId | string (uuid) |  | (nullable)
MarketingService | createLoyaltyProgramme | response | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | createLoyaltyProgramme | response | earnRules | array of object | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].points | number | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | createLoyaltyProgramme | response | earnRules[].multiplier | number
MarketingService | createLoyaltyProgramme | response | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | createLoyaltyProgramme | response | isActive | boolean
MarketingService | createLoyaltyProgramme | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createMenu | request | code | string | yes | (max length 64)
FnbService | createMenu | request | name | string | yes | (max length 200)
FnbService | createMenu | request | outletId | string (uuid) | yes
FnbService | createMenu | request | availability | MenuAvailability |  | When this menu is in force.
FnbService | createMenu | request | availability.daysOfWeek | array of integer
FnbService | createMenu | request | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | request | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | request | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | request | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | id | string (uuid) | yes
FnbService | createMenu | response | code | string | yes | (max length 64)
FnbService | createMenu | response | name | string | yes | (max length 200)
FnbService | createMenu | response | outletId | string (uuid) | yes
FnbService | createMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | createMenu | response | availability.daysOfWeek | array of integer
FnbService | createMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | sections | array of MenuSection
FnbService | createMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | createMenu | response | sections[].code | string | yes
FnbService | createMenu | response | sections[].name | string | yes
FnbService | createMenu | response | sections[].sortOrder | integer | yes
FnbService | createMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | createMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | createMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | createMenu | response | sections[].items[].name | string | yes
FnbService | createMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | createMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createMenu | response | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | createMenu | response | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | createMenu | response | sections[].items[].sortOrder | integer
FnbService | createMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | createMenu | response | sections[].items[].stationId | string (uuid) |  | Not used for routing (ADAM CR-277 (4), 28 October 2026; CHG-R11TEN-002). (nullable)
FnbService | createMenu | response | sections[].items[].menuSectionId | string (uuid) | yes | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only)
FnbService | createMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | createMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | createMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | createMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | createMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | createMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | createMenu | response | sections[].items[].unavailableNote | string |  | The free text with an other unavailable reason (setItemAvailability); reviewed quarterly so the common ones become reasons (audit R222). (max length 500; read-only; nullable)
FnbService | createMenu | response | isActive | boolean | yes
FnbService | createMenu | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | createMenu | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | createMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createMerchandise | request | sku | string | yes | (max length 64)
RetailService | createMerchandise | request | barcode | string |  | (max length 128)
RetailService | createMerchandise | request | name | string | yes | (max length 200)
RetailService | createMerchandise | request | description | string |  | What the item is, in the guest's words.
RetailService | createMerchandise | request | outletId | string (uuid) | yes
RetailService | createMerchandise | request | categoryId | string (uuid)
RetailService | createMerchandise | request | variantId | string (uuid) | yes
RetailService | createMerchandise | request | inventoryItemId | string (uuid)
RetailService | createMerchandise | request | isReturnable | boolean |  | (default True)
RetailService | createMerchandise | request | returnWindowDays | integer
RetailService | createMerchandise | request | requiresSerialNumber | boolean |  | (default False)
RetailService | createMerchandise | request | imageAssetRef | string
RetailService | createMerchandise | request | isDroppable | boolean |  | Whether the item may go to shop-and-drop; the venue sets chilled, fragile or oversized items false (R8 blocker APPROVALS-TENANCY-C34). (default True)
RetailService | createMerchandise | request | isPublished | boolean |  | Whether guests and visitors may see the item (MerchandiseItem.isPublished; CHG-R10ORD-025). (default False)
RetailService | createMerchandise | response | description | string |  | What the item is, in the guest's words.
RetailService | createMerchandise | response | id | string (uuid) | yes
RetailService | createMerchandise | response | sku | string | yes | Unique per outlet (ADAM CR-104, CHG-R10ORD-017); lookupMerchandise matches it exactly.
RetailService | createMerchandise | response | barcode | string |  | Unique per outlet where set (ADAM CR-104; was unique per venue, which the table has no venue column to key); lookupMerchandise matches it exactly and returns one row. (nullable)
RetailService | createMerchandise | response | name | string | yes
RetailService | createMerchandise | response | outletId | string (uuid) | yes
RetailService | createMerchandise | response | categoryId | string (uuid) |  | (nullable)
RetailService | createMerchandise | response | variantId | string (uuid) | yes | The catalogue variant sold.
RetailService | createMerchandise | response | inventoryItemId | string (uuid) |  | The stock item depleted on sale. (nullable)
RetailService | createMerchandise | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createMerchandise | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createMerchandise | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createMerchandise | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createMerchandise | response | onHand | number | yes
RetailService | createMerchandise | response | isReturnable | boolean |  | (default True)
RetailService | createMerchandise | response | returnWindowDays | integer |  | (nullable)
RetailService | createMerchandise | response | requiresSerialNumber | boolean |  | (default False)
RetailService | createMerchandise | response | imageAssetRef | string |  | (nullable)
RetailService | createMerchandise | response | isActive | boolean | yes
RetailService | createMerchandise | response | isPublished | boolean |  | Whether a guest or a visitor may see the item (the lead's answer of 25 October 2026 to the r10 lanes' questions, question 22; CHG-R10ORD-025): the flag listMerchandise and lookupMerchandise already n… (default False)
RetailService | createMerchandise | response | isDroppable | boolean |  | Whether the item may be dropped for later collection (R8 blocker APPROVALS-TENANCY-C34). (default True)
RetailService | createMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createMessageTemplate | request | id | string (uuid) | yes | (read-only)
MarketingService | createMessageTemplate | request | code | string | yes | (max length 64)
MarketingService | createMessageTemplate | request | name | string | yes | (max length 200)
MarketingService | createMessageTemplate | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createMessageTemplate | request | subjects | object |  | Per language.
MarketingService | createMessageTemplate | request | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | createMessageTemplate | request | mergeFields | array of string
MarketingService | createMessageTemplate | request | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | createMessageTemplate | request | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | createMessageTemplate | request | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | createMessageTemplate | request | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | createMessageTemplate | response | id | string (uuid) | yes | (read-only)
MarketingService | createMessageTemplate | response | code | string | yes | (max length 64)
MarketingService | createMessageTemplate | response | name | string | yes | (max length 200)
MarketingService | createMessageTemplate | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createMessageTemplate | response | subjects | object |  | Per language.
MarketingService | createMessageTemplate | response | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | createMessageTemplate | response | mergeFields | array of string
MarketingService | createMessageTemplate | response | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | createMessageTemplate | response | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | createMessageTemplate | response | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | createMessageTemplate | response | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | createMessageTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | createMfaChallenge | request | action | string | yes | What the step-up is for.
IdentityService | createMfaChallenge | request | methodId | string (uuid)
IdentityService | createMfaChallenge | request | venueId | string (uuid) |  | For a guest, the venue whose VenueSettings.identity.guestTwoStep applies (sign-in venue, or the venue of the booking being acted on). (nullable)
IdentityService | createMfaChallenge | response | challengeId | string
IdentityService | createMfaChallenge | response | expiresAt | string (date-time)
IdentityService | createMfaChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createModifierGroup | request | id | string (uuid) | yes | (read-only)
FnbService | createModifierGroup | request | code | string | yes
FnbService | createModifierGroup | request | name | string | yes
FnbService | createModifierGroup | request | minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | createModifierGroup | request | maxSelections | integer | yes | (min 1)
FnbService | createModifierGroup | request | options | array of object | yes | (min items 1)
FnbService | createModifierGroup | request | options[].id | string (uuid) | yes
FnbService | createModifierGroup | request | options[].name | string | yes
FnbService | createModifierGroup | request | options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createModifierGroup | request | options[].priceDelta.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createModifierGroup | request | options[].priceDelta.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createModifierGroup | request | options[].priceDelta.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createModifierGroup | request | options[].isDefault | boolean
FnbService | createModifierGroup | request | options[].isAvailable | boolean
FnbService | createModifierGroup | request | options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | createModifierGroup | request | scopePath | string |  | The partition key (ADR-0005).
FnbService | createModifierGroup | response | id | string (uuid) | yes | (read-only)
FnbService | createModifierGroup | response | code | string | yes
FnbService | createModifierGroup | response | name | string | yes
FnbService | createModifierGroup | response | minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | createModifierGroup | response | maxSelections | integer | yes | (min 1)
FnbService | createModifierGroup | response | options | array of object | yes | (min items 1)
FnbService | createModifierGroup | response | options[].id | string (uuid) | yes
FnbService | createModifierGroup | response | options[].name | string | yes
FnbService | createModifierGroup | response | options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createModifierGroup | response | options[].priceDelta.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createModifierGroup | response | options[].priceDelta.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createModifierGroup | response | options[].priceDelta.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createModifierGroup | response | options[].isDefault | boolean
FnbService | createModifierGroup | response | options[].isAvailable | boolean
FnbService | createModifierGroup | response | options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | createModifierGroup | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | createModifierGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createOrder | request | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createOrder | request | venueId | string (uuid) | yes
OrderService | createOrder | request | channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
OrderService | createOrder | request | shiftId | string (uuid)
OrderService | createOrder | request | subjectId | string (uuid) |  | Null for an anonymous sale. (nullable)
OrderService | createOrder | request | guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
OrderService | createOrder | request | catalogueBundleVersion | string |  | The bundle the client priced from.
OrderService | createOrder | request | lines | array of CreateOrderLine | yes | (min items 1)
OrderService | createOrder | request | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createOrder | request | lines[].variantId | string (uuid) | yes
OrderService | createOrder | request | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createOrder | request | lines[].performanceId | string (uuid)
OrderService | createOrder | request | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createOrder | request | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createOrder | request | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createOrder | request | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createOrder | request | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createOrder | request | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createOrder | request | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createOrder | request | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createOrder | request | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | createOrder | request | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | createOrder | request | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | createOrder | request | lines[].quantity | integer | yes | (min 1)
OrderService | createOrder | request | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createOrder | request | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createOrder | request | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createOrder | request | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | request | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | request | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | request | lines[].holderName | string |  | (nullable)
OrderService | createOrder | request | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createOrder | request | recordedAt | string (date-time) | yes
OrderService | createOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | createOrder | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | createOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | createOrder | response | channel | object | yes | Where it came from.
OrderService | createOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | createOrder | response | venueId | string (uuid) | yes
OrderService | createOrder | response | scopePath | string | yes
OrderService | createOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | createOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | createOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | createOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | createOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | createOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | createOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | createOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | createOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | createOrder | response | droppedPromotions[].name | string
OrderService | createOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | createOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | createOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines | array of OrderLine | yes
OrderService | createOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createOrder | response | lines[].variantId | string (uuid) | yes
OrderService | createOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createOrder | response | lines[].performanceId | string (uuid)
OrderService | createOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createOrder | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | createOrder | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | createOrder | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | createOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | createOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].holderName | string |  | (nullable)
OrderService | createOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | createOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | createOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | createOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | createOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | createOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | createOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | createOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | createOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | createOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | createOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | createOrder | response | payments | array of Payment
OrderService | createOrder | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | createOrder | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | createOrder | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | createOrder | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | createOrder | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | createOrder | response | payments[].id | string (uuid) | yes
OrderService | createOrder | response | payments[].orderId | string (uuid) | yes
OrderService | createOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | createOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | createOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | createOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | createOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | createOrder | response | payments[].providerName | string |  | (nullable)
OrderService | createOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | createOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | createOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | createOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | createOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | createOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | createOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | createOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | principalId | string (uuid)
OrderService | createOrder | response | workstationId | string (uuid)
OrderService | createOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | createOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | createOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | createOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | createOrder | response | createdAt | string (date-time) | yes
OrderService | createOrder | response | recordedAt | string (date-time) | yes
OrderService | createOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createOrgUnit | request | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | createOrgUnit | request | parentId | string (uuid) | yes | Required for every level except tenant, which the cell creates at provisioning.
TenancyService | createOrgUnit | request | code | string | yes | Becomes the final ltree segment. (max length 64; pattern ^[a-z0-9_]+$)
TenancyService | createOrgUnit | request | name | string | yes | (max length 200)
TenancyService | createOrgUnit | response | id | string (uuid) | yes
TenancyService | createOrgUnit | response | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | createOrgUnit | response | parentId | string (uuid) |  | (nullable)
TenancyService | createOrgUnit | response | path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | createOrgUnit | response | code | string | yes | (max length 64)
TenancyService | createOrgUnit | response | name | string | yes | (max length 200)
TenancyService | createOrgUnit | response | isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | createOrgUnit | response | childCount | integer |  | (min 0)
TenancyService | createOrgUnit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createOutlet | request | id | string (uuid) | yes | (read-only)
TenancyService | createOutlet | request | code | string | yes | Unique within the venue (409 duplicate-code; ADAM CR-074, CHG-DDL-008): the database holds it with a unique index on (venue_id, code), so two concurrent creates cannot both keep one code. (max length 64)
TenancyService | createOutlet | request | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | createOutlet | request | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | createOutlet | request | venueId | string (uuid) | yes
TenancyService | createOutlet | request | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | createOutlet | request | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | createOutlet | request | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | createOutlet | request | zone | string |  | (nullable)
TenancyService | createOutlet | request | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | createOutlet | request | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | createOutlet | request | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | createOutlet | request | orderNumberPrefix | enum (A, B, C, D, E, F, G, H, …) |  | The one letter this outlet's F&B order numbers start with (ADAM CR-293 (2), option A, 29 October 2026; CHG-R11TEN-003): one capital letter A to Z, or null for none. (max length 1; nullable)
TenancyService | createOutlet | request | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | createOutlet | request | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | createOutlet | request | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | createOutlet | request | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | createOutlet | request | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | createOutlet | request | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | request | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | request | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | createOutlet | request | isActive | boolean
TenancyService | createOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | createOutlet | response | code | string | yes | Unique within the venue (409 duplicate-code; ADAM CR-074, CHG-DDL-008): the database holds it with a unique index on (venue_id, code), so two concurrent creates cannot both keep one code. (max length 64)
TenancyService | createOutlet | response | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | createOutlet | response | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | createOutlet | response | venueId | string (uuid) | yes
TenancyService | createOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | createOutlet | response | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | createOutlet | response | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | createOutlet | response | zone | string |  | (nullable)
TenancyService | createOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | createOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | createOutlet | response | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | createOutlet | response | orderNumberPrefix | enum (A, B, C, D, E, F, G, H, …) |  | The one letter this outlet's F&B order numbers start with (ADAM CR-293 (2), option A, 29 October 2026; CHG-R11TEN-003): one capital letter A to Z, or null for none. (max length 1; nullable)
TenancyService | createOutlet | response | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | createOutlet | response | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | createOutlet | response | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | createOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | createOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | createOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | response | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | createOutlet | response | isActive | boolean
TenancyService | createOutlet | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createPayment | request | id | string (uuid) | yes | Client-generated UUIDv7 of the payment, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createPayment | request | orderId | string (uuid) | yes
OrderService | createPayment | request | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createPayment | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | request | tenderCurrency | string |  | The currency the guest handed over, where it is not the venue's — becomes Payment.tenderCurrency. (pattern ^[A-Z]{3}$; nullable)
OrderService | createPayment | request | tenderAmount | object |  | What the guest handed over, in tenderCurrency — becomes Payment.tenderAmount, one name for one concept (renamed from tenderedAmount on 26 September).
OrderService | createPayment | request | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | request | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | request | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | request | walletAuthorisationId | string |  | Cross-cell wallet hold, where the guest's home cell is elsewhere. (nullable)
OrderService | createPayment | request | walletHoldId | string (uuid) |  | For a wallet tender, the hold wallet.holdWalletFunds placed (SD-027). (nullable)
OrderService | createPayment | request | returnUrl | string (uri) |  | Where the provider returns the guest after a 3-D Secure challenge or hosted page (SD-034). (nullable)
OrderService | createPayment | request | terminalId | string (uuid) |  | The card terminal to instruct, for a card payment at a till (ECR flow, SD-034). (nullable)
OrderService | createPayment | request | deviceId | string (uuid) |  | (nullable)
OrderService | createPayment | request | recordedAt | string (date-time) | yes
OrderService | createPayment | response | tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | createPayment | response | tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | createPayment | response | tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | createPayment | response | tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | createPayment | response | tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | createPayment | response | id | string (uuid) | yes
OrderService | createPayment | response | orderId | string (uuid) | yes
OrderService | createPayment | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createPayment | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | createPayment | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | createPayment | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | createPayment | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | createPayment | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | createPayment | response | providerName | string |  | (nullable)
OrderService | createPayment | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | createPayment | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | createPayment | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | createPayment | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | createPayment | response | nextAction.kind | enum (redirect, terminal)
OrderService | createPayment | response | nextAction.url | string (uri) |  | (nullable)
OrderService | createPayment | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | createPayment | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | createPayment | response | recordedAt | string (date-time) | yes
OrderService | createPayment | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createPayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createPaymentProviderConnection | request | id | string (uuid)
OrderService | createPaymentProviderConnection | request | providerId | string (uuid) |  | Which provider this connection is to (ADAM CR-165, 18 October 2026; CHG-CRA-004): a key to payments.provider, whose kind already says stripe or networkInternational. (nullable)
OrderService | createPaymentProviderConnection | request | code | string | yes
OrderService | createPaymentProviderConnection | request | name | string
OrderService | createPaymentProviderConnection | request | providerKind | enum (gateway, psp, acquirer, walletProvider, bnplProvider) | yes
OrderService | createPaymentProviderConnection | request | environment | enum (sandbox, production)
OrderService | createPaymentProviderConnection | request | credentialFingerprint | string |  | Written, never read back. (read-only)
OrderService | createPaymentProviderConnection | request | capabilities | object
OrderService | createPaymentProviderConnection | request | capabilities.methods | array of string
OrderService | createPaymentProviderConnection | request | capabilities.currencies | array of string
OrderService | createPaymentProviderConnection | request | capabilities.partialCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.multipleCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.refundWindowDays | integer |  | (nullable)
OrderService | createPaymentProviderConnection | request | capabilities.tokenisation | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.threeDSecure | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.cardPresent | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | merchantAccountId | string (uuid) |  | (nullable)
OrderService | createPaymentProviderConnection | request | status | enum (draft, testing, active, degraded, disabled)
OrderService | createPaymentProviderConnection | request | lastTestedAt | string (date-time) |  | (nullable)
OrderService | createPaymentProviderConnection | request | scopePath | string
OrderService | createPaymentProviderConnection | request | credentialRef | string |  | Where the provider credential is kept (4 October 2026, CHG-FXC-010; ADM-570): the vault reference the credential was stored under, as SetPaymentProviderRequest.credentialRef.
OrderService | createPaymentProviderConnection | response | id | string (uuid)
OrderService | createPaymentProviderConnection | response | providerId | string (uuid) |  | Which provider this connection is to (ADAM CR-165, 18 October 2026; CHG-CRA-004): a key to payments.provider, whose kind already says stripe or networkInternational. (nullable)
OrderService | createPaymentProviderConnection | response | code | string | yes
OrderService | createPaymentProviderConnection | response | name | string
OrderService | createPaymentProviderConnection | response | providerKind | enum (gateway, psp, acquirer, walletProvider, bnplProvider) | yes
OrderService | createPaymentProviderConnection | response | environment | enum (sandbox, production)
OrderService | createPaymentProviderConnection | response | credentialFingerprint | string |  | Written, never read back. (read-only)
OrderService | createPaymentProviderConnection | response | capabilities | object
OrderService | createPaymentProviderConnection | response | capabilities.methods | array of string
OrderService | createPaymentProviderConnection | response | capabilities.currencies | array of string
OrderService | createPaymentProviderConnection | response | capabilities.partialCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.multipleCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.refundWindowDays | integer |  | (nullable)
OrderService | createPaymentProviderConnection | response | capabilities.tokenisation | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.threeDSecure | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.cardPresent | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | merchantAccountId | string (uuid) |  | (nullable)
OrderService | createPaymentProviderConnection | response | status | enum (draft, testing, active, degraded, disabled)
OrderService | createPaymentProviderConnection | response | lastTestedAt | string (date-time) |  | (nullable)
OrderService | createPaymentProviderConnection | response | scopePath | string
OrderService | createPaymentProviderConnection | response | credentialRef | string |  | Where the provider credential is kept (4 October 2026, CHG-FXC-010; ADM-570): the vault reference the credential was stored under, as SetPaymentProviderRequest.credentialRef.
OrderService | createPaymentProviderConnection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPerformances | request | startsAt | string (date-time) | yes
CatalogueService | createPerformances | request | endsAt | string (date-time) | yes
CatalogueService | createPerformances | request | admissionRulesId | string (uuid)
CatalogueService | createPerformances | request | seatMapId | string (uuid)
CatalogueService | createPerformances | request | language | string |  | As Performance.language; every performance of a generated series takes it (decided 29 September, rev 3 REV3-17). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | createPerformances | request | format | string |  | As Performance.format (decided 29 September, rev 3 REV3-17). (max length 40; nullable)
CatalogueService | createPerformances | request | minutesOnScreen | integer |  | As Performance.minutesOnScreen; every performance of a generated series takes it (DI-167, DI-169; CHG-R4-014). (min 0; max 1440)
CatalogueService | createPerformances | request | slotLengthMinutes | integer |  | The slot length the form asks for (DI-167, DI-995; CHG-R4-014): every generated performance ends this many minutes after it starts. (min 1; max 1440)
CatalogueService | createPerformances | request | recurrence | object |  | Generate a series rather than a single performance.
CatalogueService | createPerformances | request | recurrence.intervalMinutes | integer |  | (min 1)
CatalogueService | createPerformances | request | recurrence.until | string (date-time)
CatalogueService | createPerformances | request | recurrence.daysOfWeek | array of integer
CatalogueService | createPerformances | request | recurrence.firstStartTime | string |  | The first start of each day, HH:MM on the region's clock (DI-995, 24 September minutes M24-01; CHG-R4-014). (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
CatalogueService | createPerformances | request | recurrence.lastStartTime | string |  | The last start of each day, HH:MM on the region's clock (DI-995; CHG-R4-014): no slot of the day starts after it, so a series every 30 minutes from 10:00 with a last start of 17:30 makes 16 slots a d… (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
CatalogueService | createPerformances | response | created | integer
CatalogueService | createPerformances | response | performances | array of Performance
CatalogueService | createPerformances | response | performances[].id | string (uuid) | yes
CatalogueService | createPerformances | response | performances[].eventId | string (uuid) | yes
CatalogueService | createPerformances | response | performances[].startsAt | string (date-time) | yes
CatalogueService | createPerformances | response | performances[].endsAt | string (date-time) | yes
CatalogueService | createPerformances | response | performances[].approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | createPerformances | response | performances[].requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | createPerformances | response | performances[].status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | createPerformances | response | performances[].admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createPerformances | response | performances[].seatMapId | string (uuid) |  | (nullable)
CatalogueService | createPerformances | response | performances[].language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | createPerformances | response | performances[].format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | createPerformances | response | performances[].minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | createPerformances | param (path) | eventId | string (uuid) | yes
CatalogueService | createPerformances | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPerformances | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
PlatformService | createPlan | request | currencyCode | string |  | The ISO 4217 currency of the plan's basePrice and every overageUnitPrice of its limits (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | code | string | yes | (max length 64)
PlatformService | createPlan | request | name | string | yes | (max length 200)
PlatformService | createPlan | request | description | string |  | (max length 1000)
PlatformService | createPlan | request | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlan | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlan | request | limits | array of EntitlementLimit | yes
PlatformService | createPlan | request | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlan | request | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlan | request | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlan | request | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | request | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | request | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | request | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | request | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlan | request | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlan | request | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlan | request | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlan | request | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlan | request | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlan | request | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlan | request | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlan | response | currencyCode | string |  | The ISO 4217 currency of the plan's basePrice and every overageUnitPrice of its limits (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | code | string | yes | (max length 64)
PlatformService | createPlan | response | name | string | yes | (max length 200)
PlatformService | createPlan | response | description | string |  | (max length 1000)
PlatformService | createPlan | response | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlan | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlan | response | limits | array of EntitlementLimit | yes
PlatformService | createPlan | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlan | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlan | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlan | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | response | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | response | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlan | response | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlan | response | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlan | response | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlan | response | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlan | response | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlan | response | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlan | response | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlan | response | id | string (uuid) | yes
PlatformService | createPlan | response | version | string | yes | Existing subscribers stay on the version they were sold.
PlatformService | createPlan | response | isActive | boolean | yes
PlatformService | createPlan | response | subscriberCount | integer | yes
PlatformService | createPlan | response | publishedAt | string (date-time)
PlatformService | createPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createPlanVersion | request | currencyCode | string |  | The ISO 4217 currency of the plan's basePrice and every overageUnitPrice of its limits (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | code | string | yes | (max length 64)
PlatformService | createPlanVersion | request | name | string | yes | (max length 200)
PlatformService | createPlanVersion | request | description | string |  | (max length 1000)
PlatformService | createPlanVersion | request | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlanVersion | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlanVersion | request | limits | array of EntitlementLimit | yes
PlatformService | createPlanVersion | request | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlanVersion | request | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlanVersion | request | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | request | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | request | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlanVersion | request | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlanVersion | request | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlanVersion | request | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlanVersion | request | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlanVersion | request | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlanVersion | request | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlanVersion | request | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlanVersion | response | currencyCode | string |  | The ISO 4217 currency of the plan's basePrice and every overageUnitPrice of its limits (ADAM CR-202, option A as the lead ruled it for r10, 25 October 2026; CHG-R10ID-017): a platform price is stored… (min length 3; max length 3; pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | code | string | yes | (max length 64)
PlatformService | createPlanVersion | response | name | string | yes | (max length 200)
PlatformService | createPlanVersion | response | description | string |  | (max length 1000)
PlatformService | createPlanVersion | response | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlanVersion | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlanVersion | response | limits | array of EntitlementLimit | yes
PlatformService | createPlanVersion | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlanVersion | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlanVersion | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | response | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | response | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlanVersion | response | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlanVersion | response | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlanVersion | response | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlanVersion | response | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlanVersion | response | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlanVersion | response | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlanVersion | response | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlanVersion | response | id | string (uuid) | yes
PlatformService | createPlanVersion | response | version | string | yes | Existing subscribers stay on the version they were sold.
PlatformService | createPlanVersion | response | isActive | boolean | yes
PlatformService | createPlanVersion | response | subscriberCount | integer | yes
PlatformService | createPlanVersion | response | publishedAt | string (date-time)
PlatformService | createPlanVersion | param (path) | planId | string (uuid) | yes
PlatformService | createPlanVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createPreview | request | platform | enum (ios, android, web)
WhiteLabelService | createPreview | request | theme | enum (light, dark) |  | Deprecated with Theme.darkMode (CHG-CSA-035); ignored.
WhiteLabelService | createPreview | request | language | string |  | (pattern ^[a-z]{2}$)
WhiteLabelService | createPreview | request | outputs | array of enum (app, pdfTicket, appleWalletPass, googleWalletPass) |  | What to render besides the app (CHG-CSA-041).
WhiteLabelService | createPreview | request | productId | string (uuid) |  | The product whose ticket and passes to render; a sample ticket where absent. (nullable)
WhiteLabelService | createPreview | request | expiresInHours | integer |  | (min 1; max 168; default 24)
WhiteLabelService | createPreview | response | previewId | string (uuid) | yes
WhiteLabelService | createPreview | response | url | string | yes
WhiteLabelService | createPreview | response | platform | enum (ios, android, web)
WhiteLabelService | createPreview | response | theme | enum (light, dark) |  | Deprecated with Theme.darkMode (CHG-CSA-035); the preview always renders the venue's theme.
WhiteLabelService | createPreview | response | language | string |  | (pattern ^[a-z]{2}$)
WhiteLabelService | createPreview | response | outputPreviews | array of object |  | The PDF ticket and the Apple and Google Wallet passes, previewed with the app (Chinmay, 2 October, workbook Q151: in Block A; CHG-CSA-041). (read-only)
WhiteLabelService | createPreview | response | outputPreviews[].output | enum (app, pdfTicket, appleWalletPass, googleWalletPass) | yes
WhiteLabelService | createPreview | response | outputPreviews[].url | string | yes | A short-lived link to the rendered output (the PDF, the .pkpass, or the Google pass preview), expiring with the preview.
WhiteLabelService | createPreview | response | expiresAt | string (date-time) | yes
WhiteLabelService | createPreview | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPriceList | request | code | string | yes | (max length 64)
CatalogueService | createPriceList | request | name | string | yes | (max length 200)
CatalogueService | createPriceList | request | venueId | string (uuid) | yes
CatalogueService | createPriceList | request | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes | (min items 1)
CatalogueService | createPriceList | request | validFrom | string (date-time)
CatalogueService | createPriceList | request | validTo | string (date-time)
CatalogueService | createPriceList | request | priority | integer |  | (default 0)
CatalogueService | createPriceList | request | description | string |  | The price list master fields (data model DM3) are written here since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001); each is optional and means what it means on PriceList. (nullable)
CatalogueService | createPriceList | request | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …)
CatalogueService | createPriceList | request | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | tags | array of string
CatalogueService | createPriceList | request | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | brand | string |  | (max length 100; nullable)
CatalogueService | createPriceList | request | businessUnit | string |  | (max length 100; nullable)
CatalogueService | createPriceList | request | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | createPriceList | request | marketCode | string |  | (max length 40; nullable)
CatalogueService | createPriceList | request | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit)
CatalogueService | createPriceList | request | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | allowOverrides | boolean
CatalogueService | createPriceList | request | allowInheritance | boolean
CatalogueService | createPriceList | request | allowMultipleCurrencies | boolean
CatalogueService | createPriceList | request | allowProductSpecificRates | boolean
CatalogueService | createPriceList | response | id | string (uuid) | yes
CatalogueService | createPriceList | response | code | string | yes
CatalogueService | createPriceList | response | name | string | yes
CatalogueService | createPriceList | response | venueId | string (uuid) | yes
CatalogueService | createPriceList | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | createPriceList | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | createPriceList | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | createPriceList | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | createPriceList | response | validTo | string (date-time) |  | (nullable)
CatalogueService | createPriceList | response | priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | createPriceList | response | description | string |  | Price list master fields (29 September, data model DM3), set with createPriceList and updatePriceList since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001). (nullable)
CatalogueService | createPriceList | response | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | createPriceList | response | status | object |  | (default active)
CatalogueService | createPriceList | response | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | tags | array of string
CatalogueService | createPriceList | response | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | brand | string |  | (max length 100; nullable)
CatalogueService | createPriceList | response | businessUnit | string |  | (max length 100; nullable)
CatalogueService | createPriceList | response | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | createPriceList | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | createPriceList | response | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | createPriceList | response | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | allowOverrides | boolean |  | (default False)
CatalogueService | createPriceList | response | allowInheritance | boolean |  | (default True)
CatalogueService | createPriceList | response | allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | createPriceList | response | allowProductSpecificRates | boolean |  | (default True)
CatalogueService | createPriceList | response | clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | createPriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPriceList | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | createPromoBlock | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createPromoBlock | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | request | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createPromoBlock | request | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | createPromoBlock | request | linkTarget | LinkTarget
WhiteLabelService | createPromoBlock | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createPromoBlock | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createPromoBlock | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createPromoBlock | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.productId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.eventId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | createPromoBlock | request | linkTarget.url | string
WhiteLabelService | createPromoBlock | request | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | createPromoBlock | request | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createPromoBlock | request | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | createPromoBlock | request | sortOrder | integer
WhiteLabelService | createPromoBlock | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createPromoBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createPromoBlock | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | response | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createPromoBlock | response | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | createPromoBlock | response | linkTarget | LinkTarget
WhiteLabelService | createPromoBlock | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createPromoBlock | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createPromoBlock | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createPromoBlock | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.productId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.eventId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | createPromoBlock | response | linkTarget.url | string
WhiteLabelService | createPromoBlock | response | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | createPromoBlock | response | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createPromoBlock | response | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | createPromoBlock | response | sortOrder | integer
WhiteLabelService | createPromoBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createPromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPromotion | request | code | string | yes | Unique per tenant (6 October 2026, CHG-R4-015; the rule of audit R108 for configuration codes). (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | createPromotion | request | name | string | yes | (max length 200)
CatalogueService | createPromotion | request | nameLocalised | object |  | The promotion's name in each of the tenant's enabled languages (ADAM CR-231, option A, decided 25 October 2026; CHG-R10CAT-012), keyed by ISO 639-1 code, as Product.nameLocalised. (nullable)
CatalogueService | createPromotion | request | description | string |  | (max length 1000)
CatalogueService | createPromotion | request | descriptionLocalised | object |  | The description in each enabled language, as nameLocalised; falls back to description. (nullable)
CatalogueService | createPromotion | request | label | object |  | The guest-facing label, the pill on the offer card (BUNDLE, RENTAL, MEMBERSHIP, SEASON, PARKING on WEB-032), per language as nameLocalised (ADAM CR-225 and CR-231, option A, decided 25 October 2026;… (nullable)
CatalogueService | createPromotion | request | venues | array of PromotionVenue |  | Where a guest may use the offer, as the offer card's venue line shows it (ADAM CR-225, option A, decided 25 October 2026; CHG-R10CAT-012).
CatalogueService | createPromotion | request | venues[].venueId | string (uuid) | yes | A venue node of the tenant (checked with tenancy#scopeRecords on write).
CatalogueService | createPromotion | request | venues[].name | string | yes | The venue's name as the back office gives it for guests. (max length 200)
CatalogueService | createPromotion | request | venues[].nameLocalised | object |  | The name in each enabled language; falls back to name (ADAM CR-231). (nullable)
CatalogueService | createPromotion | request | venueId | string (uuid) | yes
CatalogueService | createPromotion | request | discount | Discount | yes
CatalogueService | createPromotion | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createPromotion | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createPromotion | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createPromotion | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createPromotion | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createPromotion | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createPromotion | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createPromotion | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createPromotion | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createPromotion | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createPromotion | request | conditions.variantIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.productKinds | array of string
CatalogueService | createPromotion | request | conditions.categoryIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createPromotion | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createPromotion | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createPromotion | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createPromotion | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createPromotion | request | conditions.daysOfWeek | array of integer
CatalogueService | createPromotion | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createPromotion | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createPromotion | request | conditions.performanceIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createPromotion | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createPromotion | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createPromotion | request | stackingMode | object |  | (default bestOnly)
CatalogueService | createPromotion | request | stackingGroup | string |  | (max length 64)
CatalogueService | createPromotion | request | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | createPromotion | request | validFrom | string (date-time) | yes
CatalogueService | createPromotion | request | validTo | string (date-time)
CatalogueService | createPromotion | request | maxRedemptions | integer |  | (nullable)
CatalogueService | createPromotion | request | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | createPromotion | request | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | createPromotion | request | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | createPromotion | request | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | createPromotion | request | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | createPromotion | response | code | string | yes | Unique per tenant (6 October 2026, CHG-R4-015; the rule of audit R108 for configuration codes). (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | createPromotion | response | name | string | yes | (max length 200)
CatalogueService | createPromotion | response | nameLocalised | object |  | The promotion's name in each of the tenant's enabled languages (ADAM CR-231, option A, decided 25 October 2026; CHG-R10CAT-012), keyed by ISO 639-1 code, as Product.nameLocalised. (nullable)
CatalogueService | createPromotion | response | description | string |  | (max length 1000)
CatalogueService | createPromotion | response | descriptionLocalised | object |  | The description in each enabled language, as nameLocalised; falls back to description. (nullable)
CatalogueService | createPromotion | response | label | object |  | The guest-facing label, the pill on the offer card (BUNDLE, RENTAL, MEMBERSHIP, SEASON, PARKING on WEB-032), per language as nameLocalised (ADAM CR-225 and CR-231, option A, decided 25 October 2026;… (nullable)
CatalogueService | createPromotion | response | venues | array of PromotionVenue |  | Where a guest may use the offer, as the offer card's venue line shows it (ADAM CR-225, option A, decided 25 October 2026; CHG-R10CAT-012).
CatalogueService | createPromotion | response | venues[].venueId | string (uuid) | yes | A venue node of the tenant (checked with tenancy#scopeRecords on write).
CatalogueService | createPromotion | response | venues[].name | string | yes | The venue's name as the back office gives it for guests. (max length 200)
CatalogueService | createPromotion | response | venues[].nameLocalised | object |  | The name in each enabled language; falls back to name (ADAM CR-231). (nullable)
CatalogueService | createPromotion | response | venueId | string (uuid) | yes
CatalogueService | createPromotion | response | discount | Discount | yes
CatalogueService | createPromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createPromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createPromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createPromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createPromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createPromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createPromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createPromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createPromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createPromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createPromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.productKinds | array of string
CatalogueService | createPromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createPromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createPromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createPromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createPromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createPromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | createPromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createPromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createPromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createPromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createPromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createPromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | createPromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | createPromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | createPromotion | response | validFrom | string (date-time) | yes
CatalogueService | createPromotion | response | validTo | string (date-time)
CatalogueService | createPromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | createPromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | createPromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | createPromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | createPromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | createPromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | createPromotion | response | id | string (uuid) | yes
CatalogueService | createPromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | createPromotion | response | isPaused | boolean
CatalogueService | createPromotion | response | redemptionCount | integer
CatalogueService | createPromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | createPromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | createPromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createQueue | request | code | string | yes | (max length 64)
VenueOpsService | createQueue | request | name | LocalisedText | yes
VenueOpsService | createQueue | request | venueId | string (uuid) | yes
VenueOpsService | createQueue | request | attractionProductId | string (uuid)
VenueOpsService | createQueue | request | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | createQueue | request | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | createQueue | request | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | createQueue | request | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | createQueue | request | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | createQueue | request | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | request | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | request | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | createQueue | request | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | createQueue | request | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | createQueue | request | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | createQueue | request | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | createQueue | request | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | createQueue | request | cycleMinutes | number | yes | (min 0)
VenueOpsService | createQueue | request | maxPartySize | integer |  | (default 6)
VenueOpsService | createQueue | request | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | createQueue | request | heightRequirementCm | integer |  | (nullable)
VenueOpsService | createQueue | request | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | createQueue | request | zone | string |  | (nullable)
VenueOpsService | createQueue | request | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | createQueue | request | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | createQueue | request | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | request | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | request | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | createQueue | request | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | createQueue | request | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | createQueue | request | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | createQueue | response | code | string | yes | (max length 64)
VenueOpsService | createQueue | response | name | LocalisedText | yes
VenueOpsService | createQueue | response | venueId | string (uuid) | yes
VenueOpsService | createQueue | response | attractionProductId | string (uuid)
VenueOpsService | createQueue | response | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | createQueue | response | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | createQueue | response | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | createQueue | response | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | createQueue | response | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | createQueue | response | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | response | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | response | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | createQueue | response | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | createQueue | response | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | createQueue | response | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | createQueue | response | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | createQueue | response | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | createQueue | response | cycleMinutes | number | yes | (min 0)
VenueOpsService | createQueue | response | maxPartySize | integer |  | (default 6)
VenueOpsService | createQueue | response | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | createQueue | response | heightRequirementCm | integer |  | (nullable)
VenueOpsService | createQueue | response | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | createQueue | response | zone | string |  | (nullable)
VenueOpsService | createQueue | response | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | createQueue | response | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | createQueue | response | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | response | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | response | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | createQueue | response | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | createQueue | response | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | createQueue | response | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | createQueue | response | id | string (uuid) | yes
VenueOpsService | createQueue | response | status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | createQueue | response | statusReason | string |  | (nullable)
VenueOpsService | createQueue | response | waitingPartyCount | integer | yes
VenueOpsService | createQueue | response | waitingGuestCount | integer
VenueOpsService | createQueue | response | currentWaitMinutes | integer |  | (nullable)
VenueOpsService | createQueue | response | waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | createQueue | response | waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | createQueue | response | manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | createQueue | response | manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | createQueue | response | expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | createQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createReferral | request | id | string (uuid) | yes | (read-only)
MarketingService | createReferral | request | referrerSubjectId | string (uuid) | yes
MarketingService | createReferral | request | refereeSubjectId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | code | string | yes | (read-only)
MarketingService | createReferral | request | status | enum (issued, registered, qualified, rewarded, expired, void) | yes | (read-only)
MarketingService | createReferral | request | qualifyingAction | enum (firstPurchase, firstVisit, membershipPurchase)
MarketingService | createReferral | request | referrerRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | refereeRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | expiresAt | string (date-time) |  | (nullable)
MarketingService | createReferral | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createReferral | response | id | string (uuid) | yes | (read-only)
MarketingService | createReferral | response | referrerSubjectId | string (uuid) | yes
MarketingService | createReferral | response | refereeSubjectId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | code | string | yes | (read-only)
MarketingService | createReferral | response | status | enum (issued, registered, qualified, rewarded, expired, void) | yes | (read-only)
MarketingService | createReferral | response | qualifyingAction | enum (firstPurchase, firstVisit, membershipPurchase)
MarketingService | createReferral | response | referrerRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | refereeRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | expiresAt | string (date-time) |  | (nullable)
MarketingService | createReferral | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createReferral | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createRefund | request | id | string (uuid) | yes | Client-generated UUIDv7 of the refund, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createRefund | request | lineIds | array of string (uuid) |  | Omit to refund the whole order.
OrderService | createRefund | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | request | reason | string | yes | (min length 3; max length 500)
OrderService | createRefund | request | secondaryAuthorisation | object |  | Required above the venue's requiresSecondUserAbove.
OrderService | createRefund | request | secondaryAuthorisation.principalId | string (uuid) | yes
OrderService | createRefund | request | secondaryAuthorisation.credential | string | yes | The second person's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | createRefund | request | refundToOriginalTender | boolean |  | (default True)
OrderService | createRefund | request | alternateTender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) |  | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createRefund | request | recordedAt | string (date-time) | yes
OrderService | createRefund | response | id | string (uuid) | yes
OrderService | createRefund | response | orderId | string (uuid) | yes
OrderService | createRefund | response | batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | createRefund | response | fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | createRefund | response | taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | createRefund | response | settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | createRefund | response | fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | createRefund | response | fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | tenderCurrency | string |  | A refund goes back in the currency the guest paid (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | createRefund | response | tenderAmount | object |  | The refund in tenderCurrency, at that currency's own scale (CHG-FIN-001), its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192). (read-only)
OrderService | createRefund | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | createRefund | response | lines | array of object |  | What the refund took from each order line (ADAM CR-208, option A; CHG-R10ORD-014): child rows, orders.refund_line, one per line refunded, written by createRefund. (read-only)
OrderService | createRefund | response | lines[].orderLineId | string (uuid) | yes
OrderService | createRefund | response | lines[].refundedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | response | lines[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | lines[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | lines[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | lines[].appliedPercentage | number |  | The time band of this line's own performance (ADAM CR-208). (nullable)
OrderService | createRefund | response | payments | array of object |  | What the refund took from each payment (ADAM CR-208, option A; CHG-R10ORD-014): child rows, orders.refund_payment (the decision's refund_allocation; naming-and-style bans allocation in DDL), one per… (read-only)
OrderService | createRefund | response | payments[].paymentId | string (uuid) | yes
OrderService | createRefund | response | payments[].refundedAmount | object | yes | In the base currency, for the ledger.
OrderService | createRefund | response | payments[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | payments[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | payments[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | payments[].tenderAmount | object |  | In the payment's tender currency (Payment.tenderCurrency), at that currency's scale; null where the payment was in the base currency. (nullable)
OrderService | createRefund | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | createRefund | response | reason | string
OrderService | createRefund | response | requestedByPrincipalId | string (uuid)
OrderService | createRefund | response | secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | createRefund | response | approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | createRefund | response | ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | createRefund | response | gatewayReference | string |  | (nullable)
OrderService | createRefund | response | createdAt | string (date-time) | yes
OrderService | createRefund | response | completedAt | string (date-time) |  | (nullable)
OrderService | createRefund | param (path) | orderId | string (uuid) | yes
OrderService | createRefund | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createRefundRequest | request | orderId | string (uuid) | yes
OrderService | createRefundRequest | request | lineIds | array of string (uuid)
OrderService | createRefundRequest | request | reason | string | yes | (min length 3; max length 1000)
OrderService | createRefundRequest | response | requestId | string
OrderService | createRefundRequest | response | status | enum (submitted, moreInfoRequested, approved, declined)
OrderService | createRefundRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createReport | request | name | string | yes | (max length 200)
ReportingService | createReport | request | description | string |  | (max length 1000)
ReportingService | createReport | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | createReport | request | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | createReport | request | columns | array of ReportColumn | yes | (min items 1)
ReportingService | createReport | request | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | request | columns[].field | string | yes
ReportingService | createReport | request | columns[].label | string
ReportingService | createReport | request | columns[].aggregation | object |  | (default none)
ReportingService | createReport | request | columns[].sortOrder | integer
ReportingService | createReport | request | columns[].sortDirection | enum (asc, desc)
ReportingService | createReport | request | columns[].format | string |  | (nullable)
ReportingService | createReport | request | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | createReport | request | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | createReport | request | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | createReport | request | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | createReport | request | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | createReport | request | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | createReport | request | filters | array of ReportFilter
ReportingService | createReport | request | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | request | filters[].field | string | yes
ReportingService | createReport | request | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | createReport | request | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | createReport | request | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | createReport | request | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | createReport | request | groupBy | array of string
ReportingService | createReport | request | parameters | array of ReportParameter
ReportingService | createReport | request | parameters[].key | string | yes
ReportingService | createReport | request | parameters[].label | string | yes
ReportingService | createReport | request | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | createReport | request | parameters[].isRequired | boolean | yes
ReportingService | createReport | request | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | createReport | request | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | createReport | request | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | createReport | response | name | string | yes | (max length 200)
ReportingService | createReport | response | description | string |  | (max length 1000)
ReportingService | createReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | createReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | createReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | createReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | response | columns[].field | string | yes
ReportingService | createReport | response | columns[].label | string
ReportingService | createReport | response | columns[].aggregation | object |  | (default none)
ReportingService | createReport | response | columns[].sortOrder | integer
ReportingService | createReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | createReport | response | columns[].format | string |  | (nullable)
ReportingService | createReport | response | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | createReport | response | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | createReport | response | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | createReport | response | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | createReport | response | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | createReport | response | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | createReport | response | filters | array of ReportFilter
ReportingService | createReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | response | filters[].field | string | yes
ReportingService | createReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | createReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | createReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | createReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | createReport | response | groupBy | array of string
ReportingService | createReport | response | parameters | array of ReportParameter
ReportingService | createReport | response | parameters[].key | string | yes
ReportingService | createReport | response | parameters[].label | string | yes
ReportingService | createReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | createReport | response | parameters[].isRequired | boolean | yes
ReportingService | createReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | createReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | createReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | createReport | response | id | string (uuid) | yes
ReportingService | createReport | response | version | string | yes | The current version.
ReportingService | createReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | createReport | response | isRetired | boolean | yes
ReportingService | createReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | createReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | createReport | response | createdAt | string (date-time) | yes
ReportingService | createReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | createReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | createReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createResaleListing | request | entitlementId | string (uuid) | yes
OrderService | createResaleListing | request | askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createResaleListing | request | askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createResaleListing | request | askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createResaleListing | request | askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createResaleListing | request | sellerSubjectId | string (uuid) |  | The holder listing it. (nullable)
OrderService | createResaleListing | response | id | string (uuid) | yes | (read-only)
OrderService | createResaleListing | response | entitlementId | string (uuid) | yes
OrderService | createResaleListing | response | sellerSubjectId | string (uuid) | yes
OrderService | createResaleListing | response | askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createResaleListing | response | askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createResaleListing | response | askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createResaleListing | response | askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createResaleListing | response | priceCapPercent | number |  | A ceiling as a percentage of face value, because uncapped resale is a venue watching its own tickets sold at four times the price with its name on them. (read-only; nullable)
OrderService | createResaleListing | response | sellerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | createResaleListing | response | buyerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | createResaleListing | response | status | enum (pendingReview, listed, reserved, sold, withdrawn, expired, rejected) | yes | pendingReview and rejected added 29 September (DM5): a listing the marketplace's moderationMode sends to review waits there until approveListingModeration lists or rejects it. (read-only)
OrderService | createResaleListing | response | listedAt | string (date-time) |  | (read-only)
OrderService | createResaleListing | response | soldToSubjectId | string (uuid) |  | (read-only; nullable)
OrderService | createResaleListing | response | reviewReasons | array of enum (highResalePrice, unusualDiscount, highValueTicket, vipTicket, sellerRisk, newSeller, multipleListings, identityIssue, …) |  | Why the listing was sent to review (DM5, 29 September). (read-only)
OrderService | createResaleListing | response | moderatedByPrincipalId | string (uuid) |  | (read-only; nullable)
OrderService | createResaleListing | response | moderatedAt | string (date-time) |  | (read-only; nullable)
OrderService | createResaleListing | response | moderationReason | string |  | (max length 1000; read-only; nullable)
OrderService | createResaleListing | response | payoutStatus | enum (pending, held, paid, failed) |  | The seller is paid after the buyer is admitted, not after they pay. (read-only)
OrderService | createResaleListing | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createResaleListing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createReservation | request | id | string (uuid) | yes | Client-generated UUIDv7 of the reservation, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createReservation | request | venueId | string (uuid) | yes
OrderService | createReservation | request | subjectId | string (uuid) |  | The guest the reservation is held for.
OrderService | createReservation | request | lines | array of CreateOrderLine | yes | (min items 1)
OrderService | createReservation | request | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createReservation | request | lines[].variantId | string (uuid) | yes
OrderService | createReservation | request | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createReservation | request | lines[].performanceId | string (uuid)
OrderService | createReservation | request | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createReservation | request | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createReservation | request | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createReservation | request | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createReservation | request | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createReservation | request | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createReservation | request | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createReservation | request | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createReservation | request | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | createReservation | request | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | createReservation | request | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | createReservation | request | lines[].quantity | integer | yes | (min 1)
OrderService | createReservation | request | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createReservation | request | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createReservation | request | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createReservation | request | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createReservation | request | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createReservation | request | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createReservation | request | lines[].holderName | string |  | (nullable)
OrderService | createReservation | request | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createReservation | request | expiresAt | string (date-time) | yes
OrderService | createReservation | response | id | string (uuid) | yes
OrderService | createReservation | response | venueId | string (uuid) | yes
OrderService | createReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | createReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | createReservation | response | lines | array of CreateOrderLine
OrderService | createReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createReservation | response | lines[].variantId | string (uuid) | yes
OrderService | createReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createReservation | response | lines[].performanceId | string (uuid)
OrderService | createReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createReservation | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | createReservation | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | createReservation | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | createReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | createReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createReservation | response | lines[].holderName | string |  | (nullable)
OrderService | createReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createReservation | response | expiresAt | string (date-time) | yes
OrderService | createReservation | response | createdAt | string (date-time) | yes
OrderService | createReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | createReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResource | request | id | string (uuid) | yes | (read-only)
VenueOpsService | createResource | request | code | string | yes
VenueOpsService | createResource | request | name | string | yes
VenueOpsService | createResource | request | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | createResource | request | venueId | string (uuid) | yes
VenueOpsService | createResource | request | scopePath | string
VenueOpsService | createResource | request | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | createResource | request | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | createResource | request | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | createResource | request | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | createResource | request | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | createResource | request | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | createResource | request | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | createResource | request | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | createResource | request | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | createResource | request | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | request | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | request | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | createResource | request | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResource | request | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResource | request | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResource | request | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResource | request | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | createResource | request | isActive | boolean |  | (default True)
VenueOpsService | createResource | request | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | createResource | request | lifecycleState | object |  | The lifecycle state setResourceLifecycleState set. (read-only; nullable)
VenueOpsService | createResource | request | lifecycleEffectiveFrom | string (date-time) |  | When the lifecycle state takes effect (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | createResource | request | lifecycleReason | string |  | Why the lifecycle state changed (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | createResource | request | replacementResourceId | string (uuid) |  | The resource that replaces this one, where it was retired for a replacement. (read-only; nullable)
VenueOpsService | createResource | request | disposal | object |  | How a disposed resource left (setResourceLifecycleState), as given. (read-only; nullable)
VenueOpsService | createResource | response | id | string (uuid) | yes | (read-only)
VenueOpsService | createResource | response | code | string | yes
VenueOpsService | createResource | response | name | string | yes
VenueOpsService | createResource | response | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | createResource | response | venueId | string (uuid) | yes
VenueOpsService | createResource | response | scopePath | string
VenueOpsService | createResource | response | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | createResource | response | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | createResource | response | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | createResource | response | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | createResource | response | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | createResource | response | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | createResource | response | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | createResource | response | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | createResource | response | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | createResource | response | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | response | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | response | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | createResource | response | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResource | response | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResource | response | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResource | response | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResource | response | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | createResource | response | isActive | boolean |  | (default True)
VenueOpsService | createResource | response | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | createResource | response | lifecycleState | object |  | The lifecycle state setResourceLifecycleState set. (read-only; nullable)
VenueOpsService | createResource | response | lifecycleEffectiveFrom | string (date-time) |  | When the lifecycle state takes effect (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | createResource | response | lifecycleReason | string |  | Why the lifecycle state changed (setResourceLifecycleState). (read-only; nullable)
VenueOpsService | createResource | response | replacementResourceId | string (uuid) |  | The resource that replaces this one, where it was retired for a replacement. (read-only; nullable)
VenueOpsService | createResource | response | disposal | object |  | How a disposed resource left (setResourceLifecycleState), as given. (read-only; nullable)
VenueOpsService | createResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourceBlock | request | id | string (uuid)
VenueOpsService | createResourceBlock | request | resourceId | string (uuid) | yes
VenueOpsService | createResourceBlock | request | from | string (date-time) | yes
VenueOpsService | createResourceBlock | request | to | string (date-time) | yes
VenueOpsService | createResourceBlock | request | reason | enum (setup, teardown, maintenance, blackout, closed, operational, training) | yes
VenueOpsService | createResourceBlock | request | note | string |  | (nullable)
VenueOpsService | createResourceBlock | request | createdBy | string (uuid) |  | (nullable)
VenueOpsService | createResourceBlock | request | scopePath | string
VenueOpsService | createResourceBlock | response | id | string (uuid)
VenueOpsService | createResourceBlock | response | resourceId | string (uuid) | yes
VenueOpsService | createResourceBlock | response | from | string (date-time) | yes
VenueOpsService | createResourceBlock | response | to | string (date-time) | yes
VenueOpsService | createResourceBlock | response | reason | enum (setup, teardown, maintenance, blackout, closed, operational, training) | yes
VenueOpsService | createResourceBlock | response | note | string |  | (nullable)
VenueOpsService | createResourceBlock | response | createdBy | string (uuid) |  | (nullable)
VenueOpsService | createResourceBlock | response | scopePath | string
VenueOpsService | createResourceBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourceHold | request | id | string (uuid) | yes | Client-generated UUIDv7, as a seat hold's.
VenueOpsService | createResourceHold | request | mapId | string (uuid) | yes | The published venue map the guest picked from.
VenueOpsService | createResourceHold | request | resourceIds | array of string (uuid) | yes | Placed resources on that map, e.g. (min items 1; max items 10)
VenueOpsService | createResourceHold | request | from | string (date-time) | yes
VenueOpsService | createResourceHold | request | to | string (date-time) | yes
VenueOpsService | createResourceHold | request | partySize | integer |  | Checked against each resource's capacity; above it the hold is refused 422. (min 1; nullable)
VenueOpsService | createResourceHold | request | ttlSeconds | integer |  | 8 minutes by default, 30 in all with extensions (audit R169), as a seat hold. (min 60; max 1800; default 480)
VenueOpsService | createResourceHold | request | subjectId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | id | string (uuid) | yes
VenueOpsService | createResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | createResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | createResourceHold | response | from | string (date-time) | yes
VenueOpsService | createResourceHold | response | to | string (date-time) | yes
VenueOpsService | createResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | createResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | createResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | createResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | createResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | createResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | createResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | createResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourcePackage | request | id | string (uuid)
VenueOpsService | createResourcePackage | request | code | string | yes
VenueOpsService | createResourcePackage | request | name | string | yes
VenueOpsService | createResourcePackage | request | description | string |  | (nullable)
VenueOpsService | createResourcePackage | request | applicableVenueIds | array of string (uuid)
VenueOpsService | createResourcePackage | request | components | array of ResourceRequirement
VenueOpsService | createResourcePackage | request | components[].id | string (uuid)
VenueOpsService | createResourcePackage | request | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | request | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | request | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | createResourcePackage | request | components[].quantity | integer | yes | (default 1)
VenueOpsService | createResourcePackage | request | components[].mandatory | boolean |  | (default True)
VenueOpsService | createResourcePackage | request | components[].requiredQualifications | array of string
VenueOpsService | createResourcePackage | request | components[].requiredAttributes | object
VenueOpsService | createResourcePackage | request | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | createResourcePackage | request | components[].scopePath | string
VenueOpsService | createResourcePackage | request | components[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | createResourcePackage | request | components[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | createResourcePackage | request | allocationPriority | integer |  | (default 0)
VenueOpsService | createResourcePackage | request | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | request | effectiveTo | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | request | minimumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | request | maximumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | request | requiresApproval | boolean |  | (default False)
VenueOpsService | createResourcePackage | request | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourcePackage | request | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourcePackage | request | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourcePackage | request | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourcePackage | request | scopePath | string
VenueOpsService | createResourcePackage | response | id | string (uuid)
VenueOpsService | createResourcePackage | response | code | string | yes
VenueOpsService | createResourcePackage | response | name | string | yes
VenueOpsService | createResourcePackage | response | description | string |  | (nullable)
VenueOpsService | createResourcePackage | response | applicableVenueIds | array of string (uuid)
VenueOpsService | createResourcePackage | response | components | array of ResourceRequirement
VenueOpsService | createResourcePackage | response | components[].id | string (uuid)
VenueOpsService | createResourcePackage | response | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | response | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | response | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | createResourcePackage | response | components[].quantity | integer | yes | (default 1)
VenueOpsService | createResourcePackage | response | components[].mandatory | boolean |  | (default True)
VenueOpsService | createResourcePackage | response | components[].requiredQualifications | array of string
VenueOpsService | createResourcePackage | response | components[].requiredAttributes | object
VenueOpsService | createResourcePackage | response | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | createResourcePackage | response | components[].scopePath | string
VenueOpsService | createResourcePackage | response | components[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | createResourcePackage | response | components[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | createResourcePackage | response | allocationPriority | integer |  | (default 0)
VenueOpsService | createResourcePackage | response | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | response | effectiveTo | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | response | minimumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | response | maximumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | response | requiresApproval | boolean |  | (default False)
VenueOpsService | createResourcePackage | response | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourcePackage | response | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourcePackage | response | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourcePackage | response | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourcePackage | response | scopePath | string
VenueOpsService | createResourcePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createRetailReturn | request | id | string (uuid) | yes
RetailService | createRetailReturn | request | saleId | string | yes
RetailService | createRetailReturn | request | lines | array of object | yes | (min items 1)
RetailService | createRetailReturn | request | lines[].lineId | string | yes
RetailService | createRetailReturn | request | lines[].quantity | integer | yes | (min 1)
RetailService | createRetailReturn | request | lines[].condition | ReturnCondition: enum (resaleable, opened, damaged, faulty, missingParts) | yes | Determines whether stock is restored or written off.
RetailService | createRetailReturn | request | lines[].serialNumbers | array of string
RetailService | createRetailReturn | request | lines[].note | string |  | (max length 200)
RetailService | createRetailReturn | request | reason | ReturnReason: enum (changedMind, wrongSize, wrongItem, faulty, damagedInTransit, duplicatePurchase, giftReturn, other) | yes
RetailService | createRetailReturn | request | refundTender | string |  | Defaults to the original tender.
RetailService | createRetailReturn | request | secondaryAuthorisation | object |  | Required above the outlet's self-authorise limit.
RetailService | createRetailReturn | request | secondaryAuthorisation.principalId | string (uuid) |  | The supervisor signing.
RetailService | createRetailReturn | request | secondaryAuthorisation.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
RetailService | createRetailReturn | request | secondaryAuthorisation.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
RetailService | createRetailReturn | request | recordedAt | string (date-time) | yes
RetailService | createRetailReturn | response | id | string | yes
RetailService | createRetailReturn | response | returnNumber | string
RetailService | createRetailReturn | response | saleId | string | yes
RetailService | createRetailReturn | response | refundId | string |  | The refund raised in the Order & Payment context. (nullable)
RetailService | createRetailReturn | response | lines | array of object | yes
RetailService | createRetailReturn | response | lines[].lineId | string
RetailService | createRetailReturn | response | lines[].merchandiseId | string (uuid)
RetailService | createRetailReturn | response | lines[].name | string
RetailService | createRetailReturn | response | lines[].quantity | integer
RetailService | createRetailReturn | response | lines[].condition | ReturnCondition: enum (resaleable, opened, damaged, faulty, missingParts) |  | Determines whether stock is restored or written off.
RetailService | createRetailReturn | response | lines[].wasRestocked | boolean |  | False for opened, damaged or faulty goods, which are written off with a reason rather than silently absent.
RetailService | createRetailReturn | response | lines[].refundAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailReturn | response | lines[].refundAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailReturn | response | lines[].refundAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailReturn | response | lines[].refundAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailReturn | response | reason | ReturnReason: enum (changedMind, wrongSize, wrongItem, faulty, damagedInTransit, duplicatePurchase, giftReturn, other)
RetailService | createRetailReturn | response | refundAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createRetailReturn | response | refundAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailReturn | response | refundAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailReturn | response | refundAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailReturn | response | refundTender | string
RetailService | createRetailReturn | response | restockedQuantity | integer | yes
RetailService | createRetailReturn | response | writtenOffQuantity | integer | yes
RetailService | createRetailReturn | response | status | object | yes | (read-only)
RetailService | createRetailReturn | response | refusedReason | object |  | Set when status is refused, null otherwise. (read-only; nullable)
RetailService | createRetailReturn | response | acceptedByPrincipalId | string (uuid) |  | Who took the return at the desk.
RetailService | createRetailReturn | response | secondaryPrincipalId | string (uuid) |  | (nullable)
RetailService | createRetailReturn | response | createdAt | string (date-time) | yes
RetailService | createRetailReturn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createRetailSale | request | id | string (uuid) | yes
RetailService | createRetailSale | request | outletId | string (uuid) | yes
RetailService | createRetailSale | request | shiftId | string
RetailService | createRetailSale | request | subjectId | string (uuid)
RetailService | createRetailSale | request | lines | array of CreateRetailSaleLine | yes | (min items 1)
RetailService | createRetailSale | request | lines[].id | string (uuid) | yes
RetailService | createRetailSale | request | lines[].merchandiseId | string (uuid) | yes
RetailService | createRetailSale | request | lines[].orderLineId | string (uuid) |  | The order line this sale line is (r8 re-walk, CHG-R8RW-004): a line of the body's orderId for the same item and quantity, whose price, discount and tax the sale line copies.
RetailService | createRetailSale | request | lines[].quantity | integer | yes | (min 1)
RetailService | createRetailSale | request | lines[].serialNumbers | array of string |  | Required where the item is serialised.
RetailService | createRetailSale | request | lines[].overridePrice | object |  | Not applied here (r8 re-walk, CHG-R8RW-004).
RetailService | createRetailSale | request | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | request | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | request | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | request | lines[].overrideReason | string |  | (max length 200)
RetailService | createRetailSale | request | couponCodes | array of string |  | Not applied here (r8 walk fix, CHG-R8WFC-003).
RetailService | createRetailSale | request | orderId | string (uuid) |  | The order the till took payment on (r8 walk fix, CHG-R8WFC-003), as fnb's CreateFnbOrderRequest.salesOrderId does: RetailSale.orderId, stored in retail.sale.order_id.
RetailService | createRetailSale | request | recordedAt | string (date-time) | yes
RetailService | createRetailSale | response | id | string | yes
RetailService | createRetailSale | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | createRetailSale | response | receiptBarcode | string |  | The barcode printed on the receipt (R8 blocker APPROVALS-TENANCY-C34): the receipt number as printed, encoded as a Code 128 barcode, stored so lookupRetailSale finds a sale by receiptBarcode with an… (max length 64; read-only)
RetailService | createRetailSale | response | cashierPrincipalId | string (uuid) |  | The staff member who rang the sale up, from the session (null for a guest's own sale). (read-only; nullable)
RetailService | createRetailSale | response | orderId | string | yes | The order in the Order & Payment context.
RetailService | createRetailSale | response | outletId | string (uuid) | yes
RetailService | createRetailSale | response | shiftId | string |  | (nullable)
RetailService | createRetailSale | response | subjectId | string (uuid) |  | (nullable)
RetailService | createRetailSale | response | lines | array of object | yes
RetailService | createRetailSale | response | lines[].lineId | string
RetailService | createRetailSale | response | lines[].merchandiseId | string (uuid)
RetailService | createRetailSale | response | lines[].orderLineId | string (uuid) |  | The order line the amounts were copied from (CreateRetailSaleLine.orderLineId; r8 re-walk, CHG-R8RW-004). (nullable)
RetailService | createRetailSale | response | lines[].name | string
RetailService | createRetailSale | response | lines[].quantity | integer
RetailService | createRetailSale | response | lines[].overrideReason | string |  | The reason given with a manual price override (CreateRetailSaleLine.overrideReason); null when the price was not overridden. (max length 200; nullable)
RetailService | createRetailSale | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].serialNumbers | array of string
RetailService | createRetailSale | response | lines[].returnedQuantity | integer
RetailService | createRetailSale | response | lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | createRetailSale | response | lines[].notReturnableReason | string |  | (nullable)
RetailService | createRetailSale | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | reprintCount | integer
RetailService | createRetailSale | response | createdAt | string (date-time) | yes
RetailService | createRetailSale | response | recordedAt | string (date-time)
RetailService | createRetailSale | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | createRole | request | code | string | yes | Unique within the tenant, compared case-insensitively (decided 28 September, audit R108). (max length 64; pattern ^[A-Za-z0-9_-]+$)
IdentityService | createRole | request | name | string | yes | (max length 200)
IdentityService | createRole | request | description | string |  | (max length 500)
IdentityService | createRole | request | presetCodes | array of string |  | Presets (CapabilityTemplate.code) whose permissions fill the new role's checklist; copied, never bound (CHG-CSP-003).
IdentityService | createRole | request | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | Permissions ticked on the checklist beyond the presets.
IdentityService | createRole | response | id | string (uuid) | yes
IdentityService | createRole | response | code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | createRole | response | name | string | yes
IdentityService | createRole | response | description | string
IdentityService | createRole | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | createRole | response | inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | createRole | response | isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | createRole | response | presetCode | string |  | The preset this role was started from, for the record only (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): the first of createRole.presetCodes, or null for a role ticked by hand. (max length 64; read-only; nullable)
IdentityService | createRole | response | principalCount | integer |  | Computed on read, never stored (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): the distinct principals holding this role through a live grant (identity.delegated_access with this role_id, a prin… (read-only)
IdentityService | createRole | response | grantCount | integer |  | Computed on read, never stored (decided 14 October 2026, ADAM CR-077; CHG-IDR-002): the live grants of this role (the rows principalCount counts, one per grant, so a principal granted the role at two… (read-only)
IdentityService | createRole | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createRotaAssignment | request | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | createRotaAssignment | request | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | createRotaAssignment | request | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | createRotaAssignment | request | labourCost | object |  | Cost at the point of scheduling.
TenancyService | createRotaAssignment | request | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createRotaAssignment | request | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createRotaAssignment | request | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createRotaAssignment | request | id | string (uuid) |  | (read-only)
TenancyService | createRotaAssignment | request | principalId | string (uuid) | yes
TenancyService | createRotaAssignment | request | displayName | string |  | (read-only)
TenancyService | createRotaAssignment | request | venueId | string (uuid) | yes
TenancyService | createRotaAssignment | request | departmentId | string (uuid) |  | (nullable)
TenancyService | createRotaAssignment | request | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | createRotaAssignment | request | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | createRotaAssignment | request | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | createRotaAssignment | request | startsAt | string (date-time) | yes
TenancyService | createRotaAssignment | request | endsAt | string (date-time) | yes
TenancyService | createRotaAssignment | request | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | createRotaAssignment | request | breakMinutes | integer |  | (nullable)
TenancyService | createRotaAssignment | request | note | string |  | (nullable)
TenancyService | createRotaAssignment | response | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | createRotaAssignment | response | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | createRotaAssignment | response | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | createRotaAssignment | response | labourCost | object |  | Cost at the point of scheduling.
TenancyService | createRotaAssignment | response | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createRotaAssignment | response | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createRotaAssignment | response | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createRotaAssignment | response | id | string (uuid) |  | (read-only)
TenancyService | createRotaAssignment | response | principalId | string (uuid) | yes
TenancyService | createRotaAssignment | response | displayName | string |  | (read-only)
TenancyService | createRotaAssignment | response | venueId | string (uuid) | yes
TenancyService | createRotaAssignment | response | departmentId | string (uuid) |  | (nullable)
TenancyService | createRotaAssignment | response | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | createRotaAssignment | response | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | createRotaAssignment | response | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | createRotaAssignment | response | startsAt | string (date-time) | yes
TenancyService | createRotaAssignment | response | endsAt | string (date-time) | yes
TenancyService | createRotaAssignment | response | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | createRotaAssignment | response | breakMinutes | integer |  | (nullable)
TenancyService | createRotaAssignment | response | note | string |  | (nullable)
TenancyService | createRotaAssignment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createSaleBoard | request | id | string (uuid) | yes | (read-only)
TenancyService | createSaleBoard | request | code | string | yes | Unique within the venue (as the hand-written r0 table had it). (max length 64)
TenancyService | createSaleBoard | request | name | string | yes | (max length 200)
TenancyService | createSaleBoard | request | venueId | string (uuid) | yes
TenancyService | createSaleBoard | request | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | createSaleBoard | request | pages | array of object | yes | (min items 1)
TenancyService | createSaleBoard | request | pages[].name | string | yes
TenancyService | createSaleBoard | request | pages[].sortOrder | integer | yes
TenancyService | createSaleBoard | request | pages[].tiles | array of SaleBoardTile | yes
TenancyService | createSaleBoard | request | pages[].tiles[].position | integer | yes
TenancyService | createSaleBoard | request | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | createSaleBoard | request | pages[].tiles[].variantId | string (uuid) |  | The catalogue variant a product tile sells (catalogue.variant). (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].categoryId | string (uuid) |  | The catalogue category a category tile opens (catalogue.product_category; ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].actionCode | enum (holdSale, recallHeld, applyDiscount, guestLookup, scanMedia, reprintReceipt) |  | The till action an action tile runs (ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].label | string
TenancyService | createSaleBoard | request | pages[].tiles[].colour | string |  | #rrggbb, as the hand-written r0 table held it (char(7); audit R246; CHG-TEN-001). (pattern ^#[0-9A-Fa-f]{6}$; nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | createSaleBoard | request | isActive | boolean
TenancyService | createSaleBoard | response | id | string (uuid) | yes | (read-only)
TenancyService | createSaleBoard | response | code | string | yes | Unique within the venue (as the hand-written r0 table had it). (max length 64)
TenancyService | createSaleBoard | response | name | string | yes | (max length 200)
TenancyService | createSaleBoard | response | venueId | string (uuid) | yes
TenancyService | createSaleBoard | response | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | createSaleBoard | response | pages | array of object | yes | (min items 1)
TenancyService | createSaleBoard | response | pages[].name | string | yes
TenancyService | createSaleBoard | response | pages[].sortOrder | integer | yes
TenancyService | createSaleBoard | response | pages[].tiles | array of SaleBoardTile | yes
TenancyService | createSaleBoard | response | pages[].tiles[].position | integer | yes
TenancyService | createSaleBoard | response | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | createSaleBoard | response | pages[].tiles[].variantId | string (uuid) |  | The catalogue variant a product tile sells (catalogue.variant). (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].categoryId | string (uuid) |  | The catalogue category a category tile opens (catalogue.product_category; ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].actionCode | enum (holdSale, recallHeld, applyDiscount, guestLookup, scanMedia, reprintReceipt) |  | The till action an action tile runs (ADAM CR-080, CHG-TEN-001). (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].label | string
TenancyService | createSaleBoard | response | pages[].tiles[].colour | string |  | #rrggbb, as the hand-written r0 table held it (char(7); audit R246; CHG-TEN-001). (pattern ^#[0-9A-Fa-f]{6}$; nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | createSaleBoard | response | isActive | boolean
TenancyService | createSaleBoard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createSeatCategory | request | code | string | yes | (max length 64)
CatalogueService | createSeatCategory | request | name | string | yes | (max length 200)
CatalogueService | createSeatCategory | request | venueId | string (uuid) | yes
CatalogueService | createSeatCategory | request | displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
CatalogueService | createSeatCategory | request | rank | integer |  | Ordering for best-seat assignment.
CatalogueService | createSeatCategory | request | priceBands | array of SeatPriceBand |  | The category's price bands (decided 28 September, audit R275 (d)).
CatalogueService | createSeatCategory | request | priceBands[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | createSeatCategory | request | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | request | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | request | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | createSeatCategory | request | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | createSeatCategory | request | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | createSeatCategory | request | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatCategory | request | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatCategory | request | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatCategory | request | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatCategory | request | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | createSeatCategory | request | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | createSeatCategory | request | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | createSeatCategory | request | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | createSeatCategory | response | id | string (uuid) | yes
CatalogueService | createSeatCategory | response | code | string | yes
CatalogueService | createSeatCategory | response | name | string | yes
CatalogueService | createSeatCategory | response | venueId | string (uuid) | yes
CatalogueService | createSeatCategory | response | displayColour | string |  | (nullable)
CatalogueService | createSeatCategory | response | rank | integer | yes | Ordering for best-seat assignment.
CatalogueService | createSeatCategory | response | seatCount | integer
CatalogueService | createSeatCategory | response | priceBands | array of SeatPriceBand |  | What a seat in this category costs, by band (decided 28 September, audit R275 (d), from the BO-1045 pack).
CatalogueService | createSeatCategory | response | priceBands[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
CatalogueService | createSeatCategory | response | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | response | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | response | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | createSeatCategory | response | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | createSeatCategory | response | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | createSeatCategory | response | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatCategory | response | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatCategory | response | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatCategory | response | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatCategory | response | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | createSeatCategory | response | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | createSeatCategory | response | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | createSeatCategory | response | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | createSeatCategory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createSeatCategory | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | createSeatHold | request | id | string (uuid) | yes
CatalogueService | createSeatHold | request | performanceId | string (uuid) | yes
CatalogueService | createSeatHold | request | zoneId | string (uuid) |  | A standing zone of the performance's map (SeatAvailability.zones), with quantity (r8, GPS-C38).
CatalogueService | createSeatHold | request | quantity | integer |  | The places held in zoneId; the same per-booking limits as seatIds (r8, GPS-C38). (min 1; max 50)
CatalogueService | createSeatHold | request | seatIds | array of string |  | 50 is the ceiling of the venue setting, not the limit a caller gets. (min items 1; max items 50)
CatalogueService | createSeatHold | request | ttlSeconds | integer |  | 8 minutes by default, extendable to 30 in all (decided 28 September, audit R169). (min 60; max 1800; default 480)
CatalogueService | createSeatHold | request | subjectId | string (uuid)
CatalogueService | createSeatHold | response | id | string | yes
CatalogueService | createSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | createSeatHold | response | seatIds | array of string | yes
CatalogueService | createSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | createSeatHold | response | status | enum (held, converted, released, expired, sold) | yes | converted when the order is created; sold when the order is paid and catalogue.convertInventoryHold sells the units (ADAM CR-169, 18 October 2026; CHG-CRA-007).
CatalogueService | createSeatHold | response | inventoryReservationId | string (uuid) |  | The inventory hold these seats sit under (ADAM CR-169; CHG-CRA-007), so convertInventoryHold finds the order's seat reservations from the hold it converts. (nullable)
CatalogueService | createSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | createSeatHold | response | extensionCount | integer
CatalogueService | createSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | createSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | createSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createSegment | request | name | string | yes | (max length 200)
MarketingService | createSegment | request | description | string |  | (max length 1000)
MarketingService | createSegment | request | venueId | string (uuid)
MarketingService | createSegment | request | match | enum (all, any) |  | (default all)
MarketingService | createSegment | request | criteria | array of SegmentCriterion | yes | (min items 1)
MarketingService | createSegment | request | criteria[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createSegment | request | criteria[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createSegment | request | criteria[].value | object
MarketingService | createSegment | request | criteria[].values | array of object
MarketingService | createSegment | request | excludeSegmentIds | array of string (uuid)
MarketingService | createSegment | request | ruleGroups | array of SegmentRuleGroup |  | Nested AND / OR / NOT groups (contract gap CHG-WIR-007, BO-755; CHG-CSA-045).
MarketingService | createSegment | request | ruleGroups[].operator | enum (and, or, not)
MarketingService | createSegment | request | ruleGroups[].criteria | array of object |  | Each entry has the shape of SegmentCriterion (attribute, operator, value).
MarketingService | createSegment | request | ruleGroups[].groups | array of SegmentRuleGroup
MarketingService | createSegment | request | effectiveFrom | string (date-time) |  | The segment is evaluated for sends only from this time. (nullable)
MarketingService | createSegment | request | effectiveTo | string (date-time) |  | (nullable)
MarketingService | createSegment | request | ownerPrincipalId | string (uuid) |  | Who answers for the segment; defaults to its creator. (nullable)
MarketingService | createSegment | request | requiresApproval | boolean |  | Where true, a campaign may use the segment only after an approvals request on it is approved. (default False)
MarketingService | createSegment | response | name | string | yes | (max length 200)
MarketingService | createSegment | response | description | string |  | (max length 1000)
MarketingService | createSegment | response | venueId | string (uuid)
MarketingService | createSegment | response | match | enum (all, any) |  | (default all)
MarketingService | createSegment | response | criteria | array of SegmentCriterion | yes | (min items 1)
MarketingService | createSegment | response | criteria[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createSegment | response | criteria[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createSegment | response | criteria[].value | object
MarketingService | createSegment | response | criteria[].values | array of object
MarketingService | createSegment | response | excludeSegmentIds | array of string (uuid)
MarketingService | createSegment | response | ruleGroups | array of SegmentRuleGroup |  | Nested AND / OR / NOT groups (contract gap CHG-WIR-007, BO-755; CHG-CSA-045).
MarketingService | createSegment | response | ruleGroups[].operator | enum (and, or, not)
MarketingService | createSegment | response | ruleGroups[].criteria | array of object |  | Each entry has the shape of SegmentCriterion (attribute, operator, value).
MarketingService | createSegment | response | ruleGroups[].groups | array of SegmentRuleGroup
MarketingService | createSegment | response | effectiveFrom | string (date-time) |  | The segment is evaluated for sends only from this time. (nullable)
MarketingService | createSegment | response | effectiveTo | string (date-time) |  | (nullable)
MarketingService | createSegment | response | ownerPrincipalId | string (uuid) |  | Who answers for the segment; defaults to its creator. (nullable)
MarketingService | createSegment | response | requiresApproval | boolean |  | Where true, a campaign may use the segment only after an approvals request on it is approved. (default False)
MarketingService | createSegment | response | id | string (uuid) | yes
MarketingService | createSegment | response | lastEvaluatedSize | integer |  | (nullable)
MarketingService | createSegment | response | lastEvaluatedAt | string (date-time) |  | (nullable)
MarketingService | createSegment | response | createdAt | string (date-time) | yes
MarketingService | createSegment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createShopAndDrop | request | id | string (uuid) | yes
RetailService | createShopAndDrop | request | saleId | string |  | The retail sale, from a till. (nullable)
RetailService | createShopAndDrop | request | orderId | string |  | The paid online order, when the order service calls on payment (audit R236). (nullable)
RetailService | createShopAndDrop | request | entitlementId | string |  | The guest's ticket. (nullable)
RetailService | createShopAndDrop | request | collectionPointId | string (uuid) | yes
RetailService | createShopAndDrop | request | lineIds | array of string |  | Omit to drop the whole sale.
RetailService | createShopAndDrop | request | collectBy | string (date-time) |  | Usually venue close.
RetailService | createShopAndDrop | request | recordedAt | string (date-time) | yes
RetailService | createShopAndDrop | response | disposalMethod | enum (donated, destroyed, returnedToStock, heldLonger) |  | What disposeShopAndDrop decided for an uncollected item; null until it is called. (read-only; nullable)
RetailService | createShopAndDrop | response | disposalNote | string |  | The note sent with that decision; null when none was sent. (max length 300; read-only; nullable)
RetailService | createShopAndDrop | response | disposalDecidedAt | string (date-time) |  | When the decision was recorded (the server's time). (read-only; nullable)
RetailService | createShopAndDrop | response | disposalDecidedByPrincipalId | string (uuid) |  | Who authorised it, the caller, from the session ("recorded with who authorised it"). (read-only; nullable)
RetailService | createShopAndDrop | response | id | string | yes
RetailService | createShopAndDrop | response | dropReference | string | yes | Short and readable. (max length 32; read-only)
RetailService | createShopAndDrop | response | saleId | string |  | The till sale. (nullable)
RetailService | createShopAndDrop | response | orderId | string (uuid) |  | The paid online order that created this collection (audit R236). (nullable)
RetailService | createShopAndDrop | response | entitlementId | string |  | The ticket that claims these goods. (nullable)
RetailService | createShopAndDrop | response | subjectId | string (uuid) |  | The guest the goods are for, set at the drop from the sale's subjectId or, for an online order, the order's buyer; null when the sale named no guest (R8 blocker APPROVALS-TENANCY-C34). (nullable)
RetailService | createShopAndDrop | response | collectionPointId | string (uuid) | yes
RetailService | createShopAndDrop | response | collectionPointName | string
RetailService | createShopAndDrop | response | status | enum (awaitingCollection, partiallyCollected, collected, uncollected, disposed) | yes
RetailService | createShopAndDrop | response | lines | array of object
RetailService | createShopAndDrop | response | lines[].lineId | string
RetailService | createShopAndDrop | response | lines[].merchandiseId | string (uuid)
RetailService | createShopAndDrop | response | lines[].name | string
RetailService | createShopAndDrop | response | lines[].quantity | integer
RetailService | createShopAndDrop | response | lines[].collectedQuantity | integer
RetailService | createShopAndDrop | response | droppedAt | string (date-time)
RetailService | createShopAndDrop | response | collectBy | string (date-time) | yes
RetailService | createShopAndDrop | response | collectedAt | string (date-time) |  | (nullable)
RetailService | createShopAndDrop | response | collectedByPrincipalId | string (uuid) |  | (nullable)
RetailService | createShopAndDrop | response | verifiedBy | string |  | (nullable)
RetailService | createShopAndDrop | response | collectionNote | string |  | The note given with the latest collectShopAndDrop (ADAM CR-104, CHG-R10ORD-017); null when none was given. (max length 500; nullable)
RetailService | createShopAndDrop | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createTableReservation | request | id | string (uuid) |  | (read-only)
FnbService | createTableReservation | request | outletId | string (uuid) | yes
FnbService | createTableReservation | request | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservation | request | guestName | string
FnbService | createTableReservation | request | contactPoint | string
FnbService | createTableReservation | request | partySize | integer | yes | (min 1)
FnbService | createTableReservation | request | startsAt | string (date-time) | yes
FnbService | createTableReservation | request | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservation | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservation | request | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservation | request | tables[].tableId | string (uuid) | yes
FnbService | createTableReservation | request | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservation | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservation | request | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservation | request | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservation | request | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservation | request | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservation | request | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservation | request | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservation | request | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservation | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservation | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservation | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservation | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservation | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservation | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservation | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservation | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservation | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservation | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservation | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservation | request | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | createTableReservation | response | outletId | string (uuid) | yes
FnbService | createTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservation | response | guestName | string
FnbService | createTableReservation | response | contactPoint | string
FnbService | createTableReservation | response | partySize | integer | yes | (min 1)
FnbService | createTableReservation | response | startsAt | string (date-time) | yes
FnbService | createTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | createTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservation | response | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservation | response | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservation | response | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservation | response | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createTableReservationForGuest | request | id | string (uuid) |  | (read-only)
FnbService | createTableReservationForGuest | request | outletId | string (uuid) | yes
FnbService | createTableReservationForGuest | request | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservationForGuest | request | guestName | string
FnbService | createTableReservationForGuest | request | contactPoint | string
FnbService | createTableReservationForGuest | request | partySize | integer | yes | (min 1)
FnbService | createTableReservationForGuest | request | startsAt | string (date-time) | yes
FnbService | createTableReservationForGuest | request | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservationForGuest | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservationForGuest | request | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservationForGuest | request | tables[].tableId | string (uuid) | yes
FnbService | createTableReservationForGuest | request | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservationForGuest | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservationForGuest | request | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservationForGuest | request | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservationForGuest | request | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservationForGuest | request | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservationForGuest | request | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservationForGuest | request | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservationForGuest | request | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservationForGuest | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservationForGuest | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservationForGuest | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservationForGuest | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservationForGuest | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservationForGuest | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservationForGuest | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservationForGuest | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservationForGuest | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservationForGuest | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservationForGuest | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservationForGuest | request | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservationForGuest | response | id | string (uuid) |  | (read-only)
FnbService | createTableReservationForGuest | response | outletId | string (uuid) | yes
FnbService | createTableReservationForGuest | response | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservationForGuest | response | guestName | string
FnbService | createTableReservationForGuest | response | contactPoint | string
FnbService | createTableReservationForGuest | response | partySize | integer | yes | (min 1)
FnbService | createTableReservationForGuest | response | startsAt | string (date-time) | yes
FnbService | createTableReservationForGuest | response | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservationForGuest | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservationForGuest | response | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservationForGuest | response | tables[].tableId | string (uuid) | yes
FnbService | createTableReservationForGuest | response | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservationForGuest | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservationForGuest | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservationForGuest | response | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservationForGuest | response | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservationForGuest | response | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservationForGuest | response | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservationForGuest | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservationForGuest | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservationForGuest | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservationForGuest | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservationForGuest | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservationForGuest | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservationForGuest | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservationForGuest | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservationForGuest | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservationForGuest | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservationForGuest | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservationForGuest | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservationForGuest | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservationForGuest | response | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservationForGuest | param (path) | outletId | string (uuid) | yes
FnbService | createTableReservationForGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createTaxCode | request | code | string | yes | (max length 64)
LedgerService | createTaxCode | request | name | string | yes | (max length 200)
LedgerService | createTaxCode | request | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createTaxCode | request | rate | number | yes | (min 0; max 100)
LedgerService | createTaxCode | request | compoundOnTaxCodeId | string (uuid)
LedgerService | createTaxCode | request | isInclusive | boolean |  | (default False)
LedgerService | createTaxCode | request | accountId | string (uuid) | yes
LedgerService | createTaxCode | request | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | createTaxCode | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
LedgerService | createTaxCode | response | id | string (uuid) | yes
LedgerService | createTaxCode | response | code | string | yes | (max length 64)
LedgerService | createTaxCode | response | name | string | yes | (max length 200)
LedgerService | createTaxCode | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createTaxCode | response | appliesTo | array of enum (goods, services, admission, food, accommodation, donation, gratuity, fee) |  | What this code covers, and donation is why the field exists (CF-84).
LedgerService | createTaxCode | response | rate | number | yes | (min 0; max 100)
LedgerService | createTaxCode | response | compoundOnTaxCodeId | string (uuid) |  | When set, this tax applies to the base plus the referenced tax, not to the base alone. (nullable)
LedgerService | createTaxCode | response | isInclusive | boolean |  | True when the displayed price already contains this tax.
LedgerService | createTaxCode | response | accountId | string (uuid)
LedgerService | createTaxCode | response | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | createTaxCode | response | effectiveTo | string (date) |  | A day in the region's time zone, local midnight to local midnight. (nullable)
LedgerService | createTaxCode | response | isActive | boolean | yes
LedgerService | createTaxCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createTenant | request | code | string | yes | (max length 64; pattern ^[a-z0-9-]+$)
PlatformService | createTenant | request | name | string | yes | (max length 200)
PlatformService | createTenant | request | billingEmail | string | yes
PlatformService | createTenant | request | billingAddress | string |  | (max length 500)
PlatformService | createTenant | request | accountManagerPrincipalId | string (uuid)
PlatformService | createTenant | request | planId | string (uuid)
PlatformService | createTenant | response | id | string (uuid) | yes
PlatformService | createTenant | response | code | string | yes
PlatformService | createTenant | response | name | string | yes
PlatformService | createTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | createTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | createTenant | response | suspensionReason | string |  | (nullable)
PlatformService | createTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | createTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | createTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | createTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | createTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | createTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | planVersion | string |  | The version of the plan the tenant is on (with planId, the key of the plan row; R8 blocker APPROVALS-TENANCY-C15, CHG-R8INT-023). (read-only; nullable)
PlatformService | createTenant | response | planName | string |  | (nullable)
PlatformService | createTenant | response | cellCount | integer
PlatformService | createTenant | response | venueCount | integer
PlatformService | createTenant | response | cellHost | string |  | The host of the tenant's home cell (the host part of Cell.apiEndpoint of the cell that holds the tenant in its home region), derived on read through control.cell_tenant. (read-only; nullable)
PlatformService | createTenant | response | cellHosts | array of object |  | One entry per region the tenant is in, for a multi-region tenant; the entry with isHome true is cellHost. (read-only)
PlatformService | createTenant | response | cellHosts[].regionId | string (uuid) | yes
PlatformService | createTenant | response | cellHosts[].cellId | string (uuid) | yes
PlatformService | createTenant | response | cellHosts[].host | string | yes
PlatformService | createTenant | response | cellHosts[].isHome | boolean | yes
PlatformService | createTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | createTenant | response | billingEmail | string
PlatformService | createTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | createTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | createdAt | string (date-time) | yes
PlatformService | createTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | createTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createTicketTemplate | request | name | string |  | (max length 200)
OrderService | createTicketTemplate | request | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms)
OrderService | createTicketTemplate | request | isRecyclable | boolean
OrderService | createTicketTemplate | request | recycleAfterDays | integer |  | (min 0; nullable)
OrderService | createTicketTemplate | request | appliesToProductKinds | array of string
OrderService | createTicketTemplate | request | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | createTicketTemplate | request | selectionPriority | integer
OrderService | createTicketTemplate | request | layoutRef | string |  | The artwork, as a media-asset reference.
OrderService | createTicketTemplate | request | localeVariants | object
OrderService | createTicketTemplate | request | isActive | boolean
OrderService | createTicketTemplate | response | scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
OrderService | createTicketTemplate | response | id | string (uuid) | yes
OrderService | createTicketTemplate | response | name | string | yes
OrderService | createTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | createTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | createTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | createTicketTemplate | response | appliesToProductKinds | array of string
OrderService | createTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | createTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | createTicketTemplate | response | layoutRef | string
OrderService | createTicketTemplate | response | localeVariants | object
OrderService | createTicketTemplate | response | isActive | boolean | yes
OrderService | createTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportPassType | request | venueId | string (uuid) | yes
VenueOpsService | createTransportPassType | request | code | string | yes | (max length 32)
VenueOpsService | createTransportPassType | request | name | LocalisedText | yes
VenueOpsService | createTransportPassType | request | description | LocalisedText
VenueOpsService | createTransportPassType | request | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | createTransportPassType | request | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | createTransportPassType | request | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | createTransportPassType | request | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | createTransportPassType | request | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | createTransportPassType | request | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | createTransportPassType | request | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | createTransportPassType | response | venueId | string (uuid) | yes
VenueOpsService | createTransportPassType | response | code | string | yes | (max length 32)
VenueOpsService | createTransportPassType | response | name | LocalisedText | yes
VenueOpsService | createTransportPassType | response | description | LocalisedText
VenueOpsService | createTransportPassType | response | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | createTransportPassType | response | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | createTransportPassType | response | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | createTransportPassType | response | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | createTransportPassType | response | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | createTransportPassType | response | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | createTransportPassType | response | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | createTransportPassType | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportPassType | response | active | boolean | yes | (default True)
VenueOpsService | createTransportPassType | response | catalogueProductId | string (uuid) |  | The catalogue openDated product this pass is sold as. (read-only)
VenueOpsService | createTransportPassType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportRoute | request | venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | request | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | createTransportRoute | request | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | createTransportRoute | request | name | LocalisedText | yes
VenueOpsService | createTransportRoute | request | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | createTransportRoute | request | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | createTransportRoute | request | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | createTransportRoute | request | stops | array of RouteStopInput | yes | (min items 2; max items 100)
VenueOpsService | createTransportRoute | request | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | request | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | createTransportRoute | request | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | request | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | createTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | createTransportRoute | response | name | LocalisedText | yes
VenueOpsService | createTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | createTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | createTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | createTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | createTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | createTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | createTransportRoute | response | stops[].station | Station
VenueOpsService | createTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | createTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | createTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | createTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | createTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | createTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | createTransportRoute | response | statusReason | string |  | Why the route's status last changed (setTransportRouteStatus). (max length 500; read-only; nullable)
VenueOpsService | createTransportRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportStation | request | venueId | string (uuid) | yes
VenueOpsService | createTransportStation | request | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportStation | request | name | LocalisedText | yes
VenueOpsService | createTransportStation | request | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportStation | request | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportStation | request | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportStation | response | venueId | string (uuid) | yes
VenueOpsService | createTransportStation | response | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportStation | response | name | LocalisedText | yes
VenueOpsService | createTransportStation | response | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportStation | response | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportStation | response | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportStation | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportStation | response | active | boolean | yes | (default True)
VenueOpsService | createTransportStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportTimetable | request | name | string | yes | (max length 120)
VenueOpsService | createTransportTimetable | request | validFrom | string (date) | yes
VenueOpsService | createTransportTimetable | request | validTo | string (date) |  | (nullable)
VenueOpsService | createTransportTimetable | request | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | createTransportTimetable | request | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | createTransportTimetable | request | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | createTransportTimetable | request | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | createTransportTimetable | request | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createTransportTimetable | request | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | createTransportTimetable | response | name | string | yes | (max length 120)
VenueOpsService | createTransportTimetable | response | validFrom | string (date) | yes
VenueOpsService | createTransportTimetable | response | validTo | string (date) |  | (nullable)
VenueOpsService | createTransportTimetable | response | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | createTransportTimetable | response | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | createTransportTimetable | response | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | createTransportTimetable | response | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | createTransportTimetable | response | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createTransportTimetable | response | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | createTransportTimetable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportTimetable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportTimetable | response | status | TransportTimetableStatus: enum (draft, published, superseded, withdrawn) | yes
VenueOpsService | createTransportTimetable | response | publishedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | createTransportTimetable | response | releasedThrough | string (date) |  | The last date whose departures have been generated. (read-only; nullable)
VenueOpsService | createTransportTimetable | response | supersededById | string (uuid) |  | (read-only; nullable)
VenueOpsService | createTransportTimetable | param (path) | routeId | string (uuid) | yes
VenueOpsService | createTransportTimetable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createUpload | request | filename | string | yes | (max length 256)
VenueOpsService | createUpload | request | contentType | string | yes
VenueOpsService | createUpload | request | sizeBytes | integer | yes | (min 1)
VenueOpsService | createUpload | request | venueId | string (uuid)
VenueOpsService | createUpload | response | id | string (uuid) |  | Added 20 August. (read-only)
VenueOpsService | createUpload | response | uploadId | string (uuid) | yes
VenueOpsService | createUpload | response | uploadUrl | string | yes | Signed.
VenueOpsService | createUpload | response | method | enum (PUT, POST) | yes
VenueOpsService | createUpload | response | headers | object
VenueOpsService | createUpload | response | maxSizeBytes | integer
VenueOpsService | createUpload | response | expiresAt | string (date-time) | yes
VenueOpsService | createUpload | response | filename | string
VenueOpsService | createUpload | response | contentType | string
VenueOpsService | createUpload | response | sizeBytes | integer
VenueOpsService | createUpload | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createUpload | response | assetId | string (uuid) |  | The asset this upload became — created by completeUpload, or the asset whose file replaceMediaAsset swapped. (read-only; nullable)
VenueOpsService | createUpload | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createUrlRedirect | request | id | string (uuid) | yes | (read-only)
MarketingService | createUrlRedirect | request | fromPath | string | yes
MarketingService | createUrlRedirect | request | toPath | string | yes
MarketingService | createUrlRedirect | request | statusCode | enum (301, 302, 307, 308) | yes
MarketingService | createUrlRedirect | request | reason | enum (contentMigrated, pageRetired, campaignExpired, restructure, slugChanged)
MarketingService | createUrlRedirect | request | createdAt | string (date-time) |  | Taken from their whitelabel.redirect, 20 September. (read-only; nullable)
MarketingService | createUrlRedirect | request | hitCount | integer |  | (read-only)
MarketingService | createUrlRedirect | request | isActive | boolean |  | (default True)
MarketingService | createUrlRedirect | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createUrlRedirect | response | id | string (uuid) | yes | (read-only)
MarketingService | createUrlRedirect | response | fromPath | string | yes
MarketingService | createUrlRedirect | response | toPath | string | yes
MarketingService | createUrlRedirect | response | statusCode | enum (301, 302, 307, 308) | yes
MarketingService | createUrlRedirect | response | reason | enum (contentMigrated, pageRetired, campaignExpired, restructure, slugChanged)
MarketingService | createUrlRedirect | response | createdAt | string (date-time) |  | Taken from their whitelabel.redirect, 20 September. (read-only; nullable)
MarketingService | createUrlRedirect | response | hitCount | integer |  | (read-only)
MarketingService | createUrlRedirect | response | isActive | boolean |  | (default True)
MarketingService | createUrlRedirect | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createUrlRedirect | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createVenueMap | request | id | string (uuid) | yes | (read-only)
VenueOpsService | createVenueMap | request | name | string | yes
VenueOpsService | createVenueMap | request | venueId | string (uuid) | yes
VenueOpsService | createVenueMap | request | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | createVenueMap | request | kind | enum (park, floor, zone, parking)
VenueOpsService | createVenueMap | request | floorLevel | integer |  | (nullable)
VenueOpsService | createVenueMap | request | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | createVenueMap | request | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | createVenueMap | request | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | createVenueMap | request | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | createVenueMap | request | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | createVenueMap | request | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | createVenueMap | request | baseImageAlignment.imageWidthPx | integer
VenueOpsService | createVenueMap | request | baseImageAlignment.imageHeightPx | integer
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].planX | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].planY | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].imageX | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].imageY | number
VenueOpsService | createVenueMap | request | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | createVenueMap | request | boundsGeoJson | string |  | (nullable)
VenueOpsService | createVenueMap | request | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | createVenueMap | request | modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | createVenueMap | request | navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | createVenueMap | request | modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | createVenueMap | request | modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | createVenueMap | request | modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | createVenueMap | request | modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | createVenueMap | request | modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | createVenueMap | request | modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | createVenueMap | request | modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].label | string | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].x | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].z | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].lat | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].lng | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].residualMetres | number |  | Measured at import. (read-only; nullable)
VenueOpsService | createVenueMap | request | model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | createVenueMap | response | id | string (uuid) | yes | (read-only)
VenueOpsService | createVenueMap | response | name | string | yes
VenueOpsService | createVenueMap | response | venueId | string (uuid) | yes
VenueOpsService | createVenueMap | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | createVenueMap | response | kind | enum (park, floor, zone, parking)
VenueOpsService | createVenueMap | response | floorLevel | integer |  | (nullable)
VenueOpsService | createVenueMap | response | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | createVenueMap | response | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | createVenueMap | response | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | createVenueMap | response | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | createVenueMap | response | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | createVenueMap | response | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | createVenueMap | response | baseImageAlignment.imageWidthPx | integer
VenueOpsService | createVenueMap | response | baseImageAlignment.imageHeightPx | integer
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].planX | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].planY | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].imageX | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].imageY | number
VenueOpsService | createVenueMap | response | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | createVenueMap | response | boundsGeoJson | string |  | (nullable)
VenueOpsService | createVenueMap | response | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | createVenueMap | response | modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | createVenueMap | response | navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | createVenueMap | response | modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | createVenueMap | response | modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | createVenueMap | response | modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | createVenueMap | response | modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | createVenueMap | response | modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | createVenueMap | response | modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | createVenueMap | response | modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].label | string | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].x | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].z | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].lat | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].lng | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].residualMetres | number |  | Measured at import. (read-only; nullable)
VenueOpsService | createVenueMap | response | model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | createVenueMap | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideAiInsight | request | decision | enum (review, accept, reject, actioned) | yes
AiService | decideAiInsight | request | reason | string |  | (max length 1000; nullable)
AiService | decideAiInsight | request | actionRef | string |  | (nullable)
AiService | decideAiInsight | response | id | string (uuid) |  | (read-only)
AiService | decideAiInsight | response | kind | enum (anomaly, forecastDeviation, trend, opportunity, executiveSummary, rootCause, forecastThreshold, marketingRecommendation) | yes
AiService | decideAiInsight | response | detectorId | string (uuid) |  | (nullable)
AiService | decideAiInsight | response | metricKey | string |  | (nullable)
AiService | decideAiInsight | response | subjectKind | enum (campaign, journey, forecastDefinition, venue) |  | What the insight is about where it is not a KPI (29 September, build): a marketing-crm campaign or journey for marketingRecommendation, a forecast definition for forecastThreshold. (nullable)
AiService | decideAiInsight | response | subjectRef | string |  | (nullable)
AiService | decideAiInsight | response | recommendedAction | object |  | For marketingRecommendation: {recommendation, parameters} as AiMarketingRecommendation. (nullable)
AiService | decideAiInsight | response | expectedImpact | object |  | A range on a named metric (metric, low, high), never a single number (design 5.6). (nullable)
AiService | decideAiInsight | response | title | string | yes
AiService | decideAiInsight | response | narrative | string |  | (nullable)
AiService | decideAiInsight | response | evidence | array of AiEvidenceItem |  | The evidence of one decision record, stored with it.
AiService | decideAiInsight | response | evidence[].label | enum (source, derived, modelInferred) | yes
AiService | decideAiInsight | response | evidence[].kind | string | yes | What it is: feature, rule, document, metric, transaction, candidateSet.
AiService | decideAiInsight | response | evidence[].ref | string |  | Where it came from: a table and id, a document chunk, a metric key. (nullable)
AiService | decideAiInsight | response | evidence[].name | string
AiService | decideAiInsight | response | evidence[].value | object |  | (nullable)
AiService | decideAiInsight | response | evidence[].observedAt | string (date-time) |  | (nullable)
AiService | decideAiInsight | response | magnitude | number |  | (nullable)
AiService | decideAiInsight | response | priority | enum (low, medium, high, critical)
AiService | decideAiInsight | response | correlationKey | string |  | (nullable)
AiService | decideAiInsight | response | status | enum (new, reviewed, accepted, rejected, actioned, measured) | yes | (read-only)
AiService | decideAiInsight | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | decideAiInsight | response | decidedAt | string (date-time) |  | (read-only; nullable)
AiService | decideAiInsight | response | actionRef | string |  | (nullable)
AiService | decideAiInsight | response | measuredImpact | object |  | (read-only; nullable)
AiService | decideAiInsight | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | decideAiInsight | response | detectedAt | string (date-time) |  | (read-only)
AiService | decideAiInsight | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | decideAiInsight | param (path) | insightId | string (uuid) | yes
AiService | decideAiInsight | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | decideApprovalRequest | request | decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | decideApprovalRequest | request | comment | string |  | (max length 1000)
TenancyService | decideApprovalRequest | request | reason | string |  | Required on rejection. (max length 500)
TenancyService | decideApprovalRequest | request | stepUpToken | string |  | Where the rule demands MFA (11.1.60).
TenancyService | decideApprovalRequest | request | signature | string |  | 11.1.57.
TenancyService | decideApprovalRequest | response | id | string | yes
TenancyService | decideApprovalRequest | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | decideApprovalRequest | response | rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | decideApprovalRequest | response | outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | decideApprovalRequest | response | allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | decideApprovalRequest | response | reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | decideApprovalRequest | response | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | decideApprovalRequest | response | subjectContract | string
TenancyService | decideApprovalRequest | response | subjectType | string
TenancyService | decideApprovalRequest | response | subjectId | string
TenancyService | decideApprovalRequest | response | scopePath | string
TenancyService | decideApprovalRequest | response | summary | string
TenancyService | decideApprovalRequest | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | decideApprovalRequest | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | decideApprovalRequest | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | decideApprovalRequest | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | decideApprovalRequest | response | attributes | object |  | The attributes the raising contract sent (CreateApprovalRequest.attributes), stored as given (ADAM CR-172, fix round 3; CHG-CRA-005). (read-only; nullable)
TenancyService | decideApprovalRequest | response | justification | string |  | (nullable)
TenancyService | decideApprovalRequest | response | requestedByPrincipalId | string (uuid) |  | The principal who raised the request, or for whom the raising contract raised it. (nullable)
TenancyService | decideApprovalRequest | response | requestedBySubjectId | string (uuid) |  | The guest who raised the request (ADAM CR-101; CHG-R10ID-016), set by the server from the guest session; null for a request a principal raised. (read-only; nullable)
TenancyService | decideApprovalRequest | response | matrixVersion | integer
TenancyService | decideApprovalRequest | response | mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | decideApprovalRequest | response | currentLevel | integer
TenancyService | decideApprovalRequest | response | totalLevels | integer
TenancyService | decideApprovalRequest | response | approvers | array of object |  | The approver chain, fixed when the request is routed (ADAM CR-102, option 1, accepted 15 October 2026; CHG-R10ID-015). (read-only)
TenancyService | decideApprovalRequest | response | approvers[].level | integer | yes | The level of the chain this approver decides at. (min 1)
TenancyService | decideApprovalRequest | response | approvers[].principalId | string (uuid) | yes | The approver, a principal of the tenant.
TenancyService | decideApprovalRequest | response | approvers[].isDelegate | boolean | yes | True when the approver stands in for another through an ApprovalDelegation in force at routing.
TenancyService | decideApprovalRequest | response | pendingApprovers | array of object |  | The rows of approvers at currentLevel who have not decided yet, with their names; derived, not stored (CHG-R10ID-015).
TenancyService | decideApprovalRequest | response | pendingApprovers[].principalId | string (uuid)
TenancyService | decideApprovalRequest | response | pendingApprovers[].displayName | string
TenancyService | decideApprovalRequest | response | pendingApprovers[].isDelegate | boolean
TenancyService | decideApprovalRequest | response | decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | decideApprovalRequest | response | decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | decideApprovalRequest | response | decisions[].level | integer | yes
TenancyService | decideApprovalRequest | response | decisions[].principalId | string (uuid) |  | The approver; null when an external workflow system decided (externalApproverRef set). (nullable)
TenancyService | decideApprovalRequest | response | decisions[].externalApproverRef | string |  | Who decided in the external provider's system, as it named them (recordExternalApprovalDecision); null for an internal approver (CHG-R8MIG-009). (nullable)
TenancyService | decideApprovalRequest | response | decisions[].externalApproverName | string |  | The external approver's display name, where the provider sent one (CHG-R8MIG-009). (max length 200; nullable)
TenancyService | decideApprovalRequest | response | decisions[].displayName | string
TenancyService | decideApprovalRequest | response | decisions[].isDelegate | boolean
TenancyService | decideApprovalRequest | response | decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].decision | enum (approve, reject, return, requestInformation) | yes | return and requestInformation are stored as decisions too, their comment in comment (decideApprovalRequest; CHG-R8MIG-009).
TenancyService | decideApprovalRequest | response | decisions[].comment | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].reason | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].usedMfa | boolean
TenancyService | decideApprovalRequest | response | decisions[].signatureRef | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].decidedAt | string (date-time) | yes
TenancyService | decideApprovalRequest | response | escalations | array of object |  | 11.1.48.
TenancyService | decideApprovalRequest | response | escalations[].at | string (date-time) | yes
TenancyService | decideApprovalRequest | response | escalations[].reason | string |  | The requester's or approver's reason; for an automatic escalation, the SLA rule that fired. (max length 300)
TenancyService | decideApprovalRequest | response | escalations[].fromLevel | integer
TenancyService | decideApprovalRequest | response | escalations[].toLevel | integer | yes
TenancyService | decideApprovalRequest | response | escalations[].wasAutomatic | boolean | yes
TenancyService | decideApprovalRequest | response | escalations[].escalatedByPrincipalId | string (uuid) |  | Who escalated it by hand (escalateApprovalRequest's caller); null for an automatic one. (nullable)
TenancyService | decideApprovalRequest | response | escalations[].addedApproverPrincipalId | string (uuid) |  | The approver the escalation added at toLevel; the original approver stays in the chain. (nullable)
TenancyService | decideApprovalRequest | response | resubmittedFromId | string |  | (nullable)
TenancyService | decideApprovalRequest | response | reopenedFromId | string |  | (nullable)
TenancyService | decideApprovalRequest | response | slaDueAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | slaBreached | boolean
TenancyService | decideApprovalRequest | response | expiresAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | assignedToPrincipalId | string (uuid) |  | Who claimed or was assigned the request in a shared queue (assignApprovalRequest; DI-723; CHG-CSP-042). (read-only; nullable)
TenancyService | decideApprovalRequest | response | assignedToDepartmentId | string (uuid) |  | The department queue it was assigned to, where it went to a department rather than a person (CHG-CSP-042). (read-only; nullable)
TenancyService | decideApprovalRequest | response | assignedAt | string (date-time) |  | (read-only; nullable)
TenancyService | decideApprovalRequest | response | assignmentNote | string |  | The note assignApprovalRequest was given, kept with the assignment (R8 blocker APPROVALS-TENANCY-C02, CHG-R8MIG-009). (max length 500; read-only; nullable)
TenancyService | decideApprovalRequest | response | approvalMatrixId | string (uuid) |  | The matrix routing chose at submit (with matrixVersion), so a decision is checked against the matrix the request was routed by (CHG-R8MIG-009). (read-only; nullable)
TenancyService | decideApprovalRequest | response | ruleId | string (uuid) |  | The matrix rule that matched on kind, scope, amount and attributes (CHG-R8MIG-009). (read-only; nullable)
TenancyService | decideApprovalRequest | response | cancelReason | string |  | Why the request was cancelled, as cancelApprovalRequest was given it (CHG-R8MIG-009). (max length 500; read-only; nullable)
TenancyService | decideApprovalRequest | response | requestedAt | string (date-time) | yes
TenancyService | decideApprovalRequest | response | completedAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | decideApprovalRequest | response | aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | decideApprovalRequest | response | aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion.action | enum (escalate, addBackupApprover, none)
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion.reason | string |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].code | string
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].contribution | number
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].detail | string |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | decideApprovalRequest | response | aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | decideApprovalRequest | response | aiAssessment.assessedAt | string (date-time)
TenancyService | decideApprovalRequest | param (path) | requestId | string (uuid) | yes
TenancyService | decideApprovalRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideOperationalRequirement | request | decision | enum (accept, modify, reject) | yes
AiService | decideOperationalRequirement | request | quantity | number |  | (nullable)
AiService | decideOperationalRequirement | request | note | string |  | (max length 1000; nullable)
AiService | decideOperationalRequirement | response | id | string (uuid) |  | (read-only)
AiService | decideOperationalRequirement | response | versionId | string (uuid) | yes
AiService | decideOperationalRequirement | response | kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …) | yes
AiService | decideOperationalRequirement | response | targetContract | string |  | The owning module that applies it: workforce, fnb, inventory, resources, access.
AiService | decideOperationalRequirement | response | subjectRef | string |  | A role, outlet, gate, item or resource type. (nullable)
AiService | decideOperationalRequirement | response | periodStart | string (date-time) | yes
AiService | decideOperationalRequirement | response | periodEnd | string (date-time)
AiService | decideOperationalRequirement | response | quantity | number | yes
AiService | decideOperationalRequirement | response | quantityP90 | number |  | The requirement at the forecast's 90th percentile, for planning to the busy case. (nullable)
AiService | decideOperationalRequirement | response | unit | string
AiService | decideOperationalRequirement | response | productivityStandard | object |  | The standard used, e.g. (nullable)
AiService | decideOperationalRequirement | response | status | enum (issued, accepted, modified, rejected, handedOver, expired) |  | (read-only)
AiService | decideOperationalRequirement | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | decideOperationalRequirement | response | decidedAt | string (date-time) |  | (read-only; nullable)
AiService | decideOperationalRequirement | response | decisionNote | string |  | (nullable)
AiService | decideOperationalRequirement | response | handoverRef | string |  | The owning module's record once handed over. (read-only; nullable)
AiService | decideOperationalRequirement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | decideOperationalRequirement | param (path) | requirementId | string (uuid) | yes
AiService | decideOperationalRequirement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | decidePricingRecommendation | request | decision | enum (accept, modify, reject, schedule, sendForApproval) | yes
CatalogueService | decidePricingRecommendation | request | rejectionReason | enum (commercialJudgment, brandPositioning, customerSensitivity, eventStrategy, incorrectSignal, dataConcern, other) |  | Required for reject.
CatalogueService | decidePricingRecommendation | request | rejectionNote | string |  | (max length 2000)
CatalogueService | decidePricingRecommendation | request | humanSelectedPrice | object |  | Required for modify; must sit inside the strategy's guardrails.
CatalogueService | decidePricingRecommendation | request | humanSelectedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | decidePricingRecommendation | request | humanSelectedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | decidePricingRecommendation | request | humanSelectedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | decidePricingRecommendation | request | scheduledFor | string (date-time) |  | Required for schedule; in the future.
CatalogueService | decidePricingRecommendation | response | id | string (uuid) | yes | (read-only)
CatalogueService | decidePricingRecommendation | response | recommendationId | string (uuid) | yes | A catalogue.pricing_recommendation (29 September, data model DM3).
CatalogueService | decidePricingRecommendation | response | decision | enum (accept, modify, reject, schedule, sendForApproval) | yes
CatalogueService | decidePricingRecommendation | response | rejectionReason | enum (commercialJudgment, brandPositioning, customerSensitivity, eventStrategy, incorrectSignal, dataConcern, other, None) |  | (nullable)
CatalogueService | decidePricingRecommendation | response | rejectionNote | string |  | (nullable)
CatalogueService | decidePricingRecommendation | response | recommendedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | decidePricingRecommendation | response | recommendedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | decidePricingRecommendation | response | recommendedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | decidePricingRecommendation | response | recommendedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | decidePricingRecommendation | response | humanSelectedPrice | object |  | (nullable)
CatalogueService | decidePricingRecommendation | response | humanSelectedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | decidePricingRecommendation | response | humanSelectedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | decidePricingRecommendation | response | humanSelectedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | decidePricingRecommendation | response | scheduledFor | string (date-time) |  | (nullable)
CatalogueService | decidePricingRecommendation | response | approvalRequestId | string (uuid) |  | The approvals request opened by sendForApproval. (nullable)
CatalogueService | decidePricingRecommendation | response | executionId | string |  | The createLiveDynamicPrice execution that carried it out, once it has. (read-only; nullable)
CatalogueService | decidePricingRecommendation | response | decidedByPrincipalId | string (uuid) | yes | (read-only)
CatalogueService | decidePricingRecommendation | response | decidedAt | string (date-time) | yes | (read-only)
CatalogueService | decidePricingRecommendation | response | scopePath | string |  | (read-only)
CatalogueService | decidePricingRecommendation | param (path) | recommendationId | string | yes | The queue item (AiRecommendationReviewDecisionQueueView.recommendationId).
CatalogueService | decidePricingRecommendation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | decideProductionAccess | request | decision | enum (approve, reject) | yes
PlatformService | decideProductionAccess | request | reason | string |  | (max length 1000; nullable)
PlatformService | decideProductionAccess | request | scopes | array of string |  | Narrow the requested scopes.
PlatformService | decideProductionAccess | request | credentialTtlDays | integer |  | (min 1; max 730; default 365)
PlatformService | decideProductionAccess | response | id | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | developerId | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | sandboxClientId | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | listingId | string (uuid) | yes
PlatformService | decideProductionAccess | response | scopes | array of string
PlatformService | decideProductionAccess | response | allowedTenantIds | array of string (uuid)
PlatformService | decideProductionAccess | response | ipAllowList | array of string
PlatformService | decideProductionAccess | response | note | string |  | (nullable)
PlatformService | decideProductionAccess | response | status | enum (pending, approved, rejected, withdrawn) | yes | (read-only)
PlatformService | decideProductionAccess | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | decidedAt | string (date-time) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | reason | string |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | productionClientId | string (uuid) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | requestedAt | string (date-time) |  | (read-only)
PlatformService | decideProductionAccess | param (path) | requestId | string (uuid) | yes
PlatformService | decideProductionAccess | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideProposedAction | request | decision | enum (approve, reject) | yes
AiService | decideProposedAction | request | reason | string |  | (max length 500)
AiService | decideProposedAction | response | id | string (uuid) | yes
AiService | decideProposedAction | response | interactionId | string (uuid)
AiService | decideProposedAction | response | translationJobId | string (uuid) |  | The proposeTranslations job that drafted this proposal; getTranslationProposals reads a job's rows by it. (read-only; nullable)
AiService | decideProposedAction | response | targetKind | enum (contentBlock, productName, emailTemplate, messageTemplate) |  | For a translation draft, what kind of thing it sits on (TranslationProposals.drafts[].targetKind); null on every other proposal (R8 blocker FOUNDATION-AI-C40). (read-only; nullable)
AiService | decideProposedAction | response | targetRef | string |  | For a translation draft, the id of the block, product or template it sits on (the path id of the target's own write, e.g. (max length 200; read-only; nullable)
AiService | decideProposedAction | response | locale | string |  | For a translation draft, the language it is in (the job's targetLocale); null otherwise. (max length 20; read-only; nullable)
AiService | decideProposedAction | response | fieldPath | string |  | For a translation draft, where it goes inside the target, as a dotted path in the target's own body (TranslationProposals.drafts[].fieldPath); null otherwise. (max length 300; read-only; nullable)
AiService | decideProposedAction | response | draftText | string |  | For a translation draft, the proposed text; null otherwise. (read-only; nullable)
AiService | decideProposedAction | response | confidence | number |  | For a walkway segment (proposeWalkways), the model's confidence in it (WalkwayProposal.confidence); null on every other proposal (ADAM CR-207, CHG-R10ORD-013). (min 0; max 1; read-only; nullable)
AiService | decideProposedAction | response | basis | enum (handMarked, seen) |  | For a walkway segment, whether it was traced from a hand mark or seen in the picture (WalkwayProposal.basis); null otherwise (ADAM CR-207). (read-only; nullable)
AiService | decideProposedAction | response | reasoning | string |  | For a walkway segment, why the model proposed it (WalkwayProposal.reasoning); null otherwise (ADAM CR-207). (read-only; nullable)
AiService | decideProposedAction | response | distanceMetres | number |  | For a walkway segment, its length along the centreline; null where the plan has no georeference and on every other proposal (ADAM CR-207). (read-only; nullable)
AiService | decideProposedAction | response | mapId | string (uuid) |  | For a walkway segment, the venue map it is on (the path's mapId, which the target's request body does not carry); null otherwise (ADAM CR-207). (read-only; nullable)
AiService | decideProposedAction | response | kind | enum (pricing, promotion, operational, financial, configuration, content, audience) | yes | content (a marketing or storefront draft from proposeMarketingContent) and audience (a lookalike segment from proposeLookalikeSegment) added 29 September (build); both are applied by a person in the…
AiService | decideProposedAction | response | targetContract | string | yes | Which contract would perform it.
AiService | decideProposedAction | response | targetOperation | string | yes
AiService | decideProposedAction | response | payload | object | yes | The request body a person would submit, ready to review.
AiService | decideProposedAction | response | summary | string
AiService | decideProposedAction | response | status | enum (proposed, approved, rejected, applied, expired) | yes | Expiry (decided 28 September, audit R213): a proposed action expires 7 days after proposedAt; an approved action not applied expires 24 hours after decidedAt.
AiService | decideProposedAction | response | expiresAt | string (date-time) |  | When the expiry timer moves this action to expired — proposedAt plus 7 days while proposed, decidedAt plus 24 hours once approved, null once rejected, applied or expired (audit R213). (read-only; nullable)
AiService | decideProposedAction | response | approvalLevel | integer |  | 8.3.65. (min 1; max 2)
AiService | decideProposedAction | response | decidedByPrincipalId | string (uuid) |  | (nullable)
AiService | decideProposedAction | response | decisionReason | string |  | Required on rejection. (nullable)
AiService | decideProposedAction | response | proposedAt | string (date-time)
AiService | decideProposedAction | response | decidedAt | string (date-time) |  | (nullable)
AiService | decideProposedAction | response | scopePath | string |  | Added 29 September (AI design 3.1): ai.proposed_action had no policy — its only references were nullable. (read-only)
AiService | decideProposedAction | response | planId | string (uuid) |  | The plan this action presents for a decision (AI design 2.2 D, 3.8). (read-only; nullable)
AiService | decideProposedAction | response | approvalRequestId | string (uuid) |  | The approvals request deciding a tier 2 or matrix-caught action (AI design 2.3). (read-only; nullable)
AiService | decideProposedAction | response | changeSetHash | string |  | Hash of the change set approved; execution refuses a plan whose hash differs (AIC-181). (read-only; nullable)
AiService | decideProposedAction | param (path) | actionId | string (uuid) | yes
AiService | decideProposedAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideRecommendations | request | placement | enum (productPage, cart, checkout, postPurchase, preVisit, inVenue, posBasket, kioskBasket, …) | yes
AiService | decideRecommendations | request | channel | string | yes
AiService | decideRecommendations | request | cartId | string (uuid) |  | (nullable)
AiService | decideRecommendations | request | productId | string (uuid) |  | The product in view, for a product-page placement. (nullable)
AiService | decideRecommendations | request | subjectId | string (uuid) |  | Known customer, where signed in. (nullable)
AiService | decideRecommendations | request | sessionRef | string |  | (nullable)
AiService | decideRecommendations | request | previewOnly | boolean |  | A staff preview that records nothing (contract gap CHG-WIR-014, BO-102; CHG-CSA-045): the slot is filled as a guest would see it, but no impression, tracking id or decision record is written. (default False)
AiService | decideRecommendations | request | maxItems | integer |  | (min 1; max 12; default 4)
AiService | decideRecommendations | request | locale | string |  | (nullable)
AiService | decideRecommendations | request | itemKinds | array of enum (upsell, crossSell, upgrade, bundle, addOn, membership, nextBestOffer, offer, …) |  | Only these kinds may fill the slot (29 September, build).
AiService | decideRecommendations | request | portfolioScope | boolean |  | Also consider the entitlements of the people the guest may act for under a delegated access (CF-132 household), not only their own (5.5.30). (default False)
AiService | decideRecommendations | response | decisionId | string (uuid) | yes
AiService | decideRecommendations | response | placement | enum (productPage, cart, checkout, postPurchase, preVisit, inVenue, posBasket, kioskBasket, …)
AiService | decideRecommendations | response | mode | enum (personalised, contextual, rulesOnly, fallback) | yes
AiService | decideRecommendations | response | items | array of AiRecommendationItem | yes
AiService | decideRecommendations | response | items[].trackingId | string (uuid) | yes | Echoed on every recordRecommendationEvents event and as orders.addCartLine.recommendationId, so attribution never guesses.
AiService | decideRecommendations | response | items[].productId | string (uuid) |  | The product recommended. (nullable)
AiService | decideRecommendations | response | items[].variantId | string (uuid) |  | What the guest adds to the cart, when there is nothing to choose (r8, ORDERS-MONEY-C40, the lead's option A): for a product item whose product has one default variant, that variant, resolved from the… (nullable)
AiService | decideRecommendations | response | items[].performanceId | string (uuid) |  | For a timed product with exactly one bookable performance in the context the engine was given (the cart's date), that performance (r8, ORDERS-MONEY-C40); otherwise null and the screen asks for the da… (nullable)
AiService | decideRecommendations | response | items[].promotionId | string (uuid) |  | For offer, a published promotion the guest is eligible for. (nullable)
AiService | decideRecommendations | response | items[].couponRef | string |  | For offer, a coupon campaign; a code is assigned only when the guest takes it (promotions.assignCoupon). (nullable)
AiService | decideRecommendations | response | items[].rewardId | string (uuid) |  | For reward, a marketing-crm loyalty reward the guest can redeem. (nullable)
AiService | decideRecommendations | response | items[].challengeId | string (uuid) |  | For challenge, a marketing-crm challenge the guest can join. (nullable)
AiService | decideRecommendations | response | items[].kind | enum (upsell, crossSell, upgrade, bundle, addOn, membership, nextBestOffer, offer, …)
AiService | decideRecommendations | response | items[].rank | integer | yes | (min 1)
AiService | decideRecommendations | response | items[].priceRef | string |  | The Pricing reference the channel resolves to a price. (nullable)
AiService | decideRecommendations | response | items[].reasonTemplateKey | string |  | The template reason (decided 29 September, decision 9): no model writes guest-visible reasons. (nullable)
AiService | decideRecommendations | response | items[].reasonText | string |  | The rendered template in the session locale, where the channel shows reasons. (nullable)
AiService | decideRecommendations | response | items[].confidenceBand | enum (high, medium, low) |  | Design 5.6: a band, never a bare percentage.
AiService | decideRecommendations | response | items[].score | number |  | Normalised score. (nullable)
AiService | decideRecommendations | response | expiresAt | string (date-time) | yes
AiService | decideRecommendations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | deleteAccessPointGroup | param (path) | groupId | string (uuid) | yes
AccessService | deleteAccessPointGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteBanner | param (path) | bannerId | string (uuid) | yes
WhiteLabelService | deleteBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | deleteBookingFlow | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteContentPage | param (path) | pageId | string (uuid) | yes
WhiteLabelService | deleteContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | deleteDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | deleteDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | deleteFavouriteRoute | param (path) | favouriteId | string (uuid) | yes
VenueOpsService | deleteFavouriteRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | deleteGuestAccount | response | requestId | string | yes | The approvals.request id of the erasure request (raised through Approvals' createApprovalRequest), which the tombstone records as pii.subject.erasure_request_id.
IdentityService | deleteGuestAccount | response | estimatedCompletionAt | string (date-time) |  | Null until a response period reaches Identity. (nullable)
IdentityService | deleteGuestAccount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | deleteGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | deleteMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | deleteMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deletePromoBlock | param (path) | promoBlockId | string (uuid) | yes
WhiteLabelService | deletePromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | deleteReport | param (path) | reportId | string (uuid) | yes
ReportingService | deleteReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | deprecateApiVersion | request | sunsetAt | string (date-time) | yes
PlatformService | deprecateApiVersion | request | reason | string | yes
PlatformService | deprecateApiVersion | request | migrationGuideUrl | string |  | (nullable)
PlatformService | deprecateApiVersion | response | version | string | yes
PlatformService | deprecateApiVersion | response | status | enum (preview, current, deprecated, sunset) | yes
PlatformService | deprecateApiVersion | response | releasedAt | string (date-time)
PlatformService | deprecateApiVersion | response | deprecatedAt | string (date-time) |  | (nullable)
PlatformService | deprecateApiVersion | response | sunsetAt | string (date-time) |  | (nullable)
PlatformService | deprecateApiVersion | response | minimumNoticeMonths | integer |  | The commitment, not the intention. (default 12)
PlatformService | deprecateApiVersion | response | migrationGuideUrl | string |  | (nullable)
PlatformService | deprecateApiVersion | response | activeClientCount | integer |  | (read-only)
PlatformService | deprecateApiVersion | response | changes | array of object |  | The developer changelog for this version (17 September minutes, M17-14): every operation added, changed, deprecated or removed, and whether the change is breaking under ADR-0026.
PlatformService | deprecateApiVersion | response | changes[].operationId | string | yes
PlatformService | deprecateApiVersion | response | changes[].contract | string
PlatformService | deprecateApiVersion | response | changes[].kind | enum (added, changed, deprecated, removed) | yes
PlatformService | deprecateApiVersion | response | changes[].breaking | boolean |  | (default False)
PlatformService | deprecateApiVersion | response | changes[].summary | string
PlatformService | deprecateApiVersion | param (path) | version | string | yes
PlatformService | deprecateApiVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | diffConfigVersion | response | fromVersion | string | yes
WhiteLabelService | diffConfigVersion | response | toVersion | string | yes
WhiteLabelService | diffConfigVersion | response | affectedProducts | array of object |  | The products served by a booking flow that differs between the two versions (area bookingFlows in changes), by the product-to-flow rule of Product.bookingFlowId. (read-only)
WhiteLabelService | diffConfigVersion | response | affectedProducts[].productId | string (uuid) | yes
WhiteLabelService | diffConfigVersion | response | affectedProducts[].name | string | yes
WhiteLabelService | diffConfigVersion | response | affectedProducts[].flowKey | string | yes | The changed flow that serves this product.
WhiteLabelService | diffConfigVersion | response | changes | array of object | yes
WhiteLabelService | diffConfigVersion | response | changes[].area | string | yes
WhiteLabelService | diffConfigVersion | response | changes[].path | string | yes
WhiteLabelService | diffConfigVersion | response | changes[].changeKind | enum (added, removed, modified) | yes
WhiteLabelService | diffConfigVersion | response | changes[].before | string |  | (nullable)
WhiteLabelService | diffConfigVersion | response | changes[].after | string |  | (nullable)
WhiteLabelService | diffConfigVersion | response | changes[].changeScope | ChangeScope: enum (runtime, buildTime) |  | Whether a change reaches guests on publish or needs a store release.
WhiteLabelService | diffConfigVersion | param (path) | version | string | yes
WhiteLabelService | diffConfigVersion | param (query) | against | string |  | Another version.
CatalogueService | editSeatMapStructure | request | addSections | array of object
CatalogueService | editSeatMapStructure | request | addSections[].code | string | yes | (max length 20)
CatalogueService | editSeatMapStructure | request | addSections[].name | string | yes | (max length 100)
CatalogueService | editSeatMapStructure | request | addSections[].boundary | array of Point
CatalogueService | editSeatMapStructure | request | addSections[].boundary[].x | number | yes
CatalogueService | editSeatMapStructure | request | addSections[].boundary[].y | number | yes
CatalogueService | editSeatMapStructure | request | addRows | array of object
CatalogueService | editSeatMapStructure | request | addRows[].sectionCode | string | yes
CatalogueService | editSeatMapStructure | request | addRows[].label | string | yes | (max length 10)
CatalogueService | editSeatMapStructure | request | addRows[].seatCount | integer | yes | (min 1; max 500)
CatalogueService | editSeatMapStructure | request | addRows[].firstSeatNumber | integer |  | (min 0; default 1)
CatalogueService | editSeatMapStructure | request | addRows[].numberingDirection | enum (leftToRight, rightToLeft) |  | (default leftToRight)
CatalogueService | editSeatMapStructure | request | addRows[].start | Point
CatalogueService | editSeatMapStructure | request | addRows[].start.x | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].start.y | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].end | Point
CatalogueService | editSeatMapStructure | request | addRows[].end.x | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].end.y | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].curveRadius | number |  | Null or absent for a straight row. (nullable)
CatalogueService | editSeatMapStructure | request | addRows[].categoryId | string (uuid) |  | (nullable)
CatalogueService | editSeatMapStructure | request | addSeats | array of object
CatalogueService | editSeatMapStructure | request | addSeats[].sectionCode | string | yes
CatalogueService | editSeatMapStructure | request | addSeats[].rowLabel | string | yes
CatalogueService | editSeatMapStructure | request | addSeats[].seatNumber | string | yes
CatalogueService | editSeatMapStructure | request | addSeats[].position | Point
CatalogueService | editSeatMapStructure | request | addSeats[].position.x | number | yes
CatalogueService | editSeatMapStructure | request | addSeats[].position.y | number | yes
CatalogueService | editSeatMapStructure | request | addSeats[].categoryId | string (uuid) |  | (nullable)
CatalogueService | editSeatMapStructure | request | addSeats[].attribute | SeatAttribute: enum (standard, accessible, companion, obstructedView, restrictedLegroom, premium, houseSeat, buffer, …) |  | BL-168.
CatalogueService | editSeatMapStructure | request | removeSeatIds | array of string (uuid)
CatalogueService | editSeatMapStructure | request | relabel | array of object
CatalogueService | editSeatMapStructure | request | relabel[].seatId | string (uuid) | yes
CatalogueService | editSeatMapStructure | request | relabel[].sectionCode | string
CatalogueService | editSeatMapStructure | request | relabel[].rowLabel | string
CatalogueService | editSeatMapStructure | request | relabel[].seatNumber | string
CatalogueService | editSeatMapStructure | response | sectionsAdded | integer
CatalogueService | editSeatMapStructure | response | seatsAdded | integer
CatalogueService | editSeatMapStructure | response | seatsRemoved | integer
CatalogueService | editSeatMapStructure | response | seatsRelabelled | integer
CatalogueService | editSeatMapStructure | param (path) | seatMapId | string (uuid) | yes
CatalogueService | editSeatMapStructure | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | editSeatMapStructure | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
AccessService | enrolFacePass | request | subjectId | string (uuid) | yes
AccessService | enrolFacePass | request | entitlementId | string (uuid) | yes | An Entitlement.id, which is a UUIDv7.
AccessService | enrolFacePass | request | template | string (password) | yes | Write-only, never returned.
AccessService | enrolFacePass | request | capturedAt | string (date-time) | yes
AccessService | enrolFacePass | request | source | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk) | yes | The three surfaces 3.2.43 allows, and the self-service kiosk since 2 October 2026 (Chinmay, BO-186; DEC-236; CHG-CSP-021): a kiosk shows the venue's consent form on its screen and enrols only where t…
AccessService | enrolFacePass | request | consent | object | yes
AccessService | enrolFacePass | request | consent.purposeId | string (uuid) | yes
AccessService | enrolFacePass | request | consent.givenAt | string (date-time) | yes
AccessService | enrolFacePass | request | consent.consentFormId | string (uuid) |  | The venue's consent form accepted (DEC-128; CHG-CSP-018). (nullable)
AccessService | enrolFacePass | request | consent.consentFormVersion | integer |  | The version of that form shown (CHG-CSP-018). (min 1; nullable)
AccessService | enrolFacePass | request | consent.guardianSubjectId | string (uuid) |  | Required where the subject is a minor. (nullable)
AccessService | enrolFacePass | request | consent.guardianRelationship | string |  | (nullable)
AccessService | enrolFacePass | request | reasonForReEnrollment | enum (appearanceChange, poorOriginalCapture, technicalIssue, guestRequest, recovery, other) |  | Required when the subject already has a Face Pass: why the face is being enrolled again (decided 29 September, writers pass) (nullable)
AccessService | enrolFacePass | response | id | string (uuid) | yes | (read-only)
AccessService | enrolFacePass | response | subjectId | string (uuid) | yes
AccessService | enrolFacePass | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | enrolFacePass | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | enrolFacePass | response | retentionAnchor | object |  | BL-106.
AccessService | enrolFacePass | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | enrolFacePass | response | enrolmentChannel | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk, entryGate) |  | Where the face was actually captured (decided 2 October 2026, Chinmay, BO-186; DEC-236; CHG-CSP-021): source with selfServiceKiosk told apart. (read-only)
AccessService | enrolFacePass | response | consentFormId | string (uuid) |  | The venue's consent form the capture was consented on, and its version below (DEC-128; CHG-CSP-018). (read-only; nullable)
AccessService | enrolFacePass | response | consentFormVersion | integer |  | (read-only; nullable)
AccessService | enrolFacePass | response | capturedAt | string (date-time) | yes
AccessService | enrolFacePass | response | consentPurposeId | string (uuid)
AccessService | enrolFacePass | response | consentGivenAt | string (date-time)
AccessService | enrolFacePass | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFacePass | response | isActive | boolean |  | (read-only)
AccessService | enrolFacePass | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | enrolFacePass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | enrolFaceTag | request | subjectId | string (uuid) | yes
AccessService | enrolFaceTag | request | entitlementId | string (uuid) | yes | An Entitlement.id, which is a UUIDv7.
AccessService | enrolFaceTag | request | template | string (password) | yes | Write-only, never returned.
AccessService | enrolFaceTag | request | capturedAt | string (date-time) | yes
AccessService | enrolFaceTag | request | source | enum (ticketCounter, entryGate) | yes | The two surfaces 3.2.44 allows, and a gate is present here exactly where it is absent from Face Pass: this one does not outlive the visit.
AccessService | enrolFaceTag | request | consent | object | yes | Per-visit rather than enduring, and still explicit.
AccessService | enrolFaceTag | request | consent.purposeId | string (uuid) | yes
AccessService | enrolFaceTag | request | consent.method | enum (onScreenAcknowledgement, signedForm) |  | How the guest consented (added 29 September, build pass, 3.2.44). (default onScreenAcknowledgement)
AccessService | enrolFaceTag | request | consent.givenAt | string (date-time) | yes
AccessService | enrolFaceTag | request | consent.consentFormId | string (uuid) |  | The venue's consent form the guest accepted (VenueSettings.biometrics.consentFormId; DEC-128; CHG-CSP-018). (nullable)
AccessService | enrolFaceTag | request | consent.consentFormVersion | integer |  | The version of that form shown (CHG-CSP-018). (min 1; nullable)
AccessService | enrolFaceTag | request | consent.guardianSubjectId | string (uuid) |  | Required where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFaceTag | request | consent.guardianRelationship | string |  | (nullable)
AccessService | enrolFaceTag | response | id | string (uuid) | yes | (read-only)
AccessService | enrolFaceTag | response | subjectId | string (uuid) | yes
AccessService | enrolFaceTag | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | enrolFaceTag | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | enrolFaceTag | response | retentionAnchor | object |  | BL-106.
AccessService | enrolFaceTag | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | enrolFaceTag | response | enrolmentChannel | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk, entryGate) |  | Where the face was actually captured (decided 2 October 2026, Chinmay, BO-186; DEC-236; CHG-CSP-021): source with selfServiceKiosk told apart. (read-only)
AccessService | enrolFaceTag | response | consentFormId | string (uuid) |  | The venue's consent form the capture was consented on, and its version below (DEC-128; CHG-CSP-018). (read-only; nullable)
AccessService | enrolFaceTag | response | consentFormVersion | integer |  | (read-only; nullable)
AccessService | enrolFaceTag | response | capturedAt | string (date-time) | yes
AccessService | enrolFaceTag | response | consentPurposeId | string (uuid)
AccessService | enrolFaceTag | response | consentGivenAt | string (date-time)
AccessService | enrolFaceTag | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFaceTag | response | isActive | boolean |  | (read-only)
AccessService | enrolFaceTag | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | enrolFaceTag | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | enrolMfaMethod | request | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | enrolMfaMethod | request | target | string |  | Phone or email for OTP methods.
IdentityService | enrolMfaMethod | response | id | string (uuid) |  | Added 20 August. (read-only)
IdentityService | enrolMfaMethod | response | methodId | string (uuid) | yes
IdentityService | enrolMfaMethod | response | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | enrolMfaMethod | response | secret | string |  | TOTP shared secret. (nullable)
IdentityService | enrolMfaMethod | response | qrCodeUri | string |  | (nullable)
IdentityService | enrolMfaMethod | response | recoveryCodes | array of string |  | Returned once, in this enrolment response (enrolMfaMethod writes them, hashed, to identity.mfa_recovery_code).
IdentityService | enrolMfaMethod | response | expiresAt | string (date-time)
IdentityService | enrolMfaMethod | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | enterWaitingRoom | response | waitingEntryId | string (uuid) | yes | A UUIDv7 minted on arrival; what the waiting page polls with.
CatalogueService | enterWaitingRoom | response | performanceId | string (uuid) | yes
CatalogueService | enterWaitingRoom | response | state | enum (notRequired, waiting, admitted, expired, closed) | yes | notRequired: the room is off, go to the sale.
CatalogueService | enterWaitingRoom | response | position | integer |  | Place in the room; null unless waiting. (min 1; nullable)
CatalogueService | enterWaitingRoom | response | aheadOfYou | integer |  | (min 0; nullable)
CatalogueService | enterWaitingRoom | response | estimatedWaitSeconds | integer |  | At the current release rate. (min 0; nullable)
CatalogueService | enterWaitingRoom | response | pollAfterSeconds | integer |  | (min 1; default 5)
CatalogueService | enterWaitingRoom | response | admission | object |  | Set when state is admitted. (nullable)
CatalogueService | enterWaitingRoom | response | admission.token | string | yes | The signed token, opaque to the client.
CatalogueService | enterWaitingRoom | response | admission.tokenId | string (uuid) |  | The token's unique id.
CatalogueService | enterWaitingRoom | response | admission.performanceId | string (uuid) | yes
CatalogueService | enterWaitingRoom | response | admission.expiresAt | string (date-time) | yes
CatalogueService | enterWaitingRoom | param (path) | performanceId | string (uuid) | yes
CatalogueService | enterWaitingRoom | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | escalateCorrectiveAction | response | id | string (uuid) | yes
FnbService | escalateCorrectiveAction | response | raisedAt | string (date-time) | yes
FnbService | escalateCorrectiveAction | response | raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | escalateCorrectiveAction | response | source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | escalateCorrectiveAction | response | sourceRef | string (uuid) |  | (nullable)
FnbService | escalateCorrectiveAction | response | severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | escalateCorrectiveAction | response | actionTaken | string |  | (nullable)
FnbService | escalateCorrectiveAction | response | disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | escalateCorrectiveAction | response | status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | escalateCorrectiveAction | response | signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | escalateCorrectiveAction | response | signedAt | string (date-time) |  | (nullable)
FnbService | escalateCorrectiveAction | response | escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | escalateCorrectiveAction | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | escalateCorrectiveAction | param (path) | actionId | string (uuid) | yes
FnbService | escalateCorrectiveAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | evaluateAiGovernance | request | capabilityKey | string | yes
AiService | evaluateAiGovernance | request | action | enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) | yes
AiService | evaluateAiGovernance | request | scopePath | string |  | (nullable)
AiService | evaluateAiGovernance | request | principalId | string (uuid) |  | (nullable)
AiService | evaluateAiGovernance | request | dataCategories | array of string
AiService | evaluateAiGovernance | request | amount | object |  | (nullable)
AiService | evaluateAiGovernance | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | evaluateAiGovernance | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | evaluateAiGovernance | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | evaluateAiGovernance | request | toolKey | string |  | (nullable)
AiService | evaluateAiGovernance | response | outcome | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | evaluateAiGovernance | response | policyVersion | string | yes
AiService | evaluateAiGovernance | response | autonomyLevel | integer |  | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | evaluateAiGovernance | response | conditions | object |  | (nullable)
AiService | evaluateAiGovernance | response | requiredApprovalTier | integer |  | (min 1; max 2; nullable)
AiService | evaluateAiGovernance | response | explanation | string
AiService | evaluateAiGovernance | response | decisionRecordId | string (uuid) |  | (nullable)
AiService | evaluateAiGovernance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | evaluateApprovalRequirement | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | evaluateApprovalRequirement | request | scopePath | string | yes
TenancyService | evaluateApprovalRequirement | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | request | attributes | object |  | Whatever the conditional rules match on (11.1.13).
TenancyService | evaluateApprovalRequirement | response | isRequired | boolean | yes
TenancyService | evaluateApprovalRequirement | response | matchedRule | object |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | evaluateApprovalRequirement | response | matchedRule.order | integer | yes | First match wins.
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount | object |  | Amounts compare in the venue's currency (the lead, 25 October 2026, r10 round 3, ADAM CR-102; CHG-R10ID-020): a request amount in another currency (a supplier's, a tender's) is converted into the cur…
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount | object |  | The upper bound, compared as minAmount is (venue currency, the day''s FX rate; CR-102).
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | response | matchedRule.riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.condition | string |  | 11.1.13. (max length 500; nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | evaluateApprovalRequirement | response | matchedRule.approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | evaluateApprovalRequirement | response | matchedRule.mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | evaluateApprovalRequirement | response | matchedRule.levels | integer |  | 11.1.3. (default 1)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiresMfa | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiresSignature | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.escalateAfterMinutes | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | evaluateApprovalRequirement | response | matchedRule.expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.subjectTypes | array of string |  | Which subjects of the kind this rule matches (decided 2 October 2026, Chinmay; CHG-CSP-028, CHG-CSP-036, CHG-CSP-031): the CreateApprovalRequest.subjectType values, for example topologyPublication or…
TenancyService | evaluateApprovalRequirement | response | matchedRule.signatureMethods | array of enum (platformKey, uaePass, externalCertificate, drawnSignature) |  | The signature methods this level accepts, where requiresSignature is true (design-notes correction on ADM-344, Block B: "Configuring which stages need a signature is a policy write"; CHG-CSP-045).
TenancyService | evaluateApprovalRequirement | response | matchedRule.externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.code | string |  | A stable code for the rule, unique within its matrix (4 October 2026, CHG-FXC-005; enforced by a unique index on (matrix_id, code) since ADAM CR-102, CHG-R10ID-015, compared without case). (max length 64; nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minimumApprovals | integer |  | N in N-of-M (CHG-FXC-005). (min 1; nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiredApproverRoleId | string (uuid) |  | A role that must be among the approvals whatever N is (the CFO in an N-of-M group); it is also one of approverRoleIds (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this rule does; null is rejectRequest (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.allowRequestChanges | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.allowDelegate | boolean |  | (default True)
TenancyService | evaluateApprovalRequirement | response | matchedRule.allowReassign | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minPercentage | number |  | A percentage threshold (a discount or a margin impact) at or above which the rule applies, beside minAmount (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.matchAttributes | object |  | The request attributes a rule matches on (CHG-FXC-005): keys module, product, department, customerType, risk, exceptionType, legalEntity, each an exact value the request's attributes must carry. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.compositeMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) |  | The approvalMode the composite screen sent, kept so it reads back what it saved; mode, levels and minimumApprovals are what the engine runs (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matrixVersion | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | approvers | array of object |  | Resolved, with delegations applied.
TenancyService | evaluateApprovalRequirement | response | approvers[].principalId | string (uuid)
TenancyService | evaluateApprovalRequirement | response | approvers[].displayName | string
TenancyService | evaluateApprovalRequirement | response | approvers[].level | integer
TenancyService | evaluateApprovalRequirement | response | approvers[].isDelegate | boolean
TenancyService | evaluateApprovalRequirement | response | approvers[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | slaMinutes | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | noApproverAvailable | boolean |  | The case that must not fail silently.
TenancyService | evaluateApprovalRequirement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | evaluatePromotions | request | venueId | string (uuid) | yes
CatalogueService | evaluatePromotions | request | channel | object | yes | Where the sale is being made.
CatalogueService | evaluatePromotions | request | subjectId | string (uuid)
CatalogueService | evaluatePromotions | request | membershipTierId | string (uuid)
CatalogueService | evaluatePromotions | request | couponCodes | array of string
CatalogueService | evaluatePromotions | request | evaluateAt | string (date-time) |  | For back-office testing of a rule before publishing.
CatalogueService | evaluatePromotions | request | orderId | string (uuid) |  | The order (orders.sales_order) being priced for payment. (nullable)
CatalogueService | evaluatePromotions | request | lines | array of object | yes | (min items 1)
CatalogueService | evaluatePromotions | request | lines[].lineId | string | yes
CatalogueService | evaluatePromotions | request | lines[].variantId | string (uuid) | yes
CatalogueService | evaluatePromotions | request | lines[].performanceId | string (uuid)
CatalogueService | evaluatePromotions | request | lines[].quantity | integer | yes | (min 1)
CatalogueService | evaluatePromotions | request | lines[].unitPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | request | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | request | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | request | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | totalDiscount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | totalDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | totalDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | totalDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines | array of object | yes
CatalogueService | evaluatePromotions | response | lines[].lineId | string | yes
CatalogueService | evaluatePromotions | response | lines[].originalPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].originalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].originalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].originalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].discount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].appliedPromotionIds | array of string (uuid)
CatalogueService | evaluatePromotions | response | applied | array of object | yes
CatalogueService | evaluatePromotions | response | applied[].promotionId | string (uuid) | yes
CatalogueService | evaluatePromotions | response | applied[].promotionCode | string | yes
CatalogueService | evaluatePromotions | response | applied[].promotionName | string
CatalogueService | evaluatePromotions | response | applied[].discount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | applied[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | applied[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | applied[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | applied[].couponCode | string |  | (nullable)
CatalogueService | evaluatePromotions | response | rejected | array of object | yes | Promotions that matched the products but did not apply, with the reason.
CatalogueService | evaluatePromotions | response | rejected[].promotionCode | string | yes
CatalogueService | evaluatePromotions | response | rejected[].promotionName | string
CatalogueService | evaluatePromotions | response | rejected[].reason | enum (conditionsNotMet, supersededByBetterOffer, exclusivePromotionApplied, redemptionLimitReached, budgetExhausted, outsideValidPeriod, wrongChannel, membershipRequired, …) | yes
CatalogueService | evaluatePromotions | response | rejected[].detail | string
CatalogueService | evaluatePromotions | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | exchangeOrderLines | request | id | string (uuid) | yes | Client-generated UUIDv7 of this exchange, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | exchangeOrderLines | request | outgoingLineIds | array of string (uuid) | yes | (min items 1)
OrderService | exchangeOrderLines | request | incomingLines | array of CreateOrderLine | yes | (min items 1)
OrderService | exchangeOrderLines | request | incomingLines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | exchangeOrderLines | request | incomingLines[].variantId | string (uuid) | yes
OrderService | exchangeOrderLines | request | incomingLines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].performanceId | string (uuid)
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | exchangeOrderLines | request | incomingLines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | exchangeOrderLines | request | incomingLines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].quantity | integer | yes | (min 1)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | request | incomingLines[].holderName | string |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].dataMaskValues | object |  | Deliberately open.
OrderService | exchangeOrderLines | request | waiveFee | boolean |  | (default False)
OrderService | exchangeOrderLines | request | reason | string |  | (max length 500)
OrderService | exchangeOrderLines | request | recordedAt | string (date-time) | yes
OrderService | exchangeOrderLines | response | orderId | string (uuid) | yes
OrderService | exchangeOrderLines | response | outgoingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | outgoingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | outgoingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | outgoingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | incomingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | incomingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | incomingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | incomingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | exchangeFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | exchangeFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | exchangeFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | exchangeFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | difference | object | yes | Only the difference settles.
OrderService | exchangeOrderLines | response | difference.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | difference.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | difference.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | newLineIds | array of string (uuid)
OrderService | exchangeOrderLines | response | revokedEntitlementIds | array of string (uuid)
OrderService | exchangeOrderLines | response | issuedEntitlementIds | array of string (uuid)
OrderService | exchangeOrderLines | param (path) | orderId | string (uuid) | yes
OrderService | exchangeOrderLines | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | explainMetricChange | request | metricKey | string | yes
AiService | explainMetricChange | request | period | string | yes | ISO period, e.g.
AiService | explainMetricChange | request | comparison | enum (previousPeriod, samePeriodLastYear, forecast) |  | (default previousPeriod)
AiService | explainMetricChange | request | dimensions | array of string
AiService | explainMetricChange | request | keep | boolean |  | (default False)
AiService | explainMetricChange | response | metricKey | string | yes
AiService | explainMetricChange | response | period | string
AiService | explainMetricChange | response | comparison | string
AiService | explainMetricChange | response | change | number | yes
AiService | explainMetricChange | response | changePercent | number |  | (nullable)
AiService | explainMetricChange | response | drivers | array of object | yes
AiService | explainMetricChange | response | drivers[].dimension | string
AiService | explainMetricChange | response | drivers[].member | string
AiService | explainMetricChange | response | drivers[].contribution | number
AiService | explainMetricChange | response | drivers[].evidence | AiEvidenceItem |  | One piece of evidence behind a decision, labelled by origin (AIC-197): read from a source system, derived by a rule or feature, or inferred by a model.
AiService | explainMetricChange | response | drivers[].evidence.label | enum (source, derived, modelInferred) | yes
AiService | explainMetricChange | response | drivers[].evidence.kind | string | yes | What it is: feature, rule, document, metric, transaction, candidateSet.
AiService | explainMetricChange | response | drivers[].evidence.ref | string |  | Where it came from: a table and id, a document chunk, a metric key. (nullable)
AiService | explainMetricChange | response | drivers[].evidence.name | string
AiService | explainMetricChange | response | drivers[].evidence.value | object |  | (nullable)
AiService | explainMetricChange | response | drivers[].evidence.observedAt | string (date-time) |  | (nullable)
AiService | explainMetricChange | response | narrative | string |  | (nullable)
AiService | explainMetricChange | response | reliability | enum (grounded, partial, conflictingSources, insufficientEvidence)
AiService | explainMetricChange | response | dataAsOf | string (date-time)
AiService | explainMetricChange | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | exportSitePackage | request | version | string |  | The published version to package; the current one where absent. (nullable)
WhiteLabelService | exportSitePackage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | exportSitePackage | response | version | string
WhiteLabelService | exportSitePackage | response | status | enum (building, ready, failed) | yes
WhiteLabelService | exportSitePackage | response | packageAssetRef | string (uuid) |  | The package in the assets library, set when ready (ADAM CR-106; CHG-R10TEN-012). (read-only; nullable)
WhiteLabelService | exportSitePackage | response | downloadUrl | string |  | Short-lived; present when ready. (nullable)
WhiteLabelService | exportSitePackage | response | expiresAt | string (date-time) |  | (nullable)
WhiteLabelService | exportSitePackage | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | exportSitePackage | response | platformStaffGrantId | string (uuid) |  | The platform-staff grant it was made under, where platform staff made it (R098). (read-only; nullable)
WhiteLabelService | exportSitePackage | response | createdAt | string (date-time) |  | (read-only)
WhiteLabelService | exportSitePackage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | exportSitePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | exportSubjectData | request | format | enum (json, csv, pdf) |  | (default json)
IdentityService | exportSubjectData | response | requestId | string | yes | The approvals.request id of the export request (raised through Approvals' createApprovalRequest), CHG-GDL-002.
IdentityService | exportSubjectData | response | format | enum (json, csv, pdf) | yes | The format asked for, or json when the request named none.
IdentityService | exportSubjectData | response | estimatedCompletionAt | string (date-time) |  | Null until a response period reaches Identity, as for deleteGuestAccount (the periods are marketing-crm setPrivacyRequestTypes deadlines[].responseDays, which Identity does not read). (nullable)
IdentityService | exportSubjectData | param (path) | subjectId | string (uuid) | yes
IdentityService | exportSubjectData | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | extendCart | response | id | string (uuid) | yes
OrderService | extendCart | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | extendCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | extendCart | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | extendCart | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | extendCart | response | venueId | string (uuid) | yes
OrderService | extendCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | extendCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | extendCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | extendCart | response | lines | array of CartLine | yes
OrderService | extendCart | response | lines[].id | string (uuid) | yes
OrderService | extendCart | response | lines[].variantId | string (uuid) | yes
OrderService | extendCart | response | lines[].productName | string |  | (read-only)
OrderService | extendCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | extendCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | extendCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | extendCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | extendCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | extendCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | extendCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | extendCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | extendCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | extendCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | extendCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | extendCart | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | extendCart | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | extendCart | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | extendCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | extendCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | extendCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | extendCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | extendCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | extendCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | extendCart | response | conflicts | array of CartConflict
OrderService | extendCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | extendCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | extendCart | response | conflicts[].message | string
OrderService | extendCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | extendCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | extendCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | extendCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | extendCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | extendCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | extendCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | extendCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | extendCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | extendCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | extendCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | extendCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | extendCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | extendCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | extendCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | extendCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | extendCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | extendCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | extendCart | response | extensionsUsed | integer |  | (read-only)
OrderService | extendCart | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | extendCart | response | locale | string
OrderService | extendCart | response | createdAt | string (date-time)
OrderService | extendCart | response | updatedAt | string (date-time)
OrderService | extendCart | param (path) | cartId | string (uuid) | yes
OrderService | extendCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | extendReservation | response | id | string (uuid) | yes
OrderService | extendReservation | response | venueId | string (uuid) | yes
OrderService | extendReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | extendReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | extendReservation | response | lines | array of CreateOrderLine
OrderService | extendReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | extendReservation | response | lines[].variantId | string (uuid) | yes
OrderService | extendReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | extendReservation | response | lines[].performanceId | string (uuid)
OrderService | extendReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | extendReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | extendReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | extendReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | extendReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | extendReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | extendReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | extendReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | extendReservation | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | extendReservation | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | extendReservation | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | extendReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | extendReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | extendReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | extendReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendReservation | response | lines[].holderName | string |  | (nullable)
OrderService | extendReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | extendReservation | response | expiresAt | string (date-time) | yes
OrderService | extendReservation | response | createdAt | string (date-time) | yes
OrderService | extendReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | extendReservation | param (path) | reservationId | string (uuid) | yes
OrderService | extendReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | extendResourceHold | response | id | string (uuid) | yes
VenueOpsService | extendResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | extendResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | extendResourceHold | response | from | string (date-time) | yes
VenueOpsService | extendResourceHold | response | to | string (date-time) | yes
VenueOpsService | extendResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | extendResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | extendResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | extendResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | extendResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | extendResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | extendResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | extendResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | extendResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | extendResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | extendResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | extendResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | extendResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | extendResourceHold | param (path) | holdId | string (uuid) | yes
VenueOpsService | extendResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | extendSeatHold | response | id | string | yes
CatalogueService | extendSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | extendSeatHold | response | seatIds | array of string | yes
CatalogueService | extendSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | extendSeatHold | response | status | enum (held, converted, released, expired, sold) | yes | converted when the order is created; sold when the order is paid and catalogue.convertInventoryHold sells the units (ADAM CR-169, 18 October 2026; CHG-CRA-007).
CatalogueService | extendSeatHold | response | inventoryReservationId | string (uuid) |  | The inventory hold these seats sit under (ADAM CR-169; CHG-CRA-007), so convertInventoryHold finds the order's seat reservations from the hold it converts. (nullable)
CatalogueService | extendSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | extendSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | extendSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | extendSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | extendSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | extendSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | extendSeatHold | response | extensionCount | integer
CatalogueService | extendSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | extendSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | extendSeatHold | param (path) | holdId | string (uuid) | yes
CatalogueService | extendSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | fireCourse | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | fireCourse | request | course | integer | yes | (min 1)
FnbService | fireCourse | request | fireAt | string (date-time) |  | For timed coursing. (nullable)
FnbService | fireCourse | response | id | string (uuid) | yes
FnbService | fireCourse | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | fireCourse | response | orderNumber | string
FnbService | fireCourse | response | outletId | string (uuid) | yes
FnbService | fireCourse | response | tableLabel | string |  | (nullable)
FnbService | fireCourse | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | fireCourse | response | coursing | object |  | BL-131. (nullable)
FnbService | fireCourse | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | fireCourse | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | fireCourse | response | priority | integer |  | Higher fires sooner.
FnbService | fireCourse | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | fireCourse | response | prioritiseReason | string |  | (nullable)
FnbService | fireCourse | response | lines | array of object | yes
FnbService | fireCourse | response | lines[].lineId | string (uuid) | yes
FnbService | fireCourse | response | lines[].name | string | yes
FnbService | fireCourse | response | lines[].quantity | integer | yes
FnbService | fireCourse | response | lines[].modifiers | array of string
FnbService | fireCourse | response | lines[].note | string |  | (nullable)
FnbService | fireCourse | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | fireCourse | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | fireCourse | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | fireCourse | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | fireCourse | response | lines[].course | integer |  | (nullable)
FnbService | fireCourse | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | fireCourse | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | fireCourse | response | createdAt | string (date-time) | yes
FnbService | fireCourse | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | fireCourse | response | elapsedSeconds | integer
FnbService | fireCourse | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | fireCourse | param (path) | ticketId | string (uuid) | yes
FnbService | fireCourse | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | forceLogout | request | reason | string |  | Why the session is ended. (min length 3; max length 500; default supervisor-takeover)
IdentityService | forceLogout | request | workstationId | string (uuid) |  | The till making the call. (nullable)
IdentityService | forceLogout | request | supervisorStepUp | object |  | The supervisor ending the session, signing on this device.
IdentityService | forceLogout | request | supervisorStepUp.principalId | string (uuid) |  | The supervisor signing.
IdentityService | forceLogout | request | supervisorStepUp.supervisorUsername | string |  | The supervisor's employee number, which is what the step-up prompt asks for (R8 blocker fix, IDENTITY-C44). (max length 200)
IdentityService | forceLogout | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
IdentityService | forceLogout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | forceLogout | param (path) | sessionId | string (uuid) | yes | The sessionId of an ActiveSession from listActiveSessions (the session's identity.session.id).
CatalogueService | generateCouponCodes | request | quantity | integer | yes | (min 1; max 50000)
CatalogueService | generateCouponCodes | request | prefix | string |  | (max length 16)
CatalogueService | generateCouponCodes | request | length | integer |  | (min 6; max 32; default 12)
CatalogueService | generateCouponCodes | request | assignToSubjectIds | array of string (uuid) |  | Personalised codes bound to named guests. (max items 50000)
CatalogueService | generateCouponCodes | response | batchId | string (uuid)
CatalogueService | generateCouponCodes | response | quantity | integer
CatalogueService | generateCouponCodes | response | status | enum (queued, generating, complete, failed)
CatalogueService | generateCouponCodes | param (path) | campaignId | string (uuid) | yes
CatalogueService | generateCouponCodes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | generateVisitPlan | request | venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | generateVisitPlan | request | dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | generateVisitPlan | request | dayVenues[].date | string (date) | yes
VenueOpsService | generateVisitPlan | request | dayVenues[].venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | request | dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | generateVisitPlan | request | party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | generateVisitPlan | request | party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | generateVisitPlan | request | party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | generateVisitPlan | request | pace | enum (packed, balanced, relaxed) |  | (default relaxed)
VenueOpsService | generateVisitPlan | request | interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | generateVisitPlan | request | cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | generateVisitPlan | request | retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | generateVisitPlan | request | mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | generateVisitPlan | request | preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | generateVisitPlan | request | presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | generateVisitPlan | request | startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | generateVisitPlan | request | locale | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | generateVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | ownership | enum (anonymous, account) |  | anonymous while the plan belongs to a device session (built and changed only; it lapses with the session), account once the guest signed in and the plan moved to their account, where it is saved and… (read-only)
VenueOpsService | generateVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | generateVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | generateVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | generateVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | generateVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | generateVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | generateVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | generateVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | generateVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | generateVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | generateVisitPlan | response | inputs.pace | enum (packed, balanced, relaxed) |  | (default relaxed)
VenueOpsService | generateVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | generateVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | generateVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | generateVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | generateVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | generateVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | generateVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | generateVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | generateVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | generateVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | generateVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | excluded[].name | string |  | The point's name, worked out on read for the left-out banner (r8 walk of ticket 28693). (nullable)
VenueOpsService | generateVisitPlan | response | excluded[].limit | object |  | The rule that left it out, worked out on read from the product's eligibility rule: for heightRule a minimum or maximum height in centimetres, for ageRule a minimum or maximum age in years. (nullable)
VenueOpsService | generateVisitPlan | response | excluded[].limit.kind | enum (minHeightCm, maxHeightCm, minAge, maxAge)
VenueOpsService | generateVisitPlan | response | excluded[].limit.value | integer |  | (min 0)
VenueOpsService | generateVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | generateVisitPlan | response | estimate | object |  | An estimated total, computed on read from current catalogue prices and stored nowhere (r8 walk of tickets 28693 and 28200; lead decision of 20 October 2026, option A; DI-1098, "with associated costin… (read-only; nullable)
VenueOpsService | generateVisitPlan | response | estimate.total | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | generateVisitPlan | response | estimate.total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | generateVisitPlan | response | estimate.total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | generateVisitPlan | response | estimate.total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | generateVisitPlan | response | estimate.currency | string | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | generateVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | generateVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | generateVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | generateVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | generateVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | generateVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].name | string |  | What the stop is called on the timeline (GST-059, GST-053; r8 walk of ticket 28693): the point's name, or the performance's title for a show, in the request language. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].zoneName | string |  | The name of the zone the stop is in, from the point's zone on the map the plan was laid out on. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnProductIds | array of string (uuid) |  | Add-ons the guest put on this stop with addAddOn (CHG-RUL-009), beside an accepted suggestion, as catalogue product ids. (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | generateVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | generateVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | generateVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | generateVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | getAiByokEnablement | response | id | string (uuid) |  | (read-only)
AiService | getAiByokEnablement | response | tenantId | string (uuid) | yes | (read-only)
AiService | getAiByokEnablement | response | enabled | boolean | yes
AiService | getAiByokEnablement | response | coverage | enum (perTask, allTasks) |  | Whether the tenant may supply a key per task or one key for everything. (default perTask)
AiService | getAiByokEnablement | response | allowedTasks | array of string |  | Where coverage is perTask: the gateway tasks a tenant key may serve.
AiService | getAiByokEnablement | response | taskModelMap | array of object |  | The provider's equivalent model for each task, chosen by TICVAI (Chinmay, 2 October, workbook Q1; closes AI-D20; CHG-CSA-001). (read-only)
AiService | getAiByokEnablement | response | taskModelMap[].taskKey | string
AiService | getAiByokEnablement | response | taskModelMap[].tier | string
AiService | getAiByokEnablement | response | taskModelMap[].modelId | string (uuid) |  | (nullable)
AiService | getAiByokEnablement | response | taskModelMap[].compatibilityPassed | boolean |  | Whether the provider's compatibility test passed for this task (AiProviderCompatibility, CHG-FUP-008); a task that has not passed stays on the TICVAI-managed model. (nullable)
AiService | getAiByokEnablement | response | reason | string |  | (max length 1000)
AiService | getAiByokEnablement | response | platformStaffGrantId | string (uuid) |  | The open platform-staff grant the change was made under (audit R098). (read-only)
AiService | getAiByokEnablement | response | decidedByPrincipalId | string (uuid) |  | (read-only)
AiService | getAiByokEnablement | response | decidedAt | string (date-time) |  | (read-only)
AiService | getAiByokEnablement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getAiByokEnablement | param (path) | tenantId | string (uuid) | yes
AiService | getAiPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
AiService | getAiPolicy | response | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | getAiPolicy | response | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue. (read-only)
AiService | getAiPolicy | response | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | getAiPolicy | response | allowedRoleIds | array of string (uuid)
AiService | getAiPolicy | response | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | getAiPolicy | response | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | getAiPolicy | response | scrubbing | object |  | Mandatory offline PII scrubbing and moderation on every LLM call (Chinmay, 2 October: "we may need to scrub personal info no matter what"; ADR-0020 amended; CHG-CSA-003). (read-only)
AiService | getAiPolicy | response | scrubbing.mode | enum (mandatory)
AiService | getAiPolicy | response | scrubbing.scrubberVersion | string |  | The pinned Presidio release (and recogniser set) in force, e.g. (read-only)
AiService | getAiPolicy | response | scrubbing.residualPatternCheck | array of enum (emiratesId, uaePhone, cardPan, iban, email) |  | The deterministic patterns run after Presidio; a match blocks the call (fail closed, 503 scrubber-unavailable). (read-only)
AiService | getAiPolicy | response | scrubbing.recognisers | array of string |  | The recogniser set in force, e.g.
AiService | getAiPolicy | response | scrubbing.reversibleTokens | boolean |  | Always true; the placeholder map stays in the cell.
AiService | getAiPolicy | response | scrubbing.guardModel | string |  | The input and output guard in force, e.g.
AiService | getAiPolicy | response | globalEndpointExclusions | object |  | What never goes to a global endpoint (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 6). (read-only)
AiService | getAiPolicy | response | globalEndpointExclusions.fieldCategories | array of enum (allergy, accessibility, familyAndChildren, health, biometric, religion, payment) |  | Allergy, accessibility and family or children data in F&B and booking prompts, and health, biometric, religion and payment data anywhere.
AiService | getAiPolicy | response | globalEndpointExclusions.fields | array of string |  | The schema fields held under those categories, e.g.
AiService | getAiPolicy | response | globalEndpointExclusions.blockedMedia | array of enum (image, audio, file) |  | Images, audio and files are never sent to a global endpoint.
AiService | getAiPolicy | response | monthlyTokenCeiling | integer |  | (nullable)
AiService | getAiPolicy | response | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | getAiPolicy | response | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | getAiPolicy | response | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | getAiPolicy | response | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | getAiPolicy | response | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | getAiPolicy | response | autonomyOverrides[].capabilityKey | string | yes
AiService | getAiPolicy | response | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getAiPolicy | response | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | getAiPolicy | response | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | getAiPolicy | response | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | getAiPolicy | response | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | getAiPolicy | response | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | getAiPolicy | response | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | getAiPolicy | response | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | getAiPolicy | response | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | getAiPolicy | response | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | getAiPolicy | response | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | getAiPolicy | response | cascade.smallModel | string
AiService | getAiPolicy | response | cascade.largeModel | string
AiService | getAiPolicy | response | cascade.escalateBelow | number |  | (default 0.7)
AiService | getAiPolicy | response | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | getAiPolicy | response | chunking.sizeTokens | integer |  | (default 512)
AiService | getAiPolicy | response | chunking.overlapTokens | integer |  | (default 64)
AiService | getAiPolicy | response | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | getAiPolicy | response | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | getAiPolicy | response | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | getAiPolicy | response | hnsw.m | integer |  | (default 16)
AiService | getAiPolicy | response | hnsw.efConstruct | integer |  | (default 128)
AiService | getAiPolicy | response | hnsw.efSearch | integer |  | (default 64)
AiService | getAiPolicy | response | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | getAiPolicy | response | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | getAiPolicy | response | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | getAiPolicy | response | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | getAiPolicy | response | glossaryTerms | array of object |  | The tenant's translation glossary (R8 blocker FOUNDATION-AI-C05, the lead's answer of 20 October 2026): terms proposeTranslations and proposeContent keep as they are (keep) or always translate one wa… (max items 500; nullable)
AiService | getAiPolicy | response | glossaryTerms[].term | string | yes | (max length 200)
AiService | getAiPolicy | response | glossaryTerms[].rule | enum (keep, translateAs) | yes
AiService | getAiPolicy | response | glossaryTerms[].translations | object |  | For translateAs, the translation per locale (ar, fr, ...). (nullable)
AiService | getAiPolicy | response | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | getAiPolicy | param (query) | scopePath | string |  | The tenant or venue node to read the policy for.
AiService | getAiUsage | response | currency | string |  | The tenant's selected currency, by default its billing currency (AED for a UAE tenant), not USD (CHG-RUL-017; Chinmay, 2 October, workbook Q8; CHG-CSA-004). (min length 3; max length 3; read-only)
AiService | getAiUsage | response | ceiling | object |  | The spend ceiling in force (getAiSpendCeiling), with the tokens it equals at the current blended rate and what is used so far (CHG-CSA-004). (read-only; nullable)
AiService | getAiUsage | response | ceiling.spend | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | ceiling.spend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | ceiling.spend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | ceiling.spend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | ceiling.tokens | integer |  | (nullable)
AiService | getAiUsage | response | ceiling.usedSpend | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | ceiling.usedSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | ceiling.usedSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | ceiling.usedSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | ceiling.usedTokens | integer
AiService | getAiUsage | response | from | string (date)
AiService | getAiUsage | response | to | string (date)
AiService | getAiUsage | response | groupBy | string
AiService | getAiUsage | response | rows | array of object
AiService | getAiUsage | response | rows[].key | string
AiService | getAiUsage | response | rows[].interactions | integer
AiService | getAiUsage | response | rows[].promptTokens | integer
AiService | getAiUsage | response | rows[].completionTokens | integer
AiService | getAiUsage | response | rows[].cost | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | rows[].cost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | rows[].cost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | rows[].cost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | rows[].p95LatencyMs | integer
AiService | getAiUsage | response | rows[].refusalRate | number
AiService | getAiUsage | response | rows[].rejectionRate | number |  | Proposals a person refused.
AiService | getAiUsage | response | forecast | object |  | A month-end projection, labelled a forecast (AI design 2.3, 4.5). (nullable)
AiService | getAiUsage | response | forecast.label | enum (forecast)
AiService | getAiUsage | response | forecast.periodEnd | string (date)
AiService | getAiUsage | response | forecast.projectedTokens | integer
AiService | getAiUsage | response | forecast.projectedCost | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | forecast.projectedCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | forecast.projectedCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | forecast.projectedCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | forecast.basis | string |  | How it was projected, e.g.
AiService | getAiUsage | param (query) | from | string (date)
AiService | getAiUsage | param (query) | groupBy | enum (tenant, venue, principal, provider, capability, day, agent, model, …)
AiService | getAiVenueSettings | response | id | string (uuid) |  | (read-only)
AiService | getAiVenueSettings | response | venueId | string (uuid) | yes
AiService | getAiVenueSettings | response | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | getAiVenueSettings | response | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | getAiVenueSettings | response | capacity | integer |  | (min 1; nullable)
AiService | getAiVenueSettings | response | openingHours | array of object |  | The usual week.
AiService | getAiVenueSettings | response | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | getAiVenueSettings | response | openingHours[].opensAt | string
AiService | getAiVenueSettings | response | openingHours[].closesAt | string
AiService | getAiVenueSettings | response | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | getAiVenueSettings | response | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | getAiVenueSettings | response | peakMonths | array of integer
AiService | getAiVenueSettings | response | averageSpend | object |  | (nullable)
AiService | getAiVenueSettings | response | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiVenueSettings | response | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiVenueSettings | response | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiVenueSettings | response | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | getAiVenueSettings | response | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | getAiVenueSettings | response | startingPatternKey | string |  | The starting pattern and version in use, e.g. (read-only)
AiService | getAiVenueSettings | response | updatedAt | string (date-time) |  | (read-only)
AiService | getAiVenueSettings | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getAiVenueSettings | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getAppBuild | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | getAppBuild | response | platform | enum (ios, android) | yes
WhiteLabelService | getAppBuild | response | configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | getAppBuild | response | storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | getAppBuild | response | versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | getAppBuild | response | buildNumber | integer |  | (read-only)
WhiteLabelService | getAppBuild | response | status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the white-label jobs component's, in the workers host, from appBuild.requested (ADAM CR-106); from submitted on it is read from the store with the client's credential, or… (read-only)
WhiteLabelService | getAppBuild | response | failureReason | string |  | (read-only; nullable)
WhiteLabelService | getAppBuild | response | packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | getAppBuild | response | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getAppBuild | response | submitToStore | boolean |  | (default False)
WhiteLabelService | getAppBuild | response | requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | getAppBuild | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | getAppBuild | response | finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | getAppBuild | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getAppBuild | param (path) | appBuildId | string (uuid) | yes
WhiteLabelService | getAppIcons | response | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getAppIcons | response | derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getAppIcons | response | derived[].platform | enum (ios, android, web)
WhiteLabelService | getAppIcons | response | derived[].size | string
WhiteLabelService | getAppIcons | response | derived[].assetRef | string (uuid)
WhiteLabelService | getAppIcons | response | changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getAppIcons | response | liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getAppIcons | response | requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
CatalogueService | getAvailability | response | items | array of PerformanceAvailability | yes
CatalogueService | getAvailability | response | items[].channelCapacityId | string (uuid) | yes
CatalogueService | getAvailability | response | items[].performanceId | string (uuid) | yes | The performance this channel capacity belongs to (ChannelCapacity.performanceId), so rows for several performances can be told apart.
CatalogueService | getAvailability | response | items[].startsAt | string (date-time) |  | The performance's start, so a time tile and its day part (morning, afternoon, evening, split at the venue's BookingFlowConfig.dayPartBoundaries) come from this one call (rev 3 REV3-1). (read-only)
CatalogueService | getAvailability | response | items[].capacity | integer | yes
CatalogueService | getAvailability | response | items[].sold | integer | yes
CatalogueService | getAvailability | response | items[].leased | integer | yes | Held by terminals but not yet sold.
CatalogueService | getAvailability | response | items[].remaining | integer | yes
CatalogueService | getAvailability | response | items[].byChannel | array of object |  | Per-channel position.
CatalogueService | getAvailability | response | items[].byChannel[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | getAvailability | response | items[].byChannel[].allocated | integer
CatalogueService | getAvailability | response | items[].byChannel[].sold | integer
CatalogueService | getAvailability | response | items[].byChannel[].remaining | integer
CatalogueService | getAvailability | response | nextCursor | string
CatalogueService | getAvailability | response | hasMore | boolean | yes
CatalogueService | getAvailability | param (query) | performanceId | string (uuid)
CatalogueService | getAvailability | param (query) | channelCapacityId | string (uuid)
CatalogueService | getAvailability | param (query) | eventId | string (uuid) |  | Every performance of this event starting between from and to (rev 3 REV3-1).
CatalogueService | getAvailability | param (query) | from | string (date-time) |  | Required with eventId.
CatalogueService | getAvailability | param (query) | to | string (date-time) |  | Required with eventId.
CatalogueService | getAvailability | param (query) | pageSize | integer
CatalogueService | getAvailability | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | getAvailability | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
FnbService | getBill | response | visitId | string | yes
FnbService | getBill | response | covers | integer
FnbService | getBill | response | lines | array of object | yes
FnbService | getBill | response | lines[].lineId | string | yes
FnbService | getBill | response | lines[].orderId | string
FnbService | getBill | response | lines[].name | string | yes
FnbService | getBill | response | lines[].quantity | integer | yes
FnbService | getBill | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | lines[].categoryCode | string |  | (nullable)
FnbService | getBill | response | lines[].seatNumber | integer |  | (nullable)
FnbService | getBill | response | subtotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | serviceCharge | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | serviceCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | serviceCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | serviceCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | param (path) | visitId | string (uuid) | yes
OrderService | getBillingStatement | response | id | string (uuid) | yes | A name-based UUID (v5) of agreementId, periodStart and periodEnd, so the same statement has the same id on every read (ADAM CR-099).
OrderService | getBillingStatement | response | agreementId | string (uuid) | yes | The membership agreement this statement is one billing cycle of (identity.customer_membership.id; ADAM CR-099).
OrderService | getBillingStatement | response | subjectId | string (uuid) |  | (read-only)
OrderService | getBillingStatement | response | periodStart | string (date) | yes
OrderService | getBillingStatement | response | periodEnd | string (date) | yes
OrderService | getBillingStatement | response | lines | array of BillingStatementLine
OrderService | getBillingStatement | response | lines[].occurredAt | string (date-time) | yes
OrderService | getBillingStatement | response | lines[].kind | enum (charge, refund, failedAttempt, adjustment) | yes
OrderService | getBillingStatement | response | lines[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].description | string
OrderService | getBillingStatement | response | lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].taxRate | number |  | 2.14.23. (nullable)
OrderService | getBillingStatement | response | lines[].taxInvoiceId | string (uuid) |  | The finance tax invoice issued for this charge, where one was (issueTaxInvoice); the guest downloads it with getTaxDocumentRendition. (nullable)
OrderService | getBillingStatement | response | lines[].declineClass | string |  | Present on failedAttempt only, and it is what turns *"your payment failed"* into something a guest can act on: a soft decline means try again, a hard one means the card needs replacing. (nullable)
OrderService | getBillingStatement | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | pdfUrl | string (uri) |  | Set when getBillingStatement is called with format=pdf; a short-lived link. (read-only; nullable)
OrderService | getBillingStatement | response | isTaxInvoice | boolean | yes | Always false, and stated rather than assumed. (default False; read-only)
OrderService | getBillingStatement | param (path) | statementId | string (uuid) | yes | The id listBillingStatements answered for the statement: a name-based UUID (v5) of agreementId, periodStart and periodEnd (ADAM CR-099).
OrderService | getBillingStatement | param (query) | format | enum (json, pdf) |  | 2.14.23.
OrderService | getBillingStatement | param (query) | language | string
WhiteLabelService | getBookingFlow | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getBookingFlow | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getBookingFlow | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getBookingFlow | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getBookingFlow | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getBookingFlow | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getBookingFlow | response | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | getBookingFlow | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getBookingFlow | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getBookingFlow | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getBookingFlow | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getBookingFlow | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getBookingFlow | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getBookingFlow | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getBookingFlow | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getBookingFlow | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getBookingFlow | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getBookingFlow | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getBookingFlow | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getBookingFlow | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getBookingFlow | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getBookingFlow | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | getBookingFlowConfig | response | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getBookingFlowConfig | response | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getBookingFlowConfig | response | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getBookingFlowConfig | response | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getBookingFlowConfig | response | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getBookingFlowConfig | response | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getBookingFlowConfig | response | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getBookingFlowConfig | response | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getBookingFlowConfig | response | heroBanner | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getBookingFlowConfig | response | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getBookingFlowConfig | response | singleEventPage | boolean |  | (default False)
WhiteLabelService | getBookingFlowConfig | response | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getBookingFlowConfig | response | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getBookingFlowConfig | response | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getBookingFlowConfig | response | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getBookingFlowConfig | response | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getBookingFlowConfig | response | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getBookingFlowConfig | response | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getBookingFlowConfig | response | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getBookingFlowConfig | response | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getBookingFlowConfig | response | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getBookingFlowConfig | param (query) | effectiveForVenueId | string (uuid) |  | Return the settings in force at this venue, the tenant's with the venue's override laid over them, and no venueOverrides (decided 29 September, rev 3 CFG-11).
WhiteLabelService | getBrandIdentity | response | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getBrandIdentity | response | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getBrandIdentity | response | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getBrandIdentity | response | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getBrandIdentity | response | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getBrandIdentity | response | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getBrandIdentity | response | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getBrandIdentity | response | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getBrandIdentity | response | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getBrandIdentity | response | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getBrandIdentity | response | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getBrandIdentity | response | showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
OrderService | getCart | response | id | string (uuid) | yes
OrderService | getCart | response | anonymousSessionToken | string |  | The guestAuth token of the anonymous session createCart opened for a visitor with no credential (GPS-C23, CHG-R8SPN-031); null on every other answer. (read-only; nullable)
OrderService | getCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | getCart | response | sessionId | string (uuid) |  | The staff or partner session that started the cart (a till's cart is its session's own); null for a guest's cart (R8 blocker IDENTITY-C49, CHG-R8MIG-021). (read-only; nullable)
OrderService | getCart | response | workstationId | string (uuid) |  | The workstation of that session; null for a guest's cart. (read-only; nullable)
OrderService | getCart | response | venueId | string (uuid) | yes
OrderService | getCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | getCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | getCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | getCart | response | lines | array of CartLine | yes
OrderService | getCart | response | lines[].id | string (uuid) | yes
OrderService | getCart | response | lines[].variantId | string (uuid) | yes
OrderService | getCart | response | lines[].productName | string |  | (read-only)
OrderService | getCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | getCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | getCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | getCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | getCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | getCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getCart | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | getCart | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | getCart | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | getCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | getCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | getCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | getCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | getCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | getCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | getCart | response | conflicts | array of CartConflict
OrderService | getCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | getCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | getCart | response | conflicts[].message | string
OrderService | getCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | getCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | getCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | getCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | getCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | getCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | getCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | getCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | getCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | getCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | getCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | getCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | getCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | getCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | getCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | getCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | getCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | getCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | getCart | response | extensionsUsed | integer |  | (read-only)
OrderService | getCart | response | maxExtensions | integer |  | The venue's cartMaxExtensions, else the tenant default, set when the cart is created (ADAM CR-184, option A; CHG-R9CR-003; see createCart). (read-only)
OrderService | getCart | response | locale | string
OrderService | getCart | response | createdAt | string (date-time)
OrderService | getCart | response | updatedAt | string (date-time)
OrderService | getCart | param (path) | cartId | string (uuid) | yes
OrderService | getCart | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
MarketingService | getCookieConsentRuntime | response | banner | CookieBannerPreferenceCenterDesignerView | yes | One version of a cookie banner and preference-centre design (pack 17.1.6).
MarketingService | getCookieConsentRuntime | response | banner.id | string (uuid) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | banner.brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | getCookieConsentRuntime | response | banner.inheritsFromId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | banner.channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | getCookieConsentRuntime | response | banner.logoAssetId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | banner.title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.position | enum (top, bottom, popup, modal) | yes
MarketingService | getCookieConsentRuntime | response | banner.themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | getCookieConsentRuntime | response | banner.buttons | array of object
MarketingService | getCookieConsentRuntime | response | banner.buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | getCookieConsentRuntime | response | banner.buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | getCookieConsentRuntime | response | banner.links | array of object
MarketingService | getCookieConsentRuntime | response | banner.links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | getCookieConsentRuntime | response | banner.categories | array of object | yes | (min items 1)
MarketingService | getCookieConsentRuntime | response | banner.categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | getCookieConsentRuntime | response | banner.categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | getCookieConsentRuntime | response | banner.languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | getCookieConsentRuntime | response | banner.regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | getCookieConsentRuntime | response | banner.recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | getCookieConsentRuntime | response | banner.noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | getCookieConsentRuntime | response | banner.version | integer |  | (min 1; read-only)
MarketingService | getCookieConsentRuntime | response | banner.status | enum (draft, published, superseded) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | banner.scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getCookieConsentRuntime | response | banner.updatedAt | string (date-time) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | noticeVersion | string | yes
MarketingService | getCookieConsentRuntime | response | requiresDecision | boolean | yes | True with no decision, an expired one, or one given against a superseded notice.
MarketingService | getCookieConsentRuntime | response | decision | object |  | The latest decision for the presented key; null without a key. (nullable)
MarketingService | getCookieConsentRuntime | response | decision.id | string (uuid) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | decision.consentKey | string | yes | Opaque, minted by us, not a device fingerprint. (max length 64; read-only)
MarketingService | getCookieConsentRuntime | response | decision.channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | getCookieConsentRuntime | response | decision.brandId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | decision.bannerDesignId | string (uuid) |  | The published CookieBannerPreferenceCenterDesignerView version the visitor was shown. (nullable)
MarketingService | getCookieConsentRuntime | response | decision.action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | getCookieConsentRuntime | response | decision.categories | array of object | yes | Every category of the design, with the decision this row gives it. (min items 1)
MarketingService | getCookieConsentRuntime | response | decision.categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getCookieConsentRuntime | response | decision.categories[].decision | enum (granted, declined) | yes
MarketingService | getCookieConsentRuntime | response | decision.noticeVersion | string | yes | The cookie notice version decided against (white-label setPolicy, kind cookie).
MarketingService | getCookieConsentRuntime | response | decision.language | string |  | (max length 10; nullable)
MarketingService | getCookieConsentRuntime | response | decision.globalPrivacyControl | boolean |  | The browser sent a Global Privacy Control signal; honoured as a CCPA/CPRA opt-out of sale and sharing. (default False)
MarketingService | getCookieConsentRuntime | response | decision.source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | getCookieConsentRuntime | response | decision.country | string |  | The edge's geolocation of the request, for the geographic statistics (2.6.63). (pattern ^[A-Z]{2}$; read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.decidedAt | string (date-time) | yes
MarketingService | getCookieConsentRuntime | response | decision.expiresAt | string (date-time) |  | A device consent expires and a subject consent does not. (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.claimedBySubjectId | string (uuid) |  | Set once, by claimDeviceConsent. (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.claimedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.scopePath | string |  | The partition key (ADR-0005), tenant-scoped: a decision with no subject still belongs to one tenant. (read-only)
MarketingService | getCookieConsentRuntime | response | allowedTechnologies | array of object | yes | Per category, the approved technologies it unlocks.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].granted | boolean |  | Whether the presented decision grants it; always true for strictlyNecessary.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies | array of object | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].name | string | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].provider | string | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].technologyType | string
MarketingService | getCookieConsentRuntime | response | consentModeSignals | object | yes | The decision in Google consent-mode terms (2.6.65), so Analytics and Tag Manager are told, not left to guess.
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adUserData | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adPersonalization | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.analyticsStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.functionalityStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.personalizationStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.securityStorage | enum (granted)
MarketingService | getCookieConsentRuntime | param (query) | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | getCookieConsentRuntime | param (query) | brandId | string (uuid)
MarketingService | getCookieConsentRuntime | param (query) | language | string |  | One of the design's languages; the tenant's default where omitted
MarketingService | getCookieConsentRuntime | param (header) | X-Consent-Key | string |  | The key the visitor's browser or app holds, if any
FnbService | getCourseRules | response | outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | getCourseRules | response | defaultCoursing | CoursingPolicy: enum (fireAndForget, holdAndFire, phased, timed, delayed) |  | How a ticket's courses are fired.
FnbService | getCourseRules | response | courseNames | array of string
FnbService | getCourseRules | response | autoFireMinutes | integer |  | (nullable)
FnbService | getCourseRules | response | serviceModeOverrides | object |  | A different default per service mode.
FnbService | getCourseRules | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | getCourseRules | param (path) | outletId | string (uuid) | yes
IdentityService | getCurrentSession | response | sessionId | string (uuid) | yes
IdentityService | getCurrentSession | response | principalId | string (uuid) | yes
IdentityService | getCurrentSession | response | roleId | string (uuid) | yes
IdentityService | getCurrentSession | response | displayName | string
IdentityService | getCurrentSession | response | scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | getCurrentSession | response | scope[].id | string (uuid) | yes
IdentityService | getCurrentSession | response | scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | getCurrentSession | response | scope[].path | string | yes | Materialised ltree path.
IdentityService | getCurrentSession | response | scope[].code | string |  | (nullable)
IdentityService | getCurrentSession | response | scope[].name | string |  | (nullable)
IdentityService | getCurrentSession | response | effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | getCurrentSession | response | permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path, after deny resolution.
IdentityService | getCurrentSession | response | permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | getCurrentSession | response | permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | getCurrentSession | response | saleBoardId | string (uuid) |  | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | getCurrentSession | response | workstation | WorkstationContext
IdentityService | getCurrentSession | response | workstation.id | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.code | string | yes
IdentityService | getCurrentSession | response | workstation.venueId | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.regionId | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | getCurrentSession | response | workstation.devices | array of object
IdentityService | getCurrentSession | response | workstation.devices[].kind | enum (receiptPrinter, ticketPrinter, cashDrawer, barcodeScanner, rfidReader, paymentTerminal, customerDisplay) | yes
IdentityService | getCurrentSession | response | workstation.devices[].driver | string | yes
IdentityService | getCurrentSession | response | workstation.devices[].identifier | string
IdentityService | getCurrentSession | response | workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | getCurrentSession | response | workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | getCurrentSession | response | workstation.timezone | string
IdentityService | getCurrentSession | response | workstation.cellName | string |  | The cell this workstation's region is served from, which is the cell the commerce host answering this request is deployed in (one cell per tenant per region, ADR-0014): the host fills it from its own…
IdentityService | getCurrentSession | response | workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | getCurrentSession | response | workstation.pinLength | enum (4, 6, 8) |  | The tenant's PasswordPolicy.pinLength, carried to the device (14 October 2026, CHG-CRD-002, ADAM CR-078). (read-only)
IdentityService | getCurrentSession | response | availableRoles | array of RoleSummary |  | The roles the principal may choose, one per grant (IDENTITY-C45, CHG-R8SPN-032), resolved on read as LoginResponse.availableRoles is, so EMP-002 can list them on a cold open or after a relaunch (getC… (read-only)
IdentityService | getCurrentSession | response | availableRoles[].id | string (uuid) | yes
IdentityService | getCurrentSession | response | availableRoles[].code | string | yes
IdentityService | getCurrentSession | response | availableRoles[].name | string | yes
IdentityService | getCurrentSession | response | availableRoles[].isPrimary | boolean |  | True for the role that is the principal's primaryRoleId (identity.principal.primary_role_id); false for the others (14 October 2026, ADAM CR-077; CHG-IDR-002).
IdentityService | getCurrentSession | response | availableRoles[].grantId | string (uuid) |  | The grant this card stands for (identity.delegated_access.id; IDENTITY-C45, CHG-R8SPN-032).
IdentityService | getCurrentSession | response | availableRoles[].scope | object |  | The scope node the grant is held at (platform.scope), with its name, so the card can say which venue (IDENTITY-C45).
IdentityService | getCurrentSession | response | availableRoles[].scope.id | string (uuid) | yes
IdentityService | getCurrentSession | response | availableRoles[].scope.level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | getCurrentSession | response | availableRoles[].scope.path | string | yes | Materialised ltree path.
IdentityService | getCurrentSession | response | availableRoles[].scope.code | string |  | (nullable)
IdentityService | getCurrentSession | response | availableRoles[].scope.name | string |  | (nullable)
IdentityService | getCurrentSession | response | openedAt | string (date-time)
IdentityService | getCurrentSession | response | expiresAt | string (date-time) |  | When the session ends at the latest: openedAt plus PasswordPolicy.sessionMaxHours (12 hours by default; proposed, client to correct).
OrderService | getCurrentShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | getCurrentShift | response | workstationId | string (uuid) | yes
OrderService | getCurrentShift | response | venueId | string (uuid) | yes
OrderService | getCurrentShift | response | scopePath | string | yes
OrderService | getCurrentShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | getCurrentShift | response | principalDisplayName | string
OrderService | getCurrentShift | response | incidents | array of object |  | BL-097.
OrderService | getCurrentShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | getCurrentShift | response | incidents[].at | string (date-time)
OrderService | getCurrentShift | response | incidents[].principalId | string (uuid)
OrderService | getCurrentShift | response | incidents[].note | string |  | (nullable)
OrderService | getCurrentShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | getCurrentShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getCurrentShift | response | depositBoxCode | string |  | (nullable)
OrderService | getCurrentShift | response | bagNumber | string |  | (nullable)
OrderService | getCurrentShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | getCurrentShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | getCurrentShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | getCurrentShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | getCurrentShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | getCurrentShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | getCurrentShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | getCurrentShift | response | openedAt | string (date-time) | yes
OrderService | getCurrentShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | getCurrentShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | getCurrentShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | getCurrentShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | getCurrentShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | getCurrentShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | getCurrentShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | getCurrentShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | getCurrentShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | getCurrentShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | getCurrentShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | getCurrentShift | response | approvals | array of object
OrderService | getCurrentShift | response | approvals[].kind | enum (open, close, variance, reopen) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance, reopen from reopenShift (the supervisor who signed it, the time and the reason).
OrderService | getCurrentShift | response | approvals[].principalId | string (uuid) | yes
OrderService | getCurrentShift | response | approvals[].at | string (date-time) | yes
OrderService | getCurrentShift | response | approvals[].reason | string
ReportingService | getDashboard | response | name | string | yes | (max length 200)
ReportingService | getDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | getDashboard | response | description | string |  | (max length 1000)
ReportingService | getDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | getDashboard | response | isShared | boolean |  | (default False)
ReportingService | getDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | getDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | getDashboard | response | tiles[].title | string
ReportingService | getDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | getDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | getDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | getDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | getDashboard | response | tiles[].position | object | yes
ReportingService | getDashboard | response | tiles[].position.row | integer | yes
ReportingService | getDashboard | response | tiles[].position.column | integer | yes
ReportingService | getDashboard | response | tiles[].position.width | integer | yes
ReportingService | getDashboard | response | tiles[].position.height | integer | yes
ReportingService | getDashboard | response | id | string (uuid) | yes
ReportingService | getDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | getDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | getDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | getDashboard | response | createdAt | string (date-time) | yes
ReportingService | getDashboard | response | tileData | array of object
ReportingService | getDashboard | response | tileData[].tileId | string (uuid)
ReportingService | getDashboard | response | tileData[].result | ReportResult
ReportingService | getDashboard | response | tileData[].result.executionId | string | yes
ReportingService | getDashboard | response | tileData[].result.columns | array of object | yes
ReportingService | getDashboard | response | tileData[].result.rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | getDashboard | response | tileData[].result.totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | getDashboard | response | tileData[].result.rowCount | integer
ReportingService | getDashboard | response | tileData[].result.nextCursor | string |  | (nullable)
ReportingService | getDashboard | response | tileData[].result.generatedAt | string (date-time)
ReportingService | getDashboard | response | tileData[].result.dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | getDashboard | response | tileData[].isCached | boolean
ReportingService | getDashboard | response | tileData[].error | string |  | (nullable)
ReportingService | getDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | getDashboard | param (query) | refresh | boolean |  | Bypass cached tile data.
WhiteLabelService | getDeepLinkScheme | response | baseUrl | string | yes | The primary domain, or the platform subdomain where none is primary.
WhiteLabelService | getDeepLinkScheme | response | patterns | array of object | yes | The patterns, fixed (4 October 2026, CHG-FXC-009).
WhiteLabelService | getDeepLinkScheme | response | patterns[].kind | string | yes | A LinkTarget.kind, or bookingFlow.
WhiteLabelService | getDeepLinkScheme | response | patterns[].pattern | string | yes | e.g.
WhiteLabelService | getDeepLinkScheme | response | appLinksEnabled | boolean
TenancyService | getDeviceAssignment | response | deviceId | string (uuid) | yes | From the path of setDeviceAssignment. (read-only)
TenancyService | getDeviceAssignment | response | ownerOrgUnitId | string (uuid) |  | Who the device belongs to — the cost centre that replaces it when it breaks. (nullable)
TenancyService | getDeviceAssignment | response | custodianPrincipalId | string (uuid) |  | Who is holding it right now. (nullable)
TenancyService | getDeviceAssignment | response | assignedWorkstationId | string (uuid) |  | (nullable)
TenancyService | getDeviceAssignment | response | locationScopePath | string |  | (nullable)
TenancyService | getDeviceAssignment | response | lastSeenLocation | string |  | Reported by the heartbeat; distinct from where it is supposed to be. (read-only; nullable)
TenancyService | getDeviceAssignment | response | assetTag | string |  | (nullable)
TenancyService | getDeviceAssignment | response | acquiredAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | getDeviceAssignment | response | warrantyExpiresAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | getDeviceAssignment | response | assignedAt | string (date-time) |  | (read-only)
TenancyService | getDeviceAssignment | response | scopePath | string |  | The device's own platform.device.scope_path, set by the server on every write (ADAM CR-278, option A, 28 October 2026; CHG-R11TEN-005), so whoever can change the device can change who holds it. (read-only)
TenancyService | getDeviceAssignment | param (path) | deviceId | string (uuid) | yes
AiService | getEffectiveAiPolicy | response | capabilityKey | string | yes
AiService | getEffectiveAiPolicy | response | scopePath | string
AiService | getEffectiveAiPolicy | response | autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getEffectiveAiPolicy | response | autonomyCeiling | integer |  | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getEffectiveAiPolicy | response | rules | array of object | yes
AiService | getEffectiveAiPolicy | response | rules[].rule | AiGovernanceRule |  | One rule of a governance policy version: which actions on which data, under which conditions, get which outcome (AIC-147..160).
AiService | getEffectiveAiPolicy | response | rules[].rule.effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | getEffectiveAiPolicy | response | rules[].rule.capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | getEffectiveAiPolicy | response | rules[].rule.actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | getEffectiveAiPolicy | response | rules[].rule.dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | getEffectiveAiPolicy | response | rules[].rule.purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | getEffectiveAiPolicy | response | rules[].rule.maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | getEffectiveAiPolicy | response | rules[].rule.roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | getEffectiveAiPolicy | response | rules[].rule.environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | getEffectiveAiPolicy | response | rules[].rule.conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | getEffectiveAiPolicy | response | rules[].policyKey | string
AiService | getEffectiveAiPolicy | response | rules[].version | integer
AiService | getEffectiveAiPolicy | response | rules[].scopePath | string
AiService | getEffectiveAiPolicy | response | exceptions | array of AiPolicyException
AiService | getEffectiveAiPolicy | response | exceptions[].id | string (uuid) |  | (read-only)
AiService | getEffectiveAiPolicy | response | exceptions[].policyId | string (uuid) | yes
AiService | getEffectiveAiPolicy | response | exceptions[].capabilityKey | string |  | (nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].reason | string | yes | (max length 2000)
AiService | getEffectiveAiPolicy | response | exceptions[].compensatingControls | array of string
AiService | getEffectiveAiPolicy | response | exceptions[].startsAt | string (date-time) |  | (nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].expiresAt | string (date-time) | yes | Required.
AiService | getEffectiveAiPolicy | response | exceptions[].status | enum (active, expired, revoked) |  | (read-only)
AiService | getEffectiveAiPolicy | response | exceptions[].approvedByPrincipalId | string (uuid) |  | (read-only)
AiService | getEffectiveAiPolicy | response | exceptions[].revokedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].revokedAt | string (date-time) |  | (read-only; nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].revokeReason | string |  | (read-only; nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getEffectiveAiPolicy | response | conflicts | array of object |  | Conflicting rules and the more restrictive result they resolved to (AIC-161).
AiService | getEffectiveAiPolicy | response | conflicts[].description | string
AiService | getEffectiveAiPolicy | response | conflicts[].resolvedTo | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) |  | What the governance decision point returns (design 3.8, AIC-166).
AiService | getEffectiveAiPolicy | response | resolvedAt | string (date-time)
AiService | getEffectiveAiPolicy | param (query) | capabilityKey | string | yes
AiService | getEffectiveAiPolicy | param (query) | scopePath | string
AiService | getEffectiveAiPolicy | param (query) | environment | enum (development, sandbox, staging, production)
AccessService | getEntitlement | response | id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | getEntitlement | response | templateId | string (uuid) | yes | The definition it was issued against.
AccessService | getEntitlement | response | productId | string (uuid) | yes
AccessService | getEntitlement | response | productName | string |  | Read with the entitlement, not stored on it (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009), as TicketStatus.productName: the product's name from catalogue.product (catalogue#productRecords), in the cal… (read-only)
AccessService | getEntitlement | response | venueName | string |  | The venue's name, read from platform.scope by venueId; not stored. (read-only)
AccessService | getEntitlement | response | imageUrl | string (uri) |  | The product's primary image (catalogue.product_media), read with the entitlement; null when the product has none. (read-only; nullable)
AccessService | getEntitlement | response | guestCategory | string |  | The guest category of the order line it was issued for (adult, child, ...), from the line's variant (catalogue#productRecords); null for an entitlement no order line issued. (read-only; nullable)
AccessService | getEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id). (nullable)
AccessService | getEntitlement | response | orderLineId | string (uuid) |  | The order line it was issued for; the ticket list groups cards by it (CHG-R8MIG-009).
AccessService | getEntitlement | response | subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | getEntitlement | response | venueId | string (uuid)
AccessService | getEntitlement | response | scopePath | string
AccessService | getEntitlement | response | mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | getEntitlement | response | changeVersion | integer (int64) | yes | What the offline package's delta counts (ADAM CR-239, option A; Chinmay, 25 October 2026; CHG-R10ORD-011). (read-only)
AccessService | getEntitlement | response | mediaLinkedAt | string (date-time) |  | When the entitlement was put on its media (ADAM CR-226, option A; Chinmay, 25 October 2026; CHG-R10ORD-012): written when mediaCode is set or rotated: at issue (issueOrderEntitlements, onto new media… (read-only; nullable)
AccessService | getEntitlement | response | rotationSecret | string |  | The rotation seed, stored on the entitlement (ADAM CR-167, option A; CHG-R10ORD-010): the Base32 shared secret the rotating code is derived from (getEntitlementCredential rotation.secret, audit R230)… (nullable)
AccessService | getEntitlement | response | credentialFormat | object |  | The credential this entitlement was issued with, resolved once at issue by issueOrderEntitlements: the product's credentialFormatOverride, else the sales channel's ticketCredentialFormat, else platfo… (nullable)
AccessService | getEntitlement | response | status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | getEntitlement | response | statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | getEntitlement | response | validFrom | string (date-time) | yes
AccessService | getEntitlement | response | validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | getEntitlement | response | entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | getEntitlement | response | entriesAllowed | integer |  | (nullable)
AccessService | getEntitlement | response | lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | getEntitlement | response | firstEntryAt | string (date-time) |  | recordedAt of the first admission, written by the same writes as lastEntryAt; it starts a time-bound entitlement's window (DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | getEntitlement | response | timeBoundUntil | string (date-time) |  | Where the template is time-bound, when its window closes: firstEntryAt plus the validity rule's minutesAfterFirstScan (decided 2 October 2026, Chinmay, BO-159; DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | getEntitlement | response | lifecycleLabel | enum (created, pendingFulfillment, active, partiallyUsed, used, expired, suspended, cancelled, …) |  | The Virtual Ticket status in the client's 13 names, mapped onto the entitlement model (decided 2 October 2026, Chinmay, critical set 2, BO-336: "Map the pack's 13 names onto the model; add any missin… (read-only)
AccessService | getEntitlement | response | cancellationKind | enum (voided, refunded, performanceCancelled, superseded) |  | Which act cancelled the entitlement, so the pack's Voided, Refunded and Reissued / superseded are told apart while status keeps the one r1 value cancelled (DEC-266; CHG-CSP-033). (read-only; nullable)
AccessService | getEntitlement | response | frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | getEntitlement | response | suspendedReason | string |  | (nullable)
AccessService | getEntitlement | response | freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | getEntitlement | response | freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | getEntitlement | response | isNameBound | boolean |  | (default False)
AccessService | getEntitlement | response | holderName | string |  | (nullable)
AccessService | getEntitlement | response | sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | getEntitlement | response | issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | getEntitlement | response | supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | getEntitlement | response | walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | getEntitlement | response | facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | getEntitlement | response | invitationId | string (uuid) |  | The invitation that issued it (4 October 2026, CHG-FXC-007): orders.issueInvitation issues the entitlement without an order, because an invitation never enters the order path. (nullable)
AccessService | getEntitlement | param (path) | entitlementId | string (uuid) | yes
AccessService | getEntitlementCredential | response | mediaCode | string
AccessService | getEntitlementCredential | response | credentialFormat | object |  | The entitlement's credentialFormat; platformSignedQr where it is null (CHG-R6-031).
AccessService | getEntitlementCredential | response | payload | string
AccessService | getEntitlementCredential | response | expiresAt | string (date-time) |  | (nullable)
AccessService | getEntitlementCredential | response | rotation | object |  | The time-based seed the rotating code is derived from (audit R230). (nullable)
AccessService | getEntitlementCredential | response | rotation.secret | string | yes | Base32 shared secret.
AccessService | getEntitlementCredential | response | rotation.timeStepSeconds | integer | yes | 30 seconds for an admission QR (Chinmay, 3 October 2026, Block A business rules: GST-055's admission QR rotates every 30 seconds; CHG-RUL-018). (min 10; max 60; default 30)
AccessService | getEntitlementCredential | response | rotation.digits | integer | yes | (min 6; max 10; default 8)
AccessService | getEntitlementCredential | response | rotation.algorithm | enum (SHA1, SHA256, SHA512) | yes | (default SHA256)
AccessService | getEntitlementCredential | response | rotation.validFrom | string (date-time) | yes
AccessService | getEntitlementCredential | response | rotation.validTo | string (date-time) | yes | The seed stops verifying after this.
AccessService | getEntitlementCredential | param (path) | entitlementId | string (uuid) | yes
AccessService | getEntitlementCredential | param (query) | rotate | boolean
AccessService | getEntitlementHistory | param (path) | entitlementId | string (uuid) | yes
VenueOpsService | getExpiringRights | param (query) | withinDays | integer
AccessService | getFacePassEnrolment | response | id | string (uuid) | yes | (read-only)
AccessService | getFacePassEnrolment | response | subjectId | string (uuid) | yes
AccessService | getFacePassEnrolment | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | getFacePassEnrolment | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | getFacePassEnrolment | response | retentionAnchor | object |  | BL-106.
AccessService | getFacePassEnrolment | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | getFacePassEnrolment | response | enrolmentChannel | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk, entryGate) |  | Where the face was actually captured (decided 2 October 2026, Chinmay, BO-186; DEC-236; CHG-CSP-021): source with selfServiceKiosk told apart. (read-only)
AccessService | getFacePassEnrolment | response | consentFormId | string (uuid) |  | The venue's consent form the capture was consented on, and its version below (DEC-128; CHG-CSP-018). (read-only; nullable)
AccessService | getFacePassEnrolment | response | consentFormVersion | integer |  | (read-only; nullable)
AccessService | getFacePassEnrolment | response | capturedAt | string (date-time) | yes
AccessService | getFacePassEnrolment | response | consentPurposeId | string (uuid)
AccessService | getFacePassEnrolment | response | consentGivenAt | string (date-time)
AccessService | getFacePassEnrolment | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | getFacePassEnrolment | response | isActive | boolean |  | (read-only)
AccessService | getFacePassEnrolment | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | getFacePassEnrolment | param (path) | enrolmentId | string (uuid) | yes
FnbService | getFnbDeliveryPolicy | response | id | string (uuid) |  | (read-only)
FnbService | getFnbDeliveryPolicy | response | outletId | string (uuid) | yes
FnbService | getFnbDeliveryPolicy | response | collectionEnabled | boolean |  | (default True)
FnbService | getFnbDeliveryPolicy | response | deliveryEnabled | boolean |  | (default False)
FnbService | getFnbDeliveryPolicy | response | collectionPoint | string |  | (max length 200; nullable)
FnbService | getFnbDeliveryPolicy | response | collectionHoldMinutes | integer |  | (default 20)
FnbService | getFnbDeliveryPolicy | response | asapCollectionMinutes | integer |  | (default 25)
FnbService | getFnbDeliveryPolicy | response | asapDeliveryMinutes | integer |  | (default 45)
FnbService | getFnbDeliveryPolicy | response | slotMinutes | integer |  | (default 30)
FnbService | getFnbDeliveryPolicy | response | minimumOrder | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | deliveryFee | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | radiusKm | number |  | (min 0; nullable)
FnbService | getFnbDeliveryPolicy | response | emiratesServed | array of string
FnbService | getFnbDeliveryPolicy | response | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | getFnbDeliveryPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | getFnbDeliveryPolicy | param (query) | outletId | string (uuid) | yes
FnbService | getFnbDeliveryPolicy | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
FnbService | getFnbOrder | response | id | string (uuid) | yes
FnbService | getFnbOrder | response | orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | getFnbOrder | response | outletId | string (uuid) | yes
FnbService | getFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | getFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | getFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getFnbOrder | response | lines | array of object | yes
FnbService | getFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | getFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | getFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | getFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | getFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | getFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | getFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | getFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | getFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | getFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | getFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | getFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | getFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | getFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | getFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | getFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | getFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | getFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | getFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | getFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | getFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | response | createdAt | string (date-time) | yes
FnbService | getFnbOrder | response | recordedAt | string (date-time)
FnbService | getFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | param (path) | orderId | string (uuid) | yes
WhiteLabelService | getFonts | response | primaryLatin | string | yes
WhiteLabelService | getFonts | response | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getFonts | response | secondaryLatin | string |  | (nullable)
WhiteLabelService | getFonts | response | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getFonts | response | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getFonts | response | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
AiService | getForecast | response | items | array of AiForecastPoint | yes
AiService | getForecast | response | items[].id | string (uuid) |  | (read-only)
AiService | getForecast | response | items[].versionId | string (uuid) | yes
AiService | getForecast | response | items[].scenarioId | string (uuid) |  | Set where the point belongs to a what-if scenario rather than the version itself. (nullable)
AiService | getForecast | response | items[].targetStart | string (date-time) | yes
AiService | getForecast | response | items[].targetEnd | string (date-time)
AiService | getForecast | response | items[].dimensionKey | string |  | Canonical key of the breakdown, e.g. (nullable)
AiService | getForecast | response | items[].p10 | number |  | (nullable)
AiService | getForecast | response | items[].p50 | number | yes
AiService | getForecast | response | items[].p90 | number |  | (nullable)
AiService | getForecast | response | items[].unit | string
AiService | getForecast | response | items[].drivers | object |  | Component decomposition or SHAP contributions, largest first (ADM-506). (nullable)
AiService | getForecast | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getForecast | response | nextCursor | string
AiService | getForecast | response | hasMore | boolean | yes
AiService | getForecast | response | version | AiForecastVersion |  | An immutable forecast version (AIP-032): producer, model version, data cut-off, horizon and status.
AiService | getForecast | response | version.id | string (uuid) |  | (read-only)
AiService | getForecast | response | version.definitionId | string (uuid) | yes
AiService | getForecast | response | version.versionNumber | integer | yes | (min 1)
AiService | getForecast | response | version.module | object |  | The module of the version's definition (AiForecastDefinition.module), copied when the version is produced; the module whose AI publish permission publishForecastVersion requires (CHG-FUP-004). (read-only)
AiService | getForecast | response | version.status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | getForecast | response | version.basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | getForecast | response | version.maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | getForecast | response | version.maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | getForecast | response | version.maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | getForecast | response | version.maturity.sources | array of object
AiService | getForecast | response | version.maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | getForecast | response | version.maturity.limitedHistory | boolean
AiService | getForecast | response | version.maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | getForecast | response | version.producerRef | string
AiService | getForecast | response | version.modelVersion | string |  | (nullable)
AiService | getForecast | response | version.dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | getForecast | response | version.horizonStart | string (date-time)
AiService | getForecast | response | version.horizonEnd | string (date-time)
AiService | getForecast | response | version.qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | getForecast | response | version.publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | getForecast | response | version.publishedAt | string (date-time) |  | (read-only; nullable)
AiService | getForecast | response | version.decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | getForecast | response | version.createdAt | string (date-time) |  | (read-only)
AiService | getForecast | response | version.scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getForecast | response | stale | boolean
AiService | getForecast | param (query) | definitionKey | string | yes
AiService | getForecast | param (query) | versionId | string (uuid)
AiService | getForecast | param (query) | from | string (date-time)
AiService | getForecast | param (query) | to | string (date-time)
AiService | getForecast | param (query) | dimensionKey | string |  | A canonical breakdown key, e.g.
AiService | getForecast | param (query) | scenarioId | string (uuid)
AiService | getForecast | param (query) | pageSize | integer
AiService | getForecast | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | getForecastAccuracy | response | items | array of AiForecastAccuracy | yes
AiService | getForecastAccuracy | response | items[].id | string (uuid) |  | (read-only)
AiService | getForecastAccuracy | response | items[].definitionId | string (uuid) | yes
AiService | getForecastAccuracy | response | items[].versionId | string (uuid) |  | (nullable)
AiService | getForecastAccuracy | response | items[].producerRef | string
AiService | getForecastAccuracy | response | items[].horizonDays | integer | yes | (min 0)
AiService | getForecastAccuracy | response | items[].periodStart | string (date-time) | yes
AiService | getForecastAccuracy | response | items[].periodEnd | string (date-time)
AiService | getForecastAccuracy | response | items[].wape | number |  | (nullable)
AiService | getForecastAccuracy | response | items[].bias | number |  | (nullable)
AiService | getForecastAccuracy | response | items[].intervalCoverage | number |  | Share of actuals inside the 10th-90th percentile band. (min 0; max 1; nullable)
AiService | getForecastAccuracy | response | items[].baselineWape | number |  | (nullable)
AiService | getForecastAccuracy | response | items[].measuredAt | string (date-time) |  | (read-only)
AiService | getForecastAccuracy | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getForecastAccuracy | response | nextCursor | string
AiService | getForecastAccuracy | response | hasMore | boolean | yes
AiService | getForecastAccuracy | param (query) | definitionKey | string | yes
AiService | getForecastAccuracy | param (query) | horizonDays | integer
AiService | getForecastAccuracy | param (query) | from | string (date-time)
AiService | getForecastAccuracy | param (query) | pageSize | integer
AiService | getForecastAccuracy | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | getForm | response | id | string (uuid) | yes | (read-only)
MarketingService | getForm | response | name | string | yes
MarketingService | getForm | response | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | getForm | response | consentPurposes | array of enum (facePass, faceTag, marketing, photography, waiver) |  | What a consentForm consents to (Chinmay, 2 October, batch 4; follows BO-188: biometric capture needs consent on the venue's own form; CHG-CSA-026).
MarketingService | getForm | response | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | getForm | response | fields | array of FormField
MarketingService | getForm | response | fields[].key | string | yes
MarketingService | getForm | response | fields[].label | string | yes
MarketingService | getForm | response | fields[].labelLocalised | object
MarketingService | getForm | response | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | getForm | response | fields[].options | array of string
MarketingService | getForm | response | fields[].isRequired | boolean |  | (default False)
MarketingService | getForm | response | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | getForm | response | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | getForm | response | fields[].showWhen | object |  | (nullable)
MarketingService | getForm | response | fields[].showWhen.field | string
MarketingService | getForm | response | fields[].showWhen.equals | string
MarketingService | getForm | response | fields[].presentation | enum (dropDown, radio, checkBoxes) |  | How a choice is drawn (products module, 16 October 2026 minutes 4.13: the data mask's field types are text, drop-down, radio and check box; CHG-R8PRD-009). (nullable)
MarketingService | getForm | response | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | getForm | response | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | getForm | response | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | getForm | response | appliesToProductIds | array of string (uuid)
MarketingService | getForm | response | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | getForm | response | minimumAge | integer |  | (nullable)
MarketingService | getForm | response | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | getForm | response | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | getForm | response | legalReviewedBy | string |  | (nullable)
MarketingService | getForm | response | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | getForm | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getForm | param (path) | formId | string (uuid) | yes
MarketingService | getForm | param (query) | version | integer
VenueOpsService | getGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | getGameCard | response | kind | string
VenueOpsService | getGameCard | response | venueId | string (uuid) | yes
VenueOpsService | getGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | getGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | getGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | getGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | getGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | getGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | getGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | getGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | getGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | getGameCard | response | id | string (uuid) |  | The card's own id (4 October 2026, CHG-FXC-006): the {cardId} of setGameCardLifecycle, which had no column to match, and the id of the Wallet view wallet.loadGameCredits and wallet.adjustGameCard ret… (read-only)
VenueOpsService | getGameCard | response | walletId | string (uuid) |  | Where the card's credits are held (4 October 2026, CHG-FXC-006). (read-only; nullable)
VenueOpsService | getGameCard | param (path) | cardCode | string | yes
WalletService | getGiftCard | response | cardCode | string | yes
WalletService | getGiftCard | response | kind | string
WalletService | getGiftCard | response | faceValue | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getGiftCard | response | faceValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getGiftCard | response | faceValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getGiftCard | response | faceValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getGiftCard | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getGiftCard | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getGiftCard | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getGiftCard | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getGiftCard | response | status | enum (issued, active, partiallyRedeemed, redeemed, expired, blocked) | yes
WalletService | getGiftCard | response | blockedReason | string |  | (nullable)
WalletService | getGiftCard | response | subjectId | string (uuid) |  | The registered owner, if any (R8 blocker ORDERS-MONEY-C27): the guest named when the card was issued (the buyer, or the guest whose refund became store credit); null for a card sold to nobody in part… (read-only; nullable)
WalletService | getGiftCard | response | issuedAt | string (date-time) | yes
WalletService | getGiftCard | response | activatedAt | string (date-time) |  | (nullable)
WalletService | getGiftCard | response | expiresAt | string (date-time) |  | (nullable)
WalletService | getGiftCard | param (path) | cardCode | string | yes
OrderService | getGroupBooking | response | id | string (uuid) | yes
OrderService | getGroupBooking | response | kind | enum (general, school, corporate, party) |  | (default general)
OrderService | getGroupBooking | response | packageProductId | string |  | The school-trip format or party package. (nullable)
OrderService | getGroupBooking | response | yearGroup | string |  | (max length 40; nullable)
OrderService | getGroupBooking | response | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | getGroupBooking | response | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | getGroupBooking | response | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | getGroupBooking | response | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | getGroupBooking | response | finalHeadcountDueBy | string (date-time) |  | (nullable)
OrderService | getGroupBooking | response | quoteSentAt | string (date-time) |  | (read-only; nullable)
OrderService | getGroupBooking | response | riskAssessmentSentAt | string (date-time) |  | (read-only; nullable)
OrderService | getGroupBooking | response | preferredDate | string (date) |  | The date the guest asked for on requestGroupBooking — what its 409 dateUnavailable is checked against. (nullable)
OrderService | getGroupBooking | response | performanceId | string (uuid) |  | The session, for a timed or session package (DEC-121, Chinmay, 2 October 2026: a date and, for session products, a session; R8 blocker ORDERS-MONEY-C41, CHG-R8MIG-017): a catalogue.performance on pre… (nullable)
OrderService | getGroupBooking | response | orderId | string (uuid) | yes
OrderService | getGroupBooking | response | leaderSubjectId | string (uuid) | yes
OrderService | getGroupBooking | response | organisationName | string |  | (nullable)
OrderService | getGroupBooking | response | expectedSize | integer | yes
OrderService | getGroupBooking | response | confirmedSize | integer |  | (nullable)
OrderService | getGroupBooking | response | minimumSize | integer |  | Below which the group rate does not apply. (nullable)
OrderService | getGroupBooking | response | attendeeCaptureRequired | boolean |  | Whether names are needed before admission. (default False)
OrderService | getGroupBooking | response | attendeeCaptureDueBy | string (date-time) |  | (nullable)
OrderService | getGroupBooking | response | status | enum (provisional, confirmed, namesPending, complete, cancelled) | yes
OrderService | getGroupBooking | response | version | integer |  | The row's version, its ETag (accepted 26 October 2026, Chinmay, ADAM CR-257 option A): 1 on create and bumped on every write; getGroupBooking and updateGroupBooking send it as ETag, and updateGroupBo… (min 1; default 1; read-only)
OrderService | getGroupBooking | param (path) | groupBookingId | string (uuid) | yes
CatalogueService | getGroupPackageDefinition | response | id | string (uuid) |  | (read-only)
CatalogueService | getGroupPackageDefinition | response | productId | string |  | (read-only)
CatalogueService | getGroupPackageDefinition | response | name | string |  | Read from the package's product, not stored here (R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009): catalogue.product.name, in the caller's language. (read-only)
CatalogueService | getGroupPackageDefinition | response | unitPrice | object |  | The product's price per participant (pricingBasis perParticipant) or per package, read from the product's current price; not stored here. (read-only)
CatalogueService | getGroupPackageDefinition | response | unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getGroupPackageDefinition | response | unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getGroupPackageDefinition | response | unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getGroupPackageDefinition | response | minimumSize | integer |  | The smallest group the package is sold to; null means one participant. (min 1; nullable)
CatalogueService | getGroupPackageDefinition | response | kind | enum (school, party, corporate, tourOperator, community) | yes | corporate, tourOperator and community are the group types the approved group-booking screens draw beside school and party (CHG-SGU-024; R8 blocker ORDERS-MONEY-C20, CHG-R8MIG-009).
CatalogueService | getGroupPackageDefinition | response | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | getGroupPackageDefinition | response | durationMinutes | integer | yes | (min 15)
CatalogueService | getGroupPackageDefinition | response | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | getGroupPackageDefinition | response | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | getGroupPackageDefinition | response | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | getGroupPackageDefinition | response | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | getGroupPackageDefinition | response | includes | array of string
CatalogueService | getGroupPackageDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | getGroupPackageDefinition | param (path) | productId | string | yes
CatalogueService | getGroupPackageDefinition | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
FnbService | getGuestBill | response | visitId | string | yes
FnbService | getGuestBill | response | covers | integer
FnbService | getGuestBill | response | lines | array of object | yes
FnbService | getGuestBill | response | lines[].lineId | string | yes
FnbService | getGuestBill | response | lines[].orderId | string
FnbService | getGuestBill | response | lines[].name | string | yes
FnbService | getGuestBill | response | lines[].quantity | integer | yes
FnbService | getGuestBill | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | lines[].categoryCode | string |  | (nullable)
FnbService | getGuestBill | response | lines[].seatNumber | integer |  | (nullable)
FnbService | getGuestBill | response | subtotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | serviceCharge | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | serviceCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | serviceCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | serviceCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | param (path) | sessionId | string (uuid) | yes
CatalogueService | getGuestBundle | response | id | string (uuid) | yes
CatalogueService | getGuestBundle | response | name | string | yes
CatalogueService | getGuestBundle | response | description | string |  | (nullable)
CatalogueService | getGuestBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional)
CatalogueService | getGuestBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | getGuestBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getGuestBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getGuestBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getGuestBundle | response | savingsAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getGuestBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getGuestBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getGuestBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getGuestBundle | response | savingsPercentage | number |  | (nullable)
CatalogueService | getGuestBundle | response | components | array of BundleComponent
CatalogueService | getGuestBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | getGuestBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | getGuestBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | getGuestBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | getGuestBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | getGuestBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | getGuestBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | getGuestBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | getGuestBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | getGuestBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | getGuestBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | getGuestBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | getGuestBundle | response | choiceGroups | array of BundleChoiceGroup
CatalogueService | getGuestBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | getGuestBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | getGuestBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | getGuestBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | getGuestBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | getGuestBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | getGuestBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | getGuestBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | getGuestBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | getGuestBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | getGuestBundle | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | getGuestBundle | response | validTo | string (date-time) |  | (nullable)
CatalogueService | getGuestBundle | param (path) | bundleId | string (uuid) | yes
CatalogueService | getGuestBundle | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
MarketingService | getGuestConsents | response | subjectId | string (uuid) | yes
MarketingService | getGuestConsents | response | purposes | array of object | yes
MarketingService | getGuestConsents | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional, storedPaymentCredential, facePassEnrolment) | yes | storedPaymentCredential (a card saved for later, storePaymentToken) and facePassEnrolment (a face enrolled for entry, enrolFacePass) are purposes of their own (R8 blocker ORDERS-MONEY-C21, CHG-R8MIG-…
MarketingService | getGuestConsents | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | getGuestConsents | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getGuestConsents | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | getGuestConsents | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | getGuestConsents | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | getGuestConsents | param (path) | subjectId | string (uuid) | yes
MarketingService | getGuestConversation | response | id | string (uuid) | yes
MarketingService | getGuestConversation | response | state | ConversationState: enum (withAssistant, queued, withAgent, waitingOnGuest, resolved, abandoned, timedOut) | yes | withAssistant and queued are different, and the second has a person waiting.
MarketingService | getGuestConversation | response | queuePosition | integer |  | Place among the unclaimed conversations in its queue, from the live agent queue (audit R149). (read-only; nullable)
MarketingService | getGuestConversation | response | estimatedWaitSeconds | integer |  | From the live agent queue, the conversations ahead divided across that queue's agents online now (audit R149). (read-only; nullable)
MarketingService | getGuestConversation | response | messages | array of GuestConversationMessage | yes | Oldest first; after afterMessageId when it was sent
MarketingService | getGuestConversation | response | messages[].id | string (uuid) | yes
MarketingService | getGuestConversation | response | messages[].sender | enum (guest, agent, assistant, system) | yes
MarketingService | getGuestConversation | response | messages[].body | string | yes
MarketingService | getGuestConversation | response | messages[].attachments | array of object
MarketingService | getGuestConversation | response | messages[].attachments[].assetId | string (uuid)
MarketingService | getGuestConversation | response | messages[].attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | getGuestConversation | response | messages[].sentAt | string (date-time) | yes
MarketingService | getGuestConversation | param (path) | conversationId | string (uuid) | yes
MarketingService | getGuestConversation | param (query) | afterMessageId | string (uuid) |  | Only the messages sent after this one, oldest first, so a polling chat fetches what is new
CatalogueService | getGuestCouponCode | response | code | string | yes
CatalogueService | getGuestCouponCode | response | status | CouponStatus: enum (issued, assigned, redeemed, expired, voided) | yes
CatalogueService | getGuestCouponCode | response | isValid | boolean |  | True when the code can be applied now; else invalidReason says why.
CatalogueService | getGuestCouponCode | response | invalidReason | enum (expired, notYetValid, voided, alreadyRedeemed, notAssignedToGuest, wrongVenue) |  | (nullable)
CatalogueService | getGuestCouponCode | response | discount | Discount
CatalogueService | getGuestCouponCode | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | getGuestCouponCode | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | getGuestCouponCode | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getGuestCouponCode | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getGuestCouponCode | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getGuestCouponCode | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getGuestCouponCode | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getGuestCouponCode | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getGuestCouponCode | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getGuestCouponCode | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getGuestCouponCode | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | getGuestCouponCode | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | getGuestCouponCode | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | getGuestCouponCode | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | getGuestCouponCode | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | getGuestCouponCode | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | getGuestCouponCode | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | getGuestCouponCode | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getGuestCouponCode | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getGuestCouponCode | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getGuestCouponCode | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | getGuestCouponCode | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | getGuestCouponCode | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | getGuestCouponCode | response | validTo | string (date-time) |  | (nullable)
CatalogueService | getGuestCouponCode | param (path) | code | string | yes
CatalogueService | getGuestCouponCode | param (query) | venueId | string (uuid) |  | The venue the guest is buying at, so wrongVenue can be answered; a guest session carries no venue.
MarketingService | getGuestLoyalty | response | leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | getGuestLoyalty | response | subjectId | string (uuid) | yes
MarketingService | getGuestLoyalty | response | programmeId | string (uuid) | yes
MarketingService | getGuestLoyalty | response | pointsBalance | integer | yes
MarketingService | getGuestLoyalty | response | lifetimePoints | integer
MarketingService | getGuestLoyalty | response | tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | getGuestLoyalty | response | tierCode | string | yes
MarketingService | getGuestLoyalty | response | tierName | string
MarketingService | getGuestLoyalty | response | pointsToNextTier | integer |  | (nullable)
MarketingService | getGuestLoyalty | response | nextExpiryPoints | integer |  | (nullable)
MarketingService | getGuestLoyalty | response | nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | getGuestLoyalty | param (path) | subjectId | string (uuid) | yes
MarketingService | getGuestLoyalty | param (query) | programmeId | string (uuid) | yes | Which programme.
FnbService | getGuestMenu | response | outletId | string (uuid) | yes
FnbService | getGuestMenu | response | menuId | string (uuid) | yes
FnbService | getGuestMenu | response | name | string | yes
FnbService | getGuestMenu | response | inForceUntil | string (date-time) | yes | When this menu stops applying. (nullable)
FnbService | getGuestMenu | response | currency | string |  | (pattern ^[A-Z]{3}$)
FnbService | getGuestMenu | response | currencyScale | integer
FnbService | getGuestMenu | response | sections | array of object | yes
FnbService | getGuestMenu | response | sections[].name | string
FnbService | getGuestMenu | response | sections[].sortOrder | integer
FnbService | getGuestMenu | response | sections[].items | array of object
FnbService | getGuestMenu | response | sections[].items[].menuItemId | string (uuid) | yes
FnbService | getGuestMenu | response | sections[].items[].name | string | yes
FnbService | getGuestMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestMenu | response | sections[].items[].imageAssetRef | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].isAvailable | boolean | yes | Marked, not removed.
FnbService | getGuestMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) | yes | Always present.
FnbService | getGuestMenu | response | sections[].items[].allergenDetail | object |  | What the dish contains and what it may contain, told apart (3 October 2026, CHG-R1S-022: the kiosk and guest menus promise the difference and the flat list cannot carry it).
FnbService | getGuestMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].modifierGroups | array of ModifierGroup
FnbService | getGuestMenu | param (path) | outletId | string (uuid) | yes
FnbService | getGuestMenu | param (query) | at | string (date-time) |  | Evaluate menu availability at this time rather than now.
FnbService | getGuestMenu | param (query) | language | string
FnbService | getGuestMenu | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
FnbService | getGuestOrderStatus | response | orderId | string | yes
FnbService | getGuestOrderStatus | response | orderNumber | string
FnbService | getGuestOrderStatus | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getGuestOrderStatus | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getGuestOrderStatus | response | isReadyForCollection | boolean
FnbService | getGuestOrderStatus | response | lines | array of object | yes | Per-line status.
FnbService | getGuestOrderStatus | response | lines[].name | string
FnbService | getGuestOrderStatus | response | lines[].quantity | integer
FnbService | getGuestOrderStatus | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | getGuestOrderStatus | param (path) | orderId | string (uuid) | yes
OrderService | getGuestRefundPolicy | response | venueId | string (uuid) | yes
OrderService | getGuestRefundPolicy | response | timeBands | array of object | yes | Refundable percentage by time before the performance, as on RefundPolicy.
OrderService | getGuestRefundPolicy | response | timeBands[].hoursBefore | integer | yes | (min 0)
OrderService | getGuestRefundPolicy | response | timeBands[].percentage | number | yes | (min 0; max 100)
OrderService | getGuestRefundPolicy | response | allowPartial | boolean | yes
OrderService | getGuestRefundPolicy | response | refundWindowDays | integer | yes | As on RefundPolicy; null means no window. (min 0; nullable)
OrderService | getGuestRefundPolicy | param (path) | venueId | string (uuid) | yes
IdentityService | getGuestSession | response | subjectId | string (uuid) | yes
IdentityService | getGuestSession | response | displayName | string |  | (nullable)
IdentityService | getGuestSession | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | getGuestSession | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | getGuestSession | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | getGuestSession | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | getGuestSession | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | getGuestSession | response | mfaMethods[].id | string (uuid) | yes
IdentityService | getGuestSession | response | mfaMethods[].principalId | string (uuid) |  | The principal who enrolled it; null for a guest. (read-only; nullable)
IdentityService | getGuestSession | response | mfaMethods[].subjectId | string (uuid) |  | The guest who enrolled it; null for a principal. (read-only; nullable)
IdentityService | getGuestSession | response | mfaMethods[].secret | string |  | The totp shared secret, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | getGuestSession | response | mfaMethods[].destination | string |  | The full phone number (smsOtp) or email (emailOtp) the code goes to, encrypted with the tenant's field key (ADR-0063); null for other kinds. (nullable)
IdentityService | getGuestSession | response | mfaMethods[].pendingExpiresAt | string (date-time) |  | While isActive is false, when the unconfirmed enrolment lapses; null once verified. (nullable)
IdentityService | getGuestSession | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | getGuestSession | response | mfaMethods[].label | string |  | (nullable)
IdentityService | getGuestSession | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | getGuestSession | response | mfaMethods[].isActive | boolean | yes
IdentityService | getGuestSession | response | mfaMethods[].isPrimary | boolean
IdentityService | getGuestSession | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | getGuestSession | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | getGuestSession | response | homeCellName | string |  | (nullable)
IdentityService | getGuestSession | response | preferredLanguage | string |  | (nullable)
IdentityService | getGuestSession | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
AiService | getGuidedChoiceSuggestion | response | id | string (uuid) |  | (read-only)
AiService | getGuidedChoiceSuggestion | response | venueId | string (uuid) | yes
AiService | getGuidedChoiceSuggestion | response | trigger | enum (productsUploaded, mappedProductWithdrawn, productsUncovered, manual) | yes
AiService | getGuidedChoiceSuggestion | response | status | enum (running, proposed, noSuggestion, failed, superseded) | yes | (read-only)
AiService | getGuidedChoiceSuggestion | response | productCount | integer |  | (min 0; read-only)
AiService | getGuidedChoiceSuggestion | response | questions | array of object |  | The questions chosen, in the order asked. (read-only)
AiService | getGuidedChoiceSuggestion | response | questions[].attribute | string |  | The catalogue attribute asked about: audience, level, minimum height or age, duration, price band, format, language.
AiService | getGuidedChoiceSuggestion | response | questions[].order | integer |  | (min 1)
AiService | getGuidedChoiceSuggestion | response | questions[].split | object |  | How evenly it divides the bookable products: products per answer.
AiService | getGuidedChoiceSuggestion | response | questions[].droppedBecause | string |  | Set where an attribute was considered and dropped (an answer would leave nothing bookable). (nullable)
AiService | getGuidedChoiceSuggestion | response | questions[].answers | array of object
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].value | string
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].leadsTo | enum (product, category, flow)
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].targetRef | string
AiService | getGuidedChoiceSuggestion | response | wordingSource | enum (model, attributeNames) |  | Where the text came from. (read-only)
AiService | getGuidedChoiceSuggestion | response | modelVersion | string |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | promptTemplateVersion | string |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | guidedChoiceId | string (uuid) |  | The white-label draft GuidedChoice it produced. (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | createdAt | string (date-time) |  | (read-only)
AiService | getGuidedChoiceSuggestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getGuidedChoiceSuggestion | param (path) | suggestionId | string (uuid) | yes
FnbService | getHaccpStatus | response | checksDue | integer
FnbService | getHaccpStatus | response | checksMissed | integer
FnbService | getHaccpStatus | response | openActions | integer
FnbService | getHaccpStatus | response | unsignedActions | integer
FnbService | getHaccpStatus | response | oldestOpenActionAgeHours | integer |  | (nullable)
FnbService | getHaccpStatus | response | lastInspectionAt | string (date-time) |  | (nullable)
WhiteLabelService | getHomepageLayout | response | templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | getHomepageLayout | response | landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | getHomepageLayout | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getHomepageLayout | response | sections | array of object | yes
WhiteLabelService | getHomepageLayout | response | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getHomepageLayout | response | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getHomepageLayout | response | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getHomepageLayout | response | sections[].sortOrder | integer | yes
WhiteLabelService | getHomepageLayout | response | sections[].isVisible | boolean | yes
WhiteLabelService | getHomepageLayout | response | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getHomepageLayout | response | sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | getHomepageLayout | response | sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | getHomepageLayout | response | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
FnbService | getKitchenSla | response | outletId | string (uuid) |  | The outlet, from the path. (read-only)
FnbService | getKitchenSla | response | targets | array of object
FnbService | getKitchenSla | response | targets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getKitchenSla | response | targets[].targetMinutes | integer | yes | (min 1)
FnbService | getKitchenSla | response | targets[].warnAtPercent | integer |  | (default 80)
FnbService | getKitchenSla | response | priorityWeights | object |  | The weight of each signal the board names — age, promise time, table stage, a VIP marker.
FnbService | getKitchenSla | response | priorityWeights.age | integer |  | (min 0)
FnbService | getKitchenSla | response | priorityWeights.targetReadyAt | integer |  | Promise time. (min 0)
FnbService | getKitchenSla | response | priorityWeights.tableStage | integer |  | (min 0)
FnbService | getKitchenSla | response | priorityWeights.vip | integer |  | (min 0)
FnbService | getKitchenSla | param (path) | outletId | string (uuid) | yes
CatalogueService | getLatestBundle | response | version | string | yes | The venue's bundle number: a per-venue integer, 1 for the first publish and one more than the venue's highest for each publish after, as its decimal string; unique with venueId (ADAM CR-110, option 1…
CatalogueService | getLatestBundle | response | venueId | string (uuid) | yes
CatalogueService | getLatestBundle | response | note | string |  | The publisher's note from publishBundle's body; BundleSummary.note (ADAM CR-110, option 1; CHG-R10CAT-010). (max length 500; read-only; nullable)
CatalogueService | getLatestBundle | response | publishedAt | string (date-time) |  | When the bundle was published; BundleSummary.publishedAt (CHG-R8MIG-015). (read-only; nullable)
CatalogueService | getLatestBundle | response | publishedBy | string (uuid) |  | Who published it; BundleSummary.publishedBy (CHG-R8MIG-015). (read-only; nullable)
CatalogueService | getLatestBundle | response | isDelta | boolean | yes
CatalogueService | getLatestBundle | response | baseVersion | string |  | Present when isDelta. (nullable)
CatalogueService | getLatestBundle | response | signature | string | yes | Detached signature over contentHash.
CatalogueService | getLatestBundle | response | signatureKeyId | string | yes
CatalogueService | getLatestBundle | response | contentHash | string | yes
CatalogueService | getLatestBundle | response | staleAfter | string (date-time) | yes
CatalogueService | getLatestBundle | response | payload | object | yes | Products, variants, price lists, prices, tax codes, events, performances, envelope definitions, data mask field definitions and the venue's sale boards.
CatalogueService | getLatestBundle | response | payload.saleBoards | array of object |  | The venue's sale boards as tenancy.listSaleBoards returns them, read from platform.sale_board when the bundle is snapshotted (decided 28 September, audit R129 (4)).
CatalogueService | getLatestBundle | param (query) | since | string |  | Applied bundle version.
CatalogueService | getLatestBundle | param (header) | If-None-Match | string
MarketingService | getLoyaltyPosition | response | subjectId | string (uuid)
MarketingService | getLoyaltyPosition | response | programmeId | string (uuid)
MarketingService | getLoyaltyPosition | response | pointsBalance | integer
MarketingService | getLoyaltyPosition | response | pointsPending | integer |  | Earned and not yet cleared — a purchase inside the refund window.
MarketingService | getLoyaltyPosition | response | tier | string
MarketingService | getLoyaltyPosition | response | nextTier | string |  | The name of the next MarketingProgrammeTier by rank above the guest's current tier, resolved at read. (nullable)
MarketingService | getLoyaltyPosition | response | pointsToNextTier | integer |  | (nullable)
MarketingService | getLoyaltyPosition | response | expiringPoints | integer
MarketingService | getLoyaltyPosition | response | expiringAt | string (date-time) |  | Points that lapse unannounced are a complaint. (nullable)
MarketingService | getLoyaltyPosition | param (query) | programmeId | string (uuid) | yes | Which programme.
VenueOpsService | getMapResourceAvailability | response | mapId | string (uuid) | yes
VenueOpsService | getMapResourceAvailability | response | mapVersion | integer | yes | The published venue-map version the placements were read from; the client checks it against the map it cached.
VenueOpsService | getMapResourceAvailability | response | from | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | response | to | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | response | totals | object
VenueOpsService | getMapResourceAvailability | response | totals.total | integer
VenueOpsService | getMapResourceAvailability | response | totals.available | integer
VenueOpsService | getMapResourceAvailability | response | totals.held | integer
VenueOpsService | getMapResourceAvailability | response | totals.booked | integer
VenueOpsService | getMapResourceAvailability | response | totals.unavailable | integer
VenueOpsService | getMapResourceAvailability | response | nextAvailableDate | string (date) |  | The first date after from, within 30 days, with at least one free resource; null when this window already has one or nothing is free within the horizon. (nullable)
VenueOpsService | getMapResourceAvailability | response | resources | array of object | yes
VenueOpsService | getMapResourceAvailability | response | resources[].resourceId | string (uuid) | yes
VenueOpsService | getMapResourceAvailability | response | resources[].placedResourceId | string (uuid) |  | The venue-map.PlacedResource it was read from.
VenueOpsService | getMapResourceAvailability | response | resources[].label | string | yes | As on the map, e.g.
VenueOpsService | getMapResourceAvailability | response | resources[].kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) |  | BL-135.
VenueOpsService | getMapResourceAvailability | response | resources[].zone | string
VenueOpsService | getMapResourceAvailability | response | resources[].capacity | integer
VenueOpsService | getMapResourceAvailability | response | resources[].priceBandCode | string
VenueOpsService | getMapResourceAvailability | response | resources[].variantId | string (uuid) |  | What the cart line names to buy it.
VenueOpsService | getMapResourceAvailability | response | resources[].price | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getMapResourceAvailability | response | resources[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getMapResourceAvailability | response | resources[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getMapResourceAvailability | response | resources[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getMapResourceAvailability | response | resources[].status | enum (available, held, booked, unavailable) | yes | unavailable covers maintenance, a blackout, a block and a placement marked not bookable; the map greys all of them the same way.
VenueOpsService | getMapResourceAvailability | param (query) | mapId | string (uuid) | yes | The venue-map.VenueMap whose placed resources to report.
VenueOpsService | getMapResourceAvailability | param (query) | from | string (date-time) | yes | Start of the window.
VenueOpsService | getMapResourceAvailability | param (query) | to | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | param (query) | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) |  | Only resources of this kind, e.g.
VenueOpsService | getMapResourceAvailability | param (query) | minCapacity | integer |  | Only resources that seat or hold at least this many guests (capacity), so a party can narrow the map to cabanas big enough for it (r8 walk of tickets 28163 and 28204; lead decision of 20 October 2026…
VenueOpsService | getMapResourceAvailability | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
VenueOpsService | getMediaAsset | response | id | string (uuid) | yes
VenueOpsService | getMediaAsset | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | getMediaAsset | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | getMediaAsset | response | filename | string | yes
VenueOpsService | getMediaAsset | response | contentType | string | yes
VenueOpsService | getMediaAsset | response | sizeBytes | integer | yes
VenueOpsService | getMediaAsset | response | title | LocalisedText
VenueOpsService | getMediaAsset | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | getMediaAsset | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | getMediaAsset | response | width | integer |  | (nullable)
VenueOpsService | getMediaAsset | response | height | integer |  | (nullable)
VenueOpsService | getMediaAsset | response | hasTransparency | boolean |  | Whether the image has an alpha channel with any pixel not fully opaque, recorded from the file when the upload completes; null for a file that is not an image (ADAM CR-106, option 1; CHG-R10TEN-012). (read-only; nullable)
VenueOpsService | getMediaAsset | response | durationSeconds | number |  | (nullable)
VenueOpsService | getMediaAsset | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | getMediaAsset | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | getMediaAsset | response | tags | array of string
VenueOpsService | getMediaAsset | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | getMediaAsset | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | getMediaAsset | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | getMediaAsset | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | getMediaAsset | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | getMediaAsset | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | getMediaAsset | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | getMediaAsset | response | rights.licensor | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | getMediaAsset | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | getMediaAsset | response | rights.attributionText | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | getMediaAsset | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | getMediaAsset | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | getMediaAsset | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | getMediaAsset | response | isRightsExpired | boolean
VenueOpsService | getMediaAsset | response | version | integer
VenueOpsService | getMediaAsset | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | getMediaAsset | response | createdAt | string (date-time) | yes
VenueOpsService | getMediaAsset | response | extractedText | string |  | The text pulled out of an uploaded document (R8 blocker ORDERS-MONEY-C19): written by the upload's processing job once text extraction finishes (PDF, Word and plain-text kinds), replaced when the fil… (read-only; nullable)
VenueOpsService | getMediaAsset | response | releasedByPrincipalId | string (uuid) |  | The reviewer who released the asset from quarantined (R8 blocker ORDERS-MONEY-C24, CHG-R8MIG-022); null if it never was. (read-only; nullable)
VenueOpsService | getMediaAsset | response | releasedAt | string (date-time) |  | When it was released from quarantined. (read-only; nullable)
VenueOpsService | getMediaAsset | response | derivatives | array of object |  | Generated from the original, never uploaded separately.
VenueOpsService | getMediaAsset | response | derivatives[].label | string
VenueOpsService | getMediaAsset | response | derivatives[].width | integer
VenueOpsService | getMediaAsset | response | derivatives[].height | integer
VenueOpsService | getMediaAsset | response | derivatives[].sizeBytes | integer
VenueOpsService | getMediaAsset | response | derivatives[].url | string
VenueOpsService | getMediaAsset | response | usage | array of MediaUsage |  | Every place this asset is referenced.
VenueOpsService | getMediaAsset | response | usage[].extractedText | string |  | Not written; read MediaAsset.extractedText (R8 blocker ORDERS-MONEY-C19).
VenueOpsService | getMediaAsset | response | usage[].id | string (uuid) |  | Added 20 August. (read-only)
VenueOpsService | getMediaAsset | response | usage[].surface | enum (tenantBranding, homepageBanner, promoBlock, contentPage, product, event, menuItem, merchandise, …) | yes
VenueOpsService | getMediaAsset | response | usage[].referenceId | string | yes
VenueOpsService | getMediaAsset | response | usage[].label | string
VenueOpsService | getMediaAsset | response | usage[].isLive | boolean |  | True where the referencing surface is published to guests.
VenueOpsService | getMediaAsset | response | collections | array of object
VenueOpsService | getMediaAsset | response | collections[].id | string (uuid)
VenueOpsService | getMediaAsset | response | collections[].name | string
VenueOpsService | getMediaAsset | response | previousVersions | array of object
VenueOpsService | getMediaAsset | response | previousVersions[].version | integer
VenueOpsService | getMediaAsset | response | previousVersions[].replacedAt | string (date-time)
VenueOpsService | getMediaAsset | response | previousVersions[].replacedByPrincipalId | string (uuid)
VenueOpsService | getMediaAsset | param (path) | mediaId | string (uuid) | yes
OrderService | getMediaEntitlements | response | mediaCode | string | yes
OrderService | getMediaEntitlements | response | mediaKind | enum (qr, wristband, card, nfc, mobilePass) |  | From the entitlements' credentialFormat (CR-196): platformSignedQr, staticQr or null (which is platformSignedQr, CHG-R6-031) is qr, and rfidCard is card.
OrderService | getMediaEntitlements | response | subjectId | string (uuid) |  | (nullable)
OrderService | getMediaEntitlements | response | isValid | boolean | yes | True when at least one entitlement on the code counts (see the schema's description).
OrderService | getMediaEntitlements | response | invalidReason | string |  | Null while isValid. (nullable)
OrderService | getMediaEntitlements | response | canAcceptMore | boolean |  | False where the media has been surrendered, expired or blocked.
OrderService | getMediaEntitlements | response | entitlements | array of object | yes
OrderService | getMediaEntitlements | response | entitlements[].entitlementId | string (uuid)
OrderService | getMediaEntitlements | response | entitlements[].name | string
OrderService | getMediaEntitlements | response | entitlements[].kind | enum (admission, locker, fnb, retail, parking, rental, experience, membership) |  | The product's kind (catalogue.Product.kind, read through catalogue#productRecords by the entitlement's productId), mapped onto these values (ADAM CR-226, option A; Chinmay, 25 October 2026; CHG-R10OR…
OrderService | getMediaEntitlements | response | entitlements[].orderId | string (uuid)
OrderService | getMediaEntitlements | response | entitlements[].addedAt | string (date-time) |  | When the entitlement was put on this media: access.entitlement.media_linked_at, written when the media code is set or rotated (ADAM CR-226).
OrderService | getMediaEntitlements | response | entitlements[].status | object |  | Replaced isRedeemed on 17 August.
OrderService | getMediaEntitlements | response | entitlements[].entriesUsed | integer
OrderService | getMediaEntitlements | response | entitlements[].entriesAllowed | integer |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].redeemedAt | string (date-time) |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].transferredToSubjectId | string (uuid) |  | The subjectId of the entitlement whose supersedesEntitlementId names this one with issuedVia transfer (ADAM CR-226), read through access#entitlementRecords; null when it was not transferred. (nullable)
OrderService | getMediaEntitlements | response | entitlements[].validTo | string (date-time) |  | (nullable)
OrderService | getMediaEntitlements | param (path) | mediaCode | string | yes | The QR, wristband or card the guest is already carrying.
WhiteLabelService | getModuleEnablement | param (header) | X-Tenant-Id | string (uuid) |  | Which tenant a call acts in, where one cell holds many tenant databases (ADR-0038; R8 blocker fix, APPROVALS-TENANCY-C44).
MarketingService | getMyCase | response | id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | getMyCase | response | caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | getMyCase | response | subjectId | string (uuid) |  | (nullable)
MarketingService | getMyCase | response | guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | getMyCase | response | subject | string | yes | The case's one-line title, not a person.
MarketingService | getMyCase | response | kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | getMyCase | response | channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | getMyCase | response | recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | getMyCase | response | syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | getMyCase | response | categoryId | string (uuid) |  | (nullable)
MarketingService | getMyCase | response | queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | getMyCase | response | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | getMyCase | response | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | getMyCase | response | priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | getMyCase | response | assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | getMyCase | response | venueId | string (uuid) |  | (nullable)
MarketingService | getMyCase | response | relatedOrderId | string |  | (nullable)
MarketingService | getMyCase | response | slaDueAt | string (date-time) |  | (nullable)
MarketingService | getMyCase | response | isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | getMyCase | response | slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | getMyCase | response | escalationCount | integer
MarketingService | getMyCase | response | createdAt | string (date-time) | yes
MarketingService | getMyCase | response | resolvedAt | string (date-time) |  | (nullable)
MarketingService | getMyCase | response | description | string
MarketingService | getMyCase | response | resolutionNote | string |  | (nullable)
MarketingService | getMyCase | response | messages | array of CaseMessage
MarketingService | getMyCase | response | messages[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
MarketingService | getMyCase | response | messages[].resolution | string |  | What was actually done about it.
MarketingService | getMyCase | response | messages[].id | string | yes
MarketingService | getMyCase | response | messages[].body | string | yes
MarketingService | getMyCase | response | messages[].isInternal | boolean | yes
MarketingService | getMyCase | response | messages[].authorKind | enum (agent, guest, system, ai) | yes
MarketingService | getMyCase | response | messages[].authorPrincipalId | string (uuid) |  | (nullable)
MarketingService | getMyCase | response | messages[].channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getMyCase | response | messages[].attachmentRefs | array of string
MarketingService | getMyCase | response | messages[].recordedAt | string (date-time) | yes | Device time — addCaseMessage is offline-capable.
MarketingService | getMyCase | response | messages[].syncedAt | string (date-time) |  | Server time the message arrived. (read-only)
MarketingService | getMyCase | response | messages[].caseId | string (uuid) | yes | The case this message belongs to, from the path of addCaseMessage (the opening one, createCase). (read-only)
MarketingService | getMyCase | param (path) | caseId | string (uuid) | yes
CatalogueService | getMyMemberships | param (query) | includeLapsed | boolean
MarketingService | getMyProfile | response | profile | GuestProfile | yes
MarketingService | getMyProfile | response | profile.id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | getMyProfile | response | profile.subjectId | string (uuid) | yes | Opaque reference.
MarketingService | getMyProfile | response | profile.displayName | string |  | (nullable)
MarketingService | getMyProfile | response | profile.email | string |  | (nullable)
MarketingService | getMyProfile | response | profile.phone | string |  | (nullable)
MarketingService | getMyProfile | response | profile.preferredLanguage | string |  | (nullable)
MarketingService | getMyProfile | response | profile.preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) |  | Left out where the guest has no preferred channel: a guest who chose none in updateMyProfile is stored as null and answered without this field (ADAM CR-291, option B; CHG-R11GST-002).
MarketingService | getMyProfile | response | profile.guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | getMyProfile | response | profile.tags | array of string
MarketingService | getMyProfile | response | profile.engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | getMyProfile | response | profile.engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | getMyProfile | response | profile.lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | getMyProfile | response | profile.lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | getMyProfile | response | profile.lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | getMyProfile | response | profile.lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | getMyProfile | response | profile.visitCount | integer
MarketingService | getMyProfile | response | profile.lastVisitAt | string (date-time) |  | (nullable)
MarketingService | getMyProfile | response | profile.isActive | boolean | yes
MarketingService | getMyProfile | response | profile.mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | getMyProfile | response | profile.mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getMyProfile | response | preferences | GuestPreferences |  | What the guest likes, kept apart from what they permit (consent) and from who they are (the profile).
MarketingService | getMyProfile | response | preferences.id | string (uuid) |  | (read-only)
MarketingService | getMyProfile | response | preferences.subjectId | string (uuid) |  | (read-only)
MarketingService | getMyProfile | response | preferences.seatingPreference | string |  | (max length 200; nullable)
MarketingService | getMyProfile | response | preferences.drinkPreferences | array of string
MarketingService | getMyProfile | response | preferences.dietary | array of string |  | Also written by updateMyProfile.
MarketingService | getMyProfile | response | preferences.accessibility | array of string |  | Also written by updateMyProfile.
MarketingService | getMyProfile | response | preferences.preferredChannel | object |  | Stored on the profile (GuestProfile.preferredChannel) — carried here because the preference screen edits it beside the rest.
MarketingService | getMyProfile | response | preferences.updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getNavigation | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getNavigation | response | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getNavigation | response | items | array of object | yes | (max items 12)
WhiteLabelService | getNavigation | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getNavigation | response | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getNavigation | response | items[].icon | string
WhiteLabelService | getNavigation | response | items[].target | LinkTarget | yes
WhiteLabelService | getNavigation | response | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | getNavigation | response | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getNavigation | response | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | getNavigation | response | items[].target.contentPageId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.productId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.eventId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | getNavigation | response | items[].target.url | string
WhiteLabelService | getNavigation | response | items[].isVisible | boolean | yes | At most five may be visible when kind is bottomNavigation; the rest overflow.
WhiteLabelService | getNavigation | response | items[].sortOrder | integer | yes
WhiteLabelService | getNavigation | response | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getNavigation | response | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getNavigation | response | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
VenueOpsService | getNextTransportDeparture | response | departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getNextTransportDeparture | response | performanceId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getNextTransportDeparture | response | routeCode | string |  | The price card's label, e.g.
VenueOpsService | getNextTransportDeparture | response | departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | getNextTransportDeparture | response | arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | getNextTransportDeparture | response | durationMinutes | integer | yes | (min 0)
VenueOpsService | getNextTransportDeparture | response | period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | getNextTransportDeparture | response | seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | getNextTransportDeparture | response | fitsParty | boolean
VenueOpsService | getNextTransportDeparture | response | fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getNextTransportDeparture | response | fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getNextTransportDeparture | response | fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getNextTransportDeparture | response | fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getNextTransportDeparture | response | partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getNextTransportDeparture | response | partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getNextTransportDeparture | response | partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getNextTransportDeparture | response | partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getNextTransportDeparture | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | param (query) | toStationId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | param (query) | after | string (date-time)
VenueOpsService | getNextTransportDeparture | param (query) | passengers | array of string |  | As on searchTransportDepartures.
OrderService | getOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | getOrder | response | orderAccessToken | string |  | What lets the device that just checked out read the order it paid for (decided 20 October 2026, Chinmay, R8 blocker cause IDENTITY-C52, option A; CHG-R8SPN-025). (read-only; nullable)
OrderService | getOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | getOrder | response | channel | object | yes | Where it came from.
OrderService | getOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | getOrder | response | venueId | string (uuid) | yes
OrderService | getOrder | response | scopePath | string | yes
OrderService | getOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | getOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | getOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | getOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | getOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | getOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | getOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | getOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | getOrder | response | droppedPromotions[].name | string
OrderService | getOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | getOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | getOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines | array of OrderLine | yes
OrderService | getOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getOrder | response | lines[].variantId | string (uuid) | yes
OrderService | getOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getOrder | response | lines[].performanceId | string (uuid)
OrderService | getOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getOrder | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | getOrder | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | getOrder | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | getOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | getOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].holderName | string |  | (nullable)
OrderService | getOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | getOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | getOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | getOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | getOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | getOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | getOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | getOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | getOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | getOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | getOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | getOrder | response | payments | array of Payment
OrderService | getOrder | response | payments[].tipAmount | object |  | The tip recorded against this payment (addTip; r8 walk fix, CHG-R8WFC-002). (read-only; nullable)
OrderService | getOrder | response | payments[].tipAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].tipAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tipAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].tipSource | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) |  | Where the tip came from (addTip's source); null with no tip. (read-only; nullable)
OrderService | getOrder | response | payments[].tipAllocatedToPrincipalId | string (uuid) |  | The staff member the venue allocates the tip to (addTip's allocateToPrincipalId); null when tips are pooled or there is no tip. (read-only; nullable)
OrderService | getOrder | response | payments[].tipRecordedAt | string (date-time) |  | When the till or app recorded the tip (addTip's recordedAt); null with no tip. (read-only; nullable)
OrderService | getOrder | response | payments[].tipRecordedByPrincipalId | string (uuid) |  | Who recorded it, from the session (the attribution a cashier-entered tip needs, as a manual discount does); null with no tip. (read-only; nullable)
OrderService | getOrder | response | payments[].id | string (uuid) | yes
OrderService | getOrder | response | payments[].orderId | string (uuid) | yes
OrderService | getOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | getOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale, its ISO 4217 minor units from the kernel's fixed list where it is not the currency the venue trades in (ADAM CR-192, option A; CHG-R10ORD-0…
OrderService | getOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | getOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | getOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | getOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | getOrder | response | payments[].providerName | string |  | (nullable)
OrderService | getOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | getOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | getOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | getOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | getOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | getOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | getOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | getOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | principalId | string (uuid)
OrderService | getOrder | response | workstationId | string (uuid)
OrderService | getOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | getOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | getOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | getOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil, or the venue's next business-day cut-off (VenueSettings.businessDayCutoff) when the cashier sent none (CHG-GDL… (read-only; nullable)
OrderService | getOrder | response | createdAt | string (date-time) | yes
OrderService | getOrder | response | recordedAt | string (date-time) | yes
OrderService | getOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | getOrder | param (path) | orderId | string (uuid) | yes
OrderService | getOrder | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
OrderService | getOrder | param (header) | X-Order-Access-Token | string |  | Order.orderAccessToken from checkoutCart's answer, in place of a session (IDENTITY-C52, CHG-R8SPN-025).
OrderService | getOrder | param (header) | X-Device-Id | string (uuid) |  | The device a guest app or browser is (ADAM CR-191, option A, decided 21 October 2026; CHG-R9CR-004): the client UUIDv7 the app mints once per installation and keeps, the same value it sends as create…
OrderService | getOrderCalendarEvent | param (path) | orderId | string (uuid) | yes
OrderService | getOrderStatement | response | orderId | string (uuid) | yes
OrderService | getOrderStatement | response | orderNumber | string | yes
OrderService | getOrderStatement | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | currencyScale | integer |  | Resolved from the region, not stored (ADR-0018, 24 August).
OrderService | getOrderStatement | response | entries | array of object | yes | Sequential.
OrderService | getOrderStatement | response | entries[].kind | enum (sale, payment, refund, void, modification, exchange, fee, variance, …) | yes
OrderService | getOrderStatement | response | entries[].description | string
OrderService | getOrderStatement | response | entries[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | entries[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | entries[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | entries[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | entries[].runningBalance | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | entries[].runningBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | entries[].runningBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | entries[].runningBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | entries[].referenceId | string |  | (nullable)
OrderService | getOrderStatement | response | entries[].principalId | string (uuid) |  | (nullable)
OrderService | getOrderStatement | response | entries[].occurredAt | string (date-time) | yes
OrderService | getOrderStatement | response | totalPaid | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | totalPaid.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | totalPaid.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | totalPaid.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | totalRefunded | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | totalRefunded.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | totalRefunded.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | totalRefunded.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | currentBalance | object | yes | Positive means the guest owes; negative means a refund is outstanding.
OrderService | getOrderStatement | response | currentBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | currentBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | currentBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | param (path) | orderId | string (uuid) | yes
TenancyService | getOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | getOutlet | response | code | string | yes | Unique within the venue (409 duplicate-code; ADAM CR-074, CHG-DDL-008): the database holds it with a unique index on (venue_id, code), so two concurrent creates cannot both keep one code. (max length 64)
TenancyService | getOutlet | response | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | getOutlet | response | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | getOutlet | response | venueId | string (uuid) | yes
TenancyService | getOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | getOutlet | response | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | getOutlet | response | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | getOutlet | response | zone | string |  | (nullable)
TenancyService | getOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | getOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | getOutlet | response | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | getOutlet | response | orderNumberPrefix | enum (A, B, C, D, E, F, G, H, …) |  | The one letter this outlet's F&B order numbers start with (ADAM CR-293 (2), option A, 29 October 2026; CHG-R11TEN-003): one capital letter A to Z, or null for none. (max length 1; nullable)
TenancyService | getOutlet | response | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | getOutlet | response | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | getOutlet | response | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | getOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | getOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | getOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | getOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | getOutlet | response | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | getOutlet | response | isActive | boolean
TenancyService | getOutlet | param (path) | outletId | string (uuid) | yes
AccessService | getParkingEntitlement | response | id | string (uuid) |  | (read-only)
AccessService | getParkingEntitlement | response | facilityId | string (uuid) | yes
AccessService | getParkingEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | getParkingEntitlement | response | subjectId | string (uuid) |  | (nullable)
AccessService | getParkingEntitlement | response | plateNumber | string |  | Required in plateWhitelist mode, meaningless in the others. (nullable)
AccessService | getParkingEntitlement | response | plateCountry | string |  | (nullable)
AccessService | getParkingEntitlement | response | mediaCode | string |  | The code presented in none and qrHandoff modes. (nullable)
AccessService | getParkingEntitlement | response | status | object |  | Server-owned. (read-only)
AccessService | getParkingEntitlement | response | pushedAt | string (date-time) |  | (read-only; nullable)
AccessService | getParkingEntitlement | response | pushFailureReason | string |  | (read-only; nullable)
AccessService | getParkingEntitlement | response | validFrom | string (date-time) | yes
AccessService | getParkingEntitlement | response | validTo | string (date-time) | yes
AccessService | getParkingEntitlement | param (path) | entitlementId | string (uuid) | yes
OrderService | getPaymentLink | response | link | object |  | The link as its holder may see it, not the staff record.
OrderService | getPaymentLink | response | link.status | enum (issued, viewed, paid, expired, cancelled, superseded) | yes
OrderService | getPaymentLink | response | link.expiresAt | string (date-time) | yes
OrderService | getPaymentLink | response | link.releaseHoldOnExpiry | boolean
OrderService | getPaymentLink | response | lines | array of OrderLine
OrderService | getPaymentLink | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getPaymentLink | response | lines[].variantId | string (uuid) | yes
OrderService | getPaymentLink | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getPaymentLink | response | lines[].performanceId | string (uuid)
OrderService | getPaymentLink | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getPaymentLink | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getPaymentLink | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getPaymentLink | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getPaymentLink | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getPaymentLink | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getPaymentLink | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getPaymentLink | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getPaymentLink | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | getPaymentLink | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | getPaymentLink | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | getPaymentLink | response | lines[].quantity | integer | yes | (min 1)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getPaymentLink | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].holderName | string |  | (nullable)
OrderService | getPaymentLink | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getPaymentLink | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | getPaymentLink | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | getPaymentLink | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | getPaymentLink | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | getPaymentLink | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | getPaymentLink | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | getPaymentLink | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | getPaymentLink | response | lines[].discounts[].id | string (uuid) | yes
OrderService | getPaymentLink | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | getPaymentLink | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | getPaymentLink | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | getPaymentLink | response | amountDue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | amountDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | amountDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | amountDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | venueName | string
OrderService | getPaymentLink | response | expiresInSeconds | integer
OrderService | getPaymentLink | response | provider | object |  | The provider the client tokenises against (ADAM CR-099, option 1; CHG-R10ORD-016): the venue's active payments.provider for the link's channel, the one payByLink charges.
OrderService | getPaymentLink | response | provider.providerId | string (uuid) | yes
OrderService | getPaymentLink | response | provider.providerName | string
OrderService | getPaymentLink | param (path) | token | string | yes
CatalogueService | getPerformance | response | id | string (uuid) | yes
CatalogueService | getPerformance | response | eventId | string (uuid) | yes
CatalogueService | getPerformance | response | startsAt | string (date-time) | yes
CatalogueService | getPerformance | response | endsAt | string (date-time) | yes
CatalogueService | getPerformance | response | approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | getPerformance | response | requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | getPerformance | response | status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | getPerformance | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | getPerformance | response | seatMapId | string (uuid) |  | (nullable)
CatalogueService | getPerformance | response | language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | getPerformance | response | format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | getPerformance | response | minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | getPerformance | param (path) | performanceId | string (uuid) | yes
CatalogueService | getPerformance | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
WhiteLabelService | getPlatformSubdomain | response | hostname | string | yes | e.g.
WhiteLabelService | getPlatformSubdomain | response | cell | string | yes
WhiteLabelService | getPlatformSubdomain | response | certificate | enum (wildcard)
WhiteLabelService | getPlatformSubdomain | response | isPrimary | boolean |  | True while no custom domain is primary.
CatalogueService | getProduct | response | id | string (uuid) | yes
CatalogueService | getProduct | response | code | string | yes | (max length 64)
CatalogueService | getProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | getProduct | response | name | string | yes | (max length 200)
CatalogueService | getProduct | response | description | string
CatalogueService | getProduct | response | nameLocalised | object |  | The product's name in each of the tenant's enabled languages (6 October 2026, CHG-R4-011; the tenant's languages, not the venue's: CHG-R8PRD-009, ADAM CR-213), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | getProduct | response | descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | getProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | getProduct | response | venueId | string (uuid) | yes
CatalogueService | getProduct | response | scopePath | string | yes
CatalogueService | getProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | getProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | getProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | getProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | getProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | getProduct | response | validTo | string (date-time) |  | The last moment the product's entitlements are valid; null means the same as onSaleTo (ADAM CR-167 as the lead ruled it, 26 October 2026; CHG-R10OPN-003). (nullable)
CatalogueService | getProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | getProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | getProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | getProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | getProduct | response | hasVariants | boolean | yes
CatalogueService | getProduct | response | variantCount | integer
CatalogueService | getProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | getProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | getProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | getProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | getProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | getProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | getProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | getProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | getProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | getProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | getProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | getProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | getProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | getProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | getProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | getProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | getProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | getProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | getProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | getProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | getProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | getProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | getProduct | response | media[].url | string (uri) |  | The asset's stable CDN address, for a guest card (ADAM CR-221, option A, decided 25 October 2026; CHG-R10CAT-014): the asset library's public address for the asset, set on guest-facing reads (searchC… (read-only; nullable)
CatalogueService | getProduct | response | media[].thumbnailUrl | string (uri) |  | The asset library's thumbnail address for the asset, on the same reads and with the same rule as url (ADAM CR-221). (read-only; nullable)
CatalogueService | getProduct | response | media[].altText | object |  | (nullable)
CatalogueService | getProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | getProduct | response | addOnProductIds | array of string (uuid) |  | The add-ons offered with this product, in display order (accepted 26 October 2026, Chinmay, ADAM CR-252 option A): each a kind: addOn product of the same venue (a coffee break, a working lunch, an AV…
CatalogueService | getProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | getProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | getProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | getProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | getProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | getProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | getProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | getProduct | response | eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | getProduct | response | createdAt | string (date-time) | yes | When the product was created (ADAM CR-204, option A, decided 25 October 2026; CHG-R10CAT-007): catalogue.product.created_at, NOT NULL DEFAULT now(), set by the server and never by a request. (read-only)
CatalogueService | getProduct | response | updatedAt | string (date-time) |  | When the product last changed (ADAM CR-204): set by updateProduct and by every product sub-resource PUT and bulk change that versions the product; null until the first change after creation. (read-only; nullable)
CatalogueService | getProduct | param (path) | productId | string (uuid) | yes
CatalogueService | getProduct | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | getProductEligibilityRule | response | id | string (uuid) |  | (read-only)
CatalogueService | getProductEligibilityRule | response | productId | string |  | (read-only)
CatalogueService | getProductEligibilityRule | response | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | getProductEligibilityRule | response | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | getProductEligibilityRule | response | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | getProductEligibilityRule | response | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | getProductEligibilityRule | response | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | getProductEligibilityRule | response | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | getProductEligibilityRule | response | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | getProductEligibilityRule | response | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | getProductEligibilityRule | response | waiverRequired | boolean |  | (default False)
CatalogueService | getProductEligibilityRule | response | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | getProductEligibilityRule | response | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | getProductEligibilityRule | response | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | getProductEligibilityRule | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | getProductEligibilityRule | param (path) | productId | string | yes
CatalogueService | getProductEligibilityRule | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | getPromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | getPromotion | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | getPromotionUsage | response | promotionId | string (uuid) | yes
CatalogueService | getPromotionUsage | response | redemptionCount | integer | yes
CatalogueService | getPromotionUsage | response | discountGiven | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | budgetRemaining | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | budgetRemaining.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | budgetRemaining.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | budgetRemaining.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | isBudgetExhausted | boolean
CatalogueService | getPromotionUsage | response | byChannel | array of object
CatalogueService | getPromotionUsage | response | byChannel[].channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | getPromotionUsage | response | byChannel[].redemptionCount | integer
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | param (path) | promotionId | string (uuid) | yes
WhiteLabelService | getPublishReviewPolicy | response | enabled | boolean | yes | (default False)
WhiteLabelService | getPublishReviewPolicy | response | requiresReviewerOtherThanAuthor | boolean |  | (default True)
WhiteLabelService | getPublishReviewPolicy | response | appliesTo | array of enum (tenantConfig, contentBlocks) |  | What the review covers.
WhiteLabelService | getPublishReviewPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getPublishedBookingFlow | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getPublishedBookingFlow | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getPublishedBookingFlow | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getPublishedBookingFlow | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getPublishedBookingFlow | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getPublishedBookingFlow | response | steps[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getPublishedBookingFlow | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getPublishedBookingFlow | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedBookingFlow | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getPublishedBookingFlow | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getPublishedBookingFlow | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getPublishedBookingFlow | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getPublishedBookingFlow | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getPublishedBookingFlow | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getPublishedBookingFlow | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getPublishedBookingFlow | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getPublishedBookingFlow | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getPublishedBookingFlow | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getPublishedBookingFlow | param (query) | productId | string (uuid)
WhiteLabelService | getPublishedBookingFlow | param (query) | productCategoryId | string (uuid)
WhiteLabelService | getPublishedBookingFlow | param (query) | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …)
WhiteLabelService | getPublishedGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | getPublishedGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | getPublishedGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | getPublishedGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | getPublishedGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | getPublishedGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getPublishedGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | tenantId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | publishedVersion | string | yes | The ConfigVersion.version this answer was read from; a client holding the same version keeps its copy.
WhiteLabelService | getPublishedTenantConfig | response | publishedAt | string (date-time) | yes
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn | object |  | What the guest sign-in buttons need before anyone is signed in (r8, IDENTITY-C21): the public client ids of the tenant's enabled social and UAE PASS providers, derived on read from Identity's provide… (read-only)
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.apple | object
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.apple.clientId | string
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.google | object
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.google.clientId | string
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.uaePass | object
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.uaePass.authorizationUrl | string (uri)
WhiteLabelService | getPublishedTenantConfig | response | guestSignIn.uaePass.clientId | string
WhiteLabelService | getPublishedTenantConfig | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload).
WhiteLabelService | getPublishedTenantConfig | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getPublishedTenantConfig | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getPublishedTenantConfig | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getPublishedTenantConfig | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getPublishedTenantConfig | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getPublishedTenantConfig | response | brand.showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | getPublishedTenantConfig | response | assetsBaseUrl | string (uri) |  | How any guest screen turns an asset id into a picture (r8 walk of ticket 28156; lead decision of 20 October 2026, option A). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | brandUrls | object |  | The brand assets as addresses a guest can load (r8 walk of ticket 28335). (read-only; nullable)
WhiteLabelService | getPublishedTenantConfig | response | brandUrls.logoUrl | string (uri) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brandUrls.logoDarkUrl | string (uri) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brandUrls.faviconUrl | string (uri) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brandUrls.splashImageUrls | array of string (uri)
WhiteLabelService | getPublishedTenantConfig | response | brandUrls.introVideoUrl | string (uri) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | appIcons | AppIcons
WhiteLabelService | getPublishedTenantConfig | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived[].size | string
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | theme | Theme
WhiteLabelService | getPublishedTenantConfig | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getPublishedTenantConfig | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getPublishedTenantConfig | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getPublishedTenantConfig | response | theme.venueSkins | array of object |  | The guest app skin each venue takes (ADAM CR-280, option B, 28 October 2026; CHG-R11TEN-007): one entry per venue, naming one of the approved app design's skins (handoff/design-tokens/guest-app.yaml,… (default [])
WhiteLabelService | getPublishedTenantConfig | response | theme.venueSkins[].venueId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | theme.venueSkins[].skinKey | GuestAppSkinKey: enum (park, water, stadium, theatre, dining, kids, museum, rooms, …) | yes | The guest app's skins per venue kind, as the approved Mobile App v4 design draws them (handoff/design-tokens/guest-app.yaml skins.byVenueKind; ADAM CR-280, CHG-R11TEN-007).
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | fonts | FontConfig
WhiteLabelService | getPublishedTenantConfig | response | fonts.primaryLatin | string | yes
WhiteLabelService | getPublishedTenantConfig | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getPublishedTenantConfig | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | skinKey | object |  | The asked venue's guest app skin (ADAM CR-280, option B, 28 October 2026, additive; CHG-R11TEN-007): the published theme.venueSkins entry for venueId. (read-only; nullable)
WhiteLabelService | getPublishedTenantConfig | response | header | HeaderConfig
WhiteLabelService | getPublishedTenantConfig | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | getPublishedTenantConfig | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | getPublishedTenantConfig | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | getPublishedTenantConfig | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | footer.columns | array of object
WhiteLabelService | getPublishedTenantConfig | response | footer.columns[].heading | string
WhiteLabelService | getPublishedTenantConfig | response | footer.columns[].sortOrder | integer |  | The column's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | footer.columns[].links | array of object |  | The column's links in display order, stored on the column row as one value (R8 blocker WHITE-C24).
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.termsUrl | string
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | footer.copyrightText | string
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks | array of object
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks[].platform | string
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks[].url | string
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks[].sortOrder | integer |  | The link's position, written by setFooter from the array order (R8 blocker IDENTITY-C60). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | getPublishedTenantConfig | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getPublishedTenantConfig | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].icon | string
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].isVisible | boolean | yes | At most five may be visible when kind is bottomNavigation; the rest overflow.
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | getPublishedTenantConfig | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getPublishedTenantConfig | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | homepage | HomepageLayout |  | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | getPublishedTenantConfig | response | homepage.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | homepage.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | getPublishedTenantConfig | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections | array of object | yes
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | banners | array of PublishedBanner |  | The hero and other banners a guest sees now (r8 walk of ticket 28335): the banners in the published version whose state is active at the time of the read, by sortOrder. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | banners[].id | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | banners[].placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | getPublishedTenantConfig | response | banners[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | banners[].subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | banners[].imageUrl | string (uri) | yes | The stable address of the banner image.
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget | LinkTarget
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.contentPageId | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.productId | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.eventId | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | banners[].linkTarget.url | string
WhiteLabelService | getPublishedTenantConfig | response | banners[].sortOrder | integer
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks | array of PublishedPromoBlock |  | The promo blocks in the published version that are active at the time of the read, by sortOrder, with the same rule as banners. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].id | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].iconUrl | string (uri) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget | LinkTarget
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, bookingFlow, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.contentPageId | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.productId | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.eventId | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.date | string (date) |  | Used when kind is bookingFlow, the date the flow opens on. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].linkTarget.url | string
WhiteLabelService | getPublishedTenantConfig | response | promoBlocks[].sortOrder | integer
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow | object |  | The booking-flow display settings, resolved for venueId when one was sent (the tenant's values with that venue's venueOverrides entry laid over, rev 3 CFG-11).
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getPublishedTenantConfig | response | languages | LanguageConfig
WhiteLabelService | getPublishedTenantConfig | response | languages.languages | array of string | yes | A tenant may add or select interface languages beyond English and Arabic (Chinmay, 2 October, workbook Q145; CHG-CSA-039).
WhiteLabelService | getPublishedTenantConfig | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage | array of object |  | How complete the interface strings are in each enabled language (CHG-CSA-039). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage[].language | string
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage[].coveragePercent | number |  | (min 0; max 100)
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage[].status | enum (complete, draft, missing)
WhiteLabelService | getPublishedTenantConfig | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps[].language | string
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps[].areas | array of string |  | The kinds of the missing items, from the closed list contentPages, banners, promoBlocks, faqs, policies (ADAM CR-194).
WhiteLabelService | getPublishedTenantConfig | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | getPublishedTenantConfig | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | getPublishedTenantConfig | response | enabledModules | array of ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | The modules the tenant has enabled and published, so a guest surface hides a tab or a homepage section for a module that is off.
WhiteLabelService | getPublishedTenantConfig | response | enabledFeatures | array of string |  | The featureKey of every feature toggle that is on in the published version.
WhiteLabelService | getPublishedTenantConfig | response | isInMaintenance | boolean | yes | Live state (setMaintenanceMode), as on getTenantAppStatus.
WhiteLabelService | getPublishedTenantConfig | response | maintenanceMessage | object |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.storeUrl | object |  | The store page of the tenant's app for each platform. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.storeUrl.ios | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.storeUrl.android | string (uri) |  | (pattern ^https://; nullable)
WhiteLabelService | getPublishedTenantConfig | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | getPublishedTenantConfig | response | availabilityMessage | object |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.phone | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.address | object |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders | array of PublishedAnalyticsProvider |  | The analytics platforms the storefront and app load (Chinmay, 3 October 2026, Pattern 4; CHG-GCF-005): a guest reads them here instead of listAnalyticsProviders, which needs TENANT_CONFIGURE.
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].otherProviderName | string |  | The provider's name, when provider is other (StorefrontAnalyticsProvider.providerLabel). (max length 100; nullable)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].measurementId | string | yes | What the tag or SDK reports to (GA4 G-..., Tag Manager GTM-..., a pixel id). (max length 100)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory).
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation | object |  | The provider the guest app tokenises cards with (4 October 2026, CHG-FXC-010; GST-071): the providerId storePaymentToken requires, its kind and the publishable key the client SDK needs. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation.providerId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation.providerKind | string | yes
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation.publishableKey | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | param (query) | venueId | string (uuid) |  | The venue the guest picked (WEB-001, GST-001).
TenancyService | getRegionSettings | response | scopePath | string | yes | The partition key (ADR-0005): the path of the region in regionId, set by the server when updateRegionSettings first saves the row, and ignored on input. (read-only)
TenancyService | getRegionSettings | response | countryCode | string | yes | ISO 3166-1 alpha-2. (pattern ^[A-Z]{2}$)
TenancyService | getRegionSettings | response | currencyCode | string | yes | (pattern ^[A-Z]{3}$)
TenancyService | getRegionSettings | response | currencyScale | integer | yes | Decimal places for this region's currency. (min 0; max 4)
TenancyService | getRegionSettings | response | timeZone | string | yes | IANA zone, e.g.
TenancyService | getRegionSettings | response | dateFormat | string |  | (default dd/MM/yyyy)
TenancyService | getRegionSettings | response | numberFormat | string |  | (default #,##0.00)
TenancyService | getRegionSettings | response | fiscalYearStartMonth | integer | yes | Varies by country. (min 1; max 12)
TenancyService | getRegionSettings | response | allowedAiResidencies | array of string |  | The region's compliance gate on AI providers (decided 28 September, audit R203; ADR-0009). (default [])
TenancyService | getRegionSettings | response | aiResidencyClass | enum (uaeOnly, globalAllowed, onPrem) |  | The tenant's AI residency class (decided 2 October 2026, Chinmay, "AI residency: per-tenant residency class"; DEC-539; CHG-CSP-009; amends AI-D02 and ADR-0009 section 1). (default uaeOnly)
TenancyService | getRegionSettings | response | aiResidencyClassLocked | boolean |  | Set by TICVAI at onboarding for a government, bank or health tenant (DEC-539), which must stay uaeOnly. (default False; read-only)
TenancyService | getRegionSettings | response | tenantCategory | enum (private, semiGovernment, government, banking, payments, health, difc, adgm) |  | What kind of organisation the tenant is, for AI residency (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 2, and Chinmay's per-tenant residency… (default private; read-only)
TenancyService | getRegionSettings | response | aiResidencyOptIn | object |  | The evidence a globalAllowed opt-in needs under PDPL Article 23 (DEC-539; CHG-CSP-009): the tenant's references to its vendor contract, its DPIA and the notice guests see. (nullable)
TenancyService | getRegionSettings | response | aiResidencyOptIn.vendorContractReference | string |  | (max length 200)
TenancyService | getRegionSettings | response | aiResidencyOptIn.dpiaReference | string |  | (max length 200)
TenancyService | getRegionSettings | response | aiResidencyOptIn.guestNoticeReference | string |  | (max length 200)
TenancyService | getRegionSettings | response | aiResidencyOptIn.confirmedByPrincipalId | string (uuid) |  | (read-only)
TenancyService | getRegionSettings | response | aiResidencyOptIn.confirmedAt | string (date-time) |  | (read-only)
TenancyService | getRegionSettings | response | localLanguageNameLocales | array of string |  | The languages an outlet name must also be given in, in this country (decided 2 October 2026, Chinmay, batch 2 #26: "English plus the local language where the country needs it"; DEC-031; CHG-CSP-005). (default [])
TenancyService | getRegionSettings | response | requiredBillingDocuments | array of object |  | Which documents a TICVAI customer's billing entity must upload, in this country (decided 2 October 2026, Chinmay, batch 6 set 7, ADM-411: "Trade licence always; VAT certificate when a TRN is entered;… (default [{'documentType': 'tradeLicence', 'requiredWhen': 'always'}, {'documentType': 'vatCertificate', 'requiredWhen': 'trnEntered'}])
TenancyService | getRegionSettings | response | requiredBillingDocuments[].documentType | string |  | The document kind, as the subscription contract's PartnerDocument names it (tradeLicence, vatCertificate, ...). (max length 64)
TenancyService | getRegionSettings | response | requiredBillingDocuments[].requiredWhen | enum (always, trnEntered)
TenancyService | getRegionSettings | response | minorAgeThreshold | integer |  | The age below which a guest is a minor here, set per country (decided 2 October 2026, Chinmay, critical set 1, BO-187: "Guardian consent on the venue's form; minor age per country"; DEC-237; CHG-CSP-… (min 0; max 21; default 18)
TenancyService | getRegionSettings | response | placement | Placement |  | Read-only here. (read-only)
TenancyService | getRegionSettings | response | placement.mode | enum (shared, dedicated, isolated, clientHosted) | yes
TenancyService | getRegionSettings | response | placement.cellName | string
TenancyService | getRegionSettings | response | placement.cloudRegion | string
TenancyService | getRegionSettings | response | cellName | string |  | The cell serving this region. (read-only)
TenancyService | getRegionSettings | param (path) | regionId | string (uuid) | yes
ReportingService | getReport | response | name | string | yes | (max length 200)
ReportingService | getReport | response | description | string |  | (max length 1000)
ReportingService | getReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | getReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | getReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | getReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | getReport | response | columns[].field | string | yes
ReportingService | getReport | response | columns[].label | string
ReportingService | getReport | response | columns[].aggregation | object |  | (default none)
ReportingService | getReport | response | columns[].sortOrder | integer
ReportingService | getReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | getReport | response | columns[].format | string |  | (nullable)
ReportingService | getReport | response | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | getReport | response | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | getReport | response | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | getReport | response | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | getReport | response | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | getReport | response | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | getReport | response | filters | array of ReportFilter
ReportingService | getReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | getReport | response | filters[].field | string | yes
ReportingService | getReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | getReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | getReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | getReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | getReport | response | groupBy | array of string
ReportingService | getReport | response | parameters | array of ReportParameter
ReportingService | getReport | response | parameters[].key | string | yes
ReportingService | getReport | response | parameters[].label | string | yes
ReportingService | getReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | getReport | response | parameters[].isRequired | boolean | yes
ReportingService | getReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | getReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | getReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | getReport | response | id | string (uuid) | yes
ReportingService | getReport | response | version | string | yes | The current version.
ReportingService | getReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | getReport | response | isRetired | boolean | yes
ReportingService | getReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | getReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | getReport | response | createdAt | string (date-time) | yes
ReportingService | getReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | getReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | getReport | param (path) | reportId | string (uuid) | yes
OrderService | getReservation | response | id | string (uuid) | yes
OrderService | getReservation | response | venueId | string (uuid) | yes
OrderService | getReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | getReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | getReservation | response | lines | array of CreateOrderLine
OrderService | getReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getReservation | response | lines[].variantId | string (uuid) | yes
OrderService | getReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getReservation | response | lines[].performanceId | string (uuid)
OrderService | getReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getReservation | response | lines[].attributes.attendees | integer |  | How many people a meeting-room booking is for (GST-075; R8 blocker cause GPS-C28, CHG-R8SPN-034). (min 1; nullable)
OrderService | getReservation | response | lines[].attributes.parking | object |  | A parking line's plate and day (R8 blocker ORDERS-MONEY-C22, CHG-R8MIG-023): carried from addCartLine to the order line and passed to issueOrderEntitlements, which writes the parking entitlement's pl… (nullable)
OrderService | getReservation | response | lines[].attributes.bundle | object |  | A bundle line's picks (R8 blocker ORDERS-MONEY-C43, the lead's answer B for r8; CHG-R8MIG-023): the bundle and the option the guest chose in each choice group. (nullable)
OrderService | getReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | getReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getReservation | response | lines[].holderName | string |  | (nullable)
OrderService | getReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getReservation | response | expiresAt | string (date-time) | yes
OrderService | getReservation | response | createdAt | string (date-time) | yes
OrderService | getReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | getReservation | param (path) | reservationId | string (uuid) | yes
VenueOpsService | getResourceHold | response | id | string (uuid) | yes
VenueOpsService | getResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | getResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | getResourceHold | response | from | string (date-time) | yes
VenueOpsService | getResourceHold | response | to | string (date-time) | yes
VenueOpsService | getResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | getResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | getResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | getResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | getResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | getResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | getResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | getResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | getResourceHold | param (path) | holdId | string (uuid) | yes
RetailService | getRetailSale | response | id | string | yes
RetailService | getRetailSale | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | getRetailSale | response | receiptBarcode | string |  | The barcode printed on the receipt (R8 blocker APPROVALS-TENANCY-C34): the receipt number as printed, encoded as a Code 128 barcode, stored so lookupRetailSale finds a sale by receiptBarcode with an… (max length 64; read-only)
RetailService | getRetailSale | response | cashierPrincipalId | string (uuid) |  | The staff member who rang the sale up, from the session (null for a guest's own sale). (read-only; nullable)
RetailService | getRetailSale | response | orderId | string | yes | The order in the Order & Payment context.
RetailService | getRetailSale | response | outletId | string (uuid) | yes
RetailService | getRetailSale | response | shiftId | string |  | (nullable)
RetailService | getRetailSale | response | subjectId | string (uuid) |  | (nullable)
RetailService | getRetailSale | response | lines | array of object | yes
RetailService | getRetailSale | response | lines[].lineId | string
RetailService | getRetailSale | response | lines[].merchandiseId | string (uuid)
RetailService | getRetailSale | response | lines[].orderLineId | string (uuid) |  | The order line the amounts were copied from (CreateRetailSaleLine.orderLineId; r8 re-walk, CHG-R8RW-004). (nullable)
RetailService | getRetailSale | response | lines[].name | string
RetailService | getRetailSale | response | lines[].quantity | integer
RetailService | getRetailSale | response | lines[].overrideReason | string |  | The reason given with a manual price override (CreateRetailSaleLine.overrideReason); null when the price was not overridden. (max length 200; nullable)
RetailService | getRetailSale | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].serialNumbers | array of string
RetailService | getRetailSale | response | lines[].returnedQuantity | integer
RetailService | getRetailSale | response | lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | getRetailSale | response | lines[].notReturnableReason | string |  | (nullable)
RetailService | getRetailSale | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | reprintCount | integer
RetailService | getRetailSale | response | createdAt | string (date-time) | yes
RetailService | getRetailSale | response | recordedAt | string (date-time)
RetailService | getRetailSale | param (path) | saleId | string (uuid) | yes
RetailService | getReturnPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | getReturnPolicy | response | outletId | string (uuid) | yes
RetailService | getReturnPolicy | response | defaultWindowDays | integer | yes | (min 0)
RetailService | getReturnPolicy | response | requiresReceipt | boolean | yes | (default True)
RetailService | getReturnPolicy | response | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | getReturnPolicy | response | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | getReturnPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getReturnPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | requiresApprovalAbove | object |  | Retired (r8, decision R144), so no return raises an approval request.
RetailService | getReturnPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | getReturnPolicy | response | nonReturnableCategoryIds | array of string (uuid)
RetailService | getReturnPolicy | param (path) | outletId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | performanceId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | seatMapId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | renderMode | enum (graphical, list) | yes | The mode the server actually used.
CatalogueService | getSeatAvailability | response | viewBox | object |  | The coordinate space the seat positions are in, as SeatMap.viewBox, so the section view is drawn from this response alone (WEB-007, GST-049; r8 walk of ticket 28197). (nullable)
CatalogueService | getSeatAvailability | response | viewBox.width | number
CatalogueService | getSeatAvailability | response | viewBox.height | number
CatalogueService | getSeatAvailability | response | stagePosition | object |  | Where the stage sits in the same space, as SeatMap.stagePosition; the section view orients the seats towards it. (nullable)
CatalogueService | getSeatAvailability | response | stagePosition.x | number | yes
CatalogueService | getSeatAvailability | response | stagePosition.y | number | yes
CatalogueService | getSeatAvailability | response | totals | object | yes
CatalogueService | getSeatAvailability | response | totals.total | integer
CatalogueService | getSeatAvailability | response | totals.available | integer
CatalogueService | getSeatAvailability | response | totals.held | integer
CatalogueService | getSeatAvailability | response | totals.sold | integer
CatalogueService | getSeatAvailability | response | totals.blocked | integer
CatalogueService | getSeatAvailability | response | totals.buffered | integer
CatalogueService | getSeatAvailability | response | byCategory | array of object
CatalogueService | getSeatAvailability | response | byCategory[].categoryId | string (uuid)
CatalogueService | getSeatAvailability | response | byCategory[].available | integer
CatalogueService | getSeatAvailability | response | byCategory[].sold | integer
CatalogueService | getSeatAvailability | response | byCategory[].price | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getSeatAvailability | response | byCategory[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getSeatAvailability | response | byCategory[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getSeatAvailability | response | byCategory[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getSeatAvailability | response | maxSeatsPerGuestOrder | integer |  | The most seats one guest booking may hold at this performance's venue (ADAM CR-187, 25 October 2026): the venue's VenueSettings.seating.maxSeatsPerGuestOrder (default 10, bounds 1 to 50, decided 29 S… (min 1; max 50; read-only)
CatalogueService | getSeatAvailability | response | zones | array of object |  | The standing zones and what is left in each (r8, GPS-C38): a zone has no seats, so it is sold by quantity (createSeatHold zoneId and quantity).
CatalogueService | getSeatAvailability | response | zones[].zoneId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | zones[].name | string | yes
CatalogueService | getSeatAvailability | response | zones[].remaining | integer | yes | (min 0)
CatalogueService | getSeatAvailability | response | zones[].keepTogether | boolean |  | (default True)
CatalogueService | getSeatAvailability | response | sections | array of object |  | The map's sections with what a guest screen needs to show the view from each (decided 29 September, rev 3 23SEP-14): the photo where the venue supplied one, otherwise null and the client renders the…
CatalogueService | getSeatAvailability | response | sections[].code | string | yes
CatalogueService | getSeatAvailability | response | sections[].name | string | yes
CatalogueService | getSeatAvailability | response | sections[].viewAssetId | string (uuid) |  | As Section.viewAssetId. (nullable)
CatalogueService | getSeatAvailability | response | sections[].boundary | array of Point |  | As Section.boundary. (nullable)
CatalogueService | getSeatAvailability | response | sections[].boundary[].x | number | yes
CatalogueService | getSeatAvailability | response | sections[].boundary[].y | number | yes
CatalogueService | getSeatAvailability | response | seats | array of object | yes
CatalogueService | getSeatAvailability | response | seats[].seatId | string | yes
CatalogueService | getSeatAvailability | response | seats[].status | SeatStatus: enum (available, held, sold, blocked, buffered, unavailable) | yes
CatalogueService | getSeatAvailability | response | seats[].categoryId | string (uuid) |  | (nullable)
CatalogueService | getSeatAvailability | response | seats[].displayLabel | string |  | What the guest sees, e.g.
CatalogueService | getSeatAvailability | response | seats[].position | object |  | The seat's coordinates on the map, as on Seat. (nullable)
CatalogueService | getSeatAvailability | response | seats[].position.x | number | yes
CatalogueService | getSeatAvailability | response | seats[].position.y | number | yes
CatalogueService | getSeatAvailability | param (path) | performanceId | string (uuid) | yes
CatalogueService | getSeatAvailability | param (query) | sectionCode | string
CatalogueService | getSeatAvailability | param (query) | categoryId | string (uuid)
CatalogueService | getSeatAvailability | param (query) | availableOnly | boolean
CatalogueService | getSeatAvailability | param (query) | mode | enum (auto, graphical, list) |  | graphical requires geometry and returns coordinates.
CatalogueService | getSeatAvailability | param (header) | X-Venue-Id | string (uuid) |  | The venue a guest app or site is browsing, named on every public read of venue data (decided 25 October 2026, Chinmay, ADAM CR-198 option A; CHG-R10ID-010; the rule is on guestAuth).
CatalogueService | getSeatHold | response | id | string | yes
CatalogueService | getSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | getSeatHold | response | seatIds | array of string | yes
CatalogueService | getSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | getSeatHold | response | status | enum (held, converted, released, expired, sold) | yes | converted when the order is created; sold when the order is paid and catalogue.convertInventoryHold sells the units (ADAM CR-169, 18 October 2026; CHG-CRA-007).
CatalogueService | getSeatHold | response | inventoryReservationId | string (uuid) |  | The inventory hold these seats sit under (ADAM CR-169; CHG-CRA-007), so convertInventoryHold finds the order's seat reservations from the hold it converts. (nullable)
CatalogueService | getSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | getSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | getSeatHold | response | extensionCount | integer
CatalogueService | getSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | getSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | getSeatHold | param (path) | holdId | string (uuid) | yes
MarketingService | getSeoMetadata | response | id | string (uuid) | yes | (read-only)
MarketingService | getSeoMetadata | response | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | getSeoMetadata | response | entityId | string (uuid) | yes
MarketingService | getSeoMetadata | response | locale | string
MarketingService | getSeoMetadata | response | title | string |  | (nullable)
MarketingService | getSeoMetadata | response | metaDescription | string |  | (nullable)
MarketingService | getSeoMetadata | response | keywords | array of string
MarketingService | getSeoMetadata | response | canonicalUrl | string |  | (nullable)
MarketingService | getSeoMetadata | response | slug | string |  | 22.11.6. (nullable)
MarketingService | getSeoMetadata | response | hreflang | object |  | 22.11.11.
MarketingService | getSeoMetadata | response | schemaOrgType | string |  | (nullable)
MarketingService | getSeoMetadata | response | openGraph | object
MarketingService | getSeoMetadata | response | isAutoGenerated | boolean |  | 22.11.2. (default True)
MarketingService | getSeoMetadata | response | noIndex | boolean |  | (default False)
MarketingService | getSeoMetadata | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getSeoMetadata | param (query) | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | getSeoMetadata | param (query) | entityId | string (uuid) | yes
MarketingService | getSeoMetadata | param (query) | locale | string |  | Absent means the tenant's default language.
OrderService | getShiftCountLines | response | items | array of CashCountLine | yes
OrderService | getShiftCountLines | response | items[].id | string (uuid)
OrderService | getShiftCountLines | response | items[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | getShiftCountLines | response | items[].depositBoxId | string (uuid) |  | (nullable)
OrderService | getShiftCountLines | response | items[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | getShiftCountLines | response | items[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | getShiftCountLines | response | items[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | getShiftCountLines | response | items[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | getShiftCountLines | response | items[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getShiftCountLines | response | items[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShiftCountLines | response | items[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShiftCountLines | response | items[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShiftCountLines | response | items[].countedBy | string (uuid) |  | (nullable)
OrderService | getShiftCountLines | response | items[].countedAt | string (date-time)
OrderService | getShiftCountLines | response | items[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | getShiftCountLines | response | nextCursor | string
OrderService | getShiftCountLines | response | hasMore | boolean | yes
OrderService | getShiftCountLines | param (path) | shiftId | string (uuid) | yes
OrderService | getShiftCountLines | param (query) | countKind | enum (openingFloat, close, movement)
OrderService | getShiftCountLines | param (query) | pageSize | integer
OrderService | getShiftCountLines | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | getSitePackage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | getSitePackage | response | version | string
WhiteLabelService | getSitePackage | response | status | enum (building, ready, failed) | yes
WhiteLabelService | getSitePackage | response | packageAssetRef | string (uuid) |  | The package in the assets library, set when ready (ADAM CR-106; CHG-R10TEN-012). (read-only; nullable)
WhiteLabelService | getSitePackage | response | downloadUrl | string |  | Short-lived; present when ready. (nullable)
WhiteLabelService | getSitePackage | response | expiresAt | string (date-time) |  | (nullable)
WhiteLabelService | getSitePackage | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | getSitePackage | response | platformStaffGrantId | string (uuid) |  | The platform-staff grant it was made under, where platform staff made it (R098). (read-only; nullable)
WhiteLabelService | getSitePackage | response | createdAt | string (date-time) |  | (read-only)
WhiteLabelService | getSitePackage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getSitePackage | param (path) | packageId | string (uuid) | yes
WhiteLabelService | getSiteSetupProgress | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getSiteSetupProgress | response | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | getSiteSetupProgress | response | currentStep | object |  | (nullable)
WhiteLabelService | getSiteSetupProgress | response | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | getSiteSetupProgress | response | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | getSiteSetupProgress | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getSiteSetupProgress | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts | array of StoreAccount | yes
WhiteLabelService | getStoreAccounts | response | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | getStoreAccounts | response | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | getStoreAccounts | response | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | getStoreAccounts | response | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | getStoreAccounts | response | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key. (nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].passTypeIdentifier | string |  | The Apple Wallet Pass Type ID (pass.<reverse-domain>), registered in the client's own Apple Developer account, one per brand (Chinmay, 12 October 2026: the client owns the certificate; CHG-R6-033). (pattern ^pass\.[A-Za-z0-9.-]+$; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].passCertificateSecretRef | string |  | The Pass Type ID certificate, from the client's Apple Developer account. (nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].passCertificatePassword | string (password) |  | The password of the .p12 sent in passCertificateSecretRef. (nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].hasPassCertificate | boolean |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].passCertificateExpiresAt | string (date-time) |  | When the pass certificate expires, read from the certificate when it is stored (CHG-R6-033). (read-only; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].listing | object |  | The store listing.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.category | string
WhiteLabelService | getStoreAccounts | response | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | getStoreAccounts | response | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | getStoreAccounts | response | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | getStoreAccounts | response | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | items | array of object | yes
WhiteLabelService | getStoreAccounts | response | items[].item | enum (appleDunsNumber, appleDeveloperAccount, googlePlayDeveloperAccount, storeListing, appIcons, publishedConfiguration) | yes
WhiteLabelService | getStoreAccounts | response | items[].done | boolean | yes
WhiteLabelService | getStoreAccounts | response | items[].clientOwned | boolean |  | True for the three accounts, which only the client can open.
WhiteLabelService | getStoreAccounts | response | items[].guidance | string |  | What to do next, in the operator's language.
IdentityService | getSubjectDataExport | response | requestId | string (uuid) | yes
IdentityService | getSubjectDataExport | response | subjectId | string (uuid) | yes
IdentityService | getSubjectDataExport | response | format | enum (json, csv, pdf) | yes
IdentityService | getSubjectDataExport | response | status | enum (awaitingApproval, running, ready, failed, rejected, expired) | yes | As SubjectDataExport.status.
IdentityService | getSubjectDataExport | response | requestedAt | string (date-time) | yes
IdentityService | getSubjectDataExport | response | readyAt | string (date-time) |  | (nullable)
IdentityService | getSubjectDataExport | response | downloadUrl | string (uri) |  | A signed link to the file in the tenant's private storage, valid for five minutes from this answer (as the package's other short-lived signed links); null unless status is ready. (nullable)
IdentityService | getSubjectDataExport | response | downloadUrlExpiresAt | string (date-time) |  | When downloadUrl stops working; null with no link. (nullable)
IdentityService | getSubjectDataExport | response | fileSizeBytes | integer (int64) |  | (nullable)
IdentityService | getSubjectDataExport | response | failureReason | string |  | Why the job failed, with failed; null otherwise. (nullable)
IdentityService | getSubjectDataExport | param (path) | subjectId | string (uuid) | yes
IdentityService | getSubjectDataExport | param (path) | requestId | string (uuid) | yes | The requestId exportSubjectData answered with.
FnbService | getTableMap | response | outletId | string (uuid) | yes
FnbService | getTableMap | response | zones | array of string
FnbService | getTableMap | response | tables | array of TableState | yes
FnbService | getTableMap | response | tables[].scopePath | string | yes | Where the row is owned: the path of the scope that wrote it (its venue, or the region or tenant that configured it), set by the server from the caller's scope and never taken from a request. (read-only)
FnbService | getTableMap | response | tables[].id | string (uuid) | yes | (read-only)
FnbService | getTableMap | response | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | getTableMap | response | tables[].capacity | integer | yes | (min 1)
FnbService | getTableMap | response | tables[].zone | string |  | (nullable)
FnbService | getTableMap | response | tables[].position | object
FnbService | getTableMap | response | tables[].position.x | number
FnbService | getTableMap | response | tables[].position.y | number
FnbService | getTableMap | response | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | getTableMap | response | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | getTableMap | response | tables[].codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | getTableMap | response | tables[].status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | getTableMap | response | tables[].visitId | string (uuid) |  | (nullable)
FnbService | getTableMap | response | tables[].covers | integer |  | (nullable)
FnbService | getTableMap | response | tables[].seatedAt | string (date-time) |  | (nullable)
FnbService | getTableMap | response | tables[].serverPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableMap | response | tables[].billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableMap | response | tables[].billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableMap | response | tables[].billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableMap | response | tables[].billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableMap | param (path) | outletId | string (uuid) | yes
FnbService | getTableVisit | response | id | string (uuid) | yes
FnbService | getTableVisit | response | tableId | string (uuid) | yes
FnbService | getTableVisit | response | tableLabel | string
FnbService | getTableVisit | response | outletId | string (uuid) | yes
FnbService | getTableVisit | response | covers | integer | yes
FnbService | getTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | getTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders | array of FnbOrder | yes
FnbService | getTableVisit | response | orders[].id | string (uuid) | yes
FnbService | getTableVisit | response | orders[].orderNumber | string | yes | Short and called out across a counter (ADAM CR-277 (3) and CR-293 (2); CHG-R11TEN-003).
FnbService | getTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | getTableVisit | response | orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | getTableVisit | response | orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | getTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getTableVisit | response | orders[].lines | array of object | yes
FnbService | getTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | getTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | getTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | getTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | getTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | getTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | getTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | getTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | getTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | getTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | getTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | getTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | getTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | getTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | getTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | getTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | getTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | getTableVisit | response | orders[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | getTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | getTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | getTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | getTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | getTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | openedAt | string (date-time) | yes
FnbService | getTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | getTableVisit | response | serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | getTableVisit | response | note | string |  | The server's note on the visit (updateTableVisit). (max length 500; read-only; nullable)
FnbService | getTableVisit | param (path) | visitId | string (uuid) | yes
LedgerService | getTaxDocumentRendition | response | documentId | string (uuid) | yes
LedgerService | getTaxDocumentRendition | response | documentKind | enum (taxInvoice, creditMemo) | yes
LedgerService | getTaxDocumentRendition | response | documentNumber | string
LedgerService | getTaxDocumentRendition | response | language | string |  | (nullable)
LedgerService | getTaxDocumentRendition | response | contentType | string |  | (default application/pdf)
LedgerService | getTaxDocumentRendition | response | url | string (uri) | yes
LedgerService | getTaxDocumentRendition | response | expiresAt | string (date-time) | yes
LedgerService | getTaxDocumentRendition | param (path) | documentId | string (uuid) | yes | A tax invoice id or a credit memo id.
LedgerService | getTaxDocumentRendition | param (query) | language | string
LedgerService | getTaxInvoice | response | id | string (uuid) | yes | (read-only)
LedgerService | getTaxInvoice | response | invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | getTaxInvoice | response | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | getTaxInvoice | response | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | getTaxInvoice | response | legalEntityId | string (uuid) | yes
LedgerService | getTaxInvoice | response | templateId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | venueId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | orderIds | array of string (uuid)
LedgerService | getTaxInvoice | response | supplierName | string
LedgerService | getTaxInvoice | response | supplierAddress | string |  | (nullable)
LedgerService | getTaxInvoice | response | supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | getTaxInvoice | response | buyerName | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerAddress | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | getTaxInvoice | response | buyerTaxRegistrationNumber | string |  | (nullable)