## Read me
TICVAI backend build plan: first release (POS, Guest App web and mobile, White Labelling)
Services | 16
Operations (APIs) to build | 697
API schemas they send or return | 487
Tables | 468
Migrations | 34
Backend and DevOps tasks | 417
Points | 2054
How to read it
Build plan | Every backend and DevOps task. Step 1 can start now; a task at step N waits for at least one task at step N-1. Wave is when the screens need it.
Migrations | One forward-only migration per database schema, in the order they run. Each only references tables created before it; keys that would point forward are added by the last migration.
Tables | Every table the first release reads or writes, plus the tables their foreign keys reach, with the migration that creates each.
Services / APIs / API schemas | What each service builds, every operation to build, and the request and response schemas those operations use, with where each is stored.
Assignees | From docs/active/team.json, balanced by points. Points are relative size (1, 2, 3, 5, 8), not hours.
Generated by tools/build-service-docs.py from the contracts, the delivery slice, the lineage and the DDL in backend/. Re-run it; do not edit this file.

## Build plan
Step | Wave | Key | Parent | Task | Points | Assignee | Service | Depends on | Description
1 | 1 | SETUP-CI | SETUP | [DevOps] CI pipelines for the backend and frontend repositories | 3 | Hrushikant Patkar |  |  | CI pipelines for the backend and frontend repositories. In **ticvai-backend** and **ticvai-frontend** (the repositories the setup zip creates). CI is GitHub Actions (decided 28 September, audit R057). Done when: every merge request runs build, tests and lint in both, a red run blocks the merge, and a failing test on a branch shows in the MR. Tool versions per setup/dependencies.md.
1 | 1 | SETUP-ENV | SETUP | [DevOps] Dev and staging environments (Terraform, ADR-0007 infra repository) | 5 | Hrushikant Patkar |  |  | Dev and staging environments (Terraform, ADR-0007 infra repository). In **ticvai-infra** (ADR-0007: one parameterised `cell` module, one tfvars per environment). The provider is Azure in a UAE region, Terraform `azurerm`, with each cell's secrets in its Azure Key Vault (decided 28 September, audit R057). Done when: `terraform plan` and `apply` build dev and staging from nothing, state is remote and locked, and the cell mapping and Azure region are written in the infra README.
2 | 1 | SETUP-CLIENTS | SETUP | [DevOps] Generate the typed API clients from contracts/ for the frontend workspace | 3 | Hrushikant Patkar |  | SETUP-CI | Generate the typed API clients from contracts/ for the frontend workspace. In **ticvai-frontend** `packages/api-client`: generated from the package's `contracts/`, re-generated by one command and checked in CI on GitHub Actions (audit R057). Done when: every in-release operation has a typed call, the build fails if the contracts change without a re-generate, and screen tickets stop stubbing calls.
2 | 1 | SETUP-DB | SETUP | [DevOps] PostgreSQL (tenant and control databases) and a forward-only migration runner that applies the MIG epic in order | 5 | Hrushikant Patkar |  | SETUP-ENV | PostgreSQL (tenant and control databases) and a forward-only migration runner that applies the MIG epic in order. In **ticvai-backend**: `SqlMigrationRunner` (in the starter) applies `db/tenant` and `db/control` - the package's derived DDL - in file order and records each file with its checksum in `platform.schema_version`. The databases run on Azure in the UAE region, connection strings from the cell's Key Vault (audit R057). Done when: both databases exist in dev, the runner applies every MIG file to an empty database, and a second run applies nothing.
2 | 1 | SETUP-OBS | SETUP | [DevOps] Logging and monitoring basics | 2 | Hrushikant Patkar |  | SETUP-ENV | Logging and monitoring basics. In **ticvai-backend** and **ticvai-infra**: structured logs and traces (OpenTelemetry, already referenced by the starter) shipped from dev and staging in the Azure UAE region (audit R057). Done when: a request can be followed from the API log to its trace, and an error raises an alert someone receives.
2 | 1 | SETUP-HOSTS | PLATFORM | [BE] Hosts for the deployables on .NET 10: commerce, access, operations and workers, each composing its modules | 3 | Pranay Shinde |  | SETUP-CI | Hosts for the deployables on .NET 10: commerce, access, operations and workers, each composing its modules. In ticvai-backend, on .NET 10 LTS (decided 30 September; ADR-0055). Four .NET hosts in one solution: commerce (Identity, Tenancy, Catalogue, Order, Ledger, Wallet), access (Access), operations (F&B, Retail, Inventory, VenueOps, Marketing, WhiteLabel, Reporting, Platform, CrossRegion) and workers (the outbox relay, every module's event consumers, scheduled jobs), each composing its modules through IModule. ticvai-ai stays the Python service. Done when: each host starts locally with its modules registered and a health endpoint, CI builds one image per host, and moving a module to another host is a change of one registration.
2 | 1 | SETUP-QDRANT | PLATFORM | [BE] Qdrant cluster in dev and staging: 3 nodes, TLS, snapshots, monitoring | 3 | Hrushikant Patkar |  | SETUP-ENV | Qdrant cluster in dev and staging: 3 nodes, TLS, snapshots, monitoring. In ticvai-infra (Terraform): a self-hosted 3-node Qdrant cluster in Azure UAE North for dev and staging (ADR-0049), pinned to 1.16 or later, with TLS, JWT RBAC on and the signing key in the cell's Key Vault, snapshot storage in the UAE, and monitoring and alerts on node health, disk and latency. Check Qdrant Hybrid Cloud on our own AKS as an alternative before building. Done when: the cluster survives the loss of one node, a snapshot of a test collection restores into a fresh cluster, and a request without a valid token is refused.
3 | 1 | MIG-BASELINE | MIG | [DB] Migration baseline: schemas, extensions, migration register, RLS helper functions and the monthly partition helpers (ADR-0056) | 3 | Hrushikant Patkar |  | SETUP-DB | From backend/tenant/000-schemas.sql, 001-extensions.sql, 002-migration-register.sql, the helper functions at the top of 920-row-level-security.sql and 930-partitioning.sql; the control database's own 000-002. Everything else in the MIG epic runs after this.
3 | 1 | ARCH-TESTS | PLATFORM | [BE] Architecture tests for 17 modules: no module references another, and no module's SQL names another's schema | 3 | Tanmay Dukhande |  | SETUP-HOSTS | Architecture tests for 17 modules: no module references another, and no module's SQL names another's schema. Extend tests/Ticvai.ArchitectureTests/ModuleBoundaryTests.cs from six modules to 17 (ADR-0055), and add a test that fails when a module's SQL names another module's schema other than through a published read view. Done when: a deliberate cross-module reference and a raw cross-schema query each fail the build in CI.
3 | 1 | KERNEL-ID | PLATFORM | [BE] One id type: UUIDv7 from Id.New() in the kernel and in offline-core | 2 | Tanmay Dukhande |  | SETUP-HOSTS | One id type: UUIDv7 from Id.New() in the kernel and in offline-core. Replace the kernel's ULID generator (Ticvai.Shared.Kernel Primitives/Ulid.cs) with Id.New(), a UUIDv7 Guid (RFC 9562) written big-endian so PostgreSQL's uuid order is time order (ADR-0056), and the same generator in ticvai-frontend packages/offline-core for ids created offline. Done when: ids made by the server and by an offline till sort by creation time in PostgreSQL, a .NET-to-TypeScript round-trip test agrees byte for byte, and no ULID string is generated anywhere.
3 | 1 | OFFLINE-JOURNAL | OFFLINE | [BE] Offline journal in packages/offline-core: record, replay and the conflict policies | 8 | Pradnya Yeram |  | SETUP-CLIENTS | Offline journal in packages/offline-core: record, replay and the conflict policies. In ticvai-frontend packages/offline-core: an append-only journal of sales and scans taken offline, replay on reconnect, and the conflict policies the contracts declare (SD-047). Done when: a POS takes ten cash sales with the network off and all ten reach the server once when it returns.
3 | 1 | PLATFORM-MIGRATE | PLATFORM | [BE] Migration fan-out across tenant databases, and expand-then-contract changes | 5 | Hrushikant Patkar |  | SETUP-DB | Migration fan-out across tenant databases, and expand-then-contract changes. Apply a migration to every tenant database with progress and resume, and the rule that a schema change ships in two steps so old and new code both run (SD-049). Done when: a column rename reaches three seeded tenant databases with no downtime.
3 | 1 | PLATFORM-OBSERVE | PLATFORM | [BE] Observability with tenant and venue on every trace, and the first dashboards | 5 | Hrushikant Patkar |  | SETUP-OBS | Observability with tenant and venue on every trace, and the first dashboards. OpenTelemetry attributes for tenant, venue and workstation; dashboards for the sale path and sync; alerts on error rate and latency (SD-048). Done when: a failed POS sale can be found by venue and till within a minute.
4 | 1 | MIG-CONTROL | MIG | [DB] Migration V0002__control.sql: control (17 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE | Control database. Tables: control.api_client, control.api_licence, control.api_version, control.content_block, control.developer_account, control.integration_listing, control.invoice, control.invoice_line, control.licence_add_on, control.licence_add_on_limit, control.partner, control.partner_agreement, control.partner_application, control.partner_change_request, control.production_access_request, control.seo_metadata, control.tenant. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
4 | 1 | MIG-PARTITIONS | PLATFORM | [DB] Monthly partitions: create three months ahead, detach what retention has expired | 3 | Pranay Shinde |  | MIG-BASELINE SETUP-HOSTS | Monthly partitions: create three months ahead, detach what retention has expired. A job in the workers host that keeps monthly range partitions three months ahead on the time-partitioned tables (access.scan_event, platform.outbox, platform.dead_letter, platform.audit_record, ledger.journal_line, marketing.message_dispatch, kernel.inbox; ADR-0056) in every tenant database, and detaches and archives partitions past their retention (ADR-0047). Done when: a new tenant database has partitions three months ahead, a run with the clock moved forward creates the next month, and an expired partition is detached, not deleted row by row.
4 | 1 | MIG-PII | MIG | [DB] Migration V0007__pii.sql: pii (5 tables) | 3 | Tanmay Dukhande | IdentityService | MIG-BASELINE | Tenant database. Tables: pii.consent_identifier, pii.subject, pii.subject_biometric, pii.subject_contact, pii.subject_document. Source DDL: backend/tenant/010-pii.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
4 | 1 | MIG-PRICING | MIG | [DB] Migration V0004__pricing.sql: pricing (3 tables) | 2 | Tanmay Dukhande | CatalogueService | MIG-BASELINE | Tenant database. Tables: pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule. Source DDL: backend/tenant/010-pricing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
4 | 1 | MIG-SUBSCRIPTION | MIG | [DB] Migration V0005__subscription.sql: subscription (4 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE | Tenant database. Tables: subscription.contract, subscription.plan, subscription.plan_limit, subscription.plan_module. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
4 | 1 | MIG-TENANCY | MIG | [DB] Migration V0003__tenancy.sql: tenancy (1 tables) | 1 | Tanmay Dukhande | TenancyService | MIG-BASELINE | Tenant database. Tables: tenancy.device_assignment. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
4 | 1 | MIG-TRANSPORT | MIG | [DB] Migration V0006__transport.sql: transport (12 tables) | 8 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE | Tenant database. Tables: transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.favourite_route, transport.network_import, transport.pass_type, transport.route, transport.route_stop, transport.station, transport.timetable, transport.timetable_run. Source DDL: backend/tenant/010-transport.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
4 | 1 | DB-READ-VIEWS | PLATFORM | [BE] Published read views for cross-module reads, generated from the lineage | 5 | Pranay Shinde |  | MIG-BASELINE | Published read views for cross-module reads, generated from the lineage. A deriver reads handoff/api-data-lineage.json and generates, per owning module, the views other modules may read (894 cross-schema reads on 30 September; ADR-0055), applied by the migrations. Done when: every cross-schema read in the Block A slice goes through a published view, the views regenerate with one command, and a raw cross-schema read is reported by the lineage check.
4 | 1 | DB-ROLES | PLATFORM | [BE] One Postgres role per deployable; the AI role read-only | 2 | Tanmay Dukhande |  | MIG-BASELINE | One Postgres role per deployable; the AI role read-only. Roles for commerce, access, operations, ticvai-ai and workers (ADR-0055), created in the baseline migrations and granted their modules' schemas plus the published read views; the ticvai-ai role is read-only on the transactional schemas (ADR-0020). Done when: each host connects with its own role from the cell's Key Vault, and a write from the AI role to a transactional table is refused by PostgreSQL.
5 | 1 | MIG-GAMES | MIG | [DB] Migration V0008__games.sql: games (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PII | Tenant database. Tables: games.card, games.credit_ledger. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
5 | 1 | MIG-IDENTITY | MIG | [DB] Migration V0009__identity.sql: identity (13 tables) | 8 | Tanmay Dukhande | IdentityService | MIG-BASELINE MIG-PII | Tenant database. Tables: identity.delegated_access, identity.guest_identity_verification, identity.guest_verification_policy, identity.mfa_challenge, identity.mfa_method, identity.mfa_recovery_code, identity.otp_challenge, identity.password_policy, identity.platform_staff_grant, identity.principal, identity.principal_credential, identity.refresh_token, identity.role. Source DDL: backend/tenant/010-identity.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-APPROVALS | MIG | [DB] Migration V0010__approvals.sql: approvals (6 tables) | 5 | Tanmay Dukhande | TenancyService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: approvals.decision, approvals.delegation, approvals.external_provider, approvals.matrix, approvals.request, approvals.rule. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-ASSETS | MIG | [DB] Migration V0013__assets.sql: assets (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: assets.asset_version, assets.media_asset, assets.media_collection, assets.media_collection_member, assets.media_fingerprint, assets.media_upload, assets.media_usage. Source DDL: backend/tenant/010-assets.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-REPORTING | MIG | [DB] Migration V0011__reporting.sql: reporting (15 tables) | 8 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: reporting.alert, reporting.alert_rule, reporting.dashboard, reporting.dashboard_tile, reporting.dashboard_view, reporting.execution, reporting.kpi_definition, reporting.natural_language_query, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter, reporting.schedule, reporting.semantic_model. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-RESOURCES | MIG | [DB] Migration V0015__resources.sql: resources (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: resources.booking, resources.resource, resources.resource_block, resources.resource_hold, resources.resource_package, resources.resource_requirement, resources.resource_schedule. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-SYNC | MIG | [DB] Migration V0012__sync.sql: sync (1 tables) | 1 | Pranay Shinde | CrossRegionService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: sync.rejection. Source DDL: backend/tenant/010-sync.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-WHITELABEL | MIG | [DB] Migration V0016__whitelabel.sql: whitelabel (25 tables) | 8 | Tanmay Dukhande | WhiteLabelService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: whitelabel.analytics_provider, whitelabel.app_build, whitelabel.banner, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.content_page, whitelabel.custom_domain, whitelabel.faq_category, whitelabel.faq_entry, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_item, whitelabel.policy, whitelabel.promo_block, whitelabel.site_setup_progress, whitelabel.store_account, whitelabel.tenant_config. Source DDL: backend/tenant/010-whitelabel.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
6 | 1 | MIG-WORKFORCE | MIG | [DB] Migration V0017__workforce.sql: workforce (1 tables) | 1 | Tanmay Dukhande | TenancyService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: workforce.rota_assignment. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
7 | 1 | MIG-AI | MIG | [DB] Migration V0014__ai.sql: ai (46 tables) | 8 | Pranay Shinde | AiService | MIG-ASSETS MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: ai.action_plan, ai.activity, ai.anomaly_detector, ai.answer_feedback, ai.assistant_profile, ai.byok_enablement, ai.capability, ai.capability_maturity, ai.chunk_embedding, ai.conversation, ai.decision_record, ai.eval_run, ai.eval_suite, ai.forecast_definition, ai.forecast_point, ai.forecast_scenario, ai.forecast_version, ai.governance_alert, ai.governance_policy, ai.governance_policy_version, ai.guided_choice_suggestion, ai.history_import, ai.history_observation, ai.incident, ai.index_entry, ai.index_job, ai.index_source, ai.insight, ai.intervention, ai.knowledge_collection, ai.knowledge_document, ai.knowledge_gap, ai.message, ai.model, ai.operational_requirement, ai.policy, ai.policy_exception, ai.prompt_template, ai.proposed_action, ai.provider, ai.rec_decision, ai.rec_decline, ai.rec_event, ai.release, ai.suggestion, ai.venue_settings. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
7 | 1 | MIG-PLATFORM | MIG | [DB] Migration V0018__platform.sql: platform (17 tables) | 8 | Tanmay Dukhande | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: platform.audit_record, platform.denomination, platform.device, platform.device_heartbeat, platform.dsar_request, platform.guest_link, platform.idempotency_record, platform.outbox, platform.outlet, platform.region_settings, platform.sale_board, platform.sale_board_page, platform.sale_board_tile, platform.scope, platform.tenant, platform.venue_settings, platform.workstation. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
8 | 1 | SETUP-AUTH | SETUP | [DevOps] Sign-in working end to end against IdentityService | 5 | Hrushikant Patkar |  | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Sign-in working end to end against IdentityService. In **ticvai-backend** and **ticvai-frontend**: the identity sign-in operations, `ICurrentPrincipal` and `ITenantContext` filled from the session, signing keys from the cell's Azure Key Vault (audit R057). Done when: a seeded staff member signs in from a web app and an app, gets their effective permissions, and a request without a session gets 401.
8 | 1 | MIG-MAINTENANCE | MIG | [DB] Migration V0020__maintenance.sql: maintenance (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: maintenance.asset, maintenance.incident, maintenance.inspection, maintenance.inspection_template, maintenance.inspection_template_item, maintenance.work_order. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
8 | 1 | MIG-SEATING | MIG | [DB] Migration V0019__seating.sql: seating (6 tables) | 3 | Tanmay Dukhande | CatalogueService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Tenant database. Tables: seating.seat, seating.seat_block, seating.seat_category, seating.seat_hold, seating.seat_map, seating.seat_price_band. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
8 | 1 | MIG-WALLET | MIG | [DB] Migration V0021__wallet.sql: wallet (23 tables) | 8 | Pranay Shinde | WalletService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Tenant database. Tables: wallet.accounting_mapping, wallet.adjustment, wallet.authentication_policy, wallet.auto_reload_setting, wallet.balance, wallet.channel_rules, wallet.configuration_version, wallet.configuration_version_snapshot, wallet.consumption_policy, wallet.credit_lot, wallet.credit_type, wallet.exit_settlement, wallet.funding_rules, wallet.gift_card, wallet.hold, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rules, wallet.transfer_rules, wallet.wallet, wallet.wallet_transaction, wallet.wallet_type. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
9 | 1 | MIG-CATALOGUE | MIG | [DB] Migration V0022__catalogue.sql: catalogue (31 tables) | 8 | Tanmay Dukhande | CatalogueService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM MIG-SEATING | Tenant database. Tables: catalogue.alternative_code, catalogue.audit_entry, catalogue.channel_allocation, catalogue.channel_capacity, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, catalogue.entitlement_template, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.group_package, catalogue.import_job, catalogue.inventory_hold, catalogue.performance, catalogue.price, catalogue.price_category, catalogue.price_list, catalogue.price_resolution_policy, catalogue.pricing_test_case, catalogue.product, catalogue.product_category, catalogue.product_eligibility_rule, catalogue.product_media, catalogue.product_version, catalogue.published_bundle, catalogue.rate, catalogue.rounding_profile, catalogue.variant, catalogue.waitlist_entry. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
9 | 1 | PLATFORM-KERNEL | PLATFORM | [BE] Request kernel: hostname to tenant routing, per-transaction scope, error model and 429 | 8 | Pranay Shinde |  | SETUP-AUTH SETUP-DB | Request kernel: hostname to tenant routing, per-transaction scope, error model and 429. In ticvai-backend. Resolve the tenant from the hostname (control-plane routing table, SD-021), open every transaction with the tenant and scope settings the row-level policies read (SD-059), one problem-details error model, and 429 with Retry-After on the hot public operations (SD-043). Done when: two seeded tenants on two hostnames cannot read each other's rows, and a flood test returns 429 instead of 500.
10 | 1 | MIG-LEDGER | MIG | [DB] Migration V0023__ledger.sql: ledger (19 tables) | 8 | Tanmay Dukhande | LedgerService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: ledger.account, ledger.cost_center, ledger.credit_memo, ledger.credit_memo_line, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.event_budget, ledger.fiscal_period, ledger.fx_provider_assignment, ledger.fx_rate, ledger.journal_entry, ledger.journal_line, ledger.legal_entity, ledger.posting, ledger.price_variance, ledger.tax_code, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template. Source DDL: backend/tenant/010-ledger.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
10 | 1 | OFFLINE-BUNDLE | OFFLINE | [BE] Signed catalogue and entitlement bundles, and the lease client | 8 | Tanmay Dukhande |  | PLATFORM-KERNEL | Signed catalogue and entitlement bundles, and the lease client. The signed bundle a till or scanner trades from offline, including entitlements and dynamic access policy for the scanner (SD-052), and the lease each workstation holds (SD-047). Done when: a till with an expired lease stops selling offline and says why.
10 | 1 | PLATFORM-AUDIT | PLATFORM | [BE] Audit interceptor for every write | 3 | Tanmay Dukhande |  | PLATFORM-KERNEL | Audit interceptor for every write. Who, what, when, tenant and venue for every write, written once by an interceptor rather than per operation (SD-057). Done when: any write in the Block A slice leaves one audit row a support user can read.
10 | 1 | PLATFORM-FLAGS | PLATFORM | [BE] Release flags per tenant | 2 | Tanmay Dukhande |  | PLATFORM-KERNEL | Release flags per tenant. Half-built features stay dark per tenant between sprints (SD-051). Done when: a flag switched off for one tenant hides a screen and refuses its operations for that tenant only.
10 | 1 | PLATFORM-IDEMPOTENCY | PLATFORM | [BE] Durable idempotency: the Idempotency-Key store and middleware | 5 | Tanmay Dukhande |  | PLATFORM-KERNEL | Durable idempotency: the Idempotency-Key store and middleware. Idempotency records in PostgreSQL with Redis as a cache only (SD-024), so a retried payment or sale after a restart returns the first answer. Done when: replaying a createOrder with the same key after a service restart returns the original response and creates nothing.
10 | 1 | PLATFORM-OUTBOX | PLATFORM | [BE] Outbox, relay and inbox behind the kernel broker interface, on a local RabbitMQ | 8 | Tanmay Dukhande |  | PLATFORM-KERNEL SETUP-HOSTS | Outbox, relay and inbox behind the kernel broker interface, on a local RabbitMQ. The transactional outbox per tenant database; one relay per region in the workers host, with a lease and a polling loop per tenant database, and an inbox per tenant database for exactly-once handling (ADR-0058); publishing and consuming only through the kernel interface (IEventPublisher, IEventSubscriber). The broker per ADR-0057 is the client's choice between RabbitMQ and Kafka: build behind the kernel interface on a local RabbitMQ until they answer, with ordering per aggregate by an ordering key and dead letters drained into platform.dead_letter. A relay-lag dashboard and alert per tenant database (SD-030, SD-031, SD-032). Done when: an event written in a transaction reaches its consumer once, survives a relay restart and a redelivery, a poison message lands in platform.dead_letter, and relay lag shows on the dashboard and alerts when unpublished rows are older than 60 seconds.
10 | 1 | PLATFORM-RLS | PLATFORM | [BE] Row-level policies without a per-row subquery on hot tables | 3 | Tanmay Dukhande |  | PLATFORM-KERNEL | Row-level policies without a per-row subquery on hot tables. Scope predicates read session settings instead of joining per row (SD-016). Done when: the order and scan-event queries keep their plan with policies on, measured on the seed data.
11 | 1 | MIG-INVENTORY | MIG | [DB] Migration V0024__inventory.sql: inventory (11 tables) | 8 | Hrushikant Patkar | InventoryService | MIG-BASELINE MIG-IDENTITY MIG-LEDGER MIG-PLATFORM | Tenant database. Tables: inventory.goods_receipt, inventory.goods_receipt_line, inventory.item, inventory.kit_component, inventory.location, inventory.movement, inventory.purchase_order, inventory.requisition, inventory.serialised_item, inventory.stock_batch, inventory.supplier. Source DDL: backend/tenant/010-inventory.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
11 | 1 | MIG-PROMOTIONS | MIG | [DB] Migration V0025__promotions.sql: promotions (17 tables) | 8 | Tanmay Dukhande | CatalogueService | MIG-BASELINE MIG-LEDGER MIG-PII MIG-PLATFORM | Tenant database. Tables: promotions.allocation_component, promotions.allocation_split, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component, promotions.campaign, promotions.campaign_budget, promotions.coupon_campaign, promotions.coupon_code, promotions.coupon_code_batch, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication, promotions.promotion_evaluation_trace, promotions.promotion_rule, promotions.promotion_variant. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
11 | 1 | OFFLINE-SYNC | OFFLINE | [BE] syncOrders: a result per entry, and a bad entry quarantined instead of blocking the till | 5 | Pranay Shinde |  | OFFLINE-BUNDLE | syncOrders: a result per entry, and a bad entry quarantined instead of blocking the till. Per-entry outcomes, a quarantine a supervisor resolves, and the till carrying on with the rest (SD-028). Done when: one malformed sale in a batch of twenty is quarantined and the other nineteen are accepted.
11 | 1 | PLATFORM-PAYMENTS | PLATFORM | [BE] Payment adapter and signed webhook against the provider's test mode | 8 | Pranay Shinde |  | PLATFORM-OUTBOX | Payment adapter and signed webhook against the provider's test mode. The provider adapter, the inbound signed webhook, the provider reference on payments, 3-D Secure redirect states and the card-terminal flow for the POS (SD-034). Done when: an approved, a declined and a 3-D Secure payment each end in the right order state from the webhook alone, with polling only as the fallback. Acceptance of the declined, unknown and reconcile paths waits on the client's payment sandbox credentials: see the client's answer in the Decisions Register.
11 | 1 | PLATFORM-SAGA-PAID | PLATFORM | [BE] Order paid to tickets issued: the saga proven end to end | 5 | Pranay Shinde |  | PLATFORM-OUTBOX | Order paid to tickets issued: the saga proven end to end. order.paid consumed by the entitlement owner, tickets issued, the ledger posting once from the event, and holds converted with capacity decremented (SD-026, SD-023). Done when: a web purchase in the sandbox ends with a ticket, one ledger posting and sold capacity reduced, and a replayed event changes nothing.
11 | 1 | POS-KDS-ROUTING | OFFLINE | [BE] A POS sale reaches the kitchen: routing online, and the LAN path decision | 5 | Pranay Shinde |  | PLATFORM-OUTBOX | A POS sale reaches the kitchen: routing online, and the LAN path decision. createFnbOrder from the POS creates the kitchen ticket as the guest order does, routed to the right station (SD-046). The offline LAN path to the Kitchen Display is an ADR decision; this task implements the online path and the stub the decision fills. Done when: a POS sale of a burger and a drink shows on the grill and bar stations.
12 | 1 | MIG-ORDERS | MIG | [DB] Migration V0026__orders.sql: orders (33 tables) | 8 | Pranay Shinde | OrderService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-LEDGER MIG-PII MIG-PLATFORM MIG-PROMOTIONS | Tenant database. Tables: orders.cart, orders.cart_line, orders.cash_count_line, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, orders.fraud_rule, orders.group_booking, orders.invitation, orders.no_sale_event, orders.order_event, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.payment_link, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, orders.refund, orders.refund_policy, orders.refund_policy_time_band, orders.resale_listing, orders.reservation, orders.reservation_line, orders.sales_order, orders.stored_value_authorisation, orders.ticket_template, orders.ticket_template_channel, orders.ticket_transfer, orders.visit_reminder, orders.wallet_pass. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
13 | 1 | MIG-ACCESS | MIG | [DB] Migration V0027__access.sql: access (23 tables) | 8 | Hrushikant Patkar | AccessService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: access.access_attribute, access.access_device, access.access_incident, access.access_point, access.access_point_group, access.accreditation_credential, access.admission_rules, access.biometric_audit_event, access.biometric_profile, access.blacklist, access.configuration_change, access.credential_policy, access.device_binding, access.dynamic_policy, access.dynamic_policy_version, access.entitlement, access.entry_rule_point, access.face_reenrolment_attempt, access.gate_mode_change, access.gate_mode_policy, access.parking_entitlement, access.parking_facility, access.scan_event. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
13 | 1 | MIG-MARKETING | MIG | [DB] Migration V0028__marketing.sql: marketing (49 tables) | 8 | Pranay Shinde | MarketingService | MIG-AI MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: marketing.agent_availability, marketing.attribution_touch, marketing.booking_consent_record, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.case, marketing.case_message, marketing.challenge, marketing.challenge_progress, marketing.consent_propagation, marketing.consent_purpose, marketing.consent_purpose_channel, marketing.consent_question, marketing.consent_question_version, marketing.consent_record, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment, marketing.cookie_banner_design, marketing.device_consent, marketing.device_consent_category, marketing.form_definition, marketing.form_definition_field, marketing.form_submission, marketing.guest_device, marketing.guest_document, marketing.guest_preference, marketing.guest_profile, marketing.invitation, marketing.invitation_campaign, marketing.journey, marketing.loyalty_position, marketing.loyalty_programme, marketing.loyalty_rule, marketing.message_dispatch, marketing.message_template, marketing.message_template_version, marketing.points_earning_rule, marketing.points_redemption_rule, marketing.privacy_notice_governance, marketing.programme_tier, marketing.referral, marketing.review, marketing.segment, marketing.segment_criterion, marketing.subscription, marketing.tracking_technology, marketing.wishlist_item. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
14 | 1 | MIG-FNB | MIG | [DB] Migration V0029__fnb.sql: fnb (34 tables) | 8 | Hrushikant Patkar | FnbService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-INVENTORY MIG-ORDERS MIG-PII MIG-PLATFORM MIG-SEATING | Tenant database. Tables: fnb.cold_chain_event, fnb.corrective_action, fnb.course_rule, fnb.delivery_location, fnb.delivery_location_outlet, fnb.delivery_policy, fnb.dining_table, fnb.kitchen_exception, fnb.kitchen_station, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.location_session, fnb.menu, fnb.menu_item, fnb.menu_item_modifier, fnb.menu_section, fnb.modifier_group, fnb.modifier_option, fnb.order_fulfilment, fnb.production_plan, fnb.production_plan_line, fnb.production_run, fnb.recipe, fnb.recipe_ingredient, fnb.reservation_table, fnb.service_order, fnb.service_order_line, fnb.sold_out_item, fnb.table_combination, fnb.table_reservation, fnb.table_session, fnb.table_visit, fnb.temperature_log, fnb.waitlist_entry. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
14 | 1 | MIG-PAYMENTS | MIG | [DB] Migration V0030__payments.sql: payments (11 tables) | 8 | Pranay Shinde | OrderService | MIG-BASELINE MIG-MARKETING MIG-ORDERS MIG-PII | Tenant database. Tables: payments.dunning_case, payments.instalment, payments.instalment_plan, payments.instalment_policy, payments.method, payments.payment_attempt, payments.provider, payments.provider_connection, payments.routing_rule, payments.stored_forward, payments.token. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
14 | 1 | MIG-QUEUE | MIG | [DB] Migration V0031__queue.sql: queue (5 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-MAINTENANCE MIG-PII MIG-PLATFORM | Tenant database. Tables: queue.entry, queue.feed, queue.queue, queue.queue_operating_window, queue.reading. Source DDL: backend/tenant/010-queue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
14 | 1 | MIG-VENUEMAP | MIG | [DB] Migration V0033__venuemap.sql: venuemap (8 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-ASSETS MIG-BASELINE MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS MIG-RESOURCES | Tenant database. Tables: venuemap.import_job, venuemap.map, venuemap.map_version, venuemap.path, venuemap.placed_resource, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item. Source DDL: backend/tenant/010-venuemap.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
15 | 1 | MIG-RETAIL | MIG | [DB] Migration V0032__retail.sql: retail (10 tables) | 5 | Pranay Shinde | RetailService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-FNB MIG-IDENTITY MIG-INVENTORY MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: retail.merchandise, retail.reservation, retail.reservation_line, retail.return, retail.return_line, retail.return_policy, retail.sale, retail.sale_line, retail.shop_and_drop, retail.shop_and_drop_line. Source DDL: backend/tenant/010-retail.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing.
16 | 1 | MIG-FOREIGN-KEYS | MIG | [DB] Migration V0034__cross_schema_foreign_keys.sql (37 keys) | 3 | Hrushikant Patkar |  | MIG-ACCESS MIG-AI MIG-APPROVALS MIG-ASSETS MIG-CATALOGUE MIG-CONTROL MIG-FNB MIG-GAMES MIG-IDENTITY MIG-INVENTORY MIG-LEDGER MIG-MAINTENANCE MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM MIG-PRICING MIG-PROMOTIONS MIG-QUEUE MIG-REPORTING MIG-RESOURCES MIG-RETAIL MIG-SEATING MIG-SUBSCRIPTION MIG-SYNC MIG-TENANCY MIG-TRANSPORT MIG-VENUEMAP MIG-WALLET MIG-WHITELABEL MIG-WORKFORCE | The foreign keys that point from a schema into one created after it: ai (2), assets (2), catalogue (3), games (1), identity (2), ledger (2), maintenance (2), orders (2), pii (2), platform (3), pricing (1), promotions (1), reporting (1), resources (2), seating (2), subscription (1), sync (1), transport (1), wallet (2), whitelabel (2), workforce (2). From 900-foreign-keys.sql.
17 | 1 | SETUP-SEED | SETUP | [DevOps] Seed data: the reference fixture (two brands, three regions, AED and OMR) every test runs against | 5 | Hrushikant Patkar |  | MIG-ACCESS MIG-AI MIG-APPROVALS MIG-ASSETS MIG-BASELINE MIG-CATALOGUE MIG-CONTROL MIG-FNB MIG-FOREIGN-KEYS MIG-GAMES MIG-IDENTITY MIG-INVENTORY MIG-LEDGER MIG-MAINTENANCE MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM MIG-PRICING MIG-PROMOTIONS MIG-QUEUE MIG-REPORTING MIG-RESOURCES MIG-RETAIL MIG-SEATING MIG-SUBSCRIPTION MIG-SYNC MIG-TENANCY MIG-TRANSPORT MIG-VENUEMAP MIG-WALLET MIG-WHITELABEL MIG-WORKFORCE | Seed data: the reference fixture (two brands, three regions, AED and OMR) every test runs against. In **ticvai-backend** `db/seed`: the reference fixture quality-gates 8 requires - two brands, three regions across two countries, AED and OMR - with products, prices, events, tills, staff, roles and denominations, so apps can be built before the Back Office setup screens exist. The denominations and roles seed from docs/active/seed-data-proposal.md (proposed, client to correct - audit R229). Done when: it loads on a migrated database, integration tests run against it, and the frontend mock server serves the same data.
5 | 1 | SVC-TENANCY-DEVICES-1 | SVC-TENANCY-DEVICES | [BE] TenancyService: setDeviceAssignment | 2 | Deep Khanvilkar | TenancyService | MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeviceAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-devices Helper task: Tanmay Dukhande owns the service and reviews.
6 | 1 | SVC-IDENTITY-ADMINISTRATION-1 | SVC-IDENTITY-ADMINISTRATION | [BE] IdentityService: createPrincipal, createRole, listPrincipals, listRoles | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPrincipal, createRole, listPrincipals, listRoles. Spec: handoff/service-docs/backend/IdentityService.md#group-administration Helper task: Tanmay Dukhande owns the service and reviews.
6 | 1 | SVC-IDENTITY-ADMINISTRATION-2 | SVC-IDENTITY-ADMINISTRATION | [BE] IdentityService: openPlatformStaffGrant, updatePrincipal | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: openPlatformStaffGrant, updatePrincipal. Spec: handoff/service-docs/backend/IdentityService.md#group-administration Helper task: Tanmay Dukhande owns the service and reviews.
6 | 1 | SVC-IDENTITY-MFA-1 | SVC-IDENTITY-MFA | [BE] IdentityService: createMfaChallenge, enrolMfaMethod, listMfaMethods, removeMfaMethod | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMfaChallenge, enrolMfaMethod, listMfaMethods, removeMfaMethod. Spec: handoff/service-docs/backend/IdentityService.md#group-mfa Helper task: Tanmay Dukhande owns the service and reviews.
6 | 1 | SVC-PLATFORM-PUBLICAPI-2 | SVC-PLATFORM-PUBLICAPI | [BE] PlatformService: registerDeveloper, rotateApiCredential, setApiLicensing, setDeveloperMembers | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: registerDeveloper, rotateApiCredential, setApiLicensing, setDeveloperMembers. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi Helper task: Hrushikant Patkar owns the service and reviews.
7 | 1 | SVC-TENANCY-APPROVALS-1 | SVC-TENANCY-APPROVALS | [BE] TenancyService: approveMatrixMultiLevel, approveRoleAuthorityDelegation | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveMatrixMultiLevel, approveRoleAuthorityDelegation. Spec: handoff/service-docs/backend/TenancyService.md#group-approvals Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-TENANCY-DELEGATION-1 | SVC-TENANCY-DELEGATION | [BE] TenancyService: createApprovalDelegation | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createApprovalDelegation. Spec: handoff/service-docs/backend/TenancyService.md#group-delegation Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-TENANCY-MATRIX-1 | SVC-TENANCY-MATRIX | [BE] TenancyService: setApprovalExternalProvider, setApprovalMatrix | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalExternalProvider, setApprovalMatrix. Spec: handoff/service-docs/backend/TenancyService.md#group-matrix Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | SVC-WHITELABEL-APPPUBLISHING | [BE] WhiteLabelService: getAppBuild, getStoreAccounts, listAppBuilds, requestAppBuild | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAppBuild, getStoreAccounts, listAppBuilds, requestAppBuild. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-apppublishing Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-WHITELABEL-APPPUBLISHING-2 | SVC-WHITELABEL-APPPUBLISHING | [BE] WhiteLabelService: setStoreAccounts | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setStoreAccounts. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-apppublishing Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | SVC-WHITELABEL-BOOKINGFLOWS | [BE] WhiteLabelService: listBookingFlowTypes, listBookingFlows, updateBookingFlowDefinition, validateBookingFlow | 8 | Tanmay Dukhande | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBookingFlowTypes, listBookingFlows, updateBookingFlowDefinition, validateBookingFlow. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-bookingflows
7 | 1 | SVC-WHITELABEL-CONTENT-4 | SVC-WHITELABEL-CONTENT | [BE] WhiteLabelService: listGuidedChoices, listPolicies, listPromoBlocks, proposeGuidedChoice | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listGuidedChoices, listPolicies, listPromoBlocks, proposeGuidedChoice. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-WHITELABEL-PUBLISHING-1 | SVC-WHITELABEL-PUBLISHING | [BE] WhiteLabelService: createPreview, diffConfigVersion, getSiteSetupProgress, listConfigVersions | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPreview, diffConfigVersion, getSiteSetupProgress, listConfigVersions. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing Helper task: Tanmay Dukhande owns the service and reviews.
7 | 1 | SVC-WHITELABEL-PUBLISHING-2 | SVC-WHITELABEL-PUBLISHING | [BE] WhiteLabelService: publishTenantConfig, restoreConfigVersion, setSiteSetupProgress, validateTenantConfig | 8 | Tanmay Dukhande | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishTenantConfig, restoreConfigVersion, setSiteSetupProgress, validateTenantConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing
8 | 1 | SVC-IDENTITY-GUESTAUTH-1 | SVC-IDENTITY-GUESTAUTH | [BE] IdentityService: deleteGuestAccount, getGuestSession, getMyIdentityVerification, guestLogout | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteGuestAccount, getGuestSession, getMyIdentityVerification, guestLogout. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-IDENTITY-GUESTAUTH-3 | SVC-IDENTITY-GUESTAUTH | [BE] IdentityService: registerGuest, requestGuestOtp, submitGuestIdentityDocument, verifyGuestOtp | 8 | Tanmay Dukhande | IdentityService | MIG-ASSETS MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: registerGuest, requestGuestOtp, submitGuestIdentityDocument, verifyGuestOtp. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth
8 | 1 | SVC-IDENTITY-MFA-2 | SVC-IDENTITY-MFA | [BE] IdentityService: verifyMfaChallenge, verifyMfaEnrolment | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: verifyMfaChallenge, verifyMfaEnrolment. Spec: handoff/service-docs/backend/IdentityService.md#group-mfa Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-TENANCY-REGION-1 | SVC-TENANCY-REGION | [BE] TenancyService: updateRegionSettings | 2 | Chinmay Patkar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateRegionSettings. Spec: handoff/service-docs/backend/TenancyService.md#group-region Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-TENANCY-ROTA-1 | SVC-TENANCY-ROTA | [BE] TenancyService: createRotaAssignment, listRotaAssignments | 5 | Deep Khanvilkar | TenancyService | MIG-IDENTITY MIG-PLATFORM MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRotaAssignment, listRotaAssignments. Spec: handoff/service-docs/backend/TenancyService.md#group-rota Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-TENANCY-SCOPE-1 | SVC-TENANCY-SCOPE | [BE] TenancyService: createOrgUnit, listOrgUnits, updateOrgUnit | 3 | Sanket Keluskar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createOrgUnit, listOrgUnits, updateOrgUnit. Spec: handoff/service-docs/backend/TenancyService.md#group-scope Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-TENANCY-WORKSTATION-1 | SVC-TENANCY-WORKSTATION | [BE] TenancyService: configureWorkstation, createOutlet, createSaleBoard, listDevices | 8 | Tanmay Dukhande | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureWorkstation, createOutlet, createSaleBoard, listDevices. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation
8 | 1 | SVC-TENANCY-WORKSTATION-2 | SVC-TENANCY-WORKSTATION | [BE] TenancyService: listOutlets, listSaleBoards, listWorkstations, recordDeviceHeartbeat | 5 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listOutlets, listSaleBoards, listWorkstations, recordDeviceHeartbeat. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-TENANCY-WORKSTATION-3 | SVC-TENANCY-WORKSTATION | [BE] TenancyService: updateOutlet, updateSaleBoard | 3 | Sanket Keluskar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateOutlet, updateSaleBoard. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation Helper task: Tanmay Dukhande owns the service and reviews.
8 | 1 | SVC-WHITELABEL-OVERVIEW-1 | SVC-WHITELABEL-OVERVIEW | [BE] WhiteLabelService: getTenantAppStatus, getTenantConfig, listAnalyticsProviders, recordStorefrontSessionEvents | 8 | Tanmay Dukhande | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getTenantAppStatus, getTenantConfig, listAnalyticsProviders, recordStorefrontSessionEvents. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-overview
10 | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | SVC-WHITELABEL-BOOKINGFLOWS | [BE] WhiteLabelService: createBookingFlowDefinition, deleteBookingFlow, getBookingFlow, getPublishedBookingFlow | 8 | Tanmay Dukhande | WhiteLabelService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBookingFlowDefinition, deleteBookingFlow, getBookingFlow, getPublishedBookingFlow. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-bookingflows
13 | 1 | SVC-IDENTITY-GUESTAUTH-2 | SVC-IDENTITY-GUESTAUTH | [BE] IdentityService: guestPasswordLogin, guestSocialLogin, guestUaePassLogin, linkGuestCheckout | 8 | Tanmay Dukhande | IdentityService | MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: guestPasswordLogin, guestSocialLogin, guestUaePassLogin, linkGuestCheckout. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth
14 | 1 | SVC-IDENTITY-IDENTITY-1 | SVC-IDENTITY-IDENTITY | [BE] IdentityService: changeOwnCredential, exportSubjectData, forceLogout, getCurrentSession | 5 | Deep Khanvilkar | IdentityService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: changeOwnCredential, exportSubjectData, forceLogout, getCurrentSession. Spec: handoff/service-docs/backend/IdentityService.md#group-identity Helper task: Tanmay Dukhande owns the service and reviews.
14 | 1 | SVC-IDENTITY-IDENTITY-2 | SVC-IDENTITY-IDENTITY | [BE] IdentityService: grantDelegation, listDelegations, login, refreshToken | 8 | Tanmay Dukhande | IdentityService | MIG-IDENTITY MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: grantDelegation, listDelegations, login, refreshToken. Spec: handoff/service-docs/backend/IdentityService.md#group-identity
14 | 1 | SVC-IDENTITY-IDENTITY-3 | SVC-IDENTITY-IDENTITY | [BE] IdentityService: selectRole, setGuestVerificationPolicy, setPasswordPolicy, verifyGuestEmail | 8 | Tanmay Dukhande | IdentityService | MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: selectRole, setGuestVerificationPolicy, setPasswordPolicy, verifyGuestEmail. Spec: handoff/service-docs/backend/IdentityService.md#group-identity
6 | 1 | SVC-IDENTITY-SESSION-1 | SVC-IDENTITY-SESSION | [BE] IdentityService: listActiveSessions | 1 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-IDENTITY-3 SVC-IDENTITY-MFA-2 | Operations: listActiveSessions. Spec: handoff/service-docs/backend/IdentityService.md#group-session Helper task: Tanmay Dukhande owns the service and reviews.
14 | 1 | SVC-PLATFORM-PUBLICAPI-1 | SVC-PLATFORM-PUBLICAPI | [BE] PlatformService: certifyIntegration, createApiClient, decideProductionAccess, deprecateApiVersion | 8 | Hrushikant Patkar | PlatformService | MIG-CONTROL MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: certifyIntegration, createApiClient, decideProductionAccess, deprecateApiVersion. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi
14 | 1 | SVC-TENANCY-REQUEST-1 | SVC-TENANCY-REQUEST | [BE] TenancyService: createApprovalRequest, decideApprovalRequest, evaluateApprovalRequirement | 8 | Tanmay Dukhande | TenancyService | MIG-APPROVALS MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createApprovalRequest, decideApprovalRequest, evaluateApprovalRequirement. Spec: handoff/service-docs/backend/TenancyService.md#group-request
14 | 1 | SVC-TENANCY-TENANCY-1 | SVC-TENANCY-TENANCY | [BE] TenancyService: getVenueSettings, getWorkstationHealth, setVenueSettings | 8 | Tanmay Dukhande | TenancyService | MIG-ACCESS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getVenueSettings, getWorkstationHealth, setVenueSettings. Spec: handoff/service-docs/backend/TenancyService.md#group-tenancy
5 | 2 | SVC-PLATFORM-LICENSING-1 | SVC-PLATFORM-LICENSING | [BE] PlatformService: addLicenceAddOn | 2 | Chinmay Patkar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addLicenceAddOn. Spec: handoff/service-docs/backend/PlatformService.md#group-licensing Helper task: Hrushikant Patkar owns the service and reviews.
5 | 2 | SVC-PLATFORM-PLAN-1 | SVC-PLATFORM-PLAN | [BE] PlatformService: createPlan, createPlanVersion | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPlan, createPlanVersion. Spec: handoff/service-docs/backend/PlatformService.md#group-plan Helper task: Hrushikant Patkar owns the service and reviews.
5 | 2 | SVC-PLATFORM-SUBSCRIPTION-1 | SVC-PLATFORM-SUBSCRIPTION | [BE] PlatformService: setSubscription | 2 | Chinmay Patkar | PlatformService | MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSubscription. Spec: handoff/service-docs/backend/PlatformService.md#group-subscription Helper task: Hrushikant Patkar owns the service and reviews.
5 | 2 | SVC-PLATFORM-TENANT-2 | SVC-PLATFORM-TENANT | [BE] PlatformService: terminateTenant, updateTenant | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: terminateTenant, updateTenant. Spec: handoff/service-docs/backend/PlatformService.md#group-tenant Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-WHITELABEL-BRAND-1 | SVC-WHITELABEL-BRAND | [BE] WhiteLabelService: getAppIcons, getBrandIdentity, setAppIcons, setBrandIdentity | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAppIcons, getBrandIdentity, setAppIcons, setBrandIdentity. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-brand Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-BRANDING-1 | SVC-WHITELABEL-BRANDING | [BE] WhiteLabelService: getBookingFlowConfig, setBookingFlowConfig | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBookingFlowConfig, setBookingFlowConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-branding Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-CONTENT-1 | SVC-WHITELABEL-CONTENT | [BE] WhiteLabelService: createBanner, createContentPage, createGuidedChoice, createPromoBlock | 8 | Tanmay Dukhande | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBanner, createContentPage, createGuidedChoice, createPromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content
7 | 2 | SVC-WHITELABEL-CONTENT-2 | SVC-WHITELABEL-CONTENT | [BE] WhiteLabelService: deleteBanner, deleteContentPage, deleteGuidedChoice, deletePromoBlock | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteBanner, deleteContentPage, deleteGuidedChoice, deletePromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-CONTENT-5 | SVC-WHITELABEL-CONTENT | [BE] WhiteLabelService: publishGuidedChoice, setFaqs, setPolicy, unpublishGuidedChoice | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishGuidedChoice, setFaqs, setPolicy, unpublishGuidedChoice. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-CONTENT-6 | SVC-WHITELABEL-CONTENT | [BE] WhiteLabelService: updateBanner, updateContentPage, updateGuidedChoice, updatePromoBlock | 8 | Tanmay Dukhande | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateBanner, updateContentPage, updateGuidedChoice, updatePromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content
7 | 1 | SVC-WHITELABEL-CONTENT-3 | SVC-WHITELABEL-CONTENT | [BE] WhiteLabelService: getPublishedGuidedChoice, listBanners, listContentPages, listFaqs | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-4 SVC-WHITELABEL-CONTENT-5 SVC-WHITELABEL-CONTENT-6 | Operations: getPublishedGuidedChoice, listBanners, listContentPages, listFaqs. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-HOMEPAGE-1 | SVC-WHITELABEL-HOMEPAGE | [BE] WhiteLabelService: getHomepageLayout, setHomepageLayout | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getHomepageLayout, setHomepageLayout. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-homepage Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-MODULES-1 | SVC-WHITELABEL-MODULES | [BE] WhiteLabelService: getFeatureToggles, getModuleEnablement, setFeatureToggles, setLanguages | 3 | Sanket Keluskar | WhiteLabelService | MIG-CONTROL MIG-SUBSCRIPTION MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFeatureToggles, getModuleEnablement, setFeatureToggles, setLanguages. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-modules Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-MODULES-2 | SVC-WHITELABEL-MODULES | [BE] WhiteLabelService: setModuleEnablement | 1 | Chinmay Patkar | WhiteLabelService | MIG-CONTROL MIG-SUBSCRIPTION MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setModuleEnablement. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-modules Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-NAVIGATION-1 | SVC-WHITELABEL-NAVIGATION | [BE] WhiteLabelService: getNavigation, setHeader, setNavigation | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getNavigation, setHeader, setNavigation. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-navigation Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-OVERVIEW-2 | SVC-WHITELABEL-OVERVIEW | [BE] WhiteLabelService: setAnalyticsProvider, setMaintenanceMode | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAnalyticsProvider, setMaintenanceMode. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-overview Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-THEME-1 | SVC-WHITELABEL-THEME | [BE] WhiteLabelService: getFonts, getTheme, setFonts, setTheme | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFonts, getTheme, setFonts, setTheme. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-theme Helper task: Tanmay Dukhande owns the service and reviews.
7 | 2 | SVC-WHITELABEL-WHITE-LABEL-1 | SVC-WHITELABEL-WHITE-LABEL | [BE] WhiteLabelService: claimCustomDomain, listCustomDomains, relinquishCustomDomain, verifyCustomDomain | 5 | Deep Khanvilkar | WhiteLabelService | MIG-CONTROL MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimCustomDomain, listCustomDomains, relinquishCustomDomain, verifyCustomDomain. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-white-label Helper task: Tanmay Dukhande owns the service and reviews.
8 | 2 | SVC-PLATFORM-TENANT-1 | SVC-PLATFORM-TENANT | [BE] PlatformService: createTenant, listTenants, reactivateTenant, suspendTenant | 8 | Hrushikant Patkar | PlatformService | MIG-CONTROL MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createTenant, listTenants, reactivateTenant, suspendTenant. Spec: handoff/service-docs/backend/PlatformService.md#group-tenant
14 | 2 | SVC-WHITELABEL-WHITELABEL-1 | SVC-WHITELABEL-WHITELABEL | [BE] WhiteLabelService: createContentBlock, publishContentBlock, setFooter | 8 | Tanmay Dukhande | WhiteLabelService | MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createContentBlock, publishContentBlock, setFooter. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-whitelabel
9 | 1 | SVC-WALLET-CARD-1 | SVC-WALLET-CARD | [BE] WalletService: loadGameCredits | 3 | Sanket Keluskar | WalletService | MIG-GAMES MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: loadGameCredits. Spec: handoff/service-docs/backend/WalletService.md#group-card Helper task: Pranay Shinde owns the service and reviews.
9 | 1 | SVC-WALLET-WALLET-1 | SVC-WALLET-WALLET | [BE] WalletService: captureWalletHold, expireCreditLots, getWallet, holdWalletFunds | 8 | Pranay Shinde | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: captureWalletHold, expireCreditLots, getWallet, holdWalletFunds. Spec: handoff/service-docs/backend/WalletService.md#group-wallet
10 | 1 | SVC-CATALOGUE-CATALOGUE-3 | SVC-CATALOGUE-CATALOGUE | [BE] CatalogueService: searchCatalogue, setCurrencyRoundingRule, setDynamicPriceRule, setDynamicPricingGuardrailPolicy | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PLATFORM MIG-PRICING MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: searchCatalogue, setCurrencyRoundingRule, setDynamicPriceRule, setDynamicPricingGuardrailPolicy. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue
10 | 1 | SVC-CATALOGUE-CATALOGUE-4 | SVC-CATALOGUE-CATALOGUE | [BE] CatalogueService: setPriceCategoryRateType, setProductCategories | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPriceCategoryRateType, setProductCategories. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | SVC-CATALOGUE-ENTITLEMENT | [BE] CatalogueService: createEntitlementTemplate | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createEntitlementTemplate. Spec: handoff/service-docs/backend/CatalogueService.md#group-entitlement Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-EVENT-1 | SVC-CATALOGUE-EVENT | [BE] CatalogueService: createEvent, getPerformance, listEvents, listPerformances | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createEvent, getPerformance, listEvents, listPerformances. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-EVENT-2 | SVC-CATALOGUE-EVENT | [BE] CatalogueService: updateEvent, updatePerformance | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateEvent, updatePerformance. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-EVENTS-1 | SVC-CATALOGUE-EVENTS | [BE] CatalogueService: cloneEvent, setEventLifecycleState | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cloneEvent, setEventLifecycleState. Spec: handoff/service-docs/backend/CatalogueService.md#group-events Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-LEASE-1 | SVC-CATALOGUE-LEASE | [BE] CatalogueService: acquireInventoryHold, listInventoryHolds, relinquishInventoryHold, renewInventoryHold | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: acquireInventoryHold, listInventoryHolds, relinquishInventoryHold, renewInventoryHold. Spec: handoff/service-docs/backend/CatalogueService.md#group-lease
10 | 1 | SVC-CATALOGUE-PRICING-1 | SVC-CATALOGUE-PRICING | [BE] CatalogueService: copyPriceList, createPriceList, setPrices, updatePriceList | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: copyPriceList, createPriceList, setPrices, updatePriceList. Spec: handoff/service-docs/backend/CatalogueService.md#group-pricing
10 | 1 | SVC-CATALOGUE-PRODUCT-3 | SVC-CATALOGUE-PRODUCT | [BE] CatalogueService: resolveProductByCode, setAlternativeCodes, setGroupPackageDefinition, setProductEligibilityRule | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveProductByCode, setAlternativeCodes, setGroupPackageDefinition, setProductEligibilityRule. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-PRODUCT-4 | SVC-CATALOGUE-PRODUCT | [BE] CatalogueService: updateProduct | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateProduct. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Tanmay Dukhande owns the service and reviews.
11 | 1 | SVC-LEDGER-FINANCE-1 | SVC-LEDGER-FINANCE | [BE] LedgerService: ingestFxRates, setFxProvider | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: ingestFxRates, setFxProvider. Spec: handoff/service-docs/backend/LedgerService.md#group-finance Helper task: Tanmay Dukhande owns the service and reviews.
11 | 1 | SVC-LEDGER-FISCAL-1 | SVC-LEDGER-FISCAL | [BE] LedgerService: createLegalEntity | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createLegalEntity. Spec: handoff/service-docs/backend/LedgerService.md#group-fiscal Helper task: Tanmay Dukhande owns the service and reviews.
11 | 1 | SVC-LEDGER-LEDGER-1 | SVC-LEDGER-LEDGER | [BE] LedgerService: listFxRates, setFxRate | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listFxRates, setFxRate. Spec: handoff/service-docs/backend/LedgerService.md#group-ledger Helper task: Tanmay Dukhande owns the service and reviews.
11 | 1 | SVC-LEDGER-TAX-3 | SVC-LEDGER-TAX | [BE] LedgerService: transmitEInvoices, updateTaxCode | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: transmitEInvoices, updateTaxCode. Spec: handoff/service-docs/backend/LedgerService.md#group-tax Helper task: Tanmay Dukhande owns the service and reviews.
12 | 1 | SVC-CATALOGUE-BUNDLE-2 | SVC-CATALOGUE-BUNDLE | [BE] CatalogueService: publishBundle, updateBundle | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishBundle, updateBundle. Spec: handoff/service-docs/backend/CatalogueService.md#group-bundle Helper task: Tanmay Dukhande owns the service and reviews.
12 | 1 | SVC-CATALOGUE-COUPON-1 | SVC-CATALOGUE-COUPON | [BE] CatalogueService: createCouponCampaign, generateCouponCodes, getCouponCode | 8 | Tanmay Dukhande | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCouponCampaign, generateCouponCodes, getCouponCode. Spec: handoff/service-docs/backend/CatalogueService.md#group-coupon
12 | 1 | SVC-CATALOGUE-DRAFTED-1 | SVC-CATALOGUE-DRAFTED | [BE] CatalogueService: createBulkProductCatalogue, setBookingVelocityTime, setBundleComponent, setBundleDefinition | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PRICING MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBulkProductCatalogue, setBookingVelocityTime, setBundleComponent, setBundleDefinition. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted
12 | 1 | SVC-CATALOGUE-DRAFTED-2 | SVC-CATALOGUE-DRAFTED | [BE] CatalogueService: setBuyGetBogo, setCampaignBudgetFinancial, setCodeDistributionManager, setCouponPromoCode | 8 | Tanmay Dukhande | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBuyGetBogo, setCampaignBudgetFinancial, setCodeDistributionManager, setCouponPromoCode. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted
12 | 1 | SVC-CATALOGUE-DRAFTED-3 | SVC-CATALOGUE-DRAFTED | [BE] CatalogueService: setCrossCategoryPromotion, setDemandOccupancyAvailability, setEligibilityRule, setFixedPriceOffer | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PRICING MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCrossCategoryPromotion, setDemandOccupancyAvailability, setEligibilityRule, setFixedPriceOffer. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted
12 | 1 | SVC-CATALOGUE-DRAFTED-4 | SVC-CATALOGUE-DRAFTED | [BE] CatalogueService: setGiftFreeProduct, setGuestChoiceBuild, setPriceHierarchyInheritance, setPriceListMaster | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGiftFreeProduct, setGuestChoiceBuild, setPriceHierarchyInheritance, setPriceListMaster. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted
12 | 1 | SVC-CATALOGUE-DRAFTED-5 | SVC-CATALOGUE-DRAFTED | [BE] CatalogueService: setPromotionRule, setRateStructure, setRulePriorityConflict | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PRICING MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPromotionRule, setRateStructure, setRulePriorityConflict. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted
12 | 1 | SVC-CATALOGUE-EVALUATION-1 | SVC-CATALOGUE-EVALUATION | [BE] CatalogueService: evaluatePromotions | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: evaluatePromotions. Spec: handoff/service-docs/backend/CatalogueService.md#group-evaluation Helper task: Tanmay Dukhande owns the service and reviews.
12 | 1 | SVC-CATALOGUE-PROMOTION-1 | SVC-CATALOGUE-PROMOTION | [BE] CatalogueService: analysePromotionConflicts, createCommercialCampaign, createPromotion, getPromotion | 8 | Tanmay Dukhande | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: analysePromotionConflicts, createCommercialCampaign, createPromotion, getPromotion. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion
12 | 1 | SVC-CATALOGUE-PROMOTION-2 | SVC-CATALOGUE-PROMOTION | [BE] CatalogueService: getPromotionUsage, listPromotions, publishPromotion, updateCommercialCampaign | 8 | Tanmay Dukhande | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getPromotionUsage, listPromotions, publishPromotion, updateCommercialCampaign. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion
12 | 1 | SVC-CATALOGUE-PROMOTION-3 | SVC-CATALOGUE-PROMOTION | [BE] CatalogueService: updatePromotion | 3 | Sanket Keluskar | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updatePromotion. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion Helper task: Tanmay Dukhande owns the service and reviews.
12 | 1 | SVC-CATALOGUE-PROMOTIONS-1 | SVC-CATALOGUE-PROMOTIONS | [BE] CatalogueService: setPromotionVariants | 2 | Chinmay Patkar | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPromotionVariants. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotions Helper task: Tanmay Dukhande owns the service and reviews.
13 | 1 | SVC-CATALOGUE-CATALOGUE-2 | SVC-CATALOGUE-CATALOGUE | [BE] CatalogueService: joinWaitlist, leaveWaitlist, listGuestMemberships, listProductCategories | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: joinWaitlist, leaveWaitlist, listGuestMemberships, listProductCategories. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue Helper task: Tanmay Dukhande owns the service and reviews.
13 | 1 | SVC-LEDGER-TAX-1 | SVC-LEDGER-TAX | [BE] LedgerService: createTaxCode, getTaxDocumentRendition, getTaxInvoice, issueCreditMemo | 8 | Tanmay Dukhande | LedgerService | MIG-CONTROL MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createTaxCode, getTaxDocumentRendition, getTaxInvoice, issueCreditMemo. Spec: handoff/service-docs/backend/LedgerService.md#group-tax
13 | 1 | SVC-LEDGER-TAX-2 | SVC-LEDGER-TAX | [BE] LedgerService: issueTaxInvoice, listCreditMemos, listTaxInvoices, setEInvoicingProvider | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: issueTaxInvoice, listCreditMemos, listTaxInvoices, setEInvoicingProvider. Spec: handoff/service-docs/backend/LedgerService.md#group-tax
13 | 1 | SVC-ORDER-CASH-1 | SVC-ORDER-CASH | [BE] OrderService: createCashMovement, listCashMovements | 5 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCashMovement, listCashMovements. Spec: handoff/service-docs/backend/OrderService.md#group-cash Helper task: Pranay Shinde owns the service and reviews.
13 | 1 | SVC-ORDER-ORDER-3 | SVC-ORDER-ORDER | [BE] OrderService: getOrderStatement, getVisitReminder, holdOrder, listOrders | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getOrderStatement, getVisitReminder, holdOrder, listOrders. Spec: handoff/service-docs/backend/OrderService.md#group-order
13 | 1 | SVC-ORDER-ORDER-4 | SVC-ORDER-ORDER | [BE] OrderService: modifyOrder, reprintOrder, rescheduleOrder, resumeOrder | 8 | Pranay Shinde | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: modifyOrder, reprintOrder, rescheduleOrder, resumeOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order
13 | 1 | SVC-ORDER-POLICY-1 | SVC-ORDER-POLICY | [BE] OrderService: setRefundPolicy | 2 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRefundPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-policy Helper task: Pranay Shinde owns the service and reviews.
13 | 1 | SVC-ORDER-REFUND-1 | SVC-ORDER-REFUND | [BE] OrderService: createRefund, createRefundRequest, listOrderRefunds | 5 | Deep Khanvilkar | OrderService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createRefund, createRefundRequest, listOrderRefunds. Spec: handoff/service-docs/backend/OrderService.md#group-refund Helper task: Pranay Shinde owns the service and reviews.
13 | 1 | SVC-ORDER-SHIFT-1 | SVC-ORDER-SHIFT | [BE] OrderService: acceptShiftVariance, adjustDepositBoxFloat, allocateDepositBox, approveShiftOpen | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acceptShiftVariance, adjustDepositBoxFloat, allocateDepositBox, approveShiftOpen. Spec: handoff/service-docs/backend/OrderService.md#group-shift
13 | 1 | SVC-ORDER-SHIFT-2 | SVC-ORDER-SHIFT | [BE] OrderService: closeDepositBoxes, closeShift, getCurrentShift, getShift | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeDepositBoxes, closeShift, getCurrentShift, getShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift
13 | 1 | SVC-ORDER-SHIFT-3 | SVC-ORDER-SHIFT | [BE] OrderService: listDenominations, listDepositBoxes, listShifts, openShift | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDenominations, listDepositBoxes, listShifts, openShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift
13 | 1 | SVC-ORDER-SHIFT-4 | SVC-ORDER-SHIFT | [BE] OrderService: recordNoSale, reopenShift, resumeShift, setDenominations | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordNoSale, reopenShift, resumeShift, setDenominations. Spec: handoff/service-docs/backend/OrderService.md#group-shift
13 | 1 | SVC-ORDER-SHIFT-5 | SVC-ORDER-SHIFT | [BE] OrderService: suspendShift, withdrawFromDepositBox | 8 | Pranay Shinde | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: suspendShift, withdrawFromDepositBox. Spec: handoff/service-docs/backend/OrderService.md#group-shift
13 | 1 | SVC-ORDER-SYNC-1 | SVC-ORDER-SYNC | [BE] OrderService: syncOrders | 5 | Deep Khanvilkar | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PLATFORM MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: syncOrders. Spec: handoff/service-docs/backend/OrderService.md#group-sync Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-ACCESS-ACCESS-1 | SVC-ACCESS-ACCESS | [BE] AccessService: approveManualOverrideSupervisor, bindCredentialDevice, deleteAccessPointGroup, enrolFacePass | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveManualOverrideSupervisor, bindCredentialDevice, deleteAccessPointGroup, enrolFacePass. Spec: handoff/service-docs/backend/AccessService.md#group-access
14 | 1 | SVC-ACCESS-ACCESS-2 | SVC-ACCESS-ACCESS | [BE] AccessService: enrolFaceTag, getEntitlement, getEntitlementCredential, getEntitlementHistory | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: enrolFaceTag, getEntitlement, getEntitlementCredential, getEntitlementHistory. Spec: handoff/service-docs/backend/AccessService.md#group-access Helper task: Hrushikant Patkar owns the service and reviews.
14 | 1 | SVC-ACCESS-ACCESS-4 | SVC-ACCESS-ACCESS | [BE] AccessService: revokeFacePass, rollbackAccessPolicy, setAccessAttributeCatalog, setAccessPointGroup | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: revokeFacePass, rollbackAccessPolicy, setAccessAttributeCatalog, setAccessPointGroup. Spec: handoff/service-docs/backend/AccessService.md#group-access
14 | 1 | SVC-ACCESS-ACCESS-5 | SVC-ACCESS-ACCESS | [BE] AccessService: setBiometricVerificationProfile, setBleBeaconGeofence, setContextTimeEvent, setCredentialActivationDisplay | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBiometricVerificationProfile, setBleBeaconGeofence, setContextTimeEvent, setCredentialActivationDisplay. Spec: handoff/service-docs/backend/AccessService.md#group-access
14 | 1 | SVC-ACCESS-ACCESS-6 | SVC-ACCESS-ACCESS | [BE] AccessService: setDeviceBindingPolicy, setFaceMatchingVerification, setFacePassEnrollment, setFaceTagTemporaryEnrollment | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeviceBindingPolicy, setFaceMatchingVerification, setFacePassEnrollment, setFaceTagTemporaryEnrollment. Spec: handoff/service-docs/backend/AccessService.md#group-access
14 | 1 | SVC-ACCESS-ACCESS-7 | SVC-ACCESS-ACCESS | [BE] AccessService: setGateModePolicy, setParkingFacility, setVirtualTicketIdentity, setVisualAccessRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGateModePolicy, setParkingFacility, setVirtualTicketIdentity, setVisualAccessRule. Spec: handoff/service-docs/backend/AccessService.md#group-access
14 | 1 | SVC-ACCESS-ACCESS-8 | SVC-ACCESS-ACCESS | [BE] AccessService: setVisualDynamicPolicy, updateParkingEntitlement | 3 | Sanket Keluskar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setVisualDynamicPolicy, updateParkingEntitlement. Spec: handoff/service-docs/backend/AccessService.md#group-access Helper task: Hrushikant Patkar owns the service and reviews.
14 | 1 | SVC-ACCESS-ACCESSPOINT-1 | SVC-ACCESS-ACCESSPOINT | [BE] AccessService: addBlacklistEntry, createAccessPoint, createAdmissionRules, setAccessPointGeofence | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addBlacklistEntry, createAccessPoint, createAdmissionRules, setAccessPointGeofence. Spec: handoff/service-docs/backend/AccessService.md#group-accesspoint
14 | 1 | SVC-ACCESS-ACCESSPOINT-2 | SVC-ACCESS-ACCESSPOINT | [BE] AccessService: setTurnstileMode, updateAccessPoint, updateAdmissionRules | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTurnstileMode, updateAccessPoint, updateAdmissionRules. Spec: handoff/service-docs/backend/AccessService.md#group-accesspoint
14 | 1 | SVC-CATALOGUE-CATALOGUE-1 | SVC-CATALOGUE-CATALOGUE | [BE] CatalogueService: bulkChangePrices, cloneProduct, commitCatalogueImport, getMyMemberships | 8 | Tanmay Dukhande | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bulkChangePrices, cloneProduct, commitCatalogueImport, getMyMemberships. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue
14 | 1 | SVC-ORDER-CART-1 | SVC-ORDER-CART | [BE] OrderService: abandonCart, addCartLine, applyCartPromoCode, checkoutCart | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: abandonCart, addCartLine, applyCartPromoCode, checkoutCart. Spec: handoff/service-docs/backend/OrderService.md#group-cart
14 | 1 | SVC-ORDER-CART-2 | SVC-ORDER-CART | [BE] OrderService: claimCart, createCart, extendCart, getCart | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PII MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimCart, createCart, extendCart, getCart. Spec: handoff/service-docs/backend/OrderService.md#group-cart
14 | 1 | SVC-ORDER-CART-3 | SVC-ORDER-CART | [BE] OrderService: removeCartLine, updateCartLine | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeCartLine, updateCartLine. Spec: handoff/service-docs/backend/OrderService.md#group-cart
14 | 1 | SVC-ORDER-ORDER-1 | SVC-ORDER-ORDER | [BE] OrderService: appendEntitlementToMedia, applyManualDiscount, claimTicketTransfer, createOrder | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: appendEntitlementToMedia, applyManualDiscount, claimTicketTransfer, createOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order
14 | 1 | SVC-ORDER-ORDER-2 | SVC-ORDER-ORDER | [BE] OrderService: exchangeOrderLines, getMediaEntitlements, getOrder, getOrderCalendarEvent | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: exchangeOrderLines, getMediaEntitlements, getOrder, getOrderCalendarEvent. Spec: handoff/service-docs/backend/OrderService.md#group-order
14 | 1 | SVC-ORDER-ORDER-5 | SVC-ORDER-ORDER | [BE] OrderService: setVisitReminder, transferOrderTickets, voidOrder | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setVisitReminder, transferOrderTickets, voidOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order
15 | 1 | SVC-CATALOGUE-BUNDLE-1 | SVC-CATALOGUE-BUNDLE | [BE] CatalogueService: createBundle, getBundle, getLatestBundle, listCatalogueBundles | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-FNB MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBundle, getBundle, getLatestBundle, listCatalogueBundles. Spec: handoff/service-docs/backend/CatalogueService.md#group-bundle
15 | 1 | SVC-ORDER-ORDERS-1 | SVC-ORDER-ORDERS | [BE] OrderService: createResaleListing, createTicketTemplate, getBillingStatement, getGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createResaleListing, createTicketTemplate, getBillingStatement, getGroupBooking. Spec: handoff/service-docs/backend/OrderService.md#group-orders
15 | 1 | SVC-ORDER-ORDERS-2 | SVC-ORDER-ORDERS | [BE] OrderService: getPaymentLink, issueWalletPass, listBillingStatements, listMyOrders | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getPaymentLink, issueWalletPass, listBillingStatements, listMyOrders. Spec: handoff/service-docs/backend/OrderService.md#group-orders
15 | 1 | SVC-ORDER-ORDERS-3 | SVC-ORDER-ORDERS | [BE] OrderService: listPaymentTokens, payByLink, reissueEntitlement, requestGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPaymentTokens, payByLink, reissueEntitlement, requestGroupBooking. Spec: handoff/service-docs/backend/OrderService.md#group-orders
15 | 1 | SVC-ORDER-ORDERS-4 | SVC-ORDER-ORDERS | [BE] OrderService: setPaymentProvider, shareEntitlement, storePaymentToken, updateTicketTemplate | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentProvider, shareEntitlement, storePaymentToken, updateTicketTemplate. Spec: handoff/service-docs/backend/OrderService.md#group-orders
14 | 1 | SVC-ACCESS-SYNC-1 | SVC-ACCESS-SYNC | [BE] AccessService: getOfflinePackage | 2 | Chinmay Patkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 | Operations: getOfflinePackage. Spec: handoff/service-docs/backend/AccessService.md#group-sync Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-ORDER-PAYMENT-1 | SVC-ORDER-PAYMENT | [BE] OrderService: addTip, capturePayment, createPayment, inquirePaymentStatus | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: addTip, capturePayment, createPayment, inquirePaymentStatus. Spec: handoff/service-docs/backend/OrderService.md#group-payment Acceptance of the declined, unknown and reconcile paths waits on the client's payment sandbox credentials: see the client's answer in the Decisions Register.
15 | 1 | SVC-ORDER-PAYMENTS-1 | SVC-ORDER-PAYMENTS | [BE] OrderService: createInstalmentPlan, createPaymentProviderConnection, listInstalmentPlans, setInstalmentPolicy | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createInstalmentPlan, createPaymentProviderConnection, listInstalmentPlans, setInstalmentPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-payments
9 | 2 | SVC-CATALOGUE-CATEGORY-1 | SVC-CATALOGUE-CATEGORY | [BE] CatalogueService: createSeatCategory | 2 | Chinmay Patkar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatCategory. Spec: handoff/service-docs/backend/CatalogueService.md#group-category Helper task: Tanmay Dukhande owns the service and reviews.
9 | 2 | SVC-CATALOGUE-HOLD-1 | SVC-CATALOGUE-HOLD | [BE] CatalogueService: createSeatHold, extendSeatHold, getSeatHold, relinquishSeatHold | 5 | Deep Khanvilkar | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createSeatHold, extendSeatHold, getSeatHold, relinquishSeatHold. Spec: handoff/service-docs/backend/CatalogueService.md#group-hold Helper task: Tanmay Dukhande owns the service and reviews.
9 | 2 | SVC-CATALOGUE-AVAILABILITY-1 | SVC-CATALOGUE-AVAILABILITY | [BE] CatalogueService: getSeatAvailability | 2 | Chinmay Patkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-HOLD-1 | Operations: getSeatAvailability. Spec: handoff/service-docs/backend/CatalogueService.md#group-availability Helper task: Tanmay Dukhande owns the service and reviews.
9 | 2 | SVC-WALLET-GIFTCARD-1 | SVC-WALLET-GIFTCARD | [BE] WalletService: getGiftCard | 1 | Chinmay Patkar | WalletService | MIG-WALLET PLATFORM-KERNEL | Operations: getGiftCard. Spec: handoff/service-docs/backend/WalletService.md#group-giftcard Helper task: Pranay Shinde owns the service and reviews.
9 | 2 | SVC-WALLET-RETAIL-2 | SVC-WALLET-RETAIL | [BE] WalletService: transferWalletBalance | 3 | Sanket Keluskar | WalletService | MIG-PII MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferWalletBalance. Spec: handoff/service-docs/backend/WalletService.md#group-retail Helper task: Pranay Shinde owns the service and reviews.
9 | 2 | SVC-WALLET-WALLET-2 | SVC-WALLET-WALLET | [BE] WalletService: listWalletTransactions, publishWalletConfiguration, releaseWalletHold, restoreWalletConfigurationVersion | 8 | Pranay Shinde | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listWalletTransactions, publishWalletConfiguration, releaseWalletHold, restoreWalletConfigurationVersion. Spec: handoff/service-docs/backend/WalletService.md#group-wallet
9 | 2 | SVC-WALLET-WALLET-3 | SVC-WALLET-WALLET | [BE] WalletService: setWalletFundingRules, setWalletRefundPolicy | 3 | Sanket Keluskar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletFundingRules, setWalletRefundPolicy. Spec: handoff/service-docs/backend/WalletService.md#group-wallet Helper task: Pranay Shinde owns the service and reviews.
10 | 2 | SVC-CATALOGUE-RECOMMENDATION-1 | SVC-CATALOGUE-RECOMMENDATION | [BE] CatalogueService: recommendSeats | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 | Operations: recommendSeats. Spec: handoff/service-docs/backend/CatalogueService.md#group-recommendation Helper task: Tanmay Dukhande owns the service and reviews.
11 | 2 | SVC-LEDGER-ACCOUNTS-1 | SVC-LEDGER-ACCOUNTS | [BE] LedgerService: createAccount, updateAccount | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAccount, updateAccount. Spec: handoff/service-docs/backend/LedgerService.md#group-accounts Helper task: Tanmay Dukhande owns the service and reviews.
11 | 2 | SVC-LEDGER-REPORTING-1 | SVC-LEDGER-REPORTING | [BE] LedgerService: getFinancialReport | 1 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-KERNEL SVC-LEDGER-ACCOUNTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-SHIFT-2 | Operations: getFinancialReport. Spec: handoff/service-docs/backend/LedgerService.md#group-reporting Helper task: Tanmay Dukhande owns the service and reviews.
13 | 2 | SVC-ORDER-RESERVATION-1 | SVC-ORDER-RESERVATION | [BE] OrderService: cancelReservation, getReservation, listReservations | 5 | Pranay Shinde | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelReservation, getReservation, listReservations. Spec: handoff/service-docs/backend/OrderService.md#group-reservation
15 | 2 | SVC-ORDER-DUNNING-1 | SVC-ORDER-DUNNING | [BE] OrderService: listMyPaymentIssues, retryMyDunningPayment | 3 | Sanket Keluskar | OrderService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listMyPaymentIssues, retryMyDunningPayment. Spec: handoff/service-docs/backend/OrderService.md#group-dunning Helper task: Pranay Shinde owns the service and reviews.
15 | 2 | SVC-WALLET-RETAIL-1 | SVC-WALLET-RETAIL | [BE] WalletService: getWalletAutoReloadSetting, getWalletExitBalance, setWalletAutoReloadSetting, settleWalletAtExit | 8 | Pranay Shinde | WalletService | MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getWalletAutoReloadSetting, getWalletExitBalance, setWalletAutoReloadSetting, settleWalletAtExit. Spec: handoff/service-docs/backend/WalletService.md#group-retail
6 | 1 | SVC-VENUEOPS-CARD-1 | SVC-VENUEOPS-CARD | [BE] VenueOpsService: getGameCard, issueGameCard, transferGameCard | 5 | Deep Khanvilkar | VenueOpsService | MIG-GAMES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGameCard, issueGameCard, transferGameCard. Spec: handoff/service-docs/backend/VenueOpsService.md#group-card Helper task: Hrushikant Patkar owns the service and reviews.
7 | 1 | SVC-VENUEOPS-ASSET-1 | SVC-VENUEOPS-ASSET | [BE] VenueOpsService: deleteMediaAsset, getMediaAsset, replaceMediaAsset, searchMedia | 8 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteMediaAsset, getMediaAsset, replaceMediaAsset, searchMedia. Spec: handoff/service-docs/backend/VenueOpsService.md#group-asset
9 | 1 | SVC-VENUEOPS-INSPECTION-1 | SVC-VENUEOPS-INSPECTION | [BE] VenueOpsService: createInspectionTemplate | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createInspectionTemplate. Spec: handoff/service-docs/backend/VenueOpsService.md#group-inspection Helper task: Hrushikant Patkar owns the service and reviews.
12 | 1 | SVC-INVENTORY-INVENTORY-1 | SVC-INVENTORY-INVENTORY | [BE] InventoryService: bulkUpdateProducts, listSerialisedItems | 3 | Sanket Keluskar | InventoryService | MIG-CATALOGUE MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bulkUpdateProducts, listSerialisedItems. Spec: handoff/service-docs/backend/InventoryService.md#group-inventory Helper task: Hrushikant Patkar owns the service and reviews.
10 | 1 | SVC-CATALOGUE-PRODUCT-1 | SVC-CATALOGUE-PRODUCT | [BE] CatalogueService: checkBookingEligibility, getGroupPackageDefinition, getProduct, getProductEligibilityRule | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-INVENTORY-INVENTORY-1 | Operations: checkBookingEligibility, getGroupPackageDefinition, getProduct, getProductEligibilityRule. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Tanmay Dukhande owns the service and reviews.
10 | 1 | SVC-CATALOGUE-PRODUCT-2 | SVC-CATALOGUE-PRODUCT | [BE] CatalogueService: listAlternativeCodes, listGroupPackages, listProductVariants, listProducts | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-INVENTORY-INVENTORY-1 SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-4 | Operations: listAlternativeCodes, listGroupPackages, listProductVariants, listProducts. Spec: handoff/service-docs/backend/CatalogueService.md#group-product
14 | 1 | SVC-ACCESS-ACCESS-3 | SVC-ACCESS-ACCESS | [BE] AccessService: getFacePassEnrolment, listEntitlements, listMyEntitlements, listParkingFacilities | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-PRODUCT-4 SVC-IDENTITY-IDENTITY-2 SVC-INVENTORY-INVENTORY-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-PLATFORM-PUBLICAPI-2 | Operations: getFacePassEnrolment, listEntitlements, listMyEntitlements, listParkingFacilities. Spec: handoff/service-docs/backend/AccessService.md#group-access
12 | 1 | SVC-INVENTORY-ITEM-1 | SVC-INVENTORY-ITEM | [BE] InventoryService: createInventoryItem, setInventoryKitDefinition, updateInventoryItem | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createInventoryItem, setInventoryKitDefinition, updateInventoryItem. Spec: handoff/service-docs/backend/InventoryService.md#group-item Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-BILL-1 | SVC-FNB-BILL | [BE] FnbService: closeTableVisit | 3 | Sanket Keluskar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeTableVisit. Spec: handoff/service-docs/backend/FnbService.md#group-bill Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-FNB-1 | SVC-FNB-FNB | [BE] FnbService: attachModifierGroup, buildProductionPlan, chaseStation, createTableReservation | 8 | Hrushikant Patkar | FnbService | MIG-AI MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: attachModifierGroup, buildProductionPlan, chaseStation, createTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb
15 | 1 | SVC-FNB-FNB-3 | SVC-FNB-FNB | [BE] FnbService: joinRestaurantWaitlist, leaveRestaurantWaitlist, list86Events, listTableReservations | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: joinRestaurantWaitlist, leaveRestaurantWaitlist, list86Events, listTableReservations. Spec: handoff/service-docs/backend/FnbService.md#group-fnb
15 | 1 | SVC-FNB-FNB-4 | SVC-FNB-FNB | [BE] FnbService: logColdChain, logKitchenException, logTemperature, markOrderCollected | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: logColdChain, logKitchenException, logTemperature, markOrderCollected. Spec: handoff/service-docs/backend/FnbService.md#group-fnb
15 | 1 | SVC-FNB-FNB-5 | SVC-FNB-FNB | [BE] FnbService: moveTableVisit, notifyServer, printOrderLabel, rebalanceStationLoad | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-IDENTITY MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: moveTableVisit, notifyServer, printOrderLabel, rebalanceStationLoad. Spec: handoff/service-docs/backend/FnbService.md#group-fnb
15 | 1 | SVC-FNB-FNB-6 | SVC-FNB-FNB | [BE] FnbService: recallKitchenTicket, refireItem, releaseProductionPlan, seatTableReservation | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recallKitchenTicket, refireItem, releaseProductionPlan, seatTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb
15 | 1 | SVC-FNB-FNB-7 | SVC-FNB-FNB | [BE] FnbService: setCourseRules, setKitchenSla, setTableCombinations, signCorrectiveAction | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCourseRules, setKitchenSla, setTableCombinations, signCorrectiveAction. Spec: handoff/service-docs/backend/FnbService.md#group-fnb Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-GUESTORDERING-1 | SVC-FNB-GUESTORDERING | [BE] FnbService: claimLocationSession, claimTableSession, createDeliveryLocation, createGuestFnbOrder | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimLocationSession, claimTableSession, createDeliveryLocation, createGuestFnbOrder. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering
15 | 1 | SVC-FNB-GUESTORDERING-3 | SVC-FNB-GUESTORDERING | [BE] FnbService: listDeliveryLocations, listDiningOutlets, listFulfilmentSlots, recordOrderHandover | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDeliveryLocations, listDiningOutlets, listFulfilmentSlots, recordOrderHandover. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-GUESTORDERING-4 | SVC-FNB-GUESTORDERING | [BE] FnbService: setDeliveryLocationOutletMapping, setFnbDeliveryPolicy, updateDeliveryLocation | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeliveryLocationOutletMapping, setFnbDeliveryPolicy, updateDeliveryLocation. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-KITCHEN-1 | SVC-FNB-KITCHEN | [BE] FnbService: listKitchenStations, listKitchenTickets, prioritiseKitchenTicket, setKitchenStations | 8 | Hrushikant Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listKitchenStations, listKitchenTickets, prioritiseKitchenTicket, setKitchenStations. Spec: handoff/service-docs/backend/FnbService.md#group-kitchen
15 | 1 | SVC-FNB-KITCHEN-2 | SVC-FNB-KITCHEN | [BE] FnbService: setKitchenTicketStatus | 3 | Sanket Keluskar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setKitchenTicketStatus. Spec: handoff/service-docs/backend/FnbService.md#group-kitchen Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-MENU-1 | SVC-FNB-MENU | [BE] FnbService: createMenu, getMenu, listMenus, setItemAvailability | 8 | Hrushikant Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMenu, getMenu, listMenus, setItemAvailability. Spec: handoff/service-docs/backend/FnbService.md#group-menu
15 | 1 | SVC-FNB-MODIFIER-1 | SVC-FNB-MODIFIER | [BE] FnbService: createModifierGroup, listModifierGroups | 3 | Sanket Keluskar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createModifierGroup, listModifierGroups. Spec: handoff/service-docs/backend/FnbService.md#group-modifier Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-ORDER-1 | SVC-FNB-ORDER | [BE] FnbService: createFnbOrder, getFnbOrder, listFnbOrders | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createFnbOrder, getFnbOrder, listFnbOrders. Spec: handoff/service-docs/backend/FnbService.md#group-order
15 | 1 | SVC-FNB-PRODUCTION-1 | SVC-FNB-PRODUCTION | [BE] FnbService: setRecipe | 2 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRecipe. Spec: handoff/service-docs/backend/FnbService.md#group-production Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-FNB-TABLE-1 | SVC-FNB-TABLE | [BE] FnbService: clearTable, getTableMap, mergeTableVisits, openTableVisit | 8 | Hrushikant Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: clearTable, getTableMap, mergeTableVisits, openTableVisit. Spec: handoff/service-docs/backend/FnbService.md#group-table
15 | 1 | SVC-FNB-TABLE-2 | SVC-FNB-TABLE | [BE] FnbService: setTableLayout | 2 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTableLayout. Spec: handoff/service-docs/backend/FnbService.md#group-table Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-VENUEOPS-ENTRY-1 | SVC-VENUEOPS-ENTRY | [BE] VenueOpsService: getWaitingGuest, joinQueue, leaveQueue, listQueueEntries | 5 | Deep Khanvilkar | VenueOpsService | MIG-MARKETING MIG-PROMOTIONS MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingGuest, joinQueue, leaveQueue, listQueueEntries. Spec: handoff/service-docs/backend/VenueOpsService.md#group-entry Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-VENUEOPS-FEED-1 | SVC-VENUEOPS-FEED | [BE] VenueOpsService: configureQueueFeed, getQueueFeedHealth | 3 | Sanket Keluskar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureQueueFeed, getQueueFeedHealth. Spec: handoff/service-docs/backend/VenueOpsService.md#group-feed Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-VENUEOPS-QUEUE-1 | SVC-VENUEOPS-QUEUE | [BE] VenueOpsService: createQueue, getQueue, listQueues, updateQueue | 8 | Hrushikant Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createQueue, getQueue, listQueues, updateQueue. Spec: handoff/service-docs/backend/VenueOpsService.md#group-queue
15 | 1 | SVC-VENUEOPS-VENUEMAP-1 | SVC-VENUEOPS-VENUEMAP | [BE] VenueOpsService: createVenueMap, getVenueMap, getVenueMapGraph, importVenueGeometry | 8 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-PLATFORM MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVenueMap, getVenueMap, getVenueMapGraph, importVenueGeometry. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap
15 | 1 | SVC-VENUEOPS-VENUEMAP-2 | SVC-VENUEOPS-VENUEMAP | [BE] VenueOpsService: listBookableVenueMaps, publishVenueMap, setPlacedResource, setVenuePoint | 8 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-ASSETS MIG-CATALOGUE MIG-PLATFORM MIG-PROMOTIONS MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBookableVenueMaps, publishVenueMap, setPlacedResource, setVenuePoint. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap
15 | 1 | SVC-VENUEOPS-VISITPLAN-1 | SVC-VENUEOPS-VISITPLAN | [BE] VenueOpsService: bookVisitPlan, generateVisitPlan, getVisitPlan, listVisitPlanAlternatives | 8 | Hrushikant Patkar | VenueOpsService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bookVisitPlan, generateVisitPlan, getVisitPlan, listVisitPlanAlternatives. Spec: handoff/service-docs/backend/VenueOpsService.md#group-visitplan
10 | 1 | SVC-CATALOGUE-CAPACITY-1 | SVC-CATALOGUE-CAPACITY | [BE] CatalogueService: getAvailability | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 | Operations: getAvailability. Spec: handoff/service-docs/backend/CatalogueService.md#group-capacity Helper task: Tanmay Dukhande owns the service and reviews.
15 | 1 | SVC-VENUEOPS-VISITPLAN-2 | SVC-VENUEOPS-VISITPLAN | [BE] VenueOpsService: updateVisitPlan | 3 | Sanket Keluskar | VenueOpsService | MIG-CATALOGUE MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateVisitPlan. Spec: handoff/service-docs/backend/VenueOpsService.md#group-visitplan Helper task: Hrushikant Patkar owns the service and reviews.
15 | 1 | SVC-VENUEOPS-WAITTIME-1 | SVC-VENUEOPS-WAITTIME | [BE] VenueOpsService: getWaitTimes | 1 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-KERNEL SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-QUEUE-1 | Operations: getWaitTimes. Spec: handoff/service-docs/backend/VenueOpsService.md#group-waittime Helper task: Hrushikant Patkar owns the service and reviews.
16 | 1 | SVC-RETAIL-FLOOR-1 | SVC-RETAIL-FLOOR | [BE] RetailService: lookupMerchandise, lookupShopAndDrop, reserveMerchandise | 3 | Sanket Keluskar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: lookupMerchandise, lookupShopAndDrop, reserveMerchandise. Spec: handoff/service-docs/backend/RetailService.md#group-floor Helper task: Pranay Shinde owns the service and reviews.
16 | 1 | SVC-RETAIL-MERCHANDISE-1 | SVC-RETAIL-MERCHANDISE | [BE] RetailService: createMerchandise, listMerchandise, updateMerchandise | 5 | Deep Khanvilkar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMerchandise, listMerchandise, updateMerchandise. Spec: handoff/service-docs/backend/RetailService.md#group-merchandise Helper task: Pranay Shinde owns the service and reviews.
16 | 1 | SVC-RETAIL-RETURN-1 | SVC-RETAIL-RETURN | [BE] RetailService: createRetailReturn, getReturnPolicy, lookupRetailSale, setReturnPolicy | 8 | Pranay Shinde | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailReturn, getReturnPolicy, lookupRetailSale, setReturnPolicy. Spec: handoff/service-docs/backend/RetailService.md#group-return
16 | 1 | SVC-RETAIL-SALE-1 | SVC-RETAIL-SALE | [BE] RetailService: createRetailSale, getRetailSale, listRetailSales, reprintReceipt | 8 | Pranay Shinde | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailSale, getRetailSale, listRetailSales, reprintReceipt. Spec: handoff/service-docs/backend/RetailService.md#group-sale
7 | 2 | SVC-VENUEOPS-ASSET-2 | SVC-VENUEOPS-ASSET | [BE] VenueOpsService: updateMediaAsset | 2 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateMediaAsset. Spec: handoff/service-docs/backend/VenueOpsService.md#group-asset Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-VENUEOPS-COLLECTION-1 | SVC-VENUEOPS-COLLECTION | [BE] VenueOpsService: createCollection, listCollections | 2 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCollection, listCollections. Spec: handoff/service-docs/backend/VenueOpsService.md#group-collection Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-VENUEOPS-RESOURCES-1 | SVC-VENUEOPS-RESOURCES | [BE] VenueOpsService: createResource, createResourceBlock, createResourceHold, createResourcePackage | 8 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResource, createResourceBlock, createResourceHold, createResourcePackage. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources
7 | 2 | SVC-VENUEOPS-RESOURCES-3 | SVC-VENUEOPS-RESOURCES | [BE] VenueOpsService: listProductStartTimes, releaseResourceBlock, relinquishResourceHold, setExperienceResourceRequirements | 3 | Sanket Keluskar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductStartTimes, releaseResourceBlock, relinquishResourceHold, setExperienceResourceRequirements. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-VENUEOPS-RESOURCES-4 | SVC-VENUEOPS-RESOURCES | [BE] VenueOpsService: setResourceSchedule, updateResource, updateResourcePackage | 8 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResourceSchedule, updateResource, updateResourcePackage. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources
15 | 1 | SVC-VENUEOPS-RESOURCES-2 | SVC-VENUEOPS-RESOURCES | [BE] VenueOpsService: extendResourceHold, getMapResourceAvailability, getResourceAvailability, getResourceHold | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-VENUEMAP PLATFORM-KERNEL SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 | Operations: extendResourceHold, getMapResourceAvailability, getResourceAvailability, getResourceHold. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-VENUEOPS-UPLOAD-1 | SVC-VENUEOPS-UPLOAD | [BE] VenueOpsService: completeUpload, createUpload | 5 | Deep Khanvilkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: completeUpload, createUpload. Spec: handoff/service-docs/backend/VenueOpsService.md#group-upload Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-VENUEOPS-RIGHTS-1 | SVC-VENUEOPS-RIGHTS | [BE] VenueOpsService: getExpiringRights | 1 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-KERNEL SVC-VENUEOPS-ASSET-1 SVC-VENUEOPS-ASSET-2 SVC-VENUEOPS-UPLOAD-1 | Operations: getExpiringRights. Spec: handoff/service-docs/backend/VenueOpsService.md#group-rights Helper task: Hrushikant Patkar owns the service and reviews.
12 | 2 | SVC-INVENTORY-RECEIPT-1 | SVC-INVENTORY-RECEIPT | [BE] InventoryService: createGoodsReceipt, rejectReceivedGoods | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createGoodsReceipt, rejectReceivedGoods. Spec: handoff/service-docs/backend/InventoryService.md#group-receipt Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | SVC-FNB-FNB-2 | SVC-FNB-FNB | [BE] FnbService: escalateCorrectiveAction, fireCourse, getHaccpStatus, holdCourse | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: escalateCorrectiveAction, fireCourse, getHaccpStatus, holdCourse. Spec: handoff/service-docs/backend/FnbService.md#group-fnb
15 | 1 | SVC-FNB-GUESTORDERING-2 | SVC-FNB-GUESTORDERING | [BE] FnbService: getFnbDeliveryPolicy, getGuestBill, getGuestMenu, getGuestOrderStatus | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-ORDERS PLATFORM-KERNEL SVC-FNB-BILL-1 SVC-FNB-FNB-2 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-TABLE-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 | Operations: getFnbDeliveryPolicy, getGuestBill, getGuestMenu, getGuestOrderStatus. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | SVC-FNB-FNB-8 | SVC-FNB-FNB | [BE] FnbService: updateTableReservation | 3 | Sanket Keluskar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | SVC-FNB-MENU-2 | SVC-FNB-MENU | [BE] FnbService: setMenuSections, updateMenu | 5 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMenuSections, updateMenu. Spec: handoff/service-docs/backend/FnbService.md#group-menu Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-FARE-1 | SVC-VENUEOPS-FARE | [BE] VenueOpsService: getTransportFareTable, quoteTransportFare, setTransportFareTable | 8 | Hrushikant Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getTransportFareTable, quoteTransportFare, setTransportFareTable. Spec: handoff/service-docs/backend/VenueOpsService.md#group-fare
5 | 3 | SVC-VENUEOPS-FAVOURITE-1 | SVC-VENUEOPS-FAVOURITE | [BE] VenueOpsService: deleteFavouriteRoute, listMyFavouriteRoutes, saveFavouriteRoute | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteFavouriteRoute, listMyFavouriteRoutes, saveFavouriteRoute. Spec: handoff/service-docs/backend/VenueOpsService.md#group-favourite Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-NETWORKIMPORT-1 | SVC-VENUEOPS-NETWORKIMPORT | [BE] VenueOpsService: applyTransportNetworkImport, importTransportNetwork | 5 | Deep Khanvilkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyTransportNetworkImport, importTransportNetwork. Spec: handoff/service-docs/backend/VenueOpsService.md#group-networkimport Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-PASS-1 | SVC-VENUEOPS-PASS | [BE] VenueOpsService: createTransportPassType, listTransportPassOffers | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportPassType, listTransportPassOffers. Spec: handoff/service-docs/backend/VenueOpsService.md#group-pass Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-ROUTE-1 | SVC-VENUEOPS-ROUTE | [BE] VenueOpsService: createTransportRoute, getTransportRoute, getTransportRouteMap, listTransportRoutes | 8 | Hrushikant Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportRoute, getTransportRoute, getTransportRouteMap, listTransportRoutes. Spec: handoff/service-docs/backend/VenueOpsService.md#group-route
5 | 3 | SVC-VENUEOPS-ROUTE-2 | SVC-VENUEOPS-ROUTE | [BE] VenueOpsService: updateTransportRoute | 2 | Chinmay Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateTransportRoute. Spec: handoff/service-docs/backend/VenueOpsService.md#group-route Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-STATION-1 | SVC-VENUEOPS-STATION | [BE] VenueOpsService: createTransportStation, listTransportStations | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportStation, listTransportStations. Spec: handoff/service-docs/backend/VenueOpsService.md#group-station Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-TIMETABLE-1 | SVC-VENUEOPS-TIMETABLE | [BE] VenueOpsService: createTransportTimetable, publishTransportTimetable | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportTimetable, publishTransportTimetable. Spec: handoff/service-docs/backend/VenueOpsService.md#group-timetable Helper task: Hrushikant Patkar owns the service and reviews.
5 | 3 | SVC-VENUEOPS-DEPARTURE-1 | SVC-VENUEOPS-DEPARTURE | [BE] VenueOpsService: getNextTransportDeparture, searchTransportDepartures | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-FARE-1 SVC-VENUEOPS-NETWORKIMPORT-1 SVC-VENUEOPS-ROUTE-1 SVC-VENUEOPS-ROUTE-2 SVC-VENUEOPS-STATION-1 SVC-VENUEOPS-TIMETABLE-1 | Operations: getNextTransportDeparture, searchTransportDepartures. Spec: handoff/service-docs/backend/VenueOpsService.md#group-departure Helper task: Hrushikant Patkar owns the service and reviews.
8 | 1 | SVC-AI-AI-2 | SVC-AI-AI | [BE] AiService: setSuggestionProvider | 1 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSuggestionProvider. Spec: handoff/service-docs/backend/AiService.md#group-ai Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-ASSIST-1 | SVC-AI-ASSIST | [BE] AiService: createAiConversation, listAiConversations, sendAiMessage | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAiConversation, listAiConversations, sendAiMessage. Spec: handoff/service-docs/backend/AiService.md#group-assist Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-CONFIG-1 | SVC-AI-CONFIG | [BE] AiService: getAiPolicy, setAiByokEnablement, setAiPolicy, setAiProvider | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAiPolicy, setAiByokEnablement, setAiPolicy, setAiProvider. Spec: handoff/service-docs/backend/AiService.md#group-config
8 | 1 | SVC-AI-FORECAST-1 | SVC-AI-FORECAST | [BE] AiService: createForecastScenario, decideOperationalRequirement, getAiVenueSettings, getVenueHistoryImport | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createForecastScenario, decideOperationalRequirement, getAiVenueSettings, getVenueHistoryImport. Spec: handoff/service-docs/backend/AiService.md#group-forecast Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-FORECAST-2 | SVC-AI-FORECAST | [BE] AiService: importVenueHistory, listVenueHistoryImports, publishForecastVersion, runForecast | 8 | Pranay Shinde | AiService | MIG-AI MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: importVenueHistory, listVenueHistoryImports, publishForecastVersion, runForecast. Spec: handoff/service-docs/backend/AiService.md#group-forecast
8 | 1 | SVC-AI-FORECAST-3 | SVC-AI-FORECAST | [BE] AiService: setAiVenueSettings | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiVenueSettings. Spec: handoff/service-docs/backend/AiService.md#group-forecast Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-GOVERNANCE-1 | SVC-AI-GOVERNANCE | [BE] AiService: configureAiCapability, createAiGovernancePolicyDraft, createAiPolicyException, decideProposedAction | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAiCapability, createAiGovernancePolicyDraft, createAiPolicyException, decideProposedAction. Spec: handoff/service-docs/backend/AiService.md#group-governance
8 | 1 | SVC-AI-GOVERNANCE-2 | SVC-AI-GOVERNANCE | [BE] AiService: evaluateAiGovernance, getAiUsage, publishAiGovernancePolicy, resumeAiCapability | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: evaluateAiGovernance, getAiUsage, publishAiGovernancePolicy, resumeAiCapability. Spec: handoff/service-docs/backend/AiService.md#group-governance
8 | 1 | SVC-AI-INSIGHTS-1 | SVC-AI-INSIGHTS | [BE] AiService: decideAiInsight, explainMetricChange | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideAiInsight, explainMetricChange. Spec: handoff/service-docs/backend/AiService.md#group-insights Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-KNOWLEDGE-1 | SVC-AI-KNOWLEDGE | [BE] AiService: configureAssistantProfile, recordAnswerFeedback | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAssistantProfile, recordAnswerFeedback. Spec: handoff/service-docs/backend/AiService.md#group-knowledge Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-MODELS-1 | SVC-AI-MODELS | [BE] AiService: promoteAiRelease, publishPromptTemplate, rollbackAiRelease, runAiEvaluation | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: promoteAiRelease, publishPromptTemplate, rollbackAiRelease, runAiEvaluation. Spec: handoff/service-docs/backend/AiService.md#group-models
8 | 1 | SVC-AI-MODELS-2 | SVC-AI-MODELS | [BE] AiService: setAiModel | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiModel. Spec: handoff/service-docs/backend/AiService.md#group-models Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-MONITORING-1 | SVC-AI-MONITORING | [BE] AiService: containAiIncident | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: containAiIncident. Spec: handoff/service-docs/backend/AiService.md#group-monitoring Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-RECOMMEND-1 | SVC-AI-RECOMMEND | [BE] AiService: decideRecommendations, recordRecommendationEvents | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideRecommendations, recordRecommendationEvents. Spec: handoff/service-docs/backend/AiService.md#group-recommend Helper task: Pranay Shinde owns the service and reviews.
8 | 1 | SVC-AI-RETRIEVAL-2 | SVC-AI-RETRIEVAL | [BE] AiService: setIndexSource | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setIndexSource. Spec: handoff/service-docs/backend/AiService.md#group-retrieval Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-CASE-1 | SVC-MARKETING-CASE | [BE] MarketingService: createCase, listCases | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCase, listCases. Spec: handoff/service-docs/backend/MarketingService.md#group-case Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-CONSENT-1 | SVC-MARKETING-CONSENT | [BE] MarketingService: claimDeviceConsent, createConsentQuestion, getCookieConsentRuntime, getDeviceConsentHistory | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: claimDeviceConsent, createConsentQuestion, getCookieConsentRuntime, getDeviceConsentHistory. Spec: handoff/service-docs/backend/MarketingService.md#group-consent
14 | 1 | SVC-MARKETING-CONSENT-3 | SVC-MARKETING-CONSENT | [BE] MarketingService: listPublishedTrackingTechnologies, recordConsent, recordConsentAnswers, recordDeviceConsent | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPublishedTrackingTechnologies, recordConsent, recordConsentAnswers, recordDeviceConsent. Spec: handoff/service-docs/backend/MarketingService.md#group-consent
14 | 1 | SVC-MARKETING-CONSENT-4 | SVC-MARKETING-CONSENT | [BE] MarketingService: setConsentPurposes, setCookieBannerDesign, setTrackingTechnology, updateConsentQuestion | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setConsentPurposes, setCookieBannerDesign, setTrackingTechnology, updateConsentQuestion. Spec: handoff/service-docs/backend/MarketingService.md#group-consent
14 | 1 | SVC-MARKETING-GUEST-1 | SVC-MARKETING-GUEST | [BE] MarketingService: addToWishlist, getGuestProfile, getWishlist, listGuestDevices | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addToWishlist, getGuestProfile, getWishlist, listGuestDevices. Spec: handoff/service-docs/backend/MarketingService.md#group-guest Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-GUEST-2 | SVC-MARKETING-GUEST | [BE] MarketingService: registerGuestDevice, removeFromWishlist, revokeGuestDevice, searchGuests | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: registerGuestDevice, removeFromWishlist, revokeGuestDevice, searchGuests. Spec: handoff/service-docs/backend/MarketingService.md#group-guest Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-LOYALTY-1 | SVC-MARKETING-LOYALTY | [BE] MarketingService: createLoyaltyProgramme, listLoyaltyProgrammes, setLoyaltyRules | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createLoyaltyProgramme, listLoyaltyProgrammes, setLoyaltyRules. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty
14 | 1 | SVC-MARKETING-MARKETING-1 | SVC-MARKETING-MARKETING | [BE] MarketingService: createChallenge, createForm, createInvitationCampaign, createReferral | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createChallenge, createForm, createInvitationCampaign, createReferral. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing
14 | 1 | SVC-MARKETING-MARKETING-3 | SVC-MARKETING-MARKETING | [BE] MarketingService: handoverToAgent, identifyGuest, listMyCases, raiseMyCase | 8 | Pranay Shinde | MarketingService | MIG-ACCESS MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: handoverToAgent, identifyGuest, listMyCases, raiseMyCase. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing
14 | 1 | SVC-MARKETING-MARKETING-4 | SVC-MARKETING-MARKETING | [BE] MarketingService: redeemLoyaltyPoints, replyToMyCase, respondToInvitation, sendConversationMessage | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: redeemLoyaltyPoints, replyToMyCase, respondToInvitation, sendConversationMessage. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing
14 | 1 | SVC-MARKETING-MARKETING-5 | SVC-MARKETING-MARKETING | [BE] MarketingService: setAgentAvailability, setMarketingSubscription, setSeoMetadata, updateGuestPreferences | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-CONTROL MIG-IDENTITY MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAgentAvailability, setMarketingSubscription, setSeoMetadata, updateGuestPreferences. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing
14 | 1 | SVC-MARKETING-MARKETING-2 | SVC-MARKETING-MARKETING | [BE] MarketingService: getLoyaltyPosition, getMarketingSubscription, getMyChallenges, getWaiverStatus | 3 | Sanket Keluskar | MarketingService | MIG-ACCESS MIG-CATALOGUE MIG-MARKETING PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PRODUCT-4 SVC-INVENTORY-INVENTORY-1 SVC-MARKETING-LOYALTY-1 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-5 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 | Operations: getLoyaltyPosition, getMarketingSubscription, getMyChallenges, getWaiverStatus. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-MARKETING-6 | SVC-MARKETING-MARKETING | [BE] MarketingService: updateMyProfile, uploadGuestDocument | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateMyProfile, uploadGuestDocument. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-CONSENT-2 | SVC-MARKETING-CONSENT | [BE] MarketingService: getGuestConsents, listConsentAnswers, listConsentPurposes, listConsentQuestions | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-3 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-4 SVC-MARKETING-MARKETING-6 SVC-ORDER-CART-1 SVC-ORDER-ORDERS-4 | Operations: getGuestConsents, listConsentAnswers, listConsentPurposes, listConsentQuestions. Spec: handoff/service-docs/backend/MarketingService.md#group-consent Helper task: Pranay Shinde owns the service and reviews.
14 | 1 | SVC-MARKETING-SEGMENT-1 | SVC-MARKETING-SEGMENT | [BE] MarketingService: createSegment | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSegment. Spec: handoff/service-docs/backend/MarketingService.md#group-segment Helper task: Pranay Shinde owns the service and reviews.
15 | 1 | SVC-AI-AI-1 | SVC-AI-AI | [BE] AiService: proposeTranslations, proposeVenueLabels, requestSuggestion, setAiCredential | 8 | Pranay Shinde | AiService | MIG-AI MIG-CONTROL MIG-FNB MIG-INVENTORY MIG-MARKETING MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeTranslations, proposeVenueLabels, requestSuggestion, setAiCredential. Spec: handoff/service-docs/backend/AiService.md#group-ai
16 | 1 | SVC-AI-RETRIEVAL-1 | SVC-AI-RETRIEVAL | [BE] AiService: createKnowledgeCollection, ingestKnowledgeDocument, reindexSource, semanticSearch | 8 | Pranay Shinde | AiService | MIG-AI MIG-ASSETS MIG-CATALOGUE MIG-FNB MIG-MAINTENANCE MIG-MARKETING MIG-REPORTING MIG-RETAIL MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createKnowledgeCollection, ingestKnowledgeDocument, reindexSource, semanticSearch. Spec: handoff/service-docs/backend/AiService.md#group-retrieval
8 | 2 | SVC-AI-CONFIGURE-1 | SVC-AI-CONFIGURE | [BE] AiService: getGuidedChoiceSuggestion, suggestGuidedChoice | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGuidedChoiceSuggestion, suggestGuidedChoice. Spec: handoff/service-docs/backend/AiService.md#group-configure Helper task: Pranay Shinde owns the service and reviews.
8 | 2 | SVC-AI-GOVERNANCE-3 | SVC-AI-GOVERNANCE | [BE] AiService: simulateAiGovernancePolicy | 1 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateAiGovernancePolicy. Spec: handoff/service-docs/backend/AiService.md#group-governance Helper task: Pranay Shinde owns the service and reviews.
14 | 2 | SVC-AI-GENERATE-1 | SVC-AI-GENERATE | [BE] AiService: proposeMarketingContent | 3 | Sanket Keluskar | AiService | MIG-AI MIG-CATALOGUE MIG-CONTROL MIG-MARKETING MIG-PROMOTIONS MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeMarketingContent. Spec: handoff/service-docs/backend/AiService.md#group-generate Helper task: Pranay Shinde owns the service and reviews.
14 | 2 | SVC-MARKETING-CAMPAIGN-1 | SVC-MARKETING-CAMPAIGN | [BE] MarketingService: createCampaign, launchCampaign, stopCampaign, updateCampaign | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCampaign, launchCampaign, stopCampaign, updateCampaign. Spec: handoff/service-docs/backend/MarketingService.md#group-campaign
14 | 2 | SVC-MARKETING-MESSAGE-1 | SVC-MARKETING-MESSAGE | [BE] MarketingService: createMessageTemplate, listMyNotifications, markMyNotificationsRead | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMessageTemplate, listMyNotifications, markMyNotificationsRead. Spec: handoff/service-docs/backend/MarketingService.md#group-message
14 | 3 | SVC-MARKETING-FEEDBACK-1 | SVC-MARKETING-FEEDBACK | [BE] MarketingService: submitReview | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: submitReview. Spec: handoff/service-docs/backend/MarketingService.md#group-feedback Helper task: Pranay Shinde owns the service and reviews.
7 | 1 | SVC-REPORTING-EXECUTION-1 | SVC-REPORTING-EXECUTION | [BE] ReportingService: runReport | 1 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MENU-1 SVC-FNB-MENU-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-2 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-3 | Operations: runReport. Spec: handoff/service-docs/backend/ReportingService.md#group-execution Helper task: Hrushikant Patkar owns the service and reviews.
7 | 1 | SVC-REPORTING-REPORTING-1 | SVC-REPORTING-REPORTING | [BE] ReportingService: createKpi, deleteDashboard, listAlerts, setAlertRule | 5 | Deep Khanvilkar | ReportingService | MIG-IDENTITY MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MENU-1 SVC-FNB-MENU-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-2 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-3 | Operations: createKpi, deleteDashboard, listAlerts, setAlertRule. Spec: handoff/service-docs/backend/ReportingService.md#group-reporting Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-REPORTING-CATALOGUE-1 | SVC-REPORTING-CATALOGUE | [BE] ReportingService: createReport, deleteReport, getReport, listReports | 8 | Hrushikant Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createReport, deleteReport, getReport, listReports. Spec: handoff/service-docs/backend/ReportingService.md#group-catalogue
7 | 2 | SVC-REPORTING-CATALOGUE-2 | SVC-REPORTING-CATALOGUE | [BE] ReportingService: updateReport | 3 | Sanket Keluskar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateReport. Spec: handoff/service-docs/backend/ReportingService.md#group-catalogue Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | SVC-REPORTING-DASHBOARD-1 | SVC-REPORTING-DASHBOARD | [BE] ReportingService: createDashboard, getDashboard, recordDashboardView, updateDashboard | 8 | Hrushikant Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MENU-1 SVC-FNB-MENU-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-2 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-3 | Operations: createDashboard, getDashboard, recordDashboardView, updateDashboard. Spec: handoff/service-docs/backend/ReportingService.md#group-dashboard
7 | 2 | SVC-REPORTING-REPORTING-2 | SVC-REPORTING-REPORTING | [BE] ReportingService: setSemanticModel | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSemanticModel. Spec: handoff/service-docs/backend/ReportingService.md#group-reporting Helper task: Hrushikant Patkar owns the service and reviews.
8 | 2 | SVC-REPORTING-NATURALLANGUAGE-1 | SVC-REPORTING-NATURALLANGUAGE | [BE] ReportingService: askReportingQuestion, saveNaturalLanguageQuery | 8 | Hrushikant Patkar | ReportingService | MIG-AI MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MENU-1 SVC-FNB-MENU-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-2 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-3 | Operations: askReportingQuestion, saveNaturalLanguageQuery. Spec: handoff/service-docs/backend/ReportingService.md#group-naturallanguage
4 | 2 | VM-MIG-ACCREDITATION | VM-DB | [DB] Migration: accreditation for Venue Management (4 tables) | 3 | Tanmay Dukhande |  | MIG-BASELINE | Tables: accreditation.application, accreditation.credential, accreditation.holder, accreditation.validity. Source DDL: backend/tenant/010-accreditation.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
5 | 2 | VM-MIG-CONTROL | VM-DB | [DB] Migration: control for Venue Management (4 tables) | 2 | Hrushikant Patkar |  | MIG-CONTROL | Tables: control.channel_listing, control.rollout, control.webhook_delivery, control.webhook_subscription. Source DDL: backend/control/010-control.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
5 | 2 | VM-MIG-TENANCY | VM-DB | [DB] Migration: tenancy for Venue Management (4 tables) | 2 | Tanmay Dukhande |  | MIG-TENANCY | Tables: tenancy.device_audit, tenancy.device_credential, tenancy.device_firmware, tenancy.device_rollout. Source DDL: backend/tenant/010-tenancy.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
6 | 2 | VM-MIG-GAMES | VM-DB | [DB] Migration: games for Venue Management (3 tables) | 2 | Hrushikant Patkar |  | MIG-GAMES | Tables: games.game, games.play, games.reader_sync_status. Source DDL: backend/tenant/010-games.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
6 | 2 | VM-MIG-IDENTITY | VM-DB | [DB] Migration: identity for Venue Management (1 tables) | 1 | Tanmay Dukhande |  | MIG-IDENTITY | Tables: identity.role_permission. Source DDL: backend/tenant/010-identity.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
7 | 2 | VM-MIG-APPROVALS | VM-DB | [DB] Migration: approvals for Venue Management (1 tables) | 1 | Tanmay Dukhande |  | MIG-APPROVALS | Tables: approvals.escalation. Source DDL: backend/tenant/010-approvals.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
7 | 2 | VM-MIG-REPORTING | VM-DB | [DB] Migration: reporting for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-REPORTING | Tables: reporting.kpi_target, reporting.schedule_recipient. Source DDL: backend/tenant/010-reporting.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
7 | 2 | VM-MIG-RESOURCES | VM-DB | [DB] Migration: resources for Venue Management (3 tables) | 2 | Hrushikant Patkar |  | MIG-RESOURCES | Tables: resources.performance_participant, resources.qualification, resources.selection_policy. Source DDL: backend/tenant/010-resources.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
7 | 2 | VM-MIG-WORKFORCE | VM-DB | [DB] Migration: workforce for Venue Management (6 tables) | 3 | Tanmay Dukhande |  | MIG-WORKFORCE | Tables: workforce.announcement, workforce.announcement_receipt, workforce.attendance, workforce.attendance_amendment, workforce.shift, workforce.shift_swap. Source DDL: backend/tenant/010-workforce.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
8 | 2 | VM-MIG-AI | VM-DB | [DB] Migration: ai for Venue Management (1 tables) | 1 | Pranay Shinde |  | MIG-AI | Tables: ai.approval_request_score. Source DDL: backend/tenant/010-ai.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
8 | 2 | VM-MIG-PLATFORM | VM-DB | [DB] Migration: platform for Venue Management (5 tables) | 2 | Tanmay Dukhande |  | MIG-PLATFORM | Tables: platform.audit_read, platform.configuration_profile, platform.connectivity_policy, platform.offline_policy, platform.profile_deployment. Source DDL: backend/tenant/010-platform.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
9 | 2 | VM-MIG-MAINTENANCE | VM-DB | [DB] Migration: maintenance for Venue Management (9 tables) | 5 | Hrushikant Patkar |  | MIG-MAINTENANCE | Tables: maintenance.asset_document, maintenance.asset_status_change, maintenance.incident_authority_notification, maintenance.incident_investigation_note, maintenance.incident_involved_party, maintenance.preventive_plan, maintenance.priority_scoring_model, maintenance.vendor_service_request, maintenance.work_order_attachment. Source DDL: backend/tenant/010-maintenance.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
10 | 2 | VM-MIG-CATALOGUE | VM-DB | [DB] Migration: catalogue for Venue Management (3 tables) | 2 | Tanmay Dukhande |  | MIG-CATALOGUE | Tables: catalogue.donation_campaign, catalogue.performance_template, catalogue.variant_dimension. Source DDL: backend/tenant/010-catalogue.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
11 | 2 | VM-MIG-LEDGER | VM-DB | [DB] Migration: ledger for Venue Management (6 tables) | 3 | Tanmay Dukhande |  | MIG-LEDGER | Tables: ledger.account_mapping, ledger.deposit, ledger.fiscal_period_event, ledger.recognition_schedule, ledger.settlement, ledger.settlement_exception. Source DDL: backend/tenant/010-ledger.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
12 | 2 | VM-MIG-INVENTORY | VM-DB | [DB] Migration: inventory for Venue Management (9 tables) | 5 | Hrushikant Patkar |  | MIG-INVENTORY | Tables: inventory.count, inventory.count_line, inventory.purchase_order_line, inventory.quotation, inventory.quotation_line, inventory.requisition_line, inventory.supplier_contract, inventory.transfer, inventory.transfer_line. Source DDL: backend/tenant/010-inventory.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
12 | 2 | VM-MIG-PROMOTIONS | VM-DB | [DB] Migration: promotions for Venue Management (2 tables) | 1 | Tanmay Dukhande |  | MIG-PROMOTIONS | Tables: promotions.upsell_rule, promotions.voucher. Source DDL: backend/tenant/010-promotions.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
13 | 2 | VM-MIG-ORDERS | VM-DB | [DB] Migration: orders for Venue Management (7 tables) | 5 | Pranay Shinde |  | MIG-ORDERS | Tables: orders.after_sale_policy, orders.after_sale_request, orders.chargeback, orders.chargeback_evidence, orders.chargeback_investigation_log, orders.group_quote, orders.refund_batch. Source DDL: backend/tenant/010-orders.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
14 | 2 | VM-MIG-ACCESS | VM-DB | [DB] Migration: access for Venue Management (2 tables) | 2 | Hrushikant Patkar |  | MIG-ACCESS | Tables: access.media_replacement_policy, access.policy_scope_assignment. Source DDL: backend/tenant/010-access.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
14 | 2 | VM-MIG-MARKETING | VM-DB | [DB] Migration: marketing for Venue Management (2 tables) | 2 | Pranay Shinde |  | MIG-MARKETING | Tables: marketing.journey_step, marketing.lost_item. Source DDL: backend/tenant/010-marketing.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
15 | 2 | VM-MIG-FNB | VM-DB | [DB] Migration: fnb for Venue Management (4 tables) | 2 | Hrushikant Patkar |  | MIG-FNB | Tables: fnb.allergen_verdict, fnb.ingredient_substitute, fnb.substitution_rule, fnb.temperature_checkpoint. Source DDL: backend/tenant/010-fnb.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
15 | 2 | VM-MIG-PAYMENTS | VM-DB | [DB] Migration: payments for Venue Management (1 tables) | 1 | Pranay Shinde |  | MIG-PAYMENTS | Tables: payments.provider_cost. Source DDL: backend/tenant/010-payments.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
16 | 2 | VM-MIG-RETAIL | VM-DB | [DB] Migration: retail for Venue Management (1 tables) | 1 | Pranay Shinde |  | MIG-RETAIL | Tables: retail.store_rule. Source DDL: backend/tenant/010-retail.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing.
6 | 2 | VM-PLATFORM-PUBLICAPI-1 | VM-BE-PLATFORM | [BE] PlatformService: createWebhookSubscription, listApiClients, listWebhookDeliveries, listWebhookSubscriptions | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations beyond the first release: createWebhookSubscription, listApiClients, listWebhookDeliveries, listWebhookSubscriptions. Additive to PlatformService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
6 | 2 | VM-PLATFORM-ROLLOUT-1 | VM-BE-PLATFORM | [BE] PlatformService: startRollout | 1 | Chinmay Patkar | PlatformService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations beyond the first release: startRollout. Additive to PlatformService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | VM-TENANCY-MATRIX-1 | VM-BE-TENANCY | [BE] TenancyService: listApprovalMatrices | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS PLATFORM-KERNEL SVC-TENANCY-APPROVALS-1 SVC-TENANCY-MATRIX-1 | Operations beyond the first release: listApprovalMatrices. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
8 | 2 | VM-IDENTITY-ADMINISTRATION-1 | VM-BE-IDENTITY | [BE] IdentityService: listPlatformStaffGrants, resolvePermissions | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-2 SVC-ORDER-ORDERS-4 SVC-PLATFORM-PUBLICAPI-2 SVC-TENANCY-SCOPE-1 VM-MIG-IDENTITY | Operations beyond the first release: listPlatformStaffGrants, resolvePermissions. Additive to IdentityService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
8 | 2 | VM-TENANCY-ANNOUNCEMENTS-1 | VM-BE-TENANCY | [BE] TenancyService: acknowledgeAnnouncement, getAnnouncementReach, listAnnouncements, publishAnnouncement | 5 | Tanmay Dukhande | TenancyService | MIG-IDENTITY MIG-PLATFORM MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: acknowledgeAnnouncement, getAnnouncementReach, listAnnouncements, publishAnnouncement. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
8 | 2 | VM-TENANCY-DEVICES-1 | VM-BE-TENANCY | [BE] TenancyService: createDeviceFirmware, getDeviceFirmware, issueDeviceCredential, listDeviceFirmware | 5 | Tanmay Dukhande | TenancyService | MIG-ASSETS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-TENANCY | Operations beyond the first release: createDeviceFirmware, getDeviceFirmware, issueDeviceCredential, listDeviceFirmware. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
8 | 2 | VM-TENANCY-DEVICES-2 | VM-BE-TENANCY | [BE] TenancyService: revokeDeviceCredential, rollbackDeviceFirmware, setDeviceFirmwareStatus, startDeviceFirmwareRollout | 8 | Tanmay Dukhande | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-TENANCY | Operations beyond the first release: revokeDeviceCredential, rollbackDeviceFirmware, setDeviceFirmwareStatus, startDeviceFirmwareRollout. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
8 | 2 | VM-TENANCY-REQUEST-1 | VM-BE-TENANCY | [BE] TenancyService: escalateApprovalRequest, listApprovalRequests, resubmitApprovalRequest, withdrawApprovalRequest | 8 | Tanmay Dukhande | TenancyService | MIG-APPROVALS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-APPROVALS | Operations beyond the first release: escalateApprovalRequest, listApprovalRequests, resubmitApprovalRequest, withdrawApprovalRequest. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
8 | 2 | VM-TENANCY-ROTA-1 | VM-BE-TENANCY | [BE] TenancyService: requestShiftSwap, updateRotaAssignment | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS MIG-IDENTITY MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: requestShiftSwap, updateRotaAssignment. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
8 | 2 | VM-TENANCY-WORKSTATION-1 | VM-BE-TENANCY | [BE] TenancyService: getWorkstation, registerDevice | 5 | Tanmay Dukhande | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: getWorkstation, registerDevice. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
9 | 2 | VM-TENANCY-TENANCY-1 | VM-BE-TENANCY | [BE] TenancyService: deployConfigurationProfile, listAuditRecords, setConfigurationProfile, setConnectivityThresholds | 8 | Tanmay Dukhande | TenancyService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PLATFORM | Operations beyond the first release: deployConfigurationProfile, listAuditRecords, setConfigurationProfile, setConnectivityThresholds. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
9 | 2 | VM-TENANCY-TENANCY-2 | VM-BE-TENANCY | [BE] TenancyService: setOfflinePolicy | 2 | Chinmay Patkar | TenancyService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PLATFORM | Operations beyond the first release: setOfflinePolicy. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
10 | 2 | VM-PLATFORM-SUBSCRIPTION-1 | VM-BE-PLATFORM | [BE] PlatformService: listChannelListings, setChannelListing | 3 | Sanket Keluskar | PlatformService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations beyond the first release: listChannelListings, setChannelListing. Additive to PlatformService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
14 | 2 | VM-TENANCY-ATTENDANCE-1 | VM-BE-TENANCY | [BE] TenancyService: amendAttendance, listAttendance, recordAttendance | 5 | Tanmay Dukhande | TenancyService | MIG-ACCESS MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: amendAttendance, listAttendance, recordAttendance. Additive to TenancyService; its first-release owner (Tanmay Dukhande) reviews.
10 | 2 | VM-CATALOGUE-BUNDLE-1 | VM-BE-CATALOGUE | [BE] CatalogueService: reportBundleApplied | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: reportBundleApplied. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
10 | 2 | VM-CATALOGUE-CAPACITY-1 | VM-BE-CATALOGUE | [BE] CatalogueService: createChannelCapacity, getChannelAllocations, listChannelCapacities, relinquishChannelAllocation | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: createChannelCapacity, getChannelAllocations, listChannelCapacities, relinquishChannelAllocation. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews.
10 | 2 | VM-CATALOGUE-CAPACITY-2 | VM-BE-CATALOGUE | [BE] CatalogueService: setChannelAllocations, updateChannelCapacity | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setChannelAllocations, updateChannelCapacity. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
10 | 2 | VM-CATALOGUE-EVENT-1 | VM-BE-CATALOGUE | [BE] CatalogueService: cancelPerformance, createPerformances, getEvent | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: cancelPerformance, createPerformances, getEvent. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews.
10 | 2 | VM-CATALOGUE-LEASE-1 | VM-BE-CATALOGUE | [BE] CatalogueService: forceReleaseInventoryHold | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: forceReleaseInventoryHold. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
10 | 2 | VM-CATALOGUE-PRICING-1 | VM-BE-CATALOGUE | [BE] CatalogueService: listPrices | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-INVENTORY-INVENTORY-1 | Operations beyond the first release: listPrices. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
11 | 2 | VM-CATALOGUE-CATALOGUE-1 | VM-BE-CATALOGUE | [BE] CatalogueService: createDonationCampaign, listDonationCampaigns, listWaitlistEntries, offerWaitlistCapacity | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: createDonationCampaign, listDonationCampaigns, listWaitlistEntries, offerWaitlistCapacity. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews.
11 | 2 | VM-CATALOGUE-CATALOGUE-2 | VM-BE-CATALOGUE | [BE] CatalogueService: updateDonationCampaign | 2 | Chinmay Patkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: updateDonationCampaign. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
11 | 2 | VM-CATALOGUE-EVENTS-1 | VM-BE-CATALOGUE | [BE] CatalogueService: listPerformanceTemplates, setPerformanceTemplate | 2 | Chinmay Patkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: listPerformanceTemplates, setPerformanceTemplate. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
11 | 2 | VM-CATALOGUE-PRODUCT-1 | VM-BE-CATALOGUE | [BE] CatalogueService: createProduct, setProductAttributes, transitionProductLifecycle | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-CATALOGUE | Operations beyond the first release: createProduct, setProductAttributes, transitionProductLifecycle. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews.
11 | 2 | VM-LEDGER-JOURNAL-1 | VM-BE-LEDGER | [BE] LedgerService: approveJournalEntry, createJournalEntry, getJournalEntry, listJournalEntries | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: approveJournalEntry, createJournalEntry, getJournalEntry, listJournalEntries. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews.
11 | 2 | VM-LEDGER-JOURNAL-2 | VM-BE-LEDGER | [BE] LedgerService: reverseJournalEntry | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: reverseJournalEntry. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
12 | 2 | VM-LEDGER-FINANCE-1 | VM-BE-LEDGER | [BE] LedgerService: settleDeposit, validateRecognitionSchedules | 3 | Sanket Keluskar | LedgerService | MIG-CATALOGUE MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: settleDeposit, validateRecognitionSchedules. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
12 | 2 | VM-LEDGER-FISCAL-1 | VM-BE-LEDGER | [BE] LedgerService: closeFiscalPeriod, listFiscalPeriods | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-LEDGER | Operations beyond the first release: closeFiscalPeriod, listFiscalPeriods. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
12 | 2 | VM-LEDGER-LEDGER-1 | VM-BE-LEDGER | [BE] LedgerService: abandonPeriodClose, beginPeriodClose, getTrialBalance, listLedgerEntries | 5 | Tanmay Dukhande | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: abandonPeriodClose, beginPeriodClose, getTrialBalance, listLedgerEntries. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews.
12 | 2 | VM-LEDGER-LEDGER-2 | VM-BE-LEDGER | [BE] LedgerService: rejectJournal, reopenPeriod | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: rejectJournal, reopenPeriod. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
12 | 2 | VM-LEDGER-SETTLEMENT-2 | VM-BE-LEDGER | [BE] LedgerService: resolveSettlementException | 2 | Chinmay Patkar | LedgerService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: resolveSettlementException. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
13 | 2 | VM-CATALOGUE-UPSELL-1 | VM-BE-CATALOGUE | [BE] CatalogueService: createUpsellRule, deleteUpsellRule, listUpsellRules | 3 | Sanket Keluskar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations beyond the first release: createUpsellRule, deleteUpsellRule, listUpsellRules. Additive to CatalogueService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
13 | 2 | VM-LEDGER-RECOGNITION-1 | VM-BE-LEDGER | [BE] LedgerService: createRecognitionSchedule, getDeferredRevenue, listRecognitionSchedules, runRecognition | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: createRecognitionSchedule, getDeferredRevenue, listRecognitionSchedules, runRecognition. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews.
13 | 2 | VM-ORDER-ORDERS-3 | VM-BE-ORDER | [BE] OrderService: updateGroupBooking | 2 | Chinmay Patkar | OrderService | MIG-ORDERS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: updateGroupBooking. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
13 | 2 | VM-ORDER-POLICY-1 | VM-BE-ORDER | [BE] OrderService: getRefundPolicy | 2 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-POLICY-1 | Operations beyond the first release: getRefundPolicy. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
14 | 2 | VM-ACCESS-ACCESSPOINT-1 | VM-BE-ACCESS | [BE] AccessService: listAccessPoints | 2 | Chinmay Patkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 | Operations beyond the first release: listAccessPoints. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
14 | 2 | VM-ACCESS-SYNC-1 | VM-BE-ACCESS | [BE] AccessService: listScans, syncScans | 3 | Sanket Keluskar | AccessService | MIG-ACCESS MIG-PLATFORM MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: listScans, syncScans. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
14 | 2 | VM-ORDER-DRAFTED-1 | VM-BE-ORDER | [BE] OrderService: listTicketReissueFulfillment | 1 | Chinmay Patkar | OrderService | MIG-ACCESS MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ORDER-CART-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-SYNC-1 VM-MIG-ORDERS | Operations beyond the first release: listTicketReissueFulfillment. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
14 | 2 | VM-ORDER-ORDERS-1 | VM-BE-ORDER | [BE] OrderService: assignChargeback, authoriseStoredValue, captureStoredValue, createGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PII MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS VM-MIG-PROMOTIONS | Operations beyond the first release: assignChargeback, authoriseStoredValue, captureStoredValue, createGroupBooking. Additive to OrderService; its first-release owner (Pranay Shinde) reviews.
14 | 2 | VM-ORDER-ORDERS-2 | VM-BE-ORDER | [BE] OrderService: getChargebackAnalytics, recordChargeback, recordChargebackOutcome, relinquishStoredValue | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-LEDGER VM-MIG-ORDERS | Operations beyond the first release: getChargebackAnalytics, recordChargeback, recordChargebackOutcome, relinquishStoredValue. Additive to OrderService; its first-release owner (Pranay Shinde) reviews.
11 | 2 | VM-LEDGER-REPORTING-1 | VM-BE-LEDGER | [BE] LedgerService: getVatReturn | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-KERNEL SVC-LEDGER-FISCAL-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-REFUND-1 SVC-ORDER-SHIFT-2 VM-LEDGER-FINANCE-1 VM-LEDGER-JOURNAL-1 VM-LEDGER-JOURNAL-2 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 | Operations beyond the first release: getVatReturn. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews.
14 | 2 | VM-ORDER-REFUND-1 | VM-BE-ORDER | [BE] OrderService: approveRefund, createBulkRefund | 5 | Pranay Shinde | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations beyond the first release: approveRefund, createBulkRefund. Additive to OrderService; its first-release owner (Pranay Shinde) reviews.
15 | 2 | VM-ACCESS-ACCESS-1 | VM-BE-ACCESS | [BE] AccessService: listCredentialReplacementReissue | 1 | Chinmay Patkar | AccessService | PLATFORM-KERNEL VM-MIG-ACCESS | Operations beyond the first release: listCredentialReplacementReissue. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-ACCESS-VALIDATION-1 | VM-BE-ACCESS | [BE] AccessService: lookupTicket, overrideAccess, validateAccess, validateGroupAccess | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations beyond the first release: lookupTicket, overrideAccess, validateAccess, validateGroupAccess. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews.
16 | 2 | VM-LEDGER-SETTLEMENT-1 | VM-BE-LEDGER | [BE] LedgerService: getSettlement, ingestSettlementFile, listSettlementExceptions, listSettlements | 8 | Tanmay Dukhande | LedgerService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER VM-MIG-PAYMENTS | Operations beyond the first release: getSettlement, ingestSettlementFile, listSettlementExceptions, listSettlements. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews.
5 | 2 | VM-VENUEOPS-DEPARTURE-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: listTransportRouteDepartures, updateTransportDeparture | 2 | Chinmay Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-TIMETABLE-1 | Operations beyond the first release: listTransportRouteDepartures, updateTransportDeparture. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | VM-VENUEOPS-GAME-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: listGames, updateGame | 3 | Sanket Keluskar | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations beyond the first release: listGames, updateGame. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | VM-VENUEOPS-PLAY-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: recordGamePlay, syncGamePlays | 5 | Deep Khanvilkar | VenueOpsService | MIG-GAMES MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations beyond the first release: recordGamePlay, syncGamePlays. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
7 | 2 | VM-ORDER-SYNC-1 | VM-BE-ORDER | [BE] OrderService: listSyncRejections | 2 | Chinmay Patkar | OrderService | MIG-SYNC PLATFORM-KERNEL SVC-ORDER-SYNC-1 VM-ACCESS-SYNC-1 VM-VENUEOPS-PLAY-1 | Operations beyond the first release: listSyncRejections. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
8 | 2 | VM-VENUEOPS-RESOURCES-2 | VM-BE-VENUEOPS | [BE] VenueOpsService: listResources, reorderPerformanceManifest, setResourceQualifications | 3 | Sanket Keluskar | VenueOpsService | MIG-IDENTITY MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: listResources, reorderPerformanceManifest, setResourceQualifications. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
9 | 2 | VM-VENUEOPS-INCIDENT-2 | VM-BE-VENUEOPS | [BE] VenueOpsService: updateIncident | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: updateIncident. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
9 | 2 | VM-VENUEOPS-MAINTENANCE-2 | VM-BE-VENUEOPS | [BE] VenueOpsService: rejectWorkOrder | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: rejectWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
9 | 2 | VM-VENUEOPS-WORK-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: cancelWorkOrder | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: cancelWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
9 | 2 | VM-VENUEOPS-WORKORDER-3 | VM-BE-VENUEOPS | [BE] VenueOpsService: updateWorkOrder, verifyWorkOrder | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: updateWorkOrder, verifyWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
10 | 2 | VM-VENUEOPS-ASSET-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: createAsset, getAsset, getAssetHistory, listAssets | 8 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: createAsset, getAsset, getAssetHistory, listAssets. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
10 | 2 | VM-VENUEOPS-ASSET-2 | VM-BE-VENUEOPS | [BE] VenueOpsService: lookupAsset, setAssetStatus, updateAsset | 8 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: lookupAsset, setAssetStatus, updateAsset. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
10 | 2 | VM-VENUEOPS-INCIDENT-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: getIncident, listIncidents, recordAuthorityNotification, reportIncident | 8 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: getIncident, listIncidents, recordAuthorityNotification, reportIncident. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
10 | 2 | VM-VENUEOPS-WORKORDER-2 | VM-BE-VENUEOPS | [BE] VenueOpsService: listVendorServiceRequests, listWorkOrders, suggestWorkOrderAssignee, updateVendorServiceRequest | 8 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE VM-MIG-RESOURCES VM-MIG-WORKFORCE | Operations beyond the first release: listVendorServiceRequests, listWorkOrders, suggestWorkOrderAssignee, updateVendorServiceRequest. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
12 | 2 | VM-INVENTORY-ITEM-1 | VM-BE-INVENTORY | [BE] InventoryService: listInventoryItems | 2 | Chinmay Patkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 | Operations beyond the first release: listInventoryItems. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
12 | 2 | VM-INVENTORY-MOVEMENT-1 | VM-BE-INVENTORY | [BE] InventoryService: createStockMovement, listStockMovements | 3 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: createStockMovement, listStockMovements. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
12 | 2 | VM-INVENTORY-RECEIPT-1 | VM-BE-INVENTORY | [BE] InventoryService: listGoodsReceipts | 1 | Chinmay Patkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-RECEIPT-1 | Operations beyond the first release: listGoodsReceipts. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
12 | 2 | VM-INVENTORY-STOCK-1 | VM-BE-INVENTORY | [BE] InventoryService: getStockPositions, getStockValuation, listStockLocations | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-LEDGER PLATFORM-KERNEL SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-LEDGER-ACCOUNTS-1 | Operations beyond the first release: getStockPositions, getStockValuation, listStockLocations. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
12 | 2 | VM-VENUEOPS-MAINTENANCE-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: acceptWorkOrder, attachWorkOrderEvidence, closeWorkOrder, pauseWorkOrder | 8 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-INVENTORY MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: acceptWorkOrder, attachWorkOrderEvidence, closeWorkOrder, pauseWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
12 | 2 | VM-VENUEOPS-WORKORDER-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: completeWorkOrder, createVendorServiceRequest, createWorkOrder, getWorkOrder | 8 | Hrushikant Patkar | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-MAINTENANCE | Operations beyond the first release: completeWorkOrder, createVendorServiceRequest, createWorkOrder, getWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
13 | 2 | VM-INVENTORY-COUNT-1 | VM-BE-INVENTORY | [BE] InventoryService: cancelStockCount, getCountVariance, listStockCounts, postStockCount | 8 | Hrushikant Patkar | InventoryService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-INVENTORY | Operations beyond the first release: cancelStockCount, getCountVariance, listStockCounts, postStockCount. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
13 | 2 | VM-INVENTORY-COUNT-2 | VM-BE-INVENTORY | [BE] InventoryService: recountStockCount, startStockCount, submitCountLines | 5 | Deep Khanvilkar | InventoryService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: recountStockCount, startStockCount, submitCountLines. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
13 | 2 | VM-INVENTORY-PROCUREMENT-1 | VM-BE-INVENTORY | [BE] InventoryService: acknowledgePurchaseOrder, cancelRequisition, closePurchaseOrderShort, rejectRequisition | 8 | Hrushikant Patkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: acknowledgePurchaseOrder, cancelRequisition, closePurchaseOrderShort, rejectRequisition. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
13 | 2 | VM-INVENTORY-PROCUREMENT-2 | VM-BE-INVENTORY | [BE] InventoryService: returnRequisition, sendPurchaseOrder | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: returnRequisition, sendPurchaseOrder. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
13 | 2 | VM-INVENTORY-PURCHASEORDER-1 | VM-BE-INVENTORY | [BE] InventoryService: cancelPurchaseOrder, createPurchaseOrder, getPurchaseOrder, listPurchaseOrders | 8 | Hrushikant Patkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: cancelPurchaseOrder, createPurchaseOrder, getPurchaseOrder, listPurchaseOrders. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
13 | 2 | VM-INVENTORY-REQUISITION-1 | VM-BE-INVENTORY | [BE] InventoryService: approveRequisition, createRequisition, getSuggestedRequisitions, listRequisitions | 8 | Hrushikant Patkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: approveRequisition, createRequisition, getSuggestedRequisitions, listRequisitions. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
13 | 2 | VM-INVENTORY-SUPPLIER-1 | VM-BE-INVENTORY | [BE] InventoryService: compareQuotations, createSupplier, createSupplierContract, listSupplierContracts | 8 | Hrushikant Patkar | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: compareQuotations, createSupplier, createSupplierContract, listSupplierContracts. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
13 | 2 | VM-INVENTORY-SUPPLIER-2 | VM-BE-INVENTORY | [BE] InventoryService: listSuppliers, recordQuotation, updateSupplierContract | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: listSuppliers, recordQuotation, updateSupplierContract. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
13 | 2 | VM-INVENTORY-TRANSFER-1 | VM-BE-INVENTORY | [BE] InventoryService: closeTransferShort, createStockTransfer, listStockTransfers, receiveStockTransfer | 8 | Hrushikant Patkar | InventoryService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: closeTransferShort, createStockTransfer, listStockTransfers, receiveStockTransfer. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
14 | 2 | VM-VENUEOPS-RESOURCES-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: bookResource, checkInResource, checkOutResource, getPerformanceManifest | 8 | Hrushikant Patkar | VenueOpsService | MIG-MARKETING MIG-ORDERS MIG-PII MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: bookResource, checkInResource, checkOutResource, getPerformanceManifest. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews.
15 | 2 | VM-FNB-FNB-1 | VM-BE-FNB | [BE] FnbService: completeProductionRun, enterCountLine, getProductionRun, listProductionRuns | 8 | Hrushikant Patkar | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: completeProductionRun, enterCountLine, getProductionRun, listProductionRuns. Additive to FnbService; its first-release owner (Hrushikant Patkar) reviews.
15 | 2 | VM-FNB-ORDER-1 | VM-BE-FNB | [BE] FnbService: amendFnbOrder | 2 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: amendFnbOrder. Additive to FnbService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-FNB-PRODUCTION-1 | VM-BE-FNB | [BE] FnbService: listRecipes, recordWaste | 3 | Sanket Keluskar | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: listRecipes, recordWaste. Additive to FnbService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-FNB-SERVICE-1 | VM-BE-FNB | [BE] FnbService: acceptFnbOrder, cancelFnbOrder | 5 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: acceptFnbOrder, cancelFnbOrder. Additive to FnbService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-INVENTORY-INVENTORY-1 | VM-BE-INVENTORY | [BE] InventoryService: getStockTransfer, listExpiringBatches, updateRequisitionLines, updateSupplier | 8 | Hrushikant Patkar | InventoryService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: getStockTransfer, listExpiringBatches, updateRequisitionLines, updateSupplier. Additive to InventoryService; its first-release owner (Hrushikant Patkar) reviews.
15 | 2 | VM-VENUEOPS-ENTRY-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: callNextParties | 1 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: callNextParties. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-VENUEOPS-FEED-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: listQueueFeeds, testQueueFeed | 2 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: listQueueFeeds, testQueueFeed. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-VENUEOPS-QUEUE-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: setQueueStatus | 3 | Sanket Keluskar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setQueueStatus. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-VENUEOPS-VENUEMAP-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: setPathClosure | 2 | Chinmay Patkar | VenueOpsService | MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setPathClosure. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
15 | 2 | VM-VENUEOPS-WAITTIME-1 | VM-BE-VENUEOPS | [BE] VenueOpsService: setWaitTime | 2 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setWaitTime. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
16 | 2 | VM-FNB-FNB-2 | VM-BE-FNB | [BE] FnbService: planProductionRun, requestRecount, setIngredientSubstitutes, setSubstitutionRules | 5 | Hrushikant Patkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB | Operations beyond the first release: planProductionRun, requestRecount, setIngredientSubstitutes, setSubstitutionRules. Additive to FnbService; its first-release owner (Hrushikant Patkar) reviews.
16 | 2 | VM-FNB-FNB-3 | VM-BE-FNB | [BE] FnbService: setTemperatureCheckpoint, verifyAllergens | 2 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB | Operations beyond the first release: setTemperatureCheckpoint, verifyAllergens. Additive to FnbService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
17 | 2 | VM-RETAIL-RETAIL-1 | VM-BE-RETAIL | [BE] RetailService: disposeShopAndDrop, listStoreRules, setStoreRules | 3 | Sanket Keluskar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RETAIL | Operations beyond the first release: disposeShopAndDrop, listStoreRules, setStoreRules. Additive to RetailService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
9 | 2 | VM-AI-RISK-1 | VM-BE-AI | [BE] AiService: getApprovalRequestScore | 1 | Chinmay Patkar | AiService | PLATFORM-KERNEL VM-MIG-AI | Operations beyond the first release: getApprovalRequestScore. Additive to AiService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
14 | 2 | VM-MARKETING-CAMPAIGN-1 | VM-BE-MARKETING | [BE] MarketingService: listCampaigns | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-SEGMENT-1 | Operations beyond the first release: listCampaigns. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
14 | 2 | VM-MARKETING-SEGMENT-1 | VM-BE-MARKETING | [BE] MarketingService: listSegments | 1 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-SEGMENT-1 | Operations beyond the first release: listSegments. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
15 | 2 | VM-MARKETING-MARKETING-1 | VM-BE-MARKETING | [BE] MarketingService: createJourney, listJourneys, listLostItems, matchLostItem | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MARKETING | Operations beyond the first release: createJourney, listJourneys, listLostItems, matchLostItem. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews.
15 | 2 | VM-MARKETING-MARKETING-2 | VM-BE-MARKETING | [BE] MarketingService: recordLostItem | 3 | Sanket Keluskar | MarketingService | MIG-PII MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MARKETING | Operations beyond the first release: recordLostItem. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews.
7 | 2 | VM-REPORTING-EXECUTION-1 | VM-BE-REPORTING | [BE] ReportingService: listReportExecutions | 1 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-EXECUTION-1 | Operations beyond the first release: listReportExecutions. Additive to ReportingService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
8 | 2 | VM-REPORTING-SCHEDULE-1 | VM-BE-REPORTING | [BE] ReportingService: createReportSchedule | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MENU-1 SVC-FNB-MENU-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-2 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-3 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-BUNDLE-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-CATALOGUE-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-EVENTS-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-FNB-FNB-1 VM-FNB-FNB-2 VM-FNB-FNB-3 VM-FNB-ORDER-1 VM-FNB-PRODUCTION-1 VM-FNB-SERVICE-1 VM-INVENTORY-COUNT-1 VM-INVENTORY-COUNT-2 VM-INVENTORY-INVENTORY-1 VM-INVENTORY-MOVEMENT-1 VM-INVENTORY-PROCUREMENT-1 VM-INVENTORY-PROCUREMENT-2 VM-INVENTORY-PURCHASEORDER-1 VM-INVENTORY-REQUISITION-1 VM-INVENTORY-SUPPLIER-1 VM-INVENTORY-SUPPLIER-2 VM-INVENTORY-TRANSFER-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-JOURNAL-1 VM-LEDGER-JOURNAL-2 VM-LEDGER-LEDGER-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-REPORTING VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 VM-RETAIL-RETAIL-1 | Operations beyond the first release: createReportSchedule. Additive to ReportingService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.
13 | 2 | VM-REPORTING-REPORTING-1 | VM-BE-REPORTING | [BE] ReportingService: acknowledgeAlert, getKpiValues, getSupplierPerformance | 3 | Sanket Keluskar | ReportingService | MIG-IDENTITY MIG-INVENTORY MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-8 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-KITCHEN-2 SVC-FNB-MENU-1 SVC-FNB-MENU-2 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-INVENTORY-1 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-2 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-3 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-BUNDLE-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-CATALOGUE-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-EVENTS-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-FNB-FNB-1 VM-FNB-FNB-2 VM-FNB-FNB-3 VM-FNB-ORDER-1 VM-FNB-PRODUCTION-1 VM-FNB-SERVICE-1 VM-INVENTORY-COUNT-1 VM-INVENTORY-COUNT-2 VM-INVENTORY-INVENTORY-1 VM-INVENTORY-MOVEMENT-1 VM-INVENTORY-PROCUREMENT-1 VM-INVENTORY-PROCUREMENT-2 VM-INVENTORY-PURCHASEORDER-1 VM-INVENTORY-REQUISITION-1 VM-INVENTORY-SUPPLIER-1 VM-INVENTORY-SUPPLIER-2 VM-INVENTORY-TRANSFER-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-JOURNAL-1 VM-LEDGER-JOURNAL-2 VM-LEDGER-LEDGER-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-ACCREDITATION VM-MIG-INVENTORY VM-MIG-REPORTING VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 VM-RETAIL-RETAIL-1 | Operations beyond the first release: acknowledgeAlert, getKpiValues, getSupplierPerformance. Additive to ReportingService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews.

## Migrations
Order | Task | Migration file | Database | Schema | Tables | Columns | References (created earlier or deferred) | Assignee | Points | Owning service
0 | MIG-BASELINE | V0001__baseline.sql | both | (baseline) | 0 | 0 |  | Hrushikant Patkar | 3
1 | MIG-CONTROL | V0002__control.sql | control | control | 17 | 293 |  | Hrushikant Patkar | 8 | PlatformService
2 | MIG-TENANCY | V0003__tenancy.sql | tenant | tenancy | 1 | 12 |  | Tanmay Dukhande | 1 | TenancyService
3 | MIG-PRICING | V0004__pricing.sql | tenant | pricing | 3 | 36 | catalogue | Tanmay Dukhande | 2 | CatalogueService
4 | MIG-SUBSCRIPTION | V0005__subscription.sql | tenant | subscription | 4 | 36 | platform | Hrushikant Patkar | 2 | PlatformService
5 | MIG-TRANSPORT | V0006__transport.sql | tenant | transport | 12 | 107 | assets | Hrushikant Patkar | 8 | VenueOpsService
6 | MIG-PII | V0007__pii.sql | tenant | pii | 5 | 51 | access, marketing | Tanmay Dukhande | 3 | IdentityService
7 | MIG-GAMES | V0008__games.sql | tenant | games | 2 | 15 | pii, platform | Hrushikant Patkar | 2 | VenueOpsService
8 | MIG-IDENTITY | V0009__identity.sql | tenant | identity | 13 | 113 | pii, platform | Tanmay Dukhande | 8 | IdentityService
9 | MIG-APPROVALS | V0010__approvals.sql | tenant | approvals | 6 | 88 | identity | Tanmay Dukhande | 5 | TenancyService
10 | MIG-REPORTING | V0011__reporting.sql | tenant | reporting | 15 | 154 | identity, platform | Hrushikant Patkar | 8 | ReportingService
11 | MIG-SYNC | V0012__sync.sql | tenant | sync | 1 | 11 | identity, platform | Pranay Shinde | 1 | CrossRegionService
12 | MIG-ASSETS | V0013__assets.sql | tenant | assets | 7 | 74 | identity, platform | Hrushikant Patkar | 5 | VenueOpsService
13 | MIG-AI | V0014__ai.sql | tenant | ai | 46 | 660 | assets, identity, pii, platform | Pranay Shinde | 8 | AiService
14 | MIG-RESOURCES | V0015__resources.sql | tenant | resources | 7 | 86 | identity, orders, pii, platform | Hrushikant Patkar | 5 | VenueOpsService
15 | MIG-WHITELABEL | V0016__whitelabel.sql | tenant | whitelabel | 25 | 220 | identity, platform, promotions | Tanmay Dukhande | 8 | WhiteLabelService
16 | MIG-WORKFORCE | V0017__workforce.sql | tenant | workforce | 1 | 17 | identity, platform | Tanmay Dukhande | 1 | TenancyService
17 | MIG-PLATFORM | V0018__platform.sql | tenant | platform | 17 | 167 | access, approvals, identity, inventory, ledger | Tanmay Dukhande | 8 | TenancyService
18 | MIG-SEATING | V0019__seating.sql | tenant | seating | 6 | 62 | catalogue, identity, pii, platform | Tanmay Dukhande | 3 | CatalogueService
19 | MIG-MAINTENANCE | V0020__maintenance.sql | tenant | maintenance | 6 | 146 | access, identity, inventory, platform | Hrushikant Patkar | 5 | VenueOpsService
20 | MIG-WALLET | V0021__wallet.sql | tenant | wallet | 23 | 208 | identity, orders, pii, platform | Pranay Shinde | 8 | WalletService
21 | MIG-CATALOGUE | V0022__catalogue.sql | tenant | catalogue | 31 | 484 | access, identity, ledger, pii, platform, seating | Tanmay Dukhande | 8 | CatalogueService
22 | MIG-LEDGER | V0023__ledger.sql | tenant | ledger | 19 | 262 | catalogue, identity, orders, platform | Tanmay Dukhande | 8 | LedgerService
23 | MIG-INVENTORY | V0024__inventory.sql | tenant | inventory | 11 | 162 | identity, ledger, platform | Hrushikant Patkar | 8 | InventoryService
24 | MIG-PROMOTIONS | V0025__promotions.sql | tenant | promotions | 17 | 193 | ledger, orders, pii, platform | Tanmay Dukhande | 8 | CatalogueService
25 | MIG-ORDERS | V0026__orders.sql | tenant | orders | 33 | 399 | access, catalogue, identity, ledger, pii, platform, promotions | Pranay Shinde | 8 | OrderService
26 | MIG-ACCESS | V0027__access.sql | tenant | access | 23 | 379 | catalogue, identity, orders, pii, platform | Hrushikant Patkar | 8 | AccessService
27 | MIG-MARKETING | V0028__marketing.sql | tenant | marketing | 49 | 585 | ai, catalogue, identity, ledger, orders, pii, platform | Pranay Shinde | 8 | MarketingService
28 | MIG-FNB | V0029__fnb.sql | tenant | fnb | 34 | 325 | access, catalogue, identity, inventory, orders, pii, platform, seating | Hrushikant Patkar | 8 | FnbService
29 | MIG-PAYMENTS | V0030__payments.sql | tenant | payments | 11 | 132 | marketing, orders, pii | Pranay Shinde | 8 | OrderService
30 | MIG-QUEUE | V0031__queue.sql | tenant | queue | 5 | 81 | access, catalogue, maintenance, pii, platform | Hrushikant Patkar | 3 | VenueOpsService
31 | MIG-RETAIL | V0032__retail.sql | tenant | retail | 10 | 110 | access, catalogue, fnb, identity, inventory, orders, pii, platform | Pranay Shinde | 5 | RetailService
32 | MIG-VENUEMAP | V0033__venuemap.sql | tenant | venuemap | 8 | 106 | access, assets, catalogue, marketing, orders, platform, promotions, resources | Hrushikant Patkar | 5 | VenueOpsService
33 | MIG-FOREIGN-KEYS | V0034__cross_schema_foreign_keys.sql | tenant | (cross-schema) | 0 | 0 |  | Hrushikant Patkar | 3

## Tables
Migration | Table | Database | Columns | Row-level security | Partitioned by month | Operations reading | Operations writing | Foreign keys to | Why it is in the release | Owning service | Source DDL
MIG-CONTROL | control.api_client | control | 14 | none |  | 4 | 3 | control.integration_listing | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.api_licence | control | 9 | none |  | 2 | 1 | control.tenant | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.api_version | control | 9 | none |  | 2 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.content_block | control | 12 | scope_path |  | 4 | 2 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.developer_account | control | 8 | none |  | 3 | 2 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.integration_listing | control | 12 | none |  | 3 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.invoice | control | 14 | none |  | 0 | 0 |  | referenced by control.invoice_line | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.invoice_line | control | 10 | none |  | 0 | 1 | control.invoice | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.licence_add_on | control | 7 | none |  | 3 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.licence_add_on_limit | control | 6 | none |  | 0 | 1 | control.licence_add_on | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner | control | 28 | scope_path |  | 0 | 0 |  | referenced by control.partner_agreement | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_agreement | control | 53 | scope_path |  | 0 | 1 | control.partner | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_application | control | 31 | scope_path |  | 0 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_change_request | control | 28 | scope_path |  | 0 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.production_access_request | control | 14 | none |  | 1 | 1 | control.api_client, control.integration_listing | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.seo_metadata | control | 15 | scope_path |  | 1 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.tenant | control | 23 | none |  | 9 | 5 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-TENANCY | tenancy.device_assignment | tenant | 12 | scope_path |  | 1 | 1 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-PRICING | pricing.dynamic_price_action | tenant | 7 | none |  | 4 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-pricing.sql
MIG-PRICING | pricing.dynamic_price_condition | tenant | 8 | none |  | 4 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-pricing.sql
MIG-PRICING | pricing.dynamic_price_rule | tenant | 21 | scope_path |  | 4 | 4 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-pricing.sql
MIG-SUBSCRIPTION | subscription.contract | tenant | 12 | none |  | 4 | 2 | platform.tenant, subscription.plan | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.plan | tenant | 15 | none |  | 5 | 2 |  | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.plan_limit | tenant | 6 | none |  | 2 | 2 | subscription.plan | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.plan_module | tenant | 3 | none |  | 2 | 0 | subscription.plan | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-TRANSPORT | transport.departure | tenant | 10 | none |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_matrix_cell | tenant | 5 | none |  | 6 | 1 | transport.fare_table | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_passenger_type | tenant | 11 | none |  | 5 | 1 | transport.fare_table | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_table | tenant | 6 | none |  | 6 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.favourite_route | tenant | 8 | venue_id |  | 3 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.network_import | tenant | 10 | venue_id |  | 2 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.pass_type | tenant | 14 | venue_id |  | 3 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.route | tenant | 12 | venue_id |  | 10 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.route_stop | tenant | 7 | none |  | 9 | 3 | transport.route | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.station | tenant | 8 | venue_id |  | 10 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.timetable | tenant | 12 | none |  | 4 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.timetable_run | tenant | 4 | none |  | 2 | 2 | transport.timetable | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-PII | pii.consent_identifier | tenant | 6 | scope_path |  | 0 | 1 |  | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject | tenant | 13 | none |  | 19 | 7 |  | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_biometric | tenant | 12 | none |  | 4 | 3 | access.entitlement, marketing.consent_purpose, pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_contact | tenant | 10 | none |  | 6 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_document | tenant | 10 | none |  | 0 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-GAMES | games.card | tenant | 13 | venue_id |  | 4 | 3 | pii.subject, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-games.sql
MIG-GAMES | games.credit_ledger | tenant | 2 | none |  | 1 | 0 | games.card | used by the first release | VenueOpsService | backend/tenant/010-games.sql
MIG-IDENTITY | identity.delegated_access | tenant | 21 | scope_path |  | 12 | 3 | identity.principal, identity.role, pii.subject, platform.scope | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.guest_identity_verification | tenant | 13 | none |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.guest_verification_policy | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_challenge | tenant | 2 | none |  | 1 | 2 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_method | tenant | 9 | none |  | 11 | 3 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_recovery_code | tenant | 2 | none |  | 2 | 2 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.otp_challenge | tenant | 2 | none |  | 2 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.password_policy | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.platform_staff_grant | tenant | 9 | scope_path |  | 1 | 0 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal | tenant | 9 | none |  | 24 | 2 | identity.role, platform.scope | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal_credential | tenant | 2 | none |  | 2 | 2 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.refresh_token | tenant | 10 | none |  | 1 | 2 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.role | tenant | 8 | none |  | 6 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-APPROVALS | approvals.decision | tenant | 13 | none |  | 2 | 1 | approvals.request, identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.delegation | tenant | 10 | scope_path |  | 4 | 2 | identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.external_provider | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.matrix | tenant | 6 | scope_path |  | 5 | 2 |  | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.request | tenant | 27 | scope_path |  | 2 | 2 | identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.rule | tenant | 18 | none |  | 6 | 2 | approvals.matrix | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-REPORTING | reporting.alert | tenant | 18 | scope_path |  | 1 | 0 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.alert_rule | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard | tenant | 10 | venue_id |  | 5 | 3 | identity.principal, platform.scope | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard_tile | tenant | 8 | none |  | 4 | 2 | reporting.dashboard, reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard_view | tenant | 5 | venue_id |  | 0 | 1 | identity.principal, reporting.dashboard | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.execution | tenant | 15 | none |  | 1 | 1 | identity.principal, reporting.report_definition, reporting.schedule | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.kpi_definition | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.natural_language_query | tenant | 9 | scope_path |  | 1 | 2 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_column | tenant | 8 | none |  | 6 | 4 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_definition | tenant | 16 | scope_path |  | 8 | 4 | identity.principal | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_definition_version | tenant | 7 | scope_path |  | 1 | 2 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_filter | tenant | 7 | none |  | 6 | 4 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_parameter | tenant | 7 | none |  | 6 | 3 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.schedule | tenant | 15 | none |  | 0 | 0 | identity.principal, reporting.report_definition | referenced by reporting.execution | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.semantic_model | tenant | 4 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-SYNC | sync.rejection | tenant | 11 | none |  | 0 | 1 | identity.principal, platform.workstation | used by the first release | CrossRegionService | backend/tenant/010-sync.sql
MIG-ASSETS | assets.asset_version | tenant | 11 | scope_path |  | 0 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_asset | tenant | 25 | venue_id |  | 14 | 3 | identity.principal, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_collection | tenant | 7 | venue_id |  | 2 | 1 | assets.media_asset, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_collection_member | tenant | 5 | none |  | 1 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_fingerprint | tenant | 7 | scope_path |  | 0 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_upload | tenant | 12 | venue_id |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_usage | tenant | 7 | none |  | 3 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-AI | ai.action_plan | tenant | 19 | scope_path |  | 1 | 1 | ai.action_plan, ai.proposed_action, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.activity | tenant | 24 | scope_path |  | 1 | 11 | ai.conversation, identity.principal, pii.subject | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.anomaly_detector | tenant | 14 | scope_path |  | 0 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.answer_feedback | tenant | 11 | scope_path |  | 1 | 1 | ai.conversation, ai.message, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.assistant_profile | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.byok_enablement | tenant | 10 | scope_path |  | 3 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.capability | tenant | 18 | scope_path |  | 5 | 3 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.capability_maturity | tenant | 9 | scope_path |  | 1 | 0 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.chunk_embedding | tenant | 12 | none |  | 4 | 2 | ai.chunk_embedding, ai.knowledge_document | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.conversation | tenant | 8 | scope_path |  | 3 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.decision_record | tenant | 25 | scope_path |  | 1 | 15 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.eval_run | tenant | 14 | scope_path |  | 2 | 1 | ai.eval_suite, ai.release, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.eval_suite | tenant | 9 | scope_path |  | 1 | 0 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_definition | tenant | 19 | scope_path |  | 2 | 2 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_point | tenant | 12 | scope_path |  | 2 | 2 | ai.forecast_scenario, ai.forecast_version | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_scenario | tenant | 8 | scope_path |  | 1 | 1 | ai.forecast_version, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_version | tenant | 17 | scope_path |  | 4 | 2 | ai.forecast_definition, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_alert | tenant | 14 | scope_path |  | 1 | 1 | ai.incident, ai.release, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_policy | tenant | 9 | scope_path |  | 2 | 2 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_policy_version | tenant | 12 | scope_path |  | 5 | 3 | ai.governance_policy, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.guided_choice_suggestion | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.history_import | tenant | 18 | scope_path |  | 3 | 1 | assets.media_asset, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.history_observation | tenant | 10 | scope_path |  | 2 | 1 | ai.history_import | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.incident | tenant | 16 | scope_path |  | 1 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_entry | tenant | 2 | none |  | 0 | 1 | ai.index_source | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_job | tenant | 14 | none |  | 1 | 1 | ai.index_source | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_source | tenant | 15 | none |  | 2 | 1 | ai.knowledge_collection | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.insight | tenant | 22 | scope_path |  | 3 | 2 | ai.anomaly_detector, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.intervention | tenant | 11 | scope_path |  | 0 | 2 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_collection | tenant | 12 | scope_path |  | 4 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_document | tenant | 11 | scope_path |  | 3 | 1 | ai.knowledge_collection | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_gap | tenant | 13 | scope_path |  | 0 | 2 | ai.knowledge_collection, ai.knowledge_document, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.message | tenant | 15 | none |  | 2 | 1 | ai.conversation, ai.proposed_action | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.model | tenant | 16 | scope_path |  | 3 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.operational_requirement | tenant | 17 | scope_path |  | 2 | 2 | ai.forecast_version, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.policy | tenant | 28 | scope_path |  | 14 | 4 | platform.tenant | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.policy_exception | tenant | 13 | scope_path |  | 2 | 2 | ai.governance_policy, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.prompt_template | tenant | 13 | scope_path |  | 3 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.proposed_action | tenant | 18 | scope_path |  | 2 | 5 | ai.action_plan, ai.activity, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.provider | tenant | 22 | scope_path |  | 10 | 2 | ai.model, platform.scope | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_decision | tenant | 19 | scope_path |  | 1 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_decline | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_event | tenant | 11 | scope_path |  | 0 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.release | tenant | 17 | scope_path |  | 6 | 5 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.suggestion | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.venue_settings | tenant | 14 | scope_path |  | 4 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-RESOURCES | resources.booking | tenant | 16 | none |  | 3 | 0 | orders.sales_order, pii.subject, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource | tenant | 16 | scope_path |  | 5 | 2 | identity.principal, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_block | tenant | 8 | scope_path |  | 5 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_hold | tenant | 15 | scope_path |  | 7 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_package | tenant | 13 | scope_path |  | 2 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_requirement | tenant | 10 | scope_path |  | 4 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_schedule | tenant | 8 | scope_path |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-WHITELABEL | whitelabel.analytics_provider | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.app_build | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.banner | tenant | 12 | none |  | 4 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.booking_flow | tenant | 10 | scope_path |  | 15 | 3 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.booking_flow_step | tenant | 7 | none |  | 10 | 4 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.config_version | tenant | 11 | scope_path |  | 8 | 1 | identity.principal | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.content_page | tenant | 11 | scope_path |  | 5 | 2 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.custom_domain | tenant | 11 | none |  | 4 | 3 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.faq_category | tenant | 5 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.faq_entry | tenant | 6 | none |  | 3 | 1 | whitelabel.faq_category | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.feature_toggle | tenant | 7 | none |  | 4 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config | tenant | 4 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config_column | tenant | 3 | none |  | 3 | 1 | whitelabel.footer_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config_social_link | tenant | 4 | none |  | 3 | 1 | whitelabel.footer_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice | tenant | 13 | venue_id |  | 8 | 4 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice_answer | tenant | 5 | none |  | 10 | 3 | whitelabel.guided_choice | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice_question | tenant | 5 | none |  | 8 | 4 | whitelabel.guided_choice | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.homepage_section | tenant | 3 | none |  | 5 | 2 | whitelabel.content_page | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.module_enablement | tenant | 7 | none |  | 4 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.navigation_item | tenant | 4 | none |  | 4 | 2 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.policy | tenant | 10 | scope_path |  | 3 | 1 | identity.principal | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.promo_block | tenant | 11 | scope_path |  | 5 | 3 | promotions.promotion | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.site_setup_progress | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.store_account | tenant | 11 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.tenant_config | tenant | 25 | none |  | 24 | 12 | platform.tenant, whitelabel.footer_config, whitelabel.homepage_section, whitelabel.navigation_item | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WORKFORCE | workforce.rota_assignment | tenant | 17 | venue_id |  | 2 | 1 | identity.principal, platform.scope, platform.workstation | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-PLATFORM | platform.audit_record | tenant | 8 | none | yes | 0 | 3 | identity.principal, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.denomination | tenant | 7 | none |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.device | tenant | 23 | none |  | 5 | 2 | platform.workstation | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.device_heartbeat | tenant | 2 | none |  | 1 | 0 | platform.device | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.dsar_request | tenant | 7 | none |  | 0 | 1 | approvals.request, platform.guest_link | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.guest_link | tenant | 5 | none |  | 0 | 0 |  | referenced by marketing.guest_profile | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.idempotency_record | tenant | 11 | scope_path |  | 0 | 9 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outbox | tenant | 15 | scope_path | yes | 0 | 42 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outlet | tenant | 9 | venue_id |  | 10 | 2 | inventory.location, ledger.cost_center, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.region_settings | tenant | 12 | none |  | 4 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board | tenant | 6 | venue_id |  | 3 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board_page | tenant | 4 | none |  | 1 | 2 | platform.sale_board | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board_tile | tenant | 2 | none |  | 1 | 2 | platform.sale_board_page | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.scope | tenant | 8 | none |  | 9 | 2 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.tenant | tenant | 2 | none |  | 0 | 0 | platform.scope | referenced by whitelabel.tenant_config | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.venue_settings | tenant | 29 | venue_id |  | 4 | 1 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.workstation | tenant | 17 | scope_path |  | 7 | 1 | access.access_point, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-SEATING | seating.seat | tenant | 11 | none |  | 1 | 0 | seating.seat_map | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_block | tenant | 10 | scope_path |  | 0 | 0 | catalogue.performance, identity.principal | referenced by seating.seat_hold | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_category | tenant | 7 | venue_id |  | 2 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_hold | tenant | 12 | none |  | 5 | 3 | catalogue.performance, identity.principal, pii.subject, seating.seat_block | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_map | tenant | 12 | venue_id |  | 0 | 0 | platform.scope | referenced by seating.seat | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_price_band | tenant | 10 | none |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-MAINTENANCE | maintenance.asset | tenant | 30 | venue_id |  | 0 | 0 | access.access_point, inventory.supplier, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.incident | tenant | 26 | venue_id |  | 0 | 0 | identity.principal, maintenance.asset, maintenance.work_order, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection | tenant | 14 | venue_id |  | 0 | 0 | identity.principal, maintenance.asset, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection_template | tenant | 9 | venue_id |  | 2 | 1 | platform.scope | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection_template_item | tenant | 11 | none |  | 1 | 1 | maintenance.inspection_template | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.work_order | tenant | 56 | venue_id |  | 2 | 0 | identity.principal, maintenance.asset, maintenance.incident, maintenance.inspection, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-WALLET | wallet.accounting_mapping | tenant | 3 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.adjustment | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.authentication_policy | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.auto_reload_setting | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.balance | tenant | 9 | none |  | 5 | 3 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.channel_rules | tenant | 10 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.configuration_version | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.configuration_version_snapshot | tenant | 6 | scope_path |  | 1 | 1 | wallet.configuration_version | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.consumption_policy | tenant | 7 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.credit_lot | tenant | 12 | scope_path |  | 5 | 1 | wallet.wallet | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.credit_type | tenant | 15 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.exit_settlement | tenant | 13 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.funding_rules | tenant | 11 | scope_path |  | 3 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.gift_card | tenant | 11 | none |  | 1 | 0 | pii.subject | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.hold | tenant | 12 | none |  | 3 | 3 | orders.sales_order | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.integration_mapping | tenant | 5 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.reconciliation_source | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.refund_policy | tenant | 7 | scope_path |  | 4 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.risk_rules | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.transfer_rules | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet | tenant | 9 | none |  | 9 | 3 | pii.subject | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet_transaction | tenant | 12 | venue_id |  | 2 | 6 | identity.principal, orders.sales_order, platform.scope, wallet.hold, wallet.wallet | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet_type | tenant | 24 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-CATALOGUE | catalogue.alternative_code | tenant | 7 | none |  | 2 | 1 | catalogue.product, catalogue.variant | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.audit_entry | tenant | 28 | scope_path |  | 0 | 10 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.channel_allocation | tenant | 19 | none |  | 1 | 1 | catalogue.channel_capacity | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.channel_capacity | tenant | 12 | none |  | 10 | 6 | catalogue.performance, seating.seat_category | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.dynamic_pricing_control | tenant | 39 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.dynamic_pricing_strategy | tenant | 26 | scope_path |  | 3 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.entitlement_template | tenant | 32 | scope_path |  | 8 | 1 | access.admission_rules | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event | tenant | 8 | scope_path |  | 9 | 4 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_capacity_profile | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_registration | tenant | 7 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_resource_plan | tenant | 4 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_schedule | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.group_package | tenant | 11 | scope_path |  | 4 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.import_job | tenant | 25 | scope_path |  | 2 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.inventory_hold | tenant | 18 | none |  | 10 | 11 | catalogue.channel_capacity, identity.principal, platform.workstation | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.performance | tenant | 11 | none |  | 13 | 3 | access.admission_rules, catalogue.event, seating.seat_map | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price | tenant | 5 | none |  | 2 | 1 | catalogue.price_list, catalogue.variant, ledger.tax_code | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_category | tenant | 16 | scope_path |  | 3 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_list | tenant | 28 | venue_id |  | 11 | 6 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_resolution_policy | tenant | 11 | scope_path |  | 3 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.pricing_test_case | tenant | 14 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product | tenant | 41 | scope_path |  | 32 | 5 | catalogue.entitlement_template, platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_category | tenant | 12 | scope_path |  | 6 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_eligibility_rule | tenant | 15 | scope_path |  | 8 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_media | tenant | 6 | none |  | 5 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_version | tenant | 9 | none |  | 0 | 1 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.published_bundle | tenant | 10 | venue_id |  | 3 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.rate | tenant | 17 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.rounding_profile | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.variant | tenant | 9 | none |  | 8 | 3 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.waitlist_entry | tenant | 11 | none |  | 2 | 2 | catalogue.performance, catalogue.variant, pii.subject | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-LEDGER | ledger.account | tenant | 15 | none |  | 3 | 2 | ledger.legal_entity | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.cost_center | tenant | 6 | venue_id |  | 0 | 0 | platform.scope | referenced by ledger.event_budget | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.credit_memo | tenant | 21 | scope_path |  | 5 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.credit_memo_line | tenant | 10 | none |  | 3 | 1 | ledger.credit_memo | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.einvoice_transmission | tenant | 17 | scope_path |  | 3 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.einvoicing_provider | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.event_budget | tenant | 8 | none |  | 1 | 0 | catalogue.event, ledger.cost_center | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fiscal_period | tenant | 9 | none |  | 1 | 0 | identity.principal, ledger.legal_entity | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fx_provider_assignment | tenant | 6 | scope_path |  | 1 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fx_rate | tenant | 13 | none |  | 7 | 2 | platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.journal_entry | tenant | 20 | none |  | 0 | 4 | identity.principal, ledger.fiscal_period | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.journal_line | tenant | 9 | venue_id | yes | 0 | 2 | ledger.journal_entry, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.legal_entity | tenant | 11 | scope_path |  | 3 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.posting | tenant | 12 | venue_id |  | 2 | 2 | ledger.account, ledger.cost_center, ledger.journal_entry, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.price_variance | tenant | 15 | venue_id |  | 0 | 1 | catalogue.variant, identity.principal, ledger.journal_entry, orders.order_line, orders.sales_order, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_code | tenant | 12 | none |  | 3 | 2 | ledger.account | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice | tenant | 32 | scope_path |  | 6 | 2 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice_line | tenant | 16 | none |  | 6 | 2 | ledger.tax_invoice | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice_template | tenant | 18 | scope_path |  | 2 | 2 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-INVENTORY | inventory.goods_receipt | tenant | 11 | none |  | 3 | 2 | identity.principal, inventory.purchase_order, ledger.journal_entry | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.goods_receipt_line | tenant | 11 | none |  | 2 | 2 | inventory.goods_receipt, inventory.item | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.item | tenant | 26 | venue_id |  | 5 | 3 | inventory.supplier, platform.scope | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.kit_component | tenant | 6 | scope_path |  | 3 | 1 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.location | tenant | 7 | venue_id |  | 0 | 0 | platform.scope | referenced by inventory.stock_batch | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.movement | tenant | 17 | none |  | 2 | 3 | identity.principal, inventory.item, ledger.cost_center, ledger.journal_entry | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.purchase_order | tenant | 29 | scope_path |  | 0 | 0 | identity.principal, inventory.requisition, inventory.supplier, platform.scope | referenced by inventory.goods_receipt | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.requisition | tenant | 20 | venue_id |  | 0 | 0 | identity.principal, platform.scope | referenced by inventory.purchase_order | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.serialised_item | tenant | 9 | none |  | 1 | 0 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.stock_batch | tenant | 10 | none |  | 2 | 0 | inventory.item, inventory.location, inventory.supplier | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.supplier | tenant | 16 | scope_path |  | 0 | 0 | ledger.account | referenced by maintenance.asset | InventoryService | backend/tenant/010-inventory.sql
MIG-PROMOTIONS | promotions.allocation_component | tenant | 9 | venue_id |  | 3 | 2 | ledger.account, ledger.legal_entity, platform.scope, promotions.allocation_split | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.allocation_split | tenant | 4 | none |  | 0 | 0 | promotions.bundle | referenced by promotions.allocation_component | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle | tenant | 20 | venue_id |  | 9 | 3 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_choice_group | tenant | 6 | none |  | 4 | 2 | promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_choice_option | tenant | 5 | none |  | 4 | 2 | promotions.bundle_choice_group | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_component | tenant | 13 | venue_id |  | 4 | 3 | platform.scope, promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.campaign | tenant | 9 | venue_id |  | 5 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.campaign_budget | tenant | 13 | none |  | 3 | 1 | promotions.campaign | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_campaign | tenant | 14 | venue_id |  | 5 | 2 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_code | tenant | 15 | scope_path |  | 4 | 3 | orders.sales_order, pii.subject | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_code_batch | tenant | 11 | none |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion | tenant | 24 | venue_id |  | 21 | 8 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_audit | tenant | 14 | venue_id |  | 0 | 22 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_channel_publication | tenant | 9 | venue_id |  | 2 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_evaluation_trace | tenant | 9 | venue_id |  | 0 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_rule | tenant | 13 | venue_id |  | 3 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_variant | tenant | 5 | none |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-ORDERS | orders.cart | tenant | 18 | venue_id |  | 11 | 8 | pii.subject, platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cart_line | tenant | 21 | none |  | 10 | 6 | catalogue.inventory_hold, catalogue.performance, catalogue.variant, orders.cart | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cash_count_line | tenant | 11 | none |  | 5 | 4 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cash_movement | tenant | 13 | none |  | 3 | 4 | identity.principal, orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box | tenant | 15 | venue_id |  | 5 | 4 | identity.principal, orders.pos_shift, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box_foreign_holding | tenant | 7 | none |  | 5 | 1 | orders.deposit_box | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box_opening_denomination | tenant | 4 | none |  | 5 | 1 | orders.deposit_box | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.fraud_rule | tenant | 12 | scope_path |  | 3 | 0 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_booking | tenant | 21 | none |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.invitation | tenant | 12 | none |  | 1 | 0 | catalogue.performance, catalogue.product, ledger.cost_center | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.no_sale_event | tenant | 8 | none |  | 1 | 1 | identity.principal, orders.pos_shift, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_event | tenant | 16 | scope_path |  | 0 | 11 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line | tenant | 23 | venue_id |  | 15 | 9 | catalogue.inventory_hold, catalogue.performance, catalogue.variant, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line_discount | tenant | 6 | none |  | 11 | 2 | orders.order_line, promotions.promotion | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line_eligibility | tenant | 7 | none |  | 11 | 1 | orders.order_line | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.payment | tenant | 18 | none |  | 22 | 15 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.payment_link | tenant | 14 | scope_path |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift | tenant | 24 | scope_path |  | 10 | 7 | identity.principal, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift_approval | tenant | 6 | none |  | 10 | 0 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift_incident | tenant | 6 | none |  | 10 | 0 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund | tenant | 18 | none |  | 4 | 3 | identity.principal, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund_policy | tenant | 8 | venue_id |  | 2 | 1 | platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund_policy_time_band | tenant | 4 | none |  | 1 | 1 | orders.refund_policy | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.resale_listing | tenant | 16 | scope_path |  | 1 | 1 | access.entitlement | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.reservation | tenant | 7 | venue_id |  | 5 | 2 | orders.sales_order, platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.reservation_line | tenant | 14 | none |  | 2 | 0 | orders.reservation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.sales_order | tenant | 20 | scope_path |  | 32 | 15 | identity.principal, orders.pos_shift, pii.subject, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.stored_value_authorisation | tenant | 9 | scope_path |  | 0 | 1 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_template | tenant | 10 | none |  | 3 | 2 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_template_channel | tenant | 3 | none |  | 2 | 0 | orders.ticket_template | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_transfer | tenant | 12 | none |  | 2 | 2 | orders.sales_order, pii.subject | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.visit_reminder | tenant | 7 | scope_path |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.wallet_pass | tenant | 9 | scope_path |  | 1 | 1 | access.entitlement | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ACCESS | access.access_attribute | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_device | tenant | 30 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_incident | tenant | 12 | scope_path |  | 0 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_point | tenant | 17 | scope_path |  | 11 | 5 | platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_point_group | tenant | 8 | scope_path |  | 4 | 2 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.accreditation_credential | tenant | 12 | scope_path |  | 1 | 0 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.admission_rules | tenant | 21 | scope_path |  | 5 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.biometric_audit_event | tenant | 18 | scope_path |  | 0 | 2 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.biometric_profile | tenant | 37 | scope_path |  | 6 | 4 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.blacklist | tenant | 10 | scope_path |  | 3 | 1 | identity.principal | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.configuration_change | tenant | 11 | scope_path |  | 0 | 22 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.credential_policy | tenant | 32 | scope_path |  | 4 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.device_binding | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.dynamic_policy | tenant | 20 | scope_path |  | 5 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.dynamic_policy_version | tenant | 10 | scope_path |  | 1 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.entitlement | tenant | 26 | scope_path |  | 19 | 7 | catalogue.product, orders.sales_order, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.entry_rule_point | tenant | 5 | none |  | 1 | 1 | access.admission_rules | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.face_reenrolment_attempt | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.gate_mode_change | tenant | 11 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.gate_mode_policy | tenant | 12 | scope_path |  | 3 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.parking_entitlement | tenant | 12 | none |  | 1 | 1 | access.parking_facility, orders.sales_order, pii.subject | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.parking_facility | tenant | 13 | venue_id |  | 2 | 1 | platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.scan_event | tenant | 22 | scope_path | yes | 3 | 1 | access.access_point, access.entitlement, identity.principal, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-MARKETING | marketing.agent_availability | tenant | 7 | none |  | 2 | 1 | identity.principal | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.attribution_touch | tenant | 8 | none |  | 2 | 0 | marketing.campaign, marketing.journey, orders.sales_order, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.booking_consent_record | tenant | 20 | scope_path |  | 2 | 0 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign | tenant | 22 | venue_id |  | 5 | 4 | identity.principal, marketing.segment, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign_target | tenant | 7 | none |  | 0 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign_variant | tenant | 10 | scope_path |  | 4 | 1 | marketing.campaign | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.case | tenant | 23 | venue_id |  | 6 | 2 | identity.principal, orders.sales_order, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.case_message | tenant | 11 | none |  | 1 | 1 | identity.principal, marketing.case | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.challenge | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.challenge_progress | tenant | 9 | none |  | 1 | 0 | marketing.challenge, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_propagation | tenant | 9 | none |  | 0 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_purpose | tenant | 8 | none |  | 3 | 1 | platform.tenant | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_purpose_channel | tenant | 3 | none |  | 2 | 1 | marketing.consent_purpose | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_question | tenant | 11 | scope_path |  | 12 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_question_version | tenant | 6 | none |  | 11 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_record | tenant | 11 | none |  | 8 | 5 | identity.principal, orders.sales_order, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation | tenant | 21 | venue_id |  | 2 | 2 | identity.principal, marketing.case, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation_message | tenant | 8 | none |  | 2 | 1 | ai.activity, marketing.conversation | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation_message_attachment | tenant | 4 | none |  | 2 | 1 | marketing.conversation_message | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.cookie_banner_design | tenant | 18 | scope_path |  | 3 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.device_consent | tenant | 16 | scope_path |  | 4 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.device_consent_category | tenant | 4 | none |  | 4 | 1 | marketing.device_consent | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_definition | tenant | 15 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_definition_field | tenant | 23 | scope_path |  | 1 | 1 | marketing.form_definition | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_submission | tenant | 12 | none |  | 2 | 0 | pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_device | tenant | 14 | none |  | 2 | 1 | pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_document | tenant | 9 | none |  | 2 | 1 | marketing.consent_purpose, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_preference | tenant | 7 | none |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_profile | tenant | 23 | none |  | 12 | 5 | marketing.loyalty_position, marketing.segment, pii.subject, platform.guest_link | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.invitation | tenant | 13 | scope_path |  | 1 | 1 | catalogue.performance, catalogue.product, ledger.cost_center | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.invitation_campaign | tenant | 11 | scope_path |  | 2 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.journey | tenant | 9 | scope_path |  | 0 | 0 |  | referenced by marketing.attribution_touch | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_position | tenant | 12 | none |  | 5 | 1 | marketing.loyalty_programme, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_programme | tenant | 7 | venue_id |  | 5 | 1 | ledger.account, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_rule | tenant | 9 | none |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_dispatch | tenant | 18 | none | yes | 2 | 5 | marketing.campaign, marketing.campaign_variant, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_template | tenant | 12 | none |  | 3 | 1 | platform.tenant | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_template_version | tenant | 16 | none |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.points_earning_rule | tenant | 6 | none |  | 2 | 1 | marketing.loyalty_programme | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.points_redemption_rule | tenant | 13 | none |  | 1 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.privacy_notice_governance | tenant | 14 | scope_path |  | 0 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.programme_tier | tenant | 11 | none |  | 3 | 2 | marketing.loyalty_programme | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.referral | tenant | 10 | scope_path |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.review | tenant | 13 | venue_id |  | 1 | 1 | identity.principal, marketing.case, orders.sales_order, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.segment | tenant | 9 | venue_id |  | 3 | 1 | platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.segment_criterion | tenant | 6 | none |  | 4 | 4 | marketing.segment | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.subscription | tenant | 8 | none |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.tracking_technology | tenant | 23 | scope_path |  | 4 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.wishlist_item | tenant | 12 | none |  | 2 | 1 | catalogue.performance, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-FNB | fnb.cold_chain_event | tenant | 9 | none |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.corrective_action | tenant | 13 | scope_path |  | 4 | 4 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.course_rule | tenant | 7 | scope_path |  | 1 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_location | tenant | 11 | venue_id |  | 6 | 2 | fnb.dining_table, platform.scope, seating.seat | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_location_outlet | tenant | 3 | none |  | 2 | 2 | fnb.delivery_location, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_policy | tenant | 16 | scope_path |  | 4 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.dining_table | tenant | 8 | none |  | 10 | 3 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_exception | tenant | 9 | none |  | 1 | 2 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_station | tenant | 8 | none |  | 6 | 2 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_ticket | tenant | 15 | none |  | 18 | 9 | identity.principal, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_ticket_line | tenant | 14 | none |  | 15 | 2 | fnb.kitchen_station, fnb.kitchen_ticket | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.location_session | tenant | 10 | venue_id |  | 2 | 1 | fnb.delivery_location, fnb.table_visit, pii.subject, platform.outlet, platform.scope | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu | tenant | 8 | none |  | 6 | 3 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_item | tenant | 15 | none |  | 13 | 5 | catalogue.variant, fnb.kitchen_station | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_item_modifier | tenant | 5 | none |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_section | tenant | 5 | none |  | 5 | 3 | fnb.menu | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.modifier_group | tenant | 6 | scope_path |  | 4 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.modifier_option | tenant | 7 | none |  | 3 | 1 | fnb.modifier_group | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.order_fulfilment | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_plan | tenant | 6 | none |  | 3 | 2 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_plan_line | tenant | 7 | none |  | 2 | 1 | fnb.production_plan | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_run | tenant | 11 | none |  | 0 | 1 | fnb.recipe | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.recipe | tenant | 4 | none |  | 2 | 1 | fnb.menu_item | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.recipe_ingredient | tenant | 6 | none |  | 1 | 1 | fnb.recipe, inventory.item | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.reservation_table | tenant | 4 | none |  | 4 | 2 | fnb.dining_table | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.service_order | tenant | 15 | none |  | 12 | 7 | fnb.kitchen_ticket, fnb.table_visit, orders.sales_order, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.service_order_line | tenant | 12 | none |  | 8 | 1 | access.entitlement, fnb.service_order | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.sold_out_item | tenant | 9 | none |  | 1 | 0 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_combination | tenant | 6 | scope_path |  | 1 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_reservation | tenant | 21 | none |  | 4 | 3 | fnb.table_visit, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_session | tenant | 9 | none |  | 2 | 2 | fnb.dining_table, fnb.table_visit, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_visit | tenant | 14 | none |  | 5 | 5 | fnb.dining_table, identity.principal, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.temperature_log | tenant | 11 | none |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.waitlist_entry | tenant | 11 | none |  | 2 | 1 | pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-PAYMENTS | payments.dunning_case | tenant | 14 | scope_path |  | 4 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.instalment | tenant | 9 | none |  | 2 | 1 | payments.instalment_plan | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.instalment_plan | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.instalment_policy | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.method | tenant | 16 | scope_path |  | 0 | 0 |  | referenced by payments.payment_attempt | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.payment_attempt | tenant | 19 | scope_path |  | 0 | 2 | orders.payment, orders.sales_order, payments.method, payments.provider_connection | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.provider | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.provider_connection | tenant | 11 | scope_path |  | 3 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.routing_rule | tenant | 9 | scope_path |  | 0 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.stored_forward | tenant | 9 | scope_path |  | 2 | 0 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.token | tenant | 9 | none |  | 4 | 1 | marketing.consent_purpose, pii.subject | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-QUEUE | queue.entry | tenant | 22 | none |  | 5 | 2 | access.entitlement, pii.subject, queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.feed | tenant | 7 | none |  | 2 | 1 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.queue | tenant | 40 | venue_id |  | 7 | 2 | access.access_point, catalogue.product, maintenance.asset, platform.scope, queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.queue_operating_window | tenant | 4 | none |  | 4 | 1 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.reading | tenant | 8 | none |  | 5 | 0 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-RETAIL | retail.merchandise | tenant | 16 | none |  | 5 | 2 | catalogue.variant, inventory.item, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.reservation | tenant | 8 | none |  | 1 | 1 | pii.subject, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.reservation_line | tenant | 5 | none |  | 1 | 1 | retail.merchandise, retail.reservation | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return | tenant | 14 | none |  | 1 | 1 | identity.principal, orders.refund, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return_line | tenant | 9 | none |  | 1 | 1 | retail.merchandise, retail.return | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return_policy | tenant | 10 | none |  | 2 | 1 | platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.sale | tenant | 13 | none |  | 5 | 2 | orders.pos_shift, orders.sales_order, pii.subject, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.sale_line | tenant | 13 | none |  | 4 | 1 | retail.merchandise, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.shop_and_drop | tenant | 15 | venue_id |  | 1 | 0 | access.entitlement, fnb.delivery_location, identity.principal, pii.subject, platform.scope, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.shop_and_drop_line | tenant | 7 | none |  | 1 | 0 | retail.merchandise, retail.shop_and_drop | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-VENUEMAP | venuemap.import_job | tenant | 11 | none |  | 2 | 1 | venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.map | tenant | 15 | scope_path |  | 9 | 2 | assets.media_asset, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.map_version | tenant | 7 | none |  | 2 | 0 |  | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.path | tenant | 10 | none |  | 6 | 1 | venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.placed_resource | tenant | 11 | none |  | 4 | 1 | catalogue.variant, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.point | tenant | 21 | none |  | 9 | 2 | access.access_point, catalogue.product, platform.outlet, venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan | tenant | 13 | scope_path |  | 6 | 3 | marketing.guest_profile, orders.cart | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan_item | tenant | 18 | none |  | 6 | 2 | catalogue.performance, catalogue.product, promotions.bundle, venuemap.point, venuemap.visit_plan | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql

## Services
Service | Owner | Tier | Operations in release | All operations | Tables it owns in release | Points | If down
AccessService | Hrushikant Patkar | commerce | 38 | 246 | 23 | 74 | Down means the gates stop. Runs at the edge with a local decision cache.
AiService | Pranay Shinde | engagement | 50 | 141 | 46 | 92 | Down degrades suggestions and the concierge. Nothing that takes money depends on it.
CatalogueService | Tanmay Dukhande | commerce | 91 | 445 | 57 | 172 | A bad publish reaches every workstation. Versioned and rollback-able for that reason.
FnbService | Hrushikant Patkar | operations | 67 | 120 | 34 | 129 | Down means the kitchen falls back to paper. Offline-capable by design.
IdentityService | Tanmay Dukhande | foundation | 37 | 89 | 18 | 57 | A restart is an outage everywhere. Deploys go out first and alone.
InventoryService | Hrushikant Patkar | operations | 7 | 58 | 11 | 13 | Down blocks receiving and counting; selling continues from the till's cache.
LedgerService | Tanmay Dukhande | commerce | 18 | 72 | 19 | 31 | Correctness over availability. A ledger that is briefly unavailable is recoverable; one that is briefly wrong is not.
MarketingService | Pranay Shinde | engagement | 60 | 264 | 49 | 105 | Down stops campaigns and guest lookup. Neither stops trading.
OrderService | Pranay Shinde | commerce | 83 | 288 | 44 | 177 | Down means no sales. Highest availability target in the platform.
PlatformService | Hrushikant Patkar | platform | 18 | 212 | 21 | 33 | Down blocks provisioning and the developer API. Trading is unaffected.
ReportingService | Hrushikant Patkar | platform | 17 | 48 | 15 | 35 | Down stops dashboards. Nothing operational depends on it.
RetailService | Pranay Shinde | operations | 14 | 25 | 10 | 24 | Down means the shop stops; the gates and the restaurant do not.
TenancyService | Tanmay Dukhande | foundation | 28 | 204 | 25 | 56 | Same as identity — nothing runs without a scope.
VenueOpsService | Hrushikant Patkar | operations | 74 | 285 | 47 | 131 | Down degrades venue operations. Selling and admitting continue.
WalletService | Pranay Shinde | commerce | 17 | 66 | 23 | 34 | It holds a liability owed to a customer. A wallet that double-spends is a financial loss, not a bug report. Deduction order across credit lots is FEFO and is decided here, once, rather than per caller.
WhiteLabelService | Tanmay Dukhande | platform | 78 | 79 | 25 | 122 | Down freezes the current published config. Guests see the last good version.

## APIs
Service | Group | Operation | Method | Path | Request schema | Response schema | Permission | Part | Wave | Task | Reads | Writes | Summary
AccessService | access | approveManualOverrideSupervisor | PUT | /manual-override-supervisor | ManualOverrideSupervisorApprovalInput | ManualOverrideSupervisorApprovalView | ACCESS_OVERRIDE | setup | 1 | SVC-ACCESS-ACCESS-1 | access.access_point, access.scan_event, cache:idempotency, identity.principal | access.scan_event, cache:idempotency | Manual Override & Supervisor Approval
AccessService | access | bindCredentialDevice | POST | /my/credentials/{credentialId}/device-bindings | CredentialDeviceBindingInput | AccessDeviceBinding |  | core | 1 | SVC-ACCESS-ACCESS-1 | access.credential_policy, access.device_binding, access.entitlement, cache:idempotency | access.device_binding, cache:idempotency | Bind my credential to this device
AccessService | access | deleteAccessPointGroup | DELETE | /access-point-groups/{groupId} |  |  | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-1 | access.access_point_group, access.gate_mode_policy, cache:idempotency | access.access_point_group, access.configuration_change, cache:idempotency | Delete an access-point group
AccessService | access | enrolFacePass | POST | /face-pass/enrolments |  | FacePassEnrolment | GUEST_MANAGE | core | 2 | SVC-ACCESS-ACCESS-1 | access.biometric_profile, access.face_reenrolment_attempt, cache:idempotency, marketing.consent_record, pii.subject, pii.subject_biometric | access.biometric_audit_event, access.face_reenrolment_attempt, cache:idempotency, marketing.consent_record, pii.subject_biometric | Register a facial profile against an entitlement
AccessService | access | enrolFaceTag | POST | /face-tag/enrolments |  | FacePassEnrolment | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-2 | access.biometric_profile, cache:idempotency, pii.subject_biometric | cache:idempotency, pii.subject_biometric | Capture a same-visit facial model, deleted when the ticket is fully redeemed
AccessService | access | getEntitlement | GET | /entitlements/{entitlementId} |  | Entitlement | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement, catalogue.entitlement_template, identity.delegated_access |  | One entitlement, with what remains on it
AccessService | access | getEntitlementCredential | GET | /entitlements/{entitlementId}/credential |  | object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement | access.entitlement | The thing that gets scanned
AccessService | access | getEntitlementHistory | GET | /entitlements/{entitlementId}/history |  | array of object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement, access.scan_event |  | Every scan, freeze, share and reissue against it
AccessService | access | getFacePassEnrolment | GET | /face-pass/enrolments/{enrolmentId} |  | FacePassEnrolment | GUEST_VIEW | core | 2 | SVC-ACCESS-ACCESS-3 | pii.subject_biometric |  | Whether a pass has a face registered, and when
AccessService | access | listEntitlements | GET | /my/entitlements/all |  | object |  | core | 1 | SVC-ACCESS-ACCESS-3 | access.admission_rules, access.entitlement, catalogue.product |  | Every entitlement this guest holds, including expired
AccessService | access | listMyEntitlements | GET | /guests/me/entitlements |  | object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-3 | access.entitlement, catalogue.entitlement_template, catalogue.product, identity.delegated_access |  | Every ticket, pass and membership this guest holds
AccessService | access | listParkingFacilities | GET | /parking-facilities |  | object | PARKING_CONFIGURE | core | 2 | SVC-ACCESS-ACCESS-3 | access.parking_facility |  | Car parks at a venue, and how each integrates
AccessService | access | revokeFacePass | DELETE | /face-pass/enrolments/{enrolmentId} |  |  | GUEST_MANAGE | core | 2 | SVC-ACCESS-ACCESS-4 | cache:idempotency, pii.subject_biometric | access.biometric_audit_event, cache:idempotency, pii.subject_biometric | Remove a facial profile
AccessService | access | rollbackAccessPolicy | POST | /dynamic-access-policy/{policyId}/rollback |  | DynamicAccessPolicyCommandCenterView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.dynamic_policy, access.dynamic_policy_version, cache:idempotency | access.configuration_change, access.dynamic_policy, access.dynamic_policy_version, cache:idempotency | Put a previous policy version back
AccessService | access | setAccessAttributeCatalog | PUT | /access-attribute-catalog | AccessAttributeCatalogInput | AccessAttributeCatalogView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_attribute, access.dynamic_policy, cache:idempotency | access.access_attribute, access.configuration_change, cache:idempotency | Add or amend an access attribute
AccessService | access | setAccessPointGroup | PUT | /access-point-groups | AccessAccessPointGroup | AccessAccessPointGroup | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.access_point_group, cache:idempotency | access.access_point_group, access.configuration_change, cache:idempotency | Create or replace an access-point group
AccessService | access | setBiometricVerificationProfile | PUT | /biometric-verification-profile | BiometricVerificationProfileBuilderInput | BiometricVerificationProfileBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.access_point, access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Biometric Verification Profile Builder
AccessService | access | setBleBeaconGeofence | PUT | /ble-beacon-geofence | BleBeaconGeofenceConfigurationInput | BleBeaconGeofenceConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.access_device, access.access_point, cache:idempotency | access.access_device, access.access_point, access.configuration_change, cache:idempotency | BLE Beacon & Geofence Configuration
AccessService | access | setContextTimeEvent | PUT | /context-time-event | ContextTimeEventCapacityPolicyBuilderInput | ContextTimeEventCapacityPolicyBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.dynamic_policy, cache:idempotency | access.configuration_change, access.dynamic_policy, access.dynamic_policy_version, cache:idempotency | Context, Time, Event & Capacity Policy Builder
AccessService | access | setCredentialActivationDisplay | PUT | /credential-activation-display | CredentialActivationDisplayRulesInput | CredentialActivationDisplayRulesView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Save a credential activation and display rule
AccessService | access | setDeviceBindingPolicy | PUT | /device-binding-policy | DeviceBindingPolicyInput | AccessCredentialPolicy | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Set the device binding policy of a venue
AccessService | access | setFaceMatchingVerification | PUT | /face-matching-verification | FaceMatchingVerificationThresholdsInput | FaceMatchingVerificationThresholdsView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Save face matching and verification thresholds
AccessService | access | setFacePassEnrollment | PUT | /face-pass-enrollment | FacePassEnrollmentConfigurationInput | FacePassEnrollmentConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Face Pass Enrollment Configuration
AccessService | access | setFaceTagTemporaryEnrollment | PUT | /face-tag-temporary | FaceTagTemporaryEnrollmentInput | FaceTagTemporaryEnrollmentView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Save a Face Tag profile
AccessService | access | setGateModePolicy | PUT | /gate-mode-policies | AccessGateModePolicy | AccessGateModePolicy | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-7 | access.access_point_group, access.gate_mode_policy, cache:idempotency | access.configuration_change, access.gate_mode_policy, cache:idempotency | Set a policy for a non-standard gate mode
AccessService | access | setParkingFacility | PUT | /parking-facilities | ParkingFacility | ParkingFacility | PARKING_CONFIGURE | setup | 2 | SVC-ACCESS-ACCESS-7 | access.parking_facility, cache:idempotency | access.configuration_change, access.parking_facility, cache:idempotency | Configure a car park and its integration
AccessService | access | setVirtualTicketIdentity | PUT | /virtual-ticket-identity | VirtualTicketIdentityMasterRecordConfigurationInput | VirtualTicketIdentityMasterRecordConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-7 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Virtual Ticket Identity & Master Record Configuration
AccessService | access | setVisualAccessRule | PUT | /visual-access-rule | VisualAccessRuleBuilderInput | VisualAccessRuleBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-7 | access.admission_rules, access.entry_rule_point, cache:idempotency | access.admission_rules, access.configuration_change, access.entry_rule_point, cache:idempotency | Visual Access Rule Builder
AccessService | access | setVisualDynamicPolicy | PUT | /visual-dynamic-policy | VisualDynamicPolicyBuilderInput | VisualDynamicPolicyBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-8 | access.access_attribute, access.dynamic_policy, cache:idempotency | access.configuration_change, access.dynamic_policy, access.dynamic_policy_version, cache:idempotency | Visual Dynamic Policy Builder
AccessService | access | updateParkingEntitlement | PATCH | /parking-entitlements/{entitlementId} | UpdateParkingEntitlementRequest | ParkingEntitlement |  | core | 2 | SVC-ACCESS-ACCESS-8 | access.parking_entitlement, cache:idempotency | access.parking_entitlement, cache:idempotency | Change the plate, or revoke
AccessService | accessPoint | addBlacklistEntry | POST | /blacklist |  | BlacklistEntry | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.blacklist, cache:idempotency | access.blacklist, cache:idempotency | Blacklist a media code
AccessService | accessPoint | createAccessPoint | POST | /access-points | CreateAccessPointRequest | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Create an access point
AccessService | accessPoint | createAdmissionRules | POST | /admission-rules | AdmissionRules | AdmissionRules | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.admission_rules, cache:idempotency | access.admission_rules, access.configuration_change, cache:idempotency | Create an admission profile
AccessService | accessPoint | setAccessPointGeofence | PUT | /access-points/{accessPointId}/geofence | AccessPointGeofence | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Set a geofence for handheld validation
AccessService | accessPoint | setTurnstileMode | PUT | /access-points/{accessPointId}/mode |  | AccessPoint | TURNSTILE_MODE_SET | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, access.access_point_group, access.gate_mode_change, access.gate_mode_policy, cache:idempotency | access.access_incident, access.access_point, access.gate_mode_change, cache:idempotency | Set the operating mode of an access point
AccessService | accessPoint | updateAccessPoint | PATCH | /access-points/{accessPointId} |  | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Update an access point
AccessService | accessPoint | updateAdmissionRules | PUT | /admission-rules/{profileId} | AdmissionRules | AdmissionRules | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.admission_rules, cache:idempotency | access.admission_rules, access.configuration_change, cache:idempotency | Update an admission profile
AccessService | sync | getOfflinePackage | GET | /access/offline-package |  | OfflinePackage | ACCESS_VALIDATE | core | 1 | SVC-ACCESS-SYNC-1 | access.access_point, access.accreditation_credential, access.admission_rules, access.blacklist, access.dynamic_policy, access.entitlement |  | Entitlement and rule set for offline validation
AiService | ai | proposeTranslations | POST | /ai/translate |  | TranslationProposals | TENANT_CONFIGURE | core | 1 | SVC-AI-AI-1 | ai.policy, ai.provider, cache:idempotency, control.content_block, marketing.message_template, marketing.message_template_version | ai.activity, ai.proposed_action, cache:idempotency | Fill translation gaps with a first pass, for a human to edit
AiService | ai | proposeVenueLabels | POST | /ai/venue-map/{mapId}/propose-labels |  | array of VenueLabelProposal | VENUE_MAP_MANAGE | core | 1 | SVC-AI-AI-1 | ai.policy, ai.provider, cache:idempotency, qdrant:knowledge, venuemap.import_job, venuemap.point | ai.activity, ai.proposed_action, cache:idempotency | Suggest what each extracted shape is
AiService | ai | requestSuggestion | POST | /ai/suggestions |  | Suggestion | AI_USE | core | 1 | SVC-AI-AI-1 | ai.capability_maturity, ai.forecast_point, ai.forecast_version, ai.history_observation, ai.insight, ai.operational_requirement, ai.policy, ai.provider, ai.rec_decline, ai.release, ai.suggestion, ai.venue_settings, cache:idempotency, cache:rec-candidates, fnb.production_plan, inventory.movement, inventory.stock_batch, marketing.attribution_touch, marketing.segment, queue.queue, queue.reading, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | ai.activity, ai.suggestion, cache:idempotency | Ask for an answer, however it is currently produced
AiService | ai | setAiCredential | PUT | /ai-providers/{providerId}/credential |  | AiProvider | AI_CONFIGURE | setup | 1 | SVC-AI-AI-1 | ai.byok_enablement, ai.provider, cache:idempotency | ai.provider, cache:idempotency | Store or rotate a provider key
AiService | ai | setSuggestionProvider | PUT | /ai/suggestion-providers |  | object | AI_CONFIGURE | setup | 1 | SVC-AI-AI-2 | ai.policy, ai.provider, ai.release, cache:idempotency | ai.policy, cache:idempotency, cache:resolution | Point a question at a rule, a model, or both
AiService | assist | createAiConversation | POST | /conversations |  | AiConversation | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.conversation, cache:idempotency | ai.conversation, cache:idempotency | Open a conversation
AiService | assist | listAiConversations | GET | /conversations |  | object | AI_USE | core | 2 | SVC-AI-ASSIST-1 | ai.conversation |  | A principal's conversation history
AiService | assist | sendAiMessage | POST | /conversations/{conversationId}/messages |  | AiMessage | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.assistant_profile, ai.capability, ai.chunk_embedding, ai.conversation, ai.knowledge_document, ai.message, ai.policy, ai.proposed_action, ai.provider, cache:answer, cache:idempotency, qdrant:knowledge | ai.activity, ai.decision_record, ai.knowledge_gap, ai.message, ai.proposed_action, cache:answer, cache:idempotency, qdrant:knowledge | Ask
AiService | config | getAiPolicy | GET | /policy |  | AiPolicy | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.policy |  | What the assistant may do here
AiService | config | setAiByokEnablement | PUT | /tenants/{tenantId}/byok | AiByokEnablement | AiByokEnablement | PLATFORM_AI_MANAGE | setup | 1 | SVC-AI-CONFIG-1 | ai.byok_enablement, cache:idempotency | ai.byok_enablement, cache:idempotency | Enable or disable bring-your-own-key for a tenant (platform)
AiService | config | setAiPolicy | PUT | /policy | AiPolicy | AiPolicy | AI_CONFIGURE | setup | 1 | SVC-AI-CONFIG-1 | ai.policy, cache:idempotency | ai.policy, cache:idempotency | Set the policy
AiService | config | setAiProvider | PUT | /providers | AiProvider | AiProvider | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-AI-CONFIG-1 | ai.byok_enablement, ai.model, ai.provider, cache:idempotency | ai.provider, cache:idempotency | Configure a provider
AiService | configure | getGuidedChoiceSuggestion | GET | /guided-choice-suggestions/{suggestionId} |  | AiGuidedChoiceSuggestion | AI_USE | core | 2 | SVC-AI-CONFIGURE-1 | ai.guided_choice_suggestion |  | The reasons behind a Help me choose suggestion
AiService | configure | suggestGuidedChoice | POST | /venues/{venueId}/guided-choice-suggestions |  | AiGuidedChoiceSuggestion | AI_USE | core | 2 | SVC-AI-CONFIGURE-1 | ai.guided_choice_suggestion, ai.policy, ai.prompt_template, cache:idempotency | ai.activity, ai.decision_record, ai.guided_choice_suggestion, cache:idempotency | Suggest a Help me choose set-up from the venue's catalogue
AiService | forecast | createForecastScenario | POST | /forecast-scenarios | AiForecastScenario | AiForecastScenario | AI_USE | setup | 1 | SVC-AI-FORECAST-1 | ai.forecast_point, ai.forecast_scenario, ai.forecast_version, cache:idempotency | ai.forecast_point, ai.forecast_scenario, cache:idempotency | Run a what-if
AiService | forecast | decideOperationalRequirement | POST | /operational-requirements/{requirementId}/decide |  | AiOperationalRequirement | AI_USE | setup | 1 | SVC-AI-FORECAST-1 | ai.operational_requirement, cache:idempotency | ai.decision_record, ai.operational_requirement, cache:idempotency | Accept, modify or reject a requirement
AiService | forecast | getAiVenueSettings | GET | /venues/{venueId}/ai-settings |  | AiVenueSettings | AI_USE | core | 1 | SVC-AI-FORECAST-1 | ai.venue_settings |  | The venue AI profile the baselines stand on
AiService | forecast | getVenueHistoryImport | GET | /history-imports/{importId} |  | AiHistoryImport | AI_USE | core | 1 | SVC-AI-FORECAST-1 | ai.history_import |  | One history import, with its findings
AiService | forecast | importVenueHistory | POST | /venues/{venueId}/history-imports |  | AiHistoryImport | AI_CONFIGURE | core | 1 | SVC-AI-FORECAST-2 | ai.history_import, assets.media_asset, cache:idempotency | ai.history_import, ai.history_observation, cache:idempotency | Import the venue's own historical exports for the AI baselines
AiService | forecast | listVenueHistoryImports | GET | /venues/{venueId}/history-imports |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.history_import |  | The venue's history imports
AiService | forecast | publishForecastVersion | POST | /forecast-versions/{versionId}/publish |  | AiForecastVersion | AI_APPROVE | setup | 1 | SVC-AI-FORECAST-2 | ai.forecast_definition, ai.forecast_version, cache:idempotency | ai.decision_record, ai.forecast_version, ai.operational_requirement, cache:idempotency | Publish a forecast version
AiService | forecast | runForecast | POST | /forecast-definitions/{definitionKey}/runs |  | AiForecastVersion | AI_CONFIGURE | setup | 1 | SVC-AI-FORECAST-2 | ai.forecast_definition, ai.forecast_version, ai.history_observation, ai.venue_settings, cache:idempotency | ai.forecast_point, ai.forecast_version, cache:idempotency | Run a forecast now
AiService | forecast | setAiVenueSettings | PUT | /venues/{venueId}/ai-settings | AiVenueSettings | AiVenueSettings | AI_CONFIGURE | core | 1 | SVC-AI-FORECAST-3 | ai.venue_settings, cache:idempotency | ai.venue_settings, cache:idempotency | Set the venue AI profile
AiService | generate | proposeMarketingContent | POST | /ai/content-drafts |  | AiContentDraftSet | AI_USE | core | 2 | SVC-AI-GENERATE-1 | ai.capability, ai.governance_policy_version, ai.policy, ai.prompt_template, ai.provider, cache:idempotency, catalogue.event, catalogue.product, control.content_block, marketing.campaign, marketing.message_template, promotions.promotion, whitelabel.banner, whitelabel.content_page, whitelabel.homepage_section, whitelabel.promo_block | ai.activity, ai.decision_record, ai.proposed_action, cache:idempotency | Draft marketing content for a person to edit and apply
AiService | governance | configureAiCapability | PUT | /governance/capabilities/{capabilityKey} | AiCapabilityRegistration | AiCapabilityRegistration | AI_CONFIGURE | setup | 1 | SVC-AI-GOVERNANCE-1 | ai.capability, cache:idempotency | ai.capability, ai.decision_record, cache:idempotency | Register a capability, or change its owner, risk class or autonomy
AiService | governance | createAiGovernancePolicyDraft | POST | /governance/policy-drafts |  | AiGovernancePolicyVersion | AI_CONFIGURE | setup | 2 | SVC-AI-GOVERNANCE-1 | ai.governance_policy, ai.governance_policy_version, cache:idempotency | ai.governance_policy, ai.governance_policy_version, cache:idempotency | Draft a governance policy, or a new version of one
AiService | governance | createAiPolicyException | POST | /governance/policy-exceptions | AiPolicyException | AiPolicyException | AI_APPROVE | setup | 1 | SVC-AI-GOVERNANCE-1 | ai.governance_policy, ai.policy_exception, cache:idempotency | ai.decision_record, ai.policy_exception, cache:idempotency | Grant a temporary exception to a governance policy
AiService | governance | decideProposedAction | POST | /proposed-actions/{actionId}/decide |  | ProposedAction | AI_USE | core | 2 | SVC-AI-GOVERNANCE-1 | ai.action_plan, ai.proposed_action, cache:idempotency | ai.action_plan, ai.activity, ai.decision_record, ai.proposed_action, cache:idempotency | Approve or reject a proposal
AiService | governance | evaluateAiGovernance | POST | /governance/evaluate |  | AiGovernanceDecision |  | core | 1 | SVC-AI-GOVERNANCE-2 | ai.capability, ai.governance_policy_version, ai.policy, ai.policy_exception, cache:governance-policy, cache:idempotency | ai.decision_record, cache:idempotency | Ask the governance decision point (service callers)
AiService | governance | getAiUsage | GET | /usage |  | AiUsageReport | AI_AUDIT_VIEW | core | 1 | SVC-AI-GOVERNANCE-2 | ai.activity, ai.model |  | Usage, cost and performance
AiService | governance | publishAiGovernancePolicy | POST | /governance/policy-versions/{versionId}/publish |  | AiGovernancePolicyVersion | AI_APPROVE | setup | 2 | SVC-AI-GOVERNANCE-2 | ai.governance_policy_version, cache:idempotency | ai.decision_record, ai.governance_policy, ai.governance_policy_version, cache:governance-policy, cache:idempotency | Publish a simulated policy version
AiService | governance | resumeAiCapability | POST | /governance/capabilities/{capabilityKey}/resume |  | AiCapabilityRegistration | AI_APPROVE | setup | 1 | SVC-AI-GOVERNANCE-2 | ai.capability, cache:idempotency | ai.capability, ai.decision_record, ai.intervention, cache:idempotency | Resume a paused capability
AiService | governance | simulateAiGovernancePolicy | POST | /governance/policy-versions/{versionId}/simulate |  | AiPolicySimulation | AI_CONFIGURE | setup | 2 | SVC-AI-GOVERNANCE-3 | ai.decision_record, ai.governance_policy_version, cache:idempotency | ai.governance_policy_version, cache:idempotency | Test a draft policy before it is published
AiService | insights | decideAiInsight | POST | /insights/{insightId}/decide |  | AiInsight | AI_USE | setup | 1 | SVC-AI-INSIGHTS-1 | ai.insight, cache:idempotency | ai.anomaly_detector, ai.insight, cache:idempotency | Review, accept, reject or mark an insight actioned
AiService | insights | explainMetricChange | POST | /insights/explain-metric-change |  | AiMetricChangeExplanation | AI_USE | setup | 1 | SVC-AI-INSIGHTS-1 | ai.insight, ai.policy, cache:idempotency | ai.activity, ai.insight, cache:idempotency | Why did this metric change
AiService | knowledge | configureAssistantProfile | PUT | /assistant-profiles/{profileKey} | AiAssistantProfile | AiAssistantProfile | AI_CONFIGURE | setup | 1 | SVC-AI-KNOWLEDGE-1 | ai.assistant_profile, ai.policy, cache:idempotency | ai.assistant_profile, cache:idempotency | Define an assistant profile
AiService | knowledge | recordAnswerFeedback | POST | /messages/{messageId}/feedback |  | AiAnswerFeedback | AI_USE | core | 2 | SVC-AI-KNOWLEDGE-1 | ai.answer_feedback, ai.message, cache:idempotency | ai.answer_feedback, ai.knowledge_gap, cache:idempotency | Say whether an answer helped
AiService | models | promoteAiRelease | POST | /releases/{releaseId}/promote |  | AiRelease | AI_APPROVE | setup | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.governance_alert, ai.release, cache:idempotency | ai.decision_record, ai.forecast_definition, ai.governance_alert, ai.policy, ai.release, cache:idempotency | Promote a release to its next stage (a person)
AiService | models | publishPromptTemplate | POST | /prompt-templates/{templateKey}/versions |  | AiPromptTemplate | AI_APPROVE | setup | 1 | SVC-AI-MODELS-1 | ai.prompt_template, cache:idempotency | ai.prompt_template, ai.release, cache:idempotency | Publish a prompt template version
AiService | models | rollbackAiRelease | POST | /releases/{releaseId}/rollback |  | AiRelease | AI_APPROVE | setup | 1 | SVC-AI-MODELS-1 | ai.release, cache:idempotency | ai.decision_record, ai.forecast_definition, ai.policy, ai.release, cache:idempotency | Roll a release back
AiService | models | runAiEvaluation | POST | /evaluations |  | AiEvaluationRun | AI_CONFIGURE | setup | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.eval_suite, ai.release, cache:idempotency | ai.eval_run, ai.release, cache:idempotency | Evaluate a candidate
AiService | models | setAiModel | PUT | /models/{modelId} | AiModel | AiModel | PLATFORM_AI_MANAGE | setup | 1 | SVC-AI-MODELS-2 | ai.model, cache:idempotency | ai.model, cache:idempotency | Add or change a platform model (platform)
AiService | monitoring | containAiIncident | POST | /incidents/{incidentId}/contain |  | AiIncident | AI_APPROVE | setup | 1 | SVC-AI-MONITORING-1 | ai.incident, cache:idempotency | ai.capability, ai.decision_record, ai.incident, ai.intervention, ai.policy_exception, ai.release, cache:idempotency | Contain an incident
AiService | recommend | decideRecommendations | POST | /recommendations/decide |  | AiRecommendationResult | AI_USE | core | 1 | SVC-AI-RECOMMEND-1 | ai.rec_decline, ai.release, cache:idempotency, cache:rec-candidates, cache:rec-features | ai.decision_record, ai.rec_decision, cache:idempotency | Fill a recommendation slot
AiService | recommend | recordRecommendationEvents | POST | /recommendations/events |  |  | AI_USE | core | 1 | SVC-AI-RECOMMEND-1 | ai.rec_decision, cache:idempotency | ai.rec_decline, ai.rec_event, cache:idempotency | Report what happened to recommended items
AiService | retrieval | createKnowledgeCollection | POST | /collections | KnowledgeCollection | KnowledgeCollection | AI_CONFIGURE | setup | 2 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, cache:idempotency, qdrant:knowledge | ai.knowledge_collection, cache:idempotency, qdrant:knowledge | Create a collection
AiService | retrieval | ingestKnowledgeDocument | POST | /collections/{collectionId}/documents | KnowledgeDocument | KnowledgeDocument | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, ai.knowledge_document, cache:embedding, cache:idempotency, qdrant:knowledge | ai.chunk_embedding, ai.knowledge_document, cache:embedding, cache:idempotency, qdrant:knowledge | Add a document
AiService | retrieval | reindexSource | POST | /index-sources/{sourceId}/reindex |  | IndexJob | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.index_job, ai.index_source, assets.media_asset, cache:embedding, cache:idempotency, catalogue.entitlement_template, catalogue.product, fnb.menu_item, maintenance.inspection_template, marketing.case, reporting.report_definition, retail.merchandise, whitelabel.content_page, whitelabel.faq_entry, whitelabel.policy | ai.chunk_embedding, ai.index_entry, ai.index_job, cache:embedding, cache:idempotency, qdrant:knowledge | Rebuild a source
AiService | retrieval | semanticSearch | POST | /search |  | array of SearchResult | AI_USE | core | 2 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, ai.knowledge_document, assets.media_asset, cache:answer, cache:idempotency, catalogue.product, qdrant:knowledge | ai.activity, cache:answer, cache:idempotency, qdrant:knowledge | Search meaning, not words
AiService | retrieval | setIndexSource | PUT | /index-sources | IndexSource | IndexSource | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-2 | ai.index_source, ai.knowledge_collection, cache:idempotency | ai.index_source, cache:idempotency | Declare a source indexed
CatalogueService | availability | getSeatAvailability | GET | /performances/{performanceId}/seat-availability |  | SeatAvailability | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-AVAILABILITY-1 | seating.seat, seating.seat_category, seating.seat_hold |  | Seat status for a performance
CatalogueService | bundle | createBundle | POST | /bundles | CreateBundleRequest | Bundle | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-1 | cache:idempotency, fnb.menu_item, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component, promotions.promotion_audit | Create a bundle
CatalogueService | bundle | getBundle | GET | /bundles/{bundleId} |  | Bundle | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-BUNDLE-1 | promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component |  | Read a bundle with components and allocation
CatalogueService | bundle | getLatestBundle | GET | /catalogue/bundles/latest |  | CatalogueBundle | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-BUNDLE-1 | catalogue.published_bundle |  | Pull the current bundle for this workstation's venue
CatalogueService | bundle | listCatalogueBundles | GET | /catalogue/bundles |  | array of BundleSummary | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-BUNDLE-1 | catalogue.product, catalogue.published_bundle |  | List published catalogue bundles
CatalogueService | bundle | publishBundle | POST | /catalogue/bundles |  | BundleSummary | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-2 | cache:idempotency, catalogue.published_bundle | cache:idempotency, catalogue.published_bundle | Compute, sign and publish a catalogue bundle
CatalogueService | bundle | updateBundle | PATCH | /bundles/{bundleId} |  | Bundle | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-2 | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_component, promotions.promotion_audit | Amend a bundle
CatalogueService | capacity | getAvailability | GET | /availability |  | PerformanceAvailabilityPage | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CAPACITY-1 | catalogue.channel_capacity, catalogue.inventory_hold, catalogue.performance |  | Live remaining capacity
CatalogueService | catalogue | bulkChangePrices | POST | /products/bulk-price |  | BulkPriceResult | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.price_list, catalogue.product | cache:idempotency, catalogue.price_list, catalogue.product_version | Reprice a category or a whole catalogue
CatalogueService | catalogue | cloneProduct | POST | /products/{productId}/clone |  | Product | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | catalogue.product, catalogue.product_media, catalogue.variant | cache:idempotency, catalogue.product, catalogue.variant | Copy a product as a new draft
CatalogueService | catalogue | commitCatalogueImport | POST | /products/import/{jobId}/commit |  | CatalogueImportJob | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.import_job | cache:idempotency, catalogue.import_job, catalogue.product, catalogue.variant | Apply a parsed catalogue import
CatalogueService | catalogue | getMyMemberships | GET | /guests/me/memberships |  | array of GuestMembership | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-CATALOGUE-1 | access.entitlement, catalogue.product, marketing.loyalty_position |  | A guest's own memberships, benefits and history
CatalogueService | catalogue | joinWaitlist | POST | /waitlist-entries | WaitlistEntry | WaitlistEntry |  | core | 2 | SVC-CATALOGUE-CATALOGUE-2 | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.waitlist_entry | cache:idempotency, catalogue.waitlist_entry | Ask to be told if capacity frees up
CatalogueService | catalogue | leaveWaitlist | DELETE | /waitlist-entries/{entryId} |  |  |  | core | 2 | SVC-CATALOGUE-CATALOGUE-2 | cache:idempotency, catalogue.waitlist_entry | cache:idempotency, catalogue.waitlist_entry | Stop waiting
CatalogueService | catalogue | listGuestMemberships | GET | /guest/memberships |  | object | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-CATALOGUE-2 | catalogue.entitlement_template, catalogue.product, orders.sales_order |  | A guest's memberships, benefits and history
CatalogueService | catalogue | listProductCategories | GET | /product-categories |  | array of ProductCategoryNode | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | catalogue.product, catalogue.product_category |  | The merchandise hierarchy — categories, brands, collections
CatalogueService | catalogue | searchCatalogue | GET | /search |  | array of object |  | core | 1 | SVC-CATALOGUE-CATALOGUE-3 | catalogue.event, catalogue.product, catalogue.product_eligibility_rule, catalogue.product_media, catalogue.variant, whitelabel.guided_choice_answer |  | Find something by name
CatalogueService | catalogue | setCurrencyRoundingRule | PUT | /rounding-profiles | RoundingProfile | RoundingProfile | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-3 | cache:idempotency, catalogue.rounding_profile | cache:idempotency, catalogue.audit_entry, catalogue.rounding_profile | Set precision and rounding for a currency
CatalogueService | catalogue | setDynamicPriceRule | PUT | /pricing/dynamic-rules/{ruleId} | DynamicPriceRuleDetail | DynamicPriceRuleDetail | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-3 | pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | Replace a rule, its conditions and its actions
CatalogueService | catalogue | setDynamicPricingGuardrailPolicy | PUT | /dynamic-pricing-controls | DynamicPricingControl | DynamicPricingControl | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-3 | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy | cache:idempotency, catalogue.audit_entry, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, platform.outbox | Set the guardrails and automation level of dynamic pricing at one scope
CatalogueService | catalogue | setPriceCategoryRateType | PUT | /price-categories | PriceCategory | PriceCategory | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-4 | cache:idempotency, catalogue.price_category, catalogue.rate | cache:idempotency, catalogue.audit_entry, catalogue.price_category | Create or update a price category or rate type
CatalogueService | catalogue | setProductCategories | PUT | /product-categories |  | array of ProductCategory | PRODUCT_CONFIGURE | core | 1 | SVC-CATALOGUE-CATALOGUE-4 | cache:idempotency, catalogue.product, catalogue.product_category, whitelabel.booking_flow | cache:idempotency, catalogue.product_category | Define the hierarchy, in the order a guest sees it
CatalogueService | category | createSeatCategory | POST | /seat-categories |  | SeatCategory | CAPACITY_CONFIGURE | setup | 2 | SVC-CATALOGUE-CATEGORY-1 | cache:idempotency, seating.seat_category, seating.seat_price_band | cache:idempotency, seating.seat_category, seating.seat_price_band | Create a seat category
CatalogueService | coupon | createCouponCampaign | POST | /coupon-campaigns | CreateCouponCampaignRequest | CouponCampaign | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-COUPON-1 | cache:idempotency, promotions.coupon_campaign | cache:idempotency, promotions.coupon_campaign, promotions.promotion_audit | Create a coupon campaign
CatalogueService | coupon | generateCouponCodes | POST | /coupon-campaigns/{campaignId}/codes |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-COUPON-1 | cache:idempotency, promotions.coupon_campaign | cache:idempotency, promotions.coupon_code, promotions.coupon_code_batch, promotions.promotion_audit | Generate codes in bulk
CatalogueService | coupon | getCouponCode | GET | /coupon-codes/{code} |  | CouponCode | PRICE_VIEW | core | 1 | SVC-CATALOGUE-COUPON-1 | promotions.coupon_code |  | Look up a code
CatalogueService | drafted | createBulkProductCatalogue | POST | /bulk-product-catalogue | BulkProductCreationCatalogueImportInput | BulkProductCreationCatalogueImportView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-1 | cache:idempotency, catalogue.import_job, catalogue.product | cache:idempotency, catalogue.audit_entry, catalogue.import_job, catalogue.product, catalogue.variant | Bulk Product Creation & Catalogue Import
CatalogueService | drafted | setBookingVelocityTime | PUT | /booking-velocity-time | BookingVelocityTimeToEventRuleBuilderInput | BookingVelocityTimeToEventRuleBuilderView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-1 | cache:idempotency, catalogue.dynamic_pricing_strategy, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | Booking Velocity & Time-to-Event Rule Builder
CatalogueService | drafted | setBundleComponent | PUT | /bundle-component | BundleComponentBuilderInput | BundleComponentBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-1 | cache:idempotency, promotions.bundle, promotions.bundle_component | cache:idempotency, promotions.bundle_component, promotions.promotion_audit | Bundle Component Builder
CatalogueService | drafted | setBundleDefinition | PUT | /bundle-definition | BundleDefinitionSetupInput | BundleDefinitionSetupView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-1 | cache:idempotency, promotions.bundle, promotions.campaign | cache:idempotency, promotions.bundle, promotions.promotion_audit | Bundle Definition & Setup
CatalogueService | drafted | setBuyGetBogo | PUT | /buy-get-bogo | BuyXGetYBogoRuleBuilderInput | BuyXGetYBogoRuleBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-2 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Buy X Get Y / BOGO Rule Builder
CatalogueService | drafted | setCampaignBudgetFinancial | PUT | /campaign-budget-financial | CampaignBudgetFinancialLimitSetupInput | CampaignBudgetFinancialLimitSetupView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-2 | cache:idempotency, promotions.campaign, promotions.campaign_budget, promotions.promotion | cache:idempotency, promotions.campaign, promotions.campaign_budget, promotions.promotion_audit | Campaign Budget & Financial Limit Setup
CatalogueService | drafted | setCodeDistributionManager | PUT | /code-distribution-manager | CodeDistributionAssignmentManagerInput | CodeDistributionAssignmentManagerView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-2 | cache:idempotency, promotions.coupon_code, promotions.coupon_code_batch | cache:idempotency, promotions.coupon_code, promotions.promotion_audit | Code Distribution & Assignment Manager
CatalogueService | drafted | setCouponPromoCode | PUT | /coupon-promo-code | CouponPromoCodeBuilderInput | CouponPromoCodeBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-2 | cache:idempotency, promotions.campaign, promotions.coupon_campaign | cache:idempotency, promotions.coupon_campaign, promotions.coupon_code, promotions.promotion_audit | Coupon & Promo Code Builder
CatalogueService | drafted | setCrossCategoryPromotion | PUT | /cross-category-promotion | CrossCategoryPromotionBuilderInput | CrossCategoryPromotionBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-3 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Cross-Category Promotion Builder
CatalogueService | drafted | setDemandOccupancyAvailability | PUT | /demand-occupancy-availability | DemandOccupancyAvailabilityRuleBuilderInput | DemandOccupancyAvailabilityRuleBuilderView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-3 | cache:idempotency, catalogue.dynamic_pricing_strategy, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | Demand, Occupancy & Availability Rule Builder
CatalogueService | drafted | setEligibilityRule | PUT | /eligibility-rule | EligibilityRuleBuilderInput | EligibilityRuleBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-3 | cache:idempotency, promotions.promotion, promotions.promotion_rule | cache:idempotency, promotions.promotion_audit, promotions.promotion_rule | Eligibility Rule Builder
CatalogueService | drafted | setFixedPriceOffer | PUT | /fixed-price-offer | FixedPriceNForXOfferBuilderInput | FixedPriceNForXOfferBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-3 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Fixed-Price & “N for X” Offer Builder
CatalogueService | drafted | setGiftFreeProduct | PUT | /gift-free-product | GiftFreeProductAddedValueOfferBuilderInput | GiftFreeProductAddedValueOfferBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-4 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Gift, Free Product & Added-Value Offer Builder
CatalogueService | drafted | setGuestChoiceBuild | PUT | /guest-choice-build | GuestChoiceBuildYourOwnBundleDesignerInput | GuestChoiceBuildYourOwnBundleDesignerView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-4 | cache:idempotency, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option | cache:idempotency, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.promotion_audit | Guest Choice & Build-Your-Own Bundle Designer
CatalogueService | drafted | setPriceHierarchyInheritance | PUT | /price-hierarchy-inheritance | PriceHierarchyInheritanceConfigurationInput | PriceHierarchyInheritanceConfigurationView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-4 | cache:idempotency, catalogue.price_list, catalogue.price_resolution_policy | cache:idempotency, catalogue.audit_entry, catalogue.price_resolution_policy | Price Hierarchy & Inheritance Configuration
CatalogueService | drafted | setPriceListMaster | PUT | /price-list-master | PriceListMasterConfigurationInput | PriceListMasterConfigurationView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-4 | cache:idempotency, catalogue.price_category, catalogue.price_list, catalogue.price_resolution_policy, catalogue.rounding_profile | cache:idempotency, catalogue.audit_entry, catalogue.price_list | Price List Master Configuration
CatalogueService | drafted | setPromotionRule | PUT | /promotion-rule | PromotionRuleBuilderInput | PromotionRuleBuilderView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-5 | cache:idempotency, promotions.promotion, promotions.promotion_rule | cache:idempotency, promotions.promotion_audit, promotions.promotion_rule | Promotion Rule Builder
CatalogueService | drafted | setRateStructure | PUT | /rate-structure | RateStructureBuilderInput | RateStructureBuilderView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-5 | cache:idempotency, catalogue.price, catalogue.price_category, catalogue.price_list, catalogue.rate, catalogue.rounding_profile | cache:idempotency, catalogue.audit_entry, catalogue.rate | Rate Structure Builder
CatalogueService | drafted | setRulePriorityConflict | PUT | /rule-priority-conflict | RulePriorityConflictInput | RulePriorityConflictView | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-5 | cache:idempotency, catalogue.dynamic_pricing_control, catalogue.price_resolution_policy, catalogue.pricing_test_case, pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule | cache:idempotency, catalogue.audit_entry, catalogue.price_resolution_policy, catalogue.pricing_test_case, pricing.dynamic_price_rule | Reorder, validate, test or save the pricing rule priority
CatalogueService | entitlement | createEntitlementTemplate | POST | /entitlement-templates | EntitlementTemplate | EntitlementTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | cache:idempotency, catalogue.entitlement_template | cache:idempotency, catalogue.entitlement_template | Create an entitlement template
CatalogueService | evaluation | evaluatePromotions | POST | /promotions/evaluate | EvaluatePromotionsRequest | PromotionEvaluation | PRICE_VIEW | core | 1 | SVC-CATALOGUE-EVALUATION-1 | cache:idempotency, catalogue.price_list, promotions.coupon_code, promotions.promotion, promotions.promotion_rule | cache:idempotency, promotions.promotion_evaluation_trace | Evaluate promotions against a cart
CatalogueService | event | createEvent | POST | /events | CreateEventRequest | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-1 | cache:idempotency, catalogue.event | cache:idempotency, catalogue.event | Create an event
CatalogueService | event | getPerformance | GET | /performances/{performanceId} |  | Performance | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-1 | catalogue.performance |  | Read a performance
CatalogueService | event | listEvents | GET | /events |  | object | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-EVENT-1 | catalogue.event |  | List events
CatalogueService | event | listPerformances | GET | /events/{eventId}/performances |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-1 | catalogue.performance, catalogue.product, catalogue.product_category |  | List performances of an event
CatalogueService | event | updateEvent | PATCH | /events/{eventId} |  | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-2 | cache:idempotency, catalogue.event | cache:idempotency, catalogue.event | Amend an event
CatalogueService | event | updatePerformance | PATCH | /performances/{performanceId} |  | Performance | PERFORMANCE_CONFIGURE | core | 2 | SVC-CATALOGUE-EVENT-2 | cache:idempotency, catalogue.performance | cache:idempotency, catalogue.performance | Amend a performance
CatalogueService | events | cloneEvent | POST | /events/{eventId}/clone |  | object | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENTS-1 | cache:idempotency, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance | cache:idempotency, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance | Copy an event, choosing what comes with it
CatalogueService | events | setEventLifecycleState | POST | /events/{eventId}/lifecycle |  |  | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENTS-1 | cache:idempotency, catalogue.channel_capacity, catalogue.event, catalogue.event_capacity_profile, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance, catalogue.price_list | cache:idempotency, catalogue.event, catalogue.performance, platform.outbox | Draft, planned, on sale, live, closed, cancelled
CatalogueService | hold | createSeatHold | POST | /seat-holds | CreateSeatHoldRequest | SeatHold | ORDER_CREATE | core | 2 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_hold | cache:idempotency, platform.outbox, seating.seat_hold | Hold specific seats
CatalogueService | hold | extendSeatHold | POST | /seat-holds/{holdId}/extend |  | SeatHold | ORDER_CREATE | core | 2 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_hold | cache:idempotency, seating.seat_hold | Extend a hold
CatalogueService | hold | getSeatHold | GET | /seat-holds/{holdId} |  | SeatHold | ORDER_VIEW | core | 2 | SVC-CATALOGUE-HOLD-1 | seating.seat_hold |  | Read a hold
CatalogueService | hold | relinquishSeatHold | DELETE | /seat-holds/{holdId} |  |  | ORDER_CREATE | core | 2 | SVC-CATALOGUE-HOLD-1 | seating.seat_hold | platform.outbox, seating.seat_hold | Release a hold
CatalogueService | lease | acquireInventoryHold | POST | /inventory-holds | AcquireLeaseRequest | InventoryHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-LEASE-1 | cache:idempotency, catalogue.channel_allocation, catalogue.channel_capacity, catalogue.inventory_hold, platform.workstation | cache:idempotency, catalogue.channel_allocation, catalogue.channel_capacity, catalogue.inventory_hold | Acquire an inventory hold
CatalogueService | lease | listInventoryHolds | GET | /inventory-holds |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-LEASE-1 | catalogue.inventory_hold |  | List inventory holds
CatalogueService | lease | relinquishInventoryHold | DELETE | /inventory-holds/{inventoryHoldId} |  | InventoryHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-LEASE-1 | catalogue.channel_capacity, catalogue.inventory_hold | catalogue.channel_capacity, catalogue.inventory_hold | Return unsold units
CatalogueService | lease | renewInventoryHold | POST | /inventory-holds/{inventoryHoldId}/renew |  | InventoryHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-LEASE-1 | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_hold | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_hold | Extend an inventory hold's TTL
CatalogueService | pricing | copyPriceList | POST | /price-lists/{priceListId}/copy |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Copy a price list, optionally with an adjustment
CatalogueService | pricing | createPriceList | POST | /price-lists | CreatePriceListRequest | PriceList | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Create a price list
CatalogueService | pricing | setPrices | PUT | /price-lists/{priceListId}/prices |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, cache:resolution, catalogue.price_list | Set prices in bulk
CatalogueService | pricing | updatePriceList | PATCH | /price-lists/{priceListId} |  | PriceList | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Amend a price list
CatalogueService | product | checkBookingEligibility | POST | /eligibility-checks | EligibilityCheckRequest | EligibilityCheckResult | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product, catalogue.product_eligibility_rule |  | Can this party take part
CatalogueService | product | getGroupPackageDefinition | GET | /products/{productId}/group-package |  | GroupPackageDefinition | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-PRODUCT-1 | catalogue.group_package |  | A school-trip format or party package
CatalogueService | product | getProduct | GET | /products/{productId} |  | Product | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product, catalogue.product_media |  | Read a product
CatalogueService | product | getProductEligibilityRule | GET | /products/{productId}/eligibility-rule |  | ProductEligibilityRule | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product_eligibility_rule |  | Who may take part: age, height, supervision
CatalogueService | product | listAlternativeCodes | GET | /products/{productId}/alternative-codes |  | array of AlternativeCode | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.alternative_code |  | External identifiers for a product
CatalogueService | product | listGroupPackages | GET | /group-packages |  | object | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-PRODUCT-2 | catalogue.group_package |  | The school-trip formats or party packages on offer
CatalogueService | product | listProductVariants | GET | /products/{productId}/variants |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.variant |  | List generated variants
CatalogueService | product | listProducts | GET | /products |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.product, catalogue.product_category, catalogue.product_eligibility_rule, catalogue.product_media, whitelabel.guided_choice_answer |  | List products
CatalogueService | product | resolveProductByCode | GET | /products/resolve |  | ProductVariant | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-3 | catalogue.variant |  | Resolve a partner code to a product
CatalogueService | product | setAlternativeCodes | PUT | /products/{productId}/alternative-codes |  | array of AlternativeCode | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | cache:idempotency, catalogue.alternative_code | cache:idempotency, catalogue.alternative_code | Set external identifiers
CatalogueService | product | setGroupPackageDefinition | PUT | /products/{productId}/group-package | GroupPackageDefinition | GroupPackageDefinition | PRODUCT_CONFIGURE | setup | 2 | SVC-CATALOGUE-PRODUCT-3 | catalogue.group_package | catalogue.group_package | Define a school-trip format or party package
CatalogueService | product | setProductEligibilityRule | PUT | /products/{productId}/eligibility-rule | ProductEligibilityRule | ProductEligibilityRule | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | catalogue.product_eligibility_rule | catalogue.product_eligibility_rule | Set age, height and supervision limits
CatalogueService | product | updateProduct | PATCH | /products/{productId} | UpdateProductRequest | Product | PRODUCT_CONFIGURE | core | 1 | SVC-CATALOGUE-PRODUCT-4 | cache:idempotency, catalogue.product, catalogue.product_media, whitelabel.booking_flow | cache:idempotency, catalogue.product, catalogue.product_media | Update a product
CatalogueService | promotion | analysePromotionConflicts | GET | /promotions/{promotionId}/conflicts |  | ConflictAnalysis | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Analyse stacking against live promotions
CatalogueService | promotion | createCommercialCampaign | POST | /commercial-campaigns | CreateCommercialCampaignRequest | CommercialCampaign | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-1 | cache:idempotency, promotions.campaign, promotions.campaign_budget | cache:idempotency, promotions.campaign, promotions.promotion_audit | Create a commercial campaign
CatalogueService | promotion | createPromotion | POST | /promotions | CreatePromotionRequest | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-1 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Create a promotion
CatalogueService | promotion | getPromotion | GET | /promotions/{promotionId} |  | Promotion or GuestPromotion | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Read a promotion
CatalogueService | promotion | getPromotionUsage | GET | /promotions/{promotionId}/usage |  | PromotionUsage | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-2 | promotions.promotion |  | Redemption count and discount given
CatalogueService | promotion | listPromotions | GET | /promotions |  | object | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-2 | promotions.promotion |  | List promotions
CatalogueService | promotion | publishPromotion | POST | /promotions/{promotionId}/publish |  | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-2 | cache:idempotency, promotions.promotion, promotions.promotion_channel_publication | cache:idempotency, platform.outbox, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication | Publish a promotion
CatalogueService | promotion | updateCommercialCampaign | PATCH | /commercial-campaigns/{campaignId} |  | CommercialCampaign | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-2 | cache:idempotency, promotions.bundle, promotions.campaign, promotions.campaign_budget, promotions.coupon_campaign, promotions.promotion | cache:idempotency, promotions.campaign, promotions.promotion_audit | Amend a commercial campaign
CatalogueService | promotion | updatePromotion | PATCH | /promotions/{promotionId} |  | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-3 | cache:idempotency, promotions.promotion, promotions.promotion_channel_publication | cache:idempotency, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication | Amend a promotion
CatalogueService | promotions | setPromotionVariants | PUT | /promotions/{promotionId}/variants |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTIONS-1 | cache:idempotency, promotions.promotion, promotions.promotion_variant | cache:idempotency, promotions.promotion, promotions.promotion_audit, promotions.promotion_variant | A/B test two versions against each other
CatalogueService | recommendation | recommendSeats | POST | /performances/{performanceId}/seat-recommendations | SeatRecommendationRequest | object | PRODUCT_VIEW | core | 2 | SVC-CATALOGUE-RECOMMENDATION-1 | catalogue.performance |  | Recommend seats for a party
FnbService | bill | closeTableVisit | POST | /table-visits/{visitId}/close |  | object | ORDER_CREATE | core | 1 | SVC-FNB-BILL-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Settle and close a visit
FnbService | fnb | attachModifierGroup | PUT | /menu-items/{menuItemId}/modifier-groups |  | MenuItem | PRODUCT_CONFIGURE | setup | 2 | SVC-FNB-FNB-1 | cache:idempotency, fnb.menu_item, fnb.modifier_group | cache:idempotency, cache:resolution, fnb.menu_item, fnb.menu_item_modifier | Give an item its choices
FnbService | fnb | buildProductionPlan | POST | /production-plans | ProductionPlan | ProductionPlan | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-1 | ai.suggestion, cache:idempotency, fnb.menu_item, fnb.menu_item_modifier, fnb.production_plan, fnb.production_plan_line, fnb.recipe | cache:idempotency, fnb.production_plan, fnb.production_plan_line | Turn a forecast into a prep list
FnbService | fnb | chaseStation | POST | /kitchen-stations/{stationId}/chase |  |  | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-1 | cache:idempotency, fnb.kitchen_station, fnb.kitchen_ticket | cache:idempotency, fnb.kitchen_exception | The pass asks a station where an item is
FnbService | fnb | createTableReservation | POST | /table-reservations | TableReservation | TableReservation |  | core | 2 | SVC-FNB-FNB-1 | cache:idempotency, fnb.dining_table, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Book a table in advance
FnbService | fnb | escalateCorrectiveAction | POST | /food-safety/corrective-actions/{actionId}/escalate |  | CorrectiveAction | INCIDENT_MANAGE | setup | 2 | SVC-FNB-FNB-2 | cache:idempotency, fnb.corrective_action, identity.principal | cache:idempotency, fnb.corrective_action | Escalate a finding
FnbService | fnb | fireCourse | POST | /kitchen-tickets/{ticketId}/fire |  | KitchenTicket | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Send a held course to the pass
FnbService | fnb | getHaccpStatus | GET | /food-safety/status |  | object | INCIDENT_VIEW | core | 2 | SVC-FNB-FNB-2 | fnb.cold_chain_event, fnb.corrective_action, fnb.temperature_log |  | Where this venue stands, right now
FnbService | fnb | holdCourse | POST | /kitchen-tickets/{ticketId}/hold |  | KitchenTicket | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Stop a course going out
FnbService | fnb | joinRestaurantWaitlist | POST | /waitlist | RestaurantWaitlist | RestaurantWaitlist | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-3 | cache:idempotency, fnb.dining_table, fnb.waitlist_entry, platform.outlet | cache:idempotency, fnb.waitlist_entry | Add a party to an outlet's waitlist
FnbService | fnb | leaveRestaurantWaitlist | POST | /waitlist/{entryId}/leave |  | RestaurantWaitlist | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-3 | fnb.waitlist_entry |  | Take a party off an outlet's waitlist
FnbService | fnb | list86Events | GET | /outlets/{outletId}/86-events |  | object | PRODUCT_VIEW | core | 2 | SVC-FNB-FNB-3 | fnb.menu_item, fnb.sold_out_item |  | What came off the menu today, when, and for how long
FnbService | fnb | listTableReservations | GET | /table-reservations |  | object | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-3 | fnb.dining_table, fnb.reservation_table, fnb.table_reservation |  | Bookings for a service period
FnbService | fnb | logColdChain | POST | /food-safety/cold-chain | ColdChainEvent | ColdChainEvent | INCIDENT_REPORT | setup | 2 | SVC-FNB-FNB-4 | cache:idempotency, fnb.cold_chain_event, inventory.goods_receipt | cache:idempotency, fnb.cold_chain_event, fnb.corrective_action | The temperature a delivery arrived at, and what was decided
FnbService | fnb | logKitchenException | POST | /kitchen-exceptions |  | KitchenException | INCIDENT_REPORT | core | 2 | SVC-FNB-FNB-4 | cache:idempotency, fnb.kitchen_exception, fnb.kitchen_station | cache:idempotency, fnb.kitchen_exception | Something went wrong that is not a refire
FnbService | fnb | logTemperature | POST | /food-safety/temperature-logs | TemperatureLog | object | INCIDENT_REPORT | setup | 2 | SVC-FNB-FNB-4 | cache:idempotency, fnb.corrective_action, fnb.temperature_log, platform.scope | cache:idempotency, fnb.corrective_action, fnb.temperature_log | Record a temperature check, in range or not
FnbService | fnb | markOrderCollected | POST | /orders/{orderId}/collected |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-4 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.kitchen_ticket, fnb.service_order | The guest took it
FnbService | fnb | moveTableVisit | POST | /table-visits/{visitId}/move |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.dining_table, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.kitchen_ticket, fnb.table_visit | Move a party to a different table, mid-service
FnbService | fnb | notifyServer | POST | /table-visits/{visitId}/notify-server |  |  | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-5 | cache:idempotency, fnb.table_visit, identity.principal | cache:idempotency, marketing.message_dispatch | The kitchen calls the server to the pass
FnbService | fnb | printOrderLabel | POST | /kitchen-tickets/{ticketId}/label |  | OrderLabel | ORDER_VIEW | core | 2 | SVC-FNB-FNB-5 | fnb.kitchen_ticket |  | A label for the bag
FnbService | fnb | rebalanceStationLoad | POST | /kitchen-stations/rebalance | StationRebalance | StationRebalance | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-FNB-5 | cache:idempotency, fnb.kitchen_station | cache:idempotency, cache:resolution, fnb.kitchen_station | Move work between stations mid-service
FnbService | fnb | recallKitchenTicket | POST | /kitchen-tickets/{ticketId}/recall |  | KitchenTicket | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-6 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Bring back a ticket that was bumped by mistake
FnbService | fnb | refireItem | POST | /kitchen-tickets/{ticketId}/refire |  | KitchenTicket | ORDER_MODIFY | core | 2 | SVC-FNB-FNB-6 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket_line, inventory.movement | Make it again
FnbService | fnb | releaseProductionPlan | POST | /production-plans/{planId}/release |  | ProductionPlan | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.production_plan, fnb.production_plan_line | cache:idempotency, fnb.production_plan, fnb.production_run | Make the plan real
FnbService | fnb | seatTableReservation | POST | /table-reservations/{reservationId}/seat |  | TableReservation | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.dining_table, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.table_reservation, fnb.table_session, fnb.table_visit | The party arrived and has been sat down
FnbService | fnb | setCourseRules | PUT | /outlets/{outletId}/course-rules | CourseRules | CourseRules | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-FNB-7 | cache:idempotency, fnb.course_rule | cache:idempotency, cache:resolution, fnb.course_rule | How this outlet courses by default
FnbService | fnb | setKitchenSla | PUT | /outlets/{outletId}/kitchen-sla | KitchenSla | KitchenSla | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-FNB-7 | cache:idempotency | cache:idempotency, cache:resolution | How long a ticket may sit before it is late
FnbService | fnb | setTableCombinations | PUT | /outlets/{outletId}/table-combinations |  | object | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.dining_table, fnb.table_combination | cache:idempotency, cache:resolution, fnb.dining_table, fnb.table_combination | Which tables can be pushed together, and to what capacity
FnbService | fnb | signCorrectiveAction | POST | /food-safety/corrective-actions/{actionId}/sign |  | CorrectiveAction | INCIDENT_MANAGE | setup | 2 | SVC-FNB-FNB-7 | cache:idempotency, fnb.corrective_action, identity.principal | cache:idempotency, fnb.corrective_action | Say what was done, and put a name to it
FnbService | fnb | updateTableReservation | PATCH | /table-reservations/{reservationId} | TableReservation | TableReservation |  | core | 2 | SVC-FNB-FNB-8 | cache:idempotency, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Change or cancel a booking
FnbService | guestOrdering | claimLocationSession | POST | /location-sessions |  | LocationSession |  | core | 2 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.location_session | cache:idempotency, fnb.location_session | Tell the platform where the guest is
FnbService | guestOrdering | claimTableSession | POST | /table-sessions |  | TableSession |  | core | 2 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.table_session | cache:idempotency, fnb.table_session | Identify which table a guest is sitting at
FnbService | guestOrdering | createDeliveryLocation | POST | /delivery-locations |  | DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_location, fnb.dining_table, platform.outlet | cache:idempotency, fnb.delivery_location, fnb.delivery_location_outlet | Add a place food can be delivered to
FnbService | guestOrdering | createGuestFnbOrder | POST | /guest-orders | CreateGuestOrderRequest | GuestOrderResult |  | core | 2 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_policy, fnb.location_session, fnb.menu_item, fnb.menu_item_modifier, inventory.stock_level | cache:idempotency, fnb.kitchen_ticket, fnb.order_fulfilment, fnb.service_order | A guest orders food
FnbService | guestOrdering | getFnbDeliveryPolicy | GET | /fnb-delivery-policy |  | FnbDeliveryPolicy | PRODUCT_VIEW | core | 2 | SVC-FNB-GUESTORDERING-2 | fnb.delivery_policy |  | How an outlet does takeaway and delivery
FnbService | guestOrdering | getGuestBill | GET | /table-sessions/{sessionId}/bill |  | Bill |  | core | 2 | SVC-FNB-GUESTORDERING-2 | fnb.service_order, fnb.table_session, orders.payment |  | The bill for the guest's table
FnbService | guestOrdering | getGuestMenu | GET | /outlets/{outletId}/guest-menu |  | GuestMenu |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.modifier_group, fnb.modifier_option |  | The menu a guest sees
FnbService | guestOrdering | getGuestOrderStatus | GET | /guest-orders/{orderId} |  | GuestOrderStatus |  | core | 2 | SVC-FNB-GUESTORDERING-2 | fnb.delivery_location, fnb.kitchen_ticket, fnb.service_order |  | Track an order
FnbService | guestOrdering | listDeliveryLocations | GET | /venues/{venueId}/delivery-locations |  | object |  | core | 2 | SVC-FNB-GUESTORDERING-3 | fnb.delivery_location, fnb.delivery_location_outlet |  | Where an order can be delivered
FnbService | guestOrdering | listDiningOutlets | GET | /venues/{venueId}/dining |  | object |  | core | 2 | SVC-FNB-GUESTORDERING-3 | fnb.menu, fnb.service_order, platform.outlet |  | Where a guest can eat, right now
FnbService | guestOrdering | listFulfilmentSlots | GET | /outlets/{outletId}/fulfilment-slots |  | object |  | core | 2 | SVC-FNB-GUESTORDERING-3 | fnb.delivery_policy, platform.outlet |  | Collection times or delivery windows still open
FnbService | guestOrdering | recordOrderHandover | POST | /guest-orders/{orderId}/delivery |  | GuestOrderStatus | ORDER_MODIFY | core | 1 | SVC-FNB-GUESTORDERING-3 | cache:idempotency, fnb.delivery_location, fnb.delivery_location_outlet, fnb.service_order | cache:idempotency, fnb.service_order | Record that an order reached the guest
FnbService | guestOrdering | setDeliveryLocationOutletMapping | PUT | /venues/{venueId}/delivery-location-outlets |  | array of DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_location, platform.outlet | cache:idempotency, cache:resolution, fnb.delivery_location_outlet | Set which outlets deliver to which delivery locations
FnbService | guestOrdering | setFnbDeliveryPolicy | PUT | /fnb-delivery-policy | FnbDeliveryPolicy | FnbDeliveryPolicy | PRODUCT_CONFIGURE | setup | 2 | SVC-FNB-GUESTORDERING-4 | fnb.delivery_policy | fnb.delivery_policy | Set takeaway and delivery rules
FnbService | guestOrdering | updateDeliveryLocation | PATCH | /delivery-locations/{locationId} |  | DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_location | cache:idempotency, fnb.delivery_location | Rename a delivery location, or take it out of service
FnbService | kitchen | listKitchenStations | GET | /kitchen/stations |  | object | PRODUCT_VIEW | core | 2 | SVC-FNB-KITCHEN-1 | fnb.kitchen_station |  | List preparation stations and their routing
FnbService | kitchen | listKitchenTickets | GET | /kitchen/tickets |  | object | ORDER_VIEW | core | 1 | SVC-FNB-KITCHEN-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line |  | Kitchen ticket queue
FnbService | kitchen | prioritiseKitchenTicket | POST | /kitchen/tickets/{ticketId}/prioritise |  | KitchenTicket | ORDER_MODIFY | core | 2 | SVC-FNB-KITCHEN-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Move a ticket up the queue
FnbService | kitchen | setKitchenStations | PUT | /kitchen/stations |  | array of KitchenStation | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-KITCHEN-1 | cache:idempotency, fnb.kitchen_station | cache:idempotency, fnb.kitchen_station | Configure stations and item routing
FnbService | kitchen | setKitchenTicketStatus | PUT | /kitchen/tickets/{ticketId}/status |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-KITCHEN-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket, platform.outbox | Advance a kitchen ticket
FnbService | menu | createMenu | POST | /menus | CreateMenuRequest | Menu | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Create a menu
FnbService | menu | getMenu | GET | /menus/{menuId} |  | Menu | PRODUCT_VIEW | core | 2 | SVC-FNB-MENU-1 | fnb.menu, fnb.menu_item, fnb.menu_section |  | Read a menu with sections and items
FnbService | menu | listMenus | GET | /menus |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-MENU-1 | fnb.menu, fnb.menu_item, fnb.menu_section |  | List menus
FnbService | menu | setItemAvailability | PUT | /menu-items/{itemId}/availability |  | MenuItem | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu_item | cache:idempotency, fnb.menu_item | Mark an item available or eighty-sixed
FnbService | menu | setMenuSections | PUT | /menus/{menuId}/sections |  | Menu | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-MENU-2 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Set menu sections and their item ordering
FnbService | menu | updateMenu | PATCH | /menus/{menuId} |  | Menu | PRODUCT_CONFIGURE | core | 2 | SVC-FNB-MENU-2 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Amend a menu
FnbService | modifier | createModifierGroup | POST | /modifier-groups | ModifierGroup | ModifierGroup | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MODIFIER-1 | cache:idempotency, fnb.modifier_group, fnb.modifier_option | cache:idempotency, fnb.modifier_group, fnb.modifier_option | Create a modifier group
FnbService | modifier | listModifierGroups | GET | /modifier-groups |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-MODIFIER-1 | fnb.modifier_group, fnb.modifier_option |  | List modifier groups
FnbService | order | createFnbOrder | POST | /fnb-orders | CreateFnbOrderRequest | FnbOrder | ORDER_CREATE | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_station, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.menu_item, fnb.service_order, fnb.service_order_line | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, platform.idempotency_record, platform.outbox | Place an F&B order
FnbService | order | getFnbOrder | GET | /fnb-orders/{orderId} |  | FnbOrder | ORDER_VIEW | core | 2 | SVC-FNB-ORDER-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line |  | Read an F&B order
FnbService | order | listFnbOrders | GET | /fnb-orders |  | object | ORDER_VIEW | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line |  | List F&B orders
FnbService | production | setRecipe | PUT | /recipes | Recipe | Recipe | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-PRODUCTION-1 | cache:idempotency, fnb.recipe, fnb.recipe_ingredient | cache:idempotency, fnb.recipe, fnb.recipe_ingredient | Define a recipe for a menu item
FnbService | table | clearTable | POST | /tables/{tableId}/clear |  | TableState | ORDER_MODIFY | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.dining_table | cache:idempotency, fnb.dining_table | Mark a table cleared and free
FnbService | table | getTableMap | GET | /outlets/{outletId}/tables |  | TableMap | ORDER_VIEW | core | 1 | SVC-FNB-TABLE-1 | fnb.dining_table |  | Table map with live state
FnbService | table | mergeTableVisits | POST | /table-visits/{visitId}/merge |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Merge another visit into this one
FnbService | table | openTableVisit | POST | /table-visits | OpenTableVisitRequest | TableVisit | ORDER_CREATE | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Seat a party and open a visit
FnbService | table | setTableLayout | PUT | /outlets/{outletId}/tables |  | TableMap | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-TABLE-2 | cache:idempotency, fnb.dining_table | cache:idempotency, fnb.dining_table | Configure the table layout
IdentityService | administration | createPrincipal | POST | /principals | CreatePrincipalRequest | Principal | USER_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-1 | cache:idempotency, identity.principal | cache:idempotency, identity.principal, identity.principal_credential | Create a principal
IdentityService | administration | createRole | POST | /roles |  | Role | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-1 | cache:idempotency, identity.role | cache:idempotency, cache:resolution, identity.role | Create a role
IdentityService | administration | listPrincipals | GET | /principals |  | object | USER_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.principal |  | List principals
IdentityService | administration | listRoles | GET | /roles |  | object | ROLE_MANAGE | core | 2 | SVC-IDENTITY-ADMINISTRATION-1 | identity.role |  | List roles
IdentityService | administration | openPlatformStaffGrant | POST | /platform-staff-grants |  | PlatformStaffGrant | PLATFORM_TENANT_ACCESS | core | 2 | SVC-IDENTITY-ADMINISTRATION-2 | identity.platform_staff_grant |  | A platform operator opens a time-boxed grant into this tenant
IdentityService | administration | updatePrincipal | PATCH | /principals/{principalId} |  | Principal | USER_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-2 | cache:idempotency, identity.principal | cache:idempotency, identity.principal | Update or deactivate a principal
IdentityService | guestAuth | deleteGuestAccount | DELETE | /auth/guest/account |  | object |  | core | 2 | SVC-IDENTITY-GUESTAUTH-1 | cache:idempotency, pii.subject | cache:idempotency, pii.subject, platform.dsar_request | Self-service account deletion
IdentityService | guestAuth | getGuestSession | GET | /auth/guest/session |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | identity.guest_session, identity.mfa_method, pii.subject |  | Read the current guest session
IdentityService | guestAuth | getMyIdentityVerification | GET | /auth/guest/identity-verifications/current |  | IdentityGuestVerification |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | identity.guest_identity_verification |  | The guest's own latest identity verification
IdentityService | guestAuth | guestLogout | DELETE | /auth/guest/session |  |  |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | identity.guest_session | identity.guest_session | End a guest session
IdentityService | guestAuth | guestPasswordLogin | POST | /auth/guest/password |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | identity.mfa_method | platform.outbox | Sign in with an email or mobile and a password
IdentityService | guestAuth | guestSocialLogin | POST | /auth/guest/social |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.mfa_method, pii.subject_contact | cache:idempotency, identity.guest_session, pii.subject, platform.outbox | Sign in with Apple or Google
IdentityService | guestAuth | guestUaePassLogin | POST | /auth/guest/uae-pass |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.mfa_method, pii.subject_contact | cache:idempotency, identity.guest_session, pii.subject, pii.subject_document, platform.outbox | Sign in with a national identity provider
IdentityService | guestAuth | linkGuestCheckout | POST | /auth/guest/link-checkout |  | object |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, orders.sales_order, pii.subject_contact | cache:idempotency, orders.sales_order, pii.subject | Attach a guest checkout to an account
IdentityService | guestAuth | registerGuest | POST | /auth/guest/register | RegisterGuestRequest | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | cache:idempotency, identity.mfa_method, pii.subject | cache:idempotency, identity.guest_session, pii.subject, pii.subject_contact, platform.outbox | Create a guest account
IdentityService | guestAuth | requestGuestOtp | POST | /auth/guest/otp |  | object |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | cache:idempotency, pii.subject_contact | cache:idempotency, identity.otp_challenge, platform.outbox | Request a one-time code
IdentityService | guestAuth | submitGuestIdentityDocument | POST | /auth/guest/identity-verifications | IdentityGuestDocumentSubmission | IdentityGuestVerification |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | assets.media_asset, cache:idempotency, identity.guest_identity_verification, identity.guest_verification_policy | cache:idempotency, identity.guest_identity_verification, pii.subject_document | Submit an identity document for verification
IdentityService | guestAuth | verifyGuestOtp | POST | /auth/guest/otp/verify |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | cache:idempotency, identity.mfa_method, identity.otp_challenge, pii.subject_contact | cache:idempotency, identity.guest_session, pii.subject_contact, platform.outbox | Verify a one-time code and issue a session
IdentityService | identity | changeOwnCredential | POST | /auth/credential | ChangeCredentialRequest |  |  | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.password_policy, identity.principal, identity.principal_credential | cache:idempotency, identity.principal_credential, identity.session | Change the caller's own password or PIN
IdentityService | identity | exportSubjectData | POST | /guests/{subjectId}/data-export |  | object | GUEST_VIEW_PII | core | 2 | SVC-IDENTITY-IDENTITY-1 | access.entitlement, cache:idempotency, marketing.consent_record, marketing.form_submission, marketing.guest_document, marketing.guest_profile, orders.sales_order, pii.subject | cache:idempotency | Everything the platform holds about one guest
IdentityService | identity | forceLogout | POST | /auth/sessions/{sessionId}/force-logout |  |  | SESSION_FORCE_LOGOUT | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.session | cache:idempotency, identity.session | Supervisor termination of an abandoned session
IdentityService | identity | getCurrentSession | GET | /auth/session |  | Session |  | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:resolution, identity.delegated_access, identity.principal, identity.role, identity.session | cache:resolution | Current session and effective permissions
IdentityService | identity | grantDelegation | POST | /guests/{subjectId}/delegations |  | DelegatedAccess | GUEST_MANAGE | core | 2 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.delegated_access, pii.subject | cache:idempotency, identity.delegated_access | Let one guest act for another
IdentityService | identity | listDelegations | GET | /guests/{subjectId}/delegations |  | object | GUEST_VIEW | core | 2 | SVC-IDENTITY-IDENTITY-2 | identity.delegated_access, marketing.guest_profile, pii.subject |  | Who may act for this guest, and for whom they may act
IdentityService | identity | login | POST | /auth/login | LoginRequest | LoginResponse |  | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.delegated_access, identity.mfa_method, identity.principal, identity.principal_credential, identity.role | cache:idempotency, identity.refresh_token, identity.session, platform.outbox | Authenticate and open a session
IdentityService | identity | refreshToken | POST | /auth/refresh |  | TokenPair |  | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.refresh_token, identity.session | cache:idempotency, identity.refresh_token, identity.session | Rotate the access token
IdentityService | identity | selectRole | POST | /auth/select-role |  | Session |  | core | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.delegated_access, identity.role, identity.session | cache:idempotency, identity.session | Choose a role for a multi-role session
IdentityService | identity | setGuestVerificationPolicy | PUT | /guest-verification-policy | IdentityGuestVerificationPolicy | IdentityGuestVerificationPolicy | TENANT_CONFIGURE | setup | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.guest_verification_policy | cache:idempotency, identity.guest_verification_policy | Set which verifications a guest must pass, and when
IdentityService | identity | setPasswordPolicy | PUT | /password-policy | PasswordPolicy | PasswordPolicy | TENANT_CONFIGURE | setup | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.password_policy | cache:idempotency, identity.password_policy | Length, breach check, lockout and step-up
IdentityService | identity | verifyGuestEmail | POST | /auth/guest/verify-email |  | object | GUEST_VIEW | core | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.otp_challenge, pii.subject | cache:idempotency, identity.otp_challenge, marketing.message_dispatch, pii.subject | Send a verification link, or consume one
IdentityService | mfa | createMfaChallenge | POST | /auth/mfa/challenge |  | object |  | core | 1 | SVC-IDENTITY-MFA-1 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_challenge | Second factor at staff sign-in, and step-up for a sensitive action
IdentityService | mfa | enrolMfaMethod | POST | /auth/mfa/methods |  | MfaEnrolment |  | core | 2 | SVC-IDENTITY-MFA-1 | cache:idempotency, identity.mfa_recovery_code, identity.principal | cache:idempotency, identity.mfa_method, identity.mfa_recovery_code | Enrol an MFA method
IdentityService | mfa | listMfaMethods | GET | /auth/mfa/methods |  | array of MfaMethod |  | core | 2 | SVC-IDENTITY-MFA-1 | identity.mfa_method |  | Enrolled MFA methods
IdentityService | mfa | removeMfaMethod | DELETE | /auth/mfa/methods/{methodId} |  |  |  | core | 2 | SVC-IDENTITY-MFA-1 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_method | Remove an MFA method
IdentityService | mfa | verifyMfaChallenge | POST | /auth/mfa/challenge/{challengeId}/verify |  | object |  | core | 1 | SVC-IDENTITY-MFA-2 | cache:idempotency, identity.mfa_challenge, identity.mfa_recovery_code | cache:idempotency, identity.mfa_challenge, identity.mfa_recovery_code, identity.session, platform.outbox | Complete a sign-in or step-up challenge
IdentityService | mfa | verifyMfaEnrolment | POST | /auth/mfa/methods/{methodId} |  | MfaMethod |  | core | 2 | SVC-IDENTITY-MFA-2 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_method | Complete enrolment
IdentityService | session | listActiveSessions | GET | /auth/sessions |  | object | SESSION_FORCE_LOGOUT | core | 1 | SVC-IDENTITY-SESSION-1 | identity.principal, identity.session |  | List active sessions
InventoryService | inventory | bulkUpdateProducts | POST | /products/bulk |  | object | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-INVENTORY-1 | cache:idempotency, catalogue.price, catalogue.product, inventory.item | cache:idempotency, cache:resolution, catalogue.price, catalogue.product, inventory.item | Change many products at once, with a preview
InventoryService | inventory | listSerialisedItems | GET | /serialised-items |  | object | PRODUCT_VIEW | core | 1 | SVC-INVENTORY-INVENTORY-1 | inventory.item, inventory.serialised_item, inventory.stock_batch |  | Where each individual item is
InventoryService | item | createInventoryItem | POST | /inventory-items | CreateInventoryItemRequest | InventoryItem | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.item | cache:idempotency, inventory.item | Create an inventory item
InventoryService | item | setInventoryKitDefinition | PUT | /inventory-items/{itemId}/kit-definition | InventoryKitDefinition | InventoryKitDefinition | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.item, inventory.kit_component, inventory.movement | cache:idempotency, cache:resolution, inventory.kit_component | Make an item a kit of other stocked items
InventoryService | item | updateInventoryItem | PATCH | /inventory-items/{itemId} |  | InventoryItem | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.item | cache:idempotency, inventory.item | Amend an item
InventoryService | receipt | createGoodsReceipt | POST | /goods-receipts | CreateGoodsReceiptRequest | GoodsReceipt | PROCUREMENT_RECEIVE | setup | 2 | SVC-INVENTORY-RECEIPT-1 | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line, platform.outbox | Receive goods against a purchase order
InventoryService | receipt | rejectReceivedGoods | POST | /goods-receipts/{receiptId}/reject |  | GoodsReceipt | PROCUREMENT_RECEIVE | setup | 2 | SVC-INVENTORY-RECEIPT-1 | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | Reject received goods
LedgerService | accounts | createAccount | POST | /accounts | CreateAccountRequest | Account | ACCOUNT_CONFIGURE | setup | 2 | SVC-LEDGER-ACCOUNTS-1 | cache:idempotency, ledger.account | cache:idempotency, ledger.account | Create an account
LedgerService | accounts | updateAccount | PATCH | /accounts/{accountId} |  | Account | ACCOUNT_CONFIGURE | setup | 2 | SVC-LEDGER-ACCOUNTS-1 | cache:idempotency, ledger.account | cache:idempotency, ledger.account | Rename, remap or deactivate an account
LedgerService | finance | ingestFxRates | POST | /fx-rates/ingest |  | object | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-FINANCE-1 | ledger.fx_rate, platform.region_settings | cache:idempotency, ledger.fx_rate | Pull rates from the configured provider
LedgerService | finance | setFxProvider | PUT | /fx-rates/providers |  | array of FxProviderAssignment | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-FINANCE-1 | ledger.fx_provider_assignment, platform.region_settings | cache:idempotency, ledger.fx_provider_assignment, platform.region_settings | Which provider serves which purpose
LedgerService | fiscal | createLegalEntity | POST | /legal-entities | LegalEntity | LegalEntity | ACCOUNT_CONFIGURE | setup | 1 | SVC-LEDGER-FISCAL-1 | cache:idempotency, ledger.legal_entity | cache:idempotency, ledger.legal_entity | Create a legal entity
LedgerService | ledger | listFxRates | GET | /fx-rates |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-LEDGER-1 | ledger.fx_rate |  | The rates in force
LedgerService | ledger | setFxRate | PUT | /fx-rates | FxRate | FxRate | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-LEDGER-1 | cache:idempotency, ledger.fx_rate | cache:idempotency, ledger.fx_rate | Set a rate
LedgerService | reporting | getFinancialReport | GET | /reports/financial |  | FinancialReport | REPORT_VIEW_VENUE | core | 2 | SVC-LEDGER-REPORTING-1 | ledger.account, ledger.event_budget, ledger.fiscal_period, ledger.posting |  | Financial statements, revenue and tax summaries
LedgerService | tax | createTaxCode | POST | /tax-codes | CreateTaxCodeRequest | TaxCode | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-1 | cache:idempotency, ledger.tax_code | cache:idempotency, ledger.tax_code | Create a tax code
LedgerService | tax | getTaxDocumentRendition | GET | /tax-documents/{documentId}/rendition |  | FinTaxDocumentRendition | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-1 | ledger.credit_memo, ledger.tax_invoice |  | The PDF of a tax invoice or credit memo, in a language
LedgerService | tax | getTaxInvoice | GET | /tax-invoices/{invoiceId} |  | FinTaxInvoice | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-1 | ledger.credit_memo, ledger.einvoice_transmission, ledger.tax_invoice, ledger.tax_invoice_line |  | One tax invoice, with its lines, VAT per rate and credit memos
LedgerService | tax | issueCreditMemo | POST | /tax-invoices/{invoiceId}/credit-memos | FinIssueCreditMemoRequest | FinCreditMemo | LEDGER_POST | core | 1 | SVC-LEDGER-TAX-1 | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, orders.refund | cache:idempotency, control.invoice_line, ledger.credit_memo, ledger.credit_memo_line, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, platform.audit_record, platform.outbox | Credit all or part of a tax invoice
LedgerService | tax | issueTaxInvoice | POST | /tax-invoices | FinIssueTaxInvoiceRequest | FinTaxInvoice | LEDGER_POST | core | 1 | SVC-LEDGER-TAX-2 | cache:idempotency, ledger.legal_entity, ledger.tax_code, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, orders.order_line, orders.payment, orders.sales_order | cache:idempotency, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, platform.audit_record, platform.outbox | Issue a tax invoice for one or more paid orders
LedgerService | tax | listCreditMemos | GET | /credit-memos |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-2 | ledger.credit_memo, ledger.credit_memo_line |  | Credit memos issued, newest first
LedgerService | tax | listTaxInvoices | GET | /tax-invoices |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-2 | ledger.tax_invoice, ledger.tax_invoice_line |  | Tax invoices issued, newest first
LedgerService | tax | setEInvoicingProvider | PUT | /e-invoicing/providers | FinEInvoicingProvider | FinEInvoicingProvider | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-2 | cache:idempotency, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.legal_entity | cache:idempotency, cache:resolution, ledger.einvoicing_provider, platform.audit_record | Connect a legal entity to its accredited e-invoicing service provider
LedgerService | tax | transmitEInvoices | POST | /e-invoicing/transmissions |  | object | LEDGER_POST | setup | 1 | SVC-LEDGER-TAX-3 | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.tax_invoice, ledger.tax_invoice_line | cache:idempotency, ledger.einvoice_transmission, platform.outbox | Send issued tax documents to the e-invoicing provider
LedgerService | tax | updateTaxCode | PATCH | /tax-codes/{taxCodeId} |  | TaxCode | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-3 | cache:idempotency, ledger.tax_code | cache:idempotency, ledger.tax_code | Amend a tax code
MarketingService | campaign | createCampaign | POST | /campaigns | CreateCampaignRequest | Campaign | MARKETING_MANAGE | setup | 2 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.segment_criterion | Create a campaign
MarketingService | campaign | launchCampaign | POST | /campaigns/{campaignId}/launch |  | LaunchResult | MARKETING_SEND | setup | 2 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.attribution_touch, marketing.campaign, marketing.campaign_variant | cache:idempotency, marketing.campaign, marketing.message_dispatch | Launch or schedule a campaign
MarketingService | campaign | stopCampaign | POST | /campaigns/{campaignId}/stop |  | Campaign | MARKETING_SEND | setup | 2 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.segment_criterion | Stop a campaign mid-send
MarketingService | campaign | updateCampaign | PATCH | /campaigns/{campaignId} |  | Campaign | MARKETING_MANAGE | setup | 2 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.campaign_target, marketing.segment_criterion | Amend, pause or resume a campaign
MarketingService | case | createCase | POST | /cases | CreateCaseRequest | Case | CASE_MANAGE | core | 1 | SVC-MARKETING-CASE-1 | cache:idempotency, marketing.case | cache:idempotency, marketing.case | Raise a service case
MarketingService | case | listCases | GET | /cases |  | object | CASE_VIEW | core | 1 | SVC-MARKETING-CASE-1 | marketing.case |  | List service cases
MarketingService | consent | claimDeviceConsent | POST | /guests/{subjectId}/consents/claim-device | ClaimDeviceConsentRequest | ConsentState |  | core | 1 | SVC-MARKETING-CONSENT-1 | cache:idempotency, marketing.consent_record, marketing.device_consent, marketing.device_consent_category, marketing.guest_profile, marketing.tracking_technology | cache:idempotency, marketing.consent_propagation, marketing.consent_record, marketing.device_consent, platform.outbox | Attach a browser's cookie decision to the guest who turned out to own it
MarketingService | consent | createConsentQuestion | POST | /consent-questions | ConsentQuestion | ConsentQuestion | GUEST_MANAGE | core | 2 | SVC-MARKETING-CONSENT-1 | marketing.consent_question, marketing.consent_question_version | marketing.consent_question, marketing.consent_question_version | Define a consent question
MarketingService | consent | getCookieConsentRuntime | GET | /storefront/cookie-consent |  | CookieConsentRuntime |  | core | 1 | SVC-MARKETING-CONSENT-1 | marketing.cookie_banner_design, marketing.device_consent, marketing.device_consent_category, marketing.tracking_technology |  | What the page must show and what it may load
MarketingService | consent | getDeviceConsentHistory | GET | /consent/device/history |  | object |  | core | 2 | SVC-MARKETING-CONSENT-1 | marketing.device_consent, marketing.device_consent_category |  | A visitor's own cookie decisions, oldest first
MarketingService | consent | getGuestConsents | GET | /guests/{subjectId}/consents |  | ConsentState | GUEST_VIEW | core | 2 | SVC-MARKETING-CONSENT-2 | marketing.consent_purpose, marketing.consent_record, pii.subject |  | Read a guest's consent state
MarketingService | consent | listConsentAnswers | GET | /consent-answers |  | object | GUEST_VIEW | core | 2 | SVC-MARKETING-CONSENT-2 | marketing.booking_consent_record |  | The consent records given at booking
MarketingService | consent | listConsentPurposes | GET | /consent-purposes |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | cache:resolution, marketing.consent_purpose, marketing.consent_purpose_channel | cache:resolution | Configured consent purposes
MarketingService | consent | listConsentQuestions | GET | /consent-questions |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.consent_question, marketing.consent_question_version |  | The consent questions a venue asks at booking
MarketingService | consent | listPublishedTrackingTechnologies | GET | /storefront/cookie-consent/technologies |  | object |  | core | 2 | SVC-MARKETING-CONSENT-3 | marketing.tracking_technology |  | The approved cookie registry, as the preference centre shows it
MarketingService | consent | recordConsent | POST | /guests/{subjectId}/consents | RecordConsentRequest | ConsentState |  | core | 1 | SVC-MARKETING-CONSENT-3 | cache:idempotency, marketing.consent_record, marketing.guest_profile | cache:idempotency, marketing.consent_propagation, marketing.consent_record, marketing.guest_profile | Record a consent decision
MarketingService | consent | recordConsentAnswers | POST | /consent-answers | RecordConsentAnswersRequest | object | ORDER_CREATE | core | 1 | SVC-MARKETING-CONSENT-3 | marketing.booking_consent_record |  | Answer the consent questions a booking asks
MarketingService | consent | recordDeviceConsent | POST | /consent/device | RecordDeviceConsentRequest | DeviceConsent |  | core | 1 | SVC-MARKETING-CONSENT-3 | cache:idempotency, marketing.cookie_banner_design, marketing.device_consent, marketing.device_consent_category | cache:idempotency, marketing.device_consent, marketing.device_consent_category, pii.consent_identifier, platform.outbox | Record a visitor's cookie decision, before anyone is known
MarketingService | consent | setConsentPurposes | PUT | /consent-purposes |  | array of ConsentPurposeConfig | GUEST_MANAGE | core | 2 | SVC-MARKETING-CONSENT-4 | cache:idempotency, marketing.consent_purpose, marketing.consent_purpose_channel | cache:idempotency, cache:resolution, marketing.consent_purpose, marketing.consent_purpose_channel | Configure consent purposes
MarketingService | consent | setCookieBannerDesign | PUT | /cookie-banner-preference | CookieBannerPreferenceCenterDesignerView | CookieBannerPreferenceCenterDesignerView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | marketing.cookie_banner_design | marketing.cookie_banner_design | Save a cookie banner design as a new version
MarketingService | consent | setTrackingTechnology | PUT | /cookie-tracking-digital | CookieTrackingDigitalTechnologyRegistryView | CookieTrackingDigitalTechnologyRegistryView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | marketing.tracking_technology | marketing.tracking_technology | Add, classify or retire a tracking technology
MarketingService | consent | updateConsentQuestion | PATCH | /consent-questions/{questionId} | ConsentQuestion | ConsentQuestion | GUEST_MANAGE | core | 2 | SVC-MARKETING-CONSENT-4 | marketing.consent_question, marketing.consent_question_version | marketing.consent_question, marketing.consent_question_version | Reword, re-scope or retire a consent question
MarketingService | feedback | submitReview | POST | /reviews | SubmitReviewRequest | Review |  | core | 3 | SVC-MARKETING-FEEDBACK-1 | cache:idempotency, marketing.review | cache:idempotency, marketing.review | Submit a review
MarketingService | guest | addToWishlist | POST | /guests/{subjectId}/wishlist |  | Wishlist |  | core | 1 | SVC-MARKETING-GUEST-1 | cache:idempotency, marketing.wishlist_item | cache:idempotency, marketing.wishlist_item | Save an item
MarketingService | guest | getGuestProfile | GET | /guests/{subjectId} |  | GuestProfileDetail | GUEST_VIEW | core | 1 | SVC-MARKETING-GUEST-1 | marketing.consent_record, marketing.guest_profile, marketing.loyalty_position, pii.subject, pii.subject_contact |  | Read a guest profile
MarketingService | guest | getWishlist | GET | /guests/{subjectId}/wishlist |  | Wishlist |  | core | 1 | SVC-MARKETING-GUEST-1 | marketing.wishlist_item |  | Read a guest's saved items
MarketingService | guest | listGuestDevices | GET | /guests/{subjectId}/devices |  | object |  | core | 1 | SVC-MARKETING-GUEST-1 | marketing.guest_device |  | A guest's registered devices
MarketingService | guest | registerGuestDevice | POST | /guests/{subjectId}/devices |  | GuestDevice |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.guest_device | cache:idempotency, marketing.guest_device | Register a device for push
MarketingService | guest | removeFromWishlist | DELETE | /guests/{subjectId}/wishlist/{itemId} |  |  |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_profile | Remove a saved item
MarketingService | guest | revokeGuestDevice | DELETE | /guests/{subjectId}/devices/{deviceId} |  |  |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_profile | Revoke a device registration
MarketingService | guest | searchGuests | GET | /guests |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-GUEST-2 | marketing.guest_profile |  | Search guest profiles
MarketingService | loyalty | createLoyaltyProgramme | POST | /loyalty/programmes | LoyaltyProgramme | LoyaltyProgramme | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-1 | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | Create a loyalty programme
MarketingService | loyalty | listLoyaltyProgrammes | GET | /loyalty/programmes |  | object | MARKETING_VIEW | core | 2 | SVC-MARKETING-LOYALTY-1 | marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier |  | List loyalty programmes
MarketingService | loyalty | setLoyaltyRules | PUT | /loyalty/programmes/{programmeId}/rules | LoyaltyRuleSet | LoyaltyRuleSet | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-1 | marketing.loyalty_rule, marketing.points_redemption_rule, marketing.programme_tier | marketing.loyalty_rule, marketing.points_redemption_rule, marketing.programme_tier | Replace a programme's rules as one set
MarketingService | marketing | createChallenge | POST | /challenges | Challenge | Challenge | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.event, marketing.challenge, marketing.loyalty_programme | cache:idempotency, marketing.challenge | Define a challenge, mission or streak
MarketingService | marketing | createForm | POST | /forms | FormDefinition | FormDefinition | MARKETING_MANAGE | setup | 2 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.product, marketing.form_definition, marketing.form_definition_field | cache:idempotency, marketing.form_definition, marketing.form_definition_field | Define a waiver, survey or capture form
MarketingService | marketing | createInvitationCampaign | POST | /invitation-campaigns | InvitationCampaign | InvitationCampaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.event, catalogue.product, marketing.invitation_campaign | cache:idempotency, marketing.invitation_campaign | A quota-bounded, addressed invitation
MarketingService | marketing | createReferral | POST | /referrals | Referral | Referral | MARKETING_MANAGE | core | 2 | SVC-MARKETING-MARKETING-1 | cache:idempotency, marketing.guest_profile, marketing.referral, promotions.promotion | cache:idempotency, marketing.referral | Issue a referral code
MarketingService | marketing | getLoyaltyPosition | GET | /loyalty/position |  | object |  | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.loyalty_programme |  | A guest's points, tier and what is within reach
MarketingService | marketing | getMarketingSubscription | GET | /marketing-subscriptions |  | array of MarketingSubscription | MARKETING_VIEW | core | 2 | SVC-MARKETING-MARKETING-2 | marketing.subscription |  | What this guest has opted into
MarketingService | marketing | getMyChallenges | GET | /guests/me/challenges |  | array of object | MARKETING_VIEW | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.challenge, marketing.challenge_progress |  | Active challenges and how far along I am
MarketingService | marketing | getWaiverStatus | GET | /guests/{subjectId}/waiver-status |  | object | GUEST_VIEW | core | 2 | SVC-MARKETING-MARKETING-2 | access.entitlement, catalogue.product, marketing.form_definition, marketing.form_submission |  | Whether this guest may be issued a ticket that requires a waiver
MarketingService | marketing | handoverToAgent | POST | /conversations/{conversationId}/handover |  | Conversation |  | core | 2 | SVC-MARKETING-MARKETING-3 | cache:idempotency, marketing.agent_availability, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | cache:idempotency, marketing.conversation, platform.outbox | Pass an assistant conversation to a person
MarketingService | marketing | identifyGuest | POST | /guests/identify |  | GuestIdentification | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | access.blacklist, access.entitlement, marketing.guest_profile, marketing.loyalty_position, pii.subject |  | Resolve any identifier to a guest
MarketingService | marketing | listMyCases | GET | /my/cases |  | object |  | core | 2 | SVC-MARKETING-MARKETING-3 | marketing.case, pii.subject |  | The cases this guest raised
MarketingService | marketing | raiseMyCase | POST | /my/cases |  | Case |  | core | 2 | SVC-MARKETING-MARKETING-3 | cache:idempotency, marketing.case | cache:idempotency, marketing.case | Report something — lost property, a complaint, a question
MarketingService | marketing | redeemLoyaltyPoints | POST | /loyalty/redemptions |  | LoyaltyPosition | LOYALTY_REDEEM | core | 1 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.loyalty_position, marketing.loyalty_programme | cache:idempotency, marketing.loyalty_position, orders.stored_value_authorisation | Spend points
MarketingService | marketing | replyToMyCase | POST | /my/cases/{caseId}/messages |  | CaseDetail |  | core | 2 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.case, marketing.case_message | cache:idempotency, marketing.case_message | Reply on a case the guest raised
MarketingService | marketing | respondToInvitation | POST | /invitations/{token}/respond |  | Invitation | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.invitation, marketing.invitation_campaign, orders.invitation | cache:idempotency, marketing.invitation | Accept or decline
MarketingService | marketing | sendConversationMessage | POST | /conversations/{conversationId}/messages |  | ConversationMessage | CASE_MANAGE | core | 2 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | cache:idempotency, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | Say something, as a guest or an agent
MarketingService | marketing | setAgentAvailability | PUT | /agent-availability |  | AgentAvailability | CASE_MANAGE | setup | 2 | SVC-MARKETING-MARKETING-5 | cache:idempotency, identity.principal, marketing.agent_availability | cache:idempotency, marketing.agent_availability | An agent goes available, away or offline
MarketingService | marketing | setMarketingSubscription | PUT | /marketing-subscriptions | MarketingSubscription | MarketingSubscription | MARKETING_VIEW | core | 2 | SVC-MARKETING-MARKETING-5 | marketing.subscription | marketing.subscription | Subscribe or unsubscribe
MarketingService | marketing | setSeoMetadata | PUT | /seo-metadata | SeoMetadata | SeoMetadata | MARKETING_MANAGE | core | 2 | SVC-MARKETING-MARKETING-5 | cache:idempotency, catalogue.product, control.seo_metadata | cache:idempotency, cache:resolution, control.seo_metadata | Titles, descriptions, canonicals and hreflang
MarketingService | marketing | updateGuestPreferences | PUT | /guests/{subjectId}/preferences | GuestPreferences | GuestPreferences | GUEST_MANAGE | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.guest_preference, marketing.guest_profile | cache:idempotency, marketing.guest_preference, marketing.guest_profile | The things a regular should not have to say twice
MarketingService | marketing | updateMyProfile | PATCH | /guests/me/profile |  | GuestProfile | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_profile, pii.subject | A guest correcting their own details
MarketingService | marketing | uploadGuestDocument | POST | /guest-documents | GuestDocument | GuestDocument | GUEST_VIEW_PII | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, marketing.consent_record, marketing.guest_document, pii.subject | cache:idempotency, marketing.guest_document | Store a guest photo, ID or signed document
MarketingService | message | createMessageTemplate | POST | /message-templates | MessageTemplate | MessageTemplate | MARKETING_MANAGE | setup | 2 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_template | cache:idempotency, marketing.message_template, marketing.message_template_version | Create a message template
MarketingService | message | listMyNotifications | GET | /me/notifications |  | object |  | core | 2 | SVC-MARKETING-MESSAGE-1 | marketing.message_dispatch |  | The signed-in guest's notification feed
MarketingService | message | markMyNotificationsRead | POST | /me/notifications/read |  | object |  | core | 2 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_dispatch | cache:idempotency, marketing.message_dispatch | Mark the signed-in guest's notifications read
MarketingService | segment | createSegment | POST | /segments | CreateSegmentRequest | Segment | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-SEGMENT-1 | cache:idempotency, marketing.segment, marketing.segment_criterion | cache:idempotency, marketing.segment, marketing.segment_criterion | Create a segment
OrderService | cart | abandonCart | DELETE | /carts/{cartId} |  |  |  | core | 1 | SVC-ORDER-CART-1 | cache:idempotency, orders.cart | cache:idempotency, catalogue.inventory_hold, orders.cart | Empty it deliberately
OrderService | cart | addCartLine | POST | /carts/{cartId}/lines | AddCartLineRequest | Cart |  | core | 1 | SVC-ORDER-CART-1 | catalogue.channel_capacity, catalogue.performance, catalogue.variant, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | orders.cart, orders.cart_line, platform.idempotency_record | Add something
OrderService | cart | applyCartPromoCode | POST | /carts/{cartId}/promo-codes | ApplyCartPromoCodeRequest | Cart |  | core | 1 | SVC-ORDER-CART-1 | marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, promotions.coupon_campaign, promotions.coupon_code | orders.cart, orders.cart_line | Apply a promo code to the cart
OrderService | cart | checkoutCart | POST | /carts/{cartId}/checkout |  | Order |  | core | 1 | SVC-ORDER-CART-1 | catalogue.inventory_hold, marketing.consent_question, orders.cart, orders.cart_line, orders.fraud_rule, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | marketing.consent_record, orders.cart, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.sales_order, platform.idempotency_record, platform.outbox | Turn the cart into an order
OrderService | cart | claimCart | POST | /carts/{cartId}/claim |  | CartMergeResult |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, pii.subject | cache:idempotency, orders.cart, orders.cart_line | Attach an anonymous cart to a guest
OrderService | cart | createCart | POST | /carts |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, pii.subject, platform.scope | cache:idempotency, orders.cart | Start a cart
OrderService | cart | extendCart | POST | /carts/{cartId}/extend |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, catalogue.inventory_hold, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_hold, orders.cart | Give the guest more time
OrderService | cart | getCart | GET | /carts/{cartId} |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | catalogue.channel_capacity, catalogue.inventory_hold, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, promotions.promotion |  | The cart, priced and checked, right now
OrderService | cart | removeCartLine | DELETE | /carts/{cartId}/lines/{lineId} |  | Cart |  | core | 1 | SVC-ORDER-CART-3 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_hold, orders.cart_line | Take something out
OrderService | cart | updateCartLine | PATCH | /carts/{cartId}/lines/{lineId} |  | Cart |  | core | 1 | SVC-ORDER-CART-3 | cache:idempotency, catalogue.channel_capacity, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_hold, orders.cart_line | Change a quantity
OrderService | cash | createCashMovement | POST | /shifts/{shiftId}/cash-movements | CreateCashMovementRequest | CashMovement | CASH_LIFT | core | 1 | SVC-ORDER-CASH-1 | cache:idempotency, orders.cash_count_line, orders.cash_movement | cache:idempotency, orders.cash_count_line, orders.cash_movement | Record a cash lift or add
OrderService | cash | listCashMovements | GET | /shifts/{shiftId}/cash-movements |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-CASH-1 | orders.cash_count_line, orders.cash_movement |  | Lifts, adds and the opening float
OrderService | dunning | listMyPaymentIssues | GET | /guests/me/payment-issues |  | object |  | core | 2 | SVC-ORDER-DUNNING-1 | payments.dunning_case |  | A guest's own failed recurring payments
OrderService | dunning | retryMyDunningPayment | POST | /dunning-cases/{caseId}/retry | RetryDunningPaymentRequest | DunningCase |  | core | 2 | SVC-ORDER-DUNNING-1 | cache:idempotency, payments.dunning_case | cache:idempotency, payments.dunning_case | Retry a declined membership payment now
OrderService | order | appendEntitlementToMedia | POST | /media/{mediaCode}/entitlements | AppendEntitlementRequest | AppendEntitlementResult | ORDER_CREATE | core | 1 | SVC-ORDER-ORDER-1 | access.entitlement, cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | access.entitlement, cache:idempotency, orders.order_line, orders.payment, orders.sales_order | Add something to a ticket the guest already holds
OrderService | order | applyManualDiscount | POST | /orders/{orderId}/discounts | ManualDiscountRequest | Order | ORDER_DISCOUNT | core | 1 | SVC-ORDER-ORDER-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_line, orders.payment, orders.sales_order | Apply a discount a cashier chose
OrderService | order | claimTicketTransfer | POST | /ticket-transfers/{transferId}/claim |  | TicketTransfer |  | core | 1 | SVC-ORDER-ORDER-1 | access.entitlement, cache:idempotency, orders.ticket_transfer | access.entitlement, cache:idempotency, orders.ticket_transfer, platform.outbox | Claim transferred tickets
OrderService | order | createOrder | POST | /orders | CreateOrderRequest | Order | ORDER_CREATE | core | 1 | SVC-ORDER-ORDER-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, promotions.promotion_evaluation_trace | Create an order
OrderService | order | exchangeOrderLines | POST | /orders/{orderId}/exchanges | ExchangeOrderRequest | OrderExchangeResult | ORDER_EXCHANGE | core | 1 | SVC-ORDER-ORDER-2 | cache:idempotency, orders.sales_order | cache:idempotency, orders.order_event, orders.sales_order, platform.outbox | Exchange lines for different products or dates
OrderService | order | getMediaEntitlements | GET | /media/{mediaCode}/entitlements |  | MediaEntitlements | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | access.entitlement, access.scan_event, catalogue.entitlement_template, orders.sales_order, pii.subject |  | What is already on this media
OrderService | order | getOrder | GET | /orders/{orderId} |  | Order | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order |  | Read an order
OrderService | order | getOrderCalendarEvent | GET | /orders/{orderId}/calendar-event |  | string | ORDER_VIEW | core | 3 | SVC-ORDER-ORDER-2 | orders.order_line, orders.sales_order, platform.scope |  | The visit as a calendar entry
OrderService | order | getOrderStatement | GET | /orders/{orderId}/statement |  | OrderStatement | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | ledger.posting, orders.payment, orders.refund, orders.sales_order |  | Full financial history of an order
OrderService | order | getVisitReminder | GET | /orders/{orderId}/reminder |  | VisitReminder | ORDER_VIEW | core | 3 | SVC-ORDER-ORDER-3 | orders.visit_reminder |  | The guest's reminder for this booking
OrderService | order | holdOrder | POST | /orders/{orderId}/hold |  | Order | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-3 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Park a sale and free the till
OrderService | order | listOrders | GET | /orders |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | orders.order_line, orders.sales_order |  | List orders
OrderService | order | modifyOrder | POST | /orders/{orderId}/modify | ModifyOrderRequest | OrderModificationResult | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Add or remove lines on an existing order
OrderService | order | reprintOrder | POST | /orders/{orderId}/reprints |  | object | ORDER_REPRINT | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.sales_order | cache:idempotency, orders.sales_order | Reprint or resend tickets
OrderService | order | rescheduleOrder | POST | /orders/{orderId}/reschedule |  | OrderExchangeResult | ORDER_RESCHEDULE | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.sales_order | cache:idempotency, orders.order_event, orders.sales_order | Move an order to another performance
OrderService | order | resumeOrder | POST | /orders/{orderId}/resume |  | OrderResumeResult | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Bring a parked sale back to a till
OrderService | order | setVisitReminder | PUT | /orders/{orderId}/reminder | VisitReminder | VisitReminder | ORDER_VIEW | core | 3 | SVC-ORDER-ORDER-5 | orders.visit_reminder | orders.visit_reminder | Turn a visit reminder on or off
OrderService | order | transferOrderTickets | POST | /orders/{orderId}/transfer |  | TicketTransfer |  | core | 1 | SVC-ORDER-ORDER-5 | access.entitlement, cache:idempotency, orders.ticket_transfer | access.entitlement, cache:idempotency, orders.ticket_transfer | Transfer tickets to another guest
OrderService | order | voidOrder | POST | /orders/{orderId}/voids |  | Order | ORDER_VOID | core | 1 | SVC-ORDER-ORDER-5 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, platform.outbox | Void an order
OrderService | orders | createResaleListing | POST | /resale-listings | CreateResaleListingRequest | ResaleListing | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-1 | access.entitlement, cache:idempotency, catalogue.entitlement_template, orders.resale_listing, orders.sales_order | cache:idempotency, orders.resale_listing, platform.outbox | List an entitlement for resale
OrderService | orders | createTicketTemplate | POST | /ticket-templates | TicketTemplateRequest | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-1 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template | Create a ticket template
OrderService | orders | getBillingStatement | GET | /billing-statements/{statementId} |  | BillingStatement | ORDER_VIEW | core | 2 | SVC-ORDER-ORDERS-1 | ledger.tax_invoice_line, orders.payment, orders.sales_order, payments.dunning_case |  | One statement, with its lines
OrderService | orders | getGroupBooking | GET | /group-bookings/{groupBookingId} |  | GroupBooking | ORDER_VIEW | core | 2 | SVC-ORDER-ORDERS-1 | orders.group_booking, orders.sales_order, pii.subject |  | A group, its leader and its name-capture duty
OrderService | orders | getPaymentLink | GET | /payment-links/{token} |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment_link, orders.reservation, orders.sales_order, platform.scope |  | What a guest holding a link is being asked to pay for
OrderService | orders | issueWalletPass | POST | /wallet-passes |  | WalletPass | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | access.entitlement, cache:idempotency, orders.ticket_template, orders.wallet_pass | cache:idempotency, orders.wallet_pass | Generate an Apple or Google wallet pass
OrderService | orders | listBillingStatements | GET | /billing-statements |  | object | ORDER_VIEW | core | 2 | SVC-ORDER-ORDERS-2 | orders.payment, orders.sales_order, payments.dunning_case |  | What was charged, when, and against which agreement
OrderService | orders | listMyOrders | GET | /my/orders |  | object |  | core | 1 | SVC-ORDER-ORDERS-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order, pii.subject |  | The orders this guest placed
OrderService | orders | listPaymentTokens | GET | /payment-tokens |  | object | ORDER_VIEW | core | 2 | SVC-ORDER-ORDERS-3 | payments.token |  | A guest's saved payment methods
OrderService | orders | payByLink | POST | /payment-links/{token}/pay |  | object | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-3 | cache:idempotency, orders.payment_link, orders.reservation, orders.sales_order, payments.provider | access.entitlement, cache:idempotency, orders.payment, orders.payment_link, orders.reservation, orders.sales_order | Pay for a booking taken at a till
OrderService | orders | reissueEntitlement | POST | /entitlements/{entitlementId}/reissue |  | ReissuedEntitlement | ORDER_EXCHANGE | core | 1 | SVC-ORDER-ORDERS-3 | access.entitlement, cache:idempotency, catalogue.product | access.entitlement, cache:idempotency | Zero-value reissue of an expired entitlement for a later date
OrderService | orders | requestGroupBooking | POST | /group-booking-requests | GroupBookingRequest | GroupBooking |  | core | 2 | SVC-ORDER-ORDERS-3 | cache:idempotency, catalogue.group_package, catalogue.product, orders.group_booking | cache:idempotency, orders.group_booking, orders.sales_order | Ask for a school trip or a birthday party
OrderService | orders | setPaymentProvider | PUT | /payment-providers | SetPaymentProviderRequest | PaymentProvider | TENANT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-4 | cache:idempotency, payments.provider | cache:idempotency, payments.provider, payments.routing_rule | Configure a gateway and its routing
OrderService | orders | shareEntitlement | POST | /entitlements/{entitlementId}/share |  | EntitlementShare | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDERS-4 | access.entitlement, cache:idempotency, catalogue.entitlement_template, identity.delegated_access | access.entitlement, cache:idempotency, identity.delegated_access | Let somebody else use this, without giving it away
OrderService | orders | storePaymentToken | POST | /payment-tokens |  | PaymentToken | ORDER_CREATE | core | 2 | SVC-ORDER-ORDERS-4 | cache:idempotency, marketing.consent_record, payments.provider, payments.token | cache:idempotency, marketing.consent_record, payments.token | Save a payment method for future use
OrderService | orders | updateTicketTemplate | PATCH | /ticket-templates/{templateId} | TicketTemplateRequest | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-4 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template | Change or retire a ticket template
OrderService | payment | addTip | POST | /payments/{paymentId}/tip |  | Payment | ORDER_MODIFY | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, orders.payment | cache:idempotency, orders.payment | Record a tip against a payment
OrderService | payment | capturePayment | POST | /payments/{paymentId}/capture |  | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | ledger.fx_rate, orders.payment, payments.provider_connection | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_hold, ledger.journal_entry, ledger.journal_line, orders.order_event, orders.payment, payments.payment_attempt, platform.idempotency_record, platform.outbox | Capture a previously authorised payment
OrderService | payment | createPayment | POST | /payments | CreatePaymentRequest | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | catalogue.inventory_hold, ledger.fx_rate, orders.order_line, orders.payment, orders.sales_order, payments.provider_connection | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_hold, ledger.journal_entry, ledger.journal_line, orders.order_event, orders.payment, payments.payment_attempt, platform.idempotency_record, platform.outbox | Take a payment against an order
OrderService | payment | inquirePaymentStatus | POST | /payments/{paymentId}/inquiry |  | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, orders.payment | cache:idempotency, orders.payment, platform.outbox | Ask the provider what actually happened
OrderService | payments | createInstalmentPlan | POST | /instalment-plans |  | PayInstalmentPlan | ORDER_CREATE | core | 2 | SVC-ORDER-PAYMENTS-1 | cache:idempotency, orders.payment, orders.sales_order, payments.instalment, payments.instalment_plan, payments.instalment_policy, payments.token | cache:idempotency, orders.payment, payments.instalment, payments.instalment_plan, platform.outbox | Split an order's payment into scheduled instalments on a stored card
OrderService | payments | createPaymentProviderConnection | POST | /payment-providers | PaymentProviderConnection | PaymentProviderConnection | PAYMENT_PROVIDER_MANAGE | setup | 1 | SVC-ORDER-PAYMENTS-1 | payments.provider_connection | payments.provider_connection | Connect a provider
OrderService | payments | listInstalmentPlans | GET | /instalment-plans |  | object | PAYMENT_VIEW | core | 2 | SVC-ORDER-PAYMENTS-1 | payments.instalment, payments.instalment_plan |  | Instalment plans and their schedules
OrderService | payments | setInstalmentPolicy | PUT | /instalment-policy | PayInstalmentPolicy | PayInstalmentPolicy | PAYMENT_CONFIGURE | setup | 2 | SVC-ORDER-PAYMENTS-1 | cache:idempotency, payments.instalment_policy | cache:idempotency, cache:resolution, payments.instalment_policy | Set which products may be paid in instalments, how many and how often
OrderService | policy | setRefundPolicy | PUT | /venues/{venueId}/refund-policy | RefundPolicy | RefundPolicy | REGION_CONFIGURE | setup | 1 | SVC-ORDER-POLICY-1 | cache:idempotency, orders.refund_policy, orders.refund_policy_time_band | cache:idempotency, cache:resolution, orders.refund_policy, orders.refund_policy_time_band | Set a venue's refund policy
OrderService | refund | createRefund | POST | /orders/{orderId}/refunds | CreateRefundRequest | Refund | ORDER_REFUND | core | 1 | SVC-ORDER-REFUND-1 | cache:idempotency, orders.fraud_rule, orders.payment, orders.refund, orders.sales_order | cache:idempotency, ledger.journal_entry, ledger.posting, orders.order_event, orders.refund, platform.outbox | Refund an order, wholly or in part
OrderService | refund | createRefundRequest | POST | /refund-requests |  | object |  | core | 1 | SVC-ORDER-REFUND-1 | cache:idempotency, orders.fraud_rule, orders.refund_policy, orders.sales_order | cache:idempotency, orders.refund | Guest-initiated refund request
OrderService | refund | listOrderRefunds | GET | /orders/{orderId}/refunds |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-REFUND-1 | orders.refund |  | List refunds against an order
OrderService | reservation | cancelReservation | DELETE | /reservations/{reservationId} |  |  | ORDER_CANCEL | core | 2 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation | cache:idempotency, orders.order_event, orders.reservation | Cancel a reservation
OrderService | reservation | getReservation | GET | /reservations/{reservationId} |  | Reservation | ORDER_VIEW | core | 2 | SVC-ORDER-RESERVATION-1 | orders.reservation, orders.reservation_line |  | Read a reservation
OrderService | reservation | listReservations | GET | /reservations |  | object | ORDER_VIEW | core | 2 | SVC-ORDER-RESERVATION-1 | orders.reservation, orders.reservation_line |  | List reservations
OrderService | shift | acceptShiftVariance | POST | /shifts/{shiftId}/accept-variance |  | Shift | OVERSHORT_ACCEPT | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift, platform.outbox | Accept an over/short beyond the threshold
OrderService | shift | adjustDepositBoxFloat | POST | /deposit-boxes/{boxId}/adjust-float |  | DepositBox | CASH_ADD | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | cache:idempotency, orders.cash_movement, orders.deposit_box | Change the initial fund
OrderService | shift | allocateDepositBox | POST | /deposit-boxes | DepositBox | DepositBox | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, identity.principal, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, platform.workstation | cache:idempotency, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | Give a cashier a box and a float
OrderService | shift | approveShiftOpen | POST | /shifts/{shiftId}/approve-open |  | Shift | SHIFT_APPROVE_OPEN | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Approve a shift opening outside tolerance
OrderService | shift | closeDepositBoxes | POST | /deposit-boxes/close |  | array of DepositBox | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-2 | cache:idempotency, ledger.fx_rate, orders.cash_count_line, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | cache:idempotency, ledger.posting, orders.cash_count_line, orders.deposit_box | Close one box or all of them
OrderService | shift | closeShift | POST | /shifts/{shiftId}/close | CloseShiftRequest | ShiftCloseResult | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-2 | cache:idempotency, ledger.fx_rate, orders.cash_count_line, orders.cash_movement, orders.payment, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.venue_settings | cache:idempotency, ledger.journal_entry, orders.cash_count_line, orders.pos_shift | Blind close-out
OrderService | shift | getCurrentShift | GET | /shifts/current |  | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-2 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | The open or suspended shift on the session's workstation
OrderService | shift | getShift | GET | /shifts/{shiftId} |  | Shift | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-2 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | Read a shift
OrderService | shift | listDenominations | GET | /denominations |  | array of Denomination | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | platform.denomination, platform.region_settings |  | The notes and coins a till counts
OrderService | shift | listDepositBoxes | GET | /deposit-boxes |  | object | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | identity.principal, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination |  | Cash boxes and who holds them
OrderService | shift | listShifts | GET | /shifts |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-3 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | List shifts
OrderService | shift | openShift | POST | /shifts | OpenShiftRequest | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | cache:idempotency, identity.principal, orders.cash_count_line, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.venue_settings, platform.workstation | cache:idempotency, orders.cash_count_line, orders.pos_shift | Open a shift
OrderService | shift | recordNoSale | POST | /shifts/{shiftId}/no-sale |  | NoSaleEvent | CASH_NO_SALE | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.no_sale_event | cache:idempotency, orders.no_sale_event | Open the Deposit Box without a sale
OrderService | shift | reopenShift | POST | /shifts/{shiftId}/reopen |  | Shift | SHIFT_REOPEN | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Reopen a shift closed in error
OrderService | shift | resumeShift | POST | /shifts/{shiftId}/resume |  | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Resume a suspended shift
OrderService | shift | setDenominations | PUT | /denominations | SetDenominationsRequest | array of Denomination | REGION_CONFIGURE | setup | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, platform.denomination | cache:idempotency, platform.denomination | Set the notes and coins a region's tills count
OrderService | shift | suspendShift | POST | /shifts/{shiftId}/suspend |  | Shift | SHIFT_SUSPEND | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Suspend a shift so another user can log in
OrderService | shift | withdrawFromDepositBox | POST | /deposit-boxes/{boxId}/withdraw |  | DepositBox | CASH_LIFT | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | cache:idempotency, orders.cash_movement, orders.deposit_box | A supervisor takes cash out mid-shift
OrderService | sync | syncOrders | POST | /sync/orders |  | OrderSyncResult | ORDER_CREATE | core | 1 | SVC-ORDER-SYNC-1 | catalogue.inventory_hold, catalogue.price_list, catalogue.variant, orders.sales_order | catalogue.channel_capacity, catalogue.inventory_hold, ledger.price_variance, orders.order_line, orders.order_line_discount, orders.payment, orders.sales_order, platform.idempotency_record, platform.outbox, sync.rejection | Replay orders recorded offline
PlatformService | licensing | addLicenceAddOn | POST | /tenants/{tenantId}/licences/add-ons | LicenceAddOn | LicencePosition | PLATFORM_TENANT_MANAGE | setup | 2 | SVC-PLATFORM-LICENSING-1 | cache:idempotency, control.licence_add_on | cache:idempotency, control.licence_add_on, control.licence_add_on_limit | License a module outside the plan
PlatformService | plan | createPlan | POST | /plans | CreatePlanRequest | Plan | PLATFORM_PLAN_MANAGE | setup | 2 | SVC-PLATFORM-PLAN-1 | cache:idempotency, control.tenant, subscription.plan, subscription.plan_limit, subscription.plan_module | cache:idempotency, subscription.plan, subscription.plan_limit | Create a subscription plan
PlatformService | plan | createPlanVersion | POST | /plans/{planId} | CreatePlanRequest | Plan | PLATFORM_PLAN_MANAGE | setup | 2 | SVC-PLATFORM-PLAN-1 | cache:idempotency, control.tenant, subscription.plan, subscription.plan_limit, subscription.plan_module | cache:idempotency, subscription.plan, subscription.plan_limit | Publish a new version of a plan
PlatformService | publicApi | certifyIntegration | POST | /listings/{listingId}/certify |  | IntegrationListing | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_version, control.integration_listing | cache:idempotency, control.integration_listing | Approve, reject or revoke a certification
PlatformService | publicApi | createApiClient | POST | /api-clients | ApiClient | object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_client, control.api_licence, control.developer_account, control.integration_listing | cache:idempotency, control.api_client | Create a client with scopes and an environment
PlatformService | publicApi | decideProductionAccess | POST | /production-access-requests/{requestId}/decide |  | ProductionAccessRequest | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.integration_listing, control.production_access_request | cache:idempotency, control.api_client, control.production_access_request | Approve or reject production access
PlatformService | publicApi | deprecateApiVersion | POST | /api-versions/{version}/deprecate |  | ApiVersion | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_client, control.api_version | cache:idempotency, control.api_version, marketing.message_dispatch | Announce a sunset date and notify subscribers
PlatformService | publicApi | registerDeveloper | POST | /developers | DeveloperAccount | DeveloperAccount | DEVELOPER_VIEW | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.developer_account | cache:idempotency, control.developer_account | Register a developer or organisation
PlatformService | publicApi | rotateApiCredential | POST | /api-clients/{clientId}/credentials |  | object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_client | cache:idempotency, control.api_client | Issue a new secret, with an overlap window
PlatformService | publicApi | setApiLicensing | PUT | /api-licensing | ApiLicence | ApiLicence | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_licence | cache:idempotency, cache:resolution, control.api_licence | Which API modules a tenant has licensed, and on what terms
PlatformService | publicApi | setDeveloperMembers | PUT | /developers/{developerId}/members |  | array of object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.developer_account, identity.principal | cache:idempotency, control.developer_account, identity.delegated_access | Who at this organisation may do what
PlatformService | subscription | setSubscription | PUT | /tenants/{tenantId}/subscription | SetSubscriptionRequest | Subscription | PLATFORM_TENANT_MANAGE | setup | 2 | SVC-PLATFORM-SUBSCRIPTION-1 | cache:idempotency, subscription.contract, subscription.plan | cache:idempotency, subscription.contract | Assign or change a subscription
PlatformService | tenant | createTenant | POST | /tenants | CreateTenantRequest | Tenant | PLATFORM_TENANT_MANAGE | setup | 2 | SVC-PLATFORM-TENANT-1 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Create a tenant
PlatformService | tenant | listTenants | GET | /tenants |  | object | PLATFORM_TENANT_VIEW | core | 2 | SVC-PLATFORM-TENANT-1 | control.tenant |  | List tenants
PlatformService | tenant | reactivateTenant | POST | /tenants/{tenantId}/reactivate |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 2 | SVC-PLATFORM-TENANT-1 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Lift a suspension
PlatformService | tenant | suspendTenant | POST | /tenants/{tenantId}/suspend |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 2 | SVC-PLATFORM-TENANT-1 | cache:idempotency, control.tenant | cache:idempotency, control.tenant, platform.outbox | Suspend a tenant
PlatformService | tenant | terminateTenant | POST | /tenants/{tenantId}/terminate |  | TerminationSchedule | PLATFORM_TENANT_TERMINATE | setup | 2 | SVC-PLATFORM-TENANT-2 | cache:idempotency, control.tenant, subscription.contract | cache:idempotency, control.tenant, subscription.contract | Begin termination
PlatformService | tenant | updateTenant | PATCH | /tenants/{tenantId} |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 2 | SVC-PLATFORM-TENANT-2 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Amend tenant details
ReportingService | catalogue | createReport | POST | /reports | CreateReportRequest | ReportDefinition | REPORT_MANAGE | setup | 2 | SVC-REPORTING-CATALOGUE-1 | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter | Create a custom report definition
ReportingService | catalogue | deleteReport | DELETE | /reports/{reportId} |  |  | REPORT_MANAGE | core | 2 | SVC-REPORTING-CATALOGUE-1 | cache:idempotency, reporting.report_definition | cache:idempotency, reporting.report_definition | Retire a report definition
ReportingService | catalogue | getReport | GET | /reports/{reportId} |  | ReportDefinition | REPORT_VIEW_VENUE | core | 2 | SVC-REPORTING-CATALOGUE-1 | reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter |  | Read a report definition
ReportingService | catalogue | listReports | GET | /reports |  | object | REPORT_VIEW_VENUE | core | 2 | SVC-REPORTING-CATALOGUE-1 | reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter |  | List available report definitions
ReportingService | catalogue | updateReport | PUT | /reports/{reportId} | CreateReportRequest | ReportDefinition | REPORT_MANAGE | setup | 2 | SVC-REPORTING-CATALOGUE-2 | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter | Publish a new version of a definition
ReportingService | dashboard | createDashboard | POST | /dashboards | CreateDashboardRequest | Dashboard | REPORT_MANAGE | setup | 2 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | Create a dashboard
ReportingService | dashboard | getDashboard | GET | /dashboards/{dashboardId} |  | DashboardData | REPORT_VIEW_VENUE | core | 2 | SVC-REPORTING-DASHBOARD-1 | reporting.dashboard, reporting.dashboard_tile |  | Read a dashboard with tile data
ReportingService | dashboard | recordDashboardView | POST | /dashboards/{dashboardId}/views |  |  | REPORT_VIEW_VENUE | core | 2 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard | cache:idempotency, reporting.dashboard_view | Record that a dashboard was opened
ReportingService | dashboard | updateDashboard | PUT | /dashboards/{dashboardId} | CreateDashboardRequest | Dashboard | REPORT_MANAGE | setup | 2 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | Update a dashboard
ReportingService | execution | runReport | POST | /reports/{reportId}/run | RunReportRequest | ReportResult | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-EXECUTION-1 | cache:idempotency, reporting.execution, reporting.report_definition, reporting.report_parameter | cache:idempotency, reporting.execution | Run a report
ReportingService | naturalLanguage | askReportingQuestion | POST | /reports/ask |  | NaturalLanguageAnswer | REPORT_VIEW_VENUE | core | 2 | SVC-REPORTING-NATURALLANGUAGE-1 | ai.policy, ai.provider, cache:idempotency, reporting.kpi_definition, reporting.natural_language_query, reporting.report_column, reporting.report_filter, reporting.semantic_model | ai.activity, cache:idempotency, reporting.natural_language_query, reporting.report_column, reporting.report_filter | Natural-language reporting query
ReportingService | naturalLanguage | saveNaturalLanguageQuery | POST | /reports/ask/{conversationId}/save |  | ReportDefinition | REPORT_MANAGE | core | 2 | SVC-REPORTING-NATURALLANGUAGE-1 | ai.policy, ai.provider, cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | ai.activity, cache:idempotency, reporting.natural_language_query, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | Save a natural-language answer as a report definition
ReportingService | reporting | createKpi | POST | /kpis | KpiDefinition | KpiDefinition | REPORT_MANAGE | setup | 2 | SVC-REPORTING-REPORTING-1 | reporting.kpi_definition | reporting.kpi_definition | Define a KPI once, for everywhere
ReportingService | reporting | deleteDashboard | DELETE | /dashboards/{dashboardId} |  |  | REPORT_MANAGE | setup | 2 | SVC-REPORTING-REPORTING-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard | Archive a dashboard
ReportingService | reporting | listAlerts | GET | /alerts |  | array of Alert | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-REPORTING-1 | reporting.alert, reporting.alert_rule |  | What is currently wrong
ReportingService | reporting | setAlertRule | PUT | /alert-rules | AlertRule | AlertRule | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | cache:idempotency, identity.role, reporting.alert_rule | cache:idempotency, reporting.alert_rule | Watch a metric and tell somebody
ReportingService | reporting | setSemanticModel | PUT | /semantic-model | SemanticModel | SemanticModel | REPORT_MANAGE | setup | 2 | SVC-REPORTING-REPORTING-2 | reporting.semantic_model | reporting.semantic_model | Publish the catalogue
RetailService | floor | lookupMerchandise | GET | /merchandise/lookup |  | PriceCheck | PRODUCT_VIEW | core | 1 | SVC-RETAIL-FLOOR-1 | retail.merchandise |  | Price and stock check by barcode
RetailService | floor | lookupShopAndDrop | GET | /shop-and-drop/lookup |  | array of ShopAndDrop | ORDER_VIEW | core | 2 | SVC-RETAIL-FLOOR-1 | retail.shop_and_drop, retail.shop_and_drop_line |  | Find a guest's dropped goods
RetailService | floor | reserveMerchandise | POST | /outlets/{outletId}/reserve |  | MerchandiseReservation | ORDER_CREATE | core | 1 | SVC-RETAIL-FLOOR-1 | cache:idempotency, retail.reservation, retail.reservation_line | cache:idempotency, retail.reservation, retail.reservation_line | Reserve an item for collection
RetailService | merchandise | createMerchandise | POST | /merchandise | CreateMerchandiseRequest | MerchandiseItem | PRODUCT_CONFIGURE | setup | 1 | SVC-RETAIL-MERCHANDISE-1 | cache:idempotency, retail.merchandise | cache:idempotency, retail.merchandise | Create a merchandise item
RetailService | merchandise | listMerchandise | GET | /merchandise |  | object | PRODUCT_VIEW | core | 1 | SVC-RETAIL-MERCHANDISE-1 | retail.merchandise |  | List merchandise
RetailService | merchandise | updateMerchandise | PATCH | /merchandise/{merchandiseId} |  | MerchandiseItem | PRODUCT_CONFIGURE | setup | 1 | SVC-RETAIL-MERCHANDISE-1 | cache:idempotency, retail.merchandise | cache:idempotency, retail.merchandise | Amend a merchandise item
RetailService | return | createRetailReturn | POST | /retail-returns | CreateRetailReturnRequest | RetailReturn | ORDER_REFUND | core | 1 | SVC-RETAIL-RETURN-1 | cache:idempotency, inventory.kit_component, retail.return, retail.return_line | cache:idempotency, inventory.movement, retail.return, retail.return_line | Accept a return
RetailService | return | getReturnPolicy | GET | /outlets/{outletId}/return-policy |  | ReturnPolicy | ORDER_VIEW | core | 1 | SVC-RETAIL-RETURN-1 | cache:resolution, retail.return_policy | cache:resolution | Read the retail return policy
RetailService | return | lookupRetailSale | GET | /retail-sales/lookup |  | object | ORDER_VIEW | core | 1 | SVC-RETAIL-RETURN-1 | retail.sale, retail.sale_line |  | Find a sale from a receipt
RetailService | return | setReturnPolicy | PUT | /outlets/{outletId}/return-policy | ReturnPolicy | ReturnPolicy | REGION_CONFIGURE | setup | 1 | SVC-RETAIL-RETURN-1 | cache:idempotency, retail.return_policy | cache:idempotency, cache:resolution, retail.return_policy | Set the retail return policy
RetailService | sale | createRetailSale | POST | /retail-sales | CreateRetailSaleRequest | RetailSale | ORDER_CREATE | core | 1 | SVC-RETAIL-SALE-1 | cache:idempotency, inventory.kit_component, retail.sale, retail.sale_line | cache:idempotency, inventory.movement, retail.sale, retail.sale_line | Sell merchandise
RetailService | sale | getRetailSale | GET | /retail-sales/{saleId} |  | RetailSale | ORDER_VIEW | core | 1 | SVC-RETAIL-SALE-1 | retail.sale, retail.sale_line |  | Read a retail sale
RetailService | sale | listRetailSales | GET | /retail-sales |  | object | ORDER_VIEW | core | 1 | SVC-RETAIL-SALE-1 | retail.sale, retail.sale_line |  | List retail sales
RetailService | sale | reprintReceipt | POST | /retail-sales/{saleId}/reprint |  | object | ORDER_REPRINT | core | 1 | SVC-RETAIL-SALE-1 | cache:idempotency, retail.sale | cache:idempotency, retail.sale | Reprint or resend a receipt
TenancyService | approvals | approveMatrixMultiLevel | PUT | /matrix-multi-level | ApprovalMatrixMultiLevelApprovalConfigurationInput | ApprovalMatrixMultiLevelApprovalConfigurationView | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-APPROVALS-1 | approvals.matrix, approvals.rule, cache:idempotency | approvals.matrix, approvals.rule, cache:idempotency | Approval Matrix & Multi-Level Approval Configuration
TenancyService | approvals | approveRoleAuthorityDelegation | PUT | /role-authority-delegation | RolesAuthorityDelegationApprovalLimitsInput | RolesAuthorityDelegationApprovalLimitsView | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-APPROVALS-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, identity.principal | approvals.delegation, cache:idempotency | Roles, Authority, Delegation & Approval Limits
TenancyService | delegation | createApprovalDelegation | POST | /delegations | ApprovalDelegation | ApprovalDelegation | APPROVAL_DECIDE | setup | 1 | SVC-TENANCY-DELEGATION-1 | approvals.delegation, cache:idempotency, identity.delegated_access, identity.principal | approvals.delegation, cache:idempotency | Delegate approval authority
TenancyService | devices | setDeviceAssignment | PUT | /devices/{deviceId}/assignment | DeviceAssignment | DeviceAssignment | DEVICE_MANAGE | core | 1 | SVC-TENANCY-DEVICES-1 | tenancy.device_assignment | tenancy.device_assignment | Who owns it, who holds it, and where it is
TenancyService | matrix | setApprovalExternalProvider | PUT | /approval-external-providers | ApprovalExternalProvider | ApprovalExternalProvider | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-MATRIX-1 | approvals.external_provider, cache:idempotency, control.api_client | approvals.external_provider, cache:idempotency | Register a third-party workflow system as an approver
TenancyService | matrix | setApprovalMatrix | PUT | /approval-matrices | ApprovalMatrix | ApprovalMatrix | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-MATRIX-1 | approvals.external_provider, approvals.matrix, approvals.rule, cache:idempotency | approvals.matrix, approvals.rule, cache:idempotency | Configure what requires approval
TenancyService | region | updateRegionSettings | PUT | /regions/{regionId}/settings | RegionSettings | RegionSettings | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-REGION-1 | cache:idempotency, platform.region_settings | cache:idempotency, cache:resolution, platform.region_settings | Update region settings
TenancyService | request | createApprovalRequest | POST | /approval-requests | CreateApprovalRequest | ApprovalRequest | APPROVAL_REQUEST | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.delegation, approvals.matrix, approvals.request, approvals.rule, cache:idempotency, identity.principal | approvals.request, cache:idempotency | Raise a request
TenancyService | request | decideApprovalRequest | POST | /approval-requests/{requestId}/decide |  | ApprovalRequest | APPROVAL_DECIDE | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.request, approvals.rule, cache:idempotency, identity.principal | approvals.decision, approvals.request, cache:idempotency, control.partner_agreement, control.partner_application, control.partner_change_request, marketing.privacy_notice_governance, platform.outbox | Approve, reject, return or ask for information
TenancyService | request | evaluateApprovalRequirement | POST | /approval-requests/evaluate |  | ApprovalRequirement | APPROVAL_VIEW | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, platform.scope | cache:idempotency | Does this need approval, and from whom
TenancyService | rota | createRotaAssignment | POST | /rota-assignments | RotaAssignment | RotaAssignment | WORKFORCE_MANAGE | core | 1 | SVC-TENANCY-ROTA-1 | cache:idempotency, identity.delegated_access, identity.principal, platform.workstation, workforce.rota_assignment | cache:idempotency, workforce.rota_assignment | Put someone on the rota
TenancyService | rota | listRotaAssignments | GET | /rota-assignments |  | object | WORKFORCE_VIEW | core | 1 | SVC-TENANCY-ROTA-1 | identity.principal, workforce.rota_assignment |  | The rota
TenancyService | scope | createOrgUnit | POST | /org-units | CreateScopeNodeRequest | OrgUnit | SCOPE_MANAGE | setup | 1 | SVC-TENANCY-SCOPE-1 | cache:idempotency, platform.scope | cache:idempotency, cache:resolution, platform.scope | Create a scope node
TenancyService | scope | listOrgUnits | GET | /org-units |  | object | SCOPE_VIEW | core | 2 | SVC-TENANCY-SCOPE-1 | cache:resolution, platform.scope | cache:resolution | List scope nodes visible to the session
TenancyService | scope | updateOrgUnit | PATCH | /org-units/{orgUnitId} |  | OrgUnit | SCOPE_MANAGE | setup | 1 | SVC-TENANCY-SCOPE-1 | cache:idempotency, platform.scope | cache:idempotency, cache:resolution, platform.scope | Rename or deactivate a scope node
TenancyService | tenancy | getVenueSettings | GET | /venues/{venueId}/settings |  | VenueSettings | TENANT_VIEW | core | 1 | SVC-TENANCY-TENANCY-1 | cache:resolution, platform.venue_settings |  | Operational settings for this venue
TenancyService | tenancy | getWorkstationHealth | GET | /workstations/{workstationId}/health |  | object | DEVICE_VIEW | core | 1 | SVC-TENANCY-TENANCY-1 | platform.device, platform.device_heartbeat, platform.workstation |  | A score a manager can sort by, and what is dragging it down
TenancyService | tenancy | setVenueSettings | PUT | /venues/{venueId}/settings | VenueSettings | VenueSettings | TENANT_CONFIGURE | core | 1 | SVC-TENANCY-TENANCY-1 | access.access_point, cache:idempotency, platform.venue_settings | cache:idempotency, cache:resolution, platform.venue_settings | Set support hours, quiet hours, segregated access and alerting
TenancyService | workstation | configureWorkstation | PUT | /workstations/{workstationId} | ConfigureWorkstationRequest | Workstation | WORKSTATION_CONFIGURE | core | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.device, platform.workstation | cache:idempotency, platform.device, platform.workstation | Configure a workstation
TenancyService | workstation | createOutlet | POST | /outlets | Outlet | Outlet | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.outlet | cache:idempotency, platform.outlet | Create an outlet
TenancyService | workstation | createSaleBoard | POST | /sale-boards | SaleBoard | SaleBoard | WORKSTATION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.sale_board | cache:idempotency, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | Create a sale board
TenancyService | workstation | listDevices | GET | /devices |  | object | DEVICE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-1 | platform.device |  | List registered devices
TenancyService | workstation | listOutlets | GET | /outlets |  | array of Outlet | SCOPE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.outlet |  | List outlets
TenancyService | workstation | listSaleBoards | GET | /sale-boards |  | array of SaleBoard | SCOPE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.sale_board, platform.sale_board_page, platform.sale_board_tile |  | List sale boards
TenancyService | workstation | listWorkstations | GET | /workstations |  | object | SCOPE_VIEW | core | 2 | SVC-TENANCY-WORKSTATION-2 | platform.device, platform.workstation |  | List workstations
TenancyService | workstation | recordDeviceHeartbeat | POST | /devices/{deviceId}/heartbeat |  |  |  | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.device | platform.device, platform.outbox | Device heartbeat and status
TenancyService | workstation | updateOutlet | PATCH | /outlets/{outletId} |  | Outlet | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-3 | cache:idempotency, platform.outlet | cache:idempotency, platform.outlet | Amend an outlet
TenancyService | workstation | updateSaleBoard | PUT | /sale-boards/{saleBoardId} | SaleBoard | SaleBoard | WORKSTATION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-3 | cache:idempotency, platform.sale_board | cache:idempotency, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | Update a sale board
VenueOpsService | asset | deleteMediaAsset | DELETE | /media/{mediaId} |  |  | ASSET_LIBRARY_MANAGE | core | 2 | SVC-VENUEOPS-ASSET-1 | assets.media_usage, cache:idempotency | assets.media_usage, cache:idempotency | Delete an asset
VenueOpsService | asset | getMediaAsset | GET | /media/{mediaId} |  | MediaAssetDetail | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, assets.media_usage |  | Read an asset with derivatives and usage
VenueOpsService | asset | replaceMediaAsset | POST | /media/{mediaId}/replace |  | MediaReplaceResult | ASSET_LIBRARY_MANAGE | core | 2 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, cache:idempotency | assets.asset_version, assets.media_asset, assets.media_fingerprint, cache:idempotency | Replace the file behind an asset
VenueOpsService | asset | searchMedia | GET | /media |  | object | ASSET_LIBRARY_VIEW | core | 2 | SVC-VENUEOPS-ASSET-1 | assets.media_asset |  | Search the asset library
VenueOpsService | asset | updateMediaAsset | PATCH | /media/{mediaId} |  | MediaAsset | ASSET_LIBRARY_MANAGE | core | 2 | SVC-VENUEOPS-ASSET-2 | assets.media_asset, assets.media_usage, cache:idempotency | assets.media_asset, cache:idempotency | Amend metadata, tags or rights
VenueOpsService | card | getGameCard | GET | /game-cards/{cardCode} |  | GameCard |  | core | 2 | SVC-VENUEOPS-CARD-1 | games.card, games.credit_ledger |  | Read a card's balances
VenueOpsService | card | issueGameCard | POST | /game-cards | IssueGameCardRequest | GameCard | ORDER_CREATE | core | 1 | SVC-VENUEOPS-CARD-1 | cache:idempotency, games.card | cache:idempotency, games.card | Issue or activate a game card
VenueOpsService | card | transferGameCard | POST | /game-cards/{cardCode}/transfer |  | GameCard | ORDER_MODIFY | core | 1 | SVC-VENUEOPS-CARD-1 | cache:idempotency, games.card | cache:idempotency, games.card | Move balances to another card
VenueOpsService | collection | createCollection | POST | /media/collections |  | Collection | ASSET_LIBRARY_MANAGE | core | 2 | SVC-VENUEOPS-COLLECTION-1 | assets.media_collection, cache:idempotency | assets.media_collection, assets.media_collection_member, cache:idempotency | Create a collection
VenueOpsService | collection | listCollections | GET | /media/collections |  | array of Collection | ASSET_LIBRARY_VIEW | core | 2 | SVC-VENUEOPS-COLLECTION-1 | assets.media_collection, assets.media_collection_member |  | List collections
VenueOpsService | departure | getNextTransportDeparture | GET | /transport/departures/next |  | DepartureOffer |  | core | 3 | SVC-VENUEOPS-DEPARTURE-1 | transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | Next Available Trip
VenueOpsService | departure | searchTransportDepartures | GET | /transport/departures |  | object |  | core | 3 | SVC-VENUEOPS-DEPARTURE-1 | transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | Search Trips — departures between two stations on a date
VenueOpsService | entry | getWaitingGuest | GET | /waiting-guests/{entryId} |  | WaitingGuest |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | queue.entry |  | Read a queue entry
VenueOpsService | entry | joinQueue | POST | /waiting-guests | JoinQueueRequest | WaitingGuest |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | cache:idempotency, marketing.loyalty_position, promotions.promotion, queue.entry, queue.queue | cache:idempotency, queue.entry | Join a virtual queue
VenueOpsService | entry | leaveQueue | DELETE | /waiting-guests/{entryId} |  |  |  | core | 2 | SVC-VENUEOPS-ENTRY-1 | cache:idempotency, queue.entry | cache:idempotency, queue.entry | Leave a queue
VenueOpsService | entry | listQueueEntries | GET | /queues/{queueId}/entries |  | object | QUEUE_VIEW | core | 1 | SVC-VENUEOPS-ENTRY-1 | queue.entry |  | List entries in a queue
VenueOpsService | fare | getTransportFareTable | GET | /transport/routes/{routeId}/fare-table |  | FareTable |  | core | 3 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table |  | A route's fares and passenger types
VenueOpsService | fare | quoteTransportFare | POST | /transport/fare-quotes | FareQuoteRequest | FareQuote |  | core | 3 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.pass_type, transport.route_stop |  | Price a one-way trip or a pass for a party
VenueOpsService | fare | setTransportFareTable | PUT | /transport/routes/{routeId}/fare-table | SetFareTableRequest | FareTable | TRANSPORT_PRICE | setup | 3 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table | Set a route's fares and passenger types
VenueOpsService | favourite | deleteFavouriteRoute | DELETE | /transport/favourite-routes/{favouriteId} |  |  |  | core | 3 | SVC-VENUEOPS-FAVOURITE-1 | cache:idempotency, transport.favourite_route | cache:idempotency, transport.favourite_route | Remove a saved route
VenueOpsService | favourite | listMyFavouriteRoutes | GET | /transport/favourite-routes |  | object |  | core | 3 | SVC-VENUEOPS-FAVOURITE-1 | transport.favourite_route |  | The caller's saved routes
VenueOpsService | favourite | saveFavouriteRoute | POST | /transport/favourite-routes |  | FavouriteRoute |  | core | 3 | SVC-VENUEOPS-FAVOURITE-1 | transport.favourite_route, transport.station | transport.favourite_route | Save route
VenueOpsService | feed | configureQueueFeed | PUT | /queue-feeds | QueueFeed | QueueFeed | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-FEED-1 | cache:idempotency, queue.feed | cache:idempotency, queue.feed | Configure a sensor feed
VenueOpsService | feed | getQueueFeedHealth | GET | /queue-feeds/{feedId}/health |  | QueueFeedHealth | QUEUE_MANAGE | core | 1 | SVC-VENUEOPS-FEED-1 | queue.feed |  | Feed health
VenueOpsService | inspection | createInspectionTemplate | POST | /inspection-templates | InspectionTemplate | InspectionTemplate | INSPECTION_MANAGE | setup | 1 | SVC-VENUEOPS-INSPECTION-1 | cache:idempotency, maintenance.inspection_template, maintenance.inspection_template_item | cache:idempotency, maintenance.inspection_template, maintenance.inspection_template_item | Create an inspection template
VenueOpsService | networkImport | applyTransportNetworkImport | POST | /transport/network-imports/{importId}/apply |  | TransportNetworkImport | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-NETWORKIMPORT-1 | transport.network_import | transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable, transport.timetable_run | Apply a previewed import to the network
VenueOpsService | networkImport | importTransportNetwork | POST | /transport/network-imports | ImportTransportNetworkRequest | TransportNetworkImport | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-NETWORKIMPORT-1 | transport.network_import | transport.network_import | Read a network file into a preview
VenueOpsService | pass | createTransportPassType | POST | /transport/pass-types | CreatePassTypeRequest | PassType | TRANSPORT_PRICE | setup | 3 | SVC-VENUEOPS-PASS-1 | transport.pass_type | transport.pass_type | Define a multi-trip or unlimited pass
VenueOpsService | pass | listTransportPassOffers | GET | /transport/pass-offers |  | object |  | core | 3 | SVC-VENUEOPS-PASS-1 | transport.fare_matrix_cell, transport.fare_table, transport.pass_type, transport.route, transport.route_stop |  | Multi-trip passes for a pair of stations, priced, with the saving
VenueOpsService | queue | createQueue | POST | /queues | CreateQueueRequest | Queue | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-QUEUE-1 | cache:idempotency, queue.queue, queue.queue_operating_window | cache:idempotency, queue.queue, queue.queue_operating_window | Create a queue
VenueOpsService | queue | getQueue | GET | /queues/{queueId} |  | QueueDetail | QUEUE_VIEW | core | 1 | SVC-VENUEOPS-QUEUE-1 | queue.queue, queue.queue_operating_window |  | Read a queue with live position
VenueOpsService | queue | listQueues | GET | /queues |  | object | QUEUE_VIEW | core | 2 | SVC-VENUEOPS-QUEUE-1 | queue.queue, queue.queue_operating_window |  | List queues
VenueOpsService | queue | updateQueue | PATCH | /queues/{queueId} |  | Queue | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-QUEUE-1 | cache:idempotency, queue.queue, queue.queue_operating_window | cache:idempotency, queue.queue | Amend queue configuration
VenueOpsService | resources | createResource | POST | /resources | Resource | Resource | RESOURCE_MANAGE | setup | 2 | SVC-VENUEOPS-RESOURCES-1 | cache:idempotency, resources.resource | cache:idempotency, resources.resource | Define a bookable resource
VenueOpsService | resources | createResourceBlock | POST | /resource-blocks | ResourceBlock | ResourceBlock | RESOURCE_MANAGE | setup | 2 | SVC-VENUEOPS-RESOURCES-1 | resources.resource_block | resources.resource_block | Take a resource out of service for a window, with a reason
VenueOpsService | resources | createResourceHold | POST | /resource-holds | CreateResourceHoldRequest | ResourceHold | ORDER_CREATE | core | 3 | SVC-VENUEOPS-RESOURCES-1 | resources.resource_hold |  | Hold a specific resource picked on the map
VenueOpsService | resources | createResourcePackage | POST | /resource-packages | ResourcePackage | ResourcePackage | RESOURCE_CONFIGURE | setup | 3 | SVC-VENUEOPS-RESOURCES-1 | resources.resource_package, resources.resource_requirement | resources.resource_package, resources.resource_requirement | Define a reusable combination
VenueOpsService | resources | extendResourceHold | POST | /resource-holds/{holdId}/extend |  | ResourceHold | ORDER_CREATE | core | 3 | SVC-VENUEOPS-RESOURCES-2 | resources.resource_hold |  | Extend a resource hold
VenueOpsService | resources | getMapResourceAvailability | GET | /resource-availability |  | MapResourceAvailability | RESOURCE_VIEW | core | 3 | SVC-VENUEOPS-RESOURCES-2 | maintenance.work_order, resources.booking, resources.resource, resources.resource_block, resources.resource_hold, venuemap.map, venuemap.map_version, venuemap.placed_resource |  | Every bookable resource on a venue map, free or taken, in one call
VenueOpsService | resources | getResourceAvailability | GET | /resources/{resourceId}/availability |  | ResourceAvailability | RESOURCE_VIEW | core | 2 | SVC-VENUEOPS-RESOURCES-2 | maintenance.work_order, resources.booking, resources.resource, resources.resource_block, resources.resource_hold |  | When it is free, with conflicts already resolved
VenueOpsService | resources | getResourceHold | GET | /resource-holds/{holdId} |  | ResourceHold | ORDER_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-2 | resources.resource_hold |  | Read a resource hold
VenueOpsService | resources | listProductStartTimes | GET | /resource-start-times |  | object | RESOURCE_VIEW | core | 3 | SVC-VENUEOPS-RESOURCES-3 | resources.booking, resources.resource, resources.resource_block, resources.resource_hold, resources.resource_requirement, resources.resource_schedule |  | Start times a space sold by the hour can be booked at, for one length on one day
VenueOpsService | resources | releaseResourceBlock | DELETE | /resource-blocks/{blockId} |  |  | RESOURCE_MANAGE | setup | 2 | SVC-VENUEOPS-RESOURCES-3 | cache:idempotency, resources.resource_block | cache:idempotency, resources.resource_block | Put it back into service
VenueOpsService | resources | relinquishResourceHold | DELETE | /resource-holds/{holdId} |  |  | ORDER_CREATE | core | 3 | SVC-VENUEOPS-RESOURCES-3 | cache:idempotency, resources.resource_hold | cache:idempotency, resources.resource_hold | Give up a resource hold
VenueOpsService | resources | setExperienceResourceRequirements | PUT | /experiences/{experienceId}/resource-requirements |  | array of ResourceRequirement | RESOURCE_CONFIGURE | setup | 3 | SVC-VENUEOPS-RESOURCES-3 | resources.resource_requirement | resources.resource_requirement | Bind resource requirements to an experience
VenueOpsService | resources | setResourceSchedule | PUT | /resources/{resourceId}/schedule | ResourceSchedule | ResourceSchedule | RESOURCE_CONFIGURE | setup | 3 | SVC-VENUEOPS-RESOURCES-4 | resources.resource_schedule | resources.resource_schedule | Operating hours, working pattern and bookable slots
VenueOpsService | resources | updateResource | PUT | /resources/{resourceId} | Resource | Resource | RESOURCE_MANAGE | setup | 2 | SVC-VENUEOPS-RESOURCES-4 | resources.resource | resources.resource | Change a resource
VenueOpsService | resources | updateResourcePackage | PUT | /resource-packages/{packageId} | ResourcePackage | ResourcePackage | RESOURCE_CONFIGURE | setup | 3 | SVC-VENUEOPS-RESOURCES-4 | resources.resource_package, resources.resource_requirement | resources.resource_package, resources.resource_requirement | Change a combination
VenueOpsService | rights | getExpiringRights | GET | /media/rights-expiring |  | array of ExpiringMedia | ASSET_LIBRARY_VIEW | core | 2 | SVC-VENUEOPS-RIGHTS-1 | assets.media_asset |  | Assets whose licence is expiring or expired
VenueOpsService | route | createTransportRoute | POST | /transport/routes | CreateTransportRouteRequest | TransportRoute | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station | transport.route, transport.route_stop | Define a route with its ordered stops
VenueOpsService | route | getTransportRoute | GET | /transport/routes/{routeId} |  | TransportRoute |  | core | 3 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station |  | A route with its stops
VenueOpsService | route | getTransportRouteMap | GET | /transport/routes/{routeId}/map |  | RouteMap |  | core | 3 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station |  | The route drawn for a map, with the journey highlighted
VenueOpsService | route | listTransportRoutes | GET | /transport/routes |  | object |  | core | 3 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station |  | Routes, optionally those serving a pair of stations
VenueOpsService | route | updateTransportRoute | PATCH | /transport/routes/{routeId} |  | TransportRoute | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-ROUTE-2 | transport.route, transport.route_stop, transport.station | transport.route, transport.route_stop | Amend a route
VenueOpsService | station | createTransportStation | POST | /transport/stations | CreateStationRequest | Station | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-STATION-1 | transport.station | transport.station | Add a station
VenueOpsService | station | listTransportStations | GET | /transport/stations |  | object |  | core | 3 | SVC-VENUEOPS-STATION-1 | transport.station |  | Stations of a venue's transport network
VenueOpsService | timetable | createTransportTimetable | POST | /transport/routes/{routeId}/timetables | CreateTimetableRequest | Timetable | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-TIMETABLE-1 | transport.route, transport.timetable, transport.timetable_run | transport.timetable, transport.timetable_run | Draft a timetable for a route
VenueOpsService | timetable | publishTransportTimetable | POST | /transport/timetables/{timetableId}/publish |  | Timetable | TRANSPORT_MANAGE | setup | 3 | SVC-VENUEOPS-TIMETABLE-1 | transport.timetable, transport.timetable_run | transport.departure, transport.timetable | Publish a timetable and release its departures
VenueOpsService | upload | completeUpload | POST | /media/uploads/{uploadId}/complete |  | MediaAsset | ASSET_LIBRARY_MANAGE | core | 2 | SVC-VENUEOPS-UPLOAD-1 | assets.media_asset, assets.media_upload, cache:idempotency | assets.media_asset, assets.media_fingerprint, cache:idempotency | Confirm an upload and create the asset
VenueOpsService | upload | createUpload | POST | /media/uploads |  | UploadTicket | ASSET_LIBRARY_MANAGE | core | 2 | SVC-VENUEOPS-UPLOAD-1 | assets.media_upload, cache:idempotency | assets.media_upload, cache:idempotency | Request a signed upload URL
VenueOpsService | venueMap | createVenueMap | POST | /venue-maps | VenueMap | VenueMap | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-1 | assets.media_asset, cache:idempotency, platform.scope, venuemap.map | cache:idempotency, venuemap.map | Start a map
VenueOpsService | venueMap | getVenueMap | GET | /venue-maps/{mapId} |  | VenueMapDetail | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-1 | assets.media_asset, venuemap.map, venuemap.path, venuemap.placed_resource, venuemap.point |  | A map with its points and paths
VenueOpsService | venueMap | getVenueMapGraph | GET | /venue-maps/{mapId}/graph |  | VenueMapGraph | VENUE_MAP_VIEW | core | 2 | SVC-VENUEOPS-VENUEMAP-1 | cache:resolution, venuemap.map, venuemap.path, venuemap.point | cache:resolution | The navigation graph, ready to route over
VenueOpsService | venueMap | importVenueGeometry | POST | /venue-maps/{mapId}/import |  | VenueMapImportJob | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-1 | cache:idempotency, venuemap.import_job, venuemap.map | cache:idempotency, venuemap.import_job, venuemap.path, venuemap.point | Read a drawing into shapes
VenueOpsService | venueMap | listBookableVenueMaps | GET | /bookable-venue-maps |  | BookableVenueMaps | VENUE_MAP_VIEW | core | 3 | SVC-VENUEOPS-VENUEMAP-2 | venuemap.map, venuemap.map_version, venuemap.placed_resource |  | The published maps of a venue that carry bookable spots
VenueOpsService | venueMap | publishVenueMap | POST | /venue-maps/{mapId}/publish |  | VenueMap | VENUE_MAP_PUBLISH | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | assets.media_asset, cache:idempotency, platform.outlet, venuemap.map, venuemap.path, venuemap.point | cache:idempotency, cache:resolution, venuemap.map | Make the draft the one guests see
VenueOpsService | venueMap | setPlacedResource | POST | /venue-maps/{mapId}/resources | SetPlacedResourceRequest | PlacedResource | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | venuemap.placed_resource | venuemap.placed_resource | Place or amend a bookable resource on the map
VenueOpsService | venueMap | setVenuePoint | POST | /venue-maps/{mapId}/points | SetVenuePointRequest | VenuePoint | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | access.access_point, assets.media_asset, cache:idempotency, catalogue.product, platform.outlet, promotions.bundle, venuemap.map, venuemap.point | cache:idempotency, venuemap.point | Place or amend a point of interest
VenueOpsService | visitPlan | bookVisitPlan | POST | /visit-plans/{planId}/booking |  | VisitPlanBooking |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.product, catalogue.variant, orders.cart, orders.cart_line, promotions.bundle, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, catalogue.inventory_hold, orders.cart, orders.cart_line, venuemap.visit_plan | Book this plan — turn it into cart lines
VenueOpsService | visitPlan | generateVisitPlan | POST | /visit-plans | VisitPlanRequest | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | cache:idempotency, catalogue.performance, catalogue.product, catalogue.product_eligibility_rule, catalogue.variant, queue.reading, venuemap.map, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, venuemap.visit_plan, venuemap.visit_plan_item | Build a visit plan from the party, the dates and what they like
VenueOpsService | visitPlan | getVisitPlan | GET | /visit-plans/{planId} |  | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | venuemap.visit_plan, venuemap.visit_plan_item |  | A visit plan, at its current version or an earlier one
VenueOpsService | visitPlan | listVisitPlanAlternatives | GET | /visit-plans/{planId}/items/{itemId}/alternatives |  | object |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | catalogue.performance, catalogue.product, catalogue.product_eligibility_rule, queue.reading, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item |  | What could take this item's place
VenueOpsService | visitPlan | updateVisitPlan | PUT | /visit-plans/{planId} | VisitPlanUpdate | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-2 | cache:idempotency, catalogue.performance, catalogue.product_eligibility_rule, queue.reading, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, venuemap.visit_plan, venuemap.visit_plan_item | Swap, remove, add, move or undo, as a new version
VenueOpsService | waitTime | getWaitTimes | GET | /queues/wait-times |  | array of WaitTime |  | core | 1 | SVC-VENUEOPS-WAITTIME-1 | queue.entry, queue.queue, queue.reading |  | Wait times across a venue
WalletService | card | loadGameCredits | POST | /game-cards/{cardCode}/load |  | Wallet | WALLET_OPERATE | core | 1 | SVC-WALLET-CARD-1 | cache:idempotency, games.card, wallet.credit_lot, wallet.wallet | cache:idempotency, games.card | Load credits onto a card
WalletService | giftCard | getGiftCard | GET | /gift-cards/{cardCode} |  | GiftCard | WALLET_VIEW | core | 2 | SVC-WALLET-GIFTCARD-1 | wallet.gift_card |  | Check a gift card balance
WalletService | retail | getWalletAutoReloadSetting | GET | /wallets/{walletId}/auto-reload |  | WalletAutoReloadSetting | WALLET_VIEW | core | 2 | SVC-WALLET-RETAIL-1 | wallet.auto_reload_setting, wallet.wallet |  | A wallet's own auto top-up, if the holder set one
WalletService | retail | getWalletExitBalance | GET | /wallets/{walletId}/exit-balance |  | WalletExitBalance | WALLET_VIEW | core | 2 | SVC-WALLET-RETAIL-1 | payments.stored_forward, wallet.balance, wallet.credit_lot, wallet.refund_policy, wallet.wallet |  | What the holder owes or is owed on leaving
WalletService | retail | setWalletAutoReloadSetting | PUT | /wallets/{walletId}/auto-reload | WalletAutoReloadSetting | WalletAutoReloadSetting | WALLET_OPERATE | core | 2 | SVC-WALLET-RETAIL-1 | cache:idempotency, payments.token, wallet.auto_reload_setting, wallet.funding_rules, wallet.wallet | cache:idempotency, cache:resolution, wallet.auto_reload_setting | Top the wallet up automatically from a stored card when it runs low
WalletService | retail | settleWalletAtExit | POST | /wallets/{walletId}/exit-settlement |  | WalletExitSettlement | WALLET_OPERATE | core | 2 | SVC-WALLET-RETAIL-1 | cache:idempotency, payments.stored_forward, wallet.balance, wallet.credit_lot, wallet.exit_settlement, wallet.refund_policy, wallet.wallet | cache:idempotency, orders.payment, orders.refund, platform.outbox, wallet.exit_settlement, wallet.wallet, wallet.wallet_transaction | Settle a short balance, or refund a credit, when the holder leaves
WalletService | retail | transferWalletBalance | POST | /wallets/{walletId}/transfer |  | WalletTransaction | WALLET_OPERATE | core | 2 | SVC-WALLET-RETAIL-2 | cache:idempotency, pii.subject, wallet.wallet, wallet.wallet_transaction | cache:idempotency, wallet.wallet, wallet.wallet_transaction | Send balance to another guest
WalletService | wallet | captureWalletHold | POST | /wallet-holds/{walletHoldId}/capture |  | WalletHold | WALLET_OPERATE | setup | 2 | SVC-WALLET-WALLET-1 | wallet.balance, wallet.hold | platform.idempotency_record, platform.outbox, wallet.balance, wallet.hold, wallet.wallet_transaction | Debit a held amount
WalletService | wallet | expireCreditLots | POST | /credit-lots/expire |  | CreditExpiryResult | WALLET_OPERATE | setup | 1 | SVC-WALLET-WALLET-1 | cache:idempotency, wallet.accounting_mapping, wallet.credit_lot, wallet.credit_type, wallet.wallet | cache:idempotency, wallet.adjustment, wallet.credit_lot, wallet.wallet, wallet.wallet_transaction | Expire, extend or forfeit credit that has run out of time
WalletService | wallet | getWallet | GET | /wallets/{subjectId} |  | Wallet | WALLET_VIEW | core | 2 | SVC-WALLET-WALLET-1 | wallet.credit_lot, wallet.wallet |  | Read a guest wallet
WalletService | wallet | holdWalletFunds | POST | /wallets/{walletId}/holds |  | WalletHold | WALLET_OPERATE | setup | 2 | SVC-WALLET-WALLET-1 | wallet.balance, wallet.hold, wallet.wallet | platform.idempotency_record, platform.outbox, wallet.balance, wallet.hold, wallet.wallet_transaction | Hold wallet funds for a spend in progress
WalletService | wallet | listWalletTransactions | GET | /wallets/{subjectId}/transactions |  | object | WALLET_VIEW | core | 2 | SVC-WALLET-WALLET-2 | wallet.wallet_transaction |  | Wallet transaction history
WalletService | wallet | publishWalletConfiguration | POST | /wallet-configuration/publish |  | WalletConfigurationVersion | WALLET_CONFIGURE | setup | 2 | SVC-WALLET-WALLET-2 | cache:idempotency, wallet.accounting_mapping, wallet.authentication_policy, wallet.channel_rules, wallet.configuration_version, wallet.consumption_policy, wallet.credit_type, wallet.funding_rules, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rules, wallet.transfer_rules, wallet.wallet_type | cache:idempotency, wallet.configuration_version, wallet.configuration_version_snapshot | Validate and publish the wallet configuration as a version
WalletService | wallet | releaseWalletHold | POST | /wallet-holds/{walletHoldId}/release |  | WalletHold | WALLET_OPERATE | setup | 2 | SVC-WALLET-WALLET-2 | wallet.balance, wallet.hold | platform.idempotency_record, platform.outbox, wallet.balance, wallet.hold, wallet.wallet_transaction | Give held wallet funds back
WalletService | wallet | restoreWalletConfigurationVersion | POST | /wallet-configuration/versions/{version}/restore |  | WalletConfigurationVersion | WALLET_CONFIGURE | setup | 2 | SVC-WALLET-WALLET-2 | cache:idempotency, wallet.configuration_version, wallet.configuration_version_snapshot | cache:idempotency, wallet.accounting_mapping, wallet.authentication_policy, wallet.channel_rules, wallet.consumption_policy, wallet.credit_type, wallet.funding_rules, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rules, wallet.transfer_rules, wallet.wallet_type | Put a previous wallet configuration back as the working draft
WalletService | wallet | setWalletFundingRules | PUT | /wallet-funding-rules | WalletFundingRules | WalletFundingRules | WALLET_CONFIGURE | setup | 2 | SVC-WALLET-WALLET-3 | wallet.funding_rules | wallet.funding_rules | Amounts, channels, bonuses, limits and velocity
WalletService | wallet | setWalletRefundPolicy | PUT | /wallet-refund-policy | WalletRefundPolicy | WalletRefundPolicy | WALLET_CONFIGURE | setup | 2 | SVC-WALLET-WALLET-3 | wallet.refund_policy | wallet.refund_policy | What a refund puts back, and where
WhiteLabelService | appPublishing | getAppBuild | GET | /tenant-config/app-builds/{appBuildId} |  | AppBuild | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build |  | One app build, with its package and store status
WhiteLabelService | appPublishing | getStoreAccounts | GET | /tenant-config/store-accounts |  | StorePublishingChecklist | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.config_version, whitelabel.store_account, whitelabel.tenant_config |  | The client's store accounts and the publishing checklist
WhiteLabelService | appPublishing | listAppBuilds | GET | /tenant-config/app-builds |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build |  | The tenant's app builds, newest first
WhiteLabelService | appPublishing | requestAppBuild | POST | /tenant-config/app-builds |  | AppBuild | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build, whitelabel.config_version, whitelabel.store_account | cache:idempotency, whitelabel.app_build | Build the branded app for a store
WhiteLabelService | appPublishing | setStoreAccounts | PUT | /tenant-config/store-accounts |  | StorePublishingChecklist | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-2 | whitelabel.store_account | cache:idempotency, whitelabel.store_account | Record the client's own Apple and Google store accounts and listings
WhiteLabelService | bookingFlows | createBookingFlowDefinition | POST | /venues/{venueId}/booking-flows | BookingFlow | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Pick a booking flow for a venue
WhiteLabelService | bookingFlows | deleteBookingFlow | DELETE | /booking-flows/{bookingFlowId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | catalogue.product, catalogue.product_category, whitelabel.booking_flow | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Remove a booking flow from a venue
WhiteLabelService | bookingFlows | getBookingFlow | GET | /booking-flows/{bookingFlowId} |  | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | whitelabel.booking_flow, whitelabel.booking_flow_step |  | Read one of a venue's booking flows, every step included
WhiteLabelService | bookingFlows | getPublishedBookingFlow | GET | /venues/{venueId}/booking-flow |  | BookingFlow |  | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | catalogue.product, catalogue.product_category, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version |  | The published booking flow a product or category books through
WhiteLabelService | bookingFlows | listBookingFlowTypes | GET | /booking-flow-types |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 |  |  | The booking flow types a venue can pick from, with their steps
WhiteLabelService | bookingFlows | listBookingFlows | GET | /venues/{venueId}/booking-flows |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step |  | A venue's booking flows, in the working draft
WhiteLabelService | bookingFlows | updateBookingFlowDefinition | PATCH | /booking-flows/{bookingFlowId} |  | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Reorder a flow's steps, switch optional steps, change its settings
WhiteLabelService | bookingFlows | validateBookingFlow | POST | /booking-flows/{bookingFlowId}/validate |  | BookingFlowValidation | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow_step | Check a flow against its type
WhiteLabelService | brand | getAppIcons | GET | /tenant-config/app-icons |  | AppIcons | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-BRAND-1 | whitelabel.tenant_config |  | Read app icon set
WhiteLabelService | brand | getBrandIdentity | GET | /tenant-config/brand |  | BrandIdentity | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-BRAND-1 | whitelabel.tenant_config |  | Read brand identity
WhiteLabelService | brand | setAppIcons | PUT | /tenant-config/app-icons |  | AppIcons | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-BRAND-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set app icons
WhiteLabelService | brand | setBrandIdentity | PUT | /tenant-config/brand | BrandIdentity | BrandIdentity | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-BRAND-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set logo, favicon and splash
WhiteLabelService | branding | getBookingFlowConfig | GET | /tenant-config/booking-flow |  | BookingFlowConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-BRANDING-1 | whitelabel.tenant_config |  | How the guest booking flow looks and steps
WhiteLabelService | branding | setBookingFlowConfig | PUT | /tenant-config/booking-flow | BookingFlowConfig | BookingFlowConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-BRANDING-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.tenant_config | Set how the guest booking flow looks and steps
WhiteLabelService | content | createBanner | POST | /tenant-config/banners | Banner | Banner | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.banner | cache:idempotency, whitelabel.banner | Create a banner
WhiteLabelService | content | createContentPage | POST | /tenant-config/pages | ContentPage | ContentPage | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.content_page | cache:idempotency, whitelabel.content_page | Create a content page
WhiteLabelService | content | createGuidedChoice | POST | /venues/{venueId}/guided-choices | GuidedChoice | GuidedChoice | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-1 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Set up Help me choose for a venue
WhiteLabelService | content | createPromoBlock | POST | /tenant-config/promo-blocks | PromoBlock | PromoBlock | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Create a promotional block
WhiteLabelService | content | deleteBanner | DELETE | /tenant-config/banners/{bannerId} |  |  | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Delete a banner
WhiteLabelService | content | deleteContentPage | DELETE | /tenant-config/pages/{pageId} |  |  | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Delete a content page
WhiteLabelService | content | deleteGuidedChoice | DELETE | /guided-choices/{guidedChoiceId} |  |  | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Delete a Help me choose set-up, or dismiss a suggestion
WhiteLabelService | content | deletePromoBlock | DELETE | /tenant-config/promo-blocks/{promoBlockId} |  |  | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Delete a promotional block
WhiteLabelService | content | getPublishedGuidedChoice | GET | /venues/{venueId}/guided-choice |  | GuidedChoice |  | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | The venue's published Help me choose
WhiteLabelService | content | listBanners | GET | /tenant-config/banners |  | object | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-3 | whitelabel.banner |  | List banners
WhiteLabelService | content | listContentPages | GET | /tenant-config/pages |  | object | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-3 | whitelabel.content_page |  | List custom content pages
WhiteLabelService | content | listFaqs | GET | /tenant-config/faqs |  | array of FaqCategory | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-3 | whitelabel.faq_category, whitelabel.faq_entry |  | List FAQs
WhiteLabelService | content | listGuidedChoices | GET | /venues/{venueId}/guided-choices |  | object | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-4 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | List a venue's Help me choose set-ups
WhiteLabelService | content | listPolicies | GET | /tenant-config/policies |  | array of Policy | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-4 | whitelabel.policy |  | List legal policies
WhiteLabelService | content | listPromoBlocks | GET | /tenant-config/promo-blocks |  | array of PromoBlock | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-4 | whitelabel.promo_block |  | List promotional blocks
WhiteLabelService | content | proposeGuidedChoice | POST | /venues/{venueId}/guided-choice-suggestions |  | GuidedChoice |  | core | 1 | SVC-WHITELABEL-CONTENT-4 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Record an AI-proposed Help me choose set-up for review
WhiteLabelService | content | publishGuidedChoice | POST | /guided-choices/{guidedChoiceId}/publish |  | GuidedChoice | TENANT_PUBLISH | core | 2 | SVC-WHITELABEL-CONTENT-5 | whitelabel.booking_flow, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice | Publish a Help me choose set-up to guests
WhiteLabelService | content | setFaqs | PUT | /tenant-config/faqs |  | array of FaqCategory | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-5 | cache:idempotency, whitelabel.faq_category, whitelabel.faq_entry | cache:idempotency, whitelabel.faq_category, whitelabel.faq_entry | Set FAQ categories and entries
WhiteLabelService | content | setPolicy | PUT | /tenant-config/policies/{policyKind} |  | Policy | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-5 | cache:idempotency, whitelabel.policy | cache:idempotency, whitelabel.policy | Publish a policy version
WhiteLabelService | content | unpublishGuidedChoice | POST | /guided-choices/{guidedChoiceId}/unpublish |  | GuidedChoice | TENANT_PUBLISH | core | 2 | SVC-WHITELABEL-CONTENT-5 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | Take a Help me choose set-up off the guest app
WhiteLabelService | content | updateBanner | PATCH | /tenant-config/banners/{bannerId} |  | Banner | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.banner | cache:idempotency, whitelabel.banner | Amend or activate a banner
WhiteLabelService | content | updateContentPage | PUT | /tenant-config/pages/{pageId} | UpdateContentPageRequest | ContentPage | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.content_page | cache:idempotency, whitelabel.content_page | Amend a content page
WhiteLabelService | content | updateGuidedChoice | PATCH | /guided-choices/{guidedChoiceId} |  | GuidedChoice | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-6 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | whitelabel.guided_choice_question | Edit a Help me choose set-up, or review a suggestion
WhiteLabelService | content | updatePromoBlock | PATCH | /tenant-config/promo-blocks/{promoBlockId} |  | PromoBlock | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Amend a promotional block
WhiteLabelService | homepage | getHomepageLayout | GET | /tenant-config/homepage |  | HomepageLayout | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-HOMEPAGE-1 | whitelabel.homepage_section |  | Read homepage layout
WhiteLabelService | homepage | setHomepageLayout | PUT | /tenant-config/homepage | HomepageLayout | HomepageLayout | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-HOMEPAGE-1 | cache:idempotency, whitelabel.homepage_section | cache:idempotency, whitelabel.homepage_section | Set homepage section order
WhiteLabelService | modules | getFeatureToggles | GET | /tenant-config/features |  | array of FeatureToggle | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-MODULES-1 | cache:resolution, whitelabel.feature_toggle | cache:resolution | Read tenant feature toggles
WhiteLabelService | modules | getModuleEnablement | GET | /tenant-config/modules |  | array of ModuleEnablement | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-MODULES-1 | cache:resolution, control.licence_add_on, subscription.contract, subscription.plan, whitelabel.module_enablement | cache:resolution | Read module enablement
WhiteLabelService | modules | setFeatureToggles | PUT | /tenant-config/features |  | array of FeatureToggle | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-MODULES-1 | cache:idempotency, whitelabel.feature_toggle | cache:idempotency, cache:resolution, whitelabel.feature_toggle | Set feature toggles
WhiteLabelService | modules | setLanguages | PUT | /tenant-config/languages |  | LanguageConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-MODULES-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set enabled languages and default
WhiteLabelService | modules | setModuleEnablement | PUT | /tenant-config/modules |  | array of ModuleEnablement | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-MODULES-2 | cache:idempotency, control.licence_add_on, subscription.contract, subscription.plan, whitelabel.module_enablement | cache:idempotency, cache:resolution, whitelabel.module_enablement | Enable or disable modules
WhiteLabelService | navigation | getNavigation | GET | /tenant-config/navigation |  | NavigationConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-NAVIGATION-1 | cache:resolution, whitelabel.navigation_item | cache:resolution | Read navigation
WhiteLabelService | navigation | setHeader | PUT | /tenant-config/header | HeaderConfig | HeaderConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-NAVIGATION-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Configure the header
WhiteLabelService | navigation | setNavigation | PUT | /tenant-config/navigation | NavigationConfig | NavigationConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-NAVIGATION-1 | cache:idempotency, whitelabel.navigation_item | cache:idempotency, cache:resolution, whitelabel.navigation_item | Set main and overflow navigation
WhiteLabelService | overview | getTenantAppStatus | GET | /tenant-config/status |  | TenantAppStatus |  | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.config_version, whitelabel.tenant_config |  | App status and recent changes
WhiteLabelService | overview | getTenantConfig | GET | /tenant-config |  | TenantConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_item, whitelabel.tenant_config |  | Full working configuration
WhiteLabelService | overview | listAnalyticsProviders | GET | /tenant-config/analytics-providers |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.analytics_provider |  | The analytics platforms the storefront and app report to
WhiteLabelService | overview | recordStorefrontSessionEvents | POST | /storefront/session-events | WhiteLabelStorefrontSessionBatch |  |  | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | cache:idempotency | cache:idempotency, platform.outbox | Report a batch of browsing behaviour for fraud prevention, hashed and without personal data
WhiteLabelService | overview | setAnalyticsProvider | PUT | /tenant-config/analytics-providers | StorefrontAnalyticsProvider | StorefrontAnalyticsProvider | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency, whitelabel.analytics_provider | cache:idempotency, whitelabel.analytics_provider | Connect the storefront and app to an analytics platform
WhiteLabelService | overview | setMaintenanceMode | PUT | /tenant-config/status |  | TenantAppStatus | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Enable or clear maintenance mode, and set the live app status
WhiteLabelService | publishing | createPreview | POST | /tenant-config/preview |  | Preview | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-PUBLISHING-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Generate a preview link
WhiteLabelService | publishing | diffConfigVersion | GET | /tenant-config/versions/{version}/diff |  | ConfigDiff | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.tenant_config |  | Compare a version against the working draft
WhiteLabelService | publishing | getSiteSetupProgress | GET | /tenant-config/site-setup |  | SiteSetupProgress | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.booking_flow, whitelabel.config_version, whitelabel.site_setup_progress, whitelabel.tenant_config |  | Where the tenant is in the Site Builder
WhiteLabelService | publishing | listConfigVersions | GET | /tenant-config/versions |  | object | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.config_version |  | Version history
WhiteLabelService | publishing | publishTenantConfig | POST | /tenant-config/publish |  | ConfigVersion | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.tenant_config | cache:idempotency, whitelabel.config_version | Publish the working draft
WhiteLabelService | publishing | restoreConfigVersion | POST | /tenant-config/versions/{version}/restore |  | TenantConfig | TENANT_PUBLISH | core | 2 | SVC-WHITELABEL-PUBLISHING-2 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_item, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.feature_toggle, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_item, whitelabel.tenant_config | Restore a previous version
WhiteLabelService | publishing | setSiteSetupProgress | PUT | /tenant-config/site-setup | SiteSetupProgress | SiteSetupProgress | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.config_version, whitelabel.site_setup_progress | cache:idempotency, whitelabel.site_setup_progress | Save the Site Builder's progress
WhiteLabelService | publishing | validateTenantConfig | POST | /tenant-config/validate |  | ConfigValidationReport | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.tenant_config | cache:idempotency | Validate the working draft
WhiteLabelService | theme | getFonts | GET | /tenant-config/fonts |  | FontConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-THEME-1 | whitelabel.tenant_config |  | Read font configuration
WhiteLabelService | theme | getTheme | GET | /tenant-config/theme |  | Theme | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-THEME-1 | cache:resolution, whitelabel.tenant_config | cache:resolution | Read colour theme
WhiteLabelService | theme | setFonts | PUT | /tenant-config/fonts | FontConfig | FontConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-THEME-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set fonts
WhiteLabelService | theme | setTheme | PUT | /tenant-config/theme | Theme | Theme | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-THEME-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.tenant_config | Set colour theme
WhiteLabelService | white-label | claimCustomDomain | POST | /tenant-domains |  | CustomDomain | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-WHITE-LABEL-1 | cache:idempotency, control.tenant, whitelabel.custom_domain | cache:idempotency, whitelabel.custom_domain | Claim a domain and get a verification token
WhiteLabelService | white-label | listCustomDomains | GET | /tenant-domains |  | array of CustomDomain | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-WHITE-LABEL-1 | whitelabel.custom_domain |  | The domains this tenant has claimed
WhiteLabelService | white-label | relinquishCustomDomain | DELETE | /tenant-domains/{domainId} |  |  | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-WHITE-LABEL-1 | whitelabel.custom_domain | whitelabel.custom_domain | Give the domain up
WhiteLabelService | white-label | verifyCustomDomain | POST | /tenant-domains/{domainId}/verify |  | CustomDomain | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-WHITE-LABEL-1 | cache:idempotency, whitelabel.custom_domain | cache:idempotency, whitelabel.custom_domain | Check the record and issue the certificate
WhiteLabelService | whiteLabel | createContentBlock | POST | /content-blocks | ContentBlock | ContentBlock | TENANT_CONFIGURE | setup | 2 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, control.content_block, marketing.segment | cache:idempotency, control.content_block | Author a block of content
WhiteLabelService | whiteLabel | publishContentBlock | POST | /content-blocks/{blockId}/publish |  | ContentBlock | TENANT_PUBLISH | setup | 2 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, control.content_block, identity.principal | cache:idempotency, cache:resolution, control.content_block | Publish now, or schedule it
WhiteLabelService | whiteLabel | setFooter | PUT | /footer | FooterConfig | FooterConfig | TENANT_CONFIGURE | core | 2 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link | cache:idempotency, cache:resolution, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link | Footer columns, legal links and social

## API schemas
Contract | Schema | Fields | Stored as | Used as request | Used as response | Operations | Description
access | AccessAccessPointGroup | 8 | access.access_point_group | 1 | 1 | setAccessPointGroup | A named group of access points in one venue (e.g.
access | AccessAttributeCatalogInput | 6 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setAccessAttributeCatalog | What Access Attribute Catalog submits (decided 29 September, VM close-out).
access | AccessAttributeCatalogView | 6 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setAccessAttributeCatalog | What Access Attribute Catalog displays.
access | AccessCredentialPolicy | 32 | access.credential_policy | 0 | 1 | setDeviceBindingPolicy | One credential policy of one kind for a venue - activation and display rule, transfer policy, Virtual Ticket identity configuration or device binding policy; merges the proposed credential_display_ru…
access | AccessDeviceBinding | 15 | access.device_binding | 0 | 1 | bindCredentialDevice | One guest device bound to a credential, with its registration, last activation and security status; the binding policy in force is a deviceBinding row of access.credential_policy (declared 29 Septemb…
access | AccessGateModePolicy | 12 | access.gate_mode_policy | 1 | 1 | setGateModePolicy | One policy for a non-standard gate mode (free spin or count only as freeFlow, emergency as dropArm): who may activate it, on which gate group, whether a reason is required, emergency code, notificati…
access | AccessPoint | 17 | access.access_point | 0 | 4 | createAccessPoint, setAccessPointGeofence, setTurnstileMode, updateAccessPoint
access | AccessPointGeofence | 5 |  | 1 | 0 | setAccessPointGeofence | Where a handheld may validate for one access point, and what happens outside it.
access | AdmissionRules | 21 | access.admission_rules | 2 | 2 | createAdmissionRules, updateAdmissionRules
access | BiometricVerificationProfileBuilderInput | 11 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setBiometricVerificationProfile | What Biometric Verification Profile Builder submits.
access | BiometricVerificationProfileBuilderView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setBiometricVerificationProfile | What Biometric Verification Profile Builder displays.
access | BlacklistEntry | 9 | access.blacklist | 0 | 1 | addBlacklistEntry
access | BleBeaconGeofenceConfigurationInput | 13 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setBleBeaconGeofence | What BLE Beacon & Geofence Configuration submits.
access | BleBeaconGeofenceConfigurationView | 13 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setBleBeaconGeofence | What BLE Beacon & Geofence Configuration displays.
access | ContextTimeEventCapacityPolicyBuilderInput | 10 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setContextTimeEvent | What Context, Time, Event & Capacity Policy Builder submits.
access | ContextTimeEventCapacityPolicyBuilderView | 7 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setContextTimeEvent | What Context, Time, Event & Capacity Policy Builder displays.
access | CreateAccessPointRequest | 7 |  | 1 | 0 | createAccessPoint
access | CredentialActivationDisplayRulesInput | 6 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setCredentialActivationDisplay | What Credential Activation & Display Rules submits (decided 29 September, VM close-out).
access | CredentialActivationDisplayRulesView | 5 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setCredentialActivationDisplay | What Credential Activation & Display Rules displays.
access | CredentialDeviceBindingInput | 5 | none — request only; written as access.device_binding (declared 29 September, writers pass) | 1 | 0 | bindCredentialDevice
access | DeviceBindingPolicyInput | 4 | none — request only; written as the deviceBinding row of access.credential_policy (declared 29 September, writers pass) | 1 | 0 | setDeviceBindingPolicy
access | DynamicAccessPolicyCommandCenterView | 7 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | rollbackAccessPolicy | What Dynamic Access Policy Command Center displays.
access | Entitlement | 27 | access.entitlement | 0 | 1 | getEntitlement | What a guest actually holds.
access | FaceMatchingVerificationThresholdsInput | 13 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setFaceMatchingVerification | What Face Matching & Verification Thresholds submits (decided 29 September, VM close-out).
access | FaceMatchingVerificationThresholdsView | 12 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFaceMatchingVerification | What Face Matching & Verification Thresholds displays.
access | FacePassEnrollmentConfigurationInput | 11 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setFacePassEnrollment | What Face Pass Enrollment Configuration submits.
access | FacePassEnrollmentConfigurationView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFacePassEnrollment | What Face Pass Enrollment Configuration displays.
access | FacePassEnrolment | 12 | pii.subject_biometric | 0 | 3 | enrolFacePass, enrolFaceTag, getFacePassEnrolment | 3.2.43.
access | FaceTagTemporaryEnrollmentInput | 9 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setFaceTagTemporaryEnrollment | What Face Tag Temporary Enrollment submits (decided 29 September, VM close-out).
access | FaceTagTemporaryEnrollmentView | 8 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFaceTagTemporaryEnrollment | What Face Tag Temporary Enrollment displays.
access | ManualOverrideSupervisorApprovalInput | 7 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | approveManualOverrideSupervisor | What Manual Override & Supervisor Approval submits.
access | ManualOverrideSupervisorApprovalView | 7 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | approveManualOverrideSupervisor | What Manual Override & Supervisor Approval displays.
access | OfflinePackage | 12 | none — generated artefact in object storage | 0 | 1 | getOfflinePackage
access | ParkingEntitlement | 12 | access.parking_entitlement | 0 | 1 | updateParkingEntitlement | Issued at payment of an order that contains a parking product (decided 28 September, audit R166).
access | ParkingFacility | 13 | access.parking_facility | 1 | 1 | setParkingFacility
access | UpdateParkingEntitlementRequest | 3 | none — request only; applied to access.parking_entitlement | 1 | 0 | updateParkingEntitlement | The body of updateParkingEntitlement: only what changes.
access | VirtualTicketIdentityMasterRecordConfigurationInput | 10 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setVirtualTicketIdentity | What Virtual Ticket Identity & Master Record Configuration submits.
access | VirtualTicketIdentityMasterRecordConfigurationView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVirtualTicketIdentity | What Virtual Ticket Identity & Master Record Configuration displays.
access | VisualAccessRuleBuilderInput | 8 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setVisualAccessRule | What Visual Access Rule Builder submits.
access | VisualAccessRuleBuilderView | 8 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVisualAccessRule | What Visual Access Rule Builder displays.
access | VisualDynamicPolicyBuilderInput | 8 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setVisualDynamicPolicy | What Visual Dynamic Policy Builder submits.
access | VisualDynamicPolicyBuilderView | 5 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVisualDynamicPolicy | What Visual Dynamic Policy Builder displays.
ai | AiAnswerFeedback | 11 | ai.answer_feedback | 0 | 1 | recordAnswerFeedback | What a person thought of an answer (AIC-062).
ai | AiAssistantProfile | 14 | ai.assistant_profile | 1 | 1 | configureAssistantProfile | One assistant runtime, many profiles (design 5.10, C5; AIC-069..080).
ai | AiByokEnablement | 10 | ai.byok_enablement | 1 | 1 | setAiByokEnablement | Whether a tenant may bring its own model key (decided 29 September, design 8 on 5.9).
ai | AiCapabilityRegistration | 18 | ai.capability | 1 | 2 | configureAiCapability, resumeAiCapability | An entry in the capability registry (design 3.1 Registry, AIC-144, AIC-145; ADM-520).
ai | AiContentDraftSet | 4 | none — each draft is an ai.proposed_action row (kind content); proposedActionId is its id | 0 | 1 | proposeMarketingContent | What proposeMarketingContent drafted: one entry per variant per locale.
ai | AiConversation | 8 | ai.conversation | 0 | 1 | createAiConversation
ai | AiEvaluationRun | 14 | ai.eval_run | 0 | 1 | runAiEvaluation | One evaluation of a candidate against its baseline: offline golden set, backtest or shadow comparison.
ai | AiForecastScenario | 9 | ai.forecast_scenario | 1 | 1 | createForecastScenario | A what-if against a published version (ADM-507, ADM-517, BO-931).
ai | AiForecastVersion | 17 | ai.forecast_version | 0 | 2 | publishForecastVersion, runForecast | An immutable forecast version (AIP-032): producer, model version, data cut-off, horizon and status.
ai | AiGovernanceDecision | 7 | none — computed; a block also writes ai.decision_record | 0 | 1 | evaluateAiGovernance | The governance decision point's answer (design 3.8, AIC-166): outcome, policy version, conditions, required approvals and an explanation.
ai | AiGovernancePolicyVersion | 12 | ai.governance_policy_version | 0 | 2 | createAiGovernancePolicyDraft, publishAiGovernancePolicy | One version of a governance policy.
ai | AiGuidedChoiceSuggestion | 13 | ai.guided_choice_suggestion | 0 | 2 | getGuidedChoiceSuggestion, suggestGuidedChoice | One Help me choose suggestion for a venue (design 3.11, decided 29 September; C7 at autonomy "suggest").
ai | AiHistoryImport | 19 | ai.history_import | 0 | 2 | getVenueHistoryImport, importVenueHistory | One import of a venue's own history (29 September, AI functions review).
ai | AiIncident | 17 | ai.incident | 0 | 1 | containAiIncident | An AI governance incident (ADM-556): detection, containment, investigation, remediation and closure.
ai | AiInsight | 22 | ai.insight | 0 | 1 | decideAiInsight | An insight with a lifecycle (AIP-181): new, reviewed, accepted or rejected, actioned, measured.
ai | AiMessage | 15 | ai.message | 0 | 1 | sendAiMessage
ai | AiMetricChangeExplanation | 9 | none — computed; written as an ai.insight of kind rootCause when kept | 0 | 1 | explainMetricChange | Why a metric changed (AIP-176..180, ANL-056): drivers with their contribution, computed from the semantic layer.
ai | AiModel | 17 | ai.model | 1 | 1 | setAiModel | The model catalogue (design 3.1 Registry, 3.3; AIC-013, AIC-026).
ai | AiOperationalRequirement | 17 | ai.operational_requirement | 0 | 1 | decideOperationalRequirement | A requirement derived from a forecast version (design 2.2 C step 6, AIP-067): staff, POS, gates, F&B, stock or resources, computed with the tenant's productivity standards.
ai | AiPolicy | 29 | ai.policy | 1 | 2 | getAiPolicy, setAiPolicy
ai | AiPolicyException | 13 | ai.policy_exception | 1 | 1 | createAiPolicyException | A temporary, recorded exception to a governance policy (AIC-162, ADM-526): an expiry, an approver and compensating controls.
ai | AiPolicySimulation | 4 | none — computed; summary kept on ai.governance_policy_version.simulationSummary | 0 | 1 | simulateAiGovernancePolicy | What a draft policy version would have decided over recorded decisions and the test cases (ADM-527).
ai | AiPromptTemplate | 13 | ai.prompt_template | 0 | 1 | publishPromptTemplate | The prompt registry (design 3.1 Registry, AIC-022).
ai | AiProvider | 22 | ai.provider | 1 | 2 | setAiCredential, setAiProvider
ai | AiRecommendationResult | 5 | none — written as ai.rec_decision after the response | 0 | 1 | decideRecommendations | The recommendation slot's content (design 2.2 A).
ai | AiRelease | 17 | ai.release | 0 | 2 | promoteAiRelease, rollbackAiRelease | The release pointer per capability and tenant (design 3.5): draft, offline evaluation, shadow, canary, production, monitored.
ai | AiUsageReport | 5 | none — aggregated from ai.activity | 0 | 1 | getAiUsage
ai | AiVenueSettings | 15 | ai.venue_settings | 1 | 2 | getAiVenueSettings, setAiVenueSettings | The venue AI profile (29 September, AI functions review): the figures a venue gives at onboarding so every data-driven answer is useful before it has history.
ai | IndexJob | 14 | ai.index_job | 0 | 1 | reindexSource
ai | IndexSource | 14 | ai.index_source | 1 | 1 | setIndexSource | One declaration per indexed table.
ai | KnowledgeCollection | 12 | ai.knowledge_collection | 1 | 1 | createKnowledgeCollection
ai | KnowledgeDocument | 12 | ai.knowledge_document | 1 | 1 | ingestKnowledgeDocument
ai | ProposedAction | 18 | ai.proposed_action | 0 | 1 | decideProposedAction
ai | SearchResult | 10 | none — computed | 0 | 1 | semanticSearch
ai | Suggestion | 13 | ai.suggestion | 0 | 1 | requestSuggestion | One answer to one question, with its reasoning and its confidence.
ai | TranslationProposals | 2 | none — each draft is written on the block it translates | 0 | 1 | proposeTranslations | What proposeTranslations drafted.
ai | VenueLabelProposal | 7 | none — each proposal is an ai.proposed_action row; proposalId is its id | 0 | 1 | proposeVenueLabels | 1.4.24.
approvals | ApprovalDelegation | 10 | approvals.delegation | 1 | 1 | createApprovalDelegation
approvals | ApprovalExternalProvider | 16 | approvals.external_provider | 1 | 1 | setApprovalExternalProvider | 11.1.65 (29 September, build pass).
approvals | ApprovalMatrix | 7 | approvals.matrix | 1 | 1 | setApprovalMatrix
approvals | ApprovalMatrixMultiLevelApprovalConfigurationInput | 19 | none — request only; no existing table covers these fields — the closest is approvals.request at 3%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | approveMatrixMultiLevel | What Approval Matrix & Multi-Level Approval Configuration submits.
approvals | ApprovalMatrixMultiLevelApprovalConfigurationView | 19 | none — projection over approvals state, assembled at read time from tables that already exist | 0 | 1 | approveMatrixMultiLevel | What Approval Matrix & Multi-Level Approval Configuration displays.
approvals | ApprovalRequest | 30 | approvals.request | 0 | 2 | createApprovalRequest, decideApprovalRequest
approvals | ApprovalRequirement | 6 | none — computed | 0 | 1 | evaluateApprovalRequirement | The answer to "does this need approval", returned before the action.
approvals | CreateApprovalRequest | 11 | none — request only | 1 | 0 | createApprovalRequest
approvals | RolesAuthorityDelegationApprovalLimitsInput | 19 | none — request only; no existing table covers these fields — the closest is approvals.decision at 4%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | approveRoleAuthorityDelegation | What Roles, Authority, Delegation & Approval Limits submits.
approvals | RolesAuthorityDelegationApprovalLimitsView | 19 | none — projection over approvals state, assembled at read time from tables that already exist | 0 | 1 | approveRoleAuthorityDelegation | What Roles, Authority, Delegation & Approval Limits displays.
assets | Collection | 7 | assets.media_collection | 0 | 2 | createCollection, listCollections
assets | ExpiringMedia | 9 | none — computed | 0 | 1 | getExpiringRights
assets | MediaAsset | 25 | assets.media_asset | 0 | 2 | completeUpload, updateMediaAsset
assets | MediaAssetDetail | 29 | assets.media_asset | 0 | 1 | getMediaAsset
assets | MediaReplaceResult | 4 | none — computed | 0 | 1 | replaceMediaAsset
assets | UploadTicket | 12 | assets.media_upload | 0 | 1 | createUpload
catalogue | AcquireLeaseRequest | 7 |  | 1 | 0 | acquireInventoryHold | The body of acquireInventoryHold.
catalogue | AlternativeCode | 5 | catalogue.alternative_code | 0 | 2 | listAlternativeCodes, setAlternativeCodes
catalogue | BookingVelocityTimeToEventRuleBuilderInput | 12 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setBookingVelocityTime | What Booking Velocity & Time-to-Event Rule Builder submits.
catalogue | BookingVelocityTimeToEventRuleBuilderView | 12 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setBookingVelocityTime | What Booking Velocity & Time-to-Event Rule Builder displays.
catalogue | BulkPriceResult | 4 |  | 0 | 1 | bulkChangePrices | 2.9.9.
catalogue | BulkProductCreationCatalogueImportInput | 9 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | createBulkProductCatalogue | What Bulk Product Creation & Catalogue Import submits.
catalogue | BulkProductCreationCatalogueImportView | 11 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | createBulkProductCatalogue | What Bulk Product Creation & Catalogue Import displays.
catalogue | BundleSummary | 10 | none — projection over bundle | 0 | 2 | listCatalogueBundles, publishBundle | One published catalogue bundle — the signed snapshot terminals pull (ADR-0013).
catalogue | CatalogueBundle | 9 | catalogue.published_bundle | 0 | 1 | getLatestBundle
catalogue | CatalogueImportJob | 26 | catalogue.import_job | 0 | 1 | commitCatalogueImport | 1.4.2.
catalogue | CreateEventRequest | 4 |  | 1 | 0 | createEvent
catalogue | CreatePriceListRequest | 7 |  | 1 | 0 | createPriceList
catalogue | DemandOccupancyAvailabilityRuleBuilderInput | 12 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setDemandOccupancyAvailability | What Demand, Occupancy & Availability Rule Builder submits.
catalogue | DemandOccupancyAvailabilityRuleBuilderView | 12 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setDemandOccupancyAvailability | What Demand, Occupancy & Availability Rule Builder displays.
catalogue | DynamicPriceRuleDetail | 3 | none — composed from a rule, its conditions and its actions | 1 | 1 | setDynamicPriceRule | A rule is unreadable without both halves.
catalogue | DynamicPricingControl | 39 | catalogue.dynamic_pricing_control | 1 | 1 | setDynamicPricingGuardrailPolicy | The limits and the autonomy of dynamic pricing at one scope (29 September, data model DM3).
catalogue | EligibilityCheckRequest | 2 |  | 1 | 0 | checkBookingEligibility | Request only.
catalogue | EligibilityCheckResult | 3 | none — computed per request | 0 | 1 | checkBookingEligibility
catalogue | EntitlementTemplate | 33 | catalogue.entitlement_template | 1 | 1 | createEntitlementTemplate
catalogue | Event | 8 | catalogue.event | 0 | 2 | createEvent, updateEvent
catalogue | GroupPackageDefinition | 11 | catalogue.group_package | 1 | 2 | getGroupPackageDefinition, setGroupPackageDefinition
catalogue | GuestMembership | 11 |  | 0 | 1 | getMyMemberships | 19.2.26 to 19.2.28.
catalogue | InventoryHold | 18 | catalogue.inventory_hold | 0 | 3 | acquireInventoryHold, relinquishInventoryHold, renewInventoryHold
catalogue | Performance | 11 | catalogue.performance | 0 | 2 | getPerformance, updatePerformance
catalogue | PerformanceAvailabilityPage | 3 | none — computed on read | 0 | 1 | getAvailability | The getAvailability answer (named 29 September, rev 3 REV3-1).
catalogue | PriceCategory | 16 | catalogue.price_category | 1 | 1 | setPriceCategoryRateType | The library of price categories and rate types (29 September, data model DM3).
catalogue | PriceHierarchyInheritanceConfigurationInput | 3 | none — request only; no existing table covers these fields — the closest is catalogue.price_list at 17%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | setPriceHierarchyInheritance | What Price Hierarchy & Inheritance Configuration submits.
catalogue | PriceHierarchyInheritanceConfigurationView | 4 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setPriceHierarchyInheritance | What Price Hierarchy & Inheritance Configuration displays.
catalogue | PriceList | 30 | catalogue.price_list | 0 | 2 | createPriceList, updatePriceList
catalogue | PriceListMasterConfigurationInput | 24 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setPriceListMaster | What Price List Master Configuration submits.
catalogue | PriceListMasterConfigurationView | 25 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setPriceListMaster | What Price List Master Configuration displays.
catalogue | Product | 43 | catalogue.product | 0 | 3 | cloneProduct, getProduct, updateProduct
catalogue | ProductCategory | 12 | catalogue.product_category | 0 | 1 | setProductCategories | Retail Board 2 of the client's design set, 20 August.
catalogue | ProductCategoryNode | 13 | none — projection over catalogue.product_category | 0 | 1 | listProductCategories | One node of the tree listProductCategories returns.
catalogue | ProductEligibilityRule | 15 | catalogue.product_eligibility_rule | 1 | 2 | getProductEligibilityRule, setProductEligibilityRule | Participation limits for one product.
catalogue | ProductVariant | 9 | catalogue.variant | 0 | 1 | resolveProductByCode
catalogue | RateStructureBuilderInput | 13 | none — request only; no existing table covers these fields — the closest is catalogue.price at 4%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | setRateStructure | What Rate Structure Builder submits.
catalogue | RateStructureBuilderView | 14 | none — projection over catalogue state, assembled at read time from tables that already exist | 0 | 1 | setRateStructure | What Rate Structure Builder displays.
catalogue | RoundingProfile | 15 | catalogue.rounding_profile | 1 | 1 | setCurrencyRoundingRule | Precision and rounding for one currency (29 September, data model DM3).
catalogue | RulePriorityConflictInput | 5 | none — request only; the saved hierarchy and test cases are the rows listRulePriorityConflict reads | 1 | 0 | setRulePriorityConflict | What setRulePriorityConflict takes (decided 29 September, readiness close-out; VM close-out for BO-441 Reorder, Validate, Test, Save).
catalogue | RulePriorityConflictView | 8 | none — projection over the saved priority order and test cases | 0 | 1 | setRulePriorityConflict | What setRulePriorityConflict returns: the order in force, the conflicts it has and, in test mode, the result.
catalogue | UpdateProductRequest | 13 |  | 1 | 0 | updateProduct
catalogue | WaitlistEntry | 11 | catalogue.waitlist_entry | 1 | 1 | joinWaitlist
finance | Account | 15 | ledger.account | 0 | 2 | createAccount, updateAccount
finance | CreateAccountRequest | 11 |  | 1 | 0 | createAccount
finance | CreateTaxCodeRequest | 8 |  | 1 | 0 | createTaxCode
finance | FinCreditMemo | 22 | ledger.credit_memo + ledger.credit_memo_line | 0 | 1 | issueCreditMemo | 5.7.94.
finance | FinEInvoicingProvider | 12 | ledger.einvoicing_provider | 1 | 1 | setEInvoicingProvider | 6.1.1.
finance | FinIssueCreditMemoRequest | 6 | none — request only | 1 | 0 | issueCreditMemo
finance | FinIssueTaxInvoiceRequest | 6 | none — request only | 1 | 0 | issueTaxInvoice
finance | FinTaxDocumentRendition | 7 | none — a signed link to the stored PDF | 0 | 1 | getTaxDocumentRendition
finance | FinTaxInvoice | 34 | ledger.tax_invoice + ledger.tax_invoice_line | 0 | 2 | getTaxInvoice, issueTaxInvoice | 5.7.93, 5.10.3.
finance | FinancialReport | 7 | none — computed from replica | 0 | 1 | getFinancialReport
finance | FxProviderAssignment | 5 | ledger.fx_provider_assignment | 0 | 1 | setFxProvider | Which provider serves one FX purpose in one region, as setFxProvider sets it and ingestFxRates reads it.
finance | FxRate | 12 | ledger.fx_rate | 1 | 1 | setFxRate | Also the setFxRate body.
finance | LegalEntity | 11 | ledger.legal_entity | 1 | 1 | createLegalEntity | Also the createLegalEntity body.
finance | TaxCode | 12 | ledger.tax_code | 0 | 2 | createTaxCode, updateTaxCode
fnb | Bill | 8 | none — computed from visit orders | 0 | 1 | getGuestBill
fnb | ColdChainEvent | 9 | fnb.cold_chain_event | 1 | 1 | logColdChain | Board 5G.
fnb | CorrectiveAction | 13 | fnb.corrective_action | 0 | 2 | escalateCorrectiveAction, signCorrectiveAction | What was done about a finding, and who signed it.
fnb | CourseRules | 6 | fnb.course_rule | 1 | 1 | setCourseRules | An outlet's coursing default.
fnb | CreateFnbOrderRequest | 7 | none — request only | 1 | 0 | createFnbOrder
fnb | CreateGuestOrderRequest | 8 |  | 1 | 0 | createGuestFnbOrder
fnb | CreateMenuRequest | 4 | none — request only | 1 | 0 | createMenu
fnb | DeliveryLocation | 11 | fnb.delivery_location | 0 | 3 | createDeliveryLocation, setDeliveryLocationOutletMapping, updateDeliveryLocation
fnb | FnbDeliveryPolicy | 16 | fnb.delivery_policy | 1 | 2 | getFnbDeliveryPolicy, setFnbDeliveryPolicy
fnb | FnbOrder | 17 | fnb.service_order + fnb.service_order_line | 0 | 3 | createFnbOrder, getFnbOrder, markOrderCollected
fnb | GuestMenu | 7 | none — projection over menu, item and availability | 0 | 1 | getGuestMenu
fnb | GuestOrderResult | 9 | none — projection over fnb_order | 0 | 1 | createGuestFnbOrder
fnb | GuestOrderStatus | 6 | none — projection over kitchen_ticket | 0 | 2 | getGuestOrderStatus, recordOrderHandover
fnb | KitchenException | 9 | fnb.kitchen_exception | 0 | 1 | logKitchenException | Board 3, 24 August.
fnb | KitchenSla | 2 |  | 1 | 1 | setKitchenSla | How long a ticket may sit, per service mode, and what pushes it up the rail (setKitchenSla).
fnb | KitchenStation | 8 | fnb.kitchen_station | 0 | 1 | setKitchenStations
fnb | KitchenTicket | 16 | fnb.kitchen_ticket + fnb.kitchen_ticket_line | 0 | 6 | fireCourse, holdCourse, prioritiseKitchenTicket, recallKitchenTicket, refireItem, setKitchenTicketStatus
fnb | LocationSession | 9 | fnb.location_session | 0 | 1 | claimLocationSession
fnb | Menu | 9 | fnb.menu | 0 | 4 | createMenu, getMenu, setMenuSections, updateMenu
fnb | MenuItem | 15 | fnb.menu_item | 0 | 2 | attachModifierGroup, setItemAvailability
fnb | ModifierGroup | 7 | fnb.modifier_group + fnb.modifier_option | 1 | 1 | createModifierGroup | An F&B modifier is a choice added to a dish at the moment of ordering — *no onions*, *extra cheese*, *cooked medium*.
fnb | OpenTableVisitRequest | 6 | none — request only | 1 | 0 | openTableVisit
fnb | OrderLabel | 8 | none — rendered from the kitchen ticket and its order | 0 | 1 | printOrderLabel | What goes on the bag (printOrderLabel).
fnb | ProductionPlan | 7 | fnb.production_plan + fnb.production_plan_line | 1 | 2 | buildProductionPlan, releaseProductionPlan | Board 2M.
fnb | Recipe | 4 | fnb.recipe + fnb.recipe_ingredient | 1 | 1 | setRecipe
fnb | RestaurantWaitlist | 11 | fnb.waitlist_entry | 1 | 2 | joinRestaurantWaitlist, leaveRestaurantWaitlist | BL-130.
fnb | StationRebalance | 2 |  | 1 | 1 | rebalanceStationLoad | A temporary move of work between stations (rebalanceStationLoad).
fnb | TableMap | 3 | none — projection | 0 | 2 | getTableMap, setTableLayout
fnb | TableReservation | 16 | fnb.table_reservation | 2 | 3 | createTableReservation, seatTableReservation, updateTableReservation
fnb | TableSession | 9 | fnb.table_session | 0 | 1 | claimTableSession
fnb | TableState | 13 | none — projection over table and visit | 0 | 1 | clearTable
fnb | TableVisit | 15 | fnb.table_visit | 0 | 3 | mergeTableVisits, moveTableVisit, openTableVisit
fnb | TemperatureLog | 11 | fnb.temperature_log | 1 | 0 | logTemperature | Board 5J of the client F&B pack, 20 August.
games | GameCard | 13 | games.card | 0 | 3 | getGameCard, issueGameCard, transferGameCard
games | IssueGameCardRequest | 7 | none — request only | 1 | 0 | issueGameCard
identity | ChangeCredentialRequest | 3 |  | 1 | 0 | changeOwnCredential | Request only.
identity | CreatePrincipalRequest | 6 |  | 1 | 0 | createPrincipal
identity | DelegatedAccess | 18 | identity.delegated_access | 0 | 1 | grantDelegation
identity | GuestSession | 11 | none — Redis session registry | 0 | 6 | getGuestSession, guestPasswordLogin, guestSocialLogin, guestUaePassLogin, registerGuest, verifyGuestOtp
identity | IdentityGuestDocumentSubmission | 7 | none — request only; the document goes to pii.subject_document and the verification to identity.guest_identity_verification | 1 | 0 | submitGuestIdentityDocument
identity | IdentityGuestVerification | 13 | identity.guest_identity_verification | 0 | 2 | getMyIdentityVerification, submitGuestIdentityDocument | One guest identity-document verification (5.3.21; decided 29 September, build pass): the document it checks, its status, the method and who decided.
identity | IdentityGuestVerificationPolicy | 13 | identity.guest_verification_policy | 1 | 1 | setGuestVerificationPolicy | The tenant's configurable identity workflow for guests (5.3.21; decided 29 September, build pass).
identity | LoginRequest | 5 |  | 1 | 0 | login
identity | LoginResponse | 9 | none — computed | 0 | 1 | login
identity | MfaEnrolment | 7 | none — transient | 0 | 1 | enrolMfaMethod
identity | MfaMethod | 8 | identity.mfa_method | 0 | 2 | listMfaMethods, verifyMfaEnrolment
identity | PasswordPolicy | 13 | identity.password_policy | 1 | 1 | setPasswordPolicy | BL-144.
identity | PlatformStaffGrant | 9 | identity.platform_staff_grant | 0 | 1 | openPlatformStaffGrant | One platform operator's time-boxed access into this tenant (decided 28 September, audit R098).
identity | Principal | 9 | identity.principal | 0 | 2 | createPrincipal, updatePrincipal
identity | RegisterGuestRequest | 6 |  | 1 | 0 | registerGuest
identity | Role | 9 | identity.role | 0 | 1 | createRole
identity | Session | 11 |  | 0 | 2 | getCurrentSession, selectRole
identity | TokenPair | 3 | none — transient | 0 | 1 | refreshToken
inventory | CreateGoodsReceiptRequest | 6 | none — request only | 1 | 0 | createGoodsReceipt
inventory | CreateInventoryItemRequest | 16 | none — request only | 1 | 0 | createInventoryItem
inventory | GoodsReceipt | 12 | inventory.goods_receipt + inventory.goods_receipt_line | 0 | 2 | createGoodsReceipt, rejectReceivedGoods
inventory | InventoryItem | 26 | inventory.item | 0 | 2 | createInventoryItem, updateInventoryItem
inventory | InventoryKitDefinition | 2 | none — composed of the item's inventory.kit_component rows | 1 | 1 | setInventoryKitDefinition | 4.4.20.
maintenance | InspectionTemplate | 10 | maintenance.inspection_template + maintenance.inspection_template_item | 1 | 1 | createInspectionTemplate
marketing-crm | AgentAvailability | 7 | marketing.agent_availability | 0 | 1 | setAgentAvailability
marketing-crm | Campaign | 24 | marketing.campaign | 0 | 3 | createCampaign, stopCampaign, updateCampaign
marketing-crm | Case | 23 | marketing.case | 0 | 2 | createCase, raiseMyCase
marketing-crm | CaseDetail | 26 | marketing.case | 0 | 1 | replyToMyCase
marketing-crm | Challenge | 14 | marketing.challenge | 1 | 1 | createChallenge | BL-022, CF-137.
marketing-crm | ClaimDeviceConsentRequest | 1 | none — request only | 1 | 0 | claimDeviceConsent
marketing-crm | ConsentPurposeConfig | 7 | marketing.consent_purpose + marketing.consent_purpose_channel | 0 | 1 | setConsentPurposes
marketing-crm | ConsentQuestion | 11 | marketing.consent_question + marketing.consent_question_version | 2 | 2 | createConsentQuestion, updateConsentQuestion | A venue-defined consent question asked at booking (decided 29 September, rev 3 REV3-26).
marketing-crm | ConsentState | 2 | none — projection over consent_record | 0 | 3 | claimDeviceConsent, getGuestConsents, recordConsent
marketing-crm | Conversation | 22 | marketing.conversation | 0 | 1 | handoverToAgent | 22.8.
marketing-crm | ConversationMessage | 8 | marketing.conversation_message + marketing.conversation_message_attachment | 0 | 1 | sendConversationMessage
marketing-crm | CookieBannerPreferenceCenterDesignerView | 21 | marketing.cookie_banner_design | 1 | 1 | setCookieBannerDesign | One version of a cookie banner and preference-centre design (pack 17.1.6).
marketing-crm | CookieConsentRuntime | 6 | none — assembled at read time from marketing.cookie_banner_design, marketing.tracking_technology and marketing.device_consent | 0 | 1 | getCookieConsentRuntime | What getCookieConsentRuntime gives the storefront tag loader and the app SDK gate (2.6.52, 2.6.58).
marketing-crm | CookieTrackingDigitalTechnologyRegistryView | 22 | marketing.tracking_technology | 1 | 1 | setTrackingTechnology | One governed tracking technology (pack 17.1.5 Registry Fields; BL-073 §4a).
marketing-crm | CreateCampaignRequest | 14 | none — request only | 1 | 0 | createCampaign
marketing-crm | CreateCaseRequest | 13 | none — request only | 1 | 0 | createCase
marketing-crm | CreateSegmentRequest | 6 | none — request only | 1 | 0 | createSegment
marketing-crm | DeviceConsent | 17 | marketing.device_consent + marketing.device_consent_category | 0 | 1 | recordDeviceConsent | One cookie decision by a visitor nobody has identified yet (BL-073 §4b, decided 29 September).
marketing-crm | FormDefinition | 16 | marketing.form_definition + marketing.form_definition_field | 1 | 1 | createForm | CF-129, CL-04.
marketing-crm | GuestDevice | 14 | marketing.guest_device | 0 | 1 | registerGuestDevice
marketing-crm | GuestDocument | 9 | marketing.guest_document | 1 | 1 | uploadGuestDocument | BL-133.
marketing-crm | GuestIdentification | 7 |  | 0 | 1 | identifyGuest | The answer to "who is this" at a till, resolved from any identifier.
marketing-crm | GuestPreferences | 8 | marketing.guest_preference | 1 | 1 | updateGuestPreferences | What the guest likes, kept apart from what they permit (consent) and from who they are (the profile).
marketing-crm | GuestProfile | 17 | marketing.guest_profile | 0 | 1 | updateMyProfile
marketing-crm | GuestProfileDetail | 23 | marketing.guest_profile | 0 | 1 | getGuestProfile
marketing-crm | InvitationCampaign | 11 | marketing.invitation_campaign | 1 | 1 | createInvitationCampaign | BL-150.
marketing-crm | LaunchResult | 5 | none — computed | 0 | 1 | launchCampaign
marketing-crm | LoyaltyPosition | 11 | marketing.loyalty_position | 0 | 1 | redeemLoyaltyPoints
marketing-crm | LoyaltyProgramme | 9 | marketing.loyalty_programme + marketing.points_earning_rule + marketing.programme_tier | 1 | 1 | createLoyaltyProgramme
marketing-crm | LoyaltyRuleSet | 4 | none — composed from the rule tables of one programme | 1 | 1 | setLoyaltyRules | Every rule a programme runs on, read and written as one thing.
marketing-crm | MarketingSubscription | 8 | marketing.subscription | 1 | 2 | getMarketingSubscription, setMarketingSubscription | Drafted 4 September.
marketing-crm | MessageTemplate | 11 | marketing.message_template | 1 | 1 | createMessageTemplate
marketing-crm | RecordConsentAnswersRequest | 4 | none — request only | 1 | 0 | recordConsentAnswers
marketing-crm | RecordConsentRequest | 6 | none — request only | 1 | 0 | recordConsent
marketing-crm | RecordDeviceConsentRequest | 11 | none — request only | 1 | 0 | recordDeviceConsent | What the banner or preference centre sends to recordDeviceConsent.
marketing-crm | Referral | 10 | marketing.referral | 1 | 1 | createReferral | BL-034.
marketing-crm | Review | 13 | marketing.review | 0 | 1 | submitReview
marketing-crm | Segment | 10 | marketing.segment + marketing.segment_criterion | 0 | 1 | createSegment
marketing-crm | SeoMetadata | 15 | control.seo_metadata | 1 | 1 | setSeoMetadata | 22.11.1 to 22.11.12, CF-137.
marketing-crm | SubmitReviewRequest | 8 | none — request only | 1 | 0 | submitReview
marketing-crm | Wishlist | 2 | none — wrapper. The items are the table, keyed by subject | 0 | 2 | addToWishlist, getWishlist
orders | AddCartLineRequest | 10 | none — request only | 1 | 0 | addCartLine
orders | AppendEntitlementRequest | 5 | none — request only | 1 | 0 | appendEntitlementToMedia
orders | AppendEntitlementResult | 3 | none — computed | 0 | 1 | appendEntitlementToMedia
orders | ApplyCartPromoCodeRequest | 1 | none — request only | 1 | 0 | applyCartPromoCode
orders | BillingStatement | 10 | none — computed from orders.payment and payments.dunning_case | 0 | 1 | getBillingStatement | 2.14.19-2.14.23, 5.7.96, BL-100.
orders | Cart | 21 | orders.cart | 0 | 7 | addCartLine, applyCartPromoCode, createCart, extendCart, getCart, removeCartLine, updateCartLine
orders | CartMergeResult | 3 | none — computed | 0 | 1 | claimCart
orders | CreateOrderRequest | 9 |  | 1 | 0 | createOrder
orders | CreatePaymentRequest | 12 |  | 1 | 0 | createPayment
orders | CreateRefundRequest | 8 |  | 1 | 0 | createRefund
orders | CreateResaleListingRequest | 3 | none — request only | 1 | 0 | createResaleListing | Request only; persisted as ResaleListing.
orders | EntitlementShare | 7 | none — a view of the identity.delegated_access row shareEntitlement writes | 0 | 1 | shareEntitlement | A second person's right to present an entitlement the owner still holds.
orders | ExchangeOrderRequest | 6 |  | 1 | 0 | exchangeOrderLines
orders | GroupBooking | 21 | orders.group_booking | 0 | 2 | getGroupBooking, requestGroupBooking | BL-028.
orders | GroupBookingRequest | 10 |  | 1 | 0 | requestGroupBooking | Request only.
orders | Invitation | 13 | orders.invitation | 0 | 1 | respondToInvitation | 8.1.3 to 8.1.5.
orders | ManualDiscountRequest | 8 | none — request only | 1 | 0 | applyManualDiscount
orders | MediaEntitlements | 7 | none — projection over entitlement and scan history | 0 | 1 | getMediaEntitlements
orders | ModifyOrderRequest | 5 |  | 1 | 0 | modifyOrder
orders | Order | 25 | orders.sales_order + orders.order_line | 0 | 6 | applyManualDiscount, checkoutCart, createOrder, getOrder, holdOrder, voidOrder
orders | OrderExchangeResult | 8 | none — computed | 0 | 2 | exchangeOrderLines, rescheduleOrder
orders | OrderModificationResult | 7 | none — computed | 0 | 1 | modifyOrder
orders | OrderResumeResult | 3 | none — computed | 0 | 1 | resumeOrder
orders | OrderStatement | 8 | none — computed from order, payment, refund and ledger | 0 | 1 | getOrderStatement
orders | OrderSyncResult | 3 | none — computed | 0 | 1 | syncOrders
orders | Payment | 19 | orders.payment | 0 | 4 | addTip, capturePayment, createPayment, inquirePaymentStatus
orders | PaymentProvider | 15 | payments.provider | 0 | 1 | setPaymentProvider | BL-116, CF-131.
orders | PaymentToken | 9 | payments.token | 0 | 1 | storePaymentToken | BL-116.
orders | Refund | 18 | orders.refund | 0 | 1 | createRefund
orders | RefundPolicy | 9 | orders.refund_policy + orders.refund_policy_time_band | 1 | 1 | setRefundPolicy | Venue-configured.
orders | ReissuedEntitlement | 5 | none — computed; both entitlements live in access.entitlement | 0 | 1 | reissueEntitlement | The zero-value reissue — the old entitlement voided, the new one issued, and the reason that links them.
orders | ResaleListing | 16 | orders.resale_listing | 0 | 1 | createResaleListing | BL-060.
orders | Reservation | 8 | orders.reservation + orders.reservation_line | 0 | 1 | getReservation | An unpaid hold, not a booking.
orders | SetPaymentProviderRequest | 16 | none — request only; the provider lands in payments.provider and its rules in payments.routing_rule | 1 | 0 | setPaymentProvider | Request only.
orders | TicketTemplate | 11 | orders.ticket_template + orders.ticket_template_channel | 0 | 2 | createTicketTemplate, updateTicketTemplate | BL-102.
orders | TicketTemplateRequest | 10 |  | 2 | 0 | createTicketTemplate, updateTicketTemplate | Request only; persisted as TicketTemplate.
orders | TicketTransfer | 12 | orders.ticket_transfer | 0 | 2 | claimTicketTransfer, transferOrderTickets
orders | VisitReminder | 7 | orders.visit_reminder | 1 | 2 | getVisitReminder, setVisitReminder | One reminder per booking, set by the guest.
orders | WalletPass | 9 | orders.wallet_pass | 0 | 1 | issueWalletPass | BL-029.
payments | DunningCase | 14 | payments.dunning_case | 0 | 1 | retryMyDunningPayment | BL-100.
payments | PayInstalmentPlan | 12 | payments.instalment_plan + payments.instalment | 0 | 1 | createInstalmentPlan | 4.2.17.
payments | PayInstalmentPolicy | 9 | payments.instalment_policy | 1 | 1 | setInstalmentPolicy | 4.2.17, 2.14.19.
payments | PaymentProviderConnection | 11 | payments.provider_connection | 1 | 1 | createPaymentProviderConnection | Boards 2.2 and 2.4.
payments | RetryDunningPaymentRequest | 1 |  | 1 | 0 | retryMyDunningPayment | Request only.
promotions | Bundle | 22 | promotions.bundle + promotions.bundle_component | 0 | 3 | createBundle, getBundle, updateBundle
promotions | BundleComponentBuilderInput | 7 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setBundleComponent | What Bundle Component Builder submits.
promotions | BundleComponentBuilderView | 7 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setBundleComponent | What Bundle Component Builder displays.
promotions | BundleDefinitionSetupInput | 15 | none — request only; no existing table covers these fields — the closest is promotions.allocation_split at 5%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | setBundleDefinition | What Bundle Definition & Setup submits.
promotions | BundleDefinitionSetupView | 15 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setBundleDefinition | What Bundle Definition & Setup displays.
promotions | BuyXGetYBogoRuleBuilderInput | 15 | none — request only; no existing table covers these fields — the closest is promotions.bundle_component at 7%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | setBuyGetBogo | What Buy X Get Y / BOGO Rule Builder submits.
promotions | BuyXGetYBogoRuleBuilderView | 15 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setBuyGetBogo | What Buy X Get Y / BOGO Rule Builder displays.
promotions | CampaignBudgetFinancialLimitSetupInput | 24 | none — request only; saved as the `promotions.campaign` header (campaign, budget owner, business entity, venue, effective dates) and its `promotions.campaign_budget` lines (one per budget amount given, with funding source, cost centre and scope) (DM5, 29 September: data model for the agreed operations) | 1 | 0 | setCampaignBudgetFinancial | What Campaign Budget & Financial Limit Setup submits.
promotions | CampaignBudgetFinancialLimitSetupView | 24 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setCampaignBudgetFinancial | What Campaign Budget & Financial Limit Setup displays.
promotions | CodeDistributionAssignmentManagerInput | 5 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setCodeDistributionManager | What Code Distribution & Assignment Manager submits.
promotions | CodeDistributionAssignmentManagerView | 12 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setCodeDistributionManager | What Code Distribution & Assignment Manager displays.
promotions | CommercialCampaign | 10 | promotions.campaign + promotions.campaign_budget | 0 | 2 | createCommercialCampaign, updateCommercialCampaign | A commercial campaign: the grouping of promotions, coupon campaigns and bundles that share an owner, a business entity, dates and a budget.
promotions | ConflictAnalysis | 3 | none — computed | 0 | 1 | analysePromotionConflicts
promotions | CouponCampaign | 14 | promotions.coupon_campaign | 0 | 1 | createCouponCampaign
promotions | CouponCode | 14 | promotions.coupon_code | 0 | 1 | getCouponCode
promotions | CouponPromoCodeBuilderInput | 10 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setCouponPromoCode | What Coupon & Promo Code Builder submits.
promotions | CouponPromoCodeBuilderView | 10 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setCouponPromoCode | What Coupon & Promo Code Builder displays.
promotions | CreateBundleRequest | 17 | none — request only | 1 | 0 | createBundle
promotions | CreateCommercialCampaignRequest | 8 | none — request only; saved as a `promotions.campaign` row (CommercialCampaign) | 1 | 0 | createCommercialCampaign | What createCommercialCampaign takes: the campaign header only.
promotions | CreateCouponCampaignRequest | 10 | none — request only | 1 | 0 | createCouponCampaign
promotions | CreatePromotionRequest | 17 | none — request only | 1 | 0 | createPromotion
promotions | CrossCategoryPromotionBuilderInput | 10 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setCrossCategoryPromotion | What Cross-Category Promotion Builder submits.
promotions | CrossCategoryPromotionBuilderView | 10 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setCrossCategoryPromotion | What Cross-Category Promotion Builder displays.
promotions | EligibilityRuleBuilderInput | 20 | none — request only; saved as a `promotions.promotion_rule` row (PromotionRule, ruleType eligibility, its criteria as the condition group and ruleEffect as effect) (DM5, 29 September: data model for the agreed operations) | 1 | 0 | setEligibilityRule | What Eligibility Rule Builder submits.
promotions | EligibilityRuleBuilderView | 20 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setEligibilityRule | What Eligibility Rule Builder displays.
promotions | EvaluatePromotionsRequest | 8 | none — request only | 1 | 0 | evaluatePromotions
promotions | FixedPriceNForXOfferBuilderInput | 8 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setFixedPriceOffer | What Fixed-Price & “N for X” Offer Builder submits.
promotions | FixedPriceNForXOfferBuilderView | 8 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setFixedPriceOffer | What Fixed-Price & “N for X” Offer Builder displays.
promotions | GiftFreeProductAddedValueOfferBuilderInput | 15 | none — request only; no existing table covers these fields — the closest is promotions.bundle_component at 7%, so this is not an update to anything the package stores today and no new table has been decided | 1 | 0 | setGiftFreeProduct | What Gift, Free Product & Added-Value Offer Builder submits.
promotions | GiftFreeProductAddedValueOfferBuilderView | 15 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setGiftFreeProduct | What Gift, Free Product & Added-Value Offer Builder displays.
promotions | GuestChoiceBuildYourOwnBundleDesignerInput | 8 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setGuestChoiceBuild | What Guest Choice & Build-Your-Own Bundle Designer submits.
promotions | GuestChoiceBuildYourOwnBundleDesignerView | 8 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setGuestChoiceBuild | What Guest Choice & Build-Your-Own Bundle Designer displays.
promotions | Promotion | 24 | promotions.promotion | 0 | 3 | createPromotion, publishPromotion, updatePromotion
promotions | PromotionEvaluation | 4 | none — computed | 0 | 1 | evaluatePromotions
promotions | PromotionRuleBuilderInput | 20 | none — request only; saved as a `promotions.promotion_rule` row (PromotionRule, ruleType benefit) (DM5, 29 September: data model for the agreed operations) | 1 | 0 | setPromotionRule | What Promotion Rule Builder submits.
promotions | PromotionRuleBuilderView | 20 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setPromotionRule | What Promotion Rule Builder displays.
promotions | PromotionUsage | 7 | none — aggregated from ledger and orders | 0 | 1 | getPromotionUsage
public-api | ApiClient | 14 | control.api_client | 1 | 0 | createApiClient | CF-135a.
public-api | ApiLicence | 9 | control.api_licence | 1 | 1 | setApiLicensing | 13.3.24, decision D5.
public-api | ApiVersion | 9 | control.api_version | 0 | 1 | deprecateApiVersion | 13.1.31 to 13.1.35, ADR-0026.
public-api | DeveloperAccount | 8 | control.developer_account | 1 | 1 | registerDeveloper | 13.1.6 to 13.1.9.
public-api | IntegrationListing | 12 | control.integration_listing | 0 | 1 | certifyIntegration | 13.1.50, decision D1.
public-api | ProductionAccessRequest | 14 | control.production_access_request | 0 | 1 | decideProductionAccess | A developer's request for production keys (17 September minutes, M17-06): sandbox, then certification, then production.
queue | CreateQueueRequest | 20 | none — request only | 1 | 0 | createQueue
queue | JoinQueueRequest | 8 | none — request only | 1 | 0 | joinQueue
queue | Queue | 31 | queue.queue + queue.queue_operating_window | 0 | 2 | createQueue, updateQueue
queue | QueueDetail | 36 | queue.queue | 0 | 1 | getQueue
queue | QueueFeed | 8 | queue.feed | 1 | 1 | configureQueueFeed
queue | QueueFeedHealth | 8 | none — computed | 0 | 1 | getQueueFeedHealth
queue | WaitTime | 11 | none — computed from readings and throughput | 0 | 1 | getWaitTimes
queue | WaitingGuest | 22 | queue.entry | 0 | 2 | getWaitingGuest, joinQueue
reporting | Alert | 18 | reporting.alert | 0 | 1 | listAlerts | A raised alert.
reporting | AlertRule | 13 | reporting.alert_rule | 1 | 1 | setAlertRule | BL-152, CF-134.
reporting | CreateDashboardRequest | 6 | none — request only | 2 | 0 | createDashboard, updateDashboard
reporting | CreateReportRequest | 10 | none — request only | 2 | 0 | createReport, updateReport
reporting | Dashboard | 11 | reporting.dashboard + reporting.dashboard_tile | 0 | 2 | createDashboard, updateDashboard
reporting | DashboardData | 12 | none — computed | 0 | 1 | getDashboard
reporting | KpiDefinition | 12 | reporting.kpi_definition | 1 | 1 | createKpi | BI boards 2.5 and 10.2.
reporting | NaturalLanguageAnswer | 13 | none — computed | 0 | 1 | askReportingQuestion
reporting | ReportDefinition | 19 | reporting.report_definition + reporting.report_column + reporting.report_filter | 0 | 4 | createReport, getReport, saveNaturalLanguageQuery, updateReport
reporting | ReportResult | 8 | none — result set, cached in object storage | 0 | 1 | runReport
reporting | RunReportRequest | 5 | none — request only | 1 | 0 | runReport
reporting | SemanticModel | 5 | reporting.semantic_model | 1 | 1 | setSemanticModel | BI boards 3.3 and 10.6.
resources | CreateResourceHoldRequest | 8 | none — request only | 1 | 0 | createResourceHold
resources | MapResourceAvailability | 6 | none — computed from placed resources, bookings, holds and blocks | 0 | 1 | getMapResourceAvailability | What getMapResourceAvailability returns: every placed resource on one map, for one window, in one answer (rev 3 REV3-15).
resources | Resource | 16 | resources.resource | 2 | 2 | createResource, updateResource | A specific object, not a quantity of interchangeable ones.
resources | ResourceAvailability | 3 |  | 0 | 1 | getResourceAvailability | Free windows, with setup and teardown already subtracted.
resources | ResourceBlock | 8 | resources.resource_block | 1 | 1 | createResourceBlock | Board 2.07.
resources | ResourceHold | 15 | resources.resource_hold | 0 | 3 | createResourceHold, extendResourceHold, getResourceHold | A guest's pick on the map, held while they pay (decided 29 September, rev 3 REV3-15).
resources | ResourcePackage | 14 | resources.resource_package | 2 | 2 | createResourcePackage, updateResourcePackage | Board 1.08.
resources | ResourceRequirement | 10 | resources.resource_requirement | 0 | 1 | setExperienceResourceRequirements | A type and a quantity, never a named resource.
resources | ResourceSchedule | 9 | resources.resource_schedule | 1 | 1 | setResourceSchedule | Boards 2.03 and 2.04.
retail | CreateMerchandiseRequest | 12 | none — request only | 1 | 0 | createMerchandise
retail | CreateRetailReturnRequest | 7 | none — request only | 1 | 0 | createRetailReturn
retail | CreateRetailSaleRequest | 7 | none — request only | 1 | 0 | createRetailSale
retail | MerchandiseItem | 16 | retail.merchandise | 0 | 2 | createMerchandise, updateMerchandise
retail | MerchandiseReservation | 9 | retail.reservation + retail.reservation_line | 0 | 1 | reserveMerchandise
retail | PriceCheck | 10 | none — computed | 0 | 1 | lookupMerchandise
retail | RetailReturn | 15 | retail.return + retail.return_line | 0 | 1 | createRetailReturn
retail | RetailSale | 14 | retail.sale + retail.sale_line | 0 | 2 | createRetailSale, getRetailSale
retail | ReturnPolicy | 10 | retail.return_policy | 1 | 2 | getReturnPolicy, setReturnPolicy
retail | ShopAndDrop | 15 | retail.shop_and_drop + retail.shop_and_drop_line | 0 | 1 | lookupShopAndDrop
seating | CreateSeatHoldRequest | 5 | none — request only | 1 | 0 | createSeatHold
seating | SeatAvailability | 7 | none — computed from seat, hold and block | 0 | 1 | getSeatAvailability
seating | SeatCategory | 8 | seating.seat_category | 0 | 1 | createSeatCategory
seating | SeatHold | 11 | seating.seat_hold | 0 | 3 | createSeatHold, extendSeatHold, getSeatHold
seating | SeatRecommendationRequest | 6 | none — request only | 1 | 0 | recommendSeats
shift | CashMovement | 14 | orders.cash_movement | 0 | 1 | createCashMovement
shift | CloseShiftRequest | 5 |  | 1 | 0 | closeShift
shift | CreateCashMovementRequest | 7 |  | 1 | 0 | createCashMovement
shift | Denomination | 7 | platform.denomination | 0 | 2 | listDenominations, setDenominations | Raised in review by Tanmay: denominations belong in a table, not in JSON.
shift | DepositBox | 17 | orders.deposit_box + orders.deposit_box_opening_denomination + orders.deposit_box_foreign_holding | 1 | 4 | adjustDepositBoxFloat, allocateDepositBox, closeDepositBoxes, withdrawFromDepositBox | 5.8.
shift | NoSaleEvent | 8 | orders.no_sale_event | 0 | 1 | recordNoSale
shift | OpenShiftRequest | 5 |  | 1 | 0 | openShift
shift | SetDenominationsRequest | 3 |  | 1 | 0 | setDenominations | Request only.
shift | Shift | 28 | orders.pos_shift + orders.pos_shift_approval + orders.pos_shift_incident | 0 | 8 | acceptShiftVariance, approveShiftOpen, getCurrentShift, getShift, openShift, reopenShift, resumeShift, suspendShift | approvals and incidents are child rows (26 September, pull audit R099): orders.pos_shift_approval and orders.pos_shift_incident, one row per item, keyed to the shift.
shift | ShiftCloseResult | 6 | none — computed | 0 | 1 | closeShift
subscription | CreatePlanRequest | 12 | none — request only | 2 | 0 | createPlan, createPlanVersion
subscription | CreateTenantRequest | 6 | none — request only | 1 | 0 | createTenant
subscription | LicenceAddOn | 7 | control.licence_add_on + control.licence_add_on_limit | 1 | 0 | addLicenceAddOn | Belongs to the tenant, not the plan.
subscription | LicencePosition | 4 | none — union of the tenant's plan (control.tenant.plan_id -> subscription.plan_module, subscription.plan_limit) and its add-ons (control.licence_add_on, control.licence_add_on_limit by tenant_id) | 0 | 1 | addLicenceAddOn
subscription | Plan | 17 | subscription.plan + subscription.plan_module + subscription.plan_limit | 0 | 2 | createPlan, createPlanVersion | A plan's modules and limits are rows, keyed on plan_id.
subscription | SetSubscriptionRequest | 5 | none — request only | 1 | 0 | setSubscription
subscription | Subscription | 11 | subscription.contract | 0 | 1 | setSubscription
subscription | Tenant | 22 | control.tenant | 0 | 4 | createTenant, reactivateTenant, suspendTenant, updateTenant
subscription | TerminationSchedule | 6 | none — projection of control.tenant's termination columns (termination_scheduled_at, termination_retention_until, termination_requested_by_principal_id); isReversible is computed from the retention date | 0 | 1 | terminateTenant
tenancy | ConfigureWorkstationRequest | 12 |  | 1 | 0 | configureWorkstation
tenancy | CreateScopeNodeRequest | 4 |  | 1 | 0 | createOrgUnit
tenancy | DeviceAssignment | 11 | tenancy.device_assignment | 1 | 1 | setDeviceAssignment | 16.2.9 to 16.2.11.
tenancy | OrgUnit | 8 | platform.scope | 0 | 2 | createOrgUnit, updateOrgUnit
tenancy | Outlet | 10 | platform.outlet | 1 | 3 | createOutlet, listOutlets, updateOutlet
tenancy | RegionSettings | 10 | platform.region_settings | 1 | 1 | updateRegionSettings
tenancy | SaleBoard | 7 | platform.sale_board | 2 | 3 | createSaleBoard, listSaleBoards, updateSaleBoard
tenancy | VenueSettings | 28 | platform.venue_settings | 1 | 2 | getVenueSettings, setVenueSettings | Venue-level operational configuration that no other level can answer.
tenancy | Workstation | 20 | platform.workstation | 0 | 1 | configureWorkstation
transport | CreatePassTypeRequest | 11 | none — request only | 1 | 0 | createTransportPassType
transport | CreateStationRequest | 6 | none — request only | 1 | 0 | createTransportStation
transport | CreateTimetableRequest | 7 | none — request only | 1 | 0 | createTransportTimetable
transport | CreateTransportRouteRequest | 8 | none — request only | 1 | 0 | createTransportRoute
transport | DepartureOffer | 12 | none — projection | 0 | 1 | getNextTransportDeparture
transport | FareQuote | 7 | none — computed | 0 | 1 | quoteTransportFare
transport | FareQuoteRequest | 6 | none — request only | 1 | 0 | quoteTransportFare
transport | FareTable | 8 | transport.fare_table + transport.fare_passenger_type + transport.fare_matrix_cell | 0 | 2 | getTransportFareTable, setTransportFareTable
transport | FavouriteRoute | 9 | transport.favourite_route | 0 | 1 | saveFavouriteRoute | Unique per guest, venue and ordered pair of stations.
transport | ImportTransportNetworkRequest | 3 | none — request only | 1 | 0 | importTransportNetwork
transport | PassType | 14 | transport.pass_type | 0 | 1 | createTransportPassType
transport | RouteMap | 6 | none — projection | 0 | 1 | getTransportRouteMap
transport | SetFareTableRequest | 6 | none — request only | 1 | 0 | setTransportFareTable
transport | Station | 8 | transport.station | 0 | 1 | createTransportStation
transport | Timetable | 13 | transport.timetable + transport.timetable_run | 0 | 2 | createTransportTimetable, publishTransportTimetable
transport | TransportNetworkImport | 11 | transport.network_import | 0 | 2 | applyTransportNetworkImport, importTransportNetwork
transport | TransportRoute | 13 | transport.route + transport.route_stop | 0 | 3 | createTransportRoute, getTransportRoute, updateTransportRoute
venue-map | BookableVenueMaps | 2 |  | 0 | 1 | listBookableVenueMaps | What listBookableVenueMaps returns: the published maps of one venue that carry bookable spots (decided 29 September, readiness close-out).
venue-map | PlacedResource | 12 | venuemap.placed_resource | 0 | 1 | setPlacedResource | A bookable resource where it stands on the map (decided 29 September, rev 3 REV3-15 and GAP-C2): cabana B09 on the Beach, 15 guests, Large.
venue-map | SetPlacedResourceRequest | 13 |  | 1 | 0 | setPlacedResource | What setPlacedResource takes: a PlacedResource without its server-owned fields.
venue-map | SetVenuePointRequest | 23 |  | 1 | 0 | setVenuePoint | What setVenuePoint takes: a VenuePoint without its server-owned fields, plus the point to amend.
venue-map | VenueMap | 15 | venuemap.map | 1 | 2 | createVenueMap, publishVenueMap | A park map, or a floor plan.
venue-map | VenueMapDetail | 5 |  | 0 | 1 | getVenueMap | 19.2.55.
venue-map | VenueMapGraph | 6 |  | 0 | 1 | getVenueMapGraph | 19.2.56.
venue-map | VenueMapImportJob | 12 | venuemap.import_job | 0 | 1 | importVenueGeometry | Two-phase, following seating.ImportJob, and carrying its lesson: a job that finds nothing is not a successful job.
venue-map | VenuePoint | 22 | venuemap.point | 0 | 1 | setVenuePoint | 19.2.57 to 19.2.60.
venue-map | VisitPlan | 16 | venuemap.visit_plan | 0 | 3 | generateVisitPlan, getVisitPlan, updateVisitPlan | A guest's visit plan (29 September, MOB-6): the Plan tab.
venue-map | VisitPlanBooking | 5 | none — computed; the lines are orders.cart_line rows | 0 | 1 | bookVisitPlan | What bookVisitPlan returns (29 September, MOB-6): the cart handoff.
venue-map | VisitPlanRequest | 13 | none — request only; kept as `inputs` on venuemap.visit_plan | 1 | 0 | generateVisitPlan | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
venue-map | VisitPlanUpdate | 2 | none — request only; lands as a new version of venuemap.visit_plan_item rows | 1 | 0 | updateVisitPlan | What updateVisitPlan takes (29 September, MOB-6).
wallet | CreditExpiryResult | 6 |  | 0 | 1 | expireCreditLots | Board 3.9.
wallet | GiftCard | 9 | wallet.gift_card | 0 | 1 | getGiftCard
wallet | Wallet | 10 | wallet.wallet + wallet.credit_lot | 0 | 2 | getWallet, loadGameCredits
wallet | WalletAutoReloadSetting | 10 | wallet.auto_reload_setting | 1 | 2 | getWalletAutoReloadSetting, setWalletAutoReloadSetting | 4.2.17, 4.3.28.
wallet | WalletConfigurationVersion | 6 | wallet.configuration_version | 0 | 2 | publishWalletConfiguration, restoreWalletConfigurationVersion | Boards 1.10 and 10.8.
wallet | WalletExitBalance | 8 | none — computed from wallet.wallet, wallet.credit_lot and held offline transactions | 0 | 1 | getWalletExitBalance
wallet | WalletExitSettlement | 13 | wallet.exit_settlement | 0 | 1 | settleWalletAtExit | 4.3.4.
wallet | WalletFundingRules | 12 | wallet.funding_rules | 1 | 1 | setWalletFundingRules | Board 2, which is the 27 August minute one screen for one.
wallet | WalletHold | 11 | wallet.hold | 0 | 3 | captureWalletHold, holdWalletFunds, releaseWalletHold | Taken from the backend workbook, 20 September.
wallet | WalletRefundPolicy | 6 | wallet.refund_policy | 1 | 1 | setWalletRefundPolicy | Boards 7.4 and 7.5.
wallet | WalletTransaction | 11 | wallet.wallet_transaction | 0 | 1 | transferWalletBalance
white-label | AppBuild | 15 | whitelabel.app_build | 0 | 2 | getAppBuild, requestAppBuild | One build of the tenant's branded app (decided 24 September, M24-08).
white-label | AppIcons | 5 | none — embedded in tenant_config | 0 | 2 | getAppIcons, setAppIcons
white-label | Banner | 11 | whitelabel.banner | 1 | 2 | createBanner, updateBanner
white-label | BookingFlow | 11 | whitelabel.booking_flow | 1 | 4 | createBookingFlowDefinition, getBookingFlow, getPublishedBookingFlow, updateBookingFlowDefinition | A venue's booking flow (decided 29 September, W12: operators pick their flows, see which steps are required, set their own order).
white-label | BookingFlowConfig | 29 | none — embedded in tenant_config | 1 | 2 | getBookingFlowConfig, setBookingFlowConfig | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
white-label | BookingFlowValidation | 2 | none — computed | 0 | 1 | validateBookingFlow
white-label | BrandIdentity | 11 | none — embedded in tenant_config | 1 | 2 | getBrandIdentity, setBrandIdentity | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload), PNG or SVG and at most 2 MB (decided 28 September, audit R270).
white-label | ConfigDiff | 3 | none — computed | 0 | 1 | diffConfigVersion
white-label | ConfigValidationReport | 4 | none — computed | 0 | 1 | validateTenantConfig
white-label | ConfigVersion | 11 | whitelabel.config_version | 0 | 1 | publishTenantConfig
white-label | ContentBlock | 12 | control.content_block | 1 | 2 | createContentBlock, publishContentBlock | BL-172.
white-label | ContentPage | 11 | whitelabel.content_page | 1 | 2 | createContentPage, updateContentPage
white-label | CustomDomain | 11 | whitelabel.custom_domain | 0 | 3 | claimCustomDomain, listCustomDomains, verifyCustomDomain | 24 August.
white-label | FaqCategory | 5 | whitelabel.faq_category + whitelabel.faq_entry | 0 | 2 | listFaqs, setFaqs
white-label | FeatureToggle | 5 | whitelabel.feature_toggle | 0 | 2 | getFeatureToggles, setFeatureToggles
white-label | FontConfig | 6 | none — embedded in tenant_config | 1 | 2 | getFonts, setFonts
white-label | FooterConfig | 6 | whitelabel.footer_config + whitelabel.footer_config_column + whitelabel.footer_config_social_link | 1 | 1 | setFooter | BL-002.
white-label | GuidedChoice | 14 | whitelabel.guided_choice + whitelabel.guided_choice_question + whitelabel.guided_choice_answer | 1 | 6 | createGuidedChoice, getPublishedGuidedChoice, proposeGuidedChoice, publishGuidedChoice, unpublishGuidedChoice, updateGuidedChoice | Help me choose (decided 29 September, rev 3 REV3-11).
white-label | HeaderConfig | 5 | none — embedded in tenant_config | 1 | 1 | setHeader
white-label | HomepageLayout | 2 | whitelabel.homepage_section | 1 | 2 | getHomepageLayout, setHomepageLayout
white-label | LanguageConfig | 4 | none — embedded in tenant_config | 0 | 1 | setLanguages
white-label | ModuleEnablement | 5 | whitelabel.module_enablement | 0 | 2 | getModuleEnablement, setModuleEnablement
white-label | NavigationConfig | 4 | whitelabel.navigation_item | 1 | 2 | getNavigation, setNavigation | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
white-label | Policy | 9 | whitelabel.policy | 0 | 2 | listPolicies, setPolicy
white-label | Preview | 6 | none — short-lived, cache only | 0 | 1 | createPreview
white-label | PromoBlock | 11 | whitelabel.promo_block | 1 | 3 | createPromoBlock, listPromoBlocks, updatePromoBlock
white-label | SiteSetupProgress | 7 | whitelabel.site_setup_progress | 1 | 2 | getSiteSetupProgress, setSiteSetupProgress | The Site Builder's saved progress, one row per tenant (decided 29 September, W12 and M24-05).
white-label | StorePublishingChecklist | 2 | none — computed | 0 | 2 | getStoreAccounts, setStoreAccounts
white-label | StorefrontAnalyticsProvider | 13 | whitelabel.analytics_provider | 1 | 1 | setAnalyticsProvider | One analytics platform the storefront or app reports to (22.10.29, 29 September build).
white-label | TenantAppStatus | 19 | none — computed | 0 | 2 | getTenantAppStatus, setMaintenanceMode | Computed on read.
white-label | TenantConfig | 28 | whitelabel.tenant_config | 0 | 2 | getTenantConfig, restoreConfigVersion | The tenant's working draft, one row per tenant (see the header).
white-label | Theme | 10 | none — embedded in tenant_config | 1 | 2 | getTheme, setTheme
white-label | UpdateContentPageRequest | 8 | none — request only; the fields land on whitelabel.content_page | 1 | 0 | updateContentPage | The body of updateContentPage: the fields a tenant edits.
white-label | WhiteLabelStorefrontSessionBatch | 8 | none — request only; published as storefront.sessionEvent through platform.outbox | 1 | 0 | recordStorefrontSessionEvents | One beacon from the storefront or guest-app runtime (8.3.40; decided 29 September, build pass, group G2).
workforce | RotaAssignment | 17 | workforce.rota_assignment | 1 | 1 | createRotaAssignment

## Fields
Service | Operation | Where | Field | Type | Required | Notes
OrderService | abandonCart | param (path) | cartId | string (uuid) | yes
OrderService | abandonCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | acceptShiftVariance | request | reason | string | yes | Retained for audit. (min length 3; max length 500)
OrderService | acceptShiftVariance | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | acceptShiftVariance | response | workstationId | string (uuid) | yes
OrderService | acceptShiftVariance | response | venueId | string (uuid) | yes
OrderService | acceptShiftVariance | response | scopePath | string | yes
OrderService | acceptShiftVariance | response | principalId | string (uuid) | yes | Who opened it.
OrderService | acceptShiftVariance | response | principalDisplayName | string
OrderService | acceptShiftVariance | response | incidents | array of object |  | BL-097.
OrderService | acceptShiftVariance | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | acceptShiftVariance | response | incidents[].at | string (date-time)
OrderService | acceptShiftVariance | response | incidents[].principalId | string (uuid)
OrderService | acceptShiftVariance | response | incidents[].note | string |  | (nullable)
OrderService | acceptShiftVariance | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | acceptShiftVariance | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | acceptShiftVariance | response | depositBoxCode | string |  | (nullable)
OrderService | acceptShiftVariance | response | bagNumber | string |  | (nullable)
OrderService | acceptShiftVariance | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | acceptShiftVariance | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | acceptShiftVariance | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | acceptShiftVariance | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | acceptShiftVariance | response | openedAt | string (date-time) | yes
OrderService | acceptShiftVariance | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | acceptShiftVariance | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | acceptShiftVariance | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | acceptShiftVariance | response | closedAt | string (date-time) |  | (nullable)
OrderService | acceptShiftVariance | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | acceptShiftVariance | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | acceptShiftVariance | response | approvals | array of object
OrderService | acceptShiftVariance | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | acceptShiftVariance | response | approvals[].principalId | string (uuid) | yes
OrderService | acceptShiftVariance | response | approvals[].at | string (date-time) | yes
OrderService | acceptShiftVariance | response | approvals[].reason | string
OrderService | acceptShiftVariance | param (path) | shiftId | string (uuid) | yes
OrderService | acceptShiftVariance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | acquireInventoryHold | request | holderKind | InventoryHoldHolderKind: enum (workstation, cart) |  | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | acquireInventoryHold | request | cartId | string (uuid) |  | Required when holderKind is cart, else 400. (nullable)
CatalogueService | acquireInventoryHold | request | channel | object |  | Which channel's allocation to draw from.
CatalogueService | acquireInventoryHold | request | id | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | acquireInventoryHold | request | channelCapacityId | string (uuid) | yes
CatalogueService | acquireInventoryHold | request | requestedUnits | integer | yes | (min 1)
CatalogueService | acquireInventoryHold | request | ttlSeconds | integer | yes | Short TTLs limit stranding when a terminal dies; long TTLs survive longer outages. (min 30; max 3600; default 900)
CatalogueService | acquireInventoryHold | response | id | string | yes
CatalogueService | acquireInventoryHold | response | channelCapacityId | string (uuid) | yes
CatalogueService | acquireInventoryHold | response | holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | acquireInventoryHold | response | holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | acquireInventoryHold | response | holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | acquireInventoryHold | response | convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | acquireInventoryHold | response | convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | acquireInventoryHold | response | parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | acquireInventoryHold | response | requestedUnits | integer
CatalogueService | acquireInventoryHold | response | channel | object |  | Allocation this lease draws from.
CatalogueService | acquireInventoryHold | response | grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | acquireInventoryHold | response | consumedUnits | integer | yes
CatalogueService | acquireInventoryHold | response | status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | acquireInventoryHold | response | acquiredAt | string (date-time) | yes
CatalogueService | acquireInventoryHold | response | expiresAt | string (date-time) | yes
CatalogueService | acquireInventoryHold | response | releasedAt | string (date-time) |  | (nullable)
CatalogueService | acquireInventoryHold | response | forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | acquireInventoryHold | response | forceReleaseReason | string |  | (nullable)
CatalogueService | acquireInventoryHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | addBlacklistEntry | request | mediaCode | string | yes | (max length 256)
AccessService | addBlacklistEntry | request | reason | string | yes | (min length 3; max length 500)
AccessService | addBlacklistEntry | request | expiresAt | string (date-time)
AccessService | addBlacklistEntry | response | mediaCode | string | yes | Unique within the tenant (decided 28 September, audit R108): one entry per code.
AccessService | addBlacklistEntry | response | reason | string | yes
AccessService | addBlacklistEntry | response | addedAt | string (date-time) | yes
AccessService | addBlacklistEntry | response | addedByPrincipalId | string (uuid) | yes
AccessService | addBlacklistEntry | response | expiresAt | string (date-time) |  | (nullable)
AccessService | addBlacklistEntry | response | listType | enum (blacklist, whitelist) |  | A blacklist entry refuses the media; a whitelist entry is an approved exception to a restriction (added 29 September, data-model close-out DM1). (default blacklist)
AccessService | addBlacklistEntry | response | disableScope | enum (entireCredential, venueAccess, attractionAccess, reEntry, fastPass, specificEntitlement) |  | What the entry disables (added 29 September, data-model close-out DM1). (default entireCredential)
AccessService | addBlacklistEntry | response | distributedTo | array of enum (centralPlatform, venueEdge, onlineGates, offlineRevocationPackage) |  | Where the restriction has been distributed so far, as listCredentialDisableBlacklist returns it (added 29 September, data-model close-out DM1).
AccessService | addBlacklistEntry | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | addBlacklistEntry | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addCartLine | request | variantId | string (uuid) | yes
OrderService | addCartLine | request | quantity | integer | yes | (min 1)
OrderService | addCartLine | request | performanceId | string (uuid)
OrderService | addCartLine | request | bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | addCartLine | request | bookedWindow.startsAt | string (date-time) | yes
OrderService | addCartLine | request | bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | addCartLine | request | recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | addCartLine | request | tableReservationId | string (uuid) |  | A table deposit line (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation in awaitingDeposit this pays for, sent with variantId set to the booking's deposit.variantId and quantity 1. (nullable)
OrderService | addCartLine | request | seatIds | array of string (uuid) |  | At most VenueSettings.seating.maxSeatsPerGuestOrder seats per booking on a guest channel (default 10, bounds 1 to 50, decided 29 September, rev 3 REV3-7); at most 10 per sale on staff and POS (audit… (max items 50)
OrderService | addCartLine | request | resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant and quantity is 1. (nullable)
OrderService | addCartLine | request | parentLineId | string (uuid) |  | For an add-on attaching to a ticket already in the cart. (nullable)
OrderService | addCartLine | request | attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | addCartLine | request | attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | addCartLine | request | attributes.transport.routeId | string (uuid) | yes | The transport.TransportRoute.
OrderService | addCartLine | request | attributes.transport.fromStationId | string (uuid) | yes | Boarding station, a stop of the route.
OrderService | addCartLine | request | attributes.transport.toStationId | string (uuid) | yes | Alighting station, a later stop of the route.
OrderService | addCartLine | request | attributes.transport.passengerTypeCode | string |  | The fare table's passenger type (adult, child, ...). (pattern ^[a-z][a-zA-Z0-9]{0,31}$; nullable)
OrderService | addCartLine | request | attributes.transport.passTypeId | string (uuid) |  | Pass purchase only. (nullable)
OrderService | addCartLine | request | attributes.transport.passEntitlementId | string (uuid) |  | A seat reserved with a pass already owned. (nullable)
OrderService | addCartLine | response | id | string (uuid) | yes
OrderService | addCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | addCartLine | response | venueId | string (uuid) | yes
OrderService | addCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | addCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | addCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | addCartLine | response | lines | array of CartLine | yes
OrderService | addCartLine | response | lines[].id | string (uuid) | yes
OrderService | addCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | addCartLine | response | lines[].productName | string |  | (read-only)
OrderService | addCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | addCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | addCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | addCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | addCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | addCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | addCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | addCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | addCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | addCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | addCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | addCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | addCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | addCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | addCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | addCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | addCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | addCartLine | response | conflicts | array of CartConflict
OrderService | addCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | addCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | addCartLine | response | conflicts[].message | string
OrderService | addCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | addCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | addCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | addCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | addCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | addCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | addCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | addCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | addCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | addCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | addCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | addCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | addCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | addCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | addCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | addCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | addCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | addCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | addCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | addCartLine | response | maxExtensions | integer |  | (read-only)
OrderService | addCartLine | response | locale | string
OrderService | addCartLine | response | createdAt | string (date-time)
OrderService | addCartLine | response | updatedAt | string (date-time)
OrderService | addCartLine | param (path) | cartId | string (uuid) | yes
OrderService | addCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | addLicenceAddOn | request | tenantId | string (uuid) |  | The tenant the add-on was sold to — the tenantId in the path, never the body. (read-only)
PlatformService | addLicenceAddOn | request | moduleKey | string | yes
PlatformService | addLicenceAddOn | request | limitOverrides | array of EntitlementLimit
PlatformService | addLicenceAddOn | request | limitOverrides[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | addLicenceAddOn | request | limitOverrides[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageAllowed | boolean |  | (default False)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | request | price | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | request | validFrom | string (date)
PlatformService | addLicenceAddOn | request | validTo | string (date) |  | (nullable)
PlatformService | addLicenceAddOn | request | note | string |  | (max length 500)
PlatformService | addLicenceAddOn | response | tenantId | string (uuid) | yes
PlatformService | addLicenceAddOn | response | planId | string (uuid) |  | (nullable)
PlatformService | addLicenceAddOn | response | licensedModules | array of object | yes | Union of plan modules and add-ons.
PlatformService | addLicenceAddOn | response | licensedModules[].moduleKey | string | yes
PlatformService | addLicenceAddOn | response | licensedModules[].displayName | string
PlatformService | addLicenceAddOn | response | licensedModules[].source | enum (plan, addOn) | yes
PlatformService | addLicenceAddOn | response | licensedModules[].validTo | string (date) |  | (nullable)
PlatformService | addLicenceAddOn | response | limits | array of EntitlementLimit | yes
PlatformService | addLicenceAddOn | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | addLicenceAddOn | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | addLicenceAddOn | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | param (path) | tenantId | string (uuid) | yes
PlatformService | addLicenceAddOn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addTip | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | addTip | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | request | source | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) | yes | serviceCharge is not a tip and is separated deliberately — it is revenue in most jurisdictions, and pooling it with tips is how a payroll dispute starts.
OrderService | addTip | request | allocateToPrincipalId | string (uuid) |  | Where the venue allocates rather than pools.
OrderService | addTip | request | recordedAt | string (date-time) | yes
OrderService | addTip | response | id | string (uuid) | yes
OrderService | addTip | response | orderId | string (uuid) | yes
OrderService | addTip | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | addTip | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | addTip | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | addTip | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | addTip | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | addTip | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | addTip | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addTip | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | addTip | response | providerName | string |  | (nullable)
OrderService | addTip | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | addTip | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | addTip | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | addTip | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | addTip | response | nextAction.kind | enum (redirect, terminal)
OrderService | addTip | response | nextAction.url | string (uri) |  | (nullable)
OrderService | addTip | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | addTip | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | addTip | response | recordedAt | string (date-time) | yes
OrderService | addTip | response | syncedAt | string (date-time) |  | (nullable)
OrderService | addTip | param (path) | paymentId | string (uuid) | yes
OrderService | addTip | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | addToWishlist | request | variantId | string (uuid) | yes
MarketingService | addToWishlist | request | performanceId | string (uuid) |  | Saving a specific date rather than the product generally. (nullable)
MarketingService | addToWishlist | request | note | string |  | (max length 200)
MarketingService | addToWishlist | response | subjectId | string (uuid) | yes
MarketingService | addToWishlist | response | items | array of object | yes
MarketingService | addToWishlist | response | items[].id | string (uuid) | yes
MarketingService | addToWishlist | response | items[].variantId | string (uuid) | yes
MarketingService | addToWishlist | response | items[].productName | string
MarketingService | addToWishlist | response | items[].performanceId | string (uuid) |  | (nullable)
MarketingService | addToWishlist | response | items[].performanceStartsAt | string (date-time) |  | (nullable)
MarketingService | addToWishlist | response | items[].price | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | addToWishlist | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | addToWishlist | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | addToWishlist | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | addToWishlist | response | items[].imageAssetRef | string |  | (nullable)
MarketingService | addToWishlist | response | items[].isAvailable | boolean | yes | False where the product has been withdrawn or the performance has passed.
MarketingService | addToWishlist | response | items[].unavailableReason | string |  | (nullable)
MarketingService | addToWishlist | response | items[].note | string |  | (nullable)
MarketingService | addToWishlist | response | items[].addedAt | string (date-time) | yes
MarketingService | addToWishlist | param (path) | subjectId | string (uuid) | yes
MarketingService | addToWishlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | adjustDepositBoxFloat | request | amount | object | yes | The change to the float, signed.
OrderService | adjustDepositBoxFloat | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | request | reason | string | yes | (max length 300)
OrderService | adjustDepositBoxFloat | response | id | string (uuid) |  | (read-only)
OrderService | adjustDepositBoxFloat | response | cashierPrincipalId | string (uuid) | yes
OrderService | adjustDepositBoxFloat | response | cashierName | string |  | (read-only)
OrderService | adjustDepositBoxFloat | response | venueId | string (uuid) | yes
OrderService | adjustDepositBoxFloat | response | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | adjustDepositBoxFloat | response | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | adjustDepositBoxFloat | response | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | adjustDepositBoxFloat | response | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | adjustDepositBoxFloat | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | openingDenominations | array of object |  | 5.8.3.
OrderService | adjustDepositBoxFloat | response | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | adjustDepositBoxFloat | response | openingDenominations[].count | integer | yes | (min 0)
OrderService | adjustDepositBoxFloat | response | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | adjustDepositBoxFloat | response | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | adjustDepositBoxFloat | response | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | adjustDepositBoxFloat | response | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | adjustDepositBoxFloat | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | adjustDepositBoxFloat | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | adjustDepositBoxFloat | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | adjustDepositBoxFloat | response | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | adjustDepositBoxFloat | response | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | adjustDepositBoxFloat | response | closedAt | string (date-time) |  | (nullable)
OrderService | adjustDepositBoxFloat | param (path) | boxId | string (uuid) | yes
OrderService | adjustDepositBoxFloat | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | allocateDepositBox | request | id | string (uuid) |  | (read-only)
OrderService | allocateDepositBox | request | cashierPrincipalId | string (uuid) | yes
OrderService | allocateDepositBox | request | cashierName | string |  | (read-only)
OrderService | allocateDepositBox | request | venueId | string (uuid) | yes
OrderService | allocateDepositBox | request | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | allocateDepositBox | request | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | allocateDepositBox | request | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | allocateDepositBox | request | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | openingDenominations | array of object |  | 5.8.3.
OrderService | allocateDepositBox | request | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | allocateDepositBox | request | openingDenominations[].count | integer | yes | (min 0)
OrderService | allocateDepositBox | request | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | allocateDepositBox | request | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | allocateDepositBox | request | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | allocateDepositBox | request | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | allocateDepositBox | request | closedAt | string (date-time) |  | (nullable)
OrderService | allocateDepositBox | response | id | string (uuid) |  | (read-only)
OrderService | allocateDepositBox | response | cashierPrincipalId | string (uuid) | yes
OrderService | allocateDepositBox | response | cashierName | string |  | (read-only)
OrderService | allocateDepositBox | response | venueId | string (uuid) | yes
OrderService | allocateDepositBox | response | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | allocateDepositBox | response | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | allocateDepositBox | response | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | allocateDepositBox | response | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | openingDenominations | array of object |  | 5.8.3.
OrderService | allocateDepositBox | response | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | allocateDepositBox | response | openingDenominations[].count | integer | yes | (min 0)
OrderService | allocateDepositBox | response | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | allocateDepositBox | response | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | allocateDepositBox | response | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | allocateDepositBox | response | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | allocateDepositBox | response | closedAt | string (date-time) |  | (nullable)
OrderService | allocateDepositBox | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | analysePromotionConflicts | response | promotionId | string (uuid) | yes
CatalogueService | analysePromotionConflicts | response | conflicts | array of object | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].otherPromotionId | string (uuid) | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].otherPromotionCode | string | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].overlap | enum (products, period, channel, full) | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].combinedDiscount | number | yes | Combined percentage where both apply to the same line.
CatalogueService | analysePromotionConflicts | response | conflicts[].isBlocking | boolean |  | True where the combination would produce a line price of zero or below (decided 28 September, audit R101).
CatalogueService | analysePromotionConflicts | response | conflicts[].isNearZero | boolean |  | True where the combination leaves a net line price above zero but below the venue setting promotions.nearZeroLinePrice (proposed AED 1.00; decided 28 September, audit R096 (5)).
CatalogueService | analysePromotionConflicts | response | worstCaseDiscount | number | yes | Largest combined discount any single line could receive.
CatalogueService | analysePromotionConflicts | param (path) | promotionId | string (uuid) | yes
OrderService | appendEntitlementToMedia | request | id | string (uuid) | yes | Client-generated UUIDv7 of the new order this creates, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | appendEntitlementToMedia | request | lines | array of object | yes | (min items 1)
OrderService | appendEntitlementToMedia | request | lines[].variantId | string (uuid) | yes
OrderService | appendEntitlementToMedia | request | lines[].quantity | integer | yes | (min 1)
OrderService | appendEntitlementToMedia | request | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | request | paymentMethod | enum (card, cash, wallet, giftCard, chargeToAccount)
OrderService | appendEntitlementToMedia | request | note | string |  | (max length 300)
OrderService | appendEntitlementToMedia | request | recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order | object | yes | A new order.
OrderService | appendEntitlementToMedia | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | appendEntitlementToMedia | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | appendEntitlementToMedia | response | order.channel | object | yes | Where it came from.
OrderService | appendEntitlementToMedia | response | order.venueId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.scopePath | string | yes
OrderService | appendEntitlementToMedia | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | appendEntitlementToMedia | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].name | string
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.lines | array of OrderLine | yes
OrderService | appendEntitlementToMedia | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | appendEntitlementToMedia | response | order.lines[].variantId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].performanceId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | appendEntitlementToMedia | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | appendEntitlementToMedia | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | appendEntitlementToMedia | response | order.lines[].holderName | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | appendEntitlementToMedia | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | appendEntitlementToMedia | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | appendEntitlementToMedia | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | appendEntitlementToMedia | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | appendEntitlementToMedia | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | appendEntitlementToMedia | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | appendEntitlementToMedia | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | appendEntitlementToMedia | response | order.payments | array of Payment
OrderService | appendEntitlementToMedia | response | order.payments[].id | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].orderId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | appendEntitlementToMedia | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | appendEntitlementToMedia | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].providerName | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.principalId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.workstationId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.createdAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media | object | yes | The full set now on the media, so the cashier can say what the QR does.
OrderService | appendEntitlementToMedia | response | media.mediaCode | string | yes
OrderService | appendEntitlementToMedia | response | media.mediaKind | enum (qr, wristband, card, nfc, mobilePass)
OrderService | appendEntitlementToMedia | response | media.subjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.isValid | boolean | yes
OrderService | appendEntitlementToMedia | response | media.invalidReason | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.canAcceptMore | boolean |  | False where the media has been surrendered, expired or blocked.
OrderService | appendEntitlementToMedia | response | media.entitlements | array of object | yes
OrderService | appendEntitlementToMedia | response | media.entitlements[].entitlementId | string (uuid)
OrderService | appendEntitlementToMedia | response | media.entitlements[].name | string
OrderService | appendEntitlementToMedia | response | media.entitlements[].kind | enum (admission, locker, fnb, retail, parking, rental, experience, membership)
OrderService | appendEntitlementToMedia | response | media.entitlements[].orderId | string (uuid)
OrderService | appendEntitlementToMedia | response | media.entitlements[].addedAt | string (date-time)
OrderService | appendEntitlementToMedia | response | media.entitlements[].status | object |  | Replaced isRedeemed on 17 August.
OrderService | appendEntitlementToMedia | response | media.entitlements[].entriesUsed | integer
OrderService | appendEntitlementToMedia | response | media.entitlements[].entriesAllowed | integer |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].redeemedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].transferredToSubjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].validTo | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | addedEntitlementIds | array of string (uuid)
OrderService | appendEntitlementToMedia | param (path) | mediaCode | string | yes | The QR, wristband or card the guest is already carrying.
OrderService | appendEntitlementToMedia | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | applyCartPromoCode | request | code | string | yes | The code as the guest typed it. (min length 1; max length 100)
OrderService | applyCartPromoCode | response | id | string (uuid) | yes
OrderService | applyCartPromoCode | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | applyCartPromoCode | response | venueId | string (uuid) | yes
OrderService | applyCartPromoCode | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | applyCartPromoCode | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | applyCartPromoCode | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | applyCartPromoCode | response | lines | array of CartLine | yes
OrderService | applyCartPromoCode | response | lines[].id | string (uuid) | yes
OrderService | applyCartPromoCode | response | lines[].variantId | string (uuid) | yes
OrderService | applyCartPromoCode | response | lines[].productName | string |  | (read-only)
OrderService | applyCartPromoCode | response | lines[].quantity | integer | yes | (min 1)
OrderService | applyCartPromoCode | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | applyCartPromoCode | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | applyCartPromoCode | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | applyCartPromoCode | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | applyCartPromoCode | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | applyCartPromoCode | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | applyCartPromoCode | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | applyCartPromoCode | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | applyCartPromoCode | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | applyCartPromoCode | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | applyCartPromoCode | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | applyCartPromoCode | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | applyCartPromoCode | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | applyCartPromoCode | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | applyCartPromoCode | response | conflicts | array of CartConflict
OrderService | applyCartPromoCode | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | applyCartPromoCode | response | conflicts[].lineIds | array of string (uuid)
OrderService | applyCartPromoCode | response | conflicts[].message | string
OrderService | applyCartPromoCode | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | applyCartPromoCode | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | applyCartPromoCode | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | applyCartPromoCode | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | applyCartPromoCode | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | applyCartPromoCode | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | applyCartPromoCode | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | applyCartPromoCode | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | applyCartPromoCode | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | applyCartPromoCode | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | applyCartPromoCode | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | applyCartPromoCode | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | applyCartPromoCode | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | applyCartPromoCode | response | extensionsUsed | integer |  | (read-only)
OrderService | applyCartPromoCode | response | maxExtensions | integer |  | (read-only)
OrderService | applyCartPromoCode | response | locale | string
OrderService | applyCartPromoCode | response | createdAt | string (date-time)
OrderService | applyCartPromoCode | response | updatedAt | string (date-time)
OrderService | applyCartPromoCode | param (path) | cartId | string (uuid) | yes
OrderService | applyCartPromoCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | applyManualDiscount | request | id | string (uuid) | yes | Client-generated UUIDv7 of this discount, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | applyManualDiscount | request | lineId | string (uuid) |  | Omit to discount the order rather than a line. (nullable)
OrderService | applyManualDiscount | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | request | percentage | number |  | (min 0; max 100)
OrderService | applyManualDiscount | request | reason | string | yes | Required, and free text rather than a code list. (min length 3; max length 300)
OrderService | applyManualDiscount | request | reasonCode | string |  | Optional alongside the free text, where the venue maintains a list. (nullable)
OrderService | applyManualDiscount | request | approverPrincipalId | string (uuid) |  | Required above the venue threshold. (nullable)
OrderService | applyManualDiscount | request | recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | applyManualDiscount | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | applyManualDiscount | response | channel | object | yes | Where it came from.
OrderService | applyManualDiscount | response | venueId | string (uuid) | yes
OrderService | applyManualDiscount | response | scopePath | string | yes
OrderService | applyManualDiscount | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | applyManualDiscount | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | applyManualDiscount | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | applyManualDiscount | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | applyManualDiscount | response | droppedPromotions[].name | string
OrderService | applyManualDiscount | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | applyManualDiscount | response | totalPriceVariance | object |  | Sum across lines.
OrderService | applyManualDiscount | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines | array of OrderLine | yes
OrderService | applyManualDiscount | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | applyManualDiscount | response | lines[].variantId | string (uuid) | yes
OrderService | applyManualDiscount | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | applyManualDiscount | response | lines[].performanceId | string (uuid)
OrderService | applyManualDiscount | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | applyManualDiscount | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | applyManualDiscount | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | applyManualDiscount | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | applyManualDiscount | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | applyManualDiscount | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | applyManualDiscount | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | applyManualDiscount | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | applyManualDiscount | response | lines[].quantity | integer | yes | (min 1)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].holderName | string |  | (nullable)
OrderService | applyManualDiscount | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | applyManualDiscount | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | applyManualDiscount | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | applyManualDiscount | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | applyManualDiscount | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | applyManualDiscount | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | applyManualDiscount | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | applyManualDiscount | response | lines[].discounts[].id | string (uuid) | yes
OrderService | applyManualDiscount | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | applyManualDiscount | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | applyManualDiscount | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | applyManualDiscount | response | payments | array of Payment
OrderService | applyManualDiscount | response | payments[].id | string (uuid) | yes
OrderService | applyManualDiscount | response | payments[].orderId | string (uuid) | yes
OrderService | applyManualDiscount | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | applyManualDiscount | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | applyManualDiscount | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | applyManualDiscount | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | applyManualDiscount | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | applyManualDiscount | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | applyManualDiscount | response | payments[].providerName | string |  | (nullable)
OrderService | applyManualDiscount | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | applyManualDiscount | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | applyManualDiscount | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | principalId | string (uuid)
OrderService | applyManualDiscount | response | workstationId | string (uuid)
OrderService | applyManualDiscount | response | shiftId | string (uuid) |  | (nullable)
OrderService | applyManualDiscount | response | subjectId | string (uuid) |  | (nullable)
OrderService | applyManualDiscount | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | applyManualDiscount | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | applyManualDiscount | response | createdAt | string (date-time) | yes
OrderService | applyManualDiscount | response | recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | syncedAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | param (path) | orderId | string (uuid) | yes
OrderService | applyManualDiscount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | applyTransportNetworkImport | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | applyTransportNetworkImport | response | venueId | string (uuid) | yes | (read-only)
VenueOpsService | applyTransportNetworkImport | response | format | enum (csvBundle, gtfs) | yes
VenueOpsService | applyTransportNetworkImport | response | sourceRef | string (uuid) | yes
VenueOpsService | applyTransportNetworkImport | response | status | TransportNetworkImportStatus: enum (validating, previewReady, failed, applied, expired) | yes | validating → previewReady or failed; previewReady → applied, or expired after 7 days unapplied (proposed, client to correct).
VenueOpsService | applyTransportNetworkImport | response | preview | object |  | What applying would write. (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | response | preview.stationsToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.stationsToUpdate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.routesToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.routesToUpdate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.stopsToWrite | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.timetablesToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | findings | array of TransportNetworkImportFinding |  | (max items 1000; read-only)
VenueOpsService | applyTransportNetworkImport | response | findings[].code | enum (nothingFound, fileMissing, headerMismatch, stationCodeDuplicate, stationCoordinatesMissing, routeCodeDuplicate, routeStopUnknownStation, routeOffsetsNotIncreasing, …) | yes | stationCoordinatesMissing is a warning (the station is listed and left off the map); routeActiveStopsChanged is a warning (those stops are skipped); every other code is an error and blocks the apply.
VenueOpsService | applyTransportNetworkImport | response | findings[].severity | enum (error, warning) | yes
VenueOpsService | applyTransportNetworkImport | response | findings[].file | string |  | e.g. (nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].row | integer |  | (min 1; nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].reference | string |  | The station (nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].message | string | yes | (max length 500)
VenueOpsService | applyTransportNetworkImport | response | createdBy | string (uuid) |  | (read-only)
VenueOpsService | applyTransportNetworkImport | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | applyTransportNetworkImport | response | appliedBy | string (uuid) |  | (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | response | appliedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | param (path) | importId | string (uuid) | yes
VenueOpsService | applyTransportNetworkImport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | approveManualOverrideSupervisor | request | supervisorId | string | yes | Approving supervisor
AccessService | approveManualOverrideSupervisor | request | scanId | string | yes | The denied scan being overridden
AccessService | approveManualOverrideSupervisor | request | selectType | enum (guestService, ticketingError, operationalException, managementAuthorization, technicalFailure, eventException, other) | yes | Override reason category
AccessService | approveManualOverrideSupervisor | request | reasonNote | string |  | Free-text justification
AccessService | approveManualOverrideSupervisor | request | accessPointId | string |  | Gate
AccessService | approveManualOverrideSupervisor | request | deviceId | string |  | Device
AccessService | approveManualOverrideSupervisor | request | originalDecision | string |  | Original validation decision, read only and never rewritten
AccessService | approveManualOverrideSupervisor | response | supervisorId | string | yes | Approving supervisor
AccessService | approveManualOverrideSupervisor | response | scanId | string | yes | The denied scan being overridden
AccessService | approveManualOverrideSupervisor | response | selectType | enum (guestService, ticketingError, operationalException, managementAuthorization, technicalFailure, eventException, other) | yes | Override reason category
AccessService | approveManualOverrideSupervisor | response | reasonNote | string |  | Free-text justification
AccessService | approveManualOverrideSupervisor | response | accessPointId | string |  | Gate
AccessService | approveManualOverrideSupervisor | response | deviceId | string |  | Device
AccessService | approveManualOverrideSupervisor | response | originalDecision | string |  | Original validation decision, read only and never rewritten
AccessService | approveManualOverrideSupervisor | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | approveMatrixMultiLevel | request | code | string | yes | Stable rule code the PUT upserts by
TenancyService | approveMatrixMultiLevel | request | approvalMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) | yes | How approvers at this rule combine
TenancyService | approveMatrixMultiLevel | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveMatrixMultiLevel | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveMatrixMultiLevel | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveMatrixMultiLevel | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveMatrixMultiLevel | request | percentage | number |  | Percentage
TenancyService | approveMatrixMultiLevel | request | module | string |  | Module
TenancyService | approveMatrixMultiLevel | request | product | string |  | Product
TenancyService | approveMatrixMultiLevel | request | venue | string |  | Venue
TenancyService | approveMatrixMultiLevel | request | department | string |  | Department
TenancyService | approveMatrixMultiLevel | request | customerType | string |  | Customer Type
TenancyService | approveMatrixMultiLevel | request | risk | string |  | Risk
TenancyService | approveMatrixMultiLevel | request | exceptionType | string |  | Exception Type
TenancyService | approveMatrixMultiLevel | request | legalEntity | string |  | Legal Entity
TenancyService | approveMatrixMultiLevel | request | minimumApprovals | integer |  | N in N-of-M: approvals needed from the approver group
TenancyService | approveMatrixMultiLevel | request | rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this level does
TenancyService | approveMatrixMultiLevel | request | requestChanges | boolean |  | Approvers may return the request for changes
TenancyService | approveMatrixMultiLevel | request | delegate | boolean |  | Approvers may delegate
TenancyService | approveMatrixMultiLevel | request | reassign | boolean |  | The request may be reassigned
TenancyService | approveMatrixMultiLevel | request | skipConditions | string |  | Skip Conditions
TenancyService | approveMatrixMultiLevel | request | requiredApproverRole | string |  | Role that must always approve, e.g.
TenancyService | approveMatrixMultiLevel | response | code | string | yes | Stable rule code the PUT upserts by
TenancyService | approveMatrixMultiLevel | response | approvalMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) | yes | How approvers at this rule combine
TenancyService | approveMatrixMultiLevel | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveMatrixMultiLevel | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveMatrixMultiLevel | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveMatrixMultiLevel | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveMatrixMultiLevel | response | percentage | number |  | Percentage
TenancyService | approveMatrixMultiLevel | response | module | string |  | Module
TenancyService | approveMatrixMultiLevel | response | product | string |  | Product
TenancyService | approveMatrixMultiLevel | response | venue | string |  | Venue
TenancyService | approveMatrixMultiLevel | response | department | string |  | Department
TenancyService | approveMatrixMultiLevel | response | customerType | string |  | Customer Type
TenancyService | approveMatrixMultiLevel | response | risk | string |  | Risk
TenancyService | approveMatrixMultiLevel | response | exceptionType | string |  | Exception Type
TenancyService | approveMatrixMultiLevel | response | legalEntity | string |  | Legal Entity
TenancyService | approveMatrixMultiLevel | response | minimumApprovals | integer |  | N in N-of-M: approvals needed from the approver group
TenancyService | approveMatrixMultiLevel | response | rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this level does
TenancyService | approveMatrixMultiLevel | response | requestChanges | boolean |  | Approvers may return the request for changes
TenancyService | approveMatrixMultiLevel | response | delegate | boolean |  | Approvers may delegate
TenancyService | approveMatrixMultiLevel | response | reassign | boolean |  | The request may be reassigned
TenancyService | approveMatrixMultiLevel | response | skipConditions | string |  | Skip Conditions
TenancyService | approveMatrixMultiLevel | response | requiredApproverRole | string |  | Role that must always approve, e.g.
TenancyService | approveMatrixMultiLevel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | approveRoleAuthorityDelegation | request | user | string |  | User
TenancyService | approveRoleAuthorityDelegation | request | role | string |  | Role
TenancyService | approveRoleAuthorityDelegation | request | position | string |  | Position
TenancyService | approveRoleAuthorityDelegation | request | department | string |  | Department
TenancyService | approveRoleAuthorityDelegation | request | venue | string |  | Venue
TenancyService | approveRoleAuthorityDelegation | request | businessUnit | string |  | Business Unit
TenancyService | approveRoleAuthorityDelegation | request | legalEntity | string |  | Legal Entity
TenancyService | approveRoleAuthorityDelegation | request | region | string |  | Region
TenancyService | approveRoleAuthorityDelegation | request | delegator | string | yes | Delegator
TenancyService | approveRoleAuthorityDelegation | request | delegate | string | yes | Delegate
TenancyService | approveRoleAuthorityDelegation | request | scope | string |  | Scope
TenancyService | approveRoleAuthorityDelegation | request | start | string (date-time) | yes | Delegation start
TenancyService | approveRoleAuthorityDelegation | request | end | string (date-time) | yes | Delegation end
TenancyService | approveRoleAuthorityDelegation | request | reason | string |  | Reason
TenancyService | approveRoleAuthorityDelegation | request | delegationType | enum (leave, travel, vacancy, eventOperations) |  | Why temporary authority is granted
TenancyService | approveRoleAuthorityDelegation | request | requiredRole | string |  | Required role
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveRoleAuthorityDelegation | request | requestKind | string |  | What the authority limit covers, e.g.
TenancyService | approveRoleAuthorityDelegation | request | authorityPercentage | number |  | Percentage limit where the authority is a percentage, e.g.
TenancyService | approveRoleAuthorityDelegation | response | user | string |  | User
TenancyService | approveRoleAuthorityDelegation | response | role | string |  | Role
TenancyService | approveRoleAuthorityDelegation | response | position | string |  | Position
TenancyService | approveRoleAuthorityDelegation | response | department | string |  | Department
TenancyService | approveRoleAuthorityDelegation | response | venue | string |  | Venue
TenancyService | approveRoleAuthorityDelegation | response | businessUnit | string |  | Business Unit
TenancyService | approveRoleAuthorityDelegation | response | legalEntity | string |  | Legal Entity
TenancyService | approveRoleAuthorityDelegation | response | region | string |  | Region
TenancyService | approveRoleAuthorityDelegation | response | delegator | string | yes | Delegator
TenancyService | approveRoleAuthorityDelegation | response | delegate | string | yes | Delegate
TenancyService | approveRoleAuthorityDelegation | response | scope | string |  | Scope
TenancyService | approveRoleAuthorityDelegation | response | start | string (date-time) | yes | Delegation start
TenancyService | approveRoleAuthorityDelegation | response | end | string (date-time) | yes | Delegation end
TenancyService | approveRoleAuthorityDelegation | response | reason | string |  | Reason
TenancyService | approveRoleAuthorityDelegation | response | delegationType | enum (leave, travel, vacancy, eventOperations) |  | Why temporary authority is granted
TenancyService | approveRoleAuthorityDelegation | response | requiredRole | string |  | Required role
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveRoleAuthorityDelegation | response | requestKind | string |  | What the authority limit covers, e.g.
TenancyService | approveRoleAuthorityDelegation | response | authorityPercentage | number |  | Percentage limit where the authority is a percentage, e.g.
TenancyService | approveRoleAuthorityDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | approveShiftOpen | request | reason | string | yes | (min length 3; max length 300)
OrderService | approveShiftOpen | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | approveShiftOpen | response | workstationId | string (uuid) | yes
OrderService | approveShiftOpen | response | venueId | string (uuid) | yes
OrderService | approveShiftOpen | response | scopePath | string | yes
OrderService | approveShiftOpen | response | principalId | string (uuid) | yes | Who opened it.
OrderService | approveShiftOpen | response | principalDisplayName | string
OrderService | approveShiftOpen | response | incidents | array of object |  | BL-097.
OrderService | approveShiftOpen | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | approveShiftOpen | response | incidents[].at | string (date-time)
OrderService | approveShiftOpen | response | incidents[].principalId | string (uuid)
OrderService | approveShiftOpen | response | incidents[].note | string |  | (nullable)
OrderService | approveShiftOpen | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | approveShiftOpen | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | approveShiftOpen | response | depositBoxCode | string |  | (nullable)
OrderService | approveShiftOpen | response | bagNumber | string |  | (nullable)
OrderService | approveShiftOpen | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | approveShiftOpen | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | approveShiftOpen | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | approveShiftOpen | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | approveShiftOpen | response | openedAt | string (date-time) | yes
OrderService | approveShiftOpen | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | approveShiftOpen | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | approveShiftOpen | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | approveShiftOpen | response | closedAt | string (date-time) |  | (nullable)
OrderService | approveShiftOpen | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | approveShiftOpen | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | approveShiftOpen | response | approvals | array of object
OrderService | approveShiftOpen | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | approveShiftOpen | response | approvals[].principalId | string (uuid) | yes
OrderService | approveShiftOpen | response | approvals[].at | string (date-time) | yes
OrderService | approveShiftOpen | response | approvals[].reason | string
OrderService | approveShiftOpen | param (path) | shiftId | string (uuid) | yes
OrderService | approveShiftOpen | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | askReportingQuestion | request | question | string | yes | (min length 3; max length 1000)
ReportingService | askReportingQuestion | request | conversationId | string |  | Continue a prior exchange for follow-up questions.
ReportingService | askReportingQuestion | request | venueId | string (uuid) |  | Narrows the answer to one venue.
ReportingService | askReportingQuestion | response | conversationId | string | yes
ReportingService | askReportingQuestion | response | question | string | yes
ReportingService | askReportingQuestion | response | interpretation | string | yes | What the question was understood to mean, in plain language.
ReportingService | askReportingQuestion | response | semanticSpec | object |  | What the model returned instead of SQL (design 2.2 E, 5.7): metric, dimensions, filters, period, comparison, as validated against the semantic model. (nullable)
ReportingService | askReportingQuestion | response | semanticSpec.metric | string | yes | A measure field code in the SemanticModel, or a KpiDefinition.code.
ReportingService | askReportingQuestion | response | semanticSpec.dimensions | array of string |  | Field codes to group by. (max items 5)
ReportingService | askReportingQuestion | response | semanticSpec.filters | array of object
ReportingService | askReportingQuestion | response | semanticSpec.filters[].field | string | yes | A SemanticModel field code.
ReportingService | askReportingQuestion | response | semanticSpec.filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, isNull, …) | yes
ReportingService | askReportingQuestion | response | semanticSpec.filters[].values | array of object |  | Open on purpose; typed by the field.
ReportingService | askReportingQuestion | response | semanticSpec.period | string | yes | ISO 8601 interval in the venue's time zone, e.g.
ReportingService | askReportingQuestion | response | semanticSpec.comparison | enum (previousPeriod, samePeriodLastYear, target, benchmark) |  | As getKpiValues compareTo. (nullable)
ReportingService | askReportingQuestion | response | semanticSpec.semanticModelVersion | integer |  | The SemanticModel.version the spec was validated and compiled against. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery | object |  | The query the spec compiled to: data source, columns, filters, grouping, and the compiled SQL in compiledSql. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) |  | What a report may be built over.
ReportingService | askReportingQuestion | response | generatedQuery.columns | array of ReportColumn
ReportingService | askReportingQuestion | response | generatedQuery.columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].field | string | yes
ReportingService | askReportingQuestion | response | generatedQuery.columns[].label | string
ReportingService | askReportingQuestion | response | generatedQuery.columns[].aggregation | object |  | (default none)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].sortOrder | integer
ReportingService | askReportingQuestion | response | generatedQuery.columns[].sortDirection | enum (asc, desc)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].format | string |  | (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.filters | array of ReportFilter
ReportingService | askReportingQuestion | response | generatedQuery.filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery.filters[].field | string | yes
ReportingService | askReportingQuestion | response | generatedQuery.filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | askReportingQuestion | response | generatedQuery.filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | askReportingQuestion | response | generatedQuery.filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | askReportingQuestion | response | generatedQuery.filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | askReportingQuestion | response | generatedQuery.groupBy | array of string
ReportingService | askReportingQuestion | response | generatedQuery.compiledSql | string |  | The SQL the semantic spec compiled to, exactly as run on the analytical replica (29 September, design 5.7). (nullable)
ReportingService | askReportingQuestion | response | result | object | yes | Null when the question is outside the semantic model. (nullable)
ReportingService | askReportingQuestion | response | result.executionId | string | yes
ReportingService | askReportingQuestion | response | result.columns | array of object | yes
ReportingService | askReportingQuestion | response | result.columns[].key | string
ReportingService | askReportingQuestion | response | result.columns[].label | string
ReportingService | askReportingQuestion | response | result.columns[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …)
ReportingService | askReportingQuestion | response | result.rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | askReportingQuestion | response | result.totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | askReportingQuestion | response | result.rowCount | integer
ReportingService | askReportingQuestion | response | result.nextCursor | string |  | (nullable)
ReportingService | askReportingQuestion | response | result.generatedAt | string (date-time)
ReportingService | askReportingQuestion | response | result.dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | askReportingQuestion | response | dataAsOf | string (date-time) |  | Replica position the answer was read at, the result's dataAsOf, stated beside the answer so a figure that moved is not argued about. (nullable)
ReportingService | askReportingQuestion | response | reliability | ReportingAnswerReliability: enum (grounded, partial, conflictingSources, insufficientEvidence) | yes | How far an analytics answer can be relied on (decided 29 September, AI system design 5.6): a category, never a bare percentage.
ReportingService | askReportingQuestion | response | unavailableReason | object |  | Set only when reliability is insufficientEvidence because the question is outside the semantic model ("not available yet"); names which part is not modelled. (nullable)
ReportingService | askReportingQuestion | response | confidence | number |  | Superseded by reliability on 29 September (design 5.6, never a bare percentage for analytics). (min 0; max 1)
ReportingService | askReportingQuestion | response | suggestedFollowUps | array of string
ReportingService | askReportingQuestion | response | modelVersion | string
ReportingService | askReportingQuestion | response | tokensUsed | integer
ReportingService | askReportingQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | attachModifierGroup | request | groupIds | array of string (uuid) | yes
FnbService | attachModifierGroup | response | id | string (uuid) | yes
FnbService | attachModifierGroup | response | productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | attachModifierGroup | response | name | string | yes
FnbService | attachModifierGroup | response | description | string |  | (nullable)
FnbService | attachModifierGroup | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | attachModifierGroup | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | attachModifierGroup | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | attachModifierGroup | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | attachModifierGroup | response | sortOrder | integer
FnbService | attachModifierGroup | response | modifierGroupIds | array of string (uuid)
FnbService | attachModifierGroup | response | stationId | string (uuid) |  | (nullable)
FnbService | attachModifierGroup | response | menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | attachModifierGroup | response | isStockTracked | boolean |  | True where a recipe exists.
FnbService | attachModifierGroup | response | isAvailable | boolean | yes
FnbService | attachModifierGroup | response | unavailableReason | string |  | (nullable)
FnbService | attachModifierGroup | response | restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | attachModifierGroup | response | preparationMinutes | integer |  | (nullable)
FnbService | attachModifierGroup | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | attachModifierGroup | param (path) | menuItemId | string (uuid) | yes
FnbService | attachModifierGroup | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | attachModifierGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | bindCredentialDevice | request | deviceId | string | yes | The app's stable device identifier (max length 128)
AccessService | bindCredentialDevice | request | deviceReference | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | request | appInstallationId | string |  | (max length 128; nullable)
AccessService | bindCredentialDevice | request | os | string |  | (max length 64; nullable)
AccessService | bindCredentialDevice | request | otp | string |  | Verified one-time code, where the policy is otpVerificationRequired and this is a device change (max length 12; nullable)
AccessService | bindCredentialDevice | response | id | string (uuid) | yes
AccessService | bindCredentialDevice | response | subjectId | string (uuid) |  | The guest (pii.subject) (nullable)
AccessService | bindCredentialDevice | response | entitlementId | string (uuid) | yes
AccessService | bindCredentialDevice | response | credentialBindingId | string (uuid) |  | (nullable)
AccessService | bindCredentialDevice | response | deviceId | string | yes | (max length 200)
AccessService | bindCredentialDevice | response | deviceReference | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | response | appInstallationId | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | response | os | string |  | (max length 50; nullable)
AccessService | bindCredentialDevice | response | registeredAt | string (date-time) | yes
AccessService | bindCredentialDevice | response | lastActivatedAt | string (date-time) |  | (nullable)
AccessService | bindCredentialDevice | response | lastKnownVenueId | string (uuid) |  | (nullable)
AccessService | bindCredentialDevice | response | securityStatus | enum (normal, suspicious, blocked) | yes | (default normal)
AccessService | bindCredentialDevice | response | deactivatedAt | string (date-time) |  | Set when the binding is removed (deactivation, or a transfer of the credential) (nullable)
AccessService | bindCredentialDevice | response | scopePath | string | yes | ltree of the owning scope node
AccessService | bindCredentialDevice | response | updatedAt | string (date-time) |  | (read-only)
AccessService | bindCredentialDevice | param (path) | credentialId | string (uuid) | yes | The Virtual Ticket (access.entitlement.id); decided 29 September, writers pass
AccessService | bindCredentialDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | bookVisitPlan | request | baseVersion | integer | yes | The version the guest is looking at. (min 1)
VenueOpsService | bookVisitPlan | request | cartId | string (uuid) |  | The guest's open cart. (nullable)
VenueOpsService | bookVisitPlan | request | itemIds | array of string (uuid) |  | Only these items.
VenueOpsService | bookVisitPlan | request | includeAddOns | boolean |  | Also add the add-ons the guest accepted on the plan (VisitPlanItem.addOnAccepted). (default True)
VenueOpsService | bookVisitPlan | response | planId | string (uuid) | yes
VenueOpsService | bookVisitPlan | response | cartId | string (uuid) | yes
VenueOpsService | bookVisitPlan | response | added | array of object | yes
VenueOpsService | bookVisitPlan | response | added[].itemId | string (uuid)
VenueOpsService | bookVisitPlan | response | added[].cartLineId | string (uuid)
VenueOpsService | bookVisitPlan | response | added[].leaseExpiresAt | string (date-time) |  | (nullable)
VenueOpsService | bookVisitPlan | response | notAdded | array of object | yes | Items that could not be added, with the addCartLine refusal each met.
VenueOpsService | bookVisitPlan | response | notAdded[].itemId | string (uuid)
VenueOpsService | bookVisitPlan | response | notAdded[].reason | string |  | The orders CartProblem code, e.g.
VenueOpsService | bookVisitPlan | response | freeItems | integer |  | Stops that need nothing bought.
VenueOpsService | bookVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | bookVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | buildProductionPlan | request | id | string (uuid) | yes
FnbService | buildProductionPlan | request | outletId | string (uuid)
FnbService | buildProductionPlan | request | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone.
FnbService | buildProductionPlan | request | status | enum (draft, released, superseded, cancelled) | yes
FnbService | buildProductionPlan | request | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | buildProductionPlan | request | lines | array of object | yes
FnbService | buildProductionPlan | request | lines[].itemId | string (uuid) | yes
FnbService | buildProductionPlan | request | lines[].suggestedQuantity | number |  | (nullable)
FnbService | buildProductionPlan | request | lines[].plannedQuantity | number | yes
FnbService | buildProductionPlan | request | lines[].uom | string
FnbService | buildProductionPlan | request | lines[].stationId | string (uuid) |  | (nullable)
FnbService | buildProductionPlan | request | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | buildProductionPlan | response | id | string (uuid) | yes
FnbService | buildProductionPlan | response | outletId | string (uuid)
FnbService | buildProductionPlan | response | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone.
FnbService | buildProductionPlan | response | status | enum (draft, released, superseded, cancelled) | yes
FnbService | buildProductionPlan | response | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | buildProductionPlan | response | lines | array of object | yes
FnbService | buildProductionPlan | response | lines[].itemId | string (uuid) | yes
FnbService | buildProductionPlan | response | lines[].suggestedQuantity | number |  | (nullable)
FnbService | buildProductionPlan | response | lines[].plannedQuantity | number | yes
FnbService | buildProductionPlan | response | lines[].uom | string
FnbService | buildProductionPlan | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | buildProductionPlan | response | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | buildProductionPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | bulkChangePrices | request | dryRun | boolean |  | (default True)
CatalogueService | bulkChangePrices | request | selection | object | yes | A selection, not a list of ids.
CatalogueService | bulkChangePrices | request | selection.categoryId | string (uuid) |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.productKind | string |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.priceListId | string (uuid) |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | bulkChangePrices | request | adjustment | object | yes
CatalogueService | bulkChangePrices | request | adjustment.mode | enum (percentage, absolute, setTo) | yes
CatalogueService | bulkChangePrices | request | adjustment.value | string | yes | A decimal string, never a float (naming-and-style 5.1). (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | bulkChangePrices | request | adjustment.roundTo | string |  | An increment in the region's currency, as a decimal string (0.5, 5). (pattern ^\d+(\.\d{1,4})?$; nullable)
CatalogueService | bulkChangePrices | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | bulkChangePrices | response | applied | boolean | yes
CatalogueService | bulkChangePrices | response | productsMatched | integer | yes
CatalogueService | bulkChangePrices | response | pricesChanged | integer
CatalogueService | bulkChangePrices | response | skipped | array of object |  | Products the selection matched and the adjustment could not touch — a fixed-price bundle, a partner net rate, a product in an open period.
CatalogueService | bulkChangePrices | response | skipped[].productId | string (uuid)
CatalogueService | bulkChangePrices | response | skipped[].reason | string
CatalogueService | bulkChangePrices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | bulkUpdateProducts | request | previewOnly | boolean |  | (default True)
InventoryService | bulkUpdateProducts | request | selector | object | yes
InventoryService | bulkUpdateProducts | request | changes | object | yes
InventoryService | bulkUpdateProducts | response | matched | integer
InventoryService | bulkUpdateProducts | response | succeeded | integer
InventoryService | bulkUpdateProducts | response | failed | integer
InventoryService | bulkUpdateProducts | response | failures | array of object |  | One entry per product the change was refused for.
InventoryService | bulkUpdateProducts | response | failures[].productId | string (uuid) | yes
InventoryService | bulkUpdateProducts | response | failures[].code | string | yes | The validation rule the product failed, as in Problem.errors[].code.
InventoryService | bulkUpdateProducts | response | failures[].message | string
InventoryService | bulkUpdateProducts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | cancelReservation | param (path) | reservationId | string (uuid) | yes
OrderService | cancelReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | capturePayment | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | id | string (uuid) | yes
OrderService | capturePayment | response | orderId | string (uuid) | yes
OrderService | capturePayment | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | capturePayment | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | capturePayment | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | capturePayment | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | capturePayment | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | capturePayment | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | capturePayment | response | providerName | string |  | (nullable)
OrderService | capturePayment | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | capturePayment | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | capturePayment | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | capturePayment | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | capturePayment | response | nextAction.kind | enum (redirect, terminal)
OrderService | capturePayment | response | nextAction.url | string (uri) |  | (nullable)
OrderService | capturePayment | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | capturePayment | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | capturePayment | response | recordedAt | string (date-time) | yes
OrderService | capturePayment | response | syncedAt | string (date-time) |  | (nullable)
OrderService | capturePayment | param (path) | paymentId | string (uuid) | yes
OrderService | capturePayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | captureWalletHold | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | captureWalletHold | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | captureWalletHold | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | captureWalletHold | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | captureWalletHold | response | walletHoldId | string (uuid) | yes
WalletService | captureWalletHold | response | walletId | string (uuid) | yes
WalletService | captureWalletHold | response | orderId | string (uuid) |  | (nullable)
WalletService | captureWalletHold | response | paymentId | string (uuid) |  | (nullable)
WalletService | captureWalletHold | response | walletHoldAmount | number | yes
WalletService | captureWalletHold | response | currencyCode | string | yes | (max length 10)
WalletService | captureWalletHold | response | walletHoldStatus | string | yes | (max length 20)
WalletService | captureWalletHold | response | expiresAt | string (date-time) | yes
WalletService | captureWalletHold | response | createdAt | string (date-time) | yes
WalletService | captureWalletHold | response | capturedAt | string (date-time) |  | (nullable)
WalletService | captureWalletHold | response | releasedAt | string (date-time) |  | (nullable)
WalletService | captureWalletHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | captureWalletHold | param (path) | walletHoldId | string (uuid) | yes
PlatformService | certifyIntegration | request | decision | enum (certify, reject, revoke) | yes
PlatformService | certifyIntegration | request | certifiedUntil | string (date) |  | (nullable)
PlatformService | certifyIntegration | request | notes | string |  | (nullable)
PlatformService | certifyIntegration | response | id | string (uuid) | yes | (read-only)
PlatformService | certifyIntegration | response | developerId | string (uuid) | yes
PlatformService | certifyIntegration | response | name | string | yes
PlatformService | certifyIntegration | response | category | enum (crm, marketing, accounting, hotel, transport, analytics, accessibility, other) | yes
PlatformService | certifyIntegration | response | description | string
PlatformService | certifyIntegration | response | integrationUrl | string
PlatformService | certifyIntegration | response | requiredScopes | array of string
PlatformService | certifyIntegration | response | status | enum (draft, submitted, inReview, certified, rejected, revoked, delisted) | yes | (read-only)
PlatformService | certifyIntegration | response | certifiedUntil | string (date) |  | Certification expires. (read-only; nullable)
PlatformService | certifyIntegration | response | certifiedAgainstVersion | string |  | (read-only; nullable)
PlatformService | certifyIntegration | response | listingFeeModel | enum (none, flat, revenueShare) |  | (nullable)
PlatformService | certifyIntegration | response | visibility | enum (public, private) |  | private: certified for production access and never shown in the marketplace (17 September minutes, M17-06). (default public)
PlatformService | certifyIntegration | param (path) | listingId | string (uuid) | yes
PlatformService | certifyIntegration | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | changeOwnCredential | request | method | enum (password, pin) | yes | Which credential is being changed.
IdentityService | changeOwnCredential | request | currentCredential | string | yes | (max length 512)
IdentityService | changeOwnCredential | request | newCredential | string | yes | (max length 512)
IdentityService | changeOwnCredential | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | chaseStation | request | ticketId | string (uuid) | yes
FnbService | chaseStation | request | lineId | string (uuid) |  | (nullable)
FnbService | chaseStation | request | recordedAt | string (date-time) | yes | Device time of the chase.
FnbService | chaseStation | param (path) | stationId | string (uuid) | yes
FnbService | chaseStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | checkBookingEligibility | request | productIds | array of string | yes | (min items 1)
CatalogueService | checkBookingEligibility | request | party | array of EligibilityDeclaration | yes | (min items 1)
CatalogueService | checkBookingEligibility | request | party[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
CatalogueService | checkBookingEligibility | request | party[].ageYears | integer |  | (nullable)
CatalogueService | checkBookingEligibility | request | party[].heightBandIndex | integer |  | Which band of the rule's heightBandsCm, counting from 0. (nullable)
CatalogueService | checkBookingEligibility | request | party[].confidentSwimmer | boolean |  | Superseded by the consent record for the product's swim consent question (decided 29 September, rev 3 REV3-26); see ProductEligibilityRule.swimAbility. (nullable)
CatalogueService | checkBookingEligibility | request | party[].guardianSigned | boolean |  | (default False)
CatalogueService | checkBookingEligibility | response | eligible | boolean | yes
CatalogueService | checkBookingEligibility | response | guests | array of object
CatalogueService | checkBookingEligibility | response | guests[].index | integer
CatalogueService | checkBookingEligibility | response | guests[].eligible | boolean
CatalogueService | checkBookingEligibility | response | guests[].reasons | array of enum (tooYoung, tooOld, tooShort, tooTall, needsAdult, needsGuardianSignature, needsSwimmer)
CatalogueService | checkBookingEligibility | response | waiverRequired | boolean
CatalogueService | checkBookingEligibility | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | checkoutCart | request | subjectId | string (uuid) |  | The guest the order is for.
OrderService | checkoutCart | request | marketingConsents | array of object |  | Marketing opt-ins given at checkout (29 September, M18-15).
OrderService | checkoutCart | request | marketingConsents[].channel | enum (email, sms, whatsapp, push) | yes
OrderService | checkoutCart | request | marketingConsents[].purpose | string | yes | The consent purpose code (marketing ConsentPurpose), for example marketing. (max length 60)
OrderService | checkoutCart | request | marketingConsents[].granted | boolean | yes | True only when the guest ticked it.
OrderService | checkoutCart | request | marketingConsents[].noticeVersion | string |  | The version of the consent notice shown. (max length 40)
OrderService | checkoutCart | request | attendees | array of object |  | The named holder for each cart line that needs one.
OrderService | checkoutCart | request | attendees[].lineId | string (uuid) | yes | A CartLine.id in this cart.
OrderService | checkoutCart | request | attendees[].holderName | string | yes
OrderService | checkoutCart | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | checkoutCart | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | checkoutCart | response | channel | object | yes | Where it came from.
OrderService | checkoutCart | response | venueId | string (uuid) | yes
OrderService | checkoutCart | response | scopePath | string | yes
OrderService | checkoutCart | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | checkoutCart | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | checkoutCart | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | checkoutCart | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | checkoutCart | response | droppedPromotions[].name | string
OrderService | checkoutCart | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | checkoutCart | response | totalPriceVariance | object |  | Sum across lines.
OrderService | checkoutCart | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines | array of OrderLine | yes
OrderService | checkoutCart | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | checkoutCart | response | lines[].variantId | string (uuid) | yes
OrderService | checkoutCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | checkoutCart | response | lines[].performanceId | string (uuid)
OrderService | checkoutCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | checkoutCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | checkoutCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | checkoutCart | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | checkoutCart | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | checkoutCart | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | checkoutCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | checkoutCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | checkoutCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | checkoutCart | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | checkoutCart | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].holderName | string |  | (nullable)
OrderService | checkoutCart | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | checkoutCart | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | checkoutCart | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | checkoutCart | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | checkoutCart | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | checkoutCart | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | checkoutCart | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | checkoutCart | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | checkoutCart | response | lines[].discounts[].id | string (uuid) | yes
OrderService | checkoutCart | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | checkoutCart | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | checkoutCart | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | checkoutCart | response | payments | array of Payment
OrderService | checkoutCart | response | payments[].id | string (uuid) | yes
OrderService | checkoutCart | response | payments[].orderId | string (uuid) | yes
OrderService | checkoutCart | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | checkoutCart | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | checkoutCart | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | checkoutCart | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | checkoutCart | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | checkoutCart | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | checkoutCart | response | payments[].providerName | string |  | (nullable)
OrderService | checkoutCart | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | checkoutCart | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | checkoutCart | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | checkoutCart | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | checkoutCart | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | checkoutCart | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | checkoutCart | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | payments[].recordedAt | string (date-time) | yes
OrderService | checkoutCart | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | principalId | string (uuid)
OrderService | checkoutCart | response | workstationId | string (uuid)
OrderService | checkoutCart | response | shiftId | string (uuid) |  | (nullable)
OrderService | checkoutCart | response | subjectId | string (uuid) |  | (nullable)
OrderService | checkoutCart | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | checkoutCart | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | checkoutCart | response | createdAt | string (date-time) | yes
OrderService | checkoutCart | response | recordedAt | string (date-time) | yes
OrderService | checkoutCart | response | syncedAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | param (path) | cartId | string (uuid) | yes
OrderService | checkoutCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | claimCart | response | cart | Cart | yes
OrderService | claimCart | response | cart.id | string (uuid) | yes
OrderService | claimCart | response | cart.token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | claimCart | response | cart.venueId | string (uuid) | yes
OrderService | claimCart | response | cart.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | claimCart | response | cart.subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | claimCart | response | cart.status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | claimCart | response | cart.lines | array of CartLine | yes
OrderService | claimCart | response | cart.lines[].id | string (uuid) | yes
OrderService | claimCart | response | cart.lines[].variantId | string (uuid) | yes
OrderService | claimCart | response | cart.lines[].productName | string |  | (read-only)
OrderService | claimCart | response | cart.lines[].quantity | integer | yes | (min 1)
OrderService | claimCart | response | cart.lines[].performanceId | string (uuid) |  | (nullable)
OrderService | claimCart | response | cart.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | claimCart | response | cart.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | claimCart | response | cart.lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | claimCart | response | cart.lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | claimCart | response | cart.lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | claimCart | response | cart.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | claimCart | response | cart.lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | claimCart | response | cart.lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | claimCart | response | cart.lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | claimCart | response | cart.lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | claimCart | response | cart.lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | claimCart | response | cart.lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | claimCart | response | cart.conflicts | array of CartConflict
OrderService | claimCart | response | cart.conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | claimCart | response | cart.conflicts[].lineIds | array of string (uuid)
OrderService | claimCart | response | cart.conflicts[].message | string
OrderService | claimCart | response | cart.conflicts[].isBlocking | boolean |  | Most are not.
OrderService | claimCart | response | cart.consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | claimCart | response | cart.consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | claimCart | response | cart.consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | claimCart | response | cart.consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | claimCart | response | cart.consentQuestions[].helpText | object |  | (nullable)
OrderService | claimCart | response | cart.consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | claimCart | response | cart.consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | claimCart | response | cart.consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | claimCart | response | cart.consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | claimCart | response | cart.consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | claimCart | response | cart.consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | claimCart | response | cart.consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | claimCart | response | cart.consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | claimCart | response | cart.consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | claimCart | response | cart.subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | claimCart | response | cart.couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | claimCart | response | cart.expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | claimCart | response | cart.extensionsUsed | integer |  | (read-only)
OrderService | claimCart | response | cart.maxExtensions | integer |  | (read-only)
OrderService | claimCart | response | cart.locale | string
OrderService | claimCart | response | cart.createdAt | string (date-time)
OrderService | claimCart | response | cart.updatedAt | string (date-time)
OrderService | claimCart | response | mergedLineCount | integer
OrderService | claimCart | response | droppedLines | array of object |  | Reported, never silent.
OrderService | claimCart | response | droppedLines[].productName | string
OrderService | claimCart | response | droppedLines[].reason | enum (noCapacity, expired, notSellableOnChannel, duplicate)
OrderService | claimCart | param (path) | cartId | string (uuid) | yes
OrderService | claimCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | claimCustomDomain | request | hostname | string | yes
WhiteLabelService | claimCustomDomain | request | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) | yes
WhiteLabelService | claimCustomDomain | request | verificationMethod | enum (dnsTxt, cname, httpFile) |  | (default dnsTxt)
WhiteLabelService | claimCustomDomain | response | id | string (uuid) | yes
WhiteLabelService | claimCustomDomain | response | tenantId | string (uuid) | yes
WhiteLabelService | claimCustomDomain | response | hostname | string | yes
WhiteLabelService | claimCustomDomain | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal)
WhiteLabelService | claimCustomDomain | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | claimCustomDomain | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | claimCustomDomain | response | verificationToken | string |  | (read-only)
WhiteLabelService | claimCustomDomain | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | claimCustomDomain | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | claimCustomDomain | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | claimCustomDomain | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | claimCustomDomain | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | claimCustomDomain | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | claimCustomDomain | response | failureReason | string |  | (nullable)
WhiteLabelService | claimCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | claimDeviceConsent | request | consentKey | string | yes | (max length 64)
MarketingService | claimDeviceConsent | response | subjectId | string (uuid) | yes
MarketingService | claimDeviceConsent | response | purposes | array of object | yes
MarketingService | claimDeviceConsent | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | claimDeviceConsent | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | claimDeviceConsent | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | claimDeviceConsent | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | claimDeviceConsent | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | claimDeviceConsent | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | claimDeviceConsent | param (path) | subjectId | string (uuid) | yes
MarketingService | claimDeviceConsent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | claimLocationSession | request | locationCode | string |  | From the QR or NFC tag.
FnbService | claimLocationSession | request | seatReference | object |  | For seated venues where the seat is the address and there is no code to scan.
FnbService | claimLocationSession | request | seatReference.performanceId | string (uuid)
FnbService | claimLocationSession | request | seatReference.seatId | string
FnbService | claimLocationSession | request | partySize | integer |  | (min 1)
FnbService | claimLocationSession | response | id | string (uuid) | yes
FnbService | claimLocationSession | response | locationId | string (uuid) | yes
FnbService | claimLocationSession | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | claimLocationSession | response | label | string | yes
FnbService | claimLocationSession | response | outletId | string (uuid) |  | The outlet serving this location. (nullable)
FnbService | claimLocationSession | response | visitId | string (uuid) |  | The table visit this session orders onto, where the location is a table. (nullable)
FnbService | claimLocationSession | response | joinedExistingVisit | boolean
FnbService | claimLocationSession | response | subjectId | string (uuid)
FnbService | claimLocationSession | response | expiresAt | string (date-time) | yes | Sessions expire so a guest who leaves cannot order to a lounger now occupied by someone else.
FnbService | claimLocationSession | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | claimTableSession | request | tableCode | string | yes | From the table QR.
FnbService | claimTableSession | request | partySize | integer |  | (min 1)
FnbService | claimTableSession | response | id | string (uuid) | yes
FnbService | claimTableSession | response | outletId | string (uuid) | yes
FnbService | claimTableSession | response | outletName | string
FnbService | claimTableSession | response | tableId | string (uuid) | yes
FnbService | claimTableSession | response | tableLabel | string | yes
FnbService | claimTableSession | response | visitId | string (uuid) | yes | The table visit this session orders onto.
FnbService | claimTableSession | response | joinedExistingVisit | boolean
FnbService | claimTableSession | response | subjectId | string (uuid)
FnbService | claimTableSession | response | expiresAt | string (date-time) | yes | Sessions expire so a guest who leaves cannot order to a table now occupied by someone else.
FnbService | claimTableSession | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | claimTicketTransfer | request | claimToken | string | yes | The token carried in the claim link, checked against TicketTransfer.claimToken.
OrderService | claimTicketTransfer | response | id | string (uuid) | yes
OrderService | claimTicketTransfer | response | orderId | string (uuid) | yes
OrderService | claimTicketTransfer | response | ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | claimTicketTransfer | response | fromSubjectId | string (uuid)
OrderService | claimTicketTransfer | response | toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | claimTicketTransfer | response | recipientAddressMasked | string
OrderService | claimTicketTransfer | response | status | enum (offered, claimed, expired, cancelled) | yes
OrderService | claimTicketTransfer | response | claimUrl | string |  | (nullable)
OrderService | claimTicketTransfer | response | claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | claimTicketTransfer | response | offeredAt | string (date-time) | yes
OrderService | claimTicketTransfer | response | claimedAt | string (date-time) |  | (nullable)
OrderService | claimTicketTransfer | response | expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | claimTicketTransfer | param (path) | transferId | string (uuid) | yes
OrderService | claimTicketTransfer | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | clearTable | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | clearTable | response | id | string (uuid) | yes
FnbService | clearTable | response | label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | clearTable | response | capacity | integer | yes | (min 1)
FnbService | clearTable | response | zone | string |  | (nullable)
FnbService | clearTable | response | position | object
FnbService | clearTable | response | position.x | number
FnbService | clearTable | response | position.y | number
FnbService | clearTable | response | shape | enum (round, square, rectangle, booth, bar)
FnbService | clearTable | response | isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | clearTable | response | status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | clearTable | response | visitId | string (uuid) |  | (nullable)
FnbService | clearTable | response | covers | integer |  | (nullable)
FnbService | clearTable | response | seatedAt | string (date-time) |  | (nullable)
FnbService | clearTable | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | clearTable | response | billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | clearTable | response | billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | clearTable | response | billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | clearTable | response | billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | clearTable | param (path) | tableId | string (uuid) | yes
FnbService | clearTable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | cloneEvent | request | include | array of enum (schedule, pricing, seatMap, capacityProfile, resourceRequirements, staffPlan, registrationForm, accessRules)
CatalogueService | cloneEvent | request | shiftDatesByDays | integer |  | (nullable)
CatalogueService | cloneEvent | request | newName | string |  | (nullable)
CatalogueService | cloneEvent | response | eventId | string (uuid)
CatalogueService | cloneEvent | param (path) | eventId | string (uuid) | yes
CatalogueService | cloneEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | cloneProduct | request | code | string | yes
CatalogueService | cloneProduct | request | name | string | yes
CatalogueService | cloneProduct | request | includeVariants | boolean |  | (default True)
CatalogueService | cloneProduct | request | includePrices | boolean |  | (default False)
CatalogueService | cloneProduct | response | id | string (uuid) | yes
CatalogueService | cloneProduct | response | code | string | yes | (max length 64)
CatalogueService | cloneProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | cloneProduct | response | name | string | yes | (max length 200)
CatalogueService | cloneProduct | response | description | string
CatalogueService | cloneProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | cloneProduct | response | venueId | string (uuid) | yes
CatalogueService | cloneProduct | response | scopePath | string | yes
CatalogueService | cloneProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | cloneProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | cloneProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | cloneProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | cloneProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | cloneProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | cloneProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | cloneProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | cloneProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | cloneProduct | response | hasVariants | boolean | yes
CatalogueService | cloneProduct | response | variantCount | integer
CatalogueService | cloneProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | cloneProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | cloneProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | cloneProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | cloneProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | cloneProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | cloneProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | cloneProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | cloneProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | cloneProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | cloneProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | cloneProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | cloneProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | cloneProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | cloneProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | cloneProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | cloneProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | cloneProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | cloneProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | cloneProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | cloneProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | cloneProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | cloneProduct | response | media[].altText | object |  | (nullable)
CatalogueService | cloneProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | cloneProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | cloneProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | cloneProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | cloneProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | cloneProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | cloneProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | cloneProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | cloneProduct | param (path) | productId | string (uuid) | yes
CatalogueService | cloneProduct | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeDepositBoxes | request | boxIds | array of string (uuid)
OrderService | closeDepositBoxes | request | allOpenAtVenue | boolean
OrderService | closeDepositBoxes | request | counts | array of object | yes | One count per box being closed that has traded (audit R123 (4)).
OrderService | closeDepositBoxes | request | counts[].boxId | string (uuid) | yes
OrderService | closeDepositBoxes | request | counts[].countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeDepositBoxes | request | counts[].countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeDepositBoxes | request | counts[].countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeDepositBoxes | request | counts[].countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeDepositBoxes | request | counts[].countedDenominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].id | string (uuid)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].countedBy | string (uuid) |  | (nullable)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].countedAt | string (date-time)
OrderService | closeDepositBoxes | request | counts[].countedDenominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | closeDepositBoxes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeShift | request | countedCash | array of CountedDenominationLine | yes | The cashier's blind count, one line per denomination counted (decided 29 September, readiness close-out; our build plan). (min items 1)
OrderService | closeShift | request | countedCash[].denominationId | string (uuid) | yes | References platform.denomination (Denomination.id) — face value, kind and counting order live there.
OrderService | closeShift | request | countedCash[].count | integer | yes | How many of this note or coin were counted. (min 0; max 100000)
OrderService | closeShift | request | countedCash[].total | object |  | count times the face value, in the denomination's currency.
OrderService | closeShift | request | countedCash[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | request | countedCash[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | request | countedCash[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | request | nonCashDeclared | array of object |  | Declared totals per non-cash tender, for reconciliation against captured payments.
OrderService | closeShift | request | nonCashDeclared[].tender | string | yes
OrderService | closeShift | request | nonCashDeclared[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | request | nonCashDeclared[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | request | nonCashDeclared[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | request | nonCashDeclared[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | request | notes | string |  | (max length 1000)
OrderService | closeShift | request | releaseHeldLeases | boolean |  | Return unsold inventory leases held by this workstation (ADR-0013 C103). (default True)
OrderService | closeShift | request | recordedAt | string (date-time) | yes
OrderService | closeShift | response | shift | Shift | yes | approvals and incidents are child rows (26 September, pull audit R099): orders.pos_shift_approval and orders.pos_shift_incident, one row per item, keyed to the shift.
OrderService | closeShift | response | shift.id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeShift | response | shift.workstationId | string (uuid) | yes
OrderService | closeShift | response | shift.venueId | string (uuid) | yes
OrderService | closeShift | response | shift.scopePath | string | yes
OrderService | closeShift | response | shift.principalId | string (uuid) | yes | Who opened it.
OrderService | closeShift | response | shift.principalDisplayName | string
OrderService | closeShift | response | shift.incidents | array of object |  | BL-097.
OrderService | closeShift | response | shift.incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | closeShift | response | shift.incidents[].at | string (date-time)
OrderService | closeShift | response | shift.incidents[].principalId | string (uuid)
OrderService | closeShift | response | shift.incidents[].note | string |  | (nullable)
OrderService | closeShift | response | shift.status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | closeShift | response | shift.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | closeShift | response | shift.depositBoxCode | string |  | (nullable)
OrderService | closeShift | response | shift.bagNumber | string |  | (nullable)
OrderService | closeShift | response | shift.openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | closeShift | response | shift.expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | closeShift | response | shift.countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | closeShift | response | shift.variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | closeShift | response | shift.openedAt | string (date-time) | yes
OrderService | closeShift | response | shift.recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | closeShift | response | shift.suspendedAt | string (date-time) |  | (nullable)
OrderService | closeShift | response | shift.suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | closeShift | response | shift.closedAt | string (date-time) |  | (nullable)
OrderService | closeShift | response | shift.closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | closeShift | response | shift.syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | closeShift | response | shift.approvals | array of object
OrderService | closeShift | response | shift.approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | closeShift | response | shift.approvals[].principalId | string (uuid) | yes
OrderService | closeShift | response | shift.approvals[].at | string (date-time) | yes
OrderService | closeShift | response | shift.approvals[].reason | string
OrderService | closeShift | response | expectedCash | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | countedCash | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | variance | object | yes | Counted minus expected.
OrderService | closeShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | requiresAcceptance | boolean | yes | True when the variance exceeds the venue's shiftVarianceThreshold (audit R094).
OrderService | closeShift | response | nonCashVariances | array of object
OrderService | closeShift | response | nonCashVariances[].tender | string | yes
OrderService | closeShift | response | nonCashVariances[].declared | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].declared.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].declared.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].declared.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | nonCashVariances[].captured | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].captured.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].captured.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].captured.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | nonCashVariances[].variance | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | param (path) | shiftId | string (uuid) | yes
OrderService | closeShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | closeTableVisit | request | payments | array of object | yes | (min items 1)
FnbService | closeTableVisit | request | payments[].subBillId | string | yes
FnbService | closeTableVisit | request | payments[].tender | string | yes
FnbService | closeTableVisit | request | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | request | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | request | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | request | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | request | gratuity | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | request | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | request | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | request | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit | TableVisit | yes
FnbService | closeTableVisit | response | visit.id | string (uuid) | yes
FnbService | closeTableVisit | response | visit.tableId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.tableLabel | string
FnbService | closeTableVisit | response | visit.outletId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.covers | integer | yes
FnbService | closeTableVisit | response | visit.status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | closeTableVisit | response | visit.serverPrincipalId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.subjectId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders | array of FnbOrder | yes
FnbService | closeTableVisit | response | visit.orders[].id | string (uuid) | yes
FnbService | closeTableVisit | response | visit.orders[].orderNumber | string | yes
FnbService | closeTableVisit | response | visit.orders[].outletId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | closeTableVisit | response | visit.orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | closeTableVisit | response | visit.orders[].lines | array of object | yes
FnbService | closeTableVisit | response | visit.orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | closeTableVisit | response | visit.orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | closeTableVisit | response | visit.orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | closeTableVisit | response | visit.orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].createdAt | string (date-time) | yes
FnbService | closeTableVisit | response | visit.orders[].recordedAt | string (date-time)
FnbService | closeTableVisit | response | visit.orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.mergedFromVisitIds | array of string (uuid)
FnbService | closeTableVisit | response | visit.runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | response | visit.runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | response | visit.runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit.gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | closeTableVisit | response | visit.gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | response | visit.gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | response | visit.gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit.openedAt | string (date-time) | yes
FnbService | closeTableVisit | response | visit.closedAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | orderIds | array of string | yes
FnbService | closeTableVisit | param (path) | visitId | string (uuid) | yes
FnbService | closeTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | commitCatalogueImport | response | id | string (uuid) | yes
CatalogueService | commitCatalogueImport | response | status | enum (parsing, previewReady, committing, committed, failed) | yes
CatalogueService | commitCatalogueImport | response | outcome | enum (parsed, parsedWithFindings, nothingFound, unreadable)
CatalogueService | commitCatalogueImport | response | parsedCount | integer | yes
CatalogueService | commitCatalogueImport | response | createCount | integer
CatalogueService | commitCatalogueImport | response | updateCount | integer
CatalogueService | commitCatalogueImport | response | findings | array of object |  | What an operator sees before committing — missing prices, duplicate codes, unknown categories, codes that do not match the tenant's schema.
CatalogueService | commitCatalogueImport | response | findings[].row | integer
CatalogueService | commitCatalogueImport | response | findings[].severity | enum (error, warning)
CatalogueService | commitCatalogueImport | response | findings[].message | string
CatalogueService | commitCatalogueImport | response | scopePath | string |  | The partition key (ADR-0005).
CatalogueService | commitCatalogueImport | response | jobKind | enum (productImport, environmentTransfer, pricingBulkUpdate, pricingImport) |  | One job table for every catalogue bulk operation (29 September, data model DM3): product import (the original use), environment transfer (ADM-124) and bulk pricing update or import (ADM-080). (default productImport)
CatalogueService | commitCatalogueImport | response | direction | enum (export, import, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | sourceEnvironment | enum (development, sandbox, uat, staging, production, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | targetEnvironment | enum (development, sandbox, uat, staging, production, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | productIds | array of string (uuid)
CatalogueService | commitCatalogueImport | response | components | array of string |  | Transfer components, per ProductImportExportEnvironmentTransferView.components.
CatalogueService | commitCatalogueImport | response | referenceMappings | object |  | [{kind, sourceRef, targetRef}]. (nullable)
CatalogueService | commitCatalogueImport | response | missingReferences | array of string
CatalogueService | commitCatalogueImport | response | fileId | string (uuid) |  | (nullable)
CatalogueService | commitCatalogueImport | response | sourceFormat | string |  | (max length 40; nullable)
CatalogueService | commitCatalogueImport | response | columnMappings | object |  | [{sourceColumn, targetField, suggestedByAi, confirmed}]. (nullable)
CatalogueService | commitCatalogueImport | response | parameters | object |  | Bulk pricing: {selectBy, selectionValues, operation, adjustmentPercent, adjustmentAmount, targetCurrency, effectivePeriodFrom, effectivePeriodTo}. (nullable)
CatalogueService | commitCatalogueImport | response | warningCount | integer |  | (default 0)
CatalogueService | commitCatalogueImport | response | errorCount | integer |  | (default 0)
CatalogueService | commitCatalogueImport | response | changeRequestId | string (uuid) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | response | requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | commitCatalogueImport | response | completedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | param (path) | jobId | string (uuid) | yes
CatalogueService | commitCatalogueImport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | completeUpload | request | title | LocalisedText
VenueOpsService | completeUpload | request | altText | LocalisedText
VenueOpsService | completeUpload | request | tags | array of string
VenueOpsService | completeUpload | request | collectionIds | array of string (uuid)
VenueOpsService | completeUpload | request | rights | MediaRights |  | Licensing terms.
VenueOpsService | completeUpload | request | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | completeUpload | request | rights.licensor | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.licenceReference | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | completeUpload | request | rights.validTo | string (date) |  | (nullable)
VenueOpsService | completeUpload | request | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | completeUpload | request | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | completeUpload | request | rights.attributionText | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | completeUpload | request | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | completeUpload | request | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | completeUpload | request | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | id | string (uuid) | yes
VenueOpsService | completeUpload | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive) | yes
VenueOpsService | completeUpload | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | completeUpload | response | filename | string | yes
VenueOpsService | completeUpload | response | contentType | string | yes
VenueOpsService | completeUpload | response | sizeBytes | integer | yes
VenueOpsService | completeUpload | response | title | LocalisedText
VenueOpsService | completeUpload | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | completeUpload | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | completeUpload | response | width | integer |  | (nullable)
VenueOpsService | completeUpload | response | height | integer |  | (nullable)
VenueOpsService | completeUpload | response | durationSeconds | number |  | (nullable)
VenueOpsService | completeUpload | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | completeUpload | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | completeUpload | response | tags | array of string
VenueOpsService | completeUpload | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | completeUpload | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | completeUpload | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | completeUpload | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | completeUpload | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | completeUpload | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | completeUpload | response | rights.licensor | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | completeUpload | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | completeUpload | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | completeUpload | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | completeUpload | response | rights.attributionText | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | completeUpload | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | completeUpload | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | completeUpload | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | isRightsExpired | boolean
VenueOpsService | completeUpload | response | version | integer
VenueOpsService | completeUpload | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | completeUpload | response | createdAt | string (date-time) | yes
VenueOpsService | completeUpload | param (path) | uploadId | string (uuid) | yes
VenueOpsService | completeUpload | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | configureAiCapability | request | id | string (uuid) |  | (read-only)
AiService | configureAiCapability | request | capabilityKey | string | yes | Stable key, unique per tenant: assistant.guest, forecast.attendance, risk.transaction, config.assistant, recommend.checkout.
AiService | configureAiCapability | request | family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …) | yes | The fourteen capabilities of the AI system design (section 1.1), C1 to C14 in order: gateway and model registry, governance decision point, action pipeline and human oversight, knowledge and retrieva…
AiService | configureAiCapability | request | name | string
AiService | configureAiCapability | request | description | string |  | (nullable)
AiService | configureAiCapability | request | ownerPrincipalId | string (uuid) |  | The accountable business owner (AIC-144). (nullable)
AiService | configureAiCapability | request | businessFunction | string |  | (nullable)
AiService | configureAiCapability | request | riskClass | AiRiskClass: enum (low, medium, high, critical) | yes | Business, customer, financial, operational, security and compliance impact of a capability or action type (AIC-144, ADM-521).
AiService | configureAiCapability | request | autonomyCeiling | object |  | The first-release ceiling for this capability (design 3.8 table). (read-only)
AiService | configureAiCapability | request | autonomyLevel | object | yes | The level in force at this scope.
AiService | configureAiCapability | request | dataCategories | array of string |  | Data categories the capability reads (ADM-524).
AiService | configureAiCapability | request | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | configureAiCapability | request | lifecycle.development | enum (draft, pilot, active, retired)
AiService | configureAiCapability | request | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | configureAiCapability | request | lifecycle.production | enum (draft, pilot, active, retired)
AiService | configureAiCapability | request | degradationMode | enum (rulesOnly, searchOnly, humanHandoff, hidden, failOpen, lastPublished) |  | What the capability does when its model or the service is unavailable (design 3.7, AIC-241).
AiService | configureAiCapability | request | status | enum (active, paused) |  | Paused by pauseAiCapability: the capability answers from its degradation mode until resumed. (read-only)
AiService | configureAiCapability | request | pausedReason | string |  | (read-only; nullable)
AiService | configureAiCapability | request | pausedAt | string (date-time) |  | (read-only; nullable)
AiService | configureAiCapability | request | updatedAt | string (date-time) |  | (read-only)
AiService | configureAiCapability | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAiCapability | response | id | string (uuid) |  | (read-only)
AiService | configureAiCapability | response | capabilityKey | string | yes | Stable key, unique per tenant: assistant.guest, forecast.attendance, risk.transaction, config.assistant, recommend.checkout.
AiService | configureAiCapability | response | family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …) | yes | The fourteen capabilities of the AI system design (section 1.1), C1 to C14 in order: gateway and model registry, governance decision point, action pipeline and human oversight, knowledge and retrieva…
AiService | configureAiCapability | response | name | string
AiService | configureAiCapability | response | description | string |  | (nullable)
AiService | configureAiCapability | response | ownerPrincipalId | string (uuid) |  | The accountable business owner (AIC-144). (nullable)
AiService | configureAiCapability | response | businessFunction | string |  | (nullable)
AiService | configureAiCapability | response | riskClass | AiRiskClass: enum (low, medium, high, critical) | yes | Business, customer, financial, operational, security and compliance impact of a capability or action type (AIC-144, ADM-521).
AiService | configureAiCapability | response | autonomyCeiling | object |  | The first-release ceiling for this capability (design 3.8 table). (read-only)
AiService | configureAiCapability | response | autonomyLevel | object | yes | The level in force at this scope.
AiService | configureAiCapability | response | dataCategories | array of string |  | Data categories the capability reads (ADM-524).
AiService | configureAiCapability | response | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | configureAiCapability | response | lifecycle.development | enum (draft, pilot, active, retired)
AiService | configureAiCapability | response | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | configureAiCapability | response | lifecycle.production | enum (draft, pilot, active, retired)
AiService | configureAiCapability | response | degradationMode | enum (rulesOnly, searchOnly, humanHandoff, hidden, failOpen, lastPublished) |  | What the capability does when its model or the service is unavailable (design 3.7, AIC-241).
AiService | configureAiCapability | response | status | enum (active, paused) |  | Paused by pauseAiCapability: the capability answers from its degradation mode until resumed. (read-only)
AiService | configureAiCapability | response | pausedReason | string |  | (read-only; nullable)
AiService | configureAiCapability | response | pausedAt | string (date-time) |  | (read-only; nullable)
AiService | configureAiCapability | response | updatedAt | string (date-time) |  | (read-only)
AiService | configureAiCapability | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAiCapability | param (path) | capabilityKey | string | yes
AiService | configureAiCapability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | configureAssistantProfile | request | id | string (uuid) |  | (read-only)
AiService | configureAssistantProfile | request | profileKey | string | yes
AiService | configureAssistantProfile | request | name | string
AiService | configureAssistantProfile | request | audience | enum (staff, guest, support) | yes
AiService | configureAssistantProfile | request | roleIds | array of string (uuid)
AiService | configureAssistantProfile | request | module | object |  | (nullable)
AiService | configureAssistantProfile | request | collectionIds | array of string (uuid) |  | Knowledge collections it retrieves from.
AiService | configureAssistantProfile | request | toolKeys | array of string |  | Registered tools it may propose (an assistant only reads; a change request goes to the configuration assistant, AIC-078).
AiService | configureAssistantProfile | request | modelTask | string |  | The gateway task, e.g.
AiService | configureAssistantProfile | request | guestCapabilityScope | array of string |  | For a guest profile: the same values as AiPolicy.guestCapabilityScope, narrowed.
AiService | configureAssistantProfile | request | locales | array of string
AiService | configureAssistantProfile | request | handoverTarget | string |  | Where "ask a person" goes: a support queue or a staff role. (nullable)
AiService | configureAssistantProfile | request | isActive | boolean |  | (default True)
AiService | configureAssistantProfile | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAssistantProfile | response | id | string (uuid) |  | (read-only)
AiService | configureAssistantProfile | response | profileKey | string | yes
AiService | configureAssistantProfile | response | name | string
AiService | configureAssistantProfile | response | audience | enum (staff, guest, support) | yes
AiService | configureAssistantProfile | response | roleIds | array of string (uuid)
AiService | configureAssistantProfile | response | module | object |  | (nullable)
AiService | configureAssistantProfile | response | collectionIds | array of string (uuid) |  | Knowledge collections it retrieves from.
AiService | configureAssistantProfile | response | toolKeys | array of string |  | Registered tools it may propose (an assistant only reads; a change request goes to the configuration assistant, AIC-078).
AiService | configureAssistantProfile | response | modelTask | string |  | The gateway task, e.g.
AiService | configureAssistantProfile | response | guestCapabilityScope | array of string |  | For a guest profile: the same values as AiPolicy.guestCapabilityScope, narrowed.
AiService | configureAssistantProfile | response | locales | array of string
AiService | configureAssistantProfile | response | handoverTarget | string |  | Where "ask a person" goes: a support queue or a staff role. (nullable)
AiService | configureAssistantProfile | response | isActive | boolean |  | (default True)
AiService | configureAssistantProfile | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAssistantProfile | param (path) | profileKey | string | yes
AiService | configureAssistantProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | configureQueueFeed | request | id | string (uuid) | yes
VenueOpsService | configureQueueFeed | request | queueId | string (uuid) | yes
VenueOpsService | configureQueueFeed | request | adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) | yes | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | request | adaptorName | string |  | Named vendor where adaptor is vendorAdaptor. (nullable)
VenueOpsService | configureQueueFeed | request | credentialsRef | string |  | Key vault reference. (nullable)
VenueOpsService | configureQueueFeed | request | expectedIntervalSeconds | integer |  | Beyond this without a reading, the feed is considered quiet. (default 60)
VenueOpsService | configureQueueFeed | request | isEnabled | boolean | yes
VenueOpsService | configureQueueFeed | request | health | object |  | Whether the feed is currently reporting, computed on read — what listQueueFeeds promises per row. (read-only)
VenueOpsService | configureQueueFeed | request | health.feedId | string (uuid) | yes
VenueOpsService | configureQueueFeed | request | health.adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) |  | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | request | health.isHealthy | boolean | yes | Healthy means the last reading arrived within the feed's expected interval (decided 28 September, audit R106 (1)): lastReadingAt is no older than expectedIntervalSeconds.
VenueOpsService | configureQueueFeed | request | health.isQuiet | boolean | yes | No reading within the expected interval.
VenueOpsService | configureQueueFeed | request | health.lastReadingAt | string (date-time) |  | (nullable)
VenueOpsService | configureQueueFeed | request | health.expectedIntervalSeconds | integer |  | The feed's expectedIntervalSeconds — the interval isQuiet is judged against, returned here so a health panel does not need the feed row as well.
VenueOpsService | configureQueueFeed | request | health.readingsLastHour | integer
VenueOpsService | configureQueueFeed | request | health.discardedLastHour | integer |  | Out-of-order readings rejected in the last hour — rows of queue.reading for this feed with disposition: discardedOutOfOrder.
VenueOpsService | configureQueueFeed | response | id | string (uuid) | yes
VenueOpsService | configureQueueFeed | response | queueId | string (uuid) | yes
VenueOpsService | configureQueueFeed | response | adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) | yes | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | response | adaptorName | string |  | Named vendor where adaptor is vendorAdaptor. (nullable)
VenueOpsService | configureQueueFeed | response | credentialsRef | string |  | Key vault reference. (nullable)
VenueOpsService | configureQueueFeed | response | expectedIntervalSeconds | integer |  | Beyond this without a reading, the feed is considered quiet. (default 60)
VenueOpsService | configureQueueFeed | response | isEnabled | boolean | yes
VenueOpsService | configureQueueFeed | response | health | object |  | Whether the feed is currently reporting, computed on read — what listQueueFeeds promises per row. (read-only)
VenueOpsService | configureQueueFeed | response | health.feedId | string (uuid) | yes
VenueOpsService | configureQueueFeed | response | health.adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) |  | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | configureQueueFeed | response | health.isHealthy | boolean | yes | Healthy means the last reading arrived within the feed's expected interval (decided 28 September, audit R106 (1)): lastReadingAt is no older than expectedIntervalSeconds.
VenueOpsService | configureQueueFeed | response | health.isQuiet | boolean | yes | No reading within the expected interval.
VenueOpsService | configureQueueFeed | response | health.lastReadingAt | string (date-time) |  | (nullable)
VenueOpsService | configureQueueFeed | response | health.expectedIntervalSeconds | integer |  | The feed's expectedIntervalSeconds — the interval isQuiet is judged against, returned here so a health panel does not need the feed row as well.
VenueOpsService | configureQueueFeed | response | health.readingsLastHour | integer
VenueOpsService | configureQueueFeed | response | health.discardedLastHour | integer |  | Out-of-order readings rejected in the last hour — rows of queue.reading for this feed with disposition: discardedOutOfOrder.
VenueOpsService | configureQueueFeed | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | configureWorkstation | request | cashierInputMode | enum (keyboard, touch, scanner, hybrid) |  | BL-061. (default hybrid)
TenancyService | configureWorkstation | request | guestDisplayContent | array of enum (lineItems, total, loyaltyBalance, promotions, branding, upsell, queuePosition) |  | What the guest-facing screen shows while a sale is in progress.
TenancyService | configureWorkstation | request | loadedMediaStockId | string (uuid) |  | BL-095. (nullable)
TenancyService | configureWorkstation | request | mediaStockRemaining | integer |  | Decremented on issue. (read-only; nullable)
TenancyService | configureWorkstation | request | name | string | yes | (max length 200)
TenancyService | configureWorkstation | request | saleBoardId | string (uuid) | yes
TenancyService | configureWorkstation | request | departmentId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | accessPointId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | devices | array of DeviceBinding
TenancyService | configureWorkstation | request | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | configureWorkstation | request | devices[].driver | string | yes | Driver identifier.
TenancyService | configureWorkstation | request | devices[].identifier | string |  | Serial
TenancyService | configureWorkstation | request | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | configureWorkstation | request | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | configureWorkstation | request | edgeNodeId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | isActive | boolean |  | (default True)
TenancyService | configureWorkstation | response | id | string (uuid) | yes
TenancyService | configureWorkstation | response | code | string | yes | (max length 64)
TenancyService | configureWorkstation | response | name | string | yes | (max length 200)
TenancyService | configureWorkstation | response | venueId | string (uuid) | yes
TenancyService | configureWorkstation | response | regionId | string (uuid) | yes
TenancyService | configureWorkstation | response | departmentId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | response | scopePath | string | yes
TenancyService | configureWorkstation | response | saleBoard | object | yes | Determines which front end loads.
TenancyService | configureWorkstation | response | saleBoard.id | string (uuid) | yes
TenancyService | configureWorkstation | response | saleBoard.kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | configureWorkstation | response | saleBoard.name | string
TenancyService | configureWorkstation | response | accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator. (nullable)
TenancyService | configureWorkstation | response | devices | array of DeviceBinding
TenancyService | configureWorkstation | response | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | configureWorkstation | response | devices[].driver | string | yes | Driver identifier.
TenancyService | configureWorkstation | response | devices[].identifier | string |  | Serial
TenancyService | configureWorkstation | response | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | configureWorkstation | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
TenancyService | configureWorkstation | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
TenancyService | configureWorkstation | response | timeZone | string | yes
TenancyService | configureWorkstation | response | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | configureWorkstation | response | edgeNodeId | string (uuid) |  | Present when deploymentProfile is venueEdge. (nullable)
TenancyService | configureWorkstation | response | healthScore | integer |  | Board 1 of the client's POS set. (min 0; max 100; read-only; nullable)
TenancyService | configureWorkstation | response | configurationProfileId | string (uuid) |  | Which profile this workstation runs, and at which version. (nullable)
TenancyService | configureWorkstation | response | catalogueState | CatalogueState |  | The workstation's local catalogue position.
TenancyService | configureWorkstation | response | catalogueState.appliedBundleVersion | string | yes
TenancyService | configureWorkstation | response | catalogueState.appliedAt | string (date-time) | yes
TenancyService | configureWorkstation | response | catalogueState.staleAfter | string (date-time) | yes | Beyond this the terminal refuses to trade.
TenancyService | configureWorkstation | response | catalogueState.isStale | boolean | yes
TenancyService | configureWorkstation | response | catalogueState.pendingBundleVersion | string |  | Published but not yet applied. (nullable)
TenancyService | configureWorkstation | response | offlineCapable | boolean |  | Derived from deploymentProfile.
TenancyService | configureWorkstation | response | isActive | boolean
TenancyService | configureWorkstation | param (path) | workstationId | string (uuid) | yes
TenancyService | configureWorkstation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | containAiIncident | request | actions | array of object | yes | (min items 1)
AiService | containAiIncident | request | actions[].action | enum (pauseCapability, rollbackRelease, revokeException, disableTool) | yes
AiService | containAiIncident | request | actions[].targetRef | string | yes
AiService | containAiIncident | request | note | string |  | (max length 1000; nullable)
AiService | containAiIncident | response | id | string (uuid) |  | (read-only)
AiService | containAiIncident | response | reference | string | yes | (read-only)
AiService | containAiIncident | response | title | string | yes
AiService | containAiIncident | response | kind | enum (governance, operational, both)
AiService | containAiIncident | response | severity | enum (low, medium, high, critical) | yes
AiService | containAiIncident | response | status | enum (open, contained, investigating, remediating, closed) | yes | (read-only)
AiService | containAiIncident | response | capabilityKeys | array of string
AiService | containAiIncident | response | alertIds | array of string (uuid)
AiService | containAiIncident | response | operationalIncidentRef | string |  | The linked operational incident, where both apply (AIC-250). (nullable)
AiService | containAiIncident | response | containment | array of object |  | (read-only)
AiService | containAiIncident | response | containment[].action | string
AiService | containAiIncident | response | containment[].targetRef | string
AiService | containAiIncident | response | containment[].at | string (date-time)
AiService | containAiIncident | response | containment[].byPrincipalId | string (uuid)
AiService | containAiIncident | response | rootCause | string |  | (nullable)
AiService | containAiIncident | response | remediation | string |  | (nullable)
AiService | containAiIncident | response | ownerPrincipalId | string (uuid) |  | (nullable)
AiService | containAiIncident | response | openedAt | string (date-time) |  | (read-only)
AiService | containAiIncident | response | containedAt | string (date-time) |  | (read-only; nullable)
AiService | containAiIncident | response | closedAt | string (date-time) |  | (read-only; nullable)
AiService | containAiIncident | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | containAiIncident | param (path) | incidentId | string (uuid) | yes
AiService | containAiIncident | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | copyPriceList | request | code | string | yes | (max length 64)
CatalogueService | copyPriceList | request | name | string | yes | (max length 200)
CatalogueService | copyPriceList | request | adjustmentPercent | number |  | Applied to every copied price.
CatalogueService | copyPriceList | request | roundTo | string |  | Round adjusted prices to this increment, e.g. (pattern ^\d+(\.\d{1,4})?$)
CatalogueService | copyPriceList | request | validFrom | string (date-time)
CatalogueService | copyPriceList | request | validTo | string (date-time)
CatalogueService | copyPriceList | response | priceList | PriceList
CatalogueService | copyPriceList | response | priceList.id | string (uuid) | yes
CatalogueService | copyPriceList | response | priceList.code | string | yes
CatalogueService | copyPriceList | response | priceList.name | string | yes
CatalogueService | copyPriceList | response | priceList.venueId | string (uuid) | yes
CatalogueService | copyPriceList | response | priceList.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | copyPriceList | response | priceList.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | copyPriceList | response | priceList.channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | copyPriceList | response | priceList.validFrom | string (date-time) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.validTo | string (date-time) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | copyPriceList | response | priceList.description | string |  | Price list master fields (29 September, data model DM3), set with setPriceListMaster (ADM-058). (nullable)
CatalogueService | copyPriceList | response | priceList.priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | copyPriceList | response | priceList.status | object |  | (default active)
CatalogueService | copyPriceList | response | priceList.ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.tags | array of string
CatalogueService | copyPriceList | response | priceList.legalEntityId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.brand | string |  | (max length 100; nullable)
CatalogueService | copyPriceList | response | priceList.businessUnit | string |  | (max length 100; nullable)
CatalogueService | copyPriceList | response | priceList.countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | copyPriceList | response | priceList.marketCode | string |  | (max length 40; nullable)
CatalogueService | copyPriceList | response | priceList.scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | copyPriceList | response | priceList.defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.allowOverrides | boolean |  | (default False)
CatalogueService | copyPriceList | response | priceList.allowInheritance | boolean |  | (default True)
CatalogueService | copyPriceList | response | priceList.allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | copyPriceList | response | priceList.allowProductSpecificRates | boolean |  | (default True)
CatalogueService | copyPriceList | response | priceList.clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | copyPriceList | response | copiedPriceCount | integer
CatalogueService | copyPriceList | param (path) | priceListId | string (uuid) | yes
CatalogueService | copyPriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | createAccessPoint | request | code | string | yes | (max length 64)
AccessService | createAccessPoint | request | name | string | yes | (max length 200)
AccessService | createAccessPoint | request | venueId | string (uuid) | yes
AccessService | createAccessPoint | request | direction | Direction: enum (entry, exit, reentry, crossover) | yes
AccessService | createAccessPoint | request | antiPassbackEnabled | boolean |  | (default False)
AccessService | createAccessPoint | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAccessPoint | request | driver | string
AccessService | createAccessPoint | response | id | string (uuid) | yes
AccessService | createAccessPoint | response | code | string | yes
AccessService | createAccessPoint | response | name | string | yes
AccessService | createAccessPoint | response | venueId | string (uuid) | yes
AccessService | createAccessPoint | response | scopePath | string
AccessService | createAccessPoint | response | externalCredentialSources | object |  | BL-108.
AccessService | createAccessPoint | response | scanAnomalyRules | object |  | BL-104.
AccessService | createAccessPoint | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | createAccessPoint | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | createAccessPoint | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | createAccessPoint | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | createAccessPoint | response | antiPassbackEnabled | boolean
AccessService | createAccessPoint | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | createAccessPoint | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | createAccessPoint | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | createAccessPoint | response | geofence.latitude | number
AccessService | createAccessPoint | response | geofence.longitude | number
AccessService | createAccessPoint | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | createAccessPoint | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | createAccessPoint | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | createAccessPoint | response | isActive | boolean | yes
AccessService | createAccessPoint | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | createAccessPoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createAccount | request | code | string | yes | (max length 64; pattern ^[A-Za-z0-9._-]+$)
LedgerService | createAccount | request | externalCode | string |  | (max length 64)
LedgerService | createAccount | request | name | string | yes | (max length 200)
LedgerService | createAccount | request | type | AccountType: enum (asset, liability, equity, revenue, expense) | yes
LedgerService | createAccount | request | parentId | string (uuid)
LedgerService | createAccount | request | legalEntityId | string (uuid) | yes
LedgerService | createAccount | request | isPostable | boolean |  | (default True)
LedgerService | createAccount | request | isSuspense | boolean |  | See Account.isSuspense. (default False)
LedgerService | createAccount | request | subType | string |  | See Account.subType. (nullable)
LedgerService | createAccount | request | tags | array of string |  | See Account.tags.
LedgerService | createAccount | request | notes | string |  | See Account.notes. (nullable)
LedgerService | createAccount | response | id | string (uuid) | yes
LedgerService | createAccount | response | code | string | yes | (max length 64)
LedgerService | createAccount | response | externalCode | string |  | Code in the client's own chart. (nullable)
LedgerService | createAccount | response | isSuspense | boolean |  | 5.7.x. (default False)
LedgerService | createAccount | response | subType | string |  | 5.7.27. (nullable)
LedgerService | createAccount | response | tags | array of string |  | How a venue groups accounts for its own reporting.
LedgerService | createAccount | response | notes | string |  | 5.7.27. (nullable)
LedgerService | createAccount | response | name | string | yes | (max length 200)
LedgerService | createAccount | response | type | AccountType: enum (asset, liability, equity, revenue, expense) | yes
LedgerService | createAccount | response | parentId | string (uuid) |  | (nullable)
LedgerService | createAccount | response | legalEntityId | string (uuid) | yes
LedgerService | createAccount | response | currency | string |  | (pattern ^[A-Z]{3}$)
LedgerService | createAccount | response | isPostable | boolean | yes | False for parent accounts, which aggregate only.
LedgerService | createAccount | response | isActive | boolean | yes
LedgerService | createAccount | response | balance | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | createAccount | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | createAccount | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | createAccount | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | createAccount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | createAdmissionRules | request | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | createAdmissionRules | request | code | string | yes | (max length 64)
AccessService | createAdmissionRules | request | perProductRules | object |  | BL-059.
AccessService | createAdmissionRules | request | name | string | yes | (max length 200)
AccessService | createAdmissionRules | request | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | createAdmissionRules | request | closeMinutesAfter | integer | yes
AccessService | createAdmissionRules | request | maxDurationMinutes | integer |  | (nullable)
AccessService | createAdmissionRules | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAdmissionRules | request | maxReentries | integer |  | (nullable)
AccessService | createAdmissionRules | request | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | createAdmissionRules | request | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | createAdmissionRules | request | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | createAdmissionRules | request | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | createAdmissionRules | request | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | createAdmissionRules | request | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | createAdmissionRules | request | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | createAdmissionRules | request | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | createAdmissionRules | request | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | createAdmissionRules | request | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | createAdmissionRules | request | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | createAdmissionRules | request | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | createAdmissionRules | request | validity.from | string (date)
AccessService | createAdmissionRules | request | validity.to | string (date) |  | Inclusive.
AccessService | createAdmissionRules | request | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | createAdmissionRules | request | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | createAdmissionRules | request | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | createAdmissionRules | request | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | createAdmissionRules | request | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | createAdmissionRules | request | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | createAdmissionRules | request | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | createAdmissionRules | request | crossover.sameDayOnly | boolean |  | (default True)
AccessService | createAdmissionRules | request | crossover.differentDayAccess | boolean |  | (default False)
AccessService | createAdmissionRules | request | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | createAdmissionRules | request | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | request | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | request | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | createAdmissionRules | request | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | createAdmissionRules | request | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | createAdmissionRules | request | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | createAdmissionRules | request | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | createAdmissionRules | request | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | createAdmissionRules | request | scopePath | string |  | The partition key (ADR-0005).
AccessService | createAdmissionRules | response | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | createAdmissionRules | response | code | string | yes | (max length 64)
AccessService | createAdmissionRules | response | perProductRules | object |  | BL-059.
AccessService | createAdmissionRules | response | name | string | yes | (max length 200)
AccessService | createAdmissionRules | response | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | createAdmissionRules | response | closeMinutesAfter | integer | yes
AccessService | createAdmissionRules | response | maxDurationMinutes | integer |  | (nullable)
AccessService | createAdmissionRules | response | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAdmissionRules | response | maxReentries | integer |  | (nullable)
AccessService | createAdmissionRules | response | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | createAdmissionRules | response | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | createAdmissionRules | response | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | createAdmissionRules | response | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | createAdmissionRules | response | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | createAdmissionRules | response | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | createAdmissionRules | response | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | createAdmissionRules | response | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | createAdmissionRules | response | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | createAdmissionRules | response | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | createAdmissionRules | response | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | createAdmissionRules | response | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | createAdmissionRules | response | validity.from | string (date)
AccessService | createAdmissionRules | response | validity.to | string (date) |  | Inclusive.
AccessService | createAdmissionRules | response | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | createAdmissionRules | response | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | createAdmissionRules | response | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | createAdmissionRules | response | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | createAdmissionRules | response | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | createAdmissionRules | response | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | createAdmissionRules | response | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | createAdmissionRules | response | crossover.sameDayOnly | boolean |  | (default True)
AccessService | createAdmissionRules | response | crossover.differentDayAccess | boolean |  | (default False)
AccessService | createAdmissionRules | response | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | createAdmissionRules | response | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | response | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | response | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | createAdmissionRules | response | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | createAdmissionRules | response | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | createAdmissionRules | response | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | createAdmissionRules | response | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | createAdmissionRules | response | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | createAdmissionRules | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | createAdmissionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiConversation | request | module | object | yes | Which part of the platform the conversation is about (8.4.1).
AiService | createAiConversation | request | locale | string |  | 8.4.3.
AiService | createAiConversation | response | id | string (uuid) | yes
AiService | createAiConversation | response | principalId | string (uuid) | yes
AiService | createAiConversation | response | scopePath | string
AiService | createAiConversation | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
AiService | createAiConversation | response | locale | string
AiService | createAiConversation | response | messageCount | integer
AiService | createAiConversation | response | startedAt | string (date-time) | yes
AiService | createAiConversation | response | lastMessageAt | string (date-time)
AiService | createAiConversation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiGovernancePolicyDraft | request | policyId | string (uuid) |  | An existing policy to draft the next version of. (nullable)
AiService | createAiGovernancePolicyDraft | request | policyKey | string |  | Required for a new policy. (nullable)
AiService | createAiGovernancePolicyDraft | request | name | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | request | kind | enum (action, data, scope, autonomy, approval, environment) |  | (nullable)
AiService | createAiGovernancePolicyDraft | request | capabilityKeys | array of string
AiService | createAiGovernancePolicyDraft | request | rules | array of AiGovernanceRule | yes | (min items 1)
AiService | createAiGovernancePolicyDraft | request | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | createAiGovernancePolicyDraft | request | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | createAiGovernancePolicyDraft | request | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | createAiGovernancePolicyDraft | request | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | createAiGovernancePolicyDraft | request | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | createAiGovernancePolicyDraft | request | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | createAiGovernancePolicyDraft | request | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | createAiGovernancePolicyDraft | request | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | createAiGovernancePolicyDraft | request | changeNote | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | response | id | string (uuid) |  | (read-only)
AiService | createAiGovernancePolicyDraft | response | policyId | string (uuid) | yes
AiService | createAiGovernancePolicyDraft | response | version | integer | yes | (min 1)
AiService | createAiGovernancePolicyDraft | response | status | enum (draft, simulated, published, superseded) | yes
AiService | createAiGovernancePolicyDraft | response | rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | createAiGovernancePolicyDraft | response | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | createAiGovernancePolicyDraft | response | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | createAiGovernancePolicyDraft | response | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | createAiGovernancePolicyDraft | response | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | createAiGovernancePolicyDraft | response | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | createAiGovernancePolicyDraft | response | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | createAiGovernancePolicyDraft | response | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | createAiGovernancePolicyDraft | response | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | createAiGovernancePolicyDraft | response | changeNote | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | response | simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | createAiGovernancePolicyDraft | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | supersededAt | string (date-time) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createAiGovernancePolicyDraft | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiPolicyException | request | id | string (uuid) |  | (read-only)
AiService | createAiPolicyException | request | policyId | string (uuid) | yes
AiService | createAiPolicyException | request | capabilityKey | string |  | (nullable)
AiService | createAiPolicyException | request | reason | string | yes | (max length 2000)
AiService | createAiPolicyException | request | compensatingControls | array of string
AiService | createAiPolicyException | request | startsAt | string (date-time) |  | (nullable)
AiService | createAiPolicyException | request | expiresAt | string (date-time) | yes | Required.
AiService | createAiPolicyException | request | status | enum (active, expired, revoked) |  | (read-only)
AiService | createAiPolicyException | request | approvedByPrincipalId | string (uuid) |  | (read-only)
AiService | createAiPolicyException | request | revokedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | createAiPolicyException | request | revokedAt | string (date-time) |  | (read-only; nullable)
AiService | createAiPolicyException | request | revokeReason | string |  | (read-only; nullable)
AiService | createAiPolicyException | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createAiPolicyException | response | id | string (uuid) |  | (read-only)
AiService | createAiPolicyException | response | policyId | string (uuid) | yes
AiService | createAiPolicyException | response | capabilityKey | string |  | (nullable)
AiService | createAiPolicyException | response | reason | string | yes | (max length 2000)
AiService | createAiPolicyException | response | compensatingControls | array of string
AiService | createAiPolicyException | response | startsAt | string (date-time) |  | (nullable)
AiService | createAiPolicyException | response | expiresAt | string (date-time) | yes | Required.
AiService | createAiPolicyException | response | status | enum (active, expired, revoked) |  | (read-only)
AiService | createAiPolicyException | response | approvedByPrincipalId | string (uuid) |  | (read-only)
AiService | createAiPolicyException | response | revokedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | createAiPolicyException | response | revokedAt | string (date-time) |  | (read-only; nullable)
AiService | createAiPolicyException | response | revokeReason | string |  | (read-only; nullable)
AiService | createAiPolicyException | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createAiPolicyException | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createApiClient | request | id | string (uuid) | yes | (read-only)
PlatformService | createApiClient | request | developerId | string (uuid) | yes
PlatformService | createApiClient | request | name | string | yes
PlatformService | createApiClient | request | clientId | string |  | (read-only)
PlatformService | createApiClient | request | environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | createApiClient | request | scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | createApiClient | request | issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | createApiClient | request | certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | createApiClient | request | credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | createApiClient | request | expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | createApiClient | request | allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | createApiClient | request | ipAllowList | array of string |  | 13.1.38.
PlatformService | createApiClient | request | status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | createApiClient | request | lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | createApiClient | response | client | ApiClient |  | CF-135a.
PlatformService | createApiClient | response | client.id | string (uuid) | yes | (read-only)
PlatformService | createApiClient | response | client.developerId | string (uuid) | yes
PlatformService | createApiClient | response | client.name | string | yes
PlatformService | createApiClient | response | client.clientId | string |  | (read-only)
PlatformService | createApiClient | response | client.environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | createApiClient | response | client.scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | createApiClient | response | client.issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | createApiClient | response | client.certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | createApiClient | response | client.credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | createApiClient | response | client.expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | createApiClient | response | client.allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | createApiClient | response | client.ipAllowList | array of string |  | 13.1.38.
PlatformService | createApiClient | response | client.status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | createApiClient | response | client.lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | createApiClient | response | clientSecret | string (password)
PlatformService | createApiClient | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createApprovalDelegation | request | id | string (uuid) |  | (read-only)
TenancyService | createApprovalDelegation | request | delegatorPrincipalId | string (uuid) | yes | A principal id (identity.Principal.id).
TenancyService | createApprovalDelegation | request | delegatePrincipalId | string (uuid) | yes | A principal id, resolved to a name the same way as delegatorPrincipalId.
TenancyService | createApprovalDelegation | request | kinds | array of ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) |  | Absent means everything the delegator may approve.
TenancyService | createApprovalDelegation | request | maxAmount | object |  | A delegate may be given less authority than the delegator, never more.
TenancyService | createApprovalDelegation | request | maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalDelegation | request | maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalDelegation | request | maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalDelegation | request | from | string (date-time) | yes
TenancyService | createApprovalDelegation | request | to | string (date-time) | yes | Required.
TenancyService | createApprovalDelegation | request | reason | string
TenancyService | createApprovalDelegation | request | isActive | boolean |  | (read-only)
TenancyService | createApprovalDelegation | request | scopePath | string |  | The partition key (ADR-0005).
TenancyService | createApprovalDelegation | response | id | string (uuid) |  | (read-only)
TenancyService | createApprovalDelegation | response | delegatorPrincipalId | string (uuid) | yes | A principal id (identity.Principal.id).
TenancyService | createApprovalDelegation | response | delegatePrincipalId | string (uuid) | yes | A principal id, resolved to a name the same way as delegatorPrincipalId.
TenancyService | createApprovalDelegation | response | kinds | array of ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) |  | Absent means everything the delegator may approve.
TenancyService | createApprovalDelegation | response | maxAmount | object |  | A delegate may be given less authority than the delegator, never more.
TenancyService | createApprovalDelegation | response | maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalDelegation | response | maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalDelegation | response | maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalDelegation | response | from | string (date-time) | yes
TenancyService | createApprovalDelegation | response | to | string (date-time) | yes | Required.
TenancyService | createApprovalDelegation | response | reason | string
TenancyService | createApprovalDelegation | response | isActive | boolean |  | (read-only)
TenancyService | createApprovalDelegation | response | scopePath | string |  | The partition key (ADR-0005).
TenancyService | createApprovalDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createApprovalRequest | request | id | string (uuid) | yes
TenancyService | createApprovalRequest | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | createApprovalRequest | request | subjectContract | string | yes | Which contract owns the thing being approved.
TenancyService | createApprovalRequest | request | subjectType | string | yes
TenancyService | createApprovalRequest | request | subjectId | string | yes | A reference, never a copy.
TenancyService | createApprovalRequest | request | scopePath | string | yes
TenancyService | createApprovalRequest | request | summary | string | yes | What the approver sees in their queue before opening it. (max length 300)
TenancyService | createApprovalRequest | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | createApprovalRequest | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalRequest | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalRequest | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalRequest | request | attributes | object
TenancyService | createApprovalRequest | request | justification | string |  | (max length 1000)
TenancyService | createApprovalRequest | request | isDraft | boolean |  | True saves the request at draft without routing it; submitApprovalRequest sends it later (decided 28 September, audit R129). (default False)
TenancyService | createApprovalRequest | response | id | string | yes
TenancyService | createApprovalRequest | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | createApprovalRequest | response | rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | createApprovalRequest | response | outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | createApprovalRequest | response | allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | createApprovalRequest | response | reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | createApprovalRequest | response | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | createApprovalRequest | response | subjectContract | string
TenancyService | createApprovalRequest | response | subjectType | string
TenancyService | createApprovalRequest | response | subjectId | string
TenancyService | createApprovalRequest | response | scopePath | string
TenancyService | createApprovalRequest | response | summary | string
TenancyService | createApprovalRequest | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | createApprovalRequest | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalRequest | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalRequest | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalRequest | response | justification | string |  | (nullable)
TenancyService | createApprovalRequest | response | requestedByPrincipalId | string (uuid) | yes
TenancyService | createApprovalRequest | response | matrixVersion | integer
TenancyService | createApprovalRequest | response | mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | createApprovalRequest | response | currentLevel | integer
TenancyService | createApprovalRequest | response | totalLevels | integer
TenancyService | createApprovalRequest | response | pendingApprovers | array of object
TenancyService | createApprovalRequest | response | pendingApprovers[].principalId | string (uuid)
TenancyService | createApprovalRequest | response | pendingApprovers[].displayName | string
TenancyService | createApprovalRequest | response | pendingApprovers[].isDelegate | boolean
TenancyService | createApprovalRequest | response | decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | createApprovalRequest | response | decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | createApprovalRequest | response | decisions[].level | integer | yes
TenancyService | createApprovalRequest | response | decisions[].principalId | string (uuid) | yes
TenancyService | createApprovalRequest | response | decisions[].displayName | string
TenancyService | createApprovalRequest | response | decisions[].isDelegate | boolean
TenancyService | createApprovalRequest | response | decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].decision | enum (approve, reject) | yes
TenancyService | createApprovalRequest | response | decisions[].comment | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].reason | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].usedMfa | boolean
TenancyService | createApprovalRequest | response | decisions[].signatureRef | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].decidedAt | string (date-time) | yes
TenancyService | createApprovalRequest | response | escalations | array of object |  | 11.1.48.
TenancyService | createApprovalRequest | response | escalations[].at | string (date-time)
TenancyService | createApprovalRequest | response | escalations[].reason | string
TenancyService | createApprovalRequest | response | escalations[].fromLevel | integer
TenancyService | createApprovalRequest | response | escalations[].toLevel | integer
TenancyService | createApprovalRequest | response | escalations[].wasAutomatic | boolean
TenancyService | createApprovalRequest | response | resubmittedFromId | string |  | (nullable)
TenancyService | createApprovalRequest | response | reopenedFromId | string |  | (nullable)
TenancyService | createApprovalRequest | response | slaDueAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | slaBreached | boolean
TenancyService | createApprovalRequest | response | expiresAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | requestedAt | string (date-time) | yes
TenancyService | createApprovalRequest | response | completedAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | createApprovalRequest | response | aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | createApprovalRequest | response | aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | createApprovalRequest | response | aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion.action | enum (escalate, addBackupApprover, none)
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion.reason | string |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | createApprovalRequest | response | aiAssessment.signals[].code | string
TenancyService | createApprovalRequest | response | aiAssessment.signals[].contribution | number
TenancyService | createApprovalRequest | response | aiAssessment.signals[].detail | string |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | createApprovalRequest | response | aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | createApprovalRequest | response | aiAssessment.assessedAt | string (date-time)
TenancyService | createApprovalRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createBanner | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createBanner | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | request | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | request | imageAssetRef | string (uuid) | yes
WhiteLabelService | createBanner | request | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | createBanner | request | linkTarget | LinkTarget
WhiteLabelService | createBanner | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createBanner | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createBanner | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createBanner | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.productId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.eventId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.url | string
WhiteLabelService | createBanner | request | startsAt | string (date-time) | yes
WhiteLabelService | createBanner | request | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createBanner | request | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | createBanner | request | sortOrder | integer
WhiteLabelService | createBanner | request | isActive | boolean
WhiteLabelService | createBanner | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createBanner | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | response | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | response | imageAssetRef | string (uuid) | yes
WhiteLabelService | createBanner | response | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | createBanner | response | linkTarget | LinkTarget
WhiteLabelService | createBanner | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createBanner | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createBanner | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createBanner | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.productId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.eventId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.url | string
WhiteLabelService | createBanner | response | startsAt | string (date-time) | yes
WhiteLabelService | createBanner | response | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createBanner | response | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | createBanner | response | sortOrder | integer
WhiteLabelService | createBanner | response | isActive | boolean
WhiteLabelService | createBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createBookingFlowDefinition | request | id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | createBookingFlowDefinition | request | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | createBookingFlowDefinition | request | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | createBookingFlowDefinition | request | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | createBookingFlowDefinition | request | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | createBookingFlowDefinition | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | createBookingFlowDefinition | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createBookingFlowDefinition | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | createBookingFlowDefinition | request | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | request | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | createBookingFlowDefinition | request | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | createBookingFlowDefinition | request | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | createBookingFlowDefinition | request | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | createBookingFlowDefinition | request | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | createBookingFlowDefinition | request | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | createBookingFlowDefinition | request | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createBookingFlowDefinition | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | createBookingFlowDefinition | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | createBookingFlowDefinition | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | createBookingFlowDefinition | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | createBookingFlowDefinition | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | createBookingFlowDefinition | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | createBookingFlowDefinition | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createBookingFlowDefinition | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | createBookingFlowDefinition | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | createBookingFlowDefinition | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | createBookingFlowDefinition | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | createBookingFlowDefinition | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | createBookingFlowDefinition | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | createBookingFlowDefinition | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | createBookingFlowDefinition | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createBookingFlowDefinition | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | param (path) | venueId | string (uuid) | yes
WhiteLabelService | createBookingFlowDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createBulkProductCatalogue | request | rowCorrections | array of object |  | Corrections to individual records before re-validating
CatalogueService | createBulkProductCatalogue | request | rowCorrections[].row | integer
CatalogueService | createBulkProductCatalogue | request | rowCorrections[].field | string
CatalogueService | createBulkProductCatalogue | request | rowCorrections[].value | string
CatalogueService | createBulkProductCatalogue | request | excludedRows | array of integer |  | Rows to exclude
CatalogueService | createBulkProductCatalogue | request | jobId | string (uuid) |  | Existing job to re-validate or commit; empty to start a new one (nullable)
CatalogueService | createBulkProductCatalogue | request | fileId | string |  | Uploaded source file id
CatalogueService | createBulkProductCatalogue | request | sourceFormat | enum (excel, csv, spreadsheetTemplate, catalogueFile, pdfBrochure, productDocument) |  | Supported source (pack p.6)
CatalogueService | createBulkProductCatalogue | request | targetVenueId | string (uuid) |  | Target venue/site
CatalogueService | createBulkProductCatalogue | request | defaultTemplateId | string (uuid) |  | Default product configuration (template) applied to every row (nullable)
CatalogueService | createBulkProductCatalogue | request | columnMapping | array of object |  | Source columns mapped to TICVAI fields
CatalogueService | createBulkProductCatalogue | request | columnMapping[].sourceColumn | string
CatalogueService | createBulkProductCatalogue | request | columnMapping[].targetField | string
CatalogueService | createBulkProductCatalogue | request | mode | enum (validate, commit) |  | validate previews without creating; commit runs the import (decided 29 September, readiness close-out)
CatalogueService | createBulkProductCatalogue | response | previewProducts | array of object |  | Products that the import will create, previewed before creation; all are created in draft
CatalogueService | createBulkProductCatalogue | response | previewProducts[].row | integer
CatalogueService | createBulkProductCatalogue | response | previewProducts[].productName | string
CatalogueService | createBulkProductCatalogue | response | previewProducts[].productType | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | createBulkProductCatalogue | response | previewProducts[].excluded | boolean
CatalogueService | createBulkProductCatalogue | response | previewProducts[].aiProposed | boolean
CatalogueService | createBulkProductCatalogue | response | validationIssues | array of object |  | Record errors to correct before import (decided 29 September, readiness close-out)
CatalogueService | createBulkProductCatalogue | response | validationIssues[].row | integer
CatalogueService | createBulkProductCatalogue | response | validationIssues[].field | string
CatalogueService | createBulkProductCatalogue | response | validationIssues[].code | enum (missingRequired, invalidValue, unknownReference, duplicate, unmappedColumn)
CatalogueService | createBulkProductCatalogue | response | validationIssues[].message | string
CatalogueService | createBulkProductCatalogue | response | excludedRows | array of integer |  | Rows excluded from the import
CatalogueService | createBulkProductCatalogue | response | jobId | string (uuid) |  | Import job id
CatalogueService | createBulkProductCatalogue | response | status | string |  | Job status: parsing, previewReady, committing, committed or failed (as CatalogueImportJob)
CatalogueService | createBulkProductCatalogue | response | sourceFormat | enum (excel, csv, spreadsheetTemplate, catalogueFile, pdfBrochure, productDocument) |  | Supported source (pack p.6)
CatalogueService | createBulkProductCatalogue | response | targetVenueId | string (uuid) |  | Target venue/site
CatalogueService | createBulkProductCatalogue | response | parsedCount | integer |  | Records parsed
CatalogueService | createBulkProductCatalogue | response | createdCount | integer |  | Products created (after commit)
CatalogueService | createBulkProductCatalogue | response | failedCount | integer |  | Records failed
CatalogueService | createBulkProductCatalogue | response | errorReportUrl | string (uri) |  | Downloadable error report (nullable)
CatalogueService | createBulkProductCatalogue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createBundle | request | code | string | yes | (max length 64)
CatalogueService | createBundle | request | name | string | yes | (max length 200)
CatalogueService | createBundle | request | description | string |  | (max length 1000)
CatalogueService | createBundle | request | venueId | string (uuid) | yes
CatalogueService | createBundle | request | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | createBundle | request | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | request | components | array of BundleComponent | yes | (min items 0)
CatalogueService | createBundle | request | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | request | components[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | createBundle | request | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | createBundle | request | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | createBundle | request | components[].quantity | integer | yes | (min 1)
CatalogueService | createBundle | request | components[].isOptional | boolean |  | (default False)
CatalogueService | createBundle | request | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | createBundle | request | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | createBundle | request | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | createBundle | request | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | createBundle | request | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | createBundle | request | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | createBundle | request | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | request | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | createBundle | request | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | createBundle | request | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | createBundle | request | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | createBundle | request | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | request | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | createBundle | request | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | createBundle | request | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | createBundle | request | allocation | object | yes
CatalogueService | createBundle | request | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | createBundle | request | allocation.components | array of AllocationComponent | yes
CatalogueService | createBundle | request | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | request | allocation.components[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | createBundle | request | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | request | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | createBundle | request | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | createBundle | request | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | createBundle | request | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | createBundle | request | validFrom | string (date-time)
CatalogueService | createBundle | request | validTo | string (date-time)
CatalogueService | createBundle | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | createBundle | request | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | createBundle | request | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | createBundle | request | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | createBundle | request | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | createBundle | request | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | createBundle | response | code | string | yes | (max length 64)
CatalogueService | createBundle | response | name | string | yes | (max length 200)
CatalogueService | createBundle | response | description | string |  | (max length 1000)
CatalogueService | createBundle | response | venueId | string (uuid) | yes
CatalogueService | createBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | createBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | createBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | createBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | createBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | createBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | createBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | createBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | createBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | createBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | createBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | createBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | createBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | createBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | createBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | createBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | createBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | createBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | createBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | createBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | createBundle | response | allocation | object | yes
CatalogueService | createBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | createBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | createBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | createBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | createBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | createBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | createBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | createBundle | response | validFrom | string (date-time)
CatalogueService | createBundle | response | validTo | string (date-time)
CatalogueService | createBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | createBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | createBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | createBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | createBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | createBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | createBundle | response | id | string (uuid) | yes
CatalogueService | createBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price.
CatalogueService | createBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | response | savingsPercentage | number
CatalogueService | createBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | createBundle | response | isActive | boolean | yes
CatalogueService | createBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createCampaign | request | name | string | yes | (max length 200)
MarketingService | createCampaign | request | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | createCampaign | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCampaign | request | venueId | string (uuid)
MarketingService | createCampaign | request | segmentId | string (uuid) | yes
MarketingService | createCampaign | request | content | CampaignContent | yes
MarketingService | createCampaign | request | content.templateId | string (uuid) | yes
MarketingService | createCampaign | request | content.subjectOverride | object
MarketingService | createCampaign | request | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | createCampaign | request | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | createCampaign | request | trigger | CampaignTrigger
MarketingService | createCampaign | request | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | createCampaign | request | trigger.delayHours | integer
MarketingService | createCampaign | request | trigger.conditions | array of SegmentCriterion
MarketingService | createCampaign | request | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createCampaign | request | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createCampaign | request | trigger.conditions[].value | object
MarketingService | createCampaign | request | trigger.conditions[].values | array of object
MarketingService | createCampaign | request | scheduledFor | string (date-time)
MarketingService | createCampaign | request | consentPurpose | object |  | (default marketing)
MarketingService | createCampaign | request | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | createCampaign | request | sendWindow.startTime | string
MarketingService | createCampaign | request | sendWindow.endTime | string
MarketingService | createCampaign | request | sendWindow.timeZone | string
MarketingService | createCampaign | request | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | createCampaign | request | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | createCampaign | request | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | createCampaign | request | variants[].id | string (uuid) |  | (read-only)
MarketingService | createCampaign | request | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | createCampaign | request | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | createCampaign | request | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | createCampaign | request | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | createCampaign | request | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | createCampaign | request | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | createCampaign | request | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | createCampaign | request | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | createCampaign | request | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | createCampaign | request | abTest | object |  | How the variants are tested. (nullable)
MarketingService | createCampaign | request | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | createCampaign | request | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | createCampaign | request | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | createCampaign | request | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | createCampaign | request | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | createCampaign | request | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | createCampaign | response | name | string | yes | (max length 200)
MarketingService | createCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | createCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCampaign | response | venueId | string (uuid)
MarketingService | createCampaign | response | segmentId | string (uuid) | yes
MarketingService | createCampaign | response | content | CampaignContent | yes
MarketingService | createCampaign | response | content.templateId | string (uuid) | yes
MarketingService | createCampaign | response | content.subjectOverride | object
MarketingService | createCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | createCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | createCampaign | response | trigger | CampaignTrigger
MarketingService | createCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | createCampaign | response | trigger.delayHours | integer
MarketingService | createCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | createCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createCampaign | response | trigger.conditions[].value | object
MarketingService | createCampaign | response | trigger.conditions[].values | array of object
MarketingService | createCampaign | response | scheduledFor | string (date-time)
MarketingService | createCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | createCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | createCampaign | response | sendWindow.startTime | string
MarketingService | createCampaign | response | sendWindow.endTime | string
MarketingService | createCampaign | response | sendWindow.timeZone | string
MarketingService | createCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | createCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | createCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | createCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | createCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | createCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | createCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | createCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | createCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | createCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | createCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | createCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | createCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | createCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | createCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | createCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | createCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | createCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | createCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | createCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | createCampaign | response | id | string (uuid) | yes
MarketingService | createCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | createCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | createCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | createCampaign | response | isPaused | boolean
MarketingService | createCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | createCampaign | response | createdAt | string (date-time) | yes
MarketingService | createCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | createCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | createCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | createCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCart | request | venueId | string (uuid) | yes
OrderService | createCart | request | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | createCart | request | subjectId | string (uuid) |  | (nullable)
OrderService | createCart | request | locale | string
OrderService | createCart | response | id | string (uuid) | yes
OrderService | createCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | createCart | response | venueId | string (uuid) | yes
OrderService | createCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | createCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | createCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | createCart | response | lines | array of CartLine | yes
OrderService | createCart | response | lines[].id | string (uuid) | yes
OrderService | createCart | response | lines[].variantId | string (uuid) | yes
OrderService | createCart | response | lines[].productName | string |  | (read-only)
OrderService | createCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | createCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | createCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | createCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | createCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | createCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | createCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | createCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | createCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | createCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | createCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | createCart | response | conflicts | array of CartConflict
OrderService | createCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | createCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | createCart | response | conflicts[].message | string
OrderService | createCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | createCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | createCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | createCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | createCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | createCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | createCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | createCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | createCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | createCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | createCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | createCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | createCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | createCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | createCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | createCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | createCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | createCart | response | extensionsUsed | integer |  | (read-only)
OrderService | createCart | response | maxExtensions | integer |  | (read-only)
OrderService | createCart | response | locale | string
OrderService | createCart | response | createdAt | string (date-time)
OrderService | createCart | response | updatedAt | string (date-time)
OrderService | createCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createCase | request | id | string (uuid) | yes
MarketingService | createCase | request | subjectId | string (uuid)
MarketingService | createCase | request | subject | string | yes | (max length 200)
MarketingService | createCase | request | description | string | yes | (max length 10000)
MarketingService | createCase | request | categoryId | string (uuid)
MarketingService | createCase | request | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | createCase | request | priority | object |  | (default normal)
MarketingService | createCase | request | kind | CaseKind: enum (lostProperty, complaint, question, accessibility, refundRequest, other) |  | What the guest says the case is about, in their words rather than the venue's taxonomy — raiseMyCase asks for it and categoryId is what staff file it under.
MarketingService | createCase | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCase | request | venueId | string (uuid)
MarketingService | createCase | request | relatedOrderId | string
MarketingService | createCase | request | attachmentRefs | array of string |  | Stored on the opening CaseMessage, not on the case.
MarketingService | createCase | request | recordedAt | string (date-time) | yes | Device time the case was raised.
MarketingService | createCase | response | id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | createCase | response | caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | createCase | response | subjectId | string (uuid) |  | (nullable)
MarketingService | createCase | response | guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | createCase | response | subject | string | yes | The case's one-line title, not a person.
MarketingService | createCase | response | kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | createCase | response | channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | createCase | response | recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | createCase | response | syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | createCase | response | categoryId | string (uuid) |  | (nullable)
MarketingService | createCase | response | queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | createCase | response | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | createCase | response | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | createCase | response | priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | createCase | response | assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | createCase | response | venueId | string (uuid) |  | (nullable)
MarketingService | createCase | response | relatedOrderId | string |  | (nullable)
MarketingService | createCase | response | slaDueAt | string (date-time) |  | (nullable)
MarketingService | createCase | response | isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | createCase | response | slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | createCase | response | escalationCount | integer
MarketingService | createCase | response | createdAt | string (date-time) | yes
MarketingService | createCase | response | resolvedAt | string (date-time) |  | (nullable)
MarketingService | createCase | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | request | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | request | kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | createCashMovement | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | request | denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | createCashMovement | request | denominations[].id | string (uuid)
OrderService | createCashMovement | request | denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | createCashMovement | request | denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | createCashMovement | request | denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | createCashMovement | request | denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | createCashMovement | request | denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | createCashMovement | request | denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | createCashMovement | request | denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | request | denominations[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | request | denominations[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | request | denominations[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | request | denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | createCashMovement | request | denominations[].countedAt | string (date-time)
OrderService | createCashMovement | request | denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | createCashMovement | request | reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | createCashMovement | request | reason | string |  | (max length 500)
OrderService | createCashMovement | request | recordedAt | string (date-time) | yes
OrderService | createCashMovement | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | response | kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | createCashMovement | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | response | denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | createCashMovement | response | denominations[].id | string (uuid)
OrderService | createCashMovement | response | denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | createCashMovement | response | denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | createCashMovement | response | denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | createCashMovement | response | denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | createCashMovement | response | denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | createCashMovement | response | denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | createCashMovement | response | denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | response | denominations[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | response | denominations[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | response | denominations[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | response | denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | createCashMovement | response | denominations[].countedAt | string (date-time)
OrderService | createCashMovement | response | denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | createCashMovement | response | reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | createCashMovement | response | reason | string |  | (max length 500)
OrderService | createCashMovement | response | recordedAt | string (date-time) | yes
OrderService | createCashMovement | response | shiftId | string (uuid) | yes
OrderService | createCashMovement | response | depositBoxId | string (uuid) |  | The box the cash moved in or out of. (nullable)
OrderService | createCashMovement | response | witnessPrincipalId | string (uuid) |  | The cashier who countersigned a withdrawal. (nullable)
OrderService | createCashMovement | response | withdrawalReason | object |  | (nullable)
OrderService | createCashMovement | response | authorisedByPrincipalId | string (uuid) | yes | The principal who authorised the movement, recorded for audit.
OrderService | createCashMovement | response | sequence | integer | yes | Monotonic within the shift.
OrderService | createCashMovement | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createCashMovement | param (path) | shiftId | string (uuid) | yes
OrderService | createCashMovement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createChallenge | request | id | string (uuid) | yes | (read-only)
MarketingService | createChallenge | request | name | string | yes
MarketingService | createChallenge | request | kind | enum (visit, spend, ride, collection, streak, referral, survey, social, …) | yes | What an entrant does to progress.
MarketingService | createChallenge | request | scope | enum (individual, family, group, team) |  | 22.6.7 and 22.6.8. (default individual)
MarketingService | createChallenge | request | goal | object | yes | What completes it.
MarketingService | createChallenge | request | goal.metric | string
MarketingService | createChallenge | request | goal.target | number
MarketingService | createChallenge | request | goal.withinDays | integer |  | (nullable)
MarketingService | createChallenge | request | eventId | string (uuid) |  | (nullable)
MarketingService | createChallenge | request | rewardKind | enum (badge, loyaltyPoints, walletCredit, voucher, entitlement, none) |  | 22.6.13.
MarketingService | createChallenge | request | rewardValue | integer |  | Points, for rewardKind: loyaltyPoints only. (min 1; nullable)
MarketingService | createChallenge | request | rewardAmount | object |  | The credit, for rewardKind: walletCredit only. (nullable)
MarketingService | createChallenge | request | rewardAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createChallenge | request | rewardAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createChallenge | request | rewardAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createChallenge | request | badgeAssetId | string (uuid) |  | (nullable)
MarketingService | createChallenge | request | startsAt | string (date-time)
MarketingService | createChallenge | request | endsAt | string (date-time) |  | (nullable)
MarketingService | createChallenge | request | status | enum (draft, active, paused, ended, archived) | yes | (read-only)
MarketingService | createChallenge | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createChallenge | response | id | string (uuid) | yes | (read-only)
MarketingService | createChallenge | response | name | string | yes
MarketingService | createChallenge | response | kind | enum (visit, spend, ride, collection, streak, referral, survey, social, …) | yes | What an entrant does to progress.
MarketingService | createChallenge | response | scope | enum (individual, family, group, team) |  | 22.6.7 and 22.6.8. (default individual)
MarketingService | createChallenge | response | goal | object | yes | What completes it.
MarketingService | createChallenge | response | goal.metric | string
MarketingService | createChallenge | response | goal.target | number
MarketingService | createChallenge | response | goal.withinDays | integer |  | (nullable)
MarketingService | createChallenge | response | eventId | string (uuid) |  | (nullable)
MarketingService | createChallenge | response | rewardKind | enum (badge, loyaltyPoints, walletCredit, voucher, entitlement, none) |  | 22.6.13.
MarketingService | createChallenge | response | rewardValue | integer |  | Points, for rewardKind: loyaltyPoints only. (min 1; nullable)
MarketingService | createChallenge | response | rewardAmount | object |  | The credit, for rewardKind: walletCredit only. (nullable)
MarketingService | createChallenge | response | rewardAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createChallenge | response | rewardAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createChallenge | response | rewardAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createChallenge | response | badgeAssetId | string (uuid) |  | (nullable)
MarketingService | createChallenge | response | startsAt | string (date-time)
MarketingService | createChallenge | response | endsAt | string (date-time) |  | (nullable)
MarketingService | createChallenge | response | status | enum (draft, active, paused, ended, archived) | yes | (read-only)
MarketingService | createChallenge | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createCollection | request | name | string | yes | (max length 200)
VenueOpsService | createCollection | request | description | string |  | (max length 1000)
VenueOpsService | createCollection | request | venueId | string (uuid)
VenueOpsService | createCollection | request | parentCollectionId | string (uuid)
VenueOpsService | createCollection | response | id | string (uuid) | yes
VenueOpsService | createCollection | response | name | string | yes | Unique per tenant (decided 28 September, audit R108).
VenueOpsService | createCollection | response | description | string |  | (nullable)
VenueOpsService | createCollection | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | response | parentCollectionId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | response | assetCount | integer | yes
VenueOpsService | createCollection | response | coverAssetId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createCommercialCampaign | request | venueId | string (uuid) | yes
CatalogueService | createCommercialCampaign | request | code | string |  | Unique at the venue when given. (max length 64; nullable)
CatalogueService | createCommercialCampaign | request | name | string | yes | (max length 200)
CatalogueService | createCommercialCampaign | request | description | string |  | (max length 1000; nullable)
CatalogueService | createCommercialCampaign | request | ownerPrincipalId | string (uuid) |  | The campaign (and budget) owner. (nullable)
CatalogueService | createCommercialCampaign | request | legalEntityId | string (uuid) |  | The business entity that funds and books the campaign. (nullable)
CatalogueService | createCommercialCampaign | request | validFrom | string (date-time) |  | (nullable)
CatalogueService | createCommercialCampaign | request | validTo | string (date-time) |  | (nullable)
CatalogueService | createCommercialCampaign | response | id | string (uuid) | yes | (read-only)
CatalogueService | createCommercialCampaign | response | venueId | string (uuid) | yes
CatalogueService | createCommercialCampaign | response | code | string |  | (max length 64; nullable)
CatalogueService | createCommercialCampaign | response | name | string | yes | (max length 200)
CatalogueService | createCommercialCampaign | response | description | string |  | (max length 1000; nullable)
CatalogueService | createCommercialCampaign | response | ownerPrincipalId | string (uuid) |  | The campaign (and budget) owner. (nullable)
CatalogueService | createCommercialCampaign | response | legalEntityId | string (uuid) |  | The business entity that funds and books the campaign. (nullable)
CatalogueService | createCommercialCampaign | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | createCommercialCampaign | response | validTo | string (date-time) |  | (nullable)
CatalogueService | createCommercialCampaign | response | budgets | array of CampaignBudget |  | The rows of promotions.campaign_budget, one per budget line.
CatalogueService | createCommercialCampaign | response | budgets[].id | string (uuid) |  | (read-only)
CatalogueService | createCommercialCampaign | response | budgets[].budgetType | enum (total, discount, reward, freeProduct) | yes | The spend this line caps (total campaign, discount, reward or free-product budget).
CatalogueService | createCommercialCampaign | response | budgets[].fundingSource | enum (venue, department, marketing, partner) |  | Who pays for it; partner is a co-funded (e.g. (nullable)
CatalogueService | createCommercialCampaign | response | budgets[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createCommercialCampaign | response | budgets[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCommercialCampaign | response | budgets[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCommercialCampaign | response | budgets[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCommercialCampaign | response | budgets[].scope | enum (entireCampaign, promotion, product, channel, partner, customerSegment) |  | What the line covers. (default entireCampaign)
CatalogueService | createCommercialCampaign | response | budgets[].scopeRef | string |  | The promotion, product, partner or segment id, or the SalesChannel value, that scope names. (nullable)
CatalogueService | createCommercialCampaign | response | budgets[].ownerPrincipalId | string (uuid) |  | The budget owner. (nullable)
CatalogueService | createCommercialCampaign | response | budgets[].costCentre | string |  | (max length 64; nullable)
CatalogueService | createCommercialCampaign | response | budgets[].department | string |  | (max length 100; nullable)
CatalogueService | createCommercialCampaign | response | budgets[].validFrom | string (date-time) |  | (nullable)
CatalogueService | createCommercialCampaign | response | budgets[].validTo | string (date-time) |  | (nullable)
CatalogueService | createCommercialCampaign | response | budgets[].thresholdPolicy | BudgetThresholdPolicy |  | The automatic actions as a budget line is consumed (Threshold Actions & Automatic Suspension).
CatalogueService | createCommercialCampaign | response | budgets[].thresholdPolicy.steps | array of object
CatalogueService | createCommercialCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createConsentQuestion | request | id | string (uuid) | yes | (read-only)
MarketingService | createConsentQuestion | request | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | createConsentQuestion | request | text | object | yes | The question as the guest reads it, per locale.
MarketingService | createConsentQuestion | request | helpText | object |  | (nullable)
MarketingService | createConsentQuestion | request | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | createConsentQuestion | request | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | createConsentQuestion | request | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | createConsentQuestion | request | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | createConsentQuestion | request | status | enum (active, retired) | yes | (default active)
MarketingService | createConsentQuestion | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createConsentQuestion | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | createConsentQuestion | response | id | string (uuid) | yes | (read-only)
MarketingService | createConsentQuestion | response | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | createConsentQuestion | response | text | object | yes | The question as the guest reads it, per locale.
MarketingService | createConsentQuestion | response | helpText | object |  | (nullable)
MarketingService | createConsentQuestion | response | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | createConsentQuestion | response | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | createConsentQuestion | response | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | createConsentQuestion | response | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | createConsentQuestion | response | status | enum (active, retired) | yes | (default active)
MarketingService | createConsentQuestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createConsentQuestion | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | createConsentQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentBlock | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentBlock | request | pageId | string (uuid) |  | (nullable)
WhiteLabelService | createContentBlock | request | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | createContentBlock | request | position | integer
WhiteLabelService | createContentBlock | request | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | createContentBlock | request | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | createContentBlock | request | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | createContentBlock | request | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | createContentBlock | request | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | createContentBlock | request | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | createContentBlock | request | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | createContentBlock | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentBlock | response | pageId | string (uuid) |  | (nullable)
WhiteLabelService | createContentBlock | response | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | createContentBlock | response | position | integer
WhiteLabelService | createContentBlock | response | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | createContentBlock | response | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | createContentBlock | response | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | createContentBlock | response | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | createContentBlock | response | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | createContentBlock | response | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | createContentBlock | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | createContentBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentPage | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentPage | request | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | createContentPage | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createContentPage | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | createContentPage | request | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | createContentPage | request | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | createContentPage | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createContentPage | request | categoryCode | string |  | (nullable)
WhiteLabelService | createContentPage | request | sortOrder | integer
WhiteLabelService | createContentPage | request | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | createContentPage | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentPage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentPage | response | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | createContentPage | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createContentPage | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | createContentPage | response | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | createContentPage | response | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | createContentPage | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createContentPage | response | categoryCode | string |  | (nullable)
WhiteLabelService | createContentPage | response | sortOrder | integer
WhiteLabelService | createContentPage | response | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | createContentPage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentPage | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | createCouponCampaign | request | code | string | yes | (max length 64)
CatalogueService | createCouponCampaign | request | name | string | yes | (max length 200)
CatalogueService | createCouponCampaign | request | venueId | string (uuid) | yes
CatalogueService | createCouponCampaign | request | discount | Discount | yes
CatalogueService | createCouponCampaign | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createCouponCampaign | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createCouponCampaign | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createCouponCampaign | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | createCouponCampaign | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | createCouponCampaign | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createCouponCampaign | request | conditions.variantIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.productKinds | array of string
CatalogueService | createCouponCampaign | request | conditions.categoryIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createCouponCampaign | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createCouponCampaign | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createCouponCampaign | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createCouponCampaign | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createCouponCampaign | request | conditions.daysOfWeek | array of integer
CatalogueService | createCouponCampaign | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createCouponCampaign | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createCouponCampaign | request | conditions.performanceIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createCouponCampaign | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createCouponCampaign | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | createCouponCampaign | request | isSingleUse | boolean |  | True generates individually redeemable codes. (default True)
CatalogueService | createCouponCampaign | request | maxRedemptionsPerCode | integer |  | (default 1)
CatalogueService | createCouponCampaign | request | validFrom | string (date-time) | yes
CatalogueService | createCouponCampaign | request | validTo | string (date-time)
CatalogueService | createCouponCampaign | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the codes are issued under, as the Coupon & Promo Code Builder names it. (nullable)
CatalogueService | createCouponCampaign | response | code | string | yes | (max length 64)
CatalogueService | createCouponCampaign | response | name | string | yes | (max length 200)
CatalogueService | createCouponCampaign | response | venueId | string (uuid) | yes
CatalogueService | createCouponCampaign | response | discount | Discount | yes
CatalogueService | createCouponCampaign | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createCouponCampaign | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createCouponCampaign | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createCouponCampaign | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | createCouponCampaign | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | createCouponCampaign | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createCouponCampaign | response | conditions.variantIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.productKinds | array of string
CatalogueService | createCouponCampaign | response | conditions.categoryIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createCouponCampaign | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createCouponCampaign | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createCouponCampaign | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createCouponCampaign | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createCouponCampaign | response | conditions.daysOfWeek | array of integer
CatalogueService | createCouponCampaign | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createCouponCampaign | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createCouponCampaign | response | conditions.performanceIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createCouponCampaign | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createCouponCampaign | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | createCouponCampaign | response | isSingleUse | boolean |  | True generates individually redeemable codes. (default True)
CatalogueService | createCouponCampaign | response | maxRedemptionsPerCode | integer |  | (default 1)
CatalogueService | createCouponCampaign | response | validFrom | string (date-time) | yes
CatalogueService | createCouponCampaign | response | validTo | string (date-time)
CatalogueService | createCouponCampaign | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the codes are issued under, as the Coupon & Promo Code Builder names it. (nullable)
CatalogueService | createCouponCampaign | response | id | string (uuid) | yes
CatalogueService | createCouponCampaign | response | generatedCount | integer | yes
CatalogueService | createCouponCampaign | response | redeemedCount | integer | yes
CatalogueService | createCouponCampaign | response | isActive | boolean
CatalogueService | createCouponCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createDashboard | request | name | string | yes | (max length 200)
ReportingService | createDashboard | request | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | createDashboard | request | description | string |  | (max length 1000)
ReportingService | createDashboard | request | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | createDashboard | request | isShared | boolean |  | (default False)
ReportingService | createDashboard | request | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | createDashboard | request | tiles[].id | string (uuid) | yes
ReportingService | createDashboard | request | tiles[].title | string
ReportingService | createDashboard | request | tiles[].reportId | string (uuid) | yes
ReportingService | createDashboard | request | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | createDashboard | request | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | createDashboard | request | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | createDashboard | request | tiles[].position | object | yes
ReportingService | createDashboard | request | tiles[].position.row | integer | yes
ReportingService | createDashboard | request | tiles[].position.column | integer | yes
ReportingService | createDashboard | request | tiles[].position.width | integer | yes
ReportingService | createDashboard | request | tiles[].position.height | integer | yes
ReportingService | createDashboard | response | name | string | yes | (max length 200)
ReportingService | createDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | createDashboard | response | description | string |  | (max length 1000)
ReportingService | createDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | createDashboard | response | isShared | boolean |  | (default False)
ReportingService | createDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | createDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | createDashboard | response | tiles[].title | string
ReportingService | createDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | createDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | createDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | createDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | createDashboard | response | tiles[].position | object | yes
ReportingService | createDashboard | response | tiles[].position.row | integer | yes
ReportingService | createDashboard | response | tiles[].position.column | integer | yes
ReportingService | createDashboard | response | tiles[].position.width | integer | yes
ReportingService | createDashboard | response | tiles[].position.height | integer | yes
ReportingService | createDashboard | response | id | string (uuid) | yes
ReportingService | createDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | createDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | createDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | createDashboard | response | createdAt | string (date-time) | yes
ReportingService | createDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createDeliveryLocation | request | venueId | string (uuid) | yes
FnbService | createDeliveryLocation | request | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | createDeliveryLocation | request | label | string | yes | (max length 200)
FnbService | createDeliveryLocation | request | zone | string |  | (nullable)
FnbService | createDeliveryLocation | request | tableId | string (uuid) |  | (nullable)
FnbService | createDeliveryLocation | request | seatId | string |  | (nullable)
FnbService | createDeliveryLocation | request | servingOutletIds | array of string (uuid)
FnbService | createDeliveryLocation | request | walkTimeMinutes | integer |  | (min 0; nullable)
FnbService | createDeliveryLocation | response | id | string (uuid) | yes
FnbService | createDeliveryLocation | response | venueId | string (uuid) | yes
FnbService | createDeliveryLocation | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | createDeliveryLocation | response | label | string | yes | What a runner is told.
FnbService | createDeliveryLocation | response | zone | string |  | (nullable)
FnbService | createDeliveryLocation | response | tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | createDeliveryLocation | response | seatId | string |  | Set where the seat is the address. (nullable)
FnbService | createDeliveryLocation | response | servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | createDeliveryLocation | response | isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | createDeliveryLocation | response | unserviceableReason | string |  | (nullable)
FnbService | createDeliveryLocation | response | walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | createDeliveryLocation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createEntitlementTemplate | request | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | createEntitlementTemplate | request | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | createEntitlementTemplate | request | code | string | yes | (max length 64)
CatalogueService | createEntitlementTemplate | request | name | string | yes | (max length 200)
CatalogueService | createEntitlementTemplate | request | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | createEntitlementTemplate | request | validFromOffsetDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | validForDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | createEntitlementTemplate | request | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | createEntitlementTemplate | request | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createEntitlementTemplate | request | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createEntitlementTemplate | request | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createEntitlementTemplate | request | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createEntitlementTemplate | request | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].from | string
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].to | string
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].daysOfWeek | array of string
CatalogueService | createEntitlementTemplate | request | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | createEntitlementTemplate | request | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | createEntitlementTemplate | request | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | createEntitlementTemplate | request | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | createEntitlementTemplate | request | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | createEntitlementTemplate | request | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | createEntitlementTemplate | request | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | createEntitlementTemplate | request | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | createEntitlementTemplate | request | reentryAllowed | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | createEntitlementTemplate | request | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | createEntitlementTemplate | request | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createEntitlementTemplate | request | isTransferable | boolean |  | (default True)
CatalogueService | createEntitlementTemplate | request | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | createEntitlementTemplate | request | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | createEntitlementTemplate | request | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | createEntitlementTemplate | request | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | createEntitlementTemplate | request | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | createEntitlementTemplate | request | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | createEntitlementTemplate | request | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | createEntitlementTemplate | request | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | createEntitlementTemplate | request | isActive | boolean
CatalogueService | createEntitlementTemplate | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | createEntitlementTemplate | response | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | createEntitlementTemplate | response | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | createEntitlementTemplate | response | code | string | yes | (max length 64)
CatalogueService | createEntitlementTemplate | response | name | string | yes | (max length 200)
CatalogueService | createEntitlementTemplate | response | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | createEntitlementTemplate | response | validFromOffsetDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | validForDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | createEntitlementTemplate | response | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | createEntitlementTemplate | response | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createEntitlementTemplate | response | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createEntitlementTemplate | response | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createEntitlementTemplate | response | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createEntitlementTemplate | response | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].from | string
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].to | string
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].daysOfWeek | array of string
CatalogueService | createEntitlementTemplate | response | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | createEntitlementTemplate | response | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | createEntitlementTemplate | response | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | createEntitlementTemplate | response | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | createEntitlementTemplate | response | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | createEntitlementTemplate | response | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | createEntitlementTemplate | response | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | createEntitlementTemplate | response | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | createEntitlementTemplate | response | reentryAllowed | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | createEntitlementTemplate | response | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | createEntitlementTemplate | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createEntitlementTemplate | response | isTransferable | boolean |  | (default True)
CatalogueService | createEntitlementTemplate | response | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | createEntitlementTemplate | response | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | createEntitlementTemplate | response | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | createEntitlementTemplate | response | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | createEntitlementTemplate | response | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | createEntitlementTemplate | response | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | createEntitlementTemplate | response | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | createEntitlementTemplate | response | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | createEntitlementTemplate | response | isActive | boolean
CatalogueService | createEntitlementTemplate | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | createEntitlementTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createEvent | request | code | string | yes | Unique per tenant (decided 28 September, audit R108). (max length 64)
CatalogueService | createEvent | request | name | string | yes | (max length 200)
CatalogueService | createEvent | request | venueId | string (uuid) | yes
CatalogueService | createEvent | request | parentEventId | string (uuid)
CatalogueService | createEvent | response | id | string (uuid) | yes
CatalogueService | createEvent | response | code | string | yes
CatalogueService | createEvent | response | name | string | yes
CatalogueService | createEvent | response | venueId | string (uuid) | yes
CatalogueService | createEvent | response | scopePath | string | yes
CatalogueService | createEvent | response | parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | createEvent | response | performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | createEvent | response | isActive | boolean
CatalogueService | createEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createFnbOrder | request | id | string (uuid) | yes
FnbService | createFnbOrder | request | outletId | string (uuid) | yes
FnbService | createFnbOrder | request | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | createFnbOrder | request | tableVisitId | string (uuid) |  | Required for table service. (nullable)
FnbService | createFnbOrder | request | lines | array of CreateFnbOrderLine | yes | (min items 1)
FnbService | createFnbOrder | request | lines[].id | string (uuid) | yes
FnbService | createFnbOrder | request | lines[].menuItemId | string (uuid) | yes
FnbService | createFnbOrder | request | lines[].quantity | integer | yes | (min 1)
FnbService | createFnbOrder | request | lines[].modifierOptionIds | array of string (uuid)
FnbService | createFnbOrder | request | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createFnbOrder | request | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | createFnbOrder | request | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | createFnbOrder | request | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | createFnbOrder | request | salesOrderId | string (uuid) |  | The orders.sales_order this F&B order fulfils (SD-046, 29 September). (nullable)
FnbService | createFnbOrder | request | recordedAt | string (date-time) | yes
FnbService | createFnbOrder | response | id | string (uuid) | yes
FnbService | createFnbOrder | response | orderNumber | string | yes
FnbService | createFnbOrder | response | outletId | string (uuid) | yes
FnbService | createFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | createFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | createFnbOrder | response | lines | array of object | yes
FnbService | createFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | createFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | createFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | createFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | createFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | createFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | createFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | createFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | createFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | createFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | createFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | createFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | createFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | createFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | createFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | createFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | createFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | createFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | createFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | createFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | createFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | response | createdAt | string (date-time) | yes
FnbService | createFnbOrder | response | recordedAt | string (date-time)
FnbService | createFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createForecastScenario | request | id | string (uuid) |  | (read-only)
AiService | createForecastScenario | request | name | string
AiService | createForecastScenario | request | baseVersionId | string (uuid) | yes
AiService | createForecastScenario | request | changes | array of object | yes | (min items 1)
AiService | createForecastScenario | request | changes[].lever | enum (price, capacity, openingHours, weather, event, marketing, staffing, closure) | yes
AiService | createForecastScenario | request | changes[].target | string |  | (nullable)
AiService | createForecastScenario | request | changes[].value | object |  | (nullable)
AiService | createForecastScenario | request | status | enum (computing, ready, failed) |  | (read-only)
AiService | createForecastScenario | request | result | object |  | Deltas against the base version by subject and period. (read-only; nullable)
AiService | createForecastScenario | request | createdByPrincipalId | string (uuid) |  | (read-only)
AiService | createForecastScenario | request | createdAt | string (date-time) |  | (read-only)
AiService | createForecastScenario | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createForecastScenario | response | id | string (uuid) |  | (read-only)
AiService | createForecastScenario | response | name | string
AiService | createForecastScenario | response | baseVersionId | string (uuid) | yes
AiService | createForecastScenario | response | changes | array of object | yes | (min items 1)
AiService | createForecastScenario | response | changes[].lever | enum (price, capacity, openingHours, weather, event, marketing, staffing, closure) | yes
AiService | createForecastScenario | response | changes[].target | string |  | (nullable)
AiService | createForecastScenario | response | changes[].value | object |  | (nullable)
AiService | createForecastScenario | response | status | enum (computing, ready, failed) |  | (read-only)
AiService | createForecastScenario | response | result | object |  | Deltas against the base version by subject and period. (read-only; nullable)
AiService | createForecastScenario | response | createdByPrincipalId | string (uuid) |  | (read-only)
AiService | createForecastScenario | response | createdAt | string (date-time) |  | (read-only)
AiService | createForecastScenario | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createForecastScenario | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createForm | request | id | string (uuid) | yes | (read-only)
MarketingService | createForm | request | name | string | yes
MarketingService | createForm | request | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | createForm | request | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | createForm | request | fields | array of FormField
MarketingService | createForm | request | fields[].key | string | yes
MarketingService | createForm | request | fields[].label | string | yes
MarketingService | createForm | request | fields[].labelLocalised | object
MarketingService | createForm | request | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | createForm | request | fields[].options | array of string
MarketingService | createForm | request | fields[].isRequired | boolean |  | (default False)
MarketingService | createForm | request | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | createForm | request | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | createForm | request | fields[].showWhen | object |  | (nullable)
MarketingService | createForm | request | fields[].showWhen.field | string
MarketingService | createForm | request | fields[].showWhen.equals | string
MarketingService | createForm | request | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | createForm | request | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | createForm | request | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | createForm | request | appliesToProductIds | array of string (uuid)
MarketingService | createForm | request | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | createForm | request | minimumAge | integer |  | (nullable)
MarketingService | createForm | request | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | createForm | request | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | createForm | request | legalReviewedBy | string |  | (nullable)
MarketingService | createForm | request | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | createForm | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createForm | response | id | string (uuid) | yes | (read-only)
MarketingService | createForm | response | name | string | yes
MarketingService | createForm | response | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | createForm | response | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | createForm | response | fields | array of FormField
MarketingService | createForm | response | fields[].key | string | yes
MarketingService | createForm | response | fields[].label | string | yes
MarketingService | createForm | response | fields[].labelLocalised | object
MarketingService | createForm | response | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | createForm | response | fields[].options | array of string
MarketingService | createForm | response | fields[].isRequired | boolean |  | (default False)
MarketingService | createForm | response | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | createForm | response | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | createForm | response | fields[].showWhen | object |  | (nullable)
MarketingService | createForm | response | fields[].showWhen.field | string
MarketingService | createForm | response | fields[].showWhen.equals | string
MarketingService | createForm | response | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | createForm | response | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | createForm | response | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | createForm | response | appliesToProductIds | array of string (uuid)
MarketingService | createForm | response | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | createForm | response | minimumAge | integer |  | (nullable)
MarketingService | createForm | response | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | createForm | response | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | createForm | response | legalReviewedBy | string |  | (nullable)
MarketingService | createForm | response | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | createForm | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createForm | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | createGoodsReceipt | request | id | string (uuid) | yes
InventoryService | createGoodsReceipt | request | purchaseOrderId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | locationId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | deliveryNoteReference | string |  | (max length 128)
InventoryService | createGoodsReceipt | request | lines | array of object | yes | (min items 1)
InventoryService | createGoodsReceipt | request | lines[].itemId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | lines[].receivedQuantity | number | yes | (min 0)
InventoryService | createGoodsReceipt | request | lines[].unit | string
InventoryService | createGoodsReceipt | request | lines[].batchNumber | string |  | (max length 64)
InventoryService | createGoodsReceipt | request | lines[].expiryDate | string (date) |  | Required for perishable items.
InventoryService | createGoodsReceipt | request | lines[].note | string |  | (max length 200)
InventoryService | createGoodsReceipt | request | recordedAt | string (date-time) | yes
InventoryService | createGoodsReceipt | response | id | string (uuid) | yes
InventoryService | createGoodsReceipt | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152), e.g. (read-only)
InventoryService | createGoodsReceipt | response | purchaseOrderId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | locationId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | deliveryNoteReference | string |  | (nullable)
InventoryService | createGoodsReceipt | response | lines | array of object | yes
InventoryService | createGoodsReceipt | response | lines[].lineId | string (uuid) |  | One batch or expiry line of the receipt. (read-only)
InventoryService | createGoodsReceipt | response | lines[].itemId | string (uuid)
InventoryService | createGoodsReceipt | response | lines[].itemName | string
InventoryService | createGoodsReceipt | response | lines[].orderedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].receivedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].rejectedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].batchNumber | string |  | (nullable)
InventoryService | createGoodsReceipt | response | lines[].expiryDate | string (date) |  | (nullable)
InventoryService | createGoodsReceipt | response | lines[].unitCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createGoodsReceipt | response | lines[].unitCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createGoodsReceipt | response | lines[].unitCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createGoodsReceipt | response | lines[].unitCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createGoodsReceipt | response | totalValue | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createGoodsReceipt | response | totalValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createGoodsReceipt | response | totalValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createGoodsReceipt | response | totalValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createGoodsReceipt | response | receivedByPrincipalId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | journalEntryId | string |  | The accrual the supplier invoice will later match against. (nullable)
InventoryService | createGoodsReceipt | response | createdAt | string (date-time) | yes
InventoryService | createGoodsReceipt | response | recordedAt | string (date-time)
InventoryService | createGoodsReceipt | response | syncedAt | string (date-time) |  | (nullable)
InventoryService | createGoodsReceipt | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createGuestFnbOrder | request | id | string (uuid) | yes
FnbService | createGuestFnbOrder | request | locationSessionId | string (uuid) |  | From claimLocationSession. (nullable)
FnbService | createGuestFnbOrder | request | outletId | string (uuid) |  | Required for collection. (nullable)
FnbService | createGuestFnbOrder | request | fulfilment | object |  | Required for takeaway and address delivery; refused with 422 when it breaks the outlet's FnbDeliveryPolicy. (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.id | string (uuid) |  | (read-only)
FnbService | createGuestFnbOrder | request | fulfilment.orderId | string (uuid) |  | The guest order this fulfils (FnbOrder.id). (read-only)
FnbService | createGuestFnbOrder | request | fulfilment.mode | enum (collection, delivery, inVenue) | yes | collection from a counter, delivery to an address outside the venue, inVenue to a table, seat, cabana or named location (the location session).
FnbService | createGuestFnbOrder | request | fulfilment.collectionAt | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.windowStart | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.windowEnd | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress | object |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.building | string |  | (max length 200)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.unit | string |  | (max length 60; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.emirate | string |  | (max length 60)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.directions | string |  | (max length 500; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee | object |  | (read-only; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | request | fulfilment.cutlery | boolean |  | (default False)
FnbService | createGuestFnbOrder | request | fulfilment.scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | createGuestFnbOrder | request | lines | array of CreateGuestOrderLine | yes | (min items 1)
FnbService | createGuestFnbOrder | request | lines[].id | string (uuid) | yes
FnbService | createGuestFnbOrder | request | lines[].menuItemId | string (uuid) | yes
FnbService | createGuestFnbOrder | request | lines[].quantity | integer | yes | (min 1; max 20)
FnbService | createGuestFnbOrder | request | lines[].modifierOptionIds | array of string (uuid)
FnbService | createGuestFnbOrder | request | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createGuestFnbOrder | request | quotedTotal | object | yes | What the guest was shown.
FnbService | createGuestFnbOrder | request | quotedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | request | quotedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | request | quotedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | request | paymentMethod | enum (card, wallet, roomCharge, addToTab)
FnbService | createGuestFnbOrder | request | recordedAt | string (date-time) | yes
FnbService | createGuestFnbOrder | response | orderId | string | yes
FnbService | createGuestFnbOrder | response | orderNumber | string | yes | Short and readable.
FnbService | createGuestFnbOrder | response | fulfilment | enum (collect, deliverToLocation, tableService, deliverToAddress) |  | How the order reaches the guest, in the request's terms: collect is GuestOrderFulfilment.mode collection; deliverToAddress is delivery; inVenue is tableService where the location session is a table a…
FnbService | createGuestFnbOrder | response | deliveryLabel | string |  | Where it is going, as a runner would read it. (nullable)
FnbService | createGuestFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | createGuestFnbOrder | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createGuestFnbOrder | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | response | collectionPoint | string |  | (nullable)
FnbService | createGuestFnbOrder | response | tableLabel | string |  | (nullable)
FnbService | createGuestFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createGuidedChoice | request | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | createGuidedChoice | request | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | createGuidedChoice | request | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | createGuidedChoice | request | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | createGuidedChoice | request | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | createGuidedChoice | request | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | createGuidedChoice | request | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | createGuidedChoice | request | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | request | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | createGuidedChoice | request | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | request | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | request | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | createGuidedChoice | request | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | createGuidedChoice | request | status | object | yes | (read-only)
WhiteLabelService | createGuidedChoice | request | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | createGuidedChoice | request | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | createGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | createGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | createGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | createGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | createGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | createGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | createGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | createGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | createGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | createGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | createGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | createGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | createGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createInspectionTemplate | request | instructions | string |  | The procedure itself.
VenueOpsService | createInspectionTemplate | request | id | string (uuid) | yes
VenueOpsService | createInspectionTemplate | request | code | string | yes | (max length 64)
VenueOpsService | createInspectionTemplate | request | name | string | yes | (max length 200)
VenueOpsService | createInspectionTemplate | request | venueId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | request | appliesToAssetCategoryId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | request | frequency | enum (preOpening, postClosing, daily, weekly, monthly, annual, adHoc)
VenueOpsService | createInspectionTemplate | request | items | array of object | yes | (min items 1)
VenueOpsService | createInspectionTemplate | request | items[].key | string | yes
VenueOpsService | createInspectionTemplate | request | items[].label | string | yes
VenueOpsService | createInspectionTemplate | request | items[].kind | InspectionItemKind: enum (passFail, yesNo, numeric, text, photo, signature) | yes
VenueOpsService | createInspectionTemplate | request | items[].isRequired | boolean | yes
VenueOpsService | createInspectionTemplate | request | items[].isSafetyCritical | boolean |  | A failed safety-critical item blocks the inspection from passing and cannot be overridden by completing the rest. (default False)
VenueOpsService | createInspectionTemplate | request | items[].requiresPhotoOnFail | boolean |  | (default True)
VenueOpsService | createInspectionTemplate | request | items[].minValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | request | items[].maxValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | request | items[].guidance | string |  | (nullable)
VenueOpsService | createInspectionTemplate | request | retentionYears | integer |  | Compliance inspections are retained alongside the financial trail. (default 7)
VenueOpsService | createInspectionTemplate | request | isActive | boolean
VenueOpsService | createInspectionTemplate | response | instructions | string |  | The procedure itself.
VenueOpsService | createInspectionTemplate | response | id | string (uuid) | yes
VenueOpsService | createInspectionTemplate | response | code | string | yes | (max length 64)
VenueOpsService | createInspectionTemplate | response | name | string | yes | (max length 200)
VenueOpsService | createInspectionTemplate | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | response | appliesToAssetCategoryId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | response | frequency | enum (preOpening, postClosing, daily, weekly, monthly, annual, adHoc)
VenueOpsService | createInspectionTemplate | response | items | array of object | yes | (min items 1)
VenueOpsService | createInspectionTemplate | response | items[].key | string | yes
VenueOpsService | createInspectionTemplate | response | items[].label | string | yes
VenueOpsService | createInspectionTemplate | response | items[].kind | InspectionItemKind: enum (passFail, yesNo, numeric, text, photo, signature) | yes
VenueOpsService | createInspectionTemplate | response | items[].isRequired | boolean | yes
VenueOpsService | createInspectionTemplate | response | items[].isSafetyCritical | boolean |  | A failed safety-critical item blocks the inspection from passing and cannot be overridden by completing the rest. (default False)
VenueOpsService | createInspectionTemplate | response | items[].requiresPhotoOnFail | boolean |  | (default True)
VenueOpsService | createInspectionTemplate | response | items[].minValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | response | items[].maxValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | response | items[].guidance | string |  | (nullable)
VenueOpsService | createInspectionTemplate | response | retentionYears | integer |  | Compliance inspections are retained alongside the financial trail. (default 7)
VenueOpsService | createInspectionTemplate | response | isActive | boolean
VenueOpsService | createInspectionTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createInstalmentPlan | request | orderId | string (uuid) | yes
OrderService | createInstalmentPlan | request | frequency | enum (monthly, quarterly, custom) | yes
OrderService | createInstalmentPlan | request | instalmentCount | integer | yes | (min 2)
OrderService | createInstalmentPlan | request | firstDueDate | string (date)
OrderService | createInstalmentPlan | request | customDueDates | array of string (date) |  | Required with custom; one per instalment after the first.
OrderService | createInstalmentPlan | request | paymentTokenId | string (uuid) | yes
OrderService | createInstalmentPlan | response | id | string (uuid) | yes
OrderService | createInstalmentPlan | response | orderId | string (uuid) | yes
OrderService | createInstalmentPlan | response | subjectId | string (uuid) |  | (nullable)
OrderService | createInstalmentPlan | response | frequency | enum (monthly, quarterly, custom) | yes
OrderService | createInstalmentPlan | response | paymentTokenId | string (uuid)
OrderService | createInstalmentPlan | response | status | enum (active, completed, inArrears, cancelled) | yes
OrderService | createInstalmentPlan | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createInstalmentPlan | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createInstalmentPlan | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createInstalmentPlan | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createInstalmentPlan | response | paidToDate | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createInstalmentPlan | response | paidToDate.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createInstalmentPlan | response | paidToDate.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createInstalmentPlan | response | paidToDate.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createInstalmentPlan | response | nextDueDate | string (date) |  | (nullable)
OrderService | createInstalmentPlan | response | instalments | array of PayInstalment | yes
OrderService | createInstalmentPlan | response | instalments[].sequence | integer | yes | (min 1)
OrderService | createInstalmentPlan | response | instalments[].dueDate | string (date) | yes
OrderService | createInstalmentPlan | response | instalments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createInstalmentPlan | response | instalments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createInstalmentPlan | response | instalments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createInstalmentPlan | response | instalments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createInstalmentPlan | response | instalments[].status | enum (scheduled, paid, failed, waived, cancelled) | yes
OrderService | createInstalmentPlan | response | instalments[].paymentId | string (uuid) |  | (nullable)
OrderService | createInstalmentPlan | response | instalments[].dunningCaseId | string (uuid) |  | (nullable)
OrderService | createInstalmentPlan | response | instalments[].attemptedAt | string (date-time) |  | (nullable)
OrderService | createInstalmentPlan | response | createdAt | string (date-time)
OrderService | createInstalmentPlan | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createInstalmentPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | createInventoryItem | request | sku | string | yes | (max length 64)
InventoryService | createInventoryItem | request | barcode | string |  | (max length 128)
InventoryService | createInventoryItem | request | name | string | yes | (max length 200)
InventoryService | createInventoryItem | request | venueId | string (uuid) | yes
InventoryService | createInventoryItem | request | categoryId | string (uuid)
InventoryService | createInventoryItem | request | baseUnit | string | yes | The unit stock is held in.
InventoryService | createInventoryItem | request | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | createInventoryItem | request | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | createInventoryItem | request | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | createInventoryItem | request | reorderPoint | number |  | (min 0)
InventoryService | createInventoryItem | request | reorderQuantity | number |  | (min 0)
InventoryService | createInventoryItem | request | parLevel | number |  | (min 0)
InventoryService | createInventoryItem | request | preferredSupplierId | string (uuid)
InventoryService | createInventoryItem | request | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | createInventoryItem | request | isPerishable | boolean |  | (default False)
InventoryService | createInventoryItem | request | shelfLifeDays | integer |  | (nullable)
InventoryService | createInventoryItem | response | sku | string | yes | (max length 64)
InventoryService | createInventoryItem | response | barcode | string |  | (max length 128)
InventoryService | createInventoryItem | response | name | string | yes | (max length 200)
InventoryService | createInventoryItem | response | venueId | string (uuid) | yes
InventoryService | createInventoryItem | response | categoryId | string (uuid)
InventoryService | createInventoryItem | response | baseUnit | string | yes | The unit stock is held in.
InventoryService | createInventoryItem | response | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | createInventoryItem | response | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | createInventoryItem | response | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | createInventoryItem | response | reorderPoint | number |  | (min 0)
InventoryService | createInventoryItem | response | reorderQuantity | number |  | (min 0)
InventoryService | createInventoryItem | response | parLevel | number |  | (min 0)
InventoryService | createInventoryItem | response | preferredSupplierId | string (uuid)
InventoryService | createInventoryItem | response | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | createInventoryItem | response | isPerishable | boolean |  | (default False)
InventoryService | createInventoryItem | response | shelfLifeDays | integer |  | (nullable)
InventoryService | createInventoryItem | response | id | string (uuid) | yes
InventoryService | createInventoryItem | response | onHand | number | yes | Derived from movements.
InventoryService | createInventoryItem | response | onOrder | number
InventoryService | createInventoryItem | response | inTransit | number
InventoryService | createInventoryItem | response | available | number |  | On-hand minus allocated, where allocated is stock reserved for orders (decided 28 September, audit R171).
InventoryService | createInventoryItem | response | averageCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createInventoryItem | response | averageCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createInventoryItem | response | averageCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createInventoryItem | response | averageCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createInventoryItem | response | lastPurchasePrice | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createInventoryItem | response | lastPurchasePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createInventoryItem | response | lastPurchasePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createInventoryItem | response | lastPurchasePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createInventoryItem | response | isBelowReorderPoint | boolean
InventoryService | createInventoryItem | response | hasMovements | boolean |  | True locks costing method and base unit.
InventoryService | createInventoryItem | response | isActive | boolean | yes
InventoryService | createInventoryItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createInvitationCampaign | request | id | string (uuid) | yes | (read-only)
MarketingService | createInvitationCampaign | request | name | string | yes
MarketingService | createInvitationCampaign | request | eventId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | request | productId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | request | quota | integer | yes | Places held, not invitations sent.
MarketingService | createInvitationCampaign | request | overInvitePercent | number |  | How many more may be invited than there are places. (default 0)
MarketingService | createInvitationCampaign | request | issuedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | request | acceptedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | request | respondByAt | string (date-time) |  | (nullable)
MarketingService | createInvitationCampaign | request | status | enum (draft, open, closed, cancelled) | yes | (read-only)
MarketingService | createInvitationCampaign | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createInvitationCampaign | response | id | string (uuid) | yes | (read-only)
MarketingService | createInvitationCampaign | response | name | string | yes
MarketingService | createInvitationCampaign | response | eventId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | response | productId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | response | quota | integer | yes | Places held, not invitations sent.
MarketingService | createInvitationCampaign | response | overInvitePercent | number |  | How many more may be invited than there are places. (default 0)
MarketingService | createInvitationCampaign | response | issuedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | response | acceptedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | response | respondByAt | string (date-time) |  | (nullable)
MarketingService | createInvitationCampaign | response | status | enum (draft, open, closed, cancelled) | yes | (read-only)
MarketingService | createInvitationCampaign | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createInvitationCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createKnowledgeCollection | request | id | string (uuid) |  | (read-only)
AiService | createKnowledgeCollection | request | name | string | yes
AiService | createKnowledgeCollection | request | description | string
AiService | createKnowledgeCollection | request | scopeLevel | enum (tenant, region, venue) | yes
AiService | createKnowledgeCollection | request | scopePath | string |  | (read-only)
AiService | createKnowledgeCollection | request | documentCount | integer |  | (read-only)
AiService | createKnowledgeCollection | request | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | createKnowledgeCollection | request | retrieval | enum (dense, hybrid) |  | Set at creation and not changeable. (default hybrid)
AiService | createKnowledgeCollection | request | sparseModel | string |  | The sparse signal, where retrieval is hybrid. (nullable)
AiService | createKnowledgeCollection | request | idfScope | enum (shard, tenant, venue) |  | Which population the sparse score measures rarity against (ADR-0021). (default tenant)
AiService | createKnowledgeCollection | request | embeddingModel | string |  | This is what decides how many collections exist (ADR-0021). (read-only)
AiService | createKnowledgeCollection | request | isActive | boolean
AiService | createKnowledgeCollection | response | id | string (uuid) |  | (read-only)
AiService | createKnowledgeCollection | response | name | string | yes
AiService | createKnowledgeCollection | response | description | string
AiService | createKnowledgeCollection | response | scopeLevel | enum (tenant, region, venue) | yes
AiService | createKnowledgeCollection | response | scopePath | string |  | (read-only)
AiService | createKnowledgeCollection | response | documentCount | integer |  | (read-only)
AiService | createKnowledgeCollection | response | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | createKnowledgeCollection | response | retrieval | enum (dense, hybrid) |  | Set at creation and not changeable. (default hybrid)
AiService | createKnowledgeCollection | response | sparseModel | string |  | The sparse signal, where retrieval is hybrid. (nullable)
AiService | createKnowledgeCollection | response | idfScope | enum (shard, tenant, venue) |  | Which population the sparse score measures rarity against (ADR-0021). (default tenant)
AiService | createKnowledgeCollection | response | embeddingModel | string |  | This is what decides how many collections exist (ADR-0021). (read-only)
AiService | createKnowledgeCollection | response | isActive | boolean
AiService | createKnowledgeCollection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createKpi | request | id | string (uuid)
ReportingService | createKpi | request | code | string | yes | takings and admissions are seeded for every tenant as system KPIs (decided 28 September, audit R283), and the five accreditation KPIs for every tenant with the accreditation module (29 September, bui…
ReportingService | createKpi | request | name | string | yes
ReportingService | createKpi | request | description | string |  | (nullable)
ReportingService | createKpi | request | domain | string |  | (nullable)
ReportingService | createKpi | request | formula | string |  | Expressed against the semantic model, not against tables.
ReportingService | createKpi | request | unit | enum (currency, count, percentage, duration, ratio, score)
ReportingService | createKpi | request | higherIsBetter | boolean |  | Refund rate and revenue both go up. (default True)
ReportingService | createKpi | request | defaultPeriod | string |  | (nullable)
ReportingService | createKpi | request | owner | string (uuid) |  | (nullable)
ReportingService | createKpi | request | scopePath | string
ReportingService | createKpi | request | isActive | boolean |  | (default True)
ReportingService | createKpi | response | id | string (uuid)
ReportingService | createKpi | response | code | string | yes | takings and admissions are seeded for every tenant as system KPIs (decided 28 September, audit R283), and the five accreditation KPIs for every tenant with the accreditation module (29 September, bui…
ReportingService | createKpi | response | name | string | yes
ReportingService | createKpi | response | description | string |  | (nullable)
ReportingService | createKpi | response | domain | string |  | (nullable)
ReportingService | createKpi | response | formula | string |  | Expressed against the semantic model, not against tables.
ReportingService | createKpi | response | unit | enum (currency, count, percentage, duration, ratio, score)
ReportingService | createKpi | response | higherIsBetter | boolean |  | Refund rate and revenue both go up. (default True)
ReportingService | createKpi | response | defaultPeriod | string |  | (nullable)
ReportingService | createKpi | response | owner | string (uuid) |  | (nullable)
ReportingService | createKpi | response | scopePath | string
ReportingService | createKpi | response | isActive | boolean |  | (default True)
ReportingService | createKpi | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createLegalEntity | request | id | string (uuid) | yes | (read-only)
LedgerService | createLegalEntity | request | code | string | yes | (max length 64)
LedgerService | createLegalEntity | request | name | string | yes | (max length 200)
LedgerService | createLegalEntity | request | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createLegalEntity | request | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | createLegalEntity | request | currencyScale | integer | yes | (min 0; max 4)
LedgerService | createLegalEntity | request | taxRegistrationNumber | string |  | (nullable)
LedgerService | createLegalEntity | request | fiscalYearStartMonth | integer | yes | (min 1; max 12)
LedgerService | createLegalEntity | request | regionIds | array of string (uuid)
LedgerService | createLegalEntity | request | isActive | boolean
LedgerService | createLegalEntity | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | createLegalEntity | response | id | string (uuid) | yes | (read-only)
LedgerService | createLegalEntity | response | code | string | yes | (max length 64)
LedgerService | createLegalEntity | response | name | string | yes | (max length 200)
LedgerService | createLegalEntity | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createLegalEntity | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | createLegalEntity | response | currencyScale | integer | yes | (min 0; max 4)
LedgerService | createLegalEntity | response | taxRegistrationNumber | string |  | (nullable)
LedgerService | createLegalEntity | response | fiscalYearStartMonth | integer | yes | (min 1; max 12)
LedgerService | createLegalEntity | response | regionIds | array of string (uuid)
LedgerService | createLegalEntity | response | isActive | boolean
LedgerService | createLegalEntity | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | createLegalEntity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createLoyaltyProgramme | request | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | createLoyaltyProgramme | request | tiers[].id | string (uuid) |  | (read-only)
MarketingService | createLoyaltyProgramme | request | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | request | tiers[].code | string | yes | (max length 40)
MarketingService | createLoyaltyProgramme | request | tiers[].name | string | yes | (max length 120)
MarketingService | createLoyaltyProgramme | request | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | createLoyaltyProgramme | request | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | createLoyaltyProgramme | request | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].isActive | boolean |  | (default True)
MarketingService | createLoyaltyProgramme | request | id | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | request | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | createLoyaltyProgramme | request | name | string | yes
MarketingService | createLoyaltyProgramme | request | venueId | string (uuid) |  | (nullable)
MarketingService | createLoyaltyProgramme | request | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | createLoyaltyProgramme | request | earnRules | array of object | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].points | number | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | createLoyaltyProgramme | request | earnRules[].multiplier | number
MarketingService | createLoyaltyProgramme | request | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | createLoyaltyProgramme | request | isActive | boolean
MarketingService | createLoyaltyProgramme | response | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | createLoyaltyProgramme | response | tiers[].id | string (uuid) |  | (read-only)
MarketingService | createLoyaltyProgramme | response | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | response | tiers[].code | string | yes | (max length 40)
MarketingService | createLoyaltyProgramme | response | tiers[].name | string | yes | (max length 120)
MarketingService | createLoyaltyProgramme | response | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | createLoyaltyProgramme | response | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | createLoyaltyProgramme | response | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].isActive | boolean |  | (default True)
MarketingService | createLoyaltyProgramme | response | id | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | response | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | createLoyaltyProgramme | response | name | string | yes
MarketingService | createLoyaltyProgramme | response | venueId | string (uuid) |  | (nullable)
MarketingService | createLoyaltyProgramme | response | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | createLoyaltyProgramme | response | earnRules | array of object | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].points | number | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | createLoyaltyProgramme | response | earnRules[].multiplier | number
MarketingService | createLoyaltyProgramme | response | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | createLoyaltyProgramme | response | isActive | boolean
MarketingService | createLoyaltyProgramme | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createMenu | request | code | string | yes | (max length 64)
FnbService | createMenu | request | name | string | yes | (max length 200)
FnbService | createMenu | request | outletId | string (uuid) | yes
FnbService | createMenu | request | availability | MenuAvailability |  | When this menu is in force.
FnbService | createMenu | request | availability.daysOfWeek | array of integer
FnbService | createMenu | request | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | request | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | request | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | request | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | id | string (uuid) | yes
FnbService | createMenu | response | code | string | yes | (max length 64)
FnbService | createMenu | response | name | string | yes | (max length 200)
FnbService | createMenu | response | outletId | string (uuid) | yes
FnbService | createMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | createMenu | response | availability.daysOfWeek | array of integer
FnbService | createMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | sections | array of MenuSection
FnbService | createMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | createMenu | response | sections[].code | string | yes
FnbService | createMenu | response | sections[].name | string | yes
FnbService | createMenu | response | sections[].sortOrder | integer | yes
FnbService | createMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | createMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | createMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | createMenu | response | sections[].items[].name | string | yes
FnbService | createMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | createMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createMenu | response | sections[].items[].sortOrder | integer
FnbService | createMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | createMenu | response | sections[].items[].stationId | string (uuid) |  | (nullable)
FnbService | createMenu | response | sections[].items[].menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | createMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | createMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | createMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | createMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | createMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | createMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | createMenu | response | isActive | boolean | yes
FnbService | createMenu | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | createMenu | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | createMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createMerchandise | request | sku | string | yes | (max length 64)
RetailService | createMerchandise | request | barcode | string |  | (max length 128)
RetailService | createMerchandise | request | name | string | yes | (max length 200)
RetailService | createMerchandise | request | description | string |  | What the item is, in the guest's words.
RetailService | createMerchandise | request | outletId | string (uuid) | yes
RetailService | createMerchandise | request | categoryId | string (uuid)
RetailService | createMerchandise | request | variantId | string (uuid) | yes
RetailService | createMerchandise | request | inventoryItemId | string (uuid)
RetailService | createMerchandise | request | isReturnable | boolean |  | (default True)
RetailService | createMerchandise | request | returnWindowDays | integer
RetailService | createMerchandise | request | requiresSerialNumber | boolean |  | (default False)
RetailService | createMerchandise | request | imageAssetRef | string
RetailService | createMerchandise | response | description | string |  | What the item is, in the guest's words.
RetailService | createMerchandise | response | id | string (uuid) | yes
RetailService | createMerchandise | response | sku | string | yes
RetailService | createMerchandise | response | barcode | string |  | (nullable)
RetailService | createMerchandise | response | name | string | yes
RetailService | createMerchandise | response | outletId | string (uuid) | yes
RetailService | createMerchandise | response | categoryId | string (uuid) |  | (nullable)
RetailService | createMerchandise | response | variantId | string (uuid) | yes | The catalogue variant sold.
RetailService | createMerchandise | response | inventoryItemId | string (uuid) |  | The stock item depleted on sale. (nullable)
RetailService | createMerchandise | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createMerchandise | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createMerchandise | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createMerchandise | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createMerchandise | response | onHand | number | yes
RetailService | createMerchandise | response | isReturnable | boolean |  | (default True)
RetailService | createMerchandise | response | returnWindowDays | integer |  | (nullable)
RetailService | createMerchandise | response | requiresSerialNumber | boolean |  | (default False)
RetailService | createMerchandise | response | imageAssetRef | string |  | (nullable)
RetailService | createMerchandise | response | isActive | boolean | yes
RetailService | createMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createMessageTemplate | request | id | string (uuid) | yes | (read-only)
MarketingService | createMessageTemplate | request | code | string | yes | (max length 64)
MarketingService | createMessageTemplate | request | name | string | yes | (max length 200)
MarketingService | createMessageTemplate | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createMessageTemplate | request | subjects | object |  | Per language.
MarketingService | createMessageTemplate | request | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | createMessageTemplate | request | mergeFields | array of string
MarketingService | createMessageTemplate | request | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | createMessageTemplate | request | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | createMessageTemplate | request | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | createMessageTemplate | request | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | createMessageTemplate | response | id | string (uuid) | yes | (read-only)
MarketingService | createMessageTemplate | response | code | string | yes | (max length 64)
MarketingService | createMessageTemplate | response | name | string | yes | (max length 200)
MarketingService | createMessageTemplate | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createMessageTemplate | response | subjects | object |  | Per language.
MarketingService | createMessageTemplate | response | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | createMessageTemplate | response | mergeFields | array of string
MarketingService | createMessageTemplate | response | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | createMessageTemplate | response | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | createMessageTemplate | response | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | createMessageTemplate | response | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | createMessageTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | createMfaChallenge | request | action | string | yes | What the step-up is for.
IdentityService | createMfaChallenge | request | methodId | string (uuid)
IdentityService | createMfaChallenge | request | venueId | string (uuid) |  | For a guest, the venue whose VenueSettings.identity.guestTwoStep applies (sign-in venue, or the venue of the booking being acted on). (nullable)
IdentityService | createMfaChallenge | response | challengeId | string
IdentityService | createMfaChallenge | response | expiresAt | string (date-time)
IdentityService | createMfaChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createModifierGroup | request | id | string (uuid) | yes
FnbService | createModifierGroup | request | code | string | yes
FnbService | createModifierGroup | request | name | string | yes
FnbService | createModifierGroup | request | minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | createModifierGroup | request | maxSelections | integer | yes | (min 1)
FnbService | createModifierGroup | request | options | array of object | yes | (min items 1)
FnbService | createModifierGroup | request | options[].id | string (uuid) | yes
FnbService | createModifierGroup | request | options[].name | string | yes
FnbService | createModifierGroup | request | options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createModifierGroup | request | options[].priceDelta.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createModifierGroup | request | options[].priceDelta.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createModifierGroup | request | options[].priceDelta.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createModifierGroup | request | options[].isDefault | boolean
FnbService | createModifierGroup | request | options[].isAvailable | boolean
FnbService | createModifierGroup | request | options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | createModifierGroup | request | scopePath | string |  | The partition key (ADR-0005).
FnbService | createModifierGroup | response | id | string (uuid) | yes
FnbService | createModifierGroup | response | code | string | yes
FnbService | createModifierGroup | response | name | string | yes
FnbService | createModifierGroup | response | minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | createModifierGroup | response | maxSelections | integer | yes | (min 1)
FnbService | createModifierGroup | response | options | array of object | yes | (min items 1)
FnbService | createModifierGroup | response | options[].id | string (uuid) | yes
FnbService | createModifierGroup | response | options[].name | string | yes
FnbService | createModifierGroup | response | options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createModifierGroup | response | options[].priceDelta.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createModifierGroup | response | options[].priceDelta.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createModifierGroup | response | options[].priceDelta.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createModifierGroup | response | options[].isDefault | boolean
FnbService | createModifierGroup | response | options[].isAvailable | boolean
FnbService | createModifierGroup | response | options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | createModifierGroup | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | createModifierGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createOrder | request | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createOrder | request | venueId | string (uuid) | yes
OrderService | createOrder | request | channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
OrderService | createOrder | request | shiftId | string (uuid)
OrderService | createOrder | request | subjectId | string (uuid) |  | Null for an anonymous sale. (nullable)
OrderService | createOrder | request | guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
OrderService | createOrder | request | catalogueBundleVersion | string |  | The bundle the client priced from.
OrderService | createOrder | request | lines | array of CreateOrderLine | yes | (min items 1)
OrderService | createOrder | request | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createOrder | request | lines[].variantId | string (uuid) | yes
OrderService | createOrder | request | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createOrder | request | lines[].performanceId | string (uuid)
OrderService | createOrder | request | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createOrder | request | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createOrder | request | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createOrder | request | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createOrder | request | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createOrder | request | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createOrder | request | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createOrder | request | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createOrder | request | lines[].quantity | integer | yes | (min 1)
OrderService | createOrder | request | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createOrder | request | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createOrder | request | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createOrder | request | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | request | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | request | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | request | lines[].holderName | string |  | (nullable)
OrderService | createOrder | request | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createOrder | request | recordedAt | string (date-time) | yes
OrderService | createOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | createOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | createOrder | response | channel | object | yes | Where it came from.
OrderService | createOrder | response | venueId | string (uuid) | yes
OrderService | createOrder | response | scopePath | string | yes
OrderService | createOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | createOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | createOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | createOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | createOrder | response | droppedPromotions[].name | string
OrderService | createOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | createOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | createOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines | array of OrderLine | yes
OrderService | createOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createOrder | response | lines[].variantId | string (uuid) | yes
OrderService | createOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createOrder | response | lines[].performanceId | string (uuid)
OrderService | createOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | createOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].holderName | string |  | (nullable)
OrderService | createOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | createOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | createOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | createOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | createOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | createOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | createOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | createOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | createOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | createOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | createOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | createOrder | response | payments | array of Payment
OrderService | createOrder | response | payments[].id | string (uuid) | yes
OrderService | createOrder | response | payments[].orderId | string (uuid) | yes
OrderService | createOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | createOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | createOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | createOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | createOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | createOrder | response | payments[].providerName | string |  | (nullable)
OrderService | createOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | createOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | createOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | createOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | createOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | createOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | createOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | createOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | principalId | string (uuid)
OrderService | createOrder | response | workstationId | string (uuid)
OrderService | createOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | createOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | createOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | createOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | createOrder | response | createdAt | string (date-time) | yes
OrderService | createOrder | response | recordedAt | string (date-time) | yes
OrderService | createOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createOrgUnit | request | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | createOrgUnit | request | parentId | string (uuid) | yes | Required for every level except tenant, which the cell creates at provisioning.
TenancyService | createOrgUnit | request | code | string | yes | Becomes the final ltree segment. (max length 64; pattern ^[a-z0-9_]+$)
TenancyService | createOrgUnit | request | name | string | yes | (max length 200)
TenancyService | createOrgUnit | response | id | string (uuid) | yes
TenancyService | createOrgUnit | response | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | createOrgUnit | response | parentId | string (uuid) |  | (nullable)
TenancyService | createOrgUnit | response | path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | createOrgUnit | response | code | string | yes | (max length 64)
TenancyService | createOrgUnit | response | name | string | yes | (max length 200)
TenancyService | createOrgUnit | response | isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | createOrgUnit | response | childCount | integer |  | (min 0)
TenancyService | createOrgUnit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createOutlet | request | id | string (uuid) | yes | (read-only)
TenancyService | createOutlet | request | code | string | yes | (max length 64)
TenancyService | createOutlet | request | name | string | yes | (max length 200)
TenancyService | createOutlet | request | venueId | string (uuid) | yes
TenancyService | createOutlet | request | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | createOutlet | request | zone | string |  | (nullable)
TenancyService | createOutlet | request | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | createOutlet | request | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | createOutlet | request | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | createOutlet | request | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | createOutlet | request | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | request | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | request | isActive | boolean
TenancyService | createOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | createOutlet | response | code | string | yes | (max length 64)
TenancyService | createOutlet | response | name | string | yes | (max length 200)
TenancyService | createOutlet | response | venueId | string (uuid) | yes
TenancyService | createOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | createOutlet | response | zone | string |  | (nullable)
TenancyService | createOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | createOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | createOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | createOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | createOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | response | isActive | boolean
TenancyService | createOutlet | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createPayment | request | id | string (uuid) | yes | Client-generated UUIDv7 of the payment, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createPayment | request | orderId | string (uuid) | yes
OrderService | createPayment | request | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createPayment | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | request | tenderCurrency | string |  | The currency the guest handed over, where it is not the venue's — becomes Payment.tenderCurrency. (pattern ^[A-Z]{3}$; nullable)
OrderService | createPayment | request | tenderAmount | object |  | What the guest handed over, in tenderCurrency — becomes Payment.tenderAmount, one name for one concept (renamed from tenderedAmount on 26 September).
OrderService | createPayment | request | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | request | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | request | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | request | walletAuthorisationId | string |  | Cross-cell wallet hold, where the guest's home cell is elsewhere. (nullable)
OrderService | createPayment | request | walletHoldId | string (uuid) |  | For a wallet tender, the hold wallet.holdWalletFunds placed (SD-027). (nullable)
OrderService | createPayment | request | returnUrl | string (uri) |  | Where the provider returns the guest after a 3-D Secure challenge or hosted page (SD-034). (nullable)
OrderService | createPayment | request | terminalId | string (uuid) |  | The card terminal to instruct, for a card payment at a till (ECR flow, SD-034). (nullable)
OrderService | createPayment | request | deviceId | string (uuid) |  | (nullable)
OrderService | createPayment | request | recordedAt | string (date-time) | yes
OrderService | createPayment | response | id | string (uuid) | yes
OrderService | createPayment | response | orderId | string (uuid) | yes
OrderService | createPayment | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createPayment | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | createPayment | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | createPayment | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | createPayment | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | createPayment | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | createPayment | response | providerName | string |  | (nullable)
OrderService | createPayment | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | createPayment | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | createPayment | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | createPayment | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | createPayment | response | nextAction.kind | enum (redirect, terminal)
OrderService | createPayment | response | nextAction.url | string (uri) |  | (nullable)
OrderService | createPayment | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | createPayment | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | createPayment | response | recordedAt | string (date-time) | yes
OrderService | createPayment | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createPayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createPaymentProviderConnection | request | id | string (uuid)
OrderService | createPaymentProviderConnection | request | code | string | yes
OrderService | createPaymentProviderConnection | request | name | string
OrderService | createPaymentProviderConnection | request | providerKind | enum (gateway, psp, acquirer, walletProvider, bnplProvider) | yes
OrderService | createPaymentProviderConnection | request | environment | enum (sandbox, production)
OrderService | createPaymentProviderConnection | request | credentialFingerprint | string |  | Written, never read back. (read-only)
OrderService | createPaymentProviderConnection | request | capabilities | object
OrderService | createPaymentProviderConnection | request | capabilities.methods | array of string
OrderService | createPaymentProviderConnection | request | capabilities.currencies | array of string
OrderService | createPaymentProviderConnection | request | capabilities.partialCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.multipleCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.refundWindowDays | integer |  | (nullable)
OrderService | createPaymentProviderConnection | request | capabilities.tokenisation | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.threeDSecure | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.cardPresent | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | merchantAccountId | string (uuid) |  | (nullable)
OrderService | createPaymentProviderConnection | request | status | enum (draft, testing, active, degraded, disabled)
OrderService | createPaymentProviderConnection | request | lastTestedAt | string (date-time) |  | (nullable)
OrderService | createPaymentProviderConnection | request | scopePath | string
OrderService | createPaymentProviderConnection | response | id | string (uuid)
OrderService | createPaymentProviderConnection | response | code | string | yes
OrderService | createPaymentProviderConnection | response | name | string
OrderService | createPaymentProviderConnection | response | providerKind | enum (gateway, psp, acquirer, walletProvider, bnplProvider) | yes
OrderService | createPaymentProviderConnection | response | environment | enum (sandbox, production)
OrderService | createPaymentProviderConnection | response | credentialFingerprint | string |  | Written, never read back. (read-only)
OrderService | createPaymentProviderConnection | response | capabilities | object
OrderService | createPaymentProviderConnection | response | capabilities.methods | array of string
OrderService | createPaymentProviderConnection | response | capabilities.currencies | array of string
OrderService | createPaymentProviderConnection | response | capabilities.partialCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.multipleCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.refundWindowDays | integer |  | (nullable)
OrderService | createPaymentProviderConnection | response | capabilities.tokenisation | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.threeDSecure | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.cardPresent | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | merchantAccountId | string (uuid) |  | (nullable)
OrderService | createPaymentProviderConnection | response | status | enum (draft, testing, active, degraded, disabled)
OrderService | createPaymentProviderConnection | response | lastTestedAt | string (date-time) |  | (nullable)
OrderService | createPaymentProviderConnection | response | scopePath | string
OrderService | createPaymentProviderConnection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createPlan | request | code | string | yes | (max length 64)
PlatformService | createPlan | request | name | string | yes | (max length 200)
PlatformService | createPlan | request | description | string |  | (max length 1000)
PlatformService | createPlan | request | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlan | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlan | request | limits | array of EntitlementLimit | yes
PlatformService | createPlan | request | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlan | request | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlan | request | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlan | request | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | request | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | request | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | request | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | request | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlan | request | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlan | request | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlan | request | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlan | request | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlan | response | code | string | yes | (max length 64)
PlatformService | createPlan | response | name | string | yes | (max length 200)
PlatformService | createPlan | response | description | string |  | (max length 1000)
PlatformService | createPlan | response | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlan | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlan | response | limits | array of EntitlementLimit | yes
PlatformService | createPlan | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlan | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlan | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlan | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | response | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | response | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlan | response | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlan | response | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlan | response | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlan | response | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlan | response | id | string (uuid) | yes
PlatformService | createPlan | response | version | string | yes | Existing subscribers stay on the version they were sold.
PlatformService | createPlan | response | isActive | boolean | yes
PlatformService | createPlan | response | subscriberCount | integer | yes
PlatformService | createPlan | response | publishedAt | string (date-time)
PlatformService | createPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createPlanVersion | request | code | string | yes | (max length 64)
PlatformService | createPlanVersion | request | name | string | yes | (max length 200)
PlatformService | createPlanVersion | request | description | string |  | (max length 1000)
PlatformService | createPlanVersion | request | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlanVersion | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlanVersion | request | limits | array of EntitlementLimit | yes
PlatformService | createPlanVersion | request | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlanVersion | request | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlanVersion | request | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | request | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | request | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlanVersion | request | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlanVersion | request | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlanVersion | request | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlanVersion | request | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlanVersion | response | code | string | yes | (max length 64)
PlatformService | createPlanVersion | response | name | string | yes | (max length 200)
PlatformService | createPlanVersion | response | description | string |  | (max length 1000)
PlatformService | createPlanVersion | response | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlanVersion | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlanVersion | response | limits | array of EntitlementLimit | yes
PlatformService | createPlanVersion | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlanVersion | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlanVersion | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | response | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | response | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlanVersion | response | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlanVersion | response | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlanVersion | response | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlanVersion | response | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlanVersion | response | id | string (uuid) | yes
PlatformService | createPlanVersion | response | version | string | yes | Existing subscribers stay on the version they were sold.
PlatformService | createPlanVersion | response | isActive | boolean | yes
PlatformService | createPlanVersion | response | subscriberCount | integer | yes
PlatformService | createPlanVersion | response | publishedAt | string (date-time)
PlatformService | createPlanVersion | param (path) | planId | string (uuid) | yes
PlatformService | createPlanVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createPreview | request | platform | enum (ios, android, web)
WhiteLabelService | createPreview | request | theme | enum (light, dark)
WhiteLabelService | createPreview | request | language | string |  | (pattern ^[a-z]{2}$)
WhiteLabelService | createPreview | request | expiresInHours | integer |  | (min 1; max 168; default 24)
WhiteLabelService | createPreview | response | previewId | string (uuid) | yes
WhiteLabelService | createPreview | response | url | string | yes
WhiteLabelService | createPreview | response | platform | enum (ios, android, web)
WhiteLabelService | createPreview | response | theme | enum (light, dark)
WhiteLabelService | createPreview | response | language | string |  | (pattern ^[a-z]{2}$)
WhiteLabelService | createPreview | response | expiresAt | string (date-time) | yes
WhiteLabelService | createPreview | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPriceList | request | code | string | yes | (max length 64)
CatalogueService | createPriceList | request | name | string | yes | (max length 200)
CatalogueService | createPriceList | request | venueId | string (uuid) | yes
CatalogueService | createPriceList | request | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes | (min items 1)
CatalogueService | createPriceList | request | validFrom | string (date-time)
CatalogueService | createPriceList | request | validTo | string (date-time)
CatalogueService | createPriceList | request | priority | integer |  | (default 0)
CatalogueService | createPriceList | response | id | string (uuid) | yes
CatalogueService | createPriceList | response | code | string | yes
CatalogueService | createPriceList | response | name | string | yes
CatalogueService | createPriceList | response | venueId | string (uuid) | yes
CatalogueService | createPriceList | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | createPriceList | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | createPriceList | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | createPriceList | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | createPriceList | response | validTo | string (date-time) |  | (nullable)
CatalogueService | createPriceList | response | priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | createPriceList | response | description | string |  | Price list master fields (29 September, data model DM3), set with setPriceListMaster (ADM-058). (nullable)
CatalogueService | createPriceList | response | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | createPriceList | response | status | object |  | (default active)
CatalogueService | createPriceList | response | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | tags | array of string
CatalogueService | createPriceList | response | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | brand | string |  | (max length 100; nullable)
CatalogueService | createPriceList | response | businessUnit | string |  | (max length 100; nullable)
CatalogueService | createPriceList | response | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | createPriceList | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | createPriceList | response | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | createPriceList | response | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | allowOverrides | boolean |  | (default False)
CatalogueService | createPriceList | response | allowInheritance | boolean |  | (default True)
CatalogueService | createPriceList | response | allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | createPriceList | response | allowProductSpecificRates | boolean |  | (default True)
CatalogueService | createPriceList | response | clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | createPriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPriceList | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
IdentityService | createPrincipal | request | username | string | yes | (max length 256)
IdentityService | createPrincipal | request | displayName | string | yes | (max length 200)
IdentityService | createPrincipal | request | initialCredential | string |  | (max length 512)
IdentityService | createPrincipal | request | mustChangeCredential | boolean |  | (default True)
IdentityService | createPrincipal | request | validTo | string (date-time)
IdentityService | createPrincipal | request | roleIds | array of string (uuid)
IdentityService | createPrincipal | response | id | string (uuid) | yes
IdentityService | createPrincipal | response | username | string | yes
IdentityService | createPrincipal | response | displayName | string | yes
IdentityService | createPrincipal | response | isActive | boolean | yes
IdentityService | createPrincipal | response | validFrom | string (date-time) |  | (nullable)
IdentityService | createPrincipal | response | validTo | string (date-time) |  | Past this, resolution returns DENY regardless of grants. (nullable)
IdentityService | createPrincipal | response | primaryRoleId | string (uuid) |  | Determines the landing screen when the principal holds several roles and picks one at login. (nullable)
IdentityService | createPrincipal | response | roles | array of RoleSummary
IdentityService | createPrincipal | response | roles[].id | string (uuid) | yes
IdentityService | createPrincipal | response | roles[].code | string | yes
IdentityService | createPrincipal | response | roles[].name | string | yes
IdentityService | createPrincipal | response | roles[].isPrimary | boolean
IdentityService | createPrincipal | response | lastLoginAt | string (date-time) |  | (nullable)
IdentityService | createPrincipal | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createPromoBlock | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createPromoBlock | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | request | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createPromoBlock | request | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | createPromoBlock | request | linkTarget | LinkTarget
WhiteLabelService | createPromoBlock | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createPromoBlock | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createPromoBlock | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createPromoBlock | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.productId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.eventId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.url | string
WhiteLabelService | createPromoBlock | request | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | createPromoBlock | request | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createPromoBlock | request | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | createPromoBlock | request | sortOrder | integer
WhiteLabelService | createPromoBlock | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createPromoBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createPromoBlock | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | response | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createPromoBlock | response | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | createPromoBlock | response | linkTarget | LinkTarget
WhiteLabelService | createPromoBlock | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createPromoBlock | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createPromoBlock | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createPromoBlock | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.productId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.eventId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.url | string
WhiteLabelService | createPromoBlock | response | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | createPromoBlock | response | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createPromoBlock | response | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | createPromoBlock | response | sortOrder | integer
WhiteLabelService | createPromoBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createPromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPromotion | request | code | string | yes | (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | createPromotion | request | name | string | yes | (max length 200)
CatalogueService | createPromotion | request | description | string |  | (max length 1000)
CatalogueService | createPromotion | request | venueId | string (uuid) | yes
CatalogueService | createPromotion | request | discount | Discount | yes
CatalogueService | createPromotion | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createPromotion | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createPromotion | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createPromotion | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createPromotion | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createPromotion | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createPromotion | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createPromotion | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | createPromotion | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | createPromotion | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createPromotion | request | conditions.variantIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.productKinds | array of string
CatalogueService | createPromotion | request | conditions.categoryIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createPromotion | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createPromotion | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createPromotion | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createPromotion | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createPromotion | request | conditions.daysOfWeek | array of integer
CatalogueService | createPromotion | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createPromotion | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createPromotion | request | conditions.performanceIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createPromotion | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createPromotion | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | createPromotion | request | stackingMode | object |  | (default bestOnly)
CatalogueService | createPromotion | request | stackingGroup | string |  | (max length 64)
CatalogueService | createPromotion | request | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | createPromotion | request | validFrom | string (date-time) | yes
CatalogueService | createPromotion | request | validTo | string (date-time)
CatalogueService | createPromotion | request | maxRedemptions | integer |  | (nullable)
CatalogueService | createPromotion | request | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | createPromotion | request | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | createPromotion | request | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | createPromotion | request | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | createPromotion | request | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | createPromotion | response | code | string | yes | (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | createPromotion | response | name | string | yes | (max length 200)
CatalogueService | createPromotion | response | description | string |  | (max length 1000)
CatalogueService | createPromotion | response | venueId | string (uuid) | yes
CatalogueService | createPromotion | response | discount | Discount | yes
CatalogueService | createPromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createPromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createPromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createPromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createPromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createPromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createPromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createPromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | createPromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | createPromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createPromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.productKinds | array of string
CatalogueService | createPromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createPromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createPromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createPromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createPromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createPromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | createPromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createPromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createPromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createPromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createPromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | createPromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | createPromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | createPromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | createPromotion | response | validFrom | string (date-time) | yes
CatalogueService | createPromotion | response | validTo | string (date-time)
CatalogueService | createPromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | createPromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | createPromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | createPromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | createPromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | createPromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | createPromotion | response | id | string (uuid) | yes
CatalogueService | createPromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | createPromotion | response | isPaused | boolean
CatalogueService | createPromotion | response | redemptionCount | integer
CatalogueService | createPromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | createPromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | createPromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createQueue | request | code | string | yes | (max length 64)
VenueOpsService | createQueue | request | name | LocalisedText | yes
VenueOpsService | createQueue | request | venueId | string (uuid) | yes
VenueOpsService | createQueue | request | attractionProductId | string (uuid)
VenueOpsService | createQueue | request | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | createQueue | request | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | createQueue | request | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | createQueue | request | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | createQueue | request | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | createQueue | request | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | request | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | request | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | createQueue | request | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | createQueue | request | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | createQueue | request | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | createQueue | request | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | createQueue | request | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | createQueue | request | cycleMinutes | number | yes | (min 0)
VenueOpsService | createQueue | request | maxPartySize | integer |  | (default 6)
VenueOpsService | createQueue | request | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | createQueue | request | heightRequirementCm | integer |  | (nullable)
VenueOpsService | createQueue | request | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | createQueue | request | zone | string |  | (nullable)
VenueOpsService | createQueue | request | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | createQueue | request | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | createQueue | request | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | request | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | request | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | createQueue | request | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | createQueue | request | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | createQueue | request | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | createQueue | response | code | string | yes | (max length 64)
VenueOpsService | createQueue | response | name | LocalisedText | yes
VenueOpsService | createQueue | response | venueId | string (uuid) | yes
VenueOpsService | createQueue | response | attractionProductId | string (uuid)
VenueOpsService | createQueue | response | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | createQueue | response | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | createQueue | response | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | createQueue | response | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | createQueue | response | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | createQueue | response | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | response | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | response | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | createQueue | response | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | createQueue | response | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | createQueue | response | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | createQueue | response | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | createQueue | response | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | createQueue | response | cycleMinutes | number | yes | (min 0)
VenueOpsService | createQueue | response | maxPartySize | integer |  | (default 6)
VenueOpsService | createQueue | response | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | createQueue | response | heightRequirementCm | integer |  | (nullable)
VenueOpsService | createQueue | response | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | createQueue | response | zone | string |  | (nullable)
VenueOpsService | createQueue | response | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | createQueue | response | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | createQueue | response | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | response | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | response | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | createQueue | response | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | createQueue | response | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | createQueue | response | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | createQueue | response | id | string (uuid) | yes
VenueOpsService | createQueue | response | status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | createQueue | response | statusReason | string |  | (nullable)
VenueOpsService | createQueue | response | waitingPartyCount | integer | yes
VenueOpsService | createQueue | response | waitingGuestCount | integer
VenueOpsService | createQueue | response | currentWaitMinutes | integer |  | (nullable)
VenueOpsService | createQueue | response | waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | createQueue | response | waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | createQueue | response | manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | createQueue | response | manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | createQueue | response | expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | createQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createReferral | request | id | string (uuid) | yes | (read-only)
MarketingService | createReferral | request | referrerSubjectId | string (uuid) | yes
MarketingService | createReferral | request | refereeSubjectId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | code | string | yes | (read-only)
MarketingService | createReferral | request | status | enum (issued, registered, qualified, rewarded, expired, void) | yes | (read-only)
MarketingService | createReferral | request | qualifyingAction | enum (firstPurchase, firstVisit, membershipPurchase)
MarketingService | createReferral | request | referrerRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | refereeRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | expiresAt | string (date-time) |  | (nullable)
MarketingService | createReferral | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createReferral | response | id | string (uuid) | yes | (read-only)
MarketingService | createReferral | response | referrerSubjectId | string (uuid) | yes
MarketingService | createReferral | response | refereeSubjectId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | code | string | yes | (read-only)
MarketingService | createReferral | response | status | enum (issued, registered, qualified, rewarded, expired, void) | yes | (read-only)
MarketingService | createReferral | response | qualifyingAction | enum (firstPurchase, firstVisit, membershipPurchase)
MarketingService | createReferral | response | referrerRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | refereeRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | expiresAt | string (date-time) |  | (nullable)
MarketingService | createReferral | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createReferral | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createRefund | request | id | string (uuid) | yes | Client-generated UUIDv7 of the refund, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createRefund | request | lineIds | array of string (uuid) |  | Omit to refund the whole order.
OrderService | createRefund | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | request | reason | string | yes | (min length 3; max length 500)
OrderService | createRefund | request | secondaryAuthorisation | object |  | Required above the venue's requiresSecondUserAbove.
OrderService | createRefund | request | secondaryAuthorisation.principalId | string (uuid) | yes
OrderService | createRefund | request | secondaryAuthorisation.credential | string | yes | The second person's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | createRefund | request | refundToOriginalTender | boolean |  | (default True)
OrderService | createRefund | request | alternateTender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) |  | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createRefund | request | recordedAt | string (date-time) | yes
OrderService | createRefund | response | id | string (uuid) | yes
OrderService | createRefund | response | orderId | string (uuid) | yes
OrderService | createRefund | response | batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | createRefund | response | fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | createRefund | response | taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | createRefund | response | settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | createRefund | response | fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | createRefund | response | fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | createRefund | response | status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | createRefund | response | reason | string
OrderService | createRefund | response | requestedByPrincipalId | string (uuid)
OrderService | createRefund | response | secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | createRefund | response | approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | createRefund | response | ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | createRefund | response | gatewayReference | string |  | (nullable)
OrderService | createRefund | response | createdAt | string (date-time) | yes
OrderService | createRefund | response | completedAt | string (date-time) |  | (nullable)
OrderService | createRefund | param (path) | orderId | string (uuid) | yes
OrderService | createRefund | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createRefundRequest | request | orderId | string (uuid) | yes
OrderService | createRefundRequest | request | lineIds | array of string (uuid)
OrderService | createRefundRequest | request | reason | string | yes | (min length 3; max length 1000)
OrderService | createRefundRequest | response | requestId | string
OrderService | createRefundRequest | response | status | enum (submitted, moreInfoRequested, approved, declined)
OrderService | createRefundRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createReport | request | name | string | yes | (max length 200)
ReportingService | createReport | request | description | string |  | (max length 1000)
ReportingService | createReport | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | createReport | request | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | createReport | request | columns | array of ReportColumn | yes | (min items 1)
ReportingService | createReport | request | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | request | columns[].field | string | yes
ReportingService | createReport | request | columns[].label | string
ReportingService | createReport | request | columns[].aggregation | object |  | (default none)
ReportingService | createReport | request | columns[].sortOrder | integer
ReportingService | createReport | request | columns[].sortDirection | enum (asc, desc)
ReportingService | createReport | request | columns[].format | string |  | (nullable)
ReportingService | createReport | request | filters | array of ReportFilter
ReportingService | createReport | request | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | request | filters[].field | string | yes
ReportingService | createReport | request | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | createReport | request | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | createReport | request | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | createReport | request | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | createReport | request | groupBy | array of string
ReportingService | createReport | request | parameters | array of ReportParameter
ReportingService | createReport | request | parameters[].key | string | yes
ReportingService | createReport | request | parameters[].label | string | yes
ReportingService | createReport | request | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | createReport | request | parameters[].isRequired | boolean | yes
ReportingService | createReport | request | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | createReport | request | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | createReport | request | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | createReport | response | name | string | yes | (max length 200)
ReportingService | createReport | response | description | string |  | (max length 1000)
ReportingService | createReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | createReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | createReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | createReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | response | columns[].field | string | yes
ReportingService | createReport | response | columns[].label | string
ReportingService | createReport | response | columns[].aggregation | object |  | (default none)
ReportingService | createReport | response | columns[].sortOrder | integer
ReportingService | createReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | createReport | response | columns[].format | string |  | (nullable)
ReportingService | createReport | response | filters | array of ReportFilter
ReportingService | createReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | response | filters[].field | string | yes
ReportingService | createReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | createReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | createReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | createReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | createReport | response | groupBy | array of string
ReportingService | createReport | response | parameters | array of ReportParameter
ReportingService | createReport | response | parameters[].key | string | yes
ReportingService | createReport | response | parameters[].label | string | yes
ReportingService | createReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | createReport | response | parameters[].isRequired | boolean | yes
ReportingService | createReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | createReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | createReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | createReport | response | id | string (uuid) | yes
ReportingService | createReport | response | version | string | yes | The current version.
ReportingService | createReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | createReport | response | isRetired | boolean | yes
ReportingService | createReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | createReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | createReport | response | createdAt | string (date-time) | yes
ReportingService | createReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | createReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | createReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createResaleListing | request | entitlementId | string (uuid) | yes
OrderService | createResaleListing | request | askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createResaleListing | request | askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createResaleListing | request | askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createResaleListing | request | askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createResaleListing | request | sellerSubjectId | string (uuid) |  | The holder listing it. (nullable)
OrderService | createResaleListing | response | id | string (uuid) | yes | (read-only)
OrderService | createResaleListing | response | entitlementId | string (uuid) | yes
OrderService | createResaleListing | response | sellerSubjectId | string (uuid) | yes
OrderService | createResaleListing | response | askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createResaleListing | response | askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createResaleListing | response | askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createResaleListing | response | askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createResaleListing | response | priceCapPercent | number |  | A ceiling as a percentage of face value, because uncapped resale is a venue watching its own tickets sold at four times the price with its name on them. (read-only; nullable)
OrderService | createResaleListing | response | sellerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | createResaleListing | response | buyerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | createResaleListing | response | status | enum (pendingReview, listed, reserved, sold, withdrawn, expired, rejected) | yes | pendingReview and rejected added 29 September (DM5): a listing the marketplace's moderationMode sends to review waits there until approveListingModeration lists or rejects it. (read-only)
OrderService | createResaleListing | response | listedAt | string (date-time) |  | (read-only)
OrderService | createResaleListing | response | soldToSubjectId | string (uuid) |  | (read-only; nullable)
OrderService | createResaleListing | response | reviewReasons | array of enum (highResalePrice, unusualDiscount, highValueTicket, vipTicket, sellerRisk, newSeller, multipleListings, identityIssue, …) |  | Why the listing was sent to review (DM5, 29 September). (read-only)
OrderService | createResaleListing | response | moderatedByPrincipalId | string (uuid) |  | (read-only; nullable)
OrderService | createResaleListing | response | moderatedAt | string (date-time) |  | (read-only; nullable)
OrderService | createResaleListing | response | moderationReason | string |  | (max length 1000; read-only; nullable)
OrderService | createResaleListing | response | payoutStatus | enum (pending, held, paid, failed) |  | The seller is paid after the buyer is admitted, not after they pay. (read-only)
OrderService | createResaleListing | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createResaleListing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResource | request | id | string (uuid) | yes
VenueOpsService | createResource | request | code | string | yes
VenueOpsService | createResource | request | name | string | yes
VenueOpsService | createResource | request | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | createResource | request | venueId | string (uuid) | yes
VenueOpsService | createResource | request | scopePath | string
VenueOpsService | createResource | request | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | createResource | request | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | createResource | request | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | createResource | request | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | createResource | request | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | createResource | request | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | createResource | request | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | createResource | request | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | createResource | request | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | createResource | request | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | request | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | request | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | createResource | request | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResource | request | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResource | request | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResource | request | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResource | request | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | createResource | request | isActive | boolean |  | (default True)
VenueOpsService | createResource | response | id | string (uuid) | yes
VenueOpsService | createResource | response | code | string | yes
VenueOpsService | createResource | response | name | string | yes
VenueOpsService | createResource | response | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | createResource | response | venueId | string (uuid) | yes
VenueOpsService | createResource | response | scopePath | string
VenueOpsService | createResource | response | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | createResource | response | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | createResource | response | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | createResource | response | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | createResource | response | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | createResource | response | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | createResource | response | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | createResource | response | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | createResource | response | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | createResource | response | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | response | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | response | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | createResource | response | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResource | response | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResource | response | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResource | response | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResource | response | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | createResource | response | isActive | boolean |  | (default True)
VenueOpsService | createResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourceBlock | request | id | string (uuid)
VenueOpsService | createResourceBlock | request | resourceId | string (uuid) | yes
VenueOpsService | createResourceBlock | request | from | string (date-time) | yes
VenueOpsService | createResourceBlock | request | to | string (date-time) | yes
VenueOpsService | createResourceBlock | request | reason | enum (setup, teardown, maintenance, blackout, closed, operational, training) | yes
VenueOpsService | createResourceBlock | request | note | string |  | (nullable)
VenueOpsService | createResourceBlock | request | createdBy | string (uuid) |  | (nullable)
VenueOpsService | createResourceBlock | request | scopePath | string
VenueOpsService | createResourceBlock | response | id | string (uuid)
VenueOpsService | createResourceBlock | response | resourceId | string (uuid) | yes
VenueOpsService | createResourceBlock | response | from | string (date-time) | yes
VenueOpsService | createResourceBlock | response | to | string (date-time) | yes
VenueOpsService | createResourceBlock | response | reason | enum (setup, teardown, maintenance, blackout, closed, operational, training) | yes
VenueOpsService | createResourceBlock | response | note | string |  | (nullable)
VenueOpsService | createResourceBlock | response | createdBy | string (uuid) |  | (nullable)
VenueOpsService | createResourceBlock | response | scopePath | string
VenueOpsService | createResourceBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourceHold | request | id | string (uuid) | yes | Client-generated UUIDv7, as a seat hold's.
VenueOpsService | createResourceHold | request | mapId | string (uuid) | yes | The published venue map the guest picked from.
VenueOpsService | createResourceHold | request | resourceIds | array of string (uuid) | yes | Placed resources on that map, e.g. (min items 1; max items 10)
VenueOpsService | createResourceHold | request | from | string (date-time) | yes
VenueOpsService | createResourceHold | request | to | string (date-time) | yes
VenueOpsService | createResourceHold | request | partySize | integer |  | Checked against each resource's capacity; above it the hold is refused 422. (min 1; nullable)
VenueOpsService | createResourceHold | request | ttlSeconds | integer |  | 8 minutes by default, 30 in all with extensions (audit R169), as a seat hold. (min 60; max 1800; default 480)
VenueOpsService | createResourceHold | request | subjectId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | id | string (uuid) | yes
VenueOpsService | createResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | createResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | createResourceHold | response | from | string (date-time) | yes
VenueOpsService | createResourceHold | response | to | string (date-time) | yes
VenueOpsService | createResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | createResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | createResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | createResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | createResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | createResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | createResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | createResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourcePackage | request | id | string (uuid)
VenueOpsService | createResourcePackage | request | code | string | yes
VenueOpsService | createResourcePackage | request | name | string | yes
VenueOpsService | createResourcePackage | request | description | string |  | (nullable)
VenueOpsService | createResourcePackage | request | applicableVenueIds | array of string (uuid)
VenueOpsService | createResourcePackage | request | components | array of ResourceRequirement
VenueOpsService | createResourcePackage | request | components[].id | string (uuid)
VenueOpsService | createResourcePackage | request | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | request | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | request | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | createResourcePackage | request | components[].quantity | integer | yes | (default 1)
VenueOpsService | createResourcePackage | request | components[].mandatory | boolean |  | (default True)
VenueOpsService | createResourcePackage | request | components[].requiredQualifications | array of string
VenueOpsService | createResourcePackage | request | components[].requiredAttributes | object
VenueOpsService | createResourcePackage | request | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | createResourcePackage | request | components[].scopePath | string
VenueOpsService | createResourcePackage | request | allocationPriority | integer |  | (default 0)
VenueOpsService | createResourcePackage | request | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | request | effectiveTo | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | request | minimumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | request | maximumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | request | requiresApproval | boolean |  | (default False)
VenueOpsService | createResourcePackage | request | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourcePackage | request | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourcePackage | request | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourcePackage | request | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourcePackage | request | scopePath | string
VenueOpsService | createResourcePackage | response | id | string (uuid)
VenueOpsService | createResourcePackage | response | code | string | yes
VenueOpsService | createResourcePackage | response | name | string | yes
VenueOpsService | createResourcePackage | response | description | string |  | (nullable)
VenueOpsService | createResourcePackage | response | applicableVenueIds | array of string (uuid)
VenueOpsService | createResourcePackage | response | components | array of ResourceRequirement
VenueOpsService | createResourcePackage | response | components[].id | string (uuid)
VenueOpsService | createResourcePackage | response | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | response | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | response | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | createResourcePackage | response | components[].quantity | integer | yes | (default 1)
VenueOpsService | createResourcePackage | response | components[].mandatory | boolean |  | (default True)
VenueOpsService | createResourcePackage | response | components[].requiredQualifications | array of string
VenueOpsService | createResourcePackage | response | components[].requiredAttributes | object
VenueOpsService | createResourcePackage | response | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | createResourcePackage | response | components[].scopePath | string
VenueOpsService | createResourcePackage | response | allocationPriority | integer |  | (default 0)
VenueOpsService | createResourcePackage | response | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | response | effectiveTo | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | response | minimumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | response | maximumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | response | requiresApproval | boolean |  | (default False)
VenueOpsService | createResourcePackage | response | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourcePackage | response | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourcePackage | response | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourcePackage | response | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourcePackage | response | scopePath | string
VenueOpsService | createResourcePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createRetailReturn | request | id | string (uuid) | yes
RetailService | createRetailReturn | request | saleId | string | yes
RetailService | createRetailReturn | request | lines | array of object | yes | (min items 1)
RetailService | createRetailReturn | request | lines[].lineId | string | yes
RetailService | createRetailReturn | request | lines[].quantity | integer | yes | (min 1)
RetailService | createRetailReturn | request | lines[].condition | ReturnCondition: enum (resaleable, opened, damaged, faulty, missingParts) | yes | Determines whether stock is restored or written off.
RetailService | createRetailReturn | request | lines[].serialNumbers | array of string
RetailService | createRetailReturn | request | lines[].note | string |  | (max length 200)
RetailService | createRetailReturn | request | reason | ReturnReason: enum (changedMind, wrongSize, wrongItem, faulty, damagedInTransit, duplicatePurchase, giftReturn, other) | yes
RetailService | createRetailReturn | request | refundTender | string |  | Defaults to the original tender.
RetailService | createRetailReturn | request | secondaryAuthorisation | object |  | Required above the outlet's self-authorise limit.
RetailService | createRetailReturn | request | secondaryAuthorisation.principalId | string (uuid) | yes | The supervisor signing.
RetailService | createRetailReturn | request | secondaryAuthorisation.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
RetailService | createRetailReturn | request | recordedAt | string (date-time) | yes
RetailService | createRetailReturn | response | id | string | yes
RetailService | createRetailReturn | response | returnNumber | string
RetailService | createRetailReturn | response | saleId | string | yes
RetailService | createRetailReturn | response | refundId | string |  | The refund raised in the Order & Payment context. (nullable)
RetailService | createRetailReturn | response | lines | array of object | yes
RetailService | createRetailReturn | response | lines[].lineId | string
RetailService | createRetailReturn | response | lines[].merchandiseId | string (uuid)
RetailService | createRetailReturn | response | lines[].name | string
RetailService | createRetailReturn | response | lines[].quantity | integer
RetailService | createRetailReturn | response | lines[].condition | ReturnCondition: enum (resaleable, opened, damaged, faulty, missingParts) |  | Determines whether stock is restored or written off.
RetailService | createRetailReturn | response | lines[].wasRestocked | boolean |  | False for opened, damaged or faulty goods, which are written off with a reason rather than silently absent.
RetailService | createRetailReturn | response | lines[].refundAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailReturn | response | lines[].refundAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailReturn | response | lines[].refundAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailReturn | response | lines[].refundAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailReturn | response | reason | ReturnReason: enum (changedMind, wrongSize, wrongItem, faulty, damagedInTransit, duplicatePurchase, giftReturn, other)
RetailService | createRetailReturn | response | refundAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createRetailReturn | response | refundAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailReturn | response | refundAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailReturn | response | refundAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailReturn | response | refundTender | string
RetailService | createRetailReturn | response | restockedQuantity | integer | yes
RetailService | createRetailReturn | response | writtenOffQuantity | integer | yes
RetailService | createRetailReturn | response | status | object | yes | (read-only)
RetailService | createRetailReturn | response | refusedReason | object |  | Set when status is refused, null otherwise. (read-only; nullable)
RetailService | createRetailReturn | response | acceptedByPrincipalId | string (uuid) |  | Who took the return at the desk.
RetailService | createRetailReturn | response | secondaryPrincipalId | string (uuid) |  | (nullable)
RetailService | createRetailReturn | response | createdAt | string (date-time) | yes
RetailService | createRetailReturn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createRetailSale | request | id | string (uuid) | yes
RetailService | createRetailSale | request | outletId | string (uuid) | yes
RetailService | createRetailSale | request | shiftId | string
RetailService | createRetailSale | request | subjectId | string (uuid)
RetailService | createRetailSale | request | lines | array of CreateRetailSaleLine | yes | (min items 1)
RetailService | createRetailSale | request | lines[].id | string (uuid) | yes
RetailService | createRetailSale | request | lines[].merchandiseId | string (uuid) | yes
RetailService | createRetailSale | request | lines[].quantity | integer | yes | (min 1)
RetailService | createRetailSale | request | lines[].serialNumbers | array of string |  | Required where the item is serialised.
RetailService | createRetailSale | request | lines[].overridePrice | object |  | Manual price override.
RetailService | createRetailSale | request | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | request | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | request | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | request | lines[].overrideReason | string |  | (max length 200)
RetailService | createRetailSale | request | couponCodes | array of string
RetailService | createRetailSale | request | recordedAt | string (date-time) | yes
RetailService | createRetailSale | response | id | string | yes
RetailService | createRetailSale | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | createRetailSale | response | orderId | string | yes | The order in the Order & Payment context.
RetailService | createRetailSale | response | outletId | string (uuid) | yes
RetailService | createRetailSale | response | shiftId | string |  | (nullable)
RetailService | createRetailSale | response | subjectId | string (uuid) |  | (nullable)
RetailService | createRetailSale | response | lines | array of object | yes
RetailService | createRetailSale | response | lines[].lineId | string
RetailService | createRetailSale | response | lines[].merchandiseId | string (uuid)
RetailService | createRetailSale | response | lines[].name | string
RetailService | createRetailSale | response | lines[].quantity | integer
RetailService | createRetailSale | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].serialNumbers | array of string
RetailService | createRetailSale | response | lines[].returnedQuantity | integer
RetailService | createRetailSale | response | lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | createRetailSale | response | lines[].notReturnableReason | string |  | (nullable)
RetailService | createRetailSale | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | reprintCount | integer
RetailService | createRetailSale | response | createdAt | string (date-time) | yes
RetailService | createRetailSale | response | recordedAt | string (date-time)
RetailService | createRetailSale | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | createRole | request | code | string | yes | Unique within the tenant, compared case-insensitively (decided 28 September, audit R108). (max length 64; pattern ^[A-Za-z0-9_-]+$)
IdentityService | createRole | request | name | string | yes | (max length 200)
IdentityService | createRole | request | description | string |  | (max length 500)
IdentityService | createRole | response | id | string (uuid) | yes
IdentityService | createRole | response | code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | createRole | response | name | string | yes
IdentityService | createRole | response | description | string
IdentityService | createRole | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | createRole | response | inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | createRole | response | isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | createRole | response | principalCount | integer
IdentityService | createRole | response | grantCount | integer
IdentityService | createRole | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createRotaAssignment | request | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | createRotaAssignment | request | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | createRotaAssignment | request | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | createRotaAssignment | request | labourCost | object |  | Cost at the point of scheduling.
TenancyService | createRotaAssignment | request | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createRotaAssignment | request | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createRotaAssignment | request | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createRotaAssignment | request | id | string (uuid) |  | (read-only)
TenancyService | createRotaAssignment | request | principalId | string (uuid) | yes
TenancyService | createRotaAssignment | request | displayName | string |  | (read-only)
TenancyService | createRotaAssignment | request | venueId | string (uuid) | yes
TenancyService | createRotaAssignment | request | departmentId | string (uuid) |  | (nullable)
TenancyService | createRotaAssignment | request | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | createRotaAssignment | request | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | createRotaAssignment | request | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | createRotaAssignment | request | startsAt | string (date-time) | yes
TenancyService | createRotaAssignment | request | endsAt | string (date-time) | yes
TenancyService | createRotaAssignment | request | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | createRotaAssignment | request | breakMinutes | integer |  | (nullable)
TenancyService | createRotaAssignment | request | note | string |  | (nullable)
TenancyService | createRotaAssignment | response | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | createRotaAssignment | response | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | createRotaAssignment | response | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | createRotaAssignment | response | labourCost | object |  | Cost at the point of scheduling.
TenancyService | createRotaAssignment | response | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createRotaAssignment | response | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createRotaAssignment | response | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createRotaAssignment | response | id | string (uuid) |  | (read-only)
TenancyService | createRotaAssignment | response | principalId | string (uuid) | yes
TenancyService | createRotaAssignment | response | displayName | string |  | (read-only)
TenancyService | createRotaAssignment | response | venueId | string (uuid) | yes
TenancyService | createRotaAssignment | response | departmentId | string (uuid) |  | (nullable)
TenancyService | createRotaAssignment | response | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | createRotaAssignment | response | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | createRotaAssignment | response | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | createRotaAssignment | response | startsAt | string (date-time) | yes
TenancyService | createRotaAssignment | response | endsAt | string (date-time) | yes
TenancyService | createRotaAssignment | response | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | createRotaAssignment | response | breakMinutes | integer |  | (nullable)
TenancyService | createRotaAssignment | response | note | string |  | (nullable)
TenancyService | createRotaAssignment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createSaleBoard | request | id | string (uuid) | yes | (read-only)
TenancyService | createSaleBoard | request | code | string | yes | (max length 64)
TenancyService | createSaleBoard | request | name | string | yes | (max length 200)
TenancyService | createSaleBoard | request | venueId | string (uuid) | yes
TenancyService | createSaleBoard | request | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | createSaleBoard | request | pages | array of object | yes | (min items 1)
TenancyService | createSaleBoard | request | pages[].name | string | yes
TenancyService | createSaleBoard | request | pages[].sortOrder | integer | yes
TenancyService | createSaleBoard | request | pages[].tiles | array of object | yes
TenancyService | createSaleBoard | request | pages[].tiles[].position | integer | yes
TenancyService | createSaleBoard | request | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | createSaleBoard | request | pages[].tiles[].variantId | string (uuid) |  | (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].label | string
TenancyService | createSaleBoard | request | pages[].tiles[].colour | string |  | (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | createSaleBoard | request | isActive | boolean
TenancyService | createSaleBoard | response | id | string (uuid) | yes | (read-only)
TenancyService | createSaleBoard | response | code | string | yes | (max length 64)
TenancyService | createSaleBoard | response | name | string | yes | (max length 200)
TenancyService | createSaleBoard | response | venueId | string (uuid) | yes
TenancyService | createSaleBoard | response | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | createSaleBoard | response | pages | array of object | yes | (min items 1)
TenancyService | createSaleBoard | response | pages[].name | string | yes
TenancyService | createSaleBoard | response | pages[].sortOrder | integer | yes
TenancyService | createSaleBoard | response | pages[].tiles | array of object | yes
TenancyService | createSaleBoard | response | pages[].tiles[].position | integer | yes
TenancyService | createSaleBoard | response | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | createSaleBoard | response | pages[].tiles[].variantId | string (uuid) |  | (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].label | string
TenancyService | createSaleBoard | response | pages[].tiles[].colour | string |  | (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | createSaleBoard | response | isActive | boolean
TenancyService | createSaleBoard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createSeatCategory | request | code | string | yes | (max length 64)
CatalogueService | createSeatCategory | request | name | string | yes | (max length 200)
CatalogueService | createSeatCategory | request | venueId | string (uuid) | yes
CatalogueService | createSeatCategory | request | displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
CatalogueService | createSeatCategory | request | rank | integer |  | Ordering for best-seat assignment.
CatalogueService | createSeatCategory | request | priceBands | array of SeatPriceBand |  | The category's price bands (decided 28 September, audit R275 (d)).
CatalogueService | createSeatCategory | request | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | request | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | request | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | createSeatCategory | request | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | createSeatCategory | request | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | createSeatCategory | request | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatCategory | request | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatCategory | request | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatCategory | request | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatCategory | request | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | createSeatCategory | request | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | createSeatCategory | request | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | createSeatCategory | request | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | createSeatCategory | response | id | string (uuid) | yes
CatalogueService | createSeatCategory | response | code | string | yes
CatalogueService | createSeatCategory | response | name | string | yes
CatalogueService | createSeatCategory | response | venueId | string (uuid) | yes
CatalogueService | createSeatCategory | response | displayColour | string |  | (nullable)
CatalogueService | createSeatCategory | response | rank | integer | yes | Ordering for best-seat assignment.
CatalogueService | createSeatCategory | response | seatCount | integer
CatalogueService | createSeatCategory | response | priceBands | array of SeatPriceBand |  | What a seat in this category costs, by band (decided 28 September, audit R275 (d), from the BO-1045 pack).
CatalogueService | createSeatCategory | response | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | response | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | response | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | createSeatCategory | response | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | createSeatCategory | response | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | createSeatCategory | response | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatCategory | response | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatCategory | response | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatCategory | response | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatCategory | response | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | createSeatCategory | response | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | createSeatCategory | response | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | createSeatCategory | response | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | createSeatCategory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createSeatCategory | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | createSeatHold | request | id | string (uuid) | yes
CatalogueService | createSeatHold | request | performanceId | string (uuid) | yes
CatalogueService | createSeatHold | request | seatIds | array of string | yes | 50 is the ceiling of the venue setting, not the limit a caller gets. (min items 1; max items 50)
CatalogueService | createSeatHold | request | ttlSeconds | integer |  | 8 minutes by default, extendable to 30 in all (decided 28 September, audit R169). (min 60; max 1800; default 480)
CatalogueService | createSeatHold | request | subjectId | string (uuid)
CatalogueService | createSeatHold | response | id | string | yes
CatalogueService | createSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | createSeatHold | response | seatIds | array of string | yes
CatalogueService | createSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | createSeatHold | response | status | enum (held, converted, released, expired) | yes
CatalogueService | createSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | createSeatHold | response | extensionCount | integer
CatalogueService | createSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | createSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | createSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createSegment | request | name | string | yes | (max length 200)
MarketingService | createSegment | request | description | string |  | (max length 1000)
MarketingService | createSegment | request | venueId | string (uuid)
MarketingService | createSegment | request | match | enum (all, any) |  | (default all)
MarketingService | createSegment | request | criteria | array of SegmentCriterion | yes | (min items 1)
MarketingService | createSegment | request | criteria[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createSegment | request | criteria[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createSegment | request | criteria[].value | object
MarketingService | createSegment | request | criteria[].values | array of object
MarketingService | createSegment | request | excludeSegmentIds | array of string (uuid)
MarketingService | createSegment | response | name | string | yes | (max length 200)
MarketingService | createSegment | response | description | string |  | (max length 1000)
MarketingService | createSegment | response | venueId | string (uuid)
MarketingService | createSegment | response | match | enum (all, any) |  | (default all)
MarketingService | createSegment | response | criteria | array of SegmentCriterion | yes | (min items 1)
MarketingService | createSegment | response | criteria[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createSegment | response | criteria[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createSegment | response | criteria[].value | object
MarketingService | createSegment | response | criteria[].values | array of object
MarketingService | createSegment | response | excludeSegmentIds | array of string (uuid)
MarketingService | createSegment | response | id | string (uuid) | yes
MarketingService | createSegment | response | lastEvaluatedSize | integer |  | (nullable)
MarketingService | createSegment | response | lastEvaluatedAt | string (date-time) |  | (nullable)
MarketingService | createSegment | response | createdAt | string (date-time) | yes
MarketingService | createSegment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createTableReservation | request | id | string (uuid) |  | (read-only)
FnbService | createTableReservation | request | outletId | string (uuid) | yes
FnbService | createTableReservation | request | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservation | request | guestName | string
FnbService | createTableReservation | request | contactPoint | string
FnbService | createTableReservation | request | partySize | integer | yes | (min 1)
FnbService | createTableReservation | request | startsAt | string (date-time) | yes
FnbService | createTableReservation | request | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservation | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservation | request | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservation | request | tables[].tableId | string (uuid) | yes
FnbService | createTableReservation | request | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservation | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservation | request | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservation | request | notes | string |  | Allergies
FnbService | createTableReservation | request | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservation | request | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservation | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservation | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservation | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservation | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservation | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservation | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservation | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservation | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservation | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservation | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservation | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservation | request | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | createTableReservation | response | outletId | string (uuid) | yes
FnbService | createTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservation | response | guestName | string
FnbService | createTableReservation | response | contactPoint | string
FnbService | createTableReservation | response | partySize | integer | yes | (min 1)
FnbService | createTableReservation | response | startsAt | string (date-time) | yes
FnbService | createTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | createTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservation | response | notes | string |  | Allergies
FnbService | createTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createTaxCode | request | code | string | yes | (max length 64)
LedgerService | createTaxCode | request | name | string | yes | (max length 200)
LedgerService | createTaxCode | request | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createTaxCode | request | rate | number | yes | (min 0; max 100)
LedgerService | createTaxCode | request | compoundOnTaxCodeId | string (uuid)
LedgerService | createTaxCode | request | isInclusive | boolean |  | (default False)
LedgerService | createTaxCode | request | accountId | string (uuid) | yes
LedgerService | createTaxCode | request | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | createTaxCode | response | id | string (uuid) | yes
LedgerService | createTaxCode | response | code | string | yes | (max length 64)
LedgerService | createTaxCode | response | name | string | yes | (max length 200)
LedgerService | createTaxCode | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createTaxCode | response | appliesTo | array of enum (goods, services, admission, food, accommodation, donation, gratuity, fee) |  | What this code covers, and donation is why the field exists (CF-84).
LedgerService | createTaxCode | response | rate | number | yes | (min 0; max 100)
LedgerService | createTaxCode | response | compoundOnTaxCodeId | string (uuid) |  | When set, this tax applies to the base plus the referenced tax, not to the base alone. (nullable)
LedgerService | createTaxCode | response | isInclusive | boolean |  | True when the displayed price already contains this tax.
LedgerService | createTaxCode | response | accountId | string (uuid)
LedgerService | createTaxCode | response | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | createTaxCode | response | effectiveTo | string (date) |  | A day in the region's time zone, local midnight to local midnight. (nullable)
LedgerService | createTaxCode | response | isActive | boolean | yes
LedgerService | createTaxCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createTenant | request | code | string | yes | (max length 64; pattern ^[a-z0-9-]+$)
PlatformService | createTenant | request | name | string | yes | (max length 200)
PlatformService | createTenant | request | billingEmail | string | yes
PlatformService | createTenant | request | billingAddress | string |  | (max length 500)
PlatformService | createTenant | request | accountManagerPrincipalId | string (uuid)
PlatformService | createTenant | request | planId | string (uuid)
PlatformService | createTenant | response | id | string (uuid) | yes
PlatformService | createTenant | response | code | string | yes
PlatformService | createTenant | response | name | string | yes
PlatformService | createTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | createTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | createTenant | response | suspensionReason | string |  | (nullable)
PlatformService | createTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | createTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | createTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | createTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | createTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | createTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | planName | string |  | (nullable)
PlatformService | createTenant | response | cellCount | integer
PlatformService | createTenant | response | venueCount | integer
PlatformService | createTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | createTenant | response | billingEmail | string
PlatformService | createTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | createTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | createdAt | string (date-time) | yes
PlatformService | createTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | createTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createTicketTemplate | request | name | string |  | (max length 200)
OrderService | createTicketTemplate | request | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms)
OrderService | createTicketTemplate | request | isRecyclable | boolean
OrderService | createTicketTemplate | request | recycleAfterDays | integer |  | (min 0; nullable)
OrderService | createTicketTemplate | request | appliesToProductKinds | array of string
OrderService | createTicketTemplate | request | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | createTicketTemplate | request | selectionPriority | integer
OrderService | createTicketTemplate | request | layoutRef | string |  | The artwork, as a media-asset reference.
OrderService | createTicketTemplate | request | localeVariants | object
OrderService | createTicketTemplate | request | isActive | boolean
OrderService | createTicketTemplate | response | id | string (uuid) | yes
OrderService | createTicketTemplate | response | name | string | yes
OrderService | createTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | createTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | createTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | createTicketTemplate | response | appliesToProductKinds | array of string
OrderService | createTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | createTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | createTicketTemplate | response | layoutRef | string
OrderService | createTicketTemplate | response | localeVariants | object
OrderService | createTicketTemplate | response | isActive | boolean | yes
OrderService | createTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportPassType | request | venueId | string (uuid) | yes
VenueOpsService | createTransportPassType | request | code | string | yes | (max length 32)
VenueOpsService | createTransportPassType | request | name | LocalisedText | yes
VenueOpsService | createTransportPassType | request | description | LocalisedText
VenueOpsService | createTransportPassType | request | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | createTransportPassType | request | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | createTransportPassType | request | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | createTransportPassType | request | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | createTransportPassType | request | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | createTransportPassType | request | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | createTransportPassType | request | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | createTransportPassType | response | venueId | string (uuid) | yes
VenueOpsService | createTransportPassType | response | code | string | yes | (max length 32)
VenueOpsService | createTransportPassType | response | name | LocalisedText | yes
VenueOpsService | createTransportPassType | response | description | LocalisedText
VenueOpsService | createTransportPassType | response | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | createTransportPassType | response | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | createTransportPassType | response | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | createTransportPassType | response | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | createTransportPassType | response | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | createTransportPassType | response | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | createTransportPassType | response | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | createTransportPassType | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportPassType | response | active | boolean | yes | (default True)
VenueOpsService | createTransportPassType | response | catalogueProductId | string (uuid) |  | The catalogue openDated product this pass is sold as. (read-only)
VenueOpsService | createTransportPassType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportRoute | request | venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | request | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | createTransportRoute | request | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | createTransportRoute | request | name | LocalisedText | yes
VenueOpsService | createTransportRoute | request | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | createTransportRoute | request | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | createTransportRoute | request | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | createTransportRoute | request | stops | array of RouteStopInput | yes | (min items 2; max items 100)
VenueOpsService | createTransportRoute | request | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | request | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | createTransportRoute | request | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | request | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | createTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | createTransportRoute | response | name | LocalisedText | yes
VenueOpsService | createTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | createTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | createTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | createTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | createTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | createTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | createTransportRoute | response | stops[].station | Station
VenueOpsService | createTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | createTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | createTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | createTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | createTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | createTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | createTransportRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportStation | request | venueId | string (uuid) | yes
VenueOpsService | createTransportStation | request | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportStation | request | name | LocalisedText | yes
VenueOpsService | createTransportStation | request | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportStation | request | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportStation | request | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportStation | response | venueId | string (uuid) | yes
VenueOpsService | createTransportStation | response | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportStation | response | name | LocalisedText | yes
VenueOpsService | createTransportStation | response | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportStation | response | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportStation | response | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportStation | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportStation | response | active | boolean | yes | (default True)
VenueOpsService | createTransportStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportTimetable | request | name | string | yes | (max length 120)
VenueOpsService | createTransportTimetable | request | validFrom | string (date) | yes
VenueOpsService | createTransportTimetable | request | validTo | string (date) |  | (nullable)
VenueOpsService | createTransportTimetable | request | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | createTransportTimetable | request | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | createTransportTimetable | request | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | createTransportTimetable | request | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | createTransportTimetable | request | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createTransportTimetable | request | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | createTransportTimetable | response | name | string | yes | (max length 120)
VenueOpsService | createTransportTimetable | response | validFrom | string (date) | yes
VenueOpsService | createTransportTimetable | response | validTo | string (date) |  | (nullable)
VenueOpsService | createTransportTimetable | response | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | createTransportTimetable | response | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | createTransportTimetable | response | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | createTransportTimetable | response | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | createTransportTimetable | response | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createTransportTimetable | response | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | createTransportTimetable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportTimetable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportTimetable | response | status | TransportTimetableStatus: enum (draft, published, superseded, withdrawn) | yes
VenueOpsService | createTransportTimetable | response | publishedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | createTransportTimetable | response | releasedThrough | string (date) |  | The last date whose departures have been generated. (read-only; nullable)
VenueOpsService | createTransportTimetable | response | supersededById | string (uuid) |  | (read-only; nullable)
VenueOpsService | createTransportTimetable | param (path) | routeId | string (uuid) | yes
VenueOpsService | createTransportTimetable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createUpload | request | filename | string | yes | (max length 256)
VenueOpsService | createUpload | request | contentType | string | yes
VenueOpsService | createUpload | request | sizeBytes | integer | yes | (min 1)
VenueOpsService | createUpload | request | venueId | string (uuid)
VenueOpsService | createUpload | response | id | string (uuid) |  | Added 20 August. (read-only)
VenueOpsService | createUpload | response | uploadId | string (uuid) | yes
VenueOpsService | createUpload | response | uploadUrl | string | yes | Signed.
VenueOpsService | createUpload | response | method | enum (PUT, POST) | yes
VenueOpsService | createUpload | response | headers | object
VenueOpsService | createUpload | response | maxSizeBytes | integer
VenueOpsService | createUpload | response | expiresAt | string (date-time) | yes
VenueOpsService | createUpload | response | filename | string
VenueOpsService | createUpload | response | contentType | string
VenueOpsService | createUpload | response | sizeBytes | integer
VenueOpsService | createUpload | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createUpload | response | assetId | string (uuid) |  | The asset this upload became — created by completeUpload, or the asset whose file replaceMediaAsset swapped. (read-only; nullable)
VenueOpsService | createUpload | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createVenueMap | request | id | string (uuid) | yes | (read-only)
VenueOpsService | createVenueMap | request | name | string | yes
VenueOpsService | createVenueMap | request | venueId | string (uuid) | yes
VenueOpsService | createVenueMap | request | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | createVenueMap | request | kind | enum (park, floor, zone, parking)
VenueOpsService | createVenueMap | request | floorLevel | integer |  | (nullable)
VenueOpsService | createVenueMap | request | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | createVenueMap | request | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | createVenueMap | request | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | createVenueMap | request | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | createVenueMap | request | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | createVenueMap | request | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | createVenueMap | request | baseImageAlignment.imageWidthPx | integer
VenueOpsService | createVenueMap | request | baseImageAlignment.imageHeightPx | integer
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].planX | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].planY | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].imageX | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].imageY | number
VenueOpsService | createVenueMap | request | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | createVenueMap | request | boundsGeoJson | string |  | (nullable)
VenueOpsService | createVenueMap | request | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | createVenueMap | response | id | string (uuid) | yes | (read-only)
VenueOpsService | createVenueMap | response | name | string | yes
VenueOpsService | createVenueMap | response | venueId | string (uuid) | yes
VenueOpsService | createVenueMap | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | createVenueMap | response | kind | enum (park, floor, zone, parking)
VenueOpsService | createVenueMap | response | floorLevel | integer |  | (nullable)
VenueOpsService | createVenueMap | response | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | createVenueMap | response | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | createVenueMap | response | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | createVenueMap | response | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | createVenueMap | response | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | createVenueMap | response | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | createVenueMap | response | baseImageAlignment.imageWidthPx | integer
VenueOpsService | createVenueMap | response | baseImageAlignment.imageHeightPx | integer
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].planX | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].planY | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].imageX | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].imageY | number
VenueOpsService | createVenueMap | response | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | createVenueMap | response | boundsGeoJson | string |  | (nullable)
VenueOpsService | createVenueMap | response | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | createVenueMap | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideAiInsight | request | decision | enum (review, accept, reject, actioned) | yes
AiService | decideAiInsight | request | reason | string |  | (max length 1000; nullable)
AiService | decideAiInsight | request | actionRef | string |  | (nullable)
AiService | decideAiInsight | response | id | string (uuid) |  | (read-only)
AiService | decideAiInsight | response | kind | enum (anomaly, forecastDeviation, trend, opportunity, executiveSummary, rootCause, forecastThreshold, marketingRecommendation) | yes
AiService | decideAiInsight | response | detectorId | string (uuid) |  | (nullable)
AiService | decideAiInsight | response | metricKey | string |  | (nullable)
AiService | decideAiInsight | response | subjectKind | enum (campaign, journey, forecastDefinition, venue) |  | What the insight is about where it is not a KPI (29 September, build): a marketing-crm campaign or journey for marketingRecommendation, a forecast definition for forecastThreshold. (nullable)
AiService | decideAiInsight | response | subjectRef | string |  | (nullable)
AiService | decideAiInsight | response | recommendedAction | object |  | For marketingRecommendation: {recommendation, parameters} as AiMarketingRecommendation. (nullable)
AiService | decideAiInsight | response | expectedImpact | object |  | A range on a named metric (metric, low, high), never a single number (design 5.6). (nullable)
AiService | decideAiInsight | response | title | string | yes
AiService | decideAiInsight | response | narrative | string |  | (nullable)
AiService | decideAiInsight | response | evidence | array of AiEvidenceItem |  | The evidence of one decision record, stored with it.
AiService | decideAiInsight | response | evidence[].label | enum (source, derived, modelInferred) | yes
AiService | decideAiInsight | response | evidence[].kind | string | yes | What it is: feature, rule, document, metric, transaction, candidateSet.
AiService | decideAiInsight | response | evidence[].ref | string |  | Where it came from: a table and id, a document chunk, a metric key. (nullable)
AiService | decideAiInsight | response | evidence[].name | string
AiService | decideAiInsight | response | evidence[].value | object |  | (nullable)
AiService | decideAiInsight | response | evidence[].observedAt | string (date-time) |  | (nullable)
AiService | decideAiInsight | response | magnitude | number |  | (nullable)
AiService | decideAiInsight | response | priority | enum (low, medium, high, critical)
AiService | decideAiInsight | response | correlationKey | string |  | (nullable)
AiService | decideAiInsight | response | status | enum (new, reviewed, accepted, rejected, actioned, measured) | yes | (read-only)
AiService | decideAiInsight | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | decideAiInsight | response | decidedAt | string (date-time) |  | (read-only; nullable)
AiService | decideAiInsight | response | actionRef | string |  | (nullable)
AiService | decideAiInsight | response | measuredImpact | object |  | (read-only; nullable)
AiService | decideAiInsight | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | decideAiInsight | response | detectedAt | string (date-time) |  | (read-only)
AiService | decideAiInsight | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | decideAiInsight | param (path) | insightId | string (uuid) | yes
AiService | decideAiInsight | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | decideApprovalRequest | request | decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | decideApprovalRequest | request | comment | string |  | (max length 1000)
TenancyService | decideApprovalRequest | request | reason | string |  | Required on rejection. (max length 500)
TenancyService | decideApprovalRequest | request | stepUpToken | string |  | Where the rule demands MFA (11.1.60).
TenancyService | decideApprovalRequest | request | signature | string |  | 11.1.57.
TenancyService | decideApprovalRequest | response | id | string | yes
TenancyService | decideApprovalRequest | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | decideApprovalRequest | response | rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | decideApprovalRequest | response | outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | decideApprovalRequest | response | allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | decideApprovalRequest | response | reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | decideApprovalRequest | response | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | decideApprovalRequest | response | subjectContract | string
TenancyService | decideApprovalRequest | response | subjectType | string
TenancyService | decideApprovalRequest | response | subjectId | string
TenancyService | decideApprovalRequest | response | scopePath | string
TenancyService | decideApprovalRequest | response | summary | string
TenancyService | decideApprovalRequest | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | decideApprovalRequest | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | decideApprovalRequest | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | decideApprovalRequest | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | decideApprovalRequest | response | justification | string |  | (nullable)
TenancyService | decideApprovalRequest | response | requestedByPrincipalId | string (uuid) | yes
TenancyService | decideApprovalRequest | response | matrixVersion | integer
TenancyService | decideApprovalRequest | response | mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | decideApprovalRequest | response | currentLevel | integer
TenancyService | decideApprovalRequest | response | totalLevels | integer
TenancyService | decideApprovalRequest | response | pendingApprovers | array of object
TenancyService | decideApprovalRequest | response | pendingApprovers[].principalId | string (uuid)
TenancyService | decideApprovalRequest | response | pendingApprovers[].displayName | string
TenancyService | decideApprovalRequest | response | pendingApprovers[].isDelegate | boolean
TenancyService | decideApprovalRequest | response | decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | decideApprovalRequest | response | decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | decideApprovalRequest | response | decisions[].level | integer | yes
TenancyService | decideApprovalRequest | response | decisions[].principalId | string (uuid) | yes
TenancyService | decideApprovalRequest | response | decisions[].displayName | string
TenancyService | decideApprovalRequest | response | decisions[].isDelegate | boolean
TenancyService | decideApprovalRequest | response | decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].decision | enum (approve, reject) | yes
TenancyService | decideApprovalRequest | response | decisions[].comment | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].reason | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].usedMfa | boolean
TenancyService | decideApprovalRequest | response | decisions[].signatureRef | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].decidedAt | string (date-time) | yes
TenancyService | decideApprovalRequest | response | escalations | array of object |  | 11.1.48.
TenancyService | decideApprovalRequest | response | escalations[].at | string (date-time)
TenancyService | decideApprovalRequest | response | escalations[].reason | string
TenancyService | decideApprovalRequest | response | escalations[].fromLevel | integer
TenancyService | decideApprovalRequest | response | escalations[].toLevel | integer
TenancyService | decideApprovalRequest | response | escalations[].wasAutomatic | boolean
TenancyService | decideApprovalRequest | response | resubmittedFromId | string |  | (nullable)
TenancyService | decideApprovalRequest | response | reopenedFromId | string |  | (nullable)
TenancyService | decideApprovalRequest | response | slaDueAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | slaBreached | boolean
TenancyService | decideApprovalRequest | response | expiresAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | requestedAt | string (date-time) | yes
TenancyService | decideApprovalRequest | response | completedAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | decideApprovalRequest | response | aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | decideApprovalRequest | response | aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion.action | enum (escalate, addBackupApprover, none)
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion.reason | string |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].code | string
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].contribution | number
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].detail | string |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | decideApprovalRequest | response | aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | decideApprovalRequest | response | aiAssessment.assessedAt | string (date-time)
TenancyService | decideApprovalRequest | param (path) | requestId | string (uuid) | yes
TenancyService | decideApprovalRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideOperationalRequirement | request | decision | enum (accept, modify, reject) | yes
AiService | decideOperationalRequirement | request | quantity | number |  | (nullable)
AiService | decideOperationalRequirement | request | note | string |  | (max length 1000; nullable)
AiService | decideOperationalRequirement | response | id | string (uuid) |  | (read-only)
AiService | decideOperationalRequirement | response | versionId | string (uuid) | yes
AiService | decideOperationalRequirement | response | kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …) | yes
AiService | decideOperationalRequirement | response | targetContract | string |  | The owning module that applies it: workforce, fnb, inventory, resources, access.
AiService | decideOperationalRequirement | response | subjectRef | string |  | A role, outlet, gate, item or resource type. (nullable)
AiService | decideOperationalRequirement | response | periodStart | string (date-time) | yes
AiService | decideOperationalRequirement | response | periodEnd | string (date-time)
AiService | decideOperationalRequirement | response | quantity | number | yes
AiService | decideOperationalRequirement | response | quantityP90 | number |  | The requirement at the forecast's 90th percentile, for planning to the busy case. (nullable)
AiService | decideOperationalRequirement | response | unit | string
AiService | decideOperationalRequirement | response | productivityStandard | object |  | The standard used, e.g. (nullable)
AiService | decideOperationalRequirement | response | status | enum (issued, accepted, modified, rejected, handedOver, expired) |  | (read-only)
AiService | decideOperationalRequirement | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | decideOperationalRequirement | response | decidedAt | string (date-time) |  | (read-only; nullable)
AiService | decideOperationalRequirement | response | decisionNote | string |  | (nullable)
AiService | decideOperationalRequirement | response | handoverRef | string |  | The owning module's record once handed over. (read-only; nullable)
AiService | decideOperationalRequirement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | decideOperationalRequirement | param (path) | requirementId | string (uuid) | yes
AiService | decideOperationalRequirement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | decideProductionAccess | request | decision | enum (approve, reject) | yes
PlatformService | decideProductionAccess | request | reason | string |  | (max length 1000; nullable)
PlatformService | decideProductionAccess | request | scopes | array of string |  | Narrow the requested scopes.
PlatformService | decideProductionAccess | request | credentialTtlDays | integer |  | (min 1; max 730; default 365)
PlatformService | decideProductionAccess | response | id | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | developerId | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | sandboxClientId | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | listingId | string (uuid) | yes
PlatformService | decideProductionAccess | response | scopes | array of string
PlatformService | decideProductionAccess | response | allowedTenantIds | array of string (uuid)
PlatformService | decideProductionAccess | response | ipAllowList | array of string
PlatformService | decideProductionAccess | response | note | string |  | (nullable)
PlatformService | decideProductionAccess | response | status | enum (pending, approved, rejected, withdrawn) | yes | (read-only)
PlatformService | decideProductionAccess | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | decidedAt | string (date-time) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | reason | string |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | productionClientId | string (uuid) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | requestedAt | string (date-time) |  | (read-only)
PlatformService | decideProductionAccess | param (path) | requestId | string (uuid) | yes
PlatformService | decideProductionAccess | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideProposedAction | request | decision | enum (approve, reject) | yes
AiService | decideProposedAction | request | reason | string |  | (max length 500)
AiService | decideProposedAction | response | id | string (uuid) | yes
AiService | decideProposedAction | response | interactionId | string (uuid)
AiService | decideProposedAction | response | kind | enum (pricing, promotion, operational, financial, configuration, content, audience) | yes | content (a marketing or storefront draft from proposeMarketingContent) and audience (a lookalike segment from proposeLookalikeSegment) added 29 September (build); both are applied by a person in the…
AiService | decideProposedAction | response | targetContract | string | yes | Which contract would perform it.
AiService | decideProposedAction | response | targetOperation | string | yes
AiService | decideProposedAction | response | payload | object | yes | The request body a person would submit, ready to review.
AiService | decideProposedAction | response | summary | string
AiService | decideProposedAction | response | status | enum (proposed, approved, rejected, applied, expired) | yes | Expiry (decided 28 September, audit R213): a proposed action expires 7 days after proposedAt; an approved action not applied expires 24 hours after decidedAt.
AiService | decideProposedAction | response | expiresAt | string (date-time) |  | When the expiry timer moves this action to expired — proposedAt plus 7 days while proposed, decidedAt plus 24 hours once approved, null once rejected, applied or expired (audit R213). (read-only; nullable)
AiService | decideProposedAction | response | approvalLevel | integer |  | 8.3.65. (min 1; max 2)
AiService | decideProposedAction | response | decidedByPrincipalId | string (uuid) |  | (nullable)
AiService | decideProposedAction | response | decisionReason | string |  | Required on rejection. (nullable)
AiService | decideProposedAction | response | proposedAt | string (date-time)
AiService | decideProposedAction | response | decidedAt | string (date-time) |  | (nullable)
AiService | decideProposedAction | response | scopePath | string |  | Added 29 September (AI design 3.1): ai.proposed_action had no policy — its only references were nullable. (read-only)
AiService | decideProposedAction | response | planId | string (uuid) |  | The plan this action presents for a decision (AI design 2.2 D, 3.8). (read-only; nullable)
AiService | decideProposedAction | response | approvalRequestId | string (uuid) |  | The approvals request deciding a tier 2 or matrix-caught action (AI design 2.3). (read-only; nullable)
AiService | decideProposedAction | response | changeSetHash | string |  | Hash of the change set approved; execution refuses a plan whose hash differs (AIC-181). (read-only; nullable)
AiService | decideProposedAction | param (path) | actionId | string (uuid) | yes
AiService | decideProposedAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideRecommendations | request | placement | enum (productPage, cart, checkout, postPurchase, preVisit, inVenue, posBasket, kioskBasket, …) | yes
AiService | decideRecommendations | request | channel | string | yes
AiService | decideRecommendations | request | cartId | string (uuid) |  | (nullable)
AiService | decideRecommendations | request | productId | string (uuid) |  | The product in view, for a product-page placement. (nullable)
AiService | decideRecommendations | request | subjectId | string (uuid) |  | Known customer, where signed in. (nullable)
AiService | decideRecommendations | request | sessionRef | string |  | (nullable)
AiService | decideRecommendations | request | maxItems | integer |  | (min 1; max 12; default 4)
AiService | decideRecommendations | request | locale | string |  | (nullable)
AiService | decideRecommendations | request | itemKinds | array of enum (upsell, crossSell, upgrade, bundle, addOn, membership, nextBestOffer, offer, …) |  | Only these kinds may fill the slot (29 September, build).
AiService | decideRecommendations | request | portfolioScope | boolean |  | Also consider the entitlements of the people the guest may act for under a delegated access (CF-132 household), not only their own (5.5.30). (default False)
AiService | decideRecommendations | response | decisionId | string (uuid) | yes
AiService | decideRecommendations | response | placement | enum (productPage, cart, checkout, postPurchase, preVisit, inVenue, posBasket, kioskBasket, …)
AiService | decideRecommendations | response | mode | enum (personalised, contextual, rulesOnly, fallback) | yes
AiService | decideRecommendations | response | items | array of AiRecommendationItem | yes
AiService | decideRecommendations | response | items[].trackingId | string (uuid) | yes | Echoed on every recordRecommendationEvents event and as orders.addCartLine.recommendationId, so attribution never guesses.
AiService | decideRecommendations | response | items[].productId | string (uuid) |  | The product recommended. (nullable)
AiService | decideRecommendations | response | items[].promotionId | string (uuid) |  | For offer, a published promotion the guest is eligible for. (nullable)
AiService | decideRecommendations | response | items[].couponRef | string |  | For offer, a coupon campaign; a code is assigned only when the guest takes it (promotions.assignCoupon). (nullable)
AiService | decideRecommendations | response | items[].rewardId | string (uuid) |  | For reward, a marketing-crm loyalty reward the guest can redeem. (nullable)
AiService | decideRecommendations | response | items[].challengeId | string (uuid) |  | For challenge, a marketing-crm challenge the guest can join. (nullable)
AiService | decideRecommendations | response | items[].kind | enum (upsell, crossSell, upgrade, bundle, addOn, membership, nextBestOffer, offer, …)
AiService | decideRecommendations | response | items[].rank | integer | yes | (min 1)
AiService | decideRecommendations | response | items[].priceRef | string |  | The Pricing reference the channel resolves to a price. (nullable)
AiService | decideRecommendations | response | items[].reasonTemplateKey | string |  | The template reason (decided 29 September, decision 9): no model writes guest-visible reasons. (nullable)
AiService | decideRecommendations | response | items[].reasonText | string |  | The rendered template in the session locale, where the channel shows reasons. (nullable)
AiService | decideRecommendations | response | items[].confidenceBand | enum (high, medium, low) |  | Design 5.6: a band, never a bare percentage.
AiService | decideRecommendations | response | items[].score | number |  | Normalised score. (nullable)
AiService | decideRecommendations | response | expiresAt | string (date-time) | yes
AiService | decideRecommendations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | deleteAccessPointGroup | param (path) | groupId | string (uuid) | yes
AccessService | deleteAccessPointGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteBanner | param (path) | bannerId | string (uuid) | yes
WhiteLabelService | deleteBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | deleteBookingFlow | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteContentPage | param (path) | pageId | string (uuid) | yes
WhiteLabelService | deleteContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | deleteDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | deleteDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | deleteFavouriteRoute | param (path) | favouriteId | string (uuid) | yes
VenueOpsService | deleteFavouriteRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | deleteGuestAccount | response | requestId | string
IdentityService | deleteGuestAccount | response | estimatedCompletionAt | string (date-time)
IdentityService | deleteGuestAccount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | deleteGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | deleteMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | deleteMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deletePromoBlock | param (path) | promoBlockId | string (uuid) | yes
WhiteLabelService | deletePromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | deleteReport | param (path) | reportId | string (uuid) | yes
ReportingService | deleteReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | deprecateApiVersion | request | sunsetAt | string (date-time) | yes
PlatformService | deprecateApiVersion | request | reason | string | yes
PlatformService | deprecateApiVersion | request | migrationGuideUrl | string |  | (nullable)
PlatformService | deprecateApiVersion | response | version | string | yes
PlatformService | deprecateApiVersion | response | status | enum (preview, current, deprecated, sunset) | yes
PlatformService | deprecateApiVersion | response | releasedAt | string (date-time)
PlatformService | deprecateApiVersion | response | deprecatedAt | string (date-time) |  | (nullable)
PlatformService | deprecateApiVersion | response | sunsetAt | string (date-time) |  | (nullable)
PlatformService | deprecateApiVersion | response | minimumNoticeMonths | integer |  | The commitment, not the intention. (default 12)
PlatformService | deprecateApiVersion | response | migrationGuideUrl | string |  | (nullable)
PlatformService | deprecateApiVersion | response | activeClientCount | integer |  | (read-only)
PlatformService | deprecateApiVersion | response | changes | array of object |  | The developer changelog for this version (17 September minutes, M17-14): every operation added, changed, deprecated or removed, and whether the change is breaking under ADR-0026.
PlatformService | deprecateApiVersion | response | changes[].operationId | string | yes
PlatformService | deprecateApiVersion | response | changes[].contract | string
PlatformService | deprecateApiVersion | response | changes[].kind | enum (added, changed, deprecated, removed) | yes
PlatformService | deprecateApiVersion | response | changes[].breaking | boolean |  | (default False)
PlatformService | deprecateApiVersion | response | changes[].summary | string
PlatformService | deprecateApiVersion | param (path) | version | string | yes
PlatformService | deprecateApiVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | diffConfigVersion | response | fromVersion | string | yes
WhiteLabelService | diffConfigVersion | response | toVersion | string | yes
WhiteLabelService | diffConfigVersion | response | changes | array of object | yes
WhiteLabelService | diffConfigVersion | response | changes[].area | string | yes
WhiteLabelService | diffConfigVersion | response | changes[].path | string | yes
WhiteLabelService | diffConfigVersion | response | changes[].changeKind | enum (added, removed, modified) | yes
WhiteLabelService | diffConfigVersion | response | changes[].before | string |  | (nullable)
WhiteLabelService | diffConfigVersion | response | changes[].after | string |  | (nullable)
WhiteLabelService | diffConfigVersion | response | changes[].changeScope | ChangeScope: enum (runtime, buildTime) |  | Whether a change reaches guests on publish or needs a store release.
WhiteLabelService | diffConfigVersion | param (path) | version | string | yes
WhiteLabelService | diffConfigVersion | param (query) | against | string |  | Another version.
AccessService | enrolFacePass | request | subjectId | string (uuid) | yes
AccessService | enrolFacePass | request | entitlementId | string (uuid) | yes | An Entitlement.id, which is a UUIDv7.
AccessService | enrolFacePass | request | template | string (password) | yes | Write-only, never returned.
AccessService | enrolFacePass | request | capturedAt | string (date-time) | yes
AccessService | enrolFacePass | request | source | enum (guestApp, ticketCounter, annualPassCounter) | yes | The three surfaces 3.2.43 allows.
AccessService | enrolFacePass | request | consent | object | yes
AccessService | enrolFacePass | request | consent.purposeId | string (uuid) | yes
AccessService | enrolFacePass | request | consent.givenAt | string (date-time) | yes
AccessService | enrolFacePass | request | consent.guardianSubjectId | string (uuid) |  | Required where the subject is a minor. (nullable)
AccessService | enrolFacePass | request | consent.guardianRelationship | string |  | (nullable)
AccessService | enrolFacePass | request | reasonForReEnrollment | enum (appearanceChange, poorOriginalCapture, technicalIssue, guestRequest, recovery, other) |  | Required when the subject already has a Face Pass: why the face is being enrolled again (decided 29 September, writers pass) (nullable)
AccessService | enrolFacePass | response | id | string (uuid) | yes | (read-only)
AccessService | enrolFacePass | response | subjectId | string (uuid) | yes
AccessService | enrolFacePass | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | enrolFacePass | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | enrolFacePass | response | retentionAnchor | object |  | BL-106.
AccessService | enrolFacePass | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | enrolFacePass | response | capturedAt | string (date-time) | yes
AccessService | enrolFacePass | response | consentPurposeId | string (uuid)
AccessService | enrolFacePass | response | consentGivenAt | string (date-time)
AccessService | enrolFacePass | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFacePass | response | isActive | boolean |  | (read-only)
AccessService | enrolFacePass | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | enrolFacePass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | enrolFaceTag | request | subjectId | string (uuid) | yes
AccessService | enrolFaceTag | request | entitlementId | string (uuid) | yes | An Entitlement.id, which is a UUIDv7.
AccessService | enrolFaceTag | request | template | string (password) | yes | Write-only, never returned.
AccessService | enrolFaceTag | request | capturedAt | string (date-time) | yes
AccessService | enrolFaceTag | request | source | enum (ticketCounter, entryGate) | yes | The two surfaces 3.2.44 allows, and a gate is present here exactly where it is absent from Face Pass: this one does not outlive the visit.
AccessService | enrolFaceTag | request | consent | object | yes | Per-visit rather than enduring, and still explicit.
AccessService | enrolFaceTag | request | consent.purposeId | string (uuid) | yes
AccessService | enrolFaceTag | request | consent.method | enum (onScreenAcknowledgement, signedForm) |  | How the guest consented (added 29 September, build pass, 3.2.44). (default onScreenAcknowledgement)
AccessService | enrolFaceTag | request | consent.givenAt | string (date-time) | yes
AccessService | enrolFaceTag | request | consent.guardianSubjectId | string (uuid) |  | Required where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFaceTag | request | consent.guardianRelationship | string |  | (nullable)
AccessService | enrolFaceTag | response | id | string (uuid) | yes | (read-only)
AccessService | enrolFaceTag | response | subjectId | string (uuid) | yes
AccessService | enrolFaceTag | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | enrolFaceTag | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | enrolFaceTag | response | retentionAnchor | object |  | BL-106.
AccessService | enrolFaceTag | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | enrolFaceTag | response | capturedAt | string (date-time) | yes
AccessService | enrolFaceTag | response | consentPurposeId | string (uuid)
AccessService | enrolFaceTag | response | consentGivenAt | string (date-time)
AccessService | enrolFaceTag | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFaceTag | response | isActive | boolean |  | (read-only)
AccessService | enrolFaceTag | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | enrolFaceTag | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | enrolMfaMethod | request | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | enrolMfaMethod | request | target | string |  | Phone or email for OTP methods.
IdentityService | enrolMfaMethod | response | id | string (uuid) |  | Added 20 August. (read-only)
IdentityService | enrolMfaMethod | response | methodId | string (uuid) | yes
IdentityService | enrolMfaMethod | response | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | enrolMfaMethod | response | secret | string |  | TOTP shared secret. (nullable)
IdentityService | enrolMfaMethod | response | qrCodeUri | string |  | (nullable)
IdentityService | enrolMfaMethod | response | recoveryCodes | array of string |  | Returned once, in this enrolment response (enrolMfaMethod writes them, hashed, to identity.mfa_recovery_code).
IdentityService | enrolMfaMethod | response | expiresAt | string (date-time)
IdentityService | enrolMfaMethod | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | escalateCorrectiveAction | response | id | string (uuid) | yes
FnbService | escalateCorrectiveAction | response | raisedAt | string (date-time) | yes
FnbService | escalateCorrectiveAction | response | raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | escalateCorrectiveAction | response | source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | escalateCorrectiveAction | response | sourceRef | string (uuid) |  | (nullable)
FnbService | escalateCorrectiveAction | response | severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | escalateCorrectiveAction | response | actionTaken | string |  | (nullable)
FnbService | escalateCorrectiveAction | response | disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | escalateCorrectiveAction | response | status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | escalateCorrectiveAction | response | signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | escalateCorrectiveAction | response | signedAt | string (date-time) |  | (nullable)
FnbService | escalateCorrectiveAction | response | escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | escalateCorrectiveAction | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | escalateCorrectiveAction | param (path) | actionId | string (uuid) | yes
FnbService | escalateCorrectiveAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | evaluateAiGovernance | request | capabilityKey | string | yes
AiService | evaluateAiGovernance | request | action | enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) | yes
AiService | evaluateAiGovernance | request | scopePath | string |  | (nullable)
AiService | evaluateAiGovernance | request | principalId | string (uuid) |  | (nullable)
AiService | evaluateAiGovernance | request | dataCategories | array of string
AiService | evaluateAiGovernance | request | amount | object |  | (nullable)
AiService | evaluateAiGovernance | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | evaluateAiGovernance | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | evaluateAiGovernance | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | evaluateAiGovernance | request | toolKey | string |  | (nullable)
AiService | evaluateAiGovernance | response | outcome | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | evaluateAiGovernance | response | policyVersion | string | yes
AiService | evaluateAiGovernance | response | autonomyLevel | integer |  | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | evaluateAiGovernance | response | conditions | object |  | (nullable)
AiService | evaluateAiGovernance | response | requiredApprovalTier | integer |  | (min 1; max 2; nullable)
AiService | evaluateAiGovernance | response | explanation | string
AiService | evaluateAiGovernance | response | decisionRecordId | string (uuid) |  | (nullable)
AiService | evaluateAiGovernance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | evaluateApprovalRequirement | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | evaluateApprovalRequirement | request | scopePath | string | yes
TenancyService | evaluateApprovalRequirement | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | request | attributes | object |  | Whatever the conditional rules match on (11.1.13).
TenancyService | evaluateApprovalRequirement | response | isRequired | boolean | yes
TenancyService | evaluateApprovalRequirement | response | matchedRule | object |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | evaluateApprovalRequirement | response | matchedRule.order | integer | yes | First match wins.
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | response | matchedRule.riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.condition | string |  | 11.1.13. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | evaluateApprovalRequirement | response | matchedRule.approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | evaluateApprovalRequirement | response | matchedRule.mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | evaluateApprovalRequirement | response | matchedRule.levels | integer |  | 11.1.3. (default 1)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiresMfa | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiresSignature | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.escalateAfterMinutes | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | evaluateApprovalRequirement | response | matchedRule.expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | evaluateApprovalRequirement | response | matrixVersion | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | approvers | array of object |  | Resolved, with delegations applied.
TenancyService | evaluateApprovalRequirement | response | approvers[].principalId | string (uuid)
TenancyService | evaluateApprovalRequirement | response | approvers[].displayName | string
TenancyService | evaluateApprovalRequirement | response | approvers[].level | integer
TenancyService | evaluateApprovalRequirement | response | approvers[].isDelegate | boolean
TenancyService | evaluateApprovalRequirement | response | approvers[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | slaMinutes | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | noApproverAvailable | boolean |  | The case that must not fail silently.
TenancyService | evaluateApprovalRequirement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | evaluatePromotions | request | venueId | string (uuid) | yes
CatalogueService | evaluatePromotions | request | channel | object | yes | Where the sale is being made.
CatalogueService | evaluatePromotions | request | subjectId | string (uuid)
CatalogueService | evaluatePromotions | request | membershipTierId | string (uuid)
CatalogueService | evaluatePromotions | request | couponCodes | array of string
CatalogueService | evaluatePromotions | request | evaluateAt | string (date-time) |  | For back-office testing of a rule before publishing.
CatalogueService | evaluatePromotions | request | orderId | string (uuid) |  | The order (orders.sales_order) being priced for payment. (nullable)
CatalogueService | evaluatePromotions | request | lines | array of object | yes | (min items 1)
CatalogueService | evaluatePromotions | request | lines[].lineId | string | yes
CatalogueService | evaluatePromotions | request | lines[].variantId | string (uuid) | yes
CatalogueService | evaluatePromotions | request | lines[].performanceId | string (uuid)
CatalogueService | evaluatePromotions | request | lines[].quantity | integer | yes | (min 1)
CatalogueService | evaluatePromotions | request | lines[].unitPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | request | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | request | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | request | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | totalDiscount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | totalDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | totalDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | totalDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines | array of object | yes
CatalogueService | evaluatePromotions | response | lines[].lineId | string | yes
CatalogueService | evaluatePromotions | response | lines[].originalPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].originalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].originalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].originalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].discount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].appliedPromotionIds | array of string (uuid)
CatalogueService | evaluatePromotions | response | applied | array of object | yes
CatalogueService | evaluatePromotions | response | applied[].promotionId | string (uuid) | yes
CatalogueService | evaluatePromotions | response | applied[].promotionCode | string | yes
CatalogueService | evaluatePromotions | response | applied[].promotionName | string
CatalogueService | evaluatePromotions | response | applied[].discount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | applied[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | applied[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | applied[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | applied[].couponCode | string |  | (nullable)
CatalogueService | evaluatePromotions | response | rejected | array of object | yes | Promotions that matched the products but did not apply, with the reason.
CatalogueService | evaluatePromotions | response | rejected[].promotionCode | string | yes
CatalogueService | evaluatePromotions | response | rejected[].promotionName | string
CatalogueService | evaluatePromotions | response | rejected[].reason | enum (conditionsNotMet, supersededByBetterOffer, exclusivePromotionApplied, redemptionLimitReached, budgetExhausted, outsideValidPeriod, wrongChannel, membershipRequired, …) | yes
CatalogueService | evaluatePromotions | response | rejected[].detail | string
CatalogueService | evaluatePromotions | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | exchangeOrderLines | request | id | string (uuid) | yes | Client-generated UUIDv7 of this exchange, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | exchangeOrderLines | request | outgoingLineIds | array of string (uuid) | yes | (min items 1)
OrderService | exchangeOrderLines | request | incomingLines | array of CreateOrderLine | yes | (min items 1)
OrderService | exchangeOrderLines | request | incomingLines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | exchangeOrderLines | request | incomingLines[].variantId | string (uuid) | yes
OrderService | exchangeOrderLines | request | incomingLines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].performanceId | string (uuid)
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | exchangeOrderLines | request | incomingLines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | exchangeOrderLines | request | incomingLines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].quantity | integer | yes | (min 1)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | request | incomingLines[].holderName | string |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].dataMaskValues | object |  | Deliberately open.
OrderService | exchangeOrderLines | request | waiveFee | boolean |  | (default False)
OrderService | exchangeOrderLines | request | reason | string |  | (max length 500)
OrderService | exchangeOrderLines | request | recordedAt | string (date-time) | yes
OrderService | exchangeOrderLines | response | orderId | string (uuid) | yes
OrderService | exchangeOrderLines | response | outgoingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | outgoingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | outgoingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | outgoingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | incomingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | incomingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | incomingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | incomingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | exchangeFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | exchangeFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | exchangeFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | exchangeFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | difference | object | yes | Only the difference settles.
OrderService | exchangeOrderLines | response | difference.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | difference.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | difference.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | newLineIds | array of string (uuid)
OrderService | exchangeOrderLines | response | revokedEntitlementIds | array of string (uuid)
OrderService | exchangeOrderLines | response | issuedEntitlementIds | array of string (uuid)
OrderService | exchangeOrderLines | param (path) | orderId | string (uuid) | yes
OrderService | exchangeOrderLines | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | expireCreditLots | request | action | enum (expire, extend, forfeit) | yes
WalletService | expireCreditLots | request | lotIds | array of string (uuid)
WalletService | expireCreditLots | request | asOf | string (date) |  | (nullable)
WalletService | expireCreditLots | request | extendToDate | string (date) |  | (nullable)
WalletService | expireCreditLots | request | reason | string |  | (nullable)
WalletService | expireCreditLots | request | mode | enum (preview, apply) |  | (default preview)
WalletService | expireCreditLots | response | lotsAffected | integer
WalletService | expireCreditLots | response | totalAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | expireCreditLots | response | totalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | expireCreditLots | response | totalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | expireCreditLots | response | totalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | expireCreditLots | response | breakageAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | expireCreditLots | response | breakageAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | expireCreditLots | response | breakageAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | expireCreditLots | response | breakageAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | expireCreditLots | response | walletsAffected | integer
WalletService | expireCreditLots | response | applied | boolean
WalletService | expireCreditLots | response | asOf | string (date)
WalletService | expireCreditLots | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | explainMetricChange | request | metricKey | string | yes
AiService | explainMetricChange | request | period | string | yes | ISO period, e.g.
AiService | explainMetricChange | request | comparison | enum (previousPeriod, samePeriodLastYear, forecast) |  | (default previousPeriod)
AiService | explainMetricChange | request | dimensions | array of string
AiService | explainMetricChange | request | keep | boolean |  | (default False)
AiService | explainMetricChange | response | metricKey | string | yes
AiService | explainMetricChange | response | period | string
AiService | explainMetricChange | response | comparison | string
AiService | explainMetricChange | response | change | number | yes
AiService | explainMetricChange | response | changePercent | number |  | (nullable)
AiService | explainMetricChange | response | drivers | array of object | yes
AiService | explainMetricChange | response | drivers[].dimension | string
AiService | explainMetricChange | response | drivers[].member | string
AiService | explainMetricChange | response | drivers[].contribution | number
AiService | explainMetricChange | response | drivers[].evidence | AiEvidenceItem |  | One piece of evidence behind a decision, labelled by origin (AIC-197): read from a source system, derived by a rule or feature, or inferred by a model.
AiService | explainMetricChange | response | drivers[].evidence.label | enum (source, derived, modelInferred) | yes
AiService | explainMetricChange | response | drivers[].evidence.kind | string | yes | What it is: feature, rule, document, metric, transaction, candidateSet.
AiService | explainMetricChange | response | drivers[].evidence.ref | string |  | Where it came from: a table and id, a document chunk, a metric key. (nullable)
AiService | explainMetricChange | response | drivers[].evidence.name | string
AiService | explainMetricChange | response | drivers[].evidence.value | object |  | (nullable)
AiService | explainMetricChange | response | drivers[].evidence.observedAt | string (date-time) |  | (nullable)
AiService | explainMetricChange | response | narrative | string |  | (nullable)
AiService | explainMetricChange | response | reliability | enum (grounded, partial, conflictingSources, insufficientEvidence)
AiService | explainMetricChange | response | dataAsOf | string (date-time)
AiService | explainMetricChange | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | exportSubjectData | request | format | enum (json, csv, pdf) |  | (default json)
IdentityService | exportSubjectData | response | requestId | string | yes | The data-subject request raised for this export.
IdentityService | exportSubjectData | response | format | enum (json, csv, pdf) | yes | The format asked for, or json when the request named none.
IdentityService | exportSubjectData | response | estimatedCompletionAt | string (date-time) |  | (nullable)
IdentityService | exportSubjectData | param (path) | subjectId | string (uuid) | yes
IdentityService | exportSubjectData | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | extendCart | response | id | string (uuid) | yes
OrderService | extendCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | extendCart | response | venueId | string (uuid) | yes
OrderService | extendCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | extendCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | extendCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | extendCart | response | lines | array of CartLine | yes
OrderService | extendCart | response | lines[].id | string (uuid) | yes
OrderService | extendCart | response | lines[].variantId | string (uuid) | yes
OrderService | extendCart | response | lines[].productName | string |  | (read-only)
OrderService | extendCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | extendCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | extendCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | extendCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | extendCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | extendCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | extendCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | extendCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | extendCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | extendCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | extendCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | extendCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | extendCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | extendCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | extendCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | extendCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | extendCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | extendCart | response | conflicts | array of CartConflict
OrderService | extendCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | extendCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | extendCart | response | conflicts[].message | string
OrderService | extendCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | extendCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | extendCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | extendCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | extendCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | extendCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | extendCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | extendCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | extendCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | extendCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | extendCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | extendCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | extendCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | extendCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | extendCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | extendCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | extendCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | extendCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | extendCart | response | extensionsUsed | integer |  | (read-only)
OrderService | extendCart | response | maxExtensions | integer |  | (read-only)
OrderService | extendCart | response | locale | string
OrderService | extendCart | response | createdAt | string (date-time)
OrderService | extendCart | response | updatedAt | string (date-time)
OrderService | extendCart | param (path) | cartId | string (uuid) | yes
OrderService | extendCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | extendResourceHold | response | id | string (uuid) | yes
VenueOpsService | extendResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | extendResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | extendResourceHold | response | from | string (date-time) | yes
VenueOpsService | extendResourceHold | response | to | string (date-time) | yes
VenueOpsService | extendResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | extendResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | extendResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | extendResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | extendResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | extendResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | extendResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | extendResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | extendResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | extendResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | extendResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | extendResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | extendResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | extendResourceHold | param (path) | holdId | string (uuid) | yes
VenueOpsService | extendResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | extendSeatHold | response | id | string | yes
CatalogueService | extendSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | extendSeatHold | response | seatIds | array of string | yes
CatalogueService | extendSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | extendSeatHold | response | status | enum (held, converted, released, expired) | yes
CatalogueService | extendSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | extendSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | extendSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | extendSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | extendSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | extendSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | extendSeatHold | response | extensionCount | integer
CatalogueService | extendSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | extendSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | extendSeatHold | param (path) | holdId | string (uuid) | yes
CatalogueService | extendSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | fireCourse | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | fireCourse | request | course | integer | yes | (min 1)
FnbService | fireCourse | request | fireAt | string (date-time) |  | For timed coursing. (nullable)
FnbService | fireCourse | response | id | string (uuid) | yes
FnbService | fireCourse | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | fireCourse | response | orderNumber | string
FnbService | fireCourse | response | outletId | string (uuid) | yes
FnbService | fireCourse | response | tableLabel | string |  | (nullable)
FnbService | fireCourse | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | fireCourse | response | coursing | object |  | BL-131. (nullable)
FnbService | fireCourse | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | fireCourse | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | fireCourse | response | priority | integer |  | Higher fires sooner.
FnbService | fireCourse | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | fireCourse | response | prioritiseReason | string |  | (nullable)
FnbService | fireCourse | response | lines | array of object | yes
FnbService | fireCourse | response | lines[].lineId | string (uuid) | yes
FnbService | fireCourse | response | lines[].name | string | yes
FnbService | fireCourse | response | lines[].quantity | integer | yes
FnbService | fireCourse | response | lines[].modifiers | array of string
FnbService | fireCourse | response | lines[].note | string |  | (nullable)
FnbService | fireCourse | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | fireCourse | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | fireCourse | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | fireCourse | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | fireCourse | response | lines[].course | integer |  | (nullable)
FnbService | fireCourse | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | fireCourse | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | fireCourse | response | createdAt | string (date-time) | yes
FnbService | fireCourse | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | fireCourse | response | elapsedSeconds | integer
FnbService | fireCourse | param (path) | ticketId | string (uuid) | yes
FnbService | fireCourse | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | forceLogout | request | reason | string | yes | (min length 3; max length 500)
IdentityService | forceLogout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | forceLogout | param (path) | sessionId | string (uuid) | yes
CatalogueService | generateCouponCodes | request | quantity | integer | yes | (min 1; max 50000)
CatalogueService | generateCouponCodes | request | prefix | string |  | (max length 16)
CatalogueService | generateCouponCodes | request | length | integer |  | (min 6; max 32; default 12)
CatalogueService | generateCouponCodes | request | assignToSubjectIds | array of string (uuid) |  | Personalised codes bound to named guests. (max items 50000)
CatalogueService | generateCouponCodes | response | batchId | string (uuid)
CatalogueService | generateCouponCodes | response | quantity | integer
CatalogueService | generateCouponCodes | response | status | enum (queued, generating, complete, failed)
CatalogueService | generateCouponCodes | param (path) | campaignId | string (uuid) | yes
CatalogueService | generateCouponCodes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | generateVisitPlan | request | venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | generateVisitPlan | request | dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | generateVisitPlan | request | dayVenues[].date | string (date) | yes
VenueOpsService | generateVisitPlan | request | dayVenues[].venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | request | dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | generateVisitPlan | request | party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | generateVisitPlan | request | party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | generateVisitPlan | request | party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | generateVisitPlan | request | pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | generateVisitPlan | request | interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | generateVisitPlan | request | cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | generateVisitPlan | request | retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | generateVisitPlan | request | mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | generateVisitPlan | request | preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | generateVisitPlan | request | presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | generateVisitPlan | request | startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | generateVisitPlan | request | locale | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | generateVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | generateVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | generateVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | generateVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | generateVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | generateVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | generateVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | generateVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | generateVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | generateVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | generateVisitPlan | response | inputs.pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | generateVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | generateVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | generateVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | generateVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | generateVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | generateVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | generateVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | generateVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | generateVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | generateVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | generateVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | generateVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | generateVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | generateVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | generateVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | generateVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | generateVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | generateVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | generateVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | generateVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | generateVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | generateVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | generateVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | getAiPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
AiService | getAiPolicy | response | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | getAiPolicy | response | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue.
AiService | getAiPolicy | response | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | getAiPolicy | response | allowedRoleIds | array of string (uuid)
AiService | getAiPolicy | response | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | getAiPolicy | response | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | getAiPolicy | response | monthlyTokenCeiling | integer |  | (nullable)
AiService | getAiPolicy | response | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | getAiPolicy | response | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | getAiPolicy | response | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | getAiPolicy | response | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | getAiPolicy | response | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | getAiPolicy | response | autonomyOverrides[].capabilityKey | string | yes
AiService | getAiPolicy | response | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getAiPolicy | response | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | getAiPolicy | response | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | getAiPolicy | response | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | getAiPolicy | response | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | getAiPolicy | response | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | getAiPolicy | response | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | getAiPolicy | response | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | getAiPolicy | response | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | getAiPolicy | response | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | getAiPolicy | response | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | getAiPolicy | response | cascade.smallModel | string
AiService | getAiPolicy | response | cascade.largeModel | string
AiService | getAiPolicy | response | cascade.escalateBelow | number |  | (default 0.7)
AiService | getAiPolicy | response | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | getAiPolicy | response | chunking.sizeTokens | integer |  | (default 512)
AiService | getAiPolicy | response | chunking.overlapTokens | integer |  | (default 64)
AiService | getAiPolicy | response | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | getAiPolicy | response | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | getAiPolicy | response | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | getAiPolicy | response | hnsw.m | integer |  | (default 16)
AiService | getAiPolicy | response | hnsw.efConstruct | integer |  | (default 128)
AiService | getAiPolicy | response | hnsw.efSearch | integer |  | (default 64)
AiService | getAiPolicy | response | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | getAiPolicy | response | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | getAiPolicy | response | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | getAiPolicy | response | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | getAiPolicy | response | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | getAiPolicy | param (query) | scopePath | string |  | The tenant or venue node to read the policy for.
AiService | getAiUsage | response | from | string (date)
AiService | getAiUsage | response | to | string (date)
AiService | getAiUsage | response | groupBy | string
AiService | getAiUsage | response | rows | array of object
AiService | getAiUsage | response | rows[].key | string
AiService | getAiUsage | response | rows[].interactions | integer
AiService | getAiUsage | response | rows[].promptTokens | integer
AiService | getAiUsage | response | rows[].completionTokens | integer
AiService | getAiUsage | response | rows[].cost | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | rows[].cost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | rows[].cost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | rows[].cost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | rows[].p95LatencyMs | integer
AiService | getAiUsage | response | rows[].refusalRate | number
AiService | getAiUsage | response | rows[].rejectionRate | number |  | Proposals a person refused.
AiService | getAiUsage | response | forecast | object |  | A month-end projection, labelled a forecast (AI design 2.3, 4.5). (nullable)
AiService | getAiUsage | response | forecast.label | enum (forecast)
AiService | getAiUsage | response | forecast.periodEnd | string (date)
AiService | getAiUsage | response | forecast.projectedTokens | integer
AiService | getAiUsage | response | forecast.projectedCost | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | forecast.projectedCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | forecast.projectedCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | forecast.projectedCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | forecast.basis | string |  | How it was projected, e.g.
AiService | getAiUsage | param (query) | from | string (date)
AiService | getAiUsage | param (query) | groupBy | enum (tenant, venue, principal, provider, capability, day, agent, model, …)
AiService | getAiVenueSettings | response | id | string (uuid) |  | (read-only)
AiService | getAiVenueSettings | response | venueId | string (uuid) | yes
AiService | getAiVenueSettings | response | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | getAiVenueSettings | response | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | getAiVenueSettings | response | capacity | integer |  | (min 1; nullable)
AiService | getAiVenueSettings | response | openingHours | array of object |  | The usual week.
AiService | getAiVenueSettings | response | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | getAiVenueSettings | response | openingHours[].opensAt | string
AiService | getAiVenueSettings | response | openingHours[].closesAt | string
AiService | getAiVenueSettings | response | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | getAiVenueSettings | response | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | getAiVenueSettings | response | peakMonths | array of integer
AiService | getAiVenueSettings | response | averageSpend | object |  | (nullable)
AiService | getAiVenueSettings | response | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiVenueSettings | response | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiVenueSettings | response | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiVenueSettings | response | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | getAiVenueSettings | response | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | getAiVenueSettings | response | startingPatternKey | string |  | The pattern and version in use, e.g. (read-only)
AiService | getAiVenueSettings | response | updatedAt | string (date-time) |  | (read-only)
AiService | getAiVenueSettings | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getAiVenueSettings | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getAppBuild | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | getAppBuild | response | platform | enum (ios, android) | yes
WhiteLabelService | getAppBuild | response | configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | getAppBuild | response | storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | getAppBuild | response | versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | getAppBuild | response | buildNumber | integer |  | (read-only)
WhiteLabelService | getAppBuild | response | status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the build service's; from submitted on it is read from the store with the client's credential, or stays built when the client uploads by hand. (read-only)
WhiteLabelService | getAppBuild | response | failureReason | string |  | (read-only; nullable)
WhiteLabelService | getAppBuild | response | packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | getAppBuild | response | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getAppBuild | response | submitToStore | boolean |  | (default False)
WhiteLabelService | getAppBuild | response | requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | getAppBuild | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | getAppBuild | response | finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | getAppBuild | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getAppBuild | param (path) | appBuildId | string (uuid) | yes
WhiteLabelService | getAppIcons | response | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getAppIcons | response | derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getAppIcons | response | derived[].platform | enum (ios, android, web)
WhiteLabelService | getAppIcons | response | derived[].size | string
WhiteLabelService | getAppIcons | response | derived[].assetRef | string (uuid)
WhiteLabelService | getAppIcons | response | changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getAppIcons | response | liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getAppIcons | response | requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
CatalogueService | getAvailability | response | items | array of PerformanceAvailability | yes
CatalogueService | getAvailability | response | items[].channelCapacityId | string (uuid) | yes
CatalogueService | getAvailability | response | items[].performanceId | string (uuid) | yes | The performance this channel capacity belongs to (ChannelCapacity.performanceId), so rows for several performances can be told apart.
CatalogueService | getAvailability | response | items[].startsAt | string (date-time) |  | The performance's start, so a time tile and its day part (morning, afternoon, evening, split at the venue's BookingFlowConfig.dayPartBoundaries) come from this one call (rev 3 REV3-1). (read-only)
CatalogueService | getAvailability | response | items[].capacity | integer | yes
CatalogueService | getAvailability | response | items[].sold | integer | yes
CatalogueService | getAvailability | response | items[].leased | integer | yes | Held by terminals but not yet sold.
CatalogueService | getAvailability | response | items[].remaining | integer | yes
CatalogueService | getAvailability | response | items[].byChannel | array of object |  | Per-channel position.
CatalogueService | getAvailability | response | items[].byChannel[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | getAvailability | response | items[].byChannel[].allocated | integer
CatalogueService | getAvailability | response | items[].byChannel[].sold | integer
CatalogueService | getAvailability | response | items[].byChannel[].remaining | integer
CatalogueService | getAvailability | response | nextCursor | string
CatalogueService | getAvailability | response | hasMore | boolean | yes
CatalogueService | getAvailability | param (query) | performanceId | string (uuid)
CatalogueService | getAvailability | param (query) | channelCapacityId | string (uuid)
CatalogueService | getAvailability | param (query) | eventId | string (uuid) |  | Every performance of this event starting between from and to (rev 3 REV3-1).
CatalogueService | getAvailability | param (query) | from | string (date-time) |  | Required with eventId.
CatalogueService | getAvailability | param (query) | to | string (date-time) |  | Required with eventId.
CatalogueService | getAvailability | param (query) | pageSize | integer
CatalogueService | getAvailability | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | getBillingStatement | response | id | string (uuid) | yes
OrderService | getBillingStatement | response | subjectId | string (uuid) |  | (read-only)
OrderService | getBillingStatement | response | periodStart | string (date) | yes
OrderService | getBillingStatement | response | periodEnd | string (date) | yes
OrderService | getBillingStatement | response | lines | array of BillingStatementLine
OrderService | getBillingStatement | response | lines[].occurredAt | string (date-time) | yes
OrderService | getBillingStatement | response | lines[].kind | enum (charge, refund, failedAttempt, adjustment) | yes
OrderService | getBillingStatement | response | lines[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].description | string
OrderService | getBillingStatement | response | lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].taxRate | number |  | 2.14.23. (nullable)
OrderService | getBillingStatement | response | lines[].taxInvoiceId | string (uuid) |  | The finance tax invoice issued for this charge, where one was (issueTaxInvoice); the guest downloads it with getTaxDocumentRendition. (nullable)
OrderService | getBillingStatement | response | lines[].declineClass | string |  | Present on failedAttempt only, and it is what turns *"your payment failed"* into something a guest can act on: a soft decline means try again, a hard one means the card needs replacing. (nullable)
OrderService | getBillingStatement | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | pdfUrl | string (uri) |  | Set when getBillingStatement is called with format=pdf; a short-lived link. (read-only; nullable)
OrderService | getBillingStatement | response | isTaxInvoice | boolean | yes | Always false, and stated rather than assumed. (default False; read-only)
OrderService | getBillingStatement | param (path) | statementId | string (uuid) | yes
OrderService | getBillingStatement | param (query) | format | enum (json, pdf) |  | 2.14.23.
OrderService | getBillingStatement | param (query) | language | string
WhiteLabelService | getBookingFlow | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getBookingFlow | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getBookingFlow | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getBookingFlow | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getBookingFlow | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getBookingFlow | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getBookingFlow | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getBookingFlow | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getBookingFlow | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getBookingFlow | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getBookingFlow | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getBookingFlow | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getBookingFlow | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getBookingFlow | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getBookingFlow | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getBookingFlow | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getBookingFlow | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getBookingFlow | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getBookingFlow | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getBookingFlow | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getBookingFlow | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | getBookingFlowConfig | response | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getBookingFlowConfig | response | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getBookingFlowConfig | response | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getBookingFlowConfig | response | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getBookingFlowConfig | response | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getBookingFlowConfig | response | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getBookingFlowConfig | response | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getBookingFlowConfig | response | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getBookingFlowConfig | response | heroBanner | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getBookingFlowConfig | response | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getBookingFlowConfig | response | singleEventPage | boolean |  | (default False)
WhiteLabelService | getBookingFlowConfig | response | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getBookingFlowConfig | response | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getBookingFlowConfig | response | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getBookingFlowConfig | response | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getBookingFlowConfig | response | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getBookingFlowConfig | response | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getBookingFlowConfig | response | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getBookingFlowConfig | response | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getBookingFlowConfig | response | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getBookingFlowConfig | response | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getBookingFlowConfig | param (query) | effectiveForVenueId | string (uuid) |  | Return the settings in force at this venue, the tenant's with the venue's override laid over them, and no venueOverrides (decided 29 September, rev 3 CFG-11).
WhiteLabelService | getBrandIdentity | response | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getBrandIdentity | response | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getBrandIdentity | response | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getBrandIdentity | response | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getBrandIdentity | response | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getBrandIdentity | response | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getBrandIdentity | response | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getBrandIdentity | response | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getBrandIdentity | response | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getBrandIdentity | response | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getBrandIdentity | response | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
CatalogueService | getBundle | response | code | string | yes | (max length 64)
CatalogueService | getBundle | response | name | string | yes | (max length 200)
CatalogueService | getBundle | response | description | string |  | (max length 1000)
CatalogueService | getBundle | response | venueId | string (uuid) | yes
CatalogueService | getBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | getBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | getBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | getBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | getBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | getBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | getBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | getBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | getBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | getBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | getBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | getBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | getBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | getBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | getBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | getBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | getBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | getBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | getBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | getBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | getBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | getBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | getBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | getBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | getBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | getBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | getBundle | response | allocation | object | yes
CatalogueService | getBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | getBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | getBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | getBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | getBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | getBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | getBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | getBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | getBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | getBundle | response | validFrom | string (date-time)
CatalogueService | getBundle | response | validTo | string (date-time)
CatalogueService | getBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | getBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | getBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | getBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | getBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | getBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | getBundle | response | id | string (uuid) | yes
CatalogueService | getBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price.
CatalogueService | getBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getBundle | response | savingsPercentage | number
CatalogueService | getBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | getBundle | response | isActive | boolean | yes
CatalogueService | getBundle | param (path) | bundleId | string (uuid) | yes
OrderService | getCart | response | id | string (uuid) | yes
OrderService | getCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | getCart | response | venueId | string (uuid) | yes
OrderService | getCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | getCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | getCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | getCart | response | lines | array of CartLine | yes
OrderService | getCart | response | lines[].id | string (uuid) | yes
OrderService | getCart | response | lines[].variantId | string (uuid) | yes
OrderService | getCart | response | lines[].productName | string |  | (read-only)
OrderService | getCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | getCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | getCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | getCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | getCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | getCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | getCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | getCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | getCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | getCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | getCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | getCart | response | conflicts | array of CartConflict
OrderService | getCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | getCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | getCart | response | conflicts[].message | string
OrderService | getCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | getCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | getCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | getCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | getCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | getCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | getCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | getCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | getCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | getCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | getCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | getCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | getCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | getCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | getCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | getCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | getCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | getCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | getCart | response | extensionsUsed | integer |  | (read-only)
OrderService | getCart | response | maxExtensions | integer |  | (read-only)
OrderService | getCart | response | locale | string
OrderService | getCart | response | createdAt | string (date-time)
OrderService | getCart | response | updatedAt | string (date-time)
OrderService | getCart | param (path) | cartId | string (uuid) | yes
OrderService | getCart | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
MarketingService | getCookieConsentRuntime | response | banner | CookieBannerPreferenceCenterDesignerView | yes | One version of a cookie banner and preference-centre design (pack 17.1.6).
MarketingService | getCookieConsentRuntime | response | banner.id | string (uuid) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | banner.brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | getCookieConsentRuntime | response | banner.inheritsFromId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | banner.channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | getCookieConsentRuntime | response | banner.logoAssetId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | banner.title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.position | enum (top, bottom, popup, modal) | yes
MarketingService | getCookieConsentRuntime | response | banner.themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | getCookieConsentRuntime | response | banner.buttons | array of object
MarketingService | getCookieConsentRuntime | response | banner.buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | getCookieConsentRuntime | response | banner.buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | getCookieConsentRuntime | response | banner.links | array of object
MarketingService | getCookieConsentRuntime | response | banner.links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | getCookieConsentRuntime | response | banner.categories | array of object | yes | (min items 1)
MarketingService | getCookieConsentRuntime | response | banner.categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | getCookieConsentRuntime | response | banner.categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | getCookieConsentRuntime | response | banner.languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | getCookieConsentRuntime | response | banner.regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | getCookieConsentRuntime | response | banner.recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | getCookieConsentRuntime | response | banner.noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | getCookieConsentRuntime | response | banner.version | integer |  | (min 1; read-only)
MarketingService | getCookieConsentRuntime | response | banner.status | enum (draft, published, superseded) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | banner.scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getCookieConsentRuntime | response | banner.updatedAt | string (date-time) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | noticeVersion | string | yes
MarketingService | getCookieConsentRuntime | response | requiresDecision | boolean | yes | True with no decision, an expired one, or one given against a superseded notice.
MarketingService | getCookieConsentRuntime | response | decision | object |  | The latest decision for the presented key; null without a key. (nullable)
MarketingService | getCookieConsentRuntime | response | decision.id | string (uuid) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | decision.consentKey | string | yes | Opaque, minted by us, not a device fingerprint. (max length 64; read-only)
MarketingService | getCookieConsentRuntime | response | decision.channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | getCookieConsentRuntime | response | decision.brandId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | decision.bannerDesignId | string (uuid) |  | The published CookieBannerPreferenceCenterDesignerView version the visitor was shown. (nullable)
MarketingService | getCookieConsentRuntime | response | decision.action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | getCookieConsentRuntime | response | decision.categories | array of object | yes | Every category of the design, with the decision this row gives it. (min items 1)
MarketingService | getCookieConsentRuntime | response | decision.categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getCookieConsentRuntime | response | decision.categories[].decision | enum (granted, declined) | yes
MarketingService | getCookieConsentRuntime | response | decision.noticeVersion | string | yes | The cookie notice version decided against (white-label setPolicy, kind cookie).
MarketingService | getCookieConsentRuntime | response | decision.language | string |  | (max length 10; nullable)
MarketingService | getCookieConsentRuntime | response | decision.globalPrivacyControl | boolean |  | The browser sent a Global Privacy Control signal; honoured as a CCPA/CPRA opt-out of sale and sharing. (default False)
MarketingService | getCookieConsentRuntime | response | decision.source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | getCookieConsentRuntime | response | decision.country | string |  | The edge's geolocation of the request, for the geographic statistics (2.6.63). (pattern ^[A-Z]{2}$; read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.decidedAt | string (date-time) | yes
MarketingService | getCookieConsentRuntime | response | decision.expiresAt | string (date-time) |  | A device consent expires and a subject consent does not. (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.claimedBySubjectId | string (uuid) |  | Set once, by claimDeviceConsent. (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.claimedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.scopePath | string |  | The partition key (ADR-0005), tenant-scoped: a decision with no subject still belongs to one tenant. (read-only)
MarketingService | getCookieConsentRuntime | response | allowedTechnologies | array of object | yes | Per category, the approved technologies it unlocks.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].granted | boolean |  | Whether the presented decision grants it; always true for strictlyNecessary.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies | array of object | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].name | string | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].provider | string | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].technologyType | string
MarketingService | getCookieConsentRuntime | response | consentModeSignals | object | yes | The decision in Google consent-mode terms (2.6.65), so Analytics and Tag Manager are told, not left to guess.
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adUserData | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adPersonalization | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.analyticsStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.functionalityStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.personalizationStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.securityStorage | enum (granted)
MarketingService | getCookieConsentRuntime | param (query) | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | getCookieConsentRuntime | param (query) | brandId | string (uuid)
MarketingService | getCookieConsentRuntime | param (query) | language | string |  | One of the design's languages; the tenant's default where omitted
MarketingService | getCookieConsentRuntime | param (header) | X-Consent-Key | string |  | The key the visitor's browser or app holds, if any
CatalogueService | getCouponCode | response | code | string | yes
CatalogueService | getCouponCode | response | campaignId | string (uuid) | yes
CatalogueService | getCouponCode | response | batchId | string (uuid) |  | The generateCouponCodes batch that issued this code. (nullable)
CatalogueService | getCouponCode | response | status | CouponStatus: enum (issued, assigned, redeemed, expired, voided) | yes
CatalogueService | getCouponCode | response | assignedSubjectId | string (uuid) |  | (nullable)
CatalogueService | getCouponCode | response | redemptionCount | integer
CatalogueService | getCouponCode | response | maxRedemptions | integer
CatalogueService | getCouponCode | response | discount | Discount
CatalogueService | getCouponCode | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | getCouponCode | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | getCouponCode | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getCouponCode | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getCouponCode | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getCouponCode | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getCouponCode | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getCouponCode | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getCouponCode | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getCouponCode | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getCouponCode | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | getCouponCode | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | getCouponCode | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | getCouponCode | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | getCouponCode | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | getCouponCode | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | getCouponCode | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | getCouponCode | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getCouponCode | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getCouponCode | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getCouponCode | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | getCouponCode | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | getCouponCode | response | invalidReason | enum (expired, alreadyRedeemed, voided, notYetValid, wrongVenue, conditionsNotMet, notAssignedToGuest) |  | Why the code cannot be applied. (nullable)
CatalogueService | getCouponCode | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | getCouponCode | response | validTo | string (date-time) |  | (nullable)
CatalogueService | getCouponCode | response | redeemedAt | string (date-time) |  | (nullable)
CatalogueService | getCouponCode | response | redeemedOrderId | string |  | (nullable)
CatalogueService | getCouponCode | response | scopePath | string |  | The partition key (ADR-0005).
CatalogueService | getCouponCode | param (path) | code | string | yes
IdentityService | getCurrentSession | response | sessionId | string (uuid) | yes
IdentityService | getCurrentSession | response | principalId | string (uuid) | yes
IdentityService | getCurrentSession | response | roleId | string (uuid) | yes
IdentityService | getCurrentSession | response | displayName | string
IdentityService | getCurrentSession | response | scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | getCurrentSession | response | scope[].id | string (uuid) | yes
IdentityService | getCurrentSession | response | scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | getCurrentSession | response | scope[].path | string | yes | Materialised ltree path.
IdentityService | getCurrentSession | response | scope[].code | string |  | (nullable)
IdentityService | getCurrentSession | response | scope[].name | string |  | (nullable)
IdentityService | getCurrentSession | response | effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | getCurrentSession | response | permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path.
IdentityService | getCurrentSession | response | permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | getCurrentSession | response | permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | getCurrentSession | response | saleBoardId | string (uuid) | yes | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | getCurrentSession | response | workstation | WorkstationContext
IdentityService | getCurrentSession | response | workstation.id | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.code | string | yes
IdentityService | getCurrentSession | response | workstation.venueId | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.regionId | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | getCurrentSession | response | workstation.devices | array of object
IdentityService | getCurrentSession | response | workstation.devices[].kind | enum (receiptPrinter, ticketPrinter, cashDrawer, barcodeScanner, rfidReader, paymentTerminal, customerDisplay) | yes
IdentityService | getCurrentSession | response | workstation.devices[].driver | string | yes
IdentityService | getCurrentSession | response | workstation.devices[].identifier | string
IdentityService | getCurrentSession | response | workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | getCurrentSession | response | workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | getCurrentSession | response | workstation.timezone | string
IdentityService | getCurrentSession | response | workstation.cellName | string |  | The cell serving this workstation's region.
IdentityService | getCurrentSession | response | workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | getCurrentSession | response | openedAt | string (date-time)
IdentityService | getCurrentSession | response | expiresAt | string (date-time)
OrderService | getCurrentShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | getCurrentShift | response | workstationId | string (uuid) | yes
OrderService | getCurrentShift | response | venueId | string (uuid) | yes
OrderService | getCurrentShift | response | scopePath | string | yes
OrderService | getCurrentShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | getCurrentShift | response | principalDisplayName | string
OrderService | getCurrentShift | response | incidents | array of object |  | BL-097.
OrderService | getCurrentShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | getCurrentShift | response | incidents[].at | string (date-time)
OrderService | getCurrentShift | response | incidents[].principalId | string (uuid)
OrderService | getCurrentShift | response | incidents[].note | string |  | (nullable)
OrderService | getCurrentShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | getCurrentShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getCurrentShift | response | depositBoxCode | string |  | (nullable)
OrderService | getCurrentShift | response | bagNumber | string |  | (nullable)
OrderService | getCurrentShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | getCurrentShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | getCurrentShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | getCurrentShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | getCurrentShift | response | openedAt | string (date-time) | yes
OrderService | getCurrentShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | getCurrentShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | getCurrentShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | getCurrentShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | getCurrentShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | getCurrentShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | getCurrentShift | response | approvals | array of object
OrderService | getCurrentShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | getCurrentShift | response | approvals[].principalId | string (uuid) | yes
OrderService | getCurrentShift | response | approvals[].at | string (date-time) | yes
OrderService | getCurrentShift | response | approvals[].reason | string
ReportingService | getDashboard | response | name | string | yes | (max length 200)
ReportingService | getDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | getDashboard | response | description | string |  | (max length 1000)
ReportingService | getDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | getDashboard | response | isShared | boolean |  | (default False)
ReportingService | getDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | getDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | getDashboard | response | tiles[].title | string
ReportingService | getDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | getDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | getDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | getDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | getDashboard | response | tiles[].position | object | yes
ReportingService | getDashboard | response | tiles[].position.row | integer | yes
ReportingService | getDashboard | response | tiles[].position.column | integer | yes
ReportingService | getDashboard | response | tiles[].position.width | integer | yes
ReportingService | getDashboard | response | tiles[].position.height | integer | yes
ReportingService | getDashboard | response | id | string (uuid) | yes
ReportingService | getDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | getDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | getDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | getDashboard | response | createdAt | string (date-time) | yes
ReportingService | getDashboard | response | tileData | array of object
ReportingService | getDashboard | response | tileData[].tileId | string (uuid)
ReportingService | getDashboard | response | tileData[].result | ReportResult
ReportingService | getDashboard | response | tileData[].result.executionId | string | yes
ReportingService | getDashboard | response | tileData[].result.columns | array of object | yes
ReportingService | getDashboard | response | tileData[].result.rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | getDashboard | response | tileData[].result.totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | getDashboard | response | tileData[].result.rowCount | integer
ReportingService | getDashboard | response | tileData[].result.nextCursor | string |  | (nullable)
ReportingService | getDashboard | response | tileData[].result.generatedAt | string (date-time)
ReportingService | getDashboard | response | tileData[].result.dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | getDashboard | response | tileData[].isCached | boolean
ReportingService | getDashboard | response | tileData[].error | string |  | (nullable)
ReportingService | getDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | getDashboard | param (query) | refresh | boolean |  | Bypass cached tile data.
MarketingService | getDeviceConsentHistory | response | items | array of DeviceConsent | yes
MarketingService | getDeviceConsentHistory | response | items[].id | string (uuid) |  | (read-only)
MarketingService | getDeviceConsentHistory | response | items[].consentKey | string | yes | Opaque, minted by us, not a device fingerprint. (max length 64; read-only)
MarketingService | getDeviceConsentHistory | response | items[].channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | getDeviceConsentHistory | response | items[].brandId | string (uuid) |  | (nullable)
MarketingService | getDeviceConsentHistory | response | items[].bannerDesignId | string (uuid) |  | The published CookieBannerPreferenceCenterDesignerView version the visitor was shown. (nullable)
MarketingService | getDeviceConsentHistory | response | items[].action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | getDeviceConsentHistory | response | items[].categories | array of object | yes | Every category of the design, with the decision this row gives it. (min items 1)
MarketingService | getDeviceConsentHistory | response | items[].categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getDeviceConsentHistory | response | items[].categories[].decision | enum (granted, declined) | yes
MarketingService | getDeviceConsentHistory | response | items[].noticeVersion | string | yes | The cookie notice version decided against (white-label setPolicy, kind cookie).
MarketingService | getDeviceConsentHistory | response | items[].language | string |  | (max length 10; nullable)
MarketingService | getDeviceConsentHistory | response | items[].globalPrivacyControl | boolean |  | The browser sent a Global Privacy Control signal; honoured as a CCPA/CPRA opt-out of sale and sharing. (default False)
MarketingService | getDeviceConsentHistory | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | getDeviceConsentHistory | response | items[].country | string |  | The edge's geolocation of the request, for the geographic statistics (2.6.63). (pattern ^[A-Z]{2}$; read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].decidedAt | string (date-time) | yes
MarketingService | getDeviceConsentHistory | response | items[].expiresAt | string (date-time) |  | A device consent expires and a subject consent does not. (read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].claimedBySubjectId | string (uuid) |  | Set once, by claimDeviceConsent. (read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].claimedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].scopePath | string |  | The partition key (ADR-0005), tenant-scoped: a decision with no subject still belongs to one tenant. (read-only)
MarketingService | getDeviceConsentHistory | response | nextCursor | string
MarketingService | getDeviceConsentHistory | response | hasMore | boolean | yes
MarketingService | getDeviceConsentHistory | param (header) | X-Consent-Key | string | yes | The key the visitor's browser or app holds
MarketingService | getDeviceConsentHistory | param (query) | pageSize | integer
MarketingService | getDeviceConsentHistory | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | getEntitlement | response | id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | getEntitlement | response | templateId | string (uuid) | yes | The definition it was issued against.
AccessService | getEntitlement | response | productId | string (uuid) | yes
AccessService | getEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | getEntitlement | response | orderLineId | string (uuid)
AccessService | getEntitlement | response | subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | getEntitlement | response | venueId | string (uuid)
AccessService | getEntitlement | response | scopePath | string
AccessService | getEntitlement | response | mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | getEntitlement | response | status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | getEntitlement | response | statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | getEntitlement | response | validFrom | string (date-time) | yes
AccessService | getEntitlement | response | validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | getEntitlement | response | entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | getEntitlement | response | entriesAllowed | integer |  | (nullable)
AccessService | getEntitlement | response | lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | getEntitlement | response | frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | getEntitlement | response | suspendedReason | string |  | (nullable)
AccessService | getEntitlement | response | freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | getEntitlement | response | freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | getEntitlement | response | isNameBound | boolean |  | (default False)
AccessService | getEntitlement | response | holderName | string |  | (nullable)
AccessService | getEntitlement | response | sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | getEntitlement | response | issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | getEntitlement | response | supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | getEntitlement | response | walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | getEntitlement | response | facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | getEntitlement | param (path) | entitlementId | string (uuid) | yes
AccessService | getEntitlementCredential | response | mediaCode | string
AccessService | getEntitlementCredential | response | payload | string
AccessService | getEntitlementCredential | response | expiresAt | string (date-time) |  | (nullable)
AccessService | getEntitlementCredential | response | rotation | object |  | The time-based seed the rotating code is derived from (audit R230). (nullable)
AccessService | getEntitlementCredential | response | rotation.secret | string | yes | Base32 shared secret.
AccessService | getEntitlementCredential | response | rotation.timeStepSeconds | integer | yes | (min 10; max 60; default 30)
AccessService | getEntitlementCredential | response | rotation.digits | integer | yes | (min 6; max 10; default 8)
AccessService | getEntitlementCredential | response | rotation.algorithm | enum (SHA1, SHA256, SHA512) | yes | (default SHA256)
AccessService | getEntitlementCredential | response | rotation.validFrom | string (date-time) | yes
AccessService | getEntitlementCredential | response | rotation.validTo | string (date-time) | yes | The seed stops verifying after this.
AccessService | getEntitlementCredential | param (path) | entitlementId | string (uuid) | yes
AccessService | getEntitlementCredential | param (query) | rotate | boolean
AccessService | getEntitlementHistory | param (path) | entitlementId | string (uuid) | yes
VenueOpsService | getExpiringRights | param (query) | withinDays | integer
AccessService | getFacePassEnrolment | response | id | string (uuid) | yes | (read-only)
AccessService | getFacePassEnrolment | response | subjectId | string (uuid) | yes
AccessService | getFacePassEnrolment | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | getFacePassEnrolment | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | getFacePassEnrolment | response | retentionAnchor | object |  | BL-106.
AccessService | getFacePassEnrolment | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | getFacePassEnrolment | response | capturedAt | string (date-time) | yes
AccessService | getFacePassEnrolment | response | consentPurposeId | string (uuid)
AccessService | getFacePassEnrolment | response | consentGivenAt | string (date-time)
AccessService | getFacePassEnrolment | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | getFacePassEnrolment | response | isActive | boolean |  | (read-only)
AccessService | getFacePassEnrolment | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | getFacePassEnrolment | param (path) | enrolmentId | string (uuid) | yes
LedgerService | getFinancialReport | response | report | FinancialReportKind: enum (profitAndLoss, balanceSheet, cashFlow, revenueByVenue, revenueByProduct, taxSummary) | yes | The report getFinancialReport returns.
LedgerService | getFinancialReport | response | fiscalPeriodId | string (uuid) | yes
LedgerService | getFinancialReport | response | legalEntityId | string (uuid) |  | (nullable)
LedgerService | getFinancialReport | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | getFinancialReport | response | currencyScale | integer
LedgerService | getFinancialReport | response | generatedAt | string (date-time) | yes
LedgerService | getFinancialReport | response | sections | array of object | yes
LedgerService | getFinancialReport | response | sections[].name | string | yes
LedgerService | getFinancialReport | response | sections[].lines | array of object | yes
LedgerService | getFinancialReport | response | sections[].lines[].label | string
LedgerService | getFinancialReport | response | sections[].lines[].accountCode | string |  | (nullable)
LedgerService | getFinancialReport | response | sections[].lines[].amount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getFinancialReport | response | sections[].lines[].priorPeriodAmount | object |  | The same line for the same period last year (decided 28 September, audit R127 (3)).
LedgerService | getFinancialReport | response | sections[].total | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getFinancialReport | response | sections[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getFinancialReport | response | sections[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getFinancialReport | response | sections[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getFinancialReport | param (query) | report | FinancialReportKind: enum (profitAndLoss, balanceSheet, cashFlow, revenueByVenue, revenueByProduct, taxSummary) | yes
LedgerService | getFinancialReport | param (query) | fiscalPeriodId | string (uuid) | yes
LedgerService | getFinancialReport | param (query) | legalEntityId | string (uuid)
LedgerService | getFinancialReport | param (query) | venueId | string (uuid)
LedgerService | getFinancialReport | param (query) | costCenterId | string (uuid)
FnbService | getFnbDeliveryPolicy | response | id | string (uuid) |  | (read-only)
FnbService | getFnbDeliveryPolicy | response | outletId | string (uuid) | yes
FnbService | getFnbDeliveryPolicy | response | collectionEnabled | boolean |  | (default True)
FnbService | getFnbDeliveryPolicy | response | deliveryEnabled | boolean |  | (default False)
FnbService | getFnbDeliveryPolicy | response | collectionPoint | string |  | (max length 200; nullable)
FnbService | getFnbDeliveryPolicy | response | collectionHoldMinutes | integer |  | (default 20)
FnbService | getFnbDeliveryPolicy | response | asapCollectionMinutes | integer |  | (default 25)
FnbService | getFnbDeliveryPolicy | response | asapDeliveryMinutes | integer |  | (default 45)
FnbService | getFnbDeliveryPolicy | response | slotMinutes | integer |  | (default 30)
FnbService | getFnbDeliveryPolicy | response | minimumOrder | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | deliveryFee | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | radiusKm | number |  | (min 0; nullable)
FnbService | getFnbDeliveryPolicy | response | emiratesServed | array of string
FnbService | getFnbDeliveryPolicy | response | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | getFnbDeliveryPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | getFnbDeliveryPolicy | param (query) | outletId | string (uuid) | yes
FnbService | getFnbOrder | response | id | string (uuid) | yes
FnbService | getFnbOrder | response | orderNumber | string | yes
FnbService | getFnbOrder | response | outletId | string (uuid) | yes
FnbService | getFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getFnbOrder | response | lines | array of object | yes
FnbService | getFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | getFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | getFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | getFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | getFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | getFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | getFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | getFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | getFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | getFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | getFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | getFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | getFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | getFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | getFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | getFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | getFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | getFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | getFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | getFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | response | createdAt | string (date-time) | yes
FnbService | getFnbOrder | response | recordedAt | string (date-time)
FnbService | getFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | param (path) | orderId | string (uuid) | yes
WhiteLabelService | getFonts | response | primaryLatin | string | yes
WhiteLabelService | getFonts | response | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getFonts | response | secondaryLatin | string |  | (nullable)
WhiteLabelService | getFonts | response | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getFonts | response | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getFonts | response | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
VenueOpsService | getGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | getGameCard | response | kind | string
VenueOpsService | getGameCard | response | venueId | string (uuid) | yes
VenueOpsService | getGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | getGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | getGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | getGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | getGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | getGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | getGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | getGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | getGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | getGameCard | param (path) | cardCode | string | yes
WalletService | getGiftCard | response | cardCode | string | yes
WalletService | getGiftCard | response | kind | string
WalletService | getGiftCard | response | faceValue | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getGiftCard | response | faceValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getGiftCard | response | faceValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getGiftCard | response | faceValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getGiftCard | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getGiftCard | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getGiftCard | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getGiftCard | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getGiftCard | response | status | enum (issued, active, partiallyRedeemed, redeemed, expired, blocked) | yes
WalletService | getGiftCard | response | blockedReason | string |  | (nullable)
WalletService | getGiftCard | response | issuedAt | string (date-time) | yes
WalletService | getGiftCard | response | activatedAt | string (date-time) |  | (nullable)
WalletService | getGiftCard | response | expiresAt | string (date-time) |  | (nullable)
WalletService | getGiftCard | param (path) | cardCode | string | yes
OrderService | getGroupBooking | response | id | string (uuid) | yes
OrderService | getGroupBooking | response | kind | enum (general, school, corporate, party) |  | (default general)
OrderService | getGroupBooking | response | packageProductId | string |  | The school-trip format or party package. (nullable)
OrderService | getGroupBooking | response | yearGroup | string |  | (max length 40; nullable)
OrderService | getGroupBooking | response | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | getGroupBooking | response | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | getGroupBooking | response | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | getGroupBooking | response | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | getGroupBooking | response | finalHeadcountDueBy | string (date-time) |  | (nullable)
OrderService | getGroupBooking | response | quoteSentAt | string (date-time) |  | (read-only; nullable)
OrderService | getGroupBooking | response | riskAssessmentSentAt | string (date-time) |  | (read-only; nullable)
OrderService | getGroupBooking | response | preferredDate | string (date) |  | The date the guest asked for on requestGroupBooking — what its 409 dateUnavailable is checked against. (nullable)
OrderService | getGroupBooking | response | orderId | string (uuid) | yes
OrderService | getGroupBooking | response | leaderSubjectId | string (uuid) | yes
OrderService | getGroupBooking | response | organisationName | string |  | (nullable)
OrderService | getGroupBooking | response | expectedSize | integer | yes
OrderService | getGroupBooking | response | confirmedSize | integer |  | (nullable)
OrderService | getGroupBooking | response | minimumSize | integer |  | Below which the group rate does not apply. (nullable)
OrderService | getGroupBooking | response | attendeeCaptureRequired | boolean |  | Whether names are needed before admission. (default False)
OrderService | getGroupBooking | response | attendeeCaptureDueBy | string (date-time) |  | (nullable)
OrderService | getGroupBooking | response | status | enum (provisional, confirmed, namesPending, complete, cancelled) | yes
OrderService | getGroupBooking | param (path) | groupBookingId | string (uuid) | yes
CatalogueService | getGroupPackageDefinition | response | id | string (uuid) |  | (read-only)
CatalogueService | getGroupPackageDefinition | response | productId | string |  | (read-only)
CatalogueService | getGroupPackageDefinition | response | kind | enum (school, party) | yes
CatalogueService | getGroupPackageDefinition | response | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | getGroupPackageDefinition | response | durationMinutes | integer | yes | (min 15)
CatalogueService | getGroupPackageDefinition | response | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | getGroupPackageDefinition | response | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | getGroupPackageDefinition | response | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | getGroupPackageDefinition | response | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | getGroupPackageDefinition | response | includes | array of string
CatalogueService | getGroupPackageDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | getGroupPackageDefinition | param (path) | productId | string | yes
FnbService | getGuestBill | response | visitId | string | yes
FnbService | getGuestBill | response | covers | integer
FnbService | getGuestBill | response | lines | array of object | yes
FnbService | getGuestBill | response | lines[].lineId | string | yes
FnbService | getGuestBill | response | lines[].orderId | string
FnbService | getGuestBill | response | lines[].name | string | yes
FnbService | getGuestBill | response | lines[].quantity | integer | yes
FnbService | getGuestBill | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | lines[].categoryCode | string |  | (nullable)
FnbService | getGuestBill | response | lines[].seatNumber | integer |  | (nullable)
FnbService | getGuestBill | response | subtotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | serviceCharge | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | serviceCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | serviceCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | serviceCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | param (path) | sessionId | string (uuid) | yes
MarketingService | getGuestConsents | response | subjectId | string (uuid) | yes
MarketingService | getGuestConsents | response | purposes | array of object | yes
MarketingService | getGuestConsents | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | getGuestConsents | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | getGuestConsents | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getGuestConsents | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | getGuestConsents | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | getGuestConsents | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | getGuestConsents | param (path) | subjectId | string (uuid) | yes
FnbService | getGuestMenu | response | outletId | string (uuid) | yes
FnbService | getGuestMenu | response | menuId | string (uuid) | yes
FnbService | getGuestMenu | response | name | string | yes
FnbService | getGuestMenu | response | inForceUntil | string (date-time) | yes | When this menu stops applying. (nullable)
FnbService | getGuestMenu | response | currency | string |  | (pattern ^[A-Z]{3}$)
FnbService | getGuestMenu | response | currencyScale | integer
FnbService | getGuestMenu | response | sections | array of object | yes
FnbService | getGuestMenu | response | sections[].name | string
FnbService | getGuestMenu | response | sections[].sortOrder | integer
FnbService | getGuestMenu | response | sections[].items | array of object
FnbService | getGuestMenu | response | sections[].items[].menuItemId | string (uuid) | yes
FnbService | getGuestMenu | response | sections[].items[].name | string | yes
FnbService | getGuestMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestMenu | response | sections[].items[].imageAssetRef | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].isAvailable | boolean | yes | Marked, not removed.
FnbService | getGuestMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) | yes | Always present.
FnbService | getGuestMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].modifierGroups | array of ModifierGroup
FnbService | getGuestMenu | param (path) | outletId | string (uuid) | yes
FnbService | getGuestMenu | param (query) | at | string (date-time) |  | Evaluate menu availability at this time rather than now.
FnbService | getGuestMenu | param (query) | language | string
FnbService | getGuestOrderStatus | response | orderId | string | yes
FnbService | getGuestOrderStatus | response | orderNumber | string
FnbService | getGuestOrderStatus | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getGuestOrderStatus | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getGuestOrderStatus | response | isReadyForCollection | boolean
FnbService | getGuestOrderStatus | response | lines | array of object | yes | Per-line status.
FnbService | getGuestOrderStatus | response | lines[].name | string
FnbService | getGuestOrderStatus | response | lines[].quantity | integer
FnbService | getGuestOrderStatus | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | getGuestOrderStatus | param (path) | orderId | string (uuid) | yes
MarketingService | getGuestProfile | response | id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | getGuestProfile | response | subjectId | string (uuid) | yes | Opaque reference.
MarketingService | getGuestProfile | response | displayName | string |  | (nullable)
MarketingService | getGuestProfile | response | email | string |  | (nullable)
MarketingService | getGuestProfile | response | phone | string |  | (nullable)
MarketingService | getGuestProfile | response | preferredLanguage | string |  | (nullable)
MarketingService | getGuestProfile | response | preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getGuestProfile | response | guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | getGuestProfile | response | tags | array of string
MarketingService | getGuestProfile | response | engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | getGuestProfile | response | engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | getGuestProfile | response | lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | getGuestProfile | response | lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | getGuestProfile | response | lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | getGuestProfile | response | lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | getGuestProfile | response | visitCount | integer
MarketingService | getGuestProfile | response | lastVisitAt | string (date-time) |  | (nullable)
MarketingService | getGuestProfile | response | isActive | boolean | yes
MarketingService | getGuestProfile | response | mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | getGuestProfile | response | mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getGuestProfile | response | consents | ConsentState
MarketingService | getGuestProfile | response | consents.subjectId | string (uuid) | yes
MarketingService | getGuestProfile | response | consents.purposes | array of object | yes
MarketingService | getGuestProfile | response | consents.purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | getGuestProfile | response | consents.purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | getGuestProfile | response | consents.purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getGuestProfile | response | consents.purposes[].noticeVersion | string |  | (nullable)
MarketingService | getGuestProfile | response | consents.purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | getGuestProfile | response | consents.purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | getGuestProfile | response | loyalty | LoyaltyPosition
MarketingService | getGuestProfile | response | loyalty.leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | getGuestProfile | response | loyalty.subjectId | string (uuid) | yes
MarketingService | getGuestProfile | response | loyalty.programmeId | string (uuid) | yes
MarketingService | getGuestProfile | response | loyalty.pointsBalance | integer | yes
MarketingService | getGuestProfile | response | loyalty.lifetimePoints | integer
MarketingService | getGuestProfile | response | loyalty.tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | getGuestProfile | response | loyalty.tierCode | string | yes
MarketingService | getGuestProfile | response | loyalty.tierName | string
MarketingService | getGuestProfile | response | loyalty.pointsToNextTier | integer |  | (nullable)
MarketingService | getGuestProfile | response | loyalty.nextExpiryPoints | integer |  | (nullable)
MarketingService | getGuestProfile | response | loyalty.nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | getGuestProfile | response | openCaseCount | integer
MarketingService | getGuestProfile | response | recentOrderIds | array of string
MarketingService | getGuestProfile | response | membershipIds | array of string (uuid)
MarketingService | getGuestProfile | response | notes | string |  | (nullable)
MarketingService | getGuestProfile | param (path) | subjectId | string (uuid) | yes
IdentityService | getGuestSession | response | subjectId | string (uuid) | yes
IdentityService | getGuestSession | response | displayName | string |  | (nullable)
IdentityService | getGuestSession | response | tokens | TokenPair | yes
IdentityService | getGuestSession | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | getGuestSession | response | tokens.refreshToken | string | yes
IdentityService | getGuestSession | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | getGuestSession | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | getGuestSession | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | getGuestSession | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | getGuestSession | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | getGuestSession | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | getGuestSession | response | mfaMethods[].id | string (uuid) | yes
IdentityService | getGuestSession | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | getGuestSession | response | mfaMethods[].label | string |  | (nullable)
IdentityService | getGuestSession | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | getGuestSession | response | mfaMethods[].isActive | boolean | yes
IdentityService | getGuestSession | response | mfaMethods[].isPrimary | boolean
IdentityService | getGuestSession | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | getGuestSession | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | getGuestSession | response | homeCellName | string |  | (nullable)
IdentityService | getGuestSession | response | preferredLanguage | string |  | (nullable)
IdentityService | getGuestSession | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
AiService | getGuidedChoiceSuggestion | response | id | string (uuid) |  | (read-only)
AiService | getGuidedChoiceSuggestion | response | venueId | string (uuid) | yes
AiService | getGuidedChoiceSuggestion | response | trigger | enum (productsUploaded, mappedProductWithdrawn, productsUncovered, manual) | yes
AiService | getGuidedChoiceSuggestion | response | status | enum (running, proposed, noSuggestion, failed, superseded) | yes | (read-only)
AiService | getGuidedChoiceSuggestion | response | productCount | integer |  | (min 0; read-only)
AiService | getGuidedChoiceSuggestion | response | questions | array of object |  | The questions chosen, in the order asked. (read-only)
AiService | getGuidedChoiceSuggestion | response | questions[].attribute | string |  | The catalogue attribute asked about: audience, level, minimum height or age, duration, price band, format, language.
AiService | getGuidedChoiceSuggestion | response | questions[].order | integer |  | (min 1)
AiService | getGuidedChoiceSuggestion | response | questions[].split | object |  | How evenly it divides the bookable products: products per answer.
AiService | getGuidedChoiceSuggestion | response | questions[].droppedBecause | string |  | Set where an attribute was considered and dropped (an answer would leave nothing bookable). (nullable)
AiService | getGuidedChoiceSuggestion | response | questions[].answers | array of object
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].value | string
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].leadsTo | enum (product, category, flow)
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].targetRef | string
AiService | getGuidedChoiceSuggestion | response | wordingSource | enum (model, attributeNames) |  | Where the text came from. (read-only)
AiService | getGuidedChoiceSuggestion | response | modelVersion | string |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | promptTemplateVersion | string |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | guidedChoiceId | string (uuid) |  | The white-label draft GuidedChoice it produced. (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | createdAt | string (date-time) |  | (read-only)
AiService | getGuidedChoiceSuggestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getGuidedChoiceSuggestion | param (path) | suggestionId | string (uuid) | yes
FnbService | getHaccpStatus | response | checksDue | integer
FnbService | getHaccpStatus | response | checksMissed | integer
FnbService | getHaccpStatus | response | openActions | integer
FnbService | getHaccpStatus | response | unsignedActions | integer
FnbService | getHaccpStatus | response | oldestOpenActionAgeHours | integer |  | (nullable)
FnbService | getHaccpStatus | response | lastInspectionAt | string (date-time) |  | (nullable)
WhiteLabelService | getHomepageLayout | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getHomepageLayout | response | sections | array of object | yes
WhiteLabelService | getHomepageLayout | response | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getHomepageLayout | response | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getHomepageLayout | response | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getHomepageLayout | response | sections[].sortOrder | integer | yes
WhiteLabelService | getHomepageLayout | response | sections[].isVisible | boolean | yes
WhiteLabelService | getHomepageLayout | response | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getHomepageLayout | response | sections[].maxItems | integer |  | How many items the section shows. (nullable)
WhiteLabelService | getHomepageLayout | response | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
CatalogueService | getLatestBundle | response | version | string | yes
CatalogueService | getLatestBundle | response | venueId | string (uuid) | yes
CatalogueService | getLatestBundle | response | isDelta | boolean | yes
CatalogueService | getLatestBundle | response | baseVersion | string |  | Present when isDelta. (nullable)
CatalogueService | getLatestBundle | response | signature | string | yes | Detached signature over contentHash.
CatalogueService | getLatestBundle | response | signatureKeyId | string | yes
CatalogueService | getLatestBundle | response | contentHash | string | yes
CatalogueService | getLatestBundle | response | staleAfter | string (date-time) | yes
CatalogueService | getLatestBundle | response | payload | object | yes | Products, variants, price lists, prices, tax codes, events, performances, envelope definitions, data mask field definitions and the venue's sale boards.
CatalogueService | getLatestBundle | response | payload.saleBoards | array of object |  | The venue's sale boards as tenancy.listSaleBoards returns them, read from platform.sale_board when the bundle is snapshotted (decided 28 September, audit R129 (4)).
CatalogueService | getLatestBundle | param (query) | since | string |  | Applied bundle version.
CatalogueService | getLatestBundle | param (header) | If-None-Match | string
MarketingService | getLoyaltyPosition | response | subjectId | string (uuid)
MarketingService | getLoyaltyPosition | response | programmeId | string (uuid)
MarketingService | getLoyaltyPosition | response | pointsBalance | integer
MarketingService | getLoyaltyPosition | response | pointsPending | integer |  | Earned and not yet cleared — a purchase inside the refund window.
MarketingService | getLoyaltyPosition | response | tier | string
MarketingService | getLoyaltyPosition | response | nextTier | string |  | The name of the next MarketingProgrammeTier by rank above the guest's current tier, resolved at read. (nullable)
MarketingService | getLoyaltyPosition | response | pointsToNextTier | integer |  | (nullable)
MarketingService | getLoyaltyPosition | response | expiringPoints | integer
MarketingService | getLoyaltyPosition | response | expiringAt | string (date-time) |  | Points that lapse unannounced are a complaint. (nullable)
MarketingService | getLoyaltyPosition | param (query) | programmeId | string (uuid) | yes | Which programme.
VenueOpsService | getMapResourceAvailability | response | mapId | string (uuid) | yes
VenueOpsService | getMapResourceAvailability | response | mapVersion | integer | yes | The published venue-map version the placements were read from; the client checks it against the map it cached.
VenueOpsService | getMapResourceAvailability | response | from | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | response | to | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | response | totals | object
VenueOpsService | getMapResourceAvailability | response | totals.total | integer
VenueOpsService | getMapResourceAvailability | response | totals.available | integer
VenueOpsService | getMapResourceAvailability | response | totals.held | integer
VenueOpsService | getMapResourceAvailability | response | totals.booked | integer
VenueOpsService | getMapResourceAvailability | response | totals.unavailable | integer
VenueOpsService | getMapResourceAvailability | response | resources | array of object | yes
VenueOpsService | getMapResourceAvailability | response | resources[].resourceId | string (uuid) | yes
VenueOpsService | getMapResourceAvailability | response | resources[].placedResourceId | string (uuid) |  | The venue-map.PlacedResource it was read from.
VenueOpsService | getMapResourceAvailability | response | resources[].label | string | yes | As on the map, e.g.
VenueOpsService | getMapResourceAvailability | response | resources[].kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) |  | BL-135.
VenueOpsService | getMapResourceAvailability | response | resources[].zone | string
VenueOpsService | getMapResourceAvailability | response | resources[].capacity | integer
VenueOpsService | getMapResourceAvailability | response | resources[].priceBandCode | string
VenueOpsService | getMapResourceAvailability | response | resources[].variantId | string (uuid) |  | What the cart line names to buy it.
VenueOpsService | getMapResourceAvailability | response | resources[].price | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getMapResourceAvailability | response | resources[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getMapResourceAvailability | response | resources[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getMapResourceAvailability | response | resources[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getMapResourceAvailability | response | resources[].status | enum (available, held, booked, unavailable) | yes | unavailable covers maintenance, a blackout, a block and a placement marked not bookable; the map greys all of them the same way.
VenueOpsService | getMapResourceAvailability | param (query) | mapId | string (uuid) | yes | The venue-map.VenueMap whose placed resources to report.
VenueOpsService | getMapResourceAvailability | param (query) | from | string (date-time) | yes | Start of the window.
VenueOpsService | getMapResourceAvailability | param (query) | to | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | param (query) | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) |  | Only resources of this kind, e.g.
VenueOpsService | getMediaAsset | response | id | string (uuid) | yes
VenueOpsService | getMediaAsset | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive) | yes
VenueOpsService | getMediaAsset | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | getMediaAsset | response | filename | string | yes
VenueOpsService | getMediaAsset | response | contentType | string | yes
VenueOpsService | getMediaAsset | response | sizeBytes | integer | yes
VenueOpsService | getMediaAsset | response | title | LocalisedText
VenueOpsService | getMediaAsset | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | getMediaAsset | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | getMediaAsset | response | width | integer |  | (nullable)
VenueOpsService | getMediaAsset | response | height | integer |  | (nullable)
VenueOpsService | getMediaAsset | response | durationSeconds | number |  | (nullable)
VenueOpsService | getMediaAsset | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | getMediaAsset | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | getMediaAsset | response | tags | array of string
VenueOpsService | getMediaAsset | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | getMediaAsset | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | getMediaAsset | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | getMediaAsset | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | getMediaAsset | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | getMediaAsset | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | getMediaAsset | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | getMediaAsset | response | rights.licensor | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | getMediaAsset | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | getMediaAsset | response | rights.attributionText | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | getMediaAsset | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | getMediaAsset | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | getMediaAsset | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | getMediaAsset | response | isRightsExpired | boolean
VenueOpsService | getMediaAsset | response | version | integer
VenueOpsService | getMediaAsset | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | getMediaAsset | response | createdAt | string (date-time) | yes
VenueOpsService | getMediaAsset | response | derivatives | array of object |  | Generated from the original, never uploaded separately.
VenueOpsService | getMediaAsset | response | derivatives[].label | string
VenueOpsService | getMediaAsset | response | derivatives[].width | integer
VenueOpsService | getMediaAsset | response | derivatives[].height | integer
VenueOpsService | getMediaAsset | response | derivatives[].sizeBytes | integer
VenueOpsService | getMediaAsset | response | derivatives[].url | string
VenueOpsService | getMediaAsset | response | usage | array of MediaUsage |  | Every place this asset is referenced.
VenueOpsService | getMediaAsset | response | usage[].extractedText | string |  | Text pulled out of an uploaded document, after extraction.
VenueOpsService | getMediaAsset | response | usage[].id | string (uuid) |  | Added 20 August. (read-only)
VenueOpsService | getMediaAsset | response | usage[].surface | enum (tenantBranding, homepageBanner, promoBlock, contentPage, product, event, menuItem, merchandise, …) | yes
VenueOpsService | getMediaAsset | response | usage[].referenceId | string | yes
VenueOpsService | getMediaAsset | response | usage[].label | string
VenueOpsService | getMediaAsset | response | usage[].isLive | boolean |  | True where the referencing surface is published to guests.
VenueOpsService | getMediaAsset | response | collections | array of object
VenueOpsService | getMediaAsset | response | collections[].id | string (uuid)
VenueOpsService | getMediaAsset | response | collections[].name | string
VenueOpsService | getMediaAsset | response | previousVersions | array of object
VenueOpsService | getMediaAsset | response | previousVersions[].version | integer
VenueOpsService | getMediaAsset | response | previousVersions[].replacedAt | string (date-time)
VenueOpsService | getMediaAsset | response | previousVersions[].replacedByPrincipalId | string (uuid)
VenueOpsService | getMediaAsset | param (path) | mediaId | string (uuid) | yes
OrderService | getMediaEntitlements | response | mediaCode | string | yes
OrderService | getMediaEntitlements | response | mediaKind | enum (qr, wristband, card, nfc, mobilePass)
OrderService | getMediaEntitlements | response | subjectId | string (uuid) |  | (nullable)
OrderService | getMediaEntitlements | response | isValid | boolean | yes
OrderService | getMediaEntitlements | response | invalidReason | string |  | (nullable)
OrderService | getMediaEntitlements | response | canAcceptMore | boolean |  | False where the media has been surrendered, expired or blocked.
OrderService | getMediaEntitlements | response | entitlements | array of object | yes
OrderService | getMediaEntitlements | response | entitlements[].entitlementId | string (uuid)
OrderService | getMediaEntitlements | response | entitlements[].name | string
OrderService | getMediaEntitlements | response | entitlements[].kind | enum (admission, locker, fnb, retail, parking, rental, experience, membership)
OrderService | getMediaEntitlements | response | entitlements[].orderId | string (uuid)
OrderService | getMediaEntitlements | response | entitlements[].addedAt | string (date-time)
OrderService | getMediaEntitlements | response | entitlements[].status | object |  | Replaced isRedeemed on 17 August.
OrderService | getMediaEntitlements | response | entitlements[].entriesUsed | integer
OrderService | getMediaEntitlements | response | entitlements[].entriesAllowed | integer |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].redeemedAt | string (date-time) |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].transferredToSubjectId | string (uuid) |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].validTo | string (date-time) |  | (nullable)
OrderService | getMediaEntitlements | param (path) | mediaCode | string | yes | The QR, wristband or card the guest is already carrying.
FnbService | getMenu | response | id | string (uuid) | yes
FnbService | getMenu | response | code | string | yes | (max length 64)
FnbService | getMenu | response | name | string | yes | (max length 200)
FnbService | getMenu | response | outletId | string (uuid) | yes
FnbService | getMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | getMenu | response | availability.daysOfWeek | array of integer
FnbService | getMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | getMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | getMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | getMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | getMenu | response | sections | array of MenuSection
FnbService | getMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | getMenu | response | sections[].code | string | yes
FnbService | getMenu | response | sections[].name | string | yes
FnbService | getMenu | response | sections[].sortOrder | integer | yes
FnbService | getMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | getMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | getMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | getMenu | response | sections[].items[].name | string | yes
FnbService | getMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | getMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getMenu | response | sections[].items[].sortOrder | integer
FnbService | getMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | getMenu | response | sections[].items[].stationId | string (uuid) |  | (nullable)
FnbService | getMenu | response | sections[].items[].menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | getMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | getMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | getMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | getMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | getMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | getMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | getMenu | response | isActive | boolean | yes
FnbService | getMenu | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | getMenu | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | getMenu | param (path) | menuId | string (uuid) | yes
IdentityService | getMyIdentityVerification | response | id | string (uuid) | yes | (read-only)
IdentityService | getMyIdentityVerification | response | subjectId | string (uuid) | yes
IdentityService | getMyIdentityVerification | response | subjectDocumentId | string (uuid) |  | The pii.subject_document row submitted.
IdentityService | getMyIdentityVerification | response | documentKind | enum (passport, emiratesId, nationalId, drivingLicence, residencePermit, other)
IdentityService | getMyIdentityVerification | response | documentNumberLast4 | string |  | (max length 4; read-only; nullable)
IdentityService | getMyIdentityVerification | response | reason | enum (policyRequired, ageRestrictedPurchase, residentPricing, accountRecovery)
IdentityService | getMyIdentityVerification | response | status | enum (pending, verified, rejected, resubmissionRequested) | yes | (read-only)
IdentityService | getMyIdentityVerification | response | method | enum (manualReview, documentScanner, provider) |  | (read-only; nullable)
IdentityService | getMyIdentityVerification | response | decisionReason | string |  | (max length 300; read-only; nullable)
IdentityService | getMyIdentityVerification | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
IdentityService | getMyIdentityVerification | response | submittedAt | string (date-time) | yes | (read-only)
IdentityService | getMyIdentityVerification | response | decidedAt | string (date-time) |  | (read-only; nullable)
IdentityService | getMyIdentityVerification | response | documentImageDeletedAt | string (date-time) |  | When the scan (and any selfie) was deleted under the policy's retention. (read-only; nullable)
CatalogueService | getMyMemberships | param (query) | includeLapsed | boolean
WhiteLabelService | getNavigation | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getNavigation | response | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getNavigation | response | items | array of object | yes | (max items 12)
WhiteLabelService | getNavigation | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getNavigation | response | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getNavigation | response | items[].icon | string
WhiteLabelService | getNavigation | response | items[].target | LinkTarget | yes
WhiteLabelService | getNavigation | response | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | getNavigation | response | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getNavigation | response | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | getNavigation | response | items[].target.contentPageId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.productId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.eventId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.url | string
WhiteLabelService | getNavigation | response | items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | getNavigation | response | items[].sortOrder | integer | yes
WhiteLabelService | getNavigation | response | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getNavigation | response | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getNavigation | response | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
VenueOpsService | getNextTransportDeparture | response | departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getNextTransportDeparture | response | performanceId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getNextTransportDeparture | response | routeCode | string |  | The price card's label, e.g.
VenueOpsService | getNextTransportDeparture | response | departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | getNextTransportDeparture | response | arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | getNextTransportDeparture | response | durationMinutes | integer | yes | (min 0)
VenueOpsService | getNextTransportDeparture | response | period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | getNextTransportDeparture | response | seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | getNextTransportDeparture | response | fitsParty | boolean
VenueOpsService | getNextTransportDeparture | response | fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getNextTransportDeparture | response | fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getNextTransportDeparture | response | fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getNextTransportDeparture | response | fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getNextTransportDeparture | response | partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getNextTransportDeparture | response | partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getNextTransportDeparture | response | partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getNextTransportDeparture | response | partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getNextTransportDeparture | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | param (query) | toStationId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | param (query) | after | string (date-time)
VenueOpsService | getNextTransportDeparture | param (query) | passengers | array of string |  | As on searchTransportDepartures.
AccessService | getOfflinePackage | response | etag | string | yes
AccessService | getOfflinePackage | response | generatedAt | string (date-time) | yes
AccessService | getOfflinePackage | response | validFrom | string (date-time) | yes
AccessService | getOfflinePackage | response | validTo | string (date-time) | yes
AccessService | getOfflinePackage | response | accessPointId | string (uuid) | yes
AccessService | getOfflinePackage | response | entitlementsVersion | integer |  | The highest access.entitlement change included (SD-052, 29 September).
AccessService | getOfflinePackage | response | dynamicPolicies | array of AccessDynamicPolicy |  | The active guest-admission dynamic policies for this access point's zones (SD-052), so an offline gate applies the same rules as an online one.
AccessService | getOfflinePackage | response | dynamicPolicies[].id | string (uuid) | yes | The policyId
AccessService | getOfflinePackage | response | dynamicPolicies[].venueId | string (uuid) |  | (nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].scopePath | string | yes | ltree of the owning scope node; where it applies further is access.policy_scope_assignment
AccessService | getOfflinePackage | response | dynamicPolicies[].name | string | yes | (max length 200)
AccessService | getOfflinePackage | response | dynamicPolicies[].policyType | enum (guestAttribute, accreditation, occupancy, employee, risk, membership, timeEvent) | yes
AccessService | getOfflinePackage | response | dynamicPolicies[].contextType | enum (date, day, time, season, event, performance, specialEvent, holiday, …) |  | Context/time/event policies (setContextTimeEvent) (nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].identityType | enum (guest, member, annualPassHolder, employee, contractor, vendor, performer, media, …) |  | Identity-based policies (listIdentityMembershipAccreditation) (nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].conditionExpression | string | yes | Condition tree over access.access_attribute keys using AND, OR, NOT, IN and BETWEEN
AccessService | getOfflinePackage | response | dynamicPolicies[].result | enum (allow, deny, review, requireId, requireBiometric, requireCompanion, requireSupervisor) | yes
AccessService | getOfflinePackage | response | dynamicPolicies[].priority | integer |  | (nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].allowedZoneIds | array of string (uuid)
AccessService | getOfflinePackage | response | dynamicPolicies[].deniedZoneIds | array of string (uuid)
AccessService | getOfflinePackage | response | dynamicPolicies[].monitorThresholdPercent | integer |  | Occupancy policies. (min 0; max 100; nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].restrictThresholdPercent | integer |  | Occupancy policies. (min 0; max 100; nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].validFrom | string (date-time) |  | (nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].validTo | string (date-time) |  | The grant expires automatically at validTo (nullable)
AccessService | getOfflinePackage | response | dynamicPolicies[].status | enum (draft, pendingApproval, active, inactive, expired) | yes | (default draft)
AccessService | getOfflinePackage | response | dynamicPolicies[].currentVersion | integer | yes | The version in force (access.dynamic_policy_version) (min 1)
AccessService | getOfflinePackage | response | dynamicPolicies[].createdAt | string (date-time) |  | (read-only)
AccessService | getOfflinePackage | response | dynamicPolicies[].updatedAt | string (date-time) |  | (read-only)
AccessService | getOfflinePackage | response | entitlements | array of object | yes | Read from access.entitlement (SD-052).
AccessService | getOfflinePackage | response | entitlements[].ticketId | string (uuid) | yes | The Entitlement.id.
AccessService | getOfflinePackage | response | entitlements[].mediaCodes | array of string | yes | A ticket may carry several media over its life.
AccessService | getOfflinePackage | response | entitlements[].validFrom | string (date-time) | yes
AccessService | getOfflinePackage | response | entitlements[].validTo | string (date-time) | yes
AccessService | getOfflinePackage | response | entitlements[].performanceId | string (uuid) |  | (nullable)
AccessService | getOfflinePackage | response | entitlements[].entriesAllowed | integer | yes | (nullable)
AccessService | getOfflinePackage | response | entitlements[].entriesUsed | integer
AccessService | getOfflinePackage | response | entitlements[].reentryAllowed | boolean | yes
AccessService | getOfflinePackage | response | entitlements[].admissionRulesId | string (uuid)
AccessService | getOfflinePackage | response | delegatedRights | array of object |  | Redemption rights issued by other cells and valid at this access point.
AccessService | getOfflinePackage | response | delegatedRights[].rightId | string | yes
AccessService | getOfflinePackage | response | delegatedRights[].ticketId | string (uuid) | yes | The Entitlement.id in the issuing cell.
AccessService | getOfflinePackage | response | delegatedRights[].issuingCellId | string | yes
AccessService | getOfflinePackage | response | delegatedRights[].guestLinkId | string |  | (nullable)
AccessService | getOfflinePackage | response | delegatedRights[].mediaCodes | array of string
AccessService | getOfflinePackage | response | delegatedRights[].validFrom | string (date-time) | yes
AccessService | getOfflinePackage | response | delegatedRights[].validTo | string (date-time) | yes
AccessService | getOfflinePackage | response | delegatedRights[].entriesAllowed | integer | yes | (nullable)
AccessService | getOfflinePackage | response | delegatedRights[].entriesConsumed | integer | yes
AccessService | getOfflinePackage | response | delegatedRights[].admissionRulesId | string (uuid)
AccessService | getOfflinePackage | response | blacklist | array of string |  | Media codes to deny outright regardless of entitlement state.
AccessService | getOfflinePackage | response | admissionRules | array of object
AccessService | getOfflinePackage | response | admissionRules[].id | string (uuid) | yes
AccessService | getOfflinePackage | response | admissionRules[].openMinutesBefore | integer | yes
AccessService | getOfflinePackage | response | admissionRules[].closeMinutesAfter | integer | yes
AccessService | getOfflinePackage | response | admissionRules[].maxDurationMinutes | integer |  | (nullable)
AccessService | getOfflinePackage | response | admissionRules[].requiresExitBeforeReentry | boolean
AccessService | getOfflinePackage | response | accreditationCredentials | array of AccessAccreditationCredential |  | Accreditation credentials that admit at this access point, from access.accreditation_credential (29 September, build; BL-181).
AccessService | getOfflinePackage | response | accreditationCredentials[].id | string (uuid) | yes | The accreditation credential's id (credentialId on the events).
AccessService | getOfflinePackage | response | accreditationCredentials[].holderId | string (uuid) | yes
AccessService | getOfflinePackage | response | accreditationCredentials[].programmeId | string (uuid) |  | (nullable)
AccessService | getOfflinePackage | response | accreditationCredentials[].kind | string |  | printedBadge, mobileCredential, qr, nfcCard, rfidCard or wristband, as issued.
AccessService | getOfflinePackage | response | accreditationCredentials[].encodedIdentifier | string | yes | What the gate reads from the credential.
AccessService | getOfflinePackage | response | accreditationCredentials[].validFrom | string (date) |  | (nullable)
AccessService | getOfflinePackage | response | accreditationCredentials[].validTo | string (date) |  | (nullable)
AccessService | getOfflinePackage | response | accreditationCredentials[].zoneIds | array of string (uuid) |  | The holder's effective zones, from the event (effectiveZones).
AccessService | getOfflinePackage | response | accreditationCredentials[].holderStatus | enum (active, suspended, revoked, expired, archived) |  | The holder's status as last published; only active admits.
AccessService | getOfflinePackage | response | accreditationCredentials[].admits | boolean | yes | False once the credential is replaced or the holder is not active.
AccessService | getOfflinePackage | response | accreditationCredentials[].sourceChangedAt | string (date-time) |  | The issuedAt or changedAt of the event last applied; an older event arriving late is ignored.
AccessService | getOfflinePackage | response | accreditationCredentials[].scopePath | string | yes | The partition key (ADR-0005), the accreditation programme's scope.
AccessService | getOfflinePackage | param (query) | sinceVersion | integer |  | The entitlementsVersion of the package the device holds; omitted, the whole package (SD-052).
AccessService | getOfflinePackage | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | getOfflinePackage | param (query) | validFrom | string (date-time) | yes
AccessService | getOfflinePackage | param (query) | validTo | string (date-time) | yes
AccessService | getOfflinePackage | param (header) | If-None-Match | string
OrderService | getOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | getOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | getOrder | response | channel | object | yes | Where it came from.
OrderService | getOrder | response | venueId | string (uuid) | yes
OrderService | getOrder | response | scopePath | string | yes
OrderService | getOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | getOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | getOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | getOrder | response | droppedPromotions[].name | string
OrderService | getOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | getOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | getOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines | array of OrderLine | yes
OrderService | getOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getOrder | response | lines[].variantId | string (uuid) | yes
OrderService | getOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getOrder | response | lines[].performanceId | string (uuid)
OrderService | getOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | getOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].holderName | string |  | (nullable)
OrderService | getOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | getOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | getOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | getOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | getOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | getOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | getOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | getOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | getOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | getOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | getOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | getOrder | response | payments | array of Payment
OrderService | getOrder | response | payments[].id | string (uuid) | yes
OrderService | getOrder | response | payments[].orderId | string (uuid) | yes
OrderService | getOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | getOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | getOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | getOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | getOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | getOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | getOrder | response | payments[].providerName | string |  | (nullable)
OrderService | getOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | getOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | getOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | getOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | getOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | getOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | getOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | getOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | principalId | string (uuid)
OrderService | getOrder | response | workstationId | string (uuid)
OrderService | getOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | getOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | getOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | getOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | getOrder | response | createdAt | string (date-time) | yes
OrderService | getOrder | response | recordedAt | string (date-time) | yes
OrderService | getOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | getOrder | param (path) | orderId | string (uuid) | yes
OrderService | getOrder | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
OrderService | getOrderCalendarEvent | param (path) | orderId | string (uuid) | yes
OrderService | getOrderStatement | response | orderId | string (uuid) | yes
OrderService | getOrderStatement | response | orderNumber | string | yes
OrderService | getOrderStatement | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | currencyScale | integer |  | Resolved from the region, not stored (ADR-0018, 24 August).
OrderService | getOrderStatement | response | entries | array of object | yes | Sequential.
OrderService | getOrderStatement | response | entries[].kind | enum (sale, payment, refund, void, modification, exchange, fee, variance, …) | yes
OrderService | getOrderStatement | response | entries[].description | string
OrderService | getOrderStatement | response | entries[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | entries[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | entries[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | entries[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | entries[].runningBalance | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | entries[].runningBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | entries[].runningBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | entries[].runningBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | entries[].referenceId | string |  | (nullable)
OrderService | getOrderStatement | response | entries[].principalId | string (uuid) |  | (nullable)
OrderService | getOrderStatement | response | entries[].occurredAt | string (date-time) | yes
OrderService | getOrderStatement | response | totalPaid | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | totalPaid.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | totalPaid.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | totalPaid.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | totalRefunded | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | totalRefunded.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | totalRefunded.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | totalRefunded.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | currentBalance | object | yes | Positive means the guest owes; negative means a refund is outstanding.
OrderService | getOrderStatement | response | currentBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | currentBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | currentBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | param (path) | orderId | string (uuid) | yes
OrderService | getPaymentLink | response | link | object |  | The link as its holder may see it, not the staff record.
OrderService | getPaymentLink | response | link.status | enum (issued, viewed, paid, expired, cancelled, superseded) | yes
OrderService | getPaymentLink | response | link.expiresAt | string (date-time) | yes
OrderService | getPaymentLink | response | link.releaseHoldOnExpiry | boolean
OrderService | getPaymentLink | response | lines | array of OrderLine
OrderService | getPaymentLink | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getPaymentLink | response | lines[].variantId | string (uuid) | yes
OrderService | getPaymentLink | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getPaymentLink | response | lines[].performanceId | string (uuid)
OrderService | getPaymentLink | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getPaymentLink | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getPaymentLink | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getPaymentLink | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getPaymentLink | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getPaymentLink | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getPaymentLink | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getPaymentLink | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getPaymentLink | response | lines[].quantity | integer | yes | (min 1)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getPaymentLink | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].holderName | string |  | (nullable)
OrderService | getPaymentLink | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getPaymentLink | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | getPaymentLink | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | getPaymentLink | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | getPaymentLink | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | getPaymentLink | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | getPaymentLink | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | getPaymentLink | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | getPaymentLink | response | lines[].discounts[].id | string (uuid) | yes
OrderService | getPaymentLink | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | getPaymentLink | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | getPaymentLink | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | getPaymentLink | response | amountDue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | amountDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | amountDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | amountDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | venueName | string
OrderService | getPaymentLink | response | expiresInSeconds | integer
OrderService | getPaymentLink | param (path) | token | string | yes
CatalogueService | getPerformance | response | id | string (uuid) | yes
CatalogueService | getPerformance | response | eventId | string (uuid) | yes
CatalogueService | getPerformance | response | startsAt | string (date-time) | yes
CatalogueService | getPerformance | response | endsAt | string (date-time) | yes
CatalogueService | getPerformance | response | approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | getPerformance | response | requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | getPerformance | response | status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | getPerformance | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | getPerformance | response | seatMapId | string (uuid) |  | (nullable)
CatalogueService | getPerformance | response | language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | getPerformance | response | format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | getPerformance | param (path) | performanceId | string (uuid) | yes
CatalogueService | getProduct | response | id | string (uuid) | yes
CatalogueService | getProduct | response | code | string | yes | (max length 64)
CatalogueService | getProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | getProduct | response | name | string | yes | (max length 200)
CatalogueService | getProduct | response | description | string
CatalogueService | getProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | getProduct | response | venueId | string (uuid) | yes
CatalogueService | getProduct | response | scopePath | string | yes
CatalogueService | getProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | getProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | getProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | getProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | getProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | getProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | getProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | getProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | getProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | getProduct | response | hasVariants | boolean | yes
CatalogueService | getProduct | response | variantCount | integer
CatalogueService | getProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | getProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | getProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | getProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | getProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | getProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | getProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | getProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | getProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | getProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | getProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | getProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | getProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | getProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | getProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | getProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | getProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | getProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | getProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | getProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | getProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | getProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | getProduct | response | media[].altText | object |  | (nullable)
CatalogueService | getProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | getProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | getProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | getProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | getProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | getProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | getProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | getProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | getProduct | param (path) | productId | string (uuid) | yes
CatalogueService | getProductEligibilityRule | response | id | string (uuid) |  | (read-only)
CatalogueService | getProductEligibilityRule | response | productId | string |  | (read-only)
CatalogueService | getProductEligibilityRule | response | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | getProductEligibilityRule | response | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | getProductEligibilityRule | response | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | getProductEligibilityRule | response | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | getProductEligibilityRule | response | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | getProductEligibilityRule | response | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | getProductEligibilityRule | response | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | getProductEligibilityRule | response | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | getProductEligibilityRule | response | waiverRequired | boolean |  | (default False)
CatalogueService | getProductEligibilityRule | response | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | getProductEligibilityRule | response | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | getProductEligibilityRule | response | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | getProductEligibilityRule | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | getProductEligibilityRule | param (path) | productId | string | yes
CatalogueService | getPromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | getPromotionUsage | response | promotionId | string (uuid) | yes
CatalogueService | getPromotionUsage | response | redemptionCount | integer | yes
CatalogueService | getPromotionUsage | response | discountGiven | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | budgetRemaining | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | budgetRemaining.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | budgetRemaining.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | budgetRemaining.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | isBudgetExhausted | boolean
CatalogueService | getPromotionUsage | response | byChannel | array of object
CatalogueService | getPromotionUsage | response | byChannel[].channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | getPromotionUsage | response | byChannel[].redemptionCount | integer
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | param (path) | promotionId | string (uuid) | yes
WhiteLabelService | getPublishedBookingFlow | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getPublishedBookingFlow | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getPublishedBookingFlow | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getPublishedBookingFlow | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getPublishedBookingFlow | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getPublishedBookingFlow | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getPublishedBookingFlow | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getPublishedBookingFlow | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedBookingFlow | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getPublishedBookingFlow | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getPublishedBookingFlow | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getPublishedBookingFlow | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getPublishedBookingFlow | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getPublishedBookingFlow | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getPublishedBookingFlow | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getPublishedBookingFlow | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getPublishedBookingFlow | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getPublishedBookingFlow | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getPublishedBookingFlow | param (query) | productId | string (uuid)
WhiteLabelService | getPublishedBookingFlow | param (query) | productCategoryId | string (uuid)
WhiteLabelService | getPublishedBookingFlow | param (query) | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …)
WhiteLabelService | getPublishedGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | getPublishedGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | getPublishedGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | getPublishedGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | getPublishedGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | getPublishedGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getPublishedGuidedChoice | param (path) | venueId | string (uuid) | yes
VenueOpsService | getQueue | response | code | string | yes | (max length 64)
VenueOpsService | getQueue | response | name | LocalisedText | yes
VenueOpsService | getQueue | response | venueId | string (uuid) | yes
VenueOpsService | getQueue | response | attractionProductId | string (uuid)
VenueOpsService | getQueue | response | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | getQueue | response | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | getQueue | response | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | getQueue | response | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | getQueue | response | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | getQueue | response | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | getQueue | response | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | getQueue | response | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | getQueue | response | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | getQueue | response | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | getQueue | response | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | getQueue | response | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | getQueue | response | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | getQueue | response | cycleMinutes | number | yes | (min 0)
VenueOpsService | getQueue | response | maxPartySize | integer |  | (default 6)
VenueOpsService | getQueue | response | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | getQueue | response | heightRequirementCm | integer |  | (nullable)
VenueOpsService | getQueue | response | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | getQueue | response | zone | string |  | (nullable)
VenueOpsService | getQueue | response | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | getQueue | response | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | getQueue | response | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | getQueue | response | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | getQueue | response | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | getQueue | response | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | getQueue | response | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | getQueue | response | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | getQueue | response | id | string (uuid) | yes
VenueOpsService | getQueue | response | status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | getQueue | response | statusReason | string |  | (nullable)
VenueOpsService | getQueue | response | waitingPartyCount | integer | yes
VenueOpsService | getQueue | response | waitingGuestCount | integer
VenueOpsService | getQueue | response | currentWaitMinutes | integer |  | (nullable)
VenueOpsService | getQueue | response | waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | getQueue | response | waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | getQueue | response | manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | getQueue | response | manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | getQueue | response | expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | getQueue | response | nowServingPartyNumber | integer |  | (nullable)
VenueOpsService | getQueue | response | lastCalledAt | string (date-time) |  | (nullable)
VenueOpsService | getQueue | response | throughputLastHour | integer
VenueOpsService | getQueue | response | noShowRatePercent | number
VenueOpsService | getQueue | response | feed | QueueFeedHealth
VenueOpsService | getQueue | response | feed.feedId | string (uuid) | yes
VenueOpsService | getQueue | response | feed.adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) |  | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | getQueue | response | feed.isHealthy | boolean | yes | Healthy means the last reading arrived within the feed's expected interval (decided 28 September, audit R106 (1)): lastReadingAt is no older than expectedIntervalSeconds.
VenueOpsService | getQueue | response | feed.isQuiet | boolean | yes | No reading within the expected interval.
VenueOpsService | getQueue | response | feed.lastReadingAt | string (date-time) |  | (nullable)
VenueOpsService | getQueue | response | feed.expectedIntervalSeconds | integer |  | The feed's expectedIntervalSeconds — the interval isQuiet is judged against, returned here so a health panel does not need the feed row as well.
VenueOpsService | getQueue | response | feed.readingsLastHour | integer
VenueOpsService | getQueue | response | feed.discardedLastHour | integer |  | Out-of-order readings rejected in the last hour — rows of queue.reading for this feed with disposition: discardedOutOfOrder.
VenueOpsService | getQueue | param (path) | queueId | string (uuid) | yes
VenueOpsService | getQueueFeedHealth | response | feedId | string (uuid) | yes
VenueOpsService | getQueueFeedHealth | response | adaptor | QueueFeedAdaptor: enum (generic, mock, vendorAdaptor) |  | Vendor adaptors are bespoke work (ADR-0012).
VenueOpsService | getQueueFeedHealth | response | isHealthy | boolean | yes | Healthy means the last reading arrived within the feed's expected interval (decided 28 September, audit R106 (1)): lastReadingAt is no older than expectedIntervalSeconds.
VenueOpsService | getQueueFeedHealth | response | isQuiet | boolean | yes | No reading within the expected interval.
VenueOpsService | getQueueFeedHealth | response | lastReadingAt | string (date-time) |  | (nullable)
VenueOpsService | getQueueFeedHealth | response | expectedIntervalSeconds | integer |  | The feed's expectedIntervalSeconds — the interval isQuiet is judged against, returned here so a health panel does not need the feed row as well.
VenueOpsService | getQueueFeedHealth | response | readingsLastHour | integer
VenueOpsService | getQueueFeedHealth | response | discardedLastHour | integer |  | Out-of-order readings rejected in the last hour — rows of queue.reading for this feed with disposition: discardedOutOfOrder.
VenueOpsService | getQueueFeedHealth | param (path) | feedId | string (uuid) | yes
ReportingService | getReport | response | name | string | yes | (max length 200)
ReportingService | getReport | response | description | string |  | (max length 1000)
ReportingService | getReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | getReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | getReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | getReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | getReport | response | columns[].field | string | yes
ReportingService | getReport | response | columns[].label | string
ReportingService | getReport | response | columns[].aggregation | object |  | (default none)
ReportingService | getReport | response | columns[].sortOrder | integer
ReportingService | getReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | getReport | response | columns[].format | string |  | (nullable)
ReportingService | getReport | response | filters | array of ReportFilter
ReportingService | getReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | getReport | response | filters[].field | string | yes
ReportingService | getReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | getReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | getReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | getReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | getReport | response | groupBy | array of string
ReportingService | getReport | response | parameters | array of ReportParameter
ReportingService | getReport | response | parameters[].key | string | yes
ReportingService | getReport | response | parameters[].label | string | yes
ReportingService | getReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | getReport | response | parameters[].isRequired | boolean | yes
ReportingService | getReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | getReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | getReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | getReport | response | id | string (uuid) | yes
ReportingService | getReport | response | version | string | yes | The current version.
ReportingService | getReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | getReport | response | isRetired | boolean | yes
ReportingService | getReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | getReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | getReport | response | createdAt | string (date-time) | yes
ReportingService | getReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | getReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | getReport | param (path) | reportId | string (uuid) | yes
OrderService | getReservation | response | id | string (uuid) | yes
OrderService | getReservation | response | venueId | string (uuid) | yes
OrderService | getReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | getReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | getReservation | response | lines | array of CreateOrderLine
OrderService | getReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getReservation | response | lines[].variantId | string (uuid) | yes
OrderService | getReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getReservation | response | lines[].performanceId | string (uuid)
OrderService | getReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | getReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getReservation | response | lines[].holderName | string |  | (nullable)
OrderService | getReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getReservation | response | expiresAt | string (date-time) | yes
OrderService | getReservation | response | createdAt | string (date-time) | yes
OrderService | getReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | getReservation | param (path) | reservationId | string (uuid) | yes
VenueOpsService | getResourceAvailability | response | resourceId | string (uuid)
VenueOpsService | getResourceAvailability | response | freeWindows | array of object
VenueOpsService | getResourceAvailability | response | freeWindows[].from | string (date-time)
VenueOpsService | getResourceAvailability | response | freeWindows[].to | string (date-time)
VenueOpsService | getResourceAvailability | response | blockedWindows | array of object |  | With a reason, because they are not the same.
VenueOpsService | getResourceAvailability | response | blockedWindows[].from | string (date-time)
VenueOpsService | getResourceAvailability | response | blockedWindows[].to | string (date-time)
VenueOpsService | getResourceAvailability | response | blockedWindows[].reason | enum (booked, held, setup, teardown, maintenance, blackout, closed, cleaning) |  | held is a live ResourceHold (rev 3 REV3-15): taken now, free again if it expires.
VenueOpsService | getResourceAvailability | param (path) | resourceId | string (uuid) | yes
VenueOpsService | getResourceAvailability | param (query) | from | string (date-time) | yes
VenueOpsService | getResourceAvailability | param (query) | to | string (date-time) | yes
VenueOpsService | getResourceHold | response | id | string (uuid) | yes
VenueOpsService | getResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | getResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | getResourceHold | response | from | string (date-time) | yes
VenueOpsService | getResourceHold | response | to | string (date-time) | yes
VenueOpsService | getResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | getResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | getResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | getResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | getResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | getResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | getResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | getResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | getResourceHold | param (path) | holdId | string (uuid) | yes
RetailService | getRetailSale | response | id | string | yes
RetailService | getRetailSale | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | getRetailSale | response | orderId | string | yes | The order in the Order & Payment context.
RetailService | getRetailSale | response | outletId | string (uuid) | yes
RetailService | getRetailSale | response | shiftId | string |  | (nullable)
RetailService | getRetailSale | response | subjectId | string (uuid) |  | (nullable)
RetailService | getRetailSale | response | lines | array of object | yes
RetailService | getRetailSale | response | lines[].lineId | string
RetailService | getRetailSale | response | lines[].merchandiseId | string (uuid)
RetailService | getRetailSale | response | lines[].name | string
RetailService | getRetailSale | response | lines[].quantity | integer
RetailService | getRetailSale | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].serialNumbers | array of string
RetailService | getRetailSale | response | lines[].returnedQuantity | integer
RetailService | getRetailSale | response | lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | getRetailSale | response | lines[].notReturnableReason | string |  | (nullable)
RetailService | getRetailSale | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | reprintCount | integer
RetailService | getRetailSale | response | createdAt | string (date-time) | yes
RetailService | getRetailSale | response | recordedAt | string (date-time)
RetailService | getRetailSale | param (path) | saleId | string (uuid) | yes
RetailService | getReturnPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | getReturnPolicy | response | outletId | string (uuid) | yes
RetailService | getReturnPolicy | response | defaultWindowDays | integer | yes | (min 0)
RetailService | getReturnPolicy | response | requiresReceipt | boolean | yes | (default True)
RetailService | getReturnPolicy | response | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | getReturnPolicy | response | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | getReturnPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getReturnPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | requiresApprovalAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getReturnPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | getReturnPolicy | response | nonReturnableCategoryIds | array of string (uuid)
RetailService | getReturnPolicy | param (path) | outletId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | performanceId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | seatMapId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | renderMode | enum (graphical, list) | yes | The mode the server actually used.
CatalogueService | getSeatAvailability | response | totals | object | yes
CatalogueService | getSeatAvailability | response | totals.total | integer
CatalogueService | getSeatAvailability | response | totals.available | integer
CatalogueService | getSeatAvailability | response | totals.held | integer
CatalogueService | getSeatAvailability | response | totals.sold | integer
CatalogueService | getSeatAvailability | response | totals.blocked | integer
CatalogueService | getSeatAvailability | response | totals.buffered | integer
CatalogueService | getSeatAvailability | response | byCategory | array of object
CatalogueService | getSeatAvailability | response | byCategory[].categoryId | string (uuid)
CatalogueService | getSeatAvailability | response | byCategory[].available | integer
CatalogueService | getSeatAvailability | response | byCategory[].sold | integer
CatalogueService | getSeatAvailability | response | byCategory[].price | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getSeatAvailability | response | byCategory[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getSeatAvailability | response | byCategory[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getSeatAvailability | response | byCategory[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getSeatAvailability | response | sections | array of object |  | The map's sections with what a guest screen needs to show the view from each (decided 29 September, rev 3 23SEP-14): the photo where the venue supplied one, otherwise null and the client renders the…
CatalogueService | getSeatAvailability | response | sections[].code | string | yes
CatalogueService | getSeatAvailability | response | sections[].name | string | yes
CatalogueService | getSeatAvailability | response | sections[].viewAssetId | string (uuid) |  | As Section.viewAssetId. (nullable)
CatalogueService | getSeatAvailability | response | sections[].boundary | array of Point |  | As Section.boundary. (nullable)
CatalogueService | getSeatAvailability | response | sections[].boundary[].x | number | yes
CatalogueService | getSeatAvailability | response | sections[].boundary[].y | number | yes
CatalogueService | getSeatAvailability | response | seats | array of object | yes
CatalogueService | getSeatAvailability | response | seats[].seatId | string | yes
CatalogueService | getSeatAvailability | response | seats[].status | SeatStatus: enum (available, held, sold, blocked, buffered, unavailable) | yes
CatalogueService | getSeatAvailability | response | seats[].categoryId | string (uuid) |  | (nullable)
CatalogueService | getSeatAvailability | response | seats[].displayLabel | string |  | What the guest sees, e.g.
CatalogueService | getSeatAvailability | response | seats[].position | object |  | The seat's coordinates on the map, as on Seat. (nullable)
CatalogueService | getSeatAvailability | response | seats[].position.x | number | yes
CatalogueService | getSeatAvailability | response | seats[].position.y | number | yes
CatalogueService | getSeatAvailability | param (path) | performanceId | string (uuid) | yes
CatalogueService | getSeatAvailability | param (query) | sectionCode | string
CatalogueService | getSeatAvailability | param (query) | categoryId | string (uuid)
CatalogueService | getSeatAvailability | param (query) | availableOnly | boolean
CatalogueService | getSeatAvailability | param (query) | mode | enum (auto, graphical, list) |  | graphical requires geometry and returns coordinates.
CatalogueService | getSeatHold | response | id | string | yes
CatalogueService | getSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | getSeatHold | response | seatIds | array of string | yes
CatalogueService | getSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | getSeatHold | response | status | enum (held, converted, released, expired) | yes
CatalogueService | getSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | getSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | getSeatHold | response | extensionCount | integer
CatalogueService | getSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | getSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | getSeatHold | param (path) | holdId | string (uuid) | yes
OrderService | getShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | getShift | response | workstationId | string (uuid) | yes
OrderService | getShift | response | venueId | string (uuid) | yes
OrderService | getShift | response | scopePath | string | yes
OrderService | getShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | getShift | response | principalDisplayName | string
OrderService | getShift | response | incidents | array of object |  | BL-097.
OrderService | getShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | getShift | response | incidents[].at | string (date-time)
OrderService | getShift | response | incidents[].principalId | string (uuid)
OrderService | getShift | response | incidents[].note | string |  | (nullable)
OrderService | getShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | getShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getShift | response | depositBoxCode | string |  | (nullable)
OrderService | getShift | response | bagNumber | string |  | (nullable)
OrderService | getShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | getShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | getShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | getShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | getShift | response | openedAt | string (date-time) | yes
OrderService | getShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | getShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | getShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | getShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | getShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | getShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | getShift | response | approvals | array of object
OrderService | getShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | getShift | response | approvals[].principalId | string (uuid) | yes
OrderService | getShift | response | approvals[].at | string (date-time) | yes
OrderService | getShift | response | approvals[].reason | string
OrderService | getShift | param (path) | shiftId | string (uuid) | yes
WhiteLabelService | getSiteSetupProgress | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getSiteSetupProgress | response | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | getSiteSetupProgress | response | currentStep | object |  | (nullable)
WhiteLabelService | getSiteSetupProgress | response | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | getSiteSetupProgress | response | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | getSiteSetupProgress | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getSiteSetupProgress | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts | array of StoreAccount | yes
WhiteLabelService | getStoreAccounts | response | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | getStoreAccounts | response | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | getStoreAccounts | response | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | getStoreAccounts | response | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | getStoreAccounts | response | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key, sent once and kept in the secret store; this is its reference. (nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].listing | object |  | The store listing.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.category | string
WhiteLabelService | getStoreAccounts | response | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | getStoreAccounts | response | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | getStoreAccounts | response | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | getStoreAccounts | response | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | items | array of object | yes
WhiteLabelService | getStoreAccounts | response | items[].item | enum (appleDunsNumber, appleDeveloperAccount, googlePlayDeveloperAccount, storeListing, appIcons, publishedConfiguration) | yes
WhiteLabelService | getStoreAccounts | response | items[].done | boolean | yes
WhiteLabelService | getStoreAccounts | response | items[].clientOwned | boolean |  | True for the three accounts, which only the client can open.
WhiteLabelService | getStoreAccounts | response | items[].guidance | string |  | What to do next, in the operator's language.
FnbService | getTableMap | response | outletId | string (uuid) | yes
FnbService | getTableMap | response | zones | array of string
FnbService | getTableMap | response | tables | array of TableState | yes
FnbService | getTableMap | response | tables[].id | string (uuid) | yes
FnbService | getTableMap | response | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | getTableMap | response | tables[].capacity | integer | yes | (min 1)
FnbService | getTableMap | response | tables[].zone | string |  | (nullable)
FnbService | getTableMap | response | tables[].position | object
FnbService | getTableMap | response | tables[].position.x | number
FnbService | getTableMap | response | tables[].position.y | number
FnbService | getTableMap | response | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | getTableMap | response | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | getTableMap | response | tables[].status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | getTableMap | response | tables[].visitId | string (uuid) |  | (nullable)
FnbService | getTableMap | response | tables[].covers | integer |  | (nullable)
FnbService | getTableMap | response | tables[].seatedAt | string (date-time) |  | (nullable)
FnbService | getTableMap | response | tables[].serverPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableMap | response | tables[].billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableMap | response | tables[].billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableMap | response | tables[].billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableMap | response | tables[].billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableMap | param (path) | outletId | string (uuid) | yes
LedgerService | getTaxDocumentRendition | response | documentId | string (uuid) | yes
LedgerService | getTaxDocumentRendition | response | documentKind | enum (taxInvoice, creditMemo) | yes
LedgerService | getTaxDocumentRendition | response | documentNumber | string
LedgerService | getTaxDocumentRendition | response | language | string |  | (nullable)
LedgerService | getTaxDocumentRendition | response | contentType | string |  | (default application/pdf)
LedgerService | getTaxDocumentRendition | response | url | string (uri) | yes
LedgerService | getTaxDocumentRendition | response | expiresAt | string (date-time) | yes
LedgerService | getTaxDocumentRendition | param (path) | documentId | string (uuid) | yes | A tax invoice id or a credit memo id.
LedgerService | getTaxDocumentRendition | param (query) | language | string
LedgerService | getTaxInvoice | response | id | string (uuid) | yes | (read-only)
LedgerService | getTaxInvoice | response | invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | getTaxInvoice | response | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | getTaxInvoice | response | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | getTaxInvoice | response | legalEntityId | string (uuid) | yes
LedgerService | getTaxInvoice | response | templateId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | venueId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | orderIds | array of string (uuid)
LedgerService | getTaxInvoice | response | supplierName | string
LedgerService | getTaxInvoice | response | supplierAddress | string |  | (nullable)
LedgerService | getTaxInvoice | response | supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | getTaxInvoice | response | buyerName | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerAddress | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | getTaxInvoice | response | buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | getTaxInvoice | response | customerAccountId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | issuedAt | string (date-time) | yes
LedgerService | getTaxInvoice | response | supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | getTaxInvoice | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | languages | array of string
LedgerService | getTaxInvoice | response | supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | getTaxInvoice | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | getTaxInvoice | response | issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | getTaxInvoice | response | lines | array of FinTaxInvoiceLine | yes
LedgerService | getTaxInvoice | response | lines[].lineNumber | integer | yes | (min 1)
LedgerService | getTaxInvoice | response | lines[].orderId | string (uuid)
LedgerService | getTaxInvoice | response | lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | lines[].description | string | yes | (max length 500)
LedgerService | getTaxInvoice | response | lines[].quantity | number | yes
LedgerService | getTaxInvoice | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | lines[].taxRate | number |  | (min 0; max 100)
LedgerService | getTaxInvoice | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | getTaxInvoice | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | getTaxInvoice | response | taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | getTaxInvoice | response | taxSummary[].taxRate | number
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | getTaxInvoice | param (path) | invoiceId | string (uuid) | yes
WhiteLabelService | getTenantAppStatus | response | tenantId | string (uuid) | yes
WhiteLabelService | getTenantAppStatus | response | isPublished | boolean | yes | True once any version has been published.
WhiteLabelService | getTenantAppStatus | response | publishedVersion | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | publishedAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | draftVersion | string |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | hasUnpublishedChanges | boolean |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | activeModuleCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | licensedModuleCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | activePageCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | isInMaintenance | boolean | yes
WhiteLabelService | getTenantAppStatus | response | maintenanceMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantAppStatus | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantAppStatus | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.phone | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.address | object |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantAppStatus | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | getTenantAppStatus | response | availabilityMessage | object |  | What the sold-out or closed screen says (WEB-029). (nullable)
WhiteLabelService | getTenantAppStatus | response | venues | array of object |  | Public: the venues a guest can pick (decided 28 September, audit R267; schema named 29 September, readiness close-out, our build plan). (max items 200)
WhiteLabelService | getTenantAppStatus | response | venues[].venueId | string (uuid) | yes | The venue's scope node (tenancy.OrgUnit.id, level venue): what every guest screen that declares venueId from: session reads once the guest picks it.
WhiteLabelService | getTenantAppStatus | response | venues[].name | string | yes | The venue's name (tenancy.OrgUnit.name). (max length 200)
WhiteLabelService | getTenantAppStatus | response | venues[].city | string |  | Shown under the name so two venues with similar names can be told apart. (max length 120; nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday | object |  | Today's opening hours in the venue's time zone, from tenancy.VenueSettings opening hours. (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday.opens | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday.closes | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | getTenantAppStatus | response | whatsNew | array of object |  | Public: the guest "what's new" (decided 29 September, rev 3 GAP-B2). (max items 10)
WhiteLabelService | getTenantAppStatus | response | whatsNew[].version | string | yes | The release version.
WhiteLabelService | getTenantAppStatus | response | whatsNew[].publishedAt | string (date-time) | yes | When the release reached the tenant's cell.
WhiteLabelService | getTenantAppStatus | response | whatsNew[].notes | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantAppStatus | response | recentChanges | array of object |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | recentChanges[].area | string
WhiteLabelService | getTenantAppStatus | response | recentChanges[].description | string
WhiteLabelService | getTenantAppStatus | response | recentChanges[].principalId | string (uuid)
WhiteLabelService | getTenantAppStatus | response | recentChanges[].at | string (date-time)
WhiteLabelService | getTenantConfig | response | tenantId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | version | string | yes | The draft's working version label; the published one is ConfigVersion.version.
WhiteLabelService | getTenantConfig | response | isDraft | boolean |  | True for the working draft, which is the only row. (read-only)
WhiteLabelService | getTenantConfig | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload), PNG or SVG and at most 2 MB (decided 28 September, audit R270).
WhiteLabelService | getTenantConfig | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getTenantConfig | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getTenantConfig | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getTenantConfig | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getTenantConfig | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getTenantConfig | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getTenantConfig | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getTenantConfig | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getTenantConfig | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getTenantConfig | response | appIcons | AppIcons
WhiteLabelService | getTenantConfig | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getTenantConfig | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getTenantConfig | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | getTenantConfig | response | appIcons.derived[].size | string
WhiteLabelService | getTenantConfig | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | getTenantConfig | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getTenantConfig | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getTenantConfig | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlow | BookingFlowConfig |  | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
WhiteLabelService | getTenantConfig | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getTenantConfig | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getTenantConfig | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getTenantConfig | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getTenantConfig | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getTenantConfig | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getTenantConfig | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getTenantConfig | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getTenantConfig | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getTenantConfig | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getTenantConfig | response | bookingFlows | array of BookingFlow |  | Every venue's booking flows in the draft (whitelabel.booking_flow), so a publish snapshots them with the rest (decided 29 September, W12). (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].id | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getTenantConfig | response | bookingFlows[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getTenantConfig | response | bookingFlows[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getTenantConfig | response | bookingFlows[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getTenantConfig | response | bookingFlows[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getTenantConfig | response | theme | Theme
WhiteLabelService | getTenantConfig | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode | object |  | Optional dark variant.
WhiteLabelService | getTenantConfig | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getTenantConfig | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getTenantConfig | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getTenantConfig | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getTenantConfig | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | fonts | FontConfig
WhiteLabelService | getTenantConfig | response | fonts.primaryLatin | string | yes
WhiteLabelService | getTenantConfig | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getTenantConfig | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getTenantConfig | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getTenantConfig | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | getTenantConfig | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | getTenantConfig | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | getTenantConfig | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | getTenantConfig | response | footer.columns | array of object
WhiteLabelService | getTenantConfig | response | footer.columns[].heading | string
WhiteLabelService | getTenantConfig | response | footer.columns[].links | array of object
WhiteLabelService | getTenantConfig | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | getTenantConfig | response | footer.legalLinks.termsUrl | string
WhiteLabelService | getTenantConfig | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | getTenantConfig | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | footer.copyrightText | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks | array of object
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].platform | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].url | string
WhiteLabelService | getTenantConfig | response | notificationBranding | object |  | BL-003. (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.senderName | string
WhiteLabelService | getTenantConfig | response | notificationBranding.replyToEmail | string (email)
WhiteLabelService | getTenantConfig | response | notificationBranding.smsSenderId | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.whatsappBusinessId | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.logoAssetId | string (uuid) |  | (nullable)
WhiteLabelService | getTenantConfig | response | enabledPaymentMethods | array of string |  | BL-004. (nullable)
WhiteLabelService | getTenantConfig | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | getTenantConfig | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | getTenantConfig | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | getTenantConfig | response | header | HeaderConfig
WhiteLabelService | getTenantConfig | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | getTenantConfig | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | getTenantConfig | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getTenantConfig | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | getTenantConfig | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | navigation.items[].icon | string
WhiteLabelService | getTenantConfig | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | getTenantConfig | response | navigation.items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | getTenantConfig | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | getTenantConfig | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getTenantConfig | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getTenantConfig | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | homepage | HomepageLayout
WhiteLabelService | getTenantConfig | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | homepage.sections | array of object | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getTenantConfig | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getTenantConfig | response | homepage.sections[].maxItems | integer |  | How many items the section shows. (nullable)
WhiteLabelService | getTenantConfig | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | getTenantConfig | response | modules | array of ModuleEnablement
WhiteLabelService | getTenantConfig | response | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getTenantConfig | response | modules[].displayName | string
WhiteLabelService | getTenantConfig | response | modules[].isLicensed | boolean | yes | From the tenant's subscription.
WhiteLabelService | getTenantConfig | response | modules[].isEnabled | boolean | yes
WhiteLabelService | getTenantConfig | response | modules[].referencedBy | array of string |  | Navigation items and homepage sections pointing at this module. (read-only)
WhiteLabelService | getTenantConfig | response | features | array of FeatureToggle
WhiteLabelService | getTenantConfig | response | features[].featureKey | object | yes | guestCheckout is off by default (decided 17 September 2026, matrix 2.6.28, placement settled by [ADR-0045](../../docs/adr/0045-every-order-carries-a-proven-contact.md) 18 September): the venue sets t…
WhiteLabelService | getTenantConfig | response | features[].displayName | string
WhiteLabelService | getTenantConfig | response | features[].isEnabled | boolean | yes
WhiteLabelService | getTenantConfig | response | features[].changeScope | object | yes | Wallet and payment integrations are buildTime on native apps — enabling one needs a release, not a publish. (read-only)
WhiteLabelService | getTenantConfig | response | features[].requiresConfiguration | boolean |  | True where the feature needs credentials or setup elsewhere first.
WhiteLabelService | getTenantConfig | response | languages | LanguageConfig
WhiteLabelService | getTenantConfig | response | languages.languages | array of string | yes
WhiteLabelService | getTenantConfig | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | getTenantConfig | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | getTenantConfig | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].language | string
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].areas | array of string
WhiteLabelService | getTenantConfig | response | updatedAt | string (date-time)
WhiteLabelService | getTenantConfig | response | isInMaintenance | boolean |  | Written by setMaintenanceMode; read by getTenantAppStatus. (default False)
WhiteLabelService | getTenantConfig | response | maintenanceMessage | object |  | The message on the branded maintenance screen. (nullable)
WhiteLabelService | getTenantConfig | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantConfig | response | contact | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | contact.phone | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.address | object |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantConfig | response | availability | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | availabilityMessage | object |  | Live state, written by setMaintenanceMode (audit R073). (nullable)
WhiteLabelService | getTenantConfig | response | venues | array of object |  | The tenant's active venues, for the guest venue picker on WEB-001 and GST-001 (decided 28 September, audit R267).
WhiteLabelService | getTenantConfig | response | venues[].venueId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | venues[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | venues[].city | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | venues[].openingHours | object |  | Today's hours as shown to a guest, e.g. (nullable)
WhiteLabelService | getTenantConfig | param (query) | version | string |  | Read a published version's snapshot instead of the working draft.
WhiteLabelService | getTheme | response | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode | object |  | Optional dark variant.
WhiteLabelService | getTheme | response | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getTheme | response | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getTheme | response | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getTheme | response | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getTheme | response | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.payButton | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.link | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.badge | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
VenueOpsService | getTransportFareTable | response | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | getTransportFareTable | response | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | matrix | array of object |  | matrix only.
VenueOpsService | getTransportFareTable | response | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | getTransportFareTable | response | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | getTransportFareTable | response | passengerTypes[].name | LocalisedText | yes
VenueOpsService | getTransportFareTable | response | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | getTransportFareTable | response | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | getTransportFareTable | response | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | getTransportFareTable | response | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | getTransportFareTable | response | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | getTransportFareTable | response | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | getTransportFareTable | response | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | getTransportFareTable | response | effectiveFrom | string (date-time) | yes
VenueOpsService | getTransportFareTable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | getTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | getTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | getTransportRoute | response | name | LocalisedText | yes
VenueOpsService | getTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | getTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | getTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | getTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | getTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | getTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | getTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | getTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | getTransportRoute | response | stops[].station | Station
VenueOpsService | getTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | getTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | getTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | getTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | getTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | getTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | getTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | getTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | getTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | getTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | getTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | getTransportRoute | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportRouteMap | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRouteMap | response | lineCode | string
VenueOpsService | getTransportRouteMap | response | colour | string
VenueOpsService | getTransportRouteMap | response | stops | array of object | yes | Every stop in route order.
VenueOpsService | getTransportRouteMap | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRouteMap | response | stops[].sequence | integer | yes
VenueOpsService | getTransportRouteMap | response | stops[].name | string | yes | Localised to the caller.
VenueOpsService | getTransportRouteMap | response | stops[].shortName | string
VenueOpsService | getTransportRouteMap | response | stops[].latitude | number |  | (nullable)
VenueOpsService | getTransportRouteMap | response | stops[].longitude | number |  | (nullable)
VenueOpsService | getTransportRouteMap | response | stops[].offsetMinutes | integer
VenueOpsService | getTransportRouteMap | response | stops[].onJourney | boolean | yes | Between the boarding and alighting stops
VenueOpsService | getTransportRouteMap | response | stops[].isBoarding | boolean
VenueOpsService | getTransportRouteMap | response | stops[].isAlighting | boolean
VenueOpsService | getTransportRouteMap | response | intermediateStopCount | integer |  | Stops between boarding and alighting — the number behind "Show full route (n stops)".
VenueOpsService | getTransportRouteMap | response | bounds | object |  | The box around the stops with coordinates, for the map's initial view. (nullable)
VenueOpsService | getTransportRouteMap | response | bounds.south | number
VenueOpsService | getTransportRouteMap | response | bounds.west | number
VenueOpsService | getTransportRouteMap | response | bounds.north | number
VenueOpsService | getTransportRouteMap | response | bounds.east | number
VenueOpsService | getTransportRouteMap | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportRouteMap | param (query) | fromStationId | string (uuid)
VenueOpsService | getTransportRouteMap | param (query) | toStationId | string (uuid)
AiService | getVenueHistoryImport | response | id | string (uuid) | yes | (read-only)
AiService | getVenueHistoryImport | response | venueId | string (uuid) | yes
AiService | getVenueHistoryImport | response | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | getVenueHistoryImport | response | assetId | string (uuid)
AiService | getVenueHistoryImport | response | sourceSystem | string |  | (nullable)
AiService | getVenueHistoryImport | response | columnMapping | object
AiService | getVenueHistoryImport | response | dryRun | boolean |  | (default False)
AiService | getVenueHistoryImport | response | status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | getVenueHistoryImport | response | periodFrom | string (date) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | periodTo | string (date) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | monthsCovered | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsRead | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsLoaded | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsRejected | integer |  | (read-only)
AiService | getVenueHistoryImport | response | findings | array of object |  | (read-only)
AiService | getVenueHistoryImport | response | findings[].row | integer
AiService | getVenueHistoryImport | response | findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | getVenueHistoryImport | response | findings[].detail | string
AiService | getVenueHistoryImport | response | requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | getVenueHistoryImport | response | createdAt | string (date-time) |  | (read-only)
AiService | getVenueHistoryImport | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getVenueHistoryImport | param (path) | importId | string (uuid) | yes
VenueOpsService | getVenueMap | response | version | integer |  | The published version these points and paths belong to, which is the number a client caches and sends back as version. (read-only; nullable)
VenueOpsService | getVenueMap | response | map | VenueMap |  | A park map, or a floor plan.
VenueOpsService | getVenueMap | response | map.id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | map.name | string | yes
VenueOpsService | getVenueMap | response | map.venueId | string (uuid) | yes
VenueOpsService | getVenueMap | response | map.scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | getVenueMap | response | map.kind | enum (park, floor, zone, parking)
VenueOpsService | getVenueMap | response | map.floorLevel | integer |  | (nullable)
VenueOpsService | getVenueMap | response | map.status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | getVenueMap | response | map.publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | getVenueMap | response | map.isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | getVenueMap | response | map.baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | getVenueMap | response | map.baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | getVenueMap | response | map.baseImageAlignment.imageWidthPx | integer
VenueOpsService | getVenueMap | response | map.baseImageAlignment.imageHeightPx | integer
VenueOpsService | getVenueMap | response | map.baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | getVenueMap | response | map.tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.boundsGeoJson | string |  | (nullable)
VenueOpsService | getVenueMap | response | map.graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | getVenueMap | response | points | array of VenuePoint
VenueOpsService | getVenueMap | response | points[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | points[].mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | getVenueMap | response | points[].kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | getVenueMap | response | points[].name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | getVenueMap | response | points[].nameLocalised | object |  | (nullable)
VenueOpsService | getVenueMap | response | points[].position | object | yes | Drawing coordinates.
VenueOpsService | getVenueMap | response | points[].position.x | number | yes
VenueOpsService | getVenueMap | response | points[].position.y | number | yes
VenueOpsService | getVenueMap | response | points[].outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | getVenueMap | response | points[].productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | getVenueMap | response | points[].accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | getVenueMap | response | points[].isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | getVenueMap | response | points[].openingHours | string |  | (nullable)
VenueOpsService | getVenueMap | response | points[].iconRef | string |  | (nullable)
VenueOpsService | getVenueMap | response | points[].isActive | boolean |  | (default True)
VenueOpsService | getVenueMap | response | points[].isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | getVenueMap | response | points[].isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | getVenueMap | response | points[].description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | getVenueMap | response | points[].media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | getVenueMap | response | points[].media[].assetId | string (uuid) | yes
VenueOpsService | getVenueMap | response | points[].media[].kind | enum (image, video) | yes
VenueOpsService | getVenueMap | response | points[].media[].isPrimary | boolean |  | (default False)
VenueOpsService | getVenueMap | response | points[].media[].altText | string |  | (max length 200; nullable)
VenueOpsService | getVenueMap | response | points[].featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | getVenueMap | response | points[].featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | getVenueMap | response | points[].featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | getVenueMap | response | points[].featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | getVenueMap | response | points[].typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | getVenueMap | response | points[].interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | getVenueMap | response | points[].cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | getVenueMap | response | points[].retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | getVenueMap | response | paths | array of VenuePath
VenueOpsService | getVenueMap | response | paths[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | paths[].mapId | string (uuid) | yes | From the path of the operation that writes the path. (read-only)
VenueOpsService | getVenueMap | response | paths[].fromPointId | string (uuid) | yes
VenueOpsService | getVenueMap | response | paths[].toPointId | string (uuid) | yes
VenueOpsService | getVenueMap | response | paths[].geometry | string |  | The centreline this edge follows, as an encoded polyline. (nullable)
VenueOpsService | getVenueMap | response | paths[].distanceMetres | number |  | Computed by the server from geometry and the georeference. (read-only; nullable)
VenueOpsService | getVenueMap | response | paths[].isStepFree | boolean |  | The single most important attribute on this object. (default True)
VenueOpsService | getVenueMap | response | paths[].isIndoor | boolean |  | (default False)
VenueOpsService | getVenueMap | response | paths[].restrictedByPointId | string (uuid) |  | Where a path is one-way, it is because of a thing on it — not because of the path. (nullable)
VenueOpsService | getVenueMap | response | paths[].closedReason | string |  | Set by setPathClosure during works or an incident, never by sending it here. (read-only; nullable)
VenueOpsService | getVenueMap | response | resources | array of PlacedResource |  | The bookable resources placed on this version of the map (rev 3 REV3-15).
VenueOpsService | getVenueMap | response | resources[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | resources[].mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | getVenueMap | response | resources[].resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | getVenueMap | response | resources[].label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | getVenueMap | response | resources[].kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | getVenueMap | response | resources[].zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | getVenueMap | response | resources[].capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | getVenueMap | response | resources[].priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | getVenueMap | response | resources[].variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | getVenueMap | response | resources[].position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | getVenueMap | response | resources[].position.x | number | yes
VenueOpsService | getVenueMap | response | resources[].position.y | number | yes
VenueOpsService | getVenueMap | response | resources[].boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | getVenueMap | response | resources[].boundary[].x | number
VenueOpsService | getVenueMap | response | resources[].boundary[].y | number
VenueOpsService | getVenueMap | response | resources[].isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | getVenueMap | param (path) | mapId | string (uuid) | yes
VenueOpsService | getVenueMap | param (query) | version | integer |  | Absent means the published version.
VenueOpsService | getVenueMap | param (query) | draft | boolean |  | Read the working draft instead of a published version.
VenueOpsService | getVenueMapGraph | response | mapId | string (uuid) | yes
VenueOpsService | getVenueMapGraph | response | version | integer | yes | Bumped by a publish or a closure, and stored as VenueMap.graphVersion.
VenueOpsService | getVenueMapGraph | response | generatedAt | string (date-time)
VenueOpsService | getVenueMapGraph | response | nodes | array of object | yes
VenueOpsService | getVenueMapGraph | response | nodes[].pointId | string (uuid)
VenueOpsService | getVenueMapGraph | response | nodes[].x | number
VenueOpsService | getVenueMapGraph | response | nodes[].y | number
VenueOpsService | getVenueMapGraph | response | nodes[].kind | string
VenueOpsService | getVenueMapGraph | response | nodes[].isStepFree | boolean
VenueOpsService | getVenueMapGraph | response | edges | array of object | yes
VenueOpsService | getVenueMapGraph | response | edges[].from | string (uuid)
VenueOpsService | getVenueMapGraph | response | edges[].to | string (uuid)
VenueOpsService | getVenueMapGraph | response | edges[].distanceMetres | number
VenueOpsService | getVenueMapGraph | response | edges[].isStepFree | boolean
VenueOpsService | getVenueMapGraph | response | edges[].throughPointId | string |  | Where an access point restricts this edge. (nullable)
VenueOpsService | getVenueMapGraph | response | edges[].isClosed | boolean
VenueOpsService | getVenueMapGraph | response | components | integer |  | How many disconnected parts.
VenueOpsService | getVenueMapGraph | param (path) | mapId | string (uuid) | yes
VenueOpsService | getVenueMapGraph | param (query) | draft | boolean |  | The working draft's graph instead of the published one.
VenueOpsService | getVenueMapGraph | param (query) | stepFreeOnly | boolean |  | Returns the step-free subgraph, not a filtered copy of the whole one.
TenancyService | getVenueSettings | response | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | getVenueSettings | response | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | getVenueSettings | response | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | getVenueSettings | response | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | getVenueSettings | response | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | getVenueSettings | response | supportHours | object |  | CF-100.
TenancyService | getVenueSettings | response | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | getVenueSettings | response | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | getVenueSettings | response | supportHours.windows | array of object
TenancyService | getVenueSettings | response | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | getVenueSettings | response | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | getVenueSettings | response | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | getVenueSettings | response | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | getVenueSettings | response | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | getVenueSettings | response | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | getVenueSettings | response | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | getVenueSettings | response | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | getVenueSettings | response | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | getVenueSettings | response | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | getVenueSettings | response | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | getVenueSettings | response | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | getVenueSettings | response | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | getVenueSettings | response | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | getVenueSettings | response | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | getVenueSettings | response | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | getVenueSettings | response | segregatedAccess.schedule | array of object
TenancyService | getVenueSettings | response | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | getVenueSettings | response | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | getVenueSettings | response | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | getVenueSettings | response | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | getVenueSettings | response | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | getVenueSettings | response | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | getVenueSettings | response | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | getVenueSettings | response | alerting | object |  | CF-134.
TenancyService | getVenueSettings | response | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | getVenueSettings | response | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | getVenueSettings | response | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | getVenueSettings | response | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | getVenueSettings | response | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | getVenueSettings | response | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | getVenueSettings | response | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | getVenueSettings | response | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | getVenueSettings | response | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | getVenueSettings | response | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | getVenueSettings | response | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | getVenueSettings | response | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | getVenueSettings | response | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | getVenueSettings | response | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | getVenueSettings | response | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | getVenueSettings | response | catalogue | object |  | (nullable)
TenancyService | getVenueSettings | response | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | getVenueSettings | response | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | getVenueSettings | response | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | getVenueSettings | response | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | getVenueSettings | response | inventory | object |  | (nullable)
TenancyService | getVenueSettings | response | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | getVenueSettings | response | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | getVenueSettings | response | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | getVenueSettings | response | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | getVenueSettings | response | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | getVenueSettings | response | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | getVenueSettings | response | seating | object |  | (nullable)
TenancyService | getVenueSettings | response | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | getVenueSettings | response | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | getVenueSettings | response | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | getVenueSettings | response | promotions | object |  | (nullable)
TenancyService | getVenueSettings | response | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | getVenueSettings | response | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | getVenueSettings | response | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | getVenueSettings | response | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | getVenueSettings | response | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | getVenueSettings | response | fnb | object |  | (nullable)
TenancyService | getVenueSettings | response | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | getVenueSettings | response | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | getVenueSettings | response | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | getVenueSettings | response | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | getVenueSettings | response | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | getVenueSettings | response | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | getVenueSettings | response | queue | object |  | (nullable)
TenancyService | getVenueSettings | response | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | getVenueSettings | response | reporting | object |  | (nullable)
TenancyService | getVenueSettings | response | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | getVenueSettings | response | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | getVenueSettings | response | marketing | object |  | (nullable)
TenancyService | getVenueSettings | response | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | getVenueSettings | response | identity | object |  | (nullable)
TenancyService | getVenueSettings | response | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | getVenueSettings | response | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | getVenueSettings | response | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | getVenueSettings | response | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | getVenueSettings | param (path) | venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | getVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | getVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | getVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | getVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | getVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | getVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | getVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | getVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | getVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | getVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | getVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | getVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | getVisitPlan | response | inputs.pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | getVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | getVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | getVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | getVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | getVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | getVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | getVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | getVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | getVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | getVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | getVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | getVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | getVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | getVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | getVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | getVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | getVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | getVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | getVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | getVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | getVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | getVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | getVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | getVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | getVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | getVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | getVisitPlan | param (query) | version | integer |  | Absent means the current version.
OrderService | getVisitReminder | response | id | string (uuid) |  | (read-only)
OrderService | getVisitReminder | response | orderId | string (uuid) |  | (read-only)
OrderService | getVisitReminder | response | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | getVisitReminder | response | enabled | boolean | yes
OrderService | getVisitReminder | response | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | getVisitReminder | response | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | getVisitReminder | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | getVisitReminder | param (path) | orderId | string (uuid) | yes
VenueOpsService | getWaitTimes | param (query) | venueId | string (uuid) | yes
VenueOpsService | getWaitTimes | param (query) | category | string (uuid) |  | A catalogue product category id (ProductCategory, catalogue contract).
VenueOpsService | getWaitingGuest | response | id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | getWaitingGuest | response | queueId | string (uuid) | yes
VenueOpsService | getWaitingGuest | response | queueName | LocalisedText
VenueOpsService | getWaitingGuest | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getWaitingGuest | response | partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | getWaitingGuest | response | partySize | integer | yes
VenueOpsService | getWaitingGuest | response | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | getWaitingGuest | response | positionInQueue | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | partiesAhead | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | isFastPass | boolean
VenueOpsService | getWaitingGuest | response | priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | getWaitingGuest | response | priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | getWaitingGuest | response | priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | getWaitingGuest | response | accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | getWaitingGuest | response | entitlementId | string |  | (nullable)
VenueOpsService | getWaitingGuest | response | calledAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | admittedCount | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | joinedAt | string (date-time) | yes
VenueOpsService | getWaitingGuest | response | syncedAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | param (path) | entryId | string (uuid) | yes
MarketingService | getWaiverStatus | response | isSatisfied | boolean
MarketingService | getWaiverStatus | response | missingFormIds | array of string (uuid)
MarketingService | getWaiverStatus | response | expiringWithinDays | integer |  | (nullable)
MarketingService | getWaiverStatus | param (path) | subjectId | string (uuid) | yes
MarketingService | getWaiverStatus | param (query) | productId | string (uuid)
WalletService | getWallet | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | getWallet | response | subjectId | string (uuid) | yes
WalletService | getWallet | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWallet | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | getWallet | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | getWallet | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWallet | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | getWallet | response | credits[].sourceRef | string |  | (nullable)
WalletService | getWallet | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | getWallet | response | bonusBalance | object |  | Promotional value.
WalletService | getWallet | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | status | enum (active, suspended, closed) | yes
WalletService | getWallet | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | getWallet | response | expiresAt | string (date-time) |  | (nullable)
WalletService | getWallet | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | getWallet | param (path) | subjectId | string (uuid) | yes
WalletService | getWallet | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
WalletService | getWalletAutoReloadSetting | response | walletId | string (uuid) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | subjectId | string (uuid) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | enabled | boolean | yes
WalletService | getWalletAutoReloadSetting | response | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletAutoReloadSetting | response | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletAutoReloadSetting | response | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletAutoReloadSetting | response | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletAutoReloadSetting | response | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletAutoReloadSetting | response | paymentTokenId | string (uuid) |  | (nullable)
WalletService | getWalletAutoReloadSetting | response | maximumPerDay | integer |  | (min 1; nullable)
WalletService | getWalletAutoReloadSetting | response | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | getWalletAutoReloadSetting | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | getWalletAutoReloadSetting | param (path) | walletId | string (uuid) | yes
WalletService | getWalletExitBalance | response | walletId | string (uuid) | yes
WalletService | getWalletExitBalance | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | pendingOfflineAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | pendingOfflineAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | pendingOfflineAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | pendingOfflineAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | amountDue | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | amountDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | amountDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | amountDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | refundable | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | refundable.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | refundable.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | refundable.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | nonRefundableCredit | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | nonRefundableCredit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | nonRefundableCredit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | nonRefundableCredit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | waiveAllowedUpTo | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | waiveAllowedUpTo.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | waiveAllowedUpTo.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | waiveAllowedUpTo.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | asAt | string (date-time)
WalletService | getWalletExitBalance | param (path) | walletId | string (uuid) | yes
MarketingService | getWishlist | response | subjectId | string (uuid) | yes
MarketingService | getWishlist | response | items | array of object | yes
MarketingService | getWishlist | response | items[].id | string (uuid) | yes
MarketingService | getWishlist | response | items[].variantId | string (uuid) | yes
MarketingService | getWishlist | response | items[].productName | string
MarketingService | getWishlist | response | items[].performanceId | string (uuid) |  | (nullable)
MarketingService | getWishlist | response | items[].performanceStartsAt | string (date-time) |  | (nullable)
MarketingService | getWishlist | response | items[].price | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | getWishlist | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | getWishlist | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | getWishlist | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | getWishlist | response | items[].imageAssetRef | string |  | (nullable)
MarketingService | getWishlist | response | items[].isAvailable | boolean | yes | False where the product has been withdrawn or the performance has passed.
MarketingService | getWishlist | response | items[].unavailableReason | string |  | (nullable)
MarketingService | getWishlist | response | items[].note | string |  | (nullable)
MarketingService | getWishlist | response | items[].addedAt | string (date-time) | yes
MarketingService | getWishlist | param (path) | subjectId | string (uuid) | yes
TenancyService | getWorkstationHealth | response | score | integer
TenancyService | getWorkstationHealth | response | status | enum (healthy, warning, degraded, offline)
TenancyService | getWorkstationHealth | response | contributors | array of object
TenancyService | getWorkstationHealth | response | contributors[].factor | enum (heartbeatAge, deviceOffline, deviceBattery, firmwareOutdated, syncBacklog, errorRate, profileDrift)
TenancyService | getWorkstationHealth | response | contributors[].detail | string
TenancyService | getWorkstationHealth | response | contributors[].weight | integer
TenancyService | getWorkstationHealth | param (path) | workstationId | string (uuid) | yes
IdentityService | grantDelegation | request | overSubjectId | string (uuid) | yes
IdentityService | grantDelegation | request | delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) | yes
IdentityService | grantDelegation | request | permission | string | yes
IdentityService | grantDelegation | request | overObjectRef | string |  | (nullable)
IdentityService | grantDelegation | request | quota | integer |  | (nullable)
IdentityService | grantDelegation | request | validTo | string (date-time) |  | (nullable)
IdentityService | grantDelegation | request | isRevocableBySubject | boolean |  | (default True)
IdentityService | grantDelegation | response | id | string (uuid) | yes
IdentityService | grantDelegation | response | principalId | string (uuid) |  | (nullable)
IdentityService | grantDelegation | response | roleId | string (uuid) |  | (nullable)
IdentityService | grantDelegation | response | permission | string | yes | From the permission enum.
IdentityService | grantDelegation | response | subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | grantDelegation | response | overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | grantDelegation | response | overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | grantDelegation | response | delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | grantDelegation | response | quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | grantDelegation | response | isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | grantDelegation | response | scopePath | string | yes
IdentityService | grantDelegation | response | effect | enum (ALLOW, DENY) | yes
IdentityService | grantDelegation | response | permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | grantDelegation | response | revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | grantDelegation | response | validFrom | string (date-time) |  | (nullable)
IdentityService | grantDelegation | response | validTo | string (date-time) |  | (nullable)
IdentityService | grantDelegation | response | createdByPrincipalId | string (uuid)
IdentityService | grantDelegation | response | createdAt | string (date-time)
IdentityService | grantDelegation | param (path) | subjectId | string (uuid) | yes
IdentityService | grantDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestLogout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestLogout | param (query) | allDevices | boolean
IdentityService | guestPasswordLogin | request | identifier | string | yes | The email address or E.164 mobile number the account was registered with. (max length 256)
IdentityService | guestPasswordLogin | request | password | string | yes | (min length 8; max length 256)
IdentityService | guestPasswordLogin | request | deviceId | string |  | Names the device; a new sign-in here ends the previous session on it.
IdentityService | guestPasswordLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestPasswordLogin | response | subjectId | string (uuid) | yes
IdentityService | guestPasswordLogin | response | displayName | string |  | (nullable)
IdentityService | guestPasswordLogin | response | tokens | TokenPair | yes
IdentityService | guestPasswordLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestPasswordLogin | response | tokens.refreshToken | string | yes
IdentityService | guestPasswordLogin | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | guestPasswordLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestPasswordLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestPasswordLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestPasswordLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestPasswordLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestPasswordLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestPasswordLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestPasswordLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestPasswordLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestPasswordLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestPasswordLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestSocialLogin | request | provider | enum (apple, google) | yes
IdentityService | guestSocialLogin | request | idToken | string | yes
IdentityService | guestSocialLogin | request | deviceId | string
IdentityService | guestSocialLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestSocialLogin | response | subjectId | string (uuid) | yes
IdentityService | guestSocialLogin | response | displayName | string |  | (nullable)
IdentityService | guestSocialLogin | response | tokens | TokenPair | yes
IdentityService | guestSocialLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestSocialLogin | response | tokens.refreshToken | string | yes
IdentityService | guestSocialLogin | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | guestSocialLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestSocialLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestSocialLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestSocialLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestSocialLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestSocialLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestSocialLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestSocialLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestSocialLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestSocialLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestSocialLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestSocialLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestUaePassLogin | request | code | string | yes
IdentityService | guestUaePassLogin | request | redirectUri | string | yes
IdentityService | guestUaePassLogin | request | state | string
IdentityService | guestUaePassLogin | request | deviceId | string
IdentityService | guestUaePassLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestUaePassLogin | response | subjectId | string (uuid) | yes
IdentityService | guestUaePassLogin | response | displayName | string |  | (nullable)
IdentityService | guestUaePassLogin | response | tokens | TokenPair | yes
IdentityService | guestUaePassLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestUaePassLogin | response | tokens.refreshToken | string | yes
IdentityService | guestUaePassLogin | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | guestUaePassLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestUaePassLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestUaePassLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestUaePassLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestUaePassLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestUaePassLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestUaePassLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestUaePassLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestUaePassLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestUaePassLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestUaePassLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | handoverToAgent | request | reason | enum (guestRequested, assistantRefused, assistantFailed, outOfScope, negativeSentiment, complexIntent, paymentIssue) | yes
MarketingService | handoverToAgent | request | summary | string |  | The assistant's own summary of what the guest wants, so the agent opens with context rather than reading a transcript while somebody waits.
MarketingService | handoverToAgent | request | preferredQueueId | string (uuid)
MarketingService | handoverToAgent | response | id | string (uuid) | yes
MarketingService | handoverToAgent | response | telephony | object |  | BL-083. (nullable)
MarketingService | handoverToAgent | response | telephony.providerCallId | string
MarketingService | handoverToAgent | response | telephony.direction | enum (inbound, outbound, transferred)
MarketingService | handoverToAgent | response | telephony.fromNumberMasked | string |  | Masked, and it is still personal data. (nullable)
MarketingService | handoverToAgent | response | telephony.recordingRef | string |  | Held by the provider, referenced here. (nullable)
MarketingService | handoverToAgent | response | telephony.agentState | enum (available, onCall, wrapUp, away, offline) |  | (nullable)
MarketingService | handoverToAgent | response | assistSessionId | string (uuid) |  | BL-094. (nullable)
MarketingService | handoverToAgent | response | channel | ConversationChannel: enum (webChat, inAppChat, whatsapp, sms, email, kiosk, voice) | yes
MarketingService | handoverToAgent | response | state | ConversationState: enum (withAssistant, queued, withAgent, waitingOnGuest, resolved, abandoned, timedOut) | yes | withAssistant and queued are different, and the second has a person waiting.
MarketingService | handoverToAgent | response | subjectId | string (uuid) |  | 22.8.3. (nullable)
MarketingService | handoverToAgent | response | venueId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | assignedPrincipalId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | queueId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | queuePosition | integer |  | Place among the unclaimed conversations in queueId, from the live agent queue (audit R149). (read-only; nullable)
MarketingService | handoverToAgent | response | estimatedWaitSeconds | integer |  | From the live agent queue — the conversations ahead divided across that queue's agents online now (audit R149). (read-only; nullable)
MarketingService | handoverToAgent | response | handoverReason | enum (guestRequested, assistantRefused, assistantFailed, outOfScope, negativeSentiment, complexIntent, paymentIssue) |  | (nullable)
MarketingService | handoverToAgent | response | handoverSummary | string |  | The assistant's own account of what the guest wants, so an agent opens with context rather than reading a transcript while somebody waits. (nullable)
MarketingService | handoverToAgent | response | sentiment | enum (positive, neutral, negative, escalating) |  | 22.8.16. (nullable)
MarketingService | handoverToAgent | response | intent | string |  | 22.8.13. (nullable)
MarketingService | handoverToAgent | response | locale | string
MarketingService | handoverToAgent | response | caseId | string (uuid) |  | 22.8.12. (nullable)
MarketingService | handoverToAgent | response | messages | array of ConversationMessage
MarketingService | handoverToAgent | response | messages[].id | string (uuid) | yes
MarketingService | handoverToAgent | response | messages[].sender | enum (guest, agent, assistant, system) | yes | Resolved, never declared.
MarketingService | handoverToAgent | response | messages[].senderPrincipalId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | messages[].body | string | yes
MarketingService | handoverToAgent | response | messages[].attachments | array of object
MarketingService | handoverToAgent | response | messages[].attachments[].assetId | string (uuid)
MarketingService | handoverToAgent | response | messages[].attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | handoverToAgent | response | messages[].aiInteractionId | string (uuid) |  | Where the assistant sent it. (nullable)
MarketingService | handoverToAgent | response | messages[].sentAt | string (date-time) | yes
MarketingService | handoverToAgent | response | messages[].readAt | string (date-time) |  | (nullable)
MarketingService | handoverToAgent | response | firstResponseSeconds | integer |  | (read-only; nullable)
MarketingService | handoverToAgent | response | startedAt | string (date-time)
MarketingService | handoverToAgent | response | closedAt | string (date-time) |  | (nullable)
MarketingService | handoverToAgent | response | outcome | enum (resolved, caseRaised, abandonedByGuest, timedOut, spam) |  | (nullable)
MarketingService | handoverToAgent | param (path) | conversationId | string (uuid) | yes
MarketingService | handoverToAgent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | holdCourse | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | holdCourse | request | course | integer | yes | (min 1)
FnbService | holdCourse | request | reason | enum (tableNotReady, guestRequest, kitchenBackedUp, awaitingPrevious, other) |  | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | holdCourse | request | note | string |  | Free text. (max length 500; nullable)
FnbService | holdCourse | response | id | string (uuid) | yes
FnbService | holdCourse | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | holdCourse | response | orderNumber | string
FnbService | holdCourse | response | outletId | string (uuid) | yes
FnbService | holdCourse | response | tableLabel | string |  | (nullable)
FnbService | holdCourse | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | holdCourse | response | coursing | object |  | BL-131. (nullable)
FnbService | holdCourse | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | holdCourse | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | holdCourse | response | priority | integer |  | Higher fires sooner.
FnbService | holdCourse | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | holdCourse | response | prioritiseReason | string |  | (nullable)
FnbService | holdCourse | response | lines | array of object | yes
FnbService | holdCourse | response | lines[].lineId | string (uuid) | yes
FnbService | holdCourse | response | lines[].name | string | yes
FnbService | holdCourse | response | lines[].quantity | integer | yes
FnbService | holdCourse | response | lines[].modifiers | array of string
FnbService | holdCourse | response | lines[].note | string |  | (nullable)
FnbService | holdCourse | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | holdCourse | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | holdCourse | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | holdCourse | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | holdCourse | response | lines[].course | integer |  | (nullable)
FnbService | holdCourse | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | holdCourse | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | holdCourse | response | createdAt | string (date-time) | yes
FnbService | holdCourse | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | holdCourse | response | elapsedSeconds | integer
FnbService | holdCourse | param (path) | ticketId | string (uuid) | yes
FnbService | holdCourse | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | holdOrder | request | label | string |  | How the cashier will find it again — a name, a description, a party size. (max length 60)
OrderService | holdOrder | request | holdUntil | string (date-time)
OrderService | holdOrder | request | recordedAt | string (date-time) | yes
OrderService | holdOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | holdOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | holdOrder | response | channel | object | yes | Where it came from.
OrderService | holdOrder | response | venueId | string (uuid) | yes
OrderService | holdOrder | response | scopePath | string | yes
OrderService | holdOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | holdOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | holdOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | holdOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | holdOrder | response | droppedPromotions[].name | string
OrderService | holdOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | holdOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | holdOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines | array of OrderLine | yes
OrderService | holdOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | holdOrder | response | lines[].variantId | string (uuid) | yes
OrderService | holdOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | holdOrder | response | lines[].performanceId | string (uuid)
OrderService | holdOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | holdOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | holdOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | holdOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | holdOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | holdOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | holdOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | holdOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | holdOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | holdOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | holdOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | holdOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].holderName | string |  | (nullable)
OrderService | holdOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | holdOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | holdOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | holdOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | holdOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | holdOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | holdOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | holdOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | holdOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | holdOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | holdOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | holdOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | holdOrder | response | payments | array of Payment
OrderService | holdOrder | response | payments[].id | string (uuid) | yes
OrderService | holdOrder | response | payments[].orderId | string (uuid) | yes
OrderService | holdOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | holdOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | holdOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | holdOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | holdOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | holdOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | holdOrder | response | payments[].providerName | string |  | (nullable)
OrderService | holdOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | holdOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | holdOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | holdOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | holdOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | holdOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | holdOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | holdOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | principalId | string (uuid)
OrderService | holdOrder | response | workstationId | string (uuid)
OrderService | holdOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | holdOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | holdOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | holdOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | holdOrder | response | createdAt | string (date-time) | yes
OrderService | holdOrder | response | recordedAt | string (date-time) | yes
OrderService | holdOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | holdOrder | param (path) | orderId | string (uuid) | yes
OrderService | holdOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | holdWalletFunds | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | holdWalletFunds | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | holdWalletFunds | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | holdWalletFunds | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | holdWalletFunds | request | orderId | string |  | (nullable)
WalletService | holdWalletFunds | request | paymentId | string |  | (nullable)
WalletService | holdWalletFunds | request | expiresInSeconds | integer |  | (min 30; max 3600; default 900)
WalletService | holdWalletFunds | response | walletHoldId | string (uuid) | yes
WalletService | holdWalletFunds | response | walletId | string (uuid) | yes
WalletService | holdWalletFunds | response | orderId | string (uuid) |  | (nullable)
WalletService | holdWalletFunds | response | paymentId | string (uuid) |  | (nullable)
WalletService | holdWalletFunds | response | walletHoldAmount | number | yes
WalletService | holdWalletFunds | response | currencyCode | string | yes | (max length 10)
WalletService | holdWalletFunds | response | walletHoldStatus | string | yes | (max length 20)
WalletService | holdWalletFunds | response | expiresAt | string (date-time) | yes
WalletService | holdWalletFunds | response | createdAt | string (date-time) | yes
WalletService | holdWalletFunds | response | capturedAt | string (date-time) |  | (nullable)
WalletService | holdWalletFunds | response | releasedAt | string (date-time) |  | (nullable)
WalletService | holdWalletFunds | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | holdWalletFunds | param (path) | walletId | string (uuid) | yes
MarketingService | identifyGuest | request | token | string | yes
MarketingService | identifyGuest | request | tokenKind | enum (qr, rfid, nfc, membershipCard, walletPass, phone, email, appDeviceId, …) |  | Optional. (nullable)
MarketingService | identifyGuest | response | subjectId | string (uuid) | yes
MarketingService | identifyGuest | response | displayName | string
MarketingService | identifyGuest | response | matchedOn | enum (qr, rfid, nfc, membershipCard, walletPass, phone, email, appDeviceId, …) | yes | Which identifier resolved.
MarketingService | identifyGuest | response | confidence | enum (exact, probable) |  | probable where the match was on a shared identifier.
MarketingService | identifyGuest | response | entitlements | array of object |  | Live entitlements, so a gate or a till does not make a second call.
MarketingService | identifyGuest | response | entitlements[].entitlementId | string (uuid)
MarketingService | identifyGuest | response | entitlements[].productName | string
MarketingService | identifyGuest | response | entitlements[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) |  | What the storage layer holds, and what a guest is shown.
MarketingService | identifyGuest | response | entitlements[].validTo | string (date)
MarketingService | identifyGuest | response | loyalty | LoyaltyPosition
MarketingService | identifyGuest | response | loyalty.leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | identifyGuest | response | loyalty.subjectId | string (uuid) | yes
MarketingService | identifyGuest | response | loyalty.programmeId | string (uuid) | yes
MarketingService | identifyGuest | response | loyalty.pointsBalance | integer | yes
MarketingService | identifyGuest | response | loyalty.lifetimePoints | integer
MarketingService | identifyGuest | response | loyalty.tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | identifyGuest | response | loyalty.tierCode | string | yes
MarketingService | identifyGuest | response | loyalty.tierName | string
MarketingService | identifyGuest | response | loyalty.pointsToNextTier | integer |  | (nullable)
MarketingService | identifyGuest | response | loyalty.nextExpiryPoints | integer |  | (nullable)
MarketingService | identifyGuest | response | loyalty.nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | identifyGuest | response | isBarred | boolean |  | BL-134.
MarketingService | identifyGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | importTransportNetwork | request | format | enum (csvBundle, gtfs) | yes | A zip of the four CSV files described on importTransportNetwork, or a GTFS static feed.
VenueOpsService | importTransportNetwork | request | sourceRef | string (uuid) | yes | The uploaded file, as the MediaAsset.id from assets.completeUpload.
VenueOpsService | importTransportNetwork | request | include | array of enum (stations, routes, timetables) |  | Which parts of the file to read.
VenueOpsService | importTransportNetwork | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | importTransportNetwork | response | venueId | string (uuid) | yes | (read-only)
VenueOpsService | importTransportNetwork | response | format | enum (csvBundle, gtfs) | yes
VenueOpsService | importTransportNetwork | response | sourceRef | string (uuid) | yes
VenueOpsService | importTransportNetwork | response | status | TransportNetworkImportStatus: enum (validating, previewReady, failed, applied, expired) | yes | validating → previewReady or failed; previewReady → applied, or expired after 7 days unapplied (proposed, client to correct).
VenueOpsService | importTransportNetwork | response | preview | object |  | What applying would write. (read-only; nullable)
VenueOpsService | importTransportNetwork | response | preview.stationsToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.stationsToUpdate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.routesToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.routesToUpdate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.stopsToWrite | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.timetablesToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | findings | array of TransportNetworkImportFinding |  | (max items 1000; read-only)
VenueOpsService | importTransportNetwork | response | findings[].code | enum (nothingFound, fileMissing, headerMismatch, stationCodeDuplicate, stationCoordinatesMissing, routeCodeDuplicate, routeStopUnknownStation, routeOffsetsNotIncreasing, …) | yes | stationCoordinatesMissing is a warning (the station is listed and left off the map); routeActiveStopsChanged is a warning (those stops are skipped); every other code is an error and blocks the apply.
VenueOpsService | importTransportNetwork | response | findings[].severity | enum (error, warning) | yes
VenueOpsService | importTransportNetwork | response | findings[].file | string |  | e.g. (nullable)
VenueOpsService | importTransportNetwork | response | findings[].row | integer |  | (min 1; nullable)
VenueOpsService | importTransportNetwork | response | findings[].reference | string |  | The station (nullable)
VenueOpsService | importTransportNetwork | response | findings[].message | string | yes | (max length 500)
VenueOpsService | importTransportNetwork | response | createdBy | string (uuid) |  | (read-only)
VenueOpsService | importTransportNetwork | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | importTransportNetwork | response | appliedBy | string (uuid) |  | (read-only; nullable)
VenueOpsService | importTransportNetwork | response | appliedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | importTransportNetwork | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | importVenueGeometry | request | format | enum (pdfPlan, svgPlan, dwgPlan, dxfPlan, rasterPlan) | yes
VenueOpsService | importVenueGeometry | request | sourceRef | string (uuid) | yes | The drawing, as the MediaAsset.id from assets.completeUpload.
VenueOpsService | importVenueGeometry | request | layerMapping | object |  | Each role takes a list.
VenueOpsService | importVenueGeometry | request | layerMapping.buildingLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.pathLayer | array of string |  | Optional, and the platform derives paths without it.
VenueOpsService | importVenueGeometry | request | layerMapping.zoneLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.labelLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.boundaryLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.exitLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.emergencyExitLayer | array of string |  | Separate from exitLayer, and drawings usually blur them.
VenueOpsService | importVenueGeometry | request | layerMapping.poiLayers | object |  | Where a drawing already marks toilets, first aid and the rest.
VenueOpsService | importVenueGeometry | request | layerMapping.resourceLayer | array of string |  | The bookable resources drawn on the plan — cabanas, loungers, tables (decided 29 September, rev 3 REV3-15).
VenueOpsService | importVenueGeometry | request | layerMapping.keepOutLayer | array of string |  | Water, planting, back-of-house, plant rooms.
VenueOpsService | importVenueGeometry | request | digitNormalisation | boolean |  | A١ and A1 are one section to a person and two to a computer, and the failure is silent — the seats simply do not join, and you get geometry with no seats or seats with no geometry. (default True)
VenueOpsService | importVenueGeometry | request | georeference | object |  | 19.2.56. (nullable)
VenueOpsService | importVenueGeometry | request | georeference.originLat | number
VenueOpsService | importVenueGeometry | request | georeference.originLng | number
VenueOpsService | importVenueGeometry | request | georeference.scaleMetresPerUnit | number
VenueOpsService | importVenueGeometry | request | georeference.rotationDegrees | number |  | (default 0)
VenueOpsService | importVenueGeometry | request | georeference.anchors | array of object |  | Two points far apart. (min items 2; max items 4)
VenueOpsService | importVenueGeometry | request | georeference.anchors[].label | string
VenueOpsService | importVenueGeometry | request | georeference.anchors[].planX | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].planY | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].lat | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].lng | number
VenueOpsService | importVenueGeometry | request | manifestRef | string (uuid) |  | The seating manifest, where this map has seats, as the MediaAsset.id from assets.completeUpload, uploaded the same way as sourceRef. (nullable)
VenueOpsService | importVenueGeometry | request | resourceManifestRef | string (uuid) |  | The resource manifest, where this map carries bookable resources (decided 29 September, rev 3 REV3-15), uploaded like manifestRef. (nullable)
VenueOpsService | importVenueGeometry | request | priceBands | array of object |  | What each price band sells as, so a placed resource can be bought: the band code the manifest uses and the catalogue.ProductVariant that prices it (Family 6, Medium 10, Large 15, XL 20 on the Coastal… (nullable)
VenueOpsService | importVenueGeometry | request | priceBands[].code | string | yes | (max length 40)
VenueOpsService | importVenueGeometry | request | priceBands[].name | string |  | (nullable)
VenueOpsService | importVenueGeometry | request | priceBands[].variantId | string (uuid) | yes
VenueOpsService | importVenueGeometry | request | createMissingResources | boolean |  | Where a manifest label has no resources.Resource with that code at this venue, create one through resources.createResource (kind, capacity and zone as attributes) instead of reporting resourceCodeUnm… (default False)
VenueOpsService | importVenueGeometry | response | id | string (uuid) | yes
VenueOpsService | importVenueGeometry | response | mapId | string (uuid)
VenueOpsService | importVenueGeometry | response | status | enum (parsing, previewReady, committed, failed) | yes
VenueOpsService | importVenueGeometry | response | outcome | enum (parsed, parsedWithFindings, nothingFound, noLayersMatched, unreadable) | yes
VenueOpsService | importVenueGeometry | response | shapesFound | integer
VenueOpsService | importVenueGeometry | response | layersFound | array of string |  | Every layer name in the source, decoded.
VenueOpsService | importVenueGeometry | response | unmappedLayers | array of string
VenueOpsService | importVenueGeometry | response | manifestRowsRead | integer |  | (nullable)
VenueOpsService | importVenueGeometry | response | resourcesFound | integer |  | Bookable resource shapes found on the resource layer (rev 3 REV3-15). (nullable)
VenueOpsService | importVenueGeometry | response | resourceRowsJoined | integer |  | Resource manifest rows that joined a shape and a resources.Resource. (nullable)
VenueOpsService | importVenueGeometry | response | manifestRowsJoined | integer |  | The number to check against your own count. (nullable)
VenueOpsService | importVenueGeometry | response | findings | array of object |  | Named against the spec, so a finding maps to a section of handoff/venue-map-input-spec.md rather than to a stack trace.
VenueOpsService | importVenueGeometry | response | findings[].code | enum (duplicateLayerName, geometryOnLayerZero, unmappedLayer, mixedLayerContent, sectionCodeMismatch, digitScriptMismatch, mergedCells, totalRowDetected, …) | yes | A closed set, and each one names a rule in the spec.
VenueOpsService | importVenueGeometry | response | findings[].severity | enum (error, warning, info) | yes | warning is the important level here.
VenueOpsService | importVenueGeometry | response | findings[].message | string | yes
VenueOpsService | importVenueGeometry | response | findings[].specSection | string |  | Which part of the spec covers it — §2 Layers, §4 Digits. (nullable)
VenueOpsService | importVenueGeometry | response | findings[].affected | array of string |  | The layers, sections or rows involved.
VenueOpsService | importVenueGeometry | param (path) | mapId | string (uuid) | yes
VenueOpsService | importVenueGeometry | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | importVenueHistory | request | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | importVenueHistory | request | assetId | string (uuid) | yes | The uploaded export, in the asset library.
AiService | importVenueHistory | request | sourceSystem | string |  | What produced the file, e.g. (nullable)
AiService | importVenueHistory | request | columnMapping | object | yes | Target field to source column, e.g.
AiService | importVenueHistory | request | dryRun | boolean |  | Validate and report without loading. (default False)
AiService | importVenueHistory | response | id | string (uuid) | yes | (read-only)
AiService | importVenueHistory | response | venueId | string (uuid) | yes
AiService | importVenueHistory | response | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | importVenueHistory | response | assetId | string (uuid)
AiService | importVenueHistory | response | sourceSystem | string |  | (nullable)
AiService | importVenueHistory | response | columnMapping | object
AiService | importVenueHistory | response | dryRun | boolean |  | (default False)
AiService | importVenueHistory | response | status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | importVenueHistory | response | periodFrom | string (date) |  | (read-only; nullable)
AiService | importVenueHistory | response | periodTo | string (date) |  | (read-only; nullable)
AiService | importVenueHistory | response | monthsCovered | integer |  | (read-only)
AiService | importVenueHistory | response | rowsRead | integer |  | (read-only)
AiService | importVenueHistory | response | rowsLoaded | integer |  | (read-only)
AiService | importVenueHistory | response | rowsRejected | integer |  | (read-only)
AiService | importVenueHistory | response | findings | array of object |  | (read-only)
AiService | importVenueHistory | response | findings[].row | integer
AiService | importVenueHistory | response | findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | importVenueHistory | response | findings[].detail | string
AiService | importVenueHistory | response | requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | importVenueHistory | response | createdAt | string (date-time) |  | (read-only)
AiService | importVenueHistory | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | importVenueHistory | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | importVenueHistory | param (path) | venueId | string (uuid) | yes
AiService | importVenueHistory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | ingestFxRates | request | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | request | pairs | array of string |  | AED/USD form.
LedgerService | ingestFxRates | request | effectiveFrom | string (date) |  | Defaults to the next business day in the region timezone. (nullable)
LedgerService | ingestFxRates | request | dryRun | boolean |  | Fetch and report without writing. (default False)
LedgerService | ingestFxRates | response | source | FxRateSource: enum (manual, uaeCentralBank, ecb, openExchangeRates, cardScheme, provider) |  | Where the rate came from, and which provider specifically.
LedgerService | ingestFxRates | response | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) |  | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | response | ratesWritten | integer
LedgerService | ingestFxRates | response | unchanged | integer
LedgerService | ingestFxRates | response | largestMove | string |  | The number a person reads. (pattern ^-?\d+(\.\d{1,6})?$; nullable)
LedgerService | ingestFxRates | response | rates | array of FxRate
LedgerService | ingestFxRates | response | rates[].id | string (uuid) |  | (read-only)
LedgerService | ingestFxRates | response | rates[].fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | ingestFxRates | response | rates[].toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | ingestFxRates | response | rates[].rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | ingestFxRates | response | rates[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | response | rates[].source | object |  | (read-only)
LedgerService | ingestFxRates | response | rates[].effectiveFrom | string (date-time) | yes
LedgerService | ingestFxRates | response | rates[].effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | ingestFxRates | response | rates[].setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | ingestFxRates | response | rates[].note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | ingestFxRates | response | rates[].providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | ingestFxRates | response | rates[].fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | ingestFxRates | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | ingestKnowledgeDocument | request | id | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | request | collectionId | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | request | title | string | yes
AiService | ingestKnowledgeDocument | request | sourceAssetId | string (uuid) | yes
AiService | ingestKnowledgeDocument | request | mimeType | string
AiService | ingestKnowledgeDocument | request | reingestDocumentId | string (uuid) |  | An indexed or failed document in this collection to process again from sourceAssetId. (nullable)
AiService | ingestKnowledgeDocument | request | supersedesDocumentId | string (uuid) |  | The indexed document in this collection that this one replaces. (nullable)
AiService | ingestKnowledgeDocument | request | status | enum (processing, indexed, failed, superseded) |  | (read-only)
AiService | ingestKnowledgeDocument | request | chunkCount | integer |  | (read-only)
AiService | ingestKnowledgeDocument | request | failureReason | string |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | request | indexedAt | string (date-time) |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | request | scopePath | string |  | Added 29 September (AI design 3.1): ai.knowledge_document had no policy, so neither did its chunks. (read-only)
AiService | ingestKnowledgeDocument | response | id | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | response | collectionId | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | response | title | string | yes
AiService | ingestKnowledgeDocument | response | sourceAssetId | string (uuid) | yes
AiService | ingestKnowledgeDocument | response | mimeType | string
AiService | ingestKnowledgeDocument | response | reingestDocumentId | string (uuid) |  | An indexed or failed document in this collection to process again from sourceAssetId. (nullable)
AiService | ingestKnowledgeDocument | response | supersedesDocumentId | string (uuid) |  | The indexed document in this collection that this one replaces. (nullable)
AiService | ingestKnowledgeDocument | response | status | enum (processing, indexed, failed, superseded) |  | (read-only)
AiService | ingestKnowledgeDocument | response | chunkCount | integer |  | (read-only)
AiService | ingestKnowledgeDocument | response | failureReason | string |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | response | indexedAt | string (date-time) |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | response | scopePath | string |  | Added 29 September (AI design 3.1): ai.knowledge_document had no policy, so neither did its chunks. (read-only)
AiService | ingestKnowledgeDocument | param (path) | collectionId | string (uuid) | yes
AiService | ingestKnowledgeDocument | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | inquirePaymentStatus | response | id | string (uuid) | yes
OrderService | inquirePaymentStatus | response | orderId | string (uuid) | yes
OrderService | inquirePaymentStatus | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | inquirePaymentStatus | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | inquirePaymentStatus | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | inquirePaymentStatus | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | inquirePaymentStatus | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | inquirePaymentStatus | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | inquirePaymentStatus | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | inquirePaymentStatus | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | inquirePaymentStatus | response | providerName | string |  | (nullable)
OrderService | inquirePaymentStatus | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | inquirePaymentStatus | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | inquirePaymentStatus | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | inquirePaymentStatus | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | inquirePaymentStatus | response | nextAction.kind | enum (redirect, terminal)
OrderService | inquirePaymentStatus | response | nextAction.url | string (uri) |  | (nullable)
OrderService | inquirePaymentStatus | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | response | recordedAt | string (date-time) | yes
OrderService | inquirePaymentStatus | response | syncedAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | param (path) | paymentId | string (uuid) | yes
OrderService | inquirePaymentStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | issueCreditMemo | request | kind | enum (full, partial) | yes
LedgerService | issueCreditMemo | request | reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | issueCreditMemo | request | refundId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | request | cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | request | lines | array of object |  | Required for partial.
LedgerService | issueCreditMemo | request | lines[].lineNumber | integer | yes | (min 1)
LedgerService | issueCreditMemo | request | lines[].quantity | number |  | (nullable)
LedgerService | issueCreditMemo | request | lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | request | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | request | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | request | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | request | note | string |  | (max length 500; nullable)
LedgerService | issueCreditMemo | response | id | string (uuid) | yes | (read-only)
LedgerService | issueCreditMemo | response | creditMemoNumber | string | yes | Server-assigned from the legal entity's credit memo series, in sequence without gaps. (read-only)
LedgerService | issueCreditMemo | response | taxInvoiceId | string (uuid) | yes
LedgerService | issueCreditMemo | response | taxInvoiceNumber | string |  | (read-only)
LedgerService | issueCreditMemo | response | kind | enum (full, partial) | yes
LedgerService | issueCreditMemo | response | reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | issueCreditMemo | response | refundId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | legalEntityId | string (uuid) | yes
LedgerService | issueCreditMemo | response | buyerSubjectId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | issuedAt | string (date-time) | yes
LedgerService | issueCreditMemo | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | note | string |  | (nullable)
LedgerService | issueCreditMemo | response | renditionAssetId | string (uuid) |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | issueCreditMemo | response | issuedByPrincipalId | string (uuid) |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | lines | array of FinCreditMemoLine | yes
LedgerService | issueCreditMemo | response | lines[].invoiceLineNumber | integer | yes | (min 1)
LedgerService | issueCreditMemo | response | lines[].description | string |  | (max length 500)
LedgerService | issueCreditMemo | response | lines[].quantity | number |  | (nullable)
LedgerService | issueCreditMemo | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | lines[].taxRate | number
LedgerService | issueCreditMemo | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | issueCreditMemo | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | scopePath | string |  | (read-only)
LedgerService | issueCreditMemo | param (path) | invoiceId | string (uuid) | yes
LedgerService | issueCreditMemo | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | issueGameCard | request | id | string (uuid) | yes | Client-generated UUIDv7 for this request, and the idempotency key: it must equal the Idempotency-Key header, and a mismatch is the shared 409 Conflict.
VenueOpsService | issueGameCard | request | kind | enum (physical, digital) | yes
VenueOpsService | issueGameCard | request | cardCode | string |  | Required for physical cards, which are pre-printed.
VenueOpsService | issueGameCard | request | venueId | string (uuid) | yes
VenueOpsService | issueGameCard | request | subjectId | string (uuid)
VenueOpsService | issueGameCard | request | initialCredits | integer |  | (min 0; default 0)
VenueOpsService | issueGameCard | request | validMonths | integer |  | (min 1)
VenueOpsService | issueGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | issueGameCard | response | kind | string
VenueOpsService | issueGameCard | response | venueId | string (uuid) | yes
VenueOpsService | issueGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | issueGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | issueGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | issueGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | issueGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | issueGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | issueGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | issueGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | issueGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | issueGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | issueGameCard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | issueTaxInvoice | request | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | issueTaxInvoice | request | orderIds | array of string (uuid) | yes | One order for simplified and full; one or more for consolidated. (min items 1)
LedgerService | issueTaxInvoice | request | recipient | FinTaxInvoiceRecipient |  | Who the invoice is addressed to.
LedgerService | issueTaxInvoice | request | recipient.name | string | yes | (max length 300)
LedgerService | issueTaxInvoice | request | recipient.address | string |  | (max length 1000; nullable)
LedgerService | issueTaxInvoice | request | recipient.countryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | issueTaxInvoice | request | recipient.taxRegistrationNumber | string |  | The recipient's TRN where they are VAT-registered. (max length 30; nullable)
LedgerService | issueTaxInvoice | request | recipient.customerAccountId | string (uuid) |  | The B2B credit account (payments B2bCreditAccount) where a company is invoiced. (nullable)
LedgerService | issueTaxInvoice | request | languages | array of string |  | Overrides the template's languages for this document, within those the template offers.
LedgerService | issueTaxInvoice | request | supersedesInvoiceId | string (uuid) |  | A simplified invoice this full invoice replaces for the same supply. (nullable)
LedgerService | issueTaxInvoice | request | deliverToEmail | string (email) |  | Sends the PDF on issue as well as returning it. (nullable)
LedgerService | issueTaxInvoice | response | id | string (uuid) | yes | (read-only)
LedgerService | issueTaxInvoice | response | invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | issueTaxInvoice | response | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | issueTaxInvoice | response | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | issueTaxInvoice | response | legalEntityId | string (uuid) | yes
LedgerService | issueTaxInvoice | response | templateId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | venueId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | orderIds | array of string (uuid)
LedgerService | issueTaxInvoice | response | supplierName | string
LedgerService | issueTaxInvoice | response | supplierAddress | string |  | (nullable)
LedgerService | issueTaxInvoice | response | supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | issueTaxInvoice | response | buyerName | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerAddress | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | issueTaxInvoice | response | buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | issueTaxInvoice | response | customerAccountId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | issuedAt | string (date-time) | yes
LedgerService | issueTaxInvoice | response | supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | issueTaxInvoice | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | languages | array of string
LedgerService | issueTaxInvoice | response | supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | issueTaxInvoice | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | issueTaxInvoice | response | issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | issueTaxInvoice | response | lines | array of FinTaxInvoiceLine | yes
LedgerService | issueTaxInvoice | response | lines[].lineNumber | integer | yes | (min 1)
LedgerService | issueTaxInvoice | response | lines[].orderId | string (uuid)
LedgerService | issueTaxInvoice | response | lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | lines[].description | string | yes | (max length 500)
LedgerService | issueTaxInvoice | response | lines[].quantity | number | yes
LedgerService | issueTaxInvoice | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | lines[].taxRate | number |  | (min 0; max 100)
LedgerService | issueTaxInvoice | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | issueTaxInvoice | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | issueTaxInvoice | response | taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | issueTaxInvoice | response | taxSummary[].taxRate | number
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | issueTaxInvoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | issueWalletPass | request | entitlementId | string (uuid) | yes
OrderService | issueWalletPass | request | platform | enum (apple, google) | yes
OrderService | issueWalletPass | response | id | string (uuid) | yes
OrderService | issueWalletPass | response | entitlementId | string (uuid) | yes
OrderService | issueWalletPass | response | platform | enum (apple, google) | yes
OrderService | issueWalletPass | response | serialNumber | string | yes
OrderService | issueWalletPass | response | authenticationToken | string (password) |  | Write-only.
OrderService | issueWalletPass | response | status | enum (issued, updated, voided, expired) | yes
OrderService | issueWalletPass | response | lastPushedAt | string (date-time) |  | (nullable)
OrderService | issueWalletPass | response | deviceRegistrations | integer |  | How many devices hold it.
OrderService | issueWalletPass | response | scopePath | string |  | The partition key (ADR-0005).
OrderService | issueWalletPass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | joinQueue | request | id | string (uuid) | yes
VenueOpsService | joinQueue | request | queueId | string (uuid) | yes
VenueOpsService | joinQueue | request | partySize | integer | yes | (min 1)
VenueOpsService | joinQueue | request | entitlementId | string |  | Fast Pass or priority entitlement. (nullable)
VenueOpsService | joinQueue | request | partyHeightsCm | array of integer |  | Where the queue has a height requirement.
VenueOpsService | joinQueue | request | accessibilityNeedDeclared | boolean |  | The party declares an accessibility need (5.6.7; decided 29 September, build pass). (default False)
VenueOpsService | joinQueue | request | promotionCode | string |  | A promotion code the guest holds, checked against the lane's QueueFastPass.promotionIds (5.6.34). (max length 64; nullable)
VenueOpsService | joinQueue | request | recordedAt | string (date-time) | yes
VenueOpsService | joinQueue | response | id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | joinQueue | response | queueId | string (uuid) | yes
VenueOpsService | joinQueue | response | queueName | LocalisedText
VenueOpsService | joinQueue | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | joinQueue | response | partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | joinQueue | response | partySize | integer | yes
VenueOpsService | joinQueue | response | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | joinQueue | response | positionInQueue | integer |  | (nullable)
VenueOpsService | joinQueue | response | partiesAhead | integer |  | (nullable)
VenueOpsService | joinQueue | response | estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | isFastPass | boolean
VenueOpsService | joinQueue | response | priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | joinQueue | response | priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | joinQueue | response | priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | joinQueue | response | accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | joinQueue | response | entitlementId | string |  | (nullable)
VenueOpsService | joinQueue | response | calledAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | admittedCount | integer |  | (nullable)
VenueOpsService | joinQueue | response | joinedAt | string (date-time) | yes
VenueOpsService | joinQueue | response | syncedAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | joinRestaurantWaitlist | request | id | string (uuid) | yes
FnbService | joinRestaurantWaitlist | request | outletId | string (uuid) | yes
FnbService | joinRestaurantWaitlist | request | subjectId | string (uuid) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | partySize | integer | yes
FnbService | joinRestaurantWaitlist | request | quotedWaitMinutes | integer |  | (nullable)
FnbService | joinRestaurantWaitlist | request | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | joinRestaurantWaitlist | request | notifiedAt | string (date-time) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | joinRestaurantWaitlist | request | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | joinRestaurantWaitlist | request | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | joinRestaurantWaitlist | response | id | string (uuid) | yes
FnbService | joinRestaurantWaitlist | response | outletId | string (uuid) | yes
FnbService | joinRestaurantWaitlist | response | subjectId | string (uuid) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | partySize | integer | yes
FnbService | joinRestaurantWaitlist | response | quotedWaitMinutes | integer |  | (nullable)
FnbService | joinRestaurantWaitlist | response | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | joinRestaurantWaitlist | response | notifiedAt | string (date-time) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | joinRestaurantWaitlist | response | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | joinRestaurantWaitlist | response | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | joinRestaurantWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | joinWaitlist | request | id | string (uuid) |  | (read-only)
CatalogueService | joinWaitlist | request | performanceId | string (uuid) | yes
CatalogueService | joinWaitlist | request | variantId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | request | subjectId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | request | contactPoint | string |  | Where the offer goes.
CatalogueService | joinWaitlist | request | partySize | integer | yes | (min 1)
CatalogueService | joinWaitlist | request | status | object |  | Set by the server. (read-only)
CatalogueService | joinWaitlist | request | position | integer |  | First in, first offered. (read-only)
CatalogueService | joinWaitlist | request | offeredAt | string (date-time) |  | (read-only; nullable)
CatalogueService | joinWaitlist | request | offerExpiresAt | string (date-time) |  | The offer moves on when this passes. (read-only; nullable)
CatalogueService | joinWaitlist | request | joinedAt | string (date-time) |  | (read-only)
CatalogueService | joinWaitlist | response | id | string (uuid) |  | (read-only)
CatalogueService | joinWaitlist | response | performanceId | string (uuid) | yes
CatalogueService | joinWaitlist | response | variantId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | response | contactPoint | string |  | Where the offer goes.
CatalogueService | joinWaitlist | response | partySize | integer | yes | (min 1)
CatalogueService | joinWaitlist | response | status | object |  | Set by the server. (read-only)
CatalogueService | joinWaitlist | response | position | integer |  | First in, first offered. (read-only)
CatalogueService | joinWaitlist | response | offeredAt | string (date-time) |  | (read-only; nullable)
CatalogueService | joinWaitlist | response | offerExpiresAt | string (date-time) |  | The offer moves on when this passes. (read-only; nullable)
CatalogueService | joinWaitlist | response | joinedAt | string (date-time) |  | (read-only)
CatalogueService | joinWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | launchCampaign | request | scheduledFor | string (date-time)
MarketingService | launchCampaign | request | confirmAudienceSize | integer |  | Guard against a segment that has grown unexpectedly.
MarketingService | launchCampaign | response | campaignId | string (uuid) | yes
MarketingService | launchCampaign | response | audienceSize | integer | yes
MarketingService | launchCampaign | response | queuedCount | integer | yes
MarketingService | launchCampaign | response | excluded | array of object | yes | Why each excluded guest was excluded, in aggregate.
MarketingService | launchCampaign | response | excluded[].reason | enum (noConsent, consentRequiresRenewal, suppressed, noAddress, frequencyCap, outsideSendWindow)
MarketingService | launchCampaign | response | excluded[].count | integer
MarketingService | launchCampaign | response | scheduledFor | string (date-time) |  | (nullable)
MarketingService | launchCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | launchCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | leaveQueue | param (path) | entryId | string (uuid) | yes
VenueOpsService | leaveQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | leaveRestaurantWaitlist | request | note | string |  | Why, where the guest or host gave a reason. (max length 300; nullable)
FnbService | leaveRestaurantWaitlist | response | id | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | response | outletId | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | response | subjectId | string (uuid) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | partySize | integer | yes
FnbService | leaveRestaurantWaitlist | response | quotedWaitMinutes | integer |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | leaveRestaurantWaitlist | response | notifiedAt | string (date-time) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | leaveRestaurantWaitlist | response | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | leaveRestaurantWaitlist | response | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | leaveRestaurantWaitlist | param (path) | entryId | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | leaveWaitlist | param (path) | entryId | string (uuid) | yes
CatalogueService | leaveWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | linkGuestCheckout | request | orderReference | string | yes
IdentityService | linkGuestCheckout | request | verificationCode | string |  | From the booking confirmation.
IdentityService | linkGuestCheckout | response | attachedOrderCount | integer |  | The named booking plus any other orders with the same verified contact detail.
IdentityService | linkGuestCheckout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | list86Events | response | items | array of EightySixEvent | yes
FnbService | list86Events | response | items[].id | string (uuid) | yes
FnbService | list86Events | response | items[].outletId | string (uuid)
FnbService | list86Events | response | items[].menuItemId | string (uuid) | yes
FnbService | list86Events | response | items[].offAt | string (date-time) | yes
FnbService | list86Events | response | items[].backAt | string (date-time) |  | (nullable)
FnbService | list86Events | response | items[].reason | enum (ranOut, qualityIssue, equipmentDown, supplierFailure, seasonal, other) |  | other always carries a note (audit R222).
FnbService | list86Events | response | items[].note | string |  | The note given with the 86. (max length 500; nullable)
FnbService | list86Events | response | items[].calledByPrincipalId | string (uuid)
FnbService | list86Events | response | items[].refusedOrderCount | integer |  | (default 0; read-only)
FnbService | list86Events | response | nextCursor | string
FnbService | list86Events | response | hasMore | boolean | yes
FnbService | list86Events | param (path) | outletId | string (uuid) | yes
FnbService | list86Events | param (query) | from | string (date) |  | First calendar day, in the Region's time zone, not UTC.
FnbService | list86Events | param (query) | pageSize | integer
FnbService | list86Events | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listActiveSessions | response | items | array of ActiveSession | yes
IdentityService | listActiveSessions | response | items[].status | object | yes | A registry that only holds live sessions cannot answer why one ended.
IdentityService | listActiveSessions | response | items[].sessionId | string | yes
IdentityService | listActiveSessions | response | items[].principalId | string (uuid) | yes
IdentityService | listActiveSessions | response | items[].principalName | string
IdentityService | listActiveSessions | response | items[].roleId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].roleName | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].workstationId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].workstationName | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].venueId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].ipAddress | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].deviceInfo | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].hasOpenShift | boolean |  | Revoking this session leaves cash unreconciled.
IdentityService | listActiveSessions | response | items[].mfaSatisfied | boolean
IdentityService | listActiveSessions | response | items[].startedAt | string (date-time) | yes
IdentityService | listActiveSessions | response | items[].lastSeenAt | string (date-time) | yes
IdentityService | listActiveSessions | response | nextCursor | string
IdentityService | listActiveSessions | response | hasMore | boolean | yes
IdentityService | listActiveSessions | param (query) | venueId | string (uuid) |  | Exact match on ActiveSession.venueId.
IdentityService | listActiveSessions | param (query) | principalId | string (uuid) |  | Exact match on ActiveSession.principalId.
IdentityService | listActiveSessions | param (query) | workstationId | string (uuid) |  | Exact match on ActiveSession.workstationId — who holds this till, which POS-000 Sign In asks before offering a force-logout, without paging through every session in the venue.
IdentityService | listActiveSessions | param (query) | pageSize | integer
IdentityService | listActiveSessions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiConversations | response | items | array of AiConversation | yes
AiService | listAiConversations | response | items[].id | string (uuid) | yes
AiService | listAiConversations | response | items[].principalId | string (uuid) | yes
AiService | listAiConversations | response | items[].scopePath | string
AiService | listAiConversations | response | items[].module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
AiService | listAiConversations | response | items[].locale | string
AiService | listAiConversations | response | items[].messageCount | integer
AiService | listAiConversations | response | items[].startedAt | string (date-time) | yes
AiService | listAiConversations | response | items[].lastMessageAt | string (date-time)
AiService | listAiConversations | response | nextCursor | string
AiService | listAiConversations | response | hasMore | boolean | yes
AiService | listAiConversations | param (query) | pageSize | integer
AiService | listAiConversations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listAlerts | param (query) | status | AlertStatus: enum (raised, acknowledged, resolved, expired) |  | Defaults to open alerts (decided 28 September, audit R158): with no status the list holds raised and acknowledged alerts, never resolved or expired ones.
ReportingService | listAlerts | param (query) | severity | AlertSeverity: enum (info, warning, critical)
ReportingService | listAlerts | param (query) | workstationId | string (uuid) |  | Only alerts raised for this workstation.
ReportingService | listAlerts | param (query) | shiftId | string (uuid) |  | Only alerts raised during this till shift.
ReportingService | listAlerts | param (query) | itemId | string (uuid) |  | Only alerts raised about this inventory item.
CatalogueService | listAlternativeCodes | param (path) | productId | string (uuid) | yes
WhiteLabelService | listAnalyticsProviders | response | items | array of StorefrontAnalyticsProvider | yes
WhiteLabelService | listAnalyticsProviders | response | items[].id | string (uuid) |  | (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].venueId | string (uuid) |  | (nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | listAnalyticsProviders | response | items[].providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].measurementId | string | yes | What the tag or SDK reports to (GA4 G-..., Tag Manager GTM-..., a pixel id). (max length 100)
WhiteLabelService | listAnalyticsProviders | response | items[].surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | listAnalyticsProviders | response | items[].consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | listAnalyticsProviders | response | items[].isEnabled | boolean | yes | (default True)
WhiteLabelService | listAnalyticsProviders | response | items[].reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listAnalyticsProviders | response | nextCursor | string
WhiteLabelService | listAnalyticsProviders | response | hasMore | boolean | yes
WhiteLabelService | listAnalyticsProviders | param (query) | venueId | string (uuid) |  | Staff, the rows of this venue only; guest, the venue being browsed, so its rows win over the tenant's
WhiteLabelService | listAnalyticsProviders | param (query) | pageSize | integer
WhiteLabelService | listAnalyticsProviders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listAppBuilds | response | items | array of AppBuild | yes
WhiteLabelService | listAppBuilds | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listAppBuilds | response | items[].platform | enum (ios, android) | yes
WhiteLabelService | listAppBuilds | response | items[].configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | listAppBuilds | response | items[].storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | listAppBuilds | response | items[].buildNumber | integer |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the build service's; from submitted on it is read from the store with the client's credential, or stays built when the client uploads by hand. (read-only)
WhiteLabelService | listAppBuilds | response | items[].failureReason | string |  | (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listAppBuilds | response | items[].submitToStore | boolean |  | (default False)
WhiteLabelService | listAppBuilds | response | items[].requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | listAppBuilds | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listAppBuilds | response | nextCursor | string
WhiteLabelService | listAppBuilds | response | hasMore | boolean | yes
WhiteLabelService | listAppBuilds | param (query) | platform | enum (ios, android)
WhiteLabelService | listAppBuilds | param (query) | pageSize | integer
WhiteLabelService | listAppBuilds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listBanners | response | items | array of Banner | yes
WhiteLabelService | listBanners | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listBanners | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listBanners | response | items[].subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listBanners | response | items[].imageAssetRef | string (uuid) | yes
WhiteLabelService | listBanners | response | items[].placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | listBanners | response | items[].linkTarget | LinkTarget
WhiteLabelService | listBanners | response | items[].linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | listBanners | response | items[].linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | listBanners | response | items[].linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | listBanners | response | items[].linkTarget.contentPageId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.productId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.eventId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.url | string
WhiteLabelService | listBanners | response | items[].startsAt | string (date-time) | yes
WhiteLabelService | listBanners | response | items[].endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | listBanners | response | items[].state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | listBanners | response | items[].sortOrder | integer
WhiteLabelService | listBanners | response | items[].isActive | boolean
WhiteLabelService | listBanners | response | nextCursor | string
WhiteLabelService | listBanners | response | hasMore | boolean | yes
WhiteLabelService | listBanners | param (query) | state | ScheduleState: enum (draft, scheduled, active, expired)
WhiteLabelService | listBanners | param (query) | pageSize | integer
WhiteLabelService | listBanners | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listBillingStatements | response | items | array of BillingStatement | yes
OrderService | listBillingStatements | response | items[].id | string (uuid) | yes
OrderService | listBillingStatements | response | items[].subjectId | string (uuid) |  | (read-only)
OrderService | listBillingStatements | response | items[].periodStart | string (date) | yes
OrderService | listBillingStatements | response | items[].periodEnd | string (date) | yes
OrderService | listBillingStatements | response | items[].lines | array of BillingStatementLine
OrderService | listBillingStatements | response | items[].lines[].occurredAt | string (date-time) | yes
OrderService | listBillingStatements | response | items[].lines[].kind | enum (charge, refund, failedAttempt, adjustment) | yes
OrderService | listBillingStatements | response | items[].lines[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].description | string
OrderService | listBillingStatements | response | items[].lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].taxRate | number |  | 2.14.23. (nullable)
OrderService | listBillingStatements | response | items[].lines[].taxInvoiceId | string (uuid) |  | The finance tax invoice issued for this charge, where one was (issueTaxInvoice); the guest downloads it with getTaxDocumentRendition. (nullable)
OrderService | listBillingStatements | response | items[].lines[].declineClass | string |  | Present on failedAttempt only, and it is what turns *"your payment failed"* into something a guest can act on: a soft decline means try again, a hard one means the card needs replacing. (nullable)
OrderService | listBillingStatements | response | items[].total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].pdfUrl | string (uri) |  | Set when getBillingStatement is called with format=pdf; a short-lived link. (read-only; nullable)
OrderService | listBillingStatements | response | items[].isTaxInvoice | boolean | yes | Always false, and stated rather than assumed. (default False; read-only)
OrderService | listBillingStatements | response | nextCursor | string
OrderService | listBillingStatements | response | hasMore | boolean | yes
OrderService | listBillingStatements | param (query) | from | string (date) |  | Only statements whose periodEnd is on or after this date.
OrderService | listBillingStatements | param (query) | to | string (date) |  | Only statements whose periodStart is on or before this date.
OrderService | listBillingStatements | param (query) | pageSize | integer
OrderService | listBillingStatements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listBookableVenueMaps | response | venueId | string (uuid) | yes
VenueOpsService | listBookableVenueMaps | response | maps | array of BookableVenueMapRef | yes | (max items 50)
VenueOpsService | listBookableVenueMaps | response | maps[].mapId | string (uuid) | yes
VenueOpsService | listBookableVenueMaps | response | maps[].name | string | yes
VenueOpsService | listBookableVenueMaps | response | maps[].kind | enum (park, floor, zone, parking) | yes
VenueOpsService | listBookableVenueMaps | response | maps[].floorLevel | integer |  | (nullable)
VenueOpsService | listBookableVenueMaps | response | maps[].publishedVersion | integer | yes | The VenueMap.publishedVersion a guest is served; send it to getVenueMap as version.
VenueOpsService | listBookableVenueMaps | response | maps[].placedResourceCount | integer | yes | Placed resources on the published version. (min 1)
VenueOpsService | listBookableVenueMaps | response | maps[].kinds | array of enum (cabana, lounger, table, pitch, other) |  | The kinds of spot on this map, e.g.
VenueOpsService | listBookableVenueMaps | param (query) | venueId | string (uuid) | yes | The venue whose bookable maps are wanted.
VenueOpsService | listBookableVenueMaps | param (query) | productId | string (uuid) |  | Only maps with a placed resource sold by this product's price-band variants.
VenueOpsService | listBookableVenueMaps | param (query) | kind | enum (cabana, lounger, table, pitch, other) |  | Only maps carrying at least one placed resource of this kind (PlacedResource.kind).
WhiteLabelService | listBookingFlowTypes | response | items | array of BookingFlowType | yes
WhiteLabelService | listBookingFlowTypes | response | items[].key | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | listBookingFlowTypes | response | items[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listBookingFlowTypes | response | items[].description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listBookingFlowTypes | response | items[].productKinds | array of string | yes | The catalogue ProductKind values this type books.
WhiteLabelService | listBookingFlowTypes | response | items[].steps | array of object | yes | In the type's default order.
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].requirement | enum (required, optional, conditional) | yes
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].condition | object |  | For conditional, when a guest meets the step. (nullable)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].defaultEnabled | boolean |  | (default True)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].defaultSortOrder | integer | yes | (min 0)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].settingsOwned | array of string |  | Names of BookingFlowSettings (venue-wide) or BookingFlowLevelSettings (this flow) fields shown beside the step.
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].stepSettings | array of object |  | The step's own settings, kept in BookingFlowStep.settings.
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints | array of object | yes | first and last pin a step; before puts stepKey somewhere ahead of otherStepKey.
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].kind | enum (first, last, before) | yes
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].otherStepKey | object |  | Required when kind is before. (nullable)
WhiteLabelService | listBookingFlowTypes | response | nextCursor | string
WhiteLabelService | listBookingFlowTypes | response | hasMore | boolean | yes
WhiteLabelService | listBookingFlowTypes | param (query) | productKind | string |  | Only the types that serve this catalogue product kind.
WhiteLabelService | listBookingFlowTypes | param (query) | pageSize | integer
WhiteLabelService | listBookingFlowTypes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listBookingFlows | response | items | array of BookingFlow | yes
WhiteLabelService | listBookingFlows | response | items[].id | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | listBookingFlows | response | items[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | listBookingFlows | response | items[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | listBookingFlows | response | items[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | listBookingFlows | response | items[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | listBookingFlows | response | items[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | listBookingFlows | response | items[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlows | response | items[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | listBookingFlows | response | items[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | listBookingFlows | response | items[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | listBookingFlows | response | items[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | listBookingFlows | response | items[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | listBookingFlows | response | items[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | listBookingFlows | response | items[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | listBookingFlows | response | items[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | listBookingFlows | response | items[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | listBookingFlows | response | items[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | listBookingFlows | response | items[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | listBookingFlows | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listBookingFlows | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listBookingFlows | response | nextCursor | string
WhiteLabelService | listBookingFlows | response | hasMore | boolean | yes
WhiteLabelService | listBookingFlows | param (path) | venueId | string (uuid) | yes
WhiteLabelService | listBookingFlows | param (query) | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …)
WhiteLabelService | listBookingFlows | param (query) | pageSize | integer
WhiteLabelService | listBookingFlows | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listCases | response | items | array of Case | yes
MarketingService | listCases | response | items[].id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | listCases | response | items[].caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | listCases | response | items[].subjectId | string (uuid) |  | (nullable)
MarketingService | listCases | response | items[].guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | listCases | response | items[].subject | string | yes | The case's one-line title, not a person.
MarketingService | listCases | response | items[].kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | listCases | response | items[].channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | listCases | response | items[].recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | listCases | response | items[].syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | listCases | response | items[].categoryId | string (uuid) |  | (nullable)
MarketingService | listCases | response | items[].queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | listCases | response | items[].membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | listCases | response | items[].status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | listCases | response | items[].priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | listCases | response | items[].assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | listCases | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listCases | response | items[].relatedOrderId | string |  | (nullable)
MarketingService | listCases | response | items[].slaDueAt | string (date-time) |  | (nullable)
MarketingService | listCases | response | items[].isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | listCases | response | items[].slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | listCases | response | items[].escalationCount | integer
MarketingService | listCases | response | items[].createdAt | string (date-time) | yes
MarketingService | listCases | response | items[].resolvedAt | string (date-time) |  | (nullable)
MarketingService | listCases | response | nextCursor | string
MarketingService | listCases | response | hasMore | boolean | yes
MarketingService | listCases | param (query) | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed)
MarketingService | listCases | param (query) | assignedToPrincipalId | string (uuid)
MarketingService | listCases | param (query) | breachedSla | boolean |  | Filters on Case.isSlaBreached, computed at query time the same way it is on read.
MarketingService | listCases | param (query) | priority | CasePriority: enum (low, normal, high, urgent)
MarketingService | listCases | param (query) | membershipId | string (uuid) |  | The cases about one membership, which is how the membership screens list a member's case notes (decided 29 September, coordinator decision DM4, writers pass).
MarketingService | listCases | param (query) | pageSize | integer
MarketingService | listCases | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listCashMovements | response | items | array of CashMovement | yes
OrderService | listCashMovements | response | items[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | listCashMovements | response | items[].kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | listCashMovements | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listCashMovements | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listCashMovements | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listCashMovements | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listCashMovements | response | items[].denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | listCashMovements | response | items[].denominations[].id | string (uuid)
OrderService | listCashMovements | response | items[].denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | listCashMovements | response | items[].denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | listCashMovements | response | items[].denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | listCashMovements | response | items[].denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | listCashMovements | response | items[].denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | listCashMovements | response | items[].denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | listCashMovements | response | items[].denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listCashMovements | response | items[].denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | listCashMovements | response | items[].denominations[].countedAt | string (date-time)
OrderService | listCashMovements | response | items[].denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | listCashMovements | response | items[].reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | listCashMovements | response | items[].reason | string |  | (max length 500)
OrderService | listCashMovements | response | items[].recordedAt | string (date-time) | yes
OrderService | listCashMovements | response | items[].shiftId | string (uuid) | yes
OrderService | listCashMovements | response | items[].depositBoxId | string (uuid) |  | The box the cash moved in or out of. (nullable)
OrderService | listCashMovements | response | items[].witnessPrincipalId | string (uuid) |  | The cashier who countersigned a withdrawal. (nullable)
OrderService | listCashMovements | response | items[].withdrawalReason | object |  | (nullable)
OrderService | listCashMovements | response | items[].authorisedByPrincipalId | string (uuid) | yes | The principal who authorised the movement, recorded for audit.
OrderService | listCashMovements | response | items[].sequence | integer | yes | Monotonic within the shift.
OrderService | listCashMovements | response | items[].syncedAt | string (date-time) |  | (nullable)
OrderService | listCashMovements | response | nextCursor | string
OrderService | listCashMovements | response | hasMore | boolean | yes
OrderService | listCashMovements | param (path) | shiftId | string (uuid) | yes
OrderService | listCashMovements | param (query) | pageSize | integer
OrderService | listCashMovements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listConfigVersions | response | items | array of ConfigVersion | yes
WhiteLabelService | listConfigVersions | response | items[].version | string | yes
WhiteLabelService | listConfigVersions | response | items[].publishedAt | string (date-time) | yes
WhiteLabelService | listConfigVersions | response | items[].publishedByPrincipalId | string (uuid) | yes
WhiteLabelService | listConfigVersions | response | items[].publishedByName | string
WhiteLabelService | listConfigVersions | response | items[].note | string | yes
WhiteLabelService | listConfigVersions | response | items[].isCurrent | boolean | yes
WhiteLabelService | listConfigVersions | response | items[].scheduledFor | string (date-time) |  | (nullable)
WhiteLabelService | listConfigVersions | response | items[].contentHash | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges | array of object |  | Changes in this version that will not reach guests until the next store release.
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].area | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].description | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].platforms | array of enum (ios, android, web)
WhiteLabelService | listConfigVersions | response | items[].snapshot | object |  | What this version contained. (read-only)
WhiteLabelService | listConfigVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listConfigVersions | response | nextCursor | string
WhiteLabelService | listConfigVersions | response | hasMore | boolean | yes
WhiteLabelService | listConfigVersions | param (query) | pageSize | integer
WhiteLabelService | listConfigVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentAnswers | response | items | array of BookingConsentRecord | yes
MarketingService | listConsentAnswers | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listConsentAnswers | response | items[].questionId | string (uuid) | yes
MarketingService | listConsentAnswers | response | items[].questionVersion | integer | yes | (min 1)
MarketingService | listConsentAnswers | response | items[].questionKind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | listConsentAnswers | response | items[].answer | enum (yes, no) | yes
MarketingService | listConsentAnswers | response | items[].scope | enum (perPerson, perBooking) | yes
MarketingService | listConsentAnswers | response | items[].blocksBooking | boolean |  | The answer is the question's blockingAnswer at that version. (read-only)
MarketingService | listConsentAnswers | response | items[].cartId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].cartLineId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].orderId | string (uuid) |  | Set by orders.checkoutCart when the cart becomes an order. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].orderLineId | string (uuid) |  | (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].personIndex | integer |  | (min 0; nullable)
MarketingService | listConsentAnswers | response | items[].personName | string |  | (max length 120; nullable)
MarketingService | listConsentAnswers | response | items[].personSubjectId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].answeredBySubjectId | string (uuid) |  | The guest who answered, from the session. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].answeredByPrincipalId | string (uuid) |  | The staff member who answered on the guest's behalf. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | listConsentAnswers | response | items[].answeredAt | string (date-time) | yes
MarketingService | listConsentAnswers | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | listConsentAnswers | response | nextCursor | string
MarketingService | listConsentAnswers | response | hasMore | boolean | yes
MarketingService | listConsentAnswers | param (query) | orderId | string (uuid)
MarketingService | listConsentAnswers | param (query) | subjectId | string (uuid)
MarketingService | listConsentAnswers | param (query) | questionId | string (uuid)
MarketingService | listConsentAnswers | param (query) | pageSize | integer
MarketingService | listConsentAnswers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentPurposes | response | items | array of ConsentPurposeConfig | yes
MarketingService | listConsentPurposes | response | items[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | listConsentPurposes | response | items[].displayName | string
MarketingService | listConsentPurposes | response | items[].description | string
MarketingService | listConsentPurposes | response | items[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | listConsentPurposes | response | items[].noticeVersion | string | yes | Current version of the notice.
MarketingService | listConsentPurposes | response | items[].isRequiredForService | boolean | yes | True for transactional.
MarketingService | listConsentPurposes | response | items[].expiresAfterMonths | integer |  | (nullable)
MarketingService | listConsentPurposes | response | nextCursor | string
MarketingService | listConsentPurposes | response | hasMore | boolean | yes
MarketingService | listConsentPurposes | param (query) | pageSize | integer
MarketingService | listConsentPurposes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentQuestions | response | items | array of ConsentQuestion | yes
MarketingService | listConsentQuestions | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listConsentQuestions | response | items[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | listConsentQuestions | response | items[].text | object | yes | The question as the guest reads it, per locale.
MarketingService | listConsentQuestions | response | items[].helpText | object |  | (nullable)
MarketingService | listConsentQuestions | response | items[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | listConsentQuestions | response | items[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | listConsentQuestions | response | items[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | listConsentQuestions | response | items[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | listConsentQuestions | response | items[].status | enum (active, retired) | yes | (default active)
MarketingService | listConsentQuestions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | listConsentQuestions | response | items[].updatedAt | string (date-time) |  | (read-only)
MarketingService | listConsentQuestions | response | nextCursor | string
MarketingService | listConsentQuestions | response | hasMore | boolean | yes
MarketingService | listConsentQuestions | param (query) | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom)
MarketingService | listConsentQuestions | param (query) | status | enum (active, retired)
MarketingService | listConsentQuestions | param (query) | pageSize | integer
MarketingService | listConsentQuestions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listContentPages | response | items | array of ContentPage | yes
WhiteLabelService | listContentPages | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listContentPages | response | items[].slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | listContentPages | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listContentPages | response | items[].body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | listContentPages | response | items[].isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | listContentPages | response | items[].status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | listContentPages | response | items[].iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | listContentPages | response | items[].categoryCode | string |  | (nullable)
WhiteLabelService | listContentPages | response | items[].sortOrder | integer
WhiteLabelService | listContentPages | response | items[].isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | listContentPages | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listContentPages | response | nextCursor | string
WhiteLabelService | listContentPages | response | hasMore | boolean | yes
WhiteLabelService | listContentPages | param (query) | status | ContentStatus: enum (draft, published, archived) |  | Staff only.
WhiteLabelService | listContentPages | param (query) | categoryCode | string |  | Only pages with this categoryCode.
WhiteLabelService | listContentPages | param (query) | slug | string |  | Only the page with this slug — how a screen fetches one known page.
WhiteLabelService | listContentPages | param (query) | pageSize | integer
WhiteLabelService | listContentPages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listCreditMemos | response | items | array of FinCreditMemo | yes
LedgerService | listCreditMemos | response | items[].id | string (uuid) | yes | (read-only)
LedgerService | listCreditMemos | response | items[].creditMemoNumber | string | yes | Server-assigned from the legal entity's credit memo series, in sequence without gaps. (read-only)
LedgerService | listCreditMemos | response | items[].taxInvoiceId | string (uuid) | yes
LedgerService | listCreditMemos | response | items[].taxInvoiceNumber | string |  | (read-only)
LedgerService | listCreditMemos | response | items[].kind | enum (full, partial) | yes
LedgerService | listCreditMemos | response | items[].reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | listCreditMemos | response | items[].refundId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].legalEntityId | string (uuid) | yes
LedgerService | listCreditMemos | response | items[].buyerSubjectId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].issuedAt | string (date-time) | yes
LedgerService | listCreditMemos | response | items[].currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].note | string |  | (nullable)
LedgerService | listCreditMemos | response | items[].renditionAssetId | string (uuid) |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | listCreditMemos | response | items[].issuedByPrincipalId | string (uuid) |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].lines | array of FinCreditMemoLine | yes
LedgerService | listCreditMemos | response | items[].lines[].invoiceLineNumber | integer | yes | (min 1)
LedgerService | listCreditMemos | response | items[].lines[].description | string |  | (max length 500)
LedgerService | listCreditMemos | response | items[].lines[].quantity | number |  | (nullable)
LedgerService | listCreditMemos | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].lines[].taxRate | number
LedgerService | listCreditMemos | response | items[].lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | listCreditMemos | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].scopePath | string |  | (read-only)
LedgerService | listCreditMemos | response | nextCursor | string
LedgerService | listCreditMemos | response | hasMore | boolean | yes
LedgerService | listCreditMemos | param (query) | taxInvoiceId | string (uuid)
LedgerService | listCreditMemos | param (query) | refundId | string (uuid)
LedgerService | listCreditMemos | param (query) | legalEntityId | string (uuid)
LedgerService | listCreditMemos | param (query) | issuedFrom | string (date)
LedgerService | listCreditMemos | param (query) | issuedTo | string (date)
LedgerService | listCreditMemos | param (query) | pageSize | integer
LedgerService | listCreditMemos | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listDelegations | response | items | object | yes
IdentityService | listDelegations | response | items.heldByThisGuest | array of DelegatedAccess
IdentityService | listDelegations | response | items.heldByThisGuest[].id | string (uuid) | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].principalId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].roleId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].permission | string | yes | From the permission enum.
IdentityService | listDelegations | response | items.heldByThisGuest[].subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | listDelegations | response | items.heldByThisGuest[].scopePath | string | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].effect | enum (ALLOW, DENY) | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].validFrom | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].validTo | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].createdByPrincipalId | string (uuid)
IdentityService | listDelegations | response | items.heldByThisGuest[].createdAt | string (date-time)
IdentityService | listDelegations | response | items.heldOverThisGuest | array of DelegatedAccess
IdentityService | listDelegations | response | items.heldOverThisGuest[].id | string (uuid) | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].principalId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].roleId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].permission | string | yes | From the permission enum.
IdentityService | listDelegations | response | items.heldOverThisGuest[].subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | listDelegations | response | items.heldOverThisGuest[].scopePath | string | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].effect | enum (ALLOW, DENY) | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].validFrom | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].validTo | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].createdByPrincipalId | string (uuid)
IdentityService | listDelegations | response | items.heldOverThisGuest[].createdAt | string (date-time)
IdentityService | listDelegations | response | nextCursor | string
IdentityService | listDelegations | response | hasMore | boolean | yes
IdentityService | listDelegations | param (path) | subjectId | string (uuid) | yes
IdentityService | listDelegations | param (query) | pageSize | integer
IdentityService | listDelegations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listDeliveryLocations | response | items | array of DeliveryLocation | yes
FnbService | listDeliveryLocations | response | items[].id | string (uuid) | yes
FnbService | listDeliveryLocations | response | items[].venueId | string (uuid) | yes
FnbService | listDeliveryLocations | response | items[].kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | listDeliveryLocations | response | items[].label | string | yes | What a runner is told.
FnbService | listDeliveryLocations | response | items[].zone | string |  | (nullable)
FnbService | listDeliveryLocations | response | items[].tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | listDeliveryLocations | response | items[].seatId | string |  | Set where the seat is the address. (nullable)
FnbService | listDeliveryLocations | response | items[].servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | listDeliveryLocations | response | items[].isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | listDeliveryLocations | response | items[].unserviceableReason | string |  | (nullable)
FnbService | listDeliveryLocations | response | items[].walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | listDeliveryLocations | response | nextCursor | string
FnbService | listDeliveryLocations | response | hasMore | boolean | yes
FnbService | listDeliveryLocations | param (path) | venueId | string (uuid) | yes
FnbService | listDeliveryLocations | param (query) | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …)
FnbService | listDeliveryLocations | param (query) | servingOutletId | string (uuid) |  | Only locations this outlet delivers to.
FnbService | listDeliveryLocations | param (query) | pageSize | integer
FnbService | listDeliveryLocations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listDenominations | param (query) | includeInactive | boolean
OrderService | listDepositBoxes | response | items | array of DepositBox | yes
OrderService | listDepositBoxes | response | items[].id | string (uuid) |  | (read-only)
OrderService | listDepositBoxes | response | items[].cashierPrincipalId | string (uuid) | yes
OrderService | listDepositBoxes | response | items[].cashierName | string |  | (read-only)
OrderService | listDepositBoxes | response | items[].venueId | string (uuid) | yes
OrderService | listDepositBoxes | response | items[].workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | listDepositBoxes | response | items[].shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | listDepositBoxes | response | items[].status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | listDepositBoxes | response | items[].openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].openingDenominations | array of object |  | 5.8.3.
OrderService | listDepositBoxes | response | items[].openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | listDepositBoxes | response | items[].openingDenominations[].count | integer | yes | (min 0)
OrderService | listDepositBoxes | response | items[].withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | listDepositBoxes | response | items[].expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | listDepositBoxes | response | items[].allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | listDepositBoxes | response | items[].closedAt | string (date-time) |  | (nullable)
OrderService | listDepositBoxes | response | nextCursor | string
OrderService | listDepositBoxes | response | hasMore | boolean | yes
OrderService | listDepositBoxes | param (query) | openOnly | boolean
OrderService | listDepositBoxes | param (query) | pageSize | integer
OrderService | listDepositBoxes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listDevices | response | items | array of RegisteredDevice | yes
TenancyService | listDevices | response | items[].id | string (uuid) | yes | (read-only)
TenancyService | listDevices | response | items[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | listDevices | response | items[].driver | string | yes | Built to an open standard where one exists — ESC/POS, UnifiedPOS, OSDP.
TenancyService | listDevices | response | items[].identifier | string |  | (nullable)
TenancyService | listDevices | response | items[].workstationId | string (uuid) |  | Required for every kind except mobileHandset, which is bound to no workstation (18.1.5, 29 September); registerDevice refuses either mistake with 422. (nullable)
TenancyService | listDevices | response | items[].model | string |  | (nullable)
TenancyService | listDevices | response | items[].pushToken | string (password) |  | BL-163. (nullable)
TenancyService | listDevices | response | items[].pushPlatform | enum (ios, android, web, windows) |  | (nullable)
TenancyService | listDevices | response | items[].pushFailureCount | integer |  | Consecutive failures. (default 0; read-only)
TenancyService | listDevices | response | items[].offlineScope | enum (none, readOnly, sellAndScan, fullVenue) |  | BL-163. (nullable)
TenancyService | listDevices | response | items[].firmwareVersion | string |  | As the device last reported it on its heartbeat. (read-only; nullable)
TenancyService | listDevices | response | items[].isRequired | boolean |  | True blocks shift open when the device is unreachable.
TenancyService | listDevices | response | items[].status | enum (online, offline, error, consumableLow, needsAttention, unknown) |  | What the device last said on its heartbeat; unknown until it has. (read-only)
TenancyService | listDevices | response | items[].batteryPercent | integer |  | Board 1 of the client's POS design set, 20 August. (min 0; max 100; read-only; nullable)
TenancyService | listDevices | response | items[].lastCheckedAt | string (date-time) |  | Distinct from lastHeartbeatAt. (read-only; nullable)
TenancyService | listDevices | response | items[].health | enum (healthy, warning, degraded, offline, unknown) |  | Derived, not reported. (default unknown; read-only)
TenancyService | listDevices | response | items[].lastHeartbeatAt | string (date-time) |  | (read-only; nullable)
TenancyService | listDevices | response | items[].capabilities | array of DeviceCapability: enum (genderClassification) |  | BL-179. (read-only)
TenancyService | listDevices | response | items[].enrolmentState | enum (registered, enrolled, provisioned, active, deactivated, retired) |  | BL-160. (default registered; read-only)
TenancyService | listDevices | response | items[].retiredAt | string (date-time) |  | Set when enrolmentState reaches retired, and null otherwise. (read-only; nullable)
TenancyService | listDevices | response | items[].configurationProfileId | string (uuid) |  | The profile this device was provisioned with. (read-only; nullable)
TenancyService | listDevices | response | nextCursor | string
TenancyService | listDevices | response | hasMore | boolean | yes
TenancyService | listDevices | param (query) | workstationId | string (uuid)
TenancyService | listDevices | param (query) | kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …)
TenancyService | listDevices | param (query) | pageSize | integer
TenancyService | listDevices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listDiningOutlets | response | items | array of DiningOutlet | yes
FnbService | listDiningOutlets | response | items[].outletId | string (uuid) | yes
FnbService | listDiningOutlets | response | items[].name | string | yes
FnbService | listDiningOutlets | response | items[].kind | string | yes
FnbService | listDiningOutlets | response | items[].zone | string |  | (nullable)
FnbService | listDiningOutlets | response | items[].cuisine | array of string
FnbService | listDiningOutlets | response | items[].isOpenNow | boolean | yes
FnbService | listDiningOutlets | response | items[].opensAt | string (date-time) |  | (nullable)
FnbService | listDiningOutlets | response | items[].closesAt | string (date-time) |  | (nullable)
FnbService | listDiningOutlets | response | items[].orderingMethod | GuestOrderingMethod: enum (tableService, appToTable, appToCollect, counterOnly, notAvailable) | yes | How a guest may order at this outlet.
FnbService | listDiningOutlets | response | items[].estimatedWaitMinutes | integer |  | From current kitchen ticket volume, not a fixed figure. (nullable)
FnbService | listDiningOutlets | response | items[].imageAssetRef | string |  | (nullable)
FnbService | listDiningOutlets | response | items[].menuId | string (uuid) |  | (nullable)
FnbService | listDiningOutlets | response | nextCursor | string
FnbService | listDiningOutlets | response | hasMore | boolean | yes
FnbService | listDiningOutlets | param (path) | venueId | string (uuid) | yes
FnbService | listDiningOutlets | param (query) | openNow | boolean
FnbService | listDiningOutlets | param (query) | orderingMethod | GuestOrderingMethod: enum (tableService, appToTable, appToCollect, counterOnly, notAvailable)
FnbService | listDiningOutlets | param (query) | pageSize | integer
FnbService | listDiningOutlets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listEntitlements | response | items | array of Entitlement | yes
AccessService | listEntitlements | response | items[].id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | listEntitlements | response | items[].templateId | string (uuid) | yes | The definition it was issued against.
AccessService | listEntitlements | response | items[].productId | string (uuid) | yes
AccessService | listEntitlements | response | items[].orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | listEntitlements | response | items[].orderLineId | string (uuid)
AccessService | listEntitlements | response | items[].subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | listEntitlements | response | items[].venueId | string (uuid)
AccessService | listEntitlements | response | items[].scopePath | string
AccessService | listEntitlements | response | items[].mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | listEntitlements | response | items[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | listEntitlements | response | items[].statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | listEntitlements | response | items[].validFrom | string (date-time) | yes
AccessService | listEntitlements | response | items[].validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | listEntitlements | response | items[].entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | listEntitlements | response | items[].entriesAllowed | integer |  | (nullable)
AccessService | listEntitlements | response | items[].lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | listEntitlements | response | items[].frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | listEntitlements | response | items[].suspendedReason | string |  | (nullable)
AccessService | listEntitlements | response | items[].freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | listEntitlements | response | items[].freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | listEntitlements | response | items[].isNameBound | boolean |  | (default False)
AccessService | listEntitlements | response | items[].holderName | string |  | (nullable)
AccessService | listEntitlements | response | items[].sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | listEntitlements | response | items[].issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | listEntitlements | response | items[].supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | listEntitlements | response | items[].walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | listEntitlements | response | items[].facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | listEntitlements | response | nextCursor | string
AccessService | listEntitlements | response | hasMore | boolean | yes
AccessService | listEntitlements | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | listEntitlements | param (query) | includeExpired | boolean
AccessService | listEntitlements | param (query) | pageSize | integer
AccessService | listEntitlements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listEvents | response | items | array of Event | yes
CatalogueService | listEvents | response | items[].id | string (uuid) | yes
CatalogueService | listEvents | response | items[].code | string | yes
CatalogueService | listEvents | response | items[].name | string | yes
CatalogueService | listEvents | response | items[].venueId | string (uuid) | yes
CatalogueService | listEvents | response | items[].scopePath | string | yes
CatalogueService | listEvents | response | items[].parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | listEvents | response | items[].performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | listEvents | response | items[].isActive | boolean
CatalogueService | listEvents | response | nextCursor | string
CatalogueService | listEvents | response | hasMore | boolean | yes
CatalogueService | listEvents | param (query) | pageSize | integer
CatalogueService | listEvents | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listFnbOrders | response | items | array of FnbOrder | yes
FnbService | listFnbOrders | response | items[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].orderNumber | string | yes
FnbService | listFnbOrders | response | items[].outletId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | listFnbOrders | response | items[].tableVisitId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | listFnbOrders | response | items[].lines | array of object | yes
FnbService | listFnbOrders | response | items[].lines[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].lines[].menuItemId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].lines[].quantity | integer | yes | (min 1)
FnbService | listFnbOrders | response | items[].lines[].modifierOptionIds | array of string (uuid)
FnbService | listFnbOrders | response | items[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | listFnbOrders | response | items[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | listFnbOrders | response | items[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | listFnbOrders | response | items[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | listFnbOrders | response | items[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | listFnbOrders | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | listFnbOrders | response | items[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | listFnbOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | listFnbOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | listFnbOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | listFnbOrders | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | listFnbOrders | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | listFnbOrders | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | listFnbOrders | response | items[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | listFnbOrders | response | items[].kitchenTickets[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | listFnbOrders | response | items[].kitchenTickets[].orderNumber | string
FnbService | listFnbOrders | response | items[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | listFnbOrders | response | items[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | listFnbOrders | response | items[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].lines | array of object | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].elapsedSeconds | integer
FnbService | listFnbOrders | response | items[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | items[].createdAt | string (date-time) | yes
FnbService | listFnbOrders | response | items[].recordedAt | string (date-time)
FnbService | listFnbOrders | response | items[].syncedAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | nextCursor | string
FnbService | listFnbOrders | response | hasMore | boolean | yes
FnbService | listFnbOrders | param (query) | outletId | string (uuid)
FnbService | listFnbOrders | param (query) | tableVisitId | string (uuid)
FnbService | listFnbOrders | param (query) | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …)
FnbService | listFnbOrders | param (query) | pageSize | integer
FnbService | listFnbOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listFulfilmentSlots | response | items | FulfilmentSlots | yes
FnbService | listFulfilmentSlots | response | items.slots | array of object
FnbService | listFulfilmentSlots | response | items.slots[].start | string (date-time)
FnbService | listFulfilmentSlots | response | items.slots[].end | string (date-time) |  | (nullable)
FnbService | listFulfilmentSlots | response | items.slots[].isAsap | boolean
FnbService | listFulfilmentSlots | response | nextCursor | string
FnbService | listFulfilmentSlots | response | hasMore | boolean | yes
FnbService | listFulfilmentSlots | param (path) | outletId | string (uuid) | yes
FnbService | listFulfilmentSlots | param (query) | mode | enum (collection, delivery) | yes
FnbService | listFulfilmentSlots | param (query) | date | string (date) |  | A calendar day, in the Region's time zone, not UTC.
FnbService | listFulfilmentSlots | param (query) | pageSize | integer
FnbService | listFulfilmentSlots | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listFxRates | response | items | array of FxRate | yes
LedgerService | listFxRates | response | items[].id | string (uuid) |  | (read-only)
LedgerService | listFxRates | response | items[].fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listFxRates | response | items[].toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listFxRates | response | items[].rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | listFxRates | response | items[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | listFxRates | response | items[].source | object |  | (read-only)
LedgerService | listFxRates | response | items[].effectiveFrom | string (date-time) | yes
LedgerService | listFxRates | response | items[].effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | listFxRates | response | items[].setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | listFxRates | response | items[].note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | listFxRates | response | items[].providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | listFxRates | response | items[].fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | listFxRates | response | nextCursor | string
LedgerService | listFxRates | response | hasMore | boolean | yes
LedgerService | listFxRates | param (query) | asAt | string (date-time) |  | Rates in force at this instant.
LedgerService | listFxRates | param (query) | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation)
LedgerService | listFxRates | param (query) | venueId | string (uuid) |  | Narrows the region's rates to the currencies this venue shows.
LedgerService | listFxRates | param (query) | pageSize | integer
LedgerService | listFxRates | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listGroupPackages | response | items | array of GroupPackageDefinition | yes
CatalogueService | listGroupPackages | response | items[].id | string (uuid) |  | (read-only)
CatalogueService | listGroupPackages | response | items[].productId | string |  | (read-only)
CatalogueService | listGroupPackages | response | items[].kind | enum (school, party) | yes
CatalogueService | listGroupPackages | response | items[].maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | listGroupPackages | response | items[].durationMinutes | integer | yes | (min 15)
CatalogueService | listGroupPackages | response | items[].hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | listGroupPackages | response | items[].pricingBasis | enum (perParticipant, perPackage)
CatalogueService | listGroupPackages | response | items[].freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | listGroupPackages | response | items[].paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | listGroupPackages | response | items[].includes | array of string
CatalogueService | listGroupPackages | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | listGroupPackages | response | nextCursor | string
CatalogueService | listGroupPackages | response | hasMore | boolean | yes
CatalogueService | listGroupPackages | param (query) | kind | enum (school, party)
CatalogueService | listGroupPackages | param (query) | pageSize | integer
CatalogueService | listGroupPackages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listGuestDevices | response | items | array of GuestDevice | yes
MarketingService | listGuestDevices | response | items[].id | string (uuid) | yes
MarketingService | listGuestDevices | response | items[].subjectId | string (uuid) | yes
MarketingService | listGuestDevices | response | items[].platform | enum (ios, android, web) | yes
MarketingService | listGuestDevices | response | items[].tokenFingerprint | string |  | Hash of the token, not the token.
MarketingService | listGuestDevices | response | items[].tokenRef | string |  | A vault reference to the push token, written by the server from registerGuestDevice.token — the same pattern as PaymentProvider.credentialRef.
MarketingService | listGuestDevices | response | items[].appVersion | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].osVersion | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].deviceModel | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].locale | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].status | enum (active, revoked, failed) | yes
MarketingService | listGuestDevices | response | items[].failureCount | integer |  | Consecutive delivery failures.
MarketingService | listGuestDevices | response | items[].registeredAt | string (date-time) | yes
MarketingService | listGuestDevices | response | items[].lastSeenAt | string (date-time) |  | (nullable)
MarketingService | listGuestDevices | response | items[].revokedAt | string (date-time) |  | (nullable)
MarketingService | listGuestDevices | response | nextCursor | string
MarketingService | listGuestDevices | response | hasMore | boolean | yes
MarketingService | listGuestDevices | param (path) | subjectId | string (uuid) | yes
MarketingService | listGuestDevices | param (query) | pageSize | integer
MarketingService | listGuestDevices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listGuestMemberships | response | items | array of GuestMembership | yes
CatalogueService | listGuestMemberships | response | items[].entitlementId | string (uuid) | yes | The access.Entitlement.id this membership is — a UUIDv7, like every entitlement id.
CatalogueService | listGuestMemberships | response | items[].productId | string (uuid) | yes
CatalogueService | listGuestMemberships | response | items[].name | string | yes
CatalogueService | listGuestMemberships | response | items[].tier | string |  | (nullable)
CatalogueService | listGuestMemberships | response | items[].status | enum (active, frozen, suspended, expired, cancelled) | yes | Derived from the entitlement, not held here.
CatalogueService | listGuestMemberships | response | items[].validFrom | string (date)
CatalogueService | listGuestMemberships | response | items[].validTo | string (date)
CatalogueService | listGuestMemberships | response | items[].frozenDays | integer |  | Days lost to a freeze and added back to validTo.
CatalogueService | listGuestMemberships | response | items[].benefits | array of object |  | 5.4.31.
CatalogueService | listGuestMemberships | response | items[].benefits[].code | string
CatalogueService | listGuestMemberships | response | items[].benefits[].name | string
CatalogueService | listGuestMemberships | response | items[].benefits[].value | string |  | (nullable)
CatalogueService | listGuestMemberships | response | items[].renewsOn | string (date) |  | (nullable)
CatalogueService | listGuestMemberships | response | items[].previousTerms | array of object |  | Prior terms, including lapsed ones.
CatalogueService | listGuestMemberships | response | items[].previousTerms[].validFrom | string (date)
CatalogueService | listGuestMemberships | response | items[].previousTerms[].validTo | string (date)
CatalogueService | listGuestMemberships | response | items[].previousTerms[].endedBecause | enum (expired, renewed, cancelled, upgraded)
CatalogueService | listGuestMemberships | response | nextCursor | string
CatalogueService | listGuestMemberships | response | hasMore | boolean | yes
CatalogueService | listGuestMemberships | param (query) | includeLapsed | boolean
CatalogueService | listGuestMemberships | param (query) | pageSize | integer
CatalogueService | listGuestMemberships | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listGuidedChoices | response | items | array of GuidedChoice | yes
WhiteLabelService | listGuidedChoices | response | items[].id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | listGuidedChoices | response | items[].mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | listGuidedChoices | response | items[].showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | listGuidedChoices | response | items[].behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | listGuidedChoices | response | items[].showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | listGuidedChoices | response | items[].questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | listGuidedChoices | response | items[].questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listGuidedChoices | response | items[].questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | listGuidedChoices | response | items[].questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | listGuidedChoices | response | items[].questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | listGuidedChoices | response | items[].status | object | yes | (read-only)
WhiteLabelService | listGuidedChoices | response | items[].source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | listGuidedChoices | response | items[].suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listGuidedChoices | response | nextCursor | string
WhiteLabelService | listGuidedChoices | response | hasMore | boolean | yes
WhiteLabelService | listGuidedChoices | param (path) | venueId | string (uuid) | yes
WhiteLabelService | listGuidedChoices | param (query) | status | GuidedChoiceStatus: enum (draft, published)
WhiteLabelService | listGuidedChoices | param (query) | source | enum (manual, aiSuggested)
WhiteLabelService | listGuidedChoices | param (query) | pageSize | integer
WhiteLabelService | listGuidedChoices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listInstalmentPlans | response | items | array of PayInstalmentPlan | yes
OrderService | listInstalmentPlans | response | items[].id | string (uuid) | yes
OrderService | listInstalmentPlans | response | items[].orderId | string (uuid) | yes
OrderService | listInstalmentPlans | response | items[].subjectId | string (uuid) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].frequency | enum (monthly, quarterly, custom) | yes
OrderService | listInstalmentPlans | response | items[].paymentTokenId | string (uuid)
OrderService | listInstalmentPlans | response | items[].status | enum (active, completed, inArrears, cancelled) | yes
OrderService | listInstalmentPlans | response | items[].total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listInstalmentPlans | response | items[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listInstalmentPlans | response | items[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listInstalmentPlans | response | items[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listInstalmentPlans | response | items[].paidToDate | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listInstalmentPlans | response | items[].paidToDate.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listInstalmentPlans | response | items[].paidToDate.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listInstalmentPlans | response | items[].paidToDate.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listInstalmentPlans | response | items[].nextDueDate | string (date) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].instalments | array of PayInstalment | yes
OrderService | listInstalmentPlans | response | items[].instalments[].sequence | integer | yes | (min 1)
OrderService | listInstalmentPlans | response | items[].instalments[].dueDate | string (date) | yes
OrderService | listInstalmentPlans | response | items[].instalments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listInstalmentPlans | response | items[].instalments[].status | enum (scheduled, paid, failed, waived, cancelled) | yes
OrderService | listInstalmentPlans | response | items[].instalments[].paymentId | string (uuid) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].instalments[].dunningCaseId | string (uuid) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].instalments[].attemptedAt | string (date-time) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].createdAt | string (date-time)
OrderService | listInstalmentPlans | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | listInstalmentPlans | response | nextCursor | string
OrderService | listInstalmentPlans | response | hasMore | boolean | yes
OrderService | listInstalmentPlans | param (query) | orderId | string (uuid)
OrderService | listInstalmentPlans | param (query) | status | enum (active, completed, inArrears, cancelled)
OrderService | listInstalmentPlans | param (query) | pageSize | integer
OrderService | listInstalmentPlans | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listInventoryHolds | response | items | array of InventoryHold | yes
CatalogueService | listInventoryHolds | response | items[].id | string | yes
CatalogueService | listInventoryHolds | response | items[].channelCapacityId | string (uuid) | yes
CatalogueService | listInventoryHolds | response | items[].holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | listInventoryHolds | response | items[].holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | listInventoryHolds | response | items[].holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | listInventoryHolds | response | items[].convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | listInventoryHolds | response | items[].convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | listInventoryHolds | response | items[].parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | listInventoryHolds | response | items[].requestedUnits | integer
CatalogueService | listInventoryHolds | response | items[].channel | object |  | Allocation this lease draws from.
CatalogueService | listInventoryHolds | response | items[].grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | listInventoryHolds | response | items[].consumedUnits | integer | yes
CatalogueService | listInventoryHolds | response | items[].status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | listInventoryHolds | response | items[].acquiredAt | string (date-time) | yes
CatalogueService | listInventoryHolds | response | items[].expiresAt | string (date-time) | yes
CatalogueService | listInventoryHolds | response | items[].releasedAt | string (date-time) |  | (nullable)
CatalogueService | listInventoryHolds | response | items[].forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | listInventoryHolds | response | items[].forceReleaseReason | string |  | (nullable)
CatalogueService | listInventoryHolds | response | nextCursor | string
CatalogueService | listInventoryHolds | response | hasMore | boolean | yes
CatalogueService | listInventoryHolds | param (query) | channelCapacityId | string (uuid)
CatalogueService | listInventoryHolds | param (query) | holderWorkstationId | string (uuid)
CatalogueService | listInventoryHolds | param (query) | status | LeaseStatus: enum (active, expired, released, forceReleased, converted)
CatalogueService | listInventoryHolds | param (query) | pageSize | integer
CatalogueService | listInventoryHolds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listKitchenStations | response | items | array of KitchenStation | yes
FnbService | listKitchenStations | response | items[].id | string (uuid) | yes
FnbService | listKitchenStations | response | items[].code | string | yes
FnbService | listKitchenStations | response | items[].name | string | yes
FnbService | listKitchenStations | response | items[].outletId | string (uuid)
FnbService | listKitchenStations | response | items[].menuItemIds | array of string (uuid) |  | Items routed to this station.
FnbService | listKitchenStations | response | items[].displayWorkstationIds | array of string (uuid) |  | The kitchen displays assigned to this station (decided 28 September, audit R277), as tenancy Workstation ids, primary first and fallbacks after it.
FnbService | listKitchenStations | response | items[].displayEndpoint | string |  | The P15 Kitchen Display device this station's tickets go to (19 Sep: the display is TICVAI software on commodity hardware, per station, with a fallback device where the primary is down — 18 Aug minut… (nullable)
FnbService | listKitchenStations | response | items[].isActive | boolean
FnbService | listKitchenStations | response | nextCursor | string
FnbService | listKitchenStations | response | hasMore | boolean | yes
FnbService | listKitchenStations | param (query) | outletId | string (uuid) |  | One outlet's stations.
FnbService | listKitchenStations | param (query) | pageSize | integer
FnbService | listKitchenStations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listKitchenTickets | response | items | array of KitchenTicket | yes
FnbService | listKitchenTickets | response | items[].id | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | listKitchenTickets | response | items[].orderNumber | string
FnbService | listKitchenTickets | response | items[].outletId | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].tableLabel | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | listKitchenTickets | response | items[].coursing | object |  | BL-131. (nullable)
FnbService | listKitchenTickets | response | items[].buzzerCode | string |  | BL-128. (nullable)
FnbService | listKitchenTickets | response | items[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listKitchenTickets | response | items[].priority | integer |  | Higher fires sooner.
FnbService | listKitchenTickets | response | items[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | listKitchenTickets | response | items[].prioritiseReason | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines | array of object | yes
FnbService | listKitchenTickets | response | items[].lines[].lineId | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].lines[].name | string | yes
FnbService | listKitchenTickets | response | items[].lines[].quantity | integer | yes
FnbService | listKitchenTickets | response | items[].lines[].modifiers | array of string
FnbService | listKitchenTickets | response | items[].lines[].note | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | listKitchenTickets | response | items[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].course | integer |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listKitchenTickets | response | items[].createdAt | string (date-time) | yes
FnbService | listKitchenTickets | response | items[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | listKitchenTickets | response | items[].elapsedSeconds | integer
FnbService | listKitchenTickets | response | nextCursor | string
FnbService | listKitchenTickets | response | hasMore | boolean | yes
FnbService | listKitchenTickets | param (query) | stationId | string (uuid) |  | Route to a preparation station — grill, cold, bar.
FnbService | listKitchenTickets | param (query) | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | listKitchenTickets | param (query) | course | integer |  | The course filter (decided 28 September, audit R277).
FnbService | listKitchenTickets | param (query) | pageSize | integer
FnbService | listKitchenTickets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listLoyaltyProgrammes | response | items | array of LoyaltyProgramme | yes
MarketingService | listLoyaltyProgrammes | response | items[].tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].id | string (uuid) |  | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].code | string | yes | (max length 40)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].name | string | yes | (max length 120)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].rank | integer | yes | Order, not threshold.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].isActive | boolean |  | (default True)
MarketingService | listLoyaltyProgrammes | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | listLoyaltyProgrammes | response | items[].name | string | yes
MarketingService | listLoyaltyProgrammes | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | listLoyaltyProgrammes | response | items[].earnRules | array of object | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].points | number | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].multiplier | number
MarketingService | listLoyaltyProgrammes | response | items[].pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].isActive | boolean
MarketingService | listLoyaltyProgrammes | response | nextCursor | string
MarketingService | listLoyaltyProgrammes | response | hasMore | boolean | yes
MarketingService | listLoyaltyProgrammes | param (query) | pageSize | integer
MarketingService | listLoyaltyProgrammes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listMenus | response | items | array of Menu | yes
FnbService | listMenus | response | items[].id | string (uuid) | yes
FnbService | listMenus | response | items[].code | string | yes | (max length 64)
FnbService | listMenus | response | items[].name | string | yes | (max length 200)
FnbService | listMenus | response | items[].outletId | string (uuid) | yes
FnbService | listMenus | response | items[].availability | MenuAvailability |  | When this menu is in force.
FnbService | listMenus | response | items[].availability.daysOfWeek | array of integer
FnbService | listMenus | response | items[].availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | listMenus | response | items[].availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | listMenus | response | items[].availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | listMenus | response | items[].availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | listMenus | response | items[].sections | array of MenuSection
FnbService | listMenus | response | items[].sections[].id | string (uuid) |  | (read-only)
FnbService | listMenus | response | items[].sections[].code | string | yes
FnbService | listMenus | response | items[].sections[].name | string | yes
FnbService | listMenus | response | items[].sections[].sortOrder | integer | yes
FnbService | listMenus | response | items[].sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | listMenus | response | items[].isActive | boolean | yes
FnbService | listMenus | response | items[].publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | listMenus | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | listMenus | response | nextCursor | string
FnbService | listMenus | response | hasMore | boolean | yes
FnbService | listMenus | param (query) | outletId | string (uuid)
FnbService | listMenus | param (query) | activeAt | string (date-time) |  | Return menus in force at this time — breakfast, lunch, happy hour.
FnbService | listMenus | param (query) | pageSize | integer
FnbService | listMenus | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | listMerchandise | response | items | array of MerchandiseItem or GuestMerchandiseItem | yes
RetailService | listMerchandise | response | nextCursor | string
RetailService | listMerchandise | response | hasMore | boolean | yes
RetailService | listMerchandise | param (query) | outletId | string (uuid) |  | Exact match.
RetailService | listMerchandise | param (query) | categoryId | string (uuid) |  | Exact match on categoryId.
RetailService | listMerchandise | param (query) | inStockOnly | boolean |  | True returns only items with onHand greater than zero at their own outlet.
RetailService | listMerchandise | param (query) | search | string |  | Case-insensitive "contains" match over name, sku, barcode and description.
RetailService | listMerchandise | param (query) | pageSize | integer
RetailService | listMerchandise | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listModifierGroups | response | items | array of ModifierGroup | yes
FnbService | listModifierGroups | response | items[].id | string (uuid) | yes
FnbService | listModifierGroups | response | items[].code | string | yes
FnbService | listModifierGroups | response | items[].name | string | yes
FnbService | listModifierGroups | response | items[].minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | listModifierGroups | response | items[].maxSelections | integer | yes | (min 1)
FnbService | listModifierGroups | response | items[].options | array of object | yes | (min items 1)
FnbService | listModifierGroups | response | items[].options[].id | string (uuid) | yes
FnbService | listModifierGroups | response | items[].options[].name | string | yes
FnbService | listModifierGroups | response | items[].options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listModifierGroups | response | items[].options[].isDefault | boolean
FnbService | listModifierGroups | response | items[].options[].isAvailable | boolean
FnbService | listModifierGroups | response | items[].options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | listModifierGroups | response | items[].scopePath | string |  | The partition key (ADR-0005).
FnbService | listModifierGroups | response | nextCursor | string
FnbService | listModifierGroups | response | hasMore | boolean | yes
FnbService | listModifierGroups | param (query) | pageSize | integer
FnbService | listModifierGroups | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyCases | response | items | array of Case | yes
MarketingService | listMyCases | response | items[].id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | listMyCases | response | items[].caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | listMyCases | response | items[].subjectId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | listMyCases | response | items[].subject | string | yes | The case's one-line title, not a person.
MarketingService | listMyCases | response | items[].kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | listMyCases | response | items[].channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | listMyCases | response | items[].recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | listMyCases | response | items[].syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | listMyCases | response | items[].categoryId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | listMyCases | response | items[].membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | listMyCases | response | items[].status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | listMyCases | response | items[].priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | listMyCases | response | items[].assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].relatedOrderId | string |  | (nullable)
MarketingService | listMyCases | response | items[].slaDueAt | string (date-time) |  | (nullable)
MarketingService | listMyCases | response | items[].isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | listMyCases | response | items[].slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | listMyCases | response | items[].escalationCount | integer
MarketingService | listMyCases | response | items[].createdAt | string (date-time) | yes
MarketingService | listMyCases | response | items[].resolvedAt | string (date-time) |  | (nullable)
MarketingService | listMyCases | response | nextCursor | string
MarketingService | listMyCases | response | hasMore | boolean | yes
MarketingService | listMyCases | param (query) | pageSize | integer
MarketingService | listMyCases | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listMyEntitlements | response | items | array of Entitlement | yes
AccessService | listMyEntitlements | response | items[].id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | listMyEntitlements | response | items[].templateId | string (uuid) | yes | The definition it was issued against.
AccessService | listMyEntitlements | response | items[].productId | string (uuid) | yes
AccessService | listMyEntitlements | response | items[].orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | listMyEntitlements | response | items[].orderLineId | string (uuid)
AccessService | listMyEntitlements | response | items[].subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | listMyEntitlements | response | items[].venueId | string (uuid)
AccessService | listMyEntitlements | response | items[].scopePath | string
AccessService | listMyEntitlements | response | items[].mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | listMyEntitlements | response | items[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | listMyEntitlements | response | items[].statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | listMyEntitlements | response | items[].validFrom | string (date-time) | yes
AccessService | listMyEntitlements | response | items[].validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | listMyEntitlements | response | items[].entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | listMyEntitlements | response | items[].entriesAllowed | integer |  | (nullable)
AccessService | listMyEntitlements | response | items[].lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | listMyEntitlements | response | items[].suspendedReason | string |  | (nullable)
AccessService | listMyEntitlements | response | items[].freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | listMyEntitlements | response | items[].freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | listMyEntitlements | response | items[].isNameBound | boolean |  | (default False)
AccessService | listMyEntitlements | response | items[].holderName | string |  | (nullable)
AccessService | listMyEntitlements | response | items[].sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | listMyEntitlements | response | items[].issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | listMyEntitlements | response | items[].supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | listMyEntitlements | response | items[].walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | listMyEntitlements | response | items[].facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | listMyEntitlements | response | nextCursor | string
AccessService | listMyEntitlements | response | hasMore | boolean | yes
AccessService | listMyEntitlements | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | listMyEntitlements | param (query) | state | enum (usableNow, upcoming, expired, all)
AccessService | listMyEntitlements | param (query) | includeShared | boolean |  | Entitlements shared with this guest by somebody else (shareEntitlement).
AccessService | listMyEntitlements | param (query) | pageSize | integer
AccessService | listMyEntitlements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listMyFavouriteRoutes | response | items | array of FavouriteRoute | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].venueId | string (uuid) | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].fromStationName | string |  | (read-only)
VenueOpsService | listMyFavouriteRoutes | response | items[].toStationName | string |  | (read-only)
VenueOpsService | listMyFavouriteRoutes | response | items[].label | string |  | (nullable)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listMyFavouriteRoutes | response | items[].createdAt | string (date-time) | yes
VenueOpsService | listMyFavouriteRoutes | response | nextCursor | string
VenueOpsService | listMyFavouriteRoutes | response | hasMore | boolean | yes
VenueOpsService | listMyFavouriteRoutes | param (query) | venueId | string (uuid) | yes
VenueOpsService | listMyFavouriteRoutes | param (query) | pageSize | integer
VenueOpsService | listMyFavouriteRoutes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyNotifications | response | items | array of GuestNotification | yes
MarketingService | listMyNotifications | response | items[].id | string | yes
MarketingService | listMyNotifications | response | items[].kind | enum (queueCall, orderReady, bookingChange, venueAlert, offer, other)
MarketingService | listMyNotifications | response | items[].title | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | listMyNotifications | response | items[].body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | listMyNotifications | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listMyNotifications | response | items[].deepLink | string |  | Where tapping the notification leads in the app (an order, a queue ticket, a booking). (nullable)
MarketingService | listMyNotifications | response | items[].queuedAt | string (date-time) | yes
MarketingService | listMyNotifications | response | items[].read | boolean | yes
MarketingService | listMyNotifications | response | nextCursor | string
MarketingService | listMyNotifications | response | hasMore | boolean | yes
MarketingService | listMyNotifications | response | unreadCount | integer |  | (min 0)
MarketingService | listMyNotifications | param (query) | pageSize | integer
MarketingService | listMyNotifications | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyNotifications | param (query) | unreadOnly | boolean
MarketingService | listMyNotifications | param (query) | venueId | string (uuid) |  | Only notifications from this venue.
OrderService | listMyOrders | response | items | array of Order | yes
OrderService | listMyOrders | response | items[].id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | listMyOrders | response | items[].orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | listMyOrders | response | items[].channel | object | yes | Where it came from.
OrderService | listMyOrders | response | items[].venueId | string (uuid) | yes
OrderService | listMyOrders | response | items[].scopePath | string | yes
OrderService | listMyOrders | response | items[].status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | listMyOrders | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | listMyOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | listMyOrders | response | items[].droppedPromotions[].promotionId | string (uuid) | yes
OrderService | listMyOrders | response | items[].droppedPromotions[].name | string
OrderService | listMyOrders | response | items[].droppedPromotions[].reason | enum (budgetCapReached)
OrderService | listMyOrders | response | items[].totalPriceVariance | object |  | Sum across lines.
OrderService | listMyOrders | response | items[].totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].lines | array of OrderLine | yes
OrderService | listMyOrders | response | items[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | listMyOrders | response | items[].lines[].variantId | string (uuid) | yes
OrderService | listMyOrders | response | items[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | listMyOrders | response | items[].lines[].performanceId | string (uuid)
OrderService | listMyOrders | response | items[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | listMyOrders | response | items[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | listMyOrders | response | items[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | listMyOrders | response | items[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | listMyOrders | response | items[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | listMyOrders | response | items[].lines[].quantity | integer | yes | (min 1)
OrderService | listMyOrders | response | items[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | listMyOrders | response | items[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | listMyOrders | response | items[].lines[].holderName | string |  | (nullable)
OrderService | listMyOrders | response | items[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | listMyOrders | response | items[].lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | listMyOrders | response | items[].lines[].priceVariance | object |  | Server minus quoted.
OrderService | listMyOrders | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | listMyOrders | response | items[].lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | listMyOrders | response | items[].lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | listMyOrders | response | items[].lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | listMyOrders | response | items[].lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | listMyOrders | response | items[].payments | array of Payment
OrderService | listMyOrders | response | items[].payments[].id | string (uuid) | yes
OrderService | listMyOrders | response | items[].payments[].orderId | string (uuid) | yes
OrderService | listMyOrders | response | items[].payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | listMyOrders | response | items[].payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | listMyOrders | response | items[].payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | listMyOrders | response | items[].payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | listMyOrders | response | items[].payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | listMyOrders | response | items[].payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | listMyOrders | response | items[].payments[].providerName | string |  | (nullable)
OrderService | listMyOrders | response | items[].payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | listMyOrders | response | items[].payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | listMyOrders | response | items[].payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | listMyOrders | response | items[].payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | items[].payments[].recordedAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | items[].principalId | string (uuid)
OrderService | listMyOrders | response | items[].workstationId | string (uuid)
OrderService | listMyOrders | response | items[].shiftId | string (uuid) |  | (nullable)
OrderService | listMyOrders | response | items[].subjectId | string (uuid) |  | (nullable)
OrderService | listMyOrders | response | items[].holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | listMyOrders | response | items[].heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | listMyOrders | response | items[].createdAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].recordedAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].syncedAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | nextCursor | string
OrderService | listMyOrders | response | hasMore | boolean | yes
OrderService | listMyOrders | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
OrderService | listMyOrders | param (query) | since | string (date) |  | Only orders whose createdAt falls on or after this date.
OrderService | listMyOrders | param (query) | pageSize | integer
OrderService | listMyOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listMyPaymentIssues | response | items | array of DunningCase | yes
OrderService | listMyPaymentIssues | response | items[].id | string (uuid) | yes
OrderService | listMyPaymentIssues | response | items[].subjectId | string (uuid)
OrderService | listMyPaymentIssues | response | items[].orderId | string |  | The order whose renewal failed.
OrderService | listMyPaymentIssues | response | items[].amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyPaymentIssues | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyPaymentIssues | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyPaymentIssues | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyPaymentIssues | response | items[].state | DunningState: enum (scheduled, inProgress, exhausted, recovered, resolvedManually) | yes | BL-100.
OrderService | listMyPaymentIssues | response | items[].declineClass | object |  | From the most recent attempt.
OrderService | listMyPaymentIssues | response | items[].attemptsMade | integer | yes
OrderService | listMyPaymentIssues | response | items[].nextAttemptAt | string (date-time) |  | Null where the case has ended or the decline is hard. (nullable)
OrderService | listMyPaymentIssues | response | items[].firstFailedAt | string (date-time) | yes
OrderService | listMyPaymentIssues | response | items[].resolvedAt | string (date-time) |  | (nullable)
OrderService | listMyPaymentIssues | response | items[].resolution | enum (paidByOtherMeans, cardReplaced, writeOff, cancelledByGuest, None) |  | (nullable)
OrderService | listMyPaymentIssues | response | items[].resolutionNote | string |  | What resolveDunningCase was told, which had nowhere to land until now. (max length 500; nullable)
OrderService | listMyPaymentIssues | response | items[].resolvedByPrincipalId | string (uuid) |  | Who closed it. (read-only; nullable)
OrderService | listMyPaymentIssues | response | items[].scopePath | string |  | The partition key (ADR-0005).
OrderService | listMyPaymentIssues | response | nextCursor | string
OrderService | listMyPaymentIssues | response | hasMore | boolean | yes
OrderService | listMyPaymentIssues | param (query) | pageSize | integer
OrderService | listMyPaymentIssues | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOrderRefunds | response | items | array of Refund | yes
OrderService | listOrderRefunds | response | items[].id | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].orderId | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | listOrderRefunds | response | items[].fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | listOrderRefunds | response | items[].taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | listOrderRefunds | response | items[].settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | listOrderRefunds | response | items[].fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | listOrderRefunds | response | items[].fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrderRefunds | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | listOrderRefunds | response | items[].status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | listOrderRefunds | response | items[].reason | string
OrderService | listOrderRefunds | response | items[].requestedByPrincipalId | string (uuid)
OrderService | listOrderRefunds | response | items[].secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | listOrderRefunds | response | items[].approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | listOrderRefunds | response | items[].ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | listOrderRefunds | response | items[].gatewayReference | string |  | (nullable)
OrderService | listOrderRefunds | response | items[].createdAt | string (date-time) | yes
OrderService | listOrderRefunds | response | items[].completedAt | string (date-time) |  | (nullable)
OrderService | listOrderRefunds | response | nextCursor | string
OrderService | listOrderRefunds | response | hasMore | boolean | yes
OrderService | listOrderRefunds | param (path) | orderId | string (uuid) | yes
OrderService | listOrderRefunds | param (query) | pageSize | integer
OrderService | listOrderRefunds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOrders | response | items | array of OrderSummary | yes
OrderService | listOrders | response | items[].id | string (uuid) | yes
OrderService | listOrders | response | items[].orderNumber | string | yes
OrderService | listOrders | response | items[].status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | listOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrders | response | items[].refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listOrders | response | items[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrders | response | items[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrders | response | items[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrders | response | items[].channel | object |  | The same vocabulary as Order.channel, which this projects.
OrderService | listOrders | response | items[].lineCount | integer
OrderService | listOrders | response | items[].principalId | string (uuid) |  | The cashier who raised it — what the held-orders list shows.
OrderService | listOrders | response | items[].holdLabel | string |  | As Order.holdLabel. (nullable)
OrderService | listOrders | response | items[].heldUntil | string (date-time) |  | As Order.heldUntil, so a held-orders list can warn about the ones about to lapse. (nullable)
OrderService | listOrders | response | items[].createdAt | string (date-time) | yes
OrderService | listOrders | response | nextCursor | string
OrderService | listOrders | response | hasMore | boolean | yes
OrderService | listOrders | param (query) | venueId | string (uuid) |  | Exact match.
OrderService | listOrders | param (query) | principalId | string (uuid) |  | The cashier who raised the order.
OrderService | listOrders | param (query) | shiftId | string (uuid) |  | Exact match on the shift the order was taken in.
OrderService | listOrders | param (query) | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …)
OrderService | listOrders | param (query) | createdFrom | string (date-time) |  | Only orders whose createdAt is at or after this instant.
OrderService | listOrders | param (query) | createdTo | string (date-time) |  | Only orders whose createdAt is before this instant.
OrderService | listOrders | param (query) | pageSize | integer
OrderService | listOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listOrgUnits | response | items | array of OrgUnit | yes
TenancyService | listOrgUnits | response | items[].id | string (uuid) | yes
TenancyService | listOrgUnits | response | items[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | listOrgUnits | response | items[].parentId | string (uuid) |  | (nullable)
TenancyService | listOrgUnits | response | items[].path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | listOrgUnits | response | items[].code | string | yes | (max length 64)
TenancyService | listOrgUnits | response | items[].name | string | yes | (max length 200)
TenancyService | listOrgUnits | response | items[].isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | listOrgUnits | response | items[].childCount | integer |  | (min 0)
TenancyService | listOrgUnits | response | nextCursor | string
TenancyService | listOrgUnits | response | hasMore | boolean | yes
TenancyService | listOrgUnits | param (query) | under | string |  | Return descendants of this path only.
TenancyService | listOrgUnits | param (query) | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet)
TenancyService | listOrgUnits | param (query) | includeInactive | boolean
TenancyService | listOrgUnits | param (query) | pageSize | integer
TenancyService | listOrgUnits | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listOutlets | param (query) | venueId | string (uuid)
TenancyService | listOutlets | param (query) | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile)
AccessService | listParkingFacilities | response | items | array of ParkingFacility | yes
AccessService | listParkingFacilities | response | items[].id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | listParkingFacilities | response | items[].name | string | yes
AccessService | listParkingFacilities | response | items[].venueId | string (uuid) | yes
AccessService | listParkingFacilities | response | items[].mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | listParkingFacilities | response | items[].capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | listParkingFacilities | response | items[].takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | listParkingFacilities | response | items[].vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | listParkingFacilities | response | items[].vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | listParkingFacilities | response | items[].pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | listParkingFacilities | response | items[].isActive | boolean
AccessService | listParkingFacilities | response | nextCursor | string
AccessService | listParkingFacilities | response | hasMore | boolean | yes
AccessService | listParkingFacilities | param (query) | venueId | string (uuid) |  | Required for a guest caller; optional for staff, where it narrows the list.
AccessService | listParkingFacilities | param (query) | pageSize | integer
AccessService | listParkingFacilities | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listPaymentTokens | response | items | array of PaymentToken | yes
OrderService | listPaymentTokens | response | items[].id | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].subjectId | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].providerId | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].token | string (password) | yes | Write-only, never returned.
OrderService | listPaymentTokens | response | items[].method | string
OrderService | listPaymentTokens | response | items[].maskedIdentifier | string |  | What a guest sees — the last four digits, the card brand.
OrderService | listPaymentTokens | response | items[].expiresAt | string (date) |  | (nullable)
OrderService | listPaymentTokens | response | items[].isDefault | boolean | yes
OrderService | listPaymentTokens | response | items[].consentPurposeId | string (uuid) |  | Storing a card for future use is a purpose a guest consents to, separate from the payment they are making now. (nullable)
OrderService | listPaymentTokens | response | nextCursor | string
OrderService | listPaymentTokens | response | hasMore | boolean | yes
OrderService | listPaymentTokens | param (query) | pageSize | integer
OrderService | listPaymentTokens | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPerformances | response | items | array of Performance | yes
CatalogueService | listPerformances | response | items[].id | string (uuid) | yes
CatalogueService | listPerformances | response | items[].eventId | string (uuid) | yes
CatalogueService | listPerformances | response | items[].startsAt | string (date-time) | yes
CatalogueService | listPerformances | response | items[].endsAt | string (date-time) | yes
CatalogueService | listPerformances | response | items[].approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | listPerformances | response | items[].requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | listPerformances | response | items[].status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | listPerformances | response | items[].admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | listPerformances | response | items[].seatMapId | string (uuid) |  | (nullable)
CatalogueService | listPerformances | response | items[].language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | listPerformances | response | items[].format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | listPerformances | response | nextCursor | string
CatalogueService | listPerformances | response | hasMore | boolean | yes
CatalogueService | listPerformances | param (path) | eventId | string (uuid) | yes
CatalogueService | listPerformances | param (query) | from | string (date-time) |  | Only performances whose startsAt is at or after this instant.
CatalogueService | listPerformances | param (query) | to | string (date-time) |  | Only performances whose startsAt is before this instant.
CatalogueService | listPerformances | param (query) | categoryId | string (uuid) |  | Only performances of products in this product category (a product in several categories matches each), the calendar's category filter (17 September minutes M17-03, added 30 September).
CatalogueService | listPerformances | param (query) | language | string |  | Only performances given in this language, e.g.
CatalogueService | listPerformances | param (query) | pageSize | integer
CatalogueService | listPerformances | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listPolicies | param (query) | includeHistory | boolean |  | Every version rather than the current one per kind (audit R163).
WhiteLabelService | listPolicies | param (query) | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) |  | Only this policy kind.
IdentityService | listPrincipals | response | items | array of Principal | yes
IdentityService | listPrincipals | response | items[].id | string (uuid) | yes
IdentityService | listPrincipals | response | items[].username | string | yes
IdentityService | listPrincipals | response | items[].displayName | string | yes
IdentityService | listPrincipals | response | items[].isActive | boolean | yes
IdentityService | listPrincipals | response | items[].validFrom | string (date-time) |  | (nullable)
IdentityService | listPrincipals | response | items[].validTo | string (date-time) |  | Past this, resolution returns DENY regardless of grants. (nullable)
IdentityService | listPrincipals | response | items[].primaryRoleId | string (uuid) |  | Determines the landing screen when the principal holds several roles and picks one at login. (nullable)
IdentityService | listPrincipals | response | items[].roles | array of RoleSummary
IdentityService | listPrincipals | response | items[].roles[].id | string (uuid) | yes
IdentityService | listPrincipals | response | items[].roles[].code | string | yes
IdentityService | listPrincipals | response | items[].roles[].name | string | yes
IdentityService | listPrincipals | response | items[].roles[].isPrimary | boolean
IdentityService | listPrincipals | response | items[].lastLoginAt | string (date-time) |  | (nullable)
IdentityService | listPrincipals | response | nextCursor | string
IdentityService | listPrincipals | response | hasMore | boolean | yes
IdentityService | listPrincipals | param (query) | scopePath | string |  | Principals whose home scope (identity.principal.home_scope_id) is this node or any node beneath it — a prefix match on the materialised path, the way scope_path is compared everywhere (shared/common.…
IdentityService | listPrincipals | param (query) | isActive | boolean |  | Exact match on Principal.isActive.
IdentityService | listPrincipals | param (query) | pageSize | integer
IdentityService | listPrincipals | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listProductStartTimes | response | items | array of ProductStartTime | yes
VenueOpsService | listProductStartTimes | response | items[].startsAt | string (date-time) | yes
VenueOpsService | listProductStartTimes | response | items[].endsAt | string (date-time) | yes | startsAt plus the variant's durationMinutes; the cart line's bookedWindow.endsAt.
VenueOpsService | listProductStartTimes | response | items[].freeCount | integer | yes | Resources of the room type free for the whole window. (min 1)
VenueOpsService | listProductStartTimes | response | nextCursor | string
VenueOpsService | listProductStartTimes | response | hasMore | boolean | yes
VenueOpsService | listProductStartTimes | param (query) | productId | string (uuid) | yes | A catalogue.Product with requiresTimeWindow true, else 422.
VenueOpsService | listProductStartTimes | param (query) | variantId | string (uuid) | yes | The length variant; its length value's durationMinutes is the window.
VenueOpsService | listProductStartTimes | param (query) | date | string (date) | yes | The venue-local date.
VenueOpsService | listProductStartTimes | param (query) | stepMinutes | enum (15, 30, 60) |  | Spacing of the offered start times.
VenueOpsService | listProductStartTimes | param (query) | pageSize | integer
VenueOpsService | listProductStartTimes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProductVariants | response | items | array of ProductVariant | yes
CatalogueService | listProductVariants | response | items[].id | string (uuid) | yes
CatalogueService | listProductVariants | response | items[].productId | string (uuid) | yes
CatalogueService | listProductVariants | response | items[].sku | string | yes
CatalogueService | listProductVariants | response | items[].axisValues | object | yes
CatalogueService | listProductVariants | response | items[].name | string |  | Taken from their variant tables, 20 September. (max length 150; nullable)
CatalogueService | listProductVariants | response | items[].barcode | string |  | Taken from their variant tables, 20 September. (max length 64; nullable)
CatalogueService | listProductVariants | response | items[].isDefault | boolean |  | Taken from their variant tables. (default False)
CatalogueService | listProductVariants | response | items[].isActive | boolean | yes | False when retired.
CatalogueService | listProductVariants | response | items[].description | object |  | Who this ticket type is for and what it includes, shown behind the (i) on each Adult, Child, Senior or Infant row (decided 29 September, 23SEP-6). (nullable)
CatalogueService | listProductVariants | response | nextCursor | string
CatalogueService | listProductVariants | response | hasMore | boolean | yes
CatalogueService | listProductVariants | param (path) | productId | string (uuid) | yes
CatalogueService | listProductVariants | param (query) | pageSize | integer
CatalogueService | listProductVariants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProducts | response | items | array of Product | yes
CatalogueService | listProducts | response | items[].id | string (uuid) | yes
CatalogueService | listProducts | response | items[].code | string | yes | (max length 64)
CatalogueService | listProducts | response | items[].familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | listProducts | response | items[].name | string | yes | (max length 200)
CatalogueService | listProducts | response | items[].description | string
CatalogueService | listProducts | response | items[].kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | listProducts | response | items[].venueId | string (uuid) | yes
CatalogueService | listProducts | response | items[].scopePath | string | yes
CatalogueService | listProducts | response | items[].createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | listProducts | response | items[].approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | listProducts | response | items[].responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | listProducts | response | items[].onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | listProducts | response | items[].onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | listProducts | response | items[].categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | listProducts | response | items[].lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | listProducts | response | items[].isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | listProducts | response | items[].isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | listProducts | response | items[].hasVariants | boolean | yes
CatalogueService | listProducts | response | items[].variantCount | integer
CatalogueService | listProducts | response | items[].segmentTags | array of string |  | 7.3.5.
CatalogueService | listProducts | response | items[].codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | listProducts | response | items[].channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | listProducts | response | items[].entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | listProducts | response | items[].blockedOffline | boolean |  | True for seated and retail.
CatalogueService | listProducts | response | items[].dataMaskValues | object |  | Custom fields.
CatalogueService | listProducts | response | items[].guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | listProducts | response | items[].notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | listProducts | response | items[].salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | listProducts | response | items[].salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | listProducts | response | items[].salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | listProducts | response | items[].salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | listProducts | response | items[].bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | listProducts | response | items[].displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | listProducts | response | items[].displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | listProducts | response | items[].displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | listProducts | response | items[].displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | listProducts | response | items[].media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | listProducts | response | items[].media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | listProducts | response | items[].media[].kind | enum (image, video) | yes
CatalogueService | listProducts | response | items[].media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | listProducts | response | items[].media[].displayOrder | integer |  | (default 100)
CatalogueService | listProducts | response | items[].media[].altText | object |  | (nullable)
CatalogueService | listProducts | response | items[].consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | listProducts | response | items[].requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | listProducts | response | items[].productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | listProducts | response | items[].operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | listProducts | response | items[].businessUnitId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | listProducts | response | items[].attractionId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].siteId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].locationId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | listProducts | response | items[].marketCode | string |  | (max length 40; nullable)
CatalogueService | listProducts | response | items[].salesTerritory | string |  | (max length 100; nullable)
CatalogueService | listProducts | response | nextCursor | string
CatalogueService | listProducts | response | hasMore | boolean | yes
CatalogueService | listProducts | param (query) | venueId | string (uuid)
CatalogueService | listProducts | param (query) | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …)
CatalogueService | listProducts | param (query) | isSellable | boolean
CatalogueService | listProducts | param (query) | categoryId | string (uuid) |  | Only products filed under this category (Product.categoryId) or any category below it in the tree, so a tile for *Guided tours* also lists what sits under its subcategories.
CatalogueService | listProducts | param (query) | segmentTag | string |  | Only products carrying this tag in segmentTags, or a tag below it (level matches level/beginner; level/beginner matches only itself).
CatalogueService | listProducts | param (query) | guidedAnswerIds | array of string (uuid) |  | Help me choose answers, as filters (decided 29 September, W4).
CatalogueService | listProducts | param (query) | pageSize | integer
CatalogueService | listProducts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPromotions | response | items | array of Promotion or GuestPromotion | yes
CatalogueService | listPromotions | response | nextCursor | string
CatalogueService | listPromotions | response | hasMore | boolean | yes
CatalogueService | listPromotions | param (query) | venueId | string (uuid)
CatalogueService | listPromotions | param (query) | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended)
CatalogueService | listPromotions | param (query) | activeAt | string (date-time)
CatalogueService | listPromotions | param (query) | pageSize | integer
CatalogueService | listPromotions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listPublishedTrackingTechnologies | response | items | array of PublishedTrackingTechnology | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].name | string | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].provider | string | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | listPublishedTrackingTechnologies | response | items[].technologyType | string
MarketingService | listPublishedTrackingTechnologies | response | items[].purpose | string |  | (nullable)
MarketingService | listPublishedTrackingTechnologies | response | items[].durationDays | integer |  | Null for session storage. (nullable)
MarketingService | listPublishedTrackingTechnologies | response | items[].isThirdParty | boolean | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].privacyInformation | string |  | (nullable)
MarketingService | listPublishedTrackingTechnologies | response | nextCursor | string
MarketingService | listPublishedTrackingTechnologies | response | hasMore | boolean | yes
MarketingService | listPublishedTrackingTechnologies | param (query) | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | listPublishedTrackingTechnologies | param (query) | category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing)
MarketingService | listPublishedTrackingTechnologies | param (query) | pageSize | integer
MarketingService | listPublishedTrackingTechnologies | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listQueueEntries | response | items | array of WaitingGuest | yes
VenueOpsService | listQueueEntries | response | items[].id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | listQueueEntries | response | items[].queueId | string (uuid) | yes
VenueOpsService | listQueueEntries | response | items[].queueName | LocalisedText
VenueOpsService | listQueueEntries | response | items[].subjectId | string (uuid) |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | listQueueEntries | response | items[].partySize | integer | yes
VenueOpsService | listQueueEntries | response | items[].status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | listQueueEntries | response | items[].positionInQueue | integer |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].partiesAhead | integer |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].isFastPass | boolean
VenueOpsService | listQueueEntries | response | items[].priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | listQueueEntries | response | items[].priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | listQueueEntries | response | items[].priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | listQueueEntries | response | items[].accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | listQueueEntries | response | items[].entitlementId | string |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].calledAt | string (date-time) |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].admittedCount | integer |  | (nullable)
VenueOpsService | listQueueEntries | response | items[].joinedAt | string (date-time) | yes
VenueOpsService | listQueueEntries | response | items[].syncedAt | string (date-time) |  | (nullable)
VenueOpsService | listQueueEntries | response | nextCursor | string
VenueOpsService | listQueueEntries | response | hasMore | boolean | yes
VenueOpsService | listQueueEntries | param (path) | queueId | string (uuid) | yes
VenueOpsService | listQueueEntries | param (query) | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released)
VenueOpsService | listQueueEntries | param (query) | pageSize | integer
VenueOpsService | listQueueEntries | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listQueues | response | items | array of Queue | yes
VenueOpsService | listQueues | response | items[].code | string | yes | (max length 64)
VenueOpsService | listQueues | response | items[].name | LocalisedText | yes
VenueOpsService | listQueues | response | items[].venueId | string (uuid) | yes
VenueOpsService | listQueues | response | items[].attractionProductId | string (uuid)
VenueOpsService | listQueues | response | items[].assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | listQueues | response | items[].accessPointId | string (uuid) |  | (nullable)
VenueOpsService | listQueues | response | items[].kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | listQueues | response | items[].operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | listQueues | response | items[].operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | listQueues | response | items[].operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | listQueues | response | items[].operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | listQueues | response | items[].operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | listQueues | response | items[].parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | listQueues | response | items[].loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | listQueues | response | items[].inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | listQueues | response | items[].notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | listQueues | response | items[].capacityPerCycle | integer | yes | (min 1)
VenueOpsService | listQueues | response | items[].cycleMinutes | number | yes | (min 0)
VenueOpsService | listQueues | response | items[].maxPartySize | integer |  | (default 6)
VenueOpsService | listQueues | response | items[].returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | listQueues | response | items[].heightRequirementCm | integer |  | (nullable)
VenueOpsService | listQueues | response | items[].fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | listQueues | response | items[].zone | string |  | (nullable)
VenueOpsService | listQueues | response | items[].fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | listQueues | response | items[].fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | listQueues | response | items[].fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | listQueues | response | items[].fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | listQueues | response | items[].fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | listQueues | response | items[].fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | listQueues | response | items[].fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | listQueues | response | items[].fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | listQueues | response | items[].id | string (uuid) | yes
VenueOpsService | listQueues | response | items[].status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | listQueues | response | items[].statusReason | string |  | (nullable)
VenueOpsService | listQueues | response | items[].waitingPartyCount | integer | yes
VenueOpsService | listQueues | response | items[].waitingGuestCount | integer
VenueOpsService | listQueues | response | items[].currentWaitMinutes | integer |  | (nullable)
VenueOpsService | listQueues | response | items[].waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | listQueues | response | items[].waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | listQueues | response | items[].manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | listQueues | response | items[].manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | listQueues | response | items[].expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | listQueues | response | nextCursor | string
VenueOpsService | listQueues | response | hasMore | boolean | yes
VenueOpsService | listQueues | param (query) | venueId | string (uuid)
VenueOpsService | listQueues | param (query) | openOnly | boolean
VenueOpsService | listQueues | param (query) | pageSize | integer
VenueOpsService | listQueues | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listReports | response | items | array of ReportDefinition | yes
ReportingService | listReports | response | items[].name | string | yes | (max length 200)
ReportingService | listReports | response | items[].description | string |  | (max length 1000)
ReportingService | listReports | response | items[].category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | listReports | response | items[].dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | listReports | response | items[].columns | array of ReportColumn | yes | (min items 1)
ReportingService | listReports | response | items[].columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | listReports | response | items[].columns[].field | string | yes
ReportingService | listReports | response | items[].columns[].label | string
ReportingService | listReports | response | items[].columns[].aggregation | object |  | (default none)
ReportingService | listReports | response | items[].columns[].sortOrder | integer
ReportingService | listReports | response | items[].columns[].sortDirection | enum (asc, desc)
ReportingService | listReports | response | items[].columns[].format | string |  | (nullable)
ReportingService | listReports | response | items[].filters | array of ReportFilter
ReportingService | listReports | response | items[].filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | listReports | response | items[].filters[].field | string | yes
ReportingService | listReports | response | items[].filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | listReports | response | items[].filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | listReports | response | items[].filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | listReports | response | items[].filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | listReports | response | items[].groupBy | array of string
ReportingService | listReports | response | items[].parameters | array of ReportParameter
ReportingService | listReports | response | items[].parameters[].key | string | yes
ReportingService | listReports | response | items[].parameters[].label | string | yes
ReportingService | listReports | response | items[].parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | listReports | response | items[].parameters[].isRequired | boolean | yes
ReportingService | listReports | response | items[].parameters[].defaultValue | object |  | Open on purpose.
ReportingService | listReports | response | items[].requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | listReports | response | items[].maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | listReports | response | items[].id | string (uuid) | yes
ReportingService | listReports | response | items[].version | string | yes | The current version.
ReportingService | listReports | response | items[].isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | listReports | response | items[].isRetired | boolean | yes
ReportingService | listReports | response | items[].estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | listReports | response | items[].createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | listReports | response | items[].createdAt | string (date-time) | yes
ReportingService | listReports | response | items[].lastRunAt | string (date-time) |  | (nullable)
ReportingService | listReports | response | items[].scopePath | string |  | The partition key (ADR-0005).
ReportingService | listReports | response | nextCursor | string
ReportingService | listReports | response | hasMore | boolean | yes
ReportingService | listReports | param (query) | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …)
ReportingService | listReports | param (query) | search | string
ReportingService | listReports | param (query) | pageSize | integer
ReportingService | listReports | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listReservations | response | items | array of Reservation | yes
OrderService | listReservations | response | items[].id | string (uuid) | yes
OrderService | listReservations | response | items[].venueId | string (uuid) | yes
OrderService | listReservations | response | items[].subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | listReservations | response | items[].status | enum (held, converted, expired, cancelled) | yes
OrderService | listReservations | response | items[].lines | array of CreateOrderLine
OrderService | listReservations | response | items[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | listReservations | response | items[].lines[].variantId | string (uuid) | yes
OrderService | listReservations | response | items[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | listReservations | response | items[].lines[].performanceId | string (uuid)
OrderService | listReservations | response | items[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | listReservations | response | items[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | listReservations | response | items[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | listReservations | response | items[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | listReservations | response | items[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | listReservations | response | items[].lines[].quantity | integer | yes | (min 1)
OrderService | listReservations | response | items[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | listReservations | response | items[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | listReservations | response | items[].lines[].holderName | string |  | (nullable)
OrderService | listReservations | response | items[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | listReservations | response | items[].expiresAt | string (date-time) | yes
OrderService | listReservations | response | items[].createdAt | string (date-time) | yes
OrderService | listReservations | response | items[].convertedOrderId | string (uuid) |  | (nullable)
OrderService | listReservations | response | nextCursor | string
OrderService | listReservations | response | hasMore | boolean | yes
OrderService | listReservations | param (query) | status | enum (held, converted, expired, cancelled) |  | Exact match.
OrderService | listReservations | param (query) | expiringWithinMinutes | integer |  | Only held reservations whose expiresAt falls within this many minutes of now — the ones about to release capacity.
OrderService | listReservations | param (query) | pageSize | integer
OrderService | listReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | listRetailSales | response | items | array of RetailSale | yes
RetailService | listRetailSales | response | items[].id | string | yes
RetailService | listRetailSales | response | items[].receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | listRetailSales | response | items[].orderId | string | yes | The order in the Order & Payment context.
RetailService | listRetailSales | response | items[].outletId | string (uuid) | yes
RetailService | listRetailSales | response | items[].shiftId | string |  | (nullable)
RetailService | listRetailSales | response | items[].subjectId | string (uuid) |  | (nullable)
RetailService | listRetailSales | response | items[].lines | array of object | yes
RetailService | listRetailSales | response | items[].lines[].lineId | string
RetailService | listRetailSales | response | items[].lines[].merchandiseId | string (uuid)
RetailService | listRetailSales | response | items[].lines[].name | string
RetailService | listRetailSales | response | items[].lines[].quantity | integer
RetailService | listRetailSales | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].serialNumbers | array of string
RetailService | listRetailSales | response | items[].lines[].returnedQuantity | integer
RetailService | listRetailSales | response | items[].lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | listRetailSales | response | items[].lines[].notReturnableReason | string |  | (nullable)
RetailService | listRetailSales | response | items[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].reprintCount | integer
RetailService | listRetailSales | response | items[].createdAt | string (date-time) | yes
RetailService | listRetailSales | response | items[].recordedAt | string (date-time)
RetailService | listRetailSales | response | nextCursor | string
RetailService | listRetailSales | response | hasMore | boolean | yes
RetailService | listRetailSales | param (query) | outletId | string (uuid) |  | Exact match.
RetailService | listRetailSales | param (query) | shiftId | string |  | Exact match.
RetailService | listRetailSales | param (query) | createdFrom | string (date-time) |  | Sales with createdAt at or after this instant.
RetailService | listRetailSales | param (query) | createdTo | string (date-time) |  | Sales with createdAt before this instant.
RetailService | listRetailSales | param (query) | pageSize | integer
RetailService | listRetailSales | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listRoles | response | items | array of Role | yes
IdentityService | listRoles | response | items[].id | string (uuid) | yes
IdentityService | listRoles | response | items[].code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | listRoles | response | items[].name | string | yes
IdentityService | listRoles | response | items[].description | string
IdentityService | listRoles | response | items[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | listRoles | response | items[].inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | listRoles | response | items[].isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | listRoles | response | items[].principalCount | integer
IdentityService | listRoles | response | items[].grantCount | integer
IdentityService | listRoles | response | nextCursor | string
IdentityService | listRoles | response | hasMore | boolean | yes
IdentityService | listRoles | param (query) | pageSize | integer
IdentityService | listRoles | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listRotaAssignments | response | items | array of RotaAssignment | yes
TenancyService | listRotaAssignments | response | items[].overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | listRotaAssignments | response | items[].restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | listRotaAssignments | response | items[].breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | listRotaAssignments | response | items[].labourCost | object |  | Cost at the point of scheduling.
TenancyService | listRotaAssignments | response | items[].labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | listRotaAssignments | response | items[].labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | listRotaAssignments | response | items[].labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | listRotaAssignments | response | items[].id | string (uuid) |  | (read-only)
TenancyService | listRotaAssignments | response | items[].principalId | string (uuid) | yes
TenancyService | listRotaAssignments | response | items[].displayName | string |  | (read-only)
TenancyService | listRotaAssignments | response | items[].venueId | string (uuid) | yes
TenancyService | listRotaAssignments | response | items[].departmentId | string (uuid) |  | (nullable)
TenancyService | listRotaAssignments | response | items[].position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | listRotaAssignments | response | items[].requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | listRotaAssignments | response | items[].workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | listRotaAssignments | response | items[].startsAt | string (date-time) | yes
TenancyService | listRotaAssignments | response | items[].endsAt | string (date-time) | yes
TenancyService | listRotaAssignments | response | items[].status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | listRotaAssignments | response | items[].breakMinutes | integer |  | (nullable)
TenancyService | listRotaAssignments | response | items[].note | string |  | (nullable)
TenancyService | listRotaAssignments | response | nextCursor | string
TenancyService | listRotaAssignments | response | hasMore | boolean | yes
TenancyService | listRotaAssignments | param (query) | from | string (date) |  | First calendar day, in the Region's time zone, not UTC.
TenancyService | listRotaAssignments | param (query) | to | string (date) |  | Last calendar day, in the Region's time zone, not UTC.
TenancyService | listRotaAssignments | param (query) | principalId | string (uuid)
TenancyService | listRotaAssignments | param (query) | departmentId | string (uuid)
TenancyService | listRotaAssignments | param (query) | pageSize | integer
TenancyService | listRotaAssignments | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listSaleBoards | param (query) | venueId | string (uuid)
TenancyService | listSaleBoards | param (query) | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed)
InventoryService | listSerialisedItems | response | items | array of SerialisedItem | yes
InventoryService | listSerialisedItems | response | items[].id | string (uuid) | yes
InventoryService | listSerialisedItems | response | items[].itemId | string (uuid) | yes
InventoryService | listSerialisedItems | response | items[].batchId | string (uuid) |  | The batch it arrived in, where the item is both lotted and serialised. (nullable)
InventoryService | listSerialisedItems | response | items[].serial | string | yes | Unique within the item, not globally.
InventoryService | listSerialisedItems | response | items[].locationId | string (uuid)
InventoryService | listSerialisedItems | response | items[].status | enum (inStock, reserved, sold, returned, damaged, lost, inTransit, warranty) | yes
InventoryService | listSerialisedItems | response | items[].soldOnOrderLineId | string (uuid) |  | The link that makes serialisation worth having. (nullable)
InventoryService | listSerialisedItems | response | items[].warrantyUntil | string (date) |  | (nullable)
InventoryService | listSerialisedItems | response | items[].receivedAt | string (date-time)
InventoryService | listSerialisedItems | response | nextCursor | string
InventoryService | listSerialisedItems | response | hasMore | boolean | yes
InventoryService | listSerialisedItems | param (query) | serial | string |  | Exact match.
InventoryService | listSerialisedItems | param (query) | status | string
InventoryService | listSerialisedItems | param (query) | pageSize | integer
InventoryService | listSerialisedItems | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listShifts | response | items | array of Shift | yes
OrderService | listShifts | response | items[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | listShifts | response | items[].workstationId | string (uuid) | yes
OrderService | listShifts | response | items[].venueId | string (uuid) | yes
OrderService | listShifts | response | items[].scopePath | string | yes
OrderService | listShifts | response | items[].principalId | string (uuid) | yes | Who opened it.
OrderService | listShifts | response | items[].principalDisplayName | string
OrderService | listShifts | response | items[].incidents | array of object |  | BL-097.
OrderService | listShifts | response | items[].incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | listShifts | response | items[].incidents[].at | string (date-time)
OrderService | listShifts | response | items[].incidents[].principalId | string (uuid)
OrderService | listShifts | response | items[].incidents[].note | string |  | (nullable)
OrderService | listShifts | response | items[].status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | listShifts | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | listShifts | response | items[].depositBoxCode | string |  | (nullable)
OrderService | listShifts | response | items[].bagNumber | string |  | (nullable)
OrderService | listShifts | response | items[].openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | listShifts | response | items[].expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | listShifts | response | items[].countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | listShifts | response | items[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | listShifts | response | items[].openedAt | string (date-time) | yes
OrderService | listShifts | response | items[].recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | listShifts | response | items[].suspendedAt | string (date-time) |  | (nullable)
OrderService | listShifts | response | items[].suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | listShifts | response | items[].closedAt | string (date-time) |  | (nullable)
OrderService | listShifts | response | items[].closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | listShifts | response | items[].syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | listShifts | response | items[].approvals | array of object
OrderService | listShifts | response | items[].approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | listShifts | response | items[].approvals[].principalId | string (uuid) | yes
OrderService | listShifts | response | items[].approvals[].at | string (date-time) | yes
OrderService | listShifts | response | items[].approvals[].reason | string
OrderService | listShifts | response | nextCursor | string
OrderService | listShifts | response | hasMore | boolean | yes
OrderService | listShifts | param (query) | workstationId | string (uuid)
OrderService | listShifts | param (query) | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed)
OrderService | listShifts | param (query) | openedFrom | string (date-time)
OrderService | listShifts | param (query) | openedTo | string (date-time)
OrderService | listShifts | param (query) | pageSize | integer
OrderService | listShifts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listTableReservations | response | items | array of TableReservation | yes
FnbService | listTableReservations | response | items[].id | string (uuid) |  | (read-only)
FnbService | listTableReservations | response | items[].outletId | string (uuid) | yes
FnbService | listTableReservations | response | items[].subjectId | string (uuid) |  | (nullable)
FnbService | listTableReservations | response | items[].guestName | string
FnbService | listTableReservations | response | items[].contactPoint | string
FnbService | listTableReservations | response | items[].partySize | integer | yes | (min 1)
FnbService | listTableReservations | response | items[].startsAt | string (date-time) | yes
FnbService | listTableReservations | response | items[].durationMinutes | integer |  | How long the cover is held.
FnbService | listTableReservations | response | items[].tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | listTableReservations | response | items[].tables[].reservationId | string (uuid) | yes
FnbService | listTableReservations | response | items[].tables[].tableId | string (uuid) | yes
FnbService | listTableReservations | response | items[].tables[].createdAt | string (date-time) | yes
FnbService | listTableReservations | response | items[].status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | listTableReservations | response | items[].groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | listTableReservations | response | items[].notes | string |  | Allergies
FnbService | listTableReservations | response | items[].actualPartySize | integer |  | (read-only; nullable)
FnbService | listTableReservations | response | items[].tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | listTableReservations | response | items[].deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | listTableReservations | response | items[].deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listTableReservations | response | items[].deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | listTableReservations | response | items[].deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | listTableReservations | response | items[].deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | listTableReservations | response | items[].deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | listTableReservations | response | items[].deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | listTableReservations | response | items[].deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | listTableReservations | response | items[].createdAt | string (date-time) |  | (read-only)
FnbService | listTableReservations | response | nextCursor | string
FnbService | listTableReservations | response | hasMore | boolean | yes
FnbService | listTableReservations | param (query) | outletId | string (uuid)
FnbService | listTableReservations | param (query) | date | string (date) |  | A calendar day, in the Region's time zone, not UTC.
FnbService | listTableReservations | param (query) | pageSize | integer
FnbService | listTableReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listTaxInvoices | response | items | array of FinTaxInvoice | yes
LedgerService | listTaxInvoices | response | items[].id | string (uuid) | yes | (read-only)
LedgerService | listTaxInvoices | response | items[].invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | listTaxInvoices | response | items[].invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | listTaxInvoices | response | items[].status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | listTaxInvoices | response | items[].legalEntityId | string (uuid) | yes
LedgerService | listTaxInvoices | response | items[].templateId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].venueId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].orderIds | array of string (uuid)
LedgerService | listTaxInvoices | response | items[].supplierName | string
LedgerService | listTaxInvoices | response | items[].supplierAddress | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | listTaxInvoices | response | items[].buyerName | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerAddress | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | listTaxInvoices | response | items[].buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].customerAccountId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].issuedAt | string (date-time) | yes
LedgerService | listTaxInvoices | response | items[].supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | listTaxInvoices | response | items[].currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].languages | array of string
LedgerService | listTaxInvoices | response | items[].supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | listTaxInvoices | response | items[].issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].lines | array of FinTaxInvoiceLine | yes
LedgerService | listTaxInvoices | response | items[].lines[].lineNumber | integer | yes | (min 1)
LedgerService | listTaxInvoices | response | items[].lines[].orderId | string (uuid)
LedgerService | listTaxInvoices | response | items[].lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].lines[].description | string | yes | (max length 500)
LedgerService | listTaxInvoices | response | items[].lines[].quantity | number | yes
LedgerService | listTaxInvoices | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].lines[].taxRate | number |  | (min 0; max 100)
LedgerService | listTaxInvoices | response | items[].lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | listTaxInvoices | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxRate | number
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | listTaxInvoices | response | nextCursor | string
LedgerService | listTaxInvoices | response | hasMore | boolean | yes
LedgerService | listTaxInvoices | param (query) | orderId | string (uuid) |  | Invoices covering this order, including a consolidated invoice that names it.
LedgerService | listTaxInvoices | param (query) | legalEntityId | string (uuid)
LedgerService | listTaxInvoices | param (query) | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated)
LedgerService | listTaxInvoices | param (query) | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded)
LedgerService | listTaxInvoices | param (query) | issuedFrom | string (date) |  | A day in the region's time zone, local midnight to local midnight.
LedgerService | listTaxInvoices | param (query) | issuedTo | string (date) |  | A day in the region's time zone, local midnight to local midnight.
LedgerService | listTaxInvoices | param (query) | pageSize | integer
LedgerService | listTaxInvoices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
PlatformService | listTenants | response | items | array of Tenant | yes
PlatformService | listTenants | response | items[].id | string (uuid) | yes
PlatformService | listTenants | response | items[].code | string | yes
PlatformService | listTenants | response | items[].name | string | yes
PlatformService | listTenants | response | items[].status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | listTenants | response | items[].suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | listTenants | response | items[].suspensionReason | string |  | (nullable)
PlatformService | listTenants | response | items[].suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | listTenants | response | items[].suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | listTenants | response | items[].terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | listTenants | response | items[].terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | listTenants | response | items[].terminationReason | string |  | (max length 1000; nullable)
PlatformService | listTenants | response | items[].terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].planId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].planName | string |  | (nullable)
PlatformService | listTenants | response | items[].cellCount | integer
PlatformService | listTenants | response | items[].venueCount | integer
PlatformService | listTenants | response | items[].regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | listTenants | response | items[].billingEmail | string
PlatformService | listTenants | response | items[].billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | listTenants | response | items[].accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].createdAt | string (date-time) | yes
PlatformService | listTenants | response | items[].activatedAt | string (date-time) |  | (nullable)
PlatformService | listTenants | response | nextCursor | string
PlatformService | listTenants | response | hasMore | boolean | yes
PlatformService | listTenants | param (query) | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated)
PlatformService | listTenants | param (query) | planId | string (uuid)
PlatformService | listTenants | param (query) | pageSize | integer
PlatformService | listTenants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportPassOffers | response | items | array of PassOffer | yes
VenueOpsService | listTransportPassOffers | response | items[].passTypeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportPassOffers | response | items[].catalogueProductId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | items[].routeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportPassOffers | response | items[].name | string | yes
VenueOpsService | listTransportPassOffers | response | items[].description | string
VenueOpsService | listTransportPassOffers | response | items[].kind | enum (multiTrip, unlimited)
VenueOpsService | listTransportPassOffers | response | items[].trips | integer |  | (nullable)
VenueOpsService | listTransportPassOffers | response | items[].validityDays | integer | yes
VenueOpsService | listTransportPassOffers | response | items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | listTransportPassOffers | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listTransportPassOffers | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listTransportPassOffers | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listTransportPassOffers | response | items[].saving | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | listTransportPassOffers | response | items[].saving.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listTransportPassOffers | response | items[].saving.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listTransportPassOffers | response | items[].saving.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listTransportPassOffers | response | nextCursor | string
VenueOpsService | listTransportPassOffers | response | hasMore | boolean | yes
VenueOpsService | listTransportPassOffers | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | param (query) | toStationId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | param (query) | pageSize | integer
VenueOpsService | listTransportPassOffers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportRoutes | response | items | array of TransportRoute | yes
VenueOpsService | listTransportRoutes | response | items[].venueId | string (uuid) | yes
VenueOpsService | listTransportRoutes | response | items[].code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | listTransportRoutes | response | items[].lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | listTransportRoutes | response | items[].name | LocalisedText | yes
VenueOpsService | listTransportRoutes | response | items[].colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | listTransportRoutes | response | items[].pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | listTransportRoutes | response | items[].bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | listTransportRoutes | response | items[].stops | array of RouteStop | yes
VenueOpsService | listTransportRoutes | response | items[].stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | listTransportRoutes | response | items[].stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | listTransportRoutes | response | items[].stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | listTransportRoutes | response | items[].stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | listTransportRoutes | response | items[].stops[].station | Station
VenueOpsService | listTransportRoutes | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | listTransportRoutes | response | items[].totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | listTransportRoutes | response | items[].catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | listTransportRoutes | response | items[].catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | listTransportRoutes | response | nextCursor | string
VenueOpsService | listTransportRoutes | response | hasMore | boolean | yes
VenueOpsService | listTransportRoutes | param (query) | venueId | string (uuid) | yes
VenueOpsService | listTransportRoutes | param (query) | fromStationId | string (uuid)
VenueOpsService | listTransportRoutes | param (query) | toStationId | string (uuid)
VenueOpsService | listTransportRoutes | param (query) | status | TransportRouteStatus: enum (draft, active, suspended, retired)
VenueOpsService | listTransportRoutes | param (query) | pageSize | integer
VenueOpsService | listTransportRoutes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportStations | response | items | array of Station | yes
VenueOpsService | listTransportStations | response | items[].venueId | string (uuid) | yes
VenueOpsService | listTransportStations | response | items[].code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | listTransportStations | response | items[].name | LocalisedText | yes
VenueOpsService | listTransportStations | response | items[].shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | listTransportStations | response | items[].latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | listTransportStations | response | items[].longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | listTransportStations | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportStations | response | items[].active | boolean | yes | (default True)
VenueOpsService | listTransportStations | response | nextCursor | string
VenueOpsService | listTransportStations | response | hasMore | boolean | yes
VenueOpsService | listTransportStations | param (query) | venueId | string (uuid) | yes
VenueOpsService | listTransportStations | param (query) | includeInactive | boolean
VenueOpsService | listTransportStations | param (query) | pageSize | integer
VenueOpsService | listTransportStations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listVenueHistoryImports | response | items | array of AiHistoryImport | yes
AiService | listVenueHistoryImports | response | items[].id | string (uuid) | yes | (read-only)
AiService | listVenueHistoryImports | response | items[].venueId | string (uuid) | yes
AiService | listVenueHistoryImports | response | items[].dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | listVenueHistoryImports | response | items[].assetId | string (uuid)
AiService | listVenueHistoryImports | response | items[].sourceSystem | string |  | (nullable)
AiService | listVenueHistoryImports | response | items[].columnMapping | object
AiService | listVenueHistoryImports | response | items[].dryRun | boolean |  | (default False)
AiService | listVenueHistoryImports | response | items[].status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | listVenueHistoryImports | response | items[].periodFrom | string (date) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].periodTo | string (date) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].monthsCovered | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsRead | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsLoaded | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsRejected | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].findings | array of object |  | (read-only)
AiService | listVenueHistoryImports | response | items[].findings[].row | integer
AiService | listVenueHistoryImports | response | items[].findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | listVenueHistoryImports | response | items[].findings[].detail | string
AiService | listVenueHistoryImports | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | listVenueHistoryImports | response | items[].createdAt | string (date-time) |  | (read-only)
AiService | listVenueHistoryImports | response | items[].completedAt | string (date-time) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listVenueHistoryImports | response | nextCursor | string
AiService | listVenueHistoryImports | response | hasMore | boolean | yes
AiService | listVenueHistoryImports | param (path) | venueId | string (uuid) | yes
AiService | listVenueHistoryImports | param (query) | pageSize | integer
AiService | listVenueHistoryImports | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listVisitPlanAlternatives | response | items | array of VisitPlanAlternative | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].kind | enum (attraction, show, meal, shop, rest) | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].venueId | string (uuid) | yes | The item's day venue; an alternative is never from another venue (30 September, MoM 4.7).
VenueOpsService | listVisitPlanAlternatives | response | items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].productId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].name | string
VenueOpsService | listVisitPlanAlternatives | response | items[].startsAt | string (date-time) | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].durationMinutes | integer
VenueOpsService | listVisitPlanAlternatives | response | items[].walkMinutes | integer |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].expectedWaitMinutes | integer |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].matchedInterests | array of string
VenueOpsService | listVisitPlanAlternatives | response | items[].reason | string | yes | Why it is offered, in words the sheet shows, e.g.
VenueOpsService | listVisitPlanAlternatives | response | nextCursor | string
VenueOpsService | listVisitPlanAlternatives | response | hasMore | boolean | yes
VenueOpsService | listVisitPlanAlternatives | param (path) | planId | string (uuid) | yes
VenueOpsService | listVisitPlanAlternatives | param (path) | itemId | string (uuid) | yes
VenueOpsService | listVisitPlanAlternatives | param (query) | kind | enum (attraction, show, meal, shop, rest) |  | Only alternatives of this kind.
VenueOpsService | listVisitPlanAlternatives | param (query) | pageSize | integer
VenueOpsService | listVisitPlanAlternatives | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WalletService | listWalletTransactions | response | items | array of WalletTransaction | yes
WalletService | listWalletTransactions | response | items[].id | string | yes
WalletService | listWalletTransactions | response | items[].walletId | string (uuid) |  | The wallet this movement is on (SD-027, 29 September).
WalletService | listWalletTransactions | response | items[].walletHoldId | string (uuid) |  | The hold a spend settled, where it came through holdWalletFunds. (nullable)
WalletService | listWalletTransactions | response | items[].kind | WalletTransactionKind: enum (topUp, spend, refund, adjustment, bonus, expiry, transfer) | yes
WalletService | listWalletTransactions | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | listWalletTransactions | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | listWalletTransactions | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | listWalletTransactions | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | listWalletTransactions | response | items[].balanceAfter | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | listWalletTransactions | response | items[].balanceAfter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | listWalletTransactions | response | items[].balanceAfter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | listWalletTransactions | response | items[].balanceAfter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | listWalletTransactions | response | items[].orderId | string |  | (nullable)
WalletService | listWalletTransactions | response | items[].venueId | string (uuid) |  | (nullable)
WalletService | listWalletTransactions | response | items[].reason | string |  | (nullable)
WalletService | listWalletTransactions | response | items[].principalId | string (uuid) |  | (nullable)
WalletService | listWalletTransactions | response | items[].recordedAt | string (date-time) | yes
WalletService | listWalletTransactions | response | nextCursor | string
WalletService | listWalletTransactions | response | hasMore | boolean | yes
WalletService | listWalletTransactions | param (path) | subjectId | string (uuid) | yes
WalletService | listWalletTransactions | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
WalletService | listWalletTransactions | param (query) | pageSize | integer
WalletService | listWalletTransactions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listWorkstations | response | items | array of Workstation | yes
TenancyService | listWorkstations | response | items[].id | string (uuid) | yes
TenancyService | listWorkstations | response | items[].code | string | yes | (max length 64)
TenancyService | listWorkstations | response | items[].name | string | yes | (max length 200)
TenancyService | listWorkstations | response | items[].venueId | string (uuid) | yes
TenancyService | listWorkstations | response | items[].regionId | string (uuid) | yes
TenancyService | listWorkstations | response | items[].departmentId | string (uuid) |  | (nullable)
TenancyService | listWorkstations | response | items[].scopePath | string | yes
TenancyService | listWorkstations | response | items[].saleBoard | object | yes | Determines which front end loads.
TenancyService | listWorkstations | response | items[].saleBoard.id | string (uuid) | yes
TenancyService | listWorkstations | response | items[].saleBoard.kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | listWorkstations | response | items[].saleBoard.name | string
TenancyService | listWorkstations | response | items[].accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator. (nullable)
TenancyService | listWorkstations | response | items[].devices | array of DeviceBinding
TenancyService | listWorkstations | response | items[].devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | listWorkstations | response | items[].devices[].driver | string | yes | Driver identifier.
TenancyService | listWorkstations | response | items[].devices[].identifier | string |  | Serial
TenancyService | listWorkstations | response | items[].devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | listWorkstations | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
TenancyService | listWorkstations | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
TenancyService | listWorkstations | response | items[].timeZone | string | yes
TenancyService | listWorkstations | response | items[].deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | listWorkstations | response | items[].edgeNodeId | string (uuid) |  | Present when deploymentProfile is venueEdge. (nullable)
TenancyService | listWorkstations | response | items[].healthScore | integer |  | Board 1 of the client's POS set. (min 0; max 100; read-only; nullable)
TenancyService | listWorkstations | response | items[].configurationProfileId | string (uuid) |  | Which profile this workstation runs, and at which version. (nullable)
TenancyService | listWorkstations | response | items[].catalogueState | CatalogueState |  | The workstation's local catalogue position.
TenancyService | listWorkstations | response | items[].catalogueState.appliedBundleVersion | string | yes
TenancyService | listWorkstations | response | items[].catalogueState.appliedAt | string (date-time) | yes
TenancyService | listWorkstations | response | items[].catalogueState.staleAfter | string (date-time) | yes | Beyond this the terminal refuses to trade.
TenancyService | listWorkstations | response | items[].catalogueState.isStale | boolean | yes
TenancyService | listWorkstations | response | items[].catalogueState.pendingBundleVersion | string |  | Published but not yet applied. (nullable)
TenancyService | listWorkstations | response | items[].offlineCapable | boolean |  | Derived from deploymentProfile.
TenancyService | listWorkstations | response | items[].isActive | boolean
TenancyService | listWorkstations | response | nextCursor | string
TenancyService | listWorkstations | response | hasMore | boolean | yes
TenancyService | listWorkstations | param (query) | venueId | string (uuid)
TenancyService | listWorkstations | param (query) | saleBoardKind | SaleBoardKind: enum (ticketing, fnb, retail, mixed)
TenancyService | listWorkstations | param (query) | pageSize | integer
TenancyService | listWorkstations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WalletService | loadGameCredits | request | id | string (uuid) | yes
WalletService | loadGameCredits | request | credits | integer | yes | (min 1)
WalletService | loadGameCredits | request | bonusCredits | integer |  | (min 0; default 0)
WalletService | loadGameCredits | request | amountPaid | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | request | amountPaid.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | request | amountPaid.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | request | amountPaid.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | request | orderId | string
WalletService | loadGameCredits | request | recordedAt | string (date-time) | yes
WalletService | loadGameCredits | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | loadGameCredits | response | subjectId | string (uuid) | yes
WalletService | loadGameCredits | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | loadGameCredits | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | loadGameCredits | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | response | credits[].sourceRef | string |  | (nullable)
WalletService | loadGameCredits | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | loadGameCredits | response | bonusBalance | object |  | Promotional value.
WalletService | loadGameCredits | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | status | enum (active, suspended, closed) | yes
WalletService | loadGameCredits | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | loadGameCredits | response | expiresAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | param (path) | cardCode | string | yes
WalletService | loadGameCredits | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logColdChain | request | id | string (uuid) | yes
FnbService | logColdChain | request | goodsReceiptId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | transferId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | recordedAt | string (date-time) | yes
FnbService | logColdChain | request | valueCelsius | number | yes
FnbService | logColdChain | request | thresholdCelsius | number
FnbService | logColdChain | request | decision | enum (accepted, acceptedWithNote, partiallyRejected, rejected) | yes
FnbService | logColdChain | request | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | supplierClaimRaised | boolean |  | (default False)
FnbService | logColdChain | response | id | string (uuid) | yes
FnbService | logColdChain | response | goodsReceiptId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | transferId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | recordedAt | string (date-time) | yes
FnbService | logColdChain | response | valueCelsius | number | yes
FnbService | logColdChain | response | thresholdCelsius | number
FnbService | logColdChain | response | decision | enum (accepted, acceptedWithNote, partiallyRejected, rejected) | yes
FnbService | logColdChain | response | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | supplierClaimRaised | boolean |  | (default False)
FnbService | logColdChain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logKitchenException | request | kind | enum (equipmentDown, itemRanOut, lateDelivery, staffShort, powerLoss, spillage, other) | yes | chased is not offered here — chaseStation records it.
FnbService | logKitchenException | request | outletId | string (uuid) | yes | The outlet whose kitchen it happened in.
FnbService | logKitchenException | request | stationId | string (uuid) |  | (nullable)
FnbService | logKitchenException | request | ticketId | string (uuid) |  | The ticket it happened on, where there was one. (nullable)
FnbService | logKitchenException | request | durationMinutes | integer |  | (nullable)
FnbService | logKitchenException | request | note | string |  | (nullable)
FnbService | logKitchenException | request | recordedAt | string (date-time) | yes | Device time, not arrival time.
FnbService | logKitchenException | response | id | string (uuid) | yes
FnbService | logKitchenException | response | outletId | string (uuid)
FnbService | logKitchenException | response | stationId | string (uuid) |  | (nullable)
FnbService | logKitchenException | response | ticketId | string (uuid) |  | (nullable)
FnbService | logKitchenException | response | kind | enum (equipmentDown, itemRanOut, lateDelivery, staffShort, powerLoss, spillage, chased, other) | yes | other always carries a note (audit R222).
FnbService | logKitchenException | response | durationMinutes | integer |  | (nullable)
FnbService | logKitchenException | response | raisedAt | string (date-time) | yes
FnbService | logKitchenException | response | raisedByPrincipalId | string (uuid)
FnbService | logKitchenException | response | note | string |  | (nullable)
FnbService | logKitchenException | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logTemperature | request | id | string (uuid) | yes
FnbService | logTemperature | request | checkPointId | string (uuid) | yes | The unit, station or delivery being read.
FnbService | logTemperature | request | checkPointKind | enum (fridge, freezer, holdingCabinet, blastChiller, coreProbe, delivery, displayCounter, ambient)
FnbService | logTemperature | request | recordedAt | string (date-time) | yes
FnbService | logTemperature | request | recordedByPrincipalId | string (uuid)
FnbService | logTemperature | request | valueCelsius | number | yes
FnbService | logTemperature | request | minCelsius | number |  | (nullable)
FnbService | logTemperature | request | maxCelsius | number |  | (nullable)
FnbService | logTemperature | request | outcome | enum (inRange, outOfRange, notTaken) | yes | notTaken is a record, not an absence.
FnbService | logTemperature | request | deviceReported | boolean |  | A probe reading and a person's reading are different evidence. (default False)
FnbService | logTemperature | request | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | log | TemperatureLog |  | Board 5J of the client F&B pack, 20 August.
FnbService | logTemperature | response | log.id | string (uuid) | yes
FnbService | logTemperature | response | log.checkPointId | string (uuid) | yes | The unit, station or delivery being read.
FnbService | logTemperature | response | log.checkPointKind | enum (fridge, freezer, holdingCabinet, blastChiller, coreProbe, delivery, displayCounter, ambient)
FnbService | logTemperature | response | log.recordedAt | string (date-time) | yes
FnbService | logTemperature | response | log.recordedByPrincipalId | string (uuid)
FnbService | logTemperature | response | log.valueCelsius | number | yes
FnbService | logTemperature | response | log.minCelsius | number |  | (nullable)
FnbService | logTemperature | response | log.maxCelsius | number |  | (nullable)
FnbService | logTemperature | response | log.outcome | enum (inRange, outOfRange, notTaken) | yes | notTaken is a record, not an absence.
FnbService | logTemperature | response | log.deviceReported | boolean |  | A probe reading and a person's reading are different evidence. (default False)
FnbService | logTemperature | response | log.correctiveActionId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction | CorrectiveAction |  | What was done about a finding, and who signed it.
FnbService | logTemperature | response | correctiveAction.id | string (uuid) | yes
FnbService | logTemperature | response | correctiveAction.raisedAt | string (date-time) | yes
FnbService | logTemperature | response | correctiveAction.raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | logTemperature | response | correctiveAction.source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | logTemperature | response | correctiveAction.sourceRef | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | logTemperature | response | correctiveAction.actionTaken | string |  | (nullable)
FnbService | logTemperature | response | correctiveAction.disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | logTemperature | response | correctiveAction.signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.signedAt | string (date-time) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | logTemperature | response | correctiveAction.scopePath | string |  | The partition key (ADR-0005).
FnbService | logTemperature | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | login | request | username | string | yes | (max length 256)
IdentityService | login | request | credential | string | yes | Password, PIN, card token or RFID token depending on method. (max length 512)
IdentityService | login | request | method | enum (password, pin, card, rfid, sso) |  | pin is how a till is actually used. (default password)
IdentityService | login | request | workstationId | string (uuid) | yes | Identifies the device.
IdentityService | login | request | deviceFingerprint | string |  | (max length 256)
IdentityService | login | response | accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | login | response | refreshToken | string | yes
IdentityService | login | response | expiresIn | integer | yes | Seconds
IdentityService | login | response | requiresRoleSelection | boolean | yes
IdentityService | login | response | requiresMfa | boolean | yes | True when the principal holds any permission listed in PasswordPolicy.mfaRequiredForPermissions (decided 28 September, audit R135).
IdentityService | login | response | hasMfaMethod | boolean |  | Whether the principal has an active MFA method.
IdentityService | login | response | mfaMethods | array of MfaMethod |  | The principal's active methods, so the client can offer the right one for the signIn challenge.
IdentityService | login | response | mfaMethods[].id | string (uuid) | yes
IdentityService | login | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | login | response | mfaMethods[].label | string |  | (nullable)
IdentityService | login | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | login | response | mfaMethods[].isActive | boolean | yes
IdentityService | login | response | mfaMethods[].isPrimary | boolean
IdentityService | login | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | login | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | login | response | availableRoles | array of RoleSummary
IdentityService | login | response | availableRoles[].id | string (uuid) | yes
IdentityService | login | response | availableRoles[].code | string | yes
IdentityService | login | response | availableRoles[].name | string | yes
IdentityService | login | response | availableRoles[].isPrimary | boolean
IdentityService | login | response | session | Session
IdentityService | login | response | session.sessionId | string (uuid) | yes
IdentityService | login | response | session.principalId | string (uuid) | yes
IdentityService | login | response | session.roleId | string (uuid) | yes
IdentityService | login | response | session.displayName | string
IdentityService | login | response | session.scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | login | response | session.scope[].id | string (uuid) | yes
IdentityService | login | response | session.scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | login | response | session.scope[].path | string | yes | Materialised ltree path.
IdentityService | login | response | session.scope[].code | string |  | (nullable)
IdentityService | login | response | session.scope[].name | string |  | (nullable)
IdentityService | login | response | session.effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | login | response | session.permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path.
IdentityService | login | response | session.permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | login | response | session.permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | login | response | session.saleBoardId | string (uuid) | yes | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | login | response | session.workstation | WorkstationContext
IdentityService | login | response | session.workstation.id | string (uuid) | yes
IdentityService | login | response | session.workstation.code | string | yes
IdentityService | login | response | session.workstation.venueId | string (uuid) | yes
IdentityService | login | response | session.workstation.regionId | string (uuid) | yes
IdentityService | login | response | session.workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | login | response | session.workstation.devices | array of object
IdentityService | login | response | session.workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | login | response | session.workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | login | response | session.workstation.timezone | string
IdentityService | login | response | session.workstation.cellName | string |  | The cell serving this workstation's region.
IdentityService | login | response | session.workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | login | response | session.openedAt | string (date-time)
IdentityService | login | response | session.expiresAt | string (date-time)
IdentityService | login | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | lookupMerchandise | response | merchandiseId | string (uuid) | yes
RetailService | lookupMerchandise | response | outletId | string (uuid) |  | The outlet whose price and stock this is: the asking workstation's outlet, or outletId for a caller with none (decided 28 September, audit R215).
RetailService | lookupMerchandise | response | sku | string
RetailService | lookupMerchandise | response | name | string | yes
RetailService | lookupMerchandise | response | listPrice | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | lookupMerchandise | response | listPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupMerchandise | response | listPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupMerchandise | response | listPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupMerchandise | response | effectivePrice | object | yes | After any live promotion.
RetailService | lookupMerchandise | response | effectivePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupMerchandise | response | effectivePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupMerchandise | response | effectivePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupMerchandise | response | appliedPromotionCode | string |  | (nullable)
RetailService | lookupMerchandise | response | onHand | number | yes
RetailService | lookupMerchandise | response | isAvailable | boolean
RetailService | lookupMerchandise | response | siblingOutlets | array of object |  | Stock elsewhere in the venue, so a colleague can be sent.
RetailService | lookupMerchandise | response | siblingOutlets[].outletId | string (uuid)
RetailService | lookupMerchandise | response | siblingOutlets[].outletName | string
RetailService | lookupMerchandise | response | siblingOutlets[].onHand | number
RetailService | lookupMerchandise | param (query) | barcode | string |  | Exact match on barcode, within the venue.
RetailService | lookupMerchandise | param (query) | sku | string |  | Exact match on sku, within the venue.
RetailService | lookupMerchandise | param (query) | includeSiblingOutlets | boolean |  | False leaves siblingOutlets empty.
RetailService | lookupMerchandise | param (query) | outletId | string (uuid) |  | The outlet to price and count at, for a caller with no workstation (audit R215).
RetailService | lookupRetailSale | response | items | array of RetailSale | yes
RetailService | lookupRetailSale | response | items[].id | string | yes
RetailService | lookupRetailSale | response | items[].receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | lookupRetailSale | response | items[].orderId | string | yes | The order in the Order & Payment context.
RetailService | lookupRetailSale | response | items[].outletId | string (uuid) | yes
RetailService | lookupRetailSale | response | items[].shiftId | string |  | (nullable)
RetailService | lookupRetailSale | response | items[].subjectId | string (uuid) |  | (nullable)
RetailService | lookupRetailSale | response | items[].lines | array of object | yes
RetailService | lookupRetailSale | response | items[].lines[].lineId | string
RetailService | lookupRetailSale | response | items[].lines[].merchandiseId | string (uuid)
RetailService | lookupRetailSale | response | items[].lines[].name | string
RetailService | lookupRetailSale | response | items[].lines[].quantity | integer
RetailService | lookupRetailSale | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].serialNumbers | array of string
RetailService | lookupRetailSale | response | items[].lines[].returnedQuantity | integer
RetailService | lookupRetailSale | response | items[].lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | lookupRetailSale | response | items[].lines[].notReturnableReason | string |  | (nullable)
RetailService | lookupRetailSale | response | items[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].reprintCount | integer
RetailService | lookupRetailSale | response | items[].createdAt | string (date-time) | yes
RetailService | lookupRetailSale | response | items[].recordedAt | string (date-time)
RetailService | lookupRetailSale | response | nextCursor | string
RetailService | lookupRetailSale | response | hasMore | boolean | yes
RetailService | lookupRetailSale | response | matchedBy | enum (receiptBarcode, receiptNumber, orderNumber) | yes | The identifier used, by the precedence above (audit R215).
RetailService | lookupRetailSale | param (query) | receiptNumber | string |  | Exact match on receiptNumber.
RetailService | lookupRetailSale | param (query) | orderNumber | string |  | Exact match on the order number of the order in the Order & Payment context.
RetailService | lookupRetailSale | param (query) | receiptBarcode | string |  | Exact match on the barcode printed on the receipt.
RetailService | lookupRetailSale | param (query) | pageSize | integer
RetailService | lookupRetailSale | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | lookupShopAndDrop | param (query) | entitlementId | string |  | Exact match on the ticket scanned at the collection point.
RetailService | lookupShopAndDrop | param (query) | dropReference | string |  | Exact match on dropReference, as printed on the slip.
RetailService | lookupShopAndDrop | param (query) | receiptNumber | string |  | Exact match on the receipt number of the sale the goods came from.
MarketingService | markMyNotificationsRead | request | ids | array of string |  | (max items 200)
MarketingService | markMyNotificationsRead | request | all | boolean |  | (default False)
MarketingService | markMyNotificationsRead | response | unreadCount | integer | yes | (min 0)
MarketingService | markMyNotificationsRead | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | markOrderCollected | request | verifiedBy | enum (buzzer, orderNumber, name, qr, none)
FnbService | markOrderCollected | request | recordedAt | string (date-time) | yes | Device time of the collection.
FnbService | markOrderCollected | response | id | string (uuid) | yes
FnbService | markOrderCollected | response | orderNumber | string | yes
FnbService | markOrderCollected | response | outletId | string (uuid) | yes
FnbService | markOrderCollected | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | markOrderCollected | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | markOrderCollected | response | lines | array of object | yes
FnbService | markOrderCollected | response | lines[].id | string (uuid) | yes
FnbService | markOrderCollected | response | lines[].menuItemId | string (uuid) | yes
FnbService | markOrderCollected | response | lines[].quantity | integer | yes | (min 1)
FnbService | markOrderCollected | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | markOrderCollected | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | markOrderCollected | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | markOrderCollected | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | markOrderCollected | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | markOrderCollected | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | markOrderCollected | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | markOrderCollected | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | markOrderCollected | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | markOrderCollected | response | kitchenTickets[].id | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | markOrderCollected | response | kitchenTickets[].orderNumber | string
FnbService | markOrderCollected | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | markOrderCollected | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | markOrderCollected | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | markOrderCollected | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines | array of object | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].name | string | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | markOrderCollected | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | markOrderCollected | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | markOrderCollected | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].elapsedSeconds | integer
FnbService | markOrderCollected | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | response | createdAt | string (date-time) | yes
FnbService | markOrderCollected | response | recordedAt | string (date-time)
FnbService | markOrderCollected | response | syncedAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | param (path) | orderId | string (uuid) | yes | The F&B order (FnbOrder.id), which is what this closes — not a sales order.
FnbService | markOrderCollected | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | mergeTableVisits | request | sourceVisitId | string (uuid) | yes
FnbService | mergeTableVisits | response | id | string (uuid) | yes
FnbService | mergeTableVisits | response | tableId | string (uuid) | yes
FnbService | mergeTableVisits | response | tableLabel | string
FnbService | mergeTableVisits | response | outletId | string (uuid) | yes
FnbService | mergeTableVisits | response | covers | integer | yes
FnbService | mergeTableVisits | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | mergeTableVisits | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | mergeTableVisits | response | subjectId | string (uuid) |  | (nullable)
FnbService | mergeTableVisits | response | orders | array of FnbOrder | yes
FnbService | mergeTableVisits | response | orders[].id | string (uuid) | yes
FnbService | mergeTableVisits | response | orders[].orderNumber | string | yes
FnbService | mergeTableVisits | response | orders[].outletId | string (uuid) | yes
FnbService | mergeTableVisits | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | mergeTableVisits | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | mergeTableVisits | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | mergeTableVisits | response | orders[].lines | array of object | yes
FnbService | mergeTableVisits | response | orders[].lines[].id | string (uuid) | yes
FnbService | mergeTableVisits | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | mergeTableVisits | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | mergeTableVisits | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | mergeTableVisits | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | mergeTableVisits | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | mergeTableVisits | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | mergeTableVisits | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | mergeTableVisits | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | mergeTableVisits | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | mergeTableVisits | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | mergeTableVisits | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | mergeTableVisits | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | mergeTableVisits | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | mergeTableVisits | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | mergeTableVisits | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | mergeTableVisits | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | mergeTableVisits | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | mergeTableVisits | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | mergeTableVisits | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | mergeTableVisits | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | mergeTableVisits | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].orderNumber | string
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | mergeTableVisits | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | mergeTableVisits | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | mergeTableVisits | response | orders[].createdAt | string (date-time) | yes
FnbService | mergeTableVisits | response | orders[].recordedAt | string (date-time)
FnbService | mergeTableVisits | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | mergeTableVisits | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | mergeTableVisits | response | mergedFromVisitIds | array of string (uuid)
FnbService | mergeTableVisits | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | mergeTableVisits | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | mergeTableVisits | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | mergeTableVisits | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | mergeTableVisits | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | mergeTableVisits | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | mergeTableVisits | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | mergeTableVisits | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | mergeTableVisits | response | openedAt | string (date-time) | yes
FnbService | mergeTableVisits | response | closedAt | string (date-time) |  | (nullable)
FnbService | mergeTableVisits | param (path) | visitId | string (uuid) | yes
FnbService | mergeTableVisits | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | modifyOrder | request | id | string (uuid) | yes | Client-generated UUIDv7 of this modification, not of the order — the order is the path's orderId.
OrderService | modifyOrder | request | addLines | array of CreateOrderLine
OrderService | modifyOrder | request | addLines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | modifyOrder | request | addLines[].variantId | string (uuid) | yes
OrderService | modifyOrder | request | addLines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | modifyOrder | request | addLines[].performanceId | string (uuid)
OrderService | modifyOrder | request | addLines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | modifyOrder | request | addLines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | modifyOrder | request | addLines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | modifyOrder | request | addLines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | modifyOrder | request | addLines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | modifyOrder | request | addLines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | modifyOrder | request | addLines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | modifyOrder | request | addLines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | modifyOrder | request | addLines[].quantity | integer | yes | (min 1)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | modifyOrder | request | addLines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | request | addLines[].holderName | string |  | (nullable)
OrderService | modifyOrder | request | addLines[].dataMaskValues | object |  | Deliberately open.
OrderService | modifyOrder | request | removeLineIds | array of string (uuid)
OrderService | modifyOrder | request | reason | string |  | (max length 500)
OrderService | modifyOrder | request | recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order | Order | yes
OrderService | modifyOrder | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | modifyOrder | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | modifyOrder | response | order.channel | object | yes | Where it came from.
OrderService | modifyOrder | response | order.venueId | string (uuid) | yes
OrderService | modifyOrder | response | order.scopePath | string | yes
OrderService | modifyOrder | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | modifyOrder | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | modifyOrder | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | modifyOrder | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | modifyOrder | response | order.droppedPromotions[].name | string
OrderService | modifyOrder | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | modifyOrder | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | modifyOrder | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.lines | array of OrderLine | yes
OrderService | modifyOrder | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | modifyOrder | response | order.lines[].variantId | string (uuid) | yes
OrderService | modifyOrder | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | modifyOrder | response | order.lines[].performanceId | string (uuid)
OrderService | modifyOrder | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | modifyOrder | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | modifyOrder | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | modifyOrder | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | modifyOrder | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | modifyOrder | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | modifyOrder | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | modifyOrder | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | modifyOrder | response | order.lines[].holderName | string |  | (nullable)
OrderService | modifyOrder | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | modifyOrder | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | modifyOrder | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | modifyOrder | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | modifyOrder | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | modifyOrder | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | modifyOrder | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | modifyOrder | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | modifyOrder | response | order.payments | array of Payment
OrderService | modifyOrder | response | order.payments[].id | string (uuid) | yes
OrderService | modifyOrder | response | order.payments[].orderId | string (uuid) | yes
OrderService | modifyOrder | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | modifyOrder | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | modifyOrder | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | modifyOrder | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | modifyOrder | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | modifyOrder | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | modifyOrder | response | order.payments[].providerName | string |  | (nullable)
OrderService | modifyOrder | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | modifyOrder | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | modifyOrder | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | modifyOrder | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | modifyOrder | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | modifyOrder | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | modifyOrder | response | order.principalId | string (uuid)
OrderService | modifyOrder | response | order.workstationId | string (uuid)
OrderService | modifyOrder | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | modifyOrder | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | modifyOrder | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | modifyOrder | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | modifyOrder | response | order.createdAt | string (date-time) | yes
OrderService | modifyOrder | response | order.recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | modifyOrder | response | addedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | addedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | addedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | addedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | removedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | removedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | removedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | removedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | balanceDue | object | yes | Positive means the guest pays; negative means a refund is due.
OrderService | modifyOrder | response | balanceDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | balanceDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | balanceDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | refundId | string (uuid) |  | (nullable)
OrderService | modifyOrder | response | revokedEntitlementIds | array of string (uuid)
OrderService | modifyOrder | response | issuedEntitlementIds | array of string (uuid)
OrderService | modifyOrder | param (path) | orderId | string (uuid) | yes
OrderService | modifyOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | moveTableVisit | request | toTableId | string (uuid) | yes
FnbService | moveTableVisit | request | reason | enum (guestRequest, tableFault, partySizeChange, serviceRecovery, other) |  | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | moveTableVisit | request | note | string |  | Free text. (max length 500; nullable)
FnbService | moveTableVisit | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | moveTableVisit | response | id | string (uuid) | yes
FnbService | moveTableVisit | response | tableId | string (uuid) | yes
FnbService | moveTableVisit | response | tableLabel | string
FnbService | moveTableVisit | response | outletId | string (uuid) | yes
FnbService | moveTableVisit | response | covers | integer | yes
FnbService | moveTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | moveTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | moveTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | moveTableVisit | response | orders | array of FnbOrder | yes
FnbService | moveTableVisit | response | orders[].id | string (uuid) | yes
FnbService | moveTableVisit | response | orders[].orderNumber | string | yes
FnbService | moveTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | moveTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | moveTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | moveTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | moveTableVisit | response | orders[].lines | array of object | yes
FnbService | moveTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | moveTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | moveTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | moveTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | moveTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | moveTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | moveTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | moveTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | moveTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | moveTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | moveTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | moveTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | moveTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | moveTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | moveTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | moveTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | moveTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | moveTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | moveTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | moveTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | moveTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | moveTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | moveTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | moveTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | moveTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | moveTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | moveTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | moveTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | moveTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | moveTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | moveTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | moveTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | moveTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | moveTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | moveTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | moveTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | moveTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | moveTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | moveTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | moveTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | moveTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | moveTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | moveTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | moveTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | moveTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | moveTableVisit | response | openedAt | string (date-time) | yes
FnbService | moveTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | moveTableVisit | param (path) | visitId | string (uuid) | yes
FnbService | moveTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | notifyServer | request | reason | enum (foodReady, guestWaiting, billRequested, assistanceNeeded, allergyQuery)
FnbService | notifyServer | param (path) | visitId | string (uuid) | yes
FnbService | notifyServer | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | openPlatformStaffGrant | request | id | string (uuid) | yes | Client-generated UUIDv7 for the grant.
IdentityService | openPlatformStaffGrant | request | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | What the operator may do in this tenant while the grant is open. (min items 1)
IdentityService | openPlatformStaffGrant | request | reason | string | yes | (min length 3; max length 500)
IdentityService | openPlatformStaffGrant | request | ticketRef | string |  | The support case this access serves, where there is one. (max length 100; nullable)
IdentityService | openPlatformStaffGrant | request | expiresAt | string (date-time) | yes | At most 8 hours after opening (proposed, client to correct).
IdentityService | openPlatformStaffGrant | response | id | string (uuid) | yes
IdentityService | openPlatformStaffGrant | response | operatorPrincipalId | string (uuid) | yes | The platform operator, from the Control Plane token. (read-only)
IdentityService | openPlatformStaffGrant | response | operatorDisplayName | string |  | (read-only)
IdentityService | openPlatformStaffGrant | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | openPlatformStaffGrant | response | reason | string | yes
IdentityService | openPlatformStaffGrant | response | ticketRef | string |  | (nullable)
IdentityService | openPlatformStaffGrant | response | openedAt | string (date-time) | yes | (read-only)
IdentityService | openPlatformStaffGrant | response | expiresAt | string (date-time) | yes
IdentityService | openPlatformStaffGrant | response | scopePath | string |  | The tenant root. (read-only)
IdentityService | openPlatformStaffGrant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | openShift | request | workstationId | string (uuid) | yes
OrderService | openShift | request | openingFloat | array of CashCountLine | yes | A count is a list of lines and the line is the row. (min items 1)
OrderService | openShift | request | openingFloat[].id | string (uuid)
OrderService | openShift | request | openingFloat[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | openShift | request | openingFloat[].depositBoxId | string (uuid) |  | (nullable)
OrderService | openShift | request | openingFloat[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | openShift | request | openingFloat[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | openShift | request | openingFloat[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | openShift | request | openingFloat[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | openShift | request | openingFloat[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | request | openingFloat[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | request | openingFloat[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | request | openingFloat[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | request | openingFloat[].countedBy | string (uuid) |  | (nullable)
OrderService | openShift | request | openingFloat[].countedAt | string (date-time)
OrderService | openShift | request | openingFloat[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | openShift | request | depositBoxCode | string |  | Physical container assigned to this shift. (max length 64)
OrderService | openShift | request | bagNumber | string |  | Required where the venue configures bag numbers as mandatory. (max length 64)
OrderService | openShift | request | recordedAt | string (date-time) |  | When the device recorded it.
OrderService | openShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | openShift | response | workstationId | string (uuid) | yes
OrderService | openShift | response | venueId | string (uuid) | yes
OrderService | openShift | response | scopePath | string | yes
OrderService | openShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | openShift | response | principalDisplayName | string
OrderService | openShift | response | incidents | array of object |  | BL-097.
OrderService | openShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | openShift | response | incidents[].at | string (date-time)
OrderService | openShift | response | incidents[].principalId | string (uuid)
OrderService | openShift | response | incidents[].note | string |  | (nullable)
OrderService | openShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | openShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | openShift | response | depositBoxCode | string |  | (nullable)
OrderService | openShift | response | bagNumber | string |  | (nullable)
OrderService | openShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | openShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | openShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | openShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | openShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | openShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | openShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | openShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | openShift | response | openedAt | string (date-time) | yes
OrderService | openShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | openShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | openShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | openShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | openShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | openShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | openShift | response | approvals | array of object
OrderService | openShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | openShift | response | approvals[].principalId | string (uuid) | yes
OrderService | openShift | response | approvals[].at | string (date-time) | yes
OrderService | openShift | response | approvals[].reason | string
OrderService | openShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | openTableVisit | request | id | string (uuid) | yes
FnbService | openTableVisit | request | tableId | string (uuid) | yes
FnbService | openTableVisit | request | covers | integer | yes | Captured at seating because it drives split-by-covers at close. (min 1)
FnbService | openTableVisit | request | serverPrincipalId | string (uuid)
FnbService | openTableVisit | request | subjectId | string (uuid)
FnbService | openTableVisit | request | recordedAt | string (date-time) | yes
FnbService | openTableVisit | response | id | string (uuid) | yes
FnbService | openTableVisit | response | tableId | string (uuid) | yes
FnbService | openTableVisit | response | tableLabel | string
FnbService | openTableVisit | response | outletId | string (uuid) | yes
FnbService | openTableVisit | response | covers | integer | yes
FnbService | openTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | openTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders | array of FnbOrder | yes
FnbService | openTableVisit | response | orders[].id | string (uuid) | yes
FnbService | openTableVisit | response | orders[].orderNumber | string | yes
FnbService | openTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | openTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | openTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | openTableVisit | response | orders[].lines | array of object | yes
FnbService | openTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | openTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | openTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | openTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | openTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | openTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | openTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | openTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | openTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | openTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | openTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | openTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | openTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | openTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | openTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | openTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | openTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | openTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | openTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | openTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | openTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | openTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | openTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | openTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | openTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | openTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | openTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | openTableVisit | response | openedAt | string (date-time) | yes
FnbService | openTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | openTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | payByLink | request | providerToken | string (password) | yes
OrderService | payByLink | request | email | string (email) |  | Optional, and only to send the ticket. (nullable)
OrderService | payByLink | response | orderId | string (uuid)
OrderService | payByLink | response | entitlementIds | array of string (uuid)
OrderService | payByLink | param (path) | token | string | yes
OrderService | payByLink | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | printOrderLabel | response | ticketId | string (uuid) | yes
FnbService | printOrderLabel | response | orderNumber | string | yes
FnbService | printOrderLabel | response | guestName | string |  | (nullable)
FnbService | printOrderLabel | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | printOrderLabel | response | deliveryLabel | string |  | Where it is going, as a runner would read it. (nullable)
FnbService | printOrderLabel | response | buzzerCode | string |  | (nullable)
FnbService | printOrderLabel | response | lines | array of object | yes
FnbService | printOrderLabel | response | lines[].name | string | yes
FnbService | printOrderLabel | response | lines[].quantity | integer | yes
FnbService | printOrderLabel | response | lines[].modifiers | array of string
FnbService | printOrderLabel | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | printOrderLabel | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) | yes | Every allergen on the order, together.
FnbService | printOrderLabel | param (path) | ticketId | string (uuid) | yes
FnbService | printOrderLabel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | prioritiseKitchenTicket | request | reason | string | yes | (min length 3; max length 500)
FnbService | prioritiseKitchenTicket | request | priority | integer |  | Absent means the top of the queue (decided 28 September, audit R125 (2)): the ticket takes the highest priority on the rail. (min 0; max 100; default 100)
FnbService | prioritiseKitchenTicket | response | id | string (uuid) | yes
FnbService | prioritiseKitchenTicket | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | prioritiseKitchenTicket | response | orderNumber | string
FnbService | prioritiseKitchenTicket | response | outletId | string (uuid) | yes
FnbService | prioritiseKitchenTicket | response | tableLabel | string |  | (nullable)
FnbService | prioritiseKitchenTicket | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | prioritiseKitchenTicket | response | coursing | object |  | BL-131. (nullable)
FnbService | prioritiseKitchenTicket | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | prioritiseKitchenTicket | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | prioritiseKitchenTicket | response | priority | integer |  | Higher fires sooner.
FnbService | prioritiseKitchenTicket | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | prioritiseKitchenTicket | response | prioritiseReason | string |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines | array of object | yes
FnbService | prioritiseKitchenTicket | response | lines[].lineId | string (uuid) | yes
FnbService | prioritiseKitchenTicket | response | lines[].name | string | yes
FnbService | prioritiseKitchenTicket | response | lines[].quantity | integer | yes
FnbService | prioritiseKitchenTicket | response | lines[].modifiers | array of string
FnbService | prioritiseKitchenTicket | response | lines[].note | string |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | prioritiseKitchenTicket | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | prioritiseKitchenTicket | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | prioritiseKitchenTicket | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | prioritiseKitchenTicket | response | lines[].course | integer |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | prioritiseKitchenTicket | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | prioritiseKitchenTicket | response | createdAt | string (date-time) | yes
FnbService | prioritiseKitchenTicket | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | prioritiseKitchenTicket | response | elapsedSeconds | integer
FnbService | prioritiseKitchenTicket | param (path) | ticketId | string (uuid) | yes
FnbService | prioritiseKitchenTicket | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | promoteAiRelease | request | toStage | enum (canary, production) |  | (nullable)
AiService | promoteAiRelease | request | canaryScope | object |  | (nullable)
AiService | promoteAiRelease | request | note | string |  | (max length 1000; nullable)
AiService | promoteAiRelease | response | id | string (uuid) |  | (read-only)
AiService | promoteAiRelease | response | capabilityKey | string | yes
AiService | promoteAiRelease | response | artefactKind | enum (model, prompt, routing, embedding, retrieval, rule) | yes
AiService | promoteAiRelease | response | candidateRef | string | yes
AiService | promoteAiRelease | response | currentRef | string |  | What production runs now: the rule, or the previously promoted artefact. (nullable)
AiService | promoteAiRelease | response | previousRef | string |  | (read-only; nullable)
AiService | promoteAiRelease | response | layer | enum (platform, tenant) | yes
AiService | promoteAiRelease | response | suggestionKind | object |  | Where the capability answers a requestSuggestion kind: promotion rewrites that kind's assignment in AiPolicy.suggestionProviders. (nullable)
AiService | promoteAiRelease | response | stage | enum (draft, offlineEval, shadow, canary, production, monitored, rolledBack, rejected) | yes | (read-only)
AiService | promoteAiRelease | response | shadowStartedAt | string (date-time) |  | (read-only; nullable)
AiService | promoteAiRelease | response | gatePassedAt | string (date-time) |  | When the shadow run passed its gate and promotionReady was raised. (read-only; nullable)
AiService | promoteAiRelease | response | canaryScope | object |  | Venues or share of traffic in canary. (nullable)
AiService | promoteAiRelease | response | promotedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | promoteAiRelease | response | promotedAt | string (date-time) |  | (read-only; nullable)
AiService | promoteAiRelease | response | rolledBackByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | promoteAiRelease | response | rolledBackAt | string (date-time) |  | (read-only; nullable)
AiService | promoteAiRelease | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | promoteAiRelease | param (path) | releaseId | string (uuid) | yes
AiService | promoteAiRelease | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | proposeGuidedChoice | request | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | request | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | proposeGuidedChoice | request | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | proposeGuidedChoice | request | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | proposeGuidedChoice | request | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | proposeGuidedChoice | request | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | proposeGuidedChoice | request | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | proposeGuidedChoice | request | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | proposeGuidedChoice | request | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | request | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | request | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | proposeGuidedChoice | request | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | request | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | proposeGuidedChoice | request | status | object | yes | (read-only)
WhiteLabelService | proposeGuidedChoice | request | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | proposeGuidedChoice | request | suggestionRef | string | yes | The id of the ai AiGuidedChoiceSuggestion that produced the proposal (suggestGuidedChoice); ai getGuidedChoiceSuggestion reads it back.
WhiteLabelService | proposeGuidedChoice | request | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | request | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | proposeGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | proposeGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | proposeGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | proposeGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | proposeGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | proposeGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | proposeGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | proposeGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | proposeGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | proposeGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | proposeGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | proposeGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | proposeGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | proposeGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | proposeGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | proposeGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | proposeMarketingContent | request | targetKind | enum (messageTemplate, subjectLine, notificationWording, contentBlock, contentPage, banner, promoBlock, homepageSection) | yes
AiService | proposeMarketingContent | request | targetRef | string |  | The template, campaign, block, page, banner or promo block the draft is for. (nullable)
AiService | proposeMarketingContent | request | channel | enum (email, sms, push, whatsapp, inApp, web, app) |  | Sets the length and form limits (an SMS segment, a push title) the draft must meet. (nullable)
AiService | proposeMarketingContent | request | brief | string | yes | What the content is for, in the author's words. (min length 10; max length 4000)
AiService | proposeMarketingContent | request | objective | enum (awareness, conversion, retention, reactivation, information) |  | (nullable)
AiService | proposeMarketingContent | request | tone | string |  | (max length 200; nullable)
AiService | proposeMarketingContent | request | locales | array of string | yes | (min items 1; max items 10)
AiService | proposeMarketingContent | request | variants | integer |  | (min 1; max 5; default 1)
AiService | proposeMarketingContent | request | glossaryRef | string |  | Terms that must not be changed or translated, as for proposeTranslations. (nullable)
AiService | proposeMarketingContent | request | groundingRefs | array of string |  | Products, events, offers or pages the text may cite, read as the caller. (max items 50)
AiService | proposeMarketingContent | response | targetKind | enum (messageTemplate, subjectLine, notificationWording, contentBlock, contentPage, banner, promoBlock, homepageSection) | yes
AiService | proposeMarketingContent | response | targetRef | string |  | (nullable)
AiService | proposeMarketingContent | response | drafts | array of object | yes
AiService | proposeMarketingContent | response | drafts[].proposedActionId | string (uuid) | yes | The ai.proposed_action row; decideProposedAction takes it.
AiService | proposeMarketingContent | response | drafts[].locale | string | yes
AiService | proposeMarketingContent | response | drafts[].variantNumber | integer | yes | (min 1; max 5)
AiService | proposeMarketingContent | response | drafts[].targetContract | string |  | marketing-crm or white-label.
AiService | proposeMarketingContent | response | drafts[].targetOperation | string |  | The owner's save operation the draft is shaped for.
AiService | proposeMarketingContent | response | drafts[].fields | object | yes | The drafted text by field, e.g.
AiService | proposeMarketingContent | response | drafts[].glossaryViolations | array of string |  | Glossary terms the draft changed.
AiService | proposeMarketingContent | response | drafts[].decisionRecordId | string (uuid)
AiService | proposeMarketingContent | response | traceId | string
AiService | proposeMarketingContent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | proposeTranslations | request | targetLocale | string | yes
AiService | proposeTranslations | request | scope | enum (allGaps, contentBlocks, productNames, emailTemplates, messageTemplates) |  | messageTemplates (29 September, build; 22.9.18) covers every channel of a marketing-crm message template: email, SMS, push, WhatsApp and in-app.
AiService | proposeTranslations | request | glossaryRef | string |  | Terms that must not be translated — a venue's ride names, its brand, its membership tiers. (nullable)
AiService | proposeTranslations | response | targetLocale | string | yes
AiService | proposeTranslations | response | drafts | array of object | yes
AiService | proposeTranslations | response | drafts[].targetKind | enum (contentBlock, productName, emailTemplate, messageTemplate) | yes
AiService | proposeTranslations | response | drafts[].targetRef | string | yes | The id of the block, product or template the draft sits on.
AiService | proposeTranslations | response | drafts[].draftText | string | yes | The first-pass translation, as saved on the draft.
AiService | proposeTranslations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | proposeVenueLabels | param (path) | mapId | string (uuid) | yes
AiService | proposeVenueLabels | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | publishAiGovernancePolicy | response | id | string (uuid) |  | (read-only)
AiService | publishAiGovernancePolicy | response | policyId | string (uuid) | yes
AiService | publishAiGovernancePolicy | response | version | integer | yes | (min 1)
AiService | publishAiGovernancePolicy | response | status | enum (draft, simulated, published, superseded) | yes
AiService | publishAiGovernancePolicy | response | rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | publishAiGovernancePolicy | response | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | publishAiGovernancePolicy | response | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | publishAiGovernancePolicy | response | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | publishAiGovernancePolicy | response | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | publishAiGovernancePolicy | response | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | publishAiGovernancePolicy | response | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | publishAiGovernancePolicy | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | publishAiGovernancePolicy | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | publishAiGovernancePolicy | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | publishAiGovernancePolicy | response | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | publishAiGovernancePolicy | response | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | publishAiGovernancePolicy | response | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | publishAiGovernancePolicy | response | changeNote | string |  | (nullable)
AiService | publishAiGovernancePolicy | response | simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | publishAiGovernancePolicy | response | draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | publishAiGovernancePolicy | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | publishAiGovernancePolicy | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | publishAiGovernancePolicy | response | supersededAt | string (date-time) |  | (read-only; nullable)
AiService | publishAiGovernancePolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | publishAiGovernancePolicy | param (path) | versionId | string (uuid) | yes
AiService | publishAiGovernancePolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | publishBundle | request | venueId | string (uuid) | yes
CatalogueService | publishBundle | request | note | string |  | (max length 500)
CatalogueService | publishBundle | request | staleAfterHours | integer |  | How long a terminal may trade on this bundle before refusing. (min 1)
CatalogueService | publishBundle | response | version | string | yes
CatalogueService | publishBundle | response | venueId | string (uuid) | yes
CatalogueService | publishBundle | response | publishedAt | string (date-time) | yes
CatalogueService | publishBundle | response | publishedBy | string (uuid) | yes
CatalogueService | publishBundle | response | contentHash | string | yes
CatalogueService | publishBundle | response | signatureKeyId | string |  | Key that signed this bundle.
CatalogueService | publishBundle | response | staleAfter | string (date-time) | yes
CatalogueService | publishBundle | response | sizeBytes | integer | yes
CatalogueService | publishBundle | response | note | string
CatalogueService | publishBundle | response | appliedByWorkstations | integer
CatalogueService | publishBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | publishContentBlock | request | publishAt | string (date-time) |  | (nullable)
WhiteLabelService | publishContentBlock | request | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | publishContentBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | publishContentBlock | response | pageId | string (uuid) |  | (nullable)
WhiteLabelService | publishContentBlock | response | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | publishContentBlock | response | position | integer
WhiteLabelService | publishContentBlock | response | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | publishContentBlock | response | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | publishContentBlock | response | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | publishContentBlock | response | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | publishContentBlock | response | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | publishContentBlock | response | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | publishContentBlock | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | publishContentBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | publishContentBlock | param (path) | blockId | string (uuid) | yes
WhiteLabelService | publishContentBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | publishForecastVersion | request | note | string |  | (max length 1000; nullable)
AiService | publishForecastVersion | response | id | string (uuid) |  | (read-only)
AiService | publishForecastVersion | response | definitionId | string (uuid) | yes
AiService | publishForecastVersion | response | versionNumber | integer | yes | (min 1)
AiService | publishForecastVersion | response | status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | publishForecastVersion | response | basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | publishForecastVersion | response | maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | publishForecastVersion | response | maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | publishForecastVersion | response | maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | publishForecastVersion | response | maturity.sources | array of object
AiService | publishForecastVersion | response | maturity.sources[].source | enum (venueSettings, startingPattern, calendar, weather, bookingsOnHand, ownHistory, importedHistory, configuration, …) | yes
AiService | publishForecastVersion | response | maturity.sources[].detail | string |  | e.g. (nullable)
AiService | publishForecastVersion | response | maturity.sources[].observations | integer |  | (nullable)
AiService | publishForecastVersion | response | maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | publishForecastVersion | response | maturity.limitedHistory | boolean
AiService | publishForecastVersion | response | maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | publishForecastVersion | response | maturity.nextStage.stage | enum (learning, established, learned)
AiService | publishForecastVersion | response | maturity.nextStage.needs | string
AiService | publishForecastVersion | response | maturity.nextStage.expectedBy | string (date) |  | (nullable)
AiService | publishForecastVersion | response | producerRef | string
AiService | publishForecastVersion | response | modelVersion | string |  | (nullable)
AiService | publishForecastVersion | response | dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | publishForecastVersion | response | horizonStart | string (date-time)
AiService | publishForecastVersion | response | horizonEnd | string (date-time)
AiService | publishForecastVersion | response | qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | publishForecastVersion | response | publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | publishForecastVersion | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | publishForecastVersion | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | publishForecastVersion | response | createdAt | string (date-time) |  | (read-only)
AiService | publishForecastVersion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | publishForecastVersion | param (path) | versionId | string (uuid) | yes
AiService | publishForecastVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | publishGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | publishGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | publishGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | publishGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | publishGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | publishGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | publishGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | publishGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | publishGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | publishGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | publishGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | publishGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | publishGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | publishGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | publishGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | publishGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | publishGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | publishGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | publishGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | publishGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | publishGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | publishGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | publishPromotion | response | code | string | yes | (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | publishPromotion | response | name | string | yes | (max length 200)
CatalogueService | publishPromotion | response | description | string |  | (max length 1000)
CatalogueService | publishPromotion | response | venueId | string (uuid) | yes
CatalogueService | publishPromotion | response | discount | Discount | yes
CatalogueService | publishPromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | publishPromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | publishPromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | publishPromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | publishPromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | publishPromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | publishPromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | publishPromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | publishPromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | publishPromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | publishPromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | publishPromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | publishPromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.productKinds | array of string
CatalogueService | publishPromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | publishPromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | publishPromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | publishPromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | publishPromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | publishPromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | publishPromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | publishPromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | publishPromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | publishPromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | publishPromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | publishPromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | publishPromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | publishPromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | publishPromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | publishPromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | publishPromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | publishPromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | publishPromotion | response | validFrom | string (date-time) | yes
CatalogueService | publishPromotion | response | validTo | string (date-time)
CatalogueService | publishPromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | publishPromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | publishPromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | publishPromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | publishPromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | publishPromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | publishPromotion | response | id | string (uuid) | yes
CatalogueService | publishPromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | publishPromotion | response | isPaused | boolean
CatalogueService | publishPromotion | response | redemptionCount | integer
CatalogueService | publishPromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | publishPromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | publishPromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | publishPromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | publishPromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | publishPromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | publishPromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | publishPromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | publishPromptTemplate | request | layer | enum (platform, tenant) | yes
AiService | publishPromptTemplate | request | task | string | yes
AiService | publishPromptTemplate | request | body | string | yes
AiService | publishPromptTemplate | request | variables | array of string
AiService | publishPromptTemplate | request | outputSchema | object |  | (nullable)
AiService | publishPromptTemplate | response | id | string (uuid) |  | (read-only)
AiService | publishPromptTemplate | response | templateKey | string | yes
AiService | publishPromptTemplate | response | version | integer | yes | (min 1)
AiService | publishPromptTemplate | response | layer | enum (platform, tenant) | yes
AiService | publishPromptTemplate | response | task | string | yes | The gateway task it serves (design 3.3), e.g.
AiService | publishPromptTemplate | response | body | string |  | The template text.
AiService | publishPromptTemplate | response | variables | array of string
AiService | publishPromptTemplate | response | outputSchema | object |  | JSON Schema the structured output must satisfy, where the task has one. (nullable)
AiService | publishPromptTemplate | response | status | enum (draft, published, retired) | yes
AiService | publishPromptTemplate | response | contentHash | string |  | (read-only)
AiService | publishPromptTemplate | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | publishPromptTemplate | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | publishPromptTemplate | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | publishPromptTemplate | param (path) | templateKey | string | yes
AiService | publishPromptTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | publishTenantConfig | request | note | string | yes | (min length 3; max length 500)
WhiteLabelService | publishTenantConfig | request | scheduledFor | string (date-time) |  | Publish at a future time.
WhiteLabelService | publishTenantConfig | response | version | string | yes
WhiteLabelService | publishTenantConfig | response | publishedAt | string (date-time) | yes
WhiteLabelService | publishTenantConfig | response | publishedByPrincipalId | string (uuid) | yes
WhiteLabelService | publishTenantConfig | response | publishedByName | string
WhiteLabelService | publishTenantConfig | response | note | string | yes
WhiteLabelService | publishTenantConfig | response | isCurrent | boolean | yes
WhiteLabelService | publishTenantConfig | response | scheduledFor | string (date-time) |  | (nullable)
WhiteLabelService | publishTenantConfig | response | contentHash | string
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges | array of object |  | Changes in this version that will not reach guests until the next store release.
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges[].area | string
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges[].description | string
WhiteLabelService | publishTenantConfig | response | pendingBuildTimeChanges[].platforms | array of enum (ios, android, web)
WhiteLabelService | publishTenantConfig | response | snapshot | object |  | What this version contained. (read-only)
WhiteLabelService | publishTenantConfig | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | publishTenantConfig | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | publishTransportTimetable | response | name | string | yes | (max length 120)
VenueOpsService | publishTransportTimetable | response | validFrom | string (date) | yes
VenueOpsService | publishTransportTimetable | response | validTo | string (date) |  | (nullable)
VenueOpsService | publishTransportTimetable | response | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | publishTransportTimetable | response | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | publishTransportTimetable | response | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | publishTransportTimetable | response | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | publishTransportTimetable | response | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | publishTransportTimetable | response | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | publishTransportTimetable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | publishTransportTimetable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | publishTransportTimetable | response | status | TransportTimetableStatus: enum (draft, published, superseded, withdrawn) | yes
VenueOpsService | publishTransportTimetable | response | publishedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | publishTransportTimetable | response | releasedThrough | string (date) |  | The last date whose departures have been generated. (read-only; nullable)
VenueOpsService | publishTransportTimetable | response | supersededById | string (uuid) |  | (read-only; nullable)
VenueOpsService | publishTransportTimetable | param (path) | timetableId | string (uuid) | yes
VenueOpsService | publishTransportTimetable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | publishVenueMap | request | note | string |  | (max length 300)
VenueOpsService | publishVenueMap | response | id | string (uuid) | yes | (read-only)
VenueOpsService | publishVenueMap | response | name | string | yes
VenueOpsService | publishVenueMap | response | venueId | string (uuid) | yes
VenueOpsService | publishVenueMap | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | publishVenueMap | response | kind | enum (park, floor, zone, parking)
VenueOpsService | publishVenueMap | response | floorLevel | integer |  | (nullable)
VenueOpsService | publishVenueMap | response | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | publishVenueMap | response | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | publishVenueMap | response | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | publishVenueMap | response | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | publishVenueMap | response | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | publishVenueMap | response | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | publishVenueMap | response | baseImageAlignment.imageWidthPx | integer
VenueOpsService | publishVenueMap | response | baseImageAlignment.imageHeightPx | integer
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].planX | number
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].planY | number
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].imageX | number
VenueOpsService | publishVenueMap | response | baseImageAlignment.anchors[].imageY | number
VenueOpsService | publishVenueMap | response | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | publishVenueMap | response | boundsGeoJson | string |  | (nullable)
VenueOpsService | publishVenueMap | response | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | publishVenueMap | param (path) | mapId | string (uuid) | yes
VenueOpsService | publishVenueMap | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | publishWalletConfiguration | request | mode | enum (validateOnly, publish) |  | (default validateOnly)
WalletService | publishWalletConfiguration | request | note | string |  | (nullable)
WalletService | publishWalletConfiguration | response | version | integer
WalletService | publishWalletConfiguration | response | publishedAt | string (date-time) |  | (nullable)
WalletService | publishWalletConfiguration | response | publishedBy | string (uuid) |  | (nullable)
WalletService | publishWalletConfiguration | response | note | string |  | (nullable)
WalletService | publishWalletConfiguration | response | findings | array of object
WalletService | publishWalletConfiguration | response | findings[].severity | enum (blocking, warning)
WalletService | publishWalletConfiguration | response | findings[].code | string
WalletService | publishWalletConfiguration | response | findings[].message | string
WalletService | publishWalletConfiguration | response | scopePath | string
WalletService | publishWalletConfiguration | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | quoteTransportFare | request | routeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | passengers | array of object |  | Omitted, one of the default type. (max items 10)
VenueOpsService | quoteTransportFare | request | passengers[].code | string | yes
VenueOpsService | quoteTransportFare | request | passengers[].count | integer | yes | (min 0; max 99)
VenueOpsService | quoteTransportFare | request | passTypeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | request | at | string (date-time) |  | The sale instant the fare table is read at.
VenueOpsService | quoteTransportFare | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | response | stopsTravelled | integer | yes | (min 1)
VenueOpsService | quoteTransportFare | response | adultFare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | lines | array of object
VenueOpsService | quoteTransportFare | response | lines[].code | string | yes
VenueOpsService | quoteTransportFare | response | lines[].catalogueVariantId | string (uuid)
VenueOpsService | quoteTransportFare | response | lines[].count | integer | yes
VenueOpsService | quoteTransportFare | response | lines[].unitPrice | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | passTypeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | quoteTransportFare | response | saving | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | saving.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | saving.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | saving.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | quoteTransportFare | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | quoteTransportFare | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | quoteTransportFare | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | quoteTransportFare | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | raiseMyCase | request | id | string (uuid) | yes | Created on the device, so a retry after a dropped connection carries the same id and is the same case.
MarketingService | raiseMyCase | request | kind | CaseKind: enum (lostProperty, complaint, question, accessibility, refundRequest, other) | yes | What the guest says the case is about, in their words rather than the venue's taxonomy — raiseMyCase asks for it and categoryId is what staff file it under.
MarketingService | raiseMyCase | request | summary | string | yes | Lands in Case.subject — the case's one-line title. (max length 200)
MarketingService | raiseMyCase | request | recordedAt | string (date-time) | yes | Device time when the guest raised it.
MarketingService | raiseMyCase | request | detail | string |  | Required, and not empty, when kind is other (decided 28 September, audit R222); a 400 otherwise. (nullable)
MarketingService | raiseMyCase | request | venueId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | request | orderRef | string |  | (nullable)
MarketingService | raiseMyCase | response | id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | raiseMyCase | response | caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | raiseMyCase | response | subjectId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | raiseMyCase | response | subject | string | yes | The case's one-line title, not a person.
MarketingService | raiseMyCase | response | kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | raiseMyCase | response | channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | raiseMyCase | response | recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | raiseMyCase | response | syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | raiseMyCase | response | categoryId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | raiseMyCase | response | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | raiseMyCase | response | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | raiseMyCase | response | priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | raiseMyCase | response | assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | venueId | string (uuid) |  | (nullable)
MarketingService | raiseMyCase | response | relatedOrderId | string |  | (nullable)
MarketingService | raiseMyCase | response | slaDueAt | string (date-time) |  | (nullable)
MarketingService | raiseMyCase | response | isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | raiseMyCase | response | slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | raiseMyCase | response | escalationCount | integer
MarketingService | raiseMyCase | response | createdAt | string (date-time) | yes
MarketingService | raiseMyCase | response | resolvedAt | string (date-time) |  | (nullable)
MarketingService | raiseMyCase | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | reactivateTenant | response | id | string (uuid) | yes
PlatformService | reactivateTenant | response | code | string | yes
PlatformService | reactivateTenant | response | name | string | yes
PlatformService | reactivateTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | reactivateTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | reactivateTenant | response | suspensionReason | string |  | (nullable)
PlatformService | reactivateTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | reactivateTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | reactivateTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | reactivateTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | reactivateTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | reactivateTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | reactivateTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | reactivateTenant | response | planName | string |  | (nullable)
PlatformService | reactivateTenant | response | cellCount | integer
PlatformService | reactivateTenant | response | venueCount | integer
PlatformService | reactivateTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | reactivateTenant | response | billingEmail | string
PlatformService | reactivateTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | reactivateTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | reactivateTenant | response | createdAt | string (date-time) | yes
PlatformService | reactivateTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | reactivateTenant | param (path) | tenantId | string (uuid) | yes
PlatformService | reactivateTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | rebalanceStationLoad | request | moves | array of object | yes
FnbService | rebalanceStationLoad | request | moves[].fromStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | request | moves[].toStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | request | moves[].categoryIds | array of string (uuid)
FnbService | rebalanceStationLoad | request | revertAt | string (date-time) |  | (nullable)
FnbService | rebalanceStationLoad | response | moves | array of object | yes
FnbService | rebalanceStationLoad | response | moves[].fromStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | response | moves[].toStationId | string (uuid) | yes
FnbService | rebalanceStationLoad | response | moves[].categoryIds | array of string (uuid)
FnbService | rebalanceStationLoad | response | revertAt | string (date-time) |  | (nullable)
FnbService | rebalanceStationLoad | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | recallKitchenTicket | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | recallKitchenTicket | response | id | string (uuid) | yes
FnbService | recallKitchenTicket | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | recallKitchenTicket | response | orderNumber | string
FnbService | recallKitchenTicket | response | outletId | string (uuid) | yes
FnbService | recallKitchenTicket | response | tableLabel | string |  | (nullable)
FnbService | recallKitchenTicket | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | recallKitchenTicket | response | coursing | object |  | BL-131. (nullable)
FnbService | recallKitchenTicket | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | recallKitchenTicket | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | recallKitchenTicket | response | priority | integer |  | Higher fires sooner.
FnbService | recallKitchenTicket | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | recallKitchenTicket | response | prioritiseReason | string |  | (nullable)
FnbService | recallKitchenTicket | response | lines | array of object | yes
FnbService | recallKitchenTicket | response | lines[].lineId | string (uuid) | yes
FnbService | recallKitchenTicket | response | lines[].name | string | yes
FnbService | recallKitchenTicket | response | lines[].quantity | integer | yes
FnbService | recallKitchenTicket | response | lines[].modifiers | array of string
FnbService | recallKitchenTicket | response | lines[].note | string |  | (nullable)
FnbService | recallKitchenTicket | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | recallKitchenTicket | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | recallKitchenTicket | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | recallKitchenTicket | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | recallKitchenTicket | response | lines[].course | integer |  | (nullable)
FnbService | recallKitchenTicket | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | recallKitchenTicket | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | recallKitchenTicket | response | createdAt | string (date-time) | yes
FnbService | recallKitchenTicket | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | recallKitchenTicket | response | elapsedSeconds | integer
FnbService | recallKitchenTicket | param (path) | ticketId | string (uuid) | yes
FnbService | recallKitchenTicket | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | recommendSeats | request | partySize | integer | yes | (min 1; max 50)
CatalogueService | recommendSeats | request | strategy | SeatRecommendationStrategy: enum (bestAvailable, bestValue, closestToStage, accessible, contiguous) | yes
CatalogueService | recommendSeats | request | categoryIds | array of string (uuid)
CatalogueService | recommendSeats | request | maxPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | recommendSeats | request | maxPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | recommendSeats | request | maxPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | recommendSeats | request | maxPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | recommendSeats | request | accessibleCount | integer |  | Wheelchair spaces in the party. (default 0)
CatalogueService | recommendSeats | request | maxOptions | integer |  | (max 10; default 3)
CatalogueService | recommendSeats | response | options | array of SeatRecommendation | yes
CatalogueService | recommendSeats | response | options[].seatIds | array of string | yes
CatalogueService | recommendSeats | response | options[].displayLabels | array of string
CatalogueService | recommendSeats | response | options[].totalPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | recommendSeats | response | options[].totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | recommendSeats | response | options[].totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | recommendSeats | response | options[].totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | recommendSeats | response | options[].categoryId | string (uuid)
CatalogueService | recommendSeats | response | options[].isContiguous | boolean | yes
CatalogueService | recommendSeats | response | options[].rank | integer | yes | Best first.
CatalogueService | recommendSeats | response | options[].rationale | string |  | Why this option was chosen — closest to stage, best value in category, only contiguous block remaining.
CatalogueService | recommendSeats | param (path) | performanceId | string (uuid) | yes
CatalogueService | recommendSeats | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | recordAnswerFeedback | request | rating | enum (helpful, notHelpful) | yes
AiService | recordAnswerFeedback | request | reason | enum (wrong, outdated, incomplete, notGrounded, unsafe, other) |  | (nullable)
AiService | recordAnswerFeedback | request | comment | string |  | (max length 1000; nullable)
AiService | recordAnswerFeedback | response | id | string (uuid) |  | (read-only)
AiService | recordAnswerFeedback | response | messageId | string (uuid) | yes
AiService | recordAnswerFeedback | response | conversationId | string (uuid) |  | (nullable)
AiService | recordAnswerFeedback | response | rating | enum (helpful, notHelpful) | yes
AiService | recordAnswerFeedback | response | reason | enum (wrong, outdated, incomplete, notGrounded, unsafe, other) |  | (nullable)
AiService | recordAnswerFeedback | response | comment | string |  | (max length 1000; nullable)
AiService | recordAnswerFeedback | response | audience | enum (staff, guest) |  | (read-only)
AiService | recordAnswerFeedback | response | principalId | string (uuid) |  | (read-only; nullable)
AiService | recordAnswerFeedback | response | subjectId | string (uuid) |  | The guest, where the audience is guest. (read-only; nullable)
AiService | recordAnswerFeedback | response | createdAt | string (date-time) |  | (read-only)
AiService | recordAnswerFeedback | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | recordAnswerFeedback | param (path) | messageId | string (uuid) | yes
AiService | recordAnswerFeedback | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | recordConsent | request | purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | recordConsent | request | decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | recordConsent | request | channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) |  | Omit to apply to every channel the purpose covers.
MarketingService | recordConsent | request | noticeVersion | string | yes
MarketingService | recordConsent | request | source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordConsent | request | recordedAt | string (date-time) | yes
MarketingService | recordConsent | response | subjectId | string (uuid) | yes
MarketingService | recordConsent | response | purposes | array of object | yes
MarketingService | recordConsent | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | recordConsent | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | recordConsent | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | recordConsent | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | recordConsent | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | recordConsent | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | recordConsent | param (path) | subjectId | string (uuid) | yes
MarketingService | recordConsent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | recordConsentAnswers | request | cartId | string (uuid) | yes | The cart the answers are given for.
MarketingService | recordConsentAnswers | request | answers | array of object | yes | (min items 1; max items 200)
MarketingService | recordConsentAnswers | request | answers[].questionId | string (uuid) | yes
MarketingService | recordConsentAnswers | request | answers[].questionVersion | integer | yes | The version the guest was shown, from Cart.consentQuestions. (min 1)
MarketingService | recordConsentAnswers | request | answers[].answer | enum (yes, no) | yes
MarketingService | recordConsentAnswers | request | answers[].cartLineId | string (uuid) |  | For a perPerson question, the line the person is on. (nullable)
MarketingService | recordConsentAnswers | request | answers[].personIndex | integer |  | For a perPerson question, the person's row in that line's eligibilityDeclaration, counting from 0. (min 0; nullable)
MarketingService | recordConsentAnswers | request | answers[].personName | string |  | (max length 120; nullable)
MarketingService | recordConsentAnswers | request | answers[].personSubjectId | string (uuid) |  | Where the person is a known guest, such as the booker or a family member. (nullable)
MarketingService | recordConsentAnswers | request | source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordConsentAnswers | request | answeredAt | string (date-time) | yes
MarketingService | recordConsentAnswers | response | items | array of BookingConsentRecord | yes
MarketingService | recordConsentAnswers | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | recordConsentAnswers | response | items[].questionId | string (uuid) | yes
MarketingService | recordConsentAnswers | response | items[].questionVersion | integer | yes | (min 1)
MarketingService | recordConsentAnswers | response | items[].questionKind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | recordConsentAnswers | response | items[].answer | enum (yes, no) | yes
MarketingService | recordConsentAnswers | response | items[].scope | enum (perPerson, perBooking) | yes
MarketingService | recordConsentAnswers | response | items[].blocksBooking | boolean |  | The answer is the question's blockingAnswer at that version. (read-only)
MarketingService | recordConsentAnswers | response | items[].cartId | string (uuid) |  | (nullable)
MarketingService | recordConsentAnswers | response | items[].cartLineId | string (uuid) |  | (nullable)
MarketingService | recordConsentAnswers | response | items[].orderId | string (uuid) |  | Set by orders.checkoutCart when the cart becomes an order. (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].orderLineId | string (uuid) |  | (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].personIndex | integer |  | (min 0; nullable)
MarketingService | recordConsentAnswers | response | items[].personName | string |  | (max length 120; nullable)
MarketingService | recordConsentAnswers | response | items[].personSubjectId | string (uuid) |  | (nullable)
MarketingService | recordConsentAnswers | response | items[].answeredBySubjectId | string (uuid) |  | The guest who answered, from the session. (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].answeredByPrincipalId | string (uuid) |  | The staff member who answered on the guest's behalf. (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordConsentAnswers | response | items[].answeredAt | string (date-time) | yes
MarketingService | recordConsentAnswers | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
MarketingService | recordConsentAnswers | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | recordConsentAnswers | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | recordDashboardView | request | venueId | string (uuid) |  | The venue the dashboard was narrowed to when opened, as Dashboard.venueId. (nullable)
ReportingService | recordDashboardView | param (path) | dashboardId | string (uuid) | yes
ReportingService | recordDashboardView | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | recordDeviceConsent | request | consentKey | string |  | The key the browser or app already holds; omitted on a first decision, and one is minted. (max length 64; nullable)
MarketingService | recordDeviceConsent | request | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | recordDeviceConsent | request | brandId | string (uuid) |  | (nullable)
MarketingService | recordDeviceConsent | request | bannerDesignId | string (uuid) |  | (nullable)
MarketingService | recordDeviceConsent | request | action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | recordDeviceConsent | request | categories | array of object |  | Required for savePreferences; ignored for the other actions, which decide every category themselves.
MarketingService | recordDeviceConsent | request | categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | recordDeviceConsent | request | categories[].decision | enum (granted, declined) | yes
MarketingService | recordDeviceConsent | request | noticeVersion | string | yes
MarketingService | recordDeviceConsent | request | language | string |  | (max length 10; nullable)
MarketingService | recordDeviceConsent | request | globalPrivacyControl | boolean |  | (default False)
MarketingService | recordDeviceConsent | request | source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordDeviceConsent | request | decidedAt | string (date-time) | yes
MarketingService | recordDeviceConsent | response | id | string (uuid) |  | (read-only)
MarketingService | recordDeviceConsent | response | consentKey | string | yes | Opaque, minted by us, not a device fingerprint. (max length 64; read-only)
MarketingService | recordDeviceConsent | response | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | recordDeviceConsent | response | brandId | string (uuid) |  | (nullable)
MarketingService | recordDeviceConsent | response | bannerDesignId | string (uuid) |  | The published CookieBannerPreferenceCenterDesignerView version the visitor was shown. (nullable)
MarketingService | recordDeviceConsent | response | action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | recordDeviceConsent | response | categories | array of object | yes | Every category of the design, with the decision this row gives it. (min items 1)
MarketingService | recordDeviceConsent | response | categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | recordDeviceConsent | response | categories[].decision | enum (granted, declined) | yes
MarketingService | recordDeviceConsent | response | noticeVersion | string | yes | The cookie notice version decided against (white-label setPolicy, kind cookie).
MarketingService | recordDeviceConsent | response | language | string |  | (max length 10; nullable)
MarketingService | recordDeviceConsent | response | globalPrivacyControl | boolean |  | The browser sent a Global Privacy Control signal; honoured as a CCPA/CPRA opt-out of sale and sharing. (default False)
MarketingService | recordDeviceConsent | response | source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | recordDeviceConsent | response | country | string |  | The edge's geolocation of the request, for the geographic statistics (2.6.63). (pattern ^[A-Z]{2}$; read-only; nullable)
MarketingService | recordDeviceConsent | response | decidedAt | string (date-time) | yes
MarketingService | recordDeviceConsent | response | expiresAt | string (date-time) |  | A device consent expires and a subject consent does not. (read-only; nullable)
MarketingService | recordDeviceConsent | response | claimedBySubjectId | string (uuid) |  | Set once, by claimDeviceConsent. (read-only; nullable)
MarketingService | recordDeviceConsent | response | claimedAt | string (date-time) |  | (read-only; nullable)
MarketingService | recordDeviceConsent | response | scopePath | string |  | The partition key (ADR-0005), tenant-scoped: a decision with no subject still belongs to one tenant. (read-only)
MarketingService | recordDeviceConsent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | recordDeviceHeartbeat | request | status | enum (online, offline, error, consumableLow, needsAttention) | yes
TenancyService | recordDeviceHeartbeat | request | detail | string |  | (max length 500)
TenancyService | recordDeviceHeartbeat | request | firmwareVersion | string
TenancyService | recordDeviceHeartbeat | request | recordedAt | string (date-time) | yes
TenancyService | recordDeviceHeartbeat | param (path) | deviceId | string (uuid) | yes
TenancyService | recordDeviceHeartbeat | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | recordNoSale | request | id | string (uuid) | yes
OrderService | recordNoSale | request | reason | enum (changeForGuest, correctFloat, retrieveDroppedCash, tillCheck, other) | yes
OrderService | recordNoSale | request | note | string |  | (max length 300)
OrderService | recordNoSale | request | recordedAt | string (date-time) | yes
OrderService | recordNoSale | response | id | string (uuid) | yes
OrderService | recordNoSale | response | shiftId | string (uuid) | yes
OrderService | recordNoSale | response | workstationId | string (uuid)
OrderService | recordNoSale | response | reason | string | yes
OrderService | recordNoSale | response | note | string |  | (nullable)
OrderService | recordNoSale | response | principalId | string (uuid) | yes
OrderService | recordNoSale | response | recordedAt | string (date-time) | yes
OrderService | recordNoSale | response | countThisShift | integer |  | Running count.
OrderService | recordNoSale | param (path) | shiftId | string (uuid) | yes
OrderService | recordNoSale | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | recordOrderHandover | request | outcome | enum (served, collected, delivered, guestNotFound, refused) | yes | served, collected and delivered move the order to the FnbOrderStatus of the same name.
FnbService | recordOrderHandover | request | deliveredToLocationId | string (uuid) |  | Required where outcome is delivered (audit R125 (1)).
FnbService | recordOrderHandover | request | runnerPrincipalId | string (uuid)
FnbService | recordOrderHandover | request | note | string |  | Required for guestNotFound and refused. (max length 500)
FnbService | recordOrderHandover | request | recordedAt | string (date-time) | yes
FnbService | recordOrderHandover | response | orderId | string | yes
FnbService | recordOrderHandover | response | orderNumber | string
FnbService | recordOrderHandover | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | recordOrderHandover | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | recordOrderHandover | response | isReadyForCollection | boolean
FnbService | recordOrderHandover | response | lines | array of object | yes | Per-line status.
FnbService | recordOrderHandover | response | lines[].name | string
FnbService | recordOrderHandover | response | lines[].quantity | integer
FnbService | recordOrderHandover | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | recordOrderHandover | param (path) | orderId | string (uuid) | yes
FnbService | recordOrderHandover | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | recordRecommendationEvents | request | events | array of object | yes | (min items 1)
AiService | recordRecommendationEvents | request | events[].decisionId | string (uuid) |  | (nullable)
AiService | recordRecommendationEvents | request | events[].trackingId | string (uuid) | yes
AiService | recordRecommendationEvents | request | events[].eventType | enum (impression, click, addToCart, dismiss, decline) | yes
AiService | recordRecommendationEvents | request | events[].productId | string (uuid) |  | (nullable)
AiService | recordRecommendationEvents | request | events[].occurredAt | string (date-time) | yes
AiService | recordRecommendationEvents | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | recordStorefrontSessionEvents | request | batchId | string (uuid) | yes | UUIDv7 minted by the runtime; a retried beacon repeats it.
WhiteLabelService | recordStorefrontSessionEvents | request | sessionRef | string | yes | The runtime's own session id, SHA-256 hashed in the browser; hashed again with the tenant key on arrival and published as storefront.sessionEvent.sessionRef. (max length 128)
WhiteLabelService | recordStorefrontSessionEvents | request | deviceIdHash | string |  | (max length 128; nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | surface | enum (guestWeb, guestApp) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | venueId | string (uuid) |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | sessionStartedAt | string (date-time) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | interactions | array of object | yes | (min items 1; max items 50)
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].kind | enum (pageView, productView, seatMapOpened, addToCart, removeFromCart, checkoutStarted, paymentPageViewed, promoCodeTried, …) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].pageKind | enum (home, product, seatMap, cart, checkout, account, content, None) |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].productId | string (uuid) |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].at | string (date-time) | yes
WhiteLabelService | recordStorefrontSessionEvents | request | interactions[].dwellMs | integer |  | (min 0; nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints | object |  | (nullable)
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.webdriver | boolean
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.headless | boolean
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.pointerEvents | integer |  | (min 0)
WhiteLabelService | recordStorefrontSessionEvents | request | automationHints.interactionsPerMinute | number |  | (min 0)
WhiteLabelService | recordStorefrontSessionEvents | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | redeemLoyaltyPoints | request | subjectId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | request | programmeId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | request | points | integer | yes
MarketingService | redeemLoyaltyPoints | request | rewardId | string (uuid) |  | (nullable)
MarketingService | redeemLoyaltyPoints | request | orderId | string (uuid) |  | Where points are being used against a sale rather than for a catalogue reward. (nullable)
MarketingService | redeemLoyaltyPoints | response | leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | redeemLoyaltyPoints | response | subjectId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | response | programmeId | string (uuid) | yes
MarketingService | redeemLoyaltyPoints | response | pointsBalance | integer | yes
MarketingService | redeemLoyaltyPoints | response | lifetimePoints | integer
MarketingService | redeemLoyaltyPoints | response | tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | redeemLoyaltyPoints | response | tierCode | string | yes
MarketingService | redeemLoyaltyPoints | response | tierName | string
MarketingService | redeemLoyaltyPoints | response | pointsToNextTier | integer |  | (nullable)
MarketingService | redeemLoyaltyPoints | response | nextExpiryPoints | integer |  | (nullable)
MarketingService | redeemLoyaltyPoints | response | nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | redeemLoyaltyPoints | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | refireItem | request | lineId | string (uuid) | yes | KitchenTicket.lines[].lineId.
FnbService | refireItem | request | reason | RefireReason: enum (overcooked, undercooked, wrongItem, dropped, cold, allergyRisk, guestChangedMind, lateAdd) | yes | Why a line was made again (refireItem).
FnbService | refireItem | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | refireItem | request | chargeable | boolean |  | False by default, and that default is the point. (default False)
FnbService | refireItem | response | id | string (uuid) | yes
FnbService | refireItem | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | refireItem | response | orderNumber | string
FnbService | refireItem | response | outletId | string (uuid) | yes
FnbService | refireItem | response | tableLabel | string |  | (nullable)
FnbService | refireItem | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | refireItem | response | coursing | object |  | BL-131. (nullable)
FnbService | refireItem | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | refireItem | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | refireItem | response | priority | integer |  | Higher fires sooner.
FnbService | refireItem | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | refireItem | response | prioritiseReason | string |  | (nullable)
FnbService | refireItem | response | lines | array of object | yes
FnbService | refireItem | response | lines[].lineId | string (uuid) | yes
FnbService | refireItem | response | lines[].name | string | yes
FnbService | refireItem | response | lines[].quantity | integer | yes
FnbService | refireItem | response | lines[].modifiers | array of string
FnbService | refireItem | response | lines[].note | string |  | (nullable)
FnbService | refireItem | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | refireItem | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | refireItem | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | refireItem | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | refireItem | response | lines[].course | integer |  | (nullable)
FnbService | refireItem | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | refireItem | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | refireItem | response | createdAt | string (date-time) | yes
FnbService | refireItem | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | refireItem | response | elapsedSeconds | integer
FnbService | refireItem | param (path) | ticketId | string (uuid) | yes
FnbService | refireItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | refreshToken | request | refreshToken | string | yes
IdentityService | refreshToken | response | accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | refreshToken | response | refreshToken | string | yes
IdentityService | refreshToken | response | expiresIn | integer | yes | Seconds
IdentityService | refreshToken | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | registerDeveloper | request | id | string (uuid) | yes | (read-only)
PlatformService | registerDeveloper | request | organisationName | string | yes
PlatformService | registerDeveloper | request | contactEmail | string (email) | yes
PlatformService | registerDeveloper | request | websiteUrl | string |  | (nullable)
PlatformService | registerDeveloper | request | countryCode | string
PlatformService | registerDeveloper | request | partnerId | string (uuid) |  | Where this developer is also a commercial partner. (nullable)
PlatformService | registerDeveloper | request | status | enum (pending, verified, suspended, closed) | yes | (read-only)
PlatformService | registerDeveloper | request | verifiedAt | string (date-time) |  | (read-only; nullable)
PlatformService | registerDeveloper | response | id | string (uuid) | yes | (read-only)
PlatformService | registerDeveloper | response | organisationName | string | yes
PlatformService | registerDeveloper | response | contactEmail | string (email) | yes
PlatformService | registerDeveloper | response | websiteUrl | string |  | (nullable)
PlatformService | registerDeveloper | response | countryCode | string
PlatformService | registerDeveloper | response | partnerId | string (uuid) |  | Where this developer is also a commercial partner. (nullable)
PlatformService | registerDeveloper | response | status | enum (pending, verified, suspended, closed) | yes | (read-only)
PlatformService | registerDeveloper | response | verifiedAt | string (date-time) |  | (read-only; nullable)
PlatformService | registerDeveloper | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | registerGuest | request | identifier | string | yes | Email address or mobile number in E.164. (max length 256)
IdentityService | registerGuest | request | channel | enum (email, sms, whatsapp) | yes
IdentityService | registerGuest | request | displayName | string |  | (max length 200)
IdentityService | registerGuest | request | password | string |  | Optional. (min length 8; max length 256)
IdentityService | registerGuest | request | preferredLanguage | string |  | (pattern ^[a-z]{2}$)
IdentityService | registerGuest | request | consents | array of object |  | Consent captured at registration, recorded with the notice version.
IdentityService | registerGuest | request | consents[].purpose | string
IdentityService | registerGuest | request | consents[].granted | boolean
IdentityService | registerGuest | request | consents[].noticeVersion | string
IdentityService | registerGuest | response | subjectId | string (uuid) | yes
IdentityService | registerGuest | response | displayName | string |  | (nullable)
IdentityService | registerGuest | response | tokens | TokenPair | yes
IdentityService | registerGuest | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | registerGuest | response | tokens.refreshToken | string | yes
IdentityService | registerGuest | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | registerGuest | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | registerGuest | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | registerGuest | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | registerGuest | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | registerGuest | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | registerGuest | response | mfaMethods[].id | string (uuid) | yes
IdentityService | registerGuest | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | registerGuest | response | mfaMethods[].label | string |  | (nullable)
IdentityService | registerGuest | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | registerGuest | response | mfaMethods[].isActive | boolean | yes
IdentityService | registerGuest | response | mfaMethods[].isPrimary | boolean
IdentityService | registerGuest | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | registerGuest | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | registerGuest | response | homeCellName | string |  | (nullable)
IdentityService | registerGuest | response | preferredLanguage | string |  | (nullable)
IdentityService | registerGuest | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | registerGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | registerGuestDevice | request | platform | enum (ios, android, web) | yes
MarketingService | registerGuestDevice | request | token | string | yes | (max length 512)
MarketingService | registerGuestDevice | request | appVersion | string
MarketingService | registerGuestDevice | request | osVersion | string
MarketingService | registerGuestDevice | request | deviceModel | string
MarketingService | registerGuestDevice | request | locale | string
MarketingService | registerGuestDevice | response | id | string (uuid) | yes
MarketingService | registerGuestDevice | response | subjectId | string (uuid) | yes
MarketingService | registerGuestDevice | response | platform | enum (ios, android, web) | yes
MarketingService | registerGuestDevice | response | tokenFingerprint | string |  | Hash of the token, not the token.
MarketingService | registerGuestDevice | response | tokenRef | string |  | A vault reference to the push token, written by the server from registerGuestDevice.token — the same pattern as PaymentProvider.credentialRef.
MarketingService | registerGuestDevice | response | appVersion | string |  | (nullable)
MarketingService | registerGuestDevice | response | osVersion | string |  | (nullable)
MarketingService | registerGuestDevice | response | deviceModel | string |  | (nullable)
MarketingService | registerGuestDevice | response | locale | string |  | (nullable)
MarketingService | registerGuestDevice | response | status | enum (active, revoked, failed) | yes
MarketingService | registerGuestDevice | response | failureCount | integer |  | Consecutive delivery failures.
MarketingService | registerGuestDevice | response | registeredAt | string (date-time) | yes
MarketingService | registerGuestDevice | response | lastSeenAt | string (date-time) |  | (nullable)
MarketingService | registerGuestDevice | response | revokedAt | string (date-time) |  | (nullable)
MarketingService | registerGuestDevice | param (path) | subjectId | string (uuid) | yes
MarketingService | registerGuestDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | reindexSource | request | reason | enum (embeddingModelChanged, fieldsChanged, driftSuspected, initialBuild)
AiService | reindexSource | response | id | string (uuid) | yes
AiService | reindexSource | response | sourceId | string (uuid) | yes
AiService | reindexSource | response | kind | enum (full, incremental, removal)
AiService | reindexSource | response | reason | string
AiService | reindexSource | response | status | enum (queued, building, verifying, swapping, complete, failed) | yes
AiService | reindexSource | response | recordsTotal | integer
AiService | reindexSource | response | recordsEmbedded | integer
AiService | reindexSource | response | recordsFailed | integer |  | The number to watch.
AiService | reindexSource | response | failureSample | array of string
AiService | reindexSource | response | shadowCollection | string |  | A full rebuild writes here and swaps on completion. (nullable)
AiService | reindexSource | response | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | reindexSource | response | embeddingModel | string
AiService | reindexSource | response | startedAt | string (date-time) | yes
AiService | reindexSource | response | completedAt | string (date-time) |  | (nullable)
AiService | reindexSource | param (path) | sourceId | string (uuid) | yes
AiService | reindexSource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reissueEntitlement | request | reason | enum (venueClosure, weather, goodwill, systemError, medicalIssue, bereavement) | yes
OrderService | reissueEntitlement | request | validFrom | string (date) |  | (nullable)
OrderService | reissueEntitlement | request | note | string |  | (nullable)
OrderService | reissueEntitlement | response | entitlementId | string (uuid) | yes | The new entitlement.
OrderService | reissueEntitlement | response | replacesEntitlementId | string (uuid) | yes | The expired one, now voided.
OrderService | reissueEntitlement | response | reason | enum (venueClosure, weather, goodwill, systemError, medicalIssue, bereavement) | yes
OrderService | reissueEntitlement | response | validFrom | string (date) |  | (nullable)
OrderService | reissueEntitlement | response | note | string |  | (nullable)
OrderService | reissueEntitlement | param (path) | entitlementId | string (uuid) | yes
OrderService | reissueEntitlement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | rejectReceivedGoods | request | lines | array of object | yes | (min items 1)
InventoryService | rejectReceivedGoods | request | lines[].lineId | string (uuid) | yes | GoodsReceipt.lines[].lineId, the batch or expiry line rejected (audit R171).
InventoryService | rejectReceivedGoods | request | lines[].quantity | number | yes | (min 0)
InventoryService | rejectReceivedGoods | request | reason | enum (damaged, wrongItem, qualityFailure, shortDated, overDelivery, other) | yes | other requires note (decided 28 September, audit R222).
InventoryService | rejectReceivedGoods | request | note | string |  | Required, at least 3 characters, when reason is other (audit R222). (max length 1000)
InventoryService | rejectReceivedGoods | response | id | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152), e.g. (read-only)
InventoryService | rejectReceivedGoods | response | purchaseOrderId | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | locationId | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | deliveryNoteReference | string |  | (nullable)
InventoryService | rejectReceivedGoods | response | lines | array of object | yes
InventoryService | rejectReceivedGoods | response | lines[].lineId | string (uuid) |  | One batch or expiry line of the receipt. (read-only)
InventoryService | rejectReceivedGoods | response | lines[].itemId | string (uuid)
InventoryService | rejectReceivedGoods | response | lines[].itemName | string
InventoryService | rejectReceivedGoods | response | lines[].orderedQuantity | number
InventoryService | rejectReceivedGoods | response | lines[].receivedQuantity | number
InventoryService | rejectReceivedGoods | response | lines[].rejectedQuantity | number
InventoryService | rejectReceivedGoods | response | lines[].batchNumber | string |  | (nullable)
InventoryService | rejectReceivedGoods | response | lines[].expiryDate | string (date) |  | (nullable)
InventoryService | rejectReceivedGoods | response | lines[].unitCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | rejectReceivedGoods | response | lines[].unitCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | rejectReceivedGoods | response | lines[].unitCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | rejectReceivedGoods | response | lines[].unitCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | rejectReceivedGoods | response | totalValue | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | rejectReceivedGoods | response | totalValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | rejectReceivedGoods | response | totalValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | rejectReceivedGoods | response | totalValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | rejectReceivedGoods | response | receivedByPrincipalId | string (uuid) | yes
InventoryService | rejectReceivedGoods | response | journalEntryId | string |  | The accrual the supplier invoice will later match against. (nullable)
InventoryService | rejectReceivedGoods | response | createdAt | string (date-time) | yes
InventoryService | rejectReceivedGoods | response | recordedAt | string (date-time)
InventoryService | rejectReceivedGoods | response | syncedAt | string (date-time) |  | (nullable)
InventoryService | rejectReceivedGoods | param (path) | receiptId | string (uuid) | yes
InventoryService | rejectReceivedGoods | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | releaseProductionPlan | response | id | string (uuid) | yes
FnbService | releaseProductionPlan | response | outletId | string (uuid)
FnbService | releaseProductionPlan | response | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone.
FnbService | releaseProductionPlan | response | status | enum (draft, released, superseded, cancelled) | yes
FnbService | releaseProductionPlan | response | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | releaseProductionPlan | response | lines | array of object | yes
FnbService | releaseProductionPlan | response | lines[].itemId | string (uuid) | yes
FnbService | releaseProductionPlan | response | lines[].suggestedQuantity | number |  | (nullable)
FnbService | releaseProductionPlan | response | lines[].plannedQuantity | number | yes
FnbService | releaseProductionPlan | response | lines[].uom | string
FnbService | releaseProductionPlan | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | releaseProductionPlan | response | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | releaseProductionPlan | param (path) | planId | string (uuid) | yes
FnbService | releaseProductionPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | releaseResourceBlock | param (path) | blockId | string (uuid) | yes
VenueOpsService | releaseResourceBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | releaseWalletHold | response | walletHoldId | string (uuid) | yes
WalletService | releaseWalletHold | response | walletId | string (uuid) | yes
WalletService | releaseWalletHold | response | orderId | string (uuid) |  | (nullable)
WalletService | releaseWalletHold | response | paymentId | string (uuid) |  | (nullable)
WalletService | releaseWalletHold | response | walletHoldAmount | number | yes
WalletService | releaseWalletHold | response | currencyCode | string | yes | (max length 10)
WalletService | releaseWalletHold | response | walletHoldStatus | string | yes | (max length 20)
WalletService | releaseWalletHold | response | expiresAt | string (date-time) | yes
WalletService | releaseWalletHold | response | createdAt | string (date-time) | yes
WalletService | releaseWalletHold | response | capturedAt | string (date-time) |  | (nullable)
WalletService | releaseWalletHold | response | releasedAt | string (date-time) |  | (nullable)
WalletService | releaseWalletHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | releaseWalletHold | param (path) | walletHoldId | string (uuid) | yes
WhiteLabelService | relinquishCustomDomain | param (path) | domainId | string (uuid) | yes
WhiteLabelService | relinquishCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | relinquishInventoryHold | request | consumedUnits | integer | yes | (min 0)
CatalogueService | relinquishInventoryHold | response | id | string | yes
CatalogueService | relinquishInventoryHold | response | channelCapacityId | string (uuid) | yes
CatalogueService | relinquishInventoryHold | response | holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | relinquishInventoryHold | response | holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | relinquishInventoryHold | response | holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | relinquishInventoryHold | response | convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | relinquishInventoryHold | response | convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | relinquishInventoryHold | response | parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | relinquishInventoryHold | response | requestedUnits | integer
CatalogueService | relinquishInventoryHold | response | channel | object |  | Allocation this lease draws from.
CatalogueService | relinquishInventoryHold | response | grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | relinquishInventoryHold | response | consumedUnits | integer | yes
CatalogueService | relinquishInventoryHold | response | status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | relinquishInventoryHold | response | acquiredAt | string (date-time) | yes
CatalogueService | relinquishInventoryHold | response | expiresAt | string (date-time) | yes
CatalogueService | relinquishInventoryHold | response | releasedAt | string (date-time) |  | (nullable)
CatalogueService | relinquishInventoryHold | response | forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | relinquishInventoryHold | response | forceReleaseReason | string |  | (nullable)
CatalogueService | relinquishInventoryHold | param (path) | inventoryHoldId | string (uuid) | yes
CatalogueService | relinquishInventoryHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | relinquishResourceHold | param (path) | holdId | string (uuid) | yes
VenueOpsService | relinquishResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | relinquishSeatHold | param (path) | holdId | string (uuid) | yes
CatalogueService | relinquishSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | removeCartLine | response | id | string (uuid) | yes
OrderService | removeCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | removeCartLine | response | venueId | string (uuid) | yes
OrderService | removeCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | removeCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | removeCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | removeCartLine | response | lines | array of CartLine | yes
OrderService | removeCartLine | response | lines[].id | string (uuid) | yes
OrderService | removeCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | removeCartLine | response | lines[].productName | string |  | (read-only)
OrderService | removeCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | removeCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | removeCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | removeCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | removeCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | removeCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | removeCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | removeCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | removeCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | removeCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | removeCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | removeCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | removeCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | removeCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | removeCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | removeCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | removeCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | removeCartLine | response | conflicts | array of CartConflict
OrderService | removeCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | removeCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | removeCartLine | response | conflicts[].message | string
OrderService | removeCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | removeCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | removeCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | removeCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | removeCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | removeCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | removeCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | removeCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | removeCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | removeCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | removeCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | removeCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | removeCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | removeCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | removeCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | removeCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | removeCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | removeCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | removeCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | removeCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | removeCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | removeCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | removeCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | removeCartLine | response | maxExtensions | integer |  | (read-only)
OrderService | removeCartLine | response | locale | string
OrderService | removeCartLine | response | createdAt | string (date-time)
OrderService | removeCartLine | response | updatedAt | string (date-time)
OrderService | removeCartLine | param (path) | cartId | string (uuid) | yes
OrderService | removeCartLine | param (path) | lineId | string (uuid) | yes
OrderService | removeCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | removeFromWishlist | param (path) | subjectId | string (uuid) | yes
MarketingService | removeFromWishlist | param (path) | itemId | string (uuid) | yes
MarketingService | removeFromWishlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | removeMfaMethod | param (path) | methodId | string (uuid) | yes
IdentityService | removeMfaMethod | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | renewInventoryHold | request | consumedUnits | integer | yes | (min 0)
CatalogueService | renewInventoryHold | request | additionalUnits | integer |  | Request more on top of the existing hold. (min 0)
CatalogueService | renewInventoryHold | response | id | string | yes
CatalogueService | renewInventoryHold | response | channelCapacityId | string (uuid) | yes
CatalogueService | renewInventoryHold | response | holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | renewInventoryHold | response | holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | renewInventoryHold | response | holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | renewInventoryHold | response | convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | renewInventoryHold | response | convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | renewInventoryHold | response | parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | renewInventoryHold | response | requestedUnits | integer
CatalogueService | renewInventoryHold | response | channel | object |  | Allocation this lease draws from.
CatalogueService | renewInventoryHold | response | grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | renewInventoryHold | response | consumedUnits | integer | yes
CatalogueService | renewInventoryHold | response | status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | renewInventoryHold | response | acquiredAt | string (date-time) | yes
CatalogueService | renewInventoryHold | response | expiresAt | string (date-time) | yes
CatalogueService | renewInventoryHold | response | releasedAt | string (date-time) |  | (nullable)
CatalogueService | renewInventoryHold | response | forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | renewInventoryHold | response | forceReleaseReason | string |  | (nullable)
CatalogueService | renewInventoryHold | param (path) | inventoryHoldId | string (uuid) | yes
CatalogueService | renewInventoryHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reopenShift | request | reason | string | yes | (min length 3; max length 500)
OrderService | reopenShift | request | supervisorStepUp | object | yes | The supervisor signing the reopen on this device (audit R144).
OrderService | reopenShift | request | supervisorStepUp.principalId | string (uuid) | yes | The supervisor signing.
OrderService | reopenShift | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | reopenShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reopenShift | response | workstationId | string (uuid) | yes
OrderService | reopenShift | response | venueId | string (uuid) | yes
OrderService | reopenShift | response | scopePath | string | yes
OrderService | reopenShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | reopenShift | response | principalDisplayName | string
OrderService | reopenShift | response | incidents | array of object |  | BL-097.
OrderService | reopenShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | reopenShift | response | incidents[].at | string (date-time)
OrderService | reopenShift | response | incidents[].principalId | string (uuid)
OrderService | reopenShift | response | incidents[].note | string |  | (nullable)
OrderService | reopenShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | reopenShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | reopenShift | response | depositBoxCode | string |  | (nullable)
OrderService | reopenShift | response | bagNumber | string |  | (nullable)
OrderService | reopenShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | reopenShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | reopenShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | reopenShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | reopenShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | reopenShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | reopenShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | reopenShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | reopenShift | response | openedAt | string (date-time) | yes
OrderService | reopenShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | reopenShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | reopenShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | reopenShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | reopenShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | reopenShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | reopenShift | response | approvals | array of object
OrderService | reopenShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | reopenShift | response | approvals[].principalId | string (uuid) | yes
OrderService | reopenShift | response | approvals[].at | string (date-time) | yes
OrderService | reopenShift | response | approvals[].reason | string
OrderService | reopenShift | param (path) | shiftId | string (uuid) | yes
OrderService | reopenShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | replaceMediaAsset | request | uploadId | string (uuid) | yes
VenueOpsService | replaceMediaAsset | request | note | string |  | (max length 500)
VenueOpsService | replaceMediaAsset | response | asset | MediaAsset | yes
VenueOpsService | replaceMediaAsset | response | asset.id | string (uuid) | yes
VenueOpsService | replaceMediaAsset | response | asset.kind | MediaKind: enum (image, video, audio, document, vector, font, archive) | yes
VenueOpsService | replaceMediaAsset | response | asset.status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | replaceMediaAsset | response | asset.filename | string | yes
VenueOpsService | replaceMediaAsset | response | asset.contentType | string | yes
VenueOpsService | replaceMediaAsset | response | asset.sizeBytes | integer | yes
VenueOpsService | replaceMediaAsset | response | asset.title | LocalisedText
VenueOpsService | replaceMediaAsset | response | asset.description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | replaceMediaAsset | response | asset.altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | replaceMediaAsset | response | asset.width | integer |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.height | integer |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.durationSeconds | number |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.customMetadata | object |  | BL-178. (nullable)
VenueOpsService | replaceMediaAsset | response | asset.sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | replaceMediaAsset | response | asset.tags | array of string
VenueOpsService | replaceMediaAsset | response | asset.categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | replaceMediaAsset | response | asset.venueId | string (uuid) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | replaceMediaAsset | response | asset.thumbnailUrl | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | replaceMediaAsset | response | asset.rights | MediaRights |  | Licensing terms.
VenueOpsService | replaceMediaAsset | response | asset.rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | replaceMediaAsset | response | asset.rights.licensor | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.licenceReference | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.validFrom | string (date) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.validTo | string (date) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | replaceMediaAsset | response | asset.rights.attributionRequired | boolean |  | (default False)
VenueOpsService | replaceMediaAsset | response | asset.rights.attributionText | string |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | replaceMediaAsset | response | asset.rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | replaceMediaAsset | response | asset.rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | replaceMediaAsset | response | asset.rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | replaceMediaAsset | response | asset.isRightsExpired | boolean
VenueOpsService | replaceMediaAsset | response | asset.version | integer
VenueOpsService | replaceMediaAsset | response | asset.uploadedByPrincipalId | string (uuid)
VenueOpsService | replaceMediaAsset | response | asset.createdAt | string (date-time) | yes
VenueOpsService | replaceMediaAsset | response | affectedSurfaces | integer | yes | How many surfaces now show the new file.
VenueOpsService | replaceMediaAsset | response | liveSurfaces | integer |  | Of those, how many are published to guests right now.
VenueOpsService | replaceMediaAsset | response | derivativesRegenerating | boolean
VenueOpsService | replaceMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | replaceMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | replyToMyCase | request | message | string | yes | (min length 1; max length 10000)
MarketingService | replyToMyCase | response | id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | replyToMyCase | response | caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | replyToMyCase | response | subjectId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | replyToMyCase | response | subject | string | yes | The case's one-line title, not a person.
MarketingService | replyToMyCase | response | kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | replyToMyCase | response | channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | replyToMyCase | response | recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | replyToMyCase | response | syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | replyToMyCase | response | categoryId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | replyToMyCase | response | membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | replyToMyCase | response | status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | replyToMyCase | response | priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | replyToMyCase | response | assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | venueId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | relatedOrderId | string |  | (nullable)
MarketingService | replyToMyCase | response | slaDueAt | string (date-time) |  | (nullable)
MarketingService | replyToMyCase | response | isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | replyToMyCase | response | slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | replyToMyCase | response | escalationCount | integer
MarketingService | replyToMyCase | response | createdAt | string (date-time) | yes
MarketingService | replyToMyCase | response | resolvedAt | string (date-time) |  | (nullable)
MarketingService | replyToMyCase | response | description | string
MarketingService | replyToMyCase | response | resolutionNote | string |  | (nullable)
MarketingService | replyToMyCase | response | messages | array of CaseMessage
MarketingService | replyToMyCase | response | messages[].resolution | string |  | What was actually done about it.
MarketingService | replyToMyCase | response | messages[].id | string | yes
MarketingService | replyToMyCase | response | messages[].body | string | yes
MarketingService | replyToMyCase | response | messages[].isInternal | boolean | yes
MarketingService | replyToMyCase | response | messages[].authorKind | enum (agent, guest, system, ai) | yes
MarketingService | replyToMyCase | response | messages[].authorPrincipalId | string (uuid) |  | (nullable)
MarketingService | replyToMyCase | response | messages[].channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | replyToMyCase | response | messages[].attachmentRefs | array of string
MarketingService | replyToMyCase | response | messages[].recordedAt | string (date-time) | yes | Device time — addCaseMessage is offline-capable.
MarketingService | replyToMyCase | response | messages[].syncedAt | string (date-time) |  | Server time the message arrived. (read-only)
MarketingService | replyToMyCase | param (path) | caseId | string (uuid) | yes
MarketingService | replyToMyCase | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | reprintOrder | request | delivery | enum (print, email, sms, whatsapp, wallet) | yes
OrderService | reprintOrder | request | destination | string
OrderService | reprintOrder | request | lineIds | array of string (uuid) |  | Omit to reprint every line.
OrderService | reprintOrder | request | reason | enum (printerFault, guestRequest, lostTicket, notReceived, other)
OrderService | reprintOrder | request | recordedAt | string (date-time) | yes | When the till reprinted — device time, as for every offline-capable write.
OrderService | reprintOrder | response | reprintCount | integer |  | The order's total, the sum of lines[].reprintCount.
OrderService | reprintOrder | response | lines | array of object |  | The count per reprinted line, as recorded on OrderLine.reprintCount.
OrderService | reprintOrder | response | lines[].lineId | string (uuid) | yes
OrderService | reprintOrder | response | lines[].reprintCount | integer | yes
OrderService | reprintOrder | response | reissuedTicketIds | array of string (uuid) |  | The entitlements reprinted.
OrderService | reprintOrder | param (path) | orderId | string (uuid) | yes
OrderService | reprintOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | reprintReceipt | request | delivery | enum (print, email, sms, whatsapp) | yes
RetailService | reprintReceipt | request | destination | string |  | Required for anything but print.
RetailService | reprintReceipt | response | reprintCount | integer
RetailService | reprintReceipt | param (path) | saleId | string (uuid) | yes
RetailService | reprintReceipt | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | requestAppBuild | request | platform | enum (ios, android) | yes
WhiteLabelService | requestAppBuild | request | configVersion | string |  | A published ConfigVersion.version.
WhiteLabelService | requestAppBuild | request | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | requestAppBuild | request | submitToStore | boolean |  | Submit with the client's recorded API credential once built. (default False)
WhiteLabelService | requestAppBuild | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | requestAppBuild | response | platform | enum (ios, android) | yes
WhiteLabelService | requestAppBuild | response | configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | requestAppBuild | response | storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | requestAppBuild | response | versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | requestAppBuild | response | buildNumber | integer |  | (read-only)
WhiteLabelService | requestAppBuild | response | status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the build service's; from submitted on it is read from the store with the client's credential, or stays built when the client uploads by hand. (read-only)
WhiteLabelService | requestAppBuild | response | failureReason | string |  | (read-only; nullable)
WhiteLabelService | requestAppBuild | response | packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | requestAppBuild | response | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | requestAppBuild | response | submitToStore | boolean |  | (default False)
WhiteLabelService | requestAppBuild | response | requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | requestAppBuild | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | requestAppBuild | response | finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | requestAppBuild | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | requestAppBuild | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | requestGroupBooking | request | kind | enum (general, school, corporate, party) | yes
OrderService | requestGroupBooking | request | packageProductId | string | yes
OrderService | requestGroupBooking | request | preferredDate | string (date) | yes
OrderService | requestGroupBooking | request | expectedSize | integer | yes | (min 2)
OrderService | requestGroupBooking | request | organisationName | string |  | The school. (max length 200; nullable)
OrderService | requestGroupBooking | request | yearGroup | string |  | (max length 40; nullable)
OrderService | requestGroupBooking | request | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | request | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | requestGroupBooking | request | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | requestGroupBooking | request | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | response | id | string (uuid) | yes
OrderService | requestGroupBooking | response | kind | enum (general, school, corporate, party) |  | (default general)
OrderService | requestGroupBooking | response | packageProductId | string |  | The school-trip format or party package. (nullable)
OrderService | requestGroupBooking | response | yearGroup | string |  | (max length 40; nullable)
OrderService | requestGroupBooking | response | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | response | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | requestGroupBooking | response | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | requestGroupBooking | response | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | requestGroupBooking | response | finalHeadcountDueBy | string (date-time) |  | (nullable)
OrderService | requestGroupBooking | response | quoteSentAt | string (date-time) |  | (read-only; nullable)
OrderService | requestGroupBooking | response | riskAssessmentSentAt | string (date-time) |  | (read-only; nullable)
OrderService | requestGroupBooking | response | preferredDate | string (date) |  | The date the guest asked for on requestGroupBooking — what its 409 dateUnavailable is checked against. (nullable)
OrderService | requestGroupBooking | response | orderId | string (uuid) | yes
OrderService | requestGroupBooking | response | leaderSubjectId | string (uuid) | yes
OrderService | requestGroupBooking | response | organisationName | string |  | (nullable)
OrderService | requestGroupBooking | response | expectedSize | integer | yes
OrderService | requestGroupBooking | response | confirmedSize | integer |  | (nullable)
OrderService | requestGroupBooking | response | minimumSize | integer |  | Below which the group rate does not apply. (nullable)
OrderService | requestGroupBooking | response | attendeeCaptureRequired | boolean |  | Whether names are needed before admission. (default False)
OrderService | requestGroupBooking | response | attendeeCaptureDueBy | string (date-time) |  | (nullable)
OrderService | requestGroupBooking | response | status | enum (provisional, confirmed, namesPending, complete, cancelled) | yes
OrderService | requestGroupBooking | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | requestGuestOtp | request | identifier | string | yes | (max length 256)
IdentityService | requestGuestOtp | request | channel | enum (whatsapp, sms, email) | yes
IdentityService | requestGuestOtp | request | purpose | enum (login, register, verify, passwordReset, stepUp) |  | (default login)
IdentityService | requestGuestOtp | response | expiresInSeconds | integer
IdentityService | requestGuestOtp | response | resendAfterSeconds | integer
IdentityService | requestGuestOtp | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | requestSuggestion | request | kind | object | yes | A guest caller may ask for prepPlan, upsell, waitTime and itinerary only.
AiService | requestSuggestion | request | subjectRef | string |  | (nullable)
AiService | requestSuggestion | request | horizon | string |  | For a forecast — nextService, 7d, 28d, or an ISO period. (nullable)
AiService | requestSuggestion | request | context | object |  | What the caller already knows.
AiService | requestSuggestion | response | id | string (uuid) | yes
AiService | requestSuggestion | response | kind | SuggestionKind: enum (price, replenishment, requisition, demandForecast, prepPlan, menuEngineering, staffing, slaTarget, …) | yes | What is being suggested.
AiService | requestSuggestion | response | basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | requestSuggestion | response | scopePath | string
AiService | requestSuggestion | response | subjectRef | string |  | What it is about — a product, an outlet, an item, a party. (nullable)
AiService | requestSuggestion | response | value | object |  | The suggestion itself.
AiService | requestSuggestion | response | confidence | number |  | Null for a heuristic and that is honest. (min 0; max 1; nullable)
AiService | requestSuggestion | response | explanation | string |  | Plain words, always present, whatever the basis.
AiService | requestSuggestion | response | inputs | object |  | What went in.
AiService | requestSuggestion | response | producerRef | string |  | The rule name or the model id and version.
AiService | requestSuggestion | response | maturity | AiMaturity | yes | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | requestSuggestion | response | maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | requestSuggestion | response | maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | requestSuggestion | response | maturity.sources | array of object
AiService | requestSuggestion | response | maturity.sources[].source | enum (venueSettings, startingPattern, calendar, weather, bookingsOnHand, ownHistory, importedHistory, configuration, …) | yes
AiService | requestSuggestion | response | maturity.sources[].detail | string |  | e.g. (nullable)
AiService | requestSuggestion | response | maturity.sources[].observations | integer |  | (nullable)
AiService | requestSuggestion | response | maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | requestSuggestion | response | maturity.limitedHistory | boolean
AiService | requestSuggestion | response | maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | requestSuggestion | response | maturity.nextStage.stage | enum (learning, established, learned)
AiService | requestSuggestion | response | maturity.nextStage.needs | string
AiService | requestSuggestion | response | maturity.nextStage.expectedBy | string (date) |  | (nullable)
AiService | requestSuggestion | response | producedAt | string (date-time) | yes
AiService | requestSuggestion | response | expiresAt | string (date-time) |  | A demand forecast for Saturday is worthless on Sunday. (nullable)
AiService | requestSuggestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | rescheduleOrder | request | targetPerformanceId | string (uuid) | yes
OrderService | rescheduleOrder | request | lineIds | array of string (uuid) |  | Omit to move the whole order.
OrderService | rescheduleOrder | request | waiveFee | boolean |  | (default False)
OrderService | rescheduleOrder | request | reason | string |  | (max length 500)
OrderService | rescheduleOrder | request | recordedAt | string (date-time) | yes
OrderService | rescheduleOrder | response | orderId | string (uuid) | yes
OrderService | rescheduleOrder | response | outgoingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | rescheduleOrder | response | outgoingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | outgoingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | outgoingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | incomingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | rescheduleOrder | response | incomingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | incomingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | incomingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | exchangeFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | rescheduleOrder | response | exchangeFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | exchangeFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | exchangeFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | difference | object | yes | Only the difference settles.
OrderService | rescheduleOrder | response | difference.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | rescheduleOrder | response | difference.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | rescheduleOrder | response | difference.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | rescheduleOrder | response | newLineIds | array of string (uuid)
OrderService | rescheduleOrder | response | revokedEntitlementIds | array of string (uuid)
OrderService | rescheduleOrder | response | issuedEntitlementIds | array of string (uuid)
OrderService | rescheduleOrder | param (path) | orderId | string (uuid) | yes
OrderService | rescheduleOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | reserveMerchandise | request | id | string (uuid) | yes
RetailService | reserveMerchandise | request | subjectId | string (uuid)
RetailService | reserveMerchandise | request | lines | array of object | yes | (min items 1)
RetailService | reserveMerchandise | request | lines[].merchandiseId | string (uuid) | yes
RetailService | reserveMerchandise | request | lines[].quantity | integer | yes | (min 1)
RetailService | reserveMerchandise | request | expiresAt | string (date-time) |  | At least 15 minutes from now and no later than the close of the venue's operating day (audit R215).
RetailService | reserveMerchandise | request | collectionNote | string |  | (max length 200)
RetailService | reserveMerchandise | response | id | string | yes
RetailService | reserveMerchandise | response | reservationNumber | string
RetailService | reserveMerchandise | response | outletId | string (uuid) | yes
RetailService | reserveMerchandise | response | subjectId | string (uuid) |  | (nullable)
RetailService | reserveMerchandise | response | lines | array of object | yes
RetailService | reserveMerchandise | response | lines[].merchandiseId | string (uuid)
RetailService | reserveMerchandise | response | lines[].name | string
RetailService | reserveMerchandise | response | lines[].quantity | integer
RetailService | reserveMerchandise | response | status | enum (reserved, collected, expired, cancelled) | yes
RetailService | reserveMerchandise | response | collectionNote | string |  | (nullable)
RetailService | reserveMerchandise | response | expiresAt | string (date-time) | yes
RetailService | reserveMerchandise | response | collectedAt | string (date-time) |  | (nullable)
RetailService | reserveMerchandise | param (path) | outletId | string (uuid) | yes
RetailService | reserveMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | resolveProductByCode | response | id | string (uuid) | yes
CatalogueService | resolveProductByCode | response | productId | string (uuid) | yes
CatalogueService | resolveProductByCode | response | sku | string | yes
CatalogueService | resolveProductByCode | response | axisValues | object | yes
CatalogueService | resolveProductByCode | response | name | string |  | Taken from their variant tables, 20 September. (max length 150; nullable)
CatalogueService | resolveProductByCode | response | barcode | string |  | Taken from their variant tables, 20 September. (max length 64; nullable)
CatalogueService | resolveProductByCode | response | isDefault | boolean |  | Taken from their variant tables. (default False)
CatalogueService | resolveProductByCode | response | isActive | boolean | yes | False when retired.
CatalogueService | resolveProductByCode | response | description | object |  | Who this ticket type is for and what it includes, shown behind the (i) on each Adult, Child, Senior or Infant row (decided 29 September, 23SEP-6). (nullable)
CatalogueService | resolveProductByCode | param (query) | code | string | yes
CatalogueService | resolveProductByCode | param (query) | partnerId | string (uuid)
MarketingService | respondToInvitation | request | response | enum (accept, decline) | yes
MarketingService | respondToInvitation | request | plusOnes | integer |  | (default 0)
MarketingService | respondToInvitation | response | id | string (uuid) | yes
MarketingService | respondToInvitation | response | campaignId | string (uuid) | yes
MarketingService | respondToInvitation | response | subjectId | string (uuid) |  | (nullable)
MarketingService | respondToInvitation | response | recipientEmail | string (email) |  | (nullable)
MarketingService | respondToInvitation | response | token | string | yes | Single-use and unguessable.
MarketingService | respondToInvitation | response | plusOnes | integer |  | (default 0)
MarketingService | respondToInvitation | response | status | enum (issued, viewed, accepted, declined, expired, revoked) | yes
MarketingService | respondToInvitation | response | entitlementIds | array of string (uuid)
MarketingService | respondToInvitation | response | respondedAt | string (date-time) |  | (nullable)
MarketingService | respondToInvitation | response | scopePath | string |  | The partition key (ADR-0005).
MarketingService | respondToInvitation | param (path) | token | string | yes
MarketingService | respondToInvitation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | restoreConfigVersion | response | tenantId | string (uuid) | yes
WhiteLabelService | restoreConfigVersion | response | version | string | yes | The draft's working version label; the published one is ConfigVersion.version.
WhiteLabelService | restoreConfigVersion | response | isDraft | boolean |  | True for the working draft, which is the only row. (read-only)
WhiteLabelService | restoreConfigVersion | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload), PNG or SVG and at most 2 MB (decided 28 September, audit R270).
WhiteLabelService | restoreConfigVersion | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | restoreConfigVersion | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | restoreConfigVersion | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | restoreConfigVersion | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | restoreConfigVersion | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | restoreConfigVersion | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | restoreConfigVersion | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | restoreConfigVersion | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | restoreConfigVersion | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | restoreConfigVersion | response | appIcons | AppIcons
WhiteLabelService | restoreConfigVersion | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | restoreConfigVersion | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | restoreConfigVersion | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | restoreConfigVersion | response | appIcons.derived[].size | string
WhiteLabelService | restoreConfigVersion | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | restoreConfigVersion | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | restoreConfigVersion | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | restoreConfigVersion | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlow | BookingFlowConfig |  | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
WhiteLabelService | restoreConfigVersion | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | restoreConfigVersion | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | restoreConfigVersion | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | restoreConfigVersion | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | restoreConfigVersion | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | restoreConfigVersion | response | bookingFlows | array of BookingFlow |  | Every venue's booking flows in the draft (whitelabel.booking_flow), so a publish snapshots them with the rest (decided 29 September, W12). (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].id | string (uuid) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | restoreConfigVersion | response | bookingFlows[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | restoreConfigVersion | response | theme | Theme
WhiteLabelService | restoreConfigVersion | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.darkMode | object |  | Optional dark variant.
WhiteLabelService | restoreConfigVersion | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | restoreConfigVersion | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | restoreConfigVersion | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | restoreConfigVersion | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | restoreConfigVersion | response | fonts | FontConfig
WhiteLabelService | restoreConfigVersion | response | fonts.primaryLatin | string | yes
WhiteLabelService | restoreConfigVersion | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | restoreConfigVersion | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | restoreConfigVersion | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | restoreConfigVersion | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | restoreConfigVersion | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | restoreConfigVersion | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | restoreConfigVersion | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | restoreConfigVersion | response | footer.columns | array of object
WhiteLabelService | restoreConfigVersion | response | footer.columns[].heading | string
WhiteLabelService | restoreConfigVersion | response | footer.columns[].links | array of object
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.termsUrl | string
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | footer.copyrightText | string
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks | array of object
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks[].platform | string
WhiteLabelService | restoreConfigVersion | response | footer.socialLinks[].url | string
WhiteLabelService | restoreConfigVersion | response | notificationBranding | object |  | BL-003. (nullable)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.senderName | string
WhiteLabelService | restoreConfigVersion | response | notificationBranding.replyToEmail | string (email)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.smsSenderId | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.whatsappBusinessId | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | notificationBranding.logoAssetId | string (uuid) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | enabledPaymentMethods | array of string |  | BL-004. (nullable)
WhiteLabelService | restoreConfigVersion | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | restoreConfigVersion | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | restoreConfigVersion | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | restoreConfigVersion | response | header | HeaderConfig
WhiteLabelService | restoreConfigVersion | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | restoreConfigVersion | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | restoreConfigVersion | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | restoreConfigVersion | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | restoreConfigVersion | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | restoreConfigVersion | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | restoreConfigVersion | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | navigation.items[].icon | string
WhiteLabelService | restoreConfigVersion | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | restoreConfigVersion | response | navigation.items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | restoreConfigVersion | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | restoreConfigVersion | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | restoreConfigVersion | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | restoreConfigVersion | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | homepage | HomepageLayout
WhiteLabelService | restoreConfigVersion | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | homepage.sections | array of object | yes
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].maxItems | integer |  | How many items the section shows. (nullable)
WhiteLabelService | restoreConfigVersion | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | restoreConfigVersion | response | modules | array of ModuleEnablement
WhiteLabelService | restoreConfigVersion | response | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | restoreConfigVersion | response | modules[].displayName | string
WhiteLabelService | restoreConfigVersion | response | modules[].isLicensed | boolean | yes | From the tenant's subscription.
WhiteLabelService | restoreConfigVersion | response | modules[].isEnabled | boolean | yes
WhiteLabelService | restoreConfigVersion | response | modules[].referencedBy | array of string |  | Navigation items and homepage sections pointing at this module. (read-only)
WhiteLabelService | restoreConfigVersion | response | features | array of FeatureToggle
WhiteLabelService | restoreConfigVersion | response | features[].featureKey | object | yes | guestCheckout is off by default (decided 17 September 2026, matrix 2.6.28, placement settled by [ADR-0045](../../docs/adr/0045-every-order-carries-a-proven-contact.md) 18 September): the venue sets t…
WhiteLabelService | restoreConfigVersion | response | features[].displayName | string
WhiteLabelService | restoreConfigVersion | response | features[].isEnabled | boolean | yes
WhiteLabelService | restoreConfigVersion | response | features[].changeScope | object | yes | Wallet and payment integrations are buildTime on native apps — enabling one needs a release, not a publish. (read-only)
WhiteLabelService | restoreConfigVersion | response | features[].requiresConfiguration | boolean |  | True where the feature needs credentials or setup elsewhere first.
WhiteLabelService | restoreConfigVersion | response | languages | LanguageConfig
WhiteLabelService | restoreConfigVersion | response | languages.languages | array of string | yes
WhiteLabelService | restoreConfigVersion | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | restoreConfigVersion | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps[].language | string
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | restoreConfigVersion | response | languages.translationGaps[].areas | array of string
WhiteLabelService | restoreConfigVersion | response | updatedAt | string (date-time)
WhiteLabelService | restoreConfigVersion | response | isInMaintenance | boolean |  | Written by setMaintenanceMode; read by getTenantAppStatus. (default False)
WhiteLabelService | restoreConfigVersion | response | maintenanceMessage | object |  | The message on the branded maintenance screen. (nullable)
WhiteLabelService | restoreConfigVersion | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | restoreConfigVersion | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | restoreConfigVersion | response | contact | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | restoreConfigVersion | response | contact.phone | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.address | object |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | restoreConfigVersion | response | availability | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | restoreConfigVersion | response | availabilityMessage | object |  | Live state, written by setMaintenanceMode (audit R073). (nullable)
WhiteLabelService | restoreConfigVersion | response | venues | array of object |  | The tenant's active venues, for the guest venue picker on WEB-001 and GST-001 (decided 28 September, audit R267).
WhiteLabelService | restoreConfigVersion | response | venues[].venueId | string (uuid) | yes
WhiteLabelService | restoreConfigVersion | response | venues[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | restoreConfigVersion | response | venues[].city | string |  | (nullable)
WhiteLabelService | restoreConfigVersion | response | venues[].openingHours | object |  | Today's hours as shown to a guest, e.g. (nullable)
WhiteLabelService | restoreConfigVersion | param (path) | version | string | yes
WhiteLabelService | restoreConfigVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | restoreWalletConfigurationVersion | request | reason | string | yes | (min length 1; max length 500)
WalletService | restoreWalletConfigurationVersion | response | version | integer
WalletService | restoreWalletConfigurationVersion | response | publishedAt | string (date-time) |  | (nullable)
WalletService | restoreWalletConfigurationVersion | response | publishedBy | string (uuid) |  | (nullable)
WalletService | restoreWalletConfigurationVersion | response | note | string |  | (nullable)
WalletService | restoreWalletConfigurationVersion | response | findings | array of object
WalletService | restoreWalletConfigurationVersion | response | findings[].severity | enum (blocking, warning)
WalletService | restoreWalletConfigurationVersion | response | findings[].code | string
WalletService | restoreWalletConfigurationVersion | response | findings[].message | string
WalletService | restoreWalletConfigurationVersion | response | scopePath | string
WalletService | restoreWalletConfigurationVersion | param (path) | version | integer | yes
WalletService | restoreWalletConfigurationVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | resumeAiCapability | request | reason | string | yes | (max length 1000)
AiService | resumeAiCapability | response | id | string (uuid) |  | (read-only)
AiService | resumeAiCapability | response | capabilityKey | string | yes | Stable key, unique per tenant: assistant.guest, forecast.attendance, risk.transaction, config.assistant, recommend.checkout.
AiService | resumeAiCapability | response | family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …) | yes | The fourteen capabilities of the AI system design (section 1.1), C1 to C14 in order: gateway and model registry, governance decision point, action pipeline and human oversight, knowledge and retrieva…
AiService | resumeAiCapability | response | name | string
AiService | resumeAiCapability | response | description | string |  | (nullable)
AiService | resumeAiCapability | response | ownerPrincipalId | string (uuid) |  | The accountable business owner (AIC-144). (nullable)
AiService | resumeAiCapability | response | businessFunction | string |  | (nullable)
AiService | resumeAiCapability | response | riskClass | AiRiskClass: enum (low, medium, high, critical) | yes | Business, customer, financial, operational, security and compliance impact of a capability or action type (AIC-144, ADM-521).
AiService | resumeAiCapability | response | autonomyCeiling | object |  | The first-release ceiling for this capability (design 3.8 table). (read-only)
AiService | resumeAiCapability | response | autonomyLevel | object | yes | The level in force at this scope.
AiService | resumeAiCapability | response | dataCategories | array of string |  | Data categories the capability reads (ADM-524).
AiService | resumeAiCapability | response | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | resumeAiCapability | response | lifecycle.development | enum (draft, pilot, active, retired)
AiService | resumeAiCapability | response | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | resumeAiCapability | response | lifecycle.production | enum (draft, pilot, active, retired)
AiService | resumeAiCapability | response | degradationMode | enum (rulesOnly, searchOnly, humanHandoff, hidden, failOpen, lastPublished) |  | What the capability does when its model or the service is unavailable (design 3.7, AIC-241).
AiService | resumeAiCapability | response | status | enum (active, paused) |  | Paused by pauseAiCapability: the capability answers from its degradation mode until resumed. (read-only)
AiService | resumeAiCapability | response | pausedReason | string |  | (read-only; nullable)
AiService | resumeAiCapability | response | pausedAt | string (date-time) |  | (read-only; nullable)
AiService | resumeAiCapability | response | updatedAt | string (date-time) |  | (read-only)
AiService | resumeAiCapability | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | resumeAiCapability | param (path) | capabilityKey | string | yes
AiService | resumeAiCapability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | resumeOrder | response | order | Order | yes
OrderService | resumeOrder | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | resumeOrder | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | resumeOrder | response | order.channel | object | yes | Where it came from.
OrderService | resumeOrder | response | order.venueId | string (uuid) | yes
OrderService | resumeOrder | response | order.scopePath | string | yes
OrderService | resumeOrder | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | resumeOrder | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | resumeOrder | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | resumeOrder | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | resumeOrder | response | order.droppedPromotions[].name | string
OrderService | resumeOrder | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | resumeOrder | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | resumeOrder | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | order.lines | array of OrderLine | yes
OrderService | resumeOrder | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | resumeOrder | response | order.lines[].variantId | string (uuid) | yes
OrderService | resumeOrder | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | resumeOrder | response | order.lines[].performanceId | string (uuid)
OrderService | resumeOrder | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | resumeOrder | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | resumeOrder | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | resumeOrder | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | resumeOrder | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | resumeOrder | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | resumeOrder | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | resumeOrder | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | resumeOrder | response | order.lines[].holderName | string |  | (nullable)
OrderService | resumeOrder | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | resumeOrder | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | resumeOrder | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | resumeOrder | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | resumeOrder | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | resumeOrder | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | resumeOrder | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | resumeOrder | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | resumeOrder | response | order.payments | array of Payment
OrderService | resumeOrder | response | order.payments[].id | string (uuid) | yes
OrderService | resumeOrder | response | order.payments[].orderId | string (uuid) | yes
OrderService | resumeOrder | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | resumeOrder | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | resumeOrder | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | resumeOrder | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | resumeOrder | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | resumeOrder | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | resumeOrder | response | order.payments[].providerName | string |  | (nullable)
OrderService | resumeOrder | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | resumeOrder | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | resumeOrder | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | resumeOrder | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | resumeOrder | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | resumeOrder | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | resumeOrder | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | resumeOrder | response | order.principalId | string (uuid)
OrderService | resumeOrder | response | order.workstationId | string (uuid)
OrderService | resumeOrder | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | resumeOrder | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | resumeOrder | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | resumeOrder | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | resumeOrder | response | order.createdAt | string (date-time) | yes
OrderService | resumeOrder | response | order.recordedAt | string (date-time) | yes
OrderService | resumeOrder | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | resumeOrder | response | hasChanged | boolean | yes | True where anything moved while the sale was parked.
OrderService | resumeOrder | response | changes | array of object
OrderService | resumeOrder | response | changes[].kind | enum (priceChanged, promotionExpired, promotionNowApplies, soldOut, seatHoldExpired, productWithdrawn)
OrderService | resumeOrder | response | changes[].lineId | string (uuid)
OrderService | resumeOrder | response | changes[].detail | string
OrderService | resumeOrder | response | changes[].wasAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | changes[].wasAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | changes[].wasAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | changes[].wasAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | response | changes[].nowAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeOrder | response | changes[].nowAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeOrder | response | changes[].nowAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeOrder | response | changes[].nowAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeOrder | param (path) | orderId | string (uuid) | yes
OrderService | resumeOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | resumeShift | request | recordedAt | string (date-time) | yes
OrderService | resumeShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | resumeShift | response | workstationId | string (uuid) | yes
OrderService | resumeShift | response | venueId | string (uuid) | yes
OrderService | resumeShift | response | scopePath | string | yes
OrderService | resumeShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | resumeShift | response | principalDisplayName | string
OrderService | resumeShift | response | incidents | array of object |  | BL-097.
OrderService | resumeShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | resumeShift | response | incidents[].at | string (date-time)
OrderService | resumeShift | response | incidents[].principalId | string (uuid)
OrderService | resumeShift | response | incidents[].note | string |  | (nullable)
OrderService | resumeShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | resumeShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | resumeShift | response | depositBoxCode | string |  | (nullable)
OrderService | resumeShift | response | bagNumber | string |  | (nullable)
OrderService | resumeShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | resumeShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | resumeShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | resumeShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | resumeShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | resumeShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | resumeShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | resumeShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | resumeShift | response | openedAt | string (date-time) | yes
OrderService | resumeShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | resumeShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | resumeShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | resumeShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | resumeShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | resumeShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | resumeShift | response | approvals | array of object
OrderService | resumeShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | resumeShift | response | approvals[].principalId | string (uuid) | yes
OrderService | resumeShift | response | approvals[].at | string (date-time) | yes
OrderService | resumeShift | response | approvals[].reason | string
OrderService | resumeShift | param (path) | shiftId | string (uuid) | yes
OrderService | resumeShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | retryMyDunningPayment | request | paymentTokenId | string (uuid) |  | A saved card other than the one that failed: the id of one of the guest's own PaymentToken rows (payments.token, stored through storePaymentToken), not a payments.method id, which names a kind of met… (nullable)
OrderService | retryMyDunningPayment | response | id | string (uuid) | yes
OrderService | retryMyDunningPayment | response | subjectId | string (uuid)
OrderService | retryMyDunningPayment | response | orderId | string |  | The order whose renewal failed.
OrderService | retryMyDunningPayment | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | retryMyDunningPayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | retryMyDunningPayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | retryMyDunningPayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | retryMyDunningPayment | response | state | DunningState: enum (scheduled, inProgress, exhausted, recovered, resolvedManually) | yes | BL-100.
OrderService | retryMyDunningPayment | response | declineClass | object |  | From the most recent attempt.
OrderService | retryMyDunningPayment | response | attemptsMade | integer | yes
OrderService | retryMyDunningPayment | response | nextAttemptAt | string (date-time) |  | Null where the case has ended or the decline is hard. (nullable)
OrderService | retryMyDunningPayment | response | firstFailedAt | string (date-time) | yes
OrderService | retryMyDunningPayment | response | resolvedAt | string (date-time) |  | (nullable)
OrderService | retryMyDunningPayment | response | resolution | enum (paidByOtherMeans, cardReplaced, writeOff, cancelledByGuest, None) |  | (nullable)
OrderService | retryMyDunningPayment | response | resolutionNote | string |  | What resolveDunningCase was told, which had nowhere to land until now. (max length 500; nullable)
OrderService | retryMyDunningPayment | response | resolvedByPrincipalId | string (uuid) |  | Who closed it. (read-only; nullable)
OrderService | retryMyDunningPayment | response | scopePath | string |  | The partition key (ADR-0005).
OrderService | retryMyDunningPayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | retryMyDunningPayment | param (path) | caseId | string (uuid) | yes
AccessService | revokeFacePass | param (path) | enrolmentId | string (uuid) | yes
AccessService | revokeFacePass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | revokeGuestDevice | param (path) | subjectId | string (uuid) | yes
MarketingService | revokeGuestDevice | param (path) | deviceId | string (uuid) | yes
MarketingService | revokeGuestDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | rollbackAccessPolicy | request | targetVersion | integer | yes | The version whose content is restored (min 1)
AccessService | rollbackAccessPolicy | request | reason | string | yes | (min length 3; max length 300)
AccessService | rollbackAccessPolicy | response | version | integer |  | Current version. (min 1)
AccessService | rollbackAccessPolicy | response | policyId | string | yes
AccessService | rollbackAccessPolicy | response | policyName | string |  | e.g.
AccessService | rollbackAccessPolicy | response | scope | string |  | Where the policy applies, e.g.
AccessService | rollbackAccessPolicy | response | policyType | enum (guestAttribute, accreditation, occupancy, employee, risk, membership, timeEvent)
AccessService | rollbackAccessPolicy | response | priority | integer
AccessService | rollbackAccessPolicy | response | status | enum (draft, pendingApproval, active, inactive, expired)
AccessService | rollbackAccessPolicy | param (path) | policyId | string | yes
AccessService | rollbackAccessPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | rollbackAiRelease | request | reason | string | yes | (max length 1000)
AiService | rollbackAiRelease | response | id | string (uuid) |  | (read-only)
AiService | rollbackAiRelease | response | capabilityKey | string | yes
AiService | rollbackAiRelease | response | artefactKind | enum (model, prompt, routing, embedding, retrieval, rule) | yes
AiService | rollbackAiRelease | response | candidateRef | string | yes
AiService | rollbackAiRelease | response | currentRef | string |  | What production runs now: the rule, or the previously promoted artefact. (nullable)
AiService | rollbackAiRelease | response | previousRef | string |  | (read-only; nullable)
AiService | rollbackAiRelease | response | layer | enum (platform, tenant) | yes
AiService | rollbackAiRelease | response | suggestionKind | object |  | Where the capability answers a requestSuggestion kind: promotion rewrites that kind's assignment in AiPolicy.suggestionProviders. (nullable)
AiService | rollbackAiRelease | response | stage | enum (draft, offlineEval, shadow, canary, production, monitored, rolledBack, rejected) | yes | (read-only)
AiService | rollbackAiRelease | response | shadowStartedAt | string (date-time) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | gatePassedAt | string (date-time) |  | When the shadow run passed its gate and promotionReady was raised. (read-only; nullable)
AiService | rollbackAiRelease | response | canaryScope | object |  | Venues or share of traffic in canary. (nullable)
AiService | rollbackAiRelease | response | promotedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | promotedAt | string (date-time) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | rolledBackByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | rolledBackAt | string (date-time) |  | (read-only; nullable)
AiService | rollbackAiRelease | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | rollbackAiRelease | param (path) | releaseId | string (uuid) | yes
AiService | rollbackAiRelease | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | rotateApiCredential | request | overlapHours | integer |  | (default 72)
PlatformService | rotateApiCredential | response | clientSecret | string (password)
PlatformService | rotateApiCredential | response | oldSecretExpiresAt | string (date-time)
PlatformService | rotateApiCredential | param (path) | clientId | string (uuid) | yes
PlatformService | rotateApiCredential | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | runAiEvaluation | request | suiteId | string (uuid) | yes
AiService | runAiEvaluation | request | releaseId | string (uuid) |  | (nullable)
AiService | runAiEvaluation | request | candidateRef | string | yes
AiService | runAiEvaluation | request | baselineRef | string |  | (nullable)
AiService | runAiEvaluation | request | kind | enum (offline, backtest, shadow) | yes
AiService | runAiEvaluation | response | id | string (uuid) |  | (read-only)
AiService | runAiEvaluation | response | suiteId | string (uuid) | yes
AiService | runAiEvaluation | response | releaseId | string (uuid) |  | (nullable)
AiService | runAiEvaluation | response | kind | enum (offline, backtest, shadow) | yes
AiService | runAiEvaluation | response | candidateRef | string
AiService | runAiEvaluation | response | baselineRef | string |  | (nullable)
AiService | runAiEvaluation | response | status | enum (queued, running, passed, failed, error) | yes | (read-only)
AiService | runAiEvaluation | response | metrics | object |  | (read-only; nullable)
AiService | runAiEvaluation | response | gate | object |  | The promotion gate thresholds (design 3.5 table) and whether each passed. (read-only; nullable)
AiService | runAiEvaluation | response | isolationCasesPassed | boolean |  | False blocks release, whatever the other metrics say. (read-only)
AiService | runAiEvaluation | response | requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | runAiEvaluation | response | startedAt | string (date-time) |  | (read-only)
AiService | runAiEvaluation | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | runAiEvaluation | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | runAiEvaluation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | runForecast | response | id | string (uuid) |  | (read-only)
AiService | runForecast | response | definitionId | string (uuid) | yes
AiService | runForecast | response | versionNumber | integer | yes | (min 1)
AiService | runForecast | response | status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | runForecast | response | basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | runForecast | response | maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | runForecast | response | maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | runForecast | response | maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | runForecast | response | maturity.sources | array of object
AiService | runForecast | response | maturity.sources[].source | enum (venueSettings, startingPattern, calendar, weather, bookingsOnHand, ownHistory, importedHistory, configuration, …) | yes
AiService | runForecast | response | maturity.sources[].detail | string |  | e.g. (nullable)
AiService | runForecast | response | maturity.sources[].observations | integer |  | (nullable)
AiService | runForecast | response | maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | runForecast | response | maturity.limitedHistory | boolean
AiService | runForecast | response | maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | runForecast | response | maturity.nextStage.stage | enum (learning, established, learned)
AiService | runForecast | response | maturity.nextStage.needs | string
AiService | runForecast | response | maturity.nextStage.expectedBy | string (date) |  | (nullable)
AiService | runForecast | response | producerRef | string
AiService | runForecast | response | modelVersion | string |  | (nullable)
AiService | runForecast | response | dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | runForecast | response | horizonStart | string (date-time)
AiService | runForecast | response | horizonEnd | string (date-time)
AiService | runForecast | response | qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | runForecast | response | publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | runForecast | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | runForecast | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | runForecast | response | createdAt | string (date-time) |  | (read-only)
AiService | runForecast | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | runForecast | param (path) | definitionKey | string | yes
AiService | runForecast | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | runReport | request | parameters | object |  | Open on purpose; its shape is the report's.
ReportingService | runReport | request | venueId | string (uuid) |  | Narrows to one venue.
ReportingService | runReport | request | dateFrom | string (date) |  | Defaults to today in the venue's time zone when not sent (decided 28 September, audit R158).
ReportingService | runReport | request | dateTo | string (date) |  | Defaults to today in the venue's time zone when not sent (audit R158).
ReportingService | runReport | request | forceAsync | boolean |  | Queue regardless of size, for a result to be collected later. (default False)
ReportingService | runReport | response | executionId | string | yes
ReportingService | runReport | response | columns | array of object | yes
ReportingService | runReport | response | columns[].key | string
ReportingService | runReport | response | columns[].label | string
ReportingService | runReport | response | columns[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …)
ReportingService | runReport | response | rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | runReport | response | totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | runReport | response | rowCount | integer
ReportingService | runReport | response | nextCursor | string |  | (nullable)
ReportingService | runReport | response | generatedAt | string (date-time)
ReportingService | runReport | response | dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | runReport | param (path) | reportId | string (uuid) | yes
ReportingService | runReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | saveFavouriteRoute | request | venueId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | request | fromStationId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | request | toStationId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | request | label | string |  | (max length 60; nullable)
VenueOpsService | saveFavouriteRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | saveFavouriteRoute | response | venueId | string (uuid) | yes
VenueOpsService | saveFavouriteRoute | response | fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | saveFavouriteRoute | response | toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | saveFavouriteRoute | response | fromStationName | string |  | (read-only)
VenueOpsService | saveFavouriteRoute | response | toStationName | string |  | (read-only)
VenueOpsService | saveFavouriteRoute | response | label | string |  | (nullable)
VenueOpsService | saveFavouriteRoute | response | adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | saveFavouriteRoute | response | adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | saveFavouriteRoute | response | adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | saveFavouriteRoute | response | adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | saveFavouriteRoute | response | createdAt | string (date-time) | yes
VenueOpsService | saveFavouriteRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | saveNaturalLanguageQuery | request | name | string | yes | (max length 200)
ReportingService | saveNaturalLanguageQuery | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …)
ReportingService | saveNaturalLanguageQuery | response | name | string | yes | (max length 200)
ReportingService | saveNaturalLanguageQuery | response | description | string |  | (max length 1000)
ReportingService | saveNaturalLanguageQuery | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | saveNaturalLanguageQuery | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | saveNaturalLanguageQuery | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | saveNaturalLanguageQuery | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | saveNaturalLanguageQuery | response | columns[].field | string | yes
ReportingService | saveNaturalLanguageQuery | response | columns[].label | string
ReportingService | saveNaturalLanguageQuery | response | columns[].aggregation | object |  | (default none)
ReportingService | saveNaturalLanguageQuery | response | columns[].sortOrder | integer
ReportingService | saveNaturalLanguageQuery | response | columns[].sortDirection | enum (asc, desc)
ReportingService | saveNaturalLanguageQuery | response | columns[].format | string |  | (nullable)
ReportingService | saveNaturalLanguageQuery | response | filters | array of ReportFilter
ReportingService | saveNaturalLanguageQuery | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | saveNaturalLanguageQuery | response | filters[].field | string | yes
ReportingService | saveNaturalLanguageQuery | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | saveNaturalLanguageQuery | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | saveNaturalLanguageQuery | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | saveNaturalLanguageQuery | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | saveNaturalLanguageQuery | response | groupBy | array of string
ReportingService | saveNaturalLanguageQuery | response | parameters | array of ReportParameter
ReportingService | saveNaturalLanguageQuery | response | parameters[].key | string | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].label | string | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].isRequired | boolean | yes
ReportingService | saveNaturalLanguageQuery | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | saveNaturalLanguageQuery | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | saveNaturalLanguageQuery | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | saveNaturalLanguageQuery | response | id | string (uuid) | yes
ReportingService | saveNaturalLanguageQuery | response | version | string | yes | The current version.
ReportingService | saveNaturalLanguageQuery | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | saveNaturalLanguageQuery | response | isRetired | boolean | yes
ReportingService | saveNaturalLanguageQuery | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | saveNaturalLanguageQuery | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | saveNaturalLanguageQuery | response | createdAt | string (date-time) | yes
ReportingService | saveNaturalLanguageQuery | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | saveNaturalLanguageQuery | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | saveNaturalLanguageQuery | param (path) | conversationId | string | yes
ReportingService | saveNaturalLanguageQuery | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | searchCatalogue | param (query) | q | string | yes
CatalogueService | searchCatalogue | param (query) | venueId | string (uuid)
CatalogueService | searchCatalogue | param (query) | kind | enum (product, event, attraction, bundle, membership, merchandise, menuItem)
CatalogueService | searchCatalogue | param (query) | guidedAnswerIds | array of string (uuid) |  | Help me choose answers, as filters (decided 29 September, W4).
CatalogueService | searchCatalogue | param (query) | pageSize | integer
MarketingService | searchGuests | response | items | array of GuestProfile | yes
MarketingService | searchGuests | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | searchGuests | response | items[].subjectId | string (uuid) | yes | Opaque reference.
MarketingService | searchGuests | response | items[].displayName | string |  | (nullable)
MarketingService | searchGuests | response | items[].email | string |  | (nullable)
MarketingService | searchGuests | response | items[].phone | string |  | (nullable)
MarketingService | searchGuests | response | items[].preferredLanguage | string |  | (nullable)
MarketingService | searchGuests | response | items[].preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | searchGuests | response | items[].guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | searchGuests | response | items[].tags | array of string
MarketingService | searchGuests | response | items[].engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | searchGuests | response | items[].engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | searchGuests | response | items[].lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | searchGuests | response | items[].lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | searchGuests | response | items[].lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | searchGuests | response | items[].lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | searchGuests | response | items[].visitCount | integer
MarketingService | searchGuests | response | items[].lastVisitAt | string (date-time) |  | (nullable)
MarketingService | searchGuests | response | items[].isActive | boolean | yes
MarketingService | searchGuests | response | items[].mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | searchGuests | response | items[].mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | searchGuests | response | nextCursor | string
MarketingService | searchGuests | response | hasMore | boolean | yes
MarketingService | searchGuests | param (query) | search | string |  | Name, email, phone or membership number.
MarketingService | searchGuests | param (query) | segmentId | string (uuid)
MarketingService | searchGuests | param (query) | hasConsentFor | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional)
MarketingService | searchGuests | param (query) | pageSize | integer
MarketingService | searchGuests | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | searchMedia | response | items | array of MediaAsset | yes
VenueOpsService | searchMedia | response | items[].id | string (uuid) | yes
VenueOpsService | searchMedia | response | items[].kind | MediaKind: enum (image, video, audio, document, vector, font, archive) | yes
VenueOpsService | searchMedia | response | items[].status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | searchMedia | response | items[].filename | string | yes
VenueOpsService | searchMedia | response | items[].contentType | string | yes
VenueOpsService | searchMedia | response | items[].sizeBytes | integer | yes
VenueOpsService | searchMedia | response | items[].title | LocalisedText
VenueOpsService | searchMedia | response | items[].description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | searchMedia | response | items[].altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | searchMedia | response | items[].width | integer |  | (nullable)
VenueOpsService | searchMedia | response | items[].height | integer |  | (nullable)
VenueOpsService | searchMedia | response | items[].durationSeconds | number |  | (nullable)
VenueOpsService | searchMedia | response | items[].customMetadata | object |  | BL-178. (nullable)
VenueOpsService | searchMedia | response | items[].sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | searchMedia | response | items[].tags | array of string
VenueOpsService | searchMedia | response | items[].categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | searchMedia | response | items[].venueId | string (uuid) |  | (nullable)
VenueOpsService | searchMedia | response | items[].url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | searchMedia | response | items[].thumbnailUrl | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | searchMedia | response | items[].rights | MediaRights |  | Licensing terms.
VenueOpsService | searchMedia | response | items[].rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | searchMedia | response | items[].rights.licensor | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.licenceReference | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.validFrom | string (date) |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.validTo | string (date) |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | searchMedia | response | items[].rights.attributionRequired | boolean |  | (default False)
VenueOpsService | searchMedia | response | items[].rights.attributionText | string |  | (nullable)
VenueOpsService | searchMedia | response | items[].rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | searchMedia | response | items[].rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | searchMedia | response | items[].rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | searchMedia | response | items[].rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | searchMedia | response | items[].isRightsExpired | boolean
VenueOpsService | searchMedia | response | items[].version | integer
VenueOpsService | searchMedia | response | items[].uploadedByPrincipalId | string (uuid)
VenueOpsService | searchMedia | response | items[].createdAt | string (date-time) | yes
VenueOpsService | searchMedia | response | nextCursor | string
VenueOpsService | searchMedia | response | hasMore | boolean | yes
VenueOpsService | searchMedia | param (query) | kind | MediaKind: enum (image, video, audio, document, vector, font, archive)
VenueOpsService | searchMedia | param (query) | tag | string
VenueOpsService | searchMedia | param (query) | collectionId | string (uuid)
VenueOpsService | searchMedia | param (query) | venueId | string (uuid)
VenueOpsService | searchMedia | param (query) | search | string |  | Matches filename, title, description and tags.
VenueOpsService | searchMedia | param (query) | unusedOnly | boolean
VenueOpsService | searchMedia | param (query) | rightsExpiringWithinDays | integer
VenueOpsService | searchMedia | param (query) | pageSize | integer
VenueOpsService | searchMedia | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | searchTransportDepartures | response | items | array of DepartureOffer | yes
VenueOpsService | searchTransportDepartures | response | items[].departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | searchTransportDepartures | response | items[].performanceId | string (uuid) | yes
VenueOpsService | searchTransportDepartures | response | items[].routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | searchTransportDepartures | response | items[].routeCode | string |  | The price card's label, e.g.
VenueOpsService | searchTransportDepartures | response | items[].departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | searchTransportDepartures | response | items[].arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | searchTransportDepartures | response | items[].durationMinutes | integer | yes | (min 0)
VenueOpsService | searchTransportDepartures | response | items[].period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | searchTransportDepartures | response | items[].seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | searchTransportDepartures | response | items[].fitsParty | boolean
VenueOpsService | searchTransportDepartures | response | items[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | searchTransportDepartures | response | items[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | searchTransportDepartures | response | items[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | searchTransportDepartures | response | items[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | searchTransportDepartures | response | items[].partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | searchTransportDepartures | response | items[].partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | searchTransportDepartures | response | items[].partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | searchTransportDepartures | response | items[].partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | searchTransportDepartures | response | nextCursor | string
VenueOpsService | searchTransportDepartures | response | hasMore | boolean | yes
VenueOpsService | searchTransportDepartures | response | adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | searchTransportDepartures | response | adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | searchTransportDepartures | response | adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | searchTransportDepartures | response | adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | searchTransportDepartures | response | periodCounts | object | yes | Departures on sale in each period on this date.
VenueOpsService | searchTransportDepartures | response | periodCounts.morning | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | response | periodCounts.afternoon | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | response | periodCounts.evening | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | response | periodCounts.night | integer |  | (min 0)
VenueOpsService | searchTransportDepartures | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | searchTransportDepartures | param (query) | toStationId | string (uuid) | yes
VenueOpsService | searchTransportDepartures | param (query) | date | string (date) | yes | Travel date, venue local.
VenueOpsService | searchTransportDepartures | param (query) | period | TimePeriod: enum (morning, afternoon, evening, night)
VenueOpsService | searchTransportDepartures | param (query) | passengers | array of string |  | The party as code:count pairs, one per passenger type (adult:2, child:1).
VenueOpsService | searchTransportDepartures | param (query) | pageSize | integer
VenueOpsService | searchTransportDepartures | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | seatTableReservation | request | tableIds | array of string (uuid) | yes | (min items 1)
FnbService | seatTableReservation | request | actualPartySize | integer
FnbService | seatTableReservation | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | seatTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | seatTableReservation | response | outletId | string (uuid) | yes
FnbService | seatTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | seatTableReservation | response | guestName | string
FnbService | seatTableReservation | response | contactPoint | string
FnbService | seatTableReservation | response | partySize | integer | yes | (min 1)
FnbService | seatTableReservation | response | startsAt | string (date-time) | yes
FnbService | seatTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | seatTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | seatTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | seatTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | seatTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | seatTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | seatTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | seatTableReservation | response | notes | string |  | Allergies
FnbService | seatTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | seatTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | seatTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | seatTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | seatTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | seatTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | seatTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | seatTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | seatTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | seatTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | seatTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | seatTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | seatTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | seatTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | seatTableReservation | param (path) | reservationId | string (uuid) | yes
FnbService | seatTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | selectRole | request | roleId | string (uuid) | yes
IdentityService | selectRole | response | sessionId | string (uuid) | yes
IdentityService | selectRole | response | principalId | string (uuid) | yes
IdentityService | selectRole | response | roleId | string (uuid) | yes
IdentityService | selectRole | response | displayName | string
IdentityService | selectRole | response | scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | selectRole | response | scope[].id | string (uuid) | yes
IdentityService | selectRole | response | scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | selectRole | response | scope[].path | string | yes | Materialised ltree path.
IdentityService | selectRole | response | scope[].code | string |  | (nullable)
IdentityService | selectRole | response | scope[].name | string |  | (nullable)
IdentityService | selectRole | response | effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | selectRole | response | permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path.
IdentityService | selectRole | response | permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | selectRole | response | permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | selectRole | response | saleBoardId | string (uuid) | yes | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | selectRole | response | workstation | WorkstationContext
IdentityService | selectRole | response | workstation.id | string (uuid) | yes
IdentityService | selectRole | response | workstation.code | string | yes
IdentityService | selectRole | response | workstation.venueId | string (uuid) | yes
IdentityService | selectRole | response | workstation.regionId | string (uuid) | yes
IdentityService | selectRole | response | workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | selectRole | response | workstation.devices | array of object
IdentityService | selectRole | response | workstation.devices[].kind | enum (receiptPrinter, ticketPrinter, cashDrawer, barcodeScanner, rfidReader, paymentTerminal, customerDisplay) | yes
IdentityService | selectRole | response | workstation.devices[].driver | string | yes
IdentityService | selectRole | response | workstation.devices[].identifier | string
IdentityService | selectRole | response | workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | selectRole | response | workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | selectRole | response | workstation.timezone | string
IdentityService | selectRole | response | workstation.cellName | string |  | The cell serving this workstation's region.
IdentityService | selectRole | response | workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | selectRole | response | openedAt | string (date-time)
IdentityService | selectRole | response | expiresAt | string (date-time)
IdentityService | selectRole | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | semanticSearch | request | query | string | yes | (min length 2; max length 500)
AiService | semanticSearch | request | kinds | array of enum (product, entitlement, membership, document, knowledge, faq, report, media)
AiService | semanticSearch | request | limit | integer |  | (max 100; default 20)
AiService | semanticSearch | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | sendAiMessage | request | content | string | yes | (min length 1; max length 8000)
AiService | sendAiMessage | request | collectionIds | array of string (uuid) |  | Restrict retrieval to named collections.
AiService | sendAiMessage | response | id | string (uuid) | yes
AiService | sendAiMessage | response | conversationId | string (uuid) | yes
AiService | sendAiMessage | response | role | enum (user, assistant, system) | yes
AiService | sendAiMessage | response | content | string | yes
AiService | sendAiMessage | response | sources | array of AiSource |  | The sources an answer was grounded in, stored with the answer (8.3.70).
AiService | sendAiMessage | response | sources[].kind | enum (document, product, entitlement, report, record)
AiService | sendAiMessage | response | sources[].id | string
AiService | sendAiMessage | response | sources[].title | string
AiService | sendAiMessage | response | sources[].collectionId | string (uuid) |  | (nullable)
AiService | sendAiMessage | response | sources[].excerpt | string
AiService | sendAiMessage | response | sources[].relevance | number
AiService | sendAiMessage | response | confidence | number |  | 8.1.5, 8.3.67. (nullable)
AiService | sendAiMessage | response | rationale | string |  | 8.3.68, 8.3.69. (nullable)
AiService | sendAiMessage | response | proposedAction | object |  | Present where the answer suggests a change. (nullable)
AiService | sendAiMessage | response | proposedAction.id | string (uuid) | yes
AiService | sendAiMessage | response | proposedAction.interactionId | string (uuid)
AiService | sendAiMessage | response | proposedAction.kind | enum (pricing, promotion, operational, financial, configuration, content, audience) | yes | content (a marketing or storefront draft from proposeMarketingContent) and audience (a lookalike segment from proposeLookalikeSegment) added 29 September (build); both are applied by a person in the…
AiService | sendAiMessage | response | proposedAction.targetContract | string | yes | Which contract would perform it.
AiService | sendAiMessage | response | proposedAction.targetOperation | string | yes
AiService | sendAiMessage | response | proposedAction.payload | object | yes | The request body a person would submit, ready to review.
AiService | sendAiMessage | response | proposedAction.summary | string
AiService | sendAiMessage | response | proposedAction.status | enum (proposed, approved, rejected, applied, expired) | yes | Expiry (decided 28 September, audit R213): a proposed action expires 7 days after proposedAt; an approved action not applied expires 24 hours after decidedAt.
AiService | sendAiMessage | response | proposedAction.expiresAt | string (date-time) |  | When the expiry timer moves this action to expired — proposedAt plus 7 days while proposed, decidedAt plus 24 hours once approved, null once rejected, applied or expired (audit R213). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.approvalLevel | integer |  | 8.3.65. (min 1; max 2)
AiService | sendAiMessage | response | proposedAction.decidedByPrincipalId | string (uuid) |  | (nullable)
AiService | sendAiMessage | response | proposedAction.decisionReason | string |  | Required on rejection. (nullable)
AiService | sendAiMessage | response | proposedAction.proposedAt | string (date-time)
AiService | sendAiMessage | response | proposedAction.decidedAt | string (date-time) |  | (nullable)
AiService | sendAiMessage | response | proposedAction.scopePath | string |  | Added 29 September (AI design 3.1): ai.proposed_action had no policy — its only references were nullable. (read-only)
AiService | sendAiMessage | response | proposedAction.planId | string (uuid) |  | The plan this action presents for a decision (AI design 2.2 D, 3.8). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.approvalRequestId | string (uuid) |  | The approvals request deciding a tier 2 or matrix-caught action (AI design 2.3). (read-only; nullable)
AiService | sendAiMessage | response | proposedAction.changeSetHash | string |  | Hash of the change set approved; execution refuses a plan whose hash differs (AIC-181). (read-only; nullable)
AiService | sendAiMessage | response | traceId | string
AiService | sendAiMessage | response | provider | AiProviderKind: enum (openai, gemini, anthropic, azureOpenai, localLlm, openaiCompatible) |  | openaiCompatible (added 29 September, AI design 3.3): a customer endpoint that speaks the OpenAI API, taken with no custom development (AIC-009).
AiService | sendAiMessage | response | model | string
AiService | sendAiMessage | response | promptTokens | integer
AiService | sendAiMessage | response | completionTokens | integer
AiService | sendAiMessage | response | latencyMs | integer
AiService | sendAiMessage | response | createdAt | string (date-time) | yes
AiService | sendAiMessage | param (path) | conversationId | string (uuid) | yes
AiService | sendAiMessage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | sendConversationMessage | request | body | string | yes | (max length 4000)
MarketingService | sendConversationMessage | request | attachments | array of object
MarketingService | sendConversationMessage | request | attachments[].assetId | string (uuid)
MarketingService | sendConversationMessage | request | attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | sendConversationMessage | response | id | string (uuid) | yes
MarketingService | sendConversationMessage | response | sender | enum (guest, agent, assistant, system) | yes | Resolved, never declared.
MarketingService | sendConversationMessage | response | senderPrincipalId | string (uuid) |  | (nullable)
MarketingService | sendConversationMessage | response | body | string | yes
MarketingService | sendConversationMessage | response | attachments | array of object
MarketingService | sendConversationMessage | response | attachments[].assetId | string (uuid)
MarketingService | sendConversationMessage | response | attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | sendConversationMessage | response | aiInteractionId | string (uuid) |  | Where the assistant sent it. (nullable)
MarketingService | sendConversationMessage | response | sentAt | string (date-time) | yes
MarketingService | sendConversationMessage | response | readAt | string (date-time) |  | (nullable)
MarketingService | sendConversationMessage | param (path) | conversationId | string (uuid) | yes
MarketingService | sendConversationMessage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setAccessAttributeCatalog | request | attributeKey | string | yes | Stable key a policy condition names, e.g. (max length 100; pattern ^[a-z][a-zA-Z0-9]*(\.[a-z][a-zA-Z0-9]*)*$)
AccessService | setAccessAttributeCatalog | request | category | enum (guest, credential, employee, location, time, operational, device, risk) | yes
AccessService | setAccessAttributeCatalog | request | label | string | yes | (max length 200)
AccessService | setAccessAttributeCatalog | request | dataType | enum (string, integer, number, boolean, date, dateTime, enum) | yes
AccessService | setAccessAttributeCatalog | request | allowedValues | array of string |  | Required when dataType is enum
AccessService | setAccessAttributeCatalog | request | enabled | boolean |  | (default True)
AccessService | setAccessAttributeCatalog | response | category | enum (guest, credential, employee, location, time, operational, device, risk) | yes
AccessService | setAccessAttributeCatalog | response | attributeKey | string | yes | Dotted governed key, e.g.
AccessService | setAccessAttributeCatalog | response | label | string
AccessService | setAccessAttributeCatalog | response | dataType | enum (string, integer, number, boolean, date, dateTime, enum)
AccessService | setAccessAttributeCatalog | response | allowedValues | array of string |  | For enum attributes, e.g.
AccessService | setAccessAttributeCatalog | response | enabled | boolean |  | Whether the venue may use this attribute in policies (e.g.
AccessService | setAccessAttributeCatalog | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setAccessPointGeofence | request | latitude | number
AccessService | setAccessPointGeofence | request | longitude | number
AccessService | setAccessPointGeofence | request | radiusMetres | integer |  | (min 5; max 5000)
AccessService | setAccessPointGeofence | request | enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setAccessPointGeofence | request | allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setAccessPointGeofence | response | id | string (uuid) | yes
AccessService | setAccessPointGeofence | response | code | string | yes
AccessService | setAccessPointGeofence | response | name | string | yes
AccessService | setAccessPointGeofence | response | venueId | string (uuid) | yes
AccessService | setAccessPointGeofence | response | scopePath | string
AccessService | setAccessPointGeofence | response | externalCredentialSources | object |  | BL-108.
AccessService | setAccessPointGeofence | response | scanAnomalyRules | object |  | BL-104.
AccessService | setAccessPointGeofence | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | setAccessPointGeofence | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | setAccessPointGeofence | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | setAccessPointGeofence | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | setAccessPointGeofence | response | antiPassbackEnabled | boolean
AccessService | setAccessPointGeofence | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | setAccessPointGeofence | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | setAccessPointGeofence | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | setAccessPointGeofence | response | geofence.latitude | number
AccessService | setAccessPointGeofence | response | geofence.longitude | number
AccessService | setAccessPointGeofence | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | setAccessPointGeofence | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setAccessPointGeofence | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setAccessPointGeofence | response | isActive | boolean | yes
AccessService | setAccessPointGeofence | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | setAccessPointGeofence | param (path) | accessPointId | string (uuid) | yes
AccessService | setAccessPointGeofence | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setAccessPointGroup | request | id | string (uuid) | yes
AccessService | setAccessPointGroup | request | venueId | string (uuid) | yes
AccessService | setAccessPointGroup | request | name | string | yes | Group name, e.g.
AccessService | setAccessPointGroup | request | parentGroupId | string (uuid) |  | Enclosing group, for nested groups (nullable)
AccessService | setAccessPointGroup | request | accessPointIds | array of string (uuid) |  | Member access points (access.access_point)
AccessService | setAccessPointGroup | request | scopePath | string | yes | ltree of the owning scope node (ADR-0005)
AccessService | setAccessPointGroup | request | createdAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | request | updatedAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | response | id | string (uuid) | yes
AccessService | setAccessPointGroup | response | venueId | string (uuid) | yes
AccessService | setAccessPointGroup | response | name | string | yes | Group name, e.g.
AccessService | setAccessPointGroup | response | parentGroupId | string (uuid) |  | Enclosing group, for nested groups (nullable)
AccessService | setAccessPointGroup | response | accessPointIds | array of string (uuid) |  | Member access points (access.access_point)
AccessService | setAccessPointGroup | response | scopePath | string | yes | ltree of the owning scope node (ADR-0005)
AccessService | setAccessPointGroup | response | createdAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | response | updatedAt | string (date-time) |  | (read-only)
AccessService | setAccessPointGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setAgentAvailability | request | state | enum (available, busy, away, offline) | yes
MarketingService | setAgentAvailability | request | maxConcurrent | integer |  | How many conversations this agent takes at once.
MarketingService | setAgentAvailability | request | queueIds | array of string (uuid)
MarketingService | setAgentAvailability | response | id | string (uuid) |  | (read-only)
MarketingService | setAgentAvailability | response | principalId | string (uuid) | yes | The caller. (read-only)
MarketingService | setAgentAvailability | response | state | enum (available, busy, away, offline) | yes
MarketingService | setAgentAvailability | response | maxConcurrent | integer |  | (nullable)
MarketingService | setAgentAvailability | response | queueIds | array of string (uuid)
MarketingService | setAgentAvailability | response | expiresAt | string (date-time) |  | When this state lapses on its own — availability expires rather than persisting through a closed laptop. (read-only; nullable)
MarketingService | setAgentAvailability | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setAgentAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiByokEnablement | request | id | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | request | tenantId | string (uuid) | yes
AiService | setAiByokEnablement | request | enabled | boolean | yes
AiService | setAiByokEnablement | request | coverage | enum (perTask, allTasks) |  | Whether the tenant may supply a key per task or one key for everything. (default perTask)
AiService | setAiByokEnablement | request | allowedTasks | array of string |  | Where coverage is perTask: the gateway tasks a tenant key may serve.
AiService | setAiByokEnablement | request | reason | string |  | (max length 1000)
AiService | setAiByokEnablement | request | platformStaffGrantId | string (uuid) |  | The open platform-staff grant the change was made under (audit R098). (read-only)
AiService | setAiByokEnablement | request | decidedByPrincipalId | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | request | decidedAt | string (date-time) |  | (read-only)
AiService | setAiByokEnablement | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiByokEnablement | response | id | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | response | tenantId | string (uuid) | yes
AiService | setAiByokEnablement | response | enabled | boolean | yes
AiService | setAiByokEnablement | response | coverage | enum (perTask, allTasks) |  | Whether the tenant may supply a key per task or one key for everything. (default perTask)
AiService | setAiByokEnablement | response | allowedTasks | array of string |  | Where coverage is perTask: the gateway tasks a tenant key may serve.
AiService | setAiByokEnablement | response | reason | string |  | (max length 1000)
AiService | setAiByokEnablement | response | platformStaffGrantId | string (uuid) |  | The open platform-staff grant the change was made under (audit R098). (read-only)
AiService | setAiByokEnablement | response | decidedByPrincipalId | string (uuid) |  | (read-only)
AiService | setAiByokEnablement | response | decidedAt | string (date-time) |  | (read-only)
AiService | setAiByokEnablement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiByokEnablement | param (path) | tenantId | string (uuid) | yes
AiService | setAiByokEnablement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiCredential | request | secret | string (password) | yes | Write-only, never returned, never logged, never in an ai.interaction.
AiService | setAiCredential | request | expiresAt | string (date-time) |  | (nullable)
AiService | setAiCredential | request | graceMinutes | integer |  | How long the previous key stays valid, so in-flight requests survive. (min 0; max 1440; default 1440)
AiService | setAiCredential | response | id | string (uuid) |  | Assigned on create.
AiService | setAiCredential | response | kind | AiProviderKind: enum (openai, gemini, anthropic, azureOpenai, localLlm, openaiCompatible) | yes | openaiCompatible (added 29 September, AI design 3.3): a customer endpoint that speaks the OpenAI API, taken with no custom development (AIC-009).
AiService | setAiCredential | response | capability | AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech) | yes | What a capability needs, not which provider serves it.
AiService | setAiCredential | response | model | string
AiService | setAiCredential | response | failoverProviderId | string (uuid) |  | BL-151. (nullable)
AiService | setAiCredential | response | degradeGracefully | boolean |  | Where no fallback answers, the surface degrades rather than errors. (default True)
AiService | setAiCredential | response | priority | integer | yes | Failover order (8.4.26).
AiService | setAiCredential | response | scopeLevel | enum (platform, tenant, venue) |  | Where this provider configuration applies, and therefore whose token pays for it.
AiService | setAiCredential | response | scopePath | string |  | Resolved scope node.
AiService | setAiCredential | response | tenantId | string (uuid) |  | Null only where scopeLevel is platform. (nullable)
AiService | setAiCredential | response | credentialRef | string |  | A key-vault reference, never the key.
AiService | setAiCredential | response | credentialRotatedAt | string (date-time) |  | (read-only; nullable)
AiService | setAiCredential | response | credentialExpiresAt | string (date-time) |  | Where the provider issues expiring keys. (nullable)
AiService | setAiCredential | response | lastVerifiedAt | string (date-time) |  | When testAiProvider last confirmed the key works. (read-only; nullable)
AiService | setAiCredential | response | endpoint | string |  | (nullable)
AiService | setAiCredential | response | residency | string |  | Where inference physically happens.
AiService | setAiCredential | response | maxTokens | integer
AiService | setAiCredential | response | isActive | boolean | yes
AiService | setAiCredential | response | managedBy | enum (ticvai, tenant) |  | Who holds the provider account, and so who pays (AI design 5.9, decided 29 September). (default ticvai)
AiService | setAiCredential | response | modelId | string (uuid) |  | The model in the catalogue (listAiModels) this provider serves. (nullable)
AiService | setAiCredential | response | taskKeys | array of string |  | Which agent tasks this provider serves (21 September minutes, M21-03: different agents may use different models chosen for the task).
AiService | setAiCredential | response | fitnessWarnings | array of object |  | The model-fitness check at the last write (21 September minutes, M21-09). (read-only)
AiService | setAiCredential | response | fitnessWarnings[].taskKey | string
AiService | setAiCredential | response | fitnessWarnings[].score | number |  | (nullable)
AiService | setAiCredential | response | fitnessWarnings[].floor | number
AiService | setAiCredential | response | fitnessWarnings[].direction | enum (underpowered, overpowered, unscored)
AiService | setAiCredential | param (path) | providerId | string (uuid) | yes
AiService | setAiCredential | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiModel | request | id | string (uuid) |  | (read-only)
AiService | setAiModel | request | layer | enum (platform, tenant) | yes
AiService | setAiModel | request | providerKind | object |  | (nullable)
AiService | setAiModel | request | producerType | enum (llm, embedding, reranker, classical, rule) | yes
AiService | setAiModel | request | modelName | string | yes | The deployment or model name as the provider knows it, or the package and version for a classical model.
AiService | setAiModel | request | capabilities | array of AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech)
AiService | setAiModel | request | contextTokens | integer |  | (nullable)
AiService | setAiModel | request | toolCalling | boolean |  | (default False)
AiService | setAiModel | request | structuredOutput | boolean |  | (default False)
AiService | setAiModel | request | languages | array of string
AiService | setAiModel | request | residency | string |  | Where inference happens. (nullable)
AiService | setAiModel | request | inputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | request | inputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | request | inputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | request | inputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | request | outputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | request | outputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | request | outputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | request | outputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | request | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | setAiModel | request | lifecycle.development | enum (draft, pilot, active, retired)
AiService | setAiModel | request | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | setAiModel | request | lifecycle.production | enum (draft, pilot, active, retired)
AiService | setAiModel | request | isDefaultForTasks | array of string |  | Tasks this model is the default for (AIC-010), e.g.
AiService | setAiModel | request | taskFitness | array of object |  | Evaluated fitness per task (21 September minutes, M21-09, our proposal): a score from the task's golden set (runAiEvaluation) and the band the task needs. (read-only)
AiService | setAiModel | request | taskFitness[].taskKey | string | yes
AiService | setAiModel | request | taskFitness[].score | number | yes | (min 0; max 1)
AiService | setAiModel | request | taskFitness[].floor | number |  | (min 0; max 1)
AiService | setAiModel | request | taskFitness[].ceiling | number |  | (min 0; max 1; nullable)
AiService | setAiModel | request | taskFitness[].evaluationRunId | string (uuid) |  | (nullable)
AiService | setAiModel | request | taskFitness[].evaluatedAt | string (date-time)
AiService | setAiModel | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiModel | response | id | string (uuid) |  | (read-only)
AiService | setAiModel | response | layer | enum (platform, tenant) | yes
AiService | setAiModel | response | providerKind | object |  | (nullable)
AiService | setAiModel | response | producerType | enum (llm, embedding, reranker, classical, rule) | yes
AiService | setAiModel | response | modelName | string | yes | The deployment or model name as the provider knows it, or the package and version for a classical model.
AiService | setAiModel | response | capabilities | array of AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech)
AiService | setAiModel | response | contextTokens | integer |  | (nullable)
AiService | setAiModel | response | toolCalling | boolean |  | (default False)
AiService | setAiModel | response | structuredOutput | boolean |  | (default False)
AiService | setAiModel | response | languages | array of string
AiService | setAiModel | response | residency | string |  | Where inference happens. (nullable)
AiService | setAiModel | response | inputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | response | inputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | response | inputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | response | inputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | response | outputCostPerMillionTokens | object |  | (nullable)
AiService | setAiModel | response | outputCostPerMillionTokens.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiModel | response | outputCostPerMillionTokens.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiModel | response | outputCostPerMillionTokens.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiModel | response | lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | setAiModel | response | lifecycle.development | enum (draft, pilot, active, retired)
AiService | setAiModel | response | lifecycle.staging | enum (draft, pilot, active, retired)
AiService | setAiModel | response | lifecycle.production | enum (draft, pilot, active, retired)
AiService | setAiModel | response | isDefaultForTasks | array of string |  | Tasks this model is the default for (AIC-010), e.g.
AiService | setAiModel | response | taskFitness | array of object |  | Evaluated fitness per task (21 September minutes, M21-09, our proposal): a score from the task's golden set (runAiEvaluation) and the band the task needs. (read-only)
AiService | setAiModel | response | taskFitness[].taskKey | string | yes
AiService | setAiModel | response | taskFitness[].score | number | yes | (min 0; max 1)
AiService | setAiModel | response | taskFitness[].floor | number |  | (min 0; max 1)
AiService | setAiModel | response | taskFitness[].ceiling | number |  | (min 0; max 1; nullable)
AiService | setAiModel | response | taskFitness[].evaluationRunId | string (uuid) |  | (nullable)
AiService | setAiModel | response | taskFitness[].evaluatedAt | string (date-time)
AiService | setAiModel | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiModel | param (path) | modelId | string (uuid) | yes
AiService | setAiModel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiPolicy | request | id | string (uuid) |  | Added 20 August. (read-only)
AiService | setAiPolicy | request | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | setAiPolicy | request | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue.
AiService | setAiPolicy | request | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | setAiPolicy | request | allowedRoleIds | array of string (uuid)
AiService | setAiPolicy | request | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | setAiPolicy | request | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | setAiPolicy | request | monthlyTokenCeiling | integer |  | (nullable)
AiService | setAiPolicy | request | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | setAiPolicy | request | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | setAiPolicy | request | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | setAiPolicy | request | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | setAiPolicy | request | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | setAiPolicy | request | autonomyOverrides[].capabilityKey | string | yes
AiService | setAiPolicy | request | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | setAiPolicy | request | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | setAiPolicy | request | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | setAiPolicy | request | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | setAiPolicy | request | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | setAiPolicy | request | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | setAiPolicy | request | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | setAiPolicy | request | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | setAiPolicy | request | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | setAiPolicy | request | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | setAiPolicy | request | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | setAiPolicy | request | cascade.smallModel | string
AiService | setAiPolicy | request | cascade.largeModel | string
AiService | setAiPolicy | request | cascade.escalateBelow | number |  | (default 0.7)
AiService | setAiPolicy | request | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | setAiPolicy | request | chunking.sizeTokens | integer |  | (default 512)
AiService | setAiPolicy | request | chunking.overlapTokens | integer |  | (default 64)
AiService | setAiPolicy | request | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | setAiPolicy | request | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | setAiPolicy | request | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | setAiPolicy | request | hnsw.m | integer |  | (default 16)
AiService | setAiPolicy | request | hnsw.efConstruct | integer |  | (default 128)
AiService | setAiPolicy | request | hnsw.efSearch | integer |  | (default 64)
AiService | setAiPolicy | request | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | setAiPolicy | request | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | setAiPolicy | request | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | setAiPolicy | request | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | setAiPolicy | request | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | setAiPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
AiService | setAiPolicy | response | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | setAiPolicy | response | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue.
AiService | setAiPolicy | response | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | setAiPolicy | response | allowedRoleIds | array of string (uuid)
AiService | setAiPolicy | response | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | setAiPolicy | response | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | setAiPolicy | response | monthlyTokenCeiling | integer |  | (nullable)
AiService | setAiPolicy | response | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | setAiPolicy | response | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | setAiPolicy | response | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | setAiPolicy | response | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | setAiPolicy | response | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | setAiPolicy | response | autonomyOverrides[].capabilityKey | string | yes
AiService | setAiPolicy | response | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | setAiPolicy | response | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | setAiPolicy | response | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | setAiPolicy | response | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | setAiPolicy | response | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | setAiPolicy | response | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | setAiPolicy | response | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | setAiPolicy | response | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | setAiPolicy | response | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | setAiPolicy | response | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | setAiPolicy | response | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | setAiPolicy | response | cascade.smallModel | string
AiService | setAiPolicy | response | cascade.largeModel | string
AiService | setAiPolicy | response | cascade.escalateBelow | number |  | (default 0.7)
AiService | setAiPolicy | response | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | setAiPolicy | response | chunking.sizeTokens | integer |  | (default 512)
AiService | setAiPolicy | response | chunking.overlapTokens | integer |  | (default 64)
AiService | setAiPolicy | response | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | setAiPolicy | response | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | setAiPolicy | response | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | setAiPolicy | response | hnsw.m | integer |  | (default 16)
AiService | setAiPolicy | response | hnsw.efConstruct | integer |  | (default 128)
AiService | setAiPolicy | response | hnsw.efSearch | integer |  | (default 64)
AiService | setAiPolicy | response | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | setAiPolicy | response | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | setAiPolicy | response | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | setAiPolicy | response | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | setAiPolicy | response | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | setAiPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiProvider | request | id | string (uuid) |  | Assigned on create.
AiService | setAiProvider | request | kind | AiProviderKind: enum (openai, gemini, anthropic, azureOpenai, localLlm, openaiCompatible) | yes | openaiCompatible (added 29 September, AI design 3.3): a customer endpoint that speaks the OpenAI API, taken with no custom development (AIC-009).
AiService | setAiProvider | request | capability | AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech) | yes | What a capability needs, not which provider serves it.
AiService | setAiProvider | request | model | string
AiService | setAiProvider | request | failoverProviderId | string (uuid) |  | BL-151. (nullable)
AiService | setAiProvider | request | degradeGracefully | boolean |  | Where no fallback answers, the surface degrades rather than errors. (default True)
AiService | setAiProvider | request | priority | integer | yes | Failover order (8.4.26).
AiService | setAiProvider | request | scopeLevel | enum (platform, tenant, venue) |  | Where this provider configuration applies, and therefore whose token pays for it.
AiService | setAiProvider | request | scopePath | string |  | Resolved scope node.
AiService | setAiProvider | request | tenantId | string (uuid) |  | Null only where scopeLevel is platform. (nullable)
AiService | setAiProvider | request | credentialRef | string |  | A key-vault reference, never the key.
AiService | setAiProvider | request | credentialRotatedAt | string (date-time) |  | (read-only; nullable)
AiService | setAiProvider | request | credentialExpiresAt | string (date-time) |  | Where the provider issues expiring keys. (nullable)
AiService | setAiProvider | request | lastVerifiedAt | string (date-time) |  | When testAiProvider last confirmed the key works. (read-only; nullable)
AiService | setAiProvider | request | endpoint | string |  | (nullable)
AiService | setAiProvider | request | residency | string |  | Where inference physically happens.
AiService | setAiProvider | request | maxTokens | integer
AiService | setAiProvider | request | isActive | boolean | yes
AiService | setAiProvider | request | managedBy | enum (ticvai, tenant) |  | Who holds the provider account, and so who pays (AI design 5.9, decided 29 September). (default ticvai)
AiService | setAiProvider | request | modelId | string (uuid) |  | The model in the catalogue (listAiModels) this provider serves. (nullable)
AiService | setAiProvider | request | taskKeys | array of string |  | Which agent tasks this provider serves (21 September minutes, M21-03: different agents may use different models chosen for the task).
AiService | setAiProvider | request | fitnessWarnings | array of object |  | The model-fitness check at the last write (21 September minutes, M21-09). (read-only)
AiService | setAiProvider | request | fitnessWarnings[].taskKey | string
AiService | setAiProvider | request | fitnessWarnings[].score | number |  | (nullable)
AiService | setAiProvider | request | fitnessWarnings[].floor | number
AiService | setAiProvider | request | fitnessWarnings[].direction | enum (underpowered, overpowered, unscored)
AiService | setAiProvider | response | id | string (uuid) |  | Assigned on create.
AiService | setAiProvider | response | kind | AiProviderKind: enum (openai, gemini, anthropic, azureOpenai, localLlm, openaiCompatible) | yes | openaiCompatible (added 29 September, AI design 3.3): a customer endpoint that speaks the OpenAI API, taken with no custom development (AIC-009).
AiService | setAiProvider | response | capability | AiCapability: enum (chat, embedding, vision, rerank, speechToText, textToSpeech) | yes | What a capability needs, not which provider serves it.
AiService | setAiProvider | response | model | string
AiService | setAiProvider | response | failoverProviderId | string (uuid) |  | BL-151. (nullable)
AiService | setAiProvider | response | degradeGracefully | boolean |  | Where no fallback answers, the surface degrades rather than errors. (default True)
AiService | setAiProvider | response | priority | integer | yes | Failover order (8.4.26).
AiService | setAiProvider | response | scopeLevel | enum (platform, tenant, venue) |  | Where this provider configuration applies, and therefore whose token pays for it.
AiService | setAiProvider | response | scopePath | string |  | Resolved scope node.
AiService | setAiProvider | response | tenantId | string (uuid) |  | Null only where scopeLevel is platform. (nullable)
AiService | setAiProvider | response | credentialRef | string |  | A key-vault reference, never the key.
AiService | setAiProvider | response | credentialRotatedAt | string (date-time) |  | (read-only; nullable)
AiService | setAiProvider | response | credentialExpiresAt | string (date-time) |  | Where the provider issues expiring keys. (nullable)
AiService | setAiProvider | response | lastVerifiedAt | string (date-time) |  | When testAiProvider last confirmed the key works. (read-only; nullable)
AiService | setAiProvider | response | endpoint | string |  | (nullable)
AiService | setAiProvider | response | residency | string |  | Where inference physically happens.
AiService | setAiProvider | response | maxTokens | integer
AiService | setAiProvider | response | isActive | boolean | yes
AiService | setAiProvider | response | managedBy | enum (ticvai, tenant) |  | Who holds the provider account, and so who pays (AI design 5.9, decided 29 September). (default ticvai)
AiService | setAiProvider | response | modelId | string (uuid) |  | The model in the catalogue (listAiModels) this provider serves. (nullable)
AiService | setAiProvider | response | taskKeys | array of string |  | Which agent tasks this provider serves (21 September minutes, M21-03: different agents may use different models chosen for the task).
AiService | setAiProvider | response | fitnessWarnings | array of object |  | The model-fitness check at the last write (21 September minutes, M21-09). (read-only)
AiService | setAiProvider | response | fitnessWarnings[].taskKey | string
AiService | setAiProvider | response | fitnessWarnings[].score | number |  | (nullable)
AiService | setAiProvider | response | fitnessWarnings[].floor | number
AiService | setAiProvider | response | fitnessWarnings[].direction | enum (underpowered, overpowered, unscored)
AiService | setAiProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setAiVenueSettings | request | id | string (uuid) |  | (read-only)
AiService | setAiVenueSettings | request | venueId | string (uuid) | yes
AiService | setAiVenueSettings | request | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | setAiVenueSettings | request | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | setAiVenueSettings | request | capacity | integer |  | (min 1; nullable)
AiService | setAiVenueSettings | request | openingHours | array of object |  | The usual week.
AiService | setAiVenueSettings | request | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | setAiVenueSettings | request | openingHours[].opensAt | string
AiService | setAiVenueSettings | request | openingHours[].closesAt | string
AiService | setAiVenueSettings | request | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | request | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | request | peakMonths | array of integer
AiService | setAiVenueSettings | request | averageSpend | object |  | (nullable)
AiService | setAiVenueSettings | request | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiVenueSettings | request | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiVenueSettings | request | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiVenueSettings | request | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | setAiVenueSettings | request | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | setAiVenueSettings | request | startingPatternKey | string |  | The pattern and version in use, e.g. (read-only)
AiService | setAiVenueSettings | request | updatedAt | string (date-time) |  | (read-only)
AiService | setAiVenueSettings | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiVenueSettings | response | id | string (uuid) |  | (read-only)
AiService | setAiVenueSettings | response | venueId | string (uuid) | yes
AiService | setAiVenueSettings | response | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | setAiVenueSettings | response | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | setAiVenueSettings | response | capacity | integer |  | (min 1; nullable)
AiService | setAiVenueSettings | response | openingHours | array of object |  | The usual week.
AiService | setAiVenueSettings | response | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | setAiVenueSettings | response | openingHours[].opensAt | string
AiService | setAiVenueSettings | response | openingHours[].closesAt | string
AiService | setAiVenueSettings | response | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | response | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | setAiVenueSettings | response | peakMonths | array of integer
AiService | setAiVenueSettings | response | averageSpend | object |  | (nullable)
AiService | setAiVenueSettings | response | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | setAiVenueSettings | response | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | setAiVenueSettings | response | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | setAiVenueSettings | response | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | setAiVenueSettings | response | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | setAiVenueSettings | response | startingPatternKey | string |  | The pattern and version in use, e.g. (read-only)
AiService | setAiVenueSettings | response | updatedAt | string (date-time) |  | (read-only)
AiService | setAiVenueSettings | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | setAiVenueSettings | param (path) | venueId | string (uuid) | yes
AiService | setAiVenueSettings | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | setAlertRule | request | id | string (uuid) | yes
ReportingService | setAlertRule | request | name | string | yes
ReportingService | setAlertRule | request | metric | object | yes | From the closed set, so a rule cannot watch something nothing produces — the same discipline MetricSource exists for.
ReportingService | setAlertRule | request | comparator | enum (above, below, outsideRange, changesBy, equals) | yes
ReportingService | setAlertRule | request | threshold | number or Money | yes | A reading of a metric or KPI, or a threshold on one.
ReportingService | setAlertRule | request | thresholdUpper | object |  | Required when comparator is outsideRange (decided 28 September, audit R158): the range is threshold to thresholdUpper, and a rule missing either, or with the upper not above the lower, is refused by… (nullable)
ReportingService | setAlertRule | request | windowMinutes | integer |  | The window is what stops an alert firing on noise. (default 15)
ReportingService | setAlertRule | request | severity | AlertSeverity: enum (info, warning, critical) | yes | How urgent an alert rule's breach is.
ReportingService | setAlertRule | request | deliverTo | array of enum (dashboardPanel, email, whatsapp, sms, push) |  | CF-134.
ReportingService | setAlertRule | request | recipientRoleIds | array of string (uuid)
ReportingService | setAlertRule | request | cooldownMinutes | integer |  | How long before the same rule may fire again. (default 30)
ReportingService | setAlertRule | request | isActive | boolean | yes
ReportingService | setAlertRule | request | scopePath | string | yes | The partition key (ADR-0005).
ReportingService | setAlertRule | response | id | string (uuid) | yes
ReportingService | setAlertRule | response | name | string | yes
ReportingService | setAlertRule | response | metric | object | yes | From the closed set, so a rule cannot watch something nothing produces — the same discipline MetricSource exists for.
ReportingService | setAlertRule | response | comparator | enum (above, below, outsideRange, changesBy, equals) | yes
ReportingService | setAlertRule | response | threshold | number or Money | yes | A reading of a metric or KPI, or a threshold on one.
ReportingService | setAlertRule | response | thresholdUpper | object |  | Required when comparator is outsideRange (decided 28 September, audit R158): the range is threshold to thresholdUpper, and a rule missing either, or with the upper not above the lower, is refused by… (nullable)
ReportingService | setAlertRule | response | windowMinutes | integer |  | The window is what stops an alert firing on noise. (default 15)
ReportingService | setAlertRule | response | severity | AlertSeverity: enum (info, warning, critical) | yes | How urgent an alert rule's breach is.
ReportingService | setAlertRule | response | deliverTo | array of enum (dashboardPanel, email, whatsapp, sms, push) |  | CF-134.
ReportingService | setAlertRule | response | recipientRoleIds | array of string (uuid)
ReportingService | setAlertRule | response | cooldownMinutes | integer |  | How long before the same rule may fire again. (default 30)
ReportingService | setAlertRule | response | isActive | boolean | yes
ReportingService | setAlertRule | response | scopePath | string | yes | The partition key (ADR-0005).
ReportingService | setAlertRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setAlternativeCodes | request | codes | array of AlternativeCode | yes
CatalogueService | setAlternativeCodes | request | codes[].code | string | yes | (max length 128)
CatalogueService | setAlternativeCodes | request | codes[].partnerId | string (uuid) | yes
CatalogueService | setAlternativeCodes | request | codes[].partnerName | string
CatalogueService | setAlternativeCodes | request | codes[].variantId | string (uuid)
CatalogueService | setAlternativeCodes | request | codes[].note | string |  | (max length 200)
CatalogueService | setAlternativeCodes | param (path) | productId | string (uuid) | yes
CatalogueService | setAlternativeCodes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setAnalyticsProvider | request | id | string (uuid) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | request | venueId | string (uuid) |  | (nullable)
WhiteLabelService | setAnalyticsProvider | request | provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | setAnalyticsProvider | request | providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | request | measurementId | string | yes | What the tag or SDK reports to (GA4 G-..., Tag Manager GTM-..., a pixel id). (max length 100)
WhiteLabelService | setAnalyticsProvider | request | surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | setAnalyticsProvider | request | consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | setAnalyticsProvider | request | isEnabled | boolean | yes | (default True)
WhiteLabelService | setAnalyticsProvider | request | reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | request | reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | setAnalyticsProvider | request | hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | setAnalyticsProvider | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setAnalyticsProvider | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | response | id | string (uuid) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | response | venueId | string (uuid) |  | (nullable)
WhiteLabelService | setAnalyticsProvider | response | provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | setAnalyticsProvider | response | providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | response | measurementId | string | yes | What the tag or SDK reports to (GA4 G-..., Tag Manager GTM-..., a pixel id). (max length 100)
WhiteLabelService | setAnalyticsProvider | response | surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | setAnalyticsProvider | response | consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | setAnalyticsProvider | response | isEnabled | boolean | yes | (default True)
WhiteLabelService | setAnalyticsProvider | response | reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | setAnalyticsProvider | response | reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | setAnalyticsProvider | response | hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | setAnalyticsProvider | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setAnalyticsProvider | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setAnalyticsProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setApiLicensing | request | id | string (uuid) |  | Added 20 August. (read-only)
PlatformService | setApiLicensing | request | tenantId | string (uuid) | yes
PlatformService | setApiLicensing | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | The example in the requirement is the shape: a venue licensing the ticketing API and not the F&B one.
PlatformService | setApiLicensing | request | callAllowancePerMonth | integer |  | (nullable)
PlatformService | setApiLicensing | request | catalogueWriteException | object |  | M17-04: the one way a client reaches a catalogue write, set by TICVAI platform staff only (setApiLicensing refuses anyone else 403 platform-staff-only). (nullable)
PlatformService | setApiLicensing | request | catalogueWriteException.clientId | string (uuid) | yes
PlatformService | setApiLicensing | request | catalogueWriteException.operationIds | array of enum (createProduct, updateProduct, setProductAttributes, createPriceList, updatePriceList, copyPriceList, setPrices, createChannelCapacity, …) | yes | (min items 1)
PlatformService | setApiLicensing | request | catalogueWriteException.reason | string | yes | (max length 500)
PlatformService | setApiLicensing | request | catalogueWriteException.grantedByPrincipalId | string (uuid) |  | (read-only)
PlatformService | setApiLicensing | request | catalogueWriteException.grantedUntil | string (date) | yes
PlatformService | setApiLicensing | request | overageRatePerThousand | number |  | (nullable)
PlatformService | setApiLicensing | request | revenueSharePercent | number |  | (nullable)
PlatformService | setApiLicensing | request | effectiveFrom | string (date)
PlatformService | setApiLicensing | request | effectiveTo | string (date) |  | (nullable)
PlatformService | setApiLicensing | response | id | string (uuid) |  | Added 20 August. (read-only)
PlatformService | setApiLicensing | response | tenantId | string (uuid) | yes
PlatformService | setApiLicensing | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | The example in the requirement is the shape: a venue licensing the ticketing API and not the F&B one.
PlatformService | setApiLicensing | response | callAllowancePerMonth | integer |  | (nullable)
PlatformService | setApiLicensing | response | catalogueWriteException | object |  | M17-04: the one way a client reaches a catalogue write, set by TICVAI platform staff only (setApiLicensing refuses anyone else 403 platform-staff-only). (nullable)
PlatformService | setApiLicensing | response | catalogueWriteException.clientId | string (uuid) | yes
PlatformService | setApiLicensing | response | catalogueWriteException.operationIds | array of enum (createProduct, updateProduct, setProductAttributes, createPriceList, updatePriceList, copyPriceList, setPrices, createChannelCapacity, …) | yes | (min items 1)
PlatformService | setApiLicensing | response | catalogueWriteException.reason | string | yes | (max length 500)
PlatformService | setApiLicensing | response | catalogueWriteException.grantedByPrincipalId | string (uuid) |  | (read-only)
PlatformService | setApiLicensing | response | catalogueWriteException.grantedUntil | string (date) | yes
PlatformService | setApiLicensing | response | overageRatePerThousand | number |  | (nullable)
PlatformService | setApiLicensing | response | revenueSharePercent | number |  | (nullable)
PlatformService | setApiLicensing | response | effectiveFrom | string (date)
PlatformService | setApiLicensing | response | effectiveTo | string (date) |  | (nullable)
PlatformService | setApiLicensing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setAppIcons | request | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source, from assets createUpload then completeUpload.
WhiteLabelService | setAppIcons | response | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | setAppIcons | response | derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | setAppIcons | response | derived[].platform | enum (ios, android, web)
WhiteLabelService | setAppIcons | response | derived[].size | string
WhiteLabelService | setAppIcons | response | derived[].assetRef | string (uuid)
WhiteLabelService | setAppIcons | response | changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | setAppIcons | response | liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | setAppIcons | response | requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | setAppIcons | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setApprovalExternalProvider | request | id | string (uuid) |  | (read-only)
TenancyService | setApprovalExternalProvider | request | code | string | yes | The provider's stable name, and the key setApprovalExternalProvider upserts on.
TenancyService | setApprovalExternalProvider | request | name | string | yes
TenancyService | setApprovalExternalProvider | request | endpointUrl | string | yes | https only.
TenancyService | setApprovalExternalProvider | request | outboundAuth | enum (bearerToken, basic, oauthClientCredentials, mutualTls) |  | (default oauthClientCredentials)
TenancyService | setApprovalExternalProvider | request | outboundCredential | string (password) |  | The credential TICVAI presents to the provider. (nullable)
TenancyService | setApprovalExternalProvider | request | signingSecret | string (password) |  | Signs every request TICVAI sends, as webhook deliveries are signed, so the provider can tell it came from TICVAI. (nullable)
TenancyService | setApprovalExternalProvider | request | apiClientId | string (uuid) | yes | The public-api client the provider calls back as.
TenancyService | setApprovalExternalProvider | request | requestMapping | array of object |  | Which request fields go to the provider, under which names.
TenancyService | setApprovalExternalProvider | request | requestMapping[].from | string | yes | A field of ApprovalRequest, e.g.
TenancyService | setApprovalExternalProvider | request | requestMapping[].to | string | yes | The provider's field name.
TenancyService | setApprovalExternalProvider | request | decisionMapping | array of object | yes | The provider's outcome values and the decision each means. (min items 2)
TenancyService | setApprovalExternalProvider | request | decisionMapping[].externalValue | string | yes
TenancyService | setApprovalExternalProvider | request | decisionMapping[].decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | setApprovalExternalProvider | request | timeoutMinutes | integer |  | How long a level waits for the provider before onTimeout applies. (default 1440)
TenancyService | setApprovalExternalProvider | request | onTimeout | enum (fallBackToRoles, escalate, reject) |  | (default fallBackToRoles)
TenancyService | setApprovalExternalProvider | request | maxAttempts | integer |  | Delivery attempts, with backoff, before a dispatch is failed and the level falls back as on timeout. (default 5)
TenancyService | setApprovalExternalProvider | request | status | enum (active, paused, disabled) |  | paused sends nothing and every level that names it falls back at once; the platform sets disabled after repeated failures, as it disables a failing webhook. (default active)
TenancyService | setApprovalExternalProvider | request | lastSuccessAt | string (date-time) |  | (read-only; nullable)
TenancyService | setApprovalExternalProvider | request | scopePath | string |  | (read-only)
TenancyService | setApprovalExternalProvider | response | id | string (uuid) |  | (read-only)
TenancyService | setApprovalExternalProvider | response | code | string | yes | The provider's stable name, and the key setApprovalExternalProvider upserts on.
TenancyService | setApprovalExternalProvider | response | name | string | yes
TenancyService | setApprovalExternalProvider | response | endpointUrl | string | yes | https only.
TenancyService | setApprovalExternalProvider | response | outboundAuth | enum (bearerToken, basic, oauthClientCredentials, mutualTls) |  | (default oauthClientCredentials)
TenancyService | setApprovalExternalProvider | response | outboundCredential | string (password) |  | The credential TICVAI presents to the provider. (nullable)
TenancyService | setApprovalExternalProvider | response | signingSecret | string (password) |  | Signs every request TICVAI sends, as webhook deliveries are signed, so the provider can tell it came from TICVAI. (nullable)
TenancyService | setApprovalExternalProvider | response | apiClientId | string (uuid) | yes | The public-api client the provider calls back as.
TenancyService | setApprovalExternalProvider | response | requestMapping | array of object |  | Which request fields go to the provider, under which names.
TenancyService | setApprovalExternalProvider | response | requestMapping[].from | string | yes | A field of ApprovalRequest, e.g.
TenancyService | setApprovalExternalProvider | response | requestMapping[].to | string | yes | The provider's field name.
TenancyService | setApprovalExternalProvider | response | decisionMapping | array of object | yes | The provider's outcome values and the decision each means. (min items 2)
TenancyService | setApprovalExternalProvider | response | decisionMapping[].externalValue | string | yes
TenancyService | setApprovalExternalProvider | response | decisionMapping[].decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | setApprovalExternalProvider | response | timeoutMinutes | integer |  | How long a level waits for the provider before onTimeout applies. (default 1440)
TenancyService | setApprovalExternalProvider | response | onTimeout | enum (fallBackToRoles, escalate, reject) |  | (default fallBackToRoles)
TenancyService | setApprovalExternalProvider | response | maxAttempts | integer |  | Delivery attempts, with backoff, before a dispatch is failed and the level falls back as on timeout. (default 5)
TenancyService | setApprovalExternalProvider | response | status | enum (active, paused, disabled) |  | paused sends nothing and every level that names it falls back at once; the platform sets disabled after repeated failures, as it disables a failing webhook. (default active)
TenancyService | setApprovalExternalProvider | response | lastSuccessAt | string (date-time) |  | (read-only; nullable)
TenancyService | setApprovalExternalProvider | response | scopePath | string |  | (read-only)
TenancyService | setApprovalExternalProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setApprovalMatrix | request | id | string (uuid) |  | (read-only)
TenancyService | setApprovalMatrix | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | setApprovalMatrix | request | scopeLevel | enum (tenant, region, venue) | yes
TenancyService | setApprovalMatrix | request | scopePath | string |  | (read-only)
TenancyService | setApprovalMatrix | request | version | integer |  | 11.1.80. (read-only)
TenancyService | setApprovalMatrix | request | rules | array of ApprovalRule | yes
TenancyService | setApprovalMatrix | request | rules[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setApprovalMatrix | request | rules[].order | integer | yes | First match wins.
TenancyService | setApprovalMatrix | request | rules[].minAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | setApprovalMatrix | request | rules[].minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | request | rules[].minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | request | rules[].minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | request | rules[].maxAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | setApprovalMatrix | request | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | request | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | request | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | request | rules[].riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | setApprovalMatrix | request | rules[].condition | string |  | 11.1.13. (nullable)
TenancyService | setApprovalMatrix | request | rules[].approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | setApprovalMatrix | request | rules[].approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | setApprovalMatrix | request | rules[].mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | setApprovalMatrix | request | rules[].levels | integer |  | 11.1.3. (default 1)
TenancyService | setApprovalMatrix | request | rules[].requiresMfa | boolean |  | (default False)
TenancyService | setApprovalMatrix | request | rules[].requiresSignature | boolean |  | (default False)
TenancyService | setApprovalMatrix | request | rules[].slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | setApprovalMatrix | request | rules[].escalateAfterMinutes | integer |  | (nullable)
TenancyService | setApprovalMatrix | request | rules[].escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | setApprovalMatrix | request | rules[].expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | setApprovalMatrix | request | rules[].externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | setApprovalMatrix | request | isActive | boolean
TenancyService | setApprovalMatrix | response | id | string (uuid) |  | (read-only)
TenancyService | setApprovalMatrix | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | setApprovalMatrix | response | scopeLevel | enum (tenant, region, venue) | yes
TenancyService | setApprovalMatrix | response | scopePath | string |  | (read-only)
TenancyService | setApprovalMatrix | response | version | integer |  | 11.1.80. (read-only)
TenancyService | setApprovalMatrix | response | rules | array of ApprovalRule | yes
TenancyService | setApprovalMatrix | response | rules[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setApprovalMatrix | response | rules[].order | integer | yes | First match wins.
TenancyService | setApprovalMatrix | response | rules[].minAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | setApprovalMatrix | response | rules[].minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | response | rules[].minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | response | rules[].minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | response | rules[].maxAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | setApprovalMatrix | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setApprovalMatrix | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setApprovalMatrix | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setApprovalMatrix | response | rules[].riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | setApprovalMatrix | response | rules[].condition | string |  | 11.1.13. (nullable)
TenancyService | setApprovalMatrix | response | rules[].approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | setApprovalMatrix | response | rules[].approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | setApprovalMatrix | response | rules[].mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | setApprovalMatrix | response | rules[].levels | integer |  | 11.1.3. (default 1)
TenancyService | setApprovalMatrix | response | rules[].requiresMfa | boolean |  | (default False)
TenancyService | setApprovalMatrix | response | rules[].requiresSignature | boolean |  | (default False)
TenancyService | setApprovalMatrix | response | rules[].slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | setApprovalMatrix | response | rules[].escalateAfterMinutes | integer |  | (nullable)
TenancyService | setApprovalMatrix | response | rules[].escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | setApprovalMatrix | response | rules[].expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | setApprovalMatrix | response | rules[].externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | setApprovalMatrix | response | isActive | boolean
TenancyService | setApprovalMatrix | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setBiometricVerificationProfile | request | faceRequirement | enum (notUsed, optional, required) | yes | Whether face verification is not used, allowed, or required at this location (e.g.
AccessService | setBiometricVerificationProfile | request | biometricType | enum (facePass, faceTag, otherProvider) | yes | Biometric model this profile uses
AccessService | setBiometricVerificationProfile | request | profileId | string (uuid) | yes | The profile row's key (access.biometric_profile.id, a UUIDv7); absent creates one (decided 29 September, writers pass)
AccessService | setBiometricVerificationProfile | request | selectType | enum (ticketProduct, ticketType, membership, annualPass, multiDayTicket, multiAttractionTicket, vipCredential, accreditation, …) | yes | Vocabulary listed under Select.
AccessService | setBiometricVerificationProfile | request | venueId | string | yes | Venue
AccessService | setBiometricVerificationProfile | request | parkId | string |  | Park
AccessService | setBiometricVerificationProfile | request | zoneId | string |  | Zone
AccessService | setBiometricVerificationProfile | request | attractionId | string |  | Attraction
AccessService | setBiometricVerificationProfile | request | gateId | string |  | Gate
AccessService | setBiometricVerificationProfile | request | name | string
AccessService | setBiometricVerificationProfile | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setBiometricVerificationProfile | response | faceRequirement | enum (notUsed, optional, required) | yes | Whether face verification is not used, allowed, or required at this location (e.g.
AccessService | setBiometricVerificationProfile | response | biometricType | enum (facePass, faceTag, otherProvider) | yes | Biometric model this profile uses
AccessService | setBiometricVerificationProfile | response | profileId | string | yes | Biometric verification profile identifier
AccessService | setBiometricVerificationProfile | response | selectType | enum (ticketProduct, ticketType, membership, annualPass, multiDayTicket, multiAttractionTicket, vipCredential, accreditation, …) | yes | Vocabulary listed under Select.
AccessService | setBiometricVerificationProfile | response | venueId | string | yes | Venue
AccessService | setBiometricVerificationProfile | response | parkId | string |  | Park
AccessService | setBiometricVerificationProfile | response | zoneId | string |  | Zone
AccessService | setBiometricVerificationProfile | response | attractionId | string |  | Attraction
AccessService | setBiometricVerificationProfile | response | gateId | string |  | Gate
AccessService | setBiometricVerificationProfile | response | name | string
AccessService | setBiometricVerificationProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setBleBeaconGeofence | request | beaconName | string |  | Beacon Name
AccessService | setBleBeaconGeofence | request | beaconId | string | yes | Beacon ID
AccessService | setBleBeaconGeofence | request | venue | string | yes | Venue
AccessService | setBleBeaconGeofence | request | zone | string |  | Zone
AccessService | setBleBeaconGeofence | request | gate | string |  | Gate
AccessService | setBleBeaconGeofence | request | proximityThreshold | integer |  | Metres
AccessService | setBleBeaconGeofence | request | activeInactive | enum (active, inactive) |  | Active/Inactive
AccessService | setBleBeaconGeofence | request | health | enum (healthy, degraded, offline) |  | Read-only, reported by the beacon
AccessService | setBleBeaconGeofence | request | lastDetected | string (date-time) |  | Last detected
AccessService | setBleBeaconGeofence | request | park | string |  | Park
AccessService | setBleBeaconGeofence | request | attraction | string |  | Attraction
AccessService | setBleBeaconGeofence | request | geofenceRadiusMeters | integer |  | Radius of a circular activation zone
AccessService | setBleBeaconGeofence | request | geofenceBoundary | array of string |  | Polygon points as lat,lng when the zone is drawn
AccessService | setBleBeaconGeofence | response | beaconName | string |  | Beacon Name
AccessService | setBleBeaconGeofence | response | beaconId | string | yes | Beacon ID
AccessService | setBleBeaconGeofence | response | venue | string | yes | Venue
AccessService | setBleBeaconGeofence | response | zone | string |  | Zone
AccessService | setBleBeaconGeofence | response | gate | string |  | Gate
AccessService | setBleBeaconGeofence | response | proximityThreshold | integer |  | Metres
AccessService | setBleBeaconGeofence | response | activeInactive | enum (active, inactive) |  | Active/Inactive
AccessService | setBleBeaconGeofence | response | health | enum (healthy, degraded, offline) |  | Read-only, reported by the beacon
AccessService | setBleBeaconGeofence | response | lastDetected | string (date-time) |  | Last detected
AccessService | setBleBeaconGeofence | response | park | string |  | Park
AccessService | setBleBeaconGeofence | response | attraction | string |  | Attraction
AccessService | setBleBeaconGeofence | response | geofenceRadiusMeters | integer |  | Radius of a circular activation zone
AccessService | setBleBeaconGeofence | response | geofenceBoundary | array of string |  | Polygon points as lat,lng when the zone is drawn
AccessService | setBleBeaconGeofence | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setBookingFlowConfig | request | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | request | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | request | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | request | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | request | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | request | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | request | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | request | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | request | heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | request | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | request | singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | request | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | request | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | request | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | request | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | setBookingFlowConfig | request | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | setBookingFlowConfig | request | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | request | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | request | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | request | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | request | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | request | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | request | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | request | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | request | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | response | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | response | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | response | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | response | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | response | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | response | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | response | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | response | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | response | heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | response | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | response | singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | response | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | response | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | response | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | response | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | setBookingFlowConfig | response | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | setBookingFlowConfig | response | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | response | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | response | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | response | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | response | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | response | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | response | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | response | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | setBookingFlowConfig | response | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | setBookingFlowConfig | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setBookingVelocityTime | request | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setBookingVelocityTime | request | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setBookingVelocityTime | request | ruleName | string |  | Rule name
CatalogueService | setBookingVelocityTime | request | ruleKind | enum (bookingVelocity, earlyBird, lastMinute, combined, decayEscalation) |  | Rule family (pack pp.80-81)
CatalogueService | setBookingVelocityTime | request | expectedPaceSource | enum (historicalBookingCurve, configuredTarget) |  | What pace variance is measured against; defaults to configuredTarget until a historical curve exists (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | request | expectedSalesPerDay | integer |  | Expected sales per day when expectedPaceSource is configuredTarget (nullable)
CatalogueService | setBookingVelocityTime | request | conditions | array of object |  | Conditions (all must hold unless conditionLogic is any)
CatalogueService | setBookingVelocityTime | request | conditions[].metric | enum (salesPerHour, salesPerDay, salesPerWeek, currentBookingPace, paceVariancePercent, remainingInventory, daysToEvent, occupancyPercent) |  | Input evaluated (pack p.80; daysToEvent 0 = same day)
CatalogueService | setBookingVelocityTime | request | conditions[].operator | enum (lt, lte, gt, gte, eq, between) |  | Comparison
CatalogueService | setBookingVelocityTime | request | conditions[].value | number |  | Threshold value (percent for percentages, count for counts, days for time-to-event)
CatalogueService | setBookingVelocityTime | request | conditions[].valueTo | number |  | Upper value when operator is between (nullable)
CatalogueService | setBookingVelocityTime | request | conditionLogic | enum (all, any) |  | How conditions combine; defaults to all (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule | array of object |  | Time-to-event steps (early-bird, decay/escalation); empty for condition-only rules
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].daysBefore | integer |  | Days before the event/visit (T-180 ...
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | timeToEventSchedule[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | request | action | object |  | Action when the conditions hold (for condition rules) (nullable)
CatalogueService | setBookingVelocityTime | request | action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | request | action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | request | action.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBookingVelocityTime | request | action.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBookingVelocityTime | request | action.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBookingVelocityTime | request | action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | request | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setBookingVelocityTime | request | enabled | boolean |  | Enabled
CatalogueService | setBookingVelocityTime | response | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setBookingVelocityTime | response | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setBookingVelocityTime | response | ruleName | string |  | Rule name
CatalogueService | setBookingVelocityTime | response | ruleKind | enum (bookingVelocity, earlyBird, lastMinute, combined, decayEscalation) |  | Rule family (pack pp.80-81)
CatalogueService | setBookingVelocityTime | response | expectedPaceSource | enum (historicalBookingCurve, configuredTarget) |  | What pace variance is measured against; defaults to configuredTarget until a historical curve exists (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | response | expectedSalesPerDay | integer |  | Expected sales per day when expectedPaceSource is configuredTarget (nullable)
CatalogueService | setBookingVelocityTime | response | conditions | array of object |  | Conditions (all must hold unless conditionLogic is any)
CatalogueService | setBookingVelocityTime | response | conditions[].metric | enum (salesPerHour, salesPerDay, salesPerWeek, currentBookingPace, paceVariancePercent, remainingInventory, daysToEvent, occupancyPercent) |  | Input evaluated (pack p.80; daysToEvent 0 = same day)
CatalogueService | setBookingVelocityTime | response | conditions[].operator | enum (lt, lte, gt, gte, eq, between) |  | Comparison
CatalogueService | setBookingVelocityTime | response | conditions[].value | number |  | Threshold value (percent for percentages, count for counts, days for time-to-event)
CatalogueService | setBookingVelocityTime | response | conditions[].valueTo | number |  | Upper value when operator is between (nullable)
CatalogueService | setBookingVelocityTime | response | conditionLogic | enum (all, any) |  | How conditions combine; defaults to all (decided 29 September, readiness close-out)
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule | array of object |  | Time-to-event steps (early-bird, decay/escalation); empty for condition-only rules
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].daysBefore | integer |  | Days before the event/visit (T-180 ...
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | timeToEventSchedule[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | response | action | object |  | Action when the conditions hold (for condition rules) (nullable)
CatalogueService | setBookingVelocityTime | response | action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setBookingVelocityTime | response | action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setBookingVelocityTime | response | action.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBookingVelocityTime | response | action.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBookingVelocityTime | response | action.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBookingVelocityTime | response | action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setBookingVelocityTime | response | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setBookingVelocityTime | response | enabled | boolean |  | Enabled
CatalogueService | setBookingVelocityTime | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setBrandIdentity | request | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | setBrandIdentity | request | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | setBrandIdentity | request | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | setBrandIdentity | request | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | setBrandIdentity | request | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | setBrandIdentity | request | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | setBrandIdentity | request | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setBrandIdentity | request | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | setBrandIdentity | request | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | setBrandIdentity | request | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | setBrandIdentity | request | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | setBrandIdentity | response | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | setBrandIdentity | response | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | setBrandIdentity | response | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | setBrandIdentity | response | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | setBrandIdentity | response | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | setBrandIdentity | response | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | setBrandIdentity | response | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setBrandIdentity | response | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | setBrandIdentity | response | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | setBrandIdentity | response | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | setBrandIdentity | response | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | setBrandIdentity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setBundleComponent | request | typesType | enum (mandatory, optional, choice, conditional, recommended) |  | Vocabulary listed under Component Types.
CatalogueService | setBundleComponent | request | fixedQuantity | integer |  | Fixed quantity
CatalogueService | setBundleComponent | request | minimum | string |  | Minimum
CatalogueService | setBundleComponent | request | maximum | string |  | Maximum
CatalogueService | setBundleComponent | request | quantityBasedOnGuestCount | integer |  | Quantity based on guest count
CatalogueService | setBundleComponent | request | quantityBasedOnTicketCount | integer |  | Quantity based on ticket count
CatalogueService | setBundleComponent | request | componentType | enum (admissionTicket, attraction, event, timeslot, experience, membership, annualPass, fBProduct, …) |  | What the component is.
CatalogueService | setBundleComponent | response | typesType | enum (mandatory, optional, choice, conditional, recommended) |  | Vocabulary listed under Component Types.
CatalogueService | setBundleComponent | response | fixedQuantity | integer |  | Fixed quantity
CatalogueService | setBundleComponent | response | minimum | string |  | Minimum
CatalogueService | setBundleComponent | response | maximum | string |  | Maximum
CatalogueService | setBundleComponent | response | quantityBasedOnGuestCount | integer |  | Quantity based on guest count
CatalogueService | setBundleComponent | response | quantityBasedOnTicketCount | integer |  | Quantity based on ticket count
CatalogueService | setBundleComponent | response | componentType | enum (admissionTicket, attraction, event, timeslot, experience, membership, annualPass, fBProduct, …) |  | What the component is.
CatalogueService | setBundleComponent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setBundleDefinition | request | bundleName | string |  | Bundle name
CatalogueService | setBundleDefinition | request | bundleId | string |  | Bundle ID
CatalogueService | setBundleDefinition | request | internalDescription | string |  | Internal description
CatalogueService | setBundleDefinition | request | guestFacingDescription | string |  | Guest-facing description
CatalogueService | setBundleDefinition | request | businessEntity | string |  | Business entity
CatalogueService | setBundleDefinition | request | venue | string |  | Venue
CatalogueService | setBundleDefinition | request | bundleCategory | string |  | Bundle category
CatalogueService | setBundleDefinition | request | owner | string |  | Owner
CatalogueService | setBundleDefinition | request | campaign | string |  | Campaign
CatalogueService | setBundleDefinition | request | effectiveDates | string |  | Effective dates
CatalogueService | setBundleDefinition | request | salesStatus | string |  | Sales status
CatalogueService | setBundleDefinition | request | appearsAsStandaloneProduct | string |  | Appears as standalone product
CatalogueService | setBundleDefinition | request | isRecommendedDuringCheckout | boolean |  | Is recommended during checkout
CatalogueService | setBundleDefinition | request | requiresAnotherProduct | string |  | Requires another product
CatalogueService | setBundleDefinition | request | bundleType | enum (fixed, configurable, buildYourOwn, dynamic, partner) |  | Bundle type
CatalogueService | setBundleDefinition | response | bundleName | string |  | Bundle name
CatalogueService | setBundleDefinition | response | bundleId | string |  | Bundle ID
CatalogueService | setBundleDefinition | response | internalDescription | string |  | Internal description
CatalogueService | setBundleDefinition | response | guestFacingDescription | string |  | Guest-facing description
CatalogueService | setBundleDefinition | response | businessEntity | string |  | Business entity
CatalogueService | setBundleDefinition | response | venue | string |  | Venue
CatalogueService | setBundleDefinition | response | bundleCategory | string |  | Bundle category
CatalogueService | setBundleDefinition | response | owner | string |  | Owner
CatalogueService | setBundleDefinition | response | campaign | string |  | Campaign
CatalogueService | setBundleDefinition | response | effectiveDates | string |  | Effective dates
CatalogueService | setBundleDefinition | response | salesStatus | string |  | Sales status
CatalogueService | setBundleDefinition | response | appearsAsStandaloneProduct | string |  | Appears as standalone product
CatalogueService | setBundleDefinition | response | isRecommendedDuringCheckout | boolean |  | Is recommended during checkout
CatalogueService | setBundleDefinition | response | requiresAnotherProduct | string |  | Requires another product
CatalogueService | setBundleDefinition | response | bundleType | enum (fixed, configurable, buildYourOwn, dynamic, partner) |  | Bundle type: all components predefined; required plus optional choices; guest selects from permitted categories; changes with availability or rules; contains internal and external products
CatalogueService | setBundleDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setBuyGetBogo | request | product | string |  | Product
CatalogueService | setBuyGetBogo | request | productCategory | string |  | Product category
CatalogueService | setBuyGetBogo | request | ticketType | string |  | Ticket type
CatalogueService | setBuyGetBogo | request | quantity | integer |  | Quantity
CatalogueService | setBuyGetBogo | request | minimumSpend | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setBuyGetBogo | request | minimumSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBuyGetBogo | request | minimumSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBuyGetBogo | request | minimumSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBuyGetBogo | request | customerSegment | string |  | Customer segment
CatalogueService | setBuyGetBogo | request | channel | string |  | Channel
CatalogueService | setBuyGetBogo | request | venue | string |  | Venue
CatalogueService | setBuyGetBogo | request | dateTime | string (date-time) |  | Date/time
CatalogueService | setBuyGetBogo | request | sameProduct | string |  | Same product
CatalogueService | setBuyGetBogo | request | differentProduct | string |  | Different product
CatalogueService | setBuyGetBogo | request | free | string |  | Free
CatalogueService | setBuyGetBogo | request | percentageDiscount | number |  | Percentage discount
CatalogueService | setBuyGetBogo | request | fixedDiscount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setBuyGetBogo | request | fixedDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBuyGetBogo | request | fixedDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBuyGetBogo | request | fixedDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBuyGetBogo | request | fixedRewardPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setBuyGetBogo | request | fixedRewardPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBuyGetBogo | request | fixedRewardPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBuyGetBogo | request | fixedRewardPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBuyGetBogo | response | product | string |  | Product
CatalogueService | setBuyGetBogo | response | productCategory | string |  | Product category
CatalogueService | setBuyGetBogo | response | ticketType | string |  | Ticket type
CatalogueService | setBuyGetBogo | response | quantity | integer |  | Quantity
CatalogueService | setBuyGetBogo | response | minimumSpend | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setBuyGetBogo | response | minimumSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBuyGetBogo | response | minimumSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBuyGetBogo | response | minimumSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBuyGetBogo | response | customerSegment | string |  | Customer segment
CatalogueService | setBuyGetBogo | response | channel | string |  | Channel
CatalogueService | setBuyGetBogo | response | venue | string |  | Venue
CatalogueService | setBuyGetBogo | response | dateTime | string (date-time) |  | Date/time
CatalogueService | setBuyGetBogo | response | sameProduct | string |  | Same product
CatalogueService | setBuyGetBogo | response | differentProduct | string |  | Different product
CatalogueService | setBuyGetBogo | response | free | string |  | Free
CatalogueService | setBuyGetBogo | response | percentageDiscount | number |  | Percentage discount
CatalogueService | setBuyGetBogo | response | fixedDiscount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setBuyGetBogo | response | fixedDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBuyGetBogo | response | fixedDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBuyGetBogo | response | fixedDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBuyGetBogo | response | fixedRewardPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setBuyGetBogo | response | fixedRewardPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setBuyGetBogo | response | fixedRewardPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setBuyGetBogo | response | fixedRewardPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setBuyGetBogo | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setCampaignBudgetFinancial | request | totalCampaignBudget | integer |  | Total campaign budget
CatalogueService | setCampaignBudgetFinancial | request | discountBudget | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCampaignBudgetFinancial | request | discountBudget.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCampaignBudgetFinancial | request | discountBudget.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCampaignBudgetFinancial | request | discountBudget.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCampaignBudgetFinancial | request | rewardBudget | string |  | Reward budget
CatalogueService | setCampaignBudgetFinancial | request | freeProductBudget | string |  | Free-product budget
CatalogueService | setCampaignBudgetFinancial | request | partnerFundedBudget | string |  | Partner-funded budget
CatalogueService | setCampaignBudgetFinancial | request | marketingFundedBudget | string |  | Marketing-funded budget
CatalogueService | setCampaignBudgetFinancial | request | venueBudget | string |  | Venue budget
CatalogueService | setCampaignBudgetFinancial | request | departmentBudget | string |  | Department budget
CatalogueService | setCampaignBudgetFinancial | request | campaign | string |  | Campaign
CatalogueService | setCampaignBudgetFinancial | request | budgetAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCampaignBudgetFinancial | request | budgetAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCampaignBudgetFinancial | request | budgetAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCampaignBudgetFinancial | request | budgetAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCampaignBudgetFinancial | request | currency | string |  | Currency
CatalogueService | setCampaignBudgetFinancial | request | effectiveDates | string |  | Effective dates
CatalogueService | setCampaignBudgetFinancial | request | budgetOwner | string |  | Budget owner
CatalogueService | setCampaignBudgetFinancial | request | costCenter | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCampaignBudgetFinancial | request | costCenter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCampaignBudgetFinancial | request | costCenter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCampaignBudgetFinancial | request | costCenter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCampaignBudgetFinancial | request | businessEntity | string |  | Business entity
CatalogueService | setCampaignBudgetFinancial | request | venue | string |  | Venue
CatalogueService | setCampaignBudgetFinancial | request | department | string |  | Department
CatalogueService | setCampaignBudgetFinancial | request | fundingSource | string |  | Funding source
CatalogueService | setCampaignBudgetFinancial | request | entireCampaign | string |  | Entire campaign
CatalogueService | setCampaignBudgetFinancial | request | promotion | string |  | Promotion
CatalogueService | setCampaignBudgetFinancial | request | product | string |  | Product
CatalogueService | setCampaignBudgetFinancial | request | channel | string |  | Channel
CatalogueService | setCampaignBudgetFinancial | request | partner | string |  | Partner
CatalogueService | setCampaignBudgetFinancial | request | customerSegment | string |  | Customer segment
CatalogueService | setCampaignBudgetFinancial | response | totalCampaignBudget | integer |  | Total campaign budget
CatalogueService | setCampaignBudgetFinancial | response | discountBudget | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCampaignBudgetFinancial | response | discountBudget.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCampaignBudgetFinancial | response | discountBudget.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCampaignBudgetFinancial | response | discountBudget.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCampaignBudgetFinancial | response | rewardBudget | string |  | Reward budget
CatalogueService | setCampaignBudgetFinancial | response | freeProductBudget | string |  | Free-product budget
CatalogueService | setCampaignBudgetFinancial | response | partnerFundedBudget | string |  | Partner-funded budget
CatalogueService | setCampaignBudgetFinancial | response | marketingFundedBudget | string |  | Marketing-funded budget
CatalogueService | setCampaignBudgetFinancial | response | venueBudget | string |  | Venue budget
CatalogueService | setCampaignBudgetFinancial | response | departmentBudget | string |  | Department budget
CatalogueService | setCampaignBudgetFinancial | response | campaign | string |  | Campaign
CatalogueService | setCampaignBudgetFinancial | response | budgetAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCampaignBudgetFinancial | response | budgetAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCampaignBudgetFinancial | response | budgetAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCampaignBudgetFinancial | response | budgetAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCampaignBudgetFinancial | response | currency | string |  | Currency
CatalogueService | setCampaignBudgetFinancial | response | effectiveDates | string |  | Effective dates
CatalogueService | setCampaignBudgetFinancial | response | budgetOwner | string |  | Budget owner
CatalogueService | setCampaignBudgetFinancial | response | costCenter | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCampaignBudgetFinancial | response | costCenter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCampaignBudgetFinancial | response | costCenter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCampaignBudgetFinancial | response | costCenter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCampaignBudgetFinancial | response | businessEntity | string |  | Business entity
CatalogueService | setCampaignBudgetFinancial | response | venue | string |  | Venue
CatalogueService | setCampaignBudgetFinancial | response | department | string |  | Department
CatalogueService | setCampaignBudgetFinancial | response | fundingSource | string |  | Funding source
CatalogueService | setCampaignBudgetFinancial | response | entireCampaign | string |  | Entire campaign
CatalogueService | setCampaignBudgetFinancial | response | promotion | string |  | Promotion
CatalogueService | setCampaignBudgetFinancial | response | product | string |  | Product
CatalogueService | setCampaignBudgetFinancial | response | channel | string |  | Channel
CatalogueService | setCampaignBudgetFinancial | response | partner | string |  | Partner
CatalogueService | setCampaignBudgetFinancial | response | customerSegment | string |  | Customer segment
CatalogueService | setCampaignBudgetFinancial | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setCodeDistributionManager | request | channelsType | enum (email, sms, whatsapp, mobileApp, crmJourney, guestPortal, b2bPortal, partnerPortal, …) |  | Vocabulary listed under Distribution Channels.
CatalogueService | setCodeDistributionManager | request | assigneeType | enum (individualCustomer, customerSegment, membershipAccount, b2bCompany, reseller, travelAgency, school, hotel, …) |  | Who the codes are assigned to.
CatalogueService | setCodeDistributionManager | request | batchId | string |  | Batch ID
CatalogueService | setCodeDistributionManager | request | assigneeReference | string |  | Customer, segment, account or partner the codes go to
CatalogueService | setCodeDistributionManager | request | quantity | integer |  | Codes to assign
CatalogueService | setCodeDistributionManager | response | channelsType | enum (email, sms, whatsapp, mobileApp, crmJourney, guestPortal, b2bPortal, partnerPortal, …) |  | Vocabulary listed under Distribution Channels.
CatalogueService | setCodeDistributionManager | response | generated | string |  | Generated
CatalogueService | setCodeDistributionManager | response | assigned | string |  | Assigned
CatalogueService | setCodeDistributionManager | response | sent | string |  | Sent
CatalogueService | setCodeDistributionManager | response | delivered | string |  | Delivered
CatalogueService | setCodeDistributionManager | response | redeemed | string |  | Redeemed
CatalogueService | setCodeDistributionManager | response | expired | integer |  | Expired
CatalogueService | setCodeDistributionManager | response | cancelled | integer |  | Cancelled
CatalogueService | setCodeDistributionManager | response | viewed | string |  | Viewed where available
CatalogueService | setCodeDistributionManager | response | assigneeType | enum (individualCustomer, customerSegment, membershipAccount, b2bCompany, reseller, travelAgency, school, hotel, …) |  | Who the codes are assigned to.
CatalogueService | setCodeDistributionManager | response | batchId | string |  | Batch ID
CatalogueService | setCodeDistributionManager | response | partner | string |  | Partner, for a partner batch
CatalogueService | setCodeDistributionManager | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setConsentPurposes | request | purposes | array of ConsentPurposeConfig | yes
MarketingService | setConsentPurposes | request | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | setConsentPurposes | request | purposes[].displayName | string
MarketingService | setConsentPurposes | request | purposes[].description | string
MarketingService | setConsentPurposes | request | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | setConsentPurposes | request | purposes[].noticeVersion | string | yes | Current version of the notice.
MarketingService | setConsentPurposes | request | purposes[].isRequiredForService | boolean | yes | True for transactional.
MarketingService | setConsentPurposes | request | purposes[].expiresAfterMonths | integer |  | (nullable)
MarketingService | setConsentPurposes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setContextTimeEvent | request | result | enum (allow, deny, review, requireId, requireBiometric, requireCompanion, requireSupervisor) | yes
AccessService | setContextTimeEvent | request | conditionExpression | string | yes | e.g.
AccessService | setContextTimeEvent | request | name | string | yes
AccessService | setContextTimeEvent | request | policyId | string | yes
AccessService | setContextTimeEvent | request | contextType | enum (date, day, time, season, event, performance, specialEvent, holiday, …) | yes | Kind of venue condition the policy reacts to
AccessService | setContextTimeEvent | request | monitorThresholdPercent | integer |  | Occupancy percent at which the band becomes Monitor
AccessService | setContextTimeEvent | request | restrictThresholdPercent | integer |  | Occupancy percent at which the band becomes Restrict
AccessService | setContextTimeEvent | request | status | enum (active, inactive) |  | inactive switches the policy off at once; active on a new or inactive policy submits it for approval (pendingApproval) (decided 29 September, writers pass) (default active)
AccessService | setContextTimeEvent | request | validFrom | string (date-time) |  | Start of validity; null for at once (decided 29 September, writers pass) (nullable)
AccessService | setContextTimeEvent | request | validTo | string (date-time) |  | End of validity: after it a timer moves the policy to expired (decided 29 September, writers pass) (nullable)
AccessService | setContextTimeEvent | response | result | enum (allow, deny, review, requireId, requireBiometric, requireCompanion, requireSupervisor) | yes
AccessService | setContextTimeEvent | response | conditionExpression | string | yes | e.g.
AccessService | setContextTimeEvent | response | name | string | yes
AccessService | setContextTimeEvent | response | policyId | string | yes
AccessService | setContextTimeEvent | response | contextType | enum (date, day, time, season, event, performance, specialEvent, holiday, …) | yes | Kind of venue condition the policy reacts to
AccessService | setContextTimeEvent | response | monitorThresholdPercent | integer |  | Occupancy percent at which the band becomes Monitor
AccessService | setContextTimeEvent | response | restrictThresholdPercent | integer |  | Occupancy percent at which the band becomes Restrict
AccessService | setContextTimeEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setCookieBannerDesign | request | id | string (uuid) |  | (read-only)
MarketingService | setCookieBannerDesign | request | brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | setCookieBannerDesign | request | inheritsFromId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | request | channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | setCookieBannerDesign | request | logoAssetId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | request | title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | position | enum (top, bottom, popup, modal) | yes
MarketingService | setCookieBannerDesign | request | themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | setCookieBannerDesign | request | buttons | array of object
MarketingService | setCookieBannerDesign | request | buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | setCookieBannerDesign | request | buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | setCookieBannerDesign | request | links | array of object
MarketingService | setCookieBannerDesign | request | links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | setCookieBannerDesign | request | categories | array of object | yes | (min items 1)
MarketingService | setCookieBannerDesign | request | categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | setCookieBannerDesign | request | categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | request | categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | setCookieBannerDesign | request | languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | setCookieBannerDesign | request | regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | setCookieBannerDesign | request | recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | setCookieBannerDesign | request | noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | setCookieBannerDesign | request | version | integer |  | (min 1; read-only)
MarketingService | setCookieBannerDesign | request | status | enum (draft, published, superseded) |  | (read-only)
MarketingService | setCookieBannerDesign | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setCookieBannerDesign | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setCookieBannerDesign | response | id | string (uuid) |  | (read-only)
MarketingService | setCookieBannerDesign | response | brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | setCookieBannerDesign | response | inheritsFromId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | response | channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | setCookieBannerDesign | response | logoAssetId | string (uuid) |  | (nullable)
MarketingService | setCookieBannerDesign | response | title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | position | enum (top, bottom, popup, modal) | yes
MarketingService | setCookieBannerDesign | response | themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | setCookieBannerDesign | response | buttons | array of object
MarketingService | setCookieBannerDesign | response | buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | setCookieBannerDesign | response | buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | setCookieBannerDesign | response | links | array of object
MarketingService | setCookieBannerDesign | response | links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | setCookieBannerDesign | response | categories | array of object | yes | (min items 1)
MarketingService | setCookieBannerDesign | response | categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | setCookieBannerDesign | response | categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | setCookieBannerDesign | response | categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | setCookieBannerDesign | response | languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | setCookieBannerDesign | response | regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | setCookieBannerDesign | response | recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | setCookieBannerDesign | response | noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | setCookieBannerDesign | response | version | integer |  | (min 1; read-only)
MarketingService | setCookieBannerDesign | response | status | enum (draft, published, superseded) |  | (read-only)
MarketingService | setCookieBannerDesign | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setCookieBannerDesign | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setCookieBannerDesign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setCouponPromoCode | request | codeType | enum (commonPromoCode, uniquePromoCode, coupon, promotionalVoucher, freeTicketCode, discountVoucher, partnerCode, employeeCode, …) |  | Kind of code.
CatalogueService | setCouponPromoCode | request | benefitType | enum (percentageDiscount, fixedValueDiscount, fixedPromotionalPrice, freeProduct, freeTicket, freeAddOn, upgrade, bundleBenefit, …) |  | What the code grants; the discount itself is calculated by the promotion rule engine rather than duplicated here.
CatalogueService | setCouponPromoCode | request | benefitValue | number |  | Benefit value: the percentage, or the amount in the promotion's currency
CatalogueService | setCouponPromoCode | request | campaign | string |  | Campaign
CatalogueService | setCouponPromoCode | request | code | string |  | Code text for a common code, or the batch pattern for unique codes
CatalogueService | setCouponPromoCode | request | maximumDiscount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCouponPromoCode | request | maximumDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCouponPromoCode | request | maximumDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCouponPromoCode | request | maximumDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCouponPromoCode | request | eligibleProducts | array of string |  | Eligible products
CatalogueService | setCouponPromoCode | request | channels | array of string |  | Channels the code works on
CatalogueService | setCouponPromoCode | request | validFrom | string (date-time) |  | Valid from
CatalogueService | setCouponPromoCode | request | validTo | string (date-time) |  | Valid to
CatalogueService | setCouponPromoCode | response | codeType | enum (commonPromoCode, uniquePromoCode, coupon, promotionalVoucher, freeTicketCode, discountVoucher, partnerCode, employeeCode, …) |  | Kind of code.
CatalogueService | setCouponPromoCode | response | benefitType | enum (percentageDiscount, fixedValueDiscount, fixedPromotionalPrice, freeProduct, freeTicket, freeAddOn, upgrade, bundleBenefit, …) |  | What the code grants; the discount itself is calculated by the promotion rule engine rather than duplicated here.
CatalogueService | setCouponPromoCode | response | benefitValue | number |  | Benefit value: the percentage, or the amount in the promotion's currency
CatalogueService | setCouponPromoCode | response | campaign | string |  | Campaign
CatalogueService | setCouponPromoCode | response | code | string |  | Code text for a common code, or the batch pattern for unique codes
CatalogueService | setCouponPromoCode | response | maximumDiscount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setCouponPromoCode | response | maximumDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setCouponPromoCode | response | maximumDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setCouponPromoCode | response | maximumDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setCouponPromoCode | response | eligibleProducts | array of string |  | Eligible products
CatalogueService | setCouponPromoCode | response | channels | array of string |  | Channels the code works on
CatalogueService | setCouponPromoCode | response | validFrom | string (date-time) |  | Valid from
CatalogueService | setCouponPromoCode | response | validTo | string (date-time) |  | Valid to
CatalogueService | setCouponPromoCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setCourseRules | request | outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setCourseRules | request | defaultCoursing | CoursingPolicy: enum (fireAndForget, holdAndFire, phased, timed, delayed) |  | How a ticket's courses are fired.
FnbService | setCourseRules | request | courseNames | array of string
FnbService | setCourseRules | request | autoFireMinutes | integer |  | (nullable)
FnbService | setCourseRules | request | serviceModeOverrides | object |  | A different default per service mode.
FnbService | setCourseRules | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setCourseRules | response | outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setCourseRules | response | defaultCoursing | CoursingPolicy: enum (fireAndForget, holdAndFire, phased, timed, delayed) |  | How a ticket's courses are fired.
FnbService | setCourseRules | response | courseNames | array of string
FnbService | setCourseRules | response | autoFireMinutes | integer |  | (nullable)
FnbService | setCourseRules | response | serviceModeOverrides | object |  | A different default per service mode.
FnbService | setCourseRules | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setCourseRules | param (path) | outletId | string (uuid) | yes
FnbService | setCourseRules | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setCourseRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setCredentialActivationDisplay | request | ruleId | string (uuid) |  | Absent creates a rule
AccessService | setCredentialActivationDisplay | request | venueId | string | yes | Venue the rule applies to
AccessService | setCredentialActivationDisplay | request | name | string | yes | (max length 200)
AccessService | setCredentialActivationDisplay | request | beforeActivationDisplay | array of enum (hideQr, blurQr, showCountdown, showAvailableAtVenue, showVenueDirections) | yes | What the guest sees before the credential activates
AccessService | setCredentialActivationDisplay | request | activeDisplay | array of enum (dynamicQr, activationTimer, credentialStatus, remainingEntitlements) | yes | What the guest sees once it is active
AccessService | setCredentialActivationDisplay | request | activationTriggers | array of string | yes | What activates the credential, e.g. (min items 1)
AccessService | setCredentialActivationDisplay | response | ruleId | string | yes
AccessService | setCredentialActivationDisplay | response | beforeActivationDisplay | array of enum (hideQr, blurQr, showCountdown, showAvailableAtVenue, showVenueDirections)
AccessService | setCredentialActivationDisplay | response | activeDisplay | array of enum (dynamicQr, activationTimer, credentialStatus, remainingEntitlements)
AccessService | setCredentialActivationDisplay | response | name | string
AccessService | setCredentialActivationDisplay | response | activationTriggers | array of string |  | Conditions that make the credential eligible, e.g.
AccessService | setCredentialActivationDisplay | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setCrossCategoryPromotion | request | ticketing | string |  | Ticketing
CatalogueService | setCrossCategoryPromotion | request | attractions | string |  | Attractions
CatalogueService | setCrossCategoryPromotion | request | events | string |  | Events
CatalogueService | setCrossCategoryPromotion | request | fB | string |  | F&B
CatalogueService | setCrossCategoryPromotion | request | retail | string |  | Retail
CatalogueService | setCrossCategoryPromotion | request | membership | string |  | Membership
CatalogueService | setCrossCategoryPromotion | request | experiences | string |  | Experiences
CatalogueService | setCrossCategoryPromotion | request | addOns | string |  | Add-ons
CatalogueService | setCrossCategoryPromotion | request | parking | string |  | Parking
CatalogueService | setCrossCategoryPromotion | request | services | string |  | Services
CatalogueService | setCrossCategoryPromotion | response | ticketing | string |  | Ticketing
CatalogueService | setCrossCategoryPromotion | response | attractions | string |  | Attractions
CatalogueService | setCrossCategoryPromotion | response | events | string |  | Events
CatalogueService | setCrossCategoryPromotion | response | fB | string |  | F&B
CatalogueService | setCrossCategoryPromotion | response | retail | string |  | Retail
CatalogueService | setCrossCategoryPromotion | response | membership | string |  | Membership
CatalogueService | setCrossCategoryPromotion | response | experiences | string |  | Experiences
CatalogueService | setCrossCategoryPromotion | response | addOns | string |  | Add-ons
CatalogueService | setCrossCategoryPromotion | response | parking | string |  | Parking
CatalogueService | setCrossCategoryPromotion | response | services | string |  | Services
CatalogueService | setCrossCategoryPromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setCurrencyRoundingRule | request | id | string (uuid) | yes | (read-only)
CatalogueService | setCurrencyRoundingRule | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setCurrencyRoundingRule | request | code | string |  | (max length 40; nullable)
CatalogueService | setCurrencyRoundingRule | request | name | string |  | (max length 200; nullable)
CatalogueService | setCurrencyRoundingRule | request | currency | string | yes | (max length 3; pattern ^[A-Z]{3}$)
CatalogueService | setCurrencyRoundingRule | request | decimalPlaces | integer | yes | Up to three without rounding the third away (MoM 1 Sep 2026 §4.5). (min 0; max 3)
CatalogueService | setCurrencyRoundingRule | request | minimumMonetaryUnit | number |  | (nullable)
CatalogueService | setCurrencyRoundingRule | request | displayPrecision | integer |  | (min 0; max 4; nullable)
CatalogueService | setCurrencyRoundingRule | request | calculationPrecision | integer |  | (min 0; max 4; default 4)
CatalogueService | setCurrencyRoundingRule | request | roundingMethod | enum (standard, roundUp, roundDown, bankers, nearestCurrencyUnit, customRegulatoryRule) | yes
CatalogueService | setCurrencyRoundingRule | request | roundingStage | enum (perItem, perTax, perFee, perLine, atOrderTotal) | yes
CatalogueService | setCurrencyRoundingRule | request | cashRoundingIncrement | number |  | (nullable)
CatalogueService | setCurrencyRoundingRule | request | status | object | yes | (default active)
CatalogueService | setCurrencyRoundingRule | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setCurrencyRoundingRule | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setCurrencyRoundingRule | response | id | string (uuid) | yes | (read-only)
CatalogueService | setCurrencyRoundingRule | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setCurrencyRoundingRule | response | code | string |  | (max length 40; nullable)
CatalogueService | setCurrencyRoundingRule | response | name | string |  | (max length 200; nullable)
CatalogueService | setCurrencyRoundingRule | response | currency | string | yes | (max length 3; pattern ^[A-Z]{3}$)
CatalogueService | setCurrencyRoundingRule | response | decimalPlaces | integer | yes | Up to three without rounding the third away (MoM 1 Sep 2026 §4.5). (min 0; max 3)
CatalogueService | setCurrencyRoundingRule | response | minimumMonetaryUnit | number |  | (nullable)
CatalogueService | setCurrencyRoundingRule | response | displayPrecision | integer |  | (min 0; max 4; nullable)
CatalogueService | setCurrencyRoundingRule | response | calculationPrecision | integer |  | (min 0; max 4; default 4)
CatalogueService | setCurrencyRoundingRule | response | roundingMethod | enum (standard, roundUp, roundDown, bankers, nearestCurrencyUnit, customRegulatoryRule) | yes
CatalogueService | setCurrencyRoundingRule | response | roundingStage | enum (perItem, perTax, perFee, perLine, atOrderTotal) | yes
CatalogueService | setCurrencyRoundingRule | response | cashRoundingIncrement | number |  | (nullable)
CatalogueService | setCurrencyRoundingRule | response | status | object | yes | (default active)
CatalogueService | setCurrencyRoundingRule | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setCurrencyRoundingRule | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setCurrencyRoundingRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setDeliveryLocationOutletMapping | request | mappings | array of object | yes | (min items 1)
FnbService | setDeliveryLocationOutletMapping | request | mappings[].locationId | string (uuid) | yes
FnbService | setDeliveryLocationOutletMapping | request | mappings[].servingOutletIds | array of string (uuid) | yes
FnbService | setDeliveryLocationOutletMapping | param (path) | venueId | string (uuid) | yes
FnbService | setDeliveryLocationOutletMapping | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setDeliveryLocationOutletMapping | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDemandOccupancyAvailability | request | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setDemandOccupancyAvailability | request | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setDemandOccupancyAvailability | request | ruleName | string |  | Rule name
CatalogueService | setDemandOccupancyAvailability | request | ruleKind | enum (occupancy, inventory, availability, demand) |  | Rule family (pack p.78-79)
CatalogueService | setDemandOccupancyAvailability | request | inputMetric | enum (ticketsSold, currentDemand, occupancyPercent, remainingCapacity, remainingInventory, availableSeats, capacityUtilization, salesPace) |  | Supported Input evaluated (pack p.78)
CatalogueService | setDemandOccupancyAvailability | request | tiers | array of object |  | Threshold matrix; tiers must not overlap
CatalogueService | setDemandOccupancyAvailability | request | tiers[].fromValue | number |  | From (inclusive)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].toValue | number |  | To (inclusive); empty for no upper bound (nullable)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | request | tiers[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setDemandOccupancyAvailability | request | demandIndexDefinition | string |  | Required when inputMetric is currentDemand: how the demand index is calculated (the pack requires it to be explicitly configured and documented) (nullable)
CatalogueService | setDemandOccupancyAvailability | request | exitThresholdOffset | number |  | Exit threshold: how far the metric must fall back below a tier's entry before the price reverses; defaults to 2 (points or units of the metric) (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | request | minimumDurationMinutes | integer |  | Minimum duration a threshold must hold before the price moves; defaults to 15 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | request | cooldownMinutes | integer |  | Cooldown after a movement before the next; defaults to 60 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | request | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setDemandOccupancyAvailability | request | enabled | boolean |  | Enabled
CatalogueService | setDemandOccupancyAvailability | response | ruleId | string |  | Rule ID; empty on create (nullable)
CatalogueService | setDemandOccupancyAvailability | response | strategyId | string |  | Strategy the rule belongs to
CatalogueService | setDemandOccupancyAvailability | response | ruleName | string |  | Rule name
CatalogueService | setDemandOccupancyAvailability | response | ruleKind | enum (occupancy, inventory, availability, demand) |  | Rule family (pack p.78-79)
CatalogueService | setDemandOccupancyAvailability | response | inputMetric | enum (ticketsSold, currentDemand, occupancyPercent, remainingCapacity, remainingInventory, availableSeats, capacityUtilization, salesPace) |  | Supported Input evaluated (pack p.78)
CatalogueService | setDemandOccupancyAvailability | response | tiers | array of object |  | Threshold matrix; tiers must not overlap
CatalogueService | setDemandOccupancyAvailability | response | tiers[].fromValue | number |  | From (inclusive)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].toValue | number |  | To (inclusive); empty for no upper bound (nullable)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action | object |  | The price action; the result still passes through the price ladder and the guardrails
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.actionType | enum (percentAdjustment, fixedAmountAdjustment, moveToBand, returnToBase) |  | What the rule does to the current price
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.percent | number |  | Adjustment in percent (negative lowers the price) when actionType is percentAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.amount | object |  | Signed amount when actionType is fixedAmountAdjustment (nullable)
CatalogueService | setDemandOccupancyAvailability | response | tiers[].action.bandCode | string |  | Target band on the strategy's price ladder (listDynamicPriceBand) when actionType is moveToBand (nullable)
CatalogueService | setDemandOccupancyAvailability | response | demandIndexDefinition | string |  | Required when inputMetric is currentDemand: how the demand index is calculated (the pack requires it to be explicitly configured and documented) (nullable)
CatalogueService | setDemandOccupancyAvailability | response | exitThresholdOffset | number |  | Exit threshold: how far the metric must fall back below a tier's entry before the price reverses; defaults to 2 (points or units of the metric) (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | response | minimumDurationMinutes | integer |  | Minimum duration a threshold must hold before the price moves; defaults to 15 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | response | cooldownMinutes | integer |  | Cooldown after a movement before the next; defaults to 60 (decided 29 September, readiness close-out)
CatalogueService | setDemandOccupancyAvailability | response | priority | integer |  | Priority within the strategy; lower wins
CatalogueService | setDemandOccupancyAvailability | response | enabled | boolean |  | Enabled
CatalogueService | setDemandOccupancyAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setDenominations | request | scopePath | string | yes | The region the write is made at — the materialised path of a region scope node.
OrderService | setDenominations | request | currencyCode | string | yes | (min length 3; max length 3)
OrderService | setDenominations | request | denominations | array of object | yes | (min items 1)
OrderService | setDenominations | request | denominations[].displayName | string | yes | (max length 60)
OrderService | setDenominations | request | denominations[].kind | enum (note, coin) | yes
OrderService | setDenominations | request | denominations[].value | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | setDenominations | request | denominations[].value.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setDenominations | request | denominations[].value.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setDenominations | request | denominations[].value.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setDenominations | request | denominations[].sortOrder | integer | yes | (min 0)
OrderService | setDenominations | request | denominations[].isActive | boolean |  | (default True)
OrderService | setDenominations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setDeveloperMembers | request | members | array of object | yes
PlatformService | setDeveloperMembers | request | members[].email | string (email)
PlatformService | setDeveloperMembers | request | members[].role | enum (owner, admin, developer, readOnly)
PlatformService | setDeveloperMembers | param (path) | developerId | string (uuid) | yes
PlatformService | setDeveloperMembers | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setDeviceAssignment | request | deviceId | string (uuid) |  | From the path of setDeviceAssignment. (read-only)
TenancyService | setDeviceAssignment | request | ownerOrgUnitId | string (uuid) |  | Who the device belongs to — the cost centre that replaces it when it breaks. (nullable)
TenancyService | setDeviceAssignment | request | custodianPrincipalId | string (uuid) |  | Who is holding it right now. (nullable)
TenancyService | setDeviceAssignment | request | assignedWorkstationId | string (uuid) |  | (nullable)
TenancyService | setDeviceAssignment | request | locationScopePath | string |  | (nullable)
TenancyService | setDeviceAssignment | request | lastSeenLocation | string |  | Reported by the heartbeat; distinct from where it is supposed to be. (read-only; nullable)
TenancyService | setDeviceAssignment | request | assetTag | string |  | (nullable)
TenancyService | setDeviceAssignment | request | acquiredAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | request | warrantyExpiresAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | request | assignedAt | string (date-time) |  | (read-only)
TenancyService | setDeviceAssignment | request | scopePath | string |  | (read-only)
TenancyService | setDeviceAssignment | response | deviceId | string (uuid) |  | From the path of setDeviceAssignment. (read-only)
TenancyService | setDeviceAssignment | response | ownerOrgUnitId | string (uuid) |  | Who the device belongs to — the cost centre that replaces it when it breaks. (nullable)
TenancyService | setDeviceAssignment | response | custodianPrincipalId | string (uuid) |  | Who is holding it right now. (nullable)
TenancyService | setDeviceAssignment | response | assignedWorkstationId | string (uuid) |  | (nullable)
TenancyService | setDeviceAssignment | response | locationScopePath | string |  | (nullable)
TenancyService | setDeviceAssignment | response | lastSeenLocation | string |  | Reported by the heartbeat; distinct from where it is supposed to be. (read-only; nullable)
TenancyService | setDeviceAssignment | response | assetTag | string |  | (nullable)
TenancyService | setDeviceAssignment | response | acquiredAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | response | warrantyExpiresAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | setDeviceAssignment | response | assignedAt | string (date-time) |  | (read-only)
TenancyService | setDeviceAssignment | response | scopePath | string |  | (read-only)
TenancyService | setDeviceAssignment | param (path) | deviceId | string (uuid) | yes
TenancyService | setDeviceAssignment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setDeviceBindingPolicy | request | venueId | string (uuid) | yes
AccessService | setDeviceBindingPolicy | request | maximumActiveDevices | integer |  | Devices the credential may be active on at once (min 1; default 1)
AccessService | setDeviceBindingPolicy | request | concurrentSessions | integer |  | (min 1; default 1)
AccessService | setDeviceBindingPolicy | request | deviceChangePolicy | enum (notAllowed, allowedBeforeFirstUse, otpVerificationRequired, operatorApprovalRequired, supervisorApprovalRequired) |  | (default otpVerificationRequired)
AccessService | setDeviceBindingPolicy | response | id | string (uuid) | yes | The ruleId (display rule) or policyId (transfer policy) of the operations
AccessService | setDeviceBindingPolicy | response | kind | enum (activationDisplay, transfer, virtualTicketIdentity, deviceBinding) | yes | Which policy this row is; the columns of the other kinds stay null
AccessService | setDeviceBindingPolicy | response | name | string |  | (max length 200; nullable)
AccessService | setDeviceBindingPolicy | response | venueId | string (uuid) |  | Required for activationDisplay and virtualTicketIdentity (one virtualTicketIdentity row per venue) (nullable)
AccessService | setDeviceBindingPolicy | response | beforeActivationDisplay | array of enum (hideQr, blurQr, showCountdown, showAvailableAtVenue, showVenueDirections) |  | activationDisplay - what the guest sees before the credential activates
AccessService | setDeviceBindingPolicy | response | activeDisplay | array of enum (dynamicQr, activationTimer, credentialStatus, remainingEntitlements) |  | activationDisplay - what the guest sees once it is active
AccessService | setDeviceBindingPolicy | response | activationTriggers | array of string |  | activationDisplay - what activates the credential, e.g.
AccessService | setDeviceBindingPolicy | response | transferAllowed | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | numberOfTransfers | integer |  | transfer (min 0; nullable)
AccessService | setDeviceBindingPolicy | response | beforeFirstValidationOnly | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | requireRecipientAccount | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | requireOtp | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | requireAcceptance | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | returnToSender | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | transferDeadlineHours | integer |  | transfer - hours before the visit after which transfer closes (min 0; nullable)
AccessService | setDeviceBindingPolicy | response | cancelPendingAllowed | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | transferAuditRequired | boolean |  | transfer (nullable)
AccessService | setDeviceBindingPolicy | response | idGenerationPattern | string |  | virtualTicketIdentity - Virtual Ticket ID format: prefix, suffix and length (nullable)
AccessService | setDeviceBindingPolicy | response | ticketClassification | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | ticketOwnershipModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | holderAssignmentRequirements | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | transferabilityReference | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | validityModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | consumptionModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | entitlementModel | string |  | virtualTicketIdentity (nullable)
AccessService | setDeviceBindingPolicy | response | mediaRequirements | array of string |  | virtualTicketIdentity - media types a ticket of this configuration must carry
AccessService | setDeviceBindingPolicy | response | maximumActiveDevices | integer |  | deviceBinding (min 1; nullable)
AccessService | setDeviceBindingPolicy | response | concurrentSessions | integer |  | deviceBinding (min 1; nullable)
AccessService | setDeviceBindingPolicy | response | deviceChangePolicy | enum (notAllowed, allowedBeforeFirstUse, otpVerificationRequired, operatorApprovalRequired, supervisorApprovalRequired) |  | deviceBinding (nullable)
AccessService | setDeviceBindingPolicy | response | scopePath | string | yes | ltree of the owning scope node
AccessService | setDeviceBindingPolicy | response | createdAt | string (date-time) |  | (read-only)
AccessService | setDeviceBindingPolicy | response | updatedAt | string (date-time) |  | (read-only)
AccessService | setDeviceBindingPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDynamicPriceRule | request | rule | PricingDynamicPriceRule | yes | Taken from the backend workbook, 20 September.
CatalogueService | setDynamicPriceRule | request | rule.id | string (uuid)
CatalogueService | setDynamicPriceRule | request | rule.pricingRuleCode | string | yes | (max length 100)
CatalogueService | setDynamicPriceRule | request | rule.name | string | yes | (max length 200)
CatalogueService | setDynamicPriceRule | request | rule.productId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.priceListId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.scopePath | string |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.channelId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.priority | integer | yes
CatalogueService | setDynamicPriceRule | request | rule.validFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.validTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.isActive | boolean | yes
CatalogueService | setDynamicPriceRule | request | rule.dynamicPricingStrategyId | string (uuid) |  | The catalogue.dynamic_pricing_strategy a dynamic rule belongs to (29 September, data model DM3). (nullable)
CatalogueService | setDynamicPriceRule | request | rule.ruleType | string |  | Static rules: PricingRuleCommandCenterView.ruleType; dynamic rules: the builder's ruleKind. (max length 40; nullable)
CatalogueService | setDynamicPriceRule | request | rule.inputMetric | string |  | (max length 40; nullable)
CatalogueService | setDynamicPriceRule | request | rule.conditionLogic | enum (all, any) |  | (default all)
CatalogueService | setDynamicPriceRule | request | rule.cooldownMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | request | rule.minimumDurationMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | request | rule.exitThresholdOffset | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.rangeMinPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.rangeMaxPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | rule.isProtected | boolean |  | A protected segment or channel: dynamic adjustments never apply. (default False)
CatalogueService | setDynamicPriceRule | request | conditions | array of PricingDynamicPriceCondition
CatalogueService | setDynamicPriceRule | request | conditions[].actionId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | request | conditions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | request | conditions[].type | string | yes | (max length 50)
CatalogueService | setDynamicPriceRule | request | conditions[].ruleOperator | string | yes | (max length 20)
CatalogueService | setDynamicPriceRule | request | conditions[].valueJson | string | yes
CatalogueService | setDynamicPriceRule | request | conditions[].sequenceNo | integer | yes
CatalogueService | setDynamicPriceRule | request | actions | array of PricingDynamicPriceAction
CatalogueService | setDynamicPriceRule | request | actions[].id | string (uuid)
CatalogueService | setDynamicPriceRule | request | actions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | request | actions[].type | string | yes | (max length 30)
CatalogueService | setDynamicPriceRule | request | actions[].value | number | yes
CatalogueService | setDynamicPriceRule | request | actions[].minPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | request | actions[].maxPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule | PricingDynamicPriceRule | yes | Taken from the backend workbook, 20 September.
CatalogueService | setDynamicPriceRule | response | rule.id | string (uuid)
CatalogueService | setDynamicPriceRule | response | rule.pricingRuleCode | string | yes | (max length 100)
CatalogueService | setDynamicPriceRule | response | rule.name | string | yes | (max length 200)
CatalogueService | setDynamicPriceRule | response | rule.productId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.priceListId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.scopePath | string |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.channelId | string (uuid) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.priority | integer | yes
CatalogueService | setDynamicPriceRule | response | rule.validFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.validTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.isActive | boolean | yes
CatalogueService | setDynamicPriceRule | response | rule.dynamicPricingStrategyId | string (uuid) |  | The catalogue.dynamic_pricing_strategy a dynamic rule belongs to (29 September, data model DM3). (nullable)
CatalogueService | setDynamicPriceRule | response | rule.ruleType | string |  | Static rules: PricingRuleCommandCenterView.ruleType; dynamic rules: the builder's ruleKind. (max length 40; nullable)
CatalogueService | setDynamicPriceRule | response | rule.inputMetric | string |  | (max length 40; nullable)
CatalogueService | setDynamicPriceRule | response | rule.conditionLogic | enum (all, any) |  | (default all)
CatalogueService | setDynamicPriceRule | response | rule.cooldownMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | response | rule.minimumDurationMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPriceRule | response | rule.exitThresholdOffset | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.rangeMinPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.rangeMaxPercent | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | rule.isProtected | boolean |  | A protected segment or channel: dynamic adjustments never apply. (default False)
CatalogueService | setDynamicPriceRule | response | conditions | array of PricingDynamicPriceCondition
CatalogueService | setDynamicPriceRule | response | conditions[].actionId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | response | conditions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | response | conditions[].type | string | yes | (max length 50)
CatalogueService | setDynamicPriceRule | response | conditions[].ruleOperator | string | yes | (max length 20)
CatalogueService | setDynamicPriceRule | response | conditions[].valueJson | string | yes
CatalogueService | setDynamicPriceRule | response | conditions[].sequenceNo | integer | yes
CatalogueService | setDynamicPriceRule | response | actions | array of PricingDynamicPriceAction
CatalogueService | setDynamicPriceRule | response | actions[].id | string (uuid)
CatalogueService | setDynamicPriceRule | response | actions[].dynamicPriceRuleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | response | actions[].type | string | yes | (max length 30)
CatalogueService | setDynamicPriceRule | response | actions[].value | number | yes
CatalogueService | setDynamicPriceRule | response | actions[].minPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | response | actions[].maxPrice | number |  | (nullable)
CatalogueService | setDynamicPriceRule | param (path) | ruleId | string (uuid) | yes
CatalogueService | setDynamicPriceRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setDynamicPricingGuardrailPolicy | request | id | string (uuid) | yes | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | request | scopeLevel | enum (global, market, venue, strategy, product, event, performance, channel) | yes
CatalogueService | setDynamicPricingGuardrailPolicy | request | scopeId | string (uuid) |  | Null at global. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMinimumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | request | absoluteMaximumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minimumMarginPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumUpliftPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumReductionPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumSingleChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumDailyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumWeeklyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minimumChangeIntervalMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumChangesPerDay | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minimumInventory | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maximumOccupancyTriggerPercent | number |  | (min 0; max 100; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | protectedRateTypes | array of enum (contractRates, membershipRates, corporateRates, promotionalLockedRates, regulatoryPrices, complimentaryRates)
CatalogueService | setDynamicPricingGuardrailPolicy | request | isFrozen | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | request | isKillSwitchActive | boolean |  | Stops every automatic change in scope at once. (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | request | automationLevel | enum (advisory, humanInTheLoop, conditionalAutonomous, autonomous) | yes | (default advisory)
CatalogueService | setDynamicPricingGuardrailPolicy | request | authorityTiers | object |  | [{maxAdjustmentPercent, action, confidenceThreshold}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | maxAdjustmentPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minAiConfidence | number |  | (min 0; max 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | minRevenueUpliftPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | evaluationFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | executionFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | quietPeriodMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | noChangeWindows | object |  | [{anchor, minutesBefore, minutesAfter, clockFrom, clockTo}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | circuitBreakers | object |  | [{trigger, threshold, enabled, tripped}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | requireGuardrailsPassed | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | request | excludeProtectedRates | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | request | requireHealthyForecastData | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | request | safeFailureBehavior | enum (holdLastPrice, returnToBase, freeze, requestReview) |  | (default holdLastPrice)
CatalogueService | setDynamicPricingGuardrailPolicy | request | activeOverride | object |  | {user, reason, overridePrice, start, expiry, returnBehavior}. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | isPaused | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | id | string (uuid) | yes | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | scopeLevel | enum (global, market, venue, strategy, product, event, performance, channel) | yes
CatalogueService | setDynamicPricingGuardrailPolicy | response | scopeId | string (uuid) |  | Null at global. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMinimumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice | object |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setDynamicPricingGuardrailPolicy | response | absoluteMaximumPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minimumMarginPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumUpliftPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumReductionPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumSingleChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumDailyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumWeeklyChangePercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minimumChangeIntervalMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumChangesPerDay | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minimumInventory | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maximumOccupancyTriggerPercent | number |  | (min 0; max 100; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | protectedRateTypes | array of enum (contractRates, membershipRates, corporateRates, promotionalLockedRates, regulatoryPrices, complimentaryRates)
CatalogueService | setDynamicPricingGuardrailPolicy | response | isFrozen | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | response | isKillSwitchActive | boolean |  | Stops every automatic change in scope at once. (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | response | automationLevel | enum (advisory, humanInTheLoop, conditionalAutonomous, autonomous) | yes | (default advisory)
CatalogueService | setDynamicPricingGuardrailPolicy | response | authorityTiers | object |  | [{maxAdjustmentPercent, action, confidenceThreshold}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | maxAdjustmentPercent | number |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minAiConfidence | number |  | (min 0; max 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | minRevenueUpliftPercent | number |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | evaluationFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | executionFrequencyMinutes | integer |  | (min 1; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | quietPeriodMinutes | integer |  | (min 0; nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | noChangeWindows | object |  | [{anchor, minutesBefore, minutesAfter, clockFrom, clockTo}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | circuitBreakers | object |  | [{trigger, threshold, enabled, tripped}]. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | requireGuardrailsPassed | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | response | excludeProtectedRates | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | response | requireHealthyForecastData | boolean |  | (default True)
CatalogueService | setDynamicPricingGuardrailPolicy | response | safeFailureBehavior | enum (holdLastPrice, returnToBase, freeze, requestReview) |  | (default holdLastPrice)
CatalogueService | setDynamicPricingGuardrailPolicy | response | activeOverride | object |  | {user, reason, overridePrice, start, expiry, returnBehavior}. (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | isPaused | boolean |  | (default False)
CatalogueService | setDynamicPricingGuardrailPolicy | response | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | effectiveTo | string (date-time) |  | (nullable)
CatalogueService | setDynamicPricingGuardrailPolicy | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setDynamicPricingGuardrailPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | setEInvoicingProvider | request | id | string (uuid) |  | (read-only)
LedgerService | setEInvoicingProvider | request | legalEntityId | string (uuid) | yes
LedgerService | setEInvoicingProvider | request | providerName | string | yes | The accredited service provider the client appoints. (max length 200)
LedgerService | setEInvoicingProvider | request | endpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | request | testEndpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | request | credentialRef | string |  | A reference to the secret in the vault; the secret is never stored here. (max length 300; nullable)
LedgerService | setEInvoicingProvider | request | participantId | string |  | The legal entity's Peppol participant identifier. (max length 100; nullable)
LedgerService | setEInvoicingProvider | request | documentFormat | enum (pintAe) |  | (default pintAe)
LedgerService | setEInvoicingProvider | request | mode | enum (disabled, test, live) | yes
LedgerService | setEInvoicingProvider | request | transmitWithinHours | integer |  | (min 1; nullable)
LedgerService | setEInvoicingProvider | request | lastAcceptedTestAt | string (date-time) |  | (read-only; nullable)
LedgerService | setEInvoicingProvider | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | setEInvoicingProvider | response | id | string (uuid) |  | (read-only)
LedgerService | setEInvoicingProvider | response | legalEntityId | string (uuid) | yes
LedgerService | setEInvoicingProvider | response | providerName | string | yes | The accredited service provider the client appoints. (max length 200)
LedgerService | setEInvoicingProvider | response | endpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | response | testEndpointUrl | string (uri) |  | (nullable)
LedgerService | setEInvoicingProvider | response | credentialRef | string |  | A reference to the secret in the vault; the secret is never stored here. (max length 300; nullable)
LedgerService | setEInvoicingProvider | response | participantId | string |  | The legal entity's Peppol participant identifier. (max length 100; nullable)
LedgerService | setEInvoicingProvider | response | documentFormat | enum (pintAe) |  | (default pintAe)
LedgerService | setEInvoicingProvider | response | mode | enum (disabled, test, live) | yes
LedgerService | setEInvoicingProvider | response | transmitWithinHours | integer |  | (min 1; nullable)
LedgerService | setEInvoicingProvider | response | lastAcceptedTestAt | string (date-time) |  | (read-only; nullable)
LedgerService | setEInvoicingProvider | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | setEInvoicingProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setEligibilityRule | request | guestType | string |  | Guest type
CatalogueService | setEligibilityRule | request | customerSegment | string |  | Customer segment
CatalogueService | setEligibilityRule | request | ageCategory | string |  | Age/category
CatalogueService | setEligibilityRule | request | membership | string |  | Membership
CatalogueService | setEligibilityRule | request | loyaltyTier | string |  | Loyalty tier
CatalogueService | setEligibilityRule | request | purchaseHistory | string |  | Purchase history
CatalogueService | setEligibilityRule | request | visitHistory | string |  | Visit history
CatalogueService | setEligibilityRule | request | transactionValue | string |  | Transaction value
CatalogueService | setEligibilityRule | request | productPurchased | string |  | Product purchased
CatalogueService | setEligibilityRule | request | channel | string |  | Channel
CatalogueService | setEligibilityRule | request | venue | string |  | Venue
CatalogueService | setEligibilityRule | request | location | string |  | Location
CatalogueService | setEligibilityRule | request | partner | string |  | Partner
CatalogueService | setEligibilityRule | request | dateTime | string (date-time) |  | Date/time
CatalogueService | setEligibilityRule | request | paymentMethod | string |  | Payment method
CatalogueService | setEligibilityRule | request | campaign | string |  | Campaign
CatalogueService | setEligibilityRule | request | customerAccountAttributes | string |  | Customer/account attributes
CatalogueService | setEligibilityRule | request | nestedGroups | string |  | Nested groups
CatalogueService | setEligibilityRule | request | multipleConditionSets | string |  | Multiple condition sets
CatalogueService | setEligibilityRule | request | ruleEffect | enum (include, exclude) |  | Whether matching guests are included or excluded.
CatalogueService | setEligibilityRule | response | guestType | string |  | Guest type
CatalogueService | setEligibilityRule | response | customerSegment | string |  | Customer segment
CatalogueService | setEligibilityRule | response | ageCategory | string |  | Age/category
CatalogueService | setEligibilityRule | response | membership | string |  | Membership
CatalogueService | setEligibilityRule | response | loyaltyTier | string |  | Loyalty tier
CatalogueService | setEligibilityRule | response | purchaseHistory | string |  | Purchase history
CatalogueService | setEligibilityRule | response | visitHistory | string |  | Visit history
CatalogueService | setEligibilityRule | response | transactionValue | string |  | Transaction value
CatalogueService | setEligibilityRule | response | productPurchased | string |  | Product purchased
CatalogueService | setEligibilityRule | response | channel | string |  | Channel
CatalogueService | setEligibilityRule | response | venue | string |  | Venue
CatalogueService | setEligibilityRule | response | location | string |  | Location
CatalogueService | setEligibilityRule | response | partner | string |  | Partner
CatalogueService | setEligibilityRule | response | dateTime | string (date-time) |  | Date/time
CatalogueService | setEligibilityRule | response | paymentMethod | string |  | Payment method
CatalogueService | setEligibilityRule | response | campaign | string |  | Campaign
CatalogueService | setEligibilityRule | response | customerAccountAttributes | string |  | Customer/account attributes
CatalogueService | setEligibilityRule | response | nestedGroups | string |  | Nested groups
CatalogueService | setEligibilityRule | response | multipleConditionSets | string |  | Multiple condition sets
CatalogueService | setEligibilityRule | response | ruleEffect | enum (include, exclude) |  | Whether matching guests are included or excluded.
CatalogueService | setEligibilityRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setEventLifecycleState | request | state | enum (draft, planned, onSale, live, closed, cancelled, archived) | yes
CatalogueService | setEventLifecycleState | request | reason | string |  | (nullable)
CatalogueService | setEventLifecycleState | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | setEventLifecycleState | param (path) | eventId | string (uuid) | yes
CatalogueService | setEventLifecycleState | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setExperienceResourceRequirements | request | requirements | array of ResourceRequirement | yes
VenueOpsService | setExperienceResourceRequirements | request | requirements[].id | string (uuid)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].quantity | integer | yes | (default 1)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].mandatory | boolean |  | (default True)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].requiredQualifications | array of string
VenueOpsService | setExperienceResourceRequirements | request | requirements[].requiredAttributes | object
VenueOpsService | setExperienceResourceRequirements | request | requirements[].substituteResourceIds | array of string (uuid)
VenueOpsService | setExperienceResourceRequirements | request | requirements[].scopePath | string
VenueOpsService | setExperienceResourceRequirements | param (path) | experienceId | string (uuid) | yes
VenueOpsService | setExperienceResourceRequirements | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setFaceMatchingVerification | request | profileId | string (uuid) |  | Absent creates a threshold profile
AccessService | setFaceMatchingVerification | request | venueId | string | yes
AccessService | setFaceMatchingVerification | request | accessContext | string | yes | Where the thresholds apply, e.g. (max length 100)
AccessService | setFaceMatchingVerification | request | highConfidenceMin | number | yes | Score at or above which the match is high confidence (allow if every other rule passes) (min 0; max 1)
AccessService | setFaceMatchingVerification | request | reviewRangeMin | number | yes | Score at or above which the match goes to operator review; below it is denied. (min 0; max 1)
AccessService | setFaceMatchingVerification | request | retryQuantity | integer |  | (min 0; max 5; default 2)
AccessService | setFaceMatchingVerification | request | livenessCheck | boolean |  | (default True)
AccessService | setFaceMatchingVerification | request | duplicateFaceCheck | boolean |  | (default True)
AccessService | setFaceMatchingVerification | request | imageQuality | enum (low, medium, high) |  | Minimum image quality accepted (default medium)
AccessService | setFaceMatchingVerification | request | captureTimeout | integer |  | Seconds (min 1; max 60; default 10)
AccessService | setFaceMatchingVerification | request | maskObstructionHandling | enum (deny, operatorReview, fallbackMethod) |  | (default operatorReview)
AccessService | setFaceMatchingVerification | request | operatorFallback | boolean |  | Review-range results go to operator verification (default True)
AccessService | setFaceMatchingVerification | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setFaceMatchingVerification | response | livenessCheck | boolean |  | Liveness check
AccessService | setFaceMatchingVerification | response | duplicateFaceCheck | boolean |  | Duplicate-face check
AccessService | setFaceMatchingVerification | response | imageQuality | enum (low, medium, high) |  | Minimum image quality accepted (decided 29 September, VM close-out)
AccessService | setFaceMatchingVerification | response | captureTimeout | integer |  | Seconds
AccessService | setFaceMatchingVerification | response | maskObstructionHandling | enum (deny, operatorReview, fallbackMethod) |  | What a masked or obstructed face leads to (decided 29 September, VM close-out)
AccessService | setFaceMatchingVerification | response | operatorFallback | boolean |  | Review-range results go to operator verification
AccessService | setFaceMatchingVerification | response | profileId | string
AccessService | setFaceMatchingVerification | response | venueId | string
AccessService | setFaceMatchingVerification | response | accessContext | string |  | Where the thresholds apply, e.g.
AccessService | setFaceMatchingVerification | response | highConfidenceMin | number |  | Score at or above which the match is high confidence (allow if all other rules pass)
AccessService | setFaceMatchingVerification | response | reviewRangeMin | number |  | Score at or above which the match goes to operator review; below it is denied
AccessService | setFaceMatchingVerification | response | retryQuantity | integer
AccessService | setFaceMatchingVerification | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setFacePassEnrollment | request | venueId | string | yes | Venue this enrolment configuration applies to
AccessService | setFacePassEnrollment | request | enrollmentChannels | array of enum (ticvaiApp, ticketCounter, annualPassCounter, selfServiceKiosk, otherAuthorizedChannel) |  | Channels where Face Pass enrolment is enabled
AccessService | setFacePassEnrollment | request | accountLoginRequired | boolean |  | Account login required
AccessService | setFacePassEnrollment | request | validTicketPassRequired | boolean |  | Valid ticket/pass required
AccessService | setFacePassEnrollment | request | identityCheckRequired | boolean |  | Identity check required
AccessService | setFacePassEnrollment | request | numberOfCaptureAttempts | integer |  | Number of capture attempts
AccessService | setFacePassEnrollment | request | minimumImageQuality | string |  | minimum image quality
AccessService | setFacePassEnrollment | request | operatorVerification | boolean |  | An operator must verify the capture
AccessService | setFacePassEnrollment | request | enrollmentExpiry | integer |  | Days an enrolment stays valid before re-enrolment is needed
AccessService | setFacePassEnrollment | request | duplicateFaceDetection | boolean |  | Block a face already associated with another annual pass
AccessService | setFacePassEnrollment | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setFacePassEnrollment | response | venueId | string | yes | Venue this enrolment configuration applies to
AccessService | setFacePassEnrollment | response | enrollmentChannels | array of enum (ticvaiApp, ticketCounter, annualPassCounter, selfServiceKiosk, otherAuthorizedChannel) |  | Channels where Face Pass enrolment is enabled
AccessService | setFacePassEnrollment | response | accountLoginRequired | boolean |  | Account login required
AccessService | setFacePassEnrollment | response | validTicketPassRequired | boolean |  | Valid ticket/pass required
AccessService | setFacePassEnrollment | response | identityCheckRequired | boolean |  | Identity check required
AccessService | setFacePassEnrollment | response | numberOfCaptureAttempts | integer |  | Number of capture attempts
AccessService | setFacePassEnrollment | response | minimumImageQuality | string |  | minimum image quality
AccessService | setFacePassEnrollment | response | operatorVerification | boolean |  | An operator must verify the capture
AccessService | setFacePassEnrollment | response | enrollmentExpiry | integer |  | Days an enrolment stays valid before re-enrolment is needed
AccessService | setFacePassEnrollment | response | duplicateFaceDetection | boolean |  | Block a face already associated with another annual pass
AccessService | setFacePassEnrollment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setFaceTagTemporaryEnrollment | request | profileId | string (uuid) |  | Absent creates a Face Tag profile
AccessService | setFaceTagTemporaryEnrollment | request | venueId | string | yes
AccessService | setFaceTagTemporaryEnrollment | request | name | string | yes | (max length 200)
AccessService | setFaceTagTemporaryEnrollment | request | enrollmentChannels | array of enum (ticketCounter, entryGate) | yes | Where a Face Tag may be captured (min items 1)
AccessService | setFaceTagTemporaryEnrollment | request | bindTo | enum (ticket, visit, temporaryCredential) | yes | What the Face Tag is bound to (default ticket)
AccessService | setFaceTagTemporaryEnrollment | request | deletionTrigger | enum (ticketFullyRedeemed, endOfVisit, ticketExpiration, credentialCancellation, operationalRetentionThreshold) | yes | When the Face Tag is deleted automatically. (default ticketFullyRedeemed)
AccessService | setFaceTagTemporaryEnrollment | request | retentionThresholdHours | integer |  | Used only when deletionTrigger is operationalRetentionThreshold, and then required. (min 1)
AccessService | setFaceTagTemporaryEnrollment | request | consentCapture | enum (onScreenAcknowledgement, signedForm) |  | How consent is taken when a Face Tag is captured (3.2.44; added 29 September, build pass). (default onScreenAcknowledgement)
AccessService | setFaceTagTemporaryEnrollment | request | status | enum (active, inactive) |  | Switches the profile on or off; an inactive profile is not applied at any gate and stays for reuse (decided 29 September, writers pass) (default active)
AccessService | setFaceTagTemporaryEnrollment | response | enrollmentChannels | array of enum (ticketCounter, entryGate) |  | Where a Face Tag may be captured
AccessService | setFaceTagTemporaryEnrollment | response | bindTo | enum (ticket, visit, temporaryCredential) |  | What the Face Tag is bound to
AccessService | setFaceTagTemporaryEnrollment | response | deletionTrigger | enum (ticketFullyRedeemed, endOfVisit, ticketExpiration, credentialCancellation, operationalRetentionThreshold) |  | When the Face Tag is automatically deleted; default ticketFullyRedeemed
AccessService | setFaceTagTemporaryEnrollment | response | profileId | string
AccessService | setFaceTagTemporaryEnrollment | response | venueId | string
AccessService | setFaceTagTemporaryEnrollment | response | name | string
AccessService | setFaceTagTemporaryEnrollment | response | retentionThresholdHours | integer |  | Used when deletionTrigger is operationalRetentionThreshold.
AccessService | setFaceTagTemporaryEnrollment | response | consentCapture | enum (onScreenAcknowledgement, signedForm) |  | How consent is taken at capture; onScreenAcknowledgement (no form to sign) unless set
AccessService | setFaceTagTemporaryEnrollment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFaqs | request | categories | array of FaqCategory | yes
WhiteLabelService | setFaqs | request | categories[].code | string | yes
WhiteLabelService | setFaqs | request | categories[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setFaqs | request | categories[].sortOrder | integer
WhiteLabelService | setFaqs | request | categories[].entries | array of object | yes
WhiteLabelService | setFaqs | request | categories[].entries[].id | string (uuid) | yes
WhiteLabelService | setFaqs | request | categories[].entries[].question | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setFaqs | request | categories[].entries[].answer | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | setFaqs | request | categories[].entries[].sortOrder | integer
WhiteLabelService | setFaqs | request | categories[].entries[].isPublished | boolean
WhiteLabelService | setFaqs | request | categories[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setFaqs | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFeatureToggles | request | features | array of object | yes
WhiteLabelService | setFeatureToggles | request | features[].featureKey | FeatureKey: enum (digitalCompanionMode, aiConciergeChat, lostAndFound, pushNotifications, socialSharing, multiLanguage, appleWallet, googlePay, …) | yes | The feature toggles a tenant can set — one list for FeatureToggle and the setFeatureToggles body, which took a free string where the response had this enum.
WhiteLabelService | setFeatureToggles | request | features[].isEnabled | boolean | yes
WhiteLabelService | setFeatureToggles | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setFixedPriceOffer | request | requiredQuantity | integer |  | Required quantity
CatalogueService | setFixedPriceOffer | request | requiredProducts | string |  | Required products
CatalogueService | setFixedPriceOffer | request | productCategory | string |  | Product category
CatalogueService | setFixedPriceOffer | request | mixAndMatchAllowed | boolean |  | Mix-and-match allowed
CatalogueService | setFixedPriceOffer | request | fixedPromotionalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setFixedPriceOffer | request | fixedPromotionalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setFixedPriceOffer | request | fixedPromotionalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setFixedPriceOffer | request | fixedPromotionalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setFixedPriceOffer | request | currency | string |  | Currency
CatalogueService | setFixedPriceOffer | request | maximumRepetitions | string |  | Maximum repetitions
CatalogueService | setFixedPriceOffer | request | minimumMaximumProductValues | string |  | Minimum/maximum product values
CatalogueService | setFixedPriceOffer | response | requiredQuantity | integer |  | Required quantity
CatalogueService | setFixedPriceOffer | response | requiredProducts | string |  | Required products
CatalogueService | setFixedPriceOffer | response | productCategory | string |  | Product category
CatalogueService | setFixedPriceOffer | response | mixAndMatchAllowed | boolean |  | Mix-and-match allowed
CatalogueService | setFixedPriceOffer | response | fixedPromotionalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setFixedPriceOffer | response | fixedPromotionalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setFixedPriceOffer | response | fixedPromotionalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setFixedPriceOffer | response | fixedPromotionalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setFixedPriceOffer | response | currency | string |  | Currency
CatalogueService | setFixedPriceOffer | response | maximumRepetitions | string |  | Maximum repetitions
CatalogueService | setFixedPriceOffer | response | minimumMaximumProductValues | string |  | Minimum/maximum product values
CatalogueService | setFixedPriceOffer | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setFnbDeliveryPolicy | request | id | string (uuid) |  | (read-only)
FnbService | setFnbDeliveryPolicy | request | outletId | string (uuid) | yes
FnbService | setFnbDeliveryPolicy | request | collectionEnabled | boolean |  | (default True)
FnbService | setFnbDeliveryPolicy | request | deliveryEnabled | boolean |  | (default False)
FnbService | setFnbDeliveryPolicy | request | collectionPoint | string |  | (max length 200; nullable)
FnbService | setFnbDeliveryPolicy | request | collectionHoldMinutes | integer |  | (default 20)
FnbService | setFnbDeliveryPolicy | request | asapCollectionMinutes | integer |  | (default 25)
FnbService | setFnbDeliveryPolicy | request | asapDeliveryMinutes | integer |  | (default 45)
FnbService | setFnbDeliveryPolicy | request | slotMinutes | integer |  | (default 30)
FnbService | setFnbDeliveryPolicy | request | minimumOrder | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | request | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | request | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | request | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | request | deliveryFee | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | request | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | request | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | request | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | request | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | request | radiusKm | number |  | (min 0; nullable)
FnbService | setFnbDeliveryPolicy | request | emiratesServed | array of string
FnbService | setFnbDeliveryPolicy | request | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | setFnbDeliveryPolicy | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setFnbDeliveryPolicy | response | id | string (uuid) |  | (read-only)
FnbService | setFnbDeliveryPolicy | response | outletId | string (uuid) | yes
FnbService | setFnbDeliveryPolicy | response | collectionEnabled | boolean |  | (default True)
FnbService | setFnbDeliveryPolicy | response | deliveryEnabled | boolean |  | (default False)
FnbService | setFnbDeliveryPolicy | response | collectionPoint | string |  | (max length 200; nullable)
FnbService | setFnbDeliveryPolicy | response | collectionHoldMinutes | integer |  | (default 20)
FnbService | setFnbDeliveryPolicy | response | asapCollectionMinutes | integer |  | (default 25)
FnbService | setFnbDeliveryPolicy | response | asapDeliveryMinutes | integer |  | (default 45)
FnbService | setFnbDeliveryPolicy | response | slotMinutes | integer |  | (default 30)
FnbService | setFnbDeliveryPolicy | response | minimumOrder | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | response | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | response | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | response | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | response | deliveryFee | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | response | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | response | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | response | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove | object |  | (nullable)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setFnbDeliveryPolicy | response | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setFnbDeliveryPolicy | response | radiusKm | number |  | (min 0; nullable)
FnbService | setFnbDeliveryPolicy | response | emiratesServed | array of string
FnbService | setFnbDeliveryPolicy | response | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | setFnbDeliveryPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setFnbDeliveryPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setFnbDeliveryPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFonts | request | primaryLatin | string | yes
WhiteLabelService | setFonts | request | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | setFonts | request | secondaryLatin | string |  | (nullable)
WhiteLabelService | setFonts | request | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | setFonts | request | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | setFonts | request | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | setFonts | response | primaryLatin | string | yes
WhiteLabelService | setFonts | response | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | setFonts | response | secondaryLatin | string |  | (nullable)
WhiteLabelService | setFonts | response | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | setFonts | response | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | setFonts | response | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | setFonts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setFonts | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | setFooter | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | setFooter | request | scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | setFooter | request | columns | array of object
WhiteLabelService | setFooter | request | columns[].heading | string
WhiteLabelService | setFooter | request | columns[].links | array of object
WhiteLabelService | setFooter | request | columns[].links[].label | string
WhiteLabelService | setFooter | request | columns[].links[].url | string
WhiteLabelService | setFooter | request | columns[].links[].opensCookiePreferences | boolean |  | (default False)
WhiteLabelService | setFooter | request | legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | setFooter | request | legalLinks.termsUrl | string
WhiteLabelService | setFooter | request | legalLinks.privacyUrl | string
WhiteLabelService | setFooter | request | legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | setFooter | request | legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | setFooter | request | copyrightText | string
WhiteLabelService | setFooter | request | socialLinks | array of object
WhiteLabelService | setFooter | request | socialLinks[].platform | string
WhiteLabelService | setFooter | request | socialLinks[].url | string
WhiteLabelService | setFooter | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | setFooter | response | scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | setFooter | response | columns | array of object
WhiteLabelService | setFooter | response | columns[].heading | string
WhiteLabelService | setFooter | response | columns[].links | array of object
WhiteLabelService | setFooter | response | columns[].links[].label | string
WhiteLabelService | setFooter | response | columns[].links[].url | string
WhiteLabelService | setFooter | response | columns[].links[].opensCookiePreferences | boolean |  | (default False)
WhiteLabelService | setFooter | response | legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | setFooter | response | legalLinks.termsUrl | string
WhiteLabelService | setFooter | response | legalLinks.privacyUrl | string
WhiteLabelService | setFooter | response | legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | setFooter | response | legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | setFooter | response | copyrightText | string
WhiteLabelService | setFooter | response | socialLinks | array of object
WhiteLabelService | setFooter | response | socialLinks[].platform | string
WhiteLabelService | setFooter | response | socialLinks[].url | string
WhiteLabelService | setFooter | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | setFxProvider | request | assignments | array of FxProviderAssignment | yes | At most one per purpose.
LedgerService | setFxProvider | request | assignments[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | setFxProvider | request | assignments[].source | FxRateSource: enum (manual, uaeCentralBank, ecb, openExchangeRates, cardScheme, provider) | yes | Where the rate came from, and which provider specifically.
LedgerService | setFxProvider | request | assignments[].credentialRef | string |  | BYOK — the key lives in the secret store, never here. (nullable)
LedgerService | setFxProvider | request | assignments[].schedule | string |  | Cron in the region timezone. (nullable)
LedgerService | setFxProvider | request | assignments[].scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | setFxProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | setFxRate | request | id | string (uuid) |  | (read-only)
LedgerService | setFxRate | request | fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | request | toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | request | rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | setFxRate | request | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | setFxRate | request | source | object |  | (read-only)
LedgerService | setFxRate | request | effectiveFrom | string (date-time) | yes
LedgerService | setFxRate | request | effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | setFxRate | request | setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | setFxRate | request | note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | setFxRate | request | providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | setFxRate | request | fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | setFxRate | response | id | string (uuid) |  | (read-only)
LedgerService | setFxRate | response | fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | response | toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | setFxRate | response | rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | setFxRate | response | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | setFxRate | response | source | object |  | (read-only)
LedgerService | setFxRate | response | effectiveFrom | string (date-time) | yes
LedgerService | setFxRate | response | effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | setFxRate | response | setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | setFxRate | response | note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | setFxRate | response | providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | setFxRate | response | fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | setFxRate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setGateModePolicy | request | id | string (uuid) | yes
AccessService | setGateModePolicy | request | venueId | string (uuid) | yes
AccessService | setGateModePolicy | request | mode | enum (freeFlow, dropArm) | yes | Non-standard operating mode governed (R221 vocabulary)
AccessService | setGateModePolicy | request | whoCanActivate | array of string |  | Roles allowed to activate this mode
AccessService | setGateModePolicy | request | accessPointGroupId | string (uuid) |  | Gate group the policy applies to (access.access_point_group); null for the whole venue (nullable)
AccessService | setGateModePolicy | request | reasonRequired | boolean |  | (default True)
AccessService | setGateModePolicy | request | emergencyCode | string |  | (nullable)
AccessService | setGateModePolicy | request | automaticNotification | boolean |  | (default False)
AccessService | setGateModePolicy | request | createsIncident | boolean |  | Activation creates an incident record (default False)
AccessService | setGateModePolicy | request | scopePath | string | yes | ltree of the owning scope node (ADR-0005)
AccessService | setGateModePolicy | request | createdAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | request | updatedAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | response | id | string (uuid) | yes
AccessService | setGateModePolicy | response | venueId | string (uuid) | yes
AccessService | setGateModePolicy | response | mode | enum (freeFlow, dropArm) | yes | Non-standard operating mode governed (R221 vocabulary)
AccessService | setGateModePolicy | response | whoCanActivate | array of string |  | Roles allowed to activate this mode
AccessService | setGateModePolicy | response | accessPointGroupId | string (uuid) |  | Gate group the policy applies to (access.access_point_group); null for the whole venue (nullable)
AccessService | setGateModePolicy | response | reasonRequired | boolean |  | (default True)
AccessService | setGateModePolicy | response | emergencyCode | string |  | (nullable)
AccessService | setGateModePolicy | response | automaticNotification | boolean |  | (default False)
AccessService | setGateModePolicy | response | createsIncident | boolean |  | Activation creates an incident record (default False)
AccessService | setGateModePolicy | response | scopePath | string | yes | ltree of the owning scope node (ADR-0005)
AccessService | setGateModePolicy | response | createdAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | response | updatedAt | string (date-time) |  | (read-only)
AccessService | setGateModePolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setGiftFreeProduct | request | basketValue | string |  | Basket value
CatalogueService | setGiftFreeProduct | request | product | string |  | Product
CatalogueService | setGiftFreeProduct | request | quantity | integer |  | Quantity
CatalogueService | setGiftFreeProduct | request | productCategory | string |  | Product category
CatalogueService | setGiftFreeProduct | request | ticket | string |  | Ticket
CatalogueService | setGiftFreeProduct | request | membership | string |  | Membership
CatalogueService | setGiftFreeProduct | request | customerSegment | string |  | Customer segment
CatalogueService | setGiftFreeProduct | request | typesType | enum (freeRetailProduct, freeFBProduct, freeTicket, freeAddOn, freeExperience, voucher, upgrade, service, …) |  | Vocabulary listed under Reward Types.
CatalogueService | setGiftFreeProduct | request | inventoryAvailability | string |  | Inventory availability
CatalogueService | setGiftFreeProduct | request | locationInventory | string |  | Location inventory
CatalogueService | setGiftFreeProduct | request | eligibleFulfillmentPoint | string |  | Eligible fulfillment point
CatalogueService | setGiftFreeProduct | request | substitutionRules | string |  | Substitution rules
CatalogueService | setGiftFreeProduct | request | doNotOfferPromotion | string |  | Do not offer promotion
CatalogueService | setGiftFreeProduct | request | provideAlternativeReward | string |  | Provide alternative reward
CatalogueService | setGiftFreeProduct | request | allowLaterFulfillment | boolean |  | Allow later fulfillment
CatalogueService | setGiftFreeProduct | response | basketValue | string |  | Basket value
CatalogueService | setGiftFreeProduct | response | product | string |  | Product
CatalogueService | setGiftFreeProduct | response | quantity | integer |  | Quantity
CatalogueService | setGiftFreeProduct | response | productCategory | string |  | Product category
CatalogueService | setGiftFreeProduct | response | ticket | string |  | Ticket
CatalogueService | setGiftFreeProduct | response | membership | string |  | Membership
CatalogueService | setGiftFreeProduct | response | customerSegment | string |  | Customer segment
CatalogueService | setGiftFreeProduct | response | typesType | enum (freeRetailProduct, freeFBProduct, freeTicket, freeAddOn, freeExperience, voucher, upgrade, service, …) |  | Vocabulary listed under Reward Types.
CatalogueService | setGiftFreeProduct | response | inventoryAvailability | string |  | Inventory availability
CatalogueService | setGiftFreeProduct | response | locationInventory | string |  | Location inventory
CatalogueService | setGiftFreeProduct | response | eligibleFulfillmentPoint | string |  | Eligible fulfillment point
CatalogueService | setGiftFreeProduct | response | substitutionRules | string |  | Substitution rules
CatalogueService | setGiftFreeProduct | response | doNotOfferPromotion | string |  | Do not offer promotion
CatalogueService | setGiftFreeProduct | response | provideAlternativeReward | string |  | Provide alternative reward
CatalogueService | setGiftFreeProduct | response | allowLaterFulfillment | boolean |  | Allow later fulfillment
CatalogueService | setGiftFreeProduct | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setGroupPackageDefinition | request | id | string (uuid) |  | (read-only)
CatalogueService | setGroupPackageDefinition | request | productId | string |  | (read-only)
CatalogueService | setGroupPackageDefinition | request | kind | enum (school, party) | yes
CatalogueService | setGroupPackageDefinition | request | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | setGroupPackageDefinition | request | durationMinutes | integer | yes | (min 15)
CatalogueService | setGroupPackageDefinition | request | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | setGroupPackageDefinition | request | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | setGroupPackageDefinition | request | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | setGroupPackageDefinition | request | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | setGroupPackageDefinition | request | includes | array of string
CatalogueService | setGroupPackageDefinition | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setGroupPackageDefinition | response | id | string (uuid) |  | (read-only)
CatalogueService | setGroupPackageDefinition | response | productId | string |  | (read-only)
CatalogueService | setGroupPackageDefinition | response | kind | enum (school, party) | yes
CatalogueService | setGroupPackageDefinition | response | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | setGroupPackageDefinition | response | durationMinutes | integer | yes | (min 15)
CatalogueService | setGroupPackageDefinition | response | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | setGroupPackageDefinition | response | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | setGroupPackageDefinition | response | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | setGroupPackageDefinition | response | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | setGroupPackageDefinition | response | includes | array of string
CatalogueService | setGroupPackageDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setGroupPackageDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setGroupPackageDefinition | param (path) | productId | string | yes
CatalogueService | setGuestChoiceBuild | request | groupName | string |  | Group name
CatalogueService | setGuestChoiceBuild | request | category | string |  | Category
CatalogueService | setGuestChoiceBuild | request | minimumSelections | string |  | Minimum selections
CatalogueService | setGuestChoiceBuild | request | maximumSelections | string |  | Maximum selections
CatalogueService | setGuestChoiceBuild | request | requiredOptional | string |  | Required/optional
CatalogueService | setGuestChoiceBuild | request | eligibleProducts | string |  | Eligible products
CatalogueService | setGuestChoiceBuild | request | additionalCharge | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setGuestChoiceBuild | request | additionalCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setGuestChoiceBuild | request | additionalCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setGuestChoiceBuild | request | additionalCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setGuestChoiceBuild | request | selectionOrder | string |  | Selection order
CatalogueService | setGuestChoiceBuild | response | groupName | string |  | Group name
CatalogueService | setGuestChoiceBuild | response | category | string |  | Category
CatalogueService | setGuestChoiceBuild | response | minimumSelections | string |  | Minimum selections
CatalogueService | setGuestChoiceBuild | response | maximumSelections | string |  | Maximum selections
CatalogueService | setGuestChoiceBuild | response | requiredOptional | string |  | Required/optional
CatalogueService | setGuestChoiceBuild | response | eligibleProducts | string |  | Eligible products
CatalogueService | setGuestChoiceBuild | response | additionalCharge | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setGuestChoiceBuild | response | additionalCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setGuestChoiceBuild | response | additionalCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setGuestChoiceBuild | response | additionalCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setGuestChoiceBuild | response | selectionOrder | string |  | Selection order
CatalogueService | setGuestChoiceBuild | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | setGuestVerificationPolicy | request | id | string (uuid) |  | (read-only)
IdentityService | setGuestVerificationPolicy | request | scopePath | string |  | The tenant, written by the server (x-ticvai-config-scope: tenant). (read-only)
IdentityService | setGuestVerificationPolicy | request | registrationRequires | array of enum (email, mobileOtp) | yes | Verifications a new account must pass before it is usable.
IdentityService | setGuestVerificationPolicy | request | idDocumentRequiredFor | array of enum (accountCreation, ageRestrictedPurchase, residentPricing, accountRecovery, walletTopUpAboveLimit) |  | The moments that need a verified ID document.
IdentityService | setGuestVerificationPolicy | request | walletTopUpLimit | Money |  | On the wire this is three fields; in the database it is one column.
IdentityService | setGuestVerificationPolicy | request | walletTopUpLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
IdentityService | setGuestVerificationPolicy | request | walletTopUpLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
IdentityService | setGuestVerificationPolicy | request | walletTopUpLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
IdentityService | setGuestVerificationPolicy | request | acceptedDocumentKinds | array of enum (passport, emiratesId, nationalId, drivingLicence, residencePermit, other) |  | Proposed default passport, emiratesId, nationalId.
IdentityService | setGuestVerificationPolicy | request | uaePassSatisfiesIdDocument | boolean |  | A guest signed in with UAE Pass (guestUaePassLogin) counts as ID-verified, since the national identity has already checked the person. (default True)
IdentityService | setGuestVerificationPolicy | request | socialLoginCountsAsEmailVerified | boolean |  | (default True)
IdentityService | setGuestVerificationPolicy | request | selfieRequired | boolean |  | (default False)
IdentityService | setGuestVerificationPolicy | request | reviewMode | enum (manual, provider, providerThenManual) |  | Who checks a document. (default manual)
IdentityService | setGuestVerificationPolicy | request | documentImageRetention | enum (deleteOnDecision, keepUntilDocumentExpiry) |  | How long the scan is kept. (default deleteOnDecision)
IdentityService | setGuestVerificationPolicy | request | maxResubmissions | integer |  | (min 0; max 10; default 3)
IdentityService | setGuestVerificationPolicy | request | updatedAt | string (date-time) |  | (read-only)
IdentityService | setGuestVerificationPolicy | response | id | string (uuid) |  | (read-only)
IdentityService | setGuestVerificationPolicy | response | scopePath | string |  | The tenant, written by the server (x-ticvai-config-scope: tenant). (read-only)
IdentityService | setGuestVerificationPolicy | response | registrationRequires | array of enum (email, mobileOtp) | yes | Verifications a new account must pass before it is usable.
IdentityService | setGuestVerificationPolicy | response | idDocumentRequiredFor | array of enum (accountCreation, ageRestrictedPurchase, residentPricing, accountRecovery, walletTopUpAboveLimit) |  | The moments that need a verified ID document.
IdentityService | setGuestVerificationPolicy | response | walletTopUpLimit | Money |  | On the wire this is three fields; in the database it is one column.
IdentityService | setGuestVerificationPolicy | response | walletTopUpLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
IdentityService | setGuestVerificationPolicy | response | walletTopUpLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
IdentityService | setGuestVerificationPolicy | response | walletTopUpLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
IdentityService | setGuestVerificationPolicy | response | acceptedDocumentKinds | array of enum (passport, emiratesId, nationalId, drivingLicence, residencePermit, other) |  | Proposed default passport, emiratesId, nationalId.
IdentityService | setGuestVerificationPolicy | response | uaePassSatisfiesIdDocument | boolean |  | A guest signed in with UAE Pass (guestUaePassLogin) counts as ID-verified, since the national identity has already checked the person. (default True)
IdentityService | setGuestVerificationPolicy | response | socialLoginCountsAsEmailVerified | boolean |  | (default True)
IdentityService | setGuestVerificationPolicy | response | selfieRequired | boolean |  | (default False)
IdentityService | setGuestVerificationPolicy | response | reviewMode | enum (manual, provider, providerThenManual) |  | Who checks a document. (default manual)
IdentityService | setGuestVerificationPolicy | response | documentImageRetention | enum (deleteOnDecision, keepUntilDocumentExpiry) |  | How long the scan is kept. (default deleteOnDecision)
IdentityService | setGuestVerificationPolicy | response | maxResubmissions | integer |  | (min 0; max 10; default 3)
IdentityService | setGuestVerificationPolicy | response | updatedAt | string (date-time) |  | (read-only)
IdentityService | setGuestVerificationPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setHeader | request | layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | setHeader | request | showLogo | boolean |  | (default True)
WhiteLabelService | setHeader | request | showMenu | boolean |  | (default True)
WhiteLabelService | setHeader | request | showNotifications | boolean |  | (default True)
WhiteLabelService | setHeader | request | backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setHeader | response | layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | setHeader | response | showLogo | boolean |  | (default True)
WhiteLabelService | setHeader | response | showMenu | boolean |  | (default True)
WhiteLabelService | setHeader | response | showNotifications | boolean |  | (default True)
WhiteLabelService | setHeader | response | backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setHeader | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setHeader | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | setHomepageLayout | request | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | request | sections | array of object | yes
WhiteLabelService | setHomepageLayout | request | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | request | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | setHomepageLayout | request | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setHomepageLayout | request | sections[].sortOrder | integer | yes
WhiteLabelService | setHomepageLayout | request | sections[].isVisible | boolean | yes
WhiteLabelService | setHomepageLayout | request | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | setHomepageLayout | request | sections[].maxItems | integer |  | How many items the section shows. (nullable)
WhiteLabelService | setHomepageLayout | request | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | setHomepageLayout | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | response | sections | array of object | yes
WhiteLabelService | setHomepageLayout | response | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setHomepageLayout | response | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | setHomepageLayout | response | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setHomepageLayout | response | sections[].sortOrder | integer | yes
WhiteLabelService | setHomepageLayout | response | sections[].isVisible | boolean | yes
WhiteLabelService | setHomepageLayout | response | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | setHomepageLayout | response | sections[].maxItems | integer |  | How many items the section shows. (nullable)
WhiteLabelService | setHomepageLayout | response | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | setHomepageLayout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setHomepageLayout | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
AiService | setIndexSource | request | id | string (uuid) |  | (read-only)
AiService | setIndexSource | request | table | string | yes | Schema-qualified, e.g.
AiService | setIndexSource | request | contract | string |  | Which contract owns it, for tracing back.
AiService | setIndexSource | request | textFields | array of string | yes | The fields a person would read. (min items 1)
AiService | setIndexSource | request | payloadFields | array of string |  | Carried alongside the vector for filtering, not embedded.
AiService | setIndexSource | request | collection | string | yes | Which embedding table it lands in (ai.chunk_embedding for the default model; one table per embedding model, AI design 5.8).
AiService | setIndexSource | request | scopeLevel | enum (tenant, region, venue) | yes
AiService | setIndexSource | request | invalidatedBy | array of string |  | Domain events that make an entry stale.
AiService | setIndexSource | request | chunkStrategy | enum (wholeRecord, paragraph, fixedTokens, section, semanticSection, parentChild) |  | Changes what is stored, so it cannot be altered without a reindex.
AiService | setIndexSource | request | parentField | string |  | Which field carries the parent context, where chunkStrategy is parentChild. (nullable)
AiService | setIndexSource | request | isActive | boolean
AiService | setIndexSource | request | entryCount | integer |  | (read-only)
AiService | setIndexSource | request | lastIndexedAt | string (date-time) |  | (read-only; nullable)
AiService | setIndexSource | request | staleCount | integer |  | Records changed since their last embedding. (read-only)
AiService | setIndexSource | response | id | string (uuid) |  | (read-only)
AiService | setIndexSource | response | table | string | yes | Schema-qualified, e.g.
AiService | setIndexSource | response | contract | string |  | Which contract owns it, for tracing back.
AiService | setIndexSource | response | textFields | array of string | yes | The fields a person would read. (min items 1)
AiService | setIndexSource | response | payloadFields | array of string |  | Carried alongside the vector for filtering, not embedded.
AiService | setIndexSource | response | collection | string | yes | Which embedding table it lands in (ai.chunk_embedding for the default model; one table per embedding model, AI design 5.8).
AiService | setIndexSource | response | scopeLevel | enum (tenant, region, venue) | yes
AiService | setIndexSource | response | invalidatedBy | array of string |  | Domain events that make an entry stale.
AiService | setIndexSource | response | chunkStrategy | enum (wholeRecord, paragraph, fixedTokens, section, semanticSection, parentChild) |  | Changes what is stored, so it cannot be altered without a reindex.
AiService | setIndexSource | response | parentField | string |  | Which field carries the parent context, where chunkStrategy is parentChild. (nullable)
AiService | setIndexSource | response | isActive | boolean
AiService | setIndexSource | response | entryCount | integer |  | (read-only)
AiService | setIndexSource | response | lastIndexedAt | string (date-time) |  | (read-only; nullable)
AiService | setIndexSource | response | staleCount | integer |  | Records changed since their last embedding. (read-only)
AiService | setIndexSource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setInstalmentPolicy | request | enabled | boolean |  | (default False)
OrderService | setInstalmentPolicy | request | eligibleProductKinds | array of enum (membership, annualPass, seasonPass, groupBooking, event)
OrderService | setInstalmentPolicy | request | minimumOrderValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setInstalmentPolicy | request | minimumOrderValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setInstalmentPolicy | request | minimumOrderValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setInstalmentPolicy | request | minimumOrderValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setInstalmentPolicy | request | allowedFrequencies | array of enum (monthly, quarterly, custom)
OrderService | setInstalmentPolicy | request | maximumInstalments | integer |  | (min 2)
OrderService | setInstalmentPolicy | request | dueAtPurchasePercent | number |  | (min 0; max 100)
OrderService | setInstalmentPolicy | request | instalmentFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setInstalmentPolicy | request | instalmentFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setInstalmentPolicy | request | instalmentFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setInstalmentPolicy | request | instalmentFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setInstalmentPolicy | request | requireStoredCard | boolean |  | (default True)
OrderService | setInstalmentPolicy | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | setInstalmentPolicy | response | enabled | boolean |  | (default False)
OrderService | setInstalmentPolicy | response | eligibleProductKinds | array of enum (membership, annualPass, seasonPass, groupBooking, event)
OrderService | setInstalmentPolicy | response | minimumOrderValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setInstalmentPolicy | response | minimumOrderValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setInstalmentPolicy | response | minimumOrderValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setInstalmentPolicy | response | minimumOrderValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setInstalmentPolicy | response | allowedFrequencies | array of enum (monthly, quarterly, custom)
OrderService | setInstalmentPolicy | response | maximumInstalments | integer |  | (min 2)
OrderService | setInstalmentPolicy | response | dueAtPurchasePercent | number |  | (min 0; max 100)
OrderService | setInstalmentPolicy | response | instalmentFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setInstalmentPolicy | response | instalmentFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setInstalmentPolicy | response | instalmentFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setInstalmentPolicy | response | instalmentFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setInstalmentPolicy | response | requireStoredCard | boolean |  | (default True)
OrderService | setInstalmentPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | setInstalmentPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setInstalmentPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | setInventoryKitDefinition | request | kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | request | components | array of InventoryKitComponent | yes
InventoryService | setInventoryKitDefinition | request | components[].kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | request | components[].componentItemId | string (uuid) | yes
InventoryService | setInventoryKitDefinition | request | components[].quantity | number | yes
InventoryService | setInventoryKitDefinition | request | components[].unit | string |  | The component's base unit where omitted. (nullable)
InventoryService | setInventoryKitDefinition | request | components[].scopePath | string |  | The partition key (ADR-0005). (read-only)
InventoryService | setInventoryKitDefinition | response | kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | response | components | array of InventoryKitComponent | yes
InventoryService | setInventoryKitDefinition | response | components[].kitItemId | string (uuid) |  | (read-only)
InventoryService | setInventoryKitDefinition | response | components[].componentItemId | string (uuid) | yes
InventoryService | setInventoryKitDefinition | response | components[].quantity | number | yes
InventoryService | setInventoryKitDefinition | response | components[].unit | string |  | The component's base unit where omitted. (nullable)
InventoryService | setInventoryKitDefinition | response | components[].scopePath | string |  | The partition key (ADR-0005). (read-only)
InventoryService | setInventoryKitDefinition | param (path) | itemId | string (uuid) | yes
InventoryService | setInventoryKitDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setItemAvailability | request | isAvailable | boolean | yes
FnbService | setItemAvailability | request | reason | enum (soldOut, ingredientUnavailable, equipmentDown, seasonal, other) |  | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | setItemAvailability | request | note | string |  | Free text. (max length 500; nullable)
FnbService | setItemAvailability | request | restoreAt | string (date-time) |  | Automatic restore, typically at next service.
FnbService | setItemAvailability | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | setItemAvailability | response | id | string (uuid) | yes
FnbService | setItemAvailability | response | productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | setItemAvailability | response | name | string | yes
FnbService | setItemAvailability | response | description | string |  | (nullable)
FnbService | setItemAvailability | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setItemAvailability | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setItemAvailability | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setItemAvailability | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setItemAvailability | response | sortOrder | integer
FnbService | setItemAvailability | response | modifierGroupIds | array of string (uuid)
FnbService | setItemAvailability | response | stationId | string (uuid) |  | (nullable)
FnbService | setItemAvailability | response | menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | setItemAvailability | response | isStockTracked | boolean |  | True where a recipe exists.
FnbService | setItemAvailability | response | isAvailable | boolean | yes
FnbService | setItemAvailability | response | unavailableReason | string |  | (nullable)
FnbService | setItemAvailability | response | restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setItemAvailability | response | preparationMinutes | integer |  | (nullable)
FnbService | setItemAvailability | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setItemAvailability | param (path) | itemId | string (uuid) | yes
FnbService | setItemAvailability | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setItemAvailability | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setKitchenSla | request | targets | array of object
FnbService | setKitchenSla | request | targets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | setKitchenSla | request | targets[].targetMinutes | integer | yes | (min 1)
FnbService | setKitchenSla | request | targets[].warnAtPercent | integer |  | (default 80)
FnbService | setKitchenSla | request | priorityWeights | object |  | The weight of each signal the board names — age, promise time, table stage, a VIP marker.
FnbService | setKitchenSla | request | priorityWeights.age | integer |  | (min 0)
FnbService | setKitchenSla | request | priorityWeights.targetReadyAt | integer |  | Promise time. (min 0)
FnbService | setKitchenSla | request | priorityWeights.tableStage | integer |  | (min 0)
FnbService | setKitchenSla | request | priorityWeights.vip | integer |  | (min 0)
FnbService | setKitchenSla | response | targets | array of object
FnbService | setKitchenSla | response | targets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | setKitchenSla | response | targets[].targetMinutes | integer | yes | (min 1)
FnbService | setKitchenSla | response | targets[].warnAtPercent | integer |  | (default 80)
FnbService | setKitchenSla | response | priorityWeights | object |  | The weight of each signal the board names — age, promise time, table stage, a VIP marker.
FnbService | setKitchenSla | response | priorityWeights.age | integer |  | (min 0)
FnbService | setKitchenSla | response | priorityWeights.targetReadyAt | integer |  | Promise time. (min 0)
FnbService | setKitchenSla | response | priorityWeights.tableStage | integer |  | (min 0)
FnbService | setKitchenSla | response | priorityWeights.vip | integer |  | (min 0)
FnbService | setKitchenSla | param (path) | outletId | string (uuid) | yes
FnbService | setKitchenSla | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setKitchenSla | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setKitchenStations | request | stations | array of KitchenStation | yes
FnbService | setKitchenStations | request | stations[].id | string (uuid) | yes
FnbService | setKitchenStations | request | stations[].code | string | yes
FnbService | setKitchenStations | request | stations[].name | string | yes
FnbService | setKitchenStations | request | stations[].outletId | string (uuid)
FnbService | setKitchenStations | request | stations[].menuItemIds | array of string (uuid) |  | Items routed to this station.
FnbService | setKitchenStations | request | stations[].displayWorkstationIds | array of string (uuid) |  | The kitchen displays assigned to this station (decided 28 September, audit R277), as tenancy Workstation ids, primary first and fallbacks after it.
FnbService | setKitchenStations | request | stations[].displayEndpoint | string |  | The P15 Kitchen Display device this station's tickets go to (19 Sep: the display is TICVAI software on commodity hardware, per station, with a fallback device where the primary is down — 18 Aug minut… (nullable)
FnbService | setKitchenStations | request | stations[].isActive | boolean
FnbService | setKitchenStations | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setKitchenStations | param (query) | outletId | string (uuid) | yes | The outlet whose stations these are.
FnbService | setKitchenStations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setKitchenTicketStatus | request | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | setKitchenTicketStatus | request | lineIds | array of string (uuid) |  | Advance specific lines.
FnbService | setKitchenTicketStatus | request | stationId | string (uuid)
FnbService | setKitchenTicketStatus | request | recordedAt | string (date-time) | yes
FnbService | setKitchenTicketStatus | response | id | string (uuid) | yes
FnbService | setKitchenTicketStatus | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | setKitchenTicketStatus | response | orderNumber | string
FnbService | setKitchenTicketStatus | response | outletId | string (uuid) | yes
FnbService | setKitchenTicketStatus | response | tableLabel | string |  | (nullable)
FnbService | setKitchenTicketStatus | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | setKitchenTicketStatus | response | coursing | object |  | BL-131. (nullable)
FnbService | setKitchenTicketStatus | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | setKitchenTicketStatus | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | setKitchenTicketStatus | response | priority | integer |  | Higher fires sooner.
FnbService | setKitchenTicketStatus | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | setKitchenTicketStatus | response | prioritiseReason | string |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines | array of object | yes
FnbService | setKitchenTicketStatus | response | lines[].lineId | string (uuid) | yes
FnbService | setKitchenTicketStatus | response | lines[].name | string | yes
FnbService | setKitchenTicketStatus | response | lines[].quantity | integer | yes
FnbService | setKitchenTicketStatus | response | lines[].modifiers | array of string
FnbService | setKitchenTicketStatus | response | lines[].note | string |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setKitchenTicketStatus | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | setKitchenTicketStatus | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | setKitchenTicketStatus | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | setKitchenTicketStatus | response | lines[].course | integer |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | setKitchenTicketStatus | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | setKitchenTicketStatus | response | createdAt | string (date-time) | yes
FnbService | setKitchenTicketStatus | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | setKitchenTicketStatus | response | elapsedSeconds | integer
FnbService | setKitchenTicketStatus | param (path) | ticketId | string (uuid) | yes
FnbService | setKitchenTicketStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setLanguages | request | languages | array of string | yes | (min items 1)
WhiteLabelService | setLanguages | request | defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | setLanguages | response | languages | array of string | yes
WhiteLabelService | setLanguages | response | defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | setLanguages | response | rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | setLanguages | response | translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | setLanguages | response | translationGaps[].language | string
WhiteLabelService | setLanguages | response | translationGaps[].missingCount | integer
WhiteLabelService | setLanguages | response | translationGaps[].areas | array of string
WhiteLabelService | setLanguages | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setLoyaltyRules | request | programmeId | string (uuid) | yes
MarketingService | setLoyaltyRules | request | campaignRules | array of MarketingLoyaltyRule |  | Bonus, multiplier and condition rules, each scoped to a campaign window.
MarketingService | setLoyaltyRules | request | campaignRules[].id | string (uuid)
MarketingService | setLoyaltyRules | request | campaignRules[].campaignId | string (uuid) | yes
MarketingService | setLoyaltyRules | request | campaignRules[].type | string | yes | (max length 30)
MarketingService | setLoyaltyRules | request | campaignRules[].pointsEarningRuleId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].rewardId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].bonusPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].multiplier | number |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].conditionsJson | string |  | (nullable)
MarketingService | setLoyaltyRules | request | campaignRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | request | tiers | array of MarketingProgrammeTier |  | The programme's tiers, in rank order.
MarketingService | setLoyaltyRules | request | tiers[].id | string (uuid) |  | (read-only)
MarketingService | setLoyaltyRules | request | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | setLoyaltyRules | request | tiers[].code | string | yes | (max length 40)
MarketingService | setLoyaltyRules | request | tiers[].name | string | yes | (max length 120)
MarketingService | setLoyaltyRules | request | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | setLoyaltyRules | request | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | setLoyaltyRules | request | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | setLoyaltyRules | request | tiers[].isActive | boolean |  | (default True)
MarketingService | setLoyaltyRules | request | redemptionRules | array of MarketingPointsRedemptionRule
MarketingService | setLoyaltyRules | request | redemptionRules[].id | string (uuid)
MarketingService | setLoyaltyRules | request | redemptionRules[].loyaltyProgramId | string (uuid) | yes
MarketingService | setLoyaltyRules | request | redemptionRules[].pointRedemptionRuleCode | string | yes | (max length 100)
MarketingService | setLoyaltyRules | request | redemptionRules[].name | string | yes | (max length 200)
MarketingService | setLoyaltyRules | request | redemptionRules[].redemptionType | string | yes | (max length 30)
MarketingService | setLoyaltyRules | request | redemptionRules[].required | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].monetaryValue | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].minimumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].maximumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].productId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].validFrom | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].validTo | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | request | redemptionRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | response | programmeId | string (uuid) | yes
MarketingService | setLoyaltyRules | response | campaignRules | array of MarketingLoyaltyRule |  | Bonus, multiplier and condition rules, each scoped to a campaign window.
MarketingService | setLoyaltyRules | response | campaignRules[].id | string (uuid)
MarketingService | setLoyaltyRules | response | campaignRules[].campaignId | string (uuid) | yes
MarketingService | setLoyaltyRules | response | campaignRules[].type | string | yes | (max length 30)
MarketingService | setLoyaltyRules | response | campaignRules[].pointsEarningRuleId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].rewardId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].bonusPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].multiplier | number |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].conditionsJson | string |  | (nullable)
MarketingService | setLoyaltyRules | response | campaignRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | response | tiers | array of MarketingProgrammeTier |  | The programme's tiers, in rank order.
MarketingService | setLoyaltyRules | response | tiers[].id | string (uuid) |  | (read-only)
MarketingService | setLoyaltyRules | response | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | setLoyaltyRules | response | tiers[].code | string | yes | (max length 40)
MarketingService | setLoyaltyRules | response | tiers[].name | string | yes | (max length 120)
MarketingService | setLoyaltyRules | response | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | setLoyaltyRules | response | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | setLoyaltyRules | response | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | setLoyaltyRules | response | tiers[].isActive | boolean |  | (default True)
MarketingService | setLoyaltyRules | response | redemptionRules | array of MarketingPointsRedemptionRule
MarketingService | setLoyaltyRules | response | redemptionRules[].id | string (uuid)
MarketingService | setLoyaltyRules | response | redemptionRules[].loyaltyProgramId | string (uuid) | yes
MarketingService | setLoyaltyRules | response | redemptionRules[].pointRedemptionRuleCode | string | yes | (max length 100)
MarketingService | setLoyaltyRules | response | redemptionRules[].name | string | yes | (max length 200)
MarketingService | setLoyaltyRules | response | redemptionRules[].redemptionType | string | yes | (max length 30)
MarketingService | setLoyaltyRules | response | redemptionRules[].required | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].monetaryValue | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].minimumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].maximumPoints | number |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].productId | string (uuid) |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].validFrom | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].validTo | string (date-time) |  | (nullable)
MarketingService | setLoyaltyRules | response | redemptionRules[].isActive | boolean | yes
MarketingService | setLoyaltyRules | param (path) | programmeId | string (uuid) | yes
MarketingService | setLoyaltyRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setMaintenanceMode | request | isInMaintenance | boolean | yes
WhiteLabelService | setMaintenanceMode | request | message | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | request | expectedBackAt | string (date-time)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | request | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | request | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.phone | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.email | string (email) |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.whatsapp | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.address | object |  | (nullable)
WhiteLabelService | setMaintenanceMode | request | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | setMaintenanceMode | request | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | setMaintenanceMode | request | availabilityMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | response | tenantId | string (uuid) | yes
WhiteLabelService | setMaintenanceMode | response | isPublished | boolean | yes | True once any version has been published.
WhiteLabelService | setMaintenanceMode | response | publishedVersion | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | publishedAt | string (date-time) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | draftVersion | string |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | hasUnpublishedChanges | boolean |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | activeModuleCount | integer |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | licensedModuleCount | integer |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | activePageCount | integer |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | isInMaintenance | boolean | yes
WhiteLabelService | setMaintenanceMode | response | maintenanceMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | setMaintenanceMode | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.phone | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.address | object |  | (nullable)
WhiteLabelService | setMaintenanceMode | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | setMaintenanceMode | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | setMaintenanceMode | response | availabilityMessage | object |  | What the sold-out or closed screen says (WEB-029). (nullable)
WhiteLabelService | setMaintenanceMode | response | venues | array of object |  | Public: the venues a guest can pick (decided 28 September, audit R267; schema named 29 September, readiness close-out, our build plan). (max items 200)
WhiteLabelService | setMaintenanceMode | response | venues[].venueId | string (uuid) | yes | The venue's scope node (tenancy.OrgUnit.id, level venue): what every guest screen that declares venueId from: session reads once the guest picks it.
WhiteLabelService | setMaintenanceMode | response | venues[].name | string | yes | The venue's name (tenancy.OrgUnit.name). (max length 200)
WhiteLabelService | setMaintenanceMode | response | venues[].city | string |  | Shown under the name so two venues with similar names can be told apart. (max length 120; nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].openingHoursToday | object |  | Today's opening hours in the venue's time zone, from tenancy.VenueSettings opening hours. (nullable)
WhiteLabelService | setMaintenanceMode | response | venues[].openingHoursToday.opens | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | setMaintenanceMode | response | venues[].openingHoursToday.closes | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | setMaintenanceMode | response | whatsNew | array of object |  | Public: the guest "what's new" (decided 29 September, rev 3 GAP-B2). (max items 10)
WhiteLabelService | setMaintenanceMode | response | whatsNew[].version | string | yes | The release version.
WhiteLabelService | setMaintenanceMode | response | whatsNew[].publishedAt | string (date-time) | yes | When the release reached the tenant's cell.
WhiteLabelService | setMaintenanceMode | response | whatsNew[].notes | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setMaintenanceMode | response | recentChanges | array of object |  | Staff only.
WhiteLabelService | setMaintenanceMode | response | recentChanges[].area | string
WhiteLabelService | setMaintenanceMode | response | recentChanges[].description | string
WhiteLabelService | setMaintenanceMode | response | recentChanges[].principalId | string (uuid)
WhiteLabelService | setMaintenanceMode | response | recentChanges[].at | string (date-time)
WhiteLabelService | setMaintenanceMode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setMarketingSubscription | request | id | string (uuid) | yes | (read-only)
MarketingService | setMarketingSubscription | request | subjectId | string (uuid) | yes | The guest — from the guest session, or from unsubscribeToken when there is no session. (read-only)
MarketingService | setMarketingSubscription | request | channel | enum (email, sms, push) | yes
MarketingService | setMarketingSubscription | request | listName | string | yes
MarketingService | setMarketingSubscription | request | isSubscribed | boolean | yes
MarketingService | setMarketingSubscription | request | source | string |  | Where the opt-in happened, because a regulator asks.
MarketingService | setMarketingSubscription | request | unsubscribeToken | string |  | Unsubscribe must work without a login.
MarketingService | setMarketingSubscription | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setMarketingSubscription | response | id | string (uuid) | yes | (read-only)
MarketingService | setMarketingSubscription | response | subjectId | string (uuid) | yes | The guest — from the guest session, or from unsubscribeToken when there is no session. (read-only)
MarketingService | setMarketingSubscription | response | channel | enum (email, sms, push) | yes
MarketingService | setMarketingSubscription | response | listName | string | yes
MarketingService | setMarketingSubscription | response | isSubscribed | boolean | yes
MarketingService | setMarketingSubscription | response | source | string |  | Where the opt-in happened, because a regulator asks.
MarketingService | setMarketingSubscription | response | unsubscribeToken | string |  | Unsubscribe must work without a login.
MarketingService | setMarketingSubscription | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setMarketingSubscription | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setMenuSections | request | sections | array of MenuSection | yes
FnbService | setMenuSections | request | sections[].id | string (uuid) |  | (read-only)
FnbService | setMenuSections | request | sections[].code | string | yes
FnbService | setMenuSections | request | sections[].name | string | yes
FnbService | setMenuSections | request | sections[].sortOrder | integer | yes
FnbService | setMenuSections | request | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | setMenuSections | request | sections[].items[].id | string (uuid) | yes
FnbService | setMenuSections | request | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | setMenuSections | request | sections[].items[].name | string | yes
FnbService | setMenuSections | request | sections[].items[].description | string |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setMenuSections | request | sections[].items[].sortOrder | integer
FnbService | setMenuSections | request | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | setMenuSections | request | sections[].items[].stationId | string (uuid) |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | setMenuSections | request | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | setMenuSections | request | sections[].items[].isAvailable | boolean | yes
FnbService | setMenuSections | request | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setMenuSections | request | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | setMenuSections | request | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setMenuSections | response | id | string (uuid) | yes
FnbService | setMenuSections | response | code | string | yes | (max length 64)
FnbService | setMenuSections | response | name | string | yes | (max length 200)
FnbService | setMenuSections | response | outletId | string (uuid) | yes
FnbService | setMenuSections | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | setMenuSections | response | availability.daysOfWeek | array of integer
FnbService | setMenuSections | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | setMenuSections | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | setMenuSections | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | setMenuSections | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | setMenuSections | response | sections | array of MenuSection
FnbService | setMenuSections | response | sections[].id | string (uuid) |  | (read-only)
FnbService | setMenuSections | response | sections[].code | string | yes
FnbService | setMenuSections | response | sections[].name | string | yes
FnbService | setMenuSections | response | sections[].sortOrder | integer | yes
FnbService | setMenuSections | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | setMenuSections | response | sections[].items[].id | string (uuid) | yes
FnbService | setMenuSections | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | setMenuSections | response | sections[].items[].name | string | yes
FnbService | setMenuSections | response | sections[].items[].description | string |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | setMenuSections | response | sections[].items[].sortOrder | integer
FnbService | setMenuSections | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | setMenuSections | response | sections[].items[].stationId | string (uuid) |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | setMenuSections | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | setMenuSections | response | sections[].items[].isAvailable | boolean | yes
FnbService | setMenuSections | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | setMenuSections | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | setMenuSections | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | setMenuSections | response | isActive | boolean | yes
FnbService | setMenuSections | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | setMenuSections | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | setMenuSections | param (path) | menuId | string (uuid) | yes
FnbService | setMenuSections | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setMenuSections | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setModuleEnablement | request | modules | array of object | yes
WhiteLabelService | setModuleEnablement | request | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | setModuleEnablement | request | modules[].isEnabled | boolean | yes
WhiteLabelService | setModuleEnablement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setNavigation | request | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | request | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | setNavigation | request | items | array of object | yes | (max items 12)
WhiteLabelService | setNavigation | request | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | request | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | request | items[].icon | string
WhiteLabelService | setNavigation | request | items[].target | LinkTarget | yes
WhiteLabelService | setNavigation | request | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | setNavigation | request | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | setNavigation | request | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | setNavigation | request | items[].target.contentPageId | string (uuid)
WhiteLabelService | setNavigation | request | items[].target.productId | string (uuid)
WhiteLabelService | setNavigation | request | items[].target.eventId | string (uuid)
WhiteLabelService | setNavigation | request | items[].target.url | string
WhiteLabelService | setNavigation | request | items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | setNavigation | request | items[].sortOrder | integer | yes
WhiteLabelService | setNavigation | request | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | setNavigation | request | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | setNavigation | request | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | response | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | setNavigation | response | items | array of object | yes | (max items 12)
WhiteLabelService | setNavigation | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | setNavigation | response | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | response | items[].icon | string
WhiteLabelService | setNavigation | response | items[].target | LinkTarget | yes
WhiteLabelService | setNavigation | response | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | setNavigation | response | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | setNavigation | response | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | setNavigation | response | items[].target.contentPageId | string (uuid)
WhiteLabelService | setNavigation | response | items[].target.productId | string (uuid)
WhiteLabelService | setNavigation | response | items[].target.eventId | string (uuid)
WhiteLabelService | setNavigation | response | items[].target.url | string
WhiteLabelService | setNavigation | response | items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | setNavigation | response | items[].sortOrder | integer | yes
WhiteLabelService | setNavigation | response | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | setNavigation | response | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | setNavigation | response | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setNavigation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setNavigation | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
AccessService | setParkingFacility | request | id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | setParkingFacility | request | name | string | yes
AccessService | setParkingFacility | request | venueId | string (uuid) | yes
AccessService | setParkingFacility | request | mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | setParkingFacility | request | capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | setParkingFacility | request | takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | setParkingFacility | request | vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | setParkingFacility | request | vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | request | endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | request | credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | setParkingFacility | request | pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | request | accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | setParkingFacility | request | isActive | boolean
AccessService | setParkingFacility | response | id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | setParkingFacility | response | name | string | yes
AccessService | setParkingFacility | response | venueId | string (uuid) | yes
AccessService | setParkingFacility | response | mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | setParkingFacility | response | capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | setParkingFacility | response | takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | setParkingFacility | response | vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | setParkingFacility | response | vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | response | endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | response | credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | setParkingFacility | response | pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | setParkingFacility | response | accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | setParkingFacility | response | isActive | boolean
AccessService | setParkingFacility | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | setPasswordPolicy | request | id | string (uuid) | yes | Assigned by the server. (read-only)
IdentityService | setPasswordPolicy | request | scopePath | string | yes | The partition key (ADR-0005), written by the server from the caller's tenant (x-ticvai-config-scope: tenant). (read-only)
IdentityService | setPasswordPolicy | request | minLength | integer | yes | A tenant may raise the length and never set it below 8 (decided 28 September, audit R126 (7)). (min 8; default 12)
IdentityService | setPasswordPolicy | request | requireBreachCheck | boolean |  | The single most effective rule. (default True)
IdentityService | setPasswordPolicy | request | maxAgeDays | integer |  | Null is the recommended value. (nullable)
IdentityService | setPasswordPolicy | request | recoveryMethods | array of enum (email, sms, securityQuestions, inPersonVerification, supportAssisted) |  | BL-132.
IdentityService | setPasswordPolicy | request | maxConcurrentSessions | integer |  | BL-145. (nullable)
IdentityService | setPasswordPolicy | request | deviceRestriction | object |  | BL-146. (nullable)
IdentityService | setPasswordPolicy | request | deviceRestriction.allowedIpRanges | array of string
IdentityService | setPasswordPolicy | request | deviceRestriction.allowedCountries | array of string
IdentityService | setPasswordPolicy | request | deviceRestriction.requireRegisteredDevice | boolean |  | (default False)
IdentityService | setPasswordPolicy | request | deviceRestriction.onViolation | enum (warn, requireStepUp, block) |  | (default requireStepUp)
IdentityService | setPasswordPolicy | request | lockoutAfterAttempts | integer |  | (default 10)
IdentityService | setPasswordPolicy | request | lockoutMinutes | integer |  | A temporary lockout, not a permanent one. (default 15)
IdentityService | setPasswordPolicy | request | forceChangeOnFirstLogon | boolean |  | (default True)
IdentityService | setPasswordPolicy | request | reusePreventionCount | integer |  | How many previous credentials a staff member may not reuse — the last 5 unless the tenant sets another (decided 28 September, audit R132). (min 0; max 24; default 5)
IdentityService | setPasswordPolicy | request | mfaRequiredForPermissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | Step-up rather than blanket MFA. (default ['ROLE_MANAGE', 'LEDGER_APPROVE', 'PLATFORM_TENANT_VIEW', 'PLATFORM_TENANT_MANAGE', 'PLATFORM_TENANT_TERMINATE', 'PLATFORM_TENANT_ACCESS', 'PLATFORM_PLAN_MANAGE', 'PLATFORM_CELL_VIEW', 'PLATFORM_CELL_MANAGE', 'PLATFORM_BILLING_VIEW', 'PLATFORM_BILLING_MANAGE', 'PLATFORM_RELEASE_VIEW', 'PLATFORM_RELEASE_MANAGE', 'PLATFORM_RELEASE_PROMOTE', 'PLATFORM_MIGRATION_VIEW', 'PLATFORM_MIGRATION_APPLY'])
IdentityService | setPasswordPolicy | response | id | string (uuid) | yes | Assigned by the server. (read-only)
IdentityService | setPasswordPolicy | response | scopePath | string | yes | The partition key (ADR-0005), written by the server from the caller's tenant (x-ticvai-config-scope: tenant). (read-only)
IdentityService | setPasswordPolicy | response | minLength | integer | yes | A tenant may raise the length and never set it below 8 (decided 28 September, audit R126 (7)). (min 8; default 12)
IdentityService | setPasswordPolicy | response | requireBreachCheck | boolean |  | The single most effective rule. (default True)
IdentityService | setPasswordPolicy | response | maxAgeDays | integer |  | Null is the recommended value. (nullable)
IdentityService | setPasswordPolicy | response | recoveryMethods | array of enum (email, sms, securityQuestions, inPersonVerification, supportAssisted) |  | BL-132.
IdentityService | setPasswordPolicy | response | maxConcurrentSessions | integer |  | BL-145. (nullable)
IdentityService | setPasswordPolicy | response | deviceRestriction | object |  | BL-146. (nullable)
IdentityService | setPasswordPolicy | response | deviceRestriction.allowedIpRanges | array of string
IdentityService | setPasswordPolicy | response | deviceRestriction.allowedCountries | array of string
IdentityService | setPasswordPolicy | response | deviceRestriction.requireRegisteredDevice | boolean |  | (default False)
IdentityService | setPasswordPolicy | response | deviceRestriction.onViolation | enum (warn, requireStepUp, block) |  | (default requireStepUp)
IdentityService | setPasswordPolicy | response | lockoutAfterAttempts | integer |  | (default 10)
IdentityService | setPasswordPolicy | response | lockoutMinutes | integer |  | A temporary lockout, not a permanent one. (default 15)
IdentityService | setPasswordPolicy | response | forceChangeOnFirstLogon | boolean |  | (default True)
IdentityService | setPasswordPolicy | response | reusePreventionCount | integer |  | How many previous credentials a staff member may not reuse — the last 5 unless the tenant sets another (decided 28 September, audit R132). (min 0; max 24; default 5)
IdentityService | setPasswordPolicy | response | mfaRequiredForPermissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | Step-up rather than blanket MFA. (default ['ROLE_MANAGE', 'LEDGER_APPROVE', 'PLATFORM_TENANT_VIEW', 'PLATFORM_TENANT_MANAGE', 'PLATFORM_TENANT_TERMINATE', 'PLATFORM_TENANT_ACCESS', 'PLATFORM_PLAN_MANAGE', 'PLATFORM_CELL_VIEW', 'PLATFORM_CELL_MANAGE', 'PLATFORM_BILLING_VIEW', 'PLATFORM_BILLING_MANAGE', 'PLATFORM_RELEASE_VIEW', 'PLATFORM_RELEASE_MANAGE', 'PLATFORM_RELEASE_PROMOTE', 'PLATFORM_MIGRATION_VIEW', 'PLATFORM_MIGRATION_APPLY'])
IdentityService | setPasswordPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setPaymentProvider | request | id | string (uuid) | yes
OrderService | setPaymentProvider | request | name | string | yes
OrderService | setPaymentProvider | request | kind | enum (networkInternational, stripe, adyen, checkout, cash, wallet, other) | yes
OrderService | setPaymentProvider | request | supportedMethods | array of enum (card, applePay, googlePay, samsungPay, wallet, bankTransfer, cash, bnpl)
OrderService | setPaymentProvider | request | supportedCurrencies | array of string
OrderService | setPaymentProvider | request | supportsTokenisation | boolean |  | The keystone.
OrderService | setPaymentProvider | request | supportsPartialCapture | boolean |  | (default True)
OrderService | setPaymentProvider | request | acceptedOnChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | BL-115.
OrderService | setPaymentProvider | request | presentmentCurrencies | array of string |  | BL-070.
OrderService | setPaymentProvider | request | supports3ds | boolean |  | (default True)
OrderService | setPaymentProvider | request | terminal | object |  | BL-119. (nullable)
OrderService | setPaymentProvider | request | terminal.emvCertificationRef | string |  | (nullable)
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit | object |  | What a terminal may approve with no connection.
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setPaymentProvider | request | terminal.offlineFloorLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setPaymentProvider | request | terminal.supportsOfflineApproval | boolean |  | (default False)
OrderService | setPaymentProvider | request | terminal.receiptSignatureRequired | boolean |  | (default False)
OrderService | setPaymentProvider | request | terminal.supportsTipOnTerminal | boolean |  | (default False)
OrderService | setPaymentProvider | request | credentialRef | string |  | A vault reference.
OrderService | setPaymentProvider | request | scopeLevel | enum (tenant, region, venue)
OrderService | setPaymentProvider | request | scopePath | string
OrderService | setPaymentProvider | request | isActive | boolean | yes
OrderService | setPaymentProvider | request | routing | array of PaymentRouting |  | The ordered rules that send payments to this provider.
OrderService | setPaymentProvider | request | routing[].id | string (uuid) | yes
OrderService | setPaymentProvider | request | routing[].priority | integer | yes
OrderService | setPaymentProvider | request | routing[].providerId | string (uuid) | yes
OrderService | setPaymentProvider | request | routing[].conditions | object |  | Match on what is known before the charge — channel, currency, method, issuer country, amount band.
OrderService | setPaymentProvider | request | routing[].conditions.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
OrderService | setPaymentProvider | request | routing[].conditions.currency | string |  | Resolved from the region, not stored (ADR-0018, 24 August). (nullable)
OrderService | setPaymentProvider | request | routing[].conditions.method | string |  | (nullable)
OrderService | setPaymentProvider | request | routing[].conditions.issuerCountry | string |  | (nullable)
OrderService | setPaymentProvider | request | routing[].conditions.minAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setPaymentProvider | request | routing[].conditions.maxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | setPaymentProvider | request | routing[].fallbackProviderId | string (uuid) |  | Where this provider declines or is unreachable. (nullable)
OrderService | setPaymentProvider | request | routing[].scopePath | string |  | The partition key (ADR-0005).
OrderService | setPaymentProvider | response | id | string (uuid) | yes
OrderService | setPaymentProvider | response | name | string | yes
OrderService | setPaymentProvider | response | kind | enum (networkInternational, stripe, adyen, checkout, cash, wallet, other) | yes
OrderService | setPaymentProvider | response | supportedMethods | array of enum (card, applePay, googlePay, samsungPay, wallet, bankTransfer, cash, bnpl)
OrderService | setPaymentProvider | response | supportedCurrencies | array of string
OrderService | setPaymentProvider | response | supportsTokenisation | boolean |  | The keystone.
OrderService | setPaymentProvider | response | supportsPartialCapture | boolean |  | (default True)
OrderService | setPaymentProvider | response | acceptedOnChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | BL-115.
OrderService | setPaymentProvider | response | presentmentCurrencies | array of string |  | BL-070.
OrderService | setPaymentProvider | response | supports3ds | boolean |  | (default True)
OrderService | setPaymentProvider | response | terminal | object |  | BL-119. (nullable)
OrderService | setPaymentProvider | response | terminal.emvCertificationRef | string |  | (nullable)
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit | object |  | What a terminal may approve with no connection.
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setPaymentProvider | response | terminal.offlineFloorLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setPaymentProvider | response | terminal.supportsOfflineApproval | boolean |  | (default False)
OrderService | setPaymentProvider | response | terminal.receiptSignatureRequired | boolean |  | (default False)
OrderService | setPaymentProvider | response | terminal.supportsTipOnTerminal | boolean |  | (default False)
OrderService | setPaymentProvider | response | credentialRef | string |  | A vault reference.
OrderService | setPaymentProvider | response | scopeLevel | enum (tenant, region, venue)
OrderService | setPaymentProvider | response | scopePath | string
OrderService | setPaymentProvider | response | isActive | boolean | yes
OrderService | setPaymentProvider | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setPaymentProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setPlacedResource | request | id | string (uuid) | yes | (read-only)
VenueOpsService | setPlacedResource | request | mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | setPlacedResource | request | resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | setPlacedResource | request | label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | setPlacedResource | request | kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | setPlacedResource | request | zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | setPlacedResource | request | capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | setPlacedResource | request | priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | setPlacedResource | request | variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | setPlacedResource | request | position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | setPlacedResource | request | position.x | number | yes
VenueOpsService | setPlacedResource | request | position.y | number | yes
VenueOpsService | setPlacedResource | request | boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | setPlacedResource | request | boundary[].x | number
VenueOpsService | setPlacedResource | request | boundary[].y | number
VenueOpsService | setPlacedResource | request | isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | setPlacedResource | request | placedResourceId | string (uuid) |  | The placed resource to amend. (nullable)
VenueOpsService | setPlacedResource | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setPlacedResource | response | mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | setPlacedResource | response | resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | setPlacedResource | response | label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | setPlacedResource | response | kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | setPlacedResource | response | zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | setPlacedResource | response | capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | setPlacedResource | response | priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | setPlacedResource | response | variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | setPlacedResource | response | position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | setPlacedResource | response | position.x | number | yes
VenueOpsService | setPlacedResource | response | position.y | number | yes
VenueOpsService | setPlacedResource | response | boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | setPlacedResource | response | boundary[].x | number
VenueOpsService | setPlacedResource | response | boundary[].y | number
VenueOpsService | setPlacedResource | response | isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | setPlacedResource | param (path) | mapId | string (uuid) | yes
VenueOpsService | setPlacedResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setPolicy | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | setPolicy | request | requiresReconsent | boolean | yes | True prompts existing guests to consent again on next launch.
WhiteLabelService | setPolicy | request | effectiveFrom | string (date)
WhiteLabelService | setPolicy | response | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) | yes
WhiteLabelService | setPolicy | response | title | string |  | The heading a guest sees, and the field a refund question retrieves against.
WhiteLabelService | setPolicy | response | version | string | yes | Immutable.
WhiteLabelService | setPolicy | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | setPolicy | response | requiresReconsent | boolean
WhiteLabelService | setPolicy | response | effectiveFrom | string (date) | yes
WhiteLabelService | setPolicy | response | publishedByPrincipalId | string (uuid)
WhiteLabelService | setPolicy | response | publishedAt | string (date-time) | yes
WhiteLabelService | setPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setPolicy | param (path) | policyKind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) | yes
WhiteLabelService | setPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPriceCategoryRateType | request | id | string (uuid) | yes | (read-only)
CatalogueService | setPriceCategoryRateType | request | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setPriceCategoryRateType | request | entryKind | enum (priceCategory, rateType) | yes
CatalogueService | setPriceCategoryRateType | request | code | string | yes | Unique per entryKind within the tenant. (max length 40)
CatalogueService | setPriceCategoryRateType | request | name | string | yes | (max length 200)
CatalogueService | setPriceCategoryRateType | request | description | string |  | (nullable)
CatalogueService | setPriceCategoryRateType | request | categoryFamily | string |  | (max length 60; nullable)
CatalogueService | setPriceCategoryRateType | request | displayName | string |  | (max length 200; nullable)
CatalogueService | setPriceCategoryRateType | request | localizedDisplayNames | object |  | (nullable)
CatalogueService | setPriceCategoryRateType | request | iconLabel | string |  | (max length 40; nullable)
CatalogueService | setPriceCategoryRateType | request | parentId | string (uuid) |  | A parent catalogue.price_category of the same entryKind. (nullable)
CatalogueService | setPriceCategoryRateType | request | isStandard | boolean |  | Shipped with the tenant; may be deactivated, not deleted. (default False)
CatalogueService | setPriceCategoryRateType | request | sortOrder | integer |  | (default 100)
CatalogueService | setPriceCategoryRateType | request | isActive | boolean | yes | (default True)
CatalogueService | setPriceCategoryRateType | request | createdAt | string (date-time) |  | (read-only)
CatalogueService | setPriceCategoryRateType | request | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setPriceCategoryRateType | response | id | string (uuid) | yes | (read-only)
CatalogueService | setPriceCategoryRateType | response | scopePath | string | yes | The partition key (ADR-0005). (read-only)
CatalogueService | setPriceCategoryRateType | response | entryKind | enum (priceCategory, rateType) | yes
CatalogueService | setPriceCategoryRateType | response | code | string | yes | Unique per entryKind within the tenant. (max length 40)
CatalogueService | setPriceCategoryRateType | response | name | string | yes | (max length 200)
CatalogueService | setPriceCategoryRateType | response | description | string |  | (nullable)
CatalogueService | setPriceCategoryRateType | response | categoryFamily | string |  | (max length 60; nullable)
CatalogueService | setPriceCategoryRateType | response | displayName | string |  | (max length 200; nullable)
CatalogueService | setPriceCategoryRateType | response | localizedDisplayNames | object |  | (nullable)
CatalogueService | setPriceCategoryRateType | response | iconLabel | string |  | (max length 40; nullable)
CatalogueService | setPriceCategoryRateType | response | parentId | string (uuid) |  | A parent catalogue.price_category of the same entryKind. (nullable)
CatalogueService | setPriceCategoryRateType | response | isStandard | boolean |  | Shipped with the tenant; may be deactivated, not deleted. (default False)
CatalogueService | setPriceCategoryRateType | response | sortOrder | integer |  | (default 100)
CatalogueService | setPriceCategoryRateType | response | isActive | boolean | yes | (default True)
CatalogueService | setPriceCategoryRateType | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | setPriceCategoryRateType | response | updatedAt | string (date-time) |  | (read-only)
CatalogueService | setPriceCategoryRateType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPriceHierarchyInheritance | request | hierarchyId | string |  | Price hierarchy ID; empty on create
CatalogueService | setPriceHierarchyInheritance | request | name | string |  | Hierarchy name
CatalogueService | setPriceHierarchyInheritance | request | levels | array of object |  | Hierarchy Builder (p.17): the ordered levels; saved as a whole so two sources can never be left at equal priority
CatalogueService | setPriceHierarchyInheritance | request | levels[].hierarchyLevel | enum (globalMaster, country, market, venue, product, approvedOverride) |  | Hierarchy Level (Example Hierarchy, p.17)
CatalogueService | setPriceHierarchyInheritance | request | levels[].priority | integer |  | Priority; the lower number is the more general level, the most specific existing price wins
CatalogueService | setPriceHierarchyInheritance | request | levels[].inheritance | boolean |  | Inheritance: the level takes its parent's price when it has none of its own
CatalogueService | setPriceHierarchyInheritance | request | levels[].overrideAllowed | boolean |  | Override Permission / Override Allowed
CatalogueService | setPriceHierarchyInheritance | request | levels[].overrideRequiresReason | boolean |  | Override Requires Reason
CatalogueService | setPriceHierarchyInheritance | request | levels[].maximumOverrideRangePercent | number |  | Maximum Override Range: largest allowed deviation from the parent price, in percent; empty for no limit (nullable)
CatalogueService | setPriceHierarchyInheritance | request | levels[].overrideExpiryDays | integer |  | Override Expiry: days an override stays in force; empty for no expiry (decided 29 September, readiness close-out) (nullable)
CatalogueService | setPriceHierarchyInheritance | request | levels[].returnToParentPrice | boolean |  | Return to Parent Price when an override expires
CatalogueService | setPriceHierarchyInheritance | request | levels[].fallbackBehavior | enum (useParent, useDefault, blockSale) |  | Fallback (p.18): what happens when a child rate does not exist
CatalogueService | setPriceHierarchyInheritance | response | hierarchyId | string |  | Price hierarchy ID; empty on create
CatalogueService | setPriceHierarchyInheritance | response | name | string |  | Hierarchy name
CatalogueService | setPriceHierarchyInheritance | response | levels | array of object |  | Hierarchy Builder (p.17): the ordered levels; saved as a whole so two sources can never be left at equal priority
CatalogueService | setPriceHierarchyInheritance | response | levels[].hierarchyLevel | enum (globalMaster, country, market, venue, product, approvedOverride) |  | Hierarchy Level (Example Hierarchy, p.17)
CatalogueService | setPriceHierarchyInheritance | response | levels[].priority | integer |  | Priority; the lower number is the more general level, the most specific existing price wins
CatalogueService | setPriceHierarchyInheritance | response | levels[].inheritance | boolean |  | Inheritance: the level takes its parent's price when it has none of its own
CatalogueService | setPriceHierarchyInheritance | response | levels[].overrideAllowed | boolean |  | Override Permission / Override Allowed
CatalogueService | setPriceHierarchyInheritance | response | levels[].overrideRequiresReason | boolean |  | Override Requires Reason
CatalogueService | setPriceHierarchyInheritance | response | levels[].maximumOverrideRangePercent | number |  | Maximum Override Range: largest allowed deviation from the parent price, in percent; empty for no limit (nullable)
CatalogueService | setPriceHierarchyInheritance | response | levels[].overrideExpiryDays | integer |  | Override Expiry: days an override stays in force; empty for no expiry (decided 29 September, readiness close-out) (nullable)
CatalogueService | setPriceHierarchyInheritance | response | levels[].returnToParentPrice | boolean |  | Return to Parent Price when an override expires
CatalogueService | setPriceHierarchyInheritance | response | levels[].fallbackBehavior | enum (useParent, useDefault, blockSale) |  | Fallback (p.18): what happens when a child rate does not exist
CatalogueService | setPriceHierarchyInheritance | response | validationIssues | array of object |  | Conflict Detection (p.18); read-only
CatalogueService | setPriceHierarchyInheritance | response | validationIssues[].code | enum (equalPriority, missingFallback, circularInheritance)
CatalogueService | setPriceHierarchyInheritance | response | validationIssues[].message | string
CatalogueService | setPriceHierarchyInheritance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPriceListMaster | request | priceListName | string |  | Price List Name
CatalogueService | setPriceListMaster | request | priceListCode | string |  | Price List Code; unique within the tenant
CatalogueService | setPriceListMaster | request | description | string |  | Description
CatalogueService | setPriceListMaster | request | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | Price List Type (Commercial Types, pp.8-9, and the directory's Price List Types)
CatalogueService | setPriceListMaster | request | legalEntity | string |  | Legal Entity
CatalogueService | setPriceListMaster | request | brand | string |  | Brand
CatalogueService | setPriceListMaster | request | businessUnit | string |  | Business Unit
CatalogueService | setPriceListMaster | request | country | string |  | Country
CatalogueService | setPriceListMaster | request | market | string |  | Market
CatalogueService | setPriceListMaster | request | venue | string |  | Venue
CatalogueService | setPriceListMaster | request | defaultCurrency | string |  | Default Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | setPriceListMaster | request | owner | string |  | Owner
CatalogueService | setPriceListMaster | request | tags | array of string |  | Tags
CatalogueService | setPriceListMaster | request | status | string |  | Status: draft, configured, inactive or archived are set here; validated is set by structure validation (ADM-057) and active / expired by Board 4 publication
CatalogueService | setPriceListMaster | request | defaultRateCategory | string |  | Default Rate Category: code of a price category from the library (ADM-050)
CatalogueService | setPriceListMaster | request | defaultRoundingProfile | string |  | Default Rounding Profile: code of a currency rounding rule (ADM-075)
CatalogueService | setPriceListMaster | request | defaultPriceHierarchy | string |  | Default Price Hierarchy: id of the price hierarchy (ADM-055) this list resolves against
CatalogueService | setPriceListMaster | request | allowOverrides | boolean |  | Allow Overrides
CatalogueService | setPriceListMaster | request | allowInheritance | boolean |  | Allow Inheritance
CatalogueService | setPriceListMaster | request | allowMultipleCurrencies | boolean |  | Allow Multiple Currencies
CatalogueService | setPriceListMaster | request | allowProductSpecificRates | boolean |  | Allow Product-Specific Rates
CatalogueService | setPriceListMaster | request | priceListId | string |  | Price List ID; empty on create, the list to update otherwise
CatalogueService | setPriceListMaster | request | scope | enum (global, country, market, brand, venue, event, businessUnit) |  | Scope: where the price list can apply (p.8)
CatalogueService | setPriceListMaster | request | clonedFromPriceListId | string |  | The price list this one was duplicated from (Duplicate, p.9: UAE Standard 2026 into UAE Standard 2027); empty when built from scratch (nullable)
CatalogueService | setPriceListMaster | response | priceListName | string |  | Price List Name
CatalogueService | setPriceListMaster | response | priceListCode | string |  | Price List Code; unique within the tenant
CatalogueService | setPriceListMaster | response | description | string |  | Description
CatalogueService | setPriceListMaster | response | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | Price List Type (Commercial Types, pp.8-9, and the directory's Price List Types)
CatalogueService | setPriceListMaster | response | legalEntity | string |  | Legal Entity
CatalogueService | setPriceListMaster | response | brand | string |  | Brand
CatalogueService | setPriceListMaster | response | businessUnit | string |  | Business Unit
CatalogueService | setPriceListMaster | response | country | string |  | Country
CatalogueService | setPriceListMaster | response | market | string |  | Market
CatalogueService | setPriceListMaster | response | venue | string |  | Venue
CatalogueService | setPriceListMaster | response | defaultCurrency | string |  | Default Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | setPriceListMaster | response | owner | string |  | Owner
CatalogueService | setPriceListMaster | response | tags | array of string |  | Tags
CatalogueService | setPriceListMaster | response | status | string |  | Status: draft, configured, inactive or archived are set here; validated is set by structure validation (ADM-057) and active / expired by Board 4 publication
CatalogueService | setPriceListMaster | response | defaultRateCategory | string |  | Default Rate Category: code of a price category from the library (ADM-050)
CatalogueService | setPriceListMaster | response | defaultRoundingProfile | string |  | Default Rounding Profile: code of a currency rounding rule (ADM-075)
CatalogueService | setPriceListMaster | response | defaultPriceHierarchy | string |  | Default Price Hierarchy: id of the price hierarchy (ADM-055) this list resolves against
CatalogueService | setPriceListMaster | response | allowOverrides | boolean |  | Allow Overrides
CatalogueService | setPriceListMaster | response | allowInheritance | boolean |  | Allow Inheritance
CatalogueService | setPriceListMaster | response | allowMultipleCurrencies | boolean |  | Allow Multiple Currencies
CatalogueService | setPriceListMaster | response | allowProductSpecificRates | boolean |  | Allow Product-Specific Rates
CatalogueService | setPriceListMaster | response | priceListId | string |  | Price List ID; empty on create, the list to update otherwise
CatalogueService | setPriceListMaster | response | scope | enum (global, country, market, brand, venue, event, businessUnit) |  | Scope: where the price list can apply (p.8)
CatalogueService | setPriceListMaster | response | clonedFromPriceListId | string |  | The price list this one was duplicated from (Duplicate, p.9: UAE Standard 2026 into UAE Standard 2027); empty when built from scratch (nullable)
CatalogueService | setPriceListMaster | response | consumingModules | array of enum (ticketing, b2c, pos, kiosk, b2b, groupSales, membership, fnb, …) |  | Dependencies: the modules that consume this list (p.9); read-only
CatalogueService | setPriceListMaster | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPrices | request | prices | array of SetPriceRequest | yes | (max items 5000)
CatalogueService | setPrices | request | prices[].variantId | string (uuid) | yes
CatalogueService | setPrices | request | prices[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | setPrices | request | prices[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPrices | request | prices[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPrices | request | prices[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPrices | request | prices[].taxCodeId | string (uuid)
CatalogueService | setPrices | response | applied | integer
CatalogueService | setPrices | param (path) | priceListId | string (uuid) | yes
CatalogueService | setPrices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPrices | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | setProductCategories | request | categories | array of ProductCategory | yes
CatalogueService | setProductCategories | request | categories[].id | string (uuid) | yes
CatalogueService | setProductCategories | request | categories[].name | string | yes
CatalogueService | setProductCategories | request | categories[].code | string |  | Taken from their category tables, 20 September. (max length 64; nullable)
CatalogueService | setProductCategories | request | categories[].nameLocalised | object
CatalogueService | setProductCategories | request | categories[].kind | enum (category, brand, collection, season, department) | yes
CatalogueService | setProductCategories | request | categories[].parentId | string (uuid) |  | One tree, not four. (nullable)
CatalogueService | setProductCategories | request | categories[].scopePath | string |  | Set by the server from the venue the caller acts at; not sent. (read-only)
CatalogueService | setProductCategories | request | categories[].displayOrder | integer |  | (default 100)
CatalogueService | setProductCategories | request | categories[].imageAssetId | string (uuid) |  | (nullable)
CatalogueService | setProductCategories | request | categories[].description | object |  | The short line a guest reads under a category option, e.g. (nullable)
CatalogueService | setProductCategories | request | categories[].bookingFlowId | string (uuid) |  | The booking flow for every product filed here that names none of its own (decided 29 September, W12, BO-115). (nullable)
CatalogueService | setProductCategories | request | categories[].isActive | boolean |  | Deactivated rather than deleted. (default True)
CatalogueService | setProductCategories | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductEligibilityRule | request | id | string (uuid) |  | (read-only)
CatalogueService | setProductEligibilityRule | request | productId | string |  | (read-only)
CatalogueService | setProductEligibilityRule | request | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | request | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | request | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | request | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | request | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | setProductEligibilityRule | request | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | setProductEligibilityRule | request | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | setProductEligibilityRule | request | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | setProductEligibilityRule | request | waiverRequired | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | request | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | setProductEligibilityRule | request | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | request | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | setProductEligibilityRule | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductEligibilityRule | response | id | string (uuid) |  | (read-only)
CatalogueService | setProductEligibilityRule | response | productId | string |  | (read-only)
CatalogueService | setProductEligibilityRule | response | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | response | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | setProductEligibilityRule | response | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | response | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | setProductEligibilityRule | response | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | setProductEligibilityRule | response | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | setProductEligibilityRule | response | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | setProductEligibilityRule | response | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | setProductEligibilityRule | response | waiverRequired | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | response | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | setProductEligibilityRule | response | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | setProductEligibilityRule | response | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | setProductEligibilityRule | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | setProductEligibilityRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setProductEligibilityRule | param (path) | productId | string | yes
CatalogueService | setPromotionRule | request | ruleName | string |  | Rule name
CatalogueService | setPromotionRule | request | ruleId | string |  | Rule ID
CatalogueService | setPromotionRule | request | promotion | string |  | Promotion
CatalogueService | setPromotionRule | request | description | string |  | Description
CatalogueService | setPromotionRule | request | owner | string |  | Owner
CatalogueService | setPromotionRule | request | businessEntity | string |  | Business entity
CatalogueService | setPromotionRule | request | venue | string |  | Venue
CatalogueService | setPromotionRule | request | ruleStatus | string |  | Rule status
CatalogueService | setPromotionRule | request | priority | string |  | Priority
CatalogueService | setPromotionRule | request | percentageDiscount | number |  | Percentage discount
CatalogueService | setPromotionRule | request | fixedDiscount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPromotionRule | request | fixedDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPromotionRule | request | fixedDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPromotionRule | request | fixedDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPromotionRule | request | fixedSellingPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPromotionRule | request | fixedSellingPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPromotionRule | request | fixedSellingPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPromotionRule | request | fixedSellingPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPromotionRule | request | freeProduct | string |  | Free product
CatalogueService | setPromotionRule | request | freeTicket | string |  | Free ticket
CatalogueService | setPromotionRule | request | addedValue | string |  | Added value
CatalogueService | setPromotionRule | request | voucher | string |  | Voucher
CatalogueService | setPromotionRule | request | rewardEntitlement | string |  | Reward entitlement
CatalogueService | setPromotionRule | request | nestedConditionGroups | string |  | Nested condition groups
CatalogueService | setPromotionRule | request | multipleOutcomes | string |  | Multiple outcomes
CatalogueService | setPromotionRule | request | ruleOrdering | string |  | Rule ordering
CatalogueService | setPromotionRule | response | ruleName | string |  | Rule name
CatalogueService | setPromotionRule | response | ruleId | string |  | Rule ID
CatalogueService | setPromotionRule | response | promotion | string |  | Promotion
CatalogueService | setPromotionRule | response | description | string |  | Description
CatalogueService | setPromotionRule | response | owner | string |  | Owner
CatalogueService | setPromotionRule | response | businessEntity | string |  | Business entity
CatalogueService | setPromotionRule | response | venue | string |  | Venue
CatalogueService | setPromotionRule | response | ruleStatus | string |  | Rule status
CatalogueService | setPromotionRule | response | priority | string |  | Priority
CatalogueService | setPromotionRule | response | percentageDiscount | number |  | Percentage discount
CatalogueService | setPromotionRule | response | fixedDiscount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPromotionRule | response | fixedDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPromotionRule | response | fixedDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPromotionRule | response | fixedDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPromotionRule | response | fixedSellingPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setPromotionRule | response | fixedSellingPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setPromotionRule | response | fixedSellingPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setPromotionRule | response | fixedSellingPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setPromotionRule | response | freeProduct | string |  | Free product
CatalogueService | setPromotionRule | response | freeTicket | string |  | Free ticket
CatalogueService | setPromotionRule | response | addedValue | string |  | Added value
CatalogueService | setPromotionRule | response | voucher | string |  | Voucher
CatalogueService | setPromotionRule | response | rewardEntitlement | string |  | Reward entitlement
CatalogueService | setPromotionRule | response | nestedConditionGroups | string |  | Nested condition groups
CatalogueService | setPromotionRule | response | multipleOutcomes | string |  | Multiple outcomes
CatalogueService | setPromotionRule | response | ruleOrdering | string |  | Rule ordering
CatalogueService | setPromotionRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setPromotionVariants | request | variants | array of PromotionVariant | yes | (min items 2; max items 4)
CatalogueService | setPromotionVariants | request | variants[].id | string (uuid) |  | (read-only)
CatalogueService | setPromotionVariants | request | variants[].promotionId | string (uuid) |  | Taken from the path. (read-only)
CatalogueService | setPromotionVariants | request | variants[].label | string | yes
CatalogueService | setPromotionVariants | request | variants[].trafficPercent | integer | yes | Share of traffic. (min 0; max 100)
CatalogueService | setPromotionVariants | request | variants[].discountPercent | number
CatalogueService | setPromotionVariants | response | promotionId | string (uuid) | yes
CatalogueService | setPromotionVariants | response | variants | array of PromotionVariant | yes
CatalogueService | setPromotionVariants | response | variants[].id | string (uuid) |  | (read-only)
CatalogueService | setPromotionVariants | response | variants[].promotionId | string (uuid) |  | Taken from the path. (read-only)
CatalogueService | setPromotionVariants | response | variants[].label | string | yes
CatalogueService | setPromotionVariants | response | variants[].trafficPercent | integer | yes | Share of traffic. (min 0; max 100)
CatalogueService | setPromotionVariants | response | variants[].discountPercent | number
CatalogueService | setPromotionVariants | param (path) | promotionId | string (uuid) | yes
CatalogueService | setPromotionVariants | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setRateStructure | request | rateId | string |  | Rate ID
CatalogueService | setRateStructure | request | rateName | string |  | Rate Name
CatalogueService | setRateStructure | request | rateCode | string |  | Rate Code
CatalogueService | setRateStructure | request | priceCategory | string |  | Price Category: code of a category from the library (ADM-050)
CatalogueService | setRateStructure | request | rateType | string |  | Rate Type: code of a rate type from the library (ADM-050), e.g.
CatalogueService | setRateStructure | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setRateStructure | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRateStructure | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRateStructure | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRateStructure | request | currency | string |  | Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | setRateStructure | request | unitBasis | enum (perTicket, perPerson, perUnit, perHour, perDay, perPerformance, perResource, perPackage, …) |  | Unit Basis (p.12); perPerformance is the pack's "Per Session" (a session is a Performance)
CatalogueService | setRateStructure | request | precision | integer |  | Precision: decimal places, 0 to 3 (MoM 1 Sep §4.5 requires up to three) (min 0; max 3)
CatalogueService | setRateStructure | request | roundingProfile | string |  | Rounding Profile: code of a currency rounding rule (ADM-075)
CatalogueService | setRateStructure | request | status | string |  | Status: draft, active or disabled
CatalogueService | setRateStructure | request | priceListId | string |  | The price list the rate belongs to
CatalogueService | setRateStructure | request | derivedFrom | object |  | Derived Rates (p.12): this rate is another rate adjusted (Child = Adult - 25%, VIP = Standard + AED 200); a commercial relationship, not dynamic pricing. (nullable)
CatalogueService | setRateStructure | request | derivedFrom.baseRateId | string
CatalogueService | setRateStructure | request | derivedFrom.adjustmentType | enum (percentage, fixedAmount)
CatalogueService | setRateStructure | request | derivedFrom.adjustmentValue | number |  | Percent or amount in the rate currency; negative reduces
CatalogueService | setRateStructure | response | rateId | string |  | Rate ID
CatalogueService | setRateStructure | response | rateName | string |  | Rate Name
CatalogueService | setRateStructure | response | rateCode | string |  | Rate Code
CatalogueService | setRateStructure | response | priceCategory | string |  | Price Category: code of a category from the library (ADM-050)
CatalogueService | setRateStructure | response | rateType | string |  | Rate Type: code of a rate type from the library (ADM-050), e.g.
CatalogueService | setRateStructure | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setRateStructure | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRateStructure | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRateStructure | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRateStructure | response | currency | string |  | Currency: ISO 4217 code (pattern ^[A-Z]{3}$)
CatalogueService | setRateStructure | response | unitBasis | enum (perTicket, perPerson, perUnit, perHour, perDay, perPerformance, perResource, perPackage, …) |  | Unit Basis (p.12); perPerformance is the pack's "Per Session" (a session is a Performance)
CatalogueService | setRateStructure | response | precision | integer |  | Precision: decimal places, 0 to 3 (MoM 1 Sep §4.5 requires up to three) (min 0; max 3)
CatalogueService | setRateStructure | response | roundingProfile | string |  | Rounding Profile: code of a currency rounding rule (ADM-075)
CatalogueService | setRateStructure | response | status | string |  | Status: draft, active or disabled
CatalogueService | setRateStructure | response | priceListId | string |  | The price list the rate belongs to
CatalogueService | setRateStructure | response | derivedFrom | object |  | Derived Rates (p.12): this rate is another rate adjusted (Child = Adult - 25%, VIP = Standard + AED 200); a commercial relationship, not dynamic pricing. (nullable)
CatalogueService | setRateStructure | response | derivedFrom.baseRateId | string
CatalogueService | setRateStructure | response | derivedFrom.adjustmentType | enum (percentage, fixedAmount)
CatalogueService | setRateStructure | response | derivedFrom.adjustmentValue | number |  | Percent or amount in the rate currency; negative reduces
CatalogueService | setRateStructure | response | validationIssues | array of object |  | Validation (pp.12-13): problems found on this rate; read-only
CatalogueService | setRateStructure | response | validationIssues[].code | enum (duplicateRate, missingAmount, unsupportedCurrency, invalidDerivedRate, circularRateRelationship)
CatalogueService | setRateStructure | response | validationIssues[].message | string
CatalogueService | setRateStructure | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setRecipe | request | menuItemId | string (uuid) | yes
FnbService | setRecipe | request | yield | number |  | Portions produced by one execution. (min 0)
FnbService | setRecipe | request | ingredients | array of object | yes | (min items 1)
FnbService | setRecipe | request | ingredients[].inventoryItemId | string (uuid) | yes
FnbService | setRecipe | request | ingredients[].quantity | number | yes | (min 0)
FnbService | setRecipe | request | ingredients[].unit | string | yes
FnbService | setRecipe | request | ingredients[].isOptional | boolean |  | (default False)
FnbService | setRecipe | request | costPerPortion | object |  | Computed, never entered (decided 28 September, audit R125 (9)): the sum of each ingredient quantity at its current inventory cost, divided by yield. (read-only)
FnbService | setRecipe | request | costPerPortion.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setRecipe | request | costPerPortion.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setRecipe | request | costPerPortion.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setRecipe | response | menuItemId | string (uuid) | yes
FnbService | setRecipe | response | yield | number |  | Portions produced by one execution. (min 0)
FnbService | setRecipe | response | ingredients | array of object | yes | (min items 1)
FnbService | setRecipe | response | ingredients[].inventoryItemId | string (uuid) | yes
FnbService | setRecipe | response | ingredients[].quantity | number | yes | (min 0)
FnbService | setRecipe | response | ingredients[].unit | string | yes
FnbService | setRecipe | response | ingredients[].isOptional | boolean |  | (default False)
FnbService | setRecipe | response | costPerPortion | object |  | Computed, never entered (decided 28 September, audit R125 (9)): the sum of each ingredient quantity at its current inventory cost, divided by yield. (read-only)
FnbService | setRecipe | response | costPerPortion.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setRecipe | response | costPerPortion.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setRecipe | response | costPerPortion.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setRecipe | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setRecipe | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setRefundPolicy | request | id | string (uuid) |  | Added 20 August. (read-only)
OrderService | setRefundPolicy | request | venueId | string (uuid) | yes | The venue in the path. (read-only)
OrderService | setRefundPolicy | request | selfAuthoriseLimit | object | yes | Up to this, a holder of ORDER_REFUND refunds alone.
OrderService | setRefundPolicy | request | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | request | requiresSecondUserAbove | object |  | Above this, a second user — cashier OR supervisor — names themselves as audit control.
OrderService | setRefundPolicy | request | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | request | requiresApprovalAbove | object | yes | Above this, an ORDER_REFUND_APPROVE holder must approve.
OrderService | setRefundPolicy | request | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | request | timeBands | array of object |  | Refundable percentage by time before the performance.
OrderService | setRefundPolicy | request | timeBands[].hoursBefore | integer | yes | (min 0)
OrderService | setRefundPolicy | request | timeBands[].percentage | number | yes | (min 0; max 100)
OrderService | setRefundPolicy | request | allowPartial | boolean |  | (default True)
OrderService | setRefundPolicy | request | refundWindowDays | integer |  | Days after purchase within which a refund may be made. (min 0; nullable)
OrderService | setRefundPolicy | request | varianceThreshold | object |  | Price variance above this is an exception requiring review rather than a routine posting (CF-38).
OrderService | setRefundPolicy | request | varianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | request | varianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | request | varianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
OrderService | setRefundPolicy | response | venueId | string (uuid) | yes | The venue in the path. (read-only)
OrderService | setRefundPolicy | response | selfAuthoriseLimit | object | yes | Up to this, a holder of ORDER_REFUND refunds alone.
OrderService | setRefundPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | requiresSecondUserAbove | object |  | Above this, a second user — cashier OR supervisor — names themselves as audit control.
OrderService | setRefundPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | requiresApprovalAbove | object | yes | Above this, an ORDER_REFUND_APPROVE holder must approve.
OrderService | setRefundPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | response | timeBands | array of object |  | Refundable percentage by time before the performance.
OrderService | setRefundPolicy | response | timeBands[].hoursBefore | integer | yes | (min 0)
OrderService | setRefundPolicy | response | timeBands[].percentage | number | yes | (min 0; max 100)
OrderService | setRefundPolicy | response | allowPartial | boolean |  | (default True)
OrderService | setRefundPolicy | response | refundWindowDays | integer |  | Days after purchase within which a refund may be made. (min 0; nullable)
OrderService | setRefundPolicy | response | varianceThreshold | object |  | Price variance above this is an exception requiring review rather than a routine posting (CF-38).
OrderService | setRefundPolicy | response | varianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | setRefundPolicy | response | varianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | setRefundPolicy | response | varianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | setRefundPolicy | param (path) | venueId | string (uuid) | yes
OrderService | setRefundPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setRefundPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setResourceSchedule | request | resourceId | string (uuid)
VenueOpsService | setResourceSchedule | request | availabilityMode | enum (alwaysAvailable, scheduled, onRequest)
VenueOpsService | setResourceSchedule | request | windows | array of object
VenueOpsService | setResourceSchedule | request | windows[].daysOfWeek | array of string
VenueOpsService | setResourceSchedule | request | windows[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | request | windows[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | request | windows[].effectiveFrom | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | request | windows[].effectiveTo | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | request | slotMinutes | integer |  | How finely this resource's time can be cut, which is a property of the resource and not of the product sold against it. (nullable)
VenueOpsService | setResourceSchedule | request | minimumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | request | maximumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | request | advanceBookingDays | integer |  | (nullable)
VenueOpsService | setResourceSchedule | request | exceptions | array of object
VenueOpsService | setResourceSchedule | request | exceptions[].date | string (date)
VenueOpsService | setResourceSchedule | request | exceptions[].closed | boolean
VenueOpsService | setResourceSchedule | request | exceptions[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | request | exceptions[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | request | scopePath | string
VenueOpsService | setResourceSchedule | response | resourceId | string (uuid)
VenueOpsService | setResourceSchedule | response | availabilityMode | enum (alwaysAvailable, scheduled, onRequest)
VenueOpsService | setResourceSchedule | response | windows | array of object
VenueOpsService | setResourceSchedule | response | windows[].daysOfWeek | array of string
VenueOpsService | setResourceSchedule | response | windows[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | response | windows[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
VenueOpsService | setResourceSchedule | response | windows[].effectiveFrom | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | response | windows[].effectiveTo | string (date) |  | (nullable)
VenueOpsService | setResourceSchedule | response | slotMinutes | integer |  | How finely this resource's time can be cut, which is a property of the resource and not of the product sold against it. (nullable)
VenueOpsService | setResourceSchedule | response | minimumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | response | maximumBookingMinutes | integer |  | (nullable)
VenueOpsService | setResourceSchedule | response | advanceBookingDays | integer |  | (nullable)
VenueOpsService | setResourceSchedule | response | exceptions | array of object
VenueOpsService | setResourceSchedule | response | exceptions[].date | string (date)
VenueOpsService | setResourceSchedule | response | exceptions[].closed | boolean
VenueOpsService | setResourceSchedule | response | exceptions[].from | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | response | exceptions[].to | string |  | Local time of day, HH:MM. (pattern ^([01]\d¦2[0-3]):[0-5]\d$; nullable)
VenueOpsService | setResourceSchedule | response | scopePath | string
VenueOpsService | setResourceSchedule | param (path) | resourceId | string (uuid) | yes
VenueOpsService | setResourceSchedule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setResourceSchedule | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
RetailService | setReturnPolicy | request | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | setReturnPolicy | request | outletId | string (uuid) | yes
RetailService | setReturnPolicy | request | defaultWindowDays | integer | yes | (min 0)
RetailService | setReturnPolicy | request | requiresReceipt | boolean | yes | (default True)
RetailService | setReturnPolicy | request | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | setReturnPolicy | request | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | setReturnPolicy | request | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | request | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | request | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | request | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | setReturnPolicy | request | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | request | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | request | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | request | requiresApprovalAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | setReturnPolicy | request | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | request | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | request | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | request | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | setReturnPolicy | request | nonReturnableCategoryIds | array of string (uuid)
RetailService | setReturnPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | setReturnPolicy | response | outletId | string (uuid) | yes
RetailService | setReturnPolicy | response | defaultWindowDays | integer | yes | (min 0)
RetailService | setReturnPolicy | response | requiresReceipt | boolean | yes | (default True)
RetailService | setReturnPolicy | response | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | setReturnPolicy | response | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | setReturnPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | response | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | setReturnPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | response | requiresApprovalAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | setReturnPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | setReturnPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | setReturnPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | setReturnPolicy | response | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | setReturnPolicy | response | nonReturnableCategoryIds | array of string (uuid)
RetailService | setReturnPolicy | param (path) | outletId | string (uuid) | yes
RetailService | setReturnPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | setRulePriorityConflict | request | orderedRuleIds | array of string |  | The rules in priority order, highest first.
CatalogueService | setRulePriorityConflict | request | resolutionMethod | enum (highestPriorityWins, mostSpecificRuleWins, cumulativeAdjustment, maximumAdjustmentWins, minimumAdjustmentWins, weightedCombination, stopProcessing, customGovernedResolution) |  | How two applicable rules are resolved; the same vocabulary as RulePriorityConflictResolutionDynamicPricingTestConsSummary.resolutionMethod. (default highestPriorityWins)
CatalogueService | setRulePriorityConflict | request | priorityHierarchy | array of enum (commercialProtection, contractMemberProtection, eventSpecificStrategy, inventoryOccupancy, bookingVelocity, timeToEvent, seasonDayTimeslot, basePrice) |  | The priority matrix, highest first; defaults to the pack's order.
CatalogueService | setRulePriorityConflict | request | mode | enum (save, validate, test) | yes | validate checks the order and returns conflicts without saving; test runs testScenario against the order and saves it as a test case; save stores the order and method, refused with 409 while a critic…
CatalogueService | setRulePriorityConflict | request | testScenario | RulePriorityTestScenario |  | A sample booking for the conflict test console (pack p.90), the same inputs as a saved test case.
CatalogueService | setRulePriorityConflict | request | testScenario.caseName | string |  | (max length 120)
CatalogueService | setRulePriorityConflict | request | testScenario.caseType | enum (lowDemand, highDemand, nearSellOut, earlyBird, lastMinute, weekendPeak, memberPurchase, b2bContract, …)
CatalogueService | setRulePriorityConflict | request | testScenario.productId | string (uuid)
CatalogueService | setRulePriorityConflict | request | testScenario.eventId | string (uuid) |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.performanceId | string (uuid) |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.date | string (date)
CatalogueService | setRulePriorityConflict | request | testScenario.timeslot | string |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | setRulePriorityConflict | request | testScenario.customerSegment | string |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | request | testScenario.basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | request | testScenario.occupancy | number |  | (min 0; max 100)
CatalogueService | setRulePriorityConflict | request | testScenario.inventory | integer |  | (min 0)
CatalogueService | setRulePriorityConflict | request | testScenario.bookingVelocity | number
CatalogueService | setRulePriorityConflict | request | testScenario.timeToEvent | integer |  | (min 0)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice | object |  | (nullable)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | request | testScenario.expectedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | mode | enum (save, validate, test)
CatalogueService | setRulePriorityConflict | response | saved | boolean
CatalogueService | setRulePriorityConflict | response | orderedRuleIds | array of string
CatalogueService | setRulePriorityConflict | response | resolutionMethod | string
CatalogueService | setRulePriorityConflict | response | priorityHierarchy | array of string
CatalogueService | setRulePriorityConflict | response | conflicts | array of object
CatalogueService | setRulePriorityConflict | response | conflicts[].code | enum (contradictoryRules, samePriority, impossibleCondition, overlappingStrategy, circularDependency, missingFallback, guardrailConflict)
CatalogueService | setRulePriorityConflict | response | conflicts[].severity | enum (critical, warning)
CatalogueService | setRulePriorityConflict | response | conflicts[].ruleIds | array of string
CatalogueService | setRulePriorityConflict | response | conflicts[].message | string
CatalogueService | setRulePriorityConflict | response | testResult | object |  | The saved test case with its deterministic result, in test mode. (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.product | string |  | Test input: product
CatalogueService | setRulePriorityConflict | response | testResult.event | string |  | Test input: event (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.performance | string |  | Test input: performance (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.date | string (date) |  | Test input: visit/event date
CatalogueService | setRulePriorityConflict | response | testResult.timeslot | string |  | Test input: timeslot (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.channel | object |  | Test input: channel
CatalogueService | setRulePriorityConflict | response | testResult.customerSegment | string |  | Test input: customer segment
CatalogueService | setRulePriorityConflict | response | testResult.basePrice | object |  | Test input: base price
CatalogueService | setRulePriorityConflict | response | testResult.basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.occupancy | number |  | Test input: occupancy percent
CatalogueService | setRulePriorityConflict | response | testResult.inventory | integer |  | Test input: remaining inventory
CatalogueService | setRulePriorityConflict | response | testResult.bookingVelocity | number |  | Test input: booking velocity, percent against expected pace
CatalogueService | setRulePriorityConflict | response | testResult.timeToEvent | integer |  | Test input: days to event (0 = same day)
CatalogueService | setRulePriorityConflict | response | testResult.calculationPath | array of string |  | Explainability: the complete calculation path, one step per line
CatalogueService | setRulePriorityConflict | response | testResult.testCaseId | string |  | Test case ID
CatalogueService | setRulePriorityConflict | response | testResult.caseName | string |  | Test case name
CatalogueService | setRulePriorityConflict | response | testResult.caseType | enum (lowDemand, highDemand, nearSellOut, earlyBird, lastMinute, weekendPeak, memberPurchase, b2bContract, …) |  | Test case type (pack p.91)
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched | array of object |  | Rules matched
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].ruleId | string |  | Rule
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].ruleName | string |  | Rule name
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].priorityLevel | enum (commercialProtection, contractMemberProtection, eventSpecificStrategy, inventoryOccupancy, bookingVelocity, timeToEvent, seasonDayTimeslot, basePrice) |  | Hierarchy level
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].adjustmentPercent | number |  | Adjustment in percent (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.rulesMatched[].applied | boolean |  | Applied after resolution
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice | object |  | Raw calculated price
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.rawCalculatedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice | object |  | Nearest allowed band
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.ladderPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.guardrailOutcome | enum (passed, cappedAtMaximum, raisedToMinimum, protectedRateApplied) |  | Guardrail result
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice | object |  | Final dynamic price
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.finalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | testResult.conflicts | array of object |  | Conflicts met while resolving this case
CatalogueService | setRulePriorityConflict | response | testResult.conflicts[].code | enum (contradictoryRules, samePriority, impossibleCondition, overlappingStrategy, circularDependency, missingFallback, guardrailConflict) |  | Conflict type (pack p.90)
CatalogueService | setRulePriorityConflict | response | testResult.conflicts[].message | string |  | Message
CatalogueService | setRulePriorityConflict | response | testResult.conflicts[].ruleIds | array of string |  | Rules involved
CatalogueService | setRulePriorityConflict | response | testResult.lastRunAt | string (date-time) |  | Last run
CatalogueService | setRulePriorityConflict | response | testResult.passed | boolean |  | Final price matched the expected price saved with the case (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice | object |  | Expected final price for regression (nullable)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | setRulePriorityConflict | response | testResult.expectedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | setRulePriorityConflict | response | savedAt | string (date-time) |  | (nullable)
CatalogueService | setRulePriorityConflict | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | setSemanticModel | request | version | integer |  | Assigned by the server on each publish. (read-only)
ReportingService | setSemanticModel | request | domains | array of object
ReportingService | setSemanticModel | request | domains[].code | string
ReportingService | setSemanticModel | request | domains[].name | string
ReportingService | setSemanticModel | request | domains[].description | string |  | (nullable)
ReportingService | setSemanticModel | request | domains[].datasets | array of object
ReportingService | setSemanticModel | request | domains[].datasets[].code | string
ReportingService | setSemanticModel | request | domains[].datasets[].name | string
ReportingService | setSemanticModel | request | domains[].datasets[].grain | string |  | What one row means.
ReportingService | setSemanticModel | request | domains[].datasets[].fields | array of object
ReportingService | setSemanticModel | request | relationships | array of object
ReportingService | setSemanticModel | request | relationships[].fromDataset | string
ReportingService | setSemanticModel | request | relationships[].toDataset | string
ReportingService | setSemanticModel | request | relationships[].cardinality | enum (oneToOne, oneToMany, manyToOne, manyToMany)
ReportingService | setSemanticModel | request | publishedAt | string (date-time) |  | (read-only; nullable)
ReportingService | setSemanticModel | request | scopePath | string
ReportingService | setSemanticModel | response | version | integer |  | Assigned by the server on each publish. (read-only)
ReportingService | setSemanticModel | response | domains | array of object
ReportingService | setSemanticModel | response | domains[].code | string
ReportingService | setSemanticModel | response | domains[].name | string
ReportingService | setSemanticModel | response | domains[].description | string |  | (nullable)
ReportingService | setSemanticModel | response | domains[].datasets | array of object
ReportingService | setSemanticModel | response | domains[].datasets[].code | string
ReportingService | setSemanticModel | response | domains[].datasets[].name | string
ReportingService | setSemanticModel | response | domains[].datasets[].grain | string |  | What one row means.
ReportingService | setSemanticModel | response | domains[].datasets[].fields | array of object
ReportingService | setSemanticModel | response | relationships | array of object
ReportingService | setSemanticModel | response | relationships[].fromDataset | string
ReportingService | setSemanticModel | response | relationships[].toDataset | string
ReportingService | setSemanticModel | response | relationships[].cardinality | enum (oneToOne, oneToMany, manyToOne, manyToMany)
ReportingService | setSemanticModel | response | publishedAt | string (date-time) |  | (read-only; nullable)
ReportingService | setSemanticModel | response | scopePath | string
ReportingService | setSemanticModel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | setSeoMetadata | request | id | string (uuid) | yes | (read-only)
MarketingService | setSeoMetadata | request | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | setSeoMetadata | request | entityId | string (uuid) | yes
MarketingService | setSeoMetadata | request | locale | string
MarketingService | setSeoMetadata | request | title | string |  | (nullable)
MarketingService | setSeoMetadata | request | metaDescription | string |  | (nullable)
MarketingService | setSeoMetadata | request | keywords | array of string
MarketingService | setSeoMetadata | request | canonicalUrl | string |  | (nullable)
MarketingService | setSeoMetadata | request | slug | string |  | 22.11.6. (nullable)
MarketingService | setSeoMetadata | request | hreflang | object |  | 22.11.11.
MarketingService | setSeoMetadata | request | schemaOrgType | string |  | (nullable)
MarketingService | setSeoMetadata | request | openGraph | object
MarketingService | setSeoMetadata | request | isAutoGenerated | boolean |  | 22.11.2. (default True)
MarketingService | setSeoMetadata | request | noIndex | boolean |  | (default False)
MarketingService | setSeoMetadata | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setSeoMetadata | response | id | string (uuid) | yes | (read-only)
MarketingService | setSeoMetadata | response | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | setSeoMetadata | response | entityId | string (uuid) | yes
MarketingService | setSeoMetadata | response | locale | string
MarketingService | setSeoMetadata | response | title | string |  | (nullable)
MarketingService | setSeoMetadata | response | metaDescription | string |  | (nullable)
MarketingService | setSeoMetadata | response | keywords | array of string
MarketingService | setSeoMetadata | response | canonicalUrl | string |  | (nullable)
MarketingService | setSeoMetadata | response | slug | string |  | 22.11.6. (nullable)
MarketingService | setSeoMetadata | response | hreflang | object |  | 22.11.11.
MarketingService | setSeoMetadata | response | schemaOrgType | string |  | (nullable)
MarketingService | setSeoMetadata | response | openGraph | object
MarketingService | setSeoMetadata | response | isAutoGenerated | boolean |  | 22.11.2. (default True)
MarketingService | setSeoMetadata | response | noIndex | boolean |  | (default False)
MarketingService | setSeoMetadata | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setSeoMetadata | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setSiteSetupProgress | request | id | string (uuid) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | request | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | setSiteSetupProgress | request | currentStep | object |  | (nullable)
WhiteLabelService | setSiteSetupProgress | request | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | setSiteSetupProgress | request | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | setSiteSetupProgress | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setSiteSetupProgress | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | response | id | string (uuid) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | response | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | setSiteSetupProgress | response | currentStep | object |  | (nullable)
WhiteLabelService | setSiteSetupProgress | response | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | setSiteSetupProgress | response | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | setSiteSetupProgress | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setSiteSetupProgress | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setSiteSetupProgress | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setStoreAccounts | request | accounts | array of StoreAccount | yes | (max items 2)
WhiteLabelService | setStoreAccounts | request | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | setStoreAccounts | request | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | setStoreAccounts | request | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | setStoreAccounts | request | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | setStoreAccounts | request | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key, sent once and kept in the secret store; this is its reference. (nullable)
WhiteLabelService | setStoreAccounts | request | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].listing | object |  | The store listing.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | request | accounts[].listing.category | string
WhiteLabelService | setStoreAccounts | request | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | setStoreAccounts | request | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | setStoreAccounts | request | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | setStoreAccounts | request | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setStoreAccounts | request | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts | array of StoreAccount | yes
WhiteLabelService | setStoreAccounts | response | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | setStoreAccounts | response | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | setStoreAccounts | response | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | setStoreAccounts | response | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | setStoreAccounts | response | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key, sent once and kept in the secret store; this is its reference. (nullable)
WhiteLabelService | setStoreAccounts | response | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].listing | object |  | The store listing.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | setStoreAccounts | response | accounts[].listing.category | string
WhiteLabelService | setStoreAccounts | response | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | setStoreAccounts | response | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | setStoreAccounts | response | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | setStoreAccounts | response | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | setStoreAccounts | response | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | setStoreAccounts | response | items | array of object | yes
WhiteLabelService | setStoreAccounts | response | items[].item | enum (appleDunsNumber, appleDeveloperAccount, googlePlayDeveloperAccount, storeListing, appIcons, publishedConfiguration) | yes
WhiteLabelService | setStoreAccounts | response | items[].done | boolean | yes
WhiteLabelService | setStoreAccounts | response | items[].clientOwned | boolean |  | True for the three accounts, which only the client can open.
WhiteLabelService | setStoreAccounts | response | items[].guidance | string |  | What to do next, in the operator's language.
WhiteLabelService | setStoreAccounts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | setSubscription | request | planId | string (uuid) | yes
PlatformService | setSubscription | request | planVersion | string |  | Defaults to the current version.
PlatformService | setSubscription | request | effectiveFrom | string (date) |  | Optional, and set by the server if omitted.
PlatformService | setSubscription | request | prorate | boolean |  | An upgrade is always prorated and a downgrade, which starts at renewal, never is (audit R214 (1)). (default True)
PlatformService | setSubscription | request | note | string |  | (max length 500)
PlatformService | setSubscription | response | tenantId | string (uuid) | yes
PlatformService | setSubscription | response | planId | string (uuid) | yes
PlatformService | setSubscription | response | planName | string
PlatformService | setSubscription | response | planVersion | string | yes
PlatformService | setSubscription | response | status | enum (trial, active, pastDue, cancelled, expired) | yes
PlatformService | setSubscription | response | startsAt | string (date) | yes
PlatformService | setSubscription | response | renewsAt | string (date) |  | (nullable)
PlatformService | setSubscription | response | cancelledAt | string (date) |  | (nullable)
PlatformService | setSubscription | response | scheduledChange | object |  | A downgrade waiting for the next renewal (decided 28 September, audit R214 (1)). (read-only; nullable)
PlatformService | setSubscription | response | scheduledChange.planId | string (uuid)
PlatformService | setSubscription | response | scheduledChange.planVersion | string
PlatformService | setSubscription | response | scheduledChange.effectiveFrom | string (date) |  | Always the renewsAt it was scheduled against.
PlatformService | setSubscription | response | currentPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | setSubscription | response | currentPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | setSubscription | response | currentPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | setSubscription | response | currentPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | setSubscription | response | billingPeriod | string
PlatformService | setSubscription | param (path) | tenantId | string (uuid) | yes
PlatformService | setSubscription | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | setSuggestionProvider | request | assignments | array of SuggestionProviderAssignment | yes | (min items 1)
AiService | setSuggestionProvider | request | assignments[].kind | SuggestionKind: enum (price, replenishment, requisition, demandForecast, prepPlan, menuEngineering, staffing, slaTarget, …) | yes | What is being suggested.
AiService | setSuggestionProvider | request | assignments[].basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | setSuggestionProvider | request | assignments[].producerRef | string | yes | The rule name, or the model id and version — the same value Suggestion.producerRef records on each answer.
AiService | setSuggestionProvider | request | assignments[].shadowProducerRef | string |  | Runs alongside and is recorded, never shown. (nullable)
AiService | setSuggestionProvider | request | assignments[].guardRails | object |  | Bounds the answer must fall within. (nullable)
AiService | setSuggestionProvider | response | assignments | array of SuggestionProviderAssignment | yes
AiService | setSuggestionProvider | response | assignments[].kind | SuggestionKind: enum (price, replenishment, requisition, demandForecast, prepPlan, menuEngineering, staffing, slaTarget, …) | yes | What is being suggested.
AiService | setSuggestionProvider | response | assignments[].basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | setSuggestionProvider | response | assignments[].producerRef | string | yes | The rule name, or the model id and version — the same value Suggestion.producerRef records on each answer.
AiService | setSuggestionProvider | response | assignments[].shadowProducerRef | string |  | Runs alongside and is recorded, never shown. (nullable)
AiService | setSuggestionProvider | response | assignments[].guardRails | object |  | Bounds the answer must fall within. (nullable)
AiService | setSuggestionProvider | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setTableCombinations | request | combinations | array of TableCombination | yes
FnbService | setTableCombinations | request | combinations[].id | string (uuid) |  | (read-only)
FnbService | setTableCombinations | request | combinations[].outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setTableCombinations | request | combinations[].tableIds | array of string (uuid) | yes | (min items 2)
FnbService | setTableCombinations | request | combinations[].combinedCovers | integer | yes | (min 1)
FnbService | setTableCombinations | request | combinations[].setupMinutes | integer |  | (default 5)
FnbService | setTableCombinations | request | combinations[].scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setTableCombinations | response | combinations | array of TableCombination | yes
FnbService | setTableCombinations | response | combinations[].id | string (uuid) |  | (read-only)
FnbService | setTableCombinations | response | combinations[].outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | setTableCombinations | response | combinations[].tableIds | array of string (uuid) | yes | (min items 2)
FnbService | setTableCombinations | response | combinations[].combinedCovers | integer | yes | (min 1)
FnbService | setTableCombinations | response | combinations[].setupMinutes | integer |  | (default 5)
FnbService | setTableCombinations | response | combinations[].scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | setTableCombinations | param (path) | outletId | string (uuid) | yes
FnbService | setTableCombinations | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setTableCombinations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | setTableLayout | request | tables | array of TableDefinition | yes
FnbService | setTableLayout | request | tables[].id | string (uuid) | yes
FnbService | setTableLayout | request | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | setTableLayout | request | tables[].capacity | integer | yes | (min 1)
FnbService | setTableLayout | request | tables[].zone | string |  | (nullable)
FnbService | setTableLayout | request | tables[].position | object
FnbService | setTableLayout | request | tables[].position.x | number
FnbService | setTableLayout | request | tables[].position.y | number
FnbService | setTableLayout | request | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | setTableLayout | request | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | setTableLayout | response | outletId | string (uuid) | yes
FnbService | setTableLayout | response | zones | array of string
FnbService | setTableLayout | response | tables | array of TableState | yes
FnbService | setTableLayout | response | tables[].id | string (uuid) | yes
FnbService | setTableLayout | response | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | setTableLayout | response | tables[].capacity | integer | yes | (min 1)
FnbService | setTableLayout | response | tables[].zone | string |  | (nullable)
FnbService | setTableLayout | response | tables[].position | object
FnbService | setTableLayout | response | tables[].position.x | number
FnbService | setTableLayout | response | tables[].position.y | number
FnbService | setTableLayout | response | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | setTableLayout | response | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | setTableLayout | response | tables[].status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | setTableLayout | response | tables[].visitId | string (uuid) |  | (nullable)
FnbService | setTableLayout | response | tables[].covers | integer |  | (nullable)
FnbService | setTableLayout | response | tables[].seatedAt | string (date-time) |  | (nullable)
FnbService | setTableLayout | response | tables[].serverPrincipalId | string (uuid) |  | (nullable)
FnbService | setTableLayout | response | tables[].billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | setTableLayout | response | tables[].billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | setTableLayout | response | tables[].billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | setTableLayout | response | tables[].billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | setTableLayout | param (path) | outletId | string (uuid) | yes
FnbService | setTableLayout | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | setTableLayout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setTheme | request | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | darkMode | object |  | Optional dark variant.
WhiteLabelService | setTheme | request | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | setTheme | request | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | setTheme | request | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | setTheme | request | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | setTheme | request | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.payButton | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.link | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.badge | ThemeComponentColour
WhiteLabelService | setTheme | request | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | request | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | darkMode | object |  | Optional dark variant.
WhiteLabelService | setTheme | response | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | setTheme | response | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | setTheme | response | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | setTheme | response | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | setTheme | response | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.payButton | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.link | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.badge | ThemeComponentColour
WhiteLabelService | setTheme | response | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | response | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | setTheme | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | setTheme | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
MarketingService | setTrackingTechnology | request | technologyId | string (uuid) |  | (read-only)
MarketingService | setTrackingTechnology | request | name | string | yes | The cookie, SDK, pixel or storage key as it appears on the device. (max length 200)
MarketingService | setTrackingTechnology | request | provider | string | yes | (max length 150)
MarketingService | setTrackingTechnology | request | domainApplication | string |  | The domain, or the app and version, it was found on. (max length 255; nullable)
MarketingService | setTrackingTechnology | request | technologyType | enum (firstPartyCookie, thirdPartyCookie, mobileSdk, analyticsTracker, advertisingPixel, sessionTechnology, personalisationTechnology, embeddedService, …) | yes
MarketingService | setTrackingTechnology | request | category | enum (strictlyNecessary, functional, analytics, personalisation, marketing, other) |  | Null until an administrator classifies it. (nullable)
MarketingService | setTrackingTechnology | request | otherCategoryLabel | string |  | The organisation-defined category, when category is other. (max length 80; nullable)
MarketingService | setTrackingTechnology | request | purpose | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | request | dataCollected | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | request | durationDays | integer |  | Null for session storage. (min 0; nullable)
MarketingService | setTrackingTechnology | request | isThirdParty | boolean | yes
MarketingService | setTrackingTechnology | request | channels | array of enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | (min items 1)
MarketingService | setTrackingTechnology | request | countries | array of string |  | Empty means every country.
MarketingService | setTrackingTechnology | request | processingPurposeCode | string |  | The DataProcessingPurposeLawfulBasisRegistryView.purposeCode it serves. (nullable)
MarketingService | setTrackingTechnology | request | consentRequired | boolean |  | False only for strictlyNecessary. (default True)
MarketingService | setTrackingTechnology | request | privacyInformation | string |  | What the preference centre tells the guest about it. (max length 1000; nullable)
MarketingService | setTrackingTechnology | request | source | enum (manual, scan) |  | (default manual; read-only)
MarketingService | setTrackingTechnology | request | status | enum (detected, approved, blocked, retired) | yes | detected is treated as blocked until approved.
MarketingService | setTrackingTechnology | request | firstDetectedAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | request | lastSeenAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setTrackingTechnology | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | setTrackingTechnology | response | technologyId | string (uuid) |  | (read-only)
MarketingService | setTrackingTechnology | response | name | string | yes | The cookie, SDK, pixel or storage key as it appears on the device. (max length 200)
MarketingService | setTrackingTechnology | response | provider | string | yes | (max length 150)
MarketingService | setTrackingTechnology | response | domainApplication | string |  | The domain, or the app and version, it was found on. (max length 255; nullable)
MarketingService | setTrackingTechnology | response | technologyType | enum (firstPartyCookie, thirdPartyCookie, mobileSdk, analyticsTracker, advertisingPixel, sessionTechnology, personalisationTechnology, embeddedService, …) | yes
MarketingService | setTrackingTechnology | response | category | enum (strictlyNecessary, functional, analytics, personalisation, marketing, other) |  | Null until an administrator classifies it. (nullable)
MarketingService | setTrackingTechnology | response | otherCategoryLabel | string |  | The organisation-defined category, when category is other. (max length 80; nullable)
MarketingService | setTrackingTechnology | response | purpose | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | response | dataCollected | string |  | (max length 500; nullable)
MarketingService | setTrackingTechnology | response | durationDays | integer |  | Null for session storage. (min 0; nullable)
MarketingService | setTrackingTechnology | response | isThirdParty | boolean | yes
MarketingService | setTrackingTechnology | response | channels | array of enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | (min items 1)
MarketingService | setTrackingTechnology | response | countries | array of string |  | Empty means every country.
MarketingService | setTrackingTechnology | response | processingPurposeCode | string |  | The DataProcessingPurposeLawfulBasisRegistryView.purposeCode it serves. (nullable)
MarketingService | setTrackingTechnology | response | consentRequired | boolean |  | False only for strictlyNecessary. (default True)
MarketingService | setTrackingTechnology | response | privacyInformation | string |  | What the preference centre tells the guest about it. (max length 1000; nullable)
MarketingService | setTrackingTechnology | response | source | enum (manual, scan) |  | (default manual; read-only)
MarketingService | setTrackingTechnology | response | status | enum (detected, approved, blocked, retired) | yes | detected is treated as blocked until approved.
MarketingService | setTrackingTechnology | response | firstDetectedAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | response | lastSeenAt | string (date-time) |  | (read-only; nullable)
MarketingService | setTrackingTechnology | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | setTrackingTechnology | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | setTrackingTechnology | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setTransportFareTable | request | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | setTransportFareTable | request | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | request | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | request | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | request | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | request | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | request | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | request | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | request | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | request | matrix | array of object |  | matrix only.
VenueOpsService | setTransportFareTable | request | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | request | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | request | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | request | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | request | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | request | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | request | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | setTransportFareTable | request | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | setTransportFareTable | request | passengerTypes[].name | LocalisedText | yes
VenueOpsService | setTransportFareTable | request | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | setTransportFareTable | request | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | setTransportFareTable | request | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | request | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | request | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | setTransportFareTable | request | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | setTransportFareTable | request | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | setTransportFareTable | request | effectiveFrom | string (date-time) | yes
VenueOpsService | setTransportFareTable | response | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | setTransportFareTable | response | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | response | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | response | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | response | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | response | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | response | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | response | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | response | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | response | matrix | array of object |  | matrix only.
VenueOpsService | setTransportFareTable | response | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | setTransportFareTable | response | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | setTransportFareTable | response | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | setTransportFareTable | response | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | setTransportFareTable | response | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | setTransportFareTable | response | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | setTransportFareTable | response | passengerTypes[].name | LocalisedText | yes
VenueOpsService | setTransportFareTable | response | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | setTransportFareTable | response | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | setTransportFareTable | response | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | response | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | setTransportFareTable | response | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | setTransportFareTable | response | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | setTransportFareTable | response | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | setTransportFareTable | response | effectiveFrom | string (date-time) | yes
VenueOpsService | setTransportFareTable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | setTransportFareTable | param (path) | routeId | string (uuid) | yes
VenueOpsService | setTransportFareTable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setTurnstileMode | request | operatingMode | AccessPointOperatingMode: enum (normal, freeFlow, dropArm, closed, podium, maintenance) | yes | BL-107 and BL-109.
AccessService | setTurnstileMode | request | mode | object |  | Optional narrowing within normal or podium: freeRotation or closed. (nullable)
AccessService | setTurnstileMode | request | reason | string |  | (max length 200)
AccessService | setTurnstileMode | request | effectiveAt | string (date-time) |  | When the change takes effect. (nullable)
AccessService | setTurnstileMode | response | id | string (uuid) | yes
AccessService | setTurnstileMode | response | code | string | yes
AccessService | setTurnstileMode | response | name | string | yes
AccessService | setTurnstileMode | response | venueId | string (uuid) | yes
AccessService | setTurnstileMode | response | scopePath | string
AccessService | setTurnstileMode | response | externalCredentialSources | object |  | BL-108.
AccessService | setTurnstileMode | response | scanAnomalyRules | object |  | BL-104.
AccessService | setTurnstileMode | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | setTurnstileMode | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | setTurnstileMode | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | setTurnstileMode | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | setTurnstileMode | response | antiPassbackEnabled | boolean
AccessService | setTurnstileMode | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | setTurnstileMode | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | setTurnstileMode | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | setTurnstileMode | response | geofence.latitude | number
AccessService | setTurnstileMode | response | geofence.longitude | number
AccessService | setTurnstileMode | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | setTurnstileMode | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | setTurnstileMode | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | setTurnstileMode | response | isActive | boolean | yes
AccessService | setTurnstileMode | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | setTurnstileMode | param (path) | accessPointId | string (uuid) | yes
AccessService | setTurnstileMode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | setVenuePoint | request | id | string (uuid) | yes | (read-only)
VenueOpsService | setVenuePoint | request | mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | setVenuePoint | request | kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | setVenuePoint | request | name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | setVenuePoint | request | nameLocalised | object |  | (nullable)
VenueOpsService | setVenuePoint | request | position | object | yes | Drawing coordinates.
VenueOpsService | setVenuePoint | request | position.x | number | yes
VenueOpsService | setVenuePoint | request | position.y | number | yes
VenueOpsService | setVenuePoint | request | outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | setVenuePoint | request | productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | setVenuePoint | request | accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | setVenuePoint | request | isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | setVenuePoint | request | openingHours | string |  | (nullable)
VenueOpsService | setVenuePoint | request | iconRef | string |  | (nullable)
VenueOpsService | setVenuePoint | request | isActive | boolean |  | (default True)
VenueOpsService | setVenuePoint | request | isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | setVenuePoint | request | isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | setVenuePoint | request | description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | request | media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | setVenuePoint | request | media[].assetId | string (uuid) | yes
VenueOpsService | setVenuePoint | request | media[].kind | enum (image, video) | yes
VenueOpsService | setVenuePoint | request | media[].isPrimary | boolean |  | (default False)
VenueOpsService | setVenuePoint | request | media[].altText | string |  | (max length 200; nullable)
VenueOpsService | setVenuePoint | request | featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | request | featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | setVenuePoint | request | featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | setVenuePoint | request | featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | setVenuePoint | request | typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | setVenuePoint | request | interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | setVenuePoint | request | cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | setVenuePoint | request | retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | setVenuePoint | request | pointId | string (uuid) |  | The point to amend. (nullable)
VenueOpsService | setVenuePoint | response | id | string (uuid) | yes | (read-only)
VenueOpsService | setVenuePoint | response | mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | setVenuePoint | response | kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | setVenuePoint | response | name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | setVenuePoint | response | nameLocalised | object |  | (nullable)
VenueOpsService | setVenuePoint | response | position | object | yes | Drawing coordinates.
VenueOpsService | setVenuePoint | response | position.x | number | yes
VenueOpsService | setVenuePoint | response | position.y | number | yes
VenueOpsService | setVenuePoint | response | outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | setVenuePoint | response | productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | setVenuePoint | response | accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | setVenuePoint | response | isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | setVenuePoint | response | openingHours | string |  | (nullable)
VenueOpsService | setVenuePoint | response | iconRef | string |  | (nullable)
VenueOpsService | setVenuePoint | response | isActive | boolean |  | (default True)
VenueOpsService | setVenuePoint | response | isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | setVenuePoint | response | isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | setVenuePoint | response | description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | response | media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | setVenuePoint | response | media[].assetId | string (uuid) | yes
VenueOpsService | setVenuePoint | response | media[].kind | enum (image, video) | yes
VenueOpsService | setVenuePoint | response | media[].isPrimary | boolean |  | (default False)
VenueOpsService | setVenuePoint | response | media[].altText | string |  | (max length 200; nullable)
VenueOpsService | setVenuePoint | response | featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | setVenuePoint | response | featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | setVenuePoint | response | featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | setVenuePoint | response | featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | setVenuePoint | response | typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | setVenuePoint | response | interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | setVenuePoint | response | cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | setVenuePoint | response | retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | setVenuePoint | param (path) | mapId | string (uuid) | yes
VenueOpsService | setVenuePoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | setVenueSettings | request | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setVenueSettings | request | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | setVenueSettings | request | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | setVenueSettings | request | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | setVenueSettings | request | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | setVenueSettings | request | supportHours | object |  | CF-100.
TenancyService | setVenueSettings | request | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | setVenueSettings | request | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | setVenueSettings | request | supportHours.windows | array of object
TenancyService | setVenueSettings | request | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | request | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | setVenueSettings | request | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | setVenueSettings | request | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | setVenueSettings | request | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | setVenueSettings | request | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | setVenueSettings | request | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | setVenueSettings | request | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | setVenueSettings | request | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | setVenueSettings | request | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | setVenueSettings | request | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | setVenueSettings | request | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | setVenueSettings | request | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | setVenueSettings | request | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | setVenueSettings | request | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettings | request | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | setVenueSettings | request | segregatedAccess.schedule | array of object
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | setVenueSettings | request | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | setVenueSettings | request | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | setVenueSettings | request | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | setVenueSettings | request | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | setVenueSettings | request | alerting | object |  | CF-134.
TenancyService | setVenueSettings | request | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | setVenueSettings | request | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | setVenueSettings | request | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | setVenueSettings | request | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | setVenueSettings | request | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | setVenueSettings | request | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | setVenueSettings | request | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | request | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | setVenueSettings | request | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | request | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | request | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | request | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | setVenueSettings | request | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | catalogue | object |  | (nullable)
TenancyService | setVenueSettings | request | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | setVenueSettings | request | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | setVenueSettings | request | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | setVenueSettings | request | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | setVenueSettings | request | inventory | object |  | (nullable)
TenancyService | setVenueSettings | request | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | setVenueSettings | request | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | seating | object |  | (nullable)
TenancyService | setVenueSettings | request | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | setVenueSettings | request | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | setVenueSettings | request | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | setVenueSettings | request | promotions | object |  | (nullable)
TenancyService | setVenueSettings | request | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | fnb | object |  | (nullable)
TenancyService | setVenueSettings | request | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | request | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | request | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | setVenueSettings | request | queue | object |  | (nullable)
TenancyService | setVenueSettings | request | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | setVenueSettings | request | reporting | object |  | (nullable)
TenancyService | setVenueSettings | request | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | setVenueSettings | request | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | setVenueSettings | request | marketing | object |  | (nullable)
TenancyService | setVenueSettings | request | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | setVenueSettings | request | identity | object |  | (nullable)
TenancyService | setVenueSettings | request | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | setVenueSettings | request | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | setVenueSettings | request | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | setVenueSettings | request | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | setVenueSettings | response | id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | setVenueSettings | response | venueId | string (uuid) |  | From the path of setVenueSettings. (read-only)
TenancyService | setVenueSettings | response | calendarDayStartHour | integer |  | Where the venue's calendar day starts (17 September minutes M17-03, added 30 September): the first hour row of every day and week calendar view (calendarView in screens/_components.yaml), so a venue… (min 0; max 23; default 6; nullable)
TenancyService | setVenueSettings | response | currencyCode | string |  | readOnly is the freeze. (pattern ^[A-Z]{3}$; read-only; nullable)
TenancyService | setVenueSettings | response | currencyScale | integer |  | Scale travels with currency (ADR-0008), and so does the freeze. (min 0; max 4; read-only; nullable)
TenancyService | setVenueSettings | response | supportHours | object |  | CF-100.
TenancyService | setVenueSettings | response | supportHours.mode | enum (alwaysOn, businessHours, custom, none)
TenancyService | setVenueSettings | response | supportHours.timezone | string |  | IANA zone the windows are read in.
TenancyService | setVenueSettings | response | supportHours.windows | array of object
TenancyService | setVenueSettings | response | supportHours.windows[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | response | supportHours.windows[].from | string |  | Wall-clock time the desk opens.
TenancyService | setVenueSettings | response | supportHours.windows[].to | string |  | Wall-clock time the desk closes.
TenancyService | setVenueSettings | response | supportHours.outOfHoursMessage | string |  | (nullable)
TenancyService | setVenueSettings | response | quietHours | object |  | When the platform does not send. (nullable)
TenancyService | setVenueSettings | response | quietHours.from | string |  | Wall-clock time sending stops
TenancyService | setVenueSettings | response | quietHours.to | string |  | Wall-clock time sending resumes
TenancyService | setVenueSettings | response | biometrics | object |  | CF-35, BL-096, BL-105, BL-106. (nullable)
TenancyService | setVenueSettings | response | biometrics.isEnabled | boolean |  | Off by default, and turning it on is refused without the two fields below. (default False)
TenancyService | setVenueSettings | response | biometrics.dpiaReference | string |  | The venue's own reference for its Article 21 assessment. (max length 200; nullable)
TenancyService | setVenueSettings | response | biometrics.consentNoticeAcknowledgedAt | string (date-time) |  | When somebody confirmed the consent forms are in place at the point of capture. (nullable)
TenancyService | setVenueSettings | response | biometrics.acknowledgedByPrincipalId | string (uuid) |  | Who confirmed it. (read-only; nullable)
TenancyService | setVenueSettings | response | biometrics.faceTagPurgeMinutesAfterClose | integer |  | BL-106. (default 0; nullable)
TenancyService | setVenueSettings | response | segregatedAccess | object |  | CF-130. (nullable)
TenancyService | setVenueSettings | response | segregatedAccess.isEnabled | boolean |  | (default False)
TenancyService | setVenueSettings | response | segregatedAccess.appliesToAccessPointIds | array of string (uuid)
TenancyService | setVenueSettings | response | segregatedAccess.schedule | array of object
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].day | enum (mon, tue, wed, thu, fri, sat, sun)
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].from | string |  | Wall-clock time
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].to | string |  | Wall-clock time
TenancyService | setVenueSettings | response | segregatedAccess.schedule[].admits | enum (all, women, womenAndChildren, families, members)
TenancyService | setVenueSettings | response | segregatedAccess.entitlementGated | boolean |  | Always true, and stated rather than assumed. (default True; read-only)
TenancyService | setVenueSettings | response | segregatedAccess.genderVerification | enum (off, staffAssisted, deviceAssisted) |  | off — the entitlement decides and a steward handles exceptions. (default off)
TenancyService | setVenueSettings | response | segregatedAccess.overrideRateAlertThreshold | number |  | Where deviceAssisted is on. (nullable)
TenancyService | setVenueSettings | response | alerting | object |  | CF-134.
TenancyService | setVenueSettings | response | alerting.channel | enum (dashboardPanel, dashboardAndEmail, dashboardAndWhatsapp) |  | (default dashboardPanel)
TenancyService | setVenueSettings | response | alerting.acknowledgementRequired | boolean |  | (default True)
TenancyService | setVenueSettings | response | alerting.escalateAfterMinutes | integer |  | (nullable)
TenancyService | setVenueSettings | response | displayCurrencies | array of string |  | Which currencies this venue shows guests (decided 28 September, audit R120 (a)). (nullable)
TenancyService | setVenueSettings | response | cartLeaseSeconds | integer |  | How long a cart holds capacity (decided 28 September, audit R169): 15 minutes, the default catalogue.acquireInventoryHold takes for ttlSeconds. (min 30; max 3600; default 900; nullable)
TenancyService | setVenueSettings | response | cartHoldExtensionMinutes | integer |  | How long one orders.extendCart extension adds. (min 1; max 30; default 5; nullable)
TenancyService | setVenueSettings | response | cartMaxExtensions | integer |  | How many extensions a cart may take before extensionCapReached (Cart.maxExtensions). (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | response | resaleCutoffHours | integer |  | Hours before the performance after which a ticket can no longer be listed for resale (orders.createResaleListing). (min 0; max 168; default 24; nullable)
TenancyService | setVenueSettings | response | exchangeCutoffHours | integer |  | Hours before the original performance after which lines can no longer be exchanged (orders.exchangeOrderLines, outsideExchangeWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | response | rescheduleCutoffHours | integer |  | Hours before the original performance after which an order can no longer be rescheduled (orders.rescheduleOrder, outsideRescheduleWindow). (min 0; max 720; default 24; nullable)
TenancyService | setVenueSettings | response | reservationMaxExtensions | integer |  | How many times orders.extendReservation may extend one reservation. (min 0; max 5; default 1; nullable)
TenancyService | setVenueSettings | response | shiftVarianceThreshold | object |  | Over or short at shift close beyond which the shift waits in pendingVariance for shift.acceptShiftVariance. (nullable)
TenancyService | setVenueSettings | response | shiftVarianceThreshold.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | shiftVarianceThreshold.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | shiftVarianceThreshold.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | catalogue | object |  | (nullable)
TenancyService | setVenueSettings | response | catalogue.maxVariantsPerProduct | integer |  | Variants one product may generate from its attributes (setProductAttributes refuses above it). (min 1; max 2000; default 200; nullable)
TenancyService | setVenueSettings | response | catalogue.waitlistOfferHoldMinutes | integer |  | How long a waitlist offer holds the released capacity for the guest it was offered to. (min 1; max 1440; default 30; nullable)
TenancyService | setVenueSettings | response | catalogue.bulkPriceChangeEscalationPercent | number |  | A bulkChangePrices run changing any price by more than this percentage needs PRICE_CONFIGURE (audit R197). (min 0; max 100; default 10; nullable)
TenancyService | setVenueSettings | response | catalogue.bulkPriceChangeEscalationCount | integer |  | A bulkChangePrices run touching more prices than this needs PRICE_CONFIGURE (audit R197). (min 1; default 50; nullable)
TenancyService | setVenueSettings | response | inventory | object |  | (nullable)
TenancyService | setVenueSettings | response | inventory.overReceiptTolerancePercent | number |  | Percent above the outstanding ordered quantity a goods receipt line may record (createGoodsReceipt). (min 0; max 25; default 5; nullable)
TenancyService | setVenueSettings | response | inventory.countVarianceTolerancePercent | number |  | Percent difference between counted and expected quantity before a count line is an exception (getCountVariance). (min 0; max 25; default 2; nullable)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount | object |  | Total variance value of a count above which posting it needs approval (postStockCount). (nullable)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | inventory.countVarianceApprovalAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | seating | object |  | (nullable)
TenancyService | setVenueSettings | response | seating.seatHoldExtensionSeconds | integer |  | What one extendSeatHold adds. (min 60; max 1800; default 300; nullable)
TenancyService | setVenueSettings | response | seating.seatHoldMaxExtensions | integer |  | How many times a seat hold may be extended. (min 0; max 5; default 2; nullable)
TenancyService | setVenueSettings | response | seating.maxSeatsPerGuestOrder | integer |  | Seats one guest may take in one booking on a guest channel (Guest Web, Guest App), decided 29 September, rev 3 REV3-7. (min 1; max 50; default 10; nullable)
TenancyService | setVenueSettings | response | promotions | object |  | (nullable)
TenancyService | setVenueSettings | response | promotions.maxDiscountPercent | number |  | The largest discount one promotion may give (createPromotion refuses above it). (min 0; max 100; default 30; nullable)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice | object |  | Net line price below which a stacked combination is flagged near-zero in analysePromotionConflicts (audit R096 (5)); a warning, not a refusal. (nullable)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | promotions.nearZeroLinePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | fnb | object |  | (nullable)
TenancyService | setVenueSettings | response | fnb.recallWindowMinutes | integer |  | Minutes after a bump during which recallKitchenTicket still recalls; after it the act is a refire. (min 0; max 60; default 10; nullable)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount | object |  | Line value above which compItem needs ORDER_DISCOUNT (audit R197). (nullable)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | setVenueSettings | response | fnb.compEscalationAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | setVenueSettings | response | fnb.foodSafetyLeadPrincipalId | string (uuid) |  | The venue's food-safety lead, to whom escalateCorrectiveAction sends every escalation (decided 28 September, audit R096 (9)). (nullable)
TenancyService | setVenueSettings | response | queue | object |  | (nullable)
TenancyService | setVenueSettings | response | queue.crossQueueLimit | integer |  | Virtual queues one guest party may wait in at once (joinQueue, crossQueueLimitReached). (min 1; max 10; default 2; nullable)
TenancyService | setVenueSettings | response | reporting | object |  | (nullable)
TenancyService | setVenueSettings | response | reporting.inlineRunRowLimit | integer |  | Estimated rows above which runReport answers 202 and runs in the background. (min 1000; max 100000; default 5000; nullable)
TenancyService | setVenueSettings | response | reporting.dashboardRefreshBudgetPerMinute | integer |  | Tile refreshes per minute, summed over a dashboard's tiles, that createDashboard allows. (min 1; default 24; nullable)
TenancyService | setVenueSettings | response | marketing | object |  | (nullable)
TenancyService | setVenueSettings | response | marketing.attributionWindowDays | integer |  | Days after a campaign touch within which a booking is attributed to it (getCampaignPerformance). (min 1; max 30; default 7; nullable)
TenancyService | setVenueSettings | response | identity | object |  | (nullable)
TenancyService | setVenueSettings | response | identity.guestOtpMaxAttempts | integer |  | Wrong entries allowed per guest one-time code before verifyGuestOtp invalidates it. (min 3; max 10; default 5; nullable)
TenancyService | setVenueSettings | response | identity.guestTwoStep | object |  | Guest two-step verification: a venue option, off unless the venue enables it in Venue Management (decided 29 September, rev 3 GAP-B1, per venue, superseding the second part of audit R167, "no guest M… (nullable)
TenancyService | setVenueSettings | response | identity.guestTwoStep.enabled | boolean |  | Off unless the venue enables it. (default False)
TenancyService | setVenueSettings | response | identity.guestTwoStep.stepUpActions | array of enum (changeContactDetails, changePassword, managePaymentMethods, transferTickets, deleteAccount) |  | The guest actions in this venue that ask an enrolled guest for the factor again, whatever the age of the session. (default ['changeContactDetails', 'changePassword', 'managePaymentMethods', 'deleteAccount'])
TenancyService | setVenueSettings | param (path) | venueId | string (uuid) | yes
TenancyService | setVenueSettings | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setVirtualTicketIdentity | request | venueId | string | yes | Venue this configuration applies to
AccessService | setVirtualTicketIdentity | request | idGenerationPattern | string |  | Virtual Ticket ID format: prefix, suffix and length
AccessService | setVirtualTicketIdentity | request | ticketClassification | string |  | Ticket classification
AccessService | setVirtualTicketIdentity | request | ticketOwnershipModel | string |  | Ticket ownership model
AccessService | setVirtualTicketIdentity | request | holderAssignmentRequirements | string |  | Holder assignment requirements
AccessService | setVirtualTicketIdentity | request | transferabilityReference | string |  | Transferability reference
AccessService | setVirtualTicketIdentity | request | validityModel | string |  | Validity model
AccessService | setVirtualTicketIdentity | request | consumptionModel | string |  | Consumption model
AccessService | setVirtualTicketIdentity | request | entitlementModel | string |  | Entitlement model
AccessService | setVirtualTicketIdentity | request | mediaRequirements | array of string |  | Media types a ticket of this configuration must carry
AccessService | setVirtualTicketIdentity | response | venueId | string | yes | Venue this configuration applies to
AccessService | setVirtualTicketIdentity | response | idGenerationPattern | string |  | Virtual Ticket ID format: prefix, suffix and length
AccessService | setVirtualTicketIdentity | response | ticketClassification | string |  | Ticket classification
AccessService | setVirtualTicketIdentity | response | ticketOwnershipModel | string |  | Ticket ownership model
AccessService | setVirtualTicketIdentity | response | holderAssignmentRequirements | string |  | Holder assignment requirements
AccessService | setVirtualTicketIdentity | response | transferabilityReference | string |  | Transferability reference
AccessService | setVirtualTicketIdentity | response | validityModel | string |  | Validity model
AccessService | setVirtualTicketIdentity | response | consumptionModel | string |  | Consumption model
AccessService | setVirtualTicketIdentity | response | entitlementModel | string |  | Entitlement model
AccessService | setVirtualTicketIdentity | response | mediaRequirements | array of string |  | Media types a ticket of this configuration must carry
AccessService | setVirtualTicketIdentity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | setVisitReminder | request | id | string (uuid) |  | (read-only)
OrderService | setVisitReminder | request | orderId | string (uuid) |  | (read-only)
OrderService | setVisitReminder | request | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | setVisitReminder | request | enabled | boolean | yes
OrderService | setVisitReminder | request | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | setVisitReminder | request | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | setVisitReminder | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | setVisitReminder | response | id | string (uuid) |  | (read-only)
OrderService | setVisitReminder | response | orderId | string (uuid) |  | (read-only)
OrderService | setVisitReminder | response | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | setVisitReminder | response | enabled | boolean | yes
OrderService | setVisitReminder | response | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | setVisitReminder | response | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | setVisitReminder | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | setVisitReminder | param (path) | orderId | string (uuid) | yes
OrderService | setVisitReminder | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | setVisitReminder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setVisualAccessRule | request | decision | enum (allow, deny, referToOperator, overrideEligible) | yes | THEN
AccessService | setVisualAccessRule | request | name | string | yes
AccessService | setVisualAccessRule | request | ruleId | string | yes
AccessService | setVisualAccessRule | request | logic | string |  | Boolean expression combining the conditions with AND / OR / NOT
AccessService | setVisualAccessRule | request | appliesTo | array of string |  | Products or credential types (WHEN)
AccessService | setVisualAccessRule | request | locationIds | array of string |  | Venue, park, zone, attraction or gate IDs (AT)
AccessService | setVisualAccessRule | request | conditions | array of string |  | Conditions (IF), e.g.
AccessService | setVisualAccessRule | request | consequences | array of string |  | Actions performed on the decision, e.g.
AccessService | setVisualAccessRule | response | decision | enum (allow, deny, referToOperator, overrideEligible) | yes | THEN
AccessService | setVisualAccessRule | response | name | string | yes
AccessService | setVisualAccessRule | response | ruleId | string | yes
AccessService | setVisualAccessRule | response | logic | string |  | Boolean expression combining the conditions with AND / OR / NOT
AccessService | setVisualAccessRule | response | appliesTo | array of string |  | Products or credential types (WHEN)
AccessService | setVisualAccessRule | response | locationIds | array of string |  | Venue, park, zone, attraction or gate IDs (AT)
AccessService | setVisualAccessRule | response | conditions | array of string |  | Conditions (IF), e.g.
AccessService | setVisualAccessRule | response | consequences | array of string |  | Actions performed on the decision, e.g.
AccessService | setVisualAccessRule | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | setVisualDynamicPolicy | request | conditionExpression | string | yes | Condition tree over catalogue attributes using AND, OR, NOT, IN and BETWEEN, e.g.
AccessService | setVisualDynamicPolicy | request | name | string | yes | e.g.
AccessService | setVisualDynamicPolicy | request | policyId | string | yes
AccessService | setVisualDynamicPolicy | request | result | enum (allow, deny, review, requireId, requireBiometric, requireCompanion, requireSupervisor) | yes | Decision the policy returns when its condition holds
AccessService | setVisualDynamicPolicy | request | priority | integer
AccessService | setVisualDynamicPolicy | request | status | enum (active, inactive) |  | inactive switches the policy off at once; active on a new or inactive policy submits it for approval (pendingApproval) (decided 29 September, writers pass) (default active)
AccessService | setVisualDynamicPolicy | request | validFrom | string (date-time) |  | Start of validity; null for at once (decided 29 September, writers pass) (nullable)
AccessService | setVisualDynamicPolicy | request | validTo | string (date-time) |  | End of validity: after it a timer moves the policy to expired (decided 29 September, writers pass) (nullable)
AccessService | setVisualDynamicPolicy | response | conditionExpression | string | yes | Condition tree over catalogue attributes using AND, OR, NOT, IN and BETWEEN, e.g.
AccessService | setVisualDynamicPolicy | response | name | string | yes | e.g.
AccessService | setVisualDynamicPolicy | response | policyId | string | yes
AccessService | setVisualDynamicPolicy | response | result | enum (allow, deny, review, requireId, requireBiometric, requireCompanion, requireSupervisor) | yes | Decision the policy returns when its condition holds
AccessService | setVisualDynamicPolicy | response | priority | integer
AccessService | setVisualDynamicPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | setWalletAutoReloadSetting | request | walletId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | request | subjectId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | request | enabled | boolean | yes
WalletService | setWalletAutoReloadSetting | request | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | request | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | request | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | request | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | request | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | request | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | request | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | request | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | request | paymentTokenId | string (uuid) |  | (nullable)
WalletService | setWalletAutoReloadSetting | request | maximumPerDay | integer |  | (min 1; nullable)
WalletService | setWalletAutoReloadSetting | request | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | setWalletAutoReloadSetting | request | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | setWalletAutoReloadSetting | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | setWalletAutoReloadSetting | response | walletId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | response | subjectId | string (uuid) |  | (read-only)
WalletService | setWalletAutoReloadSetting | response | enabled | boolean | yes
WalletService | setWalletAutoReloadSetting | response | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | response | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | response | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | response | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | response | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletAutoReloadSetting | response | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletAutoReloadSetting | response | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletAutoReloadSetting | response | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletAutoReloadSetting | response | paymentTokenId | string (uuid) |  | (nullable)
WalletService | setWalletAutoReloadSetting | response | maximumPerDay | integer |  | (min 1; nullable)
WalletService | setWalletAutoReloadSetting | response | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | setWalletAutoReloadSetting | response | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | setWalletAutoReloadSetting | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | setWalletAutoReloadSetting | param (path) | walletId | string (uuid) | yes
WalletService | setWalletAutoReloadSetting | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | setWalletAutoReloadSetting | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | setWalletFundingRules | request | walletTypeId | string (uuid) |  | (nullable)
WalletService | setWalletFundingRules | request | minimumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | minimumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | minimumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | minimumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | maximumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | maximumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | maximumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | maximumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | presetAmounts | array of Money
WalletService | setWalletFundingRules | request | presetAmounts[].amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | presetAmounts[].currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | presetAmounts[].scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | allowedChannels | array of string
WalletService | setWalletFundingRules | request | allowedFundingSources | array of enum (card, cash, bankTransfer, voucher, corporateAccount, loyaltyConversion)
WalletService | setWalletFundingRules | request | bonusRules | array of object |  | Board 2.3.
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | bonusRules[].minimumAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | bonusRules[].bonusAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | bonusRules[].bonusPercent | number |  | (nullable)
WalletService | setWalletFundingRules | request | bonusRules[].bonusCreditTypeId | string (uuid)
WalletService | setWalletFundingRules | request | bonusRules[].validFrom | string (date) |  | (nullable)
WalletService | setWalletFundingRules | request | bonusRules[].validTo | string (date) |  | (nullable)
WalletService | setWalletFundingRules | request | autoReload | object |  | Board 2.5, matrix 4.3.28.
WalletService | setWalletFundingRules | request | autoReload.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | autoReload.thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | autoReload.reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | autoReload.reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | autoReload.reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | autoReload.reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | autoReload.maximumPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | request | recurringFunding | object |  | Board 2.6, matrix 4.3.29 — *"distinct from auto-reload"*.
WalletService | setWalletFundingRules | request | recurringFunding.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | request | recurringFunding.cadence | enum (daily, weekly, monthly)
WalletService | setWalletFundingRules | request | recurringFunding.amount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | recurringFunding.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | recurringFunding.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | recurringFunding.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | recurringFunding.dayOfWeek | string |  | (nullable)
WalletService | setWalletFundingRules | request | recurringFunding.dayOfMonth | integer |  | (nullable)
WalletService | setWalletFundingRules | request | approvalAboveAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | approvalAboveAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | approvalAboveAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | approvalAboveAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | velocityLimits | object |  | A fraud control, not a commercial one.
WalletService | setWalletFundingRules | request | velocityLimits.maxTransactionsPerHour | integer |  | (nullable)
WalletService | setWalletFundingRules | request | velocityLimits.maxTransactionsPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerDay.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | request | velocityLimits.maxAmountPerMonth.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | request | scopePath | string
WalletService | setWalletFundingRules | response | walletTypeId | string (uuid) |  | (nullable)
WalletService | setWalletFundingRules | response | minimumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | minimumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | minimumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | minimumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | maximumTopUp | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | maximumTopUp.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | maximumTopUp.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | maximumTopUp.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | presetAmounts | array of Money
WalletService | setWalletFundingRules | response | presetAmounts[].amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | presetAmounts[].currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | presetAmounts[].scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | allowedChannels | array of string
WalletService | setWalletFundingRules | response | allowedFundingSources | array of enum (card, cash, bankTransfer, voucher, corporateAccount, loyaltyConversion)
WalletService | setWalletFundingRules | response | bonusRules | array of object |  | Board 2.3.
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | bonusRules[].minimumAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | bonusRules[].bonusAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | bonusRules[].bonusPercent | number |  | (nullable)
WalletService | setWalletFundingRules | response | bonusRules[].bonusCreditTypeId | string (uuid)
WalletService | setWalletFundingRules | response | bonusRules[].validFrom | string (date) |  | (nullable)
WalletService | setWalletFundingRules | response | bonusRules[].validTo | string (date) |  | (nullable)
WalletService | setWalletFundingRules | response | autoReload | object |  | Board 2.5, matrix 4.3.28.
WalletService | setWalletFundingRules | response | autoReload.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | autoReload.thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | autoReload.reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | autoReload.reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | autoReload.reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | autoReload.reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | autoReload.maximumPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | response | recurringFunding | object |  | Board 2.6, matrix 4.3.29 — *"distinct from auto-reload"*.
WalletService | setWalletFundingRules | response | recurringFunding.enabled | boolean |  | (default False)
WalletService | setWalletFundingRules | response | recurringFunding.cadence | enum (daily, weekly, monthly)
WalletService | setWalletFundingRules | response | recurringFunding.amount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | recurringFunding.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | recurringFunding.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | recurringFunding.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | recurringFunding.dayOfWeek | string |  | (nullable)
WalletService | setWalletFundingRules | response | recurringFunding.dayOfMonth | integer |  | (nullable)
WalletService | setWalletFundingRules | response | approvalAboveAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | approvalAboveAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | approvalAboveAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | approvalAboveAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | velocityLimits | object |  | A fraud control, not a commercial one.
WalletService | setWalletFundingRules | response | velocityLimits.maxTransactionsPerHour | integer |  | (nullable)
WalletService | setWalletFundingRules | response | velocityLimits.maxTransactionsPerDay | integer |  | (nullable)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerDay.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | setWalletFundingRules | response | velocityLimits.maxAmountPerMonth.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | setWalletFundingRules | response | scopePath | string
WalletService | setWalletFundingRules | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | setWalletFundingRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | setWalletRefundPolicy | request | defaultDestination | enum (originalTender, wallet, guestChoice)
WalletService | setWalletRefundPolicy | request | walletRefundCreditTypeId | string (uuid)
WalletService | setWalletRefundPolicy | request | restoreToOriginalLots | boolean |  | (default True)
WalletService | setWalletRefundPolicy | request | restoreOriginalExpiry | boolean |  | Refunding into a new lot with a fresh expiry is a gift. (default True)
WalletService | setWalletRefundPolicy | request | walletRefundBonusPercent | number |  | An incentive to take the refund as credit rather than to a card. (nullable)
WalletService | setWalletRefundPolicy | request | scopePath | string
WalletService | setWalletRefundPolicy | response | defaultDestination | enum (originalTender, wallet, guestChoice)
WalletService | setWalletRefundPolicy | response | walletRefundCreditTypeId | string (uuid)
WalletService | setWalletRefundPolicy | response | restoreToOriginalLots | boolean |  | (default True)
WalletService | setWalletRefundPolicy | response | restoreOriginalExpiry | boolean |  | Refunding into a new lot with a fresh expiry is a gift. (default True)
WalletService | setWalletRefundPolicy | response | walletRefundBonusPercent | number |  | An incentive to take the refund as credit rather than to a card. (nullable)
WalletService | setWalletRefundPolicy | response | scopePath | string
WalletService | setWalletRefundPolicy | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
WalletService | setWalletRefundPolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | settleWalletAtExit | request | action | enum (collect, refund, waive) | yes
WalletService | settleWalletAtExit | request | method | enum (card, cash, storedCard, originalPayment) |  | How money is collected or refunded.
WalletService | settleWalletAtExit | request | paymentTokenId | string (uuid) |  | (nullable)
WalletService | settleWalletAtExit | request | reason | string |  | Required with waive. (max length 500; nullable)
WalletService | settleWalletAtExit | response | id | string (uuid) | yes
WalletService | settleWalletAtExit | response | walletId | string (uuid) | yes
WalletService | settleWalletAtExit | response | action | enum (collect, refund, waive) | yes
WalletService | settleWalletAtExit | response | method | enum (card, cash, storedCard, originalPayment) |  | (nullable)
WalletService | settleWalletAtExit | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | settleWalletAtExit | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | settleWalletAtExit | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | settleWalletAtExit | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | settleWalletAtExit | response | balanceBefore | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | settleWalletAtExit | response | balanceBefore.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | settleWalletAtExit | response | balanceBefore.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | settleWalletAtExit | response | balanceBefore.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | settleWalletAtExit | response | paymentId | string (uuid) |  | (nullable)
WalletService | settleWalletAtExit | response | refundId | string (uuid) |  | (nullable)
WalletService | settleWalletAtExit | response | walletTransactionId | string |  | (nullable)
WalletService | settleWalletAtExit | response | reason | string |  | (nullable)
WalletService | settleWalletAtExit | response | settledByPrincipalId | string (uuid) |  | (nullable)
WalletService | settleWalletAtExit | response | settledAt | string (date-time) | yes
WalletService | settleWalletAtExit | response | scopePath | string |  | (read-only)
WalletService | settleWalletAtExit | param (path) | walletId | string (uuid) | yes
WalletService | settleWalletAtExit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | shareEntitlement | request | toSubjectId | string (uuid) | yes
OrderService | shareEntitlement | request | validUntil | string (date-time) |  | (nullable)
OrderService | shareEntitlement | response | id | string (uuid) | yes
OrderService | shareEntitlement | response | entitlementId | string (uuid) | yes
OrderService | shareEntitlement | response | toSubjectId | string (uuid) | yes | The guest it is shared with.
OrderService | shareEntitlement | response | validFrom | string (date-time)
OrderService | shareEntitlement | response | validUntil | string (date-time) |  | Null means until revoked or until the entitlement itself ends. (nullable)
OrderService | shareEntitlement | response | revokedAt | string (date-time) |  | (nullable)
OrderService | shareEntitlement | response | status | enum (active, revoked, expired) | yes
OrderService | shareEntitlement | param (path) | entitlementId | string (uuid) | yes
OrderService | shareEntitlement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | signCorrectiveAction | request | actionTaken | string | yes
FnbService | signCorrectiveAction | request | disposal | enum (none, discarded, reworked, quarantined, returned)
FnbService | signCorrectiveAction | response | id | string (uuid) | yes
FnbService | signCorrectiveAction | response | raisedAt | string (date-time) | yes
FnbService | signCorrectiveAction | response | raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | signCorrectiveAction | response | source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | signCorrectiveAction | response | sourceRef | string (uuid) |  | (nullable)
FnbService | signCorrectiveAction | response | severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | signCorrectiveAction | response | actionTaken | string |  | (nullable)
FnbService | signCorrectiveAction | response | disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | signCorrectiveAction | response | status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | signCorrectiveAction | response | signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | signCorrectiveAction | response | signedAt | string (date-time) |  | (nullable)
FnbService | signCorrectiveAction | response | escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | signCorrectiveAction | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | signCorrectiveAction | param (path) | actionId | string (uuid) | yes
FnbService | signCorrectiveAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | simulateAiGovernancePolicy | request | from | string (date-time) |  | (nullable)
AiService | simulateAiGovernancePolicy | request | to | string (date-time) |  | (nullable)
AiService | simulateAiGovernancePolicy | request | capabilityKeys | array of string
AiService | simulateAiGovernancePolicy | response | evaluated | integer | yes
AiService | simulateAiGovernancePolicy | response | wouldChange | integer
AiService | simulateAiGovernancePolicy | response | byOutcome | object |  | Counts per outcome, current against draft.
AiService | simulateAiGovernancePolicy | response | examples | array of object
AiService | simulateAiGovernancePolicy | response | examples[].decisionRecordId | string (uuid)
AiService | simulateAiGovernancePolicy | response | examples[].current | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) |  | What the governance decision point returns (design 3.8, AIC-166).
AiService | simulateAiGovernancePolicy | response | examples[].draft | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) |  | What the governance decision point returns (design 3.8, AIC-166).
AiService | simulateAiGovernancePolicy | response | examples[].capabilityKey | string
AiService | simulateAiGovernancePolicy | param (path) | versionId | string (uuid) | yes
AiService | simulateAiGovernancePolicy | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | stopCampaign | request | reason | string | yes | (min length 3; max length 500)
MarketingService | stopCampaign | response | name | string | yes | (max length 200)
MarketingService | stopCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | stopCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | stopCampaign | response | venueId | string (uuid)
MarketingService | stopCampaign | response | segmentId | string (uuid) | yes
MarketingService | stopCampaign | response | content | CampaignContent | yes
MarketingService | stopCampaign | response | content.templateId | string (uuid) | yes
MarketingService | stopCampaign | response | content.subjectOverride | object
MarketingService | stopCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | stopCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | stopCampaign | response | trigger | CampaignTrigger
MarketingService | stopCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | stopCampaign | response | trigger.delayHours | integer
MarketingService | stopCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | stopCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | stopCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | stopCampaign | response | trigger.conditions[].value | object
MarketingService | stopCampaign | response | trigger.conditions[].values | array of object
MarketingService | stopCampaign | response | scheduledFor | string (date-time)
MarketingService | stopCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | stopCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | stopCampaign | response | sendWindow.startTime | string
MarketingService | stopCampaign | response | sendWindow.endTime | string
MarketingService | stopCampaign | response | sendWindow.timeZone | string
MarketingService | stopCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | stopCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | stopCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | stopCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | stopCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | stopCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | stopCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | stopCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | stopCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | stopCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | stopCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | stopCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | stopCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | stopCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | stopCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | stopCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | stopCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | stopCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | stopCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | stopCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | stopCampaign | response | id | string (uuid) | yes
MarketingService | stopCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | stopCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | stopCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | stopCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | stopCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | stopCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | stopCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | stopCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | stopCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | stopCampaign | response | isPaused | boolean
MarketingService | stopCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | stopCampaign | response | createdAt | string (date-time) | yes
MarketingService | stopCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | stopCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | stopCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | stopCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | stopCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | storePaymentToken | request | providerId | string (uuid) | yes
OrderService | storePaymentToken | request | providerToken | string (password) | yes
OrderService | storePaymentToken | request | consentPurposeId | string (uuid) | yes
OrderService | storePaymentToken | request | setDefault | boolean |  | (default False)
OrderService | storePaymentToken | response | id | string (uuid) | yes
OrderService | storePaymentToken | response | subjectId | string (uuid) | yes
OrderService | storePaymentToken | response | providerId | string (uuid) | yes
OrderService | storePaymentToken | response | token | string (password) | yes | Write-only, never returned.
OrderService | storePaymentToken | response | method | string
OrderService | storePaymentToken | response | maskedIdentifier | string |  | What a guest sees — the last four digits, the card brand.
OrderService | storePaymentToken | response | expiresAt | string (date) |  | (nullable)
OrderService | storePaymentToken | response | isDefault | boolean | yes
OrderService | storePaymentToken | response | consentPurposeId | string (uuid) |  | Storing a card for future use is a purpose a guest consents to, separate from the payment they are making now. (nullable)
OrderService | storePaymentToken | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | submitGuestIdentityDocument | request | documentKind | enum (passport, emiratesId, nationalId, drivingLicence, residencePermit, other) | yes | The vocabulary of pii.subject_document.kind.
IdentityService | submitGuestIdentityDocument | request | documentNumber | string (password) | yes | Write-only, never returned. (max length 64)
IdentityService | submitGuestIdentityDocument | request | issuingCountry | string |  | (pattern ^[A-Z]{2}$; nullable)
IdentityService | submitGuestIdentityDocument | request | expiresOn | string (date) |  | (nullable)
IdentityService | submitGuestIdentityDocument | request | documentAssetId | string (uuid) | yes | The uploaded scan or photo of the document.
IdentityService | submitGuestIdentityDocument | request | selfieAssetId | string (uuid) |  | A live photo for the reviewer to compare, where the policy asks for one. (nullable)
IdentityService | submitGuestIdentityDocument | request | reason | enum (policyRequired, ageRestrictedPurchase, residentPricing, accountRecovery) |  | What the guest is verifying for; the review queue shows it. (default policyRequired)
IdentityService | submitGuestIdentityDocument | response | id | string (uuid) | yes | (read-only)
IdentityService | submitGuestIdentityDocument | response | subjectId | string (uuid) | yes
IdentityService | submitGuestIdentityDocument | response | subjectDocumentId | string (uuid) |  | The pii.subject_document row submitted.
IdentityService | submitGuestIdentityDocument | response | documentKind | enum (passport, emiratesId, nationalId, drivingLicence, residencePermit, other)
IdentityService | submitGuestIdentityDocument | response | documentNumberLast4 | string |  | (max length 4; read-only; nullable)
IdentityService | submitGuestIdentityDocument | response | reason | enum (policyRequired, ageRestrictedPurchase, residentPricing, accountRecovery)
IdentityService | submitGuestIdentityDocument | response | status | enum (pending, verified, rejected, resubmissionRequested) | yes | (read-only)
IdentityService | submitGuestIdentityDocument | response | method | enum (manualReview, documentScanner, provider) |  | (read-only; nullable)
IdentityService | submitGuestIdentityDocument | response | decisionReason | string |  | (max length 300; read-only; nullable)
IdentityService | submitGuestIdentityDocument | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
IdentityService | submitGuestIdentityDocument | response | submittedAt | string (date-time) | yes | (read-only)
IdentityService | submitGuestIdentityDocument | response | decidedAt | string (date-time) |  | (read-only; nullable)
IdentityService | submitGuestIdentityDocument | response | documentImageDeletedAt | string (date-time) |  | When the scan (and any selfie) was deleted under the policy's retention. (read-only; nullable)
IdentityService | submitGuestIdentityDocument | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | submitReview | request | id | string (uuid) | yes
MarketingService | submitReview | request | subjectId | string (uuid)
MarketingService | submitReview | request | venueId | string (uuid) | yes
MarketingService | submitReview | request | relatedOrderId | string
MarketingService | submitReview | request | rating | integer | yes | (min 1; max 5)
MarketingService | submitReview | request | body | string |  | (max length 5000)
MarketingService | submitReview | request | aspects | array of enum (exhibitions, staff, cleanliness, food, value) |  | Aspect chips — the closed set the description always named.
MarketingService | submitReview | request | recordedAt | string (date-time) | yes
MarketingService | submitReview | response | id | string (uuid) | yes
MarketingService | submitReview | response | subjectId | string (uuid)
MarketingService | submitReview | response | venueId | string (uuid) | yes
MarketingService | submitReview | response | relatedOrderId | string
MarketingService | submitReview | response | rating | integer | yes | (min 1; max 5)
MarketingService | submitReview | response | body | string |  | (max length 5000)
MarketingService | submitReview | response | aspects | array of enum (exhibitions, staff, cleanliness, food, value) |  | Aspect chips — the closed set the description always named.
MarketingService | submitReview | response | recordedAt | string (date-time) | yes
MarketingService | submitReview | response | status | enum (pendingModeration, published, hidden, rejected) | yes
MarketingService | submitReview | response | response | string |  | (nullable)
MarketingService | submitReview | response | responseIsPublic | boolean
MarketingService | submitReview | response | respondedByPrincipalId | string (uuid) |  | (nullable)
MarketingService | submitReview | response | openedCaseId | string |  | Case raised automatically where the rating fell below the venue's threshold. (nullable)
MarketingService | submitReview | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | suggestGuidedChoice | request | trigger | enum (manual) |  | (default manual)
AiService | suggestGuidedChoice | request | locales | array of string
AiService | suggestGuidedChoice | response | id | string (uuid) |  | (read-only)
AiService | suggestGuidedChoice | response | venueId | string (uuid) | yes
AiService | suggestGuidedChoice | response | trigger | enum (productsUploaded, mappedProductWithdrawn, productsUncovered, manual) | yes
AiService | suggestGuidedChoice | response | status | enum (running, proposed, noSuggestion, failed, superseded) | yes | (read-only)
AiService | suggestGuidedChoice | response | productCount | integer |  | (min 0; read-only)
AiService | suggestGuidedChoice | response | questions | array of object |  | The questions chosen, in the order asked. (read-only)
AiService | suggestGuidedChoice | response | questions[].attribute | string |  | The catalogue attribute asked about: audience, level, minimum height or age, duration, price band, format, language.
AiService | suggestGuidedChoice | response | questions[].order | integer |  | (min 1)
AiService | suggestGuidedChoice | response | questions[].split | object |  | How evenly it divides the bookable products: products per answer.
AiService | suggestGuidedChoice | response | questions[].droppedBecause | string |  | Set where an attribute was considered and dropped (an answer would leave nothing bookable). (nullable)
AiService | suggestGuidedChoice | response | questions[].answers | array of object
AiService | suggestGuidedChoice | response | questions[].answers[].value | string
AiService | suggestGuidedChoice | response | questions[].answers[].leadsTo | enum (product, category, flow)
AiService | suggestGuidedChoice | response | questions[].answers[].targetRef | string
AiService | suggestGuidedChoice | response | wordingSource | enum (model, attributeNames) |  | Where the text came from. (read-only)
AiService | suggestGuidedChoice | response | modelVersion | string |  | (read-only; nullable)
AiService | suggestGuidedChoice | response | promptTemplateVersion | string |  | (read-only; nullable)
AiService | suggestGuidedChoice | response | guidedChoiceId | string (uuid) |  | The white-label draft GuidedChoice it produced. (read-only; nullable)
AiService | suggestGuidedChoice | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | suggestGuidedChoice | response | createdAt | string (date-time) |  | (read-only)
AiService | suggestGuidedChoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | suggestGuidedChoice | param (path) | venueId | string (uuid) | yes
AiService | suggestGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | suspendShift | request | reason | string |  | (max length 200)
OrderService | suspendShift | request | recordedAt | string (date-time) | yes
OrderService | suspendShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | suspendShift | response | workstationId | string (uuid) | yes
OrderService | suspendShift | response | venueId | string (uuid) | yes
OrderService | suspendShift | response | scopePath | string | yes
OrderService | suspendShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | suspendShift | response | principalDisplayName | string
OrderService | suspendShift | response | incidents | array of object |  | BL-097.
OrderService | suspendShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | suspendShift | response | incidents[].at | string (date-time)
OrderService | suspendShift | response | incidents[].principalId | string (uuid)
OrderService | suspendShift | response | incidents[].note | string |  | (nullable)
OrderService | suspendShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | suspendShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | suspendShift | response | depositBoxCode | string |  | (nullable)
OrderService | suspendShift | response | bagNumber | string |  | (nullable)
OrderService | suspendShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | suspendShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | suspendShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | suspendShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | suspendShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | suspendShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | suspendShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | suspendShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | suspendShift | response | openedAt | string (date-time) | yes
OrderService | suspendShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | suspendShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | suspendShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | suspendShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | suspendShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | suspendShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | suspendShift | response | approvals | array of object
OrderService | suspendShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | suspendShift | response | approvals[].principalId | string (uuid) | yes
OrderService | suspendShift | response | approvals[].at | string (date-time) | yes
OrderService | suspendShift | response | approvals[].reason | string
OrderService | suspendShift | param (path) | shiftId | string (uuid) | yes
OrderService | suspendShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | suspendTenant | request | mode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) | yes | Access validation continues under every mode.
PlatformService | suspendTenant | request | reason | string | yes | (min length 3; max length 500)
PlatformService | suspendTenant | request | effectiveAt | string (date-time)
PlatformService | suspendTenant | request | noticeMessage | LocalisedText
PlatformService | suspendTenant | response | id | string (uuid) | yes
PlatformService | suspendTenant | response | code | string | yes
PlatformService | suspendTenant | response | name | string | yes
PlatformService | suspendTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | suspendTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | suspendTenant | response | suspensionReason | string |  | (nullable)
PlatformService | suspendTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | suspendTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | suspendTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | suspendTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | suspendTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | suspendTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | suspendTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | suspendTenant | response | planName | string |  | (nullable)
PlatformService | suspendTenant | response | cellCount | integer
PlatformService | suspendTenant | response | venueCount | integer
PlatformService | suspendTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | suspendTenant | response | billingEmail | string
PlatformService | suspendTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | suspendTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | suspendTenant | response | createdAt | string (date-time) | yes
PlatformService | suspendTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | suspendTenant | param (path) | tenantId | string (uuid) | yes
PlatformService | suspendTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | syncOrders | request | deviceId | string (uuid) | yes
OrderService | syncOrders | request | orders | array of OfflineOrder | yes | (min items 1; max items 200)
OrderService | syncOrders | request | orders[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | syncOrders | request | orders[].venueId | string (uuid) | yes
OrderService | syncOrders | request | orders[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
OrderService | syncOrders | request | orders[].shiftId | string (uuid)
OrderService | syncOrders | request | orders[].subjectId | string (uuid) |  | Null for an anonymous sale. (nullable)
OrderService | syncOrders | request | orders[].guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
OrderService | syncOrders | request | orders[].catalogueBundleVersion | string |  | The bundle the client priced from.
OrderService | syncOrders | request | orders[].lines | array of CreateOrderLine | yes | (min items 1)
OrderService | syncOrders | request | orders[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | syncOrders | request | orders[].lines[].variantId | string (uuid) | yes
OrderService | syncOrders | request | orders[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | syncOrders | request | orders[].lines[].performanceId | string (uuid)
OrderService | syncOrders | request | orders[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | syncOrders | request | orders[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | syncOrders | request | orders[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | syncOrders | request | orders[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | syncOrders | request | orders[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | syncOrders | request | orders[].lines[].quantity | integer | yes | (min 1)
OrderService | syncOrders | request | orders[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | syncOrders | request | orders[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | syncOrders | request | orders[].lines[].holderName | string |  | (nullable)
OrderService | syncOrders | request | orders[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | syncOrders | request | orders[].recordedAt | string (date-time) | yes
OrderService | syncOrders | request | orders[].sequence | integer | yes | Monotonic per device. (min 1)
OrderService | syncOrders | request | orders[].payments | array of CreatePaymentRequest | yes
OrderService | syncOrders | request | orders[].payments[].id | string (uuid) | yes | Client-generated UUIDv7 of the payment, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | syncOrders | request | orders[].payments[].orderId | string (uuid) | yes
OrderService | syncOrders | request | orders[].payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | syncOrders | request | orders[].payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | syncOrders | request | orders[].payments[].tenderCurrency | string |  | The currency the guest handed over, where it is not the venue's — becomes Payment.tenderCurrency. (pattern ^[A-Z]{3}$; nullable)
OrderService | syncOrders | request | orders[].payments[].tenderAmount | object |  | What the guest handed over, in tenderCurrency — becomes Payment.tenderAmount, one name for one concept (renamed from tenderedAmount on 26 September).
OrderService | syncOrders | request | orders[].payments[].walletAuthorisationId | string |  | Cross-cell wallet hold, where the guest's home cell is elsewhere. (nullable)
OrderService | syncOrders | request | orders[].payments[].walletHoldId | string (uuid) |  | For a wallet tender, the hold wallet.holdWalletFunds placed (SD-027). (nullable)
OrderService | syncOrders | request | orders[].payments[].returnUrl | string (uri) |  | Where the provider returns the guest after a 3-D Secure challenge or hosted page (SD-034). (nullable)
OrderService | syncOrders | request | orders[].payments[].terminalId | string (uuid) |  | The card terminal to instruct, for a card payment at a till (ECR flow, SD-034). (nullable)
OrderService | syncOrders | request | orders[].payments[].deviceId | string (uuid) |  | (nullable)
OrderService | syncOrders | request | orders[].payments[].recordedAt | string (date-time) | yes
OrderService | syncOrders | response | accepted | integer | yes
OrderService | syncOrders | response | stoppedAtSequence | integer |  | First entry that hit a transient failure (SD-028, 29 September): a refusal on the merits no longer stops the batch. (nullable)
OrderService | syncOrders | response | results | array of object | yes
OrderService | syncOrders | response | results[].id | string (uuid) | yes | The OfflineOrder.id this result is about.
OrderService | syncOrders | response | results[].sequence | integer | yes
OrderService | syncOrders | response | results[].status | enum (accepted, duplicate, rejected, blockedByRejection) | yes | rejected: refused on its merits and quarantined in sync.rejection; the batch continues.
OrderService | syncOrders | response | results[].orderNumber | string |  | (nullable)
OrderService | syncOrders | response | results[].priceVariance | object |  | Posted to the variance account.
OrderService | syncOrders | response | results[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | syncOrders | response | results[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | syncOrders | response | results[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | syncOrders | response | results[].varianceExceedsThreshold | boolean |  | True when review is required per the venue's variance threshold.
OrderService | syncOrders | response | results[].rejectionId | string |  | For a rejected or blockedByRejection entry, the sync.rejection row it was quarantined into (SD-028). (nullable)
OrderService | syncOrders | response | results[].error | Problem |  | RFC 9457 problem details.
OrderService | syncOrders | response | results[].error.type | string (uri) | yes | The problem type URI, https://api.ticvai.com/problems/<slug>.
OrderService | syncOrders | response | results[].error.title | string | yes
OrderService | syncOrders | response | results[].error.status | integer | yes
OrderService | syncOrders | response | results[].error.detail | string
OrderService | syncOrders | response | results[].error.instance | string
OrderService | syncOrders | response | results[].error.traceId | string
OrderService | syncOrders | response | results[].error.errors | array of object
OrderService | syncOrders | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | terminateTenant | request | reason | string | yes | (min length 3; max length 1000)
PlatformService | terminateTenant | request | retentionDays | integer | yes | (min 30; max 2555)
PlatformService | terminateTenant | request | confirmTenantCode | string | yes | Must match the tenant's code.
PlatformService | terminateTenant | response | tenantId | string (uuid) | yes
PlatformService | terminateTenant | response | scheduledAt | string (date-time) | yes
PlatformService | terminateTenant | response | retentionUntil | string (date-time) | yes | Cells are destroyed after this.
PlatformService | terminateTenant | response | isReversible | boolean | yes
PlatformService | terminateTenant | response | dataExportUrl | string |  | (nullable)
PlatformService | terminateTenant | response | requestedByPrincipalId | string (uuid)
PlatformService | terminateTenant | param (path) | tenantId | string (uuid) | yes
PlatformService | terminateTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | transferGameCard | request | targetCardCode | string | yes
VenueOpsService | transferGameCard | request | reason | enum (damaged, lost, faulty, guestRequest, upgrade) | yes
VenueOpsService | transferGameCard | request | note | string |  | (max length 500)
VenueOpsService | transferGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | transferGameCard | response | kind | string
VenueOpsService | transferGameCard | response | venueId | string (uuid) | yes
VenueOpsService | transferGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | transferGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | transferGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | transferGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | transferGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | transferGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | transferGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | transferGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | transferGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | transferGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | transferGameCard | param (path) | cardCode | string | yes
VenueOpsService | transferGameCard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | transferOrderTickets | request | ticketIds | array of string (uuid) | yes | The entitlements to hand over. (min items 1)
OrderService | transferOrderTickets | request | recipient | object | yes
OrderService | transferOrderTickets | request | recipient.channel | enum (email, sms, whatsapp) | yes
OrderService | transferOrderTickets | request | recipient.address | string | yes
OrderService | transferOrderTickets | request | message | string |  | (max length 500)
OrderService | transferOrderTickets | response | id | string (uuid) | yes
OrderService | transferOrderTickets | response | orderId | string (uuid) | yes
OrderService | transferOrderTickets | response | ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | transferOrderTickets | response | fromSubjectId | string (uuid)
OrderService | transferOrderTickets | response | toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | transferOrderTickets | response | recipientAddressMasked | string
OrderService | transferOrderTickets | response | status | enum (offered, claimed, expired, cancelled) | yes
OrderService | transferOrderTickets | response | claimUrl | string |  | (nullable)
OrderService | transferOrderTickets | response | claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | transferOrderTickets | response | offeredAt | string (date-time) | yes
OrderService | transferOrderTickets | response | claimedAt | string (date-time) |  | (nullable)
OrderService | transferOrderTickets | response | expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | transferOrderTickets | param (path) | orderId | string (uuid) | yes
OrderService | transferOrderTickets | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WalletService | transferWalletBalance | request | toSubjectId | string (uuid) |  | The recipient guest.
WalletService | transferWalletBalance | request | toWalletId | string (uuid) |  | The receiving wallet, named outright.
WalletService | transferWalletBalance | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | transferWalletBalance | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | transferWalletBalance | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | transferWalletBalance | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | transferWalletBalance | request | message | string |  | (max length 140; nullable)
WalletService | transferWalletBalance | response | id | string | yes
WalletService | transferWalletBalance | response | walletId | string (uuid) |  | The wallet this movement is on (SD-027, 29 September).
WalletService | transferWalletBalance | response | walletHoldId | string (uuid) |  | The hold a spend settled, where it came through holdWalletFunds. (nullable)
WalletService | transferWalletBalance | response | kind | WalletTransactionKind: enum (topUp, spend, refund, adjustment, bonus, expiry, transfer) | yes
WalletService | transferWalletBalance | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | transferWalletBalance | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | transferWalletBalance | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | transferWalletBalance | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | transferWalletBalance | response | balanceAfter | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | transferWalletBalance | response | balanceAfter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | transferWalletBalance | response | balanceAfter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | transferWalletBalance | response | balanceAfter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | transferWalletBalance | response | orderId | string |  | (nullable)
WalletService | transferWalletBalance | response | venueId | string (uuid) |  | (nullable)
WalletService | transferWalletBalance | response | reason | string |  | (nullable)
WalletService | transferWalletBalance | response | principalId | string (uuid) |  | (nullable)
WalletService | transferWalletBalance | response | recordedAt | string (date-time) | yes
WalletService | transferWalletBalance | param (path) | walletId | string (uuid) | yes
WalletService | transferWalletBalance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | transmitEInvoices | request | legalEntityId | string (uuid) | yes
LedgerService | transmitEInvoices | request | documentIds | array of string (uuid) |  | Tax invoice or credit memo ids.
LedgerService | transmitEInvoices | request | issuedFrom | string (date)
LedgerService | transmitEInvoices | request | issuedTo | string (date)
LedgerService | transmitEInvoices | response | queued | integer
LedgerService | transmitEInvoices | response | skippedAlreadyAccepted | integer
LedgerService | transmitEInvoices | response | transmissions | array of FinEInvoiceTransmission
LedgerService | transmitEInvoices | response | transmissions[].id | string (uuid) | yes
LedgerService | transmitEInvoices | response | transmissions[].documentKind | enum (taxInvoice, creditMemo) | yes
LedgerService | transmitEInvoices | response | transmissions[].documentId | string (uuid) | yes
LedgerService | transmitEInvoices | response | transmissions[].documentNumber | string
LedgerService | transmitEInvoices | response | transmissions[].legalEntityId | string (uuid) | yes
LedgerService | transmitEInvoices | response | transmissions[].providerId | string (uuid) |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].mode | enum (test, live)
LedgerService | transmitEInvoices | response | transmissions[].status | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) | yes | 6.1.1.
LedgerService | transmitEInvoices | response | transmissions[].payloadHash | string |  | SHA-256 of the document as sent, so a resend can be shown to be the same document. (nullable)
LedgerService | transmitEInvoices | response | transmissions[].providerMessageId | string |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].attempt | integer |  | (min 1)
LedgerService | transmitEInvoices | response | transmissions[].errorCodes | array of string
LedgerService | transmitEInvoices | response | transmissions[].errorMessage | string |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].sentAt | string (date-time) |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].answeredAt | string (date-time) |  | (nullable)
LedgerService | transmitEInvoices | response | transmissions[].createdAt | string (date-time) | yes
LedgerService | transmitEInvoices | response | transmissions[].scopePath | string |  | (read-only)
LedgerService | transmitEInvoices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | unpublishGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | unpublishGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | unpublishGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | unpublishGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | unpublishGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | unpublishGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | unpublishGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | unpublishGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | unpublishGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | unpublishGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | unpublishGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | unpublishGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | unpublishGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | unpublishGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | unpublishGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | unpublishGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | unpublishGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | unpublishGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | updateAccessPoint | request | name | string |  | (max length 200)
AccessService | updateAccessPoint | request | direction | Direction: enum (entry, exit, reentry, crossover)
AccessService | updateAccessPoint | request | antiPassbackEnabled | boolean
AccessService | updateAccessPoint | request | requiresExitBeforeReentry | boolean
AccessService | updateAccessPoint | request | isActive | boolean
AccessService | updateAccessPoint | request | driver | string |  | Driver identifier for the controller behind this access point.
AccessService | updateAccessPoint | response | id | string (uuid) | yes
AccessService | updateAccessPoint | response | code | string | yes
AccessService | updateAccessPoint | response | name | string | yes
AccessService | updateAccessPoint | response | venueId | string (uuid) | yes
AccessService | updateAccessPoint | response | scopePath | string
AccessService | updateAccessPoint | response | externalCredentialSources | object |  | BL-108.
AccessService | updateAccessPoint | response | scanAnomalyRules | object |  | BL-104.
AccessService | updateAccessPoint | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | updateAccessPoint | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | updateAccessPoint | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | updateAccessPoint | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | updateAccessPoint | response | antiPassbackEnabled | boolean
AccessService | updateAccessPoint | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | updateAccessPoint | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | updateAccessPoint | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | updateAccessPoint | response | geofence.latitude | number
AccessService | updateAccessPoint | response | geofence.longitude | number
AccessService | updateAccessPoint | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | updateAccessPoint | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | updateAccessPoint | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | updateAccessPoint | response | isActive | boolean | yes
AccessService | updateAccessPoint | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | updateAccessPoint | param (path) | accessPointId | string (uuid) | yes
AccessService | updateAccessPoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | updateAccount | request | code | string |  | Accepted only while the account has no entries. (max length 64; pattern ^[A-Za-z0-9._-]+$)
LedgerService | updateAccount | request | name | string |  | (max length 200)
LedgerService | updateAccount | request | externalCode | string |  | (max length 64)
LedgerService | updateAccount | request | isActive | boolean
LedgerService | updateAccount | request | isSuspense | boolean
LedgerService | updateAccount | request | subType | string |  | (nullable)
LedgerService | updateAccount | request | tags | array of string
LedgerService | updateAccount | request | notes | string |  | (nullable)
LedgerService | updateAccount | response | id | string (uuid) | yes
LedgerService | updateAccount | response | code | string | yes | (max length 64)
LedgerService | updateAccount | response | externalCode | string |  | Code in the client's own chart. (nullable)
LedgerService | updateAccount | response | isSuspense | boolean |  | 5.7.x. (default False)
LedgerService | updateAccount | response | subType | string |  | 5.7.27. (nullable)
LedgerService | updateAccount | response | tags | array of string |  | How a venue groups accounts for its own reporting.
LedgerService | updateAccount | response | notes | string |  | 5.7.27. (nullable)
LedgerService | updateAccount | response | name | string | yes | (max length 200)
LedgerService | updateAccount | response | type | AccountType: enum (asset, liability, equity, revenue, expense) | yes
LedgerService | updateAccount | response | parentId | string (uuid) |  | (nullable)
LedgerService | updateAccount | response | legalEntityId | string (uuid) | yes
LedgerService | updateAccount | response | currency | string |  | (pattern ^[A-Z]{3}$)
LedgerService | updateAccount | response | isPostable | boolean | yes | False for parent accounts, which aggregate only.
LedgerService | updateAccount | response | isActive | boolean | yes
LedgerService | updateAccount | response | balance | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | updateAccount | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | updateAccount | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | updateAccount | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | updateAccount | param (path) | accountId | string (uuid) | yes
LedgerService | updateAccount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | updateAdmissionRules | request | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | updateAdmissionRules | request | code | string | yes | (max length 64)
AccessService | updateAdmissionRules | request | perProductRules | object |  | BL-059.
AccessService | updateAdmissionRules | request | name | string | yes | (max length 200)
AccessService | updateAdmissionRules | request | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | updateAdmissionRules | request | closeMinutesAfter | integer | yes
AccessService | updateAdmissionRules | request | maxDurationMinutes | integer |  | (nullable)
AccessService | updateAdmissionRules | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | updateAdmissionRules | request | maxReentries | integer |  | (nullable)
AccessService | updateAdmissionRules | request | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | request | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | updateAdmissionRules | request | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | updateAdmissionRules | request | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | updateAdmissionRules | request | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | updateAdmissionRules | request | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | updateAdmissionRules | request | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | updateAdmissionRules | request | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | updateAdmissionRules | request | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | updateAdmissionRules | request | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | request | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | updateAdmissionRules | request | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | updateAdmissionRules | request | validity.from | string (date)
AccessService | updateAdmissionRules | request | validity.to | string (date) |  | Inclusive.
AccessService | updateAdmissionRules | request | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | updateAdmissionRules | request | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | updateAdmissionRules | request | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | updateAdmissionRules | request | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | updateAdmissionRules | request | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | updateAdmissionRules | request | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | updateAdmissionRules | request | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | updateAdmissionRules | request | crossover.sameDayOnly | boolean |  | (default True)
AccessService | updateAdmissionRules | request | crossover.differentDayAccess | boolean |  | (default False)
AccessService | updateAdmissionRules | request | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | updateAdmissionRules | request | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | request | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | request | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | updateAdmissionRules | request | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | updateAdmissionRules | request | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | updateAdmissionRules | request | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | updateAdmissionRules | request | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | updateAdmissionRules | request | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | updateAdmissionRules | request | scopePath | string |  | The partition key (ADR-0005).
AccessService | updateAdmissionRules | response | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | updateAdmissionRules | response | code | string | yes | (max length 64)
AccessService | updateAdmissionRules | response | perProductRules | object |  | BL-059.
AccessService | updateAdmissionRules | response | name | string | yes | (max length 200)
AccessService | updateAdmissionRules | response | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | updateAdmissionRules | response | closeMinutesAfter | integer | yes
AccessService | updateAdmissionRules | response | maxDurationMinutes | integer |  | (nullable)
AccessService | updateAdmissionRules | response | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | updateAdmissionRules | response | maxReentries | integer |  | (nullable)
AccessService | updateAdmissionRules | response | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | response | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | updateAdmissionRules | response | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | updateAdmissionRules | response | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | updateAdmissionRules | response | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | updateAdmissionRules | response | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | updateAdmissionRules | response | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | updateAdmissionRules | response | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | updateAdmissionRules | response | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | updateAdmissionRules | response | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | updateAdmissionRules | response | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | updateAdmissionRules | response | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | updateAdmissionRules | response | validity.from | string (date)
AccessService | updateAdmissionRules | response | validity.to | string (date) |  | Inclusive.
AccessService | updateAdmissionRules | response | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | updateAdmissionRules | response | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | updateAdmissionRules | response | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | updateAdmissionRules | response | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | updateAdmissionRules | response | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | updateAdmissionRules | response | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | updateAdmissionRules | response | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | updateAdmissionRules | response | crossover.sameDayOnly | boolean |  | (default True)
AccessService | updateAdmissionRules | response | crossover.differentDayAccess | boolean |  | (default False)
AccessService | updateAdmissionRules | response | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | updateAdmissionRules | response | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | response | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | updateAdmissionRules | response | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | updateAdmissionRules | response | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | updateAdmissionRules | response | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | updateAdmissionRules | response | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | updateAdmissionRules | response | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | updateAdmissionRules | response | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | updateAdmissionRules | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | updateAdmissionRules | param (path) | profileId | string (uuid) | yes
AccessService | updateAdmissionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateBanner | request | title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | request | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | request | imageAssetRef | string (uuid)
WhiteLabelService | updateBanner | request | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | updateBanner | request | linkTarget | LinkTarget
WhiteLabelService | updateBanner | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updateBanner | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updateBanner | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updateBanner | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updateBanner | request | linkTarget.productId | string (uuid)
WhiteLabelService | updateBanner | request | linkTarget.eventId | string (uuid)
WhiteLabelService | updateBanner | request | linkTarget.url | string
WhiteLabelService | updateBanner | request | startsAt | string (date-time)
WhiteLabelService | updateBanner | request | endsAt | string (date-time) |  | Null runs the banner with no end. (nullable)
WhiteLabelService | updateBanner | request | sortOrder | integer
WhiteLabelService | updateBanner | request | isActive | boolean
WhiteLabelService | updateBanner | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updateBanner | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | response | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updateBanner | response | imageAssetRef | string (uuid) | yes
WhiteLabelService | updateBanner | response | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | updateBanner | response | linkTarget | LinkTarget
WhiteLabelService | updateBanner | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updateBanner | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updateBanner | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updateBanner | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updateBanner | response | linkTarget.productId | string (uuid)
WhiteLabelService | updateBanner | response | linkTarget.eventId | string (uuid)
WhiteLabelService | updateBanner | response | linkTarget.url | string
WhiteLabelService | updateBanner | response | startsAt | string (date-time) | yes
WhiteLabelService | updateBanner | response | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | updateBanner | response | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | updateBanner | response | sortOrder | integer
WhiteLabelService | updateBanner | response | isActive | boolean
WhiteLabelService | updateBanner | param (path) | bannerId | string (uuid) | yes
WhiteLabelService | updateBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateBookingFlowDefinition | request | name | string |  | (max length 80)
WhiteLabelService | updateBookingFlowDefinition | request | isDefaultForType | boolean
WhiteLabelService | updateBookingFlowDefinition | request | isEnabled | boolean
WhiteLabelService | updateBookingFlowDefinition | request | steps | array of BookingFlowStep |  | (min items 1; max items 30)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | updateBookingFlowDefinition | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | updateBookingFlowDefinition | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | updateBookingFlowDefinition | request | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | request | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | updateBookingFlowDefinition | request | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | updateBookingFlowDefinition | request | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | updateBookingFlowDefinition | request | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | updateBookingFlowDefinition | request | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | updateBookingFlowDefinition | request | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | updateBookingFlowDefinition | response | id | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | updateBookingFlowDefinition | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | updateBookingFlowDefinition | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | updateBookingFlowDefinition | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | updateBookingFlowDefinition | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | updateBookingFlowDefinition | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | updateBookingFlowDefinition | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | updateBookingFlowDefinition | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | updateBookingFlowDefinition | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | updateBookingFlowDefinition | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | updateBookingFlowDefinition | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | updateBookingFlowDefinition | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | updateBookingFlowDefinition | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | updateBookingFlowDefinition | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updateBookingFlowDefinition | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | updateBookingFlowDefinition | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | updateBookingFlowDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateBundle | request | name | string |  | (max length 200)
CatalogueService | updateBundle | request | price | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updateBundle | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateBundle | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateBundle | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateBundle | request | validTo | string (date-time)
CatalogueService | updateBundle | request | isActive | boolean
CatalogueService | updateBundle | response | code | string | yes | (max length 64)
CatalogueService | updateBundle | response | name | string | yes | (max length 200)
CatalogueService | updateBundle | response | description | string |  | (max length 1000)
CatalogueService | updateBundle | response | venueId | string (uuid) | yes
CatalogueService | updateBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | updateBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | updateBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | updateBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | updateBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | updateBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | updateBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | updateBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | updateBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | updateBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | updateBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | updateBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | updateBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | updateBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | updateBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | updateBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | updateBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | updateBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | updateBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | updateBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | updateBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | updateBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | updateBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | updateBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | updateBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | updateBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | updateBundle | response | allocation | object | yes
CatalogueService | updateBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | updateBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | updateBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | updateBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | updateBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | updateBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updateBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | updateBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | updateBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | updateBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | updateBundle | response | validFrom | string (date-time)
CatalogueService | updateBundle | response | validTo | string (date-time)
CatalogueService | updateBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | updateBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | updateBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | updateBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | updateBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | updateBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | updateBundle | response | id | string (uuid) | yes
CatalogueService | updateBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price.
CatalogueService | updateBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateBundle | response | savingsPercentage | number
CatalogueService | updateBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | updateBundle | response | isActive | boolean | yes
CatalogueService | updateBundle | param (path) | bundleId | string (uuid) | yes
CatalogueService | updateBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateCampaign | request | name | string |  | (max length 200)
MarketingService | updateCampaign | request | isPaused | boolean
MarketingService | updateCampaign | request | scheduledFor | string (date-time)
MarketingService | updateCampaign | request | content | CampaignContent
MarketingService | updateCampaign | request | content.templateId | string (uuid) | yes
MarketingService | updateCampaign | request | content.subjectOverride | object
MarketingService | updateCampaign | request | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | updateCampaign | request | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | updateCampaign | response | name | string | yes | (max length 200)
MarketingService | updateCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | updateCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | updateCampaign | response | venueId | string (uuid)
MarketingService | updateCampaign | response | segmentId | string (uuid) | yes
MarketingService | updateCampaign | response | content | CampaignContent | yes
MarketingService | updateCampaign | response | content.templateId | string (uuid) | yes
MarketingService | updateCampaign | response | content.subjectOverride | object
MarketingService | updateCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | updateCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | updateCampaign | response | trigger | CampaignTrigger
MarketingService | updateCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | updateCampaign | response | trigger.delayHours | integer
MarketingService | updateCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | updateCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | updateCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | updateCampaign | response | trigger.conditions[].value | object
MarketingService | updateCampaign | response | trigger.conditions[].values | array of object
MarketingService | updateCampaign | response | scheduledFor | string (date-time)
MarketingService | updateCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | updateCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | updateCampaign | response | sendWindow.startTime | string
MarketingService | updateCampaign | response | sendWindow.endTime | string
MarketingService | updateCampaign | response | sendWindow.timeZone | string
MarketingService | updateCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | updateCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | updateCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | updateCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | updateCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | updateCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | updateCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | updateCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | updateCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | updateCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | updateCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | updateCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | updateCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | updateCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | updateCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | updateCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | updateCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | updateCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | updateCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | updateCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | updateCampaign | response | id | string (uuid) | yes
MarketingService | updateCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | updateCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | updateCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | updateCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | updateCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | updateCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | updateCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | updateCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | updateCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | updateCampaign | response | isPaused | boolean
MarketingService | updateCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | updateCampaign | response | createdAt | string (date-time) | yes
MarketingService | updateCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | updateCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | updateCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | updateCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | updateCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | updateCartLine | request | quantity | integer | yes | The new quantity. (min 0)
OrderService | updateCartLine | response | id | string (uuid) | yes
OrderService | updateCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | updateCartLine | response | venueId | string (uuid) | yes
OrderService | updateCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | updateCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | updateCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | updateCartLine | response | lines | array of CartLine | yes
OrderService | updateCartLine | response | lines[].id | string (uuid) | yes
OrderService | updateCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | updateCartLine | response | lines[].productName | string |  | (read-only)
OrderService | updateCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | updateCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | updateCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | updateCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | updateCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | updateCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | updateCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | updateCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | updateCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | updateCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | updateCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | updateCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | updateCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | updateCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | updateCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | updateCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | updateCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | updateCartLine | response | conflicts | array of CartConflict
OrderService | updateCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | updateCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | updateCartLine | response | conflicts[].message | string
OrderService | updateCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | updateCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | updateCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | updateCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | updateCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | updateCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | updateCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | updateCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | updateCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | updateCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | updateCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | updateCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | updateCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | updateCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | updateCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | updateCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | updateCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | updateCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | updateCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | updateCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | updateCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | updateCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | updateCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | updateCartLine | response | maxExtensions | integer |  | (read-only)
OrderService | updateCartLine | response | locale | string
OrderService | updateCartLine | response | createdAt | string (date-time)
OrderService | updateCartLine | response | updatedAt | string (date-time)
OrderService | updateCartLine | param (path) | cartId | string (uuid) | yes
OrderService | updateCartLine | param (path) | lineId | string (uuid) | yes
OrderService | updateCartLine | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | updateCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateCommercialCampaign | request | code | string |  | (max length 64; nullable)
CatalogueService | updateCommercialCampaign | request | name | string |  | (max length 200)
CatalogueService | updateCommercialCampaign | request | description | string |  | (max length 1000; nullable)
CatalogueService | updateCommercialCampaign | request | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | updateCommercialCampaign | request | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | updateCommercialCampaign | request | validFrom | string (date-time) |  | (nullable)
CatalogueService | updateCommercialCampaign | request | validTo | string (date-time) |  | (nullable)
CatalogueService | updateCommercialCampaign | response | id | string (uuid) | yes | (read-only)
CatalogueService | updateCommercialCampaign | response | venueId | string (uuid) | yes
CatalogueService | updateCommercialCampaign | response | code | string |  | (max length 64; nullable)
CatalogueService | updateCommercialCampaign | response | name | string | yes | (max length 200)
CatalogueService | updateCommercialCampaign | response | description | string |  | (max length 1000; nullable)
CatalogueService | updateCommercialCampaign | response | ownerPrincipalId | string (uuid) |  | The campaign (and budget) owner. (nullable)
CatalogueService | updateCommercialCampaign | response | legalEntityId | string (uuid) |  | The business entity that funds and books the campaign. (nullable)
CatalogueService | updateCommercialCampaign | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | updateCommercialCampaign | response | validTo | string (date-time) |  | (nullable)
CatalogueService | updateCommercialCampaign | response | budgets | array of CampaignBudget |  | The rows of promotions.campaign_budget, one per budget line.
CatalogueService | updateCommercialCampaign | response | budgets[].id | string (uuid) |  | (read-only)
CatalogueService | updateCommercialCampaign | response | budgets[].budgetType | enum (total, discount, reward, freeProduct) | yes | The spend this line caps (total campaign, discount, reward or free-product budget).
CatalogueService | updateCommercialCampaign | response | budgets[].fundingSource | enum (venue, department, marketing, partner) |  | Who pays for it; partner is a co-funded (e.g. (nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | updateCommercialCampaign | response | budgets[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updateCommercialCampaign | response | budgets[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updateCommercialCampaign | response | budgets[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updateCommercialCampaign | response | budgets[].scope | enum (entireCampaign, promotion, product, channel, partner, customerSegment) |  | What the line covers. (default entireCampaign)
CatalogueService | updateCommercialCampaign | response | budgets[].scopeRef | string |  | The promotion, product, partner or segment id, or the SalesChannel value, that scope names. (nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].ownerPrincipalId | string (uuid) |  | The budget owner. (nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].costCentre | string |  | (max length 64; nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].department | string |  | (max length 100; nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].validFrom | string (date-time) |  | (nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].validTo | string (date-time) |  | (nullable)
CatalogueService | updateCommercialCampaign | response | budgets[].thresholdPolicy | BudgetThresholdPolicy |  | The automatic actions as a budget line is consumed (Threshold Actions & Automatic Suspension).
CatalogueService | updateCommercialCampaign | response | budgets[].thresholdPolicy.steps | array of object
CatalogueService | updateCommercialCampaign | param (path) | campaignId | string (uuid) | yes
CatalogueService | updateCommercialCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateConsentQuestion | request | id | string (uuid) | yes | (read-only)
MarketingService | updateConsentQuestion | request | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | updateConsentQuestion | request | text | object | yes | The question as the guest reads it, per locale.
MarketingService | updateConsentQuestion | request | helpText | object |  | (nullable)
MarketingService | updateConsentQuestion | request | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | updateConsentQuestion | request | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | updateConsentQuestion | request | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | updateConsentQuestion | request | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | updateConsentQuestion | request | status | enum (active, retired) | yes | (default active)
MarketingService | updateConsentQuestion | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | updateConsentQuestion | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateConsentQuestion | response | id | string (uuid) | yes | (read-only)
MarketingService | updateConsentQuestion | response | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | updateConsentQuestion | response | text | object | yes | The question as the guest reads it, per locale.
MarketingService | updateConsentQuestion | response | helpText | object |  | (nullable)
MarketingService | updateConsentQuestion | response | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | updateConsentQuestion | response | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | updateConsentQuestion | response | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | updateConsentQuestion | response | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | updateConsentQuestion | response | status | enum (active, retired) | yes | (default active)
MarketingService | updateConsentQuestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | updateConsentQuestion | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateConsentQuestion | param (path) | questionId | string (uuid) | yes
MarketingService | updateConsentQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateContentPage | request | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | updateContentPage | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateContentPage | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | updateContentPage | request | isEnabled | boolean |  | (default True)
WhiteLabelService | updateContentPage | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | updateContentPage | request | categoryCode | string |  | (nullable)
WhiteLabelService | updateContentPage | request | sortOrder | integer
WhiteLabelService | updateContentPage | request | status | object |  | Only archived is taken — send it to withdraw a published page or abandon a draft (states/content.yaml).
WhiteLabelService | updateContentPage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updateContentPage | response | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | updateContentPage | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateContentPage | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | updateContentPage | response | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | updateContentPage | response | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | updateContentPage | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | updateContentPage | response | categoryCode | string |  | (nullable)
WhiteLabelService | updateContentPage | response | sortOrder | integer
WhiteLabelService | updateContentPage | response | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | updateContentPage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updateContentPage | param (path) | pageId | string (uuid) | yes
WhiteLabelService | updateContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | updateDashboard | request | name | string | yes | (max length 200)
ReportingService | updateDashboard | request | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | updateDashboard | request | description | string |  | (max length 1000)
ReportingService | updateDashboard | request | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | updateDashboard | request | isShared | boolean |  | (default False)
ReportingService | updateDashboard | request | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | updateDashboard | request | tiles[].id | string (uuid) | yes
ReportingService | updateDashboard | request | tiles[].title | string
ReportingService | updateDashboard | request | tiles[].reportId | string (uuid) | yes
ReportingService | updateDashboard | request | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | updateDashboard | request | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | updateDashboard | request | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | updateDashboard | request | tiles[].position | object | yes
ReportingService | updateDashboard | request | tiles[].position.row | integer | yes
ReportingService | updateDashboard | request | tiles[].position.column | integer | yes
ReportingService | updateDashboard | request | tiles[].position.width | integer | yes
ReportingService | updateDashboard | request | tiles[].position.height | integer | yes
ReportingService | updateDashboard | response | name | string | yes | (max length 200)
ReportingService | updateDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | updateDashboard | response | description | string |  | (max length 1000)
ReportingService | updateDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | updateDashboard | response | isShared | boolean |  | (default False)
ReportingService | updateDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | updateDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | updateDashboard | response | tiles[].title | string
ReportingService | updateDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | updateDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | updateDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | updateDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | updateDashboard | response | tiles[].position | object | yes
ReportingService | updateDashboard | response | tiles[].position.row | integer | yes
ReportingService | updateDashboard | response | tiles[].position.column | integer | yes
ReportingService | updateDashboard | response | tiles[].position.width | integer | yes
ReportingService | updateDashboard | response | tiles[].position.height | integer | yes
ReportingService | updateDashboard | response | id | string (uuid) | yes
ReportingService | updateDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | updateDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | updateDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | updateDashboard | response | createdAt | string (date-time) | yes
ReportingService | updateDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | updateDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | updateDeliveryLocation | request | label | string |  | (max length 200)
FnbService | updateDeliveryLocation | request | zone | string |  | (nullable)
FnbService | updateDeliveryLocation | request | isServiceable | boolean
FnbService | updateDeliveryLocation | request | unserviceableReason | string |  | (nullable)
FnbService | updateDeliveryLocation | request | walkTimeMinutes | integer |  | (min 0; nullable)
FnbService | updateDeliveryLocation | response | id | string (uuid) | yes
FnbService | updateDeliveryLocation | response | venueId | string (uuid) | yes
FnbService | updateDeliveryLocation | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | updateDeliveryLocation | response | label | string | yes | What a runner is told.
FnbService | updateDeliveryLocation | response | zone | string |  | (nullable)
FnbService | updateDeliveryLocation | response | tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | updateDeliveryLocation | response | seatId | string |  | Set where the seat is the address. (nullable)
FnbService | updateDeliveryLocation | response | servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | updateDeliveryLocation | response | isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | updateDeliveryLocation | response | unserviceableReason | string |  | (nullable)
FnbService | updateDeliveryLocation | response | walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | updateDeliveryLocation | param (path) | locationId | string (uuid) | yes
FnbService | updateDeliveryLocation | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | updateDeliveryLocation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateEvent | request | name | string |  | (max length 200)
CatalogueService | updateEvent | request | parentEventId | string (uuid) |  | (nullable)
CatalogueService | updateEvent | request | isActive | boolean
CatalogueService | updateEvent | response | id | string (uuid) | yes
CatalogueService | updateEvent | response | code | string | yes
CatalogueService | updateEvent | response | name | string | yes
CatalogueService | updateEvent | response | venueId | string (uuid) | yes
CatalogueService | updateEvent | response | scopePath | string | yes
CatalogueService | updateEvent | response | parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | updateEvent | response | performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | updateEvent | response | isActive | boolean
CatalogueService | updateEvent | param (path) | eventId | string (uuid) | yes
CatalogueService | updateEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateGuestPreferences | request | id | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | request | subjectId | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | request | seatingPreference | string |  | (max length 200; nullable)
MarketingService | updateGuestPreferences | request | drinkPreferences | array of string
MarketingService | updateGuestPreferences | request | dietary | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | request | accessibility | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | request | preferredChannel | object |  | Stored on the profile (GuestProfile.preferredChannel) — carried here because the preference screen edits it beside the rest.
MarketingService | updateGuestPreferences | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateGuestPreferences | response | id | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | response | subjectId | string (uuid) |  | (read-only)
MarketingService | updateGuestPreferences | response | seatingPreference | string |  | (max length 200; nullable)
MarketingService | updateGuestPreferences | response | drinkPreferences | array of string
MarketingService | updateGuestPreferences | response | dietary | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | response | accessibility | array of string |  | Also written by updateMyProfile.
MarketingService | updateGuestPreferences | response | preferredChannel | object |  | Stored on the profile (GuestProfile.preferredChannel) — carried here because the preference screen edits it beside the rest.
MarketingService | updateGuestPreferences | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | updateGuestPreferences | param (path) | subjectId | string (uuid) | yes
MarketingService | updateGuestPreferences | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | updateGuidedChoice | request | name | string |  | (max length 80)
WhiteLabelService | updateGuidedChoice | request | mode | enum (button, popupOnArrival, off)
WhiteLabelService | updateGuidedChoice | request | showBanner | boolean
WhiteLabelService | updateGuidedChoice | request | behaviour | enum (filter, recommend)
WhiteLabelService | updateGuidedChoice | request | showEverything | boolean
WhiteLabelService | updateGuidedChoice | request | questions | array of object |  | Replaces the whole question list; same shape and bounds as GuidedChoice.questions. (min items 1; max items 4)
WhiteLabelService | updateGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | updateGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | updateGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | updateGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | updateGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | updateGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | updateGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | updateGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | updateGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | updateGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | updateGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | updateGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | updateGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | updateGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | updateGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | updateGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | updateGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | updateGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | updateGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | updateGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | updateInventoryItem | request | name | string |  | (max length 200)
InventoryService | updateInventoryItem | request | categoryId | string (uuid) |  | Null clears the category (decided 28 September, audit R171). (nullable)
InventoryService | updateInventoryItem | request | reorderPoint | number |  | (min 0)
InventoryService | updateInventoryItem | request | reorderQuantity | number |  | (min 0)
InventoryService | updateInventoryItem | request | parLevel | number |  | (min 0)
InventoryService | updateInventoryItem | request | preferredSupplierId | string (uuid) |  | Null clears the preferred supplier (decided 28 September, audit R171). (nullable)
InventoryService | updateInventoryItem | request | isActive | boolean
InventoryService | updateInventoryItem | request | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) |  | Fixed at item creation.
InventoryService | updateInventoryItem | request | baseUnit | string |  | Changeable only while hasMovements is false; the 409 below is the refusal once it is true.
InventoryService | updateInventoryItem | response | sku | string | yes | (max length 64)
InventoryService | updateInventoryItem | response | barcode | string |  | (max length 128)
InventoryService | updateInventoryItem | response | name | string | yes | (max length 200)
InventoryService | updateInventoryItem | response | venueId | string (uuid) | yes
InventoryService | updateInventoryItem | response | categoryId | string (uuid)
InventoryService | updateInventoryItem | response | baseUnit | string | yes | The unit stock is held in.
InventoryService | updateInventoryItem | response | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | updateInventoryItem | response | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | updateInventoryItem | response | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | updateInventoryItem | response | reorderPoint | number |  | (min 0)
InventoryService | updateInventoryItem | response | reorderQuantity | number |  | (min 0)
InventoryService | updateInventoryItem | response | parLevel | number |  | (min 0)
InventoryService | updateInventoryItem | response | preferredSupplierId | string (uuid)
InventoryService | updateInventoryItem | response | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | updateInventoryItem | response | isPerishable | boolean |  | (default False)
InventoryService | updateInventoryItem | response | shelfLifeDays | integer |  | (nullable)
InventoryService | updateInventoryItem | response | id | string (uuid) | yes
InventoryService | updateInventoryItem | response | onHand | number | yes | Derived from movements.
InventoryService | updateInventoryItem | response | onOrder | number
InventoryService | updateInventoryItem | response | inTransit | number
InventoryService | updateInventoryItem | response | available | number |  | On-hand minus allocated, where allocated is stock reserved for orders (decided 28 September, audit R171).
InventoryService | updateInventoryItem | response | averageCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | updateInventoryItem | response | averageCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | updateInventoryItem | response | averageCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | updateInventoryItem | response | averageCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | updateInventoryItem | response | lastPurchasePrice | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | updateInventoryItem | response | lastPurchasePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | updateInventoryItem | response | lastPurchasePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | updateInventoryItem | response | lastPurchasePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | updateInventoryItem | response | isBelowReorderPoint | boolean
InventoryService | updateInventoryItem | response | hasMovements | boolean |  | True locks costing method and base unit.
InventoryService | updateInventoryItem | response | isActive | boolean | yes
InventoryService | updateInventoryItem | param (path) | itemId | string (uuid) | yes
InventoryService | updateInventoryItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateMediaAsset | request | title | LocalisedText
VenueOpsService | updateMediaAsset | request | description | LocalisedText
VenueOpsService | updateMediaAsset | request | altText | object |  | Accessibility text.
VenueOpsService | updateMediaAsset | request | tags | array of string
VenueOpsService | updateMediaAsset | request | collectionIds | array of string (uuid) |  | Replaces the asset's collection memberships.
VenueOpsService | updateMediaAsset | request | rights | MediaRights |  | Licensing terms.
VenueOpsService | updateMediaAsset | request | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | updateMediaAsset | request | rights.licensor | string |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.licenceReference | string |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.validTo | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | updateMediaAsset | request | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | updateMediaAsset | request | rights.attributionText | string |  | (nullable)
VenueOpsService | updateMediaAsset | request | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | updateMediaAsset | request | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | updateMediaAsset | request | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | updateMediaAsset | request | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | updateMediaAsset | request | status | enum (ready, archived) |  | A lifecycle move from states/media.yaml.
VenueOpsService | updateMediaAsset | response | id | string (uuid) | yes
VenueOpsService | updateMediaAsset | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive) | yes
VenueOpsService | updateMediaAsset | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | updateMediaAsset | response | filename | string | yes
VenueOpsService | updateMediaAsset | response | contentType | string | yes
VenueOpsService | updateMediaAsset | response | sizeBytes | integer | yes
VenueOpsService | updateMediaAsset | response | title | LocalisedText
VenueOpsService | updateMediaAsset | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | updateMediaAsset | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | updateMediaAsset | response | width | integer |  | (nullable)
VenueOpsService | updateMediaAsset | response | height | integer |  | (nullable)
VenueOpsService | updateMediaAsset | response | durationSeconds | number |  | (nullable)
VenueOpsService | updateMediaAsset | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | updateMediaAsset | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | updateMediaAsset | response | tags | array of string
VenueOpsService | updateMediaAsset | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | updateMediaAsset | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | updateMediaAsset | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | updateMediaAsset | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | updateMediaAsset | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | updateMediaAsset | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | updateMediaAsset | response | rights.licensor | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | updateMediaAsset | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | updateMediaAsset | response | rights.attributionText | string |  | (nullable)
VenueOpsService | updateMediaAsset | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | updateMediaAsset | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | updateMediaAsset | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | updateMediaAsset | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | updateMediaAsset | response | isRightsExpired | boolean
VenueOpsService | updateMediaAsset | response | version | integer
VenueOpsService | updateMediaAsset | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | updateMediaAsset | response | createdAt | string (date-time) | yes
VenueOpsService | updateMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | updateMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | updateMenu | request | name | string |  | (max length 200)
FnbService | updateMenu | request | availability | MenuAvailability |  | When this menu is in force.
FnbService | updateMenu | request | availability.daysOfWeek | array of integer
FnbService | updateMenu | request | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | request | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | request | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | request | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | request | isActive | boolean
FnbService | updateMenu | response | id | string (uuid) | yes
FnbService | updateMenu | response | code | string | yes | (max length 64)
FnbService | updateMenu | response | name | string | yes | (max length 200)
FnbService | updateMenu | response | outletId | string (uuid) | yes
FnbService | updateMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | updateMenu | response | availability.daysOfWeek | array of integer
FnbService | updateMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | updateMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | updateMenu | response | sections | array of MenuSection
FnbService | updateMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | updateMenu | response | sections[].code | string | yes
FnbService | updateMenu | response | sections[].name | string | yes
FnbService | updateMenu | response | sections[].sortOrder | integer | yes
FnbService | updateMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | updateMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | updateMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item sells.
FnbService | updateMenu | response | sections[].items[].name | string | yes
FnbService | updateMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | updateMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateMenu | response | sections[].items[].sortOrder | integer
FnbService | updateMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | updateMenu | response | sections[].items[].stationId | string (uuid) |  | (nullable)
FnbService | updateMenu | response | sections[].items[].menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | updateMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | updateMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | updateMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | updateMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | updateMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | updateMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | updateMenu | response | isActive | boolean | yes
FnbService | updateMenu | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | updateMenu | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | updateMenu | param (path) | menuId | string (uuid) | yes
FnbService | updateMenu | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | updateMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | updateMerchandise | request | name | string |  | (max length 200)
RetailService | updateMerchandise | request | description | string |  | What the item is, in the guest's words. (nullable)
RetailService | updateMerchandise | request | barcode | string |  | Must stay unique in the venue. (max length 128; nullable)
RetailService | updateMerchandise | request | categoryId | string (uuid)
RetailService | updateMerchandise | request | inventoryItemId | string (uuid) |  | Re-points the stock item a sale depletes. (nullable)
RetailService | updateMerchandise | request | imageAssetRef | string |  | (nullable)
RetailService | updateMerchandise | request | isReturnable | boolean
RetailService | updateMerchandise | request | returnWindowDays | integer |  | (min 0)
RetailService | updateMerchandise | request | requiresSerialNumber | boolean
RetailService | updateMerchandise | request | isActive | boolean
RetailService | updateMerchandise | response | description | string |  | What the item is, in the guest's words.
RetailService | updateMerchandise | response | id | string (uuid) | yes
RetailService | updateMerchandise | response | sku | string | yes
RetailService | updateMerchandise | response | barcode | string |  | (nullable)
RetailService | updateMerchandise | response | name | string | yes
RetailService | updateMerchandise | response | outletId | string (uuid) | yes
RetailService | updateMerchandise | response | categoryId | string (uuid) |  | (nullable)
RetailService | updateMerchandise | response | variantId | string (uuid) | yes | The catalogue variant sold.
RetailService | updateMerchandise | response | inventoryItemId | string (uuid) |  | The stock item depleted on sale. (nullable)
RetailService | updateMerchandise | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | updateMerchandise | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | updateMerchandise | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | updateMerchandise | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | updateMerchandise | response | onHand | number | yes
RetailService | updateMerchandise | response | isReturnable | boolean |  | (default True)
RetailService | updateMerchandise | response | returnWindowDays | integer |  | (nullable)
RetailService | updateMerchandise | response | requiresSerialNumber | boolean |  | (default False)
RetailService | updateMerchandise | response | imageAssetRef | string |  | (nullable)
RetailService | updateMerchandise | response | isActive | boolean | yes
RetailService | updateMerchandise | param (path) | merchandiseId | string (uuid) | yes
RetailService | updateMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | updateMyProfile | request | displayName | string
MarketingService | updateMyProfile | request | email | string (email)
MarketingService | updateMyProfile | request | phone | string
MarketingService | updateMyProfile | request | preferredLanguage | string
MarketingService | updateMyProfile | request | preferredChannel | enum (email, sms, whatsapp, push, none)
MarketingService | updateMyProfile | request | dietary | array of string |  | Health-adjacent personal data, kept structured rather than as a tag (BL-134).
MarketingService | updateMyProfile | request | accessibility | array of string |  | Same treatment, same reason.
MarketingService | updateMyProfile | response | id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | updateMyProfile | response | subjectId | string (uuid) | yes | Opaque reference.
MarketingService | updateMyProfile | response | displayName | string |  | (nullable)
MarketingService | updateMyProfile | response | email | string |  | (nullable)
MarketingService | updateMyProfile | response | phone | string |  | (nullable)
MarketingService | updateMyProfile | response | preferredLanguage | string |  | (nullable)
MarketingService | updateMyProfile | response | preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | updateMyProfile | response | guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | updateMyProfile | response | tags | array of string
MarketingService | updateMyProfile | response | engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | updateMyProfile | response | engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | updateMyProfile | response | lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | updateMyProfile | response | lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | updateMyProfile | response | lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | updateMyProfile | response | lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | updateMyProfile | response | visitCount | integer
MarketingService | updateMyProfile | response | lastVisitAt | string (date-time) |  | (nullable)
MarketingService | updateMyProfile | response | isActive | boolean | yes
MarketingService | updateMyProfile | response | mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | updateMyProfile | response | mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | updateMyProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateOrgUnit | request | name | string |  | (max length 200)
TenancyService | updateOrgUnit | request | isActive | boolean
TenancyService | updateOrgUnit | response | id | string (uuid) | yes
TenancyService | updateOrgUnit | response | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | updateOrgUnit | response | parentId | string (uuid) |  | (nullable)
TenancyService | updateOrgUnit | response | path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | updateOrgUnit | response | code | string | yes | (max length 64)
TenancyService | updateOrgUnit | response | name | string | yes | (max length 200)
TenancyService | updateOrgUnit | response | isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | updateOrgUnit | response | childCount | integer |  | (min 0)
TenancyService | updateOrgUnit | param (path) | orgUnitId | string (uuid) | yes
TenancyService | updateOrgUnit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateOutlet | request | name | string |  | (max length 200)
TenancyService | updateOutlet | request | stockLocationId | string (uuid)
TenancyService | updateOutlet | request | costCenterId | string (uuid)
TenancyService | updateOutlet | request | openingHours | array of OpeningHoursWindow |  | Replaces the whole weekly pattern.
TenancyService | updateOutlet | request | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | updateOutlet | request | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | request | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | request | isActive | boolean
TenancyService | updateOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | updateOutlet | response | code | string | yes | (max length 64)
TenancyService | updateOutlet | response | name | string | yes | (max length 200)
TenancyService | updateOutlet | response | venueId | string (uuid) | yes
TenancyService | updateOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | updateOutlet | response | zone | string |  | (nullable)
TenancyService | updateOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | updateOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | updateOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | updateOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | updateOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | updateOutlet | response | isActive | boolean
TenancyService | updateOutlet | param (path) | outletId | string (uuid) | yes
TenancyService | updateOutlet | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | updateParkingEntitlement | request | plateNumber | string |  | Personal data, under the same rules as ParkingEntitlement.plateNumber.
AccessService | updateParkingEntitlement | request | plateCountry | string |  | (nullable)
AccessService | updateParkingEntitlement | request | status | enum (revoked) |  | The only status a caller may set.
AccessService | updateParkingEntitlement | response | id | string (uuid) |  | (read-only)
AccessService | updateParkingEntitlement | response | facilityId | string (uuid) | yes
AccessService | updateParkingEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | updateParkingEntitlement | response | subjectId | string (uuid) |  | (nullable)
AccessService | updateParkingEntitlement | response | plateNumber | string |  | Required in plateWhitelist mode, meaningless in the others. (nullable)
AccessService | updateParkingEntitlement | response | plateCountry | string |  | (nullable)
AccessService | updateParkingEntitlement | response | mediaCode | string |  | The code presented in none and qrHandoff modes. (nullable)
AccessService | updateParkingEntitlement | response | status | object |  | Server-owned. (read-only)
AccessService | updateParkingEntitlement | response | pushedAt | string (date-time) |  | (read-only; nullable)
AccessService | updateParkingEntitlement | response | pushFailureReason | string |  | (read-only; nullable)
AccessService | updateParkingEntitlement | response | validFrom | string (date-time) | yes
AccessService | updateParkingEntitlement | response | validTo | string (date-time) | yes
AccessService | updateParkingEntitlement | param (path) | entitlementId | string (uuid) | yes
AccessService | updateParkingEntitlement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updatePerformance | request | startsAt | string (date-time)
CatalogueService | updatePerformance | request | endsAt | string (date-time)
CatalogueService | updatePerformance | request | status | enum (scheduled, onSale, suspended)
CatalogueService | updatePerformance | request | admissionRulesId | string (uuid)
CatalogueService | updatePerformance | request | language | string |  | As Performance.language (decided 29 September, rev 3 REV3-17). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | updatePerformance | request | format | string |  | As Performance.format (decided 29 September, rev 3 REV3-17). (max length 40; nullable)
CatalogueService | updatePerformance | response | id | string (uuid) | yes
CatalogueService | updatePerformance | response | eventId | string (uuid) | yes
CatalogueService | updatePerformance | response | startsAt | string (date-time) | yes
CatalogueService | updatePerformance | response | endsAt | string (date-time) | yes
CatalogueService | updatePerformance | response | approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | updatePerformance | response | requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | updatePerformance | response | status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | updatePerformance | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | updatePerformance | response | seatMapId | string (uuid) |  | (nullable)
CatalogueService | updatePerformance | response | language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | updatePerformance | response | format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | updatePerformance | param (path) | performanceId | string (uuid) | yes
CatalogueService | updatePerformance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updatePriceList | request | name | string |  | (max length 200)
CatalogueService | updatePriceList | request | validFrom | string (date-time)
CatalogueService | updatePriceList | request | validTo | string (date-time)
CatalogueService | updatePriceList | request | priority | integer
CatalogueService | updatePriceList | request | isActive | boolean
CatalogueService | updatePriceList | response | id | string (uuid) | yes
CatalogueService | updatePriceList | response | code | string | yes
CatalogueService | updatePriceList | response | name | string | yes
CatalogueService | updatePriceList | response | venueId | string (uuid) | yes
CatalogueService | updatePriceList | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | updatePriceList | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | updatePriceList | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | updatePriceList | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | updatePriceList | response | validTo | string (date-time) |  | (nullable)
CatalogueService | updatePriceList | response | priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | updatePriceList | response | description | string |  | Price list master fields (29 September, data model DM3), set with setPriceListMaster (ADM-058). (nullable)
CatalogueService | updatePriceList | response | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | updatePriceList | response | status | object |  | (default active)
CatalogueService | updatePriceList | response | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | tags | array of string
CatalogueService | updatePriceList | response | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | brand | string |  | (max length 100; nullable)
CatalogueService | updatePriceList | response | businessUnit | string |  | (max length 100; nullable)
CatalogueService | updatePriceList | response | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | updatePriceList | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | updatePriceList | response | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | updatePriceList | response | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | allowOverrides | boolean |  | (default False)
CatalogueService | updatePriceList | response | allowInheritance | boolean |  | (default True)
CatalogueService | updatePriceList | response | allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | updatePriceList | response | allowProductSpecificRates | boolean |  | (default True)
CatalogueService | updatePriceList | response | clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | updatePriceList | response | currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | updatePriceList | param (path) | priceListId | string (uuid) | yes
CatalogueService | updatePriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | updatePrincipal | request | displayName | string |  | (max length 200)
IdentityService | updatePrincipal | request | isActive | boolean
IdentityService | updatePrincipal | request | validTo | string (date-time) |  | (nullable)
IdentityService | updatePrincipal | request | primaryRoleId | string (uuid)
IdentityService | updatePrincipal | response | id | string (uuid) | yes
IdentityService | updatePrincipal | response | username | string | yes
IdentityService | updatePrincipal | response | displayName | string | yes
IdentityService | updatePrincipal | response | isActive | boolean | yes
IdentityService | updatePrincipal | response | validFrom | string (date-time) |  | (nullable)
IdentityService | updatePrincipal | response | validTo | string (date-time) |  | Past this, resolution returns DENY regardless of grants. (nullable)
IdentityService | updatePrincipal | response | primaryRoleId | string (uuid) |  | Determines the landing screen when the principal holds several roles and picks one at login. (nullable)
IdentityService | updatePrincipal | response | roles | array of RoleSummary
IdentityService | updatePrincipal | response | roles[].id | string (uuid) | yes
IdentityService | updatePrincipal | response | roles[].code | string | yes
IdentityService | updatePrincipal | response | roles[].name | string | yes
IdentityService | updatePrincipal | response | roles[].isPrimary | boolean
IdentityService | updatePrincipal | response | lastLoginAt | string (date-time) |  | (nullable)
IdentityService | updatePrincipal | param (path) | principalId | string (uuid) | yes
IdentityService | updatePrincipal | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateProduct | request | familyKey | string |  | The product family across the tenant's venues (decided 29 September, rev 3 REV3-18); see Product.familyKey. (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | updateProduct | request | name | string |  | (max length 200)
CatalogueService | updateProduct | request | description | string
CatalogueService | updateProduct | request | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | updateProduct | request | dataMaskValues | object
CatalogueService | updateProduct | request | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | updateProduct | request | notBookableLabel | object |  | (nullable)
CatalogueService | updateProduct | request | salesContact | object |  | See Product.salesContact (W3, 29 September). (nullable)
CatalogueService | updateProduct | request | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | updateProduct | request | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | updateProduct | request | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | updateProduct | request | bookingFlowId | string (uuid) |  | See Product.bookingFlowId (W8, W12, 29 September). (nullable)
CatalogueService | updateProduct | request | displayTags | array of ProductDisplayTag |  | (max items 6)
CatalogueService | updateProduct | request | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | updateProduct | request | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | updateProduct | request | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | updateProduct | request | media | array of ProductMedia |  | (max items 20)
CatalogueService | updateProduct | request | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | updateProduct | request | media[].kind | enum (image, video) | yes
CatalogueService | updateProduct | request | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | updateProduct | request | media[].displayOrder | integer |  | (default 100)
CatalogueService | updateProduct | request | media[].altText | object |  | (nullable)
CatalogueService | updateProduct | request | consentQuestionIds | array of string (uuid) |  | (max items 10)
CatalogueService | updateProduct | request | requiresTimeWindow | boolean
CatalogueService | updateProduct | response | id | string (uuid) | yes
CatalogueService | updateProduct | response | code | string | yes | (max length 64)
CatalogueService | updateProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | updateProduct | response | name | string | yes | (max length 200)
CatalogueService | updateProduct | response | description | string
CatalogueService | updateProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | updateProduct | response | venueId | string (uuid) | yes
CatalogueService | updateProduct | response | scopePath | string | yes
CatalogueService | updateProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | updateProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | updateProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | updateProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | updateProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | updateProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | updateProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | updateProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | updateProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | updateProduct | response | hasVariants | boolean | yes
CatalogueService | updateProduct | response | variantCount | integer
CatalogueService | updateProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | updateProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | updateProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | updateProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | updateProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | updateProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | updateProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | updateProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | updateProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | updateProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | updateProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | updateProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | updateProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | updateProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | updateProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | updateProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | updateProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | updateProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | updateProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | updateProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | updateProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | updateProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | updateProduct | response | media[].altText | object |  | (nullable)
CatalogueService | updateProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | updateProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | updateProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | updateProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | updateProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | updateProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | updateProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | updateProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | updateProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | updateProduct | param (path) | productId | string (uuid) | yes
CatalogueService | updateProduct | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updateProduct | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | updatePromoBlock | request | title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | request | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | request | iconAssetRef | string (uuid)
WhiteLabelService | updatePromoBlock | request | promotionId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget | LinkTarget
WhiteLabelService | updatePromoBlock | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updatePromoBlock | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updatePromoBlock | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updatePromoBlock | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget.productId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget.eventId | string (uuid)
WhiteLabelService | updatePromoBlock | request | linkTarget.url | string
WhiteLabelService | updatePromoBlock | request | startsAt | string (date-time)
WhiteLabelService | updatePromoBlock | request | endsAt | string (date-time)
WhiteLabelService | updatePromoBlock | request | sortOrder | integer
WhiteLabelService | updatePromoBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | updatePromoBlock | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | response | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | updatePromoBlock | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | updatePromoBlock | response | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | updatePromoBlock | response | linkTarget | LinkTarget
WhiteLabelService | updatePromoBlock | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | updatePromoBlock | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | updatePromoBlock | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | updatePromoBlock | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | updatePromoBlock | response | linkTarget.productId | string (uuid)
WhiteLabelService | updatePromoBlock | response | linkTarget.eventId | string (uuid)
WhiteLabelService | updatePromoBlock | response | linkTarget.url | string
WhiteLabelService | updatePromoBlock | response | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | updatePromoBlock | response | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | updatePromoBlock | response | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | updatePromoBlock | response | sortOrder | integer
WhiteLabelService | updatePromoBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | updatePromoBlock | param (path) | promoBlockId | string (uuid) | yes
WhiteLabelService | updatePromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | updatePromotion | request | name | string |  | (max length 200)
CatalogueService | updatePromotion | request | validTo | string (date-time)
CatalogueService | updatePromotion | request | isPaused | boolean
CatalogueService | updatePromotion | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | updatePromotion | request | conditions.variantIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.productKinds | array of string
CatalogueService | updatePromotion | request | conditions.categoryIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | updatePromotion | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | updatePromotion | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | updatePromotion | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | updatePromotion | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | updatePromotion | request | conditions.daysOfWeek | array of integer
CatalogueService | updatePromotion | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | updatePromotion | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | updatePromotion | request | conditions.performanceIds | array of string (uuid)
CatalogueService | updatePromotion | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | updatePromotion | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | updatePromotion | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | updatePromotion | request | discount | Discount
CatalogueService | updatePromotion | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | updatePromotion | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | updatePromotion | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | updatePromotion | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | updatePromotion | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | updatePromotion | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | updatePromotion | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | updatePromotion | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | updatePromotion | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | updatePromotion | response | code | string | yes | (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | updatePromotion | response | name | string | yes | (max length 200)
CatalogueService | updatePromotion | response | description | string |  | (max length 1000)
CatalogueService | updatePromotion | response | venueId | string (uuid) | yes
CatalogueService | updatePromotion | response | discount | Discount | yes
CatalogueService | updatePromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | updatePromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | updatePromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | updatePromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | updatePromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | updatePromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | updatePromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | updatePromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (setGiftFreeProduct, setBuyGetBogo). (nullable)
CatalogueService | updatePromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (setFixedPriceOffer). (min 1; nullable)
CatalogueService | updatePromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | updatePromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.productKinds | array of string
CatalogueService | updatePromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | updatePromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | updatePromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | updatePromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | updatePromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | updatePromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | updatePromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | updatePromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | updatePromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | updatePromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | updatePromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | updatePromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | updatePromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | updatePromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own, saved by setEligibilityRule) that must also hold. (nullable)
CatalogueService | updatePromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | updatePromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | updatePromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | updatePromotion | response | validFrom | string (date-time) | yes
CatalogueService | updatePromotion | response | validTo | string (date-time)
CatalogueService | updatePromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | updatePromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | updatePromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | updatePromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | updatePromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | updatePromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | updatePromotion | response | id | string (uuid) | yes
CatalogueService | updatePromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | updatePromotion | response | isPaused | boolean
CatalogueService | updatePromotion | response | redemptionCount | integer
CatalogueService | updatePromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | updatePromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | updatePromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | updatePromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | updatePromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | updatePromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | updatePromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | updatePromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateQueue | request | name | LocalisedText |  | The same locale-to-text map createQueue takes and Queue returns, so an edit form round-trips the name.
VenueOpsService | updateQueue | request | capacityPerCycle | integer |  | (min 1)
VenueOpsService | updateQueue | request | cycleMinutes | number |  | (min 0)
VenueOpsService | updateQueue | request | maxPartySize | integer |  | (min 1)
VenueOpsService | updateQueue | request | returnWindowMinutes | integer |  | (min 1)
VenueOpsService | updateQueue | request | heightRequirementCm | integer |  | (nullable)
VenueOpsService | updateQueue | request | fastPassAllocationPercent | number |  | (min 0; max 100)
VenueOpsService | updateQueue | request | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | updateQueue | request | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | updateQueue | request | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | request | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | request | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | updateQueue | request | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | updateQueue | request | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | updateQueue | request | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | updateQueue | response | code | string | yes | (max length 64)
VenueOpsService | updateQueue | response | name | LocalisedText | yes
VenueOpsService | updateQueue | response | venueId | string (uuid) | yes
VenueOpsService | updateQueue | response | attractionProductId | string (uuid)
VenueOpsService | updateQueue | response | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | updateQueue | response | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | updateQueue | response | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | updateQueue | response | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | updateQueue | response | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | updateQueue | response | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | updateQueue | response | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | updateQueue | response | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | updateQueue | response | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | updateQueue | response | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | updateQueue | response | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | updateQueue | response | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | updateQueue | response | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | updateQueue | response | cycleMinutes | number | yes | (min 0)
VenueOpsService | updateQueue | response | maxPartySize | integer |  | (default 6)
VenueOpsService | updateQueue | response | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | updateQueue | response | heightRequirementCm | integer |  | (nullable)
VenueOpsService | updateQueue | response | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | updateQueue | response | zone | string |  | (nullable)
VenueOpsService | updateQueue | response | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | updateQueue | response | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | updateQueue | response | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | response | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | updateQueue | response | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | updateQueue | response | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | updateQueue | response | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | updateQueue | response | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | updateQueue | response | id | string (uuid) | yes
VenueOpsService | updateQueue | response | status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | updateQueue | response | statusReason | string |  | (nullable)
VenueOpsService | updateQueue | response | waitingPartyCount | integer | yes
VenueOpsService | updateQueue | response | waitingGuestCount | integer
VenueOpsService | updateQueue | response | currentWaitMinutes | integer |  | (nullable)
VenueOpsService | updateQueue | response | waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | updateQueue | response | waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | updateQueue | response | manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | updateQueue | response | manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | updateQueue | response | expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | updateQueue | param (path) | queueId | string (uuid) | yes
VenueOpsService | updateQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateRegionSettings | request | countryCode | string | yes | ISO 3166-1 alpha-2. (pattern ^[A-Z]{2}$)
TenancyService | updateRegionSettings | request | currencyCode | string | yes | (pattern ^[A-Z]{3}$)
TenancyService | updateRegionSettings | request | currencyScale | integer | yes | Decimal places for this region's currency. (min 0; max 4)
TenancyService | updateRegionSettings | request | timeZone | string | yes | IANA zone, e.g.
TenancyService | updateRegionSettings | request | dateFormat | string |  | (default dd/MM/yyyy)
TenancyService | updateRegionSettings | request | numberFormat | string |  | (default #,##0.00)
TenancyService | updateRegionSettings | request | fiscalYearStartMonth | integer | yes | Varies by country. (min 1; max 12)
TenancyService | updateRegionSettings | request | allowedAiResidencies | array of string |  | The region's compliance gate on AI providers (decided 28 September, audit R203; ADR-0009). (default [])
TenancyService | updateRegionSettings | request | placement | Placement |  | Read-only here. (read-only)
TenancyService | updateRegionSettings | request | placement.mode | enum (shared, dedicated, isolated, clientHosted) | yes
TenancyService | updateRegionSettings | request | placement.cellName | string
TenancyService | updateRegionSettings | request | placement.cloudRegion | string
TenancyService | updateRegionSettings | request | cellName | string |  | The cell serving this region. (read-only)
TenancyService | updateRegionSettings | response | countryCode | string | yes | ISO 3166-1 alpha-2. (pattern ^[A-Z]{2}$)
TenancyService | updateRegionSettings | response | currencyCode | string | yes | (pattern ^[A-Z]{3}$)
TenancyService | updateRegionSettings | response | currencyScale | integer | yes | Decimal places for this region's currency. (min 0; max 4)
TenancyService | updateRegionSettings | response | timeZone | string | yes | IANA zone, e.g.
TenancyService | updateRegionSettings | response | dateFormat | string |  | (default dd/MM/yyyy)
TenancyService | updateRegionSettings | response | numberFormat | string |  | (default #,##0.00)
TenancyService | updateRegionSettings | response | fiscalYearStartMonth | integer | yes | Varies by country. (min 1; max 12)
TenancyService | updateRegionSettings | response | allowedAiResidencies | array of string |  | The region's compliance gate on AI providers (decided 28 September, audit R203; ADR-0009). (default [])
TenancyService | updateRegionSettings | response | placement | Placement |  | Read-only here. (read-only)
TenancyService | updateRegionSettings | response | placement.mode | enum (shared, dedicated, isolated, clientHosted) | yes
TenancyService | updateRegionSettings | response | placement.cellName | string
TenancyService | updateRegionSettings | response | placement.cloudRegion | string
TenancyService | updateRegionSettings | response | cellName | string |  | The cell serving this region. (read-only)
TenancyService | updateRegionSettings | param (path) | regionId | string (uuid) | yes
TenancyService | updateRegionSettings | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | updateReport | request | name | string | yes | (max length 200)
ReportingService | updateReport | request | description | string |  | (max length 1000)
ReportingService | updateReport | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | updateReport | request | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | updateReport | request | columns | array of ReportColumn | yes | (min items 1)
ReportingService | updateReport | request | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | request | columns[].field | string | yes
ReportingService | updateReport | request | columns[].label | string
ReportingService | updateReport | request | columns[].aggregation | object |  | (default none)
ReportingService | updateReport | request | columns[].sortOrder | integer
ReportingService | updateReport | request | columns[].sortDirection | enum (asc, desc)
ReportingService | updateReport | request | columns[].format | string |  | (nullable)
ReportingService | updateReport | request | filters | array of ReportFilter
ReportingService | updateReport | request | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | request | filters[].field | string | yes
ReportingService | updateReport | request | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | updateReport | request | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | updateReport | request | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | updateReport | request | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | updateReport | request | groupBy | array of string
ReportingService | updateReport | request | parameters | array of ReportParameter
ReportingService | updateReport | request | parameters[].key | string | yes
ReportingService | updateReport | request | parameters[].label | string | yes
ReportingService | updateReport | request | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | updateReport | request | parameters[].isRequired | boolean | yes
ReportingService | updateReport | request | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | updateReport | request | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | updateReport | request | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | updateReport | response | name | string | yes | (max length 200)
ReportingService | updateReport | response | description | string |  | (max length 1000)
ReportingService | updateReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | updateReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | updateReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | updateReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | response | columns[].field | string | yes
ReportingService | updateReport | response | columns[].label | string
ReportingService | updateReport | response | columns[].aggregation | object |  | (default none)
ReportingService | updateReport | response | columns[].sortOrder | integer
ReportingService | updateReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | updateReport | response | columns[].format | string |  | (nullable)
ReportingService | updateReport | response | filters | array of ReportFilter
ReportingService | updateReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | updateReport | response | filters[].field | string | yes
ReportingService | updateReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | updateReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | updateReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | updateReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | updateReport | response | groupBy | array of string
ReportingService | updateReport | response | parameters | array of ReportParameter
ReportingService | updateReport | response | parameters[].key | string | yes
ReportingService | updateReport | response | parameters[].label | string | yes
ReportingService | updateReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | updateReport | response | parameters[].isRequired | boolean | yes
ReportingService | updateReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | updateReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | updateReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | updateReport | response | id | string (uuid) | yes
ReportingService | updateReport | response | version | string | yes | The current version.
ReportingService | updateReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | updateReport | response | isRetired | boolean | yes
ReportingService | updateReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | updateReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | updateReport | response | createdAt | string (date-time) | yes
ReportingService | updateReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | updateReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | updateReport | param (path) | reportId | string (uuid) | yes
ReportingService | updateReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateResource | request | id | string (uuid) | yes
VenueOpsService | updateResource | request | code | string | yes
VenueOpsService | updateResource | request | name | string | yes
VenueOpsService | updateResource | request | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | updateResource | request | venueId | string (uuid) | yes
VenueOpsService | updateResource | request | scopePath | string
VenueOpsService | updateResource | request | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | updateResource | request | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | updateResource | request | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | updateResource | request | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | updateResource | request | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | updateResource | request | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | updateResource | request | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | updateResource | request | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | updateResource | request | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | updateResource | request | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | request | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | request | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | updateResource | request | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResource | request | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResource | request | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResource | request | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResource | request | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | updateResource | request | isActive | boolean |  | (default True)
VenueOpsService | updateResource | response | id | string (uuid) | yes
VenueOpsService | updateResource | response | code | string | yes
VenueOpsService | updateResource | response | name | string | yes
VenueOpsService | updateResource | response | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | updateResource | response | venueId | string (uuid) | yes
VenueOpsService | updateResource | response | scopePath | string
VenueOpsService | updateResource | response | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | updateResource | response | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | updateResource | response | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | updateResource | response | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | updateResource | response | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | updateResource | response | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | updateResource | response | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | updateResource | response | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | updateResource | response | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | updateResource | response | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | response | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateResource | response | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | updateResource | response | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResource | response | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResource | response | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResource | response | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResource | response | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | updateResource | response | isActive | boolean |  | (default True)
VenueOpsService | updateResource | param (path) | resourceId | string (uuid) | yes
VenueOpsService | updateResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateResourcePackage | request | id | string (uuid)
VenueOpsService | updateResourcePackage | request | code | string | yes
VenueOpsService | updateResourcePackage | request | name | string | yes
VenueOpsService | updateResourcePackage | request | description | string |  | (nullable)
VenueOpsService | updateResourcePackage | request | applicableVenueIds | array of string (uuid)
VenueOpsService | updateResourcePackage | request | components | array of ResourceRequirement
VenueOpsService | updateResourcePackage | request | components[].id | string (uuid)
VenueOpsService | updateResourcePackage | request | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | request | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | request | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | updateResourcePackage | request | components[].quantity | integer | yes | (default 1)
VenueOpsService | updateResourcePackage | request | components[].mandatory | boolean |  | (default True)
VenueOpsService | updateResourcePackage | request | components[].requiredQualifications | array of string
VenueOpsService | updateResourcePackage | request | components[].requiredAttributes | object
VenueOpsService | updateResourcePackage | request | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | updateResourcePackage | request | components[].scopePath | string
VenueOpsService | updateResourcePackage | request | allocationPriority | integer |  | (default 0)
VenueOpsService | updateResourcePackage | request | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | request | effectiveTo | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | request | minimumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | request | maximumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | request | requiresApproval | boolean |  | (default False)
VenueOpsService | updateResourcePackage | request | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResourcePackage | request | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResourcePackage | request | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResourcePackage | request | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResourcePackage | request | scopePath | string
VenueOpsService | updateResourcePackage | response | id | string (uuid)
VenueOpsService | updateResourcePackage | response | code | string | yes
VenueOpsService | updateResourcePackage | response | name | string | yes
VenueOpsService | updateResourcePackage | response | description | string |  | (nullable)
VenueOpsService | updateResourcePackage | response | applicableVenueIds | array of string (uuid)
VenueOpsService | updateResourcePackage | response | components | array of ResourceRequirement
VenueOpsService | updateResourcePackage | response | components[].id | string (uuid)
VenueOpsService | updateResourcePackage | response | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | response | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | updateResourcePackage | response | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | updateResourcePackage | response | components[].quantity | integer | yes | (default 1)
VenueOpsService | updateResourcePackage | response | components[].mandatory | boolean |  | (default True)
VenueOpsService | updateResourcePackage | response | components[].requiredQualifications | array of string
VenueOpsService | updateResourcePackage | response | components[].requiredAttributes | object
VenueOpsService | updateResourcePackage | response | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | updateResourcePackage | response | components[].scopePath | string
VenueOpsService | updateResourcePackage | response | allocationPriority | integer |  | (default 0)
VenueOpsService | updateResourcePackage | response | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | response | effectiveTo | string (date) |  | (nullable)
VenueOpsService | updateResourcePackage | response | minimumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | response | maximumMinutes | integer |  | (nullable)
VenueOpsService | updateResourcePackage | response | requiresApproval | boolean |  | (default False)
VenueOpsService | updateResourcePackage | response | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | updateResourcePackage | response | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | updateResourcePackage | response | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | updateResourcePackage | response | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | updateResourcePackage | response | scopePath | string
VenueOpsService | updateResourcePackage | param (path) | packageId | string (uuid) | yes
VenueOpsService | updateResourcePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | updateSaleBoard | request | id | string (uuid) | yes | (read-only)
TenancyService | updateSaleBoard | request | code | string | yes | (max length 64)
TenancyService | updateSaleBoard | request | name | string | yes | (max length 200)
TenancyService | updateSaleBoard | request | venueId | string (uuid) | yes
TenancyService | updateSaleBoard | request | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | updateSaleBoard | request | pages | array of object | yes | (min items 1)
TenancyService | updateSaleBoard | request | pages[].name | string | yes
TenancyService | updateSaleBoard | request | pages[].sortOrder | integer | yes
TenancyService | updateSaleBoard | request | pages[].tiles | array of object | yes
TenancyService | updateSaleBoard | request | pages[].tiles[].position | integer | yes
TenancyService | updateSaleBoard | request | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | updateSaleBoard | request | pages[].tiles[].variantId | string (uuid) |  | (nullable)
TenancyService | updateSaleBoard | request | pages[].tiles[].label | string
TenancyService | updateSaleBoard | request | pages[].tiles[].colour | string |  | (nullable)
TenancyService | updateSaleBoard | request | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | updateSaleBoard | request | isActive | boolean
TenancyService | updateSaleBoard | response | id | string (uuid) | yes | (read-only)
TenancyService | updateSaleBoard | response | code | string | yes | (max length 64)
TenancyService | updateSaleBoard | response | name | string | yes | (max length 200)
TenancyService | updateSaleBoard | response | venueId | string (uuid) | yes
TenancyService | updateSaleBoard | response | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | updateSaleBoard | response | pages | array of object | yes | (min items 1)
TenancyService | updateSaleBoard | response | pages[].name | string | yes
TenancyService | updateSaleBoard | response | pages[].sortOrder | integer | yes
TenancyService | updateSaleBoard | response | pages[].tiles | array of object | yes
TenancyService | updateSaleBoard | response | pages[].tiles[].position | integer | yes
TenancyService | updateSaleBoard | response | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | updateSaleBoard | response | pages[].tiles[].variantId | string (uuid) |  | (nullable)
TenancyService | updateSaleBoard | response | pages[].tiles[].label | string
TenancyService | updateSaleBoard | response | pages[].tiles[].colour | string |  | (nullable)
TenancyService | updateSaleBoard | response | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | updateSaleBoard | response | isActive | boolean
TenancyService | updateSaleBoard | param (path) | saleBoardId | string (uuid) | yes
TenancyService | updateSaleBoard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | updateTableReservation | request | id | string (uuid) |  | (read-only)
FnbService | updateTableReservation | request | outletId | string (uuid) | yes
FnbService | updateTableReservation | request | subjectId | string (uuid) |  | (nullable)
FnbService | updateTableReservation | request | guestName | string
FnbService | updateTableReservation | request | contactPoint | string
FnbService | updateTableReservation | request | partySize | integer | yes | (min 1)
FnbService | updateTableReservation | request | startsAt | string (date-time) | yes
FnbService | updateTableReservation | request | durationMinutes | integer |  | How long the cover is held.
FnbService | updateTableReservation | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | updateTableReservation | request | tables[].reservationId | string (uuid) | yes
FnbService | updateTableReservation | request | tables[].tableId | string (uuid) | yes
FnbService | updateTableReservation | request | tables[].createdAt | string (date-time) | yes
FnbService | updateTableReservation | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | updateTableReservation | request | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | updateTableReservation | request | notes | string |  | Allergies
FnbService | updateTableReservation | request | actualPartySize | integer |  | (read-only; nullable)
FnbService | updateTableReservation | request | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | updateTableReservation | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | updateTableReservation | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateTableReservation | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableReservation | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableReservation | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableReservation | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | updateTableReservation | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | updateTableReservation | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | updateTableReservation | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | updateTableReservation | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | updateTableReservation | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | updateTableReservation | request | createdAt | string (date-time) |  | (read-only)
FnbService | updateTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | updateTableReservation | response | outletId | string (uuid) | yes
FnbService | updateTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | updateTableReservation | response | guestName | string
FnbService | updateTableReservation | response | contactPoint | string
FnbService | updateTableReservation | response | partySize | integer | yes | (min 1)
FnbService | updateTableReservation | response | startsAt | string (date-time) | yes
FnbService | updateTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | updateTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | updateTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | updateTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | updateTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | updateTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | updateTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | updateTableReservation | response | notes | string |  | Allergies
FnbService | updateTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | updateTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | updateTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | updateTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | updateTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | updateTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | updateTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | updateTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | updateTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | updateTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | updateTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | updateTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | updateTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | updateTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | updateTableReservation | param (path) | reservationId | string (uuid) | yes
FnbService | updateTableReservation | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | updateTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | updateTaxCode | request | name | string |  | (max length 200)
LedgerService | updateTaxCode | request | rate | number |  | (min 0; max 100)
LedgerService | updateTaxCode | request | effectiveFrom | string (date) |  | Required with rate, and only meaningful with it.
LedgerService | updateTaxCode | request | isActive | boolean
LedgerService | updateTaxCode | response | id | string (uuid) | yes
LedgerService | updateTaxCode | response | code | string | yes | (max length 64)
LedgerService | updateTaxCode | response | name | string | yes | (max length 200)
LedgerService | updateTaxCode | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | updateTaxCode | response | appliesTo | array of enum (goods, services, admission, food, accommodation, donation, gratuity, fee) |  | What this code covers, and donation is why the field exists (CF-84).
LedgerService | updateTaxCode | response | rate | number | yes | (min 0; max 100)
LedgerService | updateTaxCode | response | compoundOnTaxCodeId | string (uuid) |  | When set, this tax applies to the base plus the referenced tax, not to the base alone. (nullable)
LedgerService | updateTaxCode | response | isInclusive | boolean |  | True when the displayed price already contains this tax.
LedgerService | updateTaxCode | response | accountId | string (uuid)
LedgerService | updateTaxCode | response | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | updateTaxCode | response | effectiveTo | string (date) |  | A day in the region's time zone, local midnight to local midnight. (nullable)
LedgerService | updateTaxCode | response | isActive | boolean | yes
LedgerService | updateTaxCode | param (path) | taxCodeId | string (uuid) | yes
LedgerService | updateTaxCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | updateTenant | request | name | string |  | (max length 200)
PlatformService | updateTenant | request | billingEmail | string
PlatformService | updateTenant | request | billingAddress | string |  | (max length 500)
PlatformService | updateTenant | request | accountManagerPrincipalId | string (uuid)
PlatformService | updateTenant | response | id | string (uuid) | yes
PlatformService | updateTenant | response | code | string | yes
PlatformService | updateTenant | response | name | string | yes
PlatformService | updateTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | updateTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | updateTenant | response | suspensionReason | string |  | (nullable)
PlatformService | updateTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | updateTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | updateTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | updateTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | updateTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | updateTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | updateTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | updateTenant | response | planName | string |  | (nullable)
PlatformService | updateTenant | response | cellCount | integer
PlatformService | updateTenant | response | venueCount | integer
PlatformService | updateTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | updateTenant | response | billingEmail | string
PlatformService | updateTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | updateTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | updateTenant | response | createdAt | string (date-time) | yes
PlatformService | updateTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | updateTenant | param (path) | tenantId | string (uuid) | yes
PlatformService | updateTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | updateTicketTemplate | request | name | string |  | (max length 200)
OrderService | updateTicketTemplate | request | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms)
OrderService | updateTicketTemplate | request | isRecyclable | boolean
OrderService | updateTicketTemplate | request | recycleAfterDays | integer |  | (min 0; nullable)
OrderService | updateTicketTemplate | request | appliesToProductKinds | array of string
OrderService | updateTicketTemplate | request | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | updateTicketTemplate | request | selectionPriority | integer
OrderService | updateTicketTemplate | request | layoutRef | string |  | The artwork, as a media-asset reference.
OrderService | updateTicketTemplate | request | localeVariants | object
OrderService | updateTicketTemplate | request | isActive | boolean
OrderService | updateTicketTemplate | response | id | string (uuid) | yes
OrderService | updateTicketTemplate | response | name | string | yes
OrderService | updateTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | updateTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | updateTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | updateTicketTemplate | response | appliesToProductKinds | array of string
OrderService | updateTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | updateTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | updateTicketTemplate | response | layoutRef | string
OrderService | updateTicketTemplate | response | localeVariants | object
OrderService | updateTicketTemplate | response | isActive | boolean | yes
OrderService | updateTicketTemplate | param (path) | templateId | string (uuid) | yes
OrderService | updateTicketTemplate | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
OrderService | updateTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateTransportRoute | request | name | LocalisedText
VenueOpsService | updateTransportRoute | request | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | updateTransportRoute | request | pairedRouteId | string (uuid) |  | (nullable)
VenueOpsService | updateTransportRoute | request | bookingCutoffMinutes | integer |  | (min 0; max 1440)
VenueOpsService | updateTransportRoute | request | stops | array of RouteStopInput |  | (min items 2)
VenueOpsService | updateTransportRoute | request | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | request | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | updateTransportRoute | request | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | request | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | updateTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | updateTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | updateTransportRoute | response | name | LocalisedText | yes
VenueOpsService | updateTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | updateTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | updateTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | updateTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | updateTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | updateTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | updateTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | updateTransportRoute | response | stops[].station | Station
VenueOpsService | updateTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | updateTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | updateTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | updateTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | updateTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | updateTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | updateTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | updateTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | updateTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | updateTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | updateTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | updateTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | updateTransportRoute | param (path) | routeId | string (uuid) | yes
VenueOpsService | updateTransportRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | updateVisitPlan | request | baseVersion | integer | yes | (min 1)
VenueOpsService | updateVisitPlan | request | changes | array of object | yes | (min items 1; max items 20)
VenueOpsService | updateVisitPlan | request | changes[].op | enum (swap, remove, add, move, pin, acceptAddOn, declineAddOn, revertTo) | yes
VenueOpsService | updateVisitPlan | request | changes[].itemId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].date | string (date) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].pointId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].startsAt | string (date-time) |  | (nullable)
VenueOpsService | updateVisitPlan | request | changes[].version | integer |  | For revertTo, the earlier version to restore (undo). (nullable)
VenueOpsService | updateVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | updateVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | updateVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | updateVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | updateVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | updateVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | updateVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | updateVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | updateVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | updateVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | updateVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | updateVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | updateVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | updateVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | updateVisitPlan | response | inputs.pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | updateVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | updateVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | updateVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | updateVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | updateVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | updateVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | updateVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | updateVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | updateVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | updateVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | updateVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | updateVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | updateVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | updateVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | updateVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | updateVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | updateVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | updateVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | updateVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | updateVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | updateVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | updateVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | updateVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | updateVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | updateVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | updateVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | updateVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | updateVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | updateVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | updateVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | updateVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | updateVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | uploadGuestDocument | request | id | string (uuid) | yes | (read-only)
MarketingService | uploadGuestDocument | request | subjectId | string (uuid) | yes
MarketingService | uploadGuestDocument | request | kind | enum (avatar, idDocument, visa, signedWaiver, medicalNote, accessibilityEvidence, photo, other) | yes
MarketingService | uploadGuestDocument | request | storageRef | string | yes | The stored object's key in the guest-document store, which is deliberately not assets (BL-133).
MarketingService | uploadGuestDocument | request | contentType | string
MarketingService | uploadGuestDocument | request | consentPurposeId | string (uuid)
MarketingService | uploadGuestDocument | request | retainUntil | string (date) | yes | Required, not optional.
MarketingService | uploadGuestDocument | request | uploadedAt | string (date-time) |  | (read-only)
MarketingService | uploadGuestDocument | request | uploadedByPrincipalId | string (uuid) |  | (read-only; nullable)
MarketingService | uploadGuestDocument | response | id | string (uuid) | yes | (read-only)
MarketingService | uploadGuestDocument | response | subjectId | string (uuid) | yes
MarketingService | uploadGuestDocument | response | kind | enum (avatar, idDocument, visa, signedWaiver, medicalNote, accessibilityEvidence, photo, other) | yes
MarketingService | uploadGuestDocument | response | storageRef | string | yes | The stored object's key in the guest-document store, which is deliberately not assets (BL-133).
MarketingService | uploadGuestDocument | response | contentType | string
MarketingService | uploadGuestDocument | response | consentPurposeId | string (uuid)
MarketingService | uploadGuestDocument | response | retainUntil | string (date) | yes | Required, not optional.
MarketingService | uploadGuestDocument | response | uploadedAt | string (date-time) |  | (read-only)
MarketingService | uploadGuestDocument | response | uploadedByPrincipalId | string (uuid) |  | (read-only; nullable)
MarketingService | uploadGuestDocument | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | validateBookingFlow | request | steps | array of BookingFlowStep |  | (max items 30)
WhiteLabelService | validateBookingFlow | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | validateBookingFlow | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | validateBookingFlow | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | validateBookingFlow | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | validateBookingFlow | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | validateBookingFlow | response | valid | boolean | yes
WhiteLabelService | validateBookingFlow | response | problems | array of object | yes
WhiteLabelService | validateBookingFlow | response | problems[].kind | enum (requiredStepDisabled, orderConstraintBroken, conditionNeverHolds, stepNotInType, duplicateStep, unknownStepSetting) | yes
WhiteLabelService | validateBookingFlow | response | problems[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | validateBookingFlow | response | problems[].otherStepKey | object |  | For orderConstraintBroken, the step it must come before or after. (nullable)
WhiteLabelService | validateBookingFlow | response | problems[].message | string | yes
WhiteLabelService | validateBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | validateBookingFlow | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | validateTenantConfig | response | passed | boolean | yes
WhiteLabelService | validateTenantConfig | response | errorCount | integer | yes
WhiteLabelService | validateTenantConfig | response | warningCount | integer | yes
WhiteLabelService | validateTenantConfig | response | findings | array of object | yes
WhiteLabelService | validateTenantConfig | response | findings[].kind | ConfigFindingKind: enum (missingTranslation, navigationTargetsDisabledModule, homepageReferencesMissingContent, contrastFailure, missingRequiredAsset, policyVersionMissing, noVisibleNavigationItems, unlicensedModuleEnabled, …) | yes
WhiteLabelService | validateTenantConfig | response | findings[].severity | enum (error, warning) | yes
WhiteLabelService | validateTenantConfig | response | findings[].message | string | yes
WhiteLabelService | validateTenantConfig | response | findings[].area | string
WhiteLabelService | validateTenantConfig | response | findings[].reference | string |  | (nullable)
WhiteLabelService | validateTenantConfig | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | verifyCustomDomain | response | id | string (uuid) | yes
WhiteLabelService | verifyCustomDomain | response | tenantId | string (uuid) | yes
WhiteLabelService | verifyCustomDomain | response | hostname | string | yes
WhiteLabelService | verifyCustomDomain | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal)
WhiteLabelService | verifyCustomDomain | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | verifyCustomDomain | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | verifyCustomDomain | response | verificationToken | string |  | (read-only)
WhiteLabelService | verifyCustomDomain | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | verifyCustomDomain | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | verifyCustomDomain | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | verifyCustomDomain | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | verifyCustomDomain | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | verifyCustomDomain | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | verifyCustomDomain | response | failureReason | string |  | (nullable)
WhiteLabelService | verifyCustomDomain | param (path) | domainId | string (uuid) | yes
WhiteLabelService | verifyCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyGuestEmail | request | mode | enum (send, confirm) | yes
IdentityService | verifyGuestEmail | request | token | string |  | For confirm. (nullable)
IdentityService | verifyGuestEmail | response | isVerified | boolean
IdentityService | verifyGuestEmail | response | expiresAt | string (date-time) |  | (nullable)
IdentityService | verifyGuestEmail | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyGuestOtp | request | identifier | string | yes
IdentityService | verifyGuestOtp | request | code | string | yes | (min length 4; max length 10)
IdentityService | verifyGuestOtp | request | deviceId | string
IdentityService | verifyGuestOtp | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | verifyGuestOtp | response | subjectId | string (uuid) | yes
IdentityService | verifyGuestOtp | response | displayName | string |  | (nullable)
IdentityService | verifyGuestOtp | response | tokens | TokenPair | yes
IdentityService | verifyGuestOtp | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | verifyGuestOtp | response | tokens.refreshToken | string | yes
IdentityService | verifyGuestOtp | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | verifyGuestOtp | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | verifyGuestOtp | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | verifyGuestOtp | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | verifyGuestOtp | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | verifyGuestOtp | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | verifyGuestOtp | response | mfaMethods[].id | string (uuid) | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].label | string |  | (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | verifyGuestOtp | response | mfaMethods[].isActive | boolean | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].isPrimary | boolean
IdentityService | verifyGuestOtp | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | verifyGuestOtp | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | verifyGuestOtp | response | homeCellName | string |  | (nullable)
IdentityService | verifyGuestOtp | response | preferredLanguage | string |  | (nullable)
IdentityService | verifyGuestOtp | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | verifyGuestOtp | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyMfaChallenge | request | code | string | yes
IdentityService | verifyMfaChallenge | response | stepUpToken | string |  | Null for a signIn challenge. (nullable)
IdentityService | verifyMfaChallenge | response | expiresAt | string (date-time)
IdentityService | verifyMfaChallenge | response | session | object |  | Only for a signIn challenge, and only where no role selection is still owed. (nullable)
IdentityService | verifyMfaChallenge | response | session.sessionId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.principalId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.roleId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.displayName | string
IdentityService | verifyMfaChallenge | response | session.scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | verifyMfaChallenge | response | session.scope[].id | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | verifyMfaChallenge | response | session.scope[].path | string | yes | Materialised ltree path.
IdentityService | verifyMfaChallenge | response | session.scope[].code | string |  | (nullable)
IdentityService | verifyMfaChallenge | response | session.scope[].name | string |  | (nullable)
IdentityService | verifyMfaChallenge | response | session.effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | verifyMfaChallenge | response | session.permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path.
IdentityService | verifyMfaChallenge | response | session.permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | verifyMfaChallenge | response | session.permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | verifyMfaChallenge | response | session.saleBoardId | string (uuid) | yes | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | verifyMfaChallenge | response | session.workstation | WorkstationContext
IdentityService | verifyMfaChallenge | response | session.workstation.id | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.workstation.code | string | yes
IdentityService | verifyMfaChallenge | response | session.workstation.venueId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.workstation.regionId | string (uuid) | yes
IdentityService | verifyMfaChallenge | response | session.workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | verifyMfaChallenge | response | session.workstation.devices | array of object
IdentityService | verifyMfaChallenge | response | session.workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | verifyMfaChallenge | response | session.workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | verifyMfaChallenge | response | session.workstation.timezone | string
IdentityService | verifyMfaChallenge | response | session.workstation.cellName | string |  | The cell serving this workstation's region.
IdentityService | verifyMfaChallenge | response | session.workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | verifyMfaChallenge | response | session.openedAt | string (date-time)
IdentityService | verifyMfaChallenge | response | session.expiresAt | string (date-time)
IdentityService | verifyMfaChallenge | param (path) | challengeId | string | yes
IdentityService | verifyMfaChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | verifyMfaEnrolment | request | code | string | yes
IdentityService | verifyMfaEnrolment | response | id | string (uuid) | yes
IdentityService | verifyMfaEnrolment | response | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | verifyMfaEnrolment | response | label | string |  | (nullable)
IdentityService | verifyMfaEnrolment | response | maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | verifyMfaEnrolment | response | isActive | boolean | yes
IdentityService | verifyMfaEnrolment | response | isPrimary | boolean
IdentityService | verifyMfaEnrolment | response | enrolledAt | string (date-time) | yes
IdentityService | verifyMfaEnrolment | response | lastUsedAt | string (date-time) |  | (nullable)
IdentityService | verifyMfaEnrolment | param (path) | methodId | string (uuid) | yes
IdentityService | verifyMfaEnrolment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | voidOrder | request | id | string (uuid) | yes | Client-generated UUIDv7 of this void, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | voidOrder | request | reason | VoidReason: enum (guestChangedMind, enteredInError, itemUnavailable, qualityIssue, duplicate, other) | yes | The void reason list (decided 28 September, audit R125 (4)): the one list voidOrder takes, and the list fnb.amendFnbOrder and fnb.cancelFnbOrder point to.
OrderService | voidOrder | request | note | string |  | Required when reason is other (audit R222); optional otherwise. (min length 3; max length 500; nullable)
OrderService | voidOrder | request | recordedAt | string (date-time) | yes
OrderService | voidOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | voidOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | voidOrder | response | channel | object | yes | Where it came from.
OrderService | voidOrder | response | venueId | string (uuid) | yes
OrderService | voidOrder | response | scopePath | string | yes
OrderService | voidOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | voidOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | voidOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | voidOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | voidOrder | response | droppedPromotions[].name | string
OrderService | voidOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | voidOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | voidOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines | array of OrderLine | yes
OrderService | voidOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | voidOrder | response | lines[].variantId | string (uuid) | yes
OrderService | voidOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | voidOrder | response | lines[].performanceId | string (uuid)
OrderService | voidOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | voidOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | voidOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | voidOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | voidOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | voidOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | voidOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | voidOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | voidOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | voidOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | voidOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | voidOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | voidOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].holderName | string |  | (nullable)
OrderService | voidOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | voidOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | voidOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | voidOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | voidOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | voidOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | voidOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | voidOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | voidOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | voidOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | voidOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | voidOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | voidOrder | response | payments | array of Payment
OrderService | voidOrder | response | payments[].id | string (uuid) | yes
OrderService | voidOrder | response | payments[].orderId | string (uuid) | yes
OrderService | voidOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | voidOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | voidOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | voidOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | voidOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | voidOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | voidOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | voidOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | voidOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | voidOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | voidOrder | response | payments[].providerName | string |  | (nullable)
OrderService | voidOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | voidOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | voidOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | voidOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | voidOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | voidOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | voidOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | voidOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | voidOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | voidOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | voidOrder | response | principalId | string (uuid)
OrderService | voidOrder | response | workstationId | string (uuid)
OrderService | voidOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | voidOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | voidOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | voidOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | voidOrder | response | createdAt | string (date-time) | yes
OrderService | voidOrder | response | recordedAt | string (date-time) | yes
OrderService | voidOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | voidOrder | param (path) | orderId | string (uuid) | yes
OrderService | voidOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | withdrawFromDepositBox | request | id | string (uuid) | yes | Client-generated UUIDv7 of the CashMovement this records.
OrderService | withdrawFromDepositBox | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | request | witnessPrincipalId | string (uuid) | yes | The cashier the cash came from.
OrderService | withdrawFromDepositBox | request | reason | WithdrawalReason: enum (banking, safeDrop, changeOrder, other) |  | Why a supervisor took cash out of a box.
OrderService | withdrawFromDepositBox | request | note | string |  | (max length 300)
OrderService | withdrawFromDepositBox | request | recordedAt | string (date-time) | yes
OrderService | withdrawFromDepositBox | response | id | string (uuid) |  | (read-only)
OrderService | withdrawFromDepositBox | response | cashierPrincipalId | string (uuid) | yes
OrderService | withdrawFromDepositBox | response | cashierName | string |  | (read-only)
OrderService | withdrawFromDepositBox | response | venueId | string (uuid) | yes
OrderService | withdrawFromDepositBox | response | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | withdrawFromDepositBox | response | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | withdrawFromDepositBox | response | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | withdrawFromDepositBox | response | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | openingDenominations | array of object |  | 5.8.3.
OrderService | withdrawFromDepositBox | response | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | withdrawFromDepositBox | response | openingDenominations[].count | integer | yes | (min 0)
OrderService | withdrawFromDepositBox | response | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | withdrawFromDepositBox | response | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | withdrawFromDepositBox | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | withdrawFromDepositBox | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | withdrawFromDepositBox | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | withdrawFromDepositBox | response | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | withdrawFromDepositBox | response | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | withdrawFromDepositBox | response | closedAt | string (date-time) |  | (nullable)
OrderService | withdrawFromDepositBox | param (path) | boxId | string (uuid) | yes
OrderService | withdrawFromDepositBox | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.

## Occupancy
Person | Backend and DevOps tasks | Points
Hrushikant Patkar | 83 | 540
Pranay Shinde | 66 | 457
Tanmay Dukhande | 75 | 453
Deep Khanvilkar | 58 | 287
Sanket Keluskar | 63 | 189
Chinmay Patkar | 71 | 120
Pradnya Yeram | 1 | 8