## Ask the client
# | Theme | The question | Why we are asking | What it blocks | Affects | First release (POS, Guest App, White Labelling) | Who answers | Answer | Answered on
CF-35 | Biometrics and PDPL | Does a consent notice acknowledged at a counter satisfy PDPL's 'explicit consent' for a same-visit Face Tag, or is a signature required? | Requirement 3.2.44 says Face Tag does not require a signed consent form. PDPL Article 4's exceptions are an exhaustive list with no legitimate-interests basis, so we built it requiring explicit consent anyway and recorded the deviation. | A signature is not operable at a gate. The answer changes the gate flow, not the schema. | Face Pass, facial readers, fingerprint enrolment | Yes: Face Pass enrolment is on the guest mobile app | Client counsel
CF-127 | Cookie consent | Do we build cookie consent, buy it, or drop it? | 2.6.51-2.6.65 ask for banner, categorisation, automatic site scanning for new third-party cookies, script blocking before consent, preference centre, consent records and an admin portal. 2.6.60 names GDPR, ePrivacy, CCPA, CPRA, LGPD and PDPL. | Scanning means maintaining a cookie database as third-party tags change. Buying puts a vendor on every tenant storefront, which is a data-residency question. Dropping is only available if no storefront sets a non-essential cookie. | Every tenant storefront | Yes: the guest web storefront | Client
CF-133 | UAE tax invoice | What must a compliant UAE tax invoice and credit memo contain, and is e-invoicing in the delivery window? | 5.10.3 requires 'all required fields in accordance with VAT regulations' and nothing states what those fields are. We hold the TRN, compound tax and inclusive treatment; the document itself does not exist. | Issuing a non-compliant invoice is an audit finding. Gapless sequential numbering also has to be decided per legal entity, per venue or per till. | Finance, POS receipts, refunds | Yes: POS receipts and refunds | Client finance
CF-140 | Delivery plan priorities | Can priorities be re-derived from the dependency matrix rather than from requirement counts? | Resource Management is P3 (Could) and is the most-depended-on gap in the walk - rentals, lockers, cabanas, instructor assignment and maintenance planning all sit behind it. Access Control is also P3 at 114 requirements. | A P3 prerequisite blocks every P1 that needs it. Notifications, Loyalty and Portfolio each appear at P1, P2 and P3, which is not a schedulable statement. | The whole schedule | Yes: the order everything is built in | Client + us
CF-162 | Flash-sale environment | How does a burst environment's data come back into the permanent platform? | A dedicated environment for a large sale takes tens of thousands of concurrent users for hours and then goes away. Its shape is settled; the reconciliation path is not. | Orders taken there have to land in the permanent platform afterwards, and that path has no design. | Flash sales, mega events | Later | Client + us
CF-165 | Retention and archival | Confirm the retention periods per data class so the archival rules can be built. | The policy is decided (ADR-0047) and not yet built. The archive is a separate instance, and derived stores purge at archive rather than at erasure. | Five contract changes are named and ordered. No erase operation exists yet. | Guest profiles, PII, the knowledge base | Yes: guest profiles and account deletion on the guest apps | Client
CF-169 | Dashboard authoring | Confirm who builds and edits dashboards, and whether a shared dashboard can be deleted. | 57 command centres become rows in a dashboard table, which needs three or four authoring screens that do not exist. There is also no delete operation. | The editor must surface the cost of a tile: 24 tiles on a short refresh is a performance incident nobody was warned about. | Reporting across every module | Later: back-office dashboards | Client + us
CF-170 | Approve-but-cannot-publish | On five screens, what happens after an approval - who publishes, and when does it go live? | BO-293, BO-353, ADM-247, CMS-030 and CMS-050 each declare only an approve step against a title ending in Publication. An approval with nothing to release is a dead end. | The approve operations are themselves provisional, so the approval step is not agreed either. This folds into the 577. | Membership, media, versioning, privacy, waivers | Later: none of the five screens is in the first release | Client
CF-171 | 577 unagreed operations | Will you review the 4 operations we drafted from your design packs, pack by pack? | Each cites the pack and page it came from and every citation resolves to a real page. They are drafts read out of a PDF, not agreed API. | They are 0% of the 2660 operations and exactly the ones with no data lineage. Nothing behind them can be built until they are agreed. | Back office: P08, P09, P10, P12, P13 | Later: none is in the first release | Client + us
PK | (no citation) | (no citation): confirm the 3 screens we drafted from pages -. We read 24 of your bullets as fields and set aside 26 as prose - were any of those 26 actually fields? | Every operation from this pack cites its page and carries your own sentence describing the screen. Names and types are our reading of those sentences; the sentences are yours. | 3 operations stay unagreed, and none of them can have its tables resolved until the shape is settled. | P08 (3) | Later | Client
PK | Ticket Resale Marketplace | Ticket Resale Marketplace: confirm the 1 screens we drafted from pages 32. We read 31 of your bullets as fields and set aside 9 as prose - were any of those 9 actually fields? | Every operation from this pack cites its page and carries your own sentence describing the screen. Names and types are our reading of those sentences; the sentences are yours. | 1 operations stay unagreed, and none of them can have its tables resolved until the shape is settled. | P09 (1) | Later | Client
SC-1 | AI configuration assistant | Is the AI Configuration Assistant in this delivery? 0 screens - setup discovery, guided Q&A, blueprint, execution, rollback and audit. | These screens name no operation at all. This is not an unagreed draft - there is no contract behind them. | If it is in, it needs contracts written from scratch. It is the largest single piece of undone design in the package. | P09 TICVAI Web | Later | Client
SC-2 | Forecasting | Is Forecasting in this delivery? 0 screens with no operation behind them. | Same shape as the AI assistant: screens exist, contracts do not. | Demand and revenue forecasting touches pricing, capacity and staffing. | P09 TICVAI Web | Later | Client
SC-3 | AI governance and oversight | Is AI governance in this delivery? 1 screens - capability registry, risk classification, policy builder, approval review. | The ai contract has 31 operations in total, against 1 screens of AI product with nothing behind them. | Governance of an AI feature has to exist before the feature ships, not after. | P09 TICVAI Web | Later | Client
SC-4 | Payroll — settled, listed for confirmation only | Payroll is out of scope and HR is taken as an externally mastered projection. Confirm only if you disagree. | Not a question we are asking. Your Resource Management pack, Board 3 page 45, names HRMS, Payroll and Time & Attendance as integration sources, and the requirement matrix has no row mentioning payroll, payslip, salary, wage or HRMS on any of five sheets. | Nothing. Seven payroll tables are declined and seven HR tables are taken as a projection, with the field-ownership and sync layer Board 3 requires. | Workforce, finance | Later | Client (confirm only)
SC-5 | Column prefixes | Do you want every column prefixed with its table name, and if so what is the reason? | You prefix code as access_point_code and id as <table>_id on 193 tables. We do not, because access.access_point.code is unambiguous inside its own row. | One decision disposes of 645 of your 743 change rows, and 21 table renames with it. | The whole schema | Yes: every table | Client backend
SC-6 | platform.scope | Confirm you are happy for the scope hierarchy to stay one table rather than five. | We are taking your name. Nine scope levels are enumerated and ADR-0011 makes the hierarchy binding. | Five typed tables make adding a level a new table rather than a new row. | Tenancy, everything below it | Yes: every table | Client backend

## By pack
Client design pack | Screens drafted | Pages cited | Bullets read as fields | Bullets set aside | Contracts | Platforms | In the first release
(no citation) | 3 | - | 24 | 26 | access | P08 (3)
Ticket Resale Marketplace | 1 | 32 | 31 | 9 | orders | P09 (1)

## Screens
Pack | Page | Screen / operation | What your screen says | Contract | Fields read | Bullets set aside | Operation id | In the first release | Answer
(no citation) |  | Biometric Consent & Guardian Management | Manage consent requirements associated with persistent biometric enrollment. The matrix requires App users to provide consent before Face Pass registration and requires guardian consent for minors. On-site enrollment also requires consent before facial data is captured. | access | 15 | 15 | listBiometricConsentGuardian
(no citation) |  | Biometric Lifecycle, Retention & Deletion | Manage biometric-data lifecycle and deletion rules. | access | 9 | 11 | listBiometricLifecycleRetention
(no citation) |  | Save a biometric retention rule |  | access | 0 | 0 | setBiometricLifecycleRetention
Ticket Resale Marketplace | 32 | Refunds, Disputes & Resale Exceptions | Handle exceptional scenarios that occur after a resale transaction. | orders | 31 | 9 | listRefundDisputeResale

## No contract
Product family | Platform | Screen | Screen name | Answer
AI governance and human oversight | P09 | ADM-618 | Refund Simulator, Risk Analysis & AI Advisor\t126
Other | P02 | GST-043 | Arabic / RTL Experience
Other | P05 | KSK-001 | Attract Loop
Other | P05 | KSK-014 | Out of service
Other | P06 | EMP-044 | Accessibility
Other | P06 | EMP-045 | Arabic / RTL
Other | P11 | ACC-001 | Landing / Programme Overview