## Summary
What | Value | How it is worked out
Start | 5 Oct 2026 | Block A starts Monday 5 October 2026 (decided 29 September).
Block A ends | 20 Nov 2026 | 35 working days: POS with Kitchen Display, Guest Web, Guest App, white label, Venue Management setup, AI that needs no history.
End of the six months | 2 Apr 2027 | Blocks B1, B2 and B3 run from 23 November to 2 April.
Forecast finish | 10 May 2027 | Where the scheduler places the last piece of work, with the team and pace below.
Sprints | 9 sprints of 3 weeks | The last sprint is 2 weeks, ending on 2 April.
Total effort | 16,238 points = 13,559 hours | Block A from its task sheet; Block B sized with Block A's formulas.
Block A | 3,431 points = 2,865 hours | The Block A task sheet as it stands.
Block B | 12,807 points = 10,694 hours | Screens by the Block A formula; back end at Block A's points per operation.
Pace | 9.58 points per developer per day | Block A's plan of record: 3,018 points, 35 days, 9 developers. Replaced by the measured pace on 23 October.
Hours per point | 0.835 | 8 hours a day divided by the pace.
Points per back-end operation | 2.26 | Block A's back-end points divided by its operations.
Team | 14 people | Chinmay Parab (lead) is not counted in capacity.
After month 6 | 0 screens | Only the wave-4 screens still marked deferred. Every AI function is built inside the six months (30 September); a trained model goes live per tenant after a season of its data.
Overtime to finish by 2 April | 1,991 hours | Work each person has past 2 April at normal hours; see People for hours per week.

## Sprints
Sprint | Starts | Ends | Working days | Block | Capacity (hours) | Planned (hours) | Used | Holidays | Modules worked on
Sprint 1 | 5 Oct 2026 | 23 Oct 2026 | 15 | Block A | 1392 | 982 | 71% |  | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Digital Asset Management, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations, Payments, Wallet & Cashless
Sprint 2 | 26 Oct 2026 | 13 Nov 2026 | 15 | Block A | 1392 | 1144 | 82% |  | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Digital Asset Management, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations, Payments, Wallet & Cashless, White Label & CMS
Sprint 3 | 16 Nov 2026 | 4 Dec 2026 | 12 | Block A ends, B1 starts | 1226 | 885 | 72% | 1 Dec 2026 Commemoration Day; 2 Dec 2026 National Day; 3 Dec 2026 National Day | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations, Payments, Wallet & Cashless, Food & Beverage, Retail, Inventory & Procurement
Sprint 4 | 7 Dec 2026 | 25 Dec 2026 | 15 | Block B | 1632 | 1393 | 85% |  | Foundation & Setup, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Digital Asset Management, Ticketing Catalogue & Products, Seat Management & Venue Maps, White Label & CMS, Transport, Food & Beverage, Retail, Inventory & Procurement, Resources & Capacity, Virtual Queue
Sprint 5 | 28 Dec 2026 | 15 Jan 2027 | 14 | Block B | 1523 | 1506 | 99% | 1 Jan 2027 New Year | Foundation & Setup, Digital Asset Management, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations, White Label & CMS, Food & Beverage, Retail, Admission & Access Control, Finance, Ledger & Tax, Reporting & Analytics, Marketing & CRM, AI & Intelligence
Sprint 6 | 18 Jan 2027 | 5 Feb 2027 | 15 | Block B | 1632 | 1629 | 100% |  | Foundation & Setup, Identity, Roles & Security, Subscription & Licensing, Developer Portal & Public API, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Transport, Food & Beverage, Retail, Inventory & Procurement, Accreditation, Resources & Capacity, Workforce & Staff, Maintenance & Safety
Sprint 7 | 8 Feb 2027 | 26 Feb 2027 | 15 | Block B | 1632 | 1632 | 100% |  | Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations, Payments, Wallet & Cashless, AI & Intelligence
Sprint 8 | 1 Mar 2027 | 19 Mar 2027 | 12 | Block B | 1306 | 1306 | 100% | 9 Mar 2027 Eid al-Fitr; 10 Mar 2027 Eid al-Fitr; 11 Mar 2027 Eid al-Fitr | Identity, Roles & Security, Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations, Payments, Wallet & Cashless, Food & Beverage, Rentals
Sprint 9 | 22 Mar 2027 | 2 Apr 2027 | 10 | Block B | 1088 | 1088 | 100% |  | Transport, Food & Beverage, Retail, Rentals, Inventory & Procurement, Admission & Access Control, Accreditation, Resources & Capacity, Finance, Ledger & Tax, AI & Intelligence

## Packages
Package | What it is | Modules | Requirements covered | Screens | Operations | Points | Hours | Block A hours | Block B hours | Starts | Expected completion | Lead | Team
Platform Foundation | Everything the apps stand on: sign-in, tenants and venues, devices, licensing, approvals, the public API. | 8 | 563 | 425 | 453 | 3130 | 2613 | 1062 | 1552 | 5 Oct 2026 | 24 Mar 2027 | Hrushikant Patkar | Hrushikant Patkar, Tanmay Dukhande, Pallavi Sawant, Surendra, New full-stack developer 2, New full-stack developer 1, Pradnya Yeram, Sanket Keluskar
Ticketing & Guest Commerce | What a guest buys and how: catalogue, pricing, seats and maps, orders, payments, wallet, the branded storefront and app. | 8 | 866 | 867 | 908 | 4363 | 3641 | 880 | 2763 | 5 Oct 2026 | 1 Apr 2027 | Tanmay Dukhande | Tanmay Dukhande, Chitrangi Mestry, Pranay Shinde, Deep Khanvilkar, Pradnya Yeram, Pallavi Sawant, Chinmay Patkar, New full-stack developer 1
Food, Beverage & Retail | Selling at the venue: F&B with the kitchen display, retail, rentals, stock and purchasing. | 4 | 224 | 216 | 267 | 1240 | 1034 | 340 | 695 | 6 Oct 2026 | 6 Apr 2027 | Pradnya Yeram | Pradnya Yeram, Chitrangi Mestry, Deep Khanvilkar, Pranay Shinde, New full-stack developer 1, Hrushikant Patkar, Chinmay Patkar, Sanket Keluskar
Venue Operations | Running the venue day to day: gates and access, accreditation, capacity, staff, maintenance, rides, queues. | 7 | 411 | 464 | 507 | 2356 | 1967 | 191 | 1777 | 12 Oct 2026 | 19 Apr 2027 | New full-stack developer 2 | New full-stack developer 2, Pallavi Sawant, Hrushikant Patkar, Chinmay Patkar, Sanket Keluskar, Chitrangi Mestry, Pranay Shinde, New full-stack developer 1
Finance & Insights | The money and the numbers: ledger, VAT and e-invoicing, reports and analytics. | 2 | 393 | 117 | 120 | 597 | 498 | 101 | 398 | 7 Oct 2026 | 3 May 2027 | Hrushikant Patkar | Hrushikant Patkar, Tanmay Dukhande, New full-stack developer 1, New full-stack developer 2, Chinmay Patkar, Pradnya Yeram, Pallavi Sawant, Sanket Keluskar
Customer & Marketing | Knowing and reaching the guest: CRM, segments, campaigns, loyalty, support. | 1 | 421 | 219 | 264 | 1126 | 940 | 177 | 763 | 21 Oct 2026 | 22 Apr 2027 | Pranay Shinde | Pranay Shinde, Deep Khanvilkar, Tanmay Dukhande, Surendra, Chinmay Patkar, Chitrangi Mestry, Pallavi Sawant, Pradnya Yeram
AI & Intelligence | The AI gateway and governance, the guest concierge, Help me choose, translations, the planner agent; forecasting, fraud and recommendations rules-first. | 1 | 287 | 137 | 141 | 3429 | 2863 | 114 | 2748 | 5 Oct 2026 | 10 May 2027 | Kalpita Mejari | Kalpita Mejari, Second AI engineer, Pranay Shinde, Sanket Keluskar, Deep Khanvilkar, Tanmay Dukhande, Pallavi Sawant, Chitrangi Mestry

## Modules
Package | Module | Requirements covered | Waiting on the client | Screens in A | Screens in B | Operations in A | Operations in B | Block A hours | Block B hours | Total hours | Starts | Expected completion | Sprints | Lead | Team
Platform Foundation | Foundation & Setup | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 840 | 5 Oct 2026 | 22 Jan 2027 | 1-6 | Hrushikant Patkar | Hrushikant Patkar, Surendra, Sanket Keluskar, Tanmay Dukhande, Pallavi Sawant, Pranay Shinde
Platform Foundation | Identity, Roles & Security | 144 | 0 | 9 | 22 | 37 | 52 | 83 | 162 | 245 | 5 Oct 2026 | 19 Mar 2027 | 1-8 | Deep Khanvilkar | Deep Khanvilkar, Surendra, Tanmay Dukhande, Chitrangi Mestry, Pallavi Sawant, Chinmay Patkar
Platform Foundation | Tenancy, Venues & Devices | 126 | 1 | 5 | 30 | 18 | 37 | 46 | 137 | 183 | 5 Oct 2026 | 17 Mar 2027 | 1-8 | New full-stack developer 2 | New full-stack developer 2, New full-stack developer 1, Hrushikant Patkar, Tanmay Dukhande, Pradnya Yeram, Deep Khanvilkar
Platform Foundation | Platform Operations | 4 | 0 | 0 | 12 | 0 | 51 | 7 | 126 | 133 | 12 Oct 2026 | 19 Mar 2027 | 1-8 | Pallavi Sawant | Pallavi Sawant, Pradnya Yeram, Pranay Shinde, New full-stack developer 1, Tanmay Dukhande, Chitrangi Mestry
Platform Foundation | Subscription & Licensing | 105 | 0 | 2 | 174 | 10 | 138 | 23 | 650 | 673 | 6 Oct 2026 | 24 Mar 2027 | 1-9 | New full-stack developer 2 | New full-stack developer 2, Hrushikant Patkar, Tanmay Dukhande, New full-stack developer 1, Chitrangi Mestry, Pallavi Sawant
Platform Foundation | Approval Workflows | 90 | 0 | 2 | 106 | 8 | 45 | 23 | 280 | 303 | 5 Oct 2026 | 22 Mar 2027 | 1-9 | Pradnya Yeram | Pradnya Yeram, Pranay Shinde, Pallavi Sawant, Chitrangi Mestry, New full-stack developer 1, Tanmay Dukhande
Platform Foundation | Developer Portal & Public API | 80 | 0 | 3 | 21 | 8 | 23 | 14 | 93 | 107 | 5 Oct 2026 | 19 Mar 2027 | 1-8 | Chitrangi Mestry | Chitrangi Mestry, New full-stack developer 2, New full-stack developer 1, Hrushikant Patkar, Deep Khanvilkar, Pallavi Sawant
Platform Foundation | Digital Asset Management | 14 | 0 | 1 | 38 | 10 | 16 | 26 | 104 | 129 | 12 Oct 2026 | 8 Jan 2027 | 1-5 | Surendra | Surendra, Tanmay Dukhande, New full-stack developer 2, Hrushikant Patkar, Chinmay Patkar, Deep Khanvilkar
Ticketing & Guest Commerce | Ticketing Catalogue & Products | 266 | 2 | 40 | 170 | 55 | 182 | 175 | 719 | 894 | 6 Oct 2026 | 22 Mar 2027 | 1-9 | Tanmay Dukhande | Tanmay Dukhande, Pallavi Sawant, New full-stack developer 1, Pranay Shinde, Chitrangi Mestry, Deep Khanvilkar
Ticketing & Guest Commerce | Pricing, Promotions & Bundles | 105 | 1 | 15 | 150 | 29 | 124 | 78 | 533 | 610 | 8 Oct 2026 | 25 Mar 2027 | 1-9 | Tanmay Dukhande | Tanmay Dukhande, Pallavi Sawant, Chinmay Patkar, Deep Khanvilkar, Chitrangi Mestry, Pradnya Yeram
Ticketing & Guest Commerce | Seat Management & Venue Maps | 100 | 0 | 12 | 93 | 20 | 55 | 73 | 272 | 344 | 12 Oct 2026 | 18 Mar 2027 | 1-8 | Hrushikant Patkar | Hrushikant Patkar, Pradnya Yeram, Pallavi Sawant, Surendra, Deep Khanvilkar, New full-stack developer 2
Ticketing & Guest Commerce | Orders & Reservations | 269 | 0 | 30 | 140 | 57 | 162 | 211 | 662 | 873 | 12 Oct 2026 | 25 Mar 2027 | 1-9 | Pranay Shinde | Pranay Shinde, Chitrangi Mestry, Deep Khanvilkar, Pradnya Yeram, Chinmay Patkar, Sanket Keluskar
Ticketing & Guest Commerce | Payments | 9 | 0 | 4 | 51 | 6 | 42 | 26 | 187 | 213 | 15 Oct 2026 | 18 Mar 2027 | 1-8 | Pranay Shinde | Pranay Shinde, Chitrangi Mestry, Surendra, Tanmay Dukhande, Sanket Keluskar, Chinmay Patkar
Ticketing & Guest Commerce | Wallet & Cashless | 52 | 0 | 5 | 105 | 17 | 49 | 44 | 353 | 397 | 6 Oct 2026 | 22 Mar 2027 | 1-9 | New full-stack developer 2 | New full-stack developer 2, Sanket Keluskar, Chinmay Patkar, New full-stack developer 1, Pradnya Yeram, Hrushikant Patkar
Ticketing & Guest Commerce | White Label & CMS | 65 | 0 | 32 | 8 | 78 | 1 | 210 | 16 | 225 | 5 Oct 2026 | 7 Jan 2027 | 1-5 | Chitrangi Mestry | Chitrangi Mestry, Tanmay Dukhande, Deep Khanvilkar, Chinmay Patkar, New full-stack developer 1, Sanket Keluskar
Ticketing & Guest Commerce | Transport | 0 | 0 | 11 | 1 | 21 | 10 | 63 | 21 | 85 | 9 Oct 2026 | 1 Apr 2027 | 1-9 | Deep Khanvilkar | Deep Khanvilkar, Hrushikant Patkar, Sanket Keluskar, Chinmay Patkar, Pradnya Yeram, Pallavi Sawant
Food, Beverage & Retail | Food & Beverage | 95 | 0 | 37 | 37 | 87 | 54 | 276 | 212 | 488 | 6 Oct 2026 | 5 Apr 2027 | 1-10 | Pradnya Yeram | Pradnya Yeram, Hrushikant Patkar, Deep Khanvilkar, Sanket Keluskar, New full-stack developer 1, Chitrangi Mestry
Food, Beverage & Retail | Retail | 14 | 0 | 5 | 4 | 14 | 11 | 43 | 30 | 73 | 19 Oct 2026 | 1 Apr 2027 | 1-9 | Pranay Shinde | Pranay Shinde, Chitrangi Mestry, Pradnya Yeram, Chinmay Patkar, New full-stack developer 2, Deep Khanvilkar
Food, Beverage & Retail | Rentals | 0 | 0 | 0 | 106 | 0 | 43 | 0 | 288 | 288 | 3 Mar 2027 | 6 Apr 2027 | 8-10 | Pradnya Yeram | Pradnya Yeram, Chitrangi Mestry, New full-stack developer 1, Chinmay Patkar, Deep Khanvilkar, Surendra
Food, Beverage & Retail | Inventory & Procurement | 115 | 0 | 2 | 25 | 7 | 51 | 21 | 165 | 185 | 15 Oct 2026 | 31 Mar 2027 | 1-9 | Tanmay Dukhande | Tanmay Dukhande, Pranay Shinde, Pallavi Sawant, Chitrangi Mestry, Deep Khanvilkar, New full-stack developer 2
Venue Operations | Admission & Access Control | 108 | 1 | 23 | 149 | 38 | 208 | 101 | 730 | 831 | 12 Oct 2026 | 2 Apr 2027 | 1-9 | Pallavi Sawant | Pallavi Sawant, Chinmay Patkar, Hrushikant Patkar, New full-stack developer 2, Sanket Keluskar, Chitrangi Mestry
Venue Operations | Accreditation | 58 | 0 | 0 | 72 | 0 | 47 | 0 | 224 | 224 | 19 Jan 2027 | 14 Apr 2027 | 6-10 | Deep Khanvilkar | Deep Khanvilkar, Surendra, Pallavi Sawant, New full-stack developer 2, Pranay Shinde
Venue Operations | Resources & Capacity | 92 | 1 | 7 | 55 | 15 | 46 | 38 | 208 | 245 | 14 Oct 2026 | 12 Apr 2027 | 1-10 | Hrushikant Patkar | Hrushikant Patkar, Pradnya Yeram, Chitrangi Mestry, New full-stack developer 2, Pranay Shinde, Pallavi Sawant
Venue Operations | Workforce & Staff | 27 | 0 | 0 | 34 | 2 | 47 | 5 | 173 | 178 | 12 Oct 2026 | 13 Apr 2027 | 1-10 | Chinmay Patkar | Chinmay Patkar, Tanmay Dukhande, Hrushikant Patkar, Sanket Keluskar, Deep Khanvilkar
Venue Operations | Maintenance & Safety | 75 | 0 | 1 | 28 | 1 | 41 | 7 | 170 | 177 | 15 Oct 2026 | 12 Apr 2027 | 1-10 | New full-stack developer 2 | New full-stack developer 2, Chitrangi Mestry, Sanket Keluskar, Pranay Shinde, Surendra, Hrushikant Patkar
Venue Operations | Games & Rides | 14 | 0 | 0 | 81 | 3 | 37 | 6 | 225 | 231 | 12 Oct 2026 | 19 Apr 2027 | 1-10 | Pallavi Sawant | Pallavi Sawant, Pranay Shinde, New full-stack developer 1, Sanket Keluskar, Deep Khanvilkar, Pradnya Yeram
Venue Operations | Virtual Queue | 37 | 1 | 8 | 6 | 11 | 11 | 34 | 47 | 81 | 16 Oct 2026 | 13 Apr 2027 | 1-10 | Hrushikant Patkar | Hrushikant Patkar, New full-stack developer 1, Chinmay Patkar, Pradnya Yeram, Pranay Shinde, Deep Khanvilkar
Finance & Insights | Finance, Ledger & Tax | 204 | 2 | 9 | 18 | 18 | 54 | 49 | 148 | 197 | 7 Oct 2026 | 5 Apr 2027 | 1-10 | Tanmay Dukhande | Tanmay Dukhande, Hrushikant Patkar, Pradnya Yeram, Pallavi Sawant, Sanket Keluskar, Chitrangi Mestry
Finance & Insights | Reporting & Analytics | 189 | 0 | 9 | 81 | 17 | 31 | 52 | 250 | 301 | 13 Oct 2026 | 3 May 2027 | 1-11 | Hrushikant Patkar | Hrushikant Patkar, New full-stack developer 1, New full-stack developer 2, Chinmay Patkar, Pradnya Yeram, Tanmay Dukhande
Customer & Marketing | Marketing & CRM | 421 | 1 | 33 | 186 | 60 | 204 | 177 | 763 | 940 | 21 Oct 2026 | 22 Apr 2027 | 1-10 | Pranay Shinde | Pranay Shinde, Deep Khanvilkar, Tanmay Dukhande, Surendra, Chinmay Patkar, Chitrangi Mestry
AI & Intelligence | AI & Intelligence | 287 | 2 | 20 | 117 | 50 | 91 | 114 | 2748 | 2863 | 5 Oct 2026 | 10 May 2027 | 1-11 | Kalpita Mejari | Kalpita Mejari, Second AI engineer, Pranay Shinde, Sanket Keluskar, Deep Khanvilkar, Tanmay Dukhande

## Build phases
Phase | Side | Starts | Ends | Block A hours | Block B hours | Hours | Main modules | People
0 Plumbing | back end | 5 Oct 2026 | 28 Dec 2026 | 306 | 0 | 306 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Transport, Reporting & Analytics, White Label & CMS, AI & Intelligence, Platform Operations | Hrushikant Patkar, Tanmay Dukhande, Pranay Shinde, Pradnya Yeram, Kalpita Mejari, Second AI engineer
0 Plumbing | front end | 5 Oct 2026 | 5 Oct 2026 | 2 | 0 | 2 | White Label & CMS | Chitrangi Mestry
1 Foundation | back end | 19 Oct 2026 | 24 Mar 2027 | 273 | 684 | 958 | Subscription & Licensing, Identity, Roles & Security, White Label & CMS, Approval Workflows, Platform Operations, Tenancy, Venues & Devices, Developer Portal & Public API, Foundation & Setup | Tanmay Dukhande, Hrushikant Patkar, Deep Khanvilkar, New full-stack developer 2, New full-stack developer 1, Pranay Shinde
1 Foundation | front end | 5 Oct 2026 | 17 Mar 2027 | 158 | 883 | 1041 | Subscription & Licensing, Approval Workflows, Identity, Roles & Security, White Label & CMS, Tenancy, Venues & Devices, Digital Asset Management, Developer Portal & Public API, Foundation & Setup | Chitrangi Mestry, Pradnya Yeram, Pallavi Sawant, New full-stack developer 1, Surendra, New full-stack developer 2
2 Commerce | back end | 21 Oct 2026 | 5 Apr 2027 | 510 | 1652 | 2162 | Admission & Access Control, Ticketing Catalogue & Products, Orders & Reservations, Pricing, Promotions & Bundles, Finance, Ledger & Tax, Wallet & Cashless, Seat Management & Venue Maps, Foundation & Setup | Tanmay Dukhande, Pranay Shinde, Deep Khanvilkar, Hrushikant Patkar, Sanket Keluskar, Pallavi Sawant
2 Commerce | front end | 6 Oct 2026 | 19 Mar 2027 | 491 | 1951 | 2442 | Ticketing Catalogue & Products, Orders & Reservations, Admission & Access Control, Pricing, Promotions & Bundles, Wallet & Cashless, Seat Management & Venue Maps, Foundation & Setup, Payments | Chitrangi Mestry, Pradnya Yeram, Pallavi Sawant, Chinmay Patkar, New full-stack developer 1, New full-stack developer 2
3 Operations | back end | 28 Oct 2026 | 19 Apr 2027 | 415 | 750 | 1165 | Food & Beverage, Foundation & Setup, Inventory & Procurement, Resources & Capacity, Accreditation, Workforce & Staff, Rentals, Maintenance & Safety | Hrushikant Patkar, Deep Khanvilkar, Pranay Shinde, Tanmay Dukhande, Sanket Keluskar, New full-stack developer 2
3 Operations | front end | 16 Oct 2026 | 16 Apr 2027 | 315 | 1012 | 1327 | Rentals, Food & Beverage, Games & Rides, Accreditation, Resources & Capacity, Foundation & Setup, Maintenance & Safety, Workforce & Staff | Pradnya Yeram, Chitrangi Mestry, Pallavi Sawant, Chinmay Patkar, Sanket Keluskar, New full-stack developer 1
4 Engagement | back end | 5 Oct 2026 | 10 May 2027 | 177 | 2881 | 3058 | AI & Intelligence, Marketing & CRM, Foundation & Setup | Kalpita Mejari, Second AI engineer, Pranay Shinde, Deep Khanvilkar, Tanmay Dukhande, Sanket Keluskar
4 Engagement | front end | 22 Oct 2026 | 30 Apr 2027 | 141 | 630 | 772 | Marketing & CRM, AI & Intelligence, Foundation & Setup, White Label & CMS, Orders & Reservations | Surendra, Chitrangi Mestry, Pallavi Sawant, Pradnya Yeram, Chinmay Patkar, Sanket Keluskar
5 Reporting | back end | 21 Dec 2026 | 3 May 2027 | 34 | 58 | 93 | Reporting & Analytics, Foundation & Setup | Hrushikant Patkar, Tanmay Dukhande, Chinmay Patkar, Sanket Keluskar, Deep Khanvilkar
5 Reporting | front end | 26 Oct 2026 | 3 May 2027 | 33 | 191 | 225 | Reporting & Analytics, Foundation & Setup | New full-stack developer 1, New full-stack developer 2, Chinmay Patkar, Pradnya Yeram, Surendra, Pallavi Sawant

## Gantt
Package / module | Lead | Hours | Completion | S1 |  |  | S2 |  |  | S3 |  |  | S4 |  |  | S5 |  |  | S6 |  |  | S7 |  |  | S8 |  |  | S9
|  |  |  | 05 Oct | 12 Oct | 19 Oct | 26 Oct | 02 Nov | 09 Nov | 16 Nov | 23 Nov | 30 Nov | 07 Dec | 14 Dec | 21 Dec | 28 Dec | 04 Jan | 11 Jan | 18 Jan | 25 Jan | 01 Feb | 08 Feb | 15 Feb | 22 Feb | 01 Mar | 08 Mar | 15 Mar | 22 Mar | 29 Mar | 05 Apr | 12 Apr | 19 Apr | 26 Apr | 03 May | 10 May
Platform Foundation | Hrushikant Patkar | 2613 | 24 Mar 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan; S9 29 Mar to S9 10 May
Foundation & Setup | Hrushikant Patkar | 840 | 22 Jan 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan
Identity, Roles & Security | Deep Khanvilkar | 245 | 19 Mar 2027 | bar: S1 05 Oct; S3 23 Nov to S6 18 Jan
Tenancy, Venues & Devices | New full-stack developer 2 | 183 | 17 Mar 2027 | bar: S1 05 Oct; S3 23 Nov to S6 18 Jan
Platform Operations | Pallavi Sawant | 133 | 19 Mar 2027 | bar: S3 23 Nov to S6 18 Jan
Subscription & Licensing | New full-stack developer 2 | 673 | 24 Mar 2027 | bar: S1 05 Oct; S3 23 Nov to S6 18 Jan
Approval Workflows | Pradnya Yeram | 303 | 22 Mar 2027 | bar: S1 05 Oct; S4 07 Dec to S6 18 Jan
Developer Portal & Public API | Chitrangi Mestry | 107 | 19 Mar 2027 | bar: S1 05 Oct; S4 14 Dec to S6 18 Jan
Digital Asset Management | Surendra | 129 | 8 Jan 2027 | bar: S2 09 Nov to S5 04 Jan
Ticketing & Guest Commerce | Tanmay Dukhande | 3641 | 1 Apr 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan; S9 29 Mar to S9 10 May
Ticketing Catalogue & Products | Tanmay Dukhande | 894 | 22 Mar 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan
Pricing, Promotions & Bundles | Tanmay Dukhande | 610 | 25 Mar 2027 | bar: S1 05 Oct; S2 09 Nov to S3 23 Nov; S5 04 Jan to S6 18 Jan
Seat Management & Venue Maps | Hrushikant Patkar | 344 | 18 Mar 2027 | bar: S2 09 Nov to S4 21 Dec; S5 11 Jan to S6 18 Jan
Orders & Reservations | Pranay Shinde | 873 | 25 Mar 2027 | bar: S2 09 Nov to S6 18 Jan
Payments | Pranay Shinde | 213 | 18 Mar 2027 | bar: S2 09 Nov to S3 23 Nov
Wallet & Cashless | New full-stack developer 2 | 397 | 22 Mar 2027 | bar: S1 05 Oct; S2 09 Nov to S3 23 Nov
White Label & CMS | Chitrangi Mestry | 225 | 7 Jan 2027 | bar: S1 05 Oct; S2 09 Nov to S5 04 Jan
Transport | Deep Khanvilkar | 85 | 1 Apr 2027 | bar: S1 05 Oct; S2 09 Nov to S4 21 Dec; S6 18 Jan; S9 29 Mar
Food, Beverage & Retail | Pradnya Yeram | 1034 | 6 Apr 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan; S9 29 Mar to S9 10 May
Food & Beverage | Pradnya Yeram | 488 | 5 Apr 2027 | bar: S1 05 Oct; S2 09 Nov to S4 21 Dec; S5 11 Jan to S6 18 Jan; S9 29 Mar to S9 05 Apr
Retail | Pranay Shinde | 73 | 1 Apr 2027 | bar: S2 09 Nov to S5 28 Dec; S6 18 Jan; S9 29 Mar
Rentals | Pradnya Yeram | 288 | 6 Apr 2027 | bar: S9 29 Mar to S9 05 Apr
Inventory & Procurement | Tanmay Dukhande | 185 | 31 Mar 2027 | bar: S2 09 Nov to S4 14 Dec; S6 18 Jan; S9 29 Mar
Venue Operations | New full-stack developer 2 | 1967 | 19 Apr 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan; S9 29 Mar to S9 10 May
Admission & Access Control | Pallavi Sawant | 831 | 2 Apr 2027 | bar: S2 09 Nov to S3 30 Nov; S5 11 Jan to S6 18 Jan; S9 29 Mar
Accreditation | Deep Khanvilkar | 224 | 14 Apr 2027 | bar: S6 18 Jan; S9 29 Mar to S9 12 Apr
Resources & Capacity | Hrushikant Patkar | 245 | 12 Apr 2027 | bar: S2 09 Nov to S5 28 Dec; S6 18 Jan; S9 29 Mar to S9 12 Apr
Workforce & Staff | Chinmay Patkar | 178 | 13 Apr 2027 | bar: S6 18 Jan; S9 29 Mar to S9 12 Apr
Maintenance & Safety | New full-stack developer 2 | 177 | 12 Apr 2027 | bar: S2 09 Nov to S3 23 Nov; S6 18 Jan; S9 29 Mar to S9 12 Apr
Games & Rides | Pallavi Sawant | 231 | 19 Apr 2027 | bar: S2 09 Nov to S3 16 Nov; S9 29 Mar to S9 19 Apr
Virtual Queue | Hrushikant Patkar | 81 | 13 Apr 2027 | bar: S2 09 Nov to S4 21 Dec; S9 29 Mar to S9 12 Apr
Finance & Insights | Hrushikant Patkar | 498 | 3 May 2027 | bar: S1 05 Oct; S2 09 Nov to S6 18 Jan; S9 29 Mar to S9 10 May
Finance, Ledger & Tax | Tanmay Dukhande | 197 | 5 Apr 2027 | bar: S1 05 Oct; S2 09 Nov to S3 30 Nov; S5 11 Jan to S6 18 Jan; S9 29 Mar to S9 05 Apr
Reporting & Analytics | Hrushikant Patkar | 301 | 3 May 2027 | bar: S2 09 Nov to S5 11 Jan; S9 29 Mar to S9 03 May
Customer & Marketing | Pranay Shinde | 940 | 22 Apr 2027 | bar: S1 05 Oct to S1 12 Oct; S2 09 Nov to S6 18 Jan; S9 29 Mar to S9 10 May
Marketing & CRM | Pranay Shinde | 940 | 22 Apr 2027 | bar: S2 09 Nov to S5 11 Jan; S9 29 Mar to S9 19 Apr
AI & Intelligence | Kalpita Mejari | 2863 | 10 May 2027 | bar: S1 05 Oct to S6 18 Jan; S9 29 Mar to S9 10 May
AI & Intelligence | Kalpita Mejari | 2863 | 10 May 2027 | bar: S1 05 Oct to S6 18 Jan; S9 29 Mar to S9 10 May
Block A (task sheet)
Block B (scheduled)
After 2 April

## People
Name | Role | Pace | From | Block A points | Block A work ends | Block A hours past 20 Nov | Sprint 1 hours | Sprint 2 hours | Sprint 3 hours | Sprint 4 hours | Sprint 5 hours | Sprint 6 hours | Sprint 7 hours | Sprint 8 hours | Sprint 9 hours | Last day at normal hours | Hours past 2 Apr | Overtime h/week to finish | Modules
Hrushikant Patkar | Back end and DevOps | 100% | 5 Oct 2026 | 540 | 18 Jan 2027 | 291 | 83 | 87 | 50 | 119 | 111 | 119 | 120 | 96 | 80 | 3 May 2027 | 163 | 6.6 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Subscription & Licensing, Developer Portal & Public API, Digital Asset Management, Seat Management & Venue Maps, Orders & Reservations
Pranay Shinde | Back end | 100% | 5 Oct 2026 | 457 | 23 Dec 2026 | 159 | 63 | 121 | 98 | 117 | 112 | 120 | 120 | 96 | 80 | 6 May 2027 | 186 | 7.6 | Foundation & Setup, Platform Operations, Approval Workflows, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Orders & Reservations, Payments, Wallet & Cashless
Tanmay Dukhande | Back end | 100% | 5 Oct 2026 | 453 | 17 Dec 2026 | 127 | 100 | 120 | 97 | 111 | 112 | 120 | 120 | 96 | 80 | 5 May 2027 | 182 | 7.4 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Digital Asset Management
Deep Khanvilkar | Back end | 100% | 5 Oct 2026 | 287 | 5 Jan 2027 | 217 | 36 | 81 | 44 | 52 | 98 | 120 | 120 | 96 | 80 | 10 May 2027 | 201 | 8.2 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Digital Asset Management, Ticketing Catalogue & Products
Pallavi Sawant | Full stack (Venue Management) | 100% | 5 Oct 2026 | 290 | 16 Nov 2026 | 0 | 119 | 120 | 60 | 120 | 112 | 120 | 120 | 96 | 80 | 28 Apr 2027 | 138 | 5.6 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Ticketing Catalogue & Products
Sanket Keluskar | Full stack (Venue Management) | 100% | 5 Oct 2026 | 290 | 21 Jan 2027 | 317 | 36 | 53 | 0 | 16 | 110 | 119 | 120 | 96 | 80 | 5 May 2027 | 177 | 7.2 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Subscription & Licensing, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations
Chinmay Patkar | Full stack (guest web, white label) | 100% | 5 Oct 2026 | 405 | 22 Jan 2027 | 322 | 12 | 36 | 79 | 66 | 112 | 119 | 120 | 96 | 80 | 28 Apr 2027 | 142 | 5.8 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Subscription & Licensing, Approval Workflows, Digital Asset Management, Ticketing Catalogue & Products, Pricing, Promotions & Bundles
Chitrangi Mestry | Front end (guest app, web) | 100% | 5 Oct 2026 | 280 | 16 Nov 2026 | 0 | 112 | 119 | 59 | 120 | 112 | 120 | 120 | 96 | 80 | 26 Apr 2027 | 123 | 5 | Foundation & Setup, Identity, Roles & Security, Platform Operations, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Ticketing Catalogue & Products, Pricing, Promotions & Bundles
Pradnya Yeram | Front end (POS, guest app) | 100% | 5 Oct 2026 | 244 | 10 Nov 2026 | 0 | 111 | 94 | 56 | 120 | 112 | 120 | 120 | 96 | 80 | 22 Apr 2027 | 106 | 4.3 | Foundation & Setup, Identity, Roles & Security, Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Approval Workflows, Ticketing Catalogue & Products, Pricing, Promotions & Bundles
Surendra | Full stack (Venue Management) | 60% | 5 Oct 2026 | 173 | 17 Nov 2026 | 0 | 68 | 73 | 38 | 72 | 67 | 72 | 72 | 58 | 48 | 30 Apr 2027 | 93 | 3.8 | Foundation & Setup, Identity, Roles & Security, Subscription & Licensing, Digital Asset Management, Ticketing Catalogue & Products, Seat Management & Venue Maps, Payments, Rentals
New full-stack developer 1 | Full stack (to hire) | 100% | 23 Nov 2026 | 0 |  | 0 | 0 | 0 | 56 | 120 | 112 | 120 | 120 | 96 | 80 | 3 May 2027 | 161 | 9.1 | Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Approval Workflows, Developer Portal & Public API, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps
New full-stack developer 2 | Full stack (to hire) | 100% | 23 Nov 2026 | 0 |  | 0 | 0 | 0 | 56 | 120 | 112 | 120 | 120 | 96 | 80 | 28 Apr 2027 | 143 | 8.1 | Tenancy, Venues & Devices, Subscription & Licensing, Developer Portal & Public API, Digital Asset Management, Ticketing Catalogue & Products, Pricing, Promotions & Bundles, Seat Management & Venue Maps, Orders & Reservations
Kalpita Mejari | AI engineer | 100% | 5 Oct 2026 | 0 | 23 Nov 2026 | 2 | 121 | 120 | 96 | 120 | 112 | 120 | 120 | 96 | 80 | 21 Apr 2027 | 98 | 4 | Foundation & Setup, AI & Intelligence
Second AI engineer | AI engineer | 100% | 5 Oct 2026 | 0 | 23 Nov 2026 | 2 | 121 | 120 | 96 | 120 | 112 | 120 | 120 | 96 | 80 | 16 Apr 2027 | 78 | 3.2 | Foundation & Setup, AI & Intelligence

## Release checklist
When | Step | Check | Owner
Every sprint (Friday of week 3) | Before | Every ticket in the sprint is Ready for QA or moved to the next sprint with a reason in the ticket. | Scrum lead
Every sprint | Before | CI green on main: unit, contract (the OpenAPI checks) and migration tests. | Hrushikant Patkar
Every sprint | Before | Database migrations run forward on a copy of staging data; the rollback script runs back cleanly. | Back-end owner of the service
Every sprint | Before | Feature flags set per tenant for anything half-built; nothing unfinished is visible to a venue. | Lead of the package
Every sprint | Deploy | Deploy to staging; run the smoke flows of the apps touched (buy a ticket, pay, scan, POS sale, KDS bump). | QA
Every sprint | Deploy | Demo to the client from staging; record accepted and rejected items in OpenProject. | Chinmay Parab
Every sprint | After | Measured pace per person recorded; the plan workbook regenerated with the real pace. | Chinmay Parab
Block A go-live (20 Nov 2026) | Before | The client has signed off every Block A wireframe batch (3 working days each, audit R252). | Client design reviewer
Block A go-live | Before | Payment sandbox credentials in place and a full sale-refund-settlement cycle passes (the client's answer in the Decisions Register). | Client, then Tanmay Dukhande
Block A go-live | Before | Offline: the POS sells and the scanner admits with the network cut, and reconcile when it returns. | Pradnya Yeram
Block A go-live | Before | Tax invoice, credit note and VAT fields checked against the client's answers (make-or-break items). | Pranay Shinde
Block A go-live | Before | Load test at the burst mix (ticket on-sale) and the venue-day mix; replicas as sized in handoff/sizing.json. | Hrushikant Patkar
Block A go-live | Before | Backups restore into a clean environment; the restore time is written down. | Hrushikant Patkar
Block A go-live | Before | Security: role grants reviewed per module, secrets in the vault, no test credentials in production. | Hrushikant Patkar
Block A go-live | Deploy | Production deploy in a quiet window; canary tenant first, then the pilot venue. | Hrushikant Patkar
Block A go-live | Deploy | Watch error rate and latency for the first hour of trading; the rollback is rehearsed beforehand. | On-call back end
Block A go-live | Rollback if | Payment failures above 2% of attempts, POS sale p95 above 2 seconds, or any failed gate admission not explained by the ticket. | Chinmay Parab decides
Block A go-live | After | Release notes to the client; tickets closed; the hypercare rota for the first two weeks. | Chinmay Parab
End of six months (2 Apr 2027) | Before | Every module's acceptance signed; open defects triaged into the phase-2 backlog. | Chinmay Parab and the client

## Decisions
Decision | Status | What was decided | Why | What it costs
One package, services by contract | Accepted | Each business module is one OpenAPI contract owned by one service; screens bind to operations, never to tables. | Work can be split by module and checked by machine (34 checkers) before anyone builds. | A change crosses contract, screen and ticket; the refresh keeps them in step.
Build in two blocks | Accepted | Block A ships the selling apps first (POS, KDS, guest web and app, white label, Venue Management setup); Block B the back office, console, partner, support and analytics. | Revenue-facing apps reach the client in 7 weeks; the long tail of back-office screens follows. | Back-office screens wait until B1-B3.
Size by formula, schedule by measured pace | Accepted | Points come from each screen's specification and each operation; the pace is replaced by the measured pace after sprint 1. | No hand estimates; a re-plan is a rerun. | The first forecast is only as good as Block A's planned pace until 23 October.
AI that needs no history in Block A | Accepted | Gateway and governance, concierge, Help me choose, translations and the planner agent ship in Block A; rules stand in for upsell and fraud. | Guests get AI from day one without waiting for data. | Data-driven AI is scheduled in Block B; see the AI review.
Every AI function inside six months, baseline first | Accepted 30 Sep | Forecasting, fraud, recommendations, anomaly detection and both assistants ship with a working baseline on day one and learn from the tenant's own data; a trained model replaces the baseline only when it beats it and an admin approves. | Customers never hear 'later, when you have data'; accuracy grows with use. | About 2,800 points of AI engine work; a trained model goes live per tenant only after a season of its data.
Two AI engineers from 5 October | Accepted 30 Sep | Kalpita and the second AI engineer carry the engine work from Block A onwards; no third engineer. Developers build the AI endpoints and screens like any other module. | AI engineers spend their time on what only they can build. | The AI engineers are fully loaded; about 3-4 overtime hours a week each.
CMS as a flow builder | Accepted | Operators pick their booking flows, see required and optional steps, set their own order, then finish in a configuration panel. | One engine serves every venue type the prototypes show. | The step library has to be complete before operators can compose.
Per-tenant data and models | Accepted | Models train per tenant; the LLM never reads raw data (scrubbed aggregates or code it writes); retention is tenant configuration. | Meets PDPL and client expectations on data isolation. | No pooled training; cold start relies on baselines and priors.
Load follows skill | Accepted | Tasks are assigned by skill rating and experience, not evenly; helpers take a share proportional to their ratings. | Hard work goes to people rated for it. | Back-end owners are the Block A constraint; shown as overtime, not hidden.

## Risks
Risk | Signal | What we do
Back-end owners overloaded in Block A | Their Block A work runs past 20 November (People sheet). | Deep takes a larger proportional share; the two new developers take back-end tasks from their first day; Block B start slides for the three owners only.
Pace below plan | Measured pace on 23 October under 9.6 points per developer per day. | Rerun the plan with the measured pace; use the wave-3 deferral list on 18 December.
Hiring the two developers slips | Not confirmed by 23 October. | Block B finish moves out by the scheduler's figure; the PM decides scope or date.
Client inputs late | Wireframe sign-off over 3 working days; sandbox credentials; stations and fares; cabana numbering; real photos. | Those tickets wait in 'Waiting on client' and do not count against the team's pace.
Make-or-break answers | Tax invoice fields, e-invoicing provider, VAT 201 layout, face capture consent, ID-verification provider. | Defaults are built; a different answer is a change request.
Second AI engineer not in place on 5 October | No start date confirmed this week. | Kalpita starts the Block A AI alone; the baseline layer moves one sprint and the AI engine work needs more overtime.
AI engine estimates are rough | The AI review sized the engines in engineer-weeks from the design. | Re-base on the measured pace on 23 October; the trained models are the part to move if the AI engineers fall behind.