## Summary
What | Value | How it is worked out
Start | 5 Oct 2026 | Sprint 1 starts Monday 5 October 2026.
Sprints | 13 sprints of two weeks to 2 Apr 2027 | Sprint 1 = 5-16 Oct 2026 ... Sprint 13 = 22 Mar-2 Apr 2027 (replan of 1 October; it was nine sprints of three weeks).
Block A | ends 27 Nov 2026 (Sprint 4) | Target Sprint 4 (27 Nov 2026). 123 app-modules; block test 25 Nov 2026 to 27 Nov 2026; 43 flows end to end.
Block A2 | ends 11 Dec 2026 (Sprint 5) | Target Sprint 5 (11 Dec 2026). 1 app-modules; block test 9 Dec 2026 to 11 Dec 2026; 0 flows end to end. AI engine capabilities to 7 Dec 2026.
Block B | ends 25 Dec 2026 (Sprint 6) | Target Sprint 6 (25 Dec 2026). 61 app-modules; block test 23 Dec 2026 to 25 Dec 2026; 36 flows end to end. AI engine capabilities to 16 Dec 2026.
Block C | ends 22 Jan 2027 (Sprint 8) | Target Sprint 8 (22 Jan 2027). 57 app-modules; block test 20 Jan 2027 to 22 Jan 2027; 49 flows end to end.
Block D | ends 19 Feb 2027 (Sprint 10) | Target Sprint 10 (19 Feb 2027). 79 app-modules; block test 17 Feb 2027 to 19 Feb 2027; 99 flows end to end. AI engine capabilities to 11 Mar 2027.
Forecast finish (developers) | 9 Feb 2027 | At normal hours. The plan of 30 September 2026 said 26 Apr 2027.
AI engine finish (in the plan) | 3 Mar 2027 | Two AI engineers, no third (decided 30 September). Block A 500 h (Kalpita Mejari 252, Second AI engineer 248) to 18 Nov 2026; Block A2 128 h (Kalpita Mejari 64, Second AI engineer 64) to 3 Dec 2026; phase 1 940 h (Kalpita Mejari 480, Second AI engineer 460) from 3 Dec 2026 to 3 Mar 2027, its module tests to 11 Mar 2027. Phase 2, 860 h, is outside the six-month plan: the parts that learn from tenant data (forecasting statistical and learned, fraud classifier, learning-to-rank, training and promotion, anomaly detection, dynamic pricing), after 2 April when the client's data exists, with no owner and not ticketed (Chinmay, 4 October, CHG-AIPH-001; docs/active/ai-phase-plan.json).
Total effort | 8,257 hours | Build 4,782 h, testing 1,046 h (module tests 806, block tests 240), AI engine 2,428 h.
Overtime to finish by 2 April | 0 hours (developers) | Decided 1 October: Block D keeps its scope to 2 April. Block D lands on 19 Feb 2027 at normal hours, without overtime. The AI engine's phase 2 (860 h) is after 2 April by decision, not overtime. The plan of 30 September 2026 needed about 1,293 h without the tests.
Buffer | Sprints 11-13, 2,784 hours | Sprints 11-13 (22 Feb 2027 to 2 Apr 2027) are buffer (decided 1 October): about 928 developer hours a sprint (2,784 in all) for Claude Design returns, defects, change requests and helping the AI developers.
Block A | 123 app-modules, ends 27 Nov 2026 (Sprint 4) | Previously: screens by 20 November, back end wired by 25 December. Now complete, tested and accepted as one block. Decided 1 October: Sprint 4 with 10 h of planned overtime (Tanmay Dukhande 6, Chinmay Patkar 4); at normal hours it would end 11 Dec 2026.
Ticketing depth | 4,157 tasks planned, 2,196 ticketed | Block A in full and the next block (B) task by task in release r2; Blocks C and D are ticketed as app-modules (features) and broken into tasks one block ahead, at each block's start, through the normal Tuesday/Friday release. Their tasks are already planned (plan-tasks.csv) with the keys they will get.
Pace | 6 tasks per developer per day x 3.30 points a task = 19.8 points, through Sprint 4; from Sprint 5 the ramp from 5 (16.5) rises to 2x (33.0) by Sprint 11, then held | Default: Block A's plan of record (3,018 points, 35 days, 9 developers), replaced by the measured pace; team.json sprintPlan.pace sets a scenario (tasks a developer-day, ramp).
Block A's critical path | 25.7 working days | Its longest chain of waits with every task on its own person: the shortest Block A can take at this pace, whatever the team size. Block A is 40 working days (decided 1 October; it was 35).
Points per back-end operation | 2.69 | Block A's back-end points divided by its operations.
Team | 14 people | Chinmay Parab (lead) is not counted in capacity.

## Blocks
Block | Target sprint | Final sprint | Ends | Block test | Testers | App-modules | Screens | Operations | Tables | Build hours | Test hours | AI engine hours | Flows end to end | Flows partly | Apps
A | 4 | 4 | 27 Nov 2026 | 25 Nov 2026 to 27 Nov 2026 | Pranay Shinde + Chitrangi Mestry (led by Chinmay Parab) | 123 | 476 | 1341 | 823 | 1760 | 299 | 500 | 43 | 83 | Venue Management (30), Guest Web (17), Guest App (17), POS (12), Staff App (7), TICVAI Console (7), platform (6), CMS (6), Support Console (4), API only (4), Developer Portal (3), Analytics (3), Scanner (2), Kiosk (2), Kitchen Display (2), Partner Portal (1)
A2 | 5 | 5 | 11 Dec 2026 | 9 Dec 2026 to 11 Dec 2026 | Pranay Shinde + Chitrangi Mestry (led by Chinmay Parab) | 1 | 0 | 0 | 0 | 0 | 61 | 128 | 0 | 0 | platform (1)
B | 6 | 6 | 25 Dec 2026 | 23 Dec 2026 to 25 Dec 2026 | Tanmay Dukhande + Chinmay Patkar (led by Chinmay Parab) | 61 | 418 | 505 | 92 | 1012 | 171 | 60 | 36 | 40 | Venue Management (26), TICVAI Console (12), Partner Portal (5), CMS (4), Staff App (3), Sign-up (3), Analytics (2), Kiosk (2), API only (1), Scanner (1), Developer Portal (1), platform (1)
C | 8 | 8 | 22 Jan 2027 | 20 Jan 2027 to 22 Jan 2027 | Pranay Shinde + Pallavi Sawant (led by Chinmay Parab) | 57 | 473 | 506 | 111 | 1042 | 155 | 0 | 49 | 11 | Venue Management (40), Staff App (6), Partner Portal (3), Kiosk (3), Analytics (2), Sign-up (1), Scanner (1), TICVAI Console (1)
D | 10 | 10 | 19 Feb 2027 | 17 Feb 2027 to 19 Feb 2027 | Tanmay Dukhande + Pradnya Yeram (led by Chinmay Parab) | 79 | 700 | 392 | 87 | 968 | 361 | 1740 | 99 | 4 | Venue Management (33), platform (13), Staff App (8), TICVAI Console (7), Analytics (5), Support Console (4), CMS (3), API only (2), Partner Portal (2), Accreditation Web (1), Kiosk (1)

## Sprints
Sprint | Starts | Ends | Working days | Blocks in progress | Block ending | Capacity (hours) | Planned (hours) | Used | Holidays
Sprint 1 | 5 Oct 2026 | 16 Oct 2026 | 10 | A, D |  | 928 | 849 | 91%
Sprint 2 | 19 Oct 2026 | 30 Oct 2026 | 10 | A, B |  | 928 | 924 | 100%
Sprint 3 | 2 Nov 2026 | 13 Nov 2026 | 10 | A, B, C, D |  | 928 | 923 | 99%
Sprint 4 | 16 Nov 2026 | 27 Nov 2026 | 10 | A, A2, B, C, D | A | 1008 | 771 | 76%
Sprint 5 | 30 Nov 2026 | 11 Dec 2026 | 10 | A2, B, C, D | A2 | 1088 | 1004 | 92%
Sprint 6 | 14 Dec 2026 | 25 Dec 2026 | 10 | B, C, D | B | 1088 | 1004 | 92%
Sprint 7 | 28 Dec 2026 | 8 Jan 2027 | 10 | C, D |  | 1088 | 968 | 89%
Sprint 8 | 11 Jan 2027 | 22 Jan 2027 | 10 | C, D | C | 1088 | 289 | 27%
Sprint 9 | 25 Jan 2027 | 5 Feb 2027 | 10 |  |  | 1088 | 160 | 15%
Sprint 10 | 8 Feb 2027 | 19 Feb 2027 | 10 | D | D | 1088 | 221 | 20%
Sprint 11 (buffer) | 22 Feb 2027 | 5 Mar 2027 | 10 | D |  | 1088 | 136 | 12%
Sprint 12 (buffer) | 8 Mar 2027 | 19 Mar 2027 | 10 | D |  | 1088 | 51 | 5%
Sprint 13 (buffer) | 22 Mar 2027 | 2 Apr 2027 | 10 |  |  | 1088 | 0 | 0%

## Packages
Package | What it is | Modules | App-modules | Requirements covered | Screens | Operations | Hours | Block A hours | Block A2 hours | Block B hours | Block C hours | Block D hours | Starts | Completion | Lead
Platform Foundation | Everything the apps stand on: sign-in, tenants and venues, devices, licensing, approvals, the public API. | 8 | 90 | 563 | 392 | 471 | 1704 | 385 | 48 | 913 | 286 | 71 | 5 Oct 2026 | 19 Feb 2027 | Tanmay Dukhande
Ticketing & Guest Commerce | What a guest buys and how: catalogue, pricing, seats and maps, orders, payments, wallet, the branded storefront and app. | 8 | 64 | 866 | 522 | 934 | 1421 | 652 | 0 | 244 | 523 | 0 | 5 Oct 2026 | 28 Dec 2026 | Tanmay Dukhande
Food, Beverage & Retail | Selling at the venue: F&B with the kitchen display, retail, rentals, stock and purchasing. | 4 | 30 | 224 | 212 | 286 | 517 | 282 | 0 | 0 | 82 | 153 | 9 Oct 2026 | 30 Dec 2026 | Tanmay Dukhande
Venue Operations | Running the venue day to day: gates and access, accreditation, capacity, staff, maintenance, rides, queues. | 7 | 49 | 411 | 478 | 517 | 881 | 266 | 0 | 4 | 276 | 335 | 6 Oct 2026 | 5 Jan 2027 | Hrushikant Patkar
Finance & Insights | The money and the numbers: ledger, VAT and e-invoicing, reports and analytics. | 2 | 28 | 393 | 121 | 123 | 242 | 121 | 0 | 4 | 25 | 91 | 7 Oct 2026 | 13 Jan 2027 | Pallavi Sawant
Customer & Marketing | Knowing and reaching the guest: CRM, segments, campaigns, loyalty, support. | 1 | 25 | 421 | 205 | 271 | 430 | 196 | 0 | 2 | 1 | 231 | 12 Oct 2026 | 8 Jan 2027 | Pranay Shinde
AI & Intelligence | The AI gateway and governance, the guest concierge, Help me choose, translations, the planner agent; forecasting, fraud and recommendations rules-first. | 1 | 35 | 287 | 137 | 142 | 3065 | 659 | 141 | 75 | 4 | 2187 | 5 Oct 2026 | 11 Mar 2027 | Kalpita Mejari

## Modules
Package | Module | Requirements covered | Waiting on the client | App-modules | Screens | Operations | Block A hours | Block A2 hours | Block B hours | Block C hours | Block D hours | Total hours | Starts | Completion | Sprints | Lead | Team
Platform Foundation | Foundation & Setup | 0 | 0 | 28 | 0 | 0 | 126 | 48 | 298 | 285 | 70 | 827 | 5 Oct 2026 | 19 Feb 2027 | 1-10 | Tanmay Dukhande | Tanmay Dukhande, Pranay Shinde, Hrushikant Patkar, Chinmay Patkar, Sanket Keluskar, Pallavi Sawant
Platform Foundation | Identity, Roles & Security | 144 | 0 | 18 | 44 | 94 | 91 | 0 | 64 | 0 | 0 | 155 | 5 Oct 2026 | 2 Dec 2026 | 1-5 | Chitrangi Mestry | Chitrangi Mestry, Hrushikant Patkar, Pallavi Sawant, Pradnya Yeram, Sanket Keluskar, Chinmay Patkar
Platform Foundation | Tenancy, Venues & Devices | 126 | 1 | 9 | 60 | 57 | 58 | 0 | 68 | 1 | 1 | 128 | 5 Oct 2026 | 30 Nov 2026 | 1-5 | Sanket Keluskar | Sanket Keluskar, Pallavi Sawant, Pranay Shinde, Pradnya Yeram, Chinmay Patkar, Deep Khanvilkar
Platform Foundation | Platform Operations | 4 | 0 | 3 | 18 | 52 | 6 | 0 | 56 | 0 | 0 | 62 | 7 Oct 2026 | 11 Nov 2026 | 1-3 | Pallavi Sawant | Pallavi Sawant, Chinmay Patkar, Chitrangi Mestry, Surendra, Pradnya Yeram, Sanket Keluskar
Platform Foundation | Subscription & Licensing | 105 | 0 | 15 | 156 | 150 | 39 | 0 | 275 | 0 | 0 | 315 | 5 Oct 2026 | 7 Dec 2026 | 1-5 | Pradnya Yeram | Pradnya Yeram, Pallavi Sawant, Chitrangi Mestry, Sanket Keluskar, Chinmay Patkar, Surendra
Platform Foundation | Approval Workflows | 90 | 0 | 5 | 48 | 56 | 31 | 0 | 70 | 0 | 0 | 101 | 5 Oct 2026 | 25 Nov 2026 | 1-4 | Pradnya Yeram | Pradnya Yeram, Pallavi Sawant, Chitrangi Mestry, Pranay Shinde, Sanket Keluskar, Chinmay Patkar
Platform Foundation | Developer Portal & Public API | 80 | 0 | 8 | 26 | 36 | 21 | 0 | 29 | 0 | 0 | 50 | 5 Oct 2026 | 1 Dec 2026 | 1-5 | Pradnya Yeram | Pradnya Yeram, Chitrangi Mestry, Sanket Keluskar, Pallavi Sawant, Tanmay Dukhande, Surendra
Platform Foundation | Digital Asset Management | 14 | 0 | 4 | 40 | 26 | 13 | 0 | 53 | 0 | 0 | 66 | 7 Oct 2026 | 30 Nov 2026 | 1-5 | Chitrangi Mestry | Chitrangi Mestry, Pradnya Yeram, Chinmay Patkar, Tanmay Dukhande, New full-stack developer 1, Sanket Keluskar
Ticketing & Guest Commerce | Ticketing Catalogue & Products | 266 | 2 | 14 | 109 | 249 | 148 | 0 | 204 | 1 | 0 | 353 | 5 Oct 2026 | 22 Dec 2026 | 1-6 | Tanmay Dukhande | Tanmay Dukhande, Chitrangi Mestry, Hrushikant Patkar, Pallavi Sawant, Chinmay Patkar, Pradnya Yeram
Ticketing & Guest Commerce | Pricing, Promotions & Bundles | 105 | 1 | 3 | 13 | 141 | 35 | 0 | 23 | 31 | 0 | 89 | 6 Oct 2026 | 28 Dec 2026 | 1-7 | Hrushikant Patkar | Hrushikant Patkar, Sanket Keluskar, Pallavi Sawant, Tanmay Dukhande, New full-stack developer 2, Chinmay Patkar
Ticketing & Guest Commerce | Seat Management & Venue Maps | 100 | 0 | 11 | 113 | 77 | 58 | 0 | 1 | 129 | 0 | 188 | 6 Oct 2026 | 11 Dec 2026 | 1-5 | Chitrangi Mestry | Chitrangi Mestry, Pradnya Yeram, Chinmay Patkar, Tanmay Dukhande, Pallavi Sawant, Sanket Keluskar
Ticketing & Guest Commerce | Orders & Reservations | 269 | 0 | 12 | 110 | 221 | 153 | 0 | 3 | 187 | 0 | 344 | 6 Oct 2026 | 28 Dec 2026 | 1-7 | Pranay Shinde | Pranay Shinde, Pradnya Yeram, Chinmay Patkar, Pallavi Sawant, Chitrangi Mestry, Surendra
Ticketing & Guest Commerce | Payments | 9 | 0 | 3 | 10 | 49 | 28 | 0 | 2 | 19 | 0 | 49 | 7 Oct 2026 | 17 Dec 2026 | 1-6 | Pranay Shinde | Pranay Shinde, Chinmay Patkar, Pallavi Sawant, Hrushikant Patkar, Pradnya Yeram, Chitrangi Mestry
Ticketing & Guest Commerce | Wallet & Cashless | 52 | 0 | 11 | 108 | 70 | 43 | 0 | 1 | 156 | 0 | 200 | 6 Oct 2026 | 21 Dec 2026 | 1-6 | Pranay Shinde | Pranay Shinde, Pradnya Yeram, Chinmay Patkar, Sanket Keluskar, Pallavi Sawant, New full-stack developer 2
Ticketing & Guest Commerce | White Label & CMS | 65 | 0 | 7 | 40 | 95 | 132 | 0 | 10 | 0 | 0 | 143 | 5 Oct 2026 | 30 Nov 2026 | 1-5 | Hrushikant Patkar | Hrushikant Patkar, Chitrangi Mestry, Chinmay Patkar, Deep Khanvilkar, Tanmay Dukhande, Sanket Keluskar
Ticketing & Guest Commerce | Transport | 0 | 0 | 3 | 19 | 32 | 55 | 0 | 0 | 0 | 0 | 55 | 6 Oct 2026 | 5 Nov 2026 | 1-3 | Sanket Keluskar | Sanket Keluskar, Tanmay Dukhande, Chinmay Patkar, Pranay Shinde, Pradnya Yeram, Surendra
Food, Beverage & Retail | Food & Beverage | 95 | 0 | 12 | 68 | 164 | 215 | 0 | 0 | 38 | 0 | 253 | 12 Oct 2026 | 29 Dec 2026 | 1-7 | Tanmay Dukhande | Tanmay Dukhande, Pradnya Yeram, Chitrangi Mestry, Deep Khanvilkar, Pranay Shinde, Pallavi Sawant
Food, Beverage & Retail | Retail | 14 | 0 | 6 | 13 | 23 | 32 | 0 | 0 | 10 | 0 | 42 | 13 Oct 2026 | 24 Dec 2026 | 1-6 | Pranay Shinde | Pranay Shinde, Pradnya Yeram, Chitrangi Mestry, Chinmay Patkar, Hrushikant Patkar, Deep Khanvilkar
Food, Beverage & Retail | Rentals | 0 | 0 | 7 | 107 | 43 | 2 | 0 | 0 | 31 | 112 | 145 | 5 Nov 2026 | 29 Dec 2026 | 3-7 | New full-stack developer 2 | New full-stack developer 2, Pradnya Yeram, New full-stack developer 1, Chitrangi Mestry, Sanket Keluskar, Pallavi Sawant
Food, Beverage & Retail | Inventory & Procurement | 115 | 0 | 5 | 24 | 56 | 33 | 0 | 0 | 3 | 41 | 77 | 9 Oct 2026 | 30 Dec 2026 | 1-7 | Pranay Shinde | Pranay Shinde, Deep Khanvilkar, Sanket Keluskar, Pallavi Sawant, Chitrangi Mestry, Surendra
Venue Operations | Admission & Access Control | 108 | 1 | 16 | 189 | 254 | 106 | 0 | 1 | 275 | 0 | 382 | 7 Oct 2026 | 29 Dec 2026 | 1-7 | Hrushikant Patkar | Hrushikant Patkar, Chinmay Patkar, Sanket Keluskar, Pradnya Yeram, Tanmay Dukhande, Chitrangi Mestry
Venue Operations | Accreditation | 58 | 0 | 5 | 70 | 48 | 4 | 0 | 1 | 1 | 90 | 96 | 6 Oct 2026 | 31 Dec 2026 | 1-7 | Pradnya Yeram | Pradnya Yeram, New full-stack developer 2, Hrushikant Patkar, New full-stack developer 1, Sanket Keluskar, Pallavi Sawant
Venue Operations | Resources & Capacity | 92 | 1 | 8 | 69 | 62 | 40 | 0 | 0 | 0 | 73 | 113 | 7 Oct 2026 | 1 Jan 2027 | 1-7 | Tanmay Dukhande | Tanmay Dukhande, Sanket Keluskar, Hrushikant Patkar, Pallavi Sawant, Chinmay Patkar, Chitrangi Mestry
Venue Operations | Workforce & Staff | 27 | 0 | 4 | 33 | 47 | 15 | 0 | 2 | 0 | 51 | 68 | 8 Oct 2026 | 1 Jan 2027 | 1-7 | Pranay Shinde | Pranay Shinde, Chitrangi Mestry, Tanmay Dukhande, Pallavi Sawant, Pradnya Yeram, Deep Khanvilkar
Venue Operations | Maintenance & Safety | 75 | 0 | 5 | 30 | 44 | 56 | 0 | 0 | 0 | 32 | 88 | 8 Oct 2026 | 4 Jan 2027 | 1-7 | Tanmay Dukhande | Tanmay Dukhande, Chitrangi Mestry, Pallavi Sawant, Sanket Keluskar, Deep Khanvilkar, Pranay Shinde
Venue Operations | Games & Rides | 14 | 0 | 5 | 75 | 40 | 13 | 0 | 0 | 0 | 82 | 95 | 7 Oct 2026 | 5 Jan 2027 | 1-7 | Pallavi Sawant | Pallavi Sawant, Sanket Keluskar, New full-stack developer 2, Pradnya Yeram, New full-stack developer 1, Pranay Shinde
Venue Operations | Virtual Queue | 37 | 1 | 6 | 12 | 22 | 32 | 0 | 0 | 0 | 7 | 39 | 13 Oct 2026 | 5 Jan 2027 | 1-7 | Tanmay Dukhande | Tanmay Dukhande, Chitrangi Mestry, Sanket Keluskar, Chinmay Patkar, Surendra, Pallavi Sawant
Finance & Insights | Finance, Ledger & Tax | 204 | 2 | 10 | 25 | 72 | 71 | 0 | 3 | 25 | 0 | 100 | 9 Oct 2026 | 29 Dec 2026 | 1-7 | Tanmay Dukhande | Tanmay Dukhande, Pallavi Sawant, Sanket Keluskar, Surendra, Pradnya Yeram, Chitrangi Mestry
Finance & Insights | Reporting & Analytics | 189 | 0 | 18 | 96 | 51 | 50 | 0 | 1 | 0 | 91 | 142 | 7 Oct 2026 | 13 Jan 2027 | 1-8 | Pallavi Sawant | Pallavi Sawant, Chinmay Patkar, Sanket Keluskar, Pradnya Yeram, Chitrangi Mestry, Hrushikant Patkar
Customer & Marketing | Marketing & CRM | 421 | 1 | 25 | 205 | 271 | 196 | 0 | 2 | 1 | 231 | 430 | 12 Oct 2026 | 8 Jan 2027 | 1-7 | Pranay Shinde | Pranay Shinde, Pallavi Sawant, Chinmay Patkar, Sanket Keluskar, Chitrangi Mestry, Surendra
AI & Intelligence | AI & Intelligence | 287 | 2 | 35 | 137 | 142 | 659 | 141 | 75 | 4 | 2187 | 3065 | 5 Oct 2026 | 11 Mar 2027 | 1-12 | Kalpita Mejari | Kalpita Mejari, Second AI engineer, Hrushikant Patkar, Tanmay Dukhande, Sanket Keluskar, Pradnya Yeram

## Build phases
Phase | Side | Starts | Ends | Block A hours | Block A2 hours | Block B hours | Block C hours | Block D hours | Hours | Main modules | People
0 Plumbing | back end | 5 Oct 2026 | 3 Mar 2027 | 715 | 128 | 92 | 35 | 1765 | 2735 | AI & Intelligence, Foundation & Setup, Admission & Access Control, Ticketing Catalogue & Products, Tenancy, Venues & Devices, Marketing & CRM, Orders & Reservations, Payments | Kalpita Mejari, Second AI engineer, Hrushikant Patkar, Tanmay Dukhande, Pranay Shinde, Deep Khanvilkar
0 Plumbing | front end | 30 Oct 2026 | 28 Dec 2026 | 0 | 0 | 25 | 0 | 2 | 27 | Tenancy, Venues & Devices, Platform Operations, Subscription & Licensing, Workforce & Staff, Accreditation | Chitrangi Mestry, Pradnya Yeram, Sanket Keluskar, Chinmay Patkar
1 Foundation | back end | 8 Oct 2026 | 1 Jan 2027 | 182 | 0 | 160 | 2 | 42 | 386 | Subscription & Licensing, White Label & CMS, Identity, Roles & Security, Approval Workflows, Tenancy, Venues & Devices, Accreditation, Workforce & Staff, Platform Operations | Pallavi Sawant, Hrushikant Patkar, Deep Khanvilkar, Sanket Keluskar, Surendra, Pranay Shinde
1 Foundation | front end | 5 Oct 2026 | 8 Jan 2027 | 102 | 0 | 287 | 8 | 90 | 486 | Subscription & Licensing, Identity, Roles & Security, Accreditation, White Label & CMS, Approval Workflows, Tenancy, Venues & Devices, Workforce & Staff, Developer Portal & Public API | Chitrangi Mestry, Pradnya Yeram, Chinmay Patkar, Sanket Keluskar, Pallavi Sawant, Surendra
2 Commerce | back end | 8 Oct 2026 | 29 Dec 2026 | 330 | 0 | 144 | 258 | 0 | 732 | Ticketing Catalogue & Products, Orders & Reservations, Admission & Access Control, Pricing, Promotions & Bundles, Finance, Ledger & Tax, Wallet & Cashless, Seat Management & Venue Maps, Payments | Pranay Shinde, Hrushikant Patkar, Tanmay Dukhande, Deep Khanvilkar, Pallavi Sawant, New full-stack developer 1
2 Commerce | front end | 5 Oct 2026 | 4 Jan 2027 | 223 | 0 | 75 | 463 | 3 | 763 | Admission & Access Control, Orders & Reservations, Wallet & Cashless, Ticketing Catalogue & Products, Seat Management & Venue Maps, Finance, Ledger & Tax, Food & Beverage, Pricing, Promotions & Bundles | Pradnya Yeram, Chitrangi Mestry, Sanket Keluskar, Pallavi Sawant, Chinmay Patkar, Surendra
3 Operations | back end | 5 Oct 2026 | 8 Jan 2027 | 248 | 0 | 229 | 232 | 89 | 797 | Foundation & Setup, Food & Beverage, Inventory & Procurement, Maintenance & Safety, Resources & Capacity, Rentals, Transport, Games & Rides | Tanmay Dukhande, Sanket Keluskar, Deep Khanvilkar, Pranay Shinde, Chinmay Patkar, Hrushikant Patkar
3 Operations | front end | 5 Oct 2026 | 8 Jan 2027 | 150 | 0 | 37 | 38 | 231 | 457 | Rentals, Food & Beverage, Resources & Capacity, Games & Rides, Digital Asset Management, Maintenance & Safety, Inventory & Procurement, Transport | Chitrangi Mestry, Pradnya Yeram, Sanket Keluskar, Pallavi Sawant, Surendra, Chinmay Patkar
4 Engagement | back end | 8 Oct 2026 | 9 Feb 2027 | 163 | 0 | 5 | 4 | 173 | 345 | Marketing & CRM, AI & Intelligence | Pranay Shinde, Tanmay Dukhande, Hrushikant Patkar, Deep Khanvilkar, Pallavi Sawant, Sanket Keluskar
4 Engagement | front end | 7 Oct 2026 | 12 Jan 2027 | 104 | 0 | 7 | 2 | 238 | 351 | Marketing & CRM, AI & Intelligence, White Label & CMS, Tenancy, Venues & Devices, Pricing, Promotions & Bundles, Orders & Reservations, Seat Management & Venue Maps, Reporting & Analytics | Sanket Keluskar, Pradnya Yeram, Chitrangi Mestry, Pallavi Sawant, Chinmay Patkar, New full-stack developer 2
5 Reporting | back end | 15 Oct 2026 | 8 Jan 2027 | 21 | 0 | 12 | 0 | 7 | 40 | Reporting & Analytics, Platform Operations | Deep Khanvilkar, Hrushikant Patkar, Surendra, Chinmay Patkar, Pallavi Sawant, Sanket Keluskar
5 Reporting | front end | 15 Oct 2026 | 13 Jan 2027 | 18 | 0 | 1 | 0 | 68 | 87 | Reporting & Analytics, Approval Workflows, Admission & Access Control, Platform Operations | Pradnya Yeram, Chitrangi Mestry, Sanket Keluskar, Pallavi Sawant, New full-stack developer 2, Surendra

## Gantt
Block / app-module | Lead | Hours | Done | S1 |  | S2 |  | S3 |  | S4 |  | S5 |  | S6 |  | S7 |  | S8 |  | S9 |  | S10 |  | S11 |  | S12 |  | S13
|  |  |  | 05 Oct | 12 Oct | 19 Oct | 26 Oct | 02 Nov | 09 Nov | 16 Nov | 23 Nov | 30 Nov | 07 Dec | 14 Dec | 21 Dec | 28 Dec | 04 Jan | 11 Jan | 18 Jan | 25 Jan | 01 Feb | 08 Feb | 15 Feb | 22 Feb | 01 Mar | 08 Mar | 15 Mar | 22 Mar | 29 Mar | 05 Apr
Block A (Sprints 1-4) |  | 2059 | 27 Nov 2026
Foundation · Setup and environments | Hrushikant Patkar | 19 | 14 Oct 2026
Foundation · Database migrations | Hrushikant Patkar | 82 | 14 Oct 2026
Foundation · Platform kernel | Tanmay Dukhande | 26 | 15 Oct 2026
Foundation · Offline: POS, Kitchen Display and scanner | Tanmay Dukhande | 12 | 16 Oct 2026
AI engine · Block A: gateway and guest AI (concierge, Help me choose, translations, planner) | Second AI engineer | 260 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
AI engine · Block A: baseline layer, day-one suggestions, Qdrant tenancy, evaluation | Kalpita Mejari | 248 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Identity & Security · Guest Web | Pranay Shinde | 32 | 19 Oct 2026
Identity & Security · Guest App | Chitrangi Mestry | 10 | 19 Oct 2026
Identity & Security · POS | Pranay Shinde | 9 | 20 Oct 2026
Identity & Security · Staff App (Block A) | Deep Khanvilkar | 5 | 20 Oct 2026
Identity & Security · Staff App (Block A completion) | Chitrangi Mestry | 1 | 20 Oct 2026
Identity & Security · Scanner (Block A) | Chitrangi Mestry | 2 | 20 Oct 2026
Identity & Security · CMS 1 of 2 | Deep Khanvilkar | 5 | 13 Oct 2026
Identity & Security · Support Console (Block A) | Pallavi Sawant | 3 | 20 Oct 2026
Identity & Security · TICVAI Console 1 of 3 | Tanmay Dukhande | 26 | 28 Oct 2026 | bar: 26 Oct
Identity & Security · Partner Portal (Block A) | Surendra | 3 | 20 Oct 2026
Tenancy & Venues · POS | Hrushikant Patkar | 13 | 19 Oct 2026
Tenancy & Venues · Venue Management (Block A) | Hrushikant Patkar | 18 | 4 Nov 2026 | bar: 26 Oct to 02 Nov
Subscription & Licensing · TICVAI Console 1 of 6 | Pallavi Sawant | 21 | 10 Nov 2026 | bar: 26 Oct to 09 Nov
Approvals · POS | Pranay Shinde | 37 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
Approvals · Venue Management (Block A) | Hrushikant Patkar | 13 | 30 Oct 2026 | bar: 26 Oct
Digital Assets · CMS 1 of 4 | Hrushikant Patkar | 13 | 22 Oct 2026
White Label · Guest Web | Hrushikant Patkar | 70 | 3 Nov 2026 | bar: 26 Oct to 02 Nov
White Label · Guest App | Pranay Shinde | 23 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
White Label · CMS | Chinmay Patkar | 81 | 3 Nov 2026 | bar: 26 Oct to 02 Nov
White Label · TICVAI Console | Chinmay Patkar | 5 | 29 Oct 2026 | bar: 26 Oct
Platform Foundation · Venue Management (setup) | Tanmay Dukhande | 11 | 20 Oct 2026
Platform Foundation · Venue Management (setup, the rest of the screens) | Pallavi Sawant | 21 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Platform Foundation · TICVAI Console (setup) | Deep Khanvilkar | 6 | 30 Oct 2026 | bar: 26 Oct
Platform Foundation · TICVAI Console (setup, the rest of the screens) | Pallavi Sawant | 14 | 10 Nov 2026 | bar: 26 Oct to 09 Nov
Platform Foundation · Developer Portal (setup) | Pranay Shinde | 7 | 30 Oct 2026 | bar: 26 Oct
Public API · Developer Portal (Block A) | Sanket Keluskar | 2 | 30 Oct 2026 | bar: 26 Oct
Platform Foundation · Developer Portal (setup, the rest of the screens) | Pallavi Sawant | 9 | 30 Oct 2026 | bar: 26 Oct
Public API · API only (Block A completion) | Surendra | 0 | 13 Oct 2026
Ticketing & Guest Commerce · Venue Management (setup) | Hrushikant Patkar | 81 | 3 Nov 2026 | bar: 26 Oct to 02 Nov
Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) | Tanmay Dukhande | 89 | 24 Nov 2026 | bar: 26 Oct to 23 Nov
Ticketing · Guest Web | Pranay Shinde | 32 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Ticketing · Guest App | Chitrangi Mestry | 17 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Ticketing · POS | Pradnya Yeram | 2 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Ticketing · Kiosk (Block A) | Pradnya Yeram | 2 | 27 Oct 2026 | bar: 26 Oct
Ticketing · Venue Management (Block A) | Tanmay Dukhande | 13 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Pricing & Promotions · Guest Web | Chitrangi Mestry | 1 | 20 Oct 2026
Pricing & Promotions · Guest App | Chinmay Patkar | 2 | 28 Oct 2026 | bar: 26 Oct
Seating & Maps · Guest Web | Chinmay Patkar | 13 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Seating & Maps · Guest App | Chinmay Patkar | 11 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Seating & Maps · POS | Pradnya Yeram | 2 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Seating & Maps · Venue Management (Block A) | Pradnya Yeram | 11 | 30 Oct 2026 | bar: 26 Oct
Orders & Reservations · Guest Web | Chitrangi Mestry | 19 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Orders & Reservations · Guest App | Tanmay Dukhande | 52 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Orders & Reservations · POS | Pradnya Yeram | 25 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Orders & Reservations · Venue Management (Block A) | Pranay Shinde | 39 | 11 Nov 2026 | bar: 26 Oct to 09 Nov
Payments · Guest Web | Chitrangi Mestry | 2 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Payments · Guest App | Pradnya Yeram | 2 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Payments · API only (Block A) | Hrushikant Patkar | 5 | 9 Nov 2026 | bar: 02 Nov to 09 Nov
Wallet & Cashless · Guest Web | Chinmay Patkar | 2 | 26 Oct 2026 | bar: 26 Oct
Wallet & Cashless · Guest App | Chitrangi Mestry | 4 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Wallet & Cashless · Venue Management (Block A completion) | Pranay Shinde | 8 | 11 Nov 2026 | bar: 26 Oct to 09 Nov
Admission & Access · Guest Web | Chinmay Patkar | 7 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Admission & Access · Guest App | Chinmay Patkar | 11 | 3 Nov 2026 | bar: 26 Oct to 02 Nov
Admission & Access · Scanner (Block A) | Hrushikant Patkar | 13 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Admission & Access · Venue Management (Block A) | Pranay Shinde | 21 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Admission & Access · Venue Management (Block A completion) | Hrushikant Patkar | 6 | 4 Nov 2026 | bar: 26 Oct to 02 Nov
Finance & Tax · Guest Web | Chitrangi Mestry | 4 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Finance & Tax · Guest App | Chitrangi Mestry | 3 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Finance & Tax · POS | Pradnya Yeram | 2 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Finance & Tax · Venue Management (Block A) | Pallavi Sawant | 14 | 13 Nov 2026 | bar: 26 Oct to 09 Nov
Finance & Tax · API only (Block A completion) | Sanket Keluskar | 2 | 12 Nov 2026 | bar: 26 Oct to 09 Nov
Venue Operations · Venue Management (setup) | Hrushikant Patkar | 26 | 12 Nov 2026 | bar: 26 Oct to 09 Nov
Venue Operations · Venue Management (setup, the rest of the screens) | Sanket Keluskar | 40 | 20 Nov 2026 | bar: 26 Oct to 16 Nov
Finance & Insights · Venue Management (setup) | Tanmay Dukhande | 14 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
Finance & Insights · Venue Management (setup, the rest of the screens) | Pallavi Sawant | 24 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Finance & Insights · Analytics (setup) | Deep Khanvilkar | 5 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
Transport · Guest Web | Chinmay Patkar | 4 | 28 Oct 2026 | bar: 26 Oct
Transport · Guest App | Chitrangi Mestry | 7 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Food & Beverage · Guest Web | Tanmay Dukhande | 10 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Food & Beverage · Guest App | Chinmay Patkar | 8 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Food & Beverage · POS | Pradnya Yeram | 56 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Food & Beverage · Kitchen Display | Pradnya Yeram | 17 | 13 Nov 2026 | bar: 26 Oct to 09 Nov
Food & Beverage · Staff App (Block A) | Chitrangi Mestry | 18 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Food & Beverage · Venue Management (Block A) | Pallavi Sawant | 25 | 20 Nov 2026 | bar: 26 Oct to 16 Nov
Retail · Guest Web | Chitrangi Mestry | 1 | 28 Oct 2026 | bar: 26 Oct
Retail · Guest App | Chinmay Patkar | 3 | 2 Nov 2026 | bar: 26 Oct to 02 Nov
Retail · POS | Pradnya Yeram | 11 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Resources & Capacity · Guest Web | Chitrangi Mestry | 2 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Resources & Capacity · Guest App | Pradnya Yeram | 2 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Resources & Capacity · Venue Management (Block A) | Hrushikant Patkar | 9 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Workforce · POS | Pradnya Yeram | 2 | 13 Nov 2026 | bar: 26 Oct to 09 Nov
Maintenance & Safety · Staff App (Block A) | Hrushikant Patkar | 30 | 18 Nov 2026 | bar: 26 Oct to 16 Nov
Maintenance & Safety · Venue Management (Block A) | Hrushikant Patkar | 14 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Games & Rides · Venue Management (Block A) | Hrushikant Patkar | 10 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Virtual Queue · Guest Web | Hrushikant Patkar | 3 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Virtual Queue · Guest App | Chinmay Patkar | 4 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Virtual Queue · Staff App (Block A) | Hrushikant Patkar | 4 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
Virtual Queue · Venue Management (Block A) | Sanket Keluskar | 7 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Food, Beverage & Retail · Staff App (setup) | Deep Khanvilkar | 3 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
Food, Beverage & Retail · Venue Management (setup) | Pallavi Sawant | 10 | 13 Nov 2026 | bar: 26 Oct to 09 Nov
Finance & Insights · Analytics (setup, the rest of the screens) | Sanket Keluskar | 3 | 20 Nov 2026 | bar: 26 Oct to 16 Nov
Food, Beverage & Retail · Venue Management (setup, the rest of the screens) | Sanket Keluskar | 19 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Food, Beverage & Retail · Staff App (setup, the rest of the screens) | Pranay Shinde | 8 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Marketing & CRM · Guest Web | Chinmay Patkar | 28 | 24 Nov 2026 | bar: 26 Oct to 23 Nov
Marketing & CRM · Guest App | Chinmay Patkar | 12 | 24 Nov 2026 | bar: 26 Oct to 23 Nov
Marketing & CRM · POS | Pradnya Yeram | 1 | 28 Oct 2026 | bar: 26 Oct
Marketing & CRM · Venue Management (Block A) | Pallavi Sawant | 36 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Marketing & CRM · CMS 1 of 4 | Chinmay Patkar | 3 | 23 Nov 2026 | bar: 02 Nov to 23 Nov
Marketing & CRM · Support Console (Block A) | Pallavi Sawant | 13 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
AI · Guest Web | Chinmay Patkar | 3 | 16 Nov 2026 | bar: 02 Nov to 16 Nov
AI · Guest App | Pradnya Yeram | 5 | 19 Nov 2026 | bar: 26 Oct to 16 Nov
AI · Kiosk (Block A) | Pradnya Yeram | 1 | 5 Nov 2026 | bar: 26 Oct to 02 Nov
Customer & Marketing · Venue Management (setup) | Pranay Shinde | 13 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Customer & Marketing · Venue Management (setup, the rest of the screens) | Sanket Keluskar | 25 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Customer & Marketing · CMS (setup) | Pallavi Sawant | 1 | 29 Oct 2026 | bar: 26 Oct
Customer & Marketing · CMS (setup, the rest of the screens) | Surendra | 8 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Customer & Marketing · Support Console (setup) | Sanket Keluskar | 0 | 30 Oct 2026 | bar: 26 Oct
Customer & Marketing · Support Console (setup, the rest of the screens) | Pradnya Yeram | 4 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
AI & Intelligence · Venue Management (setup) | Tanmay Dukhande | 6 | 11 Nov 2026 | bar: 26 Oct to 09 Nov
AI & Intelligence · Venue Management (setup, the rest of the screens) | Tanmay Dukhande | 14 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
AI & Intelligence · TICVAI Console (setup) | Tanmay Dukhande | 23 | 13 Nov 2026 | bar: 26 Oct to 09 Nov
AI & Intelligence · TICVAI Console (setup, the rest of the screens) | Pradnya Yeram | 17 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Reporting · POS | Pradnya Yeram | 1 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Reporting · Kitchen Display | Pradnya Yeram | 1 | 16 Nov 2026 | bar: 26 Oct to 16 Nov
Reporting · Venue Management (Block A) | Pallavi Sawant | 9 | 23 Nov 2026 | bar: 26 Oct to 23 Nov
Reporting · Analytics (Block A) | Chitrangi Mestry | 3 | 17 Nov 2026 | bar: 26 Oct to 16 Nov
Reporting · API only (Block A completion) | Surendra | 3 | 25 Nov 2026 | bar: 02 Nov to 23 Nov
Block A2 (Sprints 4-5) |  | 61 | 11 Dec 2026
AI engine · Block A2: the AI work moved out of A1 (planner, suggestions) | Kalpita Mejari | 128 | 7 Dec 2026 | bar: 23 Nov to 07 Dec
Block B (Sprints 3-6) |  | 1183 | 25 Dec 2026
Foundation · platform (later blocks) | Pallavi Sawant | 4 | 13 Nov 2026 | bar: 02 Nov to 09 Nov
Identity & Security · Staff App | Chitrangi Mestry | 4 | 4 Nov 2026 | bar: 26 Oct to 02 Nov
Identity & Security · Venue Management | Surendra | 25 | 2 Dec 2026 | bar: 19 Oct to 30 Nov
Identity & Security · CMS 2 of 2 | Pradnya Yeram | 1 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Identity & Security · Analytics | Pradnya Yeram | 2 | 9 Nov 2026 | bar: 26 Oct to 09 Nov
Identity & Security · TICVAI Console 2 of 3 | Chitrangi Mestry | 22 | 30 Nov 2026 | bar: 26 Oct to 30 Nov
Identity & Security · TICVAI Console 3 of 3 | Chinmay Patkar | 7 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Identity & Security · Sign-up | Pradnya Yeram | 1 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Identity & Security · Partner Portal | Pradnya Yeram | 10 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Tenancy & Venues · Staff App | Chitrangi Mestry | 1 | 13 Nov 2026 | bar: 26 Oct to 09 Nov
Tenancy & Venues · Venue Management 1 of 3 | Sanket Keluskar | 24 | 26 Nov 2026 | bar: 26 Oct to 23 Nov
Tenancy & Venues · Venue Management 2 of 3 | Sanket Keluskar | 22 | 18 Nov 2026 | bar: 26 Oct to 16 Nov
Tenancy & Venues · Venue Management 3 of 3 | Chitrangi Mestry | 15 | 16 Nov 2026 | bar: 19 Oct to 16 Nov
Tenancy & Venues · Analytics | Pradnya Yeram | 1 | 6 Nov 2026 | bar: 26 Oct to 02 Nov
Tenancy & Venues · TICVAI Console | Pradnya Yeram | 4 | 30 Nov 2026 | bar: 02 Nov to 30 Nov
Platform Operations · Scanner | Pallavi Sawant | 15 | 9 Nov 2026 | bar: 26 Oct to 09 Nov
Platform Operations · TICVAI Console 1 of 2 | Pallavi Sawant | 36 | 11 Nov 2026 | bar: 26 Oct to 09 Nov
Platform Operations · TICVAI Console 2 of 2 | Chitrangi Mestry | 1 | 9 Nov 2026 | bar: 02 Nov to 09 Nov
Subscription & Licensing · Venue Management 1 of 3 | Surendra | 61 | 7 Dec 2026 | bar: 26 Oct to 07 Dec
Subscription & Licensing · Venue Management 2 of 3 | Pradnya Yeram | 30 | 3 Dec 2026 | bar: 02 Nov to 30 Nov
Subscription & Licensing · Venue Management 3 of 3 | Sanket Keluskar | 6 | 1 Dec 2026 | bar: 02 Nov to 30 Nov
Subscription & Licensing · TICVAI Console 2 of 6 | Sanket Keluskar | 21 | 1 Dec 2026 | bar: 02 Nov to 30 Nov
Subscription & Licensing · TICVAI Console 3 of 6 | Pallavi Sawant | 23 | 2 Dec 2026 | bar: 02 Nov to 30 Nov
Subscription & Licensing · TICVAI Console 4 of 6 | Chinmay Patkar | 22 | 1 Dec 2026 | bar: 02 Nov to 30 Nov
Subscription & Licensing · TICVAI Console 5 of 6 | Chitrangi Mestry | 21 | 2 Dec 2026 | bar: 09 Nov to 30 Nov
Subscription & Licensing · TICVAI Console 6 of 6 | Pradnya Yeram | 5 | 2 Dec 2026 | bar: 09 Nov to 30 Nov
Subscription & Licensing · Sign-up 1 of 2 | Sanket Keluskar | 18 | 1 Dec 2026 | bar: 26 Oct to 30 Nov
Subscription & Licensing · Sign-up 2 of 2 | Pradnya Yeram | 1 | 11 Nov 2026 | bar: 09 Nov
Subscription & Licensing · Partner Portal 1 of 2 | Pradnya Yeram | 33 | 2 Dec 2026 | bar: 09 Nov to 30 Nov
Subscription & Licensing · Partner Portal 2 of 2 | Pranay Shinde | 17 | 3 Dec 2026 | bar: 19 Oct to 30 Nov
Approvals · Venue Management 1 of 5 | Pallavi Sawant | 31 | 25 Nov 2026 | bar: 26 Oct to 23 Nov
Approvals · Venue Management 2 of 5 | Sanket Keluskar | 22 | 24 Nov 2026 | bar: 09 Nov to 23 Nov
Approvals · Venue Management 3 of 5 | Chinmay Patkar | 22 | 24 Nov 2026 | bar: 26 Oct to 23 Nov
Approvals · Venue Management 4 of 5 | Chitrangi Mestry | 19 | 23 Nov 2026 | bar: 09 Nov to 23 Nov
Approvals · Venue Management 5 of 5 | Pradnya Yeram | 15 | 24 Nov 2026 | bar: 09 Nov to 23 Nov
Approvals · TICVAI Console | Pradnya Yeram | 3 | 23 Nov 2026 | bar: 09 Nov to 23 Nov
Public API · Venue Management | Chitrangi Mestry | 18 | 24 Nov 2026 | bar: 09 Nov to 23 Nov
Public API · TICVAI Console | Pradnya Yeram | 3 | 24 Nov 2026 | bar: 09 Nov to 23 Nov
Public API · Partner Portal | Chitrangi Mestry | 1 | 17 Nov 2026 | bar: 16 Nov
Public API · Developer Portal | Pranay Shinde | 7 | 1 Dec 2026 | bar: 16 Nov to 30 Nov
Digital Assets · CMS 2 of 4 | Pradnya Yeram | 25 | 30 Nov 2026 | bar: 16 Nov to 30 Nov
Digital Assets · CMS 3 of 4 | Chitrangi Mestry | 21 | 30 Nov 2026 | bar: 26 Oct to 30 Nov
Digital Assets · CMS 4 of 4 | Sanket Keluskar | 2 | 30 Nov 2026 | bar: 16 Nov to 30 Nov
White Label · Kiosk | Chitrangi Mestry | 2 | 20 Nov 2026 | bar: 16 Nov
White Label · Venue Management | Sanket Keluskar | 7 | 30 Nov 2026 | bar: 16 Nov to 30 Nov
Ticketing · Kiosk | Chitrangi Mestry | 2 | 20 Nov 2026 | bar: 16 Nov
Ticketing · Staff App | Chitrangi Mestry | 3 | 20 Nov 2026 | bar: 16 Nov
Ticketing · Venue Management 1 of 10 | Pallavi Sawant | 25 | 4 Dec 2026 | bar: 02 Nov to 30 Nov
Ticketing · Venue Management 2 of 10 | New full-stack developer 2 | 34 | 4 Dec 2026 | bar: 02 Nov to 30 Nov
Ticketing · Venue Management 3 of 10 | New full-stack developer 1 | 33 | 8 Dec 2026 | bar: 02 Nov to 07 Dec
Ticketing · Venue Management 4 of 10 | Tanmay Dukhande | 35 | 8 Dec 2026 | bar: 26 Oct to 07 Dec
Ticketing · Venue Management 5 of 10 | Hrushikant Patkar | 37 | 7 Dec 2026 | bar: 02 Nov to 07 Dec
Ticketing · Venue Management 6 of 10 | Pranay Shinde | 38 | 7 Dec 2026 | bar: 26 Oct to 07 Dec
Ticketing · Venue Management 7 of 10 | New full-stack developer 1 | 33 | 7 Dec 2026 | bar: 02 Nov to 07 Dec
Ticketing · Venue Management 8 of 10 | Pradnya Yeram | 30 | 7 Dec 2026 | bar: 26 Oct to 07 Dec
Ticketing · Venue Management 9 of 10 | Pallavi Sawant | 25 | 8 Dec 2026 | bar: 02 Nov to 07 Dec
Ticketing · Venue Management 10 of 10 | Chinmay Patkar | 5 | 7 Dec 2026 | bar: 16 Nov to 07 Dec
Ticketing · Partner Portal | Chitrangi Mestry | 3 | 4 Dec 2026 | bar: 30 Nov
Pricing & Promotions · Venue Management 1 of 8 | Hrushikant Patkar | 32 | 9 Dec 2026 | bar: 02 Nov to 07 Dec
Pricing & Promotions · Venue Management 2 of 8 | Pranay Shinde | 27 | 14 Dec 2026 | bar: 02 Nov to 14 Dec
AI engine · Operational suggestions | Second AI engineer | 60 | 16 Dec 2026 | bar: 30 Nov to 14 Dec
Block C (Sprints 5-8) |  | 1197 | 22 Jan 2027
Pricing & Promotions · Venue Management 3 of 8 | Pranay Shinde | 26 | 16 Dec 2026 | bar: 02 Nov to 14 Dec
Pricing & Promotions · Venue Management 4 of 8 | Tanmay Dukhande | 25 | 15 Dec 2026 | bar: 02 Nov to 14 Dec
Pricing & Promotions · Venue Management 5 of 8 | Pranay Shinde | 26 | 15 Dec 2026 | bar: 02 Nov to 14 Dec
Pricing & Promotions · Venue Management 6 of 8 | Tanmay Dukhande | 20 | 22 Dec 2026 | bar: 02 Nov to 21 Dec
Pricing & Promotions · Venue Management 7 of 8 | Tanmay Dukhande | 19 | 11 Dec 2026 | bar: 02 Nov to 07 Dec
Pricing & Promotions · Venue Management 8 of 8 | Pradnya Yeram | 16 | 28 Dec 2026 | bar: 16 Nov to 28 Dec
Pricing & Promotions · Analytics | Chitrangi Mestry | 1 | 8 Dec 2026 | bar: 30 Nov to 07 Dec
Seating & Maps · Staff App | Chitrangi Mestry | 2 | 2 Dec 2026 | bar: 16 Nov to 30 Nov
Seating & Maps · Venue Management 1 of 5 | Chitrangi Mestry | 24 | 8 Dec 2026 | bar: 30 Nov to 07 Dec
Seating & Maps · Venue Management 2 of 5 | Pradnya Yeram | 24 | 10 Dec 2026 | bar: 30 Nov to 07 Dec
Seating & Maps · Venue Management 3 of 5 | Chinmay Patkar | 33 | 11 Dec 2026 | bar: 30 Nov to 07 Dec
Seating & Maps · Venue Management 4 of 5 | Chinmay Patkar | 22 | 11 Dec 2026 | bar: 30 Nov to 07 Dec
Seating & Maps · Venue Management 5 of 5 | New full-stack developer 1 | 11 | 11 Dec 2026 | bar: 30 Nov to 07 Dec
Seating & Maps · Partner Portal | Hrushikant Patkar | 2 | 11 Dec 2026 | bar: 16 Nov to 07 Dec
Orders & Reservations · Kiosk | Chitrangi Mestry | 7 | 8 Dec 2026 | bar: 07 Dec
Orders & Reservations · Staff App | Chitrangi Mestry | 9 | 14 Dec 2026 | bar: 07 Dec to 14 Dec
Orders & Reservations · Venue Management 1 of 8 | Surendra | 23 | 23 Dec 2026 | bar: 07 Dec to 21 Dec
Orders & Reservations · Venue Management 2 of 8 | Tanmay Dukhande | 29 | 28 Dec 2026 | bar: 02 Nov to 28 Dec
Orders & Reservations · Venue Management 3 of 8 | New full-stack developer 1 | 23 | 28 Dec 2026 | bar: 09 Nov to 28 Dec
Orders & Reservations · Venue Management 4 of 8 | Hrushikant Patkar | 28 | 15 Dec 2026 | bar: 02 Nov to 14 Dec
Orders & Reservations · Venue Management 5 of 8 | Pradnya Yeram | 27 | 23 Dec 2026 | bar: 02 Nov to 21 Dec
Orders & Reservations · Venue Management 6 of 8 | Pradnya Yeram | 32 | 17 Dec 2026 | bar: 09 Nov to 14 Dec
Orders & Reservations · Venue Management 7 of 8 | Pradnya Yeram | 30 | 23 Dec 2026 | bar: 23 Nov to 21 Dec
Orders & Reservations · Venue Management 8 of 8 | Chinmay Patkar | 7 | 28 Dec 2026 | bar: 07 Dec to 28 Dec
Orders & Reservations · Sign-up | Sanket Keluskar | 1 | 15 Dec 2026 | bar: 14 Dec
Orders & Reservations · Partner Portal | Chinmay Patkar | 15 | 15 Dec 2026 | bar: 09 Nov to 14 Dec
Payments · Venue Management 1 of 3 | Tanmay Dukhande | 23 | 17 Dec 2026 | bar: 09 Nov to 14 Dec
Payments · Venue Management 2 of 3 | Hrushikant Patkar | 22 | 17 Dec 2026 | bar: 09 Nov to 14 Dec
Payments · Venue Management 3 of 3 | Pranay Shinde | 22 | 17 Dec 2026 | bar: 09 Nov to 14 Dec
Wallet & Cashless · Venue Management 1 of 7 | Pradnya Yeram | 26 | 17 Dec 2026 | bar: 09 Nov to 14 Dec
Wallet & Cashless · Venue Management 2 of 7 | Chinmay Patkar | 21 | 18 Dec 2026 | bar: 07 Dec to 14 Dec
Wallet & Cashless · Venue Management 3 of 7 | Chinmay Patkar | 21 | 21 Dec 2026 | bar: 07 Dec to 21 Dec
Wallet & Cashless · Venue Management 4 of 7 | New full-stack developer 1 | 21 | 18 Dec 2026 | bar: 09 Nov to 14 Dec
Wallet & Cashless · Venue Management 5 of 7 | Pallavi Sawant | 17 | 18 Dec 2026 | bar: 09 Nov to 14 Dec
Wallet & Cashless · Venue Management 6 of 7 | New full-stack developer 2 | 19 | 21 Dec 2026 | bar: 30 Nov to 21 Dec
Wallet & Cashless · Venue Management 7 of 7 | Pallavi Sawant | 17 | 21 Dec 2026 | bar: 30 Nov to 21 Dec
Admission & Access · Staff App | Chitrangi Mestry | 6 | 16 Dec 2026 | bar: 14 Dec
Admission & Access · Scanner | Chitrangi Mestry | 15 | 18 Dec 2026 | bar: 09 Nov to 14 Dec
Admission & Access · Venue Management 1 of 8 | Hrushikant Patkar | 33 | 22 Dec 2026 | bar: 30 Nov to 21 Dec
Admission & Access · Venue Management 2 of 8 | Hrushikant Patkar | 33 | 29 Dec 2026 | bar: 30 Nov to 28 Dec
Admission & Access · Venue Management 3 of 8 | Hrushikant Patkar | 31 | 21 Dec 2026 | bar: 09 Nov to 21 Dec
Admission & Access · Venue Management 4 of 8 | Tanmay Dukhande | 34 | 28 Dec 2026 | bar: 14 Dec to 28 Dec
Admission & Access · Venue Management 5 of 8 | Hrushikant Patkar | 32 | 29 Dec 2026 | bar: 09 Nov to 28 Dec
Admission & Access · Venue Management 6 of 8 | New full-stack developer 1 | 30 | 29 Dec 2026 | bar: 14 Dec to 28 Dec
Admission & Access · Venue Management 7 of 8 | Sanket Keluskar | 30 | 23 Dec 2026 | bar: 14 Dec to 21 Dec
Admission & Access · Venue Management 8 of 8 | New full-stack developer 1 | 11 | 28 Dec 2026 | bar: 14 Dec to 28 Dec
Finance & Tax · Venue Management | Tanmay Dukhande | 18 | 29 Dec 2026 | bar: 09 Nov to 28 Dec
Finance & Tax · Analytics | Pradnya Yeram | 2 | 22 Dec 2026 | bar: 14 Dec to 21 Dec
Finance & Tax · TICVAI Console | Chitrangi Mestry | 4 | 29 Dec 2026 | bar: 14 Dec to 28 Dec
Finance & Tax · Partner Portal | New full-stack developer 1 | 1 | 28 Dec 2026 | bar: 21 Dec to 28 Dec
Food & Beverage · Kiosk | Chitrangi Mestry | 1 | 21 Dec 2026 | bar: 21 Dec
Food & Beverage · Staff App | Chitrangi Mestry | 16 | 23 Dec 2026 | bar: 09 Nov to 21 Dec
Food & Beverage · Venue Management | Pallavi Sawant | 21 | 29 Dec 2026 | bar: 16 Nov to 28 Dec
Retail · Kiosk | Chitrangi Mestry | 1 | 23 Dec 2026 | bar: 21 Dec
Retail · Staff App | Chitrangi Mestry | 3 | 23 Dec 2026 | bar: 23 Nov to 21 Dec
Retail · Venue Management | Hrushikant Patkar | 3 | 24 Dec 2026 | bar: 30 Nov to 21 Dec
Rentals · Staff App 1 of 2 | Chitrangi Mestry | 26 | 24 Dec 2026 | bar: 09 Nov to 21 Dec
Block D (Sprints 6-10) |  | 1329 | 19 Feb 2027
Rentals · Staff App 2 of 2 | Chitrangi Mestry | 14 | 25 Dec 2026 | bar: 09 Nov to 21 Dec
Rentals · Venue Management 1 of 5 | New full-stack developer 2 | 29 | 29 Dec 2026 | bar: 09 Nov to 28 Dec
Rentals · Venue Management 2 of 5 | New full-stack developer 2 | 26 | 28 Dec 2026 | bar: 09 Nov to 28 Dec
Rentals · Venue Management 3 of 5 | Pallavi Sawant | 16 | 29 Dec 2026 | bar: 21 Dec to 28 Dec
Rentals · Venue Management 4 of 5 | Sanket Keluskar | 17 | 29 Dec 2026 | bar: 21 Dec to 28 Dec
Rentals · Venue Management 5 of 5 | New full-stack developer 1 | 1 | 25 Dec 2026 | bar: 21 Dec
Inventory · Staff App | Pranay Shinde | 12 | 28 Dec 2026 | bar: 16 Nov to 28 Dec
Inventory · Venue Management 1 of 2 | Pranay Shinde | 23 | 30 Dec 2026 | bar: 16 Nov to 28 Dec
Inventory · Venue Management 2 of 2 | Pradnya Yeram | 1 | 25 Dec 2026 | bar: 21 Dec
Accreditation · Venue Management 1 of 4 | Hrushikant Patkar | 28 | 30 Dec 2026 | bar: 05 Oct to 28 Dec
Accreditation · Venue Management 2 of 4 | New full-stack developer 1 | 22 | 30 Dec 2026 | bar: 05 Oct to 28 Dec
Accreditation · Venue Management 3 of 4 | New full-stack developer 2 | 22 | 31 Dec 2026 | bar: 07 Dec to 28 Dec
Accreditation · Venue Management 4 of 4 | New full-stack developer 2 | 2 | 31 Dec 2026 | bar: 28 Dec
Accreditation · Accreditation Web | Pradnya Yeram | 8 | 31 Dec 2026 | bar: 21 Dec to 28 Dec
Accreditation · platform (later blocks) | Tanmay Dukhande | 3 | 30 Dec 2026 | bar: 28 Dec
Resources & Capacity · Venue Management 1 of 4 | Hrushikant Patkar | 26 | 1 Jan 2027 | bar: 14 Dec to 28 Dec
Resources & Capacity · Venue Management 2 of 4 | New full-stack developer 1 | 20 | 31 Dec 2026 | bar: 09 Nov to 28 Dec
Resources & Capacity · Venue Management 3 of 4 | Chinmay Patkar | 19 | 1 Jan 2027 | bar: 09 Nov to 28 Dec
Resources & Capacity · Venue Management 4 of 4 | New full-stack developer 2 | 3 | 31 Dec 2026 | bar: 28 Dec
Workforce · Staff App | Chitrangi Mestry | 17 | 31 Dec 2026 | bar: 09 Nov to 28 Dec
Workforce · Venue Management 1 of 2 | Tanmay Dukhande | 26 | 1 Jan 2027 | bar: 28 Dec
Workforce · Venue Management 2 of 2 | New full-stack developer 1 | 2 | 31 Dec 2026 | bar: 28 Dec
Maintenance & Safety · Staff App | Chitrangi Mestry | 7 | 1 Jan 2027 | bar: 28 Dec
Maintenance & Safety · Venue Management 1 of 2 | Sanket Keluskar | 18 | 4 Jan 2027 | bar: 21 Dec to 04 Jan
Maintenance & Safety · Venue Management 2 of 2 | New full-stack developer 2 | 2 | 1 Jan 2027 | bar: 28 Dec
Games & Rides · Venue Management 1 of 4 | New full-stack developer 1 | 23 | 4 Jan 2027 | bar: 16 Nov to 04 Jan
Games & Rides · Venue Management 2 of 4 | Pradnya Yeram | 17 | 4 Jan 2027 | bar: 28 Dec to 04 Jan
Games & Rides · Venue Management 3 of 4 | Sanket Keluskar | 21 | 5 Jan 2027 | bar: 09 Nov to 04 Jan
Games & Rides · Venue Management 4 of 4 | New full-stack developer 2 | 15 | 5 Jan 2027 | bar: 09 Nov to 04 Jan
Virtual Queue · Staff App | Chitrangi Mestry | 2 | 31 Dec 2026 | bar: 28 Dec
Virtual Queue · Venue Management | Pallavi Sawant | 4 | 5 Jan 2027 | bar: 28 Dec to 04 Jan
Marketing & CRM · Kiosk | Chitrangi Mestry | 1 | 31 Dec 2026 | bar: 16 Nov to 28 Dec
Marketing & CRM · Staff App | Chitrangi Mestry | 7 | 1 Jan 2027 | bar: 28 Dec
Marketing & CRM · Venue Management 1 of 5 | Pranay Shinde | 29 | 6 Jan 2027 | bar: 07 Dec to 04 Jan
Marketing & CRM · Venue Management 2 of 5 | Chinmay Patkar | 25 | 6 Jan 2027 | bar: 09 Nov to 04 Jan
Marketing & CRM · Venue Management 3 of 5 | Sanket Keluskar | 24 | 7 Jan 2027 | bar: 16 Nov to 04 Jan
Marketing & CRM · Venue Management 4 of 5 | New full-stack developer 1 | 20 | 6 Jan 2027 | bar: 16 Nov to 04 Jan
Marketing & CRM · Venue Management 5 of 5 | Pranay Shinde | 28 | 7 Jan 2027 | bar: 09 Nov to 04 Jan
Marketing & CRM · CMS 2 of 4 | Hrushikant Patkar | 27 | 7 Jan 2027 | bar: 21 Dec to 04 Jan
Marketing & CRM · CMS 3 of 4 | Chinmay Patkar | 21 | 7 Jan 2027 | bar: 16 Nov to 04 Jan
Marketing & CRM · Support Console 1 of 2 | Tanmay Dukhande | 21 | 8 Jan 2027 | bar: 16 Nov to 04 Jan
Marketing & CRM · Support Console 2 of 2 | Pallavi Sawant | 5 | 7 Jan 2027 | bar: 16 Nov to 04 Jan
Marketing & CRM · Partner Portal | Deep Khanvilkar | 3 | 7 Jan 2027 | bar: 04 Jan
Marketing & CRM · CMS 4 of 4 | Hrushikant Patkar | 6 | 7 Jan 2027 | bar: 04 Jan
AI · Staff App | Chitrangi Mestry | 4 | 5 Jan 2027 | bar: 04 Jan
AI · Venue Management 1 of 2 | Tanmay Dukhande | 29 | 8 Jan 2027 | bar: 16 Nov to 04 Jan
AI · Venue Management 2 of 2 | New full-stack developer 1 | 2 | 7 Jan 2027 | bar: 04 Jan
AI · Analytics | Tanmay Dukhande | 13 | 8 Jan 2027 | bar: 16 Nov to 04 Jan
AI · Support Console | Pradnya Yeram | 2 | 7 Jan 2027 | bar: 16 Nov to 04 Jan
AI · TICVAI Console 1 of 6 | New full-stack developer 2 | 16 | 8 Jan 2027 | bar: 04 Jan
AI · TICVAI Console 2 of 6 | Tanmay Dukhande | 20 | 11 Jan 2027 | bar: 04 Jan to 11 Jan
AI · TICVAI Console 3 of 6 | Surendra | 16 | 11 Jan 2027 | bar: 16 Nov to 11 Jan
AI · TICVAI Console 4 of 6 | New full-stack developer 2 | 19 | 11 Jan 2027 | bar: 16 Nov to 11 Jan
AI · TICVAI Console 5 of 6 | Pallavi Sawant | 17 | 11 Jan 2027 | bar: 21 Dec to 11 Jan
AI · TICVAI Console 6 of 6 | Pranay Shinde | 17 | 12 Jan 2027 | bar: 04 Jan to 11 Jan
AI engine · Phase 2: learning from tenant data (training and promotion, forecasting, fraud classifier, learning-to-rank) | Second AI engineer | 743 | Phase 2
AI engine · Configuration assistant | Kalpita Mejari | 231 | 11 Mar 2027 | bar: 14 Dec to 08 Mar
AI engine · Seat-map and venue-layout generation | Second AI engineer | 80 | 5 Mar 2027 | bar: 14 Dec to 01 Mar
AI engine · Fraud and risk scoring | Second AI engineer | 140 | 4 Mar 2027 | bar: 28 Dec to 01 Mar
AI engine · Recommendations and personalisation | Kalpita Mejari | 140 | 5 Mar 2027 | bar: 18 Jan to 01 Mar
AI engine · Analytics assistant and metric explanation | Second AI engineer | 133 | 9 Mar 2027 | bar: 18 Jan to 08 Mar
AI engine · Forecasting | Kalpita Mejari | 40 | 24 Feb 2027 | bar: 07 Dec to 22 Feb
AI engine · Operational requirements and staffing | Kalpita Mejari | 60 | 25 Feb 2027 | bar: 08 Feb to 22 Feb
AI engine · Queue and wait-time prediction | Kalpita Mejari | 20 | 1 Mar 2027 | bar: 22 Feb to 01 Mar
AI engine · Approval-request scoring | Kalpita Mejari | 20 | 4 Mar 2027 | bar: 22 Feb to 01 Mar
AI engine · Marketing recommendations | Second AI engineer | 60 | 10 Mar 2027 | bar: 08 Feb to 08 Mar
AI engine · Anomaly detection (phase 2, after 2 April) | Kalpita Mejari | 100 | Phase 2
AI engine · Dynamic pricing suggestions (phase 2, after 2 April) | Kalpita Mejari | 40 | Phase 2
Reporting · Staff App | Chitrangi Mestry | 3 | 7 Jan 2027 | bar: 04 Jan
Reporting · Venue Management 1 of 2 | Pallavi Sawant | 16 | 12 Jan 2027 | bar: 16 Nov to 11 Jan
Reporting · Venue Management 2 of 2 | Deep Khanvilkar | 6 | 12 Jan 2027 | bar: 16 Nov to 11 Jan
Reporting · Analytics 1 of 4 | New full-stack developer 1 | 15 | 12 Jan 2027 | bar: 16 Nov to 11 Jan
Reporting · Analytics 2 of 4 | Surendra | 16 | 13 Jan 2027 | bar: 16 Nov to 11 Jan
Reporting · Analytics 3 of 4 | Pallavi Sawant | 17 | 13 Jan 2027 | bar: 16 Nov to 11 Jan
Reporting · Analytics 4 of 4 | New full-stack developer 1 | 4 | 13 Jan 2027 | bar: 23 Nov to 11 Jan
Reporting · Support Console | New full-stack developer 2 | 2 | 12 Jan 2027 | bar: 11 Jan
Reporting · TICVAI Console | Pradnya Yeram | 2 | 13 Jan 2027 | bar: 04 Jan to 11 Jan
Reporting · Partner Portal | Chitrangi Mestry | 2 | 12 Jan 2027 | bar: 04 Jan to 11 Jan
Reporting · platform (later blocks) | Deep Khanvilkar | 1 | 5 Oct 2026 | bar: 05 Oct
Block A
Block A2
Block B
Block C
Block D
Block test (no new feature work starts)
After 2 April

## People
Name | Role | Pace | From | Block A points | Block A work ends | S1 hours | S2 hours | S3 hours | S4 hours | S5 hours | S6 hours | S7 hours | S8 hours | S9 hours | S10 hours | S11 hours | S12 hours | S13 hours | Total hours | Of which testing | Last day at normal hours | Hours past 2 Apr | Overtime h/week to finish | Modules
Hrushikant Patkar | Back end and DevOps | 100% | 5 Oct 2026 | 511 | 25 Nov 2026 | 80 | 80 | 80 | 56 | 78 | 76 | 52 | 0 | 0 | 2 | 0 | 0 | 0 | 504 | 73 | 8 Feb 2027 | 0 | 0 | Foundation & Setup, Admission & Access Control, AI & Intelligence, White Label & CMS, Ticketing Catalogue & Products, Identity, Roles & Security
Pranay Shinde | Back end | 100% | 5 Oct 2026 | 575 | 30 Nov 2026 | 66 | 80 | 80 | 80 | 80 | 79 | 79 | 31 | 0 | 2 | 0 | 0 | 0 | 576 | 154 | 8 Feb 2027 | 0 | 0 | Foundation & Setup, Orders & Reservations, Marketing & CRM, Wallet & Cashless, AI & Intelligence, Tenancy, Venues & Devices
Tanmay Dukhande | Back end | 100% | 5 Oct 2026 | 623 | 25 Nov 2026 | 69 | 80 | 80 | 62 | 80 | 80 | 80 | 18 | 0 | 32 | 0 | 0 | 0 | 581 | 99 | 19 Feb 2027 | 0 | 0 | Foundation & Setup, AI & Intelligence, Ticketing Catalogue & Products, Food & Beverage, Admission & Access Control, Marketing & CRM
Deep Khanvilkar | Back-end helper | 100% | 5 Oct 2026 | 352 | 25 Nov 2026 | 58 | 80 | 80 | 46 | 7 | 15 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 20 | 6 Jan 2027 | 0 | 0 | Foundation & Setup, Marketing & CRM, Admission & Access Control, Food & Beverage, Orders & Reservations, AI & Intelligence
Pallavi Sawant | Full stack (Venue Management) | 100% | 5 Oct 2026 | 439 | 19 Nov 2026 | 80 | 78 | 79 | 56 | 79 | 79 | 79 | 38 | 0 | 0 | 0 | 0 | 0 | 568 | 55 | 22 Jan 2027 | 0 | 0 | Marketing & CRM, Foundation & Setup, Admission & Access Control, Subscription & Licensing, AI & Intelligence, Ticketing Catalogue & Products
Sanket Keluskar | Full stack (Venue Management) | 100% | 5 Oct 2026 | 452 | 17 Nov 2026 | 75 | 80 | 80 | 56 | 79 | 80 | 80 | 17 | 0 | 0 | 0 | 0 | 0 | 547 | 22 | 13 Jan 2027 | 0 | 0 | Foundation & Setup, Marketing & CRM, Subscription & Licensing, AI & Intelligence, Admission & Access Control, Rentals
Chinmay Patkar | Full stack (guest web, white label) | 100% | 5 Oct 2026 | 430 | 25 Nov 2026 | 75 | 79 | 79 | 62 | 79 | 78 | 78 | 9 | 0 | 0 | 0 | 0 | 0 | 539 | 152 | 13 Jan 2027 | 0 | 0 | Foundation & Setup, Marketing & CRM, Subscription & Licensing, Ticketing Catalogue & Products, Orders & Reservations, Admission & Access Control
Chitrangi Mestry | Front end (guest app, web) | 100% | 5 Oct 2026 | 345 | 30 Nov 2026 | 76 | 79 | 78 | 74 | 80 | 80 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 69 | 8 Jan 2027 | 0 | 0 | Subscription & Licensing, Ticketing Catalogue & Products, Seat Management & Venue Maps, Marketing & CRM, Admission & Access Control, Orders & Reservations
Pradnya Yeram | Front end (POS, guest app) | 100% | 5 Oct 2026 | 339 | 13 Nov 2026 | 76 | 80 | 79 | 55 | 80 | 79 | 71 | 0 | 0 | 24 | 0 | 0 | 0 | 543 | 37 | 19 Feb 2027 | 0 | 0 | Subscription & Licensing, Seat Management & Venue Maps, Admission & Access Control, Orders & Reservations, Marketing & CRM, Ticketing Catalogue & Products
Surendra | Full stack (Venue Management) | 60% | 5 Oct 2026 | 264 | 19 Nov 2026 | 47 | 47 | 48 | 34 | 48 | 48 | 48 | 2 | 0 | 0 | 0 | 0 | 0 | 322 | 6 | 11 Jan 2027 | 0 | 0 | Admission & Access Control, Marketing & CRM, Foundation & Setup, Ticketing Catalogue & Products, AI & Intelligence, Subscription & Licensing
New full-stack developer 1 | Full stack (to hire) | 100% | 23 Nov 2026 | 6 | 24 Nov 2026 | 0 | 0 | 0 | 17 | 78 | 78 | 79 | 8 | 0 | 0 | 0 | 0 | 0 | 260 | 48 | 13 Jan 2027 | 0 | 0 | Foundation & Setup, Marketing & CRM, Admission & Access Control, Wallet & Cashless, AI & Intelligence, Orders & Reservations
New full-stack developer 2 | Full stack (to hire) | 100% | 23 Nov 2026 | 8 | 23 Nov 2026 | 0 | 0 | 0 | 17 | 80 | 80 | 78 | 7 | 0 | 0 | 0 | 0 | 0 | 262 | 23 | 11 Jan 2027 | 0 | 0 | Foundation & Setup, Marketing & CRM, Admission & Access Control, Rentals, Wallet & Cashless, Accreditation
Kalpita Mejari | AI engineer | 100% | 5 Oct 2026 | 1 | 23 Nov 2026 | 77 | 80 | 80 | 77 | 78 | 73 | 80 | 80 | 80 | 80 | 80 | 24 | 0 | 888 | 92 | 10 Mar 2027 | 0 | 0 | AI & Intelligence, Foundation & Setup
Second AI engineer | AI engineer | 100% | 5 Oct 2026 | 1 | 23 Nov 2026 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 56 | 28 | 0 | 874 | 102 | 11 Mar 2027 | 0 | 0 | AI & Intelligence, Foundation & Setup

## Release checklist
When | Step | Check | Owner
Every sprint (Friday of week 2) | Before | Every ticket in the sprint is Ready for QA or moved to the next sprint with a reason in the ticket. | Scrum lead
Every sprint | Before | CI green on main: unit, contract (the OpenAPI checks) and migration tests. | Hrushikant Patkar
Every sprint | Before | Database migrations run forward on a copy of staging data; the rollback script runs back cleanly. | Back-end owner of the service
Every sprint | Before | Feature flags set per tenant for anything half-built; nothing unfinished is visible to a venue. | Lead of the package
Every sprint | Test | Each app-module whose last ticket closed has its module test passed on the integration environment (docs/active/block-test-strategy.md). | The module's tester
Every sprint | Deploy | Deploy to staging; run the smoke flows of the apps touched (buy a ticket, pay, scan, POS sale, KDS bump). | QA
Every sprint | Deploy | Demo to the client from staging; record accepted and rejected items in OpenProject. | Chinmay Parab
Every sprint | After | Measured pace per person recorded; the plan regenerated with the real pace. | Chinmay Parab
Every block (its last three working days) | Test | The block test: every flow the block claims end to end, offline runs, the load run where it adds a purchase or admission path. No new feature work starts. | The block's tester pair, led by Chinmay Parab
Every block | After | The client's acceptance session on the integration environment in the following week; signed off or open items listed. | Client
Block A go-live | Before | The client has signed off every Block A wireframe batch (3 working days each, audit R252). | Client design reviewer
Block A go-live | Before | Payment sandbox credentials in place and a full sale-refund-settlement cycle passes (the client's answer in the Decisions Register). | Client, then Tanmay Dukhande
Block A go-live | Before | Offline: the POS sells and the scanner admits with the network cut, and reconcile when it returns. | Pradnya Yeram
Block A go-live | Before | Tax invoice, credit note and VAT fields checked against the client's answers (make-or-break items). | Pranay Shinde
Block A go-live | Before | Load test at the burst mix (ticket on-sale) and the venue-day mix; replicas as sized in handoff/sizing.json. | Hrushikant Patkar
Block A go-live | Before | Backups restore into a clean environment; the restore time is written down. | Hrushikant Patkar
Block A go-live | Before | Security: role grants reviewed per module, secrets in the vault, no test credentials in production. | Hrushikant Patkar
Block A go-live | Deploy | Production deploy in a quiet window; canary tenant first, then the pilot venue. | Hrushikant Patkar
Block A go-live | Deploy | Watch error rate and latency for the first hour of trading; the rollback is rehearsed beforehand. | On-call back end
Block A go-live | Rollback if | Payment failures above 2% of attempts, POS sale p95 above 2 seconds, or any failed gate admission not explained by the ticket. | Chinmay Parab decides
Block A go-live | After | Release notes to the client; tickets closed; the hypercare rota for the first two weeks. | Chinmay Parab
End of six months (2 Apr 2027) | Before | Every module's acceptance signed; open defects triaged into the phase-2 backlog. | Chinmay Parab and the client

## Decisions
Decision | Status | What was decided | Why | What it costs
One package, services by contract | Accepted | Each business module is one OpenAPI contract owned by one service; screens bind to operations, never to tables. | Work can be split by module and checked by machine before anyone builds. | A change crosses contract, screen and ticket; the refresh keeps them in step.
Two-week sprints, four blocks of complete app-modules | Accepted 1 Oct | 13 sprints from 5 October to 2 April. A block is a set of app-modules (a module on one app, e.g. Ticketing · Guest Web, with the back end it needs), each complete and tested, ending on a sprint boundary: A (the first release), then B, C and D (the old B1-B3, with a step in between). | Each block can be tested end to end and accepted; nothing in a block waits on a later one. | Block A keeps its content, so it ends where its back end lands; B to D are sized to their sprints.
Every block tested end to end | Accepted 1 Oct | A module test per app-module (about 10% of its points, by a peer) and a block test in the last three working days of each block, when no new feature work starts (docs/active/block-test-strategy.md). | A block is accepted on its flows, not on its tickets. | About 10% more hours, and three days of each block's last sprint.
Size by formula, schedule by measured pace | Accepted | Points come from each screen's specification and each operation; the pace is replaced by the measured pace after the first sprints. | No hand estimates; a re-plan is a rerun. | The first forecast is only as good as Block A's planned pace.
Every AI function inside six months, baseline first | Accepted 30 Sep | Forecasting, fraud, recommendations, anomaly detection and both assistants ship with a working baseline on day one and learn from the tenant's own data; a trained model replaces the baseline only when it beats it and an admin approves. | Customers never hear 'later, when you have data'; accuracy grows with use. | The two AI engineers' calendar runs past 2 April (the AI review's own finding).
Two AI engineers from 5 October | Accepted 30 Sep | Kalpita and the second AI engineer carry the engine work; no third engineer. Developers build the AI endpoints and screens like any other module. | AI engineers spend their time on what only they can build. | The learned producers finish in shadow after 2 April.
CMS as a flow builder | Accepted | Operators pick their booking flows, see required and optional steps, set their own order, then finish in a configuration panel. | One engine serves every venue type the prototypes show. | The step library has to be complete before operators can compose.
Per-tenant data and models | Accepted | Models train per tenant; the LLM never reads raw data (scrubbed aggregates or code it writes); retention is tenant configuration. | Meets PDPL and client expectations on data isolation. | No pooled training; cold start relies on baselines and priors.
Load follows skill; stable owners | Accepted | Tasks are assigned by skill rating and experience, not evenly; helpers take a share proportional to their ratings. From release r2 a pushed ticket keeps its owner; a deliberate move is a --rebalance. | Hard work goes to people rated for it; boards do not reshuffle. | Back-end owners are the Block A constraint; shown as overtime, not hidden.

## Risks
Risk | Signal | What we do
Back-end owners overloaded in Block A | Their Block A work runs past Sprint 4 (People sheet). | Decided 1 October: Block A is 40 working days (it was 35) and ends Sprint 4, 27 November, with the overtime the Summary sheet gives, most of it on the three back-end owners; the two new developers take back-end tasks from their first day. Its critical path is about as long as the window, so overtime cannot be bought later in the block: it has to start early. Without it, Block A ends where the Blocks sheet says at normal hours.
Pace below plan | The plan assumes 5 tasks a developer a day through Block A, rising gradually to 2x by Sprint 11 (decided 1 October); it is re-measured after Sprint 2. | If the measured pace is lower, rerun the plan with it; blocks B to D re-cut to their sprints. At the plan of record's 9.58 points a day, Block A needed about 996 hours of overtime to end in Sprint 4 (run of 1 October).
Hiring the two developers slips | Not confirmed by 23 October. | Blocks C and D move out by the scheduler's figure; the PM decides scope or date.
Client inputs late | Wireframe sign-off over 3 working days; sandbox credentials; stations and fares; cabana numbering; real photos. | Those tickets wait in 'Waiting on client' and do not count against the team's pace.
Make-or-break answers | Tax invoice fields, e-invoicing provider, VAT 201 layout, face capture consent, ID-verification provider. | Defaults are built; a different answer is a change request.
Second AI engineer not in place on 5 October | No start date confirmed this week. | Kalpita starts the Block A AI alone; the baseline layer moves one sprint and the AI engine work needs more overtime.
AI phase 1 slips past 2 April | Phase 1 AI work ends 3 March 2027 and its module tests by mid-March; an evaluation gate or the Block A AI overrun eats the margin. | Decided 4 October (CHG-AIPH-001): a capability enters phase 1 only as a whole unit that finishes by 2 April; one that cannot moves whole to phase 2, never cut across the line. Phase 2 (the parts that learn from tenant data) starts after 2 April when the client's data exists.
Block test finds severity 1 or 2 defects | A block test cannot pass in its three days. | The defects are fixed in the next sprint's first days by the people who built the module; the block's acceptance moves, the next block does not wait.