## Hardware
S. No | Hardware Integration | Proposed Hardware | Status | Decision / standard | Source (quoted from MoM) | Client documents | Next step / task
1 | Emirates ID Reader Integration | HID | Noted | HID. Capture is configurable per ticket and per region, not fixed system behaviour. | MoM 25 Aug: "Guest/ID-proof attributes (e.g., Emirates ID, passport, handicap/PoD documentation) are configurable per ticket and per region rather than fixed system behavior."
2 | Chainway Handheld Device Integration | Chainway C66 | Noted | Chainway C66. Handheld validation runs against a secure local database on the device. | MoM 28 Jul: "The client strongly preferred a secure local database on the handheld device."
3 | RFID Reader Integration | Kaptur | OPEN | Kaptur. Bulk stock-count specifications still owed by the client. | MoM 19 Aug: "Action: Allam/Qossai to share RFID reader/device specifications and reference data." Still pending. | RFID reader specifications and reference data: asked for on 19 Aug 2026 (MoM 19 Aug), still pending.
4 | NFC readers for NFC hardware / Gaming reader | China | OPEN | Strategy settled: integrate DIRECT to reader hardware via the vendor's own SDK/API, not through an arcade-management layer. Reader displays TICVAI-pushed pricing, branding and theme; a tap fires a dry-contact signal to start/stop the game, like a turnstile. MANUFACTURER IS THE OPEN ITEM - not the approach. "China" understates this. | MoM 11 Sep: "established arcade-management vendors (e.g., Simnox, Intercard) generally refuse to integrate with TICVAI since they view it as a competing platform... TICVAI's intended approach is to integrate directly with reader hardware (via the hardware vendor's own SDK/API)." Open action: "Qossai finalizing with Chinese manufacturers; Chinmay to check for India-market alternatives."
5 | Biometric scanners for finger prints | HID/Suprema | Settled | HID / Suprema. | MoM 24 Aug: vendor selection narrowed to HID and Suprema (South Korea).
6 | Receipt Printer | Epson TM‑T88VII | Settled | Epson TM-T88VII. Assigned per workstation, with device-level status shown. | MoM 14 Aug: "Hardware & Peripheral Management: configures devices per workstation (receipt printer, cash drawer, payment terminal, barcode/ticket scanner/printer) and shows device-level status."
7 | Cash Drawer | HP | Settled | HP. Assigned per workstation. | MoM 14 Aug, as above. MoM 19 Aug confirms per-outlet assignment.
8 | Customer Display | HP, Toshiba | Settled | HP, Toshiba. | No MoM reference - hardware sheet only.
9 | Turnstile Reader Integration | HID, Axess, Suprema | Settled | HID and Suprema. Axess, Skidata, CAME, KABA and Boon Edam are STAGED as later integrations - the RFP asks for "other industry-standard systems", not those five exclusively. Integration is at two levels, turnstile and reader, over a TCP/IP event push. | MoM 24 Aug (rank 1) supersedes the RFP vendor list (rank 2): "evaluating HID and Suprema (South Korea)". MoM 2 Sep: "integration happens at two levels - the turnstile itself and the reader... Devices push events to TICVAI via a TCP/IP API." | Turnstile SDK: outstanding since 5 Aug 2026 (ADR-0015).
10 | Kitchen Display Integration | Decide later | Settled | NOT a vendor decision. Commodity touchscreen running P15 Kitchen Display, which is ours. What matters is station mapping, routing rules and offline fallback - all specified. "Decide later" implies a procurement decision that does not exist. | MoM 31 Jul: "KDS integration only." MoM 18 Aug: "each [station] mapped to specific printers or KDS devices... fallback station/device if the primary one is offline or faulty." MoM 9 Sep: KDS drives the guest-facing order-status board.
11 | Facial Readers Integration | HID, Suprema | Settled | HID, Suprema. | MoM 24 Aug: "Qossai is finalizing the access control / facial recognition vendor selection this week, evaluating HID and Suprema (South Korea)."
12 | Barcode Scanner | HP, Datalogic | Settled | HP, Datalogic. Assigned per workstation; a distinct barcode per retail variant. | MoM 7 Aug: each workstation records its connected devices. MoM 19 Aug: "a distinct barcode per variant".
13 | Kiosk Integration | BlueRhine Kiosk | Settled | BlueRhine Kiosk. | No MoM reference - hardware sheet only.
14 | Boca Printer Integration | Boca Wristband and Ticket Printer | Settled | Boca wristband and ticket printer. One unified QR code / wristband per customer across ticketing, F&B and retail - not one per product line. The client confirmed BOCA on 5 October 2026 and sent the specifications, SDK samples, operator manuals and FGL programming guide, RFID encoding for the BOCA Lemur, and the Windows driver; the unit ships to the India office when ready. We build to FGL now on an emulator (ADR-0015 Tier A), hardware validation on arrival. RFID encoding scope to confirm. | MoM 14 Aug: "Ticketing, F&B, and retail share one cart, one receipt, and one unified QR code/wristband per customer." Client email, Muhamed Allam, 5 Oct 2026 (sources/client/2026-10-05-allam-boca-printer.md): "Please note that we will be shipping the Boca printer to India once it's ready." | 5 Oct 2026, Muhamed Allam: printer specifications; SDK sample codes; operator manuals and FGL programming guide; RFID encoding on the BOCA Lemur; Windows driver (link titles only, URLs pending; sources/client/2026-10-05-allam-boca-printer.md). | DEVICE-BOCA-FGL (Block A2): the FGL driver behind the ticketPrinter port, on an emulator now; hardware test when the unit reaches India. Open client questions (Decisions Register, pending): model(s) and count, connection and host OS, ticket and wristband stock, RFID scope, arrival date and BOCA contact, mandated firmware or settings.
15 | Zebra Bluetooth Printer Integration | Zebra | Settled | Zebra. Bluetooth, for mobile/flying POS. | No MoM names Zebra directly; the RFP requires Flying POS on mobile devices.