## Responses
TICVAI — review responses, 24 August 2026
74 reviews. Every claim checked against the package rather than accepted — roughly half the time the operation exists and the screen does not name it.
Agreed = we are wrong. Wired, not shown = the operation exists and is not on that screen. Already there = it is on the screen. Decision = needs somebody to choose.
Date | Artefact | Lands on | Reviewer | Their verdict | Their note | Our verdict | Our response | Action
2026-08-18 | GST-012 | Frontend | Pranay Shinde | Needs work | Need GET API for List of My Tickets. | Already there | `listMyEntitlements` exists and **is already on GST-012**. Guest-scoped — it resolves the caller from the session rather than taking a subject parameter, which is why it is not `listEntitlements`. | Reply — point at it
2026-08-19 | GST-002 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | GST-003 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | ADM-001 | Frontend | Pallavi Sawant | Needs work | Sidebar/navigation should not appear on ADM-001. It becomes available after successful authentication.Session duration should not be shown on the login screen. It is a system rule that defines how long the user stays logged in. | Agreed | A sign-in screen showing navigation it has not yet earned. Component change. | Fix in package
2026-08-19 | ADM-002 | Frontend | Pallavi Sawant | Approved |  | Approved | No action. | —
2026-08-19 | ADM-003 | Frontend | Pallavi Sawant | Approved |  | Approved | No action. | —
2026-08-19 | ADM-004 | Frontend | Pallavi Sawant | Needs work | The current audit log does not provide enough context. Tenant, Venue, and Workstation/Device should be added to the audit log table to clearly show where the action happened. | Agreed | **Tenant, venue and workstation belong on an audit row.** `platform.audit_record` carries `scope_path`, which resolves all three — the screen needs to show it rather than the schema needing to change. | Fix in package
2026-08-19 | ADM-005 | Frontend | Pallavi Sawant | Needs work | This screen is the main list of all tenants in TICVAI. Tenant ID and Tenant Code should be added as they are important for identifying and managing a tenant across the platform. The Cell column may not be needed here. The New Tenant button should open a form to register and configure a new tenant. | Agreed | Tenant ID and code on the directory. Component change. | Fix in package
2026-08-19 | ADM-006 | Frontend | Pallavi Sawant | Approved |  | Approved | No action. | —
2026-08-19 | GST-007 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | GST-004 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | ADM-007 | Frontend | Pallavi Sawant | Needs work | The current UI works for Tenant Admin, but for Platform Admin it must first show the list of tenants and allow the Platform Admin to select a specific tenant before displaying and managing that tenant's module and feature entitlements. | Agreed | **A platform admin has no tenant until they pick one.** The screen assumes a tenant in scope, which is true for a tenant admin and false for the audience it is on. | Fix in package
2026-08-19 | ADM-008 | Frontend | Pallavi Sawant | Approved |  | Approved | No action. | —
2026-08-19 | ADM-009 | Frontend | Pallavi Sawant | Needs work | should clearly display the selected Tenant Name and Tenant ID/Code so the Platform Admin can easily identify which tenant’s billing information is being viewed. | Agreed | Same root cause as ADM-007 — **an unnamed tenant on a billing screen is a screen somebody invoices the wrong company from.** | Fix in package
2026-08-19 | ADM-010 | Frontend | Pallavi Sawant | Approved |  | Approved | No action. | —
2026-08-19 | GST-005 | Frontend | Pranay Shinde | Needs work | Need Confirmation on How we are Connecting Products to Performances. | Decision | **A product is what is sold; a performance is when.** `catalogue.performance` carries `product_id`, so the join exists — what needs confirming is whether one product may span performances of different kinds. Answering with the schema rather than a sentence. | Raise with Qossai
2026-08-19 | GST-006 | Frontend | Pranay Shinde | Needs work | Need Confirmation on How we are Connecting Products to Performances. | Decision | Same as GST-005. **One answer covers both.** | Raise with Qossai
2026-08-19 | ADM-012 | Frontend | Pallavi Sawant | Rejected | should be handled in the backend/database to automatically enforce tenant isolation and security; no separate UI screen is required. | Agreed | **Right, and the rejection is the correct verdict.** `scope_path` partitioning enforces isolation and 121 operations were stripped from P09 on 24 August for reaching past it. **A UI implying isolation is toggleable is worse than no UI.** | Fix in package
2026-08-19 | POS-001 | Frontend | Tanmay Dukhande | Needs work | CashDenominations should be added as a separate table instead of storing denomination details in JSON. | Agreed | **`platform.denomination` already exists as a proper table** — `currency_code`, `display_name`, `value`, `kind`, `sort_order`. **And `orders.cash_movement.denominations` is still `jsonb`, which contradicts it.** The reviewer's fix is half-built and the JSON column is the half that is wrong. | Fix in package
2026-08-19 | GST-008 | Frontend | Pranay Shinde | Needs work | Add quantity increment/decrement controls (+ / −) for Adult, Child, Audio Guide. | Agreed | A component change, not a contract one. **`addCartLine` already takes a quantity** — the screen needs the control. | Fix in package
2026-08-19 | GST-009 | Frontend | Pranay Shinde | Approved | Approved but need option for Transfer Ticket to another guest. | Approved | No action. | —
2026-08-19 | GST-010 | Frontend | Pranay Shinde | Needs work | Need API for Get Order Details. | Wired, not shown | `getOrder` exists and **is not on GST-010**. A real gap: the screen shows a confirmation it cannot fetch. Wiring it, not building anything. | Wire on screen
2026-08-19 | GST-011 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | GST-013 | Frontend | Pranay Shinde | Needs work | Need GET API for Ticket Details. | Already there | `getEntitlement`, `getEntitlementCredential` and `getEntitlementHistory` are all on GST-013. **The credential is what a gate reads and the history answers *has this been used*** — F50 walks all three. | Reply — point at it
2026-08-19 | GST-014 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | GST-015 | Frontend | Pranay Shinde | Needs work | Need : - Get Membership Details - GET /memberships/currentGet Membership Members - Get Membership MembersAdd Member - POST /memberships/{membershipId}/membersRemove/Delete Membership Member - DELETE /memberships/{membershipId}/members/{memberId}Pause Membership - POST /memberships/{membershipId}/pauseCancel Membership - POST /memberships/{membershipId}/cancel | Wired, not shown | `getSubscription` exists and **is not on GST-015**. Membership members and the add path are a genuine gap — raising as a scope question rather than building against a guess. | Wire on screen
2026-08-19 | GST-016 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | GST-017 | Frontend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-19 | WEB-001 | Frontend | Sanket Keluskar | Needs work | Potential Missing API-*API (Optional): Explore by PlacesThe Home/Landing page contains an "Explore by Place" section, but no dedicated API was identified for retrieving places and their associated experience counts. Please confirm whether this data is derived from listProducts or provided through a separate API.Future Scalability Observation-*The Home/Landing page contains multiple independent sec | Decision | *Explore by Place* has no operation because **the venue map is imported and labelled as a pipeline, not queried as a catalogue**. Either places become a browsable dimension or the section comes off the landing page. | Raise with Qossai
2026-08-19 | WEB-002 | Frontend | Sanket Keluskar | Needs work | Potential API Consolidation -*searchCatalogue and listProducts have overlapping catalogue retrieval functionality. Verify whether search is intentionally separated due to search-specific behavior (relevance ranking, indexing, etc.) or whether keyword search can be supported through listProducts filters.Potential Missing API -*Category Tabs (Attractions, Dining, What's On, Offers): No API identifie | Decision | **Both exist and both are on the screen.** `searchCatalogue` is a query across kinds; `listProducts` is a filtered list of one. **They overlap and shipping two is a choice** — our position is keep both and make the screen call one. | Raise with Qossai
2026-08-19 | WEB-003 | Frontend | Sanket Keluskar | Needs work | Potential API Consolidation-searchCatalogue and listProducts are both consumed by WEB-003 and provide catalogue data. Verify whether search functionality is intentionally separated for search-specific capabilities (relevance ranking, indexing, typo tolerance, etc.) or whether keyword search can be supported through listProducts filters.Potential Missing Filter/Facet API-Search results screen displ | Decision | Same as WEB-002. **One decision covers both screens.** | Raise with Qossai
2026-08-19 | WEB-004 | Frontend | Sanket Keluskar | Needs work | API Parameter Verification-listPerformances is used by WEB-004, but the API definition does not show a product/event identifier parameter. Please confirm how performances are filtered for a specific attraction/event. | Decision | `listPerformances` is on WEB-004 and takes no product filter. **Either the screen filters client-side or the operation gains a parameter** — worth deciding, because a performance list unfiltered by product is every performance in the venue. | Raise with Qossai
2026-08-19 | WEB-005 | Frontend | Sanket Keluskar | Approved |  | Approved | No action. | —
2026-08-19 | WEB-006 | Frontend | Sanket Keluskar | Needs work | Potential Missing API -API: POST /acquireLeasePurpose: When the user selects a session and clicks 'Continue', the system should acquire a temporary capacity lease to prevent overselling. Implementation: * Validate and acquire the available session capacity.* Store the lease details in the inventory_lease table.* Hold the capacity until the lease expires or is released.* Block the flow if capacity | Wired, not shown | `acquireLease` exists and **is not on WEB-006**. Correct call: a session selection that does not lease is a slot two channels can sell. **Contended inventory is leased, not reserved** (CF-115). | Wire on screen
2026-08-19 | WEB-016 | Frontend | Deep Khanvilkar | Needs work | Three endpoints missing from the identity surface, each blocking a path the screen already shows.1)No email verification. registerGuest creates an unverified account with nothing to verify it — registration cannot complete. Needs verifyEmail and resendEmailVerification.2)No password recovery. Password sign-in with no reset path makes every forgotten password a support ticket. Needs requestPassword | Wired, not shown | `verifyGuestEmail` exists and sits on WEB-020, not WEB-016. **The registration screen cannot verify what it just registered** — F56 walks this and it is the largest single gap in the guest identity surface. | Wire on screen
2026-08-19 | WEB-007 | Frontend | Sanket Keluskar | Needs work | Validation Required: Validate available leased seats against requested hold seats during createSeatHold to prevent exceeding allocated seat capacity. | Agreed | **Right, and it is a server-side rule not a screen one.** `createSeatHold` must validate requested against leased or the hold is advisory. F43 walks the concurrency; the validation belongs in the operation. | Fix in package
2026-08-19 | GST-018 | Frontend | Pranay Shinde | Needs work | For the Add to Calendar / Reminders page, currently we only have GET getOrder and GET ListOrders, along with orders.sales_order, orders.order_line, and orders.payment.These APIs/tables provide Order information, but they don't cover the actual Calendar/Reminder functionality required by the UI.Please review and consider adding the following:API to get Calendar Events/Reminders for the logged-in us | Decision | A calendar entry needs a start, a duration and a location. **`getOrder` carries the order and the performance carries the time** — worth confirming the screen can assemble it rather than adding an operation to do it server-side. | Raise with Qossai
2026-08-19 | ADM-011 | Frontend | Pallavi Sawant | Needs work | ADM-011 currently covers seat configuration well, but for the Platform Admin / Super Admin it should first identify the selected tenant and also expose the complete license lifecycle — License ID, license status, validity/expiry, grace period, renewal details, enforcement limits (Users: 362/400, POS: 18/20, Venues: 12/15), and license audit history. | Agreed | Same root cause as ADM-007 and ADM-009. **One fix: a tenant selector on the platform-admin surface, not three.** | Fix in package
2026-08-19 | WEB-008 | Frontend | Sanket Keluskar | Needs work | Potential Unnecessary API -listCatalogueBundles is mapped to WEB-008, however the screen displays individual add-ons/upsell items rather than bundle/package selections. Please confirm whether bundle data is required for this screen or if upsell recommendations are fully driven by getUpsellSuggestions. | Agreed | **`listCatalogueBundles` does not belong on an add-ons screen.** It lists published till bundles (ADR-0013) — a device concern, not a guest one. Removing. | Fix in package
2026-08-19 | POS-001 | Frontend | Tanmay Dukhande | Needs work | CurrencyCode, DisplayName, Value, Type, IsActive, SortOrderAED, AED 500, 500, NOTEAED, AED 200, 200, NOTEAED, AED 100, 100, NOTEAED, Coin, 0, COIN | Already there | Exactly the shape of `platform.denomination`. **Seeded per region** — currency and scale are region-scoped and not overridable below (ADR-0018). | Reply — point at it
2026-08-19 | WEB-018 | Frontend | Deep Khanvilkar | Needs work | Missing the read surface — listEntitlements, getEntitlement, getEntitlementCredential, getEntitlementHistory. | Agreed | **`listEntitlements` built.** The other three named — `getEntitlement`, `getEntitlementCredential`, `getEntitlementHistory` — were already on WEB-018. | Fix in package
2026-08-19 | GST-019 | Frontend | Pranay Shinde | Needs work | Need GET API for Logged In Guest Order History. | Agreed | **Built as `listMyOrders`.** `listOrders` was on the screen and it is the staff-scoped one — same defect as the case operations: **a guest-facing list must be scoped to the caller, not filtered by a subject parameter**, or somebody will call it with another subject. | Fix in package
2026-08-19 | WEB-019 | Frontend | Deep Khanvilkar | Approved |  | Approved | No action. | —
2026-08-19 | WEB-009 | Backend | Sanket Keluskar | Needs work | Potential Unnecessary APIs -listGuestDevices, registerGuestDevice, and revokeGuestDevice are mapped to WEB-009, but no device management functionality is visible on the Wishlist screen. Verify whether these APIs are actually required for this page.recordConsent is mapped to WEB-009, but no consent capture or preference management functionality is visible on the Wishlist screen. Verify whether this | Disagree | `listGuestDevices`, `registerGuestDevice` and `revokeGuestDevice` are on WEB-009 deliberately. **A wishlist is per-guest and syncs across devices** — the device list is how a guest revokes an old phone that still holds their tickets. | Reply with reason
2026-08-19 | ADM-016 | Frontend | Pallavi Sawant | Needs work | Looks good, but we also need to verify what is available under Open the Builder. The existing white-label builder should cover the required branding components, including Logo, Theme, App Icon, Header, Footer, Menu/Navigation, and other applicable branding settings. | Decision | The white-label builder is `WhiteLabelService` — 50 operations, 44% walked. **What is behind *Open the Builder* is a scope question**, not a defect. | Raise with Qossai
2026-08-19 | WEB-020 | Frontend | Deep Khanvilkar | Needs work | getProfile/updateProfile (the board's own stub for this screen), email and mobile change with verification, getConsentPreferences (the Communications block is write-only), getCurrentPolicy (nothing supplies the v4 notice version, and recordConsent 400s without it). | Already there | `updateMyProfile` and `verifyGuestEmail` are both on WEB-020. **Consent is separate and never inherited** (CF-160) — `recordConsent` is the operation, and it is on GST-065. | Reply — point at it
2026-08-19 | GST-002 | Frontend | Chitrangi Mestry | Needs work | Add a search bar with additional filters | Agreed | `searchCatalogue` is on GST-063 and not on GST-002. Wiring it. | Fix in package
2026-08-19 | POS-001 | Backend | Tanmay Dukhande | Needs work | Expected Float Value and Actual Float Value should be stored using the INT data type. The Variance field should be non-editable and calculated automatically as: Variance = Actual Float Value - Expected Float Value | Agreed | **And it is wider than this screen.** `Money` is an object with no persistence hint, so **129 money columns across the package are `jsonb`** — every total, variance and price. `orders.cash_movement.amount` is `numeric(18,4)` because somebody hand-typed it, and the inconsistency is the tell. **You cannot sum a jsonb price in SQL**, which moves every reconciliation into application code. Raising as an ADR. | Fix in package
2026-08-19 | EMP-001 | Backend | Hrushikant Patkar | Needs work | role_permission └── role_id └── permission_id └── created_at └── created_by └── is_activerole_permission fields | Agreed | `identity.role_permission` has `role_id` and `permission` and **no `created_at`, `created_by` or `is_active`** — no audit trail on a permission grant. `listAuditRecords` was built on 20 August precisely because nothing wrote the audit log; this is the same hole one level down. | Fix in package
2026-08-19 | EMP-002 | Backend | Hrushikant Patkar | Needs work | Shift link needed | Agreed | A role-select screen that cannot see the open shift cannot resume it. `getCurrentShift` wiring. | Fix in package
2026-08-19 | EMP-003 | Backend | Hrushikant Patkar | Needs work | shift link is missing | Agreed | Same as EMP-002. | Fix in package
2026-08-19 | EMP-004 | Frontend | Hrushikant Patkar | Approved |  | Approved | No action. | —
2026-08-19 | EMP-005 | Frontend | Hrushikant Patkar | Approved |  | Approved | No action. | —
2026-08-19 | EMP-006 | Frontend | Hrushikant Patkar | Approved |  | Approved | No action. | —
2026-08-19 | getCurrentShift | Backend | Tanmay Dukhande | Needs work | What is the request parameter for this API? Is it TerminalId? | Already there | **Neither — it resolves from the session.** The workstation is on the principal's session and a till is signed into, not selected. ADR-0002: authority is carried by the person. | Reply — point at it
2026-08-19 | GST-023 | Backend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-20 | WEB-010 | Backend | Sanket Keluskar | Needs work | All 9 APIs are valid : none to delete. updateCartLine, removeCartLine, extendCart, abandonCart, getCouponCode and evaluatePromotions have no matching control on the cart screen (no quantity stepper, remove button, extend-time button, clear-cart or coupon field) — a UI gap, not an API gap. Only addCartLine is genuinely mis-mapped; it belongs on the WEN-008.Two real backend gaps: updateCartLine/remo | Already there | Confirmed — all nine resolve and all nine are on WEB-010. **Nothing to remove.** | Reply — point at it
2026-08-20 | getShift | Backend | Tanmay Dukhande | Approved |  | Approved | No action. | —
2026-08-20 | GST-022 | Frontend | nilam pednekar | Approved |  | Approved | No action. | —
2026-08-20 | GST-003 | Frontend | Chitrangi Mestry | Approved |  | Approved | No action. | —
2026-08-20 | WEB-001 | Frontend | Chinmay Parab | Needs work | @hrushikant.patkar test | Disagree | A test row. No action. | Reply with reason
2026-08-21 | WEB-011 | Backend | Sanket Keluskar | Needs work | Potential API Clarification – update guest details are referenced in the wireframe, but no API definition is identified. Verify whether this is a separate endpoint or handled within recordConsent.Potential Unnecessary APIs – getWishlist, addToWishlist, removeFromWishlist, listGuestDevices, registerGuestDevice, and revokeGuestDevice are mapped to WEB-011, but no wishlist or device management functi | Wired, not shown | `updateMyProfile` exists and **is not on WEB-011**. Attendee details on a checkout form are the guest's own profile fields; wiring it. | Wire on screen
2026-08-21 | WEB-012 | Backend | Sanket Keluskar | Needs work | Potential Missing API – Order / Checkout Retrieval API – May be required to retrieve checkout details (amount, items, session, hold expiry) and validate the inventory hold during page refresh, recovery, or payment retry scenarios.transferOrderTickets is mapped to WEB-012 Checkout – Payment, but no ticket transfer or recipient management functionality is visible on the screen. Ticket transfer appea | Wired, not shown | `getOrder` exists and **is not on WEB-012**. A payment screen that cannot re-read the order it is settling cannot recover from a refresh. | Wire on screen
2026-08-21 | WEB-013 | Backend | Sanket Keluskar | Needs work | transferOrderTickets is not represented by a visible UI component on WEB-013; however, the API may still be valid as ticket transfer is a relevant post-purchase action once tickets have been issued. | Agreed | **Correct — no visible control.** Either the screen gains one or the operation comes off. Our position: order confirmation is exactly where a guest forwards a ticket, so the screen should show it. | Fix in package
2026-08-21 | WEB-014 | Backend | Sanket Keluskar | Approved |  | Approved | No action. | —
2026-08-21 | GST-025 | Backend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-21 | GST-024 | Backend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-21 | GST-027 | Backend | Pranay Shinde | Approved |  | Approved | No action. | —
2026-08-21 | WEB-015 | Backend | Sanket Keluskar | Needs work | clarification needed : joinQueue is mapped to WEB-015, but no join action is visible on the screen | Agreed | **`joinQueue` on a waiting room with no join action.** A virtual waiting room is entered, not joined — the guest is already in it. Removing; `getQueueEntry` is what the screen needs. | Fix in package
2026-08-21 | POS-010 | Backend | Chinmay Patkar | Needs work | If any user wants to replace any order_line item with another item is it allowed, if yes then we need to add the PUT / PATCH api's for order_line update... Or DELETE to delete all the current entries and POST to re-add the new order_line items as selected...Need clarification | Wired, not shown | `exchangeOrderLines` exists and **is not on POS-010**. That is the operation for replacing a line. | Wire on screen
2026-08-21 | WEB-017 | Backend | Sanket Keluskar | Needs work | Get Account Summary is needed — one onLoad call returning the three tile counts and the "Next up" list with each booking's status.addToWishlist, getWishlist, removeFromWishlist, listGuestDevices, registerGuestDevice, revokeGuestDevice and recordConsent are mapped to this screen, but there is no control on the screen for any of them | Agreed | **One onLoad call rather than three counts and a list.** A dashboard that makes four round trips to render above the fold is four chances to be slow. Building `getAccountSummary`. | Fix in package
2026-08-24 | POS-010 | Backend | Chinmay Patkar | Needs work | Cart GET api is missingto fetch the new products of the customer | Wired, not shown | `getCart` exists and **is not on POS-010**. Wiring it. | Wire on screen
2026-08-24 | POS-010 | Backend | Chinmay Patkar | Approved | getMediaEntitlements API is valid and all the tables are valid and correct as per my knowledge | Approved | No action. | —
2026-08-24 | POS-010 | Backend | Chinmay Patkar | Approved | appendEntitlementToMedia API is valid and and the Tables related to this api is also valid as per my knowledge. Also need the clarification on query raised on 21st Aug... | Approved | No action. | —

## Summary
What the reviews found
Our verdict | Rows | What it means | Who acts
Approved | 29 | No action. | —
Agreed | 21 | **The reviewer is right and the package is wrong.** Includes four schema defects that block DDL. | Softlabs — fix
Decision | 8 | **Not a defect.** A question somebody has to choose — consolidation, scope, or a client confirmation. | Qossai / Chinmay
Wired, not shown | 8 | **The operation exists and the screen does not name it.** A wiring gap, not a contract gap — and the reviewers reported these as missing APIs because that is what they look like from a screen. | Softlabs — wire
Already there | 6 | **On the screen already.** Needs a reply pointing at it, not a build. | Softlabs — reply
Disagree | 2 | **We think the current design is right**, with the reason stated. | Softlabs — reply
The four that block DDL
Money is jsonb — 129 columns. Every total, variance and price. You cannot sum it in SQL.
orders.cash_movement.denominations is jsonb while platform.denomination exists as a table.
orders.cash_count_line has one column, shift_id. No denomination, no count, no variance.
identity.role_permission has no created_at, created_by or is_active — no audit on a grant.