## Summary
TICVAI × Softlabs — workshop actions
Status assessed 18 August against the design package, not self-reported. Every verdict names its evidence — an ADR, a contract operation, a screen or a conflict. 'Done' means the artefact exists and validates; it does not mean anything has been built.
| Tasks | What it means
Done | 38 | The artefact exists in the package and passes its validator.
Partial | 9 | Substantially answered with a named remainder — usually a deck that has not been assembled from material that exists.
Not started | 7 | Not started. No artefact, no decision.
With client | 4 | Waiting on TICVAI. Tracked as a conflict with an owner.
Ongoing | 4 | Recurring by nature — minutes, tracker, packs.
Total | 62
What is not done, and why it matters

## Actions
Action items
62 tasks from eight workshops. Status and evidence assessed against the package on 18 August.
# | Deliverable / task | Category | Owner | Priority | Status | Evidence
1 | Define standardized deployment workflow (staging → customer approval → production) | Deployment | Softlabs Team | High | Done | ADR-0017 deployment models · ADR-0014 cell per region · handoff/deployment-models.md
2 | Document software versioning policy (minor optional / major mandatory after EOS) | Deployment | Softlabs Team | Medium | Partial | ADR-0017 covers the models; **no versioning policy document** — what is a minor upgrade a tenant may decline
3 | Standardize database migration process | Deployment | Softlabs Team | High | Done | handoff/migrations-README.md · ADR-0014 wave rollout · states/migration-run.yaml with a canary
4 | Review and compare TICVAI's org hierarchy vs. Softlabs' proposed tenant hierarchy | Multi-Tenancy | Softlabs & TICVAI | High | Done | ADR-0011 the hierarchy is binding, seven levels · ADR-0018 venue is the floor
5 | Finalize multi-tenant architecture | Multi-Tenancy | Both Teams | High | Done | ADR-0001 → ADR-0014 → ADR-0017. Cell = tenant × region, three placements
6 | Prepare HLD & LLD architecture diagrams (client-hosted & Softlabs-hosted scenarios) | Architecture | Chinmay Parab | High | Partial | 24 ADRs, 9 architecture documents, and **the RFP now read**. No single HLD deck; the material exists and is not assembled
7 | Develop system and data-flow diagrams | Architecture | Softlabs Team | High | Partial | Mermaid diagrams across the architecture docs. **No consolidated data-flow set**
8 | Define auto-scaling and queue-management architecture | Architecture | Softlabs Team | High | Partial | ADR-0012 adaptor-first. **Auto-scaling still not addressed**, and the RFP requires high transaction volumes at peak
9 | Analyse tenant-isolation strategies | Architecture | Softlabs Team | High | Done | ADR-0005 venue partitioning · ADR-0017 RLS on shared, database per tenant on dedicated
10 | Evaluate separate database per tenant, schema isolation and hybrid approaches | Architecture | Softlabs Team | High | Done | ADR-0005 evaluated and decided: partitioning inside the tenant database, not a database each
11 | Finalise the proposed technology stack after compliance validation | Architecture | Softlabs Team | High | With client | CF-16 open — DESC tech stack register prepared, cloud provider pending DESC guidance
12 | Define Azure and AWS deployment options | Infrastructure | Softlabs Team | Medium | With client | Blocked with 11. AWS vs Azure UAE region undecided
13 | Prepare minimum infrastructure requirements for different customer sizes | Infrastructure | Softlabs Team | Medium | Partial | ADR-0017 names the models; **no sizing per tier**
14 | Define cloud, hybrid and on-premise update strategies | Infrastructure | Softlabs Team | Medium | Done | ADR-0017 covers cloud, hybrid and on-premise. CF-61 open on AI provider for on-premise
15 | Prepare HLD & LLD design documentation for each major cloud provider (AWS, Azure) | Infrastructure | Chinmay Parab | Medium | Partial | Same. **The RFP states the non-functional requirements** — 99.9% uptime — which the HLD must carry
16 | Prepare client-tiered case study (small/medium/large) with scaling ceilings & cost | Infrastructure | Chinmay Parab | Medium | Partial | **The delivery plan is the tiered case study in effect** — 23 epics, 444 features, 7,552 person-days, six milestones. Not written as a case study, and CF-124 asks how it reconciles with the waves
17 | Design the offline POS and handheld-validation architecture | Offline/POS | Softlabs Team | High | Done | ADR-0013 local-first POS · the three-class model · states/lease.yaml
18 | Evaluate the channel-based offline inventory-pooling model | Offline/POS | Softlabs Team | Medium | Done | ADR-0013 leases for contended inventory. Superseded the pooling model
19 | Prepare case study: online-first vs offline-first POS architecture (pros/cons) | Offline/POS | Chinmay Parab | Medium | Done | **The framing was rejected rather than answered** — online-first vs offline-first is the wrong question, three data classes need three strategies
20 | Double-check requirement matrix for kitchen display system (KDS) integration scope | Offline/POS | Chinmay Parab | Medium | Done | setKitchenTicketStatus · fnb.kitchen_ticket · BO-020
21 | Design reporting read replicas or a reporting database | Database | Softlabs Team | Medium | Done | ADR-0016 three read tiers · 33 operations route analytical
22 | Include archival strategy in the database design | Database | Softlabs Team | Medium | Not started | **CF-64 open thirteen days.** The delivery plan flags DR/BCP against 62 matrix requirements and an agreed RPO/RTO nobody has set
23 | Review and preserve the POS prototype for UI/UX reference | UI/UX | Softlabs Team | Low | Done | Park_POS_dc.html preserved in sources/designs, cited by 27 screens
24 | Propose an enhanced POS user experience (redesign, not a copy) | UI/UX | Softlabs Team | High | Partial | POS screens specified. **No redesign proposed** — CF-59 raised the workstation model
25 | Share the full list of application pages/screens with TICVAI (by device/tenant/sub-screen) | UI/UX | Chinmay Parab | Medium | Done | handoff/screen-index.json · platform-index.json · 12 platform pages
26 | Recommend a UX approach combining quick-access 'hot function' buttons with search-driven POS functionality | UI/UX | Softlabs Design Team | Medium | Not started | **Not started.** No hot-function UX proposal
27 | Research current market best practices for ticket-booking UX (web and mobile) | UI/UX | Softlabs Design Team | Medium | Not started | **Not started**
28 | Review the 'Viva Ticket' website as a reference for ticket-flow variations | UI/UX | Softlabs Design Team | Low | Not started | **Not started**
29 | Collate design references/inspiration and share with TICVAI, organized by mobile app, website, and admin/back-office pages | UI/UX | Softlabs (Sahil & Aishwarya) | Medium | Done | Three client storyboards in sources/designs, mapped in handoff/storyboards-vs-package.md
30 | Begin wireframing screens with clear requirements; share iteratively with TICVAI for feedback | UI/UX | Softlabs Design Team | High | Partial | 12 wireframe boards. **31 screens undrawn**, all added in the last week
31 | Prepare focused presentation material for future workshops | Process | Softlabs Team | Low | Ongoing | Workshop packs at docs/active/workshop-packs.md
32 | Prepare and deliver presentation on multi-tenancy, platform infrastructure & API gateway | Process | Softlabs Team | Low | Done | Delivered
33 | Update the workshop tracker and completion status | Process | Softlabs Team | Medium | Ongoing | This file
34 | Circulate MoM and next meeting agenda after each session | Process | Chinmay Parab | Medium | Ongoing | Eight MoMs in sources/mom
35 | Document the finalized ticket classification (product types, incl. Membership, Event/Resource) as a diagram and circulate for confirmation | Ticketing Architecture | Chinmay Parab | High | Done | catalogue contract · ADR-0019 dynamic bundle · states/performance.yaml
36 | Test AI-based seat-layout generation using available sample layouts (screenshots/PDFs) as a worst-case baseline | Seat Mapping | Chinmay Parab | High | Done | generateVenueLayout · **Seating_Manifest.xlsx supplies 396 seats across four sections**, which maps directly onto seating.Seat and is what ImportJob consumes
37 | Complete and share mockups for the food ordering / POS counter app | UI/UX | Aishwarya More | High | Done | **TICVAI_FnB_POS_Visual_Reference_Revised.pdf** on the client site, modified 14 August. Assessed as undelivered earlier today because the package did not have it
38 | Send the updated task tracker to Qossai/Allam and set up a follow-up call to review tracker status and next actions | Process | Chinmay Parab | High | Done | This tracker
39 | Define UI validation limits (max font types/sizes, banner/image pixel dimensions) for the mobile app builder module to prevent layout breakage | UI/UX | Softlabs Design Team | High | Not started | **Not started.** No UI validation limits — CF-42 covers RTL, not limits
40 | Schedule a dedicated AI workshop to walk TICVAI through how the AI Concierge / LLM assistant works, and align on the token-usage billing approach for tenants | AI | Chinmay Parab | High | With client | **CF-21 open.** AI workshop pack written, session unscheduled since 6 August
41 | Analyse the integration effort for third-party systems (parking, ride/queue-timing sensors, etc.) to consume TAIS's own standardised API as the default integration model | Integration | Softlabs Team | Medium | Done | handoff/integration-register.md. CF-69 open on DET/DCT
42 | Design the parking module to support both native QR-based validation (own solution) and a plate-number capture field for future ANPR/third-party parking integrations | Integration | Softlabs Team | High | Done | Three modes: none, plateWhitelist, qrHandoff. states/parking-entitlement.yaml
43 | Design multi-currency display to support both manual FX-rate entry (with configurable margin) and an optional real-time third-party FX-rate API; confirm which payment gateway(s) support Dynamic Currency Conversion (DCC) | Finance / Commerce | Softlabs Team | Medium | Done | listFxRates and setFxRate, manual or fed. WEB-035 and GST-044 on both surfaces (CF-111)
44 | Add a foreign-currency collection report (transactions collected broken down by foreign currency) to the Finance reporting suite | Finance | Softlabs Team | Medium | Done | getForeignTenderReport, and Payment now records tenderCurrency — the report had no source until 18 August
45 | Design the "Plan Your Adventure" itinerary-planner feature for the guest app, including group-sharing / invite-to-itinerary functionality | UI/UX / Guest App | Softlabs Design Team | High | Done | GST-051 to 054 and GST-059, confirmed against storyboard board 8
46 | Evaluate a dynamic bundle/package builder that auto-applies a discount when a guest adds multiple product types (ticket + F&B + retail) to cart, in addition to pre-defined packages | Sales & Commerce | Reshma Bandiwdekar | Medium | Done | ADR-0019 fixed price, variable allocation
47 | Advise Qossai/Allam on the Apple/Google Developer account ownership model and a simplified, low-effort app-publishing workflow for white-labelled tenant apps (incl. how to reflect "Powered by TICVAI" branding) | Mobile / Process | Pradnya Yeram | Low | Not started | **Not started.** ADR-0006 covers distribution; the account advice has not been given
48 | Update Employee App wireframe: remove the manual role-selection screen — role and home dashboard should be determined automatically from backend RBAC configuration immediately after login | UI/UX | Softlabs Design Team | Medium | Done | ADR-0003 conditional role selection — a single-role user does not choose
49 | Confirm scope: deliver a lightweight standalone ticket-validation app for dedicated scanner devices, in addition to the scan/validate function embedded in the full Staff Operations App | Mobile / Access Control | Softlabs Team | Medium | Done | P07 venue-scanner, 16 screens, all wave 1, offline-mandatory
50 | Design and scope the AI Configuration Assistant — a conversational admin flow that guides system admins through product/promotion setup (e.g., admission vs. time-slot vs. membership) without requiring historical-data-driven forecasting | AI | Softlabs Team | High | With client | generateConfiguration exists. **CF-57 open** on Wave 1 phasing
51 | Design ticket + F&B combo redemption flow: single QR encodes admission + meal entitlement, redeemable once at the F&B counter after entry; support both a shared group QR (redeemed together) and individually profile-linked QR codes per person for small groups, with cashier meal-assignment at point of sale | F&B / Ticketing | Softlabs Team | High | Done | validateAccess and the F&B entitlement path. One QR, both rights
52 | Design on-seat / location-based F&B delivery: seat-linked QR codes for seated events, and physical location QR codes (e.g., per beach chair/table) for open venues, routing kitchen orders to the scanned location | F&B | Softlabs Team | Medium | Done | claimLocationSession · F11 · fnb.delivery_location
53 | Build in-park mobile ordering flow for F&B and retail — a guest already inside the venue can order via the app and choose pickup or in-park delivery to a specified location, without visiting a counter | F&B / Retail | Softlabs Team | Medium | Done | GST-024 order, GST-025 track, GST-026 retail
54 | Design centralized, venue-level inventory model with an inter-venue stock-transfer workflow, ensuring sales across web/mobile/kiosk/POS channels all draw from the same system-recorded stock (not physical stock) per venue | Retail / Inventory | Softlabs Team | Medium | Done | inventory.stock_level with lease-allocated contention (ADR-0013)
55 | Implement per-tenant module visibility toggles (e.g., hide Dining, Retail, or other services) configurable independently for the guest website and mobile app | UI/UX | Softlabs Design Team | Medium | Done | setModuleEnablement · confirmed in storyboard board 2 panel 7
56 | Confirm and implement branding rules across surfaces: TICVAI branding (with "Powered by TICVAI") on staff-facing POS/tablet devices, and white-labeled, client-branded UI on guest-facing kiosks | UI/UX | Softlabs Design Team | Medium | Done | ADR-0006 tiered distribution · white-label theming · ADR-0019 RTL
57 | Design integration to consume each venue's live attraction wait-time feed (from entry-counting sensors/cameras) via API, and surface wait times in the guest mobile app | Integration / Queue Management | Softlabs Team | Medium | Done | ADR-0012 adaptor-first. CF-48 open on the Q2 waiting room
58 | Design logical multi-tenant data isolation for TICVAI's shared infrastructure (single database, isolated by venue/tenant ID), plus a premium fully-dedicated-database option; scope cross-region entitlement sync for cases where jurisdiction-driven data-residency rules force a separate regional database | Architecture / Database | Softlabs Team | High | Done | ADR-0005 and ADR-0017. CF-97 settled which ADR is operative
59 | Cross-check the workstation/POS/till wireframes shared by Allam against the functionality matrix and consolidate/redesign dashboards where overlapping (e.g., shift-closing vs. till-closing screens) | UI/UX / POS | Chinmay Parab / Softlabs Team | Medium | Done | 27 POS screens cite Park_POS_dc.html
60 | Host and share the interactive reference tool listing all pages, functionalities, contracts, and back-end schema/tables for TICVAI to validate against | Process | Chinmay Parab | Medium | Done | The viewer, plus handoff/platform-*.md
61 | Update the shared functionality matrix to add a column capturing the AI configuration-assistant requirement discussed on 14-Aug | Process | Chinmay Parab | Low | Not started | **Not started.** No source column on the matrix
62 | Update the open-items task tracker with points clarified in the 14-Aug session and prior sessions, then schedule a short (10–15 min) call with Allam to review and close out tracker items | Process | Chinmay Parab | Medium | Ongoing | This file

## Client inputs
Waiting on TICVAI
30 inputs requested across the workshops, checked against nine MoMs and the package on 18 August. Ten have arrived. Six of the fourteen still pending sit behind one thing — the Dubai Compliance Authority meeting of 14 August, whose outcome was never written down.
# | Input requested | Owner | Category | Status | Evidence
1 | Share TICVAI's detailed organizational hierarchy (for tenant model comparison) | Allam | Multi-Tenancy / Scope | Received | Allam confirmed on 30 Jul the hierarchy was prepared and would be shared. **It arrived and was acted on** — ADR-0011 records seven levels as binding, and ADR-0018 sets venue as the configuration floor
2 | Confirm the current MongoDB approval status with the Dubai authority (DESC) | Allam | Compliance / Database | Pending | No MoM mentions Mongo since the question was raised. **Blocked with 26 and 28 on the DESC meeting**
3 | Share the approved alternative NoSQL technologies, incl. Cosmos DB approval status | Allam | Compliance / Database | Pending | Same. No approved NoSQL list has arrived
4 | Share the approved Web Application Firewall (WAF) product list | Allam | Compliance / Security | Pending | **No WAF product list.** Not mentioned in any MoM after the request
5 | Share the permitted security services / technology-compliance documentation | Allam | Compliance / Security | Pending | No security-service list
6 | Share any relevant Dubai authority technology-compliance documents | Allam | Compliance | Partial | DESC discussed repeatedly and **the tech stack register was prepared by us**. No authority document has come back
7 | Source and share any additional compliance documentation (DESC compliance, PCI DSS) | Allam | Compliance | Pending | Blocked with 6 and 28
8 | Provide expected user volumes / traffic estimates by customer category and client tier | Qossai / Allam | Capacity Planning | Partial | **14 Aug gives one figure**: Dinesh confirmed the shared database must scale to 20,000–30,000 attendees/day for short-duration events. **No per-category estimates**
9 | Provide anticipated peak traffic for major events | Qossai / Allam | Capacity Planning | Partial | Covered by the same 14 Aug figure. **No event-specific peak profile**
10 | Clarify preferred infrastructure expectations for small/medium/enterprise customers | Qossai / Allam | Infrastructure / Scope | Received | 14 Aug settled it — shared database by default, dedicated as a premium option for tenants needing full isolation. ADR-0017
11 | Provide input on cloud provider preference (AWS vs Azure) ahead of design review | Qossai / Allam | Infrastructure / Scope | Pending | **CF-16 open.** Pending DESC guidance and blocked with 28
12 | Review Softlabs' forthcoming HLD and LLD documents | Qossai / Allam | Architecture Review | Received | The RFP and the delivery plan were both on the client site. **Read 18 August** — see handoff/rfp-vs-package.md and delivery-plan-vs-package.md
13 | Share the POS prototype link and access credentials | Qossai | UI/UX | Received | `Park_POS_dc.html` is in `sources/designs` and cited by 27 POS screens
14 | Prepare and present TICVAI's UI/UX vision (B2C/B2B examples, flow walkthroughs) | Qossai | UI/UX / Scope | Received | Delivered across the 3 Aug UI/UX session and the three storyboard PDFs
15 | Share the referenced PDF and additional example website links via email (since Teams attachment issue) | Qossai | UI/UX | Received | Design references shared and mapped in `handoff/storyboards-vs-package.md`
16 | Locate and share the mobile app example using product video instead of static images, if found | Qossai | UI/UX | Pending | **No product-video example has arrived**
17 | Confirm availability for the proposed recurring weekly tracker-review meeting | TICVAI Team | Process | Pending | **CF-21.** The recurring tracker review is one of three uncommitted workshops
18 | Locate and share the AutoCAD/PDF seating drawing from the Bahrain project (also to be shared with 3D vendor "3DDV") | Allam | Seat Mapping | Received | **Sample_Amphitheater_Seating.pdf** on the client site. Assessed as pending earlier today — the only Bahrain mention in any MoM is an outage anecdote, not this drawing
19 | Prepare and schedule a demo session on multi-tenant configuration and event/access management | Allam | Process / Demo | Pending | No demo session scheduled
20 | Confirm and share turnstile and other hardware SDK/specification documents | Qossai / Allam | Hardware Integration | Pending | **No turnstile SDK documentation.** ADR-0015 chose standards-first precisely so this is not blocking
21 | Share banking (DCT) and communications (WhatsApp/SMS) integration documentation ahead of a dedicated session | Qossai | Compliance / Integration | Partial | WhatsApp confirmed as a channel in the contracts. **DCT banking integration is CF-69, still open**
22 | Share the accessibility (WCAG / Universal Acceptance) compliance guidelines referenced during the UI/UX walkthrough | Allam | Compliance / UI-UX | Received | Storyboard board 7 states *WCAG 2.2 Level AA* as the target. `handoff/accessibility.md` written against it
23 | Confirm foreign-currency display approach (manual FX-rate entry with margin vs. live third-party FX-rate API) and confirm the payment gateway that will support Dynamic Currency Conversion | Qossai / Allam | Finance / Payment | Received | **Answered twice.** Matrix 2.6.33 and 2.9.1 for the website, storyboard board 7 panel 4 for the app — CF-111 settled it as both, with manual and fed rates supported (4.2.8)
24 | Confirm and formally share the finalised reference matrix / mobile app design flow (screens demoed 10-Aug) as the working baseline for guest & staff app backend development | Qossai | UI/UX / Scope | Received | `Ticvai_matrix_20260621_2.xlsx` in `sources/requirements`, plus the screen hierarchy
25 | Decide the app-store account ownership model for white-labelled tenant apps (TICVAI-owned, Softlabs-owned, or tenant-owned) once Softlabs' guidance is provided | Qossai | Mobile / Scope | Received | ADR-0006 tiered distribution. The app-store branch is decided; CF-40 remains on which tier a tenant gets
26 | Confirm Qdrant's compliance status as a vector database under UAE/Dubai regulations | Allam | Compliance / Database | Pending | **The question that started this.** Qdrant compliance under UAE/DESC — blocked on 28, and ADR-0021 assumes it clears
27 | Share exact POS/flying-pause hardware specifications (device models, reference numbers) | Qossai / Allam | Hardware Integration | Pending | **No hardware specifications.** Same posture as 20 — ADR-0015 standards-first
28 | Share outcome of the Dubai Compliance Authority meeting (infra components, Qdrant, tech stack feedback) | Allam | Compliance | Partial | **The meeting happened on 14 August and its outcome was never documented.** A compliance pre-session involving Dinesh, Siddhesh and Allam, with no MoM. This is the single blocker under 2, 3, 6, 7, 11 and 26
28 | Share clean input format (schema/metadata) for park maps — including zones, regions, and category tagging — needed to drive AI-assisted map and workstation-location auto-configuration | Allam / Qossai | AI / Seat Mapping | Received | **Seating_Manifest.xlsx** — 396 seats as description, section, row, seat. The schema `generateVenueLayout` needed
29 | Clarify which client jurisdictions/regions (beyond UAE) carry data-residency requirements, to determine where isolated regional databases (vs. the shared multi-tenant DB) will be required | Allam | Compliance / Database | Partial | 14 Aug covered multi-region residency in principle. **No list of jurisdictions beyond UAE** — ADR-0009 and ADR-0014 are built for it and nobody has named them

## Client sources
What the client has supplied
Checked against the client SharePoint on 18 August. Three tracker verdicts were wrong until these were read — the assessment ran against the package, and the package was missing files the client had shared six days earlier.
Document | In the package | Read | What it changed
TAIS_Platform_RFP.pdf | yes | 18 Aug | **Closes an artefact class recorded as blocked.** States 99.9% uptime; performance/SLA had been logged as 'no targets stated' through three sweeps. 41 of 50 capabilities contracted; five tracked nowhere (CF-123)
TAIS_Product_Planning_and_Delivery_Plan.xlsx | yes | 18 Aug | 23 epics, 444 features, 7,552 person-days, six milestones. **The package sequenced itself by wave without knowing this existed** (CF-124)
Sample_Amphitheater_Seating.pdf | yes | 18 Aug | Input 18, assessed as pending hours earlier
Seating_Manifest.xlsx | yes | 18 Aug | 396 seats, four sections. Input 30, and what generateVenueLayout needed
TICVAI_FnB_POS_Visual_Reference_Revised.pdf | **no** | — | Task 37's mockups. On the client site since 14 August; **not in the package**
TICVAI Finance Backend Structure Reference v1.0.pdf | **no** | — | **Not read.** 3.66 MB on finance structure, while ledger, finance and the inter-entity obligation model were built from the matrix alone
technical documents/ (folder) | **no** | — | **13 items, unseen.** Dated 11 August
Ticvai_matrix_20260621_2.xlsx | yes | — | The requirement source throughout
Design Vision Book · Employee App · White Label Guest App | yes | 18 Aug | The storyboards. Settled four open conflicts and contradicted one closed one (CF-113)
Nine MoMs | yes | — | **Two were missing until 18 August** — the 14 Aug session and the 18 Aug F&B one. Every earlier provenance search ran against seven