## Action Items to be done (hidden)
TICVAI x Softlabs — What We Have to Create (Consolidated Open Items)
Consolidated task list
# | Deliverable / Task | Category | Owner | First Raised | Latest Update | Status | Notes | Priority
1 | Define standardized deployment workflow (staging → customer approval → production) | Deployment | Softlabs Team | Kickoff (30-Jul) | Kickoff (30-Jul) | In Progress |  | High
2 | Document software versioning policy (minor optional / major mandatory after EOS) | Deployment | Softlabs Team | Kickoff (30-Jul) | Kickoff (30-Jul) | Pending |  | Medium
3 | Standardize database migration process | Deployment | Softlabs Team | Kickoff (30-Jul) | Kickoff (30-Jul) | In Progress |  | High
4 | Review and compare TICVAI's org hierarchy vs. Softlabs' proposed tenant hierarchy | Multi-Tenancy | Softlabs & TICVAI | Kickoff (30-Jul) | Kickoff (30-Jul) | Pending |  | High
5 | Finalize multi-tenant architecture | Multi-Tenancy | Both Teams | Platform Architecture MoM (prior) | Kickoff (30-Jul) | Pending |  | High
6 | Prepare HLD & LLD architecture diagrams (client-hosted & Softlabs-hosted scenarios) | Architecture | Chinmay Parab | Discovery Day 1 (28-Jul) | MoM (31-Jul) | In Progress |  | High
7 | Develop system and data-flow diagrams | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
8 | Define auto-scaling and queue-management architecture | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
9 | Analyse tenant-isolation strategies | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
10 | Evaluate separate database per tenant, schema isolation and hybrid approaches | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
11 | Finalise the proposed technology stack after compliance validation | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending | Depends on Allam's compliance findings | High
12 | Define Azure and AWS deployment options | Infrastructure | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
13 | Prepare minimum infrastructure requirements for different customer sizes | Infrastructure | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
14 | Define cloud, hybrid and on-premise update strategies | Infrastructure | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
15 | Prepare HLD & LLD design documentation for each major cloud provider (AWS, Azure) | Infrastructure | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
16 | Prepare client-tiered case study (small/medium/large) with scaling ceilings & cost | Infrastructure | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
17 | Design the offline POS and handheld-validation architecture | Offline/POS | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
18 | Evaluate the channel-based offline inventory-pooling model | Offline/POS | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
19 | Prepare case study: online-first vs offline-first POS architecture (pros/cons) | Offline/POS | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
20 | Double-check requirement matrix for kitchen display system (KDS) integration scope | Offline/POS | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
21 | Design reporting read replicas or a reporting database | Database | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
22 | Include archival strategy in the database design | Database | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
23 | Review and preserve the POS prototype for UI/UX reference | UI/UX | Softlabs Team | Discovery Day 1 (28-Jul) | UI/UX MoM (3-Aug) | Completed | Confirmed as primary design reference during 3-Aug walkthrough | Low
24 | Propose an enhanced POS user experience (redesign, not a copy) | UI/UX | Softlabs Team | Discovery Day 1 (28-Jul) | UI/UX MoM (3-Aug) | In Progress | Direction confirmed 3-Aug; actual enhanced design still to be produced | High
25 | Share the full list of application pages/screens with TICVAI (by device/tenant/sub-screen) | UI/UX | Chinmay Parab | MoM (31-Jul) | UI/UX MoM (3-Aug) | In Progress | List exists internally in tracking spreadsheet; not yet confirmed as shared with TICVAI | Medium
26 | Recommend a UX approach combining quick-access 'hot function' buttons with search-driven POS functionality | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
27 | Research current market best practices for ticket-booking UX (web and mobile) | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
28 | Review the 'Viva Ticket' website as a reference for ticket-flow variations | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Low
29 | Collate design references/inspiration and share with TICVAI, organized by mobile app, website, and admin/back-office pages | UI/UX | Softlabs (Sahil & Aishwarya) | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
30 | Begin wireframing screens with clear requirements; share iteratively with TICVAI for feedback | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | In Progress |  | High
31 | Prepare focused presentation material for future workshops | Process | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Low
32 | Prepare and deliver presentation on multi-tenancy, platform infrastructure & API gateway | Process | Softlabs Team | Discovery Day 1 (28-Jul) | Kickoff (30-Jul) | Completed | Delivered at Kickoff session 30-Jul | Low
33 | Update the workshop tracker and completion status | Process | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Ongoing |  | Medium
34 | Circulate MoM and next meeting agenda after each session | Process | Chinmay Parab | Platform Architecture MoM (prior) | UI/UX MoM (3-Aug) | Ongoing | Recurring after every session | Medium
35 | Document the finalized ticket classification (product types, incl. Membership, Event/Resource) as a diagram and circulate for confirmation | Ticketing Architecture | Chinmay Parab | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | In Progress |  | High
36 | Test AI-based seat-layout generation using available sample layouts (screenshots/PDFs) as a worst-case baseline | Seat Mapping | Chinmay Parab | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | In Progress |  | High
37 | Complete and share mockups for the food ordering / POS counter app | UI/UX | Aishwarya More | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | In Progress |  | High
38 | Send the updated task tracker to Qossai/Allam and set up a follow-up call to review tracker status and next actions | Process | Chinmay Parab | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Muhamed Allam requested the tracker be sent today so a review call can be scheduled for tomorrow | High
39 | Define UI validation limits (max font types/sizes, banner/image pixel dimensions) for the mobile app builder module to prevent layout breakage | UI/UX | Softlabs Design Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Raised by Chinmay Parab (custom fonts/oversized banners could break the layout); Qossai & Allam agreed restrictions and upload validation are needed | High
40 | Schedule a dedicated AI workshop to walk TICVAI through how the AI Concierge / LLM assistant works, and align on the token-usage billing approach for tenants | AI | Chinmay Parab | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Explicitly requested by Qossai — AI functionality and cost model "still not clear" to him; to be discussed before finalising approach | High
41 | Analyse the integration effort for third-party systems (parking, ride/queue-timing sensors, etc.) to consume TAIS's own standardised API as the default integration model | Integration | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Agreed as the preferred standard during the 11-Aug walkthrough (vs. TAIS pushing data to each third-party's own API); Allam flagged effort still needs sizing | Medium
42 | Design the parking module to support both native QR-based validation (own solution) and a plate-number capture field for future ANPR/third-party parking integrations | Integration | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | High
43 | Design multi-currency display to support both manual FX-rate entry (with configurable margin) and an optional real-time third-party FX-rate API; confirm which payment gateway(s) support Dynamic Currency Conversion (DCC) | Finance / Commerce | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Reshma flagged FX rates fluctuate and can't be stored as static master data; Qossai noted ~90% of regional clients prefer manual entry with margin | Medium
44 | Add a foreign-currency collection report (transactions collected broken down by foreign currency) to the Finance reporting suite | Finance | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | Medium
45 | Design the "Plan Your Adventure" itinerary-planner feature for the guest app, including group-sharing / invite-to-itinerary functionality | UI/UX / Guest App | Softlabs Design Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Reference: Skidata app itinerary planner (per Allam); group-share via QR/invite proposed by Chinmay and accepted by Qossai | High
46 | Evaluate a dynamic bundle/package builder that auto-applies a discount when a guest adds multiple product types (ticket + F&B + retail) to cart, in addition to pre-defined packages | Sales & Commerce | Reshma Bandiwdekar | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | Medium
47 | Advise Qossai/Allam on the Apple/Google Developer account ownership model and a simplified, low-effort app-publishing workflow for white-labelled tenant apps (incl. how to reflect "Powered by TICVAI" branding) | Mobile / Process | Pradnya Yeram | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Client requested an easy, near-automatic publishing flow that doesn't require a developer on the tenant's side | Low
48 | Update Employee App wireframe: remove the manual role-selection screen — role and home dashboard should be determined automatically from backend RBAC configuration immediately after login | UI/UX | Softlabs Design Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Correction requested by Qossai during the 11-Aug walkthrough | Medium
49 | Confirm scope: deliver a lightweight standalone ticket-validation app for dedicated scanner devices, in addition to the scan/validate function embedded in the full Staff Operations App | Mobile / Access Control | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | Medium
High
Medium
High

## Edits or New Inputs to Scope (hidden)
Edits or New Inputs to Scope — Needed from Qossai & Allam (Consolidated Open Items)
Client-side inputs, confirmations and decisions required to move the design forward, consolidated across all sessions to date
# | Input / Edit Needed | Requested From | Category | First Raised | Latest Update | Status | Notes
1 | Share TICVAI's detailed organizational hierarchy (for tenant model comparison) | Allam | Multi-Tenancy / Scope | Platform Architecture MoM (prior) | Kickoff (30-Jul) | Pending | Allam confirmed at Kickoff it would be shared after the meeting; received
2 | Confirm the current MongoDB approval status with the Dubai authority (DESC) | Allam | Compliance / Database | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
3 | Share the approved alternative NoSQL technologies, incl. Cosmos DB approval status | Allam | Compliance / Database | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
4 | Share the approved Web Application Firewall (WAF) product list | Allam | Compliance / Security | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
5 | Share the permitted security services / technology-compliance documentation | Allam | Compliance / Security | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
6 | Share any relevant Dubai authority technology-compliance documents | Allam | Compliance | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
7 | Source and share any additional compliance documentation (DESC compliance, PCI DSS) | Allam | Compliance | MoM (31-Jul) | MoM (31-Jul) | In Progress
8 | Provide expected user volumes / traffic estimates by customer category and client tier | Qossai / Allam | Capacity Planning | Discovery Day 1 (28-Jul) | MoM (31-Jul) | Pending
9 | Provide anticipated peak traffic for major events | Qossai / Allam | Capacity Planning | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
10 | Clarify preferred infrastructure expectations for small/medium/enterprise customers | Qossai / Allam | Infrastructure / Scope | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
11 | Provide input on cloud provider preference (AWS vs Azure) ahead of design review | Qossai / Allam | Infrastructure / Scope | MoM (31-Jul) | MoM (31-Jul) | Pending
12 | Review Softlabs' forthcoming HLD and LLD documents | Qossai / Allam | Architecture Review | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending
13 | Share the POS prototype link and access credentials | Qossai | UI/UX | Discovery Day 1 (28-Jul) | UI/UX MoM (3-Aug) | Completed | Demoed live on-screen during the 3-Aug UI/UX session
14 | Prepare and present TICVAI's UI/UX vision (B2C/B2B examples, flow walkthroughs) | Qossai | UI/UX / Scope | MoM (31-Jul) | UI/UX MoM (3-Aug) | Completed | Delivered via live walkthrough on 3-Aug (POS, F&B, website)
15 | Share the referenced PDF and additional example website links via email (since Teams attachment issue) | Qossai | UI/UX | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending
16 | Locate and share the mobile app example using product video instead of static images, if found | Qossai | UI/UX | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending
17 | Confirm availability for the proposed recurring weekly tracker-review meeting | TICVAI Team | Process | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending
18 | Locate and share the AutoCAD/PDF seating drawing from the Bahrain project (also to be shared with 3D vendor "3DDV") | Allam | Seat Mapping | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending
19 | Prepare and schedule a demo session on multi-tenant configuration and event/access management | Allam | Process / Demo | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending | Tomorrow or Friday (7-Aug), TBC
20 | Confirm and share turnstile and other hardware SDK/specification documents | Qossai / Allam | Hardware Integration | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending
21 | Share banking (DCT) and communications (WhatsApp/SMS) integration documentation ahead of a dedicated session | Qossai | Compliance / Integration | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending
22 | Share the accessibility (WCAG / Universal Acceptance) compliance guidelines referenced during the UI/UX walkthrough | Allam | Compliance / UI-UX | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Allam referenced showing this "in the scope" but it was not shared during the session
23 | Confirm foreign-currency display approach (manual FX-rate entry with margin vs. live third-party FX-rate API) and confirm the payment gateway that will support Dynamic Currency Conversion | Qossai / Allam | Finance / Payment | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending
24 | Confirm and formally share the finalised reference matrix / mobile app design flow (screens demoed 11-Aug) as the working baseline for guest & staff app backend development | Qossai | UI/UX / Scope | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Qossai confirmed the matrix is the main reference; slides to be sent via email/WhatsApp
25 | Decide the app-store account ownership model for white-labelled tenant apps (TICVAI-owned, Softlabs-owned, or tenant-owned) once Softlabs' guidance is provided | Qossai | Mobile / Scope | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Qossai asked Softlabs to advise; decision needed on how "Powered by TICVAI" branding is reflected regardless of ownership

## Action Items to be done
TICVAI x Softlabs — What We Have to Create (Consolidated Open Items)
Consolidated task list
# | Deliverable / Task | Category | Owner | First Raised | Latest Update | Status | Notes | Priority
1 | Define standardized deployment workflow (staging → customer approval → production) | Deployment | Softlabs Team | Kickoff (30-Jul) | Kickoff (30-Jul) | In Progress |  | High
2 | Document software versioning policy (minor optional / major mandatory after EOS) | Deployment | Softlabs Team | Kickoff (30-Jul) | Kickoff (30-Jul) | Pending |  | Medium
3 | Standardize database migration process | Deployment | Softlabs Team | Kickoff (30-Jul) | Kickoff (30-Jul) | In Progress |  | High
4 | Review and compare TICVAI's org hierarchy vs. Softlabs' proposed tenant hierarchy | Multi-Tenancy | Softlabs & TICVAI | Kickoff (30-Jul) | Kickoff (30-Jul) | Pending |  | High
5 | Finalize multi-tenant architecture | Multi-Tenancy | Both Teams | Platform Architecture MoM (prior) | Kickoff (30-Jul) | Pending |  | High
6 | Prepare HLD & LLD architecture diagrams (client-hosted & Softlabs-hosted scenarios) | Architecture | Chinmay Parab | Discovery Day 1 (28-Jul) | MoM (31-Jul) | In Progress |  | High
7 | Develop system and data-flow diagrams | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
8 | Define auto-scaling and queue-management architecture | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
9 | Analyse tenant-isolation strategies | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
10 | Evaluate separate database per tenant, schema isolation and hybrid approaches | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
11 | Finalise the proposed technology stack after compliance validation | Architecture | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending | Depends on Allam's compliance findings | High
12 | Define Azure and AWS deployment options | Infrastructure | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
13 | Prepare minimum infrastructure requirements for different customer sizes | Infrastructure | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
14 | Define cloud, hybrid and on-premise update strategies | Infrastructure | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
15 | Prepare HLD & LLD design documentation for each major cloud provider (AWS, Azure) | Infrastructure | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
16 | Prepare client-tiered case study (small/medium/large) with scaling ceilings & cost | Infrastructure | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
17 | Design the offline POS and handheld-validation architecture | Offline/POS | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
18 | Evaluate the channel-based offline inventory-pooling model | Offline/POS | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
19 | Prepare case study: online-first vs offline-first POS architecture (pros/cons) | Offline/POS | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
20 | Double-check requirement matrix for kitchen display system (KDS) integration scope | Offline/POS | Chinmay Parab | MoM (31-Jul) | MoM (31-Jul) | Pending |  | Medium
21 | Design reporting read replicas or a reporting database | Database | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
22 | Include archival strategy in the database design | Database | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
23 | Review and preserve the POS prototype for UI/UX reference | UI/UX | Softlabs Team | Discovery Day 1 (28-Jul) | UI/UX MoM (3-Aug) | Completed | Confirmed as primary design reference during 3-Aug walkthrough | Low
24 | Propose an enhanced POS user experience (redesign, not a copy) | UI/UX | Softlabs Team | Discovery Day 1 (28-Jul) | UI/UX MoM (3-Aug) | In Progress | Direction confirmed 3-Aug; actual enhanced design still to be produced | High
25 | Share the full list of application pages/screens with TICVAI (by device/tenant/sub-screen) | UI/UX | Chinmay Parab | MoM (31-Jul) | UI/UX MoM (3-Aug) | In Progress | List exists internally in tracking spreadsheet; not yet confirmed as shared with TICVAI | Medium
26 | Recommend a UX approach combining quick-access 'hot function' buttons with search-driven POS functionality | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
27 | Research current market best practices for ticket-booking UX (web and mobile) | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
28 | Review the 'Viva Ticket' website as a reference for ticket-flow variations | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Low
29 | Collate design references/inspiration and share with TICVAI, organized by mobile app, website, and admin/back-office pages | UI/UX | Softlabs (Sahil & Aishwarya) | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
30 | Begin wireframing screens with clear requirements; share iteratively with TICVAI for feedback | UI/UX | Softlabs Design Team | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | In Progress |  | High
31 | Prepare focused presentation material for future workshops | Process | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Low
32 | Prepare and deliver presentation on multi-tenancy, platform infrastructure & API gateway | Process | Softlabs Team | Discovery Day 1 (28-Jul) | Kickoff (30-Jul) | Completed | Delivered at Kickoff session 30-Jul | Low
33 | Update the workshop tracker and completion status | Process | Softlabs Team | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Ongoing |  | Medium
34 | Circulate MoM and next meeting agenda after each session | Process | Chinmay Parab | Platform Architecture MoM (prior) | UI/UX MoM (3-Aug) | Ongoing | Recurring after every session | Medium
35 | Document the finalized ticket classification (product types, incl. Membership, Event/Resource) as a diagram and circulate for confirmation | Ticketing Architecture | Chinmay Parab | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | In Progress |  | High
36 | Test AI-based seat-layout generation using available sample layouts (screenshots/PDFs) as a worst-case baseline | Seat Mapping | Chinmay Parab | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | In Progress |  | High
37 | Complete and share mockups for the food ordering / POS counter app | UI/UX | Aishwarya More | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | In Progress |  | High
38 | Share the slides/deck presented during the Guest & Staff App UI/UX walkthrough session with TICVAI | UI/UX | Muhamed Allam | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Requested by Reshma Bandiwdekar at close of session; Muhamed confirmed he would share all slides presented | High
39 | Share the video recording and MoM for the Guest & Staff App UI/UX walkthrough session | Process | Chinmay Parab | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Requested by Rishaan Moorjani; Chinmay confirmed the recording link will be attached along with the MoM | High
40 | Send the updated task tracker to Qossai/Allam and set up a follow-up call to review tracker status and next actions | Process | Chinmay Parab | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Muhamed Allam requested the tracker be sent today so a review call can be scheduled for tomorrow | High
41 | Define UI validation limits (max font types/sizes, banner/image pixel dimensions) for the mobile app builder module to prevent layout breakage | UI/UX | Softlabs Design Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Raised by Chinmay Parab (custom fonts/oversized banners could break the layout); Qossai & Allam agreed restrictions and upload validation are needed | Medium
42 | Schedule a dedicated AI workshop to walk TICVAI through how the AI Concierge / LLM assistant works, and align on the token-usage billing approach for tenants | AI | Chinmay Parab | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Explicitly requested by Qossai — AI functionality and cost model "still not clear" to him; to be discussed before finalising approach | High
43 | Analyse the integration effort for third-party systems (parking, ride/queue-timing sensors, etc.) to consume TAIS's own standardised API as the default integration model | Integration | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Agreed as the preferred standard during the 11-Aug walkthrough (vs. TAIS pushing data to each third-party's own API); Allam flagged effort still needs sizing | Medium
44 | Design the parking module to support both native QR-based validation (own solution) and a plate-number capture field for future ANPR/third-party parking integrations | Integration | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | Medium
45 | Design multi-currency display to support both manual FX-rate entry (with configurable margin) and an optional real-time third-party FX-rate API; confirm which payment gateway(s) support Dynamic Currency Conversion (DCC) | Finance / Commerce | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Reshma flagged FX rates fluctuate and can't be stored as static master data; Qossai noted ~90% of regional clients prefer manual entry with margin | High
46 | Add a foreign-currency collection report (transactions collected broken down by foreign currency) to the Finance reporting suite | Finance | Softlabs Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | Medium
47 | Design the "Plan Your Adventure" itinerary-planner feature for the guest app, including group-sharing / invite-to-itinerary functionality | UI/UX / Guest App | Softlabs Design Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Reference: Skidata app itinerary planner (per Allam); group-share via QR/invite proposed by Chinmay and accepted by Qossai | Low
48 | Evaluate a dynamic bundle/package builder that auto-applies a discount when a guest adds multiple product types (ticket + F&B + retail) to cart, in addition to pre-defined packages | Sales & Commerce | Reshma Bandiwdekar | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | Medium
49 | Advise Qossai/Allam on the Apple/Google Developer account ownership model and a simplified, low-effort app-publishing workflow for white-labelled tenant apps (incl. how to reflect "Powered by TICVAI" branding) | Mobile / Process | Pradnya Yeram | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Client requested an easy, near-automatic publishing flow that doesn't require a developer on the tenant's side | Medium
50 | Update Employee App wireframe: remove the manual role-selection screen — role and home dashboard should be determined automatically from backend RBAC configuration immediately after login | UI/UX | Softlabs Design Team | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Correction requested by Qossai during the 11-Aug walkthrough | High

## New Inputs
Edits or New Inputs to Scope — Needed from Qossai & Allam (Consolidated Open Items)
Client-side inputs, confirmations and decisions required to move the design forward, consolidated across all sessions to date
# | Input / Edit Needed | Requested From | Category | First Raised | Latest Update | Status | Notes | Priority
1 | Share TICVAI's detailed organizational hierarchy (for tenant model comparison) | Allam | Multi-Tenancy / Scope | Platform Architecture MoM (prior) | Kickoff (30-Jul) | Completed | Allam confirmed at Kickoff it would be shared after the meeting; received | Low
2 | Confirm the current MongoDB approval status with the Dubai authority (DESC) | Allam | Compliance / Database | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
3 | Share the approved alternative NoSQL technologies, incl. Cosmos DB approval status | Allam | Compliance / Database | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
4 | Share the approved Web Application Firewall (WAF) product list | Allam | Compliance / Security | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
5 | Share the permitted security services / technology-compliance documentation | Allam | Compliance / Security | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
6 | Share any relevant Dubai authority technology-compliance documents | Allam | Compliance | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
7 | Source and share any additional compliance documentation (DESC compliance, PCI DSS) | Allam | Compliance | MoM (31-Jul) | MoM (31-Jul) | In Progress |  | High
8 | Provide expected user volumes / traffic estimates by customer category and client tier | Qossai / Allam | Capacity Planning | Discovery Day 1 (28-Jul) | MoM (31-Jul) | Pending |  | High
9 | Provide anticipated peak traffic for major events | Qossai / Allam | Capacity Planning | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | High
10 | Clarify preferred infrastructure expectations for small/medium/enterprise customers | Qossai / Allam | Infrastructure / Scope | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
11 | Provide input on cloud provider preference (AWS vs Azure) ahead of design review | Qossai / Allam | Infrastructure / Scope | MoM (31-Jul) | MoM (31-Jul) | Pending |  | High
12 | Review Softlabs' forthcoming HLD and LLD documents | Qossai / Allam | Architecture Review | Discovery Day 1 (28-Jul) | Discovery Day 1 (28-Jul) | Pending |  | Medium
13 | Share the POS prototype link and access credentials | Qossai | UI/UX | Discovery Day 1 (28-Jul) | UI/UX MoM (3-Aug) | Completed | Demoed live on-screen during the 3-Aug UI/UX session | Low
14 | Prepare and present TICVAI's UI/UX vision (B2C/B2B examples, flow walkthroughs) | Qossai | UI/UX / Scope | MoM (31-Jul) | UI/UX MoM (3-Aug) | Completed | Delivered via live walkthrough on 3-Aug (POS, F&B, website) | Low
15 | Share the referenced PDF and additional example website links via email (since Teams attachment issue) | Qossai | UI/UX | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Completed |  | Low
16 | Locate and share the mobile app example using product video instead of static images, if found | Qossai | UI/UX | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Low
17 | Confirm availability for the proposed recurring weekly tracker-review meeting | TICVAI Team | Process | UI/UX MoM (3-Aug) | UI/UX MoM (3-Aug) | Pending |  | Medium
18 | Locate and share the AutoCAD/PDF seating drawing from the Bahrain project (also to be shared with 3D vendor "3DDV") | Allam | Seat Mapping | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending |  | Medium
19 | Prepare and schedule a demo session on multi-tenant configuration and event/access management | Allam | Process / Demo | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending | Tomorrow or Friday (7-Aug), TBC | Medium
20 | Confirm and share turnstile and other hardware SDK/specification documents | Qossai / Allam | Hardware Integration | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending |  | Medium
21 | Share banking (DCT) and communications (WhatsApp/SMS) integration documentation ahead of a dedicated session | Qossai | Compliance / Integration | Ticketing Kickoff (5-Aug) | Ticketing Kickoff (5-Aug) | Pending |  | Medium
22 | Share the accessibility (WCAG / Universal Acceptance) compliance guidelines referenced during the UI/UX walkthrough | Allam | Compliance / UI-UX | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Allam referenced showing this "in the scope" but it was not shared during the session | Medium
23 | Confirm foreign-currency display approach (manual FX-rate entry with margin vs. live third-party FX-rate API) and confirm the payment gateway that will support Dynamic Currency Conversion | Qossai / Allam | Finance / Payment | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending |  | High
24 | Confirm and formally share the finalised reference matrix / mobile app design flow (screens demoed 11-Aug) as the working baseline for guest & staff app backend development | Qossai | UI/UX / Scope | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Qossai confirmed the matrix is the main reference; slides to be sent via email/WhatsApp | High
25 | Decide the app-store account ownership model for white-labelled tenant apps (TICVAI-owned, Softlabs-owned, or tenant-owned) once Softlabs' guidance is provided | Qossai | Mobile / Scope | UI/UX Walkthrough (11-Aug) | UI/UX Walkthrough (11-Aug) | Pending | Qossai asked Softlabs to advise; decision needed on how "Powered by TICVAI" branding is reflected regardless of ownership | Medium